## Slide 1: Straightedge Deficiencies: Testing Exceptions vs. Waiving Deficiencies Full Pay vs. No Pay vs. Remove & Replace
Florida Department of
TRANSPORTATION
Richard Hewitt, PE
State Construction Pavement Engineer
FDOT State Construction Office

## Slide 2
Florida Department of Transportation
Testing Exceptions vs. Waiving Deficiencies
1st paragraph
  Straightedge Testing Exceptions - Testing not required
2nd paragraph
  Testing the testing exception areas, address anything exceeding 3/8”
3rd Paragraph
  Deficiencies may be waived, if caused by factors beyond contractor’s control

## Slide 3
Florida Department of Transportation
Leave in Place vs. Remove & Replace
Remove & Replace
  District Decision
Leave in Place at No Pay
  District Decision
  Per CPAM 11.5
    Requires PA + RE + DPME + DCE approval
Leave in Place at Full Pay
  SCO Decision
  Per CPAM 11.5
    Requires PA + RE + DPME + DCE + SCE approval

## Slide 4
Florida Department of Transportation
Leave in Place: Full Pay vs. No Pay
Full Pay
  Factor beyond Contractor’s Control
No Pay
  No Factor beyond Contactor’s Control

## Slide 5
Florida Department of Transportation
Full Pay Justification – Photo & Write-up
Goal
  Show/Explain factor beyond contractor’s control
    Prime Contractor’s control, not the paving sub
What’s Needed?
  Typically:
    One Photo
      Correct photo that shows factor beyond contractor’s control
      Usually NOT a photo of straightedge testing
    Short Write-up
      Provides brief description of factor beyond contractor’s control
      Most times it’s one short sentence

## Slide 6
Florida Department of Transportation
Typical “Full Pay” Cases
Following Slides are Typical Cases where “Full Pay” is requested & illustrate:
  When “Full Pay” is Justified
  When “No Pay” is Justified
  When factor beyond contractor’s control
    Is shown in a photo
    Is NOT shown in a photo
      Doesn’t necessarily mean “full pay” isn’t warranted, just that existing photo doesn’t support “full pay”

## Slide 7
Florida Department of Transportation
Typical “Full Pay” Cases
End of Project Joint
Bridge Joint
Manhole/Structure in Lane
Drainage/Curb Issue Adjacent to Lane
Other??

## Slide 8
Florida Department of Transportation
End of Project Joint
Full Pay
  At joint, off-project pavement is rutted or not in same plane across the lane
No Pay
  At joint, off-project pavement isn’t rutted, it’s in the same plane across the lane
    Contractor should’ve been able to pave a smooth, deficiency-free joint

## Slide 9
Florida Department of Transportation
End of Project Joint
“Full Pay” Key photo - Place level/straightedge:
  Across the lane
  At the joint,
  On off-project pavement
  Shows rutting or other issue beyond contractors control
Write-up:
“Rutted, off-project pavement at end of project joint made it beyond contractor’s control to pave joint deficiency free.”
Level/straightedge across lane on off-project pavement shows rutting

## Slide 10
Florida Department of Transportation
End of Project Joint
Photo doesn’t show factor beyond contractor’s control

## Slide 11
Florida Department of Transportation
Bridge Joint
Full Pay
  Situation is beyond contractor’s control if:
    Approach slab is not in same plane AND bridge approach slab construction was not part of the contract
No Pay
  Not beyond contractor’s control if:
    Approach slab concrete is in same plane
    Approach slab concrete not in same plane, but approach slab construction was part of contract
    In both “No Pay” cases, no factor beyond contractor’s control

## Slide 12
Florida Department of Transportation
Bridge Joint
Key photo - Place level/straightedge:
  Across the lane
  On approach slab
  At the joint
  Shows approach slab not in same plane across the lane
“Full Pay” Write-up:
“Approach slab not in same plane across the lane”
“Approach slab not part of contract.”
Level/straightedge across lane on approach slab, at joint

## Slide 13
Florida Department of Transportation
Bridge Joint
Photo doesn’t show factor beyond contractor’s control

## Slide 14
Florida Department of Transportation
Manhole/Structure in Lane
Full Pay
  Key here is manhole/structure adjustment wasn’t part of the contract
  Exception is an area with numerous manholes in small area. Then it’s a challenge to pave well with all the manholes in the area, even if they were adjusted per contract
No Pay
  If manhole/structure adjustment was part of contract, then manhole adjustment & paving were within the contractor’s control (prime, not the subs)
  See exception above

## Slide 15
Florida Department of Transportation
Manhole/Structure in Lane
Key Photo:
  If manhole adjustment was not part of contract, statement is enough, but photo helps.
  If cluster of manholes prevented smooth paving, provide photo of the area.
“Full Pay” Write-up:
“Manhole adjustment not part of contract”
“Number of manholes in small area prevented smooth paving”
District “Write-up” provided in photo

## Slide 16
Florida Department of Transportation
Manhole/Structure in Lane
Another example:
“Full Pay” Write-up:
“Uneven, concrete slab in roadway prevented smooth paving.”

## Slide 17
Florida Department of Transportation
Manhole/Structure in Lane
Tough to get a bad photo for this situation
Most photos will work

## Slide 18
Florida Department of Transportation
Drainage/Curb Issue Adjacent to Lane
Full Pay
  Beyond Contractor’s Control, if:
    Existing drainage structure/curb & gutter dips down significantly
    Plans didn’t call for raising new structures/curb & gutter
No Pay
  Not beyond contractor’s control if:
    Existing structures/curb & gutter don’t dip down
      i.e. paving to curb didn’t create the deficiency
    New structures/curb & gutter were reconstructed, but placed at incorrect elevation

## Slide 19
Florida Department of Transportation
Drainage/Curb Issue Adjacent to Lane
Key Photo(s)
  Photo from across the street which shows the longitudinal dip
    facing the inlet with road running from one side of photo to other
  Second photo (on right) shows contractor attempted to mitigate the issue
“Full Pay” Write-up:
“Deficiency caused by drop in elevation around inlet.”
“Drainage structure construction was not part of contract.”

## Slide 20
Florida Department of Transportation
Drainage/Curb Issue Adjacent to Lane
Photo doesn’t show factor beyond contractor’s control

## Slide 21
Florida Department of Transportation
Other?
Other situations with factors beyond the contractor’s control may occur
Need to obtain photo that shows factor beyond contractor’s control
If not sure about photo:
  Call me & Explain situation
  I’ll let you know what photo might show it is beyond contractor’s control.

## Slide 22
Florida Department of Transportation
Contact Info
For questions & comments contact:
Richard Hewitt, P.E.
  State Construction Pavement Engineer
  Office: (386) 943-5305
  email: richard.hewitt@dot.state.fl.us