## 8A Concrete Pavement
Critical Requirement? | Topic Area | # | 8A Concrete Pavement QA/QC Guide List & Critical Requirements Items 2020/21 (Critical Requirements are in bold text) | Meets Requirements? | Inspection Notes & Comments
| Delivery Tickets | 1 | Ensure the electronic delivery ticket is furnished for each batch of concrete before unloading at the placement site. [Spec 346-6.3]
| Weather & Lighting | 2 | Unhardened concrete is protected from effects of inclement weather. Production and paving operations cease when it is raining. [Spec 350-6]
| Weather & Lighting | 3 | Ensure sufficient lighting is provided during night work. [Spec. 8-4.1]
| General Paving & Finished Surface | 4 | Ensure if any uncontrolled cracks appear during the life of the Contract, the cracked concrete is removed and replaced and effective solutions are implemented immediately to eliminate further cracks. [Spec. 350-1]
| General Paving & Finished Surface | 5 | The pavement is constructed to the full width of the lane or slab in a single construction operation. [Spec. 350-7]
| Slip-form Paver | 6 | The slip-form paver is self-propelled and equipped to spread, strike-off, consolidate, screed, and float finish the freshly placed concrete in one complete pass. [Spec. 350-3.2]
| Slip-form Paver | 7 | The slip-form paver uses automatic guidance and grade controls with the exceptions noted in the Spec. [Spec. 350-3.2]
| Forms | 8 | Forms are set to line and grade and so they rest firmly upon the subgrade surface, throughout their entire length. [Spec 350-5]
| Forms | 9 | Forms are cleaned after each use and prior to placing concrete against them. A release agent is applied in accordance with the manufacturer’s recommendations. [Spec. 350-5]
Yes | Forms | 10 | Ensure forms are not removed from freshly placed concrete for at least 12 hours after placement. After removing the forms, immediately apply curing compound to the sides of the slab. [Spec. 350-12.3]
| Consolidation & Vibration | 11 | The concrete is consolidated for the full width of the strip being placed with either surface pan type or internal type vibrators. [Spec. 350-3.]
Yes | Consolidation & Vibration | 12 | Consolidate the concrete for the full width and depth of concrete in a single pass of an approved internal vibrator system. Operate internal vibrators within a frequency range of 4,000 to 8,000 vibrations per minute (vpm). For surface vibrators, the frequency is at least 3,500 impulses per minute. [Spec. 350-3.3]
| Consolidation & Vibration | 13 | The final finish is applied using a seamless length of damp burlap over the full width of the strip of constructed pavement. [Spec. 350-11.1]
| Smoothness & Grade | 14 | Ensure the pavement surface is true to grade and uniform in appearance with a longitudinal line type texture by the grinding operation. Smoothness is tested by the 10 foot rolling straightedge, a 10 foot long rolling straightedge, or a California Type Profilograph for acceptance as defined in the Specifications. All deficiencies are corrected and retested to ensure conformity. [Spec. 352-4, 5, 6]
Yes | Smoothness & Grade | 15 | Ensure all joints are checked with straightedge before concrete becomes non-plastic and make corrections if any smoothness deficiency is found. [Spec. 350-13.3.2]
| Curing & Curing Compound | 16 | The device for application of membrane curing compound is self-propelled and capable of uniformly applying the curing compound at the specified rate. [Spec 350-3.5]
Yes | Curing & Curing Compound | 17 | Ensure the concrete is cured in accordance with the requirements of the Specifications. Do not leave the concrete exposed for a period in excess of 30 minutes between stages of curing or during the curing period. [Spec. 350-12.1]
| Curing & Curing Compound | 18 | Ensure the freshly placed concrete is continuously cured for a period of 72 hours, exclusive of any periods when the temperature of the surface of the concrete falls below 50°F. [Spec 350-12.1]
| Joint Construction & Sealing | 19 | Ensure the longitudinal joints are constructed in accordance with the details shown in the Plans and the tie bars or tie bolt assemblies are placed correctly in depth, spacing, location, and angles. For transverse joints, ensure the dowel bars are the correct diameter and length. [Spec. 350-13]
| Joint Construction & Sealing | 20 | Transverse construction joints are placed at the end of all pours and other locations where paving operations are stopped 30 minutes or longer. [Spec. 350-13.3.2]
| Joint Construction & Sealing | 21 | Accomplish the transverse contraction joint sawing in two steps. Make the initial cut 1/8 inch wide by a depth at least 1/3 of the pavement thickness and as soon as possible in no case longer than 12 hours after placing the concrete. [Spec. 350-13.3.3]
| Joint Construction & Sealing | 22 | Provide dowel load-transfer devices in all transverse joints. Firmly hold dowel bars in a position parallel to the surface in the longitudinal direction of the pavement and the centerline of the slab depth, by approved steel supports and spacers. [Spec. 350 13.3.1]
| Joint Construction & Sealing | 23 | For sawed joints that will receive sealant, ensure the joint is flushed with a jet of water to remove any remaining slurry. [Spec. 350-13.5.2]
| Joint Construction & Sealing | 24 | When using a hot-poured sealer, the heating kettle is of the indirect heating or double boiler type, using oil as a heat transfer medium. [Spec 350-13.6.1]
| Thickness | 25 | Determine the thickness by one of the methods in Section 350-15.1. If the pavement is cored, the pavement removed by the borings shall be repaired promptly. [Spec. 350-15.1]
| Thickness | 26 | On concrete slab replacement projects, measure the thickness of each removed slab by taking one thickness measurement per side of the perimeter of the removed slab (4 total measurements for each replacement slab section). Calculate the average of the measured thicknesses for a slab to determine the “thickness of the removed slab”. Use the calculated “thickness of the removed slab” for payment purposes as defined in Specification 353-11.
Yes | Traffic | 27 | After placement of the concrete, traffic is kept off the pavement for a minimum of 14 calendar days or for such period as otherwise provided in the contract documents. [Spec. 350-18]
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use filter in Critical Requirements Column to "Select All" to show all items (Guide List) or show only items with "Yes" (Critical Requirements).

## Sheet1 (hidden)
Meets Reqs
Yes
No