## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 4636076 | 4586076 | 4695091 | 4538363 | 0 | 4525473 | -1.321% | 100% | 59015 | 1.287% | 59015 | 1.273% | 330 | 169 | 51.21% | 46 | 13.94% | 0 | 0% | 10 | 3.03% | 340 | 3.03% | 555 | 544 | 329 | -0.303% | 100%
| District Let | 13753414 | 13591792 | 13922791 | 13147438 | 0 | 13322191 | -1.984% | 100% | 183138 | 1.347% | 169377 | 1.232% | 1155 | 162 | 14.03% | 99 | 8.571% | 67 | 5.801% | 0 | 0% | 1222 | 5.801% | 1483 | 1478 | 1217 | 5.368% | 100%
| All Contracts | 18389490 | 18177868 | 18617882 | 17685801 | 0 | 17847664 | -1.817% | 100% | 242153 | 1.332% | 228392 | 1.242% | 1485 | 331 | 22.29% | 145 | 9.764% | 67 | 4.512% | 10 | 0.6734% | 1562 | 5.185% | 2038 | 2022 | 1546 | 4.108% | 100%
2 | Central Let | 47517109 | 46826082 | 47719246 | 47758225 | 0 | 48276027 | 3.096% | 100% | 312869 | 0.6682% | 202137 | 0.4254% | 1766 | 456 | 25.82% | 200 | 11.33% | 186 | 10.53% | 25 | 1.416% | 1977 | 11.95% | 2446 | 2432 | 1776 | 0.5663% | 100%
| District Let | 32345205 | 32040913 | 38790677 | 39686706 | 0 | 39722319 | 23.97% | 33.33% | 6592276 | 20.57% | 6445472 | 19.93% | 1210 | 304 | 25.12% | 214 | 17.69% | 22 | 1.818% | 513 | 42.4% | 1745 | 44.21% | 2257 | 2233 | 1715 | 41.74% | 0%
| All Contracts | 79862314 | 78866995 | 86509923 | 87444931 | 0 | 87998346 | 11.58% | 84.62% | 6905145 | 8.755% | 6647609 | 8.324% | 2976 | 760 | 25.54% | 414 | 13.91% | 208 | 6.989% | 538 | 18.08% | 3722 | 25.07% | 4703 | 4665 | 3491 | 17.31% | 76.92%
3 | Central Let | 24273718 | 24060285 | 24441000 | 25461969 | 0 | 25539497 | 6.148% | 85.71% | 291779 | 1.213% | 167281 | 0.6891% | 1394 | 988 | 70.88% | 350 | 25.11% | 693 | 49.71% | 77 | 5.524% | 2164 | 55.24% | 3225 | 3221 | 1883 | 35.08% | 57.14%
| District Let | 14505083 | 14305083 | 14634272 | 14732408 | 800 | 14694381 | 2.721% | 100% | 148302 | 1.037% | 129189 | 0.8906% | 557 | 177 | 31.78% | 128 | 22.98% | 21 | 3.77% | 7 | 1.257% | 585 | 5.027% | 906 | 890 | 585 | 5.027% | 100%
| All Contracts | 38778801 | 38365368 | 39075272 | 40194377 | 800 | 40233878 | 4.87% | 90.91% | 440081 | 1.147% | 296470 | 0.7645% | 1951 | 1165 | 59.71% | 478 | 24.5% | 714 | 36.6% | 84 | 4.305% | 2749 | 40.9% | 4131 | 4111 | 2468 | 26.5% | 72.73%
4 | Central Let | 95910410 | 95171267 | 98384085 | 97345982 | 0 | 97819538 | 2.783% | 100% | 2481728 | 2.608% | 2689125 | 2.804% | 4099 | 1133 | 27.64% | 349 | 8.514% | 203 | 4.952% | 111 | 2.708% | 4413 | 7.66% | 5779 | 5759 | 4277 | 4.343% | 100%
| District Let | 154677330 | 154377330 | 158347088 | 159257852 | 1375000 | 160103660 | 3.709% | 100% | 3772432 | 2.444% | 3711509 | 2.4% | 1997 | 246 | 12.32% | 170 | 8.513% | 156 | 7.812% | 0 | 0% | 2153 | 7.812% | 2471 | 2480 | 2064 | 3.355% | 100%
| All Contracts | 250587740 | 249548597 | 256731173 | 256603834 | 1375000 | 257923198 | 3.356% | 100% | 6254160 | 2.506% | 6400634 | 2.554% | 6096 | 1379 | 22.62% | 519 | 8.514% | 359 | 5.889% | 111 | 1.821% | 6566 | 7.71% | 8250 | 8239 | 6341 | 4.019% | 100%
5 | Central Let | 26469379 | 26015379 | 26791210 | 27057218 | 0 | 26891419 | 3.367% | 100% | 369671 | 1.421% | 321830 | 1.216% | 1990 | 433 | 21.76% | 448 | 22.51% | 52 | 2.613% | 200 | 10.05% | 2242 | 12.66% | 3142 | 3104 | 2223 | 11.71% | 77.78%
| District Let | 4914622 | 4776461 | 4921721 | 4831405 | 0 | 4824162 | 0.9987% | 100% | 11926 | 0.2497% | 7099 | 0.1444% | 675 | 96 | 14.22% | 121 | 17.93% | 0 | 0% | 2 | 0.2963% | 677 | 0.2963% | 894 | 824 | 607 | -10.07% | 100%
| All Contracts | 31384001 | 30791840 | 31712931 | 31888623 | 0 | 31715581 | 3% | 100% | 381597 | 1.239% | 328929 | 1.048% | 2665 | 529 | 19.85% | 569 | 21.35% | 52 | 1.951% | 202 | 7.58% | 2919 | 9.531% | 4036 | 3928 | 2830 | 6.191% | 83.33%
6 | Central Let | 27866824 | 27564126 | 28471300 | 28512117 | 540000 | 28886468 | 4.797% | 100% | 744068 | 2.699% | 604477 | 2.169% | 1460 | 140 | 9.589% | 115 | 7.877% | 0 | 0% | 95 | 6.507% | 1555 | 6.507% | 1810 | 1618 | 1363 | -6.644% | 100%
| District Let | 7866697 | 7732302 | 7801270 | 7585624 | 0 | 621755 | -91.96% | 100% | -39934 | -0.5165% | -65427 | -0.8317% | 880 | 80 | 9.091% | 86 | 9.773% | 181 | 20.57% | 0 | 0% | 1061 | 20.57% | 1227 | 1223 | 1057 | 20.11% | 50%
| All Contracts | 35733521 | 35296428 | 36272570 | 36097741 | 540000 | 29508223 | -16.4% | 100% | 704134 | 1.995% | 539050 | 1.509% | 2340 | 220 | 9.402% | 201 | 8.59% | 181 | 7.735% | 95 | 4.06% | 2616 | 11.79% | 3037 | 2841 | 2420 | 3.419% | 83.33%
7 | Central Let | 8937902 | 8837902 | 9144467 | 9093135 | 0 | 9202070 | 4.121% | 100% | 148506 | 1.68% | 206565 | 2.311% | 710 | 104 | 14.65% | 57 | 8.028% | 0 | 0% | 7 | 0.9859% | 717 | 0.9859% | 871 | 866 | 705 | -0.7042% | 100%
| District Let | 81416430 | 80900430 | 85561598 | 85734005 | 0 | 84430818 | 4.364% | 100% | 4129408 | 5.104% | 4145168 | 5.091% | 2155 | 896 | 41.58% | 248 | 11.51% | 418 | 19.4% | 112 | 5.197% | 2685 | 24.59% | 3879 | 3987 | 2843 | 31.93% | 87.5%
| All Contracts | 90354332 | 89738332 | 94706065 | 94827140 | 0 | 93632888 | 4.34% | 100% | 4277914 | 4.767% | 4351733 | 4.816% | 2865 | 1000 | 34.9% | 305 | 10.65% | 418 | 14.59% | 119 | 4.154% | 3402 | 18.74% | 4750 | 4853 | 3548 | 23.84% | 90%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 1133672 | 1083672 | 1158672 | 1068668 | 0 | 1068668 | -1.385% | 100% | 39400 | 3.636% | 25000 | 2.205% | 357 | 4 | 1.12% | 15 | 4.202% | 0 | 0% | 0 | 0% | 357 | 0% | 376 | 155 | 136 | -61.9% | #VALUE!
| All Contracts | 1133672 | 1083672 | 1158672 | 1068668 | 0 | 1068668 | -1.385% | 100% | 39400 | 3.636% | 25000 | 2.205% | 357 | 4 | 1.12% | 15 | 4.202% | 0 | 0% | 0 | 0% | 357 | 0% | 376 | 155 | 136 | -61.9% | 100%
Totals This Qtr | Central Let | 235611418 | 233061117 | 239646399 | 239767009 | 540000 | 241140492 | 3.467% | 97.73% | 4407636 | 1.891% | 4250430 | 1.804% | 11749 | 3423 | 29.13% | 1565 | 13.32% | 1134 | 9.652% | 525 | 4.468% | 13408 | 14.12% | 17828 | 17544 | 12556 | 6.869% | 88.64%
| District Let | 310612453 | 308807983 | 325138089 | 326044106 | 1375800 | 318787954 | 3.232% | 92.86% | 14836948 | 4.805% | 14567387 | 4.69% | 8986 | 1965 | 21.87% | 1081 | 12.03% | 865 | 9.626% | 634 | 7.055% | 10485 | 16.68% | 13493 | 13270 | 10224 | 13.78% | 82.14%
| All Contracts | 546223871 | 541869100 | 564784488 | 565811115 | 1915800 | 559928446 | 3.333% | 95.83% | 19244584 | 3.552% | 18817817 | 3.445% | 20735 | 5388 | 25.99% | 2646 | 12.76% | 1999 | 9.641% | 1159 | 5.59% | 23893 | 15.23% | 31321 | 30814 | 22780 | 9.863% | 86.11%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2023/2024 | Central Let | 1137964577 | 1126871462 | 1186608484 | 1192777850 | 6046318 | 1204341087 | 6.875% | 87.1% | 49832653 | 4.422% | 48342251 | 4.248% | 50443 | 15125 | 29.98% | 6090 | 12.07% | 5317 | 10.54% | 5633 | 11.17% | 61393 | 21.71% | 79184 | 80497 | 59282 | 17.52% | 74.73%
| District Let | 970354308 | 963168906 | 1003105589 | 993021809 | 11856323 | 992287650 | 3.023% | 91.06% | 35080258 | 3.642% | 32751273 | 3.375% | 33080 | 6744 | 20.39% | 4161 | 12.58% | 1348 | 4.075% | 2277 | 6.883% | 36705 | 10.96% | 46400 | 44681 | 33776 | 2.104% | 93.5%
| All Contracts | 2108318885 | 2090040368 | 2189714073 | 2185799659 | 17902641 | 2196628737 | 5.1% | 88.67% | 84912911 | 4.063% | 81093524 | 3.846% | 83523 | 21869 | 26.18% | 10251 | 12.27% | 6665 | 7.98% | 7910 | 9.47% | 98098 | 17.45% | 125584 | 125178 | 93058 | 11.42% | 82.2%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 94.5% | 1 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | 96.89% | 1 | -12039 | 0 | 86 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 |  | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92
| 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 107.7% | 1 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | 104% | 1 | -851 | 59015 | 83 | 24 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 2 | 2 | 6 | 330 | 555 | 544 | 100% | 2 | 11 | 0 | 0 | 215 | 10 | 4636076 | 50000 | 4586076 | 4695091 | 4538363 | 0 | 0 | 0 | 4538363 | 4525473 | 100% | 2 | -12890 | 59015 | 169 | 46 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0
| 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 99.78% | 1 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 96.34% | 1 | 272547 | 95906 | 140 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 |  | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1
| 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 112.8% | 1 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | 101% | 1 | -1888 | 31977 | 22 | 49 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 97.78% | 1 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 104.7% | 1 | 0 | 41494 | 0 | 5 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 5 | 1155 | 1483 | 1478 | 100% | 3 | 5 | 0 | 0 | 328 | 0 | 13753414 | 161622 | 13591792 | 13922791 | 13147438 | 0 | 0 | 0 | 13147438 | 13322191 | 100% | 3 | 270659 | 169377 | 162 | 99 | 0 | 0 | 43809 | 0 | 0 | 0 | 43422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 183138 | 0
| District 01 Totals |  |  |  |  | 5 | 6 | 11 | 1485 | 2038 | 2022 | 100% | 5 | 16 | 0 | 0 | 543 | 10 | 18389490 | 211622 | 18177868 | 18617882 | 17685801 | 0 | 0 | 0 | 17685801 | 17847664 | 100% | 5 | 257769 | 228392 | 331 | 145 | 0 | 0 | 43809 | 0 | 0 | 12 | 102437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 10 | 242153 | 0
| 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | 106.9% | 1 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 104.2% | 1 | 456060 | 23650 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13
| 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 106.8% | 1 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 105.7% | 1 | 140312 | 178487 | 171 | 70 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594
| 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 99.33% | 1 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 97.69% | 1 | 0 | 0 | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 |  | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34
| 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 100% | 1 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | 104.5% | 1 | -52174 | 0 | 147 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253
| 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 103.2% | 1 | 19527 | 0 | 41 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 |  | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548
| 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 94.44% | 1 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 99.46% | 1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 |  | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87
| 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 97.78% | 1 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 93.97% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 |  | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05
| 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 93.33% | 1 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 102.2% | 1 | 0 | 0 | 6 | 19 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85
| 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 99.33% | 1 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 99.93% | 1 | 1123 | 0 | 40 | 24 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4
| 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 91.18% | 1 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 99.61% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 10 | 14 | 5 | 1766 | 2446 | 2432 | 100% | 10 | 14 | 12 | 0 | 655 | 25 | 47517109 | 691026 | 46826082 | 47719246 | 47758225 | -45432 | 0 | -45432 | 47712793 | 48276027 | 100% | 10 | 564848 | 202137 | 456 | 200 | 0 | 24 | 205579 | 9554 | 0 | 0 | 87022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 12043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 25 | 312869 | 9554
| 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 185.6% | 0 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 102.5% | 1 | 0 | 630 | 1 | 10 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05
| 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 149% | 0 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 141% | 0 | 0 | 2917973 | 194 | 61 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 |  | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83
| 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 134.3% | 0 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 118.6% | 0 | 1123706 | 3526869 | 109 | 143 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 3 | 8 | 30 | 1210 | 2257 | 2233 | 0% | 0 | 24 | 0 | 0 | 534 | 513 | 32345205 | 304293 | 32040913 | 38790677 | 39686706 | 0 | 0 | 0 | 39686706 | 39722319 | 33.33% | 1 | 1123706 | 6445472 | 304 | 214 | 0 | 277 | 2107509 | 1770145 | 0 | 223 | 4130482 | 115377 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 73387 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 513 | 6592276 | 2118274
| District 02 Totals |  |  |  |  | 13 | 22 | 35 | 2976 | 4703 | 4665 | 76.92% | 10 | 38 | 12 | 0 | 1189 | 538 | 79862314 | 995319 | 78866995 | 86509923 | 87444931 | -45432 | 0 | -45432 | 87399499 | 87998346 | 84.62% | 11 | 1688554 | 6647609 | 760 | 414 | 0 | 301 | 2313088 | 1779699 | 0 | 223 | 4217504 | 115377 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22809 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 72 | 1 | 85430 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 538 | 6905145 | 2127828
| 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 154.9% | 0 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | 105.1% | 1 | -6844 | 58046 | 137 | 52 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9
| 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 111.3% | 1 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 102.2% | 1 | 14152 | 1950 | 65 | 29 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 |  | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22
| 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 112.1% | 1 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | 105.5% | 1 | -1180 | 0 | 220 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28
| 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 128.9% | 0 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 103.6% | 1 | 107844 | 20899 | 225 | 78 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95
| 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 211.5% | 0 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 102.9% | 1 | 1480 | 10462 | 151 | 96 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75
| 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 95.56% | 1 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 98.69% | 1 | 0 | 0 | 52 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83
| 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 113.2% | 1 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | 110.9% | 0 | -37923 | 75924 | 138 | 47 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 7 | 9 | 10 | 1394 | 3225 | 3221 | 57.14% | 4 | 4 | 0 | 0 | 1749 | 82 | 24273718 | 213433 | 24060285 | 24441000 | 25461969 | 0 | 0 | 0 | 25461969 | 25539497 | 85.71% | 6 | 77529 | 167281 | 988 | 350 | 164 | 35 | 104825 | 0 | 247 | 22 | 96996 | 16851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 78774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 693 | 77 | 291779 | 16851
| 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 111.1% | 1 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | 98.3% | 1 | -13836 | 0 | 46 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47
| 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 89.78% | 1 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | 102.9% | 1 | -7206 | 0 | 35 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71
| 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 102.7% | 1 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | 104.4% | 1 | -16986 | 26502 | 75 | 28 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 |  | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78
| 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 120% | 1 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | 106.5% | 1 | -70800 | 102687 | 21 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 4 | 6 | 4 | 557 | 906 | 890 | 100% | 4 | 16 | 0 | 0 | 342 | 7 | 14505083 | 200000 | 14305083 | 14634272 | 14732408 | 70000 | 800 | 70800 | 14803208 | 14694381 | 100% | 4 | -108828 | 129189 | 177 | 128 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7 | 148302 | 0
| District 03 Totals |  |  |  |  | 11 | 15 | 14 | 1951 | 4131 | 4111 | 72.73% | 8 | 20 | 0 | 0 | 2091 | 89 | 38778801 | 413433 | 38365368 | 39075272 | 40194377 | 70000 | 800 | 70800 | 40265177 | 40233878 | 90.91% | 10 | -31299 | 296470 | 1165 | 478 | 164 | 35 | 104825 | 0 | 247 | 27 | 123498 | 16851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 200574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 714 | 84 | 440081 | 16851
| 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 106.9% | 1 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 104.5% | 1 | 598393 | 791712 | 277 | 92 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 107% | 1 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 101.3% | 1 | 96348 | 120572 | 150 | 38 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73
| 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 105.2% | 1 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 104% | 1 | 165689 | 877092 | 127 | 55 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 99.55% | 1 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | 89.01% | 1 | -16159 | 0 | 189 | 25 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07
| 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 99.64% | 1 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | 95.5% | 1 | -46640 | -1370 | 123 | 27 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21
| 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 99.46% | 1 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | 108.4% | 1 | -15706 | 258794 | 122 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38
| 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 94.62% | 1 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 98.41% | 1 | 69 | 0 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03
| 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 115% | 1 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | 102.4% | 1 | -3717 | 0 | 63 | 21 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19
| 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 101.8% | 1 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | 106% | 1 | -4475 | 625462 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 |  | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33
| 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 103.5% | 1 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | 88% | 1 | -344 | 16863 | 37 | 25 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 |  | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 10 | 23 | 42 | 4099 | 5779 | 5759 | 100% | 10 | 20 | 0 | 0 | 1569 | 143 | 95910410 | 739144 | 95171267 | 98384085 | 97345982 | 0 | 0 | 0 | 97345982 | 97819538 | 100% | 10 | 773458 | 2689125 | 1133 | 349 | 1 | 75 | 1545935 | 600658 | 66 | 26 | 1124437 | 116868 | 0 | 0 | 2420 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 396061 | 0 | 0 | 0 | 2954 | 1041 | 0 | 0 | 0 | 0 | 116 | 0 | 245344 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 111 | 2481728 | 953893
| 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 99.71% | 1 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 103.9% | 1 | 5349446 | 3618986 | 181 | 112 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 106.3% | 1 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | 98.31% | 1 | -11187 | 50772 | 14 | 24 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12
| 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 113.8% | 1 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | 107.4% | 1 | -2567 | 41751 | 27 | 16 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 |  | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49
| 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | 118.6% | 1 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | 87.58% | 1 | -43330 | 0 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 4 | 8 | 32 | 1997 | 2471 | 2480 | 100% | 4 | -9 | 30 | 0 | 474 | 0 | 154677330 | 300000 | 154377330 | 158347088 | 159257852 | -50970 | 1375000 | 1324030 | 160581882 | 160103660 | 100% | 4 | 5292362 | 3711509 | 246 | 170 | 0 | 0 | 2059152 | 209090 | 0 | 0 | 769927 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 168663 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 156 | 0 | 3772432 | 651215
| District 04 Totals |  |  |  |  | 14 | 31 | 74 | 6096 | 8250 | 8239 | 100% | 14 | 11 | 30 | 0 | 2043 | 143 | 250587740 | 1039144 | 249548597 | 256731173 | 256603834 | -50970 | 1375000 | 1324030 | 257927864 | 257923198 | 100% | 14 | 6065820 | 6400634 | 1379 | 519 | 1 | 75 | 3605087 | 809748 | 66 | 26 | 1894364 | 161199 | 0 | 0 | 2420 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 37 | 10 | 1084559 | 33779 | 0 | 0 | 171617 | 324226 | 0 | 0 | 0 | 0 | 230 | 0 | 339602 | 0 | 0 | 0 | 102645 | 0 | 25 | 0 | 276156 | 276156 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 359 | 111 | 6254160 | 1605108
| 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 136.5% | 0 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | 101.3% | 1 | -57178 | 154746 | 45 | 50 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34
| 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 108.3% | 1 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | 104.9% | 1 | -94902 | 39287 | 76 | 80 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3
| 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 155.3% | 0 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | 108.8% | 1 | -1791 | 104943 | 39 | 114 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8
| 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | 100.7% | 1 | -1484 | 793 | 94 | 10 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4
| 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 98.24% | 1 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | 104.6% | 1 | -515 | 40000 | 128 | 27 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1
| 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 92.67% | 1 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | 101% | 1 | -18 | 2618 | 7 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306
| 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 98% | 1 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | 106.3% | 1 | -22 | 0 | 26 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25
| 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 103.9% | 1 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | 93.31% | 1 | -1198 | 1419 | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 |  | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55
| 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 99.29% | 1 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 101.9% | 1 | 0 | -21976 | 9 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 |  | 2024-07-01 | QTR1 | 24/25 | 515 | 919900
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 9 | 17 | 15 | 1990 | 3142 | 3104 | 77.78% | 7 | 38 | 0 | 0 | 910 | 242 | 26469379 | 454000 | 26015379 | 26791210 | 27057218 | 0 | 0 | 0 | 27057218 | 26891419 | 100% | 9 | -157108 | 321830 | 433 | 448 | 0 | 0 | 153488 | 0 | 0 | 198 | 165015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 64231 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 7899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 200 | 369671 | 0
| 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 94.32% | 1 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 99.36% | 1 | 0 | 7099 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 |  | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844
| 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 60.8% | 1 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 100% | 1 | 0 | 0 | 24 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-11 | QTR4 | 23/24 | 507 | 801387
| 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 101.1% | 1 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | 103.3% | 1 | -144 | 0 | 29 | 48 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 1 | 675 | 894 | 824 | 100% | 3 | 70 | 0 | 0 | 217 | 2 | 4914622 | 138161 | 4776461 | 4921721 | 4831405 | 0 | 0 | 0 | 4831405 | 4824162 | 100% | 3 | -144 | 7099 | 96 | 121 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0
| District 05 Totals |  |  |  |  | 12 | 21 | 16 | 2665 | 4036 | 3928 | 83.33% | 10 | 108 | 0 | 0 | 1127 | 244 | 31384001 | 592161 | 30791840 | 31712931 | 31888623 | 0 | 0 | 0 | 31888623 | 31715581 | 100% | 12 | -157252 | 328929 | 529 | 569 | 0 | 0 | 153488 | 0 | 0 | 200 | 176941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 64231 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 7899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 202 | 381597 | 0
| 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 73.4% | 1 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | 105.2% | 1 | -286983 | 148832 | 48 | 29 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 119% | 1 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 106.7% | 1 | 488935 | 455645 | 61 | 44 | 0 | 0 | 55800 | 0 | 0 | 95 | 222248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 524979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 |  | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 78.93% | 1 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | 97.57% | 1 | -232397 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | 101.6% | 1 | -4559 | 0 | 16 | 22 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 4 | 8 | 8 | 1460 | 1810 | 1618 | 100% | 4 | 192 | 0 | 0 | 255 | 95 | 27866824 | 302698 | 27564126 | 28471300 | 28512117 | 0 | 540000 | 540000 | 29052117 | 28886468 | 100% | 4 | -35004 | 604477 | 140 | 115 | 0 | 0 | 165807 | 0 | 0 | 95 | 285852 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92265 | 0 | 0 | 0 | 5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 744068 | 213129
| 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 124.6% | 0 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -1.824% | 1 | -6838357 | -65427 | 60 | 80 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD
| 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | 87.5% | 1 | -21 | 0 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 2 | 3 | 2 | 880 | 1227 | 1223 | 50% | 1 | 4 | 0 | 0 | 347 | 0 | 7866697 | 134395 | 7732302 | 7801270 | 7585624 | 0 | 0 | 0 | 7585624 | 621755 | 100% | 2 | -6838378 | -65427 | 80 | 86 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0
| District 06 Totals |  |  |  |  | 6 | 11 | 10 | 2340 | 3037 | 2841 | 83.33% | 5 | 196 | 0 | 0 | 602 | 95 | 35733521 | 437093 | 35296428 | 36272570 | 36097741 | 0 | 540000 | 540000 | 36637741 | 29508223 | 100% | 6 | -6873382 | 539050 | 220 | 201 | 0 | 0 | 93991 | 0 | 0 | 95 | 285852 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 106069 | 0 | 0 | 0 | 23236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 95 | 704134 | 213129
| 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 99.8% | 1 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 106.3% | 1 | 117308 | 206565 | 66 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900
| 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 98.1% | 1 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | 101.9% | 1 | -2665 | 0 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 2 | 4 | 4 | 710 | 871 | 866 | 100% | 2 | 5 | 0 | 0 | 154 | 7 | 8937902 | 100000 | 8837902 | 9144467 | 9093135 | 0 | 0 | 0 | 9093135 | 9202070 | 100% | 2 | 114643 | 206565 | 104 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 138610 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 148506 | 63270
| 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | 335.8% | 0 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 91.04% | 1 | 0 | 207487 | 178 | 55 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300
| 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 107.8% | 1 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | 109.5% | 1 | -27960 | 0 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62
| 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 100% | 1 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | 101.4% | 1 | -125432 | 324762 | 127 | 22 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900
| 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | 105.7% | 1 | -342 | 101105 | 19 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400
| 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 98% | 1 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 108.7% | 1 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700
| 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 85.71% | 1 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 106.1% | 1 | 2811 | 30000 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300
| 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 86.4% | 1 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 107.5% | 1 | 565 | 4646 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 |  | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200
| 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 116.9% | 1 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | 105.4% | 1 | -31871 | 3477169 | 524 | 88 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 8 | 11 | 36 | 2155 | 3879 | 3987 | 87.5% | 7 | -108 | 152 | 0 | 1612 | 112 | 81416430 | 516000 | 80900430 | 85561598 | 85734005 | -570912 | 0 | -570912 | 85163093 | 84430818 | 100% | 8 | -181527 | 4145168 | 896 | 248 | 144 | 0 | 2657209 | 1778987 | 0 | 54 | 1057288 | 334177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153935 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 58 | 388903 | 71647 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 418 | 112 | 4129408 | 2272972
| District 07 Totals |  |  |  |  | 10 | 15 | 40 | 2865 | 4750 | 4853 | 90% | 9 | -103 | 152 | 0 | 1766 | 119 | 90354332 | 616000 | 89738332 | 94706065 | 94827140 | -570912 | 0 | -570912 | 94256228 | 93632888 | 100% | 10 | -66884 | 4351733 | 1000 | 305 | 144 | 0 | 2657209 | 1778987 | 0 | 54 | 1195898 | 397447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157745 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 65 | 388903 | 71647 | 0 | 0 | 0 | 0 | 22 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 418 | 119 | 4277914 | 2336242
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 38.1% | 1 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 98.62% | 1 | 0 | 25000 | 4 | 15 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 1 | 2 | 1 | 357 | 376 | 155 | #VALUE! | 1 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 100% | 1 | 0 | 25000 | 4 | 15 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0
| District 08 Totals |  |  |  |  | 1 | 2 | 1 | 357 | 376 | 155 | 100% | 1 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 100% | 1 | 0 | 25000 | 4 | 15 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 44 | 77 | 90 | 11749 | 17828 | 17544 | 88.64% | 39 | 284 | 12 | 0 | 5507 | 604 | 235611418 | 2550301 | 233061117 | 239646399 | 239767009 | -45432 | 540000 | 494568 | 240261577 | 241140492 | 97.73% | 43 | 1325476 | 4250430 | 3423 | 1565 | 165 | 134 | 2175634 | 610212 | 313 | 353 | 1956947 | 406989 | 0 | 0 | 2420 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 643366 | 0 | 0 | 0 | 9126 | 1041 | 0 | 0 | 0 | 0 | 516 | 8 | 473856 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 244541 | 238455 | 120 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 1134 | 525 | 4407636 | 1256697
| Statewide District Let Contracts SubTotal |  |  |  |  | 28 | 46 | 111 | 8986 | 13493 | 13270 | 82.14% | 23 | 223 | 182 | 0 | 3873 | 634 | 310612453 | 1804471 | 308807983 | 325138089 | 326044106 | -551882 | 1375800 | 823918 | 326868024 | 318787954 | 92.86% | 26 | -442150 | 14567387 | 1965 | 1081 | 144 | 277 | 6799088 | 3758222 | 0 | 284 | 6039547 | 493885 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 2 | 1028796 | 121938 | 15 | 0 | 200561 | 324413 | 0 | 0 | 0 | 0 | 372 | 58 | 652454 | 85050 | 0 | 0 | 0 | 0 | 135 | 13 | 258951 | 258951 | 0 | 0 | 0 | 0 | 0 | 0 | -176824 | 0 | 865 | 634 | 14836948 | 5042461
| Statewide Totals |  |  |  |  | 72 | 123 | 201 | 20735 | 31321 | 30814 | 86.11% | 62 | 507 | 194 | 0 | 9380 | 1238 | 546223871 | 4354772 | 541869100 | 564784488 | 565811115 | -597314 | 1915800 | 1318486 | 567129601 | 559928446 | 95.83% | 69 | 883326 | 18817817 | 5388 | 2646 | 309 | 411 | 8974722 | 4368434 | 313 | 637 | 7996494 | 900874 | 0 | 0 | 36792 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 0 | 0 | 219 | 32 | 1672162 | 121938 | 15 | 0 | 209687 | 325454 | 0 | 0 | 0 | 0 | 888 | 66 | 1126310 | 85050 | 0 | 0 | 102645 | 0 | 135 | 13 | 503492 | 497406 | 120 | 0 | 0 | 0 | 0 | 0 | -182353 | 0 | 1999 | 1159 | 19244584 | 6299158

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1U15 | 44448515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-01-13 | 9191000 | 9286906 | 8593729 | 95906.42 | 0 | 8866277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593729 | 8866277 | 272547 | 9151070
1 | E1U97 | 44789615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 3990000 | 4021977 | 3979990 | 31977.22 | 0 | 3978102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 1965526 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1W15 | 44464315201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-08-17 | 572414 | 613908 | 573719 | 41493.75 | 0 | 573719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573719 | 573719 | 0 | 767485
1 | T1846 | 44156115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-25 | 3477042 | 3477042 | 3332356 | 0 | 0 | 3322154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332356 | 3322154 | -10202 | 3367086
1 | T1847 | 43805715201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-10-26 | 1159034 | 1218049 | 1206007 | 59015.14 | 0 | 1205156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 1023962
2 | E200K | 43737515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-05-10 | 596179 | 596809 | 579939 | 630 | 0 | 579939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579939 | 579939 | 0 | 642935
2 | E20G1 | 43451415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-17 | 8137606 | 11055579 | 11421194 | 2917973.3 | 0 | 11421194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11421194 | 11421194 | 0 | 9316377
2 | E2Z23 | 43655815201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-15 | 23611420 | 27138289 | 28700280 | 3526869.4 | 0 | 28809279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28700280 | 28809279 | 108999 | 23815761
2 | T2820 | 43231615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 6513333 | 6536983 | 6298184 | 23649.6 | -45432 | 6786189 | -45432 | 0 | 0 | 0 | 0 | 0 | -45432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45432 | 6252752 | 6786189 | 533437 | 8131499
2 | T2834 | 44326115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 9753946 | 9932433 | 10044314 | 178487.31 | 0 | 10184626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10044314 | 10184626 | 140312 | 11499594
2 | T2896 | 44284815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 3802716 | 3802716 | 3666172 | 0 | 0 | 3666172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 4117339
2 | T2897 | 44554615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 7947765 | 7947765 | 8246084 | 0 | 0 | 8193910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 11037253
2 | T2926 | 44703715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 12488206 | 12488206 | 12735786 | 0 | 0 | 12755313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 12922548
2 | T2927 | 44762935201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 737944 | 737944 | 698279 | 0 | 0 | 698279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698279 | 698279 | 0 | 752837
2 | T2931 | 44722615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 595321 | 595321 | 526968 | 0 | 0 | 526968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526968 | 526968 | 0 | 725236
2 | T2935 | 43917715201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 688840 | 688840 | 661650 | 0 | 0 | 661650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661650 | 661650 | 0 | 865701
2 | T2958 | 44615425201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-06-14 | 3795580 | 3795580 | 3741800 | 0 | 0 | 3742922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 3808947
2 | T2980 | 45220115201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-10-25 | 1193458 | 1193458 | 1138988 | 0 | 0 | 1138988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 2555282
3 | E3V87 | 44573415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-08 | 4255368 | 4255368 | 4147787 | 0 | 0 | 4133951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 4883807
3 | E3W17 | 44759015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-10 | 3130216 | 3130216 | 3176618 | 0 | 0 | 3169412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 4310828
3 | E3W27 | 43464515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-15 | 3980189 | 4006691 | 4118899 | 26502.21 | 0 | 4101914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 4847742
3 | E3W54 | 42359155201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-07-13 | 3139310 | 3241997 | 3289104 | 102686.83 | 70800 | 3289104 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 70800 | 3359904 | 3289104 | -70800 | 2935414 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | T3719 | 43921415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-05-25 | 2161422 | 2219469 | 2278041 | 58046.15 | 0 | 2271197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 3319649
3 | T3767 | 44188125201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 1798857 | 1800807 | 1823631 | 1950 | 0 | 1837783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1816518
3 | T3774 | 44115615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-10-26 | 2352518 | 2352518 | 2482697 | 0 | 0 | 2481516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 2793292
3 | T3803 | 44403915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7221201 | 7242100 | 7302859 | 20899.02 | 0 | 7410703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 6606379
3 | T3814 | 43989215201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 2042361 | 2052823 | 2049639 | 10462.01 | 0 | 2051119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 1702970
3 | T3832 | 44986815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 391274 | 391274 | 365673 | 0 | 0 | 365673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365673 | 365673 | 0 | 417471
3 | T3847 | 44365025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 8306085 | 8382009 | 9159429 | 75924.28 | 0 | 9121506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 7884744
4 | E4T19 | 43310955201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-03-29 | 148094245 | 151713231 | 158402319 | 3618985.82 | 1375000 | 159445264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375000 | 0 | 0 | 0 | 0 | 0 | 1375000 | 1375000 | 159777319 | 159445264 | -332055 | 130080160 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
4 | E4W15 | 44611215201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-02-03 | 2771566 | 2822338 | 2686822 | 50771.57 | 0 | 2675635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 3211732
4 | E4W39 | 44412115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-02-03 | 2588046 | 2588046 | 2728223 | 0 | 0 | 2725656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 2290170
4 | E4W40 | 44609915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2023-03-03 | 1223473 | 1223473 | 1121989 | 0 | -50970 | 1027689 | -50970 | 0 | 0 | 0 | 0 | 0 | -50970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50970 | 1071019 | 1027689 | -43330 | 1203020
4 | T4477 | 23025665201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 45221786 | 46013498 | 47012029 | 791712.01 | 0 | 47480610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47012029 | 47480610 | 468581 | 48103370 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4566 | 43976115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 4627786 | 4748358 | 4545695 | 120572.24 | 0 | 4643097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545695 | 4643097 | 97402 | 5224694
4 | T4585 | 43533715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 15518729 | 16395821 | 15822170 | 877092.1 | 0 | 15987859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 15323089 | A6 | ICC - BAM/INCENTIVE-DISINCENT
4 | T4610 | 44426515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4142494 | 4142494 | 3658735 | 0 | 0 | 3642576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 4002406
4 | T4611 | 44158215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 7152130 | 7150760 | 6812663 | -1370 | 0 | 6766023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | 8132476
4 | T4612 | 42957645201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-04-27 | 6700410 | 6959205 | 7215672 | 258794.43 | 0 | 7199967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 6372835
4 | T4618 | 44384315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 1266009 | 1266009 | 1196561 | 0 | 0 | 1196630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 1146916
4 | T4634 | 44177015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1746923 | 1746923 | 1740697 | 0 | 0 | 1736981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 1767920
4 | T4640 | 43771715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 6949432 | 7359443 | 7308401 | 410010.11 | 0 | 7303926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 6229901
4 | T4642 | 44610315201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 2584711 | 2601574 | 2230880 | 16862.56 | 0 | 2230536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 2408671
5 | E55A2 | 44539515201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2022-05-03 | 2300883 | 2307982 | 2243671 | 7099.26 | 0 | 2243671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243671 | 2243671 | 0 | 3525844
5 | E56B9 | 44892315201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2023-03-07 | 698401 | 698401 | 660240 | 0 | 0 | 660240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660240 | 660240 | 0 | 801387
5 | E57B0 | 44139515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-04-04 | 1915338 | 1915338 | 1927494 | 0 | 0 | 1927350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 1563670
5 | T5725 | 44351215201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 4062453 | 4217199 | 4121213 | 154746.07 | 0 | 4064034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4121213 | 4064034 | -57178 | 5797838
5 | T5729 | 43565715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 10638248 | 10677535 | 11115999 | 39287.05 | 0 | 11021098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 15691232
5 | T5740 | 43898215201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 2406406 | 2511349 | 2568507 | 104942.61 | 0 | 2566717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568507 | 2566717 | -1791 | 2297944
5 | T5755 | 44568715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 1071415 | 1072209 | 1061331 | 793.38 | 0 | 1059847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061331 | 1059847 | -1484 | 734929
5 | T5762 | 44351415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2950212 | 2990212 | 3032852 | 40000 | 0 | 3032337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 1861686
5 | T5769 | 44571515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-10-05 | 1830300 | 1832918 | 1800435 | 2618.11 | 0 | 1800417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800435 | 1800417 | -18 | 1120306
5 | T5775 | 44570715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 937052 | 937052 | 953863 | 0 | 0 | 953841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953863 | 953841 | -22 | 869794
5 | T5776 | 44577115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 1821012 | 1822431 | 1669665 | 1418.98 | 0 | 1669182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669665 | 1669182 | -483 | 749626
5 | T5790 | 44976415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 752281 | 730305 | 733353 | -21975.86 | 0 | 733353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733353 | 733353 | 0 | 919900
6 | E6M98 | 43029159201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-24 | 6969697 | 6904270 | 6963848 | -65426.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6963848 | 0 | -6963848 | 9167407 | LBDB | LOW BID DESIGN BUILD
6 | E6O30 | 44734515201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-04-27 | 897000 | 897000 | 747267 | 0 | 0 | 747246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747267 | 747246 | -21 | 902746
6 | T6461 | 43647915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 3700000 | 3848832 | 3802731 | 148832.12 | 320000 | 3835748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 4423635 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6535 | 44389315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 18130831 | 18586475 | 18825792 | 455644.58 | 0 | 19314726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18825792 | 19314726 | 488935 | 17118737 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6549 | 44390715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 4134866 | 4134866 | 3997859 | 0 | 220000 | 3985462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6570 | 44391015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1901127 | 1901127 | 1885735 | 0 | 0 | 1881176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 1978037
7 | E7N73 | 43955315201 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2021-02-10 | 6131310 | 6338797 | 6305080 | 207487.31 | -570912 | 5734168 | -570912 | 0 | 0 | 0 | 0 | 0 | -570912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -570912 | 5734168 | 5734168 | 0 | 6350300
7 | E7P19 | 44025415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-01-11 | 5191258 | 5191258 | 5651758 | 0 | 0 | 5623798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 5707114
7 | E7P32 | 44165215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-08 | 6091557 | 6416319 | 6316136 | 324761.8 | 0 | 6190704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6316136 | 6190704 | -125432 | 6992900
7 | E7P81 | 44165615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-04-12 | 2391656 | 2492761 | 2474615 | 101104.64 | 0 | 2474272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 2000400
7 | E7Q20 | 44380615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1219976 | 1219975 | 1270757 | -0.94 | 0 | 1271460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | 1145700
7 | E7Q21 | 44602615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 2654159 | 2684159 | 2759623 | 30000 | 0 | 2762434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 2504300
7 | E7Q22 | 44165315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1489626 | 1494272 | 1546615 | 4645.84 | 0 | 1547180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 1595200
7 | E7R20 | 41075525201 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2018-05-15 | 56246888 | 59724057 | 59431792 | 3477169.13 | 0 | 59377550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59431792 | 59377550 | -54242 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | T7449 | 43953215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 4459994 | 4666559 | 4582670 | 206564.97 | 0 | 4694270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4582670 | 4694270 | 111600 | 4598900
7 | T7506 | 44549415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-03-29 | 4477908 | 4477908 | 4516174 | 0 | 0 | 4513509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 4643300
8 | E8U47 | 43854915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-09-12 | 1133672 | 1158672 | 1068668 | 25000 | 0 | 1068668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 2868747

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | -12039 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 2 | 01co | 1 | 2
01CO | 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 59015 | 83 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 3 | 01do | 3 | 5
01DO | 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 272547 | 95906 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO | 10 | 02co | 6 | 15
01DO | 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 31977 | 22 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 49 | 0 | 0 | 0 | 0 |  | DO | 3 | 02do | 16 | 18
01DO | 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 0 | 41494 | 0 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO | 7 | 03co | 19 | 25
02CO | 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 456060 | 23650 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 4 | 03do | 26 | 29
02CO | 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 140312 | 178487 | 171 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594 |  |  | 0 | 70 | 0 | 0 | 0 | 0 |  | CO | 10 | 04co | 30 | 39
02CO | 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO | 4 | 04do | 40 | 43
02CO | 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253 |  |  | 1 | 27 | 0 | 0 | 0 | 0 |  | CO | 9 | 05co | 44 | 52
02CO | 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548 |  |  | 0 | 19 | 0 | 0 | 0 | 0 | T | CO | 3 | 05do | 53 | 55
02CO | 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 4 | 06co | 56 | 59
02CO | 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 2 | 06do | 60 | 61
02CO | 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 0 | 0 | 6 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 2 | 07co | 62 | 63
02CO | 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 0 | 40 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 8 | 07do | 64 | 71
02CO | 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 72 | 71
02DO | 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 0 | 630 | 1 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05 |  |  | 87 | 10 | 0 | 0 | 0 | 0 |  | DO | 1 | 08do | 72 | 72
02DO | 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 0 | 2917973 | 194 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 1123706 | 3526869 | 109 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26 |  |  | 11 | 143 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 58046 | 137 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO |  | 0
03CO | 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1950 | 65 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 0 | 220 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 20899 | 225 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95 |  |  | 0 | 78 | 0 | 0 | -5529 | 0 |  | CO
03CO | 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 10462 | 151 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75 |  |  | 0 | 96 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 75924 | 138 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 26502 | 75 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | -70800 | 102687 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT | 2 | 35 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 598393 | 791712 | 277 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 92 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 96348 | 120572 | 150 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 877092 | 127 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 0 | 189 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | -1370 | 123 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 258794 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 0 | 63 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 625462 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 16863 | 37 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 5349446 | 3618986 | 181 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 112 | 0 | 0 | -48896 | 0 |  | DO
04DO | 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 50772 | 14 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 41751 | 27 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | -43330 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | -57178 | 154746 | 45 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 39287 | 76 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | -1791 | 104943 | 39 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8 |  |  | 167 | 114 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | -1484 | 793 | 94 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 40000 | 128 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1 |  |  | 4 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | -18 | 2618 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | -22 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | -1198 | 1419 | 9 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55 |  |  | 9 | 41 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 0 | -21976 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 | 2024-07-01 | QTR1 | 24/25 | 515 | 919900 |  |  | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 0 | 7099 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-11 | QTR4 | 23/24 | 507 | 801387 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35 |  |  | 2 | 48 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 148832 | 48 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 488935 | 455645 | 61 | 0 | 0 | 55800 | 0 | 0 | 95 | 222248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 524979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 0 | 16 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -6838357 | -65427 | 60 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD | 0 | 80 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | -21 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 117308 | 206565 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 0 | 207487 | 178 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | -125432 | 324762 | 127 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 101105 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 30000 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 4646 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | -31871 | 3477169 | 524 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 88 | 0 | 0 | -127928 | 0 |  | DO
08DO | 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 25000 | 4 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0