## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 20941284 | 20713452 | 21840596 | 21140420 | 0 | 21173629 | 2.222% | 100% | 898257 | 4.337% | 899312 | 4.294% | 1104 | 426 | 38.59% | 131 | 11.87% | 0 | 0% | 184 | 16.67% | 1288 | 16.67% | 1823 | 1805 | 1248 | 13.04% | 80%
| District Let | 33375706 | 32977609 | 33553775 | 32635194 | 0 | 32710171 | -0.811% | 100% | 252348 | 0.7652% | 178069 | 0.5335% | 1905 | 344 | 18.06% | 166 | 8.714% | 67 | 3.517% | 128 | 6.719% | 2100 | 10.24% | 2556 | 2526 | 2016 | 5.827% | 85.71%
| All Contracts | 54316990 | 53691061 | 55394371 | 53775614 | 0 | 53883800 | 0.359% | 100% | 1150605 | 2.143% | 1077381 | 1.984% | 3009 | 770 | 25.59% | 297 | 9.87% | 67 | 2.227% | 312 | 10.37% | 3388 | 12.6% | 4379 | 4331 | 3264 | 8.475% | 83.33%
2 | Central Let | 110523269 | 109099685 | 111318374 | 112890041 | 0 | 113366452 | 3.911% | 100% | 1279960 | 1.173% | 795106 | 0.7194% | 4206 | 1740 | 41.37% | 798 | 18.97% | 544 | 12.93% | 1109 | 26.37% | 5859 | 39.3% | 7397 | 7309 | 4771 | 13.43% | 75%
| District Let | 32345205 | 32040913 | 38790677 | 39686706 | 0 | 39722319 | 23.97% | 33.33% | 6592276 | 20.57% | 6445472 | 19.93% | 1210 | 304 | 25.12% | 214 | 17.69% | 22 | 1.818% | 513 | 42.4% | 1745 | 44.21% | 2257 | 2233 | 1715 | 41.74% | 0%
| All Contracts | 142868474 | 141140598 | 150109051 | 152576747 | 0 | 153088771 | 8.465% | 91.3% | 7872236 | 5.578% | 7240578 | 5.068% | 5416 | 2044 | 37.74% | 1012 | 18.69% | 566 | 10.45% | 1622 | 29.95% | 7604 | 40.4% | 9654 | 9542 | 6486 | 19.76% | 65.22%
3 | Central Let | 124592655 | 123236185 | 125222405 | 130620455 | 0 | 130482632 | 5.88% | 91.67% | 866751 | 0.7033% | 629749 | 0.5054% | 4937 | 2866 | 58.05% | 993 | 20.11% | 1483 | 30.04% | 154 | 3.119% | 6574 | 33.16% | 9568 | 9527 | 5668 | 14.81% | 79.17%
| District Let | 48388906 | 47988906 | 49219843 | 49749026 | 800 | 49965192 | 4.118% | 100% | 894811 | 1.865% | 830937 | 1.717% | 2002 | 596 | 29.77% | 267 | 13.34% | 238 | 11.89% | 21 | 1.049% | 2261 | 12.94% | 3140 | 3120 | 2257 | 12.74% | 100%
| All Contracts | 172981561 | 171225091 | 174442248 | 180369481 | 800 | 180447824 | 5.386% | 93.33% | 1761562 | 1.029% | 1460686 | 0.8444% | 6939 | 3462 | 49.89% | 1260 | 18.16% | 1721 | 24.8% | 175 | 2.522% | 8835 | 27.32% | 12708 | 12647 | 7925 | 14.21% | 83.33%
4 | Central Let | 136231474 | 135186142 | 139286391 | 137227612 | -75000 | 138030387 | 2.104% | 100% | 3171550 | 2.346% | 3270366 | 2.401% | 5847 | 1527 | 26.12% | 514 | 8.791% | 231 | 3.951% | 244 | 4.173% | 6322 | 8.124% | 8247 | 8223 | 6182 | 5.729% | 100%
| District Let | 170952172 | 170398939 | 174775003 | 174748202 | 1375000 | 175595715 | 3.05% | 100% | 3894783 | 2.286% | 3864582 | 2.261% | 3334 | 470 | 14.1% | 249 | 7.469% | 247 | 7.409% | 0 | 0% | 3581 | 7.409% | 4162 | 3878 | 3159 | -5.249% | 100%
| All Contracts | 307183646 | 305585081 | 314061394 | 311975814 | 1300000 | 313626102 | 2.631% | 100% | 7066333 | 2.312% | 7134948 | 2.323% | 9181 | 1997 | 21.75% | 763 | 8.311% | 478 | 5.206% | 244 | 2.658% | 9903 | 7.864% | 12409 | 12101 | 9341 | 1.743% | 100%
5 | Central Let | 82882748 | 81934998 | 85206192 | 88779387 | -11806 | 90361953 | 10.28% | 80% | 2354887 | 2.874% | 2323443 | 2.803% | 3820 | 967 | 25.31% | 639 | 16.73% | 52 | 1.361% | 230 | 6.021% | 4102 | 7.382% | 5747 | 5635 | 4029 | 5.471% | 86.67%
| District Let | 15439496 | 15163335 | 15493054 | 15574165 | 0 | 15595703 | 2.851% | 100% | 18928 | 0.1248% | 53559 | 0.3469% | 1105 | 179 | 16.2% | 158 | 14.3% | 0 | 0% | 2 | 0.181% | 1107 | 0.181% | 1444 | 1374 | 1037 | -6.154% | 100%
| All Contracts | 98322244 | 97098333 | 100699246 | 104353552 | -11806 | 105957656 | 9.124% | 85% | 2373815 | 2.445% | 2377002 | 2.418% | 4925 | 1146 | 23.27% | 797 | 16.18% | 52 | 1.056% | 232 | 4.711% | 5209 | 5.766% | 7191 | 7009 | 5066 | 2.863% | 90%
6 | Central Let | 61485961 | 60833781 | 62276150 | 61285135 | 1220000 | 61641849 | 1.328% | 100% | 1084069 | 1.782% | 790189 | 1.285% | 3400 | 417 | 12.26% | 242 | 7.118% | 32 | 0.9412% | 95 | 2.794% | 3527 | 3.735% | 4186 | 3828 | 3169 | -6.794% | 100%
| District Let | 17568829 | 17334434 | 18059296 | 17794829 | 0 | 8864946 | -48.86% | 100% | 542214 | 3.128% | 490467 | 2.792% | 2390 | 419 | 17.53% | 295 | 12.34% | 314 | 13.14% | 0 | 0% | 2704 | 13.14% | 3418 | 3386 | 2672 | 11.8% | 80%
| All Contracts | 79054790 | 78168215 | 80335446 | 79079964 | 1220000 | 70506795 | -9.801% | 100% | 1626283 | 2.08% | 1280656 | 1.62% | 5790 | 836 | 14.44% | 537 | 9.275% | 346 | 5.976% | 95 | 1.641% | 6231 | 7.617% | 7604 | 7214 | 5841 | 0.8808% | 92.86%
7 | Central Let | 35317362 | 34825499 | 36828666 | 36662951 | 0 | 37686825 | 8.216% | 83.33% | 1630221 | 4.681% | 1511305 | 4.279% | 1985 | 333 | 16.78% | 168 | 8.463% | 0 | 0% | 50 | 2.519% | 2035 | 2.519% | 2529 | 2505 | 2004 | 0.9572% | 100%
| District Let | 90403008 | 89816008 | 94646285 | 94750116 | 0 | 93271097 | 3.847% | 100% | 4254579 | 4.737% | 4243278 | 4.694% | 2555 | 926 | 36.24% | 276 | 10.8% | 418 | 16.36% | 112 | 4.384% | 3085 | 20.74% | 4337 | 4445 | 3243 | 26.93% | 88.89%
| All Contracts | 125720370 | 124641507 | 131474951 | 131413067 | 0 | 130957922 | 5.068% | 93.33% | 5884800 | 4.721% | 5754583 | 4.577% | 4540 | 1259 | 27.73% | 444 | 9.78% | 418 | 9.207% | 162 | 3.568% | 5120 | 12.78% | 6866 | 6950 | 5247 | 15.57% | 93.33%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 313145042 | 312366725 | 321612649 | 325743385 | 4375439 | 329149165 | 5.373% | 87.5% | 8692039 | 2.783% | 8467609 | 2.704% | 4703 | 746 | 15.86% | 457 | 9.717% | 279 | 5.932% | -80 | -1.701% | 4902 | 4.231% | 5960 | 5238 | 4035 | -14.2% | 0%
| All Contracts | 313145042 | 312366725 | 321612649 | 325743385 | 4375439 | 329149165 | 5.373% | 87.5% | 8692039 | 2.783% | 8467609 | 2.704% | 4703 | 746 | 15.86% | 457 | 9.717% | 279 | 5.932% | -80 | -1.701% | 4902 | 4.231% | 5960 | 5238 | 4035 | -14.2% | 100%
Totals This Qtr | Central Let | 571974753 | 565829742 | 581978774 | 588606001 | 1133194 | 592743727 | 4.757% | 93.55% | 11285695 | 1.995% | 10219470 | 1.787% | 25299 | 8276 | 32.71% | 3485 | 13.78% | 2342 | 9.257% | 2066 | 8.166% | 29707 | 17.42% | 39497 | 38832 | 27071 | 7.004% | 86.02%
| District Let | 721618364 | 718086869 | 746150582 | 750681623 | 5751239 | 744874308 | 3.73% | 94.12% | 25141978 | 3.501% | 24573973 | 3.405% | 19204 | 3984 | 20.75% | 2082 | 10.84% | 1585 | 8.253% | 696 | 3.624% | 21485 | 11.88% | 27274 | 26200 | 20134 | 4.843% | 88.24%
| All Contracts | 1293593117 | 1283916611 | 1328129356 | 1339287624 | 6884433 | 1337618035 | 4.183% | 93.75% | 36427673 | 2.837% | 34793443 | 2.69% | 44503 | 12260 | 27.55% | 5567 | 12.51% | 3927 | 8.824% | 2762 | 6.206% | 51192 | 15.03% | 66771 | 65032 | 47205 | 6.072% | 86.81%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2023/2024 | Central Let | 1137964577 | 1126871462 | 1186608484 | 1192777850 | 6046318 | 1204341087 | 6.875% | 87.1% | 49832653 | 4.422% | 48342251 | 4.248% | 50443 | 15125 | 29.98% | 6090 | 12.07% | 5317 | 10.54% | 5633 | 11.17% | 61393 | 21.71% | 79184 | 80497 | 59282 | 17.52% | 74.73%
| District Let | 970354308 | 963168906 | 1003105589 | 993021809 | 11856323 | 992287650 | 3.023% | 91.06% | 35080258 | 3.642% | 32751273 | 3.375% | 33080 | 6744 | 20.39% | 4161 | 12.58% | 1348 | 4.075% | 2277 | 6.883% | 36705 | 10.96% | 46400 | 44681 | 33776 | 2.104% | 93.5%
| All Contracts | 2108318885 | 2090040368 | 2189714073 | 2185799659 | 17902641 | 2196628737 | 5.1% | 88.67% | 84912911 | 4.063% | 81093524 | 3.846% | 83523 | 21869 | 26.18% | 10251 | 12.27% | 6665 | 7.98% | 7910 | 9.47% | 98098 | 17.45% | 125584 | 125178 | 93058 | 11.42% | 82.2%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1825 | 43982715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 11 | 350 | 671 | 668 | 142.6% | 0 | 3 | 0 | 0 | 147 | 174 | 8278071 | 77832 | 8200239 | 8939807 | 8867401 | 0 | 0 | 0 | 8867401 | 8929131 | 108.9% | 1 | 86356 | 661736 | 124 | 45 | 0 | 30 | 233423 | 0 | 0 | 62 | 279341 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24626 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 673447 | 398388 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-05-29 | QTR4 | 23/24 | 118 | 7852554.7
| 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 94.5% | 1 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | 96.89% | 1 | -12039 | 0 | 86 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 |  | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92
| 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 107.7% | 1 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | 104% | 1 | -851 | 59015 | 83 | 24 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4
| 01 | T1860 | 43709615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 9 | 250 | 401 | 398 | 98.8% | 1 | 3 | 0 | 0 | 151 | 0 | 4325722 | 50000 | 4275722 | 4504283 | 4508752 | 0 | 0 | 0 | 4508752 | 4493121 | 105.1% | 1 | -11661 | 178561 | 124 | 27 | 0 | 0 | 28409 | 0 | 0 | 0 | 105237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5020 | 5020 | 0 | 0 | 23159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165795 | 5020 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-10-14 | QTR2 | 24/25 |  | 2024-05-22 | QTR4 | 23/24 | 113 | 2709382.82
| 01 | T1871 | 45224115201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 174 | 196 | 195 | 99.43% | 1 | 1 | 0 | 0 | 22 | 0 | 3701415 | 50000 | 3651415 | 3701415 | 3225904 | 0 | 0 | 0 | 3225904 | 3225904 | 88.35% | 1 | 0 | 0 | 9 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-03 | QTR2 | 24/25 |  | 2024-06-16 | QTR4 | 23/24 | 107 | 4091495.64
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 5 | 6 | 26 | 1104 | 1823 | 1805 | 80% | 4 | 18 | 0 | 0 | 535 | 184 | 20941284 | 227832 | 20713452 | 21840596 | 21140420 | 0 | 0 | 0 | 21140420 | 21173629 | 100% | 5 | 61805 | 899312 | 426 | 131 | 0 | 30 | 261832 | 0 | 0 | 74 | 443593 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 5020 | 5020 | 0 | 0 | 23159 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 28597 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 898257 | 403408
| 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 99.78% | 1 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 96.34% | 1 | 272547 | 95906 | 140 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 |  | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1
| 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 112.8% | 1 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | 101% | 1 | -1888 | 31977 | 22 | 49 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1V15 | 44547115201 | 2023-01-19 | QTR3 | 22/23 | 2 | 0 | 225 | 427 | 410 | 125.3% | 0 | 17 | 0 | 0 | 74 | 128 | 7937275 | 81977 | 7855298 | 7937275 | 7998691 | 0 | 0 | 0 | 7998691 | 7941859 | 101.1% | 1 | -56832 | 0 | 102 | 26 | 0 | 5 | 23878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 28296 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-12-18 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 108 | 8527986.56
| 01 | E1W10 | 44744115201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 200 | 258 | 255 | 98.5% | 1 | 3 | 0 | 0 | 58 | 0 | 5126611 | 54498 | 5072113 | 5135303 | 4999771 | 0 | 0 | 0 | 4999771 | 4990201 | 98.39% | 1 | -9570 | 8692 | 35 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-07-12 | QTR1 | 24/25 | 108 | 5933693.34
| 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 97.78% | 1 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 104.7% | 1 | 0 | 41494 | 0 | 5 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45
| 01 | E1W19 | 44743315201 | 2023-10-19 | QTR2 | 23/24 | 1 | 0 | 175 | 202 | 197 | 97.14% | 1 | 5 | 0 | 0 | 27 | 0 | 3927820 | 50000 | 3877820 | 3927820 | 3916235 | 0 | 0 | 0 | 3916235 | 3896792 | 100.5% | 1 | -19443 | 0 | 18 | 9 | 0 | 0 | 5190 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11509 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-12-12 | QTR2 | 24/25 |  | 2024-09-23 | QTR1 | 24/25 | 108 | 3787595.4
| 01 | E1W20 | 44620215201 | 2023-10-19 | QTR2 | 23/24 | 1 | 1 | 150 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 2630586 | 50000 | 2580586 | 2630586 | 2573059 | 0 | 0 | 0 | 2573059 | 2559128 | 99.17% | 1 | -13930 | 0 | 27 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20390 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-09-12 | QTR1 | 24/25 | 118 | 2937557.72
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 7 | 9 | 7 | 1905 | 2556 | 2526 | 85.71% | 6 | 30 | 0 | 0 | 523 | 128 | 33375706 | 398097 | 32977609 | 33553775 | 32635194 | 0 | 0 | 0 | 32635194 | 32710171 | 100% | 7 | 170884 | 178069 | 344 | 166 | 0 | 5 | 72877 | 0 | 0 | 0 | 57959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 21187 | 0 | 0 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 95906 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 128 | 252348 | 0
| District 01 Totals |  |  |  |  | 12 | 15 | 33 | 3009 | 4379 | 4331 | 83.33% | 10 | 48 | 0 | 0 | 1058 | 312 | 54316990 | 625929 | 53691061 | 55394371 | 53775614 | 0 | 0 | 0 | 53775614 | 53883800 | 100% | 12 | 232689 | 1077381 | 770 | 297 | 0 | 35 | 334709 | 0 | 0 | 74 | 501552 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 26207 | 5020 | 0 | 0 | 27577 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 124503 | 0 | 0 | 0 | 0 | 0 | 67 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 312 | 1150605 | 403408
| 02 | T2804 | 44137215201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 300 | 903 | 903 | 157.7% | 0 | 0 | 0 | 0 | 179 | 424 | 7398298 | 61648 | 7336650 | 7431649 | 7733354 | 0 | 0 | 0 | 7733354 | 7955154 | 108.4% | 1 | 240397 | 33351 | 348 | 82 | 0 | 0 | 35071 | 0 | 0 | 173 | 51032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 3351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 89454 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 |  | 2024-03-02 | QTR3 | 23/24 | 208 | 6176554.21
| 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | 106.9% | 1 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 104.2% | 1 | 456060 | 23650 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13
| 02 | T2828 | 44105015201 | 2021-12-08 | QTR2 | 21/22 | 3 | 6 | 200 | 680 | 680 | 143.5% | 0 | 0 | 0 | 0 | 229 | 251 | 2858409 | 52000 | 2806409 | 2966328 | 3044806 | 0 | 0 | 0 | 3044806 | 3042275 | 108.4% | 1 | 2144 | 107919 | 320 | 73 | 0 | 0 | 42323 | 0 | 0 | 87 | 103244 | 17949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 164 | 4676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 251 | 150243 | 17949 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 208 | 3146528.67
| 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 106.8% | 1 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 105.7% | 1 | 140312 | 178487 | 171 | 70 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594
| 02 | T2838 | 44342015201 | 2022-04-27 | QTR4 | 21/22 | 2 | 5 | 300 | 661 | 661 | 146% | 0 | 0 | 0 | 0 | 223 | 138 | 11945708 | 100832 | 11844876 | 12005007 | 12120635 | 0 | 0 | 0 | 12120635 | 12067135 | 101.9% | 1 | -46610 | 59300 | 126 | 97 | 0 | 44 | 87730 | 0 | 0 | 91 | 40079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 134699 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 |  | 2024-07-17 | QTR1 | 24/25 | 208 | 12401357.97
| 02 | T2853 | 44714915201 | 2022-06-08 | QTR4 | 21/22 | 3 | 4 | 540 | 680 | 663 | 100.6% | 1 | 17 | 0 | 0 | 120 | 20 | 17135161 | 200000 | 16935161 | 17359701 | 17949301 | 0 | 0 | 0 | 17949301 | 17746566 | 104.8% | 1 | -196328 | 224540 | 72 | 48 | 0 | 17 | 89971 | 0 | 0 | 27 | 312995 | 9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 6406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25 | -83255 | 0 | 0 | 20 | 337947 | 21170 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-08-30 | QTR1 | 24/25 | 208 | 22151002.61
| 02 | T2864 | 20765825201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 140 | 451 | 451 | 207.9% | 0 | 0 | 0 | 0 | 160 | 151 | 2568964 | 50000 | 2518964 | 2668964 | 2632044 | 0 | 0 | 0 | 2632044 | 2632301 | 104.5% | 1 | 257 | 100000 | 39 | 121 | 0 | 7 | 97145 | 0 | 0 | 44 | 48577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 145722 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-08-22 | QTR1 | 24/25 | 214 | 2408715.47
| 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 99.33% | 1 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 97.69% | 1 | 0 | 0 | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 |  | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34
| 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 100% | 1 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | 104.5% | 1 | -52174 | 0 | 147 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253
| 02 | T2900 | 40392045201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 100 | 392 | 371 | 139% | 0 | 21 | 0 | 0 | 292 | 0 | 869247 | 37251 | 831996 | 869247 | 857258 | 0 | 0 | 0 | 857258 | 857258 | 103% | 1 | 0 | 0 | 173 | 59 | 0 | 0 | 2298 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 2298 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-14 | QTR1 | 24/25 | 216 | 1017097.24
| 02 | T2909 | 44607915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 250 | 447 | 445 | 99.2% | 1 | 2 | 0 | 0 | 97 | 100 | 7130409 | 68620 | 7061789 | 7130409 | 7454415 | 0 | 0 | 0 | 7454415 | 7438691 | 105.3% | 1 | -15725 | 0 | 129 | 68 | 0 | 0 | 1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 3586 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-09-06 | QTR1 | 24/25 | 208 | 7319755.75
| 02 | T2911 | 44703315201 | 2023-05-17 | QTR4 | 22/23 | 1 | 1 | 260 | 312 | 290 | 91.54% | 1 | 22 | 0 | 0 | 52 | 0 | 5899711 | 60196 | 5839515 | 5916585 | 5921537 | 0 | 0 | 0 | 5921537 | 5926778 | 101.5% | 1 | 5241 | 16874 | 26 | 26 | 0 | 0 | 9350 | 0 | 0 | 0 | 16874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36315 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-07-10 | QTR1 | 24/25 | 214 | 6079797.84
| 02 | T2922 | 44717615201 | 2023-05-17 | QTR4 | 22/23 | 1 | 0 | 200 | 261 | 256 | 97.5% | 1 | 5 | 0 | 0 | 61 | 0 | 4768192 | 52010 | 4716182 | 4768192 | 4978398 | 0 | 0 | 0 | 4978398 | 4983434 | 105.7% | 1 | 5036 | 0 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-07-22 | QTR1 | 24/25 | 214 | 5253038.86
| 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 103.2% | 1 | 19527 | 0 | 41 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 |  | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548
| 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 94.44% | 1 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 99.46% | 1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 |  | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87
| 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 97.78% | 1 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 93.97% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 |  | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05
| 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 93.33% | 1 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 102.2% | 1 | 0 | 0 | 6 | 19 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85
| 02 | T2957 | 44712915201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 164 | 157 | 95.33% | 1 | 7 | 0 | 0 | 14 | 0 | 2432061 | 50000 | 2382061 | 2483046 | 2440068 | 0 | 0 | 0 | 2440068 | 2440833 | 102.5% | 1 | 766 | 50985 | 10 | 4 | 0 | 0 | 2944 | 0 | 0 | 0 | 63883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66827 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 208 | 2377451.33
| 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 99.33% | 1 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 99.93% | 1 | 1123 | 0 | 40 | 24 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4
| 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 91.18% | 1 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 99.61% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 20 | 29 | 27 | 4206 | 7397 | 7309 | 75% | 15 | 88 | 12 | 0 | 2082 | 1109 | 110523269 | 1423583 | 109099685 | 111318374 | 112890041 | -45432 | 0 | -45432 | 112844609 | 113366452 | 100% | 20 | 560026 | 795106 | 1740 | 798 | 0 | 92 | 573908 | 9554 | 60 | 422 | 723706 | 27290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 4 | 21920 | 11829 | 0 | 0 | 0 | 0 | 364 | 616 | 35455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | -25 | -83255 | 0 | 544 | 1109 | 1279960 | 48673
| 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 185.6% | 0 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 102.5% | 1 | 0 | 630 | 1 | 10 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05
| 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 149% | 0 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 141% | 0 | 0 | 2917973 | 194 | 61 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 |  | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83
| 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 134.3% | 0 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 118.6% | 0 | 1123706 | 3526869 | 109 | 143 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 3 | 8 | 30 | 1210 | 2257 | 2233 | 0% | 0 | 24 | 0 | 0 | 534 | 513 | 32345205 | 304293 | 32040913 | 38790677 | 39686706 | 0 | 0 | 0 | 39686706 | 39722319 | 33.33% | 1 | 1123706 | 6445472 | 304 | 214 | 0 | 277 | 2107509 | 1770145 | 0 | 223 | 4130482 | 115377 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 73387 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 513 | 6592276 | 2118274
| District 02 Totals |  |  |  |  | 23 | 37 | 57 | 5416 | 9654 | 9542 | 65.22% | 15 | 112 | 12 | 0 | 2616 | 1622 | 142868474 | 1727876 | 141140598 | 150109051 | 152576747 | -45432 | 0 | -45432 | 152531315 | 153088771 | 91.3% | 21 | 1683732 | 7240578 | 2044 | 1012 | 0 | 369 | 2681417 | 1779699 | 60 | 645 | 4854188 | 142667 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22809 | 0 | 15 | 4 | 35740 | 13057 | 0 | 0 | 0 | 0 | 370 | 616 | 108842 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 120 | 0 | 0 | 0 | 0 | -25 | -83255 | 0 | 566 | 1622 | 7872236 | 2166947
| 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 154.9% | 0 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | 105.1% | 1 | -6844 | 58046 | 137 | 52 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9
| 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 107% | 1 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | 107.5% | 1 | -68789 | 0 | 292 | 81 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-02 | QTR2 | 24/25 |  | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94
| 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 111.3% | 1 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 102.2% | 1 | 14152 | 1950 | 65 | 29 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 |  | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22
| 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 112.1% | 1 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | 105.5% | 1 | -1180 | 0 | 220 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28
| 03 | T3791 | 43937615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 200 | 290 | 290 | 108% | 1 | 0 | 0 | 0 | 90 | 0 | 2097844 | 0 | 2097844 | 2104355 | 1977895 | 0 | 0 | 0 | 1977895 | 1977939 | 94.28% | 1 | 44 | 6511 | 56 | 18 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-03 | QTR1 | 24/25 | 313 | 2307183.3
| 03 | T3792 | 44117115201 | 2023-04-26 | QTR4 | 22/23 | 1 | 1 | 160 | 225 | 224 | 103.8% | 1 | 1 | 0 | 0 | 65 | 0 | 1248264 | 0 | 1248264 | 1248264 | 1306248 | 0 | 0 | 0 | 1306248 | 1306346 | 104.7% | 1 | 98 | 0 | 39 | 19 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-04-08 | QTR4 | 23/24 | 313 | 1870598.48
| 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 128.9% | 0 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 103.6% | 1 | 107844 | 20899 | 225 | 78 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95
| 03 | T3806 | 43973315201 | 2022-04-27 | QTR4 | 21/22 | 3 | 0 | 315 | 660 | 659 | 131.4% | 0 | 1 | 0 | 0 | 345 | 0 | 10103368 | 88637 | 10014731 | 10103368 | 10342165 | 0 | 0 | 0 | 10342165 | 10277452 | 102.6% | 1 | -64713 | 0 | 173 | 72 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 |  | 2024-08-14 | QTR1 | 24/25 | 308 | 10842967.81
| 03 | T3813 | 44159315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 300 | 695 | 695 | 112.7% | 1 | 0 | 0 | 0 | 387 | 8 | 6499662 | 61994 | 6437668 | 6674412 | 6885176 | 0 | 0 | 0 | 6885176 | 6899511 | 107.2% | 1 | 14336 | 174750 | 309 | 48 | 75 | 3 | 179623 | 0 | 15 | 5 | 11079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 8 | 190702 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-08 | QTR2 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 308 | 6445150.22
| 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 211.5% | 0 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 102.9% | 1 | 1480 | 10462 | 151 | 96 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75
| 03 | T3824 | 43769915201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 330 | 416 | 416 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3559704 | 0 | 3559704 | 3559704 | 3648796 | 0 | 0 | 0 | 3648796 | 3648367 | 102.5% | 1 | -429 | 0 | 58 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-30 | QTR2 | 24/25 |  | 2024-08-28 | QTR1 | 24/25 | 308 | 5711547.02
| 03 | T3826 | 44387715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 90 | 322 | 322 | 100% | 1 | 0 | 0 | 0 | 232 | 0 | 942554 | 49324 | 893230 | 942554 | 927016 | 0 | 0 | 0 | 927016 | 927016 | 103.8% | 1 | 0 | 0 | 187 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-04-03 | QTR4 | 23/24 | 314 | 1043116.04
| 03 | T3829 | 44553915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 300 | 380 | 380 | 105.7% | 1 | 0 | 0 | 0 | 63 | 17 | 12211588 | 124814 | 12086774 | 12181493 | 12519374 | 0 | 0 | 0 | 12519374 | 12516178 | 103.6% | 1 | -3196 | -30095 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | 14322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30095 | 0 | 0 | 17 | -15773 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-07-25 | QTR1 | 24/25 | 313 | 12606229.06
| 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 95.56% | 1 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 98.69% | 1 | 0 | 0 | 52 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83
| 03 | T3834 | 44563515201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 270 | 364 | 426 | 115.6% | 1 | -62 | 62 | 0 | 114 | 0 | 19944475 | 150000 | 19794475 | 19944475 | 21545566 | -363010 | 0 | -363010 | 21182556 | 21410083 | 108.2% | 1 | 227527 | 0 | 62 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 |  | 2024-08-14 | QTR1 | 24/25 | 314 | 18371047.42
| 03 | T3842 | 44404015201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 60 | 433 | 424 | 160% | 0 | 9 | 0 | 0 | 373 | 0 | 851756 | 41407 | 810349 | 851756 | 802521 | 0 | 0 | 0 | 802521 | 802521 | 99.03% | 1 | 0 | 0 | 268 | 60 | 45 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 2000 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2024-08-12 | QTR1 | 24/25 | 314 | 869555.5
| 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 113.2% | 1 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | 110.9% | 0 | -37923 | 75924 | 138 | 47 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81
| 03 | T3856 | 44573315201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 166 | 399 | 399 | 114.5% | 1 | 0 | 0 | 0 | 233 | 0 | 6737296 | 71197 | 6666099 | 6737296 | 7134385 | 0 | 0 | 0 | 7134385 | 7124379 | 106.9% | 1 | -10006 | 0 | 152 | 57 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-21 | QTR2 | 24/25 |  | 2024-07-17 | QTR1 | 24/25 | 308 | 7216077.98
| 03 | T3864 | 44562915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 3 | 230 | 347 | 329 | 97.39% | 1 | 18 | 0 | 0 | 105 | 12 | 3480880 | 51096 | 3429784 | 3589639 | 3810464 | 0 | 0 | 0 | 3810464 | 3809861 | 111.1% | 0 | -603 | 108759 | 73 | 32 | 0 | 0 | 12134 | 0 | 0 | 5 | 64017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 44742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 135093 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-08-18 | QTR1 | 24/25 | 308 | 5160701.28
| 03 | T3877 | 43775715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 1 | 273 | 325 | 320 | 98.17% | 1 | 5 | 0 | 0 | 52 | 0 | 11695437 | 150000 | 11545437 | 11701443 | 12402258 | 0 | 0 | 0 | 12402258 | 12455669 | 107.9% | 1 | 53411 | 6006 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13152 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 321 | 9851819.87
| 03 | T3880 | 43078925201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 135 | 199 | 193 | 95.56% | 1 | 6 | 0 | 0 | 64 | 0 | 3380216 | 54568 | 3325648 | 3380216 | 3471279 | 0 | 0 | 0 | 3471279 | 3471279 | 104.4% | 1 | 0 | 0 | 38 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-08-27 | QTR1 | 24/25 | 314 | 5332275.36
| 03 | T3886 | 45221235201 | 2023-09-13 | QTR1 | 23/24 | 1 | 1 | 109 | 155 | 154 | 99.08% | 1 | 1 | 0 | 0 | 46 | 0 | 1444661 | 50000 | 1394661 | 1521683 | 1385235 | 0 | 0 | 0 | 1385235 | 1385235 | 99.32% | 1 | 0 | 77022 | 22 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-05-02 | QTR4 | 23/24 | 314 | 2325343.9
| 03 | T3889 | 45221225201 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 140 | 184 | 127 | 70% | 1 | 57 | 0 | 0 | 29 | 15 | 1570117 | 50000 | 1520117 | 1689632 | 1597844 | 0 | 0 | 0 | 1597844 | 1597844 | 105.1% | 1 | 0 | 119515 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-05-24 | QTR4 | 23/24 | 313 | 1925284.7
| 03 | T3897 | 44845115201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 165 | 254 | 254 | 101.8% | 1 | 0 | 0 | 0 | 86 | 3 | 1349500 | 50000 | 1299500 | 1349500 | 1300591 | 0 | 0 | 0 | 1300591 | 1300571 | 100.1% | 1 | -20 | 0 | 74 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 3 | 1250 | 0 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-10-29 | QTR2 | 24/25 | 321 | 1617297.75
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 24 | 32 | 22 | 4937 | 9568 | 9527 | 79.17% | 19 | 41 | 62 | 0 | 4492 | 159 | 124592655 | 1356470 | 123236185 | 125222405 | 130620455 | -363010 | 0 | -363010 | 130257445 | 130482632 | 91.67% | 22 | 225189 | 629749 | 2866 | 993 | 308 | 38 | 298582 | 0 | 358 | 67 | 418133 | 16851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 49 | 154747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790 | 0 | 30913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35624 | 0 | 1483 | 154 | 866751 | 16851
| 03 | E3Q94 | 21787545201 | 2018-06-14 | QTR4 | 17/18 | 1 | 11 | 1325 | 2106 | 2106 | 117.4% | 1 | 0 | 0 | 0 | 767 | 14 | 31708584 | 150000 | 31558584 | 32410332 | 32832992 | 0 | 0 | 0 | 32832992 | 33087185 | 104.8% | 1 | 254193 | 701748 | 414 | 136 | 0 | 0 | 391404 | 0 | 198 | 10 | 243931 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 103110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 14 | 746509 | 56594 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2024-05-21 | QTR4 | 23/24 | 306 | 25965925.9
| 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 111.1% | 1 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | 98.3% | 1 | -13836 | 0 | 46 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47
| 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 89.78% | 1 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | 102.9% | 1 | -7206 | 0 | 35 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71
| 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 102.7% | 1 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | 104.4% | 1 | -16986 | 26502 | 75 | 28 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 |  | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78
| 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 120% | 1 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | 106.5% | 1 | -70800 | 102687 | 21 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3W88 | 44575515201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 120 | 128 | 124 | 96.67% | 1 | 4 | 0 | 0 | 8 | 0 | 2175239 | 50000 | 2125239 | 2175239 | 2183626 | 0 | 0 | 0 | 2183626 | 2183626 | 102.7% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-06-21 | QTR4 | 23/24 | 313 | 3085002.9
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 6 | 8 | 15 | 2002 | 3140 | 3120 | 100% | 6 | 20 | 0 | 0 | 1117 | 21 | 48388906 | 400000 | 47988906 | 49219843 | 49749026 | 70000 | 800 | 70800 | 49819826 | 49965192 | 100% | 6 | 145365 | 830937 | 596 | 267 | 0 | 0 | 391404 | 0 | 198 | 15 | 270433 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 2 | 224910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 21 | 894811 | 56594
| District 03 Totals |  |  |  |  | 30 | 40 | 37 | 6939 | 12708 | 12647 | 83.33% | 25 | 61 | 62 | 0 | 5609 | 180 | 172981561 | 1756470 | 171225091 | 174442248 | 180369481 | -293010 | 800 | -292210 | 180077271 | 180447824 | 93.33% | 28 | 370554 | 1460686 | 3462 | 1260 | 308 | 38 | 689986 | 0 | 556 | 82 | 688566 | 73445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 51 | 379657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790 | 4 | 38976 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35624 | 0 | 1721 | 175 | 1761562 | 73445
| 04 | T4472 | 41934525201 | 2018-01-31 | QTR3 | 17/18 | 2 | 10 | 1049 | 1423 | 1423 | 110.6% | 1 | 0 | 0 | 0 | 263 | 111 | 33359900 | 182880 | 33177020 | 33746993 | 33295065 | 0 | -75000 | -75000 | 33220065 | 33597249 | 101.3% | 1 | 421739 | 387093 | 176 | 87 | 0 | 0 | 456573 | 0 | 0 | 0 | -143555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188 | 0 | 0 | 71 | 56466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32197 | 0 | 0 | 40 | 81324 | 79113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 484193 | 79113 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2022-06-22 | QTR4 | 21/22 | 409 | 37475055.58 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 106.9% | 1 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 104.5% | 1 | 598393 | 791712 | 277 | 92 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 107% | 1 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 101.3% | 1 | 96348 | 120572 | 150 | 38 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73
| 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 105.2% | 1 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 104% | 1 | 165689 | 877092 | 127 | 55 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 04 | T4598 | 44399615201 | 2022-02-23 | QTR3 | 21/22 | 3 | 6 | 425 | 607 | 607 | 111.8% | 1 | 0 | 0 | 0 | 160 | 22 | 5606708 | 50000 | 5556708 | 5800857 | 5331108 | 0 | 0 | 0 | 5331108 | 5358143 | 96.43% | 1 | 30705 | 194148 | 85 | 47 | 0 | 0 | 0 | 0 | 28 | 22 | 190479 | 189820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 22 | 194148 | 189820 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-04-23 | QTR4 | 23/24 | 408 | 4811998.96
| 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 99.55% | 1 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | 89.01% | 1 | -16159 | 0 | 189 | 25 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07
| 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 99.64% | 1 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | 95.5% | 1 | -46640 | -1370 | 123 | 27 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21
| 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 99.46% | 1 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | 108.4% | 1 | -15706 | 258794 | 122 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38
| 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 94.62% | 1 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 98.41% | 1 | 69 | 0 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03
| 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 115% | 1 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | 102.4% | 1 | -3717 | 0 | 63 | 21 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19
| 04 | T4636 | 44384415201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 194 | 305 | 305 | 100% | 1 | 0 | 0 | 0 | 111 | 0 | 798900 | 41899 | 757001 | 798900 | 732677 | 0 | 0 | 0 | 732677 | 732677 | 96.79% | 1 | 0 | 0 | 86 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-06-28 | QTR4 | 23/24 | 412 | 879882.26
| 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 101.8% | 1 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | 106% | 1 | -4475 | 625462 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 |  | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33
| 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 103.5% | 1 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | 88% | 1 | -344 | 16863 | 37 | 25 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 |  | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99
| 04 | T4647 | 44699815201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 80 | 133 | 129 | 95% | 1 | 4 | 0 | 0 | 53 | 0 | 555556 | 31410 | 524146 | 555556 | 522780 | 0 | 0 | 0 | 522780 | 522780 | 99.74% | 1 | 0 | 0 | 47 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-10-30 | QTR2 | 24/25 | 412 | 659609.7
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 14 | 30 | 58 | 5847 | 8247 | 8223 | 100% | 14 | 24 | 0 | 0 | 2156 | 276 | 136231474 | 1045333 | 135186142 | 139286391 | 137227612 | 0 | -75000 | -75000 | 137152612 | 138030387 | 100% | 14 | 1225902 | 3270366 | 1527 | 514 | 1 | 75 | 2002508 | 600658 | 94 | 48 | 1182842 | 306688 | 0 | 0 | 2420 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 397249 | 0 | 0 | 71 | 59420 | 1041 | 0 | 0 | 0 | 0 | 116 | 0 | 281210 | 0 | 0 | 40 | 183969 | 79113 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 244 | 3171550 | 1222826
| 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 99.71% | 1 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 103.9% | 1 | 5349446 | 3618986 | 181 | 112 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 04 | E4V48 | 44346115201 | 2022-05-06 | QTR4 | 21/22 | 2 | 0 | 719 | 771 | 539 | 67.73% | 1 | 232 | 0 | 0 | 52 | 0 | 6383851 | 97993 | 6285858 | 6383851 | 5949070 | 0 | 0 | 0 | 5949070 | 5949070 | 94.64% | 1 | 0 | 0 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 412 | 10090648.24
| 04 | E4V50 | 43975915201 | 2022-09-02 | QTR1 | 22/23 | 1 | 2 | 246 | 338 | 338 | 111.4% | 1 | 0 | 0 | 0 | 92 | 0 | 2437437 | 50000 | 2387437 | 2522997 | 2472614 | 0 | 0 | 0 | 2472614 | 2469346 | 103.4% | 1 | -3268 | 85560 | 39 | 25 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-06-28 | QTR4 | 23/24 | 409 | 2462556.03
| 04 | E4V97 | 44175915201 | 2022-11-04 | QTR2 | 22/23 | 1 | 0 | 128 | 325 | 323 | 116.4% | 1 | 2 | 0 | 0 | 197 | 0 | 3019043 | 50000 | 2969043 | 3019043 | 2884719 | 0 | 0 | 0 | 2884719 | 2884627 | 97.16% | 1 | -92 | 0 | 151 | 23 | 0 | 0 | 0 | 0 | 23 | 0 | 18308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 18308 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-11-08 | QTR2 | 24/25 |  | 2024-08-02 | QTR1 | 24/25 | 412 | 2305583.22
| 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 106.3% | 1 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | 98.31% | 1 | -11187 | 50772 | 14 | 24 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12
| 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 113.8% | 1 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | 107.4% | 1 | -2567 | 41751 | 27 | 16 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 |  | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49
| 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | 118.6% | 1 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | 87.58% | 1 | -43330 | 0 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65
| 04 | E4W49 | 44637115201 | 2023-07-07 | QTR1 | 23/24 | 1 | 1 | 244 | 257 | 198 | 75.82% | 1 | 59 | 0 | 0 | 13 | 0 | 4434511 | 55240 | 4379271 | 4502024 | 4183947 | 0 | 0 | 0 | 4183947 | 4189012 | 95.66% | 1 | 5065 | 67513 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 412 | 5579255.71
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 35 | 3334 | 4162 | 3878 | 100% | 8 | 284 | 30 | 0 | 828 | 0 | 170952172 | 553233 | 170398939 | 174775003 | 174748202 | -50970 | 1375000 | 1324030 | 176072232 | 175595715 | 100% | 8 | 5294067 | 3864582 | 470 | 249 | 0 | 0 | 2059152 | 209090 | 51 | 0 | 892278 | 53057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 168663 | 323185 | 0 | 0 | 0 | 0 | 154 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 247 | 0 | 3894783 | 659941
| District 04 Totals |  |  |  |  | 22 | 43 | 93 | 9181 | 12409 | 12101 | 100% | 22 | 308 | 30 | 0 | 2984 | 276 | 307183646 | 1598566 | 305585081 | 314061394 | 311975814 | -50970 | 1300000 | 1249030 | 313224844 | 313626102 | 100% | 22 | 6519969 | 7134948 | 1997 | 763 | 1 | 75 | 4061660 | 809748 | 145 | 48 | 2075120 | 359745 | 0 | 0 | 2420 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 37 | 10 | 1085747 | 33779 | 0 | 71 | 228083 | 324226 | 0 | 0 | 0 | 0 | 270 | 0 | 375468 | 0 | 0 | 40 | 183969 | 79113 | 25 | 0 | 276156 | 276156 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 478 | 244 | 7066333 | 1882767
| 05 | T5721 | 44287515201 | 2021-12-08 | QTR2 | 21/22 | 3 | 7 | 510 | 817 | 805 | 107.5% | 1 | 12 | 0 | 0 | 257 | 50 | 16561765 | 150000 | 16411765 | 17284645 | 18223735 | 0 | 0 | 0 | 18223735 | 18689669 | 113.9% | 0 | 472880 | 722880 | 198 | 59 | 0 | 30 | 59072 | 0 | 0 | 0 | 671912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455 | 0 | 0 | 0 | 4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 743980 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-27 | QTR1 | 24/25 | 515 | 18568888.72
| 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 136.5% | 0 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | 101.3% | 1 | -57178 | 154746 | 45 | 50 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34
| 05 | T5728 | 44395815201 | 2021-08-25 | QTR1 | 21/22 | 6 | 5 | 600 | 848 | 847 | 99.83% | 1 | 1 | 0 | 0 | 248 | 0 | 34500000 | 150000 | 34350000 | 35703756 | 38083377 | -5932 | -11806 | -17738 | 38065638 | 39383079 | 114.7% | 0 | 1397410 | 1203756 | 187 | 61 | 0 | 0 | 557100 | 0 | 0 | 0 | 507869 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207739 | 292167 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 |  | 2024-03-15 | QTR3 | 23/24 | 509 | 32771897.49
| 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 108.3% | 1 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | 104.9% | 1 | -94902 | 39287 | 76 | 80 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3
| 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 155.3% | 0 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | 108.8% | 1 | -1791 | 104943 | 39 | 114 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8
| 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | 100.7% | 1 | -1484 | 793 | 94 | 10 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4
| 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 98.24% | 1 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | 104.6% | 1 | -515 | 40000 | 128 | 27 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1
| 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 92.67% | 1 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | 101% | 1 | -18 | 2618 | 7 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306
| 05 | T5772 | 44569315201 | 2022-10-26 | QTR2 | 22/23 | 2 | 4 | 260 | 406 | 403 | 98.85% | 1 | 3 | 0 | 0 | 146 | 0 | 1859536 | 50000 | 1809536 | 1934513 | 2110697 | 0 | 0 | 0 | 2110697 | 2104981 | 116.3% | 0 | -360 | 74977 | 110 | 36 | 0 | 0 | 2993 | 0 | 0 | 0 | 30505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33497 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-06-18 | QTR4 | 23/24 | 509 | 1660927.9
| 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 98% | 1 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | 106.3% | 1 | -22 | 0 | 26 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25
| 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 103.9% | 1 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | 93.31% | 1 | -1198 | 1419 | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 |  | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55
| 05 | T5783 | 44576715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 230 | 286 | 283 | 98.7% | 1 | 3 | 0 | 0 | 56 | 0 | 2041154 | 50000 | 1991154 | 2041154 | 2088238 | -10982 | 0 | -10982 | 2077256 | 2076683 | 104.3% | 1 | -573 | 0 | 37 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-07-31 | QTR1 | 24/25 | 509 | 1415550.25
| 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 99.29% | 1 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 101.9% | 1 | 0 | -21976 | 9 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 |  | 2024-07-01 | QTR1 | 24/25 | 515 | 919900
| 05 | T5820 | 45222925201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 120 | 133 | 85 | 60% | 1 | 48 | 0 | 0 | 13 | 0 | 607569 | 43750 | 563819 | 607569 | 467724 | 0 | 0 | 0 | 467724 | 467724 | 82.96% | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-06-06 | QTR4 | 23/24 | 513 | 1006632.6
| 05 | T5821 | 45222935201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 110 | 115 | 108 | 93.64% | 1 | 7 | 0 | 0 | 5 | 0 | 843345 | 50000 | 793345 | 843345 | 748398 | 0 | 0 | 0 | 748398 | 748398 | 94.33% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-11 | QTR2 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 512 | 1601075
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 15 | 31 | 31 | 3820 | 5747 | 5635 | 86.67% | 13 | 112 | 0 | 0 | 1635 | 292 | 82882748 | 947750 | 81934998 | 85206192 | 88779387 | -16914 | -11806 | -28720 | 88750666 | 90361953 | 80% | 12 | 1712249 | 2323443 | 967 | 639 | 0 | 30 | 772653 | 0 | 0 | 198 | 1375301 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 65686 | 0 | 0 | 0 | 30107 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 133115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 230 | 2354887 | 292167
| 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 94.32% | 1 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 99.36% | 1 | 0 | 7099 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 |  | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844
| 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 60.8% | 1 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 100% | 1 | 0 | 0 | 24 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-11 | QTR4 | 23/24 | 507 | 801387
| 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 101.1% | 1 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | 103.3% | 1 | -144 | 0 | 29 | 48 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35
| 05 | E57B9 | 44709915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 260 | 337 | 337 | 100% | 1 | 0 | 0 | 0 | 77 | 0 | 7890001 | 88000 | 7802001 | 7890001 | 8013155 | 0 | 0 | 0 | 8013155 | 8041936 | 103.1% | 1 | 28780 | 0 | 52 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 514 | 9077031.16
| 05 | E58B0 | 44878915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 2 | 170 | 213 | 213 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 2634873 | 50000 | 2584873 | 2681332 | 2729605 | 0 | 0 | 0 | 2729605 | 2729605 | 105.6% | 1 | 0 | 46460 | 31 | 12 | 0 | 0 | 7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7002 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 509 | 1708500.26
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 5 | 6 | 4 | 1105 | 1444 | 1374 | 100% | 5 | 70 | 0 | 0 | 337 | 2 | 15439496 | 276161 | 15163335 | 15493054 | 15574165 | 0 | 0 | 0 | 15574165 | 15595703 | 100% | 5 | 28636 | 53559 | 179 | 158 | 0 | 0 | 7002 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18928 | 0
| District 05 Totals |  |  |  |  | 20 | 37 | 35 | 4925 | 7191 | 7009 | 90% | 18 | 182 | 0 | 0 | 1972 | 294 | 98322244 | 1223911 | 97098333 | 100699246 | 104353552 | -16914 | -11806 | -28720 | 104324831 | 105957656 | 85% | 17 | 1740885 | 2377002 | 1146 | 797 | 0 | 30 | 779655 | 0 | 0 | 200 | 1387227 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 65686 | 0 | 0 | 0 | 30107 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 133115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 232 | 2373815 | 292167
| 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 73.4% | 1 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | 105.2% | 1 | -286983 | 148832 | 48 | 29 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6494 | 42752125201 | 2022-01-26 | QTR3 | 21/22 | 6 | 2 | 320 | 394 | 339 | 82.81% | 1 | 55 | 0 | 0 | 74 | 0 | 4221888 | 50000 | 4171888 | 4224163 | 3676222 | 0 | 200000 | 200000 | 3876222 | 3699956 | 88.69% | 1 | -176266 | 2275 | 60 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2023-12-13 | QTR2 | 23/24 | 613 | 4370412.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6504 | 42918525201 | 2021-05-26 | QTR4 | 20/21 | 1 | 2 | 450 | 541 | 512 | 93.56% | 1 | 29 | 0 | 0 | 91 | 0 | 5189595 | 57167 | 5132429 | 5303929 | 5374583 | 0 | 0 | 0 | 5374583 | 5469555 | 106.6% | 1 | 94972 | 114333 | 55 | 36 | 0 | 0 | 152939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157299 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-03-21 | QTR3 | 23/24 | 613 | 5707742.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 119% | 1 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 106.7% | 1 | 488935 | 455645 | 61 | 44 | 0 | 0 | 55800 | 0 | 0 | 95 | 262248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 564979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 |  | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6538 | 44391915201 | 2022-05-25 | QTR4 | 21/22 | 9 | 1 | 480 | 531 | 458 | 84.79% | 1 | 73 | 0 | 0 | 51 | 0 | 13790706 | 121591 | 13669115 | 13840706 | 13459785 | 0 | 480000 | 480000 | 13939785 | 13298540 | 97.29% | 1 | -641245 | 50000 | 32 | 19 | 0 | 0 | 29647 | 0 | 0 | 0 | 16702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22076 | 0 | 0 | 0 | 6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74679 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-10-02 | QTR2 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 636 | 12736630.45 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 78.93% | 1 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | 97.57% | 1 | -232397 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6559 | 43094925201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 450 | 619 | 619 | 107.1% | 1 | 0 | 0 | 0 | 169 | 0 | 8056848 | 70725 | 7986123 | 8075952 | 7918898 | 0 | 0 | 0 | 7918898 | 7945544 | 99.49% | 1 | 26646 | 19104 | 96 | 41 | 0 | 0 | 39629 | 0 | 0 | 0 | 16524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 56152 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 613 | 7161375.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | 101.6% | 1 | -4559 | 0 | 16 | 22 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037
| 06 | T6572 | 44390615201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 240 | 291 | 282 | 96.25% | 1 | 9 | 0 | 0 | 51 | 0 | 2360100 | 50000 | 2310100 | 2360100 | 2343530 | 0 | 0 | 0 | 2343530 | 2341786 | 101.4% | 1 | -1744 | 0 | 34 | 17 | 0 | 0 | 931 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 |  | 2024-09-03 | QTR1 | 24/25 | 613 | 2712981.65
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 9 | 27 | 15 | 3400 | 4186 | 3828 | 100% | 9 | 358 | 0 | 0 | 691 | 95 | 61485961 | 652181 | 60833781 | 62276150 | 61285135 | 0 | 1220000 | 1220000 | 62505135 | 61641849 | 100% | 9 | -732641 | 790189 | 417 | 242 | 0 | 0 | 388953 | 0 | 0 | 95 | 359442 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129276 | 0 | 32 | 0 | 11412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 95 | 1084069 | 213129
| 06 | E6M58 | 44492015201 | 2021-05-11 | QTR4 | 20/21 | 1 | 3 | 680 | 1057 | 1057 | 112.9% | 1 | 0 | 0 | 0 | 377 | 0 | 5167117 | 50000 | 5117117 | 5569451 | 5567027 | 0 | 0 | 0 | 5567027 | 5567027 | 108.8% | 1 | 0 | 402334 | 188 | 101 | 10 | 0 | 11007 | 0 | 0 | 0 | 120107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 449910 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-06-03 | QTR4 | 23/24 | 636 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 124.6% | 0 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -1.824% | 1 | -6838357 | -65427 | 60 | 80 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD
| 06 | E6M99 | 44694715201 | 2022-04-11 | QTR4 | 21/22 | 1 | 2 | 500 | 782 | 782 | 109% | 1 | 0 | 0 | 0 | 282 | 0 | 2597679 | 50000 | 2547679 | 2701239 | 2676164 | 0 | 0 | 0 | 2676164 | 2676164 | 105% | 1 | 0 | 103560 | 151 | 86 | 0 | 0 | -12464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 116024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 103560 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2024-10-31 | QTR2 | 24/25 |  | 2024-08-02 | QTR1 | 24/25 | 636 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | 87.5% | 1 | -21 | 0 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5
| 06 | E6O72 | 43029179201 | 2023-06-12 | QTR4 | 22/23 | 2 | 4 | 330 | 352 | 324 | 91.52% | 1 | 28 | 0 | 0 | 22 | 0 | 1937336 | 0 | 1937336 | 1987336 | 1966014 | 0 | 0 | 0 | 1966014 | 0 | 0% | 1 | -1966014 | 50000 | 0 | 22 | 0 | 0 | 13249 | 0 | 0 | 0 | 6779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28678 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-08-09 | QTR1 | 24/25 | 636 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 5 | 7 | 11 | 2390 | 3418 | 3386 | 80% | 4 | 32 | 0 | 0 | 1028 | 0 | 17568829 | 234395 | 17334434 | 18059296 | 17794829 | 0 | 0 | 0 | 17794829 | 8864946 | 100% | 5 | -8804392 | 490467 | 419 | 295 | 10 | 0 | -60024 | 0 | 0 | 0 | 126886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | 457273 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 0 | 542214 | 0
| District 06 Totals |  |  |  |  | 14 | 34 | 26 | 5790 | 7604 | 7214 | 92.86% | 13 | 390 | 0 | 0 | 1719 | 95 | 79054790 | 886576 | 78168215 | 80335446 | 79079964 | 0 | 1220000 | 1220000 | 80299964 | 70506795 | 100% | 14 | -9537033 | 1280656 | 836 | 537 | 10 | 0 | 328929 | 0 | 0 | 95 | 486328 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | 586549 | 0 | 32 | 0 | 29490 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 95 | 1626283 | 213129
| 07 | T7438 | 25632425201 | 2020-11-18 | QTR2 | 20/21 | 2 | 11 | 700 | 961 | 953 | 105% | 1 | 8 | 0 | 0 | 218 | 43 | 16728833 | 239863 | 16488970 | 18036076 | 18037280 | 0 | 0 | 0 | 18037280 | 18987569 | 115.2% | 0 | 1096394 | 1307244 | 167 | 51 | 0 | 39 | 487932 | 0 | 0 | 4 | 893855 | 7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88439 | 16356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1473608 | 23952 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-11-15 | QTR2 | 24/25 |  | 2023-10-19 | QTR2 | 23/24 | 714 | 19921100
| 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 99.8% | 1 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 106.3% | 1 | 117308 | 206565 | 66 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900
| 07 | T7481 | 44073315201 | 2022-08-31 | QTR1 | 22/23 | 3 | 0 | 225 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 3304021 | 50000 | 3254021 | 3304021 | 3182990 | 0 | 0 | 0 | 3182990 | 3174072 | 97.54% | 1 | -8918 | 0 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-12 | QTR2 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 796 | 3303500
| 07 | T7492 | 44024815201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 210 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 5438332 | 52000 | 5386332 | 5435828 | 5441055 | 0 | 0 | 0 | 5441055 | 5414623 | 100.5% | 1 | -26432 | -2504 | 24 | 16 | 0 | 0 | -2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2504 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 799 | 5496384.15
| 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 98.1% | 1 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | 101.9% | 1 | -2665 | 0 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300
| 07 | T7518 | 45248755201 | 2023-12-06 | QTR2 | 23/24 | 5 | 0 | 140 | 153 | 142 | 92.14% | 1 | 11 | 0 | 0 | 13 | 0 | 908274 | 50000 | 858274 | 908274 | 908491 | 0 | 0 | 0 | 908491 | 908491 | 105.9% | 1 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 |  | 2024-09-16 | QTR1 | 24/25 | 798 | 1515975
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 6 | 15 | 16 | 1985 | 2529 | 2505 | 100% | 6 | 24 | 0 | 0 | 494 | 50 | 35317362 | 491863 | 34825499 | 36828666 | 36662951 | 0 | 0 | 0 | 36662951 | 37686825 | 83.33% | 5 | 1175687 | 1511305 | 333 | 168 | 0 | 39 | 485428 | 0 | 0 | 4 | 1032465 | 70865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 88439 | 16356 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1630221 | 87222
| 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | 335.8% | 0 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 91.04% | 1 | 0 | 207487 | 178 | 55 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300
| 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 107.8% | 1 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | 109.5% | 1 | -27960 | 0 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62
| 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 100% | 1 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | 101.4% | 1 | -125432 | 324762 | 127 | 22 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900
| 07 | E7P35 | 44165715201 | 2022-05-11 | QTR4 | 21/22 | 2 | 3 | 400 | 458 | 458 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 8986578 | 71000 | 8915578 | 9084687 | 9016111 | 0 | 0 | 0 | 9016111 | 8840279 | 99.16% | 1 | -171882 | 98110 | 30 | 28 | 0 | 0 | 115777 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-04-18 | QTR4 | 23/24 | 799 | 8393400
| 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | 105.7% | 1 | -342 | 101105 | 19 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400
| 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 98% | 1 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 108.7% | 1 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700
| 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 85.71% | 1 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 106.1% | 1 | 2811 | 30000 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300
| 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 86.4% | 1 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 107.5% | 1 | 565 | 4646 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 |  | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200
| 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 116.9% | 1 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | 105.4% | 1 | -31871 | 3477169 | 524 | 88 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 9 | 13 | 39 | 2555 | 4337 | 4445 | 88.89% | 8 | -108 | 152 | 0 | 1670 | 112 | 90403008 | 587000 | 89816008 | 94646285 | 94750116 | -570912 | 0 | -570912 | 94179204 | 93271097 | 100% | 9 | -353409 | 4243278 | 926 | 276 | 144 | 0 | 2772986 | 1778987 | 0 | 54 | 1062733 | 334177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153935 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 58 | 392852 | 71647 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 418 | 112 | 4254579 | 2272972
| District 07 Totals |  |  |  |  | 15 | 28 | 55 | 4540 | 6866 | 6950 | 93.33% | 14 | -84 | 152 | 0 | 2164 | 162 | 125720370 | 1078863 | 124641507 | 131474951 | 131413067 | -570912 | 0 | -570912 | 130842155 | 130957922 | 93.33% | 14 | 822278 | 5754583 | 1259 | 444 | 144 | 39 | 3258414 | 1778987 | 0 | 58 | 2095198 | 405042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171738 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 65 | 481291 | 88003 | 0 | 0 | 0 | 0 | 22 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 418 | 162 | 5884800 | 2360194
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R80 | 43554315201 | 2019-06-11 | QTR4 | 18/19 | 1 | 9 | 1810 | 1897 | 1601 | 78.4% | 1 | 296 | 0 | 0 | 182 | -95 | 244979349 | 150000 | 244829349 | 251466172 | 255108575 | 0 | 4375439 | 4375439 | 259484014 | 258158459 | 105.4% | 1 | 4868615 | 6486824 | 78 | 104 | 0 | 0 | 311893 | 0 | 0 | 0 | 9734282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5045376 | 0 | 0 | 0 | 1661009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -95 | -168828 | 0 | 0 | -95 | 6556771 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 |  | 2024-02-29 | QTR3 | 23/24 | 854 | 217827999.45 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8S90 | 43945755201 | 2021-04-20 | QTR4 | 20/21 | 5 | 13 | 533 | 998 | 998 | 113.5% | 1 | 0 | 0 | 0 | 465 | 0 | 21999573 | 150000 | 21849573 | 23015619 | 24155114 | 0 | 0 | 0 | 24155114 | 24813029 | 113.6% | 0 | 1013008 | 1016046 | 287 | 106 | 56 | 0 | 446658 | 0 | 0 | 0 | 537731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 32966 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 125872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 1143227 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 854 | 23025803.13
| 08 | E8T67 | 44262415201 | 2022-04-12 | QTR4 | 21/22 | 2 | 5 | 322 | 521 | 518 | 99.07% | 1 | 3 | 0 | 0 | 199 | 0 | 12517000 | 119797 | 12397203 | 12877010 | 12203064 | 0 | 0 | 0 | 12203064 | 12123596 | 97.79% | 1 | -79468 | 360010 | 133 | 66 | 0 | 0 | 108673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796 | 0 | 0 | 0 | 257897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369366 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 854 | 13936524.01
| 08 | E8T77 | 44925315201 | 2022-05-17 | QTR4 | 21/22 | 2 | 4 | 440 | 677 | 666 | 111.6% | 1 | 11 | 0 | 0 | 237 | 0 | 5565378 | 50000 | 5515378 | 5757378 | 5730235 | 0 | 0 | 0 | 5730235 | 5763102 | 104.5% | 1 | 32867 | 192000 | 120 | 55 | 0 | 0 | 30727 | 0 | 0 | 0 | 77369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 108096 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-14 | QTR2 | 24/25 |  | 2024-09-11 | QTR1 | 24/25 | 854 | 5213379.79
| 08 | E8T82 | 42897215201 | 2022-09-13 | QTR1 | 22/23 | 2 | 2 | 568 | 619 | 464 | 72.71% | 1 | 155 | 0 | 0 | 51 | 0 | 2504148 | 58519 | 2445628 | 2711373 | 2646645 | 0 | 0 | 0 | 2646645 | 2639419 | 107.9% | 1 | 0 | 207226 | 9 | 42 | 0 | 0 | 227557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7226 | 0 | 0 | 0 | 234782 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-07-11 | QTR1 | 24/25 | 854 | 4806556.91
| 08 | E8T94 | 43578625201 | 2022-10-25 | QTR2 | 22/23 | 1 | 1 | 165 | 221 | 221 | 109.1% | 1 | 0 | 0 | 0 | 41 | 15 | 2596848 | 50000 | 2546848 | 2612139 | 2505813 | 0 | 0 | 0 | 2505813 | 2503780 | 98.31% | 1 | -2033 | 15291 | 18 | 23 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-05-17 | QTR4 | 23/24 | 854 | 2699146.4
| 08 | E8T95 | 44171915201 | 2022-10-25 | QTR2 | 22/23 | 3 | 3 | 508 | 651 | 615 | 92.91% | 1 | 36 | 0 | 0 | 143 | 0 | 21849074 | 150000 | 21699074 | 22014286 | 22325271 | 0 | 0 | 0 | 22325271 | 22079112 | 101.8% | 1 | -230948 | 165212 | 97 | 46 | 0 | 0 | 189344 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201 | 0 | 0 | 0 | 11368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225106 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 |  | 2024-10-17 | QTR2 | 24/25 | 854 | 21254879.86
| 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 38.1% | 1 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 98.62% | 1 | 0 | 25000 | 4 | 15 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 8 | 18 | 38 | 4703 | 5960 | 5238 | 0% | 8 | 722 | 0 | 0 | 1337 | -80 | 313145042 | 778316 | 312366725 | 321612649 | 325743385 | 0 | 4375439 | 4375439 | 330118824 | 329149165 | 87.5% | 7 | 5602041 | 8467609 | 746 | 457 | 56 | 0 | 1318077 | 0 | 0 | 15 | 10366653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4999204 | 0 | 16 | 0 | 1963240 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 204876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | -95 | -161602 | 0 | 279 | -80 | 8692039 | 0
| District 08 Totals |  |  |  |  | 8 | 18 | 38 | 4703 | 5960 | 5238 | 100% | 8 | 722 | 0 | 0 | 1337 | -80 | 313145042 | 778316 | 312366725 | 321612649 | 325743385 | 0 | 4375439 | 4375439 | 330118824 | 329149165 | 87.5% | 7 | 5602041 | 8467609 | 746 | 457 | 56 | 0 | 1318077 | 0 | 0 | 15 | 10366653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4999204 | 0 | 16 | 0 | 1963240 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 204876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | -95 | -161602 | 0 | 279 | -80 | 8692039 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 93 | 170 | 195 | 25299 | 39497 | 38832 | 86.02% | 80 | 665 | 74 | 0 | 12085 | 2165 | 571974753 | 6145012 | 565829742 | 581978774 | 588606001 | -425356 | 1133194 | 707838 | 589313838 | 592743727 | 93.55% | 87 | 4228217 | 10219470 | 8276 | 3485 | 309 | 304 | 4783864 | 610212 | 512 | 908 | 5535482 | 959030 | 0 | 0 | 2420 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 0 | 0 | 47 | 59 | 778006 | 5020 | 32 | 75 | 146018 | 12870 | 0 | 0 | 0 | 0 | 1322 | 645 | 789586 | 16356 | 0 | 40 | 183969 | 79113 | 0 | 60 | 380599 | 601673 | 120 | 0 | 0 | 0 | 0 | -25 | -118879 | 0 | 2342 | 2066 | 11285695 | 2284276
| Statewide District Let Contracts SubTotal |  |  |  |  | 51 | 82 | 179 | 19204 | 27274 | 26200 | 88.24% | 45 | 1074 | 182 | 0 | 7374 | 696 | 721618364 | 3531495 | 718086869 | 746150582 | 750681623 | -551882 | 5751239 | 5199357 | 755880980 | 744874308 | 94.12% | 48 | 3206898 | 24573973 | 3984 | 2082 | 210 | 282 | 8668983 | 3758222 | 249 | 309 | 16919350 | 559205 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 71 | -3438817 | 121938 | 31 | 0 | 2168219 | 324413 | 0 | 0 | 0 | 0 | 635 | 116 | 869342 | 85050 | 0 | 0 | 0 | 0 | 135 | 13 | 258951 | 258951 | 62 | 0 | 0 | 0 | 0 | -95 | -338426 | 0 | 1585 | 696 | 25141978 | 5107781
| Statewide Totals |  |  |  |  | 144 | 252 | 374 | 44503 | 66771 | 65032 | 86.81% | 125 | 1739 | 256 | 0 | 19459 | 2861 | 1293593117 | 9676507 | 1283916611 | 1328129356 | 1339287624 | -977238 | 6884433 | 5907195 | 1345194818 | 1337618035 | 93.75% | 135 | 7435115 | 34793443 | 12260 | 5567 | 519 | 586 | 13452847 | 4368434 | 761 | 1217 | 22454832 | 1518235 | 0 | 0 | 36792 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 0 | 0 | 310 | 130 | -2660811 | 126958 | 63 | 75 | 2314237 | 337283 | 0 | 0 | 0 | 0 | 1957 | 761 | 1658928 | 101406 | 0 | 40 | 183969 | 79113 | 135 | 73 | 639550 | 860624 | 182 | 0 | 0 | 0 | 0 | -120 | -457305 | 0 | 3927 | 2762 | 36427673 | 7392057

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1U15 | 44448515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-01-13 | 9191000 | 9286906 | 8593729 | 95906.42 | 0 | 8866277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593729 | 8866277 | 272547 | 9151070
1 | E1U97 | 44789615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 3990000 | 4021977 | 3979990 | 31977.22 | 0 | 3978102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 1965526 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1V15 | 44547115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-19 | 7937275 | 7937275 | 7998691 | 0 | 0 | 7941859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7998691 | 7941859 | -56832 | 8527987
1 | E1W10 | 44744115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | 5126611 | 5135303 | 4999771 | 8691.75 | 0 | 4990201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4999771 | 4990201 | -9570 | 5933693
1 | E1W15 | 44464315201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-08-17 | 572414 | 613908 | 573719 | 41493.75 | 0 | 573719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573719 | 573719 | 0 | 767485
1 | E1W19 | 44743315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2023-10-19 | 3927820 | 3927820 | 3916235 | 0 | 0 | 3896792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3916235 | 3896792 | -19443 | 3787595
1 | E1W20 | 44620215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-19 | 2630586 | 2630586 | 2573059 | 0 | 0 | 2559128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573059 | 2559128 | -13930 | 2937558
1 | T1825 | 43982715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-25 | 8278071 | 8939807 | 8867401 | 661736.23 | 0 | 8953757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8867401 | 8953757 | 86356 | 7852555
1 | T1846 | 44156115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-25 | 3477042 | 3477042 | 3332356 | 0 | 0 | 3322154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332356 | 3322154 | -10202 | 3367086
1 | T1847 | 43805715201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-10-26 | 1159034 | 1218049 | 1206007 | 59015.14 | 0 | 1205156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 1023962
1 | T1860 | 43709615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 4325722 | 4504283 | 4508752 | 178560.93 | 0 | 4497707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4508752 | 4497707 | -11045 | 2709383
1 | T1871 | 45224115201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2023-09-27 | 3701415 | 3701415 | 3225904 | 0 | 0 | 3227402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225904 | 3227402 | 1498 | 4091496
2 | E200K | 43737515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-05-10 | 596179 | 596809 | 579939 | 630 | 0 | 579939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579939 | 579939 | 0 | 642935
2 | E20G1 | 43451415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-17 | 8137606 | 11055579 | 11421194 | 2917973.3 | 0 | 11421194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11421194 | 11421194 | 0 | 9316377
2 | E2Z23 | 43655815201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-15 | 23611420 | 27138289 | 28700280 | 3526869.4 | 0 | 28809279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28700280 | 28809279 | 108999 | 23815761
2 | T2804 | 44137215201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 7398298 | 7431649 | 7748601 | 33350.85 | 0 | 7995687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7748601 | 7995687 | 247086 | 6176554
2 | T2820 | 43231615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 6513333 | 6536983 | 6298184 | 23649.6 | -45432 | 6786189 | -45432 | 0 | 0 | 0 | 0 | 0 | -45432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45432 | 6252752 | 6786189 | 533437 | 8131499
2 | T2828 | 44105015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-12-08 | 2858409 | 2966328 | 3044806 | 107919.26 | 0 | 3046950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3044806 | 3046950 | 2144 | 3146529
2 | T2834 | 44326115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 9753946 | 9932433 | 10044314 | 178487.31 | 0 | 10184626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10044314 | 10184626 | 140312 | 11499594
2 | T2838 | 44342015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 11945708 | 12005007 | 12120635 | 59299.78 | 0 | 12074024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12120635 | 12074024 | -46610 | 12401358
2 | T2853 | 44714915201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 17135161 | 17359701 | 17949301 | 224540.06 | 0 | 17752973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17949301 | 17752973 | -196328 | 22151003
2 | T2864 | 20765825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 2568964 | 2668964 | 2632044 | 100000 | 0 | 2632301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2632044 | 2632301 | 257 | 2408715
2 | T2896 | 44284815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 3802716 | 3802716 | 3666172 | 0 | 0 | 3666172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 4117339
2 | T2897 | 44554615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 7947765 | 7947765 | 8246084 | 0 | 0 | 8193910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 11037253
2 | T2900 | 40392045201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-06-15 | 869247 | 869247 | 857258 | 0 | 0 | 857258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857258 | 857258 | 0 | 1017097
2 | T2909 | 44607915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-02-22 | 7130409 | 7130409 | 7454415 | 0 | 0 | 7520621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7454415 | 7520621 | 66206 | 7319756
2 | T2911 | 44703315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 5899711 | 5916585 | 5921537 | 16874 | 0 | 5926778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5921537 | 5926778 | 5241 | 6079798
2 | T2922 | 44717615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 4768192 | 4768192 | 4978398 | 0 | 0 | 4983434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4978398 | 4983434 | 5036 | 5253039
2 | T2926 | 44703715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 12488206 | 12488206 | 12735786 | 0 | 0 | 12755313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 12922548
2 | T2927 | 44762935201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 737944 | 737944 | 698279 | 0 | 0 | 698279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698279 | 698279 | 0 | 752837
2 | T2931 | 44722615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 595321 | 595321 | 526968 | 0 | 0 | 526968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526968 | 526968 | 0 | 725236
2 | T2935 | 43917715201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 688840 | 688840 | 661650 | 0 | 0 | 661650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661650 | 661650 | 0 | 865701
2 | T2957 | 44712915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 2432061 | 2483046 | 2440068 | 50985 | 0 | 2440833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2440068 | 2440833 | 766 | 2377451
2 | T2958 | 44615425201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-06-14 | 3795580 | 3795580 | 3741800 | 0 | 0 | 3742922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 3808947
2 | T2980 | 45220115201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-10-25 | 1193458 | 1193458 | 1138988 | 0 | 0 | 1138988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 2555282
3 | E3Q94 | 21787545201 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2018-06-14 | 31708584 | 32410332 | 32832992 | 701748.39 | 0 | 33087185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32832992 | 33087185 | 254193 | 25965926
3 | E3V87 | 44573415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-08 | 4255368 | 4255368 | 4147787 | 0 | 0 | 4133951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 4883807
3 | E3W17 | 44759015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-10 | 3130216 | 3130216 | 3176618 | 0 | 0 | 3169412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 4310828
3 | E3W27 | 43464515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-15 | 3980189 | 4006691 | 4118899 | 26502.21 | 0 | 4101914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 4847742
3 | E3W54 | 42359155201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-07-13 | 3139310 | 3241997 | 3289104 | 102686.83 | 70800 | 3289104 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 70800 | 3359904 | 3289104 | -70800 | 2935414 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3W88 | 44575515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | 2175239 | 2175239 | 2183626 | 0 | 0 | 2183626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183626 | 2183626 | 0 | 3085003
3 | T3719 | 43921415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-05-25 | 2161422 | 2219469 | 2278041 | 58046.15 | 0 | 2271197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 3319649
3 | T3730 | 43972515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 13201615 | 13201615 | 14101673 | 0 | 0 | 14032884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 14987298
3 | T3767 | 44188125201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 1798857 | 1800807 | 1823631 | 1950 | 0 | 1837783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1816518
3 | T3774 | 44115615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-10-26 | 2352518 | 2352518 | 2482697 | 0 | 0 | 2481516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 2793292
3 | T3791 | 43937615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-06-14 | 2097844 | 2104355 | 1977895 | 6511.18 | 0 | 1977939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977895 | 1977939 | 44 | 2307183
3 | T3792 | 44117115201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 1248264 | 1248264 | 1306248 | 0 | 0 | 1306346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306248 | 1306346 | 98 | 1870598
3 | T3803 | 44403915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7221201 | 7242100 | 7302859 | 20899.02 | 0 | 7410703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 6606379
3 | T3806 | 43973315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 10103368 | 10103368 | 10342165 | 0 | 0 | 10277452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10342165 | 10277452 | -64713 | 10842968
3 | T3813 | 44159315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 6499662 | 6674412 | 6885176 | 174749.85 | 0 | 6899511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6885176 | 6899511 | 14336 | 6445150
3 | T3814 | 43989215201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 2042361 | 2052823 | 2049639 | 10462.01 | 0 | 2051119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 1702970
3 | T3824 | 43769915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-04-26 | 3559704 | 3559704 | 3648796 | 0 | 0 | 3648367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3648796 | 3648367 | -429 | 5711547
3 | T3826 | 44387715201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 942554 | 942554 | 927016 | 0 | 0 | 927016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927016 | 927016 | 0 | 1043116
3 | T3829 | 44553915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 12211588 | 12181493 | 12519374 | -30095 | 0 | 12516178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12519374 | 12516178 | -3196 | 12606229
3 | T3832 | 44986815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 391274 | 391274 | 365673 | 0 | 0 | 365673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365673 | 365673 | 0 | 417471
3 | T3834 | 44563515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 19944475 | 19944475 | 21545566 | 0 | -363010 | 21410083 | -363010 | 0 | 0 | 0 | 0 | 0 | -363010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -363010 | 21182556 | 21410083 | 227527 | 18371047
3 | T3842 | 44404015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 851756 | 851756 | 802521 | 0 | 0 | 802521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802521 | 802521 | 0 | 869556
3 | T3847 | 44365025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 8306085 | 8382009 | 9159429 | 75924.28 | 0 | 9121506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 7884744
3 | T3856 | 44573315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 6737296 | 6737296 | 7134385 | 0 | 0 | 7124379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7134385 | 7124379 | -10006 | 7216078
3 | T3864 | 44562915201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-04-26 | 3480880 | 3589639 | 3810464 | 108758.99 | 0 | 3809861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810464 | 3809861 | -603 | 5160701
3 | T3877 | 43775715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 11695437 | 11701443 | 12402258 | 6006 | 0 | 12455669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12402258 | 12455669 | 53411 | 9851820
3 | T3880 | 43078925201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 3380216 | 3380216 | 3471279 | 0 | 0 | 3471279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3471279 | 3471279 | 0 | 5332275
3 | T3886 | 45221235201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1444661 | 1521683 | 1385235 | 77022.4 | 0 | 1385235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385235 | 1385235 | 0 | 2325344
3 | T3889 | 45221225201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-10-25 | 1570117 | 1689632 | 1597844 | 119514.99 | 0 | 1597844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1597844 | 1597844 | 0 | 1925285
3 | T3897 | 44845115201 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2023-12-06 | 1349500 | 1349500 | 1300591 | 0 | 0 | 1300571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300591 | 1300571 | -20 | 1617298
4 | E4T19 | 43310955201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-03-29 | 148094245 | 151713231 | 158402319 | 3618985.82 | 1375000 | 159445264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375000 | 0 | 0 | 0 | 0 | 0 | 1375000 | 1375000 | 159777319 | 159445264 | -332055 | 130080160 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
4 | E4V48 | 44346115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-05-06 | 6383851 | 6383851 | 5949070 | 0 | 0 | 5949070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5949070 | 5949070 | 0 | 10090648
4 | E4V50 | 43975915201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-02 | 2437437 | 2522997 | 2472614 | 85560.06 | 0 | 2472614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2472614 | 2472614 | 0 | 2462556
4 | E4V97 | 44175915201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2022-11-04 | 3019043 | 3019043 | 2884719 | 0 | 0 | 2884627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2884719 | 2884627 | -92 | 2305583
4 | E4W15 | 44611215201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-02-03 | 2771566 | 2822338 | 2686822 | 50771.57 | 0 | 2675635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 3211732
4 | E4W39 | 44412115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-02-03 | 2588046 | 2588046 | 2728223 | 0 | 0 | 2725656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 2290170
4 | E4W40 | 44609915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2023-03-03 | 1223473 | 1223473 | 1121989 | 0 | -50970 | 1027689 | -50970 | 0 | 0 | 0 | 0 | 0 | -50970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50970 | 1071019 | 1027689 | -43330 | 1203020
4 | E4W49 | 44637115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-07 | 4434511 | 4502024 | 4183947 | 67512.92 | 0 | 4189012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4183947 | 4189012 | 5065 | 5579256
4 | T4472 | 41934525201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 33359900 | 33746993 | 33295065 | 387092.98 | -75000 | 33641803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75000 | 0 | 0 | 0 | 0 | 0 | -75000 | -75000 | 33220065 | 33641803 | 421739 | 37475056 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4477 | 23025665201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 45221786 | 46013498 | 47012029 | 791712.01 | 0 | 47480610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47012029 | 47480610 | 468581 | 48103370 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4566 | 43976115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 4627786 | 4748358 | 4545695 | 120572.24 | 0 | 4643097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545695 | 4643097 | 97402 | 5224694
4 | T4585 | 43533715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 15518729 | 16395821 | 15822170 | 877092.1 | 0 | 15987859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 15323089 | A6 | ICC - BAM/INCENTIVE-DISINCENT
4 | T4598 | 44399615201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2022-02-23 | 5606708 | 5800857 | 5331108 | 194148.24 | 0 | 5379412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5331108 | 5379412 | 48304 | 4811999
4 | T4610 | 44426515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4142494 | 4142494 | 3658735 | 0 | 0 | 3642576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 4002406
4 | T4611 | 44158215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 7152130 | 7150760 | 6812663 | -1370 | 0 | 6766023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | 8132476
4 | T4612 | 42957645201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-04-27 | 6700410 | 6959205 | 7215672 | 258794.43 | 0 | 7199967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 6372835
4 | T4618 | 44384315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 1266009 | 1266009 | 1196561 | 0 | 0 | 1196630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 1146916
4 | T4634 | 44177015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1746923 | 1746923 | 1740697 | 0 | 0 | 1736981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 1767920
4 | T4636 | 44384415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 798900 | 798900 | 732677 | 0 | 0 | 732677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732677 | 732677 | 0 | 879882
4 | T4640 | 43771715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 6949432 | 7359443 | 7308401 | 410010.11 | 0 | 7303926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 6229901
4 | T4642 | 44610315201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 2584711 | 2601574 | 2230880 | 16862.56 | 0 | 2230536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 2408671
4 | T4647 | 44699815201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2023-09-27 | 555556 | 555556 | 522780 | 0 | 0 | 522780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522780 | 522780 | 0 | 659610
5 | E55A2 | 44539515201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2022-05-03 | 2300883 | 2307982 | 2243671 | 7099.26 | 0 | 2243671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243671 | 2243671 | 0 | 3525844
5 | E56B9 | 44892315201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2023-03-07 | 698401 | 698401 | 660240 | 0 | 0 | 660240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660240 | 660240 | 0 | 801387
5 | E57B0 | 44139515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-04-04 | 1915338 | 1915338 | 1927494 | 0 | 0 | 1927350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 1563670
5 | E57B9 | 44709915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-06-06 | 7890001 | 7890001 | 8013155 | 0 | 0 | 8041936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8013155 | 8041936 | 28780 | 9077031
5 | E58B0 | 44878915201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 2634873 | 2681332 | 2729605 | 46459.81 | 0 | 2729605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2729605 | 2729605 | 0 | 1708500
5 | T5721 | 44287515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 16561765 | 17284645 | 18223735 | 722880 | 0 | 18743456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18223735 | 18743456 | 519720 | 18568889
5 | T5725 | 44351215201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 4062453 | 4217199 | 4121213 | 154746.07 | 0 | 4064034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4121213 | 4064034 | -57178 | 5797838
5 | T5728 | 44395815201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 34500000 | 35703756 | 38083377 | 1203756.14 | -17738 | 39463048 | 0 | 0 | 0 | 0 | 0 | -5932 | -5932 | -11806 | 0 | 0 | 0 | 0 | 0 | -11806 | -17738 | 38065638 | 39463048 | 1397410 | 32771897
5 | T5729 | 43565715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 10638248 | 10677535 | 11115999 | 39287.05 | 0 | 11021098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 15691232
5 | T5740 | 43898215201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 2406406 | 2511349 | 2568507 | 104942.61 | 0 | 2566717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568507 | 2566717 | -1791 | 2297944
5 | T5755 | 44568715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 1071415 | 1072209 | 1061331 | 793.38 | 0 | 1059847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061331 | 1059847 | -1484 | 734929
5 | T5762 | 44351415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2950212 | 2990212 | 3032852 | 40000 | 0 | 3032337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 1861686
5 | T5769 | 44571515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-10-05 | 1830300 | 1832918 | 1800435 | 2618.11 | 0 | 1800417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800435 | 1800417 | -18 | 1120306
5 | T5772 | 44569315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 1859536 | 1934513 | 2110697 | 74976.99 | 0 | 2110337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2110697 | 2110337 | -360 | 1660928
5 | T5775 | 44570715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 937052 | 937052 | 953863 | 0 | 0 | 953841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953863 | 953841 | -22 | 869794
5 | T5776 | 44577115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 1821012 | 1822431 | 1669665 | 1418.98 | 0 | 1669182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669665 | 1669182 | -483 | 749626
5 | T5783 | 44576715201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 2041154 | 2041154 | 2088238 | 0 | -10982 | 2076683 | 0 | 0 | 0 | 0 | 0 | -10982 | -10982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10982 | 2077256 | 2076683 | -573 | 1415550
5 | T5790 | 44976415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 752281 | 730305 | 733353 | -21975.86 | 0 | 733353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733353 | 733353 | 0 | 919900
5 | T5820 | 45222925201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 607569 | 607569 | 467724 | 0 | 0 | 467724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467724 | 467724 | 0 | 1006633
5 | T5821 | 45222935201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 843345 | 843345 | 748398 | 0 | 0 | 748398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748398 | 748398 | 0 | 1601075
6 | E6M58 | 44492015201 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2021-05-11 | 5167117 | 5569451 | 5567027 | 402333.53 | 0 | 5567027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5567027 | 5567027 | 0 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6M98 | 43029159201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-24 | 6969697 | 6904270 | 6963848 | -65426.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6963848 | 0 | -6963848 | 9167407 | LBDB | LOW BID DESIGN BUILD
6 | E6M99 | 44694715201 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2022-04-11 | 2597679 | 2701239 | 2676164 | 103559.73 | 0 | 2676164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676164 | 2676164 | 0 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
6 | E6O30 | 44734515201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-04-27 | 897000 | 897000 | 747267 | 0 | 0 | 747246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747267 | 747246 | -21 | 902746
6 | E6O72 | 43029179201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2023-06-12 | 1937336 | 1987336 | 1966014 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1966014 | 0 | -1966014 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR
6 | T6461 | 43647915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 3700000 | 3848832 | 3802731 | 148832.12 | 320000 | 3835748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 4423635 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6494 | 42752125201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 4221888 | 4224163 | 3676222 | 2275 | 200000 | 3699956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3876222 | 3699956 | -176266 | 4370413 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6504 | 42918525201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-05-26 | 5189595 | 5303929 | 5374583 | 114333.32 | 0 | 5469555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5374583 | 5469555 | 94972 | 5707743 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6535 | 44389315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 18130831 | 18586475 | 18825792 | 455644.58 | 0 | 19314726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18825792 | 19314726 | 488935 | 17118737 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6538 | 44391915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 13790706 | 13840706 | 13459785 | 50000 | 480000 | 13298540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 480000 | 480000 | 13939785 | 13298540 | -641245 | 12736630 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6549 | 44390715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 4134866 | 4134866 | 3997859 | 0 | 220000 | 3985462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6559 | 43094925201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 8056848 | 8075952 | 7918898 | 19104 | 0 | 7953812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7918898 | 7953812 | 34913 | 7161376 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6570 | 44391015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1901127 | 1901127 | 1885735 | 0 | 0 | 1881176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 1978037
6 | T6572 | 44390615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-03-29 | 2360100 | 2360100 | 2343530 | 0 | 0 | 2341786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343530 | 2341786 | -1744 | 2712982
7 | E7N73 | 43955315201 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2021-02-10 | 6131310 | 6338797 | 6305080 | 207487.31 | -570912 | 5734168 | -570912 | 0 | 0 | 0 | 0 | 0 | -570912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -570912 | 5734168 | 5734168 | 0 | 6350300
7 | E7P19 | 44025415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-01-11 | 5191258 | 5191258 | 5651758 | 0 | 0 | 5623798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 5707114
7 | E7P32 | 44165215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-08 | 6091557 | 6416319 | 6316136 | 324761.8 | 0 | 6190704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6316136 | 6190704 | -125432 | 6992900
7 | E7P35 | 44165715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-05-11 | 8986578 | 9084687 | 9016111 | 98109.75 | 0 | 8844228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9016111 | 8844228 | -171882 | 8393400
7 | E7P81 | 44165615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-04-12 | 2391656 | 2492761 | 2474615 | 101104.64 | 0 | 2474272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 2000400
7 | E7Q20 | 44380615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1219976 | 1219975 | 1270757 | -0.94 | 0 | 1271460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | 1145700
7 | E7Q21 | 44602615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 2654159 | 2684159 | 2759623 | 30000 | 0 | 2762434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 2504300
7 | E7Q22 | 44165315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1489626 | 1494272 | 1546615 | 4645.84 | 0 | 1547180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 1595200
7 | E7R20 | 41075525201 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2018-05-15 | 56246888 | 59724057 | 59431792 | 3477169.13 | 0 | 59377550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59431792 | 59377550 | -54242 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | T7438 | 25632425201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 16728833 | 18036076 | 18122029 | 1307243.7 | 0 | 19133675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18122029 | 19133675 | 1011645 | 19921100
7 | T7449 | 43953215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 4459994 | 4666559 | 4582670 | 206564.97 | 0 | 4694270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4582670 | 4694270 | 111600 | 4598900
7 | T7481 | 44073315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 3304021 | 3304021 | 3182990 | 0 | 0 | 3174072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3182990 | 3174072 | -8918 | 3303500
7 | T7492 | 44024815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 5438332 | 5435828 | 5441055 | -2504.17 | 0 | 5414623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5441055 | 5414623 | -26432 | 5496384
7 | T7506 | 44549415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-03-29 | 4477908 | 4477908 | 4516174 | 0 | 0 | 4513509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 4643300
7 | T7518 | 45248755201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 908274 | 908274 | 908491 | 0 | 0 | 908491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908491 | 908491 | 0 | 1515975
8 | E8R80 | 43554315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-06-11 | 244979349 | 251466172 | 261302745 | 6486823.61 | 4375439 | 264352629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375439 | 0 | 0 | 0 | 0 | 0 | 4375439 | 4375439 | 265678184 | 264352629 | -1325555 | 217827999 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8S90 | 43945755201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-04-20 | 21999573 | 23015619 | 24415437 | 1016045.86 | 0 | 25168122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24415437 | 25168122 | 752685 | 23025803
8 | E8T67 | 44262415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-04-12 | 12517000 | 12877010 | 12203064 | 360009.96 | 0 | 12123596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12203064 | 12123596 | -79468 | 13936524
8 | E8T77 | 44925315201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-05-17 | 5565378 | 5757378 | 5730235 | 192000 | 0 | 5763102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5730235 | 5763102 | 32867 | 5213380
8 | E8T82 | 42897215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-13 | 2504148 | 2711373 | 2646645 | 207225.59 | 0 | 2646645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2646645 | 2646645 | 0 | 4806557
8 | E8T94 | 43578625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-25 | 2596848 | 2612139 | 2505813 | 15291.47 | 0 | 2503780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2505813 | 2503780 | -2033 | 2699146
8 | E8T95 | 44171915201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-10-25 | 21849074 | 22014286 | 22325271 | 165212 | 0 | 22094324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22325271 | 22094324 | -230948 | 21254880
8 | E8U47 | 43854915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-09-12 | 1133672 | 1158672 | 1068668 | 25000 | 0 | 1068668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 2868747

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1825 | 43982715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 11 | 350 | 671 | 668 | 3 | 0 | 0 | 147 | 174 | 8278071 | 77832 | 8200239 | 8939807 | 8867401 | 0 | 0 | 0 | 8867401 | 8929131 | 86356 | 661736 | 124 | 0 | 30 | 233423 | 0 | 0 | 62 | 279341 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24626 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 174 | 673447 | 398388 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-05-29 | QTR4 | 23/24 | 118 | 7852554.7 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO | 5 | 01co | 1 | 5
01CO | 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | -12039 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 7 | 01do | 6 | 12
01CO | 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 59015 | 83 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 20 | 02co | 13 | 32
01CO | 01 | T1860 | 43709615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 9 | 250 | 401 | 398 | 3 | 0 | 0 | 151 | 0 | 4325722 | 50000 | 4275722 | 4504283 | 4508752 | 0 | 0 | 0 | 4508752 | 4493121 | -11661 | 178561 | 124 | 0 | 0 | 28409 | 0 | 0 | 0 | 105237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5020 | 5020 | 0 | 0 | 23159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165795 | 5020 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-10-14 | QTR2 | 24/25 | 2024-05-22 | QTR4 | 23/24 | 113 | 2709382.82 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO | 3 | 02do | 33 | 35
01CO | 01 | T1871 | 45224115201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 174 | 196 | 195 | 1 | 0 | 0 | 22 | 0 | 3701415 | 50000 | 3651415 | 3701415 | 3225904 | 0 | 0 | 0 | 3225904 | 3225904 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-03 | QTR2 | 24/25 | 2024-06-16 | QTR4 | 23/24 | 107 | 4091495.64 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO | 24 | 03co | 36 | 59
01DO | 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 272547 | 95906 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO | 6 | 03do | 60 | 65
01DO | 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 31977 | 22 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 49 | 0 | 0 | 0 | 0 |  | DO | 14 | 04co | 66 | 79
01DO | 01 | E1V15 | 44547115201 | 2023-01-19 | QTR3 | 22/23 | 2 | 0 | 225 | 427 | 410 | 17 | 0 | 0 | 74 | 128 | 7937275 | 81977 | 7855298 | 7937275 | 7998691 | 0 | 0 | 0 | 7998691 | 7941859 | -56832 | 0 | 102 | 0 | 5 | 23878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 28296 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-12-18 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 108 | 8527986.56 |  |  | 128 | 26 | 0 | 0 | 0 | 0 |  | DO | 8 | 04do | 80 | 87
01DO | 01 | E1W10 | 44744115201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 200 | 258 | 255 | 3 | 0 | 0 | 58 | 0 | 5126611 | 54498 | 5072113 | 5135303 | 4999771 | 0 | 0 | 0 | 4999771 | 4990201 | -9570 | 8692 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-07-12 | QTR1 | 24/25 | 108 | 5933693.34 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO | 15 | 05co | 88 | 102
01DO | 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 0 | 41494 | 0 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45 |  |  | 0 | 5 | 0 | 0 | 0 | 0 | T | DO | 5 | 05do | 103 | 107
01DO | 01 | E1W19 | 44743315201 | 2023-10-19 | QTR2 | 23/24 | 1 | 0 | 175 | 202 | 197 | 5 | 0 | 0 | 27 | 0 | 3927820 | 50000 | 3877820 | 3927820 | 3916235 | 0 | 0 | 0 | 3916235 | 3896792 | -19443 | 0 | 18 | 0 | 0 | 5190 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11509 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-12-12 | QTR2 | 24/25 | 2024-09-23 | QTR1 | 24/25 | 108 | 3787595.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO | 9 | 06co | 108 | 116
01DO | 01 | E1W20 | 44620215201 | 2023-10-19 | QTR2 | 23/24 | 1 | 1 | 150 | 186 | 186 | 0 | 0 | 0 | 36 | 0 | 2630586 | 50000 | 2580586 | 2630586 | 2573059 | 0 | 0 | 0 | 2573059 | 2559128 | -13930 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20390 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-09-12 | QTR1 | 24/25 | 118 | 2937557.72 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO | 5 | 06do | 117 | 121
02CO | 02 | T2804 | 44137215201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 300 | 903 | 903 | 0 | 0 | 0 | 179 | 424 | 7398298 | 61648 | 7336650 | 7431649 | 7733354 | 0 | 0 | 0 | 7733354 | 7955154 | 240397 | 33351 | 348 | 0 | 0 | 35071 | 0 | 0 | 173 | 51032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 3351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 89454 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 | 2024-03-02 | QTR3 | 23/24 | 208 | 6176554.21 |  |  | 424 | 82 | 0 | 0 | 0 | 0 |  | CO | 6 | 07co | 122 | 127
02CO | 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 456060 | 23650 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 9 | 07do | 128 | 136
02CO | 02 | T2828 | 44105015201 | 2021-12-08 | QTR2 | 21/22 | 3 | 6 | 200 | 680 | 680 | 0 | 0 | 0 | 229 | 251 | 2858409 | 52000 | 2806409 | 2966328 | 3044806 | 0 | 0 | 0 | 3044806 | 3042275 | 2144 | 107919 | 320 | 0 | 0 | 42323 | 0 | 0 | 87 | 103244 | 17949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 164 | 4676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 251 | 150243 | 17949 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 208 | 3146528.67 |  |  | 164 | 73 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 137 | 136
02CO | 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 140312 | 178487 | 171 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594 |  |  | 0 | 70 | 0 | 0 | 0 | 0 |  | CO | 8 | 08do | 137 | 144
02CO | 02 | T2838 | 44342015201 | 2022-04-27 | QTR4 | 21/22 | 2 | 5 | 300 | 661 | 661 | 0 | 0 | 0 | 223 | 138 | 11945708 | 100832 | 11844876 | 12005007 | 12120635 | 0 | 0 | 0 | 12120635 | 12067135 | -46610 | 59300 | 126 | 0 | 44 | 87730 | 0 | 0 | 91 | 40079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 134699 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 | 2024-07-17 | QTR1 | 24/25 | 208 | 12401357.97 |  |  | 69 | 97 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2853 | 44714915201 | 2022-06-08 | QTR4 | 21/22 | 3 | 4 | 540 | 680 | 663 | 17 | 0 | 0 | 120 | 20 | 17135161 | 200000 | 16935161 | 17359701 | 17949301 | 0 | 0 | 0 | 17949301 | 17746566 | -196328 | 224540 | 72 | 0 | 17 | 89971 | 0 | 0 | 27 | 312995 | 9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 6406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 337947 | 21170 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-08-30 | QTR1 | 24/25 | 208 | 22151002.61 |  |  | 40 | 48 | 0 | -25 | -83255 | 0 |  | CO
02CO | 02 | T2864 | 20765825201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 140 | 451 | 451 | 0 | 0 | 0 | 160 | 151 | 2568964 | 50000 | 2518964 | 2668964 | 2632044 | 0 | 0 | 0 | 2632044 | 2632301 | 257 | 100000 | 39 | 0 | 7 | 97145 | 0 | 0 | 44 | 48577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 145722 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-08-22 | QTR1 | 24/25 | 214 | 2408715.47 |  |  | 151 | 121 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253 |  |  | 1 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2900 | 40392045201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 100 | 392 | 371 | 21 | 0 | 0 | 292 | 0 | 869247 | 37251 | 831996 | 869247 | 857258 | 0 | 0 | 0 | 857258 | 857258 | 0 | 0 | 173 | 0 | 0 | 2298 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 2298 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-14 | QTR1 | 24/25 | 216 | 1017097.24 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2909 | 44607915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 250 | 447 | 445 | 2 | 0 | 0 | 97 | 100 | 7130409 | 68620 | 7061789 | 7130409 | 7454415 | 0 | 0 | 0 | 7454415 | 7438691 | -15725 | 0 | 129 | 0 | 0 | 1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 3586 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-09-06 | QTR1 | 24/25 | 208 | 7319755.75 |  |  | 100 | 68 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2911 | 44703315201 | 2023-05-17 | QTR4 | 22/23 | 1 | 1 | 260 | 312 | 290 | 22 | 0 | 0 | 52 | 0 | 5899711 | 60196 | 5839515 | 5916585 | 5921537 | 0 | 0 | 0 | 5921537 | 5926778 | 5241 | 16874 | 26 | 0 | 0 | 9350 | 0 | 0 | 0 | 16874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36315 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-07-10 | QTR1 | 24/25 | 214 | 6079797.84 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2922 | 44717615201 | 2023-05-17 | QTR4 | 22/23 | 1 | 0 | 200 | 261 | 256 | 5 | 0 | 0 | 61 | 0 | 4768192 | 52010 | 4716182 | 4768192 | 4978398 | 0 | 0 | 0 | 4978398 | 4983434 | 5036 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-07-22 | QTR1 | 24/25 | 214 | 5253038.86 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 0 | 0 | 6 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2957 | 44712915201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 164 | 157 | 7 | 0 | 0 | 14 | 0 | 2432061 | 50000 | 2382061 | 2483046 | 2440068 | 0 | 0 | 0 | 2440068 | 2440833 | 766 | 50985 | 10 | 0 | 0 | 2944 | 0 | 0 | 0 | 63883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66827 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 208 | 2377451.33 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 0 | 40 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 0 | 630 | 1 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05 |  |  | 87 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 0 | 2917973 | 194 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 1123706 | 3526869 | 109 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26 |  |  | 11 | 143 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 58046 | 137 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 0 | 292 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-02 | QTR2 | 24/25 | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94 |  |  | 22 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1950 | 65 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 0 | 220 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3791 | 43937615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 200 | 290 | 290 | 0 | 0 | 0 | 90 | 0 | 2097844 | 0 | 2097844 | 2104355 | 1977895 | 0 | 0 | 0 | 1977895 | 1977939 | 44 | 6511 | 56 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-03 | QTR1 | 24/25 | 313 | 2307183.3 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3792 | 44117115201 | 2023-04-26 | QTR4 | 22/23 | 1 | 1 | 160 | 225 | 224 | 1 | 0 | 0 | 65 | 0 | 1248264 | 0 | 1248264 | 1248264 | 1306248 | 0 | 0 | 0 | 1306248 | 1306346 | 98 | 0 | 39 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-04-08 | QTR4 | 23/24 | 313 | 1870598.48 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 20899 | 225 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95 |  |  | 0 | 78 | 0 | 0 | -5529 | 0 |  | CO
03CO | 03 | T3806 | 43973315201 | 2022-04-27 | QTR4 | 21/22 | 3 | 0 | 315 | 660 | 659 | 1 | 0 | 0 | 345 | 0 | 10103368 | 88637 | 10014731 | 10103368 | 10342165 | 0 | 0 | 0 | 10342165 | 10277452 | -64713 | 0 | 173 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 | 2024-08-14 | QTR1 | 24/25 | 308 | 10842967.81 |  |  | 0 | 72 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3813 | 44159315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 300 | 695 | 695 | 0 | 0 | 0 | 387 | 8 | 6499662 | 61994 | 6437668 | 6674412 | 6885176 | 0 | 0 | 0 | 6885176 | 6899511 | 14336 | 174750 | 309 | 75 | 3 | 179623 | 0 | 15 | 5 | 11079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 8 | 190702 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-08 | QTR2 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 308 | 6445150.22 |  |  | 8 | 48 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 10462 | 151 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75 |  |  | 0 | 96 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3824 | 43769915201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 330 | 416 | 416 | 0 | 0 | 0 | 86 | 0 | 3559704 | 0 | 3559704 | 3559704 | 3648796 | 0 | 0 | 0 | 3648796 | 3648367 | -429 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-30 | QTR2 | 24/25 | 2024-08-28 | QTR1 | 24/25 | 308 | 5711547.02 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3826 | 44387715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 90 | 322 | 322 | 0 | 0 | 0 | 232 | 0 | 942554 | 49324 | 893230 | 942554 | 927016 | 0 | 0 | 0 | 927016 | 927016 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-04-03 | QTR4 | 23/24 | 314 | 1043116.04 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3829 | 44553915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 300 | 380 | 380 | 0 | 0 | 0 | 63 | 17 | 12211588 | 124814 | 12086774 | 12181493 | 12519374 | 0 | 0 | 0 | 12519374 | 12516178 | -3196 | -30095 | 36 | 0 | 0 | 0 | 0 | 0 | 2 | 14322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | -15773 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-07-25 | QTR1 | 24/25 | 313 | 12606229.06 |  |  | 17 | 27 | 0 | 0 | -30095 | 0 |  | CO
03CO | 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3834 | 44563515201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 270 | 364 | 426 | -62 | 62 | 0 | 114 | 0 | 19944475 | 150000 | 19794475 | 19944475 | 21545566 | -363010 | 0 | -363010 | 21182556 | 21410083 | 227527 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 | 2024-08-14 | QTR1 | 24/25 | 314 | 18371047.42 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3842 | 44404015201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 60 | 433 | 424 | 9 | 0 | 0 | 373 | 0 | 851756 | 41407 | 810349 | 851756 | 802521 | 0 | 0 | 0 | 802521 | 802521 | 0 | 0 | 268 | 45 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 2000 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2024-08-12 | QTR1 | 24/25 | 314 | 869555.5 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 75924 | 138 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3856 | 44573315201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 166 | 399 | 399 | 0 | 0 | 0 | 233 | 0 | 6737296 | 71197 | 6666099 | 6737296 | 7134385 | 0 | 0 | 0 | 7134385 | 7124379 | -10006 | 0 | 152 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-21 | QTR2 | 24/25 | 2024-07-17 | QTR1 | 24/25 | 308 | 7216077.98 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3864 | 44562915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 3 | 230 | 347 | 329 | 18 | 0 | 0 | 105 | 12 | 3480880 | 51096 | 3429784 | 3589639 | 3810464 | 0 | 0 | 0 | 3810464 | 3809861 | -603 | 108759 | 73 | 0 | 0 | 12134 | 0 | 0 | 5 | 64017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 44742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 135093 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-08-18 | QTR1 | 24/25 | 308 | 5160701.28 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3877 | 43775715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 1 | 273 | 325 | 320 | 5 | 0 | 0 | 52 | 0 | 11695437 | 150000 | 11545437 | 11701443 | 12402258 | 0 | 0 | 0 | 12402258 | 12455669 | 53411 | 6006 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13152 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 321 | 9851819.87 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3880 | 43078925201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 135 | 199 | 193 | 6 | 0 | 0 | 64 | 0 | 3380216 | 54568 | 3325648 | 3380216 | 3471279 | 0 | 0 | 0 | 3471279 | 3471279 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-08-27 | QTR1 | 24/25 | 314 | 5332275.36 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3886 | 45221235201 | 2023-09-13 | QTR1 | 23/24 | 1 | 1 | 109 | 155 | 154 | 1 | 0 | 0 | 46 | 0 | 1444661 | 50000 | 1394661 | 1521683 | 1385235 | 0 | 0 | 0 | 1385235 | 1385235 | 0 | 77022 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-05-02 | QTR4 | 23/24 | 314 | 2325343.9 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3889 | 45221225201 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 140 | 184 | 127 | 57 | 0 | 0 | 29 | 15 | 1570117 | 50000 | 1520117 | 1689632 | 1597844 | 0 | 0 | 0 | 1597844 | 1597844 | 0 | 119515 | 12 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-05-24 | QTR4 | 23/24 | 313 | 1925284.7 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3897 | 44845115201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 165 | 254 | 254 | 0 | 0 | 0 | 86 | 3 | 1349500 | 50000 | 1299500 | 1349500 | 1300591 | 0 | 0 | 0 | 1300591 | 1300571 | -20 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 3 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 3 | 1250 | 0 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-10-29 | QTR2 | 24/25 | 321 | 1617297.75 |  |  | 3 | 12 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q94 | 21787545201 | 2018-06-14 | QTR4 | 17/18 | 1 | 11 | 1325 | 2106 | 2106 | 0 | 0 | 0 | 767 | 14 | 31708584 | 150000 | 31558584 | 32410332 | 32832992 | 0 | 0 | 0 | 32832992 | 33087185 | 254193 | 701748 | 414 | 0 | 0 | 391404 | 0 | 198 | 10 | 243931 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 103110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 14 | 746509 | 56594 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2024-05-21 | QTR4 | 23/24 | 306 | 25965925.9 |  |  | 14 | 136 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 26502 | 75 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | -70800 | 102687 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT | 2 | 35 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W88 | 44575515201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 120 | 128 | 124 | 4 | 0 | 0 | 8 | 0 | 2175239 | 50000 | 2125239 | 2175239 | 2183626 | 0 | 0 | 0 | 2183626 | 2183626 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-06-21 | QTR4 | 23/24 | 313 | 3085002.9 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4472 | 41934525201 | 2018-01-31 | QTR3 | 17/18 | 2 | 10 | 1049 | 1423 | 1423 | 0 | 0 | 0 | 263 | 111 | 33359900 | 182880 | 33177020 | 33746993 | 33295065 | 0 | -75000 | -75000 | 33220065 | 33597249 | 421739 | 387093 | 176 | 0 | 0 | 456573 | 0 | 0 | 0 | -143555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188 | 0 | 0 | 71 | 56466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32197 | 0 | 0 | 40 | 81324 | 79113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 484193 | 79113 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2022-06-22 | QTR4 | 21/22 | 409 | 37475055.58 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 87 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 598393 | 791712 | 277 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 92 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 96348 | 120572 | 150 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 877092 | 127 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4598 | 44399615201 | 2022-02-23 | QTR3 | 21/22 | 3 | 6 | 425 | 607 | 607 | 0 | 0 | 0 | 160 | 22 | 5606708 | 50000 | 5556708 | 5800857 | 5331108 | 0 | 0 | 0 | 5331108 | 5358143 | 30705 | 194148 | 85 | 0 | 0 | 0 | 0 | 28 | 22 | 190479 | 189820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 22 | 194148 | 189820 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-04-23 | QTR4 | 23/24 | 408 | 4811998.96 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 0 | 189 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | -1370 | 123 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 258794 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45087 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 0 | 63 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4636 | 44384415201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 194 | 305 | 305 | 0 | 0 | 0 | 111 | 0 | 798900 | 41899 | 757001 | 798900 | 732677 | 0 | 0 | 0 | 732677 | 732677 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-06-28 | QTR4 | 23/24 | 412 | 879882.26 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 625462 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 16863 | 37 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4647 | 44699815201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 80 | 133 | 129 | 4 | 0 | 0 | 53 | 0 | 555556 | 31410 | 524146 | 555556 | 522780 | 0 | 0 | 0 | 522780 | 522780 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-10-30 | QTR2 | 24/25 | 412 | 659609.7 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 5349446 | 3618986 | 181 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B5:B:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 112 | 0 | 0 | -48896 | 0 |  | DO
04DO | 04 | E4V48 | 44346115201 | 2022-05-06 | QTR4 | 21/22 | 2 | 0 | 719 | 771 | 539 | 232 | 0 | 0 | 52 | 0 | 6383851 | 97993 | 6285858 | 6383851 | 5949070 | 0 | 0 | 0 | 5949070 | 5949070 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 412 | 10090648.24 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V50 | 43975915201 | 2022-09-02 | QTR1 | 22/23 | 1 | 2 | 246 | 338 | 338 | 0 | 0 | 0 | 92 | 0 | 2437437 | 50000 | 2387437 | 2522997 | 2472614 | 0 | 0 | 0 | 2472614 | 2469346 | -3268 | 85560 | 39 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-06-28 | QTR4 | 23/24 | 409 | 2462556.03 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V97 | 44175915201 | 2022-11-04 | QTR2 | 22/23 | 1 | 0 | 128 | 325 | 323 | 2 | 0 | 0 | 197 | 0 | 3019043 | 50000 | 2969043 | 3019043 | 2884719 | 0 | 0 | 0 | 2884719 | 2884627 | -92 | 0 | 151 | 0 | 0 | 0 | 0 | 23 | 0 | 18308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 18308 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-11-08 | QTR2 | 24/25 | 2024-08-02 | QTR1 | 24/25 | 412 | 2305583.22 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 50772 | 14 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 41751 | 27 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | -43330 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W49 | 44637115201 | 2023-07-07 | QTR1 | 23/24 | 1 | 1 | 244 | 257 | 198 | 59 | 0 | 0 | 13 | 0 | 4434511 | 55240 | 4379271 | 4502024 | 4183947 | 0 | 0 | 0 | 4183947 | 4189012 | 5065 | 67513 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 412 | 5579255.71 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5721 | 44287515201 | 2021-12-08 | QTR2 | 21/22 | 3 | 7 | 510 | 817 | 805 | 12 | 0 | 0 | 257 | 50 | 16561765 | 150000 | 16411765 | 17284645 | 18223735 | 0 | 0 | 0 | 18223735 | 18689669 | 472880 | 722880 | 198 | 0 | 30 | 59072 | 0 | 0 | 0 | 671912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455 | 0 | 0 | 0 | 4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 743980 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-27 | QTR1 | 24/25 | 515 | 18568888.72 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | -57178 | 154746 | 45 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5728 | 44395815201 | 2021-08-25 | QTR1 | 21/22 | 6 | 5 | 600 | 848 | 847 | 1 | 0 | 0 | 248 | 0 | 34500000 | 150000 | 34350000 | 35703756 | 38083377 | -5932 | -11806 | -17738 | 38065638 | 39383079 | 1397410 | 1203756 | 187 | 0 | 0 | 557100 | 0 | 0 | 0 | 507869 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207739 | 292167 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 | 2024-03-15 | QTR3 | 23/24 | 509 | 32771897.49 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 39287 | 76 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | -1791 | 104943 | 39 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8 |  |  | 167 | 114 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | -1484 | 793 | 94 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 40000 | 128 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1 |  |  | 4 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | -18 | 2618 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5772 | 44569315201 | 2022-10-26 | QTR2 | 22/23 | 2 | 4 | 260 | 406 | 403 | 3 | 0 | 0 | 146 | 0 | 1859536 | 50000 | 1809536 | 1934513 | 2110697 | 0 | 0 | 0 | 2110697 | 2104981 | -360 | 74977 | 110 | 0 | 0 | 2993 | 0 | 0 | 0 | 30505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33497 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-06-18 | QTR4 | 23/24 | 509 | 1660927.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | -22 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | -1198 | 1419 | 9 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55 |  |  | 9 | 41 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5783 | 44576715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 230 | 286 | 283 | 3 | 0 | 0 | 56 | 0 | 2041154 | 50000 | 1991154 | 2041154 | 2088238 | -10982 | 0 | -10982 | 2077256 | 2076683 | -573 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-07-31 | QTR1 | 24/25 | 509 | 1415550.25 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 0 | -21976 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 | 2024-07-01 | QTR1 | 24/25 | 515 | 919900 |  |  | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5820 | 45222925201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 120 | 133 | 85 | 48 | 0 | 0 | 13 | 0 | 607569 | 43750 | 563819 | 607569 | 467724 | 0 | 0 | 0 | 467724 | 467724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-06-06 | QTR4 | 23/24 | 513 | 1006632.6 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5821 | 45222935201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 110 | 115 | 108 | 7 | 0 | 0 | 5 | 0 | 843345 | 50000 | 793345 | 843345 | 748398 | 0 | 0 | 0 | 748398 | 748398 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-11 | QTR2 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 512 | 1601075 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 0 | 7099 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-11 | QTR4 | 23/24 | 507 | 801387 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35 |  |  | 2 | 48 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B9 | 44709915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 260 | 337 | 337 | 0 | 0 | 0 | 77 | 0 | 7890001 | 88000 | 7802001 | 7890001 | 8013155 | 0 | 0 | 0 | 8013155 | 8041936 | 28780 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 514 | 9077031.16 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58B0 | 44878915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 2 | 170 | 213 | 213 | 0 | 0 | 0 | 43 | 0 | 2634873 | 50000 | 2584873 | 2681332 | 2729605 | 0 | 0 | 0 | 2729605 | 2729605 | 0 | 46460 | 31 | 0 | 0 | 7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7002 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 509 | 1708500.26 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 148832 | 48 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6494 | 42752125201 | 2022-01-26 | QTR3 | 21/22 | 6 | 2 | 320 | 394 | 339 | 55 | 0 | 0 | 74 | 0 | 4221888 | 50000 | 4171888 | 4224163 | 3676222 | 0 | 200000 | 200000 | 3876222 | 3699956 | -176266 | 2275 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2023-12-13 | QTR2 | 23/24 | 613 | 4370412.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6504 | 42918525201 | 2021-05-26 | QTR4 | 20/21 | 1 | 2 | 450 | 541 | 512 | 29 | 0 | 0 | 91 | 0 | 5189595 | 57167 | 5132429 | 5303929 | 5374583 | 0 | 0 | 0 | 5374583 | 5469555 | 94972 | 114333 | 55 | 0 | 0 | 152939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157299 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-03-21 | QTR3 | 23/24 | 613 | 5707742.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 488935 | 455645 | 61 | 0 | 0 | 55800 | 0 | 0 | 95 | 262248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 564979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6538 | 44391915201 | 2022-05-25 | QTR4 | 21/22 | 9 | 1 | 480 | 531 | 458 | 73 | 0 | 0 | 51 | 0 | 13790706 | 121591 | 13669115 | 13840706 | 13459785 | 0 | 480000 | 480000 | 13939785 | 13298540 | -641245 | 50000 | 32 | 0 | 0 | 29647 | 0 | 0 | 0 | 16702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22076 | 0 | 0 | 0 | 6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74679 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-10-02 | QTR2 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 636 | 12736630.45 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6559 | 43094925201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 450 | 619 | 619 | 0 | 0 | 0 | 169 | 0 | 8056848 | 70725 | 7986123 | 8075952 | 7918898 | 0 | 0 | 0 | 7918898 | 7945544 | 26646 | 19104 | 96 | 0 | 0 | 39629 | 0 | 0 | 0 | 16524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 56152 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 613 | 7161375.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 0 | 16 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6572 | 44390615201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 240 | 291 | 282 | 9 | 0 | 0 | 51 | 0 | 2360100 | 50000 | 2310100 | 2360100 | 2343530 | 0 | 0 | 0 | 2343530 | 2341786 | -1744 | 0 | 34 | 0 | 0 | 931 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 | 2024-09-03 | QTR1 | 24/25 | 613 | 2712981.65 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6M58 | 44492015201 | 2021-05-11 | QTR4 | 20/21 | 1 | 3 | 680 | 1057 | 1057 | 0 | 0 | 0 | 377 | 0 | 5167117 | 50000 | 5117117 | 5569451 | 5567027 | 0 | 0 | 0 | 5567027 | 5567027 | 0 | 402334 | 188 | 10 | 0 | 11007 | 0 | 0 | 0 | 120107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 449910 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-06-03 | QTR4 | 23/24 | 636 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 101 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -6838357 | -65427 | 60 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD | 0 | 80 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M99 | 44694715201 | 2022-04-11 | QTR4 | 21/22 | 1 | 2 | 500 | 782 | 782 | 0 | 0 | 0 | 282 | 0 | 2597679 | 50000 | 2547679 | 2701239 | 2676164 | 0 | 0 | 0 | 2676164 | 2676164 | 0 | 103560 | 151 | 0 | 0 | -12464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 116024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 103560 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2024-10-31 | QTR2 | 24/25 | 2024-08-02 | QTR1 | 24/25 | 636 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 86 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | -21 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O72 | 43029179201 | 2023-06-12 | QTR4 | 22/23 | 2 | 4 | 330 | 352 | 324 | 28 | 0 | 0 | 22 | 0 | 1937336 | 0 | 1937336 | 1987336 | 1966014 | 0 | 0 | 0 | 1966014 | 0 | -1966014 | 50000 | 0 | 0 | 0 | 13249 | 0 | 0 | 0 | 6779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28678 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-08-09 | QTR1 | 24/25 | 636 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7438 | 25632425201 | 2020-11-18 | QTR2 | 20/21 | 2 | 11 | 700 | 961 | 953 | 8 | 0 | 0 | 218 | 43 | 16728833 | 239863 | 16488970 | 18036076 | 18037280 | 0 | 0 | 0 | 18037280 | 18987569 | 1096394 | 1307244 | 167 | 0 | 39 | 487932 | 0 | 0 | 4 | 893855 | 7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88439 | 16356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1473608 | 23952 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-11-15 | QTR2 | 24/25 | 2023-10-19 | QTR2 | 23/24 | 714 | 19921100 |  |  | 33 | 51 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 117308 | 206565 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7481 | 44073315201 | 2022-08-31 | QTR1 | 22/23 | 3 | 0 | 225 | 294 | 294 | 0 | 0 | 0 | 69 | 0 | 3304021 | 50000 | 3254021 | 3304021 | 3182990 | 0 | 0 | 0 | 3182990 | 3174072 | -8918 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-12 | QTR2 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 796 | 3303500 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7492 | 44024815201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 210 | 250 | 250 | 0 | 0 | 0 | 40 | 0 | 5438332 | 52000 | 5386332 | 5435828 | 5441055 | 0 | 0 | 0 | 5441055 | 5414623 | -26432 | -2504 | 24 | 0 | 0 | -2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2504 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 799 | 5496384.15 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7518 | 45248755201 | 2023-12-06 | QTR2 | 23/24 | 5 | 0 | 140 | 153 | 142 | 11 | 0 | 0 | 13 | 0 | 908274 | 50000 | 858274 | 908274 | 908491 | 0 | 0 | 0 | 908491 | 908491 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 | 2024-09-16 | QTR1 | 24/25 | 798 | 1515975 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 0 | 207487 | 178 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | -125432 | 324762 | 127 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P35 | 44165715201 | 2022-05-11 | QTR4 | 21/22 | 2 | 3 | 400 | 458 | 458 | 0 | 0 | 0 | 58 | 0 | 8986578 | 71000 | 8915578 | 9084687 | 9016111 | 0 | 0 | 0 | 9016111 | 8840279 | -171882 | 98110 | 30 | 0 | 0 | 115777 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-04-18 | QTR4 | 23/24 | 799 | 8393400 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 101105 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 30000 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 4646 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | -31871 | 3477169 | 524 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 88 | 0 | 0 | -127928 | 0 |  | DO
08DO | 08 | E8R80 | 43554315201 | 2019-06-11 | QTR4 | 18/19 | 1 | 9 | 1810 | 1897 | 1601 | 296 | 0 | 0 | 182 | -95 | 244979349 | 150000 | 244829349 | 251466172 | 255108575 | 0 | 4375439 | 4375439 | 259484014 | 258158459 | 4868615 | 6486824 | 78 | 0 | 0 | 311893 | 0 | 0 | 0 | 9734282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5045376 | 0 | 0 | 0 | 1661009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -95 | 6556771 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 | 2024-02-29 | QTR3 | 23/24 | 854 | 217827999.45 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 104 | 0 | -95 | -168828 | 0 |  | DO
08DO | 08 | E8S90 | 43945755201 | 2021-04-20 | QTR4 | 20/21 | 5 | 13 | 533 | 998 | 998 | 0 | 0 | 0 | 465 | 0 | 21999573 | 150000 | 21849573 | 23015619 | 24155114 | 0 | 0 | 0 | 24155114 | 24813029 | 1013008 | 1016046 | 287 | 56 | 0 | 446658 | 0 | 0 | 0 | 537731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 32966 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 125872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 1143227 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 854 | 23025803.13 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T67 | 44262415201 | 2022-04-12 | QTR4 | 21/22 | 2 | 5 | 322 | 521 | 518 | 3 | 0 | 0 | 199 | 0 | 12517000 | 119797 | 12397203 | 12877010 | 12203064 | 0 | 0 | 0 | 12203064 | 12123596 | -79468 | 360010 | 133 | 0 | 0 | 108673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796 | 0 | 0 | 0 | 257897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369366 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 854 | 13936524.01 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T77 | 44925315201 | 2022-05-17 | QTR4 | 21/22 | 2 | 4 | 440 | 677 | 666 | 11 | 0 | 0 | 237 | 0 | 5565378 | 50000 | 5515378 | 5757378 | 5730235 | 0 | 0 | 0 | 5730235 | 5763102 | 32867 | 192000 | 120 | 0 | 0 | 30727 | 0 | 0 | 0 | 77369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 62 | 0 | 108096 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-14 | QTR2 | 24/25 | 2024-09-11 | QTR1 | 24/25 | 854 | 5213379.79 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T82 | 42897215201 | 2022-09-13 | QTR1 | 22/23 | 2 | 2 | 568 | 619 | 464 | 155 | 0 | 0 | 51 | 0 | 2504148 | 58519 | 2445628 | 2711373 | 2646645 | 0 | 0 | 0 | 2646645 | 2639419 | 0 | 207226 | 9 | 0 | 0 | 227557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234782 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-07-11 | QTR1 | 24/25 | 854 | 4806556.91 |  |  | 0 | 42 | 0 | 0 | 7226 | 0 |  | DO
08DO | 08 | E8T94 | 43578625201 | 2022-10-25 | QTR2 | 22/23 | 1 | 1 | 165 | 221 | 221 | 0 | 0 | 0 | 41 | 15 | 2596848 | 50000 | 2546848 | 2612139 | 2505813 | 0 | 0 | 0 | 2505813 | 2503780 | -2033 | 15291 | 18 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-05-17 | QTR4 | 23/24 | 854 | 2699146.4 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T95 | 44171915201 | 2022-10-25 | QTR2 | 22/23 | 3 | 3 | 508 | 651 | 615 | 36 | 0 | 0 | 143 | 0 | 21849074 | 150000 | 21699074 | 22014286 | 22325271 | 0 | 0 | 0 | 22325271 | 22079112 | -230948 | 165212 | 97 | 0 | 0 | 189344 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201 | 0 | 0 | 0 | 11368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225106 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 | 2024-10-17 | QTR2 | 24/25 | 854 | 21254879.86 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 25000 | 4 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0