## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 40435870 | 39977855 | 41444372 | 40067287 | 0 | 40701140 | 1.809% | 100% | 1054891 | 2.639% | 1008503 | 2.494% | 1704 | 511 | 29.99% | 189 | 11.09% | 29 | 1.702% | 184 | 10.8% | 1917 | 12.5% | 2595 | 2575 | 1875 | 10.04% | 85.71%
| District Let | 69427064 | 68646602 | 70906114 | 70640974 | 0 | 70497932 | 2.697% | 100% | 1729129 | 2.519% | 1479051 | 2.13% | 3412 | 532 | 15.59% | 293 | 8.587% | 185 | 5.422% | 217 | 6.36% | 3814 | 11.78% | 4585 | 4521 | 3696 | 8.324% | 76.92%
| All Contracts | 109862934 | 108624457 | 112350486 | 110708261 | 0 | 111199072 | 2.37% | 100% | 2784020 | 2.563% | 2487554 | 2.264% | 5116 | 1043 | 20.39% | 482 | 9.421% | 214 | 4.183% | 401 | 7.838% | 5731 | 12.02% | 7180 | 7096 | 5571 | 8.894% | 80%
2 | Central Let | 179503683 | 177229626 | 181270118 | 182933994 | 697536 | 182960106 | 3.233% | 96.55% | 2611750 | 1.474% | 1766436 | 0.9841% | 6576 | 2459 | 37.39% | 991 | 15.07% | 700 | 10.64% | 1468 | 22.32% | 8744 | 32.97% | 11071 | 10680 | 7230 | 9.945% | 72.41%
| District Let | 36267887 | 35861204 | 42453228 | 43242861 | 0 | 43278474 | 20.68% | 60% | 6360958 | 17.74% | 6185341 | 17.05% | 2240 | 345 | 15.4% | 380 | 16.96% | 124 | 5.536% | 599 | 26.74% | 2963 | 32.28% | 3682 | 3653 | 2928 | 30.71% | 20%
| All Contracts | 215771570 | 213090830 | 223723346 | 226176855 | 697536 | 226238580 | 6.17% | 91.18% | 8972708 | 4.211% | 7951777 | 3.685% | 8816 | 2804 | 31.81% | 1371 | 15.55% | 824 | 9.347% | 2067 | 23.45% | 11707 | 32.79% | 14753 | 14333 | 10158 | 15.22% | 64.71%
3 | Central Let | 186638365 | 184605024 | 188369332 | 195538153 | 0 | 195837654 | 6.085% | 93.75% | 1986012 | 1.076% | 1730968 | 0.9274% | 7397 | 3498 | 47.29% | 1322 | 17.87% | 1629 | 22.02% | 225 | 3.042% | 9251 | 25.06% | 13117 | 12984 | 8164 | 10.37% | 81.25%
| District Let | 68205176 | 67536934 | 69036113 | 69821487 | 800 | 70235988 | 3.996% | 90.91% | 915145 | 1.355% | 830937 | 1.218% | 3027 | 905 | 29.9% | 451 | 14.9% | 371 | 12.26% | 22 | 0.7268% | 3420 | 12.98% | 4755 | 4725 | 3369 | 11.3% | 100%
| All Contracts | 254843541 | 252141958 | 257405445 | 265359640 | 800 | 266073642 | 5.525% | 93.02% | 2901157 | 1.151% | 2561905 | 1.005% | 10424 | 4403 | 42.24% | 1773 | 17.01% | 2000 | 19.19% | 247 | 2.37% | 12671 | 21.56% | 17872 | 17709 | 11533 | 10.64% | 86.05%
4 | Central Let | 223034345 | 221147998 | 231928505 | 229007196 | -25000 | 229868429 | 3.943% | 95.83% | 9572473 | 4.329% | 9113572 | 4.086% | 9994 | 2514 | 25.16% | 909 | 9.095% | 686 | 6.864% | 991 | 9.916% | 11671 | 16.78% | 14745 | 14751 | 11328 | 13.35% | 87.5%
| District Let | 204600888 | 203621518 | 210405145 | 209843906 | 1375000 | 210742816 | 3.497% | 100% | 6095823 | 2.994% | 6332462 | 3.095% | 5479 | 1306 | 23.84% | 468 | 8.542% | 448 | 8.177% | 47 | 0.8578% | 5974 | 9.034% | 7593 | 7289 | 5515 | 0.6571% | 100%
| All Contracts | 427635233 | 424769516 | 442333650 | 438851102 | 1350000 | 440611245 | 3.729% | 97.44% | 15668296 | 3.689% | 15446034 | 3.612% | 15473 | 3820 | 24.69% | 1377 | 8.899% | 1134 | 7.329% | 1038 | 6.708% | 17645 | 14.04% | 22338 | 22040 | 16843 | 8.854% | 92.31%
5 | Central Let | 109564689 | 108239189 | 114920616 | 118794745 | -11806 | 120319528 | 11.16% | 80% | 5304901 | 4.901% | 5355926 | 4.888% | 5620 | 1373 | 24.43% | 848 | 15.09% | 52 | 0.9253% | 353 | 6.281% | 6025 | 7.206% | 8300 | 8041 | 5820 | 3.559% | 85%
| District Let | 94208454 | 93085902 | 95617891 | 96658872 | 0 | 97203672 | 4.424% | 85% | 1196192 | 1.285% | 1409437 | 1.496% | 4966 | 1344 | 27.06% | 920 | 18.53% | 32 | 0.6444% | 90 | 1.812% | 5088 | 2.457% | 7432 | 7403 | 5139 | 3.484% | 95%
| All Contracts | 203773143 | 201325091 | 210538507 | 215453617 | -11806 | 217523200 | 8.046% | 82.5% | 6501093 | 3.229% | 6765363 | 3.32% | 10586 | 2717 | 25.67% | 1768 | 16.7% | 84 | 0.7935% | 443 | 4.185% | 11113 | 4.978% | 15732 | 15444 | 10959 | 3.524% | 90%
6 | Central Let | 70647230 | 69881305 | 71490370 | 70498132 | 1600000 | 70832133 | 1.361% | 100% | 1193639 | 1.708% | 843140 | 1.193% | 4080 | 521 | 12.77% | 271 | 6.642% | 32 | 0.7843% | 95 | 2.328% | 4207 | 3.113% | 4999 | 4486 | 3694 | -9.461% | 100%
| District Let | 38646765 | 38140699 | 41408614 | 41226055 | 0 | 32048814 | -15.97% | 80% | 2829637 | 7.419% | 2761848 | 7.146% | 3770 | 816 | 21.64% | 414 | 10.98% | 320 | 8.488% | 91 | 2.414% | 4181 | 10.9% | 5411 | 5310 | 4080 | 8.223% | 90%
| All Contracts | 109293995 | 108022004 | 112898984 | 111724187 | 1600000 | 102880947 | -4.759% | 90.48% | 4023276 | 3.724% | 3604988 | 3.298% | 7850 | 1337 | 17.03% | 685 | 8.726% | 352 | 4.484% | 186 | 2.369% | 8388 | 6.854% | 10410 | 9796 | 7774 | -0.9682% | 95.24%
7 | Central Let | 72399260 | 71541076 | 74113185 | 74483234 | 0 | 75725221 | 5.849% | 81.82% | 1784634 | 2.495% | 1713928 | 2.367% | 3738 | 638 | 17.07% | 338 | 9.042% | 107 | 2.862% | 400 | 10.7% | 4245 | 13.56% | 5147 | 5026 | 4050 | 8.347% | 90.91%
| District Let | 223599420 | 222382442 | 231432717 | 232322471 | 0 | 231085765 | 3.914% | 100% | 8153623 | 3.666% | 7833298 | 3.503% | 5643 | 1401 | 24.83% | 531 | 9.41% | 418 | 7.407% | 593 | 10.51% | 6654 | 17.92% | 8526 | 8589 | 6657 | 17.97% | 93.33%
| All Contracts | 295998680 | 293923518 | 305545902 | 306805705 | 0 | 306810986 | 4.385% | 92.31% | 9938257 | 3.381% | 9547226 | 3.225% | 9381 | 2039 | 21.74% | 869 | 9.263% | 525 | 5.596% | 993 | 10.59% | 10899 | 16.18% | 13673 | 13615 | 10707 | 14.13% | 92.31%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 387784581 | 386607171 | 396888504 | 400443053 | 4375439 | 405728509 | 4.946% | 92.86% | 9517004 | 2.462% | 9103926 | 2.348% | 7554 | 1169 | 15.48% | 700 | 9.267% | 279 | 3.693% | -23 | -0.3045% | 7810 | 3.389% | 9534 | 8782 | 6913 | -8.486% | #VALUE!
| All Contracts | 387784581 | 386607171 | 396888504 | 400443053 | 4375439 | 405728509 | 4.946% | 92.86% | 9517004 | 2.462% | 9103926 | 2.348% | 7554 | 1169 | 15.48% | 700 | 9.267% | 279 | 3.693% | -23 | -0.3045% | 7810 | 3.389% | 9534 | 8782 | 6913 | -8.486% | 100%
Totals This Qtr | Central Let | 882223442 | 872622073 | 903536498 | 911322741 | 2260730 | 916244211 | 4.999% | 92.54% | 23508300 | 2.694% | 21532473 | 2.441% | 39109 | 11514 | 29.44% | 4868 | 12.45% | 3235 | 8.272% | 3716 | 9.502% | 46060 | 17.77% | 59974 | 58543 | 42161 | 7.804% | 83.58%
| District Let | 1122740235 | 1115882472 | 1158148326 | 1164199679 | 5751239 | 1160821970 | 4.027% | 91.26% | 36797511 | 3.298% | 35936300 | 3.201% | 36091 | 7818 | 21.66% | 4157 | 11.52% | 2177 | 6.032% | 1636 | 4.533% | 39904 | 10.56% | 51518 | 50272 | 38297 | 6.112% | 90.29%
| All Contracts | 2004963677 | 1988504545 | 2061684824 | 2075522420 | 8011969 | 2077066181 | 4.454% | 91.98% | 60305811 | 3.033% | 57468773 | 2.866% | 75200 | 19332 | 25.71% | 9025 | 12% | 5412 | 7.197% | 5352 | 7.117% | 85964 | 14.31% | 111492 | 108815 | 80458 | 6.992% | 86.5%
Totals Previous Quarter | Central Let | 571974753 | 565829742 | 581978774 | 588606001 | 1133194 | 592743727 | 4.757% | 93.55% | 11285695 | 1.995% | 10219470 | 1.787% | 25299 | 8276 | 32.71% | 3485 | 13.78% | 2342 | 9.257% | 2066 | 8.166% | 29707 | 17.42% | 39497 | 38832 | 27071 | 7.004% | 86.02%
| District Let | 721618364 | 718086869 | 746150582 | 750681623 | 5751239 | 744874308 | 3.73% | 94.12% | 25141978 | 3.501% | 24573973 | 3.405% | 19204 | 3984 | 20.75% | 2082 | 10.84% | 1585 | 8.253% | 696 | 3.624% | 21485 | 11.88% | 27274 | 26200 | 20134 | 4.843% | 88.24%
| All Contracts | 1293593117 | 1283916611 | 1328129356 | 1339287624 | 6884433 | 1337618035 | 4.183% | 93.75% | 36427673 | 2.837% | 34793443 | 2.69% | 44503 | 12260 | 27.55% | 5567 | 12.51% | 3927 | 8.824% | 2762 | 6.206% | 51192 | 15.03% | 66771 | 65032 | 47205 | 6.072% | 86.81%
Totals Fiscal Year 2023/2024 | Central Let | 1204341087 | 0.068748 | 0.87097 | 49832653 | 0.044222 | 48342251 | 4.248% | 5044300% | 15125 | 29.98% | 6090 | 12.07% | 5317 | 0.10541 | 563300% | 0.11167 | 6139300% | 0.21708 | 7918400% | 80497 | 5928200% | 0.17523 | 74.73% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 992287650 | 0.030232 | 0.91057 | 35080258 | 0.036422 | 32751273 | 3.375% | 3308000% | 6744 | 20.39% | 4161 | 12.58% | 1348 | 0.04075 | 227700% | 0.068833 | 3670500% | 0.10958 | 4640000% | 44681 | 3377600% | 0.02104 | 93.5% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2196628737 | 0.050998 | 0.88673 | 84912911 | 0.040627 | 81093524 | 3.846% | 8352300% | 21869 | 26.18% | 10251 | 12.27% | 6665 | 0.079798 | 791000% | 0.094704 | 9809800% | 0.1745 | 12558400% | 125178 | 9305800% | 0.11416 | 82.2% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1805 | 43943115201 | 2021-07-28 | QTR1 | 21/22 | 2 | 2 | 300 | 388 | 388 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 6184000 | 84041 | 6099959 | 6204651 | 6014186 | 0 | 0 | 0 | 6014186 | 6704450 | 109.9% | 1 | 698558 | 20651 | 56 | 32 | 0 | 0 | 14008 | 0 | 0 | 0 | 16372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38675 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-02-28 | QTR3 | 24/25 |  | 2022-11-30 | QTR2 | 22/23 | 118 | 7780401.21
| 01 | T1825 | 43982715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 11 | 350 | 671 | 668 | 142.6% | 0 | 3 | 0 | 0 | 147 | 174 | 8278071 | 77832 | 8200239 | 8939807 | 8867401 | 0 | 0 | 0 | 8867401 | 8929131 | 108.9% | 1 | 86356 | 661736 | 124 | 45 | 0 | 30 | 233423 | 0 | 0 | 62 | 279341 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24626 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 673447 | 398388 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-05-29 | QTR4 | 23/24 | 118 | 7852554.7
| 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 94.5% | 1 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | 96.89% | 1 | -12039 | 0 | 86 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 |  | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92
| 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 107.7% | 1 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | 104% | 1 | -851 | 59015 | 83 | 24 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4
| 01 | T1848 | 44593215201 | 2022-12-07 | QTR2 | 22/23 | 2 | 2 | 300 | 384 | 382 | 109% | 1 | 2 | 0 | 0 | 84 | 0 | 13310586 | 146142 | 13164444 | 13399125 | 12912681 | 0 | 0 | 0 | 12912681 | 12823061 | 97.41% | 1 | -89620 | 88540 | 29 | 26 | 0 | 0 | 82557 | 0 | 0 | 0 | 27850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -469 | 0 | 29 | 0 | 8021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 117959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-01-29 | QTR3 | 24/25 |  | 2024-05-16 | QTR4 | 23/24 | 118 | 14760503.34
| 01 | T1860 | 43709615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 9 | 250 | 401 | 398 | 98.8% | 1 | 3 | 0 | 0 | 151 | 0 | 4325722 | 50000 | 4275722 | 4504283 | 4508752 | 0 | 0 | 0 | 4508752 | 4493121 | 105.1% | 1 | -11661 | 178561 | 124 | 27 | 0 | 0 | 28409 | 0 | 0 | 0 | 105237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5020 | 5020 | 0 | 0 | 23159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165795 | 5020 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-10-14 | QTR2 | 24/25 |  | 2024-05-22 | QTR4 | 23/24 | 113 | 2709382.82
| 01 | T1871 | 45224115201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 174 | 196 | 195 | 99.43% | 1 | 1 | 0 | 0 | 22 | 0 | 3701415 | 50000 | 3651415 | 3701415 | 3225904 | 0 | 0 | 0 | 3225904 | 3225904 | 88.35% | 1 | 0 | 0 | 9 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-03 | QTR2 | 24/25 |  | 2024-06-16 | QTR4 | 23/24 | 107 | 4091495.64
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 7 | 10 | 30 | 1704 | 2595 | 2575 | 85.71% | 6 | 20 | 0 | 0 | 707 | 184 | 40435870 | 458015 | 39977855 | 41444372 | 40067287 | 0 | 0 | 0 | 40067287 | 40701140 | 100% | 7 | 670743 | 1008503 | 511 | 189 | 0 | 30 | 358397 | 0 | 0 | 74 | 487815 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 4551 | 5020 | 29 | 0 | 31180 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 36891 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 184 | 1054891 | 403408
| 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 99.78% | 1 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 96.34% | 1 | 272547 | 95906 | 140 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 |  | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1
| 01 | E1U16 | 44742915201 | 2023-07-20 | QTR1 | 23/24 | 1 | 2 | 225 | 277 | 276 | 100.9% | 1 | 1 | 0 | 0 | 49 | 3 | 7395393 | 70545 | 7324848 | 7483422 | 7804114 | 0 | 0 | 0 | 7804114 | 7806499 | 106.6% | 1 | 2385 | 88029 | 41 | 8 | 0 | 3 | 129977 | 0 | 0 | 0 | 10432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 140409 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-02-10 | QTR3 | 24/25 |  | 2024-10-25 | QTR2 | 24/25 | 108 | 7252828.57
| 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 112.8% | 1 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | 101% | 1 | -1888 | 31977 | 22 | 49 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1V11 | 44504315201 | 2023-01-19 | QTR3 | 22/23 | 1 | 2 | 150 | 254 | 249 | 135.3% | 0 | 5 | 0 | 0 | 104 | 0 | 2582000 | 50000 | 2532000 | 2736729 | 2706856 | 0 | 0 | 0 | 2706856 | 2588087 | 102.2% | 1 | -2261 | 154729 | 25 | 21 | 0 | 0 | 4229 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 116508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 168490 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-07 | QTR3 | 24/25 |  | 2024-05-06 | QTR4 | 23/24 | 115 | 3004848.32 | B0 | ACC - LUMP SUM
| 01 | E1V15 | 44547115201 | 2023-01-19 | QTR3 | 22/23 | 2 | 0 | 225 | 427 | 410 | 125.3% | 0 | 17 | 0 | 0 | 74 | 128 | 7937275 | 81977 | 7855298 | 7937275 | 7998691 | 0 | 0 | 0 | 7998691 | 7941859 | 101.1% | 1 | -56832 | 0 | 102 | 26 | 0 | 5 | 23878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 28296 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-12-18 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 108 | 8527986.56
| 01 | E1V16 | 44405015201 | 2022-06-09 | QTR4 | 21/22 | 2 | 3 | 282 | 402 | 402 | 122.7% | 0 | 0 | 0 | 0 | 116 | 4 | 5610556 | 50000 | 5560556 | 5735677 | 5817092 | 0 | 0 | 0 | 5817092 | 5791996 | 104.2% | 1 | -22111 | 125122 | 30 | 26 | 0 | 4 | 122770 | 0 | 17 | 0 | 20695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 12551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 4 | 165375 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 |  | 2024-05-15 | QTR4 | 23/24 | 108 | 4321005.33 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | E1V18 | 44620815201 | 2023-03-16 | QTR3 | 22/23 | 1 | 3 | 300 | 381 | 375 | 104% | 1 | 6 | 0 | 0 | 63 | 18 | 11855203 | 111820 | 11743383 | 12344460 | 12567270 | 0 | 0 | 0 | 12567270 | 12562055 | 107% | 1 | -5215 | 489257 | 36 | 27 | 0 | 5 | 23548 | 0 | 0 | 13 | 491849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 525875 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-19 | QTR3 | 24/25 |  | 2024-09-24 | QTR1 | 24/25 | 118 | 11076911.57
| 01 | E1V61 | 44622815201 | 2022-10-10 | QTR2 | 22/23 | 1 | 2 | 400 | 536 | 531 | 114.8% | 1 | 5 | 0 | 0 | 72 | 64 | 5258695 | 50000 | 5208695 | 5702540 | 5768353 | 0 | 0 | 0 | 5768353 | 5707872 | 109.6% | 1 | -60481 | 443845 | 34 | 38 | 0 | 5 | 16799 | 0 | 0 | 49 | 420905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 38929 | 22940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 476632 | 22940 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 |  | 2024-05-18 | QTR4 | 23/24 | 118 | 6337132.03 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1W10 | 44744115201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 200 | 258 | 255 | 98.5% | 1 | 3 | 0 | 0 | 58 | 0 | 5126611 | 54498 | 5072113 | 5135303 | 4999771 | 0 | 0 | 0 | 4999771 | 4990201 | 98.39% | 1 | -9570 | 8692 | 35 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-07-12 | QTR1 | 24/25 | 108 | 5933693.34
| 01 | E1W12 | 44738215201 | 2024-03-21 | QTR3 | 23/24 | 1 | 0 | 150 | 179 | 162 | 88.67% | 1 | 17 | 0 | 0 | 29 | 0 | 3349511 | 50000 | 3299511 | 3349511 | 3342095 | 0 | 0 | 0 | 3342095 | 3331252 | 101% | 1 | -10843 | 0 | 22 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-02-26 | QTR3 | 24/25 |  | 2024-12-16 | QTR2 | 24/25 | 115 | 3912147.05
| 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 97.78% | 1 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 104.7% | 1 | 0 | 41494 | 0 | 5 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45
| 01 | E1W19 | 44743315201 | 2023-10-19 | QTR2 | 23/24 | 1 | 0 | 175 | 202 | 197 | 97.14% | 1 | 5 | 0 | 0 | 27 | 0 | 3927820 | 50000 | 3877820 | 3927820 | 3916235 | 0 | 0 | 0 | 3916235 | 3896792 | 100.5% | 1 | -19443 | 0 | 18 | 9 | 0 | 0 | 5190 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11509 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-12-12 | QTR2 | 24/25 |  | 2024-09-23 | QTR1 | 24/25 | 108 | 3787595.4
| 01 | E1W20 | 44620215201 | 2023-10-19 | QTR2 | 23/24 | 1 | 1 | 150 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 2630586 | 50000 | 2580586 | 2630586 | 2573059 | 0 | 0 | 0 | 2573059 | 2559128 | 99.17% | 1 | -13930 | 0 | 27 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20390 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-09-12 | QTR1 | 24/25 | 118 | 2937557.72
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 13 | 16 | 19 | 3412 | 4585 | 4521 | 76.92% | 10 | 64 | 0 | 0 | 956 | 217 | 69427064 | 780462 | 68646602 | 70906114 | 70640974 | 0 | 0 | 0 | 70640974 | 70497932 | 100% | 13 | 72358 | 1479051 | 532 | 293 | 0 | 22 | 370200 | 0 | 46 | 62 | 1001840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 124722 | 22940 | 11 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 29 | 54 | 215399 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 12551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 217 | 1729129 | 22940
| District 01 Totals |  |  |  |  | 20 | 26 | 49 | 5116 | 7180 | 7096 | 80% | 16 | 84 | 0 | 0 | 1663 | 401 | 109862934 | 1238477 | 108624457 | 112350486 | 110708261 | 0 | 0 | 0 | 110708261 | 111199072 | 100% | 20 | 743101 | 2487554 | 1043 | 482 | 0 | 52 | 728597 | 0 | 46 | 136 | 1489655 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 129273 | 27960 | 40 | 0 | 35598 | 0 | 0 | 0 | 0 | 0 | 29 | 76 | 252290 | 0 | 0 | 0 | 0 | 0 | 99 | 60 | 148609 | 363218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 401 | 2784020 | 426348
| 02 | T2804 | 44137215201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 300 | 903 | 903 | 157.7% | 0 | 0 | 0 | 0 | 179 | 424 | 7398298 | 61648 | 7336650 | 7431649 | 7733354 | 0 | 0 | 0 | 7733354 | 7955154 | 108.4% | 1 | 240397 | 33351 | 348 | 82 | 0 | 0 | 35071 | 0 | 0 | 173 | 51032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 3351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 89454 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 |  | 2024-03-02 | QTR3 | 23/24 | 208 | 6176554.21
| 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | 106.9% | 1 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 104.2% | 1 | 456060 | 23650 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 |  | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13
| 02 | T2828 | 44105015201 | 2021-12-08 | QTR2 | 21/22 | 3 | 6 | 200 | 680 | 680 | 143.5% | 0 | 0 | 0 | 0 | 229 | 251 | 2858409 | 52000 | 2806409 | 2966328 | 3044806 | 0 | 0 | 0 | 3044806 | 3042275 | 108.4% | 1 | 2144 | 107919 | 320 | 73 | 0 | 0 | 42323 | 0 | 0 | 87 | 103244 | 17949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 164 | 4676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 251 | 150243 | 17949 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 208 | 3146528.67
| 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 106.8% | 1 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 105.7% | 1 | 140312 | 178487 | 171 | 70 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594
| 02 | T2838 | 44342015201 | 2022-04-27 | QTR4 | 21/22 | 2 | 5 | 300 | 661 | 661 | 146% | 0 | 0 | 0 | 0 | 223 | 138 | 11945708 | 100832 | 11844876 | 12005007 | 12120635 | 0 | 0 | 0 | 12120635 | 12067135 | 101.9% | 1 | -46610 | 59300 | 126 | 97 | 0 | 44 | 87730 | 0 | 0 | 91 | 40079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 134699 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 |  | 2024-07-17 | QTR1 | 24/25 | 208 | 12401357.97
| 02 | T2843 | 21023045201 | 2022-05-25 | QTR4 | 21/22 | 3 | 2 | 450 | 800 | 795 | 136.7% | 0 | 5 | 0 | 0 | 212 | 138 | 12094446 | 152516 | 11941930 | 12285295 | 12375077 | 0 | 0 | 0 | 12375077 | 12184067 | 102% | 1 | -191010 | 190849 | 142 | 38 | 0 | 91 | 243953 | 0 | 0 | 47 | 66569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138 | 310522 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-21 | QTR3 | 24/25 |  | 2024-10-08 | QTR2 | 24/25 | 216 | 15875563.44
| 02 | T2853 | 44714915201 | 2022-06-08 | QTR4 | 21/22 | 3 | 4 | 540 | 680 | 663 | 100.6% | 1 | 17 | 0 | 0 | 120 | 20 | 17135161 | 200000 | 16935161 | 17359701 | 17949301 | 0 | 0 | 0 | 17949301 | 17746566 | 104.8% | 1 | -196328 | 224540 | 72 | 48 | 0 | 17 | 89971 | 0 | 0 | 27 | 312995 | 9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 6406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25 | -83255 | 0 | 0 | 20 | 337947 | 21170 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-08-30 | QTR1 | 24/25 | 208 | 22151002.61
| 02 | T2864 | 20765825201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 140 | 451 | 451 | 207.9% | 0 | 0 | 0 | 0 | 160 | 151 | 2568964 | 50000 | 2518964 | 2668964 | 2632044 | 0 | 0 | 0 | 2632044 | 2632301 | 104.5% | 1 | 257 | 100000 | 39 | 121 | 0 | 7 | 97145 | 0 | 0 | 44 | 48577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 145722 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 |  | 2024-08-22 | QTR1 | 24/25 | 214 | 2408715.47
| 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 99.33% | 1 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 97.69% | 1 | 0 | 0 | 15 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 |  | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34
| 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 100% | 1 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | 104.5% | 1 | -52174 | 0 | 147 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253
| 02 | T2900 | 40392045201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 100 | 392 | 371 | 139% | 0 | 21 | 0 | 0 | 292 | 0 | 869247 | 37251 | 831996 | 869247 | 857258 | 0 | 0 | 0 | 857258 | 857258 | 103% | 1 | 0 | 0 | 173 | 59 | 0 | 0 | 2298 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 2298 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-14 | QTR1 | 24/25 | 216 | 1017097.24
| 02 | T2908 | 44534215201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 250 | 439 | 436 | 101.2% | 1 | 3 | 0 | 0 | 183 | 6 | 7659724 | 70863 | 7588861 | 7761297 | 8108037 | 0 | 0 | 0 | 8108037 | 8070080 | 106.3% | 1 | -37957 | 101573 | 159 | 24 | 0 | 3 | 8735 | 0 | 0 | 3 | 126725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 6 | 135460 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-03-05 | QTR3 | 24/25 |  | 2024-11-13 | QTR2 | 24/25 | 208 | 7157174.01
| 02 | T2909 | 44607915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 250 | 447 | 445 | 99.2% | 1 | 2 | 0 | 0 | 97 | 100 | 7130409 | 68620 | 7061789 | 7130409 | 7454415 | 0 | 0 | 0 | 7454415 | 7438691 | 105.3% | 1 | -15725 | 0 | 129 | 68 | 0 | 0 | 1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 3586 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-09-06 | QTR1 | 24/25 | 208 | 7319755.75
| 02 | T2911 | 44703315201 | 2023-05-17 | QTR4 | 22/23 | 1 | 1 | 260 | 312 | 290 | 91.54% | 1 | 22 | 0 | 0 | 52 | 0 | 5899711 | 60196 | 5839515 | 5916585 | 5921537 | 0 | 0 | 0 | 5921537 | 5926778 | 101.5% | 1 | 5241 | 16874 | 26 | 26 | 0 | 0 | 9350 | 0 | 0 | 0 | 16874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36315 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-07-10 | QTR1 | 24/25 | 214 | 6079797.84
| 02 | T2918 | 43911515201 | 2023-05-17 | QTR4 | 22/23 | 1 | 3 | 300 | 392 | 392 | 103.3% | 1 | 0 | 0 | 0 | 82 | 10 | 8269281 | 96437 | 8172844 | 8404947 | 8393938 | 0 | 0 | 0 | 8393938 | 8396288 | 102.7% | 1 | 2350 | 135667 | 54 | 28 | 0 | 10 | 137623 | 0 | 0 | 0 | 87496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 225119 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 |  | 2024-11-20 | QTR2 | 24/25 | 216 | 9740099
| 02 | T2922 | 44717615201 | 2023-05-17 | QTR4 | 22/23 | 1 | 0 | 200 | 261 | 256 | 97.5% | 1 | 5 | 0 | 0 | 61 | 0 | 4768192 | 52010 | 4716182 | 4768192 | 4978398 | 0 | 0 | 0 | 4978398 | 4983434 | 105.7% | 1 | 5036 | 0 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-07-22 | QTR1 | 24/25 | 214 | 5253038.86
| 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 103.2% | 1 | 19527 | 0 | 41 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 |  | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548
| 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 94.44% | 1 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 99.46% | 1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 |  | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87
| 02 | T2928 | 43195525201 | 2022-08-31 | QTR1 | 22/23 | 2 | 3 | 150 | 307 | 307 | 122.7% | 0 | 0 | 0 | 0 | 123 | 34 | 1070183 | 33534 | 1036649 | 1146536 | 1180671 | 0 | 0 | 0 | 1180671 | 1180315 | 113.9% | 0 | -356 | 76352 | 91 | 32 | 0 | 34 | 76352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 81752 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 |  | 2024-04-02 | QTR4 | 23/24 | 208 | 767498.48
| 02 | T2929 | 44572415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 0 | 150 | 293 | 292 | 99.33% | 1 | 1 | 0 | 0 | 131 | 12 | 2525783 | 50000 | 2475783 | 2525783 | 2526018 | 0 | 0 | 0 | 2526018 | 2526018 | 102% | 1 | 0 | 0 | 123 | 20 | 0 | 0 | 17430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 12 | 17430 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-08 | QTR3 | 24/25 |  | 2024-09-13 | QTR1 | 24/25 | 214 | 2044903
| 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 97.78% | 1 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 93.97% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 |  | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05
| 02 | T2933 | 44105815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 466 | 475 | 162.1% | 0 | -9 | 9 | 0 | 86 | 140 | 10782106 | 108347 | 10673758 | 10551459 | 10447042 | -42921 | 0 | -42921 | 10404121 | 10297505 | 96.47% | 1 | -106616 | -230647 | 57 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 17760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -248407 | 0 | 0 | 140 | -224147 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-02 | QTR3 | 24/25 |  | 2024-07-03 | QTR1 | 24/25 | 209 | 10943081
| 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 93.33% | 1 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 102.2% | 1 | 0 | 0 | 6 | 19 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85
| 02 | T2941 | 44535115201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 250 | 326 | 325 | 104.8% | 1 | 1 | 0 | 0 | 59 | 17 | 12720657 | 150000 | 12570657 | 12720657 | 12835454 | 0 | 0 | 0 | 12835454 | 12775399 | 101.6% | 1 | -60056 | 0 | 54 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-03-06 | QTR3 | 24/25 |  | 2024-11-27 | QTR2 | 24/25 | 208 | 15011207.53
| 02 | T2942 | 44549115201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 180 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 3471985 | 50000 | 3421985 | 3471985 | 3461898 | 0 | 0 | 0 | 3461898 | 3448164 | 100.8% | 1 | -13733 | 0 | 30 | 7 | 0 | 0 | 27958 | 0 | 0 | 0 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41252 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 |  | 2024-08-17 | QTR1 | 24/25 | 214 | 3741501.6
| 02 | T2957 | 44712915201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 164 | 157 | 95.33% | 1 | 7 | 0 | 0 | 14 | 0 | 2432061 | 50000 | 2382061 | 2483046 | 2440068 | 0 | 0 | 0 | 2440068 | 2440833 | 102.5% | 1 | 766 | 50985 | 10 | 4 | 0 | 0 | 2944 | 0 | 0 | 0 | 63883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66827 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 208 | 2377451.33
| 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 99.33% | 1 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 99.93% | 1 | 1123 | 0 | 40 | 24 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4
| 02 | T2964 | 44712615201 | 2024-01-31 | QTR3 | 23/24 | 1 | 1 | 400 | 434 | 132 | 29.25% | 1 | 302 | 0 | 0 | 15 | 19 | 10386249 | 138776 | 10247474 | 11083785 | 10715818 | 0 | 697536 | 697536 | 11413354 | 10715818 | 104.6% | 1 | -697536 | 697536 | 9 | 6 | 0 | 0 | 714402 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 744402 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 |  | 2024-08-02 | QTR1 | 24/25 | 208 | 15260326.27 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 91.18% | 1 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 99.61% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 29 | 42 | 39 | 6576 | 11071 | 10680 | 72.41% | 21 | 391 | 21 | 0 | 3010 | 1485 | 179503683 | 2274056 | 177229626 | 181270118 | 182933994 | -88353 | 697536 | 609183 | 183543177 | 182960106 | 96.55% | 28 | -544888 | 1766436 | 2459 | 991 | 0 | 230 | 1800361 | 9554 | 60 | 472 | 1065551 | 27290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 14725 | 0 | 0 | 4 | 27320 | 11829 | 0 | 0 | 0 | 0 | 488 | 628 | 35455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | -25 | -331662 | 0 | 700 | 1468 | 2611750 | 48673
| 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 185.6% | 0 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 102.5% | 1 | 0 | 630 | 1 | 10 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05
| 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 149% | 0 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 141% | 0 | 0 | 2917973 | 194 | 61 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 |  | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83
| 02 | E20I2 | 43556415201 | 2022-06-08 | QTR4 | 21/22 | 1 | 0 | 550 | 664 | 664 | 102.2% | 1 | 0 | 0 | 0 | 114 | 0 | 742391 | 50000 | 692391 | 742391 | 688386 | 0 | 0 | 0 | 688386 | 688386 | 99.42% | 1 | 0 | 0 | 16 | 86 | 12 | 0 | 23288 | 0 | 0 | 0 | 5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 28813 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-01-10 | QTR3 | 24/25 |  | 2024-09-09 | QTR1 | 24/25 | 214 | 1885001.5
| 02 | E20S3 | 44752515201 | 2022-06-07 | QTR4 | 21/22 | 2 | 3 | 480 | 761 | 756 | 135.6% | 0 | 5 | 0 | 0 | 195 | 86 | 3180291 | 52391 | 3127900 | 2920160 | 2867769 | 0 | 0 | 0 | 2867769 | 2867769 | 91.68% | 1 | 0 | -260131 | 25 | 80 | 90 | 0 | 0 | 0 | 0 | 86 | -260131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 86 | -260131 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 |  | 2024-09-11 | QTR1 | 24/25 | 208 | 6564146.33 | LBDB:LBDB::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 134.3% | 0 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 118.6% | 0 | 1123706 | 3526869 | 109 | 143 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 5 | 11 | 33 | 2240 | 3682 | 3653 | 20% | 1 | 29 | 0 | 0 | 843 | 599 | 36267887 | 406684 | 35861204 | 42453228 | 43242861 | 0 | 0 | 0 | 43242861 | 43278474 | 60% | 3 | 1123706 | 6185341 | 345 | 380 | 102 | 277 | 2130797 | 1770145 | 0 | 309 | 3875877 | 115377 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 73387 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 599 | 6360958 | 2118274
| District 02 Totals |  |  |  |  | 34 | 53 | 72 | 8816 | 14753 | 14333 | 64.71% | 22 | 420 | 21 | 0 | 3853 | 2084 | 215771570 | 2680740 | 213090830 | 223723346 | 226176855 | -88353 | 697536 | 609183 | 226786038 | 226238580 | 91.18% | 31 | 578818 | 7951777 | 2804 | 1371 | 102 | 507 | 3931158 | 1779699 | 60 | 781 | 4941428 | 142667 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 159 | 29309 | 0 | 15 | 4 | 41140 | 13057 | 0 | 0 | 0 | 0 | 494 | 628 | 108842 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 152 | 0 | 0 | 0 | 0 | -25 | -331662 | 0 | 824 | 2067 | 8972708 | 2166947
| 03 | T3690 | 41413265201 | 2021-02-17 | QTR3 | 20/21 | 2 | 3 | 820 | 1163 | 1163 | 108.2% | 1 | 0 | 0 | 0 | 276 | 67 | 15659012 | 142361 | 15516651 | 16135795 | 16181298 | -5000 | 0 | -5000 | 16176298 | 16849377 | 108.6% | 1 | 795630 | 476783 | 155 | 121 | 0 | 67 | 469583 | 0 | 0 | 0 | 54839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7324 | 0 | 0 | 0 | 2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 534429 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-16 | QTR3 | 24/25 |  | 2024-07-10 | QTR1 | 24/25 | 313 | 14312918.46
| 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 154.9% | 0 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | 105.1% | 1 | -6844 | 58046 | 137 | 52 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9
| 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 107% | 1 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | 107.5% | 1 | -68789 | 0 | 292 | 81 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-02 | QTR2 | 24/25 |  | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94
| 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 111.3% | 1 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 102.2% | 1 | 14152 | 1950 | 65 | 29 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 |  | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22
| 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 112.1% | 1 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | 105.5% | 1 | -1180 | 0 | 220 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28
| 03 | T3791 | 43937615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 200 | 290 | 290 | 108% | 1 | 0 | 0 | 0 | 90 | 0 | 2097844 | 0 | 2097844 | 2104355 | 1977895 | 0 | 0 | 0 | 1977895 | 1977939 | 94.28% | 1 | 44 | 6511 | 56 | 18 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-03 | QTR1 | 24/25 | 313 | 2307183.3
| 03 | T3792 | 44117115201 | 2023-04-26 | QTR4 | 22/23 | 1 | 1 | 160 | 225 | 224 | 103.8% | 1 | 1 | 0 | 0 | 65 | 0 | 1248264 | 0 | 1248264 | 1248264 | 1306248 | 0 | 0 | 0 | 1306248 | 1306346 | 104.7% | 1 | 98 | 0 | 39 | 19 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-04-08 | QTR4 | 23/24 | 313 | 1870598.48
| 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 128.9% | 0 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 103.6% | 1 | 107844 | 20899 | 225 | 78 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5529 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95
| 03 | T3806 | 43973315201 | 2022-04-27 | QTR4 | 21/22 | 3 | 0 | 315 | 660 | 659 | 131.4% | 0 | 1 | 0 | 0 | 345 | 0 | 10103368 | 88637 | 10014731 | 10103368 | 10342165 | 0 | 0 | 0 | 10342165 | 10277452 | 102.6% | 1 | -64713 | 0 | 173 | 72 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 |  | 2024-08-14 | QTR1 | 24/25 | 308 | 10842967.81
| 03 | T3813 | 44159315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 300 | 695 | 695 | 112.7% | 1 | 0 | 0 | 0 | 387 | 8 | 6499662 | 61994 | 6437668 | 6674412 | 6885176 | 0 | 0 | 0 | 6885176 | 6899511 | 107.2% | 1 | 14336 | 174750 | 309 | 48 | 75 | 3 | 179623 | 0 | 15 | 5 | 11079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 8 | 190702 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-08 | QTR2 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 308 | 6445150.22
| 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 211.5% | 0 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 102.9% | 1 | 1480 | 10462 | 151 | 96 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75
| 03 | T3815 | 44365115201 | 2022-06-15 | QTR4 | 21/22 | 3 | 1 | 285 | 566 | 566 | 122.8% | 0 | 0 | 0 | 0 | 281 | 0 | 7790941 | 53573 | 7737368 | 8040944 | 8245622 | 0 | 0 | 0 | 8245622 | 8108954 | 104.8% | 1 | -136668 | 250003 | 142 | 74 | 0 | 0 | 0 | 0 | 45 | 0 | 13902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 236102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 250003 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 |  | 2024-05-01 | QTR4 | 23/24 | 308 | 8069731.27
| 03 | T3824 | 43769915201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 330 | 416 | 416 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3559704 | 0 | 3559704 | 3559704 | 3648796 | 0 | 0 | 0 | 3648796 | 3648367 | 102.5% | 1 | -429 | 0 | 58 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-30 | QTR2 | 24/25 |  | 2024-08-28 | QTR1 | 24/25 | 308 | 5711547.02
| 03 | T3826 | 44387715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 90 | 322 | 322 | 100% | 1 | 0 | 0 | 0 | 232 | 0 | 942554 | 49324 | 893230 | 942554 | 927016 | 0 | 0 | 0 | 927016 | 927016 | 103.8% | 1 | 0 | 0 | 187 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-04-03 | QTR4 | 23/24 | 314 | 1043116.04
| 03 | T3829 | 44553915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 300 | 380 | 380 | 105.7% | 1 | 0 | 0 | 0 | 63 | 17 | 12211588 | 124814 | 12086774 | 12181493 | 12519374 | 0 | 0 | 0 | 12519374 | 12516178 | 103.6% | 1 | -3196 | -30095 | 36 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | 14322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30095 | 0 | 0 | 17 | -15773 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-07-25 | QTR1 | 24/25 | 313 | 12606229.06
| 03 | T3831 | 44575915201 | 2023-05-24 | QTR4 | 22/23 | 2 | 2 | 345 | 402 | 400 | 99.42% | 1 | 2 | 0 | 0 | 57 | 0 | 14273753 | 149748 | 14124005 | 14525242 | 15530113 | 0 | 0 | 0 | 15530113 | 15529289 | 109.9% | 1 | -824 | 251489 | 31 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 251489 | 132372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251489 | 132372 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 |  | 2024-11-01 | QTR2 | 24/25 | 321 | 15124579.71
| 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 95.56% | 1 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 98.69% | 1 | 0 | 0 | 52 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 |  | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83
| 03 | T3834 | 44563515201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 270 | 364 | 426 | 115.6% | 1 | -62 | 62 | 0 | 114 | 0 | 19944475 | 150000 | 19794475 | 19944475 | 21545566 | -363010 | 0 | -363010 | 21182556 | 21410083 | 108.2% | 1 | 227527 | 0 | 62 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 |  | 2024-08-14 | QTR1 | 24/25 | 314 | 18371047.42
| 03 | T3842 | 44404015201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 60 | 433 | 424 | 160% | 0 | 9 | 0 | 0 | 373 | 0 | 851756 | 41407 | 810349 | 851756 | 802521 | 0 | 0 | 0 | 802521 | 802521 | 99.03% | 1 | 0 | 0 | 268 | 60 | 45 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 2000 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2024-08-12 | QTR1 | 24/25 | 314 | 869555.5
| 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 113.2% | 1 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | 110.9% | 0 | -37923 | 75924 | 138 | 47 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81
| 03 | T3856 | 44573315201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 166 | 399 | 399 | 114.5% | 1 | 0 | 0 | 0 | 233 | 0 | 6737296 | 71197 | 6666099 | 6737296 | 7134385 | 0 | 0 | 0 | 7134385 | 7124379 | 106.9% | 1 | -10006 | 0 | 152 | 57 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-21 | QTR2 | 24/25 |  | 2024-07-17 | QTR1 | 24/25 | 308 | 7216077.98
| 03 | T3864 | 44562915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 3 | 230 | 347 | 329 | 97.39% | 1 | 18 | 0 | 0 | 105 | 12 | 3480880 | 51096 | 3429784 | 3589639 | 3810464 | 0 | 0 | 0 | 3810464 | 3809861 | 111.1% | 0 | -603 | 108759 | 73 | 32 | 0 | 0 | 12134 | 0 | 0 | 5 | 64017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 44742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 135093 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-08-18 | QTR1 | 24/25 | 308 | 5160701.28
| 03 | T3865 | 43774625201 | 2023-10-25 | QTR2 | 23/24 | 2 | 1 | 200 | 254 | 252 | 99.5% | 1 | 2 | 0 | 0 | 53 | 1 | 6205064 | 84584 | 6120479 | 6251095 | 6519415 | 0 | 0 | 0 | 6519415 | 6478224 | 105.8% | 1 | -41192 | 46032 | 41 | 12 | 0 | 1 | 4597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46032 | 46032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 50628 | 46032 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 |  | 2024-09-25 | QTR1 | 24/25 | 308 | 8476485.74
| 03 | T3869 | 44759115201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 235 | 388 | 388 | 101.3% | 1 | 0 | 0 | 0 | 150 | 3 | 4656452 | 50000 | 4606452 | 4656452 | 4603412 | 0 | 0 | 0 | 4603412 | 4603490 | 99.94% | 1 | 79 | 0 | 106 | 44 | 0 | 3 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 26881 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-13 | QTR3 | 24/25 |  | 2024-11-15 | QTR2 | 24/25 | 313 | 4979086.06
| 03 | T3872 | 43775625201 | 2023-11-15 | QTR2 | 23/24 | 3 | 2 | 325 | 347 | 260 | 67.69% | 1 | 87 | 0 | 0 | 40 | -18 | 7954987 | 104069 | 7850918 | 8031898 | 8038891 | 0 | 0 | 0 | 8038891 | 8021230 | 102.2% | 1 | -17661 | 76912 | 28 | 12 | 0 | 0 | 5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5831 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2025-03-27 | QTR3 | 24/25 |  | 2024-10-07 | QTR2 | 24/25 | 321 | 10589089.88 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 03 | T3875 | 44758815201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 150 | 305 | 305 | 106.7% | 1 | 0 | 0 | 0 | 155 | 0 | 4849503 | 63887 | 4785616 | 4849503 | 5213259 | 0 | 0 | 0 | 5213259 | 5178770 | 108.2% | 1 | -34488 | 0 | 115 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-02-13 | QTR3 | 24/25 |  | 2024-11-13 | QTR2 | 24/25 | 314 | 6479282.38
| 03 | T3877 | 43775715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 1 | 273 | 325 | 320 | 98.17% | 1 | 5 | 0 | 0 | 52 | 0 | 11695437 | 150000 | 11545437 | 11701443 | 12402258 | 0 | 0 | 0 | 12402258 | 12455669 | 107.9% | 1 | 53411 | 6006 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13152 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 321 | 9851819.87
| 03 | T3880 | 43078925201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 135 | 199 | 193 | 95.56% | 1 | 6 | 0 | 0 | 64 | 0 | 3380216 | 54568 | 3325648 | 3380216 | 3471279 | 0 | 0 | 0 | 3471279 | 3471279 | 104.4% | 1 | 0 | 0 | 38 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-08-27 | QTR1 | 24/25 | 314 | 5332275.36
| 03 | T3886 | 45221235201 | 2023-09-13 | QTR1 | 23/24 | 1 | 1 | 109 | 155 | 154 | 99.08% | 1 | 1 | 0 | 0 | 46 | 0 | 1444661 | 50000 | 1394661 | 1521683 | 1385235 | 0 | 0 | 0 | 1385235 | 1385235 | 99.32% | 1 | 0 | 77022 | 22 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-05-02 | QTR4 | 23/24 | 314 | 2325343.9
| 03 | T3889 | 45221225201 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 140 | 184 | 127 | 70% | 1 | 57 | 0 | 0 | 29 | 15 | 1570117 | 50000 | 1520117 | 1689632 | 1597844 | 0 | 0 | 0 | 1597844 | 1597844 | 105.1% | 1 | 0 | 119515 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-05-24 | QTR4 | 23/24 | 313 | 1925284.7
| 03 | T3897 | 44845115201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 165 | 254 | 254 | 101.8% | 1 | 0 | 0 | 0 | 86 | 3 | 1349500 | 50000 | 1299500 | 1349500 | 1300591 | 0 | 0 | 0 | 1300591 | 1300571 | 100.1% | 1 | -20 | 0 | 74 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 3 | 1250 | 0 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-10-29 | QTR2 | 24/25 | 321 | 1617297.75
| 03 | T3921 | 45146315201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 100 | 124 | 123 | 99% | 1 | 1 | 0 | 0 | 24 | 0 | 655998 | 28648 | 627350 | 655998 | 585688 | 0 | 0 | 0 | 585688 | 585688 | 93.36% | 1 | 0 | 0 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2025-02-04 | QTR3 | 24/25 |  | 2024-12-19 | QTR2 | 24/25 | 313 | 605938.95
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 32 | 48 | 31 | 7397 | 13117 | 12984 | 81.25% | 26 | 133 | 62 | 0 | 5528 | 212 | 186638365 | 2033340 | 184605024 | 188369332 | 195538153 | -368010 | 0 | -368010 | 195170143 | 195837654 | 93.75% | 30 | 790065 | 1730968 | 3498 | 1322 | 308 | 109 | 805474 | 0 | 403 | 67 | 738363 | 149223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 49 | 162071 | 0 | 0 | 0 | 48715 | 46032 | 0 | 0 | 0 | 0 | 891 | 0 | 267015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35624 | 0 | 1629 | 225 | 1986012 | 195255
| 03 | E3Q94 | 21787545201 | 2018-06-14 | QTR4 | 17/18 | 1 | 11 | 1325 | 2106 | 2106 | 117.4% | 1 | 0 | 0 | 0 | 767 | 14 | 31708584 | 150000 | 31558584 | 32410332 | 32832992 | 0 | 0 | 0 | 32832992 | 33087185 | 104.8% | 1 | 254193 | 701748 | 414 | 136 | 0 | 0 | 391404 | 0 | 198 | 10 | 243931 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 103110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 14 | 746509 | 56594 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2024-05-21 | QTR4 | 23/24 | 306 | 25965925.9
| 03 | E3T55 | 43974015201 | 2021-03-11 | QTR3 | 20/21 | 1 | 0 | 180 | 335 | 362 | 115% | 1 | -27 | 27 | 0 | 155 | 0 | 5227145 | 50000 | 5177145 | 5227145 | 5328540 | -101412 | 0 | -101412 | 5227128 | 5712178 | 110.3% | 0 | 485050 | 0 | 102 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-02-03 | QTR3 | 24/25 |  | 2022-05-31 | QTR4 | 21/22 | 314 | 4892771.41
| 03 | E3U63 | 43776415201 | 2022-06-09 | QTR4 | 21/22 | 3 | 0 | 455 | 795 | 786 | 119.3% | 1 | 9 | 0 | 0 | 334 | 6 | 7526960 | 90812 | 7436148 | 7526960 | 7541005 | 0 | 0 | 0 | 7541005 | 7382315 | 99.28% | 1 | -158690 | 0 | 137 | 106 | 0 | 1 | 2600 | 0 | 0 | 0 | 6274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 8874 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 |  | 2024-11-15 | QTR2 | 24/25 | 308 | 9579367.88
| 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 111.1% | 1 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | 98.3% | 1 | -13836 | 0 | 46 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 |  | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47
| 03 | E3W06 | 22283255201 | 2024-03-21 | QTR3 | 23/24 | 1 | 0 | 100 | 163 | 144 | 81% | 1 | 19 | 0 | 0 | 63 | 0 | 365234 | 27430 | 337804 | 365234 | 304736 | 0 | 0 | 0 | 304736 | 304736 | 90.21% | 1 | 0 | 0 | 53 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 |  | 2024-11-12 | QTR2 | 24/25 | 313 | 608746.8
| 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 89.78% | 1 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | 102.9% | 1 | -7206 | 0 | 35 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71
| 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 102.7% | 1 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | 104.4% | 1 | -16986 | 26502 | 75 | 28 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 |  | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78
| 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 120% | 1 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | 106.5% | 1 | -70800 | 102687 | 21 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3W67 | 43467115201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 140 | 153 | 144 | 93.57% | 1 | 9 | 0 | 0 | 13 | 0 | 3519862 | 50000 | 3469862 | 3519862 | 3571544 | 0 | 0 | 0 | 3571544 | 3563708 | 102.7% | 1 | -7835 | 0 | 9 | 4 | 0 | 0 | 11460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11460 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 |  | 2024-06-27 | QTR4 | 23/24 | 313 | 4787060.64
| 03 | E3W87 | 44573515201 | 2024-02-08 | QTR3 | 23/24 | 1 | 0 | 150 | 169 | 169 | 100% | 1 | 0 | 0 | 0 | 19 | 0 | 3177069 | 50000 | 3127069 | 3177069 | 3326636 | 0 | 0 | 0 | 3326636 | 3307859 | 105.8% | 1 | -18777 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2025-01-08 | QTR3 | 24/25 |  | 2024-10-31 | QTR2 | 24/25 | 321 | 4084998.81
| 03 | E3W88 | 44575515201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 120 | 128 | 124 | 96.67% | 1 | 4 | 0 | 0 | 8 | 0 | 2175239 | 50000 | 2125239 | 2175239 | 2183626 | 0 | 0 | 0 | 2183626 | 2183626 | 102.7% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-06-21 | QTR4 | 23/24 | 313 | 3085002.9
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 11 | 15 | 15 | 3027 | 4755 | 4725 | 100% | 11 | 30 | 27 | 0 | 1701 | 27 | 68205176 | 668242 | 67536934 | 69036113 | 69821487 | -31412 | 800 | -30612 | 69790875 | 70235988 | 90.91% | 10 | 445113 | 830937 | 905 | 451 | 0 | 1 | 405464 | 0 | 198 | 15 | 276707 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2 | 224910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371 | 22 | 915145 | 56594
| District 03 Totals |  |  |  |  | 43 | 63 | 46 | 10424 | 17872 | 17709 | 86.05% | 37 | 163 | 89 | 0 | 7229 | 239 | 254843541 | 2701582 | 252141958 | 257405445 | 265359640 | -399422 | 800 | -398622 | 264961018 | 266073642 | 93.02% | 40 | 1235178 | 2561905 | 4403 | 1773 | 308 | 110 | 1210938 | 0 | 601 | 82 | 1015070 | 205817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 51 | 386981 | 0 | 0 | 0 | 48715 | 46032 | 0 | 0 | 0 | 0 | 933 | 4 | 275078 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35624 | 0 | 2000 | 247 | 2901157 | 251849
| 04 | T4434 | 23144025201 | 2016-06-15 | QTR4 | 15/16 | 1 | 19 | 1200 | 1859 | 1859 | 132.3% | 0 | 0 | 0 | 0 | 338 | 321 | 26848292 | 150000 | 26698292 | 32229320 | 31919676 | 0 | 0 | 0 | 31919676 | 32107031 | 120.3% | 0 | 313643 | 5381029 | 173 | 98 | 0 | 16 | 190342 | 117524 | 0 | 70 | 1074932 | 603111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61803 | 0 | 0 | 0 | 1485 | 1485 | 0 | 0 | 0 | 0 | 8 | 0 | 76369 | 0 | 0 | 235 | 4001328 | 3287359 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22536 | 0 | 75 | 321 | 5383723 | 4009479 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 |  | 2021-12-09 | QTR2 | 21/22 | 408 | 25701172.49 | B1 | ACC - NO EXCUSE BONUS
| 04 | T4472 | 41934525201 | 2018-01-31 | QTR3 | 17/18 | 2 | 10 | 1049 | 1423 | 1423 | 110.6% | 1 | 0 | 0 | 0 | 263 | 111 | 33359900 | 182880 | 33177020 | 33746993 | 33295065 | 0 | -75000 | -75000 | 33220065 | 33597249 | 101.3% | 1 | 421739 | 387093 | 176 | 87 | 0 | 0 | 456573 | 0 | 0 | 0 | -143555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188 | 0 | 0 | 71 | 56466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32197 | 0 | 0 | 40 | 81324 | 79113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 484193 | 79113 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 |  | 2022-06-22 | QTR4 | 21/22 | 409 | 37475055.58 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 106.9% | 1 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 104.5% | 1 | 598393 | 791712 | 277 | 92 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 107% | 1 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 101.3% | 1 | 96348 | 120572 | 150 | 38 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73
| 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 105.2% | 1 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 104% | 1 | 165689 | 877092 | 127 | 55 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 04 | T4595 | 43206685201 | 2022-01-26 | QTR3 | 21/22 | 3 | 7 | 473 | 814 | 814 | 146.3% | 0 | 0 | 0 | 0 | 122 | 219 | 11281680 | 104975 | 11176705 | 11586874 | 11564646 | 0 | 0 | 0 | 11564646 | 11487612 | 102.8% | 1 | 69618 | 305194 | 81 | 41 | 42 | 99 | 165355 | 0 | 0 | 14 | 264275 | 20193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 147865 | 0 | 0 | 0 | 16221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -205740 | 0 | 42 | 219 | 400610 | 20193 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 |  | 2024-10-17 | QTR2 | 24/25 | 412 | 11191546.92
| 04 | T4596 | 43206695201 | 2022-01-26 | QTR3 | 21/22 | 3 | 2 | 426 | 868 | 918 | 181.2% | 0 | -50 | 50 | 0 | 220 | 222 | 8895418 | 83586 | 8811831 | 8898040 | 8723470 | -189300 | 0 | -189300 | 8534170 | 8790513 | 99.76% | 1 | 258966 | 2623 | 95 | 51 | 65 | 0 | 3300 | 0 | 9 | 0 | 16427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 2623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 222 | 22349 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-03-24 | QTR3 | 24/25 |  | 2024-11-08 | QTR2 | 24/25 | 412 | 8602890.25
| 04 | T4598 | 44399615201 | 2022-02-23 | QTR3 | 21/22 | 3 | 6 | 425 | 607 | 607 | 111.8% | 1 | 0 | 0 | 0 | 160 | 22 | 5606708 | 50000 | 5556708 | 5800857 | 5331108 | 0 | 0 | 0 | 5331108 | 5358143 | 96.43% | 1 | 30705 | 194148 | 85 | 47 | 0 | 0 | 0 | 0 | 28 | 22 | 190479 | 189820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 22 | 194148 | 189820 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 |  | 2024-04-23 | QTR4 | 23/24 | 408 | 4811998.96
| 04 | T4599 | 43177045201 | 2022-02-23 | QTR3 | 21/22 | 4 | 3 | 385 | 566 | 565 | 99.74% | 1 | 1 | 0 | 0 | 181 | 0 | 6578249 | 66251 | 6511998 | 6638837 | 6561389 | 0 | 0 | 0 | 6561389 | 6682743 | 102.6% | 1 | 122865 | 60588 | 135 | 46 | 0 | 0 | 17342 | 0 | 0 | 0 | 75216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98639 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 |  | 2024-01-26 | QTR3 | 23/24 | 412 | 7009923.45
| 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 99.55% | 1 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | 89.01% | 1 | -16159 | 0 | 189 | 25 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07
| 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 99.64% | 1 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | 95.5% | 1 | -46640 | -1370 | 123 | 27 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21
| 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 99.46% | 1 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | 108.4% | 1 | -15706 | 258794 | 122 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 259680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259680 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 |  | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38
| 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 94.62% | 1 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 98.41% | 1 | 69 | 0 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03
| 04 | T4619 | 44617715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 2 | 331 | 472 | 468 | 116% | 1 | 4 | 0 | 0 | 141 | 0 | 7958317 | 91207 | 7867110 | 8109946 | 8174515 | 0 | 0 | 0 | 8174515 | 8136642 | 103.4% | 1 | -37873 | 151628 | 54 | 30 | 0 | 0 | 21328 | 0 | 57 | 0 | 198554 | 106628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 219883 | 106628 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 |  | 2024-11-26 | QTR2 | 24/25 | 409 | 9211938.74
| 04 | T4624 | 43783245201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 490 | 619 | 619 | 100% | 1 | 0 | 0 | 0 | 144 | -15 | 12698955 | 150000 | 12548955 | 12584827 | 12539323 | 0 | 0 | 0 | 12539323 | 12387135 | 98.71% | 1 | -152188 | -114128 | 89 | 40 | 15 | 0 | 0 | 0 | 0 | 0 | 190110 | 0 | 0 | 0 | 7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7692 | 0 | 0 | 0 | 76937 | 43890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | -306645 | 0 | 15 | -15 | -24439 | 43890 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-03-10 | QTR3 | 24/25 |  | 2024-12-11 | QTR2 | 24/25 | 412 | 16805865.3
| 04 | T4625 | 44175515201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 234 | 458 | 458 | 100% | 1 | 0 | 0 | 0 | 224 | 0 | 3558974 | 50000 | 3508974 | 3558974 | 3328234 | 0 | 0 | 0 | 3328234 | 3328234 | 94.85% | 1 | 0 | 0 | 194 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 18044 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 |  | 2024-10-30 | QTR2 | 24/25 | 409 | 3996955.76
| 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 115% | 1 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | 102.4% | 1 | -3717 | 0 | 63 | 21 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19
| 04 | T4636 | 44384415201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 194 | 305 | 305 | 100% | 1 | 0 | 0 | 0 | 111 | 0 | 798900 | 41899 | 757001 | 798900 | 732677 | 0 | 0 | 0 | 732677 | 732677 | 96.79% | 1 | 0 | 0 | 86 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-06-28 | QTR4 | 23/24 | 412 | 879882.26
| 04 | T4637 | 44359115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 245 | 319 | 319 | 100% | 1 | 0 | 0 | 0 | 74 | 0 | 2144351 | 50000 | 2094351 | 2144351 | 2073909 | 0 | 50000 | 50000 | 2123909 | 2068781 | 98.78% | 1 | -55128 | 0 | 58 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 30506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30506 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-17 | QTR3 | 24/25 |  | 2024-08-06 | QTR1 | 24/25 | 412 | 2377316.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 101.8% | 1 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | 106% | 1 | -4475 | 625462 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 |  | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33
| 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 103.5% | 1 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | 88% | 1 | -344 | 16863 | 37 | 25 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 |  | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99
| 04 | T4644 | 44610915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 4 | 284 | 422 | 422 | 103.2% | 1 | 0 | 0 | 0 | 138 | 2 | 6184480 | 55128 | 6129352 | 6236790 | 6263543 | 0 | 0 | 0 | 6263543 | 6218472 | 101.5% | 1 | -29786 | 56272 | 88 | 41 | 3 | 0 | 0 | 0 | 0 | 0 | 37015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 37015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-25 | QTR3 | 24/25 |  | 2025-01-14 | QTR3 | 24/25 | 408 | 5567898.79
| 04 | T4647 | 44699815201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 80 | 133 | 129 | 95% | 1 | 4 | 0 | 0 | 53 | 0 | 555556 | 31410 | 524146 | 555556 | 522780 | 0 | 0 | 0 | 522780 | 522780 | 99.74% | 1 | 0 | 0 | 47 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-10-30 | QTR2 | 24/25 | 412 | 659609.7
| 04 | T4678 | 45222615201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 79 | 101 | 86 | 81.01% | 1 | 15 | 0 | 0 | 22 | 0 | 654155 | 39867 | 614288 | 654155 | 630879 | 0 | 0 | 0 | 630879 | 630879 | 102.7% | 1 | 0 | 0 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 |  | 2024-09-03 | QTR1 | 24/25 | 409 | 832301.65
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 24 | 48 | 98 | 9994 | 14745 | 14751 | 87.5% | 21 | -6 | 50 | 0 | 3760 | 1025 | 223034345 | 1886347 | 221147998 | 231928505 | 229007196 | -189300 | -25000 | -214300 | 228792896 | 229868429 | 95.83% | 23 | 1716019 | 9113572 | 2514 | 909 | 126 | 190 | 2400175 | 718182 | 160 | 132 | 3294015 | 1036620 | 0 | 0 | 9888 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 20 | 338 | 614609 | 0 | 6 | 71 | 167131 | 46416 | 0 | 0 | 0 | 0 | 307 | 0 | 374348 | 0 | 0 | 275 | 4185297 | 3366472 | 67 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | -15 | -534921 | 0 | 686 | 991 | 9572473 | 5403016
| 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 99.71% | 1 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 103.9% | 1 | 5349446 | 3618986 | 181 | 112 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | 0 | -48896 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B8:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 04 | E4U89 | 43793425201 | 2021-05-21 | QTR4 | 20/21 | 1 | 7 | 642 | 921 | 914 | 107.3% | 1 | 7 | 0 | 0 | 309 | -30 | 8845801 | 82577 | 8763224 | 9316076 | 9449453 | 0 | 0 | 0 | 9449453 | 9527705 | 108.7% | 1 | 272009 | 470275 | 174 | 51 | 84 | 0 | 11055 | 0 | 0 | 0 | 525575 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 0 | 0 | 84 | -30 | 540229 | 5610 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-10 | QTR2 | 24/25 |  | 2024-05-31 | QTR4 | 23/24 | 412 | 8524313.34
| 04 | E4V48 | 44346115201 | 2022-05-06 | QTR4 | 21/22 | 2 | 0 | 719 | 771 | 539 | 67.73% | 1 | 232 | 0 | 0 | 52 | 0 | 6383851 | 97993 | 6285858 | 6383851 | 5949070 | 0 | 0 | 0 | 5949070 | 5949070 | 94.64% | 1 | 0 | 0 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 412 | 10090648.24
| 04 | E4V49 | 44399515201 | 2021-12-03 | QTR2 | 21/22 | 2 | 10 | 320 | 523 | 523 | 119.7% | 1 | 0 | 0 | 0 | 176 | 27 | 5064095 | 50000 | 5014095 | 5491766 | 5407331 | 0 | 0 | 0 | 5407331 | 5458407 | 108.9% | 1 | 58735 | 427672 | 109 | 31 | 0 | -28 | 224222 | 167454 | 0 | 2 | 221257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20173 | 0 | 0 | 0 | 5879 | 5879 | 0 | 0 | 0 | 0 | 53 | 53 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 27 | 479190 | 173333 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-24 | QTR2 | 24/25 |  | 2023-12-29 | QTR2 | 23/24 | 408 | 4246638.67
| 04 | E4V50 | 43975915201 | 2022-09-02 | QTR1 | 22/23 | 1 | 2 | 246 | 338 | 338 | 111.4% | 1 | 0 | 0 | 0 | 92 | 0 | 2437437 | 50000 | 2387437 | 2522997 | 2472614 | 0 | 0 | 0 | 2472614 | 2469346 | 103.4% | 1 | -3268 | 85560 | 39 | 25 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 |  | 2024-06-28 | QTR4 | 23/24 | 409 | 2462556.03
| 04 | E4V74 | 43975415201 | 2022-03-04 | QTR3 | 21/22 | 2 | 6 | 220 | 364 | 364 | 111.4% | 1 | 0 | 0 | 0 | 119 | 25 | 2591421 | 50000 | 2541421 | 2746776 | 2777528 | 0 | 0 | 0 | 2777528 | 2779572 | 109.4% | 1 | 2044 | 155355 | 86 | 33 | 0 | 24 | 94773 | 0 | 0 | 0 | 86949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 181722 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-31 | QTR3 | 24/25 |  | 2023-11-08 | QTR2 | 23/24 | 408 | 2367933.4
| 04 | E4V97 | 44175915201 | 2022-11-04 | QTR2 | 22/23 | 1 | 0 | 128 | 325 | 323 | 116.4% | 1 | 2 | 0 | 0 | 197 | 0 | 3019043 | 50000 | 2969043 | 3019043 | 2884719 | 0 | 0 | 0 | 2884719 | 2884627 | 97.16% | 1 | -92 | 0 | 151 | 23 | 0 | 0 | 0 | 0 | 23 | 0 | 18308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 18308 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-11-08 | QTR2 | 24/25 |  | 2024-08-02 | QTR1 | 24/25 | 412 | 2305583.22
| 04 | E4W07 | 44359015201 | 2022-05-27 | QTR4 | 21/22 | 2 | 4 | 421 | 763 | 762 | 111.4% | 1 | 1 | 0 | 0 | 317 | 25 | 9977382 | 93560 | 9883822 | 10834234 | 10461717 | 0 | 0 | 0 | 10461717 | 10387691 | 105.1% | 1 | -74027 | 1343307 | 234 | 59 | 0 | 0 | 23575 | 0 | 0 | 25 | 888872 | 87905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 7341 | 0 | 0 | 0 | 2564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 25 | 922352 | 87905 | F461192152 | UAG CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 |  | 2024-12-10 | QTR2 | 24/25 | 409 | 11240081.43
| 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 106.3% | 1 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | 98.31% | 1 | -11187 | 50772 | 14 | 24 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12
| 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 113.8% | 1 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | 107.4% | 1 | -2567 | 41751 | 27 | 16 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 |  | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49
| 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | 118.6% | 1 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | 87.58% | 1 | -43330 | 0 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 |  | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65
| 04 | E4W49 | 44637115201 | 2023-07-07 | QTR1 | 23/24 | 1 | 1 | 244 | 257 | 198 | 75.82% | 1 | 59 | 0 | 0 | 13 | 0 | 4434511 | 55240 | 4379271 | 4502024 | 4183947 | 0 | 0 | 0 | 4183947 | 4189012 | 95.66% | 1 | 5065 | 67513 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 412 | 5579255.71
| 04 | E4W50 | 44610715201 | 2023-03-03 | QTR3 | 22/23 | 1 | 1 | 243 | 455 | 455 | 116.5% | 1 | 0 | 0 | 0 | 212 | 0 | 2849827 | 50000 | 2799827 | 2874613 | 2894545 | 0 | 0 | 0 | 2894545 | 2891318 | 103.3% | 1 | -3227 | 24785 | 139 | 33 | 0 | 0 | 0 | 0 | 40 | 0 | 24785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 24785 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 |  | 2024-11-13 | QTR2 | 24/25 | 408 | 2610595.11
| 04 | E4W58 | 44004615201 | 2023-05-05 | QTR4 | 22/23 | 1 | 2 | 175 | 210 | 210 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2786872 | 50000 | 2736872 | 2833359 | 2656902 | 0 | 0 | 0 | 2656902 | 2656977 | 97.08% | 1 | 75 | 46486 | 31 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 46486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46486 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 |  | 2024-07-30 | QTR1 | 24/25 | 409 | 2491562.11
| 04 | E4W68 | 44619815201 | 2023-09-01 | QTR1 | 23/24 | 2 | 0 | 124 | 195 | 183 | 90.32% | 1 | 12 | 0 | 0 | 71 | 0 | 1533318 | 50000 | 1483318 | 1533318 | 1448228 | 0 | 0 | 0 | 1448228 | 1445431 | 97.45% | 1 | -2797 | 0 | 63 | 8 | 0 | 0 | 6276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6276 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 |  | 2024-10-15 | QTR2 | 24/25 | 412 | 1669882.03
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 15 | 24 | 65 | 5479 | 7593 | 7289 | 100% | 15 | 304 | 30 | 0 | 2067 | 47 | 204600888 | 979370 | 203621518 | 210405145 | 209843906 | -50970 | 1375000 | 1324030 | 211167936 | 210742816 | 100% | 15 | 5546879 | 6332462 | 1306 | 468 | 84 | -4 | 2419053 | 376544 | 91 | 27 | 2686202 | 146572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 719611 | 33779 | 0 | 0 | 177106 | 329064 | 0 | 0 | 0 | 0 | 207 | 53 | 101917 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 0 | -30 | -48896 | 0 | 448 | 47 | 6095823 | 926789
| District 04 Totals |  |  |  |  | 39 | 72 | 163 | 15473 | 22338 | 22040 | 92.31% | 36 | 298 | 80 | 0 | 5827 | 1072 | 427635233 | 2865717 | 424769516 | 442333650 | 438851102 | -240270 | 1350000 | 1109730 | 439960832 | 440611245 | 97.44% | 38 | 7262898 | 15446034 | 3820 | 1377 | 210 | 186 | 4819228 | 1094726 | 251 | 159 | 5980217 | 1183192 | 0 | 0 | 9888 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 61 | 339 | 1334220 | 33779 | 6 | 71 | 344237 | 375480 | 0 | 0 | 0 | 0 | 514 | 53 | 476265 | 0 | 0 | 275 | 4185297 | 3366472 | 92 | 0 | 276156 | 276156 | 0 | 0 | 0 | 0 | 0 | -45 | -583817 | 0 | 1134 | 1038 | 15668296 | 6329805
| 05 | T5721 | 44287515201 | 2021-12-08 | QTR2 | 21/22 | 3 | 7 | 510 | 817 | 805 | 107.5% | 1 | 12 | 0 | 0 | 257 | 50 | 16561765 | 150000 | 16411765 | 17284645 | 18223735 | 0 | 0 | 0 | 18223735 | 18736509 | 114.2% | 0 | 519720 | 722880 | 198 | 59 | 0 | 30 | 59072 | 0 | 0 | 0 | 671912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455 | 0 | 0 | 0 | 4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 743980 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-27 | QTR1 | 24/25 | 515 | 18568888.72
| 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 136.5% | 0 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | 101.3% | 1 | -57178 | 154746 | 45 | 50 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34
| 05 | T5728 | 44395815201 | 2021-08-25 | QTR1 | 21/22 | 6 | 5 | 600 | 848 | 847 | 99.83% | 1 | 1 | 0 | 0 | 248 | 0 | 34500000 | 150000 | 34350000 | 35703756 | 38083377 | -5932 | -11806 | -17738 | 38065638 | 39383079 | 114.7% | 0 | 1397410 | 1203756 | 187 | 61 | 0 | 0 | 557100 | 0 | 0 | 0 | 507869 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207739 | 292167 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 |  | 2024-03-15 | QTR3 | 23/24 | 509 | 32771897.49
| 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 108.3% | 1 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | 104.9% | 1 | -94902 | 39287 | 76 | 80 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3
| 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 155.3% | 0 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | 108.8% | 1 | -1791 | 104943 | 39 | 114 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8
| 05 | T5743 | 43793515201 | 2022-02-23 | QTR3 | 21/22 | 4 | 5 | 350 | 693 | 693 | 135.1% | 0 | 0 | 0 | 0 | 220 | 123 | 4388956 | 50000 | 4338956 | 6723005 | 6937593 | 0 | 0 | 0 | 6937593 | 6933746 | 159.8% | 0 | -730 | 2334049 | 126 | 94 | 0 | 90 | 2279264 | 0 | 0 | 20 | 71667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 2351482 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 |  | 2024-10-28 | QTR2 | 24/25 | 513 | 4734607.56
| 05 | T5745 | 43219355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 6 | 560 | 621 | 621 | 102.7% | 1 | 0 | 0 | 0 | 46 | 15 | 7356536 | 82000 | 7274536 | 7830549 | 7924589 | 0 | 0 | 0 | 7924589 | 7872250 | 108.2% | 1 | -50996 | 474013 | 12 | 34 | 0 | 0 | 475337 | 0 | 0 | 0 | 39899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516578 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 |  | 2024-07-19 | QTR1 | 24/25 | 509 | 10192519.21
| 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | 100.7% | 1 | -1484 | 793 | 94 | 10 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4
| 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 98.24% | 1 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | 104.6% | 1 | -515 | 40000 | 128 | 27 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 |  | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1
| 05 | T5764 | 44581315201 | 2022-10-05 | QTR2 | 22/23 | 3 | 2 | 260 | 438 | 434 | 98.46% | 1 | 4 | 0 | 0 | 178 | 0 | 2470270 | 88750 | 2381520 | 2521141 | 2333135 | 0 | 0 | 0 | 2333135 | 2331897 | 97.92% | 1 | -1237 | 50871 | 138 | 40 | 0 | 0 | 7077 | 0 | 0 | 0 | 26123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40811 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 |  | 2024-09-20 | QTR1 | 24/25 | 514 | 2317408.58
| 05 | T5767 | 44101615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 4 | 500 | 613 | 470 | 71.4% | 1 | 143 | 0 | 0 | 113 | 0 | 10858007 | 107000 | 10751007 | 11031557 | 11200282 | -5737 | 0 | -5737 | 11194546 | 11153083 | 103.7% | 1 | -41463 | 173550 | 82 | 31 | 0 | 0 | 22533 | 0 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28633 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-09-21 | QTR1 | 24/25 | 514 | 11024234.24
| 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 92.67% | 1 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | 101% | 1 | -18 | 2618 | 7 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306
| 05 | T5772 | 44569315201 | 2022-10-26 | QTR2 | 22/23 | 2 | 4 | 260 | 406 | 403 | 98.85% | 1 | 3 | 0 | 0 | 146 | 0 | 1859536 | 50000 | 1809536 | 1934513 | 2110697 | 0 | 0 | 0 | 2110697 | 2104981 | 116.3% | 0 | -360 | 74977 | 110 | 36 | 0 | 0 | 2993 | 0 | 0 | 0 | 30505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33497 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 |  | 2024-06-18 | QTR4 | 23/24 | 509 | 1660927.9
| 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 98% | 1 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | 106.3% | 1 | -22 | 0 | 26 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25
| 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 103.9% | 1 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | 93.31% | 1 | -1198 | 1419 | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 |  | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55
| 05 | T5783 | 44576715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 230 | 286 | 283 | 98.7% | 1 | 3 | 0 | 0 | 56 | 0 | 2041154 | 50000 | 1991154 | 2041154 | 2088238 | -10982 | 0 | -10982 | 2077256 | 2076683 | 104.3% | 1 | -573 | 0 | 37 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-07-31 | QTR1 | 24/25 | 509 | 1415550.25
| 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 99.29% | 1 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 101.9% | 1 | 0 | -21976 | 9 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 |  | 2024-07-01 | QTR1 | 24/25 | 515 | 919900
| 05 | T5803 | 44760315201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 130 | 188 | 188 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 1608172 | 50000 | 1558172 | 1608172 | 1619759 | 0 | 0 | 0 | 1619759 | 1619759 | 104% | 1 | 0 | 0 | 48 | 10 | 0 | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12510 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2025-03-04 | QTR3 | 24/25 |  | 2024-11-14 | QTR2 | 24/25 | 512 | 1561950.34
| 05 | T5820 | 45222925201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 120 | 133 | 85 | 60% | 1 | 48 | 0 | 0 | 13 | 0 | 607569 | 43750 | 563819 | 607569 | 467724 | 0 | 0 | 0 | 467724 | 467724 | 82.96% | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-06-06 | QTR4 | 23/24 | 513 | 1006632.6
| 05 | T5821 | 45222935201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 110 | 115 | 108 | 93.64% | 1 | 7 | 0 | 0 | 5 | 0 | 843345 | 50000 | 793345 | 843345 | 748398 | 0 | 0 | 0 | 748398 | 748398 | 94.33% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-11 | QTR2 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 512 | 1601075
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 20 | 43 | 48 | 5620 | 8300 | 8041 | 85% | 17 | 259 | 0 | 0 | 2250 | 430 | 109564689 | 1325500 | 108239189 | 114920616 | 118794745 | -22651 | -11806 | -34457 | 118760288 | 120319528 | 80% | 16 | 1664663 | 5355926 | 1373 | 848 | 0 | 120 | 3569374 | 0 | 0 | 218 | 1519090 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 65686 | 0 | 0 | 0 | 37718 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 135009 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 353 | 5304901 | 292167
| 05 | E50B7 | 44519015201 | 2023-03-22 | QTR3 | 22/23 | 2 | 3 | 200 | 318 | 316 | 109.5% | 1 | 2 | 0 | 0 | 97 | 21 | 5675430 | 50000 | 5625430 | 5781935 | 5808256 | 0 | 0 | 0 | 5808256 | 5808213 | 103.2% | 1 | -42 | 106505 | 73 | 24 | 0 | 21 | 81505 | 0 | 0 | 0 | 1396 | 1396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 109568 | 1396 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-07 | QTR3 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 515 | 4958774.67
| 05 | E50B9 | 44530415201 | 2022-11-01 | QTR2 | 22/23 | 2 | 2 | 360 | 618 | 616 | 104.2% | 1 | 2 | 0 | 0 | 241 | 17 | 8212061 | 78500 | 8133561 | 8298265 | 8545900 | 0 | 0 | 0 | 8545900 | 8501569 | 104.5% | 1 | -33727 | 86204 | 142 | 99 | 0 | 5 | 52398 | 0 | 0 | 12 | 78440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 141442 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-04 | QTR3 | 24/25 |  | 2024-10-18 | QTR2 | 24/25 | 515 | 8347740.25
| 05 | E50F0 | 44985615201 | 2024-01-04 | QTR3 | 23/24 | 1 | 0 | 145 | 171 | 170 | 99.31% | 1 | 1 | 0 | 0 | 26 | 0 | 512012 | 33532 | 478480 | 512012 | 459051 | 0 | 0 | 0 | 459051 | 459051 | 95.94% | 1 | 0 | 0 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 |  | 2024-09-20 | QTR1 | 24/25 | 515 | 709684.5
| 05 | E50F8 | 45056015201 | 2024-02-06 | QTR3 | 23/24 | 1 | 1 | 99 | 127 | 126 | 98.99% | 1 | 1 | 0 | 0 | 28 | 0 | 265206 | 8549 | 256657 | 286124 | 270632 | 0 | 0 | 0 | 270632 | 270632 | 105.4% | 1 | 0 | 20918 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 |  | 2024-12-06 | QTR2 | 24/25 | 514 | 184540.3
| 05 | E51A5 | 44102115201 | 2020-08-04 | QTR1 | 20/21 | 1 | 3 | 340 | 431 | 430 | 99.71% | 1 | 1 | 0 | 0 | 91 | 0 | 6379293 | 53300 | 6325993 | 6413111 | 6544055 | 0 | 0 | 0 | 6544055 | 6599601 | 104.3% | 1 | 58191 | 33818 | 63 | 28 | 0 | 0 | 39765 | 0 | 0 | 0 | 33443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79708 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-01-07 | QTR3 | 24/25 |  | 2022-03-09 | QTR3 | 21/22 | 509 | 5366278.89
| 05 | E52B5 | 44892215201 | 2022-11-01 | QTR2 | 22/23 | 1 | 1 | 227 | 362 | 438 | 159.5% | 0 | -76 | 76 | 0 | 76 | 59 | 1894138 | 50000 | 1844138 | 1894138 | 1942917 | -13063 | 0 | -13063 | 1929854 | 1929854 | 104.6% | 1 | 0 | 0 | 24 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274499988 | UNDERWATER MECHANIX SERVICES LL | N/A | N/A | N/A | N/A | 2025-02-12 | QTR3 | 24/25 |  | 2024-06-20 | QTR4 | 23/24 | 513 | 2335390.2
| 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 94.32% | 1 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 99.36% | 1 | 0 | 7099 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 |  | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844
| 05 | E55B6 | 44935915201 | 2022-12-06 | QTR2 | 22/23 | 3 | 2 | 160 | 265 | 263 | 111.9% | 1 | 2 | 0 | 0 | 84 | 21 | 1222662 | 50000 | 1172662 | 1249746 | 1348640 | 0 | 0 | 0 | 1348640 | 1330056 | 113.4% | 0 | 0 | 27084 | 37 | 47 | 0 | 0 | 4402 | 0 | 0 | 0 | 36173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40575 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 |  | 2024-11-21 | QTR2 | 24/25 | 513 | 1969965.2
| 05 | E56A6 | 43585935201 | 2021-09-08 | QTR1 | 21/22 | 3 | 4 | 700 | 1022 | 1022 | 104.6% | 1 | 0 | 0 | 0 | 322 | 0 | 26294705 | 150000 | 26144705 | 26513733 | 26091334 | 0 | 0 | 0 | 26091334 | 26689837 | 102.1% | 1 | 646783 | 219028 | 172 | 118 | 14 | 0 | 215010 | 35852 | 12 | 0 | 22391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52360 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 298302 | 35852 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-19 | QTR3 | 24/25 |  | 2024-08-19 | QTR1 | 24/25 | 515 | 25307967.68
| 05 | E56B1 | 44892415201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 100 | 107 | 74 | 67% | 1 | 33 | 0 | 0 | 7 | 0 | 284414 | 17010 | 267404 | 284414 | 279401 | 0 | 0 | 0 | 279401 | 279401 | 104.5% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 |  | 2024-06-24 | QTR4 | 23/24 | 512 | 357218.5
| 05 | E56B5 | 44520815201 | 2023-02-09 | QTR3 | 22/23 | 2 | 4 | 290 | 514 | 522 | 104.5% | 1 | -8 | 8 | 0 | 219 | 5 | 4388512 | 52000 | 4336512 | 4453426 | 4571799 | 0 | 0 | 0 | 4571799 | 4544333 | 104.8% | 1 | -17160 | 64913 | 121 | 98 | 0 | 0 | 0 | 0 | 0 | 5 | 60395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 60395 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-05 | QTR3 | 24/25 |  | 2025-01-10 | QTR3 | 24/25 | 513 | 5307734.85
| 05 | E56B7 | 44852015201 | 2023-02-09 | QTR3 | 22/23 | 2 | 1 | 300 | 377 | 377 | 100% | 1 | 0 | 0 | 0 | 77 | 0 | 3806259 | 50000 | 3756259 | 3806259 | 3824085 | 0 | 0 | 0 | 3824085 | 3824085 | 101.8% | 1 | 0 | 0 | 45 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 |  | 2024-08-19 | QTR1 | 24/25 | 509 | 4832736.89
| 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 60.8% | 1 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 100% | 1 | 0 | 0 | 24 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 |  | 2024-04-11 | QTR4 | 23/24 | 507 | 801387
| 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 101.1% | 1 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | 103.3% | 1 | -144 | 0 | 29 | 48 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 |  | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35
| 05 | E57B9 | 44709915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 260 | 337 | 337 | 100% | 1 | 0 | 0 | 0 | 77 | 0 | 7890001 | 88000 | 7802001 | 7890001 | 8013155 | 0 | 0 | 0 | 8013155 | 8041936 | 103.1% | 1 | 28780 | 0 | 52 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 514 | 9077031.16
| 05 | E58A3 | 44288315201 | 2022-05-03 | QTR4 | 21/22 | 2 | 6 | 250 | 598 | 598 | 118% | 1 | 0 | 0 | 0 | 303 | 45 | 4049477 | 50000 | 3999477 | 4613851 | 4761016 | 0 | 0 | 0 | 4761016 | 4731574 | 118.3% | 0 | -29441 | 564374 | 230 | 73 | 0 | 0 | 15531 | 0 | 0 | 45 | 414568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 434074 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-12-26 | QTR2 | 24/25 |  | 2024-09-25 | QTR1 | 24/25 | 514 | 4247697.07
| 05 | E58B0 | 44878915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 2 | 170 | 213 | 213 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 2634873 | 50000 | 2584873 | 2681332 | 2729605 | 0 | 0 | 0 | 2729605 | 2729605 | 105.6% | 1 | 0 | 46460 | 31 | 12 | 0 | 0 | 7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7002 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 |  | 2024-08-01 | QTR1 | 24/25 | 509 | 1708500.26
| 05 | E58B9 | 45050715201 | 2023-04-04 | QTR4 | 22/23 | 2 | 0 | 160 | 337 | 336 | 99.38% | 1 | 1 | 0 | 0 | 147 | 30 | 2493493 | 50000 | 2443493 | 2493493 | 2516855 | 0 | 0 | 0 | 2516855 | 2516855 | 103% | 1 | 0 | 0 | 123 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 |  | 2024-08-30 | QTR1 | 24/25 | 515 | 2557573.29
| 05 | E59B1 | 44521215201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 280 | 381 | 381 | 100% | 1 | 0 | 0 | 0 | 101 | 0 | 5421862 | 54000 | 5367862 | 5450128 | 5275721 | 0 | 0 | 0 | 5275721 | 5273757 | 98.25% | 1 | -1964 | 28266 | 39 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 |  | 2024-11-16 | QTR2 | 24/25 | 512 | 5678330.57
| 05 | E59B7 | 44290715201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 250 | 360 | 360 | 100% | 1 | 0 | 0 | 0 | 110 | 0 | 7869434 | 99500 | 7769934 | 8074202 | 8845045 | 0 | 0 | 0 | 8845045 | 8849151 | 113.9% | 0 | 4106 | 204768 | 60 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 |  | 2024-09-25 | QTR1 | 24/25 | 513 | 10565451.33
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 20 | 32 | 33 | 4966 | 7432 | 7403 | 95% | 19 | 29 | 84 | 0 | 2266 | 200 | 94208454 | 1122552 | 93085902 | 95617891 | 96658872 | -13063 | 0 | -13063 | 96645809 | 97203672 | 85% | 17 | 655382 | 1409437 | 1344 | 920 | 14 | 26 | 428813 | 35852 | 12 | 64 | 658732 | 1396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 10541 | 0 | 0 | 0 | 26666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66939 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 90 | 1196192 | 37248
| District 05 Totals |  |  |  |  | 40 | 75 | 81 | 10586 | 15732 | 15444 | 90% | 36 | 288 | 84 | 0 | 4516 | 630 | 203773143 | 2448052 | 201325091 | 210538507 | 215453617 | -35714 | -11806 | -47520 | 215406097 | 217523200 | 82.5% | 33 | 2320045 | 6765363 | 2717 | 1768 | 14 | 146 | 3998187 | 35852 | 12 | 282 | 2177822 | 293563 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 4500 | 0 | 0 | 2 | 76227 | 0 | 0 | 0 | 64384 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 201948 | 0 | 0 | 13 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 443 | 6501093 | 329415
| 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 73.4% | 1 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | 105.2% | 1 | -286983 | 148832 | 48 | 29 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 |  | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6494 | 42752125201 | 2022-01-26 | QTR3 | 21/22 | 6 | 2 | 320 | 394 | 339 | 82.81% | 1 | 55 | 0 | 0 | 74 | 0 | 4221888 | 50000 | 4171888 | 4224163 | 3676222 | 0 | 200000 | 200000 | 3876222 | 3699956 | 88.69% | 1 | -176266 | 2275 | 60 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2023-12-13 | QTR2 | 23/24 | 613 | 4370412.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6504 | 42918525201 | 2021-05-26 | QTR4 | 20/21 | 1 | 2 | 450 | 541 | 512 | 93.56% | 1 | 29 | 0 | 0 | 91 | 0 | 5189595 | 57167 | 5132429 | 5303929 | 5374583 | 0 | 0 | 0 | 5374583 | 5469555 | 106.6% | 1 | 94972 | 114333 | 55 | 36 | 0 | 0 | 152939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157298 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 |  | 2024-03-21 | QTR3 | 23/24 | 613 | 5707742.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 119% | 1 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 106.7% | 1 | 488935 | 455645 | 61 | 44 | 0 | 0 | 55800 | 0 | 0 | 95 | 262248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 564979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 |  | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6538 | 44391915201 | 2022-05-25 | QTR4 | 21/22 | 9 | 1 | 480 | 531 | 458 | 84.79% | 1 | 73 | 0 | 0 | 51 | 0 | 13790706 | 121591 | 13669115 | 13840706 | 13459785 | 0 | 480000 | 480000 | 13939785 | 13298540 | 97.29% | 1 | -641245 | 50000 | 32 | 19 | 0 | 0 | 29647 | 0 | 0 | 0 | 16702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22076 | 0 | 0 | 0 | 6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74679 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-10-02 | QTR2 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 636 | 12736630.45 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 78.93% | 1 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | 97.57% | 1 | -232397 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6552 | 44393615201 | 2023-01-25 | QTR3 | 22/23 | 3 | 1 | 380 | 444 | 360 | 77.89% | 1 | 84 | 0 | 0 | 64 | 0 | 5851269 | 63745 | 5787524 | 5854220 | 5799051 | 0 | 240000 | 240000 | 6039051 | 5776322 | 99.81% | 1 | -259779 | 2951 | 46 | 18 | 0 | 0 | 23873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23873 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2025-03-25 | QTR3 | 24/25 |  | 2024-10-30 | QTR2 | 24/25 | 613 | 6438227.63 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6559 | 43094925201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 450 | 619 | 619 | 107.1% | 1 | 0 | 0 | 0 | 169 | 0 | 8056848 | 70725 | 7986123 | 8075952 | 7918898 | 0 | 0 | 0 | 7918898 | 7945544 | 99.49% | 1 | 26646 | 19104 | 96 | 41 | 0 | 0 | 39629 | 0 | 0 | 0 | 16524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 56152 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 613 | 7161375.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6569 | 44392715201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 300 | 369 | 298 | 76.33% | 1 | 71 | 0 | 0 | 69 | 0 | 3310000 | 50000 | 3260000 | 3360000 | 3413946 | 0 | 140000 | 140000 | 3553946 | 3413962 | 104.7% | 1 | -139984 | 50000 | 58 | 11 | 0 | 0 | 24433 | 0 | 0 | 0 | 34007 | 9362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26610 | 0 | 0 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85698 | 9362 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 |  | 2024-09-20 | QTR1 | 24/25 | 613 | 3762936 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | 101.6% | 1 | -4559 | 0 | 16 | 22 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037
| 06 | T6572 | 44390615201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 240 | 291 | 282 | 96.25% | 1 | 9 | 0 | 0 | 51 | 0 | 2360100 | 50000 | 2310100 | 2360100 | 2343530 | 0 | 0 | 0 | 2343530 | 2341786 | 101.4% | 1 | -1744 | 0 | 34 | 17 | 0 | 0 | 931 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 |  | 2024-09-03 | QTR1 | 24/25 | 613 | 2712981.65
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 11 | 31 | 17 | 4080 | 4999 | 4486 | 100% | 11 | 513 | 0 | 0 | 824 | 95 | 70647230 | 765926 | 69881305 | 71490370 | 70498132 | 0 | 1600000 | 1600000 | 72098132 | 70832133 | 100% | 11 | -1132404 | 843140 | 521 | 271 | 0 | 0 | 437259 | 0 | 0 | 95 | 393449 | 219362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155886 | 0 | 32 | 0 | 12060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 95 | 1193639 | 222491
| 06 | E6K68 | 43652615201 | 2021-07-29 | QTR1 | 21/22 | 2 | 13 | 480 | 705 | 705 | 119% | 1 | 0 | 0 | 0 | 134 | 91 | 14750000 | 96232 | 14653768 | 15707585 | 16003611 | 0 | 0 | 0 | 16003611 | 15768021 | 107.6% | 1 | -235590 | 957585 | 84 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 170156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1327474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26803 | 0 | 0 | 0 | 86070 | 86070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -660904 | 0 | 0 | 91 | 949597 | 86070 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-03-24 | QTR3 | 24/25 |  | 2025-02-07 | QTR3 | 24/25 | 613 | 9735202.54
| 06 | E6M58 | 44492015201 | 2021-05-11 | QTR4 | 20/21 | 1 | 3 | 680 | 1057 | 1057 | 112.9% | 1 | 0 | 0 | 0 | 377 | 0 | 5167117 | 50000 | 5117117 | 5569451 | 5567027 | 0 | 0 | 0 | 5567027 | 5567027 | 108.8% | 1 | 0 | 402334 | 188 | 101 | 10 | 0 | 11007 | 0 | 0 | 0 | 120107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 449910 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-06-03 | QTR4 | 23/24 | 636 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 124.6% | 0 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -1.824% | 1 | -6838357 | -65427 | 60 | 80 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD
| 06 | E6M99 | 44694715201 | 2022-04-11 | QTR4 | 21/22 | 1 | 2 | 500 | 782 | 782 | 109% | 1 | 0 | 0 | 0 | 282 | 0 | 2597679 | 50000 | 2547679 | 2701239 | 2676164 | 0 | 0 | 0 | 2676164 | 2676164 | 105% | 1 | 0 | 103560 | 151 | 86 | 0 | 0 | -12464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 116024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 103560 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2024-10-31 | QTR2 | 24/25 |  | 2024-08-02 | QTR1 | 24/25 | 636 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 06 | E6O05 | 44619115201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 240 | 461 | 454 | 97.08% | 1 | 7 | 0 | 0 | 221 | 0 | 743939 | 33329 | 710610 | 1132936 | 975348 | 0 | 0 | 0 | 975348 | 964351 | 135.7% | 0 | 0 | 388997 | 182 | 39 | 0 | 0 | 378000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378000 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2025-03-25 | QTR3 | 24/25 |  | 2025-01-27 | QTR3 | 24/25 | 636 | 699899
| 06 | E6O13 | 44890615201 | 2023-01-26 | QTR3 | 22/23 | 1 | 0 | 140 | 243 | 234 | 93.57% | 1 | 9 | 0 | 0 | 103 | 0 | 572000 | 24741 | 547259 | 572000 | 522404 | 0 | 0 | 0 | 522404 | 521792 | 95.35% | 1 | -612 | 0 | 95 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 |  | 2024-11-20 | QTR2 | 24/25 | 613 | 519555.8
| 06 | E6O14 | 44882815201 | 2023-04-27 | QTR4 | 22/23 | 2 | 0 | 180 | 226 | 226 | 103.3% | 1 | 0 | 0 | 0 | 46 | 0 | 1149149 | 50000 | 1099149 | 1149149 | 1071932 | 0 | 0 | 0 | 1071932 | 1071773 | 97.51% | 1 | -159 | 0 | 32 | 8 | 0 | 0 | 8346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 8346 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-02-12 | QTR3 | 24/25 |  | 2024-11-12 | QTR2 | 24/25 | 636 | 1084773.5
| 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | 87.5% | 1 | -21 | 0 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 |  | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5
| 06 | E6O72 | 43029179201 | 2023-06-12 | QTR4 | 22/23 | 2 | 4 | 330 | 352 | 324 | 91.52% | 1 | 28 | 0 | 0 | 22 | 0 | 1937336 | 0 | 1937336 | 1987336 | 1966014 | 0 | 0 | 0 | 1966014 | 0 | 0% | 1 | -1966014 | 50000 | 0 | 22 | 0 | 0 | 13249 | 0 | 0 | 0 | 6779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28678 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-08-09 | QTR1 | 24/25 | 636 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6O74 | 44480115201 | 2023-09-28 | QTR1 | 23/24 | 2 | 3 | 340 | 358 | 305 | 84.41% | 1 | 53 | 0 | 0 | 18 | 0 | 3862848 | 67369 | 3795479 | 4787648 | 4857931 | 0 | 0 | 0 | 4857931 | 4857931 | 128% | 0 | 0 | 924799 | 4 | 14 | 0 | 0 | 12221 | 0 | 0 | 0 | 663190 | 334969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276069 | 266494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951480 | 601463 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-01-07 | QTR3 | 24/25 |  | 2024-12-03 | QTR2 | 24/25 | 613 | 7127639.15
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 10 | 17 | 31 | 3770 | 5411 | 5310 | 90% | 9 | 101 | 0 | 0 | 1550 | 91 | 38646765 | 506066 | 38140699 | 41408614 | 41226055 | 0 | 0 | 0 | 41226055 | 32048814 | 80% | 8 | -9040753 | 2761848 | 816 | 414 | 10 | 0 | 338543 | 0 | 0 | 0 | 960232 | 334969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 91 | 2060816 | 266494 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 26803 | 0 | 0 | 0 | 86070 | 86070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -660904 | 0 | 320 | 91 | 2829637 | 687533
| District 06 Totals |  |  |  |  | 21 | 48 | 48 | 7850 | 10410 | 9796 | 95.24% | 20 | 614 | 0 | 0 | 2374 | 186 | 109293995 | 1271992 | 108022004 | 112898984 | 111724187 | 0 | 1600000 | 1600000 | 113324187 | 102880947 | 90.48% | 19 | -10173157 | 3604988 | 1337 | 685 | 10 | 0 | 775802 | 0 | 0 | 95 | 1353681 | 554331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 91 | 2216702 | 266494 | 32 | 0 | 30138 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 218660 | 0 | 0 | 0 | 86070 | 86070 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | -660904 | 0 | 352 | 186 | 4023276 | 910024
| 07 | T7438 | 25632425201 | 2020-11-18 | QTR2 | 20/21 | 2 | 11 | 700 | 961 | 953 | 105% | 1 | 8 | 0 | 0 | 218 | 43 | 16728833 | 239863 | 16488970 | 18036076 | 18037280 | 0 | 0 | 0 | 18037280 | 18987569 | 115.2% | 0 | 1096394 | 1307244 | 167 | 51 | 0 | 39 | 487932 | 0 | 0 | 4 | 893855 | 7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88439 | 16356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1473608 | 23952 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-11-15 | QTR2 | 24/25 |  | 2023-10-19 | QTR2 | 23/24 | 714 | 19921100
| 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 99.8% | 1 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 106.3% | 1 | 117308 | 206565 | 66 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 |  | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900
| 07 | T7458 | 25688155201 | 2021-01-27 | QTR3 | 20/21 | 2 | 7 | 398 | 888 | 888 | 184.2% | 0 | 0 | 0 | 0 | 199 | 291 | 7962187 | 57992 | 7904195 | 8615404 | 8747181 | 0 | 0 | 0 | 8747181 | 8731655 | 110.5% | 0 | 405586 | 653217 | 101 | 54 | 25 | 142 | 19202 | 0 | 19 | 92 | 516876 | 465849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 31139 | 17389 | 0 | 0 | 0 | 0 | 0 | 57 | 21127 | 21127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 291 | 603217 | 504365 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 |  | 2024-02-09 | QTR3 | 23/24 | 799 | 5285500
| 07 | T7464 | 43307125201 | 2022-05-25 | QTR4 | 21/22 | 2 | 1 | 425 | 478 | 381 | 77.18% | 1 | 97 | 0 | 0 | 53 | 0 | 5977271 | 77000 | 5900271 | 5963393 | 5896599 | 0 | 0 | 0 | 5896599 | 5865873 | 99.42% | 1 | -30725 | -13878 | 29 | 24 | 0 | 0 | 1254 | 0 | 0 | 0 | -31791 | 0 | 0 | 0 | 16658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3612 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-01-20 | QTR3 | 24/25 |  | 2024-03-06 | QTR3 | 23/24 | 796 | 4795700
| 07 | T7475 | 43764415201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 260 | 423 | 423 | 115% | 1 | 0 | 0 | 0 | 104 | 59 | 4773108 | 50000 | 4723108 | 4959207 | 5064114 | 0 | 0 | 0 | 5064114 | 5050016 | 106.9% | 1 | 31351 | 186099 | 96 | 28 | 0 | 39 | 147305 | 0 | 0 | 0 | 8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18794 | 18794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 174985 | 18794 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-03-12 | QTR3 | 24/25 |  | 2023-03-31 | QTR3 | 22/23 | 796 | 4701400
| 07 | T7481 | 44073315201 | 2022-08-31 | QTR1 | 22/23 | 3 | 0 | 225 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 3304021 | 50000 | 3254021 | 3304021 | 3182990 | 0 | 0 | 0 | 3182990 | 3174072 | 97.54% | 1 | -8918 | 0 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-12 | QTR2 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 796 | 3303500
| 07 | T7482 | 43983115201 | 2021-10-27 | QTR2 | 21/22 | 1 | 4 | 295 | 369 | 369 | 105.4% | 1 | 0 | 0 | 0 | 74 | 0 | 11256386 | 131329 | 11125057 | 10574479 | 10748589 | 0 | 0 | 0 | 10748589 | 11070556 | 99.51% | 1 | 331923 | -681906 | 32 | 26 | 0 | 0 | 0 | 0 | 16 | 0 | 1017154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1709016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | -681906 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 |  | 2023-11-06 | QTR2 | 23/24 | 796 | 13466700
| 07 | T7492 | 44024815201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 210 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 5438332 | 52000 | 5386332 | 5435828 | 5441055 | 0 | 0 | 0 | 5441055 | 5414623 | 100.5% | 1 | -26432 | -2504 | 24 | 16 | 0 | 0 | -2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2504 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 |  | 2024-08-07 | QTR1 | 24/25 | 799 | 5496384.15
| 07 | T7497 | 43940115201 | 2022-08-31 | QTR1 | 22/23 | 1 | 3 | 375 | 460 | 460 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 7112946 | 50000 | 7062946 | 7172036 | 7363800 | 0 | 0 | 0 | 7363800 | 7320296 | 103.6% | 1 | -34413 | 59091 | 47 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 48118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 61729 | 2100 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 |  | 2024-07-25 | QTR1 | 24/25 | 799 | 6545800
| 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 98.1% | 1 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | 101.9% | 1 | -2665 | 0 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300
| 07 | T7518 | 45248755201 | 2023-12-06 | QTR2 | 23/24 | 5 | 0 | 140 | 153 | 142 | 92.14% | 1 | 11 | 0 | 0 | 13 | 0 | 908274 | 50000 | 858274 | 908274 | 908491 | 0 | 0 | 0 | 908491 | 908491 | 105.9% | 1 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 |  | 2024-09-16 | QTR1 | 24/25 | 798 | 1515975
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 11 | 23 | 34 | 3738 | 5147 | 5026 | 90.91% | 10 | 121 | 0 | 0 | 1009 | 400 | 72399260 | 858184 | 71541076 | 74113185 | 74483234 | 0 | 0 | 0 | 74483234 | 75725221 | 81.82% | 9 | 1879409 | 1713928 | 638 | 338 | 25 | 220 | 653189 | 0 | 35 | 96 | 2591708 | 536714 | 0 | 0 | 16658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1673920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 27 | 167685 | 52539 | 0 | 0 | 0 | 0 | 0 | 57 | 29313 | 23227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 400 | 1784634 | 612481
| 07 | E7M37 | 43514215201 | 2019-07-31 | QTR1 | 19/20 | 3 | 12 | 1300 | 1743 | 1717 | 114% | 1 | 26 | 0 | 0 | 235 | 208 | 80980890 | 298979 | 80681912 | 84381295 | 85235769 | 0 | 0 | 0 | 85235769 | 85499813 | 106% | 1 | 413658 | 3400405 | 130 | 105 | 0 | 0 | 317727 | 24625 | 0 | 208 | 2693729 | 70028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459570 | 443526 | 0 | 0 | 16156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30396 | 0 | 0 | 208 | 3612698 | 538180 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 |  | 2024-07-24 | QTR1 | 24/25 | 798 | 87914529.56
| 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | 335.8% | 0 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 91.04% | 1 | 0 | 207487 | 178 | 55 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300
| 07 | E7P11 | 44605115201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 237 | 237 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 5505947 | 65000 | 5440947 | 5505947 | 5635303 | 0 | 0 | 0 | 5635303 | 5612523 | 103.2% | 1 | -22780 | 0 | 38 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 26520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26520 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-20 | QTR3 | 24/25 |  | 2024-03-04 | QTR3 | 23/24 | 796 | 5708568
| 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 107.8% | 1 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | 109.5% | 1 | -27960 | 0 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 |  | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62
| 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 100% | 1 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | 101.4% | 1 | -125432 | 324762 | 127 | 22 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900
| 07 | E7P35 | 44165715201 | 2022-05-11 | QTR4 | 21/22 | 2 | 3 | 400 | 458 | 458 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 8986578 | 71000 | 8915578 | 9084687 | 9016111 | 0 | 0 | 0 | 9016111 | 8840279 | 99.16% | 1 | -171882 | 98110 | 30 | 28 | 0 | 0 | 115777 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-04-18 | QTR4 | 23/24 | 799 | 8393400
| 07 | E7P50 | 41685625201 | 2024-02-14 | QTR3 | 23/24 | 1 | 0 | 40 | 60 | 51 | 77.5% | 1 | 9 | 0 | 0 | 20 | 0 | 388968 | 16000 | 372968 | 388968 | 314971 | 0 | 0 | 0 | 314971 | 314971 | 84.45% | 1 | 0 | 0 | 3 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 |  | 2024-08-26 | QTR1 | 24/25 | 796 | 427400
| 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | 105.7% | 1 | -342 | 101105 | 19 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 |  | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400
| 07 | E7P96 | 44378315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 0 | 183 | 232 | 232 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 5338647 | 50000 | 5288647 | 5338647 | 5375414 | 0 | 0 | 0 | 5375414 | 5376462 | 101.7% | 1 | 1048 | 0 | 40 | 9 | 0 | 0 | 3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3833 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-17 | QTR3 | 24/25 |  | 2024-09-23 | QTR1 | 24/25 | 798 | 5546100
| 07 | E7Q14 | 44349215201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 185 | 335 | 335 | 116.2% | 1 | 0 | 0 | 0 | 120 | 30 | 2636615 | 50000 | 2586615 | 2636615 | 2586233 | 0 | 0 | 0 | 2586233 | 2586234 | 99.99% | 1 | 1 | 0 | 101 | 19 | 0 | 0 | 25276 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25276 | 0 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 |  | 2024-12-02 | QTR2 | 24/25 | 796 | 2170285.15
| 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 98% | 1 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 108.7% | 1 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700
| 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 85.71% | 1 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 106.1% | 1 | 2811 | 30000 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300
| 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 86.4% | 1 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 107.5% | 1 | 565 | 4646 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 |  | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200
| 07 | E7R09 | 42421335201 | 2020-01-31 | QTR3 | 19/20 | 3 | 1 | 1200 | 1582 | 1572 | 110.2% | 1 | 10 | 0 | 0 | 139 | 243 | 38345345 | 150000 | 38195345 | 38534960 | 38424665 | 0 | 0 | 0 | 38424665 | 38424665 | 100.6% | 1 | 974984 | 189615 | 163 | 86 | 0 | 80 | 230717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 230717 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 |  | 2024-08-18 | QTR1 | 24/25 | 714 | 39771136 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 116.9% | 1 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | 105.4% | 1 | -31871 | 3477169 | 524 | 88 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127928 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 |  | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 15 | 23 | 52 | 5643 | 8526 | 8589 | 93.33% | 14 | -63 | 152 | 0 | 2290 | 593 | 223599420 | 1216979 | 222382442 | 231432717 | 232322471 | -570912 | 0 | -570912 | 231751559 | 231085765 | 100% | 15 | 1013502 | 7833298 | 1401 | 531 | 144 | 80 | 3350539 | 1803612 | 0 | 292 | 3782982 | 404205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613505 | 531685 | 0 | 53 | 16156 | 0 | 0 | 0 | 0 | 0 | 252 | 58 | 548765 | 71647 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | -158324 | 0 | 418 | 593 | 8153623 | 2811152
| District 07 Totals |  |  |  |  | 26 | 46 | 86 | 9381 | 13673 | 13615 | 92.31% | 24 | 58 | 152 | 0 | 3299 | 993 | 295998680 | 2075163 | 293923518 | 305545902 | 306805705 | -570912 | 0 | -570912 | 306234793 | 306810986 | 92.31% | 24 | 2892911 | 9547226 | 2039 | 869 | 169 | 300 | 4003728 | 1803612 | 35 | 388 | 6374690 | 940919 | 0 | 0 | 16658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1060415 | 531685 | 0 | 53 | 16156 | 0 | 0 | 0 | 0 | 0 | 299 | 85 | 716450 | 124186 | 0 | 0 | 0 | 0 | 22 | 57 | 29313 | 23227 | 0 | 110 | 0 | 0 | 0 | 0 | -158324 | 0 | 525 | 993 | 9938257 | 3423633
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R80 | 43554315201 | 2019-06-11 | QTR4 | 18/19 | 1 | 9 | 1810 | 1897 | 1601 | 78.4% | 1 | 296 | 0 | 0 | 182 | -95 | 244979349 | 150000 | 244829349 | 251466172 | 255108575 | 0 | 4375439 | 4375439 | 259484014 | 258158459 | 105.4% | 1 | 4868615 | 6486824 | 78 | 104 | 0 | 0 | 311893 | 0 | 0 | 0 | 9734282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5045376 | 0 | 0 | 0 | 1661009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -95 | -168828 | 0 | 0 | -95 | 6556771 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 |  | 2024-02-29 | QTR3 | 23/24 | 854 | 217827999.45 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8R82 | 43801815201 | 2020-01-16 | QTR3 | 19/20 | 2 | 5 | 1443 | 1673 | 1666 | 99.51% | 1 | 7 | 0 | 0 | 230 | 0 | 61180000 | 150000 | 61030000 | 61481136 | 61477229 | 0 | 0 | 0 | 61477229 | 63363328 | 103.8% | 1 | 4461679 | 301136 | 133 | 97 | 0 | 0 | 40265 | 0 | 0 | 0 | 59694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206332 | 0 | 0 | 0 | 3020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412001 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-02-24 | QTR3 | 24/25 |  | 2024-10-07 | QTR2 | 24/25 | 854 | 58657847.3 | A3 | ICC - DESIGN/BUILD - MINOR
| 08 | E8S90 | 43945755201 | 2021-04-20 | QTR4 | 20/21 | 5 | 13 | 533 | 998 | 998 | 113.5% | 1 | 0 | 0 | 0 | 465 | 0 | 21999573 | 150000 | 21849573 | 23015619 | 24155114 | 0 | 0 | 0 | 24155114 | 24813029 | 113.6% | 0 | 1013008 | 1016046 | 287 | 106 | 56 | 0 | 446658 | 0 | 0 | 0 | 537731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 32966 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 125872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 1143227 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 |  | 2024-05-10 | QTR4 | 23/24 | 854 | 23025803.13
| 08 | E8T40 | 44497815201 | 2021-12-14 | QTR2 | 21/22 | 1 | 4 | 451 | 635 | 633 | 105.1% | 1 | 2 | 0 | 0 | 159 | 25 | 3179902 | 50000 | 3129902 | 3285956 | 3273170 | 0 | 0 | 0 | 3273170 | 3273170 | 104.6% | 1 | 0 | 106054 | 127 | 32 | 0 | 0 | 51083 | 0 | 0 | 25 | 51409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 132422 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 |  | 2024-11-15 | QTR2 | 24/25 | 854 | 3360453.31
| 08 | E8T67 | 44262415201 | 2022-04-12 | QTR4 | 21/22 | 2 | 5 | 322 | 521 | 518 | 99.07% | 1 | 3 | 0 | 0 | 199 | 0 | 12517000 | 119797 | 12397203 | 12877010 | 12203064 | 0 | 0 | 0 | 12203064 | 12123596 | 97.79% | 1 | -79468 | 360010 | 133 | 66 | 0 | 0 | 108673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796 | 0 | 0 | 0 | 257897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369366 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 |  | 2024-03-11 | QTR3 | 23/24 | 854 | 13936524.01
| 08 | E8T77 | 44925315201 | 2022-05-17 | QTR4 | 21/22 | 2 | 4 | 440 | 677 | 666 | 111.6% | 1 | 11 | 0 | 0 | 237 | 0 | 5565378 | 50000 | 5515378 | 5757378 | 5730235 | 0 | 0 | 0 | 5730235 | 5763102 | 104.5% | 1 | 32867 | 192000 | 120 | 55 | 0 | 0 | 33771 | 0 | 0 | 0 | 77369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 111140 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-14 | QTR2 | 24/25 |  | 2024-09-11 | QTR1 | 24/25 | 854 | 5213379.79
| 08 | E8T82 | 42897215201 | 2022-09-13 | QTR1 | 22/23 | 2 | 2 | 568 | 619 | 464 | 72.71% | 1 | 155 | 0 | 0 | 51 | 0 | 2504148 | 58519 | 2445628 | 2711373 | 2646645 | 0 | 0 | 0 | 2646645 | 2639419 | 107.9% | 1 | 0 | 207226 | 9 | 42 | 0 | 0 | 227557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7226 | 0 | 0 | 0 | 234782 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-07-11 | QTR1 | 24/25 | 854 | 4806556.91
| 08 | E8T94 | 43578625201 | 2022-10-25 | QTR2 | 22/23 | 1 | 1 | 165 | 221 | 221 | 109.1% | 1 | 0 | 0 | 0 | 41 | 15 | 2596848 | 50000 | 2546848 | 2612139 | 2505813 | 0 | 0 | 0 | 2505813 | 2503780 | 98.31% | 1 | -2033 | 15291 | 18 | 23 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 |  | 2024-05-17 | QTR4 | 23/24 | 854 | 2699146.4
| 08 | E8T95 | 44171915201 | 2022-10-25 | QTR2 | 22/23 | 3 | 3 | 508 | 651 | 615 | 92.91% | 1 | 36 | 0 | 0 | 143 | 0 | 21849074 | 150000 | 21699074 | 22014286 | 22325271 | 0 | 0 | 0 | 22325271 | 22079112 | 101.8% | 1 | -230948 | 165212 | 97 | 46 | 0 | 0 | 189344 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201 | 0 | 0 | 0 | 11368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225106 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 |  | 2024-10-17 | QTR2 | 24/25 | 854 | 21254879.86
| 08 | E8U06 | 44262295201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 283 | 429 | 429 | 110.6% | 1 | 0 | 0 | 0 | 116 | 30 | 4494080 | 56314 | 4437766 | 4544080 | 4339328 | 0 | 0 | 0 | 4339328 | 4339341 | 97.78% | 1 | 13 | 50000 | 67 | 49 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 43390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 43390 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2025-02-07 | QTR3 | 24/25 |  | 2025-01-10 | QTR3 | 24/25 | 854 | 5696150.1
| 08 | E8U07 | 44969215201 | 2023-04-11 | QTR4 | 22/23 | 1 | 2 | 309 | 374 | 360 | 95.47% | 1 | 14 | 0 | 0 | 65 | 0 | 3578802 | 48428 | 3530375 | 3752049 | 3491844 | 0 | 0 | 0 | 3491844 | 3491287 | 98.89% | 1 | -556 | 173247 | 32 | 33 | 0 | 0 | 181887 | 0 | 0 | 0 | 10641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194888 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 |  | 2024-09-25 | QTR1 | 24/25 | 854 | 2800800.1
| 08 | E8U10 | 44933415201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 200 | 267 | 260 | 96.5% | 1 | 7 | 0 | 0 | 67 | 0 | 870362 | 44352 | 826010 | 876241 | 829659 | 0 | 0 | 0 | 829659 | 823780 | 99.73% | 1 | 0 | 5880 | 47 | 20 | 0 | 0 | 9988 | 0 | 0 | 0 | 9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20747 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 |  | 2024-12-02 | QTR2 | 24/25 | 854 | 937383.97
| 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 38.1% | 1 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 98.62% | 1 | 0 | 25000 | 4 | 15 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 |  | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02
| 08 | E8U57 | 44942315201 | 2023-09-12 | QTR1 | 23/24 | 1 | 0 | 165 | 196 | 196 | 101.2% | 1 | 0 | 0 | 0 | 29 | 2 | 1336393 | 50000 | 1286393 | 1336393 | 1288438 | 0 | 0 | 0 | 1288438 | 1288438 | 100.2% | 1 | 0 | 0 | 17 | 12 | 0 | 2 | 18473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18473 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2025-01-17 | QTR3 | 24/25 |  | 2024-09-17 | QTR1 | 24/25 | 854 | 1342593.14
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 14 | 25 | 51 | 7554 | 9534 | 8782 | #VALUE! | 14 | 752 | 0 | 0 | 2003 | -23 | 387784581 | 1177410 | 386607171 | 396888504 | 400443053 | 0 | 4375439 | 4375439 | 404818492 | 405728509 | 92.86% | 13 | 10063177 | 9103926 | 1169 | 700 | 56 | 2 | 1622817 | 0 | 0 | 50 | 10497893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -4748219 | 0 | 16 | 0 | 1998551 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 307567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | -95 | -161602 | 0 | 279 | -23 | 9517004 | 0
| District 08 Totals |  |  |  |  | 14 | 25 | 51 | 7554 | 9534 | 8782 | 100% | 14 | 752 | 0 | 0 | 2003 | -23 | 387784581 | 1177410 | 386607171 | 396888504 | 400443053 | 0 | 4375439 | 4375439 | 404818492 | 405728509 | 92.86% | 13 | 10063177 | 9103926 | 1169 | 700 | 56 | 2 | 1622817 | 0 | 0 | 50 | 10497893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -4748219 | 0 | 16 | 0 | 1998551 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 307567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | -95 | -161602 | 0 | 279 | -23 | 9517004 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 134 | 245 | 297 | 39109 | 59974 | 58543 | 83.58% | 112 | 1431 | 133 | 0 | 17088 | 3831 | 882223442 | 9601368 | 872622073 | 903536498 | 911322741 | -668314 | 2260730 | 1592416 | 912915157 | 916244211 | 92.54% | 124 | 5043607 | 21532473 | 11514 | 4868 | 459 | 899 | 10024229 | 727736 | 658 | 1154 | 10089991 | 2296545 | 0 | 0 | 26546 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 0 | 0 | 47 | 546 | -656392 | 5020 | 67 | 75 | 324124 | 104277 | 0 | 0 | 0 | 0 | 1785 | 677 | 1208260 | 52539 | 0 | 288 | 4185297 | 3366472 | 67 | 117 | 403826 | 624900 | 152 | 0 | 0 | 0 | 0 | -40 | -902207 | 0 | 3235 | 3716 | 23508300 | 7177491
| Statewide District Let Contracts SubTotal |  |  |  |  | 103 | 163 | 299 | 36091 | 51518 | 50272 | 90.29% | 93 | 1246 | 293 | 0 | 13676 | 1751 | 1122740235 | 6857765 | 1115882472 | 1158148326 | 1164199679 | -666357 | 5751239 | 5084882 | 1169284561 | 1160821970 | 91.26% | 94 | 9879364 | 35936300 | 7818 | 4157 | 410 | 404 | 11066226 | 3986153 | 347 | 819 | 23740465 | 1059113 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 384 | 193 | -979530 | 854898 | 42 | 53 | 2254795 | 330292 | 0 | 0 | 0 | 0 | 759 | 169 | 1348840 | 85050 | 0 | 0 | 86070 | 86070 | 173 | 13 | 271502 | 258951 | 62 | 110 | 0 | 0 | 0 | -125 | -1029726 | 0 | 2177 | 1636 | 36797511 | 6660530
| Statewide Totals |  |  |  |  | 237 | 408 | 596 | 75200 | 111492 | 108815 | 86.5% | 205 | 2677 | 426 | 0 | 30764 | 5582 | 2004963677 | 16459133 | 1988504545 | 2061684824 | 2075522420 | -1334671 | 8011969 | 6677298 | 2082199718 | 2077066181 | 91.98% | 218 | 14922971 | 57468773 | 19332 | 9025 | 869 | 1303 | 21090455 | 4713889 | 1005 | 1973 | 33830456 | 3355658 | 0 | 0 | 60918 | 0 | 0 | 0 | -1195370 | 0 | 0 | 0 | 4500 | 0 | 431 | 739 | -1635922 | 859918 | 109 | 128 | 2578919 | 434569 | 0 | 0 | 0 | 0 | 2544 | 846 | 2557100 | 137589 | 0 | 288 | 4271367 | 3452542 | 240 | 130 | 675328 | 883851 | 214 | 110 | 0 | 0 | 0 | -165 | -1931933 | 0 | 5412 | 5352 | 60305811 | 13838021

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1U15 | 44448515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-01-13 | 9191000 | 9286906 | 8593729 | 95906.42 | 0 | 8866277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593729 | 8866277 | 272547 | 9151070
1 | E1U16 | 44742915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-20 | 7395393 | 7483422 | 7804114 | 88029.32 | 0 | 7806499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7804114 | 7806499 | 2385 | 7252829
1 | E1U97 | 44789615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 3990000 | 4021977 | 3979990 | 31977.22 | 0 | 3978102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 1965526 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1V11 | 44504315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-19 | 2582000 | 2736729 | 2706856 | 154728.97 | 0 | 2704595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2706856 | 2704595 | -2261 | 3004848 | B0 | ACC - LUMP SUM
1 | E1V15 | 44547115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-19 | 7937275 | 7937275 | 7998691 | 0 | 0 | 7941859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7998691 | 7941859 | -56832 | 8527987
1 | E1V16 | 44405015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-09 | 5610556 | 5735677 | 5817092 | 125121.65 | 0 | 5794981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5817092 | 5794981 | -22111 | 4321005 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | E1V18 | 44620815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-03-16 | 11855203 | 12344460 | 12567270 | 489256.77 | 0 | 12562055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12567270 | 12562055 | -5215 | 11076912
1 | E1V61 | 44622815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-10-10 | 5258695 | 5702540 | 5768353 | 443845.04 | 0 | 5707872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5768353 | 5707872 | -60481 | 6337132 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1W10 | 44744115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | 5126611 | 5135303 | 4999771 | 8691.75 | 0 | 4990201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4999771 | 4990201 | -9570 | 5933693
1 | E1W12 | 44738215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-03-21 | 3349511 | 3349511 | 3342095 | 0 | 0 | 3331252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342095 | 3331252 | -10843 | 3912147
1 | E1W15 | 44464315201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-08-17 | 572414 | 613908 | 573719 | 41493.75 | 0 | 573719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573719 | 573719 | 0 | 767485
1 | E1W19 | 44743315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2023-10-19 | 3927820 | 3927820 | 3916235 | 0 | 0 | 3896792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3916235 | 3896792 | -19443 | 3787595
1 | E1W20 | 44620215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-19 | 2630586 | 2630586 | 2573059 | 0 | 0 | 2559128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573059 | 2559128 | -13930 | 2937558
1 | T1805 | 43943115201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-07-28 | 6184000 | 6204651 | 6014186 | 20651.35 | 0 | 6712744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014186 | 6712744 | 698558 | 7780401
1 | T1825 | 43982715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-25 | 8278071 | 8939807 | 8867401 | 661736.23 | 0 | 8953757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8867401 | 8953757 | 86356 | 7852555
1 | T1846 | 44156115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-01-25 | 3477042 | 3477042 | 3332356 | 0 | 0 | 3322154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332356 | 3322154 | -10202 | 3367086
1 | T1847 | 43805715201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-10-26 | 1159034 | 1218049 | 1206007 | 59015.14 | 0 | 1205156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 1023962
1 | T1848 | 44593215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-12-07 | 13310586 | 13399125 | 12912681 | 88539.65 | 0 | 12823061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12912681 | 12823061 | -89620 | 14760503
1 | T1860 | 43709615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 4325722 | 4504283 | 4508752 | 178560.93 | 0 | 4497707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4508752 | 4497707 | -11045 | 2709383
1 | T1871 | 45224115201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2023-09-27 | 3701415 | 3701415 | 3225904 | 0 | 0 | 3227402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225904 | 3227402 | 1498 | 4091496
2 | E200K | 43737515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-05-10 | 596179 | 596809 | 579939 | 630 | 0 | 579939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579939 | 579939 | 0 | 642935
2 | E20G1 | 43451415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-17 | 8137606 | 11055579 | 11421194 | 2917973.3 | 0 | 11421194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11421194 | 11421194 | 0 | 9316377
2 | E20I2 | 43556415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-06-08 | 742391 | 742391 | 688386 | 0 | 0 | 688386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688386 | 688386 | 0 | 1885002
2 | E20S3 | 44752515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-06-07 | 3180291 | 2920160 | 2867769 | -260131 | 0 | 2867769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867769 | 2867769 | 0 | 6564146 | LBDB:LBDB::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
2 | E2Z23 | 43655815201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-15 | 23611420 | 27138289 | 28700280 | 3526869.4 | 0 | 28809279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28700280 | 28809279 | 108999 | 23815761
2 | T2804 | 44137215201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 7398298 | 7431649 | 7748601 | 33350.85 | 0 | 7995687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7748601 | 7995687 | 247086 | 6176554
2 | T2820 | 43231615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 6513333 | 6536983 | 6298184 | 23649.6 | -45432 | 6786189 | -45432 | 0 | 0 | 0 | 0 | 0 | -45432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45432 | 6252752 | 6786189 | 533437 | 8131499
2 | T2828 | 44105015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-12-08 | 2858409 | 2966328 | 3044806 | 107919.26 | 0 | 3046950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3044806 | 3046950 | 2144 | 3146529
2 | T2834 | 44326115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 9753946 | 9932433 | 10044314 | 178487.31 | 0 | 10184626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10044314 | 10184626 | 140312 | 11499594
2 | T2838 | 44342015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 11945708 | 12005007 | 12120635 | 59299.78 | 0 | 12074024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12120635 | 12074024 | -46610 | 12401358
2 | T2843 | 21023045201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 12094446 | 12285295 | 12375077 | 190849.06 | 0 | 12184067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375077 | 12184067 | -191010 | 15875563
2 | T2853 | 44714915201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 17135161 | 17359701 | 17949301 | 224540.06 | 0 | 17752973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17949301 | 17752973 | -196328 | 22151003
2 | T2864 | 20765825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 2568964 | 2668964 | 2632044 | 100000 | 0 | 2632301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2632044 | 2632301 | 257 | 2408715
2 | T2896 | 44284815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 3802716 | 3802716 | 3666172 | 0 | 0 | 3666172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 4117339
2 | T2897 | 44554615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 7947765 | 7947765 | 8246084 | 0 | 0 | 8193910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 11037253
2 | T2900 | 40392045201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-06-15 | 869247 | 869247 | 857258 | 0 | 0 | 857258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857258 | 857258 | 0 | 1017097
2 | T2908 | 44534215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 7659724 | 7761297 | 8108037 | 101573.4 | 0 | 8070080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8108037 | 8070080 | -37957 | 7157174
2 | T2909 | 44607915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-02-22 | 7130409 | 7130409 | 7454415 | 0 | 0 | 7520621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7454415 | 7520621 | 66206 | 7319756
2 | T2911 | 44703315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 5899711 | 5916585 | 5921537 | 16874 | 0 | 5926778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5921537 | 5926778 | 5241 | 6079798
2 | T2918 | 43911515201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 8269281 | 8404947 | 8393938 | 135666.54 | 0 | 8396288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8393938 | 8396288 | 2350 | 9740099
2 | T2922 | 44717615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 4768192 | 4768192 | 4978398 | 0 | 0 | 4983434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4978398 | 4983434 | 5036 | 5253039
2 | T2926 | 44703715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 12488206 | 12488206 | 12735786 | 0 | 0 | 12755313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 12922548
2 | T2927 | 44762935201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 737944 | 737944 | 698279 | 0 | 0 | 698279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698279 | 698279 | 0 | 752837
2 | T2928 | 43195525201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-31 | 1070183 | 1146536 | 1180671 | 76352.44 | 0 | 1180315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180671 | 1180315 | -356 | 767498
2 | T2929 | 44572415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 2525783 | 2525783 | 2526018 | 0 | 0 | 2526018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2526018 | 2526018 | 0 | 2044903
2 | T2931 | 44722615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 595321 | 595321 | 526968 | 0 | 0 | 526968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526968 | 526968 | 0 | 725236
2 | T2933 | 44105815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 10782106 | 10551459 | 10447042 | -230646.71 | -42921 | 10298476 | -42921 | 0 | 0 | 0 | 0 | 0 | -42921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42921 | 10404121 | 10298476 | -105645 | 10943081
2 | T2935 | 43917715201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 688840 | 688840 | 661650 | 0 | 0 | 661650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661650 | 661650 | 0 | 865701
2 | T2941 | 44535115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 12720657 | 12720657 | 12835454 | 0 | 0 | 12775399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12835454 | 12775399 | -60056 | 15011208
2 | T2942 | 44549115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 3471985 | 3471985 | 3461898 | 0 | 0 | 3448164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3461898 | 3448164 | -13733 | 3741502
2 | T2957 | 44712915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 2432061 | 2483046 | 2440068 | 50985 | 0 | 2440833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2440068 | 2440833 | 766 | 2377451
2 | T2958 | 44615425201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-06-14 | 3795580 | 3795580 | 3741800 | 0 | 0 | 3742922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 3808947
2 | T2964 | 44712615201 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 10386249 | 11083785 | 10715818 | 697536 | 697536 | 10715818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697536 | 0 | 0 | 0 | 0 | 697536 | 697536 | 11413354 | 10715818 | -697536 | 15260326 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | T2980 | 45220115201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-10-25 | 1193458 | 1193458 | 1138988 | 0 | 0 | 1138988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 2555282
3 | E3Q94 | 21787545201 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2018-06-14 | 31708584 | 32410332 | 32832992 | 701748.39 | 0 | 33087185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32832992 | 33087185 | 254193 | 25965926
3 | E3T55 | 43974015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-11 | 5227145 | 5227145 | 5328540 | 0 | -101412 | 5712178 | -101412 | 0 | 0 | 0 | 0 | 0 | -101412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101412 | 5227128 | 5712178 | 485050 | 4892771
3 | E3U63 | 43776415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-09 | 7526960 | 7526960 | 7541005 | 0 | 0 | 7424010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7541005 | 7424010 | -116995 | 9579368
3 | E3V87 | 44573415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-08 | 4255368 | 4255368 | 4147787 | 0 | 0 | 4133951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 4883807
3 | E3W06 | 22283255201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-03-21 | 365234 | 365234 | 304736 | 0 | 0 | 304736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304736 | 304736 | 0 | 608747
3 | E3W17 | 44759015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-10 | 3130216 | 3130216 | 3176618 | 0 | 0 | 3169412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 4310828
3 | E3W27 | 43464515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-15 | 3980189 | 4006691 | 4118899 | 26502.21 | 0 | 4101914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 4847742
3 | E3W54 | 42359155201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2023-07-13 | 3139310 | 3241997 | 3289104 | 102686.83 | 70800 | 3289104 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 70800 | 3359904 | 3289104 | -70800 | 2935414 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3W67 | 43467115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | 3519862 | 3519862 | 3571544 | 0 | 0 | 3563708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3571544 | 3563708 | -7835 | 4787061
3 | E3W87 | 44573515201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-02-08 | 3177069 | 3177069 | 3326636 | 0 | 0 | 3307859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3326636 | 3307859 | -18777 | 4084999
3 | E3W88 | 44575515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | 2175239 | 2175239 | 2183626 | 0 | 0 | 2183626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183626 | 2183626 | 0 | 3085003
3 | T3690 | 41413265201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 15659012 | 16135795 | 16303848 | 476782.64 | -5000 | 16971927 | 0 | 0 | 0 | 0 | 0 | -5000 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 16298848 | 16971927 | 673080 | 14312918
3 | T3719 | 43921415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-05-25 | 2161422 | 2219469 | 2278041 | 58046.15 | 0 | 2271197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 3319649
3 | T3730 | 43972515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 13201615 | 13201615 | 14101673 | 0 | 0 | 14032884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 14987298
3 | T3767 | 44188125201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 1798857 | 1800807 | 1823631 | 1950 | 0 | 1837783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1816518
3 | T3774 | 44115615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-10-26 | 2352518 | 2352518 | 2482697 | 0 | 0 | 2481516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 2793292
3 | T3791 | 43937615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-06-14 | 2097844 | 2104355 | 1977895 | 6511.18 | 0 | 1977939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977895 | 1977939 | 44 | 2307183
3 | T3792 | 44117115201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 1248264 | 1248264 | 1306248 | 0 | 0 | 1306346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306248 | 1306346 | 98 | 1870598
3 | T3803 | 44403915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7221201 | 7242100 | 7302859 | 20899.02 | 0 | 7410703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 6606379
3 | T3806 | 43973315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 10103368 | 10103368 | 10342165 | 0 | 0 | 10277452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10342165 | 10277452 | -64713 | 10842968
3 | T3813 | 44159315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 6499662 | 6674412 | 6885176 | 174749.85 | 0 | 6899511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6885176 | 6899511 | 14336 | 6445150
3 | T3814 | 43989215201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 2042361 | 2052823 | 2049639 | 10462.01 | 0 | 2051119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 1702970
3 | T3815 | 44365115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 7790941 | 8040944 | 8245622 | 250003.2 | 0 | 8108954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8245622 | 8108954 | -136668 | 8069731
3 | T3824 | 43769915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-04-26 | 3559704 | 3559704 | 3648796 | 0 | 0 | 3648367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3648796 | 3648367 | -429 | 5711547
3 | T3826 | 44387715201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 942554 | 942554 | 927016 | 0 | 0 | 927016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927016 | 927016 | 0 | 1043116
3 | T3829 | 44553915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 12211588 | 12181493 | 12519374 | -30095 | 0 | 12516178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12519374 | 12516178 | -3196 | 12606229
3 | T3831 | 44575915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 14273753 | 14525242 | 15530113 | 251488.73 | 0 | 15529289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15530113 | 15529289 | -824 | 15124580
3 | T3832 | 44986815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 391274 | 391274 | 365673 | 0 | 0 | 365673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365673 | 365673 | 0 | 417471
3 | T3834 | 44563515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 19944475 | 19944475 | 21545566 | 0 | -363010 | 21410083 | -363010 | 0 | 0 | 0 | 0 | 0 | -363010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -363010 | 21182556 | 21410083 | 227527 | 18371047
3 | T3842 | 44404015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 851756 | 851756 | 802521 | 0 | 0 | 802521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802521 | 802521 | 0 | 869556
3 | T3847 | 44365025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 8306085 | 8382009 | 9159429 | 75924.28 | 0 | 9121506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 7884744
3 | T3856 | 44573315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 6737296 | 6737296 | 7134385 | 0 | 0 | 7124379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7134385 | 7124379 | -10006 | 7216078
3 | T3864 | 44562915201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-04-26 | 3480880 | 3589639 | 3810464 | 108758.99 | 0 | 3809861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810464 | 3809861 | -603 | 5160701
3 | T3865 | 43774625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 6205064 | 6251095 | 6519415 | 46031.59 | 0 | 6478224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6519415 | 6478224 | -41192 | 8476486
3 | T3869 | 44759115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 4656452 | 4656452 | 4603412 | 0 | 0 | 4603490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4603412 | 4603490 | 79 | 4979086
3 | T3872 | 43775625201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2023-11-15 | 7954987 | 8031898 | 8038891 | 76911.71 | 0 | 8021230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8038891 | 8021230 | -17661 | 10589090 | B5 | ACC - INCENTIVE/DISINCENTIVE
3 | T3875 | 44758815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 4849503 | 4849503 | 5213259 | 0 | 0 | 5178770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5213259 | 5178770 | -34488 | 6479282
3 | T3877 | 43775715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 11695437 | 11701443 | 12402258 | 6006 | 0 | 12455669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12402258 | 12455669 | 53411 | 9851820
3 | T3880 | 43078925201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 3380216 | 3380216 | 3471279 | 0 | 0 | 3471279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3471279 | 3471279 | 0 | 5332275
3 | T3886 | 45221235201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1444661 | 1521683 | 1385235 | 77022.4 | 0 | 1385235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385235 | 1385235 | 0 | 2325344
3 | T3889 | 45221225201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-10-25 | 1570117 | 1689632 | 1597844 | 119514.99 | 0 | 1597844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1597844 | 1597844 | 0 | 1925285
3 | T3897 | 44845115201 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2023-12-06 | 1349500 | 1349500 | 1300591 | 0 | 0 | 1300571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300591 | 1300571 | -20 | 1617298
3 | T3921 | 45146315201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2024-05-22 | 655998 | 655998 | 585688 | 0 | 0 | 585688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585688 | 585688 | 0 | 605939
4 | E4T19 | 43310955201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-03-29 | 148094245 | 151713231 | 158402319 | 3618985.82 | 1375000 | 159445264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375000 | 0 | 0 | 0 | 0 | 0 | 1375000 | 1375000 | 159777319 | 159445264 | -332055 | 130080160 | B1:B5:B8:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
4 | E4U89 | 43793425201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-21 | 8845801 | 9316076 | 9643209 | 470274.51 | 0 | 9721461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9643209 | 9721461 | 78252 | 8524313
4 | E4V48 | 44346115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-05-06 | 6383851 | 6383851 | 5949070 | 0 | 0 | 5949070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5949070 | 5949070 | 0 | 10090648
4 | E4V49 | 44399515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-12-03 | 5064095 | 5491766 | 5407331 | 427671.8 | 0 | 5466066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5407331 | 5466066 | 58735 | 4246639
4 | E4V50 | 43975915201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-02 | 2437437 | 2522997 | 2472614 | 85560.06 | 0 | 2472614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2472614 | 2472614 | 0 | 2462556
4 | E4V74 | 43975415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-03-04 | 2591421 | 2746776 | 2777528 | 155354.84 | 0 | 2779572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777528 | 2779572 | 2044 | 2367933
4 | E4V97 | 44175915201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2022-11-04 | 3019043 | 3019043 | 2884719 | 0 | 0 | 2884627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2884719 | 2884627 | -92 | 2305583
4 | E4W07 | 44359015201 | F461192152 | UAG CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-05-27 | 9977382 | 10834234 | 10461717 | 856851.64 | 0 | 10387691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10461717 | 10387691 | -74027 | 11240081
4 | E4W15 | 44611215201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-02-03 | 2771566 | 2822338 | 2686822 | 50771.57 | 0 | 2675635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 3211732
4 | E4W39 | 44412115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-02-03 | 2588046 | 2588046 | 2728223 | 0 | 0 | 2725656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 2290170
4 | E4W40 | 44609915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2023-03-03 | 1223473 | 1223473 | 1121989 | 0 | -50970 | 1027689 | -50970 | 0 | 0 | 0 | 0 | 0 | -50970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50970 | 1071019 | 1027689 | -43330 | 1203020
4 | E4W49 | 44637115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-07 | 4434511 | 4502024 | 4183947 | 67512.92 | 0 | 4189012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4183947 | 4189012 | 5065 | 5579256
4 | E4W50 | 44610715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-03-03 | 2849827 | 2874613 | 2894545 | 24785.25 | 0 | 2891318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2894545 | 2891318 | -3227 | 2610595
4 | E4W58 | 44004615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 2786872 | 2833359 | 2656902 | 46486.19 | 0 | 2656977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2656902 | 2656977 | 75 | 2491562
4 | E4W68 | 44619815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-01 | 1533318 | 1533318 | 1448228 | 0 | 0 | 1445431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448228 | 1445431 | -2797 | 1669882
4 | T4434 | 23144025201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2016-06-15 | 26848292 | 32229320 | 31919676 | 5381028.79 | 0 | 32233319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31919676 | 32233319 | 313643 | 25701172 | B1 | ACC - NO EXCUSE BONUS
4 | T4472 | 41934525201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 33359900 | 33746993 | 33295065 | 387092.98 | -75000 | 33641803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75000 | 0 | 0 | 0 | 0 | 0 | -75000 | -75000 | 33220065 | 33641803 | 421739 | 37475056 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4477 | 23025665201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 45221786 | 46013498 | 47012029 | 791712.01 | 0 | 47480610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47012029 | 47480610 | 468581 | 48103370 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4566 | 43976115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 4627786 | 4748358 | 4545695 | 120572.24 | 0 | 4643097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545695 | 4643097 | 97402 | 5224694
4 | T4585 | 43533715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 15518729 | 16395821 | 15822170 | 877092.1 | 0 | 15987859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 15323089 | A6 | ICC - BAM/INCENTIVE-DISINCENT
4 | T4595 | 43206685201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-01-26 | 11281680 | 11586874 | 11564646 | 305193.71 | 0 | 11634264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11564646 | 11634264 | 69618 | 11191547
4 | T4596 | 43206695201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 8895418 | 8898040 | 8723470 | 2622.59 | -189300 | 8793135 | -189300 | 0 | 0 | 0 | 0 | 0 | -189300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -189300 | 8534170 | 8793135 | 258966 | 8602890
4 | T4598 | 44399615201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2022-02-23 | 5606708 | 5800857 | 5331108 | 194148.24 | 0 | 5379412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5331108 | 5379412 | 48304 | 4811999
4 | T4599 | 43177045201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-02-23 | 6578249 | 6638837 | 6561389 | 60588.18 | 0 | 6775408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6561389 | 6775408 | 214019 | 7009923
4 | T4610 | 44426515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4142494 | 4142494 | 3658735 | 0 | 0 | 3642576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 4002406
4 | T4611 | 44158215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 7152130 | 7150760 | 6812663 | -1370 | 0 | 6766023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | 8132476
4 | T4612 | 42957645201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-04-27 | 6700410 | 6959205 | 7215672 | 258794.43 | 0 | 7199967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 6372835
4 | T4618 | 44384315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 1266009 | 1266009 | 1196561 | 0 | 0 | 1196630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 1146916
4 | T4619 | 44617715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 7958317 | 8109946 | 8174515 | 151628.36 | 0 | 8136642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8174515 | 8136642 | -37873 | 9211939
4 | T4624 | 43783245201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 12698955 | 12584827 | 12539323 | -114127.68 | 0 | 12390285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12539323 | 12390285 | -149037 | 16805865
4 | T4625 | 44175515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3558974 | 3558974 | 3328234 | 0 | 0 | 3328234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3328234 | 3328234 | 0 | 3996956
4 | T4634 | 44177015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1746923 | 1746923 | 1740697 | 0 | 0 | 1736981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 1767920
4 | T4636 | 44384415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 798900 | 798900 | 732677 | 0 | 0 | 732677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732677 | 732677 | 0 | 879882
4 | T4637 | 44359115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 2144351 | 2144351 | 2073909 | 0 | 50000 | 2068781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 2123909 | 2068781 | -55128 | 2377317 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4640 | 43771715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 6949432 | 7359443 | 7308401 | 410010.11 | 0 | 7303926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 6229901
4 | T4642 | 44610315201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 2584711 | 2601574 | 2230880 | 16862.56 | 0 | 2230536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 2408671
4 | T4644 | 44610915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 6184480 | 6236790 | 6263543 | 52310.27 | 0 | 6233757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6263543 | 6233757 | -29786 | 5567899
4 | T4647 | 44699815201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2023-09-27 | 555556 | 555556 | 522780 | 0 | 0 | 522780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522780 | 522780 | 0 | 659610
4 | T4678 | 45222615201 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 654155 | 654155 | 630879 | 0 | 0 | 630879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630879 | 630879 | 0 | 832302
5 | E50B7 | 44519015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-03-22 | 5675430 | 5781935 | 5808256 | 106505.2 | 0 | 5808213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5808256 | 5808213 | -42 | 4958775
5 | E50B9 | 44530415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-11-01 | 8212061 | 8298265 | 8545900 | 86204.44 | 0 | 8512173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8545900 | 8512173 | -33727 | 8347740
5 | E50F0 | 44985615201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-01-04 | 512012 | 512012 | 459051 | 0 | 0 | 459051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459051 | 459051 | 0 | 709685
5 | E50F8 | 45056015201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2024-02-06 | 265206 | 286124 | 270632 | 20917.91 | 0 | 270632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270632 | 270632 | 0 | 184540
5 | E51A5 | 44102115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-04 | 6379293 | 6413111 | 6546701 | 33817.95 | 0 | 6602247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6546701 | 6602247 | 55546 | 5366279
5 | E52B5 | 44892215201 | F274499988 | UNDERWATER MECHANIX SERVICES LL | N/A | N/A | N/A | N/A | 2022-11-01 | 1894138 | 1894138 | 1942917 | 0 | -13063 | 1929854 | -13063 | 0 | 0 | 0 | 0 | 0 | -13063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13063 | 1929854 | 1929854 | 0 | 2335390
5 | E55A2 | 44539515201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2022-05-03 | 2300883 | 2307982 | 2243671 | 7099.26 | 0 | 2243671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243671 | 2243671 | 0 | 3525844
5 | E55B6 | 44935915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-12-06 | 1222662 | 1249746 | 1348640 | 27084.29 | 0 | 1348640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348640 | 1348640 | 0 | 1969965
5 | E56A6 | 43585935201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-08 | 26294705 | 26513733 | 26091334 | 219027.86 | 0 | 26738257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26091334 | 26738257 | 646923 | 25307968
5 | E56B1 | 44892415201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2023-03-07 | 284414 | 284414 | 279401 | 0 | 0 | 279401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279401 | 279401 | 0 | 357219
5 | E56B5 | 44520815201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-02-09 | 4388512 | 4453426 | 4571799 | 64913.46 | 0 | 4554639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4571799 | 4554639 | -17160 | 5307735
5 | E56B7 | 44852015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2023-02-09 | 3806259 | 3806259 | 3824085 | 0 | 0 | 3824085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824085 | 3824085 | 0 | 4832737
5 | E56B9 | 44892315201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2023-03-07 | 698401 | 698401 | 660240 | 0 | 0 | 660240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660240 | 660240 | 0 | 801387
5 | E57B0 | 44139515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-04-04 | 1915338 | 1915338 | 1927494 | 0 | 0 | 1927350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 1563670
5 | E57B9 | 44709915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-06-06 | 7890001 | 7890001 | 8013155 | 0 | 0 | 8041936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8013155 | 8041936 | 28780 | 9077031
5 | E58A3 | 44288315201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-05-03 | 4049477 | 4613851 | 4761016 | 564373.65 | 0 | 4731574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4761016 | 4731574 | -29441 | 4247697
5 | E58B0 | 44878915201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 2634873 | 2681332 | 2729605 | 46459.81 | 0 | 2729605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2729605 | 2729605 | 0 | 1708500
5 | E58B9 | 45050715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-04-04 | 2493493 | 2493493 | 2516855 | 0 | 0 | 2516855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516855 | 2516855 | 0 | 2557573
5 | E59B1 | 44521215201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 5421862 | 5450128 | 5275721 | 28266.42 | 0 | 5273757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5275721 | 5273757 | -1964 | 5678331
5 | E59B7 | 44290715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-06-06 | 7869434 | 8074202 | 8845045 | 204768 | 0 | 8849151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8845045 | 8849151 | 4106 | 10565451
5 | T5721 | 44287515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 16561765 | 17284645 | 18223735 | 722880 | 0 | 18790296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18223735 | 18790296 | 566560 | 18568889
5 | T5725 | 44351215201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 4062453 | 4217199 | 4121213 | 154746.07 | 0 | 4064034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4121213 | 4064034 | -57178 | 5797838
5 | T5728 | 44395815201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 34500000 | 35703756 | 38083377 | 1203756.14 | -17738 | 39463048 | 0 | 0 | 0 | 0 | 0 | -5932 | -5932 | -11806 | 0 | 0 | 0 | 0 | 0 | -11806 | -17738 | 38065638 | 39463048 | 1397410 | 32771897
5 | T5729 | 43565715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 10638248 | 10677535 | 11115999 | 39287.05 | 0 | 11021098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 15691232
5 | T5740 | 43898215201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 2406406 | 2511349 | 2568507 | 104942.61 | 0 | 2566717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568507 | 2566717 | -1791 | 2297944
5 | T5743 | 43793515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 4388956 | 6723005 | 6937593 | 2334048.92 | 0 | 6936863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6937593 | 6936863 | -730 | 4734608
5 | T5745 | 43219355201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-06-15 | 7356536 | 7830549 | 7924589 | 474013.01 | 0 | 7873593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7924589 | 7873593 | -50996 | 10192519
5 | T5755 | 44568715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 1071415 | 1072209 | 1061331 | 793.38 | 0 | 1059847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061331 | 1059847 | -1484 | 734929
5 | T5762 | 44351415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2950212 | 2990212 | 3032852 | 40000 | 0 | 3032337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 1861686
5 | T5764 | 44581315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-10-05 | 2470270 | 2521141 | 2333135 | 50870.79 | 0 | 2331897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333135 | 2331897 | -1237 | 2317409
5 | T5767 | 44101615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-12-07 | 10858007 | 11031557 | 11200282 | 173549.92 | -5737 | 11153083 | 0 | 0 | 0 | 0 | 0 | -5737 | -5737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5737 | 11194546 | 11153083 | -41463 | 11024234
5 | T5769 | 44571515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-10-05 | 1830300 | 1832918 | 1800435 | 2618.11 | 0 | 1800417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800435 | 1800417 | -18 | 1120306
5 | T5772 | 44569315201 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2022-10-26 | 1859536 | 1934513 | 2110697 | 74976.99 | 0 | 2110337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2110697 | 2110337 | -360 | 1660928
5 | T5775 | 44570715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 937052 | 937052 | 953863 | 0 | 0 | 953841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953863 | 953841 | -22 | 869794
5 | T5776 | 44577115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 1821012 | 1822431 | 1669665 | 1418.98 | 0 | 1669182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669665 | 1669182 | -483 | 749626
5 | T5783 | 44576715201 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 2041154 | 2041154 | 2088238 | 0 | -10982 | 2076683 | 0 | 0 | 0 | 0 | 0 | -10982 | -10982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10982 | 2077256 | 2076683 | -573 | 1415550
5 | T5790 | 44976415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 752281 | 730305 | 733353 | -21975.86 | 0 | 733353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733353 | 733353 | 0 | 919900
5 | T5803 | 44760315201 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2023-09-13 | 1608172 | 1608172 | 1619759 | 0 | 0 | 1619759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1619759 | 1619759 | 0 | 1561950
5 | T5820 | 45222925201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 607569 | 607569 | 467724 | 0 | 0 | 467724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467724 | 467724 | 0 | 1006633
5 | T5821 | 45222935201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 843345 | 843345 | 748398 | 0 | 0 | 748398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748398 | 748398 | 0 | 1601075
6 | E6K68 | 43652615201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-29 | 14750000 | 15707585 | 16003611 | 957584.88 | 0 | 15768021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16003611 | 15768021 | -235590 | 9735203
6 | E6M58 | 44492015201 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2021-05-11 | 5167117 | 5569451 | 5567027 | 402333.53 | 0 | 5567027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5567027 | 5567027 | 0 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6M98 | 43029159201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-24 | 6969697 | 6904270 | 6963848 | -65426.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6963848 | 0 | -6963848 | 9167407 | LBDB | LOW BID DESIGN BUILD
6 | E6M99 | 44694715201 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2022-04-11 | 2597679 | 2701239 | 2676164 | 103559.73 | 0 | 2676164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676164 | 2676164 | 0 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
6 | E6O05 | 44619115201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2023-05-25 | 743939 | 1132936 | 975348 | 388997.02 | 0 | 975348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975348 | 975348 | 0 | 699899
6 | E6O13 | 44890615201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-01-26 | 572000 | 572000 | 522404 | 0 | 0 | 521792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522404 | 521792 | -612 | 519556
6 | E6O14 | 44882815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-04-27 | 1149149 | 1149149 | 1071932 | 0 | 0 | 1071773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071932 | 1071773 | -159 | 1084774
6 | E6O30 | 44734515201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-04-27 | 897000 | 897000 | 747267 | 0 | 0 | 747246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747267 | 747246 | -21 | 902746
6 | E6O72 | 43029179201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2023-06-12 | 1937336 | 1987336 | 1966014 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1966014 | 0 | -1966014 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6O74 | 44480115201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-28 | 3862848 | 4787648 | 4857931 | 924799.11 | 0 | 4857931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4857931 | 4857931 | 0 | 7127639
6 | T6461 | 43647915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 3700000 | 3848832 | 3802731 | 148832.12 | 320000 | 3835748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 4423635 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6494 | 42752125201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 4221888 | 4224163 | 3676222 | 2275 | 200000 | 3699956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3876222 | 3699956 | -176266 | 4370413 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6504 | 42918525201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-05-26 | 5189595 | 5303929 | 5374583 | 114333.32 | 0 | 5469555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5374583 | 5469555 | 94972 | 5707743 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6535 | 44389315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 18130831 | 18586475 | 18825792 | 455644.58 | 0 | 19314726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18825792 | 19314726 | 488935 | 17118737 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6538 | 44391915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 13790706 | 13840706 | 13459785 | 50000 | 480000 | 13298540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 480000 | 480000 | 13939785 | 13298540 | -641245 | 12736630 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6549 | 44390715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 4134866 | 4134866 | 3997859 | 0 | 220000 | 3985462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6552 | 44393615201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-01-25 | 5851269 | 5854220 | 5799051 | 2950.56 | 240000 | 5779273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000 | 6039051 | 5779273 | -259779 | 6438228 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6559 | 43094925201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 8056848 | 8075952 | 7918898 | 19104 | 0 | 7953812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7918898 | 7953812 | 34913 | 7161376 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6569 | 44392715201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 3310000 | 3360000 | 3413946 | 50000 | 140000 | 3413962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 3553946 | 3413962 | -139984 | 3762936 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6570 | 44391015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-01-25 | 1901127 | 1901127 | 1885735 | 0 | 0 | 1881176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 1978037
6 | T6572 | 44390615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-03-29 | 2360100 | 2360100 | 2343530 | 0 | 0 | 2341786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343530 | 2341786 | -1744 | 2712982
7 | E7M37 | 43514215201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-31 | 80980890 | 84381295 | 85368473 | 3400405.46 | 0 | 85649427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85368473 | 85649427 | 280953 | 87914530
7 | E7N73 | 43955315201 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2021-02-10 | 6131310 | 6338797 | 6305080 | 207487.31 | -570912 | 5734168 | -570912 | 0 | 0 | 0 | 0 | 0 | -570912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -570912 | 5734168 | 5734168 | 0 | 6350300
7 | E7P11 | 44605115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-01-11 | 5505947 | 5505947 | 5635303 | 0 | 0 | 5624110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5635303 | 5624110 | -11193 | 5708568
7 | E7P19 | 44025415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-01-11 | 5191258 | 5191258 | 5651758 | 0 | 0 | 5623798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 5707114
7 | E7P32 | 44165215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-08 | 6091557 | 6416319 | 6316136 | 324761.8 | 0 | 6190704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6316136 | 6190704 | -125432 | 6992900
7 | E7P35 | 44165715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-05-11 | 8986578 | 9084687 | 9016111 | 98109.75 | 0 | 8844228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9016111 | 8844228 | -171882 | 8393400
7 | E7P50 | 41685625201 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2024-02-14 | 388968 | 388968 | 314971 | 0 | 0 | 314971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314971 | 314971 | 0 | 427400
7 | E7P81 | 44165615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-04-12 | 2391656 | 2492761 | 2474615 | 101104.64 | 0 | 2474272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 2000400
7 | E7P96 | 44378315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-06-07 | 5338647 | 5338647 | 5375414 | 0 | 0 | 5376462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375414 | 5376462 | 1048 | 5546100
7 | E7Q14 | 44349215201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 2636615 | 2636615 | 2586233 | 0 | 0 | 2586234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586233 | 2586234 | 1 | 2170285
7 | E7Q20 | 44380615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1219976 | 1219975 | 1270757 | -0.94 | 0 | 1271460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | 1145700
7 | E7Q21 | 44602615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 2654159 | 2684159 | 2759623 | 30000 | 0 | 2762434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 2504300
7 | E7Q22 | 44165315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-07 | 1489626 | 1494272 | 1546615 | 4645.84 | 0 | 1547180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 1595200
7 | E7R09 | 42421335201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2020-01-31 | 38345345 | 38534960 | 39399650 | 189615.46 | 0 | 39399650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39399650 | 39399650 | 0 | 39771136 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | E7R20 | 41075525201 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2018-05-15 | 56246888 | 59724057 | 59431792 | 3477169.13 | 0 | 59377550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59431792 | 59377550 | -54242 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | T7438 | 25632425201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 16728833 | 18036076 | 18122029 | 1307243.7 | 0 | 19133675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18122029 | 19133675 | 1011645 | 19921100
7 | T7449 | 43953215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 4459994 | 4666559 | 4582670 | 206564.97 | 0 | 4694270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4582670 | 4694270 | 111600 | 4598900
7 | T7458 | 25688155201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-01-27 | 7962187 | 8615404 | 9137155 | 653217.25 | 0 | 9152768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9137155 | 9152768 | 15613 | 5285500
7 | T7464 | 43307125201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 5977271 | 5963393 | 5896599 | -13878.18 | 0 | 5865873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5896599 | 5865873 | -30725 | 4795700
7 | T7475 | 43764415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-05-26 | 4773108 | 4959207 | 5090768 | 186098.67 | 0 | 5095464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5090768 | 5095464 | 4697 | 4701400
7 | T7481 | 44073315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 3304021 | 3304021 | 3182990 | 0 | 0 | 3174072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3182990 | 3174072 | -8918 | 3303500
7 | T7482 | 43983115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 11256386 | 10574479 | 10748589 | -681906.37 | 0 | 11080512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10748589 | 11080512 | 331923 | 13466700
7 | T7492 | 44024815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 5438332 | 5435828 | 5441055 | -2504.17 | 0 | 5414623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5441055 | 5414623 | -26432 | 5496384
7 | T7497 | 43940115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 7112946 | 7172036 | 7363800 | 59090.83 | 0 | 7329386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7363800 | 7329386 | -34413 | 6545800
7 | T7506 | 44549415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-03-29 | 4477908 | 4477908 | 4516174 | 0 | 0 | 4513509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 4643300
7 | T7518 | 45248755201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 908274 | 908274 | 908491 | 0 | 0 | 908491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908491 | 908491 | 0 | 1515975
8 | E8R80 | 43554315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-06-11 | 244979349 | 251466172 | 261302745 | 6486823.61 | 4375439 | 264352629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375439 | 0 | 0 | 0 | 0 | 0 | 4375439 | 4375439 | 265678184 | 264352629 | -1325555 | 217827999 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8R82 | 43801815201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 61180000 | 61481136 | 64048083 | 301135.77 | 0 | 65938908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64048083 | 65938908 | 1890825 | 58657847 | A3 | ICC - DESIGN/BUILD - MINOR
8 | E8S90 | 43945755201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-04-20 | 21999573 | 23015619 | 24415437 | 1016045.86 | 0 | 25168122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24415437 | 25168122 | 752685 | 23025803
8 | E8T40 | 44497815201 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2021-12-14 | 3179902 | 3285956 | 3273170 | 106053.94 | 0 | 3273170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3273170 | 3273170 | 0 | 3360453
8 | E8T67 | 44262415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-04-12 | 12517000 | 12877010 | 12203064 | 360009.96 | 0 | 12123596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12203064 | 12123596 | -79468 | 13936524
8 | E8T77 | 44925315201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-05-17 | 5565378 | 5757378 | 5730235 | 192000 | 0 | 5763102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5730235 | 5763102 | 32867 | 5213380
8 | E8T82 | 42897215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-13 | 2504148 | 2711373 | 2646645 | 207225.59 | 0 | 2646645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2646645 | 2646645 | 0 | 4806557
8 | E8T94 | 43578625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-25 | 2596848 | 2612139 | 2505813 | 15291.47 | 0 | 2503780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2505813 | 2503780 | -2033 | 2699146
8 | E8T95 | 44171915201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-10-25 | 21849074 | 22014286 | 22325271 | 165212 | 0 | 22094324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22325271 | 22094324 | -230948 | 21254880
8 | E8U06 | 44262295201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2023-06-08 | 4494080 | 4544080 | 4339328 | 50000 | 0 | 4339341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4339328 | 4339341 | 13 | 5696150
8 | E8U07 | 44969215201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-04-11 | 3578802 | 3752049 | 3491844 | 173246.5 | 0 | 3491287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3491844 | 3491287 | -556 | 2800800
8 | E8U10 | 44933415201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-02-14 | 870362 | 876241 | 829659 | 5879.55 | 0 | 829659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829659 | 829659 | 0 | 937384
8 | E8U47 | 43854915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-09-12 | 1133672 | 1158672 | 1068668 | 25000 | 0 | 1068668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 2868747
8 | E8U57 | 44942315201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2023-09-12 | 1336393 | 1336393 | 1288438 | 0 | 0 | 1288438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288438 | 1288438 | 0 | 1342593

## Sheet1 (hidden)
01CO | 01 | T1805 | 43943115201 | 2021-07-28 | QTR1 | 21/22 | 2 | 2 | 300 | 388 | 388 | 0 | 0 | 0 | 88 | 0 | 6184000 | 84041 | 6099959 | 6204651 | 6014186 | 0 | 0 | 0 | 6014186 | 6704450 | 698558 | 20651 | 56 | 0 | 0 | 14008 | 0 | 0 | 0 | 16372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38675 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-02-28 | QTR3 | 24/25 | 2022-11-30 | QTR2 | 22/23 | 118 | 7780401.21 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO | 7 | 01co | 1 | 7
01CO | 01 | T1825 | 43982715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 11 | 350 | 671 | 668 | 3 | 0 | 0 | 147 | 174 | 8278071 | 77832 | 8200239 | 8939807 | 8867401 | 0 | 0 | 0 | 8867401 | 8929131 | 86356 | 661736 | 124 | 0 | 30 | 233423 | 0 | 0 | 62 | 279341 | 35169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24626 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 136058 | 363218 | 0 | 0 | 0 | 0 | 0 | 174 | 673447 | 398388 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-05-29 | QTR4 | 23/24 | 118 | 7852554.7 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO | 13 | 01do | 8 | 20
01CO | 01 | T1846 | 44156115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 200 | 308 | 297 | 11 | 0 | 0 | 108 | 0 | 3477042 | 50000 | 3427042 | 3477042 | 3332356 | 0 | 0 | 0 | 3332356 | 3320317 | -12039 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-01 | QTR1 | 24/25 | 2024-05-09 | QTR4 | 23/24 | 113 | 3367085.92 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 29 | 02co | 21 | 49
01CO | 01 | T1847 | 43805715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 6 | 130 | 247 | 247 | 0 | 0 | 0 | 107 | 10 | 1159034 | 0 | 1159034 | 1218049 | 1206007 | 0 | 0 | 0 | 1206007 | 1205156 | -851 | 59015 | 83 | 0 | 0 | 0 | 0 | 0 | 12 | 59015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59015 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 118 | 1023962.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 5 | 02do | 50 | 54
01CO | 01 | T1848 | 44593215201 | 2022-12-07 | QTR2 | 22/23 | 2 | 2 | 300 | 384 | 382 | 2 | 0 | 0 | 84 | 0 | 13310586 | 146142 | 13164444 | 13399125 | 12912681 | 0 | 0 | 0 | 12912681 | 12823061 | -89620 | 88540 | 29 | 0 | 0 | 82557 | 0 | 0 | 0 | 27850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -469 | 0 | 29 | 0 | 8021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 117959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-01-29 | QTR3 | 24/25 | 2024-05-16 | QTR4 | 23/24 | 118 | 14760503.34 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 32 | 03co | 55 | 86
01CO | 01 | T1860 | 43709615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 9 | 250 | 401 | 398 | 3 | 0 | 0 | 151 | 0 | 4325722 | 50000 | 4275722 | 4504283 | 4508752 | 0 | 0 | 0 | 4508752 | 4493121 | -11661 | 178561 | 124 | 0 | 0 | 28409 | 0 | 0 | 0 | 105237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5020 | 5020 | 0 | 0 | 23159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165795 | 5020 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-10-14 | QTR2 | 24/25 | 2024-05-22 | QTR4 | 23/24 | 113 | 2709382.82 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO | 11 | 03do | 87 | 97
01CO | 01 | T1871 | 45224115201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 174 | 196 | 195 | 1 | 0 | 0 | 22 | 0 | 3701415 | 50000 | 3651415 | 3701415 | 3225904 | 0 | 0 | 0 | 3225904 | 3225904 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-03 | QTR2 | 24/25 | 2024-06-16 | QTR4 | 23/24 | 107 | 4091495.64 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO | 24 | 04co | 98 | 121
01DO | 01 | E1U15 | 44448515201 | 2022-01-13 | QTR3 | 21/22 | 2 | 2 | 450 | 635 | 634 | 1 | 0 | 0 | 185 | 0 | 9191000 | 87099 | 9103901 | 9286906 | 8593729 | 0 | 0 | 0 | 8593729 | 8770370 | 272547 | 95906 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101654 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-11 | QTR1 | 24/25 | 2024-04-25 | QTR4 | 23/24 | 113 | 9151070.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO | 15 | 04do | 122 | 136
01DO | 01 | E1U16 | 44742915201 | 2023-07-20 | QTR1 | 23/24 | 1 | 2 | 225 | 277 | 276 | 1 | 0 | 0 | 49 | 3 | 7395393 | 70545 | 7324848 | 7483422 | 7804114 | 0 | 0 | 0 | 7804114 | 7806499 | 2385 | 88029 | 41 | 0 | 3 | 129977 | 0 | 0 | 0 | 10432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 140409 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-02-10 | QTR3 | 24/25 | 2024-10-25 | QTR2 | 24/25 | 108 | 7252828.57 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO | 20 | 05co | 137 | 156
01DO | 01 | E1U97 | 44789615201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 525 | 663 | 663 | 0 | 0 | 0 | 138 | 0 | 3990000 | 50000 | 3940000 | 4021977 | 3979990 | 0 | 0 | 0 | 3979990 | 3978102 | -1888 | 31977 | 22 | 0 | 0 | 39990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 39990 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-06-02 | QTR4 | 23/24 | 115 | 1965526.04 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 49 | 0 | 0 | 0 | 0 | T | DO | 20 | 05do | 157 | 176
01DO | 01 | E1V11 | 44504315201 | 2023-01-19 | QTR3 | 22/23 | 1 | 2 | 150 | 254 | 249 | 5 | 0 | 0 | 104 | 0 | 2582000 | 50000 | 2532000 | 2736729 | 2706856 | 0 | 0 | 0 | 2706856 | 2588087 | -2261 | 154729 | 25 | 0 | 0 | 4229 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 116508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 168490 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-07 | QTR3 | 24/25 | 2024-05-06 | QTR4 | 23/24 | 115 | 3004848.32 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | DO | 11 | 06co | 177 | 187
01DO | 01 | E1V15 | 44547115201 | 2023-01-19 | QTR3 | 22/23 | 2 | 0 | 225 | 427 | 410 | 17 | 0 | 0 | 74 | 128 | 7937275 | 81977 | 7855298 | 7937275 | 7998691 | 0 | 0 | 0 | 7998691 | 7941859 | -56832 | 0 | 102 | 0 | 5 | 23878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 28296 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-12-18 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 108 | 8527986.56 |  |  | 128 | 26 | 0 | 0 | 0 | 0 |  | DO | 10 | 06do | 188 | 197
01DO | 01 | E1V16 | 44405015201 | 2022-06-09 | QTR4 | 21/22 | 2 | 3 | 282 | 402 | 402 | 0 | 0 | 0 | 116 | 4 | 5610556 | 50000 | 5560556 | 5735677 | 5817092 | 0 | 0 | 0 | 5817092 | 5791996 | -22111 | 125122 | 30 | 0 | 4 | 122770 | 0 | 17 | 0 | 20695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 12551 | 0 | 0 | 0 | 0 | 0 | 60 | 4 | 165375 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 | 2024-05-15 | QTR4 | 23/24 | 108 | 4321005.33 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 26 | 0 | 0 | 0 | 0 |  | DO | 11 | 07co | 198 | 208
01DO | 01 | E1V18 | 44620815201 | 2023-03-16 | QTR3 | 22/23 | 1 | 3 | 300 | 381 | 375 | 6 | 0 | 0 | 63 | 18 | 11855203 | 111820 | 11743383 | 12344460 | 12567270 | 0 | 0 | 0 | 12567270 | 12562055 | -5215 | 489257 | 36 | 0 | 5 | 23548 | 0 | 0 | 13 | 491849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 525875 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-19 | QTR3 | 24/25 | 2024-09-24 | QTR1 | 24/25 | 118 | 11076911.57 |  |  | 5 | 27 | 0 | 0 | 0 | 0 |  | DO | 15 | 07do | 209 | 223
01DO | 01 | E1V61 | 44622815201 | 2022-10-10 | QTR2 | 22/23 | 1 | 2 | 400 | 536 | 531 | 5 | 0 | 0 | 72 | 64 | 5258695 | 50000 | 5208695 | 5702540 | 5768353 | 0 | 0 | 0 | 5768353 | 5707872 | -60481 | 443845 | 34 | 0 | 5 | 16799 | 0 | 0 | 49 | 420905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 38929 | 22940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 476632 | 22940 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 | 2024-05-18 | QTR4 | 23/24 | 118 | 6337132.03 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 15 | 38 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 224 | 223
01DO | 01 | E1W10 | 44744115201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 200 | 258 | 255 | 3 | 0 | 0 | 58 | 0 | 5126611 | 54498 | 5072113 | 5135303 | 4999771 | 0 | 0 | 0 | 4999771 | 4990201 | -9570 | 8692 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-07-12 | QTR1 | 24/25 | 108 | 5933693.34 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO | 14 | 08do | 224 | 237
01DO | 01 | E1W12 | 44738215201 | 2024-03-21 | QTR3 | 23/24 | 1 | 0 | 150 | 179 | 162 | 17 | 0 | 0 | 29 | 0 | 3349511 | 50000 | 3299511 | 3349511 | 3342095 | 0 | 0 | 0 | 3342095 | 3331252 | -10843 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-02-26 | QTR3 | 24/25 | 2024-12-16 | QTR2 | 24/25 | 115 | 3912147.05 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W15 | 44464315201 | 2023-08-17 | QTR1 | 23/24 | 1 | 1 | 180 | 185 | 181 | 4 | 0 | 0 | 5 | 0 | 572414 | 24523 | 547891 | 613908 | 573719 | 0 | 0 | 0 | 573719 | 573719 | 0 | 41494 | 0 | 0 | 0 | 3819 | 0 | 0 | 0 | 37675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41494 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2024-08-06 | QTR1 | 24/25 | 108 | 767485.45 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W19 | 44743315201 | 2023-10-19 | QTR2 | 23/24 | 1 | 0 | 175 | 202 | 197 | 5 | 0 | 0 | 27 | 0 | 3927820 | 50000 | 3877820 | 3927820 | 3916235 | 0 | 0 | 0 | 3916235 | 3896792 | -19443 | 0 | 18 | 0 | 0 | 5190 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11509 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-12-12 | QTR2 | 24/25 | 2024-09-23 | QTR1 | 24/25 | 108 | 3787595.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1W20 | 44620215201 | 2023-10-19 | QTR2 | 23/24 | 1 | 1 | 150 | 186 | 186 | 0 | 0 | 0 | 36 | 0 | 2630586 | 50000 | 2580586 | 2630586 | 2573059 | 0 | 0 | 0 | 2573059 | 2559128 | -13930 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20390 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-09-12 | QTR1 | 24/25 | 118 | 2937557.72 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2804 | 44137215201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 300 | 903 | 903 | 0 | 0 | 0 | 179 | 424 | 7398298 | 61648 | 7336650 | 7431649 | 7733354 | 0 | 0 | 0 | 7733354 | 7955154 | 240397 | 33351 | 348 | 0 | 0 | 35071 | 0 | 0 | 173 | 51032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 3351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 89454 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 | 2024-03-02 | QTR3 | 23/24 | 208 | 6176554.21 |  |  | 424 | 82 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2820 | 43231615201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 175 | 202 | 214 | -12 | 12 | 0 | 27 | 0 | 6513333 | 72235 | 6441098 | 6536983 | 6298184 | -45432 | 0 | -45432 | 6252752 | 6708811 | 456060 | 23650 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-09-12 | QTR1 | 24/25 | 2022-08-05 | QTR1 | 22/23 | 209 | 8131499.13 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2828 | 44105015201 | 2021-12-08 | QTR2 | 21/22 | 3 | 6 | 200 | 680 | 680 | 0 | 0 | 0 | 229 | 251 | 2858409 | 52000 | 2806409 | 2966328 | 3044806 | 0 | 0 | 0 | 3044806 | 3042275 | 2144 | 107919 | 320 | 0 | 0 | 42323 | 0 | 0 | 87 | 103244 | 17949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 164 | 4676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 251 | 150243 | 17949 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 208 | 3146528.67 |  |  | 164 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2834 | 44326115201 | 2022-01-26 | QTR3 | 21/22 | 3 | 4 | 323 | 588 | 586 | 2 | 0 | 0 | 241 | 24 | 9753946 | 119957 | 9633988 | 9932433 | 10044314 | 0 | 0 | 0 | 10044314 | 10183014 | 140312 | 178487 | 171 | 0 | 24 | 165501 | 9554 | 0 | 0 | 49043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 24 | 224382 | 9554 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-12 | QTR1 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 208 | 11499594 |  |  | 0 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2838 | 44342015201 | 2022-04-27 | QTR4 | 21/22 | 2 | 5 | 300 | 661 | 661 | 0 | 0 | 0 | 223 | 138 | 11945708 | 100832 | 11844876 | 12005007 | 12120635 | 0 | 0 | 0 | 12120635 | 12067135 | -46610 | 59300 | 126 | 0 | 44 | 87730 | 0 | 0 | 91 | 40079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 134699 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 | 2024-07-17 | QTR1 | 24/25 | 208 | 12401357.97 |  |  | 69 | 97 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2843 | 21023045201 | 2022-05-25 | QTR4 | 21/22 | 3 | 2 | 450 | 800 | 795 | 5 | 0 | 0 | 212 | 138 | 12094446 | 152516 | 11941930 | 12285295 | 12375077 | 0 | 0 | 0 | 12375077 | 12184067 | -191010 | 190849 | 142 | 0 | 91 | 243953 | 0 | 0 | 47 | 66569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 138 | 310522 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-21 | QTR3 | 24/25 | 2024-10-08 | QTR2 | 24/25 | 216 | 15875563.44 |  |  | 35 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2853 | 44714915201 | 2022-06-08 | QTR4 | 21/22 | 3 | 4 | 540 | 680 | 663 | 17 | 0 | 0 | 120 | 20 | 17135161 | 200000 | 16935161 | 17359701 | 17949301 | 0 | 0 | 0 | 17949301 | 17746566 | -196328 | 224540 | 72 | 0 | 17 | 89971 | 0 | 0 | 27 | 312995 | 9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 6406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 337947 | 21170 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-08-30 | QTR1 | 24/25 | 208 | 22151002.61 |  |  | 40 | 48 | 0 | -25 | -83255 | 0 |  | CO
02CO | 02 | T2864 | 20765825201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 140 | 451 | 451 | 0 | 0 | 0 | 160 | 151 | 2568964 | 50000 | 2518964 | 2668964 | 2632044 | 0 | 0 | 0 | 2632044 | 2632301 | 257 | 100000 | 39 | 0 | 7 | 97145 | 0 | 0 | 44 | 48577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 145722 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-16 | QTR2 | 24/25 | 2024-08-22 | QTR1 | 24/25 | 214 | 2408715.47 |  |  | 151 | 121 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2896 | 44284815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 300 | 350 | 348 | 2 | 0 | 0 | 50 | 0 | 3802716 | 50000 | 3752716 | 3802716 | 3666172 | 0 | 0 | 0 | 3666172 | 3666172 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-02 | QTR1 | 24/25 | 2024-05-01 | QTR4 | 23/24 | 208 | 4117339.34 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2897 | 44554615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 0 | 250 | 424 | 424 | 0 | 0 | 0 | 173 | 1 | 7947765 | 109280 | 7838486 | 7947765 | 8246084 | 0 | 0 | 0 | 8246084 | 8193910 | -52174 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 10431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 13310 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-05-22 | QTR4 | 23/24 | 216 | 11037253 |  |  | 1 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2900 | 40392045201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 100 | 392 | 371 | 21 | 0 | 0 | 292 | 0 | 869247 | 37251 | 831996 | 869247 | 857258 | 0 | 0 | 0 | 857258 | 857258 | 0 | 0 | 173 | 0 | 0 | 2298 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 2298 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-14 | QTR1 | 24/25 | 216 | 1017097.24 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2908 | 44534215201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 250 | 439 | 436 | 3 | 0 | 0 | 183 | 6 | 7659724 | 70863 | 7588861 | 7761297 | 8108037 | 0 | 0 | 0 | 8108037 | 8070080 | -37957 | 101573 | 159 | 0 | 3 | 8735 | 0 | 0 | 3 | 126725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 6 | 135460 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-03-05 | QTR3 | 24/25 | 2024-11-13 | QTR2 | 24/25 | 208 | 7157174.01 |  |  | 6 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2909 | 44607915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 250 | 447 | 445 | 2 | 0 | 0 | 97 | 100 | 7130409 | 68620 | 7061789 | 7130409 | 7454415 | 0 | 0 | 0 | 7454415 | 7438691 | -15725 | 0 | 129 | 0 | 0 | 1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 3586 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-09-06 | QTR1 | 24/25 | 208 | 7319755.75 |  |  | 100 | 68 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2911 | 44703315201 | 2023-05-17 | QTR4 | 22/23 | 1 | 1 | 260 | 312 | 290 | 22 | 0 | 0 | 52 | 0 | 5899711 | 60196 | 5839515 | 5916585 | 5921537 | 0 | 0 | 0 | 5921537 | 5926778 | 5241 | 16874 | 26 | 0 | 0 | 9350 | 0 | 0 | 0 | 16874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36315 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-07-10 | QTR1 | 24/25 | 214 | 6079797.84 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2918 | 43911515201 | 2023-05-17 | QTR4 | 22/23 | 1 | 3 | 300 | 392 | 392 | 0 | 0 | 0 | 82 | 10 | 8269281 | 96437 | 8172844 | 8404947 | 8393938 | 0 | 0 | 0 | 8393938 | 8396288 | 2350 | 135667 | 54 | 0 | 10 | 137623 | 0 | 0 | 0 | 87496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 225119 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 | 2024-11-20 | QTR2 | 24/25 | 216 | 9740099 |  |  | 10 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2922 | 44717615201 | 2023-05-17 | QTR4 | 22/23 | 1 | 0 | 200 | 261 | 256 | 5 | 0 | 0 | 61 | 0 | 4768192 | 52010 | 4716182 | 4768192 | 4978398 | 0 | 0 | 0 | 4978398 | 4983434 | 5036 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-07-22 | QTR1 | 24/25 | 214 | 5253038.86 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2926 | 44703715201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 200 | 260 | 260 | 0 | 0 | 0 | 60 | 0 | 12488206 | 127946 | 12360260 | 12488206 | 12735786 | 0 | 0 | 0 | 12735786 | 12755313 | 19527 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-08-30 | QTR1 | 24/25 | 2024-05-28 | QTR4 | 23/24 | 214 | 12922548 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2927 | 44762935201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 98 | 93 | 5 | 0 | 0 | 8 | 0 | 737944 | 35849 | 702095 | 737944 | 698279 | 0 | 0 | 0 | 698279 | 698279 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-08 | QTR1 | 24/25 | 2024-04-09 | QTR4 | 23/24 | 214 | 752836.87 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2928 | 43195525201 | 2022-08-31 | QTR1 | 22/23 | 2 | 3 | 150 | 307 | 307 | 0 | 0 | 0 | 123 | 34 | 1070183 | 33534 | 1036649 | 1146536 | 1180671 | 0 | 0 | 0 | 1180671 | 1180315 | -356 | 76352 | 91 | 0 | 34 | 76352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 81752 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 | 2024-04-02 | QTR4 | 23/24 | 208 | 767498.48 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2929 | 44572415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 0 | 150 | 293 | 292 | 1 | 0 | 0 | 131 | 12 | 2525783 | 50000 | 2475783 | 2525783 | 2526018 | 0 | 0 | 0 | 2526018 | 2526018 | 0 | 0 | 123 | 0 | 0 | 17430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 12 | 17430 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-08 | QTR3 | 24/25 | 2024-09-13 | QTR1 | 24/25 | 214 | 2044903 |  |  | 12 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2931 | 44722615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 90 | 90 | 88 | 2 | 0 | 0 | 0 | 0 | 595321 | 34535 | 560785 | 595321 | 526968 | 0 | 0 | 0 | 526968 | 526968 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-05 | QTR1 | 24/25 | 2024-04-12 | QTR4 | 23/24 | 208 | 725236.05 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2933 | 44105815201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 466 | 475 | -9 | 9 | 0 | 86 | 140 | 10782106 | 108347 | 10673758 | 10551459 | 10447042 | -42921 | 0 | -42921 | 10404121 | 10297505 | -106616 | -230647 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 17760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | -224147 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-02 | QTR3 | 24/25 | 2024-07-03 | QTR1 | 24/25 | 209 | 10943081 |  |  | 140 | 29 | 0 | 0 | -248407 | 0 |  | CO
02CO | 02 | T2935 | 43917715201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 120 | 145 | 137 | 8 | 0 | 0 | 25 | 0 | 688840 | 41224 | 647616 | 688840 | 661650 | 0 | 0 | 0 | 661650 | 661650 | 0 | 0 | 6 | 0 | 0 | 21865 | 0 | 0 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23025 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-03-13 | QTR3 | 23/24 | 214 | 865700.85 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2941 | 44535115201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 250 | 326 | 325 | 1 | 0 | 0 | 59 | 17 | 12720657 | 150000 | 12570657 | 12720657 | 12835454 | 0 | 0 | 0 | 12835454 | 12775399 | -60056 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-03-06 | QTR3 | 24/25 | 2024-11-27 | QTR2 | 24/25 | 208 | 15011207.53 |  |  | 17 | 9 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2942 | 44549115201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 180 | 217 | 217 | 0 | 0 | 0 | 37 | 0 | 3471985 | 50000 | 3421985 | 3471985 | 3461898 | 0 | 0 | 0 | 3461898 | 3448164 | -13733 | 0 | 30 | 0 | 0 | 27958 | 0 | 0 | 0 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41252 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 | 2024-08-17 | QTR1 | 24/25 | 214 | 3741501.6 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2957 | 44712915201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 164 | 157 | 7 | 0 | 0 | 14 | 0 | 2432061 | 50000 | 2382061 | 2483046 | 2440068 | 0 | 0 | 0 | 2440068 | 2440833 | 766 | 50985 | 10 | 0 | 0 | 2944 | 0 | 0 | 0 | 63883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66827 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-10-22 | QTR2 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 208 | 2377451.33 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2958 | 44615425201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 150 | 214 | 213 | 1 | 0 | 0 | 64 | 0 | 3795580 | 50000 | 3745580 | 3795580 | 3741800 | 0 | 0 | 0 | 3741800 | 3742922 | 1123 | 0 | 40 | 0 | 0 | 10773 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-07-26 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 3808947.4 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2964 | 44712615201 | 2024-01-31 | QTR3 | 23/24 | 1 | 1 | 400 | 434 | 132 | 302 | 0 | 0 | 15 | 19 | 10386249 | 138776 | 10247474 | 11083785 | 10715818 | 0 | 697536 | 697536 | 11413354 | 10715818 | -697536 | 697536 | 9 | 0 | 0 | 714402 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 744402 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 | 2024-08-02 | QTR1 | 24/25 | 208 | 15260326.27 | B5 | ACC - INCENTIVE/DISINCENTIVE | 19 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2980 | 45220115201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 68 | 75 | 69 | 6 | 0 | 0 | 7 | 0 | 1193458 | 50000 | 1143458 | 1193458 | 1138988 | 0 | 0 | 0 | 1138988 | 1138988 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 208 | 2555282.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E200K | 43737515201 | 2023-05-10 | QTR4 | 22/23 | 1 | 1 | 90 | 188 | 178 | 10 | 0 | 0 | 11 | 87 | 596179 | 30616 | 565564 | 596809 | 579939 | 0 | 0 | 0 | 579939 | 579939 | 0 | 630 | 1 | 0 | 87 | 6930 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 7560 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-08-08 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 208 | 642935.05 |  |  | 87 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20G1 | 43451415201 | 2021-11-17 | QTR2 | 21/22 | 3 | 5 | 300 | 716 | 702 | 14 | 0 | 0 | 255 | 161 | 8137606 | 73677 | 8063929 | 11055579 | 11421194 | 0 | 0 | 0 | 11421194 | 11370860 | 0 | 2917973 | 194 | 0 | 0 | 17743 | 0 | 0 | 161 | 2879911 | 0 | 0 | 0 | 34372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2982361 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-08-01 | QTR1 | 24/25 | 2024-05-07 | QTR4 | 23/24 | 208 | 9316376.83 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20I2 | 43556415201 | 2022-06-08 | QTR4 | 21/22 | 1 | 0 | 550 | 664 | 664 | 0 | 0 | 0 | 114 | 0 | 742391 | 50000 | 692391 | 742391 | 688386 | 0 | 0 | 0 | 688386 | 688386 | 0 | 0 | 16 | 12 | 0 | 23288 | 0 | 0 | 0 | 5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 28813 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-01-10 | QTR3 | 24/25 | 2024-09-09 | QTR1 | 24/25 | 214 | 1885001.5 |  |  | 0 | 86 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S3 | 44752515201 | 2022-06-07 | QTR4 | 21/22 | 2 | 3 | 480 | 761 | 756 | 5 | 0 | 0 | 195 | 86 | 3180291 | 52391 | 3127900 | 2920160 | 2867769 | 0 | 0 | 0 | 2867769 | 2867769 | 0 | -260131 | 25 | 90 | 0 | 0 | 0 | 0 | 86 | -260131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 86 | -260131 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 | 2024-09-11 | QTR1 | 24/25 | 208 | 6564146.33 | LBDB:LBDB::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 80 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z23 | 43655815201 | 2020-04-15 | QTR4 | 19/20 | 4 | 24 | 820 | 1353 | 1353 | 0 | 0 | 0 | 268 | 265 | 23611420 | 200000 | 23411420 | 27138289 | 27685573 | 0 | 0 | 0 | 27685573 | 27771520 | 1123706 | 3526869 | 109 | 0 | 190 | 2082836 | 1770145 | 0 | 62 | 1249941 | 115377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14584 | 0 | 15 | 0 | 13820 | 1228 | 0 | 0 | 0 | 0 | 6 | 0 | 23052 | 13403 | 0 | 0 | 0 | 0 | 0 | 13 | 218121 | 218121 | 0 | 0 | 0 | 0 | 22 | 265 | 3602355 | 2118274 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-03-26 | QTR3 | 23/24 | 214 | 23815761.26 |  |  | 11 | 143 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3690 | 41413265201 | 2021-02-17 | QTR3 | 20/21 | 2 | 3 | 820 | 1163 | 1163 | 0 | 0 | 0 | 276 | 67 | 15659012 | 142361 | 15516651 | 16135795 | 16181298 | -5000 | 0 | -5000 | 16176298 | 16849377 | 795630 | 476783 | 155 | 0 | 67 | 469583 | 0 | 0 | 0 | 54839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7324 | 0 | 0 | 0 | 2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 534429 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-16 | QTR3 | 24/25 | 2024-07-10 | QTR1 | 24/25 | 313 | 14312918.46 |  |  | 0 | 121 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3719 | 43921415201 | 2022-05-25 | QTR4 | 21/22 | 2 | 2 | 235 | 553 | 553 | 0 | 0 | 0 | 268 | 50 | 2161422 | 0 | 2161422 | 2219469 | 2278041 | 0 | 0 | 0 | 2278041 | 2271197 | -6844 | 58046 | 137 | 0 | 35 | 26771 | 0 | 79 | 15 | 31276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 50 | 58046 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-02-13 | QTR3 | 23/24 | 313 | 3319648.9 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 0 | 292 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-02 | QTR2 | 24/25 | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94 |  |  | 22 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3767 | 44188125201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 150 | 262 | 261 | 1 | 0 | 0 | 112 | 0 | 1798857 | 0 | 1798857 | 1800807 | 1823631 | 0 | 0 | 0 | 1823631 | 1837783 | 14152 | 1950 | 65 | 18 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1950 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-17 | QTR1 | 24/25 | 2024-01-11 | QTR3 | 23/24 | 314 | 1816518.22 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3774 | 44115615201 | 2022-10-26 | QTR2 | 22/23 | 2 | 0 | 240 | 520 | 519 | 1 | 0 | 0 | 280 | 0 | 2352518 | 0 | 2352518 | 2352518 | 2482697 | 0 | 0 | 0 | 2482697 | 2481516 | -1180 | 0 | 220 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 313 | 2793292.28 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3791 | 43937615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 200 | 290 | 290 | 0 | 0 | 0 | 90 | 0 | 2097844 | 0 | 2097844 | 2104355 | 1977895 | 0 | 0 | 0 | 1977895 | 1977939 | 44 | 6511 | 56 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6511 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-03 | QTR1 | 24/25 | 313 | 2307183.3 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3792 | 44117115201 | 2023-04-26 | QTR4 | 22/23 | 1 | 1 | 160 | 225 | 224 | 1 | 0 | 0 | 65 | 0 | 1248264 | 0 | 1248264 | 1248264 | 1306248 | 0 | 0 | 0 | 1306248 | 1306346 | 98 | 0 | 39 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-04-08 | QTR4 | 23/24 | 313 | 1870598.48 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3803 | 44403915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 4 | 370 | 780 | 780 | 0 | 0 | 0 | 403 | 7 | 7221201 | 64825 | 7156376 | 7242100 | 7302859 | 0 | 0 | 0 | 7302859 | 7410703 | 107844 | 20899 | 225 | 19 | 0 | 0 | 0 | 81 | 7 | 42129 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 16713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 7 | 53313 | 8550 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-14 | QTR4 | 23/24 | 308 | 6606378.95 |  |  | 0 | 78 | 0 | 0 | -5529 | 0 |  | CO
03CO | 03 | T3806 | 43973315201 | 2022-04-27 | QTR4 | 21/22 | 3 | 0 | 315 | 660 | 659 | 1 | 0 | 0 | 345 | 0 | 10103368 | 88637 | 10014731 | 10103368 | 10342165 | 0 | 0 | 0 | 10342165 | 10277452 | -64713 | 0 | 173 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 | 2024-08-14 | QTR1 | 24/25 | 308 | 10842967.81 |  |  | 0 | 72 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3813 | 44159315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 300 | 695 | 695 | 0 | 0 | 0 | 387 | 8 | 6499662 | 61994 | 6437668 | 6674412 | 6885176 | 0 | 0 | 0 | 6885176 | 6899511 | 14336 | 174750 | 309 | 75 | 3 | 179623 | 0 | 15 | 5 | 11079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 8 | 190702 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-08 | QTR2 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 308 | 6445150.22 |  |  | 8 | 48 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3814 | 43989215201 | 2021-11-17 | QTR2 | 21/22 | 1 | 1 | 165 | 596 | 596 | 0 | 0 | 0 | 431 | 0 | 2042361 | 50000 | 1992361 | 2052823 | 2049639 | 0 | 0 | 0 | 2049639 | 2051119 | 1480 | 10462 | 151 | 97 | 0 | 1430 | 0 | 87 | 0 | 23591 | 8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 25021 | 8301 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 314 | 1702969.75 |  |  | 0 | 96 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3815 | 44365115201 | 2022-06-15 | QTR4 | 21/22 | 3 | 1 | 285 | 566 | 566 | 0 | 0 | 0 | 281 | 0 | 7790941 | 53573 | 7737368 | 8040944 | 8245622 | 0 | 0 | 0 | 8245622 | 8108954 | -136668 | 250003 | 142 | 0 | 0 | 0 | 0 | 45 | 0 | 13902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 236102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 250003 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 | 2024-05-01 | QTR4 | 23/24 | 308 | 8069731.27 |  |  | 0 | 74 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3824 | 43769915201 | 2023-04-26 | QTR4 | 22/23 | 1 | 0 | 330 | 416 | 416 | 0 | 0 | 0 | 86 | 0 | 3559704 | 0 | 3559704 | 3559704 | 3648796 | 0 | 0 | 0 | 3648796 | 3648367 | -429 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-10-30 | QTR2 | 24/25 | 2024-08-28 | QTR1 | 24/25 | 308 | 5711547.02 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3826 | 44387715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 90 | 322 | 322 | 0 | 0 | 0 | 232 | 0 | 942554 | 49324 | 893230 | 942554 | 927016 | 0 | 0 | 0 | 927016 | 927016 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-04-03 | QTR4 | 23/24 | 314 | 1043116.04 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3829 | 44553915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 300 | 380 | 380 | 0 | 0 | 0 | 63 | 17 | 12211588 | 124814 | 12086774 | 12181493 | 12519374 | 0 | 0 | 0 | 12519374 | 12516178 | -3196 | -30095 | 36 | 0 | 0 | 0 | 0 | 0 | 2 | 14322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | -15773 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-07-25 | QTR1 | 24/25 | 313 | 12606229.06 |  |  | 17 | 27 | 0 | 0 | -30095 | 0 |  | CO
03CO | 03 | T3831 | 44575915201 | 2023-05-24 | QTR4 | 22/23 | 2 | 2 | 345 | 402 | 400 | 2 | 0 | 0 | 57 | 0 | 14273753 | 149748 | 14124005 | 14525242 | 15530113 | 0 | 0 | 0 | 15530113 | 15529289 | -824 | 251489 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 251489 | 132372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251489 | 132372 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 | 2024-11-01 | QTR2 | 24/25 | 321 | 15124579.71 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3832 | 44986815201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 45 | 115 | 113 | 2 | 0 | 0 | 70 | 0 | 391274 | 20764 | 370510 | 391274 | 365673 | 0 | 0 | 0 | 365673 | 365673 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 2850 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-21 | QTR1 | 24/25 | 2024-02-12 | QTR3 | 23/24 | 321 | 417470.83 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3834 | 44563515201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 270 | 364 | 426 | -62 | 62 | 0 | 114 | 0 | 19944475 | 150000 | 19794475 | 19944475 | 21545566 | -363010 | 0 | -363010 | 21182556 | 21410083 | 227527 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-11 | QTR2 | 24/25 | 2024-08-14 | QTR1 | 24/25 | 314 | 18371047.42 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3842 | 44404015201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 60 | 433 | 424 | 9 | 0 | 0 | 373 | 0 | 851756 | 41407 | 810349 | 851756 | 802521 | 0 | 0 | 0 | 802521 | 802521 | 0 | 0 | 268 | 45 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 2000 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2024-08-12 | QTR1 | 24/25 | 314 | 869555.5 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3847 | 44365025201 | 2023-01-25 | QTR3 | 22/23 | 1 | 2 | 189 | 399 | 399 | 0 | 0 | 0 | 185 | 25 | 8306085 | 77844 | 8228241 | 8382009 | 9159429 | 0 | 0 | 0 | 9159429 | 9121506 | -37923 | 75924 | 138 | 0 | 0 | 74674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 75924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 150599 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-05-15 | QTR4 | 23/24 | 313 | 7884743.81 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3856 | 44573315201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 166 | 399 | 399 | 0 | 0 | 0 | 233 | 0 | 6737296 | 71197 | 6666099 | 6737296 | 7134385 | 0 | 0 | 0 | 7134385 | 7124379 | -10006 | 0 | 152 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-21 | QTR2 | 24/25 | 2024-07-17 | QTR1 | 24/25 | 308 | 7216077.98 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3864 | 44562915201 | 2023-04-26 | QTR4 | 22/23 | 2 | 3 | 230 | 347 | 329 | 18 | 0 | 0 | 105 | 12 | 3480880 | 51096 | 3429784 | 3589639 | 3810464 | 0 | 0 | 0 | 3810464 | 3809861 | -603 | 108759 | 73 | 0 | 0 | 12134 | 0 | 0 | 5 | 64017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 44742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 135093 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-08-18 | QTR1 | 24/25 | 308 | 5160701.28 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3865 | 43774625201 | 2023-10-25 | QTR2 | 23/24 | 2 | 1 | 200 | 254 | 252 | 2 | 0 | 0 | 53 | 1 | 6205064 | 84584 | 6120479 | 6251095 | 6519415 | 0 | 0 | 0 | 6519415 | 6478224 | -41192 | 46032 | 41 | 0 | 1 | 4597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46032 | 46032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 50628 | 46032 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 | 2024-09-25 | QTR1 | 24/25 | 308 | 8476485.74 |  |  | 1 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3869 | 44759115201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 235 | 388 | 388 | 0 | 0 | 0 | 150 | 3 | 4656452 | 50000 | 4606452 | 4656452 | 4603412 | 0 | 0 | 0 | 4603412 | 4603490 | 79 | 0 | 106 | 0 | 3 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 26881 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-13 | QTR3 | 24/25 | 2024-11-15 | QTR2 | 24/25 | 313 | 4979086.06 |  |  | 3 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3872 | 43775625201 | 2023-11-15 | QTR2 | 23/24 | 3 | 2 | 325 | 347 | 260 | 87 | 0 | 0 | 40 | -18 | 7954987 | 104069 | 7850918 | 8031898 | 8038891 | 0 | 0 | 0 | 8038891 | 8021230 | -17661 | 76912 | 28 | 0 | 0 | 5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5831 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2025-03-27 | QTR3 | 24/25 | 2024-10-07 | QTR2 | 24/25 | 321 | 10589089.88 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3875 | 44758815201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 150 | 305 | 305 | 0 | 0 | 0 | 155 | 0 | 4849503 | 63887 | 4785616 | 4849503 | 5213259 | 0 | 0 | 0 | 5213259 | 5178770 | -34488 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-02-13 | QTR3 | 24/25 | 2024-11-13 | QTR2 | 24/25 | 314 | 6479282.38 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3877 | 43775715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 1 | 273 | 325 | 320 | 5 | 0 | 0 | 52 | 0 | 11695437 | 150000 | 11545437 | 11701443 | 12402258 | 0 | 0 | 0 | 12402258 | 12455669 | 53411 | 6006 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13152 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 321 | 9851819.87 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3880 | 43078925201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 135 | 199 | 193 | 6 | 0 | 0 | 64 | 0 | 3380216 | 54568 | 3325648 | 3380216 | 3471279 | 0 | 0 | 0 | 3471279 | 3471279 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-08-27 | QTR1 | 24/25 | 314 | 5332275.36 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3886 | 45221235201 | 2023-09-13 | QTR1 | 23/24 | 1 | 1 | 109 | 155 | 154 | 1 | 0 | 0 | 46 | 0 | 1444661 | 50000 | 1394661 | 1521683 | 1385235 | 0 | 0 | 0 | 1385235 | 1385235 | 0 | 77022 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77022 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-05-02 | QTR4 | 23/24 | 314 | 2325343.9 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3889 | 45221225201 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 140 | 184 | 127 | 57 | 0 | 0 | 29 | 15 | 1570117 | 50000 | 1520117 | 1689632 | 1597844 | 0 | 0 | 0 | 1597844 | 1597844 | 0 | 119515 | 12 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 119515 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-05-24 | QTR4 | 23/24 | 313 | 1925284.7 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3897 | 44845115201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 165 | 254 | 254 | 0 | 0 | 0 | 86 | 3 | 1349500 | 50000 | 1299500 | 1349500 | 1300591 | 0 | 0 | 0 | 1300591 | 1300571 | -20 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 3 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 3 | 1250 | 0 | F473134188 | GRAYBELLE CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-10-29 | QTR2 | 24/25 | 321 | 1617297.75 |  |  | 3 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3921 | 45146315201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 100 | 124 | 123 | 1 | 0 | 0 | 24 | 0 | 655998 | 28648 | 627350 | 655998 | 585688 | 0 | 0 | 0 | 585688 | 585688 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2025-02-04 | QTR3 | 24/25 | 2024-12-19 | QTR2 | 24/25 | 313 | 605938.95 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q94 | 21787545201 | 2018-06-14 | QTR4 | 17/18 | 1 | 11 | 1325 | 2106 | 2106 | 0 | 0 | 0 | 767 | 14 | 31708584 | 150000 | 31558584 | 32410332 | 32832992 | 0 | 0 | 0 | 32832992 | 33087185 | 254193 | 701748 | 414 | 0 | 0 | 391404 | 0 | 198 | 10 | 243931 | 56594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 103110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 14 | 746509 | 56594 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2024-05-21 | QTR4 | 23/24 | 306 | 25965925.9 |  |  | 14 | 136 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T55 | 43974015201 | 2021-03-11 | QTR3 | 20/21 | 1 | 0 | 180 | 335 | 362 | -27 | 27 | 0 | 155 | 0 | 5227145 | 50000 | 5177145 | 5227145 | 5328540 | -101412 | 0 | -101412 | 5227128 | 5712178 | 485050 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-02-03 | QTR3 | 24/25 | 2022-05-31 | QTR4 | 21/22 | 314 | 4892771.41 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U63 | 43776415201 | 2022-06-09 | QTR4 | 21/22 | 3 | 0 | 455 | 795 | 786 | 9 | 0 | 0 | 334 | 6 | 7526960 | 90812 | 7436148 | 7526960 | 7541005 | 0 | 0 | 0 | 7541005 | 7382315 | -158690 | 0 | 137 | 0 | 1 | 2600 | 0 | 0 | 0 | 6274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 8874 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 | 2024-11-15 | QTR2 | 24/25 | 308 | 9579367.88 |  |  | 1 | 106 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V87 | 44573415201 | 2022-12-08 | QTR2 | 22/23 | 2 | 0 | 180 | 288 | 287 | 1 | 0 | 0 | 108 | 0 | 4255368 | 50000 | 4205368 | 4255368 | 4147787 | 0 | 0 | 0 | 4147787 | 4133951 | -13836 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-10 | QTR1 | 24/25 | 2024-04-26 | QTR4 | 23/24 | 308 | 4883807.47 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W06 | 22283255201 | 2024-03-21 | QTR3 | 23/24 | 1 | 0 | 100 | 163 | 144 | 19 | 0 | 0 | 63 | 0 | 365234 | 27430 | 337804 | 365234 | 304736 | 0 | 0 | 0 | 304736 | 304736 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 | 2024-11-12 | QTR2 | 24/25 | 313 | 608746.8 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W17 | 44759015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 137 | 196 | 182 | 14 | 0 | 0 | 59 | 0 | 3130216 | 50000 | 3080216 | 3130216 | 3176618 | 0 | 0 | 0 | 3176618 | 3169412 | -7206 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 308 | 4310827.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W27 | 43464515201 | 2022-12-15 | QTR2 | 22/23 | 2 | 2 | 150 | 258 | 257 | 1 | 0 | 0 | 103 | 5 | 3980189 | 50000 | 3930189 | 4006691 | 4118899 | 0 | 0 | 0 | 4118899 | 4101914 | -16986 | 26502 | 75 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26502 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-23 | QTR1 | 24/25 | 2024-03-04 | QTR3 | 23/24 | 321 | 4847741.78 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W54 | 42359155201 | 2023-07-13 | QTR1 | 23/24 | 1 | 2 | 90 | 164 | 164 | 0 | 0 | 0 | 72 | 2 | 3139310 | 50000 | 3089310 | 3241997 | 3289104 | 70000 | 800 | 70800 | 3359904 | 3289104 | -70800 | 102687 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 121800 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-18 | QTR4 | 23/24 | 308 | 2935413.97 | B10 | ACC - BONUS/INCENT/DISINCENT | 2 | 35 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W67 | 43467115201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 140 | 153 | 144 | 9 | 0 | 0 | 13 | 0 | 3519862 | 50000 | 3469862 | 3519862 | 3571544 | 0 | 0 | 0 | 3571544 | 3563708 | -7835 | 0 | 9 | 0 | 0 | 11460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11460 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-09 | QTR3 | 24/25 | 2024-06-27 | QTR4 | 23/24 | 313 | 4787060.64 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W87 | 44573515201 | 2024-02-08 | QTR3 | 23/24 | 1 | 0 | 150 | 169 | 169 | 0 | 0 | 0 | 19 | 0 | 3177069 | 50000 | 3127069 | 3177069 | 3326636 | 0 | 0 | 0 | 3326636 | 3307859 | -18777 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2025-01-08 | QTR3 | 24/25 | 2024-10-31 | QTR2 | 24/25 | 321 | 4084998.81 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W88 | 44575515201 | 2023-11-09 | QTR2 | 23/24 | 1 | 0 | 120 | 128 | 124 | 4 | 0 | 0 | 8 | 0 | 2175239 | 50000 | 2125239 | 2175239 | 2183626 | 0 | 0 | 0 | 2183626 | 2183626 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-06-21 | QTR4 | 23/24 | 313 | 3085002.9 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4434 | 23144025201 | 2016-06-15 | QTR4 | 15/16 | 1 | 19 | 1200 | 1859 | 1859 | 0 | 0 | 0 | 338 | 321 | 26848292 | 150000 | 26698292 | 32229320 | 31919676 | 0 | 0 | 0 | 31919676 | 32107031 | 313643 | 5381029 | 173 | 0 | 16 | 190342 | 117524 | 0 | 70 | 1074932 | 603111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61803 | 0 | 0 | 0 | 1485 | 1485 | 0 | 0 | 0 | 0 | 8 | 0 | 76369 | 0 | 0 | 235 | 4001328 | 3287359 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 321 | 5383723 | 4009479 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 | 2021-12-09 | QTR2 | 21/22 | 408 | 25701172.49 | B1 | ACC - NO EXCUSE BONUS | 0 | 98 | 0 | 0 | -22536 | 0 |  | CO
04CO | 04 | T4472 | 41934525201 | 2018-01-31 | QTR3 | 17/18 | 2 | 10 | 1049 | 1423 | 1423 | 0 | 0 | 0 | 263 | 111 | 33359900 | 182880 | 33177020 | 33746993 | 33295065 | 0 | -75000 | -75000 | 33220065 | 33597249 | 421739 | 387093 | 176 | 0 | 0 | 456573 | 0 | 0 | 0 | -143555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188 | 0 | 0 | 71 | 56466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32197 | 0 | 0 | 40 | 81324 | 79113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 484193 | 79113 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2024-10-17 | QTR2 | 24/25 | 2022-06-22 | QTR4 | 21/22 | 409 | 37475055.58 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 87 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4477 | 23025665201 | 2018-05-23 | QTR4 | 17/18 | 3 | 21 | 1355 | 1820 | 1818 | 2 | 0 | 0 | 369 | 96 | 45221786 | 150000 | 45071786 | 46013498 | 46814508 | 0 | 0 | 0 | 46814508 | 47115720 | 598393 | 791712 | 277 | 0 | 75 | 1457815 | 599303 | 0 | 21 | 489759 | 22128 | 0 | 0 | 0 | 0 | 0 | 0 | -1173394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69595 | 0 | 0 | 0 | 1041 | 1041 | 0 | 0 | 0 | 0 | 20 | 0 | 78775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 96 | 784401 | 622472 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-09-08 | QTR1 | 23/24 | 408 | 48103369.82 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 92 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4566 | 43976115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 7 | 401 | 617 | 617 | 0 | 0 | 0 | 216 | 0 | 4627786 | 50000 | 4577786 | 4748358 | 4545695 | 0 | 0 | 0 | 4545695 | 4639320 | 96348 | 120572 | 150 | 1 | 0 | 43781 | 0 | 27 | 0 | 67848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 114830 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-02-15 | QTR3 | 23/24 | 408 | 5224693.73 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4585 | 43533715201 | 2021-08-25 | QTR1 | 21/22 | 1 | 6 | 576 | 788 | 788 | 0 | 0 | 0 | 202 | 10 | 15518729 | 150000 | 15368729 | 16395821 | 15822170 | 0 | 0 | 0 | 15822170 | 15987859 | 165689 | 877092 | 127 | 0 | 0 | 25236 | 0 | 0 | 0 | 397562 | 92279 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 410929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 999993 | 92279 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-03-21 | QTR3 | 23/24 | 408 | 15323088.94 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4595 | 43206685201 | 2022-01-26 | QTR3 | 21/22 | 3 | 7 | 473 | 814 | 814 | 0 | 0 | 0 | 122 | 219 | 11281680 | 104975 | 11176705 | 11586874 | 11564646 | 0 | 0 | 0 | 11564646 | 11487612 | 69618 | 305194 | 81 | 42 | 99 | 165355 | 0 | 0 | 14 | 264275 | 20193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 147865 | 0 | 0 | 0 | 16221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 219 | 400610 | 20193 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 | 2024-10-17 | QTR2 | 24/25 | 412 | 11191546.92 |  |  | 0 | 41 | 0 | 0 | -205740 | 0 |  | CO
04CO | 04 | T4596 | 43206695201 | 2022-01-26 | QTR3 | 21/22 | 3 | 2 | 426 | 868 | 918 | -50 | 50 | 0 | 220 | 222 | 8895418 | 83586 | 8811831 | 8898040 | 8723470 | -189300 | 0 | -189300 | 8534170 | 8790513 | 258966 | 2623 | 95 | 65 | 0 | 3300 | 0 | 9 | 0 | 16427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 2623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 222 | 22349 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-03-24 | QTR3 | 24/25 | 2024-11-08 | QTR2 | 24/25 | 412 | 8602890.25 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4598 | 44399615201 | 2022-02-23 | QTR3 | 21/22 | 3 | 6 | 425 | 607 | 607 | 0 | 0 | 0 | 160 | 22 | 5606708 | 50000 | 5556708 | 5800857 | 5331108 | 0 | 0 | 0 | 5331108 | 5358143 | 30705 | 194148 | 85 | 0 | 0 | 0 | 0 | 28 | 22 | 190479 | 189820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 22 | 194148 | 189820 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2024-11-19 | QTR2 | 24/25 | 2024-04-23 | QTR4 | 23/24 | 408 | 4811998.96 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4599 | 43177045201 | 2022-02-23 | QTR3 | 21/22 | 4 | 3 | 385 | 566 | 565 | 1 | 0 | 0 | 181 | 0 | 6578249 | 66251 | 6511998 | 6638837 | 6561389 | 0 | 0 | 0 | 6561389 | 6682743 | 122865 | 60588 | 135 | 0 | 0 | 17342 | 0 | 0 | 0 | 75216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98639 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 | 2024-01-26 | QTR3 | 23/24 | 412 | 7009923.45 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4610 | 44426515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 223 | 437 | 436 | 1 | 0 | 0 | 214 | 0 | 4142494 | 50000 | 4092494 | 4142494 | 3658735 | 0 | 0 | 0 | 3658735 | 3642576 | -16159 | 0 | 189 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 607 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-14 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 412 | 4002406.07 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4611 | 44158215201 | 2022-05-25 | QTR4 | 21/22 | 6 | 1 | 279 | 429 | 428 | 1 | 0 | 0 | 150 | 0 | 7152130 | 67268 | 7084862 | 7150760 | 6812663 | 0 | 0 | 0 | 6812663 | 6766023 | -46640 | -1370 | 123 | 0 | 0 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 37112 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-07-09 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 412 | 8132476.21 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4612 | 42957645201 | 2022-04-27 | QTR4 | 21/22 | 3 | 2 | 371 | 538 | 536 | 2 | 0 | 0 | 167 | 0 | 6700410 | 59912 | 6640498 | 6959205 | 7215672 | 0 | 0 | 0 | 7215672 | 7199967 | -15706 | 258794 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 259680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259680 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-09-26 | QTR1 | 24/25 | 2024-03-15 | QTR3 | 23/24 | 412 | 6372835.38 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4618 | 44384315201 | 2023-07-26 | QTR1 | 23/24 | 2 | 0 | 186 | 210 | 200 | 10 | 0 | 0 | 24 | 0 | 1266009 | 50000 | 1216009 | 1266009 | 1196561 | 0 | 0 | 0 | 1196561 | 1196630 | 69 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-08-23 | QTR1 | 24/25 | 412 | 1146916.03 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4619 | 44617715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 2 | 331 | 472 | 468 | 4 | 0 | 0 | 141 | 0 | 7958317 | 91207 | 7867110 | 8109946 | 8174515 | 0 | 0 | 0 | 8174515 | 8136642 | -37873 | 151628 | 54 | 0 | 0 | 21328 | 0 | 57 | 0 | 198554 | 106628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 219883 | 106628 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 | 2024-11-26 | QTR2 | 24/25 | 409 | 9211938.74 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4624 | 43783245201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 490 | 619 | 619 | 0 | 0 | 0 | 144 | -15 | 12698955 | 150000 | 12548955 | 12584827 | 12539323 | 0 | 0 | 0 | 12539323 | 12387135 | -152188 | -114128 | 89 | 15 | 0 | 0 | 0 | 0 | 0 | 190110 | 0 | 0 | 0 | 7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7692 | 0 | 0 | 0 | 76937 | 43890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -15 | -24439 | 43890 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-03-10 | QTR3 | 24/25 | 2024-12-11 | QTR2 | 24/25 | 412 | 16805865.3 |  |  | 0 | 40 | 0 | -15 | -306645 | 0 |  | CO
04CO | 04 | T4625 | 44175515201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 234 | 458 | 458 | 0 | 0 | 0 | 224 | 0 | 3558974 | 50000 | 3508974 | 3558974 | 3328234 | 0 | 0 | 0 | 3328234 | 3328234 | 0 | 0 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 18044 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 | 2024-10-30 | QTR2 | 24/25 | 409 | 3996955.76 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4634 | 44177015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 173 | 286 | 283 | 3 | 0 | 0 | 113 | 0 | 1746923 | 50000 | 1696923 | 1746923 | 1740697 | 0 | 0 | 0 | 1740697 | 1736981 | -3717 | 0 | 63 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27413 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-27 | QTR4 | 23/24 | 412 | 1767920.19 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4636 | 44384415201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 194 | 305 | 305 | 0 | 0 | 0 | 111 | 0 | 798900 | 41899 | 757001 | 798900 | 732677 | 0 | 0 | 0 | 732677 | 732677 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11481 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-06-28 | QTR4 | 23/24 | 412 | 879882.26 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4637 | 44359115201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 245 | 319 | 319 | 0 | 0 | 0 | 74 | 0 | 2144351 | 50000 | 2094351 | 2144351 | 2073909 | 0 | 50000 | 50000 | 2123909 | 2068781 | -55128 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 30506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30506 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-17 | QTR3 | 24/25 | 2024-08-06 | QTR1 | 24/25 | 412 | 2377316.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4640 | 43771715201 | 2023-02-22 | QTR3 | 22/23 | 2 | 4 | 278 | 325 | 325 | 0 | 0 | 0 | 42 | 37 | 6949432 | 61964 | 6887469 | 7359443 | 7308401 | 0 | 0 | 0 | 7308401 | 7303926 | -4475 | 625462 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 72039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102645 | 0 | 0 | 0 | 235326 | 235326 | 0 | 0 | 0 | 0 | 0 | 5 | 430100 | 235326 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-09-04 | QTR1 | 24/25 | 2024-04-24 | QTR4 | 23/24 | 408 | 6229901.33 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4642 | 44610315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 1 | 257 | 329 | 328 | 1 | 0 | 0 | 72 | 0 | 2584711 | 50000 | 2534711 | 2601574 | 2230880 | 0 | 0 | 0 | 2230880 | 2230536 | -344 | 16863 | 37 | 0 | 0 | 16021 | 1355 | 10 | 0 | 24729 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 42185 | 3816 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-08-28 | QTR1 | 24/25 | 2024-06-29 | QTR4 | 23/24 | 409 | 2408670.99 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4644 | 44610915201 | 2023-02-22 | QTR3 | 22/23 | 1 | 4 | 284 | 422 | 422 | 0 | 0 | 0 | 138 | 2 | 6184480 | 55128 | 6129352 | 6236790 | 6263543 | 0 | 0 | 0 | 6263543 | 6218472 | -29786 | 56272 | 88 | 3 | 0 | 0 | 0 | 0 | 0 | 37015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 37015 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-25 | QTR3 | 24/25 | 2025-01-14 | QTR3 | 24/25 | 408 | 5567898.79 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4647 | 44699815201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 80 | 133 | 129 | 4 | 0 | 0 | 53 | 0 | 555556 | 31410 | 524146 | 555556 | 522780 | 0 | 0 | 0 | 522780 | 522780 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-10-30 | QTR2 | 24/25 | 412 | 659609.7 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4678 | 45222615201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 79 | 101 | 86 | 15 | 0 | 0 | 22 | 0 | 654155 | 39867 | 614288 | 654155 | 630879 | 0 | 0 | 0 | 630879 | 630879 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 | 2024-09-03 | QTR1 | 24/25 | 409 | 832301.65 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T19 | 43310955201 | 2019-03-29 | QTR3 | 18/19 | 4 | 30 | 1400 | 1710 | 1689 | 21 | 0 | 0 | 310 | 0 | 148094245 | 150000 | 147944245 | 151713231 | 152720818 | 0 | 1375000 | 1375000 | 154095818 | 153674680 | 5349446 | 3618986 | 181 | 0 | 0 | 1977285 | 209090 | 0 | 0 | 759652 | 44331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 688498 | 33779 | 0 | 0 | 162596 | 323185 | 0 | 0 | 0 | 0 | 114 | 0 | 94258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40830 | 40830 | 0 | 0 | 0 | 0 | 131 | 0 | 3674223 | 651215 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-02-01 | QTR3 | 23/24 | 409 | 130080159.7 | B1:B5:B8:::Y | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 112 | 0 | 0 | -48896 | 0 |  | DO
04DO | 04 | E4U89 | 43793425201 | 2021-05-21 | QTR4 | 20/21 | 1 | 7 | 642 | 921 | 914 | 7 | 0 | 0 | 309 | -30 | 8845801 | 82577 | 8763224 | 9316076 | 9449453 | 0 | 0 | 0 | 9449453 | 9527705 | 272009 | 470275 | 174 | 84 | 0 | 11055 | 0 | 0 | 0 | 525575 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | -30 | 540229 | 5610 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-10 | QTR2 | 24/25 | 2024-05-31 | QTR4 | 23/24 | 412 | 8524313.34 |  |  | 0 | 51 | 0 | -30 | 0 | 0 |  | DO
04DO | 04 | E4V48 | 44346115201 | 2022-05-06 | QTR4 | 21/22 | 2 | 0 | 719 | 771 | 539 | 232 | 0 | 0 | 52 | 0 | 6383851 | 97993 | 6285858 | 6383851 | 5949070 | 0 | 0 | 0 | 5949070 | 5949070 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-09-05 | QTR1 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 412 | 10090648.24 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V49 | 44399515201 | 2021-12-03 | QTR2 | 21/22 | 2 | 10 | 320 | 523 | 523 | 0 | 0 | 0 | 176 | 27 | 5064095 | 50000 | 5014095 | 5491766 | 5407331 | 0 | 0 | 0 | 5407331 | 5458407 | 58735 | 427672 | 109 | 0 | -28 | 224222 | 167454 | 0 | 2 | 221257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20173 | 0 | 0 | 0 | 5879 | 5879 | 0 | 0 | 0 | 0 | 53 | 53 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 27 | 479190 | 173333 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-24 | QTR2 | 24/25 | 2023-12-29 | QTR2 | 23/24 | 408 | 4246638.67 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V50 | 43975915201 | 2022-09-02 | QTR1 | 22/23 | 1 | 2 | 246 | 338 | 338 | 0 | 0 | 0 | 92 | 0 | 2437437 | 50000 | 2387437 | 2522997 | 2472614 | 0 | 0 | 0 | 2472614 | 2469346 | -3268 | 85560 | 39 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 93118 | 8726 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-09 | QTR2 | 24/25 | 2024-06-28 | QTR4 | 23/24 | 409 | 2462556.03 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V74 | 43975415201 | 2022-03-04 | QTR3 | 21/22 | 2 | 6 | 220 | 364 | 364 | 0 | 0 | 0 | 119 | 25 | 2591421 | 50000 | 2541421 | 2746776 | 2777528 | 0 | 0 | 0 | 2777528 | 2779572 | 2044 | 155355 | 86 | 0 | 24 | 94773 | 0 | 0 | 0 | 86949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 181722 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-31 | QTR3 | 24/25 | 2023-11-08 | QTR2 | 23/24 | 408 | 2367933.4 |  |  | 1 | 33 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V97 | 44175915201 | 2022-11-04 | QTR2 | 22/23 | 1 | 0 | 128 | 325 | 323 | 2 | 0 | 0 | 197 | 0 | 3019043 | 50000 | 2969043 | 3019043 | 2884719 | 0 | 0 | 0 | 2884719 | 2884627 | -92 | 0 | 151 | 0 | 0 | 0 | 0 | 23 | 0 | 18308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 18308 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-11-08 | QTR2 | 24/25 | 2024-08-02 | QTR1 | 24/25 | 412 | 2305583.22 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W07 | 44359015201 | 2022-05-27 | QTR4 | 21/22 | 2 | 4 | 421 | 763 | 762 | 1 | 0 | 0 | 317 | 25 | 9977382 | 93560 | 9883822 | 10834234 | 10461717 | 0 | 0 | 0 | 10461717 | 10387691 | -74027 | 1343307 | 234 | 0 | 0 | 23575 | 0 | 0 | 25 | 888872 | 87905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 7341 | 0 | 0 | 0 | 2564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 25 | 922352 | 87905 | F461192152 | UAG CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 | 2024-12-10 | QTR2 | 24/25 | 409 | 11240081.43 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W15 | 44611215201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 255 | 309 | 309 | 0 | 0 | 0 | 54 | 0 | 2771566 | 50000 | 2721566 | 2822338 | 2686822 | 0 | 0 | 0 | 2686822 | 2675635 | -11187 | 50772 | 14 | 0 | 0 | 50772 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55047 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 408 | 3211732.12 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W39 | 44412115201 | 2023-02-03 | QTR3 | 22/23 | 1 | 1 | 181 | 249 | 249 | 0 | 0 | 0 | 68 | 0 | 2588046 | 50000 | 2538046 | 2588046 | 2728223 | 0 | 0 | 0 | 2728223 | 2725656 | -2567 | 41751 | 27 | 0 | 0 | 31095 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 43162 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-18 | QTR1 | 24/25 | 2024-05-23 | QTR4 | 23/24 | 409 | 2290170.49 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W40 | 44609915201 | 2023-03-03 | QTR3 | 22/23 | 2 | 0 | 161 | 203 | 233 | -30 | 30 | 0 | 42 | 0 | 1223473 | 50000 | 1173473 | 1223473 | 1121989 | -50970 | 0 | -50970 | 1071019 | 1027689 | -43330 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2024-07-11 | QTR1 | 24/25 | 2024-05-03 | QTR4 | 23/24 | 409 | 1203019.65 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W49 | 44637115201 | 2023-07-07 | QTR1 | 23/24 | 1 | 1 | 244 | 257 | 198 | 59 | 0 | 0 | 13 | 0 | 4434511 | 55240 | 4379271 | 4502024 | 4183947 | 0 | 0 | 0 | 4183947 | 4189012 | 5065 | 67513 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-12-06 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 412 | 5579255.71 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W50 | 44610715201 | 2023-03-03 | QTR3 | 22/23 | 1 | 1 | 243 | 455 | 455 | 0 | 0 | 0 | 212 | 0 | 2849827 | 50000 | 2799827 | 2874613 | 2894545 | 0 | 0 | 0 | 2894545 | 2891318 | -3227 | 24785 | 139 | 0 | 0 | 0 | 0 | 40 | 0 | 24785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 24785 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 | 2024-11-13 | QTR2 | 24/25 | 408 | 2610595.11 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W58 | 44004615201 | 2023-05-05 | QTR4 | 22/23 | 1 | 2 | 175 | 210 | 210 | 0 | 0 | 0 | 35 | 0 | 2786872 | 50000 | 2736872 | 2833359 | 2656902 | 0 | 0 | 0 | 2656902 | 2656977 | 75 | 46486 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 46486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46486 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 | 2024-07-30 | QTR1 | 24/25 | 409 | 2491562.11 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W68 | 44619815201 | 2023-09-01 | QTR1 | 23/24 | 2 | 0 | 124 | 195 | 183 | 12 | 0 | 0 | 71 | 0 | 1533318 | 50000 | 1483318 | 1533318 | 1448228 | 0 | 0 | 0 | 1448228 | 1445431 | -2797 | 0 | 63 | 0 | 0 | 6276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6276 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-06 | QTR3 | 24/25 | 2024-10-15 | QTR2 | 24/25 | 412 | 1669882.03 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5721 | 44287515201 | 2021-12-08 | QTR2 | 21/22 | 3 | 7 | 510 | 817 | 805 | 12 | 0 | 0 | 257 | 50 | 16561765 | 150000 | 16411765 | 17284645 | 18223735 | 0 | 0 | 0 | 18223735 | 18736509 | 519720 | 722880 | 198 | 0 | 30 | 59072 | 0 | 0 | 0 | 671912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455 | 0 | 0 | 0 | 4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 743980 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-27 | QTR1 | 24/25 | 515 | 18568888.72 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5725 | 44351215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 5 | 170 | 327 | 327 | 0 | 0 | 0 | 95 | 62 | 4062453 | 50000 | 4012453 | 4217199 | 4121213 | 0 | 0 | 0 | 4121213 | 4063114 | -57178 | 154746 | 45 | 0 | 0 | 0 | 0 | 0 | 20 | 128330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 129251 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 513 | 5797838.34 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5728 | 44395815201 | 2021-08-25 | QTR1 | 21/22 | 6 | 5 | 600 | 848 | 847 | 1 | 0 | 0 | 248 | 0 | 34500000 | 150000 | 34350000 | 35703756 | 38083377 | -5932 | -11806 | -17738 | 38065638 | 39383079 | 1397410 | 1203756 | 187 | 0 | 0 | 557100 | 0 | 0 | 0 | 507869 | 292167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207739 | 292167 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 | 2024-03-15 | QTR3 | 23/24 | 509 | 32771897.49 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5729 | 43565715201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 350 | 535 | 535 | 0 | 0 | 0 | 185 | 0 | 10638248 | 127000 | 10511248 | 10677535 | 11115999 | 0 | 0 | 0 | 11115999 | 11021098 | -94902 | 39287 | 76 | 0 | 0 | 64056 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-07 | QTR4 | 23/24 | 514 | 15691232.3 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5740 | 43898215201 | 2022-01-26 | QTR3 | 21/22 | 3 | 3 | 300 | 620 | 619 | 1 | 0 | 0 | 153 | 167 | 2406406 | 50000 | 2356406 | 2511349 | 2568507 | 0 | 0 | 0 | 2568507 | 2563775 | -1791 | 104943 | 39 | 0 | 0 | 43617 | 0 | 0 | 167 | 5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52001 | 0 | 0 | 0 | 1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 104943 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-15 | QTR4 | 23/24 | 513 | 2297943.8 |  |  | 167 | 114 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5743 | 43793515201 | 2022-02-23 | QTR3 | 21/22 | 4 | 5 | 350 | 693 | 693 | 0 | 0 | 0 | 220 | 123 | 4388956 | 50000 | 4338956 | 6723005 | 6937593 | 0 | 0 | 0 | 6937593 | 6933746 | -730 | 2334049 | 126 | 0 | 90 | 2279264 | 0 | 0 | 20 | 71667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 2351482 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 | 2024-10-28 | QTR2 | 24/25 | 513 | 4734607.56 |  |  | 13 | 94 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5745 | 43219355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 6 | 560 | 621 | 621 | 0 | 0 | 0 | 46 | 15 | 7356536 | 82000 | 7274536 | 7830549 | 7924589 | 0 | 0 | 0 | 7924589 | 7872250 | -50996 | 474013 | 12 | 0 | 0 | 475337 | 0 | 0 | 0 | 39899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516578 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-03-13 | QTR3 | 24/25 | 2024-07-19 | QTR1 | 24/25 | 509 | 10192519.21 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5755 | 44568715201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 130 | 234 | 234 | 0 | 0 | 0 | 104 | 0 | 1071415 | 20000 | 1051415 | 1072209 | 1061331 | 0 | 0 | 0 | 1061331 | 1059054 | -1484 | 793 | 94 | 0 | 0 | 5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 5815 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2023-10-25 | QTR2 | 23/24 | 512 | 734929.4 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5762 | 44351415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 170 | 329 | 322 | 7 | 0 | 0 | 155 | 4 | 2950212 | 50000 | 2900212 | 2990212 | 3032852 | 0 | 0 | 0 | 3032852 | 3032337 | -515 | 40000 | 128 | 0 | 0 | 40000 | 0 | 0 | 4 | 20812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 60812 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-07-16 | QTR1 | 24/25 | 2024-03-01 | QTR3 | 23/24 | 509 | 1861686.1 |  |  | 4 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5764 | 44581315201 | 2022-10-05 | QTR2 | 22/23 | 3 | 2 | 260 | 438 | 434 | 4 | 0 | 0 | 178 | 0 | 2470270 | 88750 | 2381520 | 2521141 | 2333135 | 0 | 0 | 0 | 2333135 | 2331897 | -1237 | 50871 | 138 | 0 | 0 | 7077 | 0 | 0 | 0 | 26123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40811 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 | 2024-09-20 | QTR1 | 24/25 | 514 | 2317408.58 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5767 | 44101615201 | 2022-12-07 | QTR2 | 22/23 | 2 | 4 | 500 | 613 | 470 | 143 | 0 | 0 | 113 | 0 | 10858007 | 107000 | 10751007 | 11031557 | 11200282 | -5737 | 0 | -5737 | 11194546 | 11153083 | -41463 | 173550 | 82 | 0 | 0 | 22533 | 0 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28633 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-09-21 | QTR1 | 24/25 | 514 | 11024234.24 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5769 | 44571515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 300 | 329 | 307 | 22 | 0 | 0 | 29 | 0 | 1830300 | 50000 | 1780300 | 1832918 | 1800435 | 0 | 0 | 0 | 1800435 | 1797799 | -18 | 2618 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-04-05 | QTR4 | 23/24 | 509 | 1120306 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5772 | 44569315201 | 2022-10-26 | QTR2 | 22/23 | 2 | 4 | 260 | 406 | 403 | 3 | 0 | 0 | 146 | 0 | 1859536 | 50000 | 1809536 | 1934513 | 2110697 | 0 | 0 | 0 | 2110697 | 2104981 | -360 | 74977 | 110 | 0 | 0 | 2993 | 0 | 0 | 0 | 30505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33497 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2024-11-26 | QTR2 | 24/25 | 2024-06-18 | QTR4 | 23/24 | 509 | 1660927.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5775 | 44570715201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 250 | 301 | 296 | 5 | 0 | 0 | 51 | 0 | 937052 | 40000 | 897052 | 937052 | 953863 | 0 | 0 | 0 | 953863 | 953841 | -22 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 509 | 869794.25 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5776 | 44577115201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 180 | 239 | 237 | 2 | 0 | 0 | 50 | 9 | 1821012 | 34500 | 1786512 | 1822431 | 1669665 | 0 | 0 | 0 | 1669665 | 1667048 | -1198 | 1419 | 9 | 0 | 0 | 0 | 0 | 0 | 7 | 6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 20302 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-07-03 | QTR1 | 24/25 | 2024-02-07 | QTR3 | 23/24 | 509 | 749625.55 |  |  | 9 | 41 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5783 | 44576715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 230 | 286 | 283 | 3 | 0 | 0 | 56 | 0 | 2041154 | 50000 | 1991154 | 2041154 | 2088238 | -10982 | 0 | -10982 | 2077256 | 2076683 | -573 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-07-31 | QTR1 | 24/25 | 509 | 1415550.25 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5790 | 44976415201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 140 | 228 | 227 | 1 | 0 | 0 | 88 | 0 | 752281 | 32500 | 719781 | 730305 | 733353 | 0 | 0 | 0 | 733353 | 733353 | 0 | -21976 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21976 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-09 | QTR1 | 24/25 | 2024-07-01 | QTR1 | 24/25 | 515 | 919900 |  |  | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5803 | 44760315201 | 2023-09-13 | QTR1 | 23/24 | 1 | 0 | 130 | 188 | 188 | 0 | 0 | 0 | 58 | 0 | 1608172 | 50000 | 1558172 | 1608172 | 1619759 | 0 | 0 | 0 | 1619759 | 1619759 | 0 | 0 | 48 | 0 | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12510 | 0 | F592934582 | HIGHWAY SAFETY DEVICES LLC | N/A | N/A | N/A | N/A | 2025-03-04 | QTR3 | 24/25 | 2024-11-14 | QTR2 | 24/25 | 512 | 1561950.34 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5820 | 45222925201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 120 | 133 | 85 | 48 | 0 | 0 | 13 | 0 | 607569 | 43750 | 563819 | 607569 | 467724 | 0 | 0 | 0 | 467724 | 467724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-06-06 | QTR4 | 23/24 | 513 | 1006632.6 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5821 | 45222935201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 110 | 115 | 108 | 7 | 0 | 0 | 5 | 0 | 843345 | 50000 | 793345 | 843345 | 748398 | 0 | 0 | 0 | 748398 | 748398 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-10-11 | QTR2 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 512 | 1601075 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50B7 | 44519015201 | 2023-03-22 | QTR3 | 22/23 | 2 | 3 | 200 | 318 | 316 | 2 | 0 | 0 | 97 | 21 | 5675430 | 50000 | 5625430 | 5781935 | 5808256 | 0 | 0 | 0 | 5808256 | 5808213 | -42 | 106505 | 73 | 0 | 21 | 81505 | 0 | 0 | 0 | 1396 | 1396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 109568 | 1396 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-07 | QTR3 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 515 | 4958774.67 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50B9 | 44530415201 | 2022-11-01 | QTR2 | 22/23 | 2 | 2 | 360 | 618 | 616 | 2 | 0 | 0 | 241 | 17 | 8212061 | 78500 | 8133561 | 8298265 | 8545900 | 0 | 0 | 0 | 8545900 | 8501569 | -33727 | 86204 | 142 | 0 | 5 | 52398 | 0 | 0 | 12 | 78440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 141442 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-04 | QTR3 | 24/25 | 2024-10-18 | QTR2 | 24/25 | 515 | 8347740.25 |  |  | 17 | 99 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50F0 | 44985615201 | 2024-01-04 | QTR3 | 23/24 | 1 | 0 | 145 | 171 | 170 | 1 | 0 | 0 | 26 | 0 | 512012 | 33532 | 478480 | 512012 | 459051 | 0 | 0 | 0 | 459051 | 459051 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-02-06 | QTR3 | 24/25 | 2024-09-20 | QTR1 | 24/25 | 515 | 709684.5 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50F8 | 45056015201 | 2024-02-06 | QTR3 | 23/24 | 1 | 1 | 99 | 127 | 126 | 1 | 0 | 0 | 28 | 0 | 265206 | 8549 | 256657 | 286124 | 270632 | 0 | 0 | 0 | 270632 | 270632 | 0 | 20918 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 | 2024-12-06 | QTR2 | 24/25 | 514 | 184540.3 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51A5 | 44102115201 | 2020-08-04 | QTR1 | 20/21 | 1 | 3 | 340 | 431 | 430 | 1 | 0 | 0 | 91 | 0 | 6379293 | 53300 | 6325993 | 6413111 | 6544055 | 0 | 0 | 0 | 6544055 | 6599601 | 58191 | 33818 | 63 | 0 | 0 | 39765 | 0 | 0 | 0 | 33443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79708 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-01-07 | QTR3 | 24/25 | 2022-03-09 | QTR3 | 21/22 | 509 | 5366278.89 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52B5 | 44892215201 | 2022-11-01 | QTR2 | 22/23 | 1 | 1 | 227 | 362 | 438 | -76 | 76 | 0 | 76 | 59 | 1894138 | 50000 | 1844138 | 1894138 | 1942917 | -13063 | 0 | -13063 | 1929854 | 1929854 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274499988 | UNDERWATER MECHANIX SERVICES LL | N/A | N/A | N/A | N/A | 2025-02-12 | QTR3 | 24/25 | 2024-06-20 | QTR4 | 23/24 | 513 | 2335390.2 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55A2 | 44539515201 | 2022-05-03 | QTR4 | 21/22 | 2 | 1 | 370 | 456 | 435 | 21 | 0 | 0 | 86 | 0 | 2300883 | 50000 | 2250883 | 2307982 | 2243671 | 0 | 0 | 0 | 2243671 | 2236572 | 0 | 7099 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-17 | QTR1 | 24/25 | 2024-01-03 | QTR3 | 23/24 | 514 | 3525844 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B6 | 44935915201 | 2022-12-06 | QTR2 | 22/23 | 3 | 2 | 160 | 265 | 263 | 2 | 0 | 0 | 84 | 21 | 1222662 | 50000 | 1172662 | 1249746 | 1348640 | 0 | 0 | 0 | 1348640 | 1330056 | 0 | 27084 | 37 | 0 | 0 | 4402 | 0 | 0 | 0 | 36173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40575 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 | 2024-11-21 | QTR2 | 24/25 | 513 | 1969965.2 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56A6 | 43585935201 | 2021-09-08 | QTR1 | 21/22 | 3 | 4 | 700 | 1022 | 1022 | 0 | 0 | 0 | 322 | 0 | 26294705 | 150000 | 26144705 | 26513733 | 26091334 | 0 | 0 | 0 | 26091334 | 26689837 | 646783 | 219028 | 172 | 14 | 0 | 215010 | 35852 | 12 | 0 | 22391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52360 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 298302 | 35852 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-03-19 | QTR3 | 24/25 | 2024-08-19 | QTR1 | 24/25 | 515 | 25307967.68 |  |  | 0 | 118 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B1 | 44892415201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 100 | 107 | 74 | 33 | 0 | 0 | 7 | 0 | 284414 | 17010 | 267404 | 284414 | 279401 | 0 | 0 | 0 | 279401 | 279401 | 0 | 0 | 4 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 | 2024-06-24 | QTR4 | 23/24 | 512 | 357218.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B5 | 44520815201 | 2023-02-09 | QTR3 | 22/23 | 2 | 4 | 290 | 514 | 522 | -8 | 8 | 0 | 219 | 5 | 4388512 | 52000 | 4336512 | 4453426 | 4571799 | 0 | 0 | 0 | 4571799 | 4544333 | -17160 | 64913 | 121 | 0 | 0 | 0 | 0 | 0 | 5 | 60395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 60395 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-05 | QTR3 | 24/25 | 2025-01-10 | QTR3 | 24/25 | 513 | 5307734.85 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B7 | 44852015201 | 2023-02-09 | QTR3 | 22/23 | 2 | 1 | 300 | 377 | 377 | 0 | 0 | 0 | 77 | 0 | 3806259 | 50000 | 3756259 | 3806259 | 3824085 | 0 | 0 | 0 | 3824085 | 3824085 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-01-15 | QTR3 | 24/25 | 2024-08-19 | QTR1 | 24/25 | 509 | 4832736.89 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B9 | 44892315201 | 2023-03-07 | QTR3 | 22/23 | 1 | 0 | 125 | 179 | 130 | 49 | 0 | 0 | 54 | 0 | 698401 | 38161 | 660240 | 698401 | 660240 | 0 | 0 | 0 | 660240 | 660240 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-09-13 | QTR1 | 24/25 | 2024-04-11 | QTR4 | 23/24 | 507 | 801387 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B0 | 44139515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 77 | 2 | 1915338 | 50000 | 1865338 | 1915338 | 1927494 | 0 | 0 | 0 | 1927494 | 1927350 | -144 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11926 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-13 | QTR1 | 24/25 | 2024-06-21 | QTR4 | 23/24 | 509 | 1563670.35 |  |  | 2 | 48 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B9 | 44709915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 260 | 337 | 337 | 0 | 0 | 0 | 77 | 0 | 7890001 | 88000 | 7802001 | 7890001 | 8013155 | 0 | 0 | 0 | 8013155 | 8041936 | 28780 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 514 | 9077031.16 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58A3 | 44288315201 | 2022-05-03 | QTR4 | 21/22 | 2 | 6 | 250 | 598 | 598 | 0 | 0 | 0 | 303 | 45 | 4049477 | 50000 | 3999477 | 4613851 | 4761016 | 0 | 0 | 0 | 4761016 | 4731574 | -29441 | 564374 | 230 | 0 | 0 | 15531 | 0 | 0 | 45 | 414568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 434074 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-12-26 | QTR2 | 24/25 | 2024-09-25 | QTR1 | 24/25 | 514 | 4247697.07 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58B0 | 44878915201 | 2023-06-06 | QTR4 | 22/23 | 1 | 2 | 170 | 213 | 213 | 0 | 0 | 0 | 43 | 0 | 2634873 | 50000 | 2584873 | 2681332 | 2729605 | 0 | 0 | 0 | 2729605 | 2729605 | 0 | 46460 | 31 | 0 | 0 | 7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7002 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2024-12-13 | QTR2 | 24/25 | 2024-08-01 | QTR1 | 24/25 | 509 | 1708500.26 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58B9 | 45050715201 | 2023-04-04 | QTR4 | 22/23 | 2 | 0 | 160 | 337 | 336 | 1 | 0 | 0 | 147 | 30 | 2493493 | 50000 | 2443493 | 2493493 | 2516855 | 0 | 0 | 0 | 2516855 | 2516855 | 0 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-02-27 | QTR3 | 24/25 | 2024-08-30 | QTR1 | 24/25 | 515 | 2557573.29 |  |  | 30 | 54 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B1 | 44521215201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 280 | 381 | 381 | 0 | 0 | 0 | 101 | 0 | 5421862 | 54000 | 5367862 | 5450128 | 5275721 | 0 | 0 | 0 | 5275721 | 5273757 | -1964 | 28266 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-03-11 | QTR3 | 24/25 | 2024-11-16 | QTR2 | 24/25 | 512 | 5678330.57 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B7 | 44290715201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 250 | 360 | 360 | 0 | 0 | 0 | 110 | 0 | 7869434 | 99500 | 7769934 | 8074202 | 8845045 | 0 | 0 | 0 | 8845045 | 8849151 | 4106 | 204768 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-03-18 | QTR3 | 24/25 | 2024-09-25 | QTR1 | 24/25 | 513 | 10565451.33 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6461 | 43647915201 | 2021-09-29 | QTR1 | 21/22 | 3 | 3 | 500 | 577 | 444 | 133 | 0 | 0 | 77 | 0 | 3700000 | 52698 | 3647302 | 3848832 | 3802731 | 0 | 320000 | 320000 | 4122731 | 3835748 | -286983 | 148832 | 48 | 0 | 0 | 102311 | 0 | 0 | 0 | 63604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 172474 | 3129 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-09-18 | QTR1 | 24/25 | 2024-06-05 | QTR4 | 23/24 | 613 | 4423635.4 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6494 | 42752125201 | 2022-01-26 | QTR3 | 21/22 | 6 | 2 | 320 | 394 | 339 | 55 | 0 | 0 | 74 | 0 | 4221888 | 50000 | 4171888 | 4224163 | 3676222 | 0 | 200000 | 200000 | 3876222 | 3699956 | -176266 | 2275 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2023-12-13 | QTR2 | 23/24 | 613 | 4370412.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6504 | 42918525201 | 2021-05-26 | QTR4 | 20/21 | 1 | 2 | 450 | 541 | 512 | 29 | 0 | 0 | 91 | 0 | 5189595 | 57167 | 5132429 | 5303929 | 5374583 | 0 | 0 | 0 | 5374583 | 5469555 | 94972 | 114333 | 55 | 0 | 0 | 152939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157298 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-12-19 | QTR2 | 24/25 | 2024-03-21 | QTR3 | 23/24 | 613 | 5707742.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6535 | 44389315201 | 2022-01-26 | QTR3 | 21/22 | 3 | 5 | 500 | 700 | 700 | 0 | 0 | 0 | 105 | 95 | 18130831 | 150000 | 17980831 | 18586475 | 18825792 | 0 | 0 | 0 | 18825792 | 19184082 | 488935 | 455645 | 61 | 0 | 0 | 55800 | 0 | 0 | 95 | 262248 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 564979 | 210000 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-09-19 | QTR1 | 24/25 | 2024-03-22 | QTR3 | 23/24 | 636 | 17118736.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6538 | 44391915201 | 2022-05-25 | QTR4 | 21/22 | 9 | 1 | 480 | 531 | 458 | 73 | 0 | 0 | 51 | 0 | 13790706 | 121591 | 13669115 | 13840706 | 13459785 | 0 | 480000 | 480000 | 13939785 | 13298540 | -641245 | 50000 | 32 | 0 | 0 | 29647 | 0 | 0 | 0 | 16702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22076 | 0 | 0 | 0 | 6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74679 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-10-02 | QTR2 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 636 | 12736630.45 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6549 | 44390715201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 280 | 315 | 256 | 59 | 0 | 0 | 35 | 0 | 4134866 | 50000 | 4084866 | 4134866 | 3997859 | 0 | 220000 | 220000 | 4217859 | 3985462 | -232397 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-20 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 636 | 4728009 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6552 | 44393615201 | 2023-01-25 | QTR3 | 22/23 | 3 | 1 | 380 | 444 | 360 | 84 | 0 | 0 | 64 | 0 | 5851269 | 63745 | 5787524 | 5854220 | 5799051 | 0 | 240000 | 240000 | 6039051 | 5776322 | -259779 | 2951 | 46 | 0 | 0 | 23873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23873 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2025-03-25 | QTR3 | 24/25 | 2024-10-30 | QTR2 | 24/25 | 613 | 6438227.63 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6559 | 43094925201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 450 | 619 | 619 | 0 | 0 | 0 | 169 | 0 | 8056848 | 70725 | 7986123 | 8075952 | 7918898 | 0 | 0 | 0 | 7918898 | 7945544 | 26646 | 19104 | 96 | 0 | 0 | 39629 | 0 | 0 | 0 | 16524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 56152 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 613 | 7161375.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6569 | 44392715201 | 2023-05-24 | QTR4 | 22/23 | 1 | 1 | 300 | 369 | 298 | 71 | 0 | 0 | 69 | 0 | 3310000 | 50000 | 3260000 | 3360000 | 3413946 | 0 | 140000 | 140000 | 3553946 | 3413962 | -139984 | 50000 | 58 | 0 | 0 | 24433 | 0 | 0 | 0 | 34007 | 9362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26610 | 0 | 0 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85698 | 9362 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 | 2024-09-20 | QTR1 | 24/25 | 613 | 3762936 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6570 | 44391015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 180 | 218 | 218 | 0 | 0 | 0 | 38 | 0 | 1901127 | 50000 | 1851127 | 1901127 | 1885735 | 0 | 0 | 0 | 1885735 | 1881176 | -4559 | 0 | 16 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37191 | 0 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46615 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-06-03 | QTR4 | 23/24 | 613 | 1978037 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6572 | 44390615201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 240 | 291 | 282 | 9 | 0 | 0 | 51 | 0 | 2360100 | 50000 | 2310100 | 2360100 | 2343530 | 0 | 0 | 0 | 2343530 | 2341786 | -1744 | 0 | 34 | 0 | 0 | 931 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 | 2024-09-03 | QTR1 | 24/25 | 613 | 2712981.65 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6K68 | 43652615201 | 2021-07-29 | QTR1 | 21/22 | 2 | 13 | 480 | 705 | 705 | 0 | 0 | 0 | 134 | 91 | 14750000 | 96232 | 14653768 | 15707585 | 16003611 | 0 | 0 | 0 | 16003611 | 15768021 | -235590 | 957585 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 170156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1327474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26803 | 0 | 0 | 0 | 86070 | 86070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 949597 | 86070 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-03-24 | QTR3 | 24/25 | 2025-02-07 | QTR3 | 24/25 | 613 | 9735202.54 |  |  | 0 | 50 | 0 | 0 | -660904 | 0 |  | DO
06DO | 06 | E6M58 | 44492015201 | 2021-05-11 | QTR4 | 20/21 | 1 | 3 | 680 | 1057 | 1057 | 0 | 0 | 0 | 377 | 0 | 5167117 | 50000 | 5117117 | 5569451 | 5567027 | 0 | 0 | 0 | 5567027 | 5567027 | 0 | 402334 | 188 | 10 | 0 | 11007 | 0 | 0 | 0 | 120107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 449910 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-06-03 | QTR4 | 23/24 | 636 | 4900000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 101 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M98 | 43029159201 | 2021-05-24 | QTR4 | 20/21 | 2 | 2 | 720 | 1041 | 1037 | 4 | 0 | 0 | 321 | 0 | 6969697 | 91407 | 6878290 | 6904270 | 6838357 | 0 | 0 | 0 | 6838357 | -125491 | -6838357 | -65427 | 60 | 0 | 0 | -71816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 13804 | 0 | 0 | 0 | 18078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | -39934 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2024-05-14 | QTR4 | 23/24 | 636 | 9167406.7 | LBDB | LOW BID DESIGN BUILD | 0 | 80 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M99 | 44694715201 | 2022-04-11 | QTR4 | 21/22 | 1 | 2 | 500 | 782 | 782 | 0 | 0 | 0 | 282 | 0 | 2597679 | 50000 | 2547679 | 2701239 | 2676164 | 0 | 0 | 0 | 2676164 | 2676164 | 0 | 103560 | 151 | 0 | 0 | -12464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 116024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 103560 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2024-10-31 | QTR2 | 24/25 | 2024-08-02 | QTR1 | 24/25 | 636 | 2860200 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 86 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O05 | 44619115201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 240 | 461 | 454 | 7 | 0 | 0 | 221 | 0 | 743939 | 33329 | 710610 | 1132936 | 975348 | 0 | 0 | 0 | 975348 | 964351 | 0 | 388997 | 182 | 0 | 0 | 378000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378000 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2025-03-25 | QTR3 | 24/25 | 2025-01-27 | QTR3 | 24/25 | 636 | 699899 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O13 | 44890615201 | 2023-01-26 | QTR3 | 22/23 | 1 | 0 | 140 | 243 | 234 | 9 | 0 | 0 | 103 | 0 | 572000 | 24741 | 547259 | 572000 | 522404 | 0 | 0 | 0 | 522404 | 521792 | -612 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 | 2024-11-20 | QTR2 | 24/25 | 613 | 519555.8 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O14 | 44882815201 | 2023-04-27 | QTR4 | 22/23 | 2 | 0 | 180 | 226 | 226 | 0 | 0 | 0 | 46 | 0 | 1149149 | 50000 | 1099149 | 1149149 | 1071932 | 0 | 0 | 0 | 1071932 | 1071773 | -159 | 0 | 32 | 0 | 0 | 8346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 8346 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-02-12 | QTR3 | 24/25 | 2024-11-12 | QTR2 | 24/25 | 636 | 1084773.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O30 | 44734515201 | 2023-04-27 | QTR4 | 22/23 | 1 | 0 | 160 | 186 | 186 | 0 | 0 | 0 | 26 | 0 | 897000 | 42988 | 854012 | 897000 | 747267 | 0 | 0 | 0 | 747267 | 747246 | -21 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-09-23 | QTR1 | 24/25 | 2024-07-18 | QTR1 | 24/25 | 613 | 902745.5 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O72 | 43029179201 | 2023-06-12 | QTR4 | 22/23 | 2 | 4 | 330 | 352 | 324 | 28 | 0 | 0 | 22 | 0 | 1937336 | 0 | 1937336 | 1987336 | 1966014 | 0 | 0 | 0 | 1966014 | 0 | -1966014 | 50000 | 0 | 0 | 0 | 13249 | 0 | 0 | 0 | 6779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28678 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-08-09 | QTR1 | 24/25 | 636 | 2649100 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O74 | 44480115201 | 2023-09-28 | QTR1 | 23/24 | 2 | 3 | 340 | 358 | 305 | 53 | 0 | 0 | 18 | 0 | 3862848 | 67369 | 3795479 | 4787648 | 4857931 | 0 | 0 | 0 | 4857931 | 4857931 | 0 | 924799 | 4 | 0 | 0 | 12221 | 0 | 0 | 0 | 663190 | 334969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276069 | 266494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951480 | 601463 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-01-07 | QTR3 | 24/25 | 2024-12-03 | QTR2 | 24/25 | 613 | 7127639.15 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7438 | 25632425201 | 2020-11-18 | QTR2 | 20/21 | 2 | 11 | 700 | 961 | 953 | 8 | 0 | 0 | 218 | 43 | 16728833 | 239863 | 16488970 | 18036076 | 18037280 | 0 | 0 | 0 | 18037280 | 18987569 | 1096394 | 1307244 | 167 | 0 | 39 | 487932 | 0 | 0 | 4 | 893855 | 7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88439 | 16356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1473608 | 23952 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-11-15 | QTR2 | 24/25 | 2023-10-19 | QTR2 | 23/24 | 714 | 19921100 |  |  | 33 | 51 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7449 | 43953215201 | 2020-11-18 | QTR2 | 20/21 | 3 | 4 | 500 | 598 | 597 | 1 | 0 | 0 | 91 | 7 | 4459994 | 50000 | 4409994 | 4666559 | 4576961 | 0 | 0 | 0 | 4576961 | 4688561 | 117308 | 206565 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 132817 | 63270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 142713 | 63270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-09-10 | QTR1 | 24/25 | 2022-10-31 | QTR2 | 22/23 | 796 | 4598900 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7458 | 25688155201 | 2021-01-27 | QTR3 | 20/21 | 2 | 7 | 398 | 888 | 888 | 0 | 0 | 0 | 199 | 291 | 7962187 | 57992 | 7904195 | 8615404 | 8747181 | 0 | 0 | 0 | 8747181 | 8731655 | 405586 | 653217 | 101 | 25 | 142 | 19202 | 0 | 19 | 92 | 516876 | 465849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 31139 | 17389 | 0 | 0 | 0 | 0 | 0 | 57 | 21127 | 21127 | 0 | 0 | 0 | 0 | 64 | 291 | 603217 | 504365 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 | 2024-02-09 | QTR3 | 23/24 | 799 | 5285500 |  |  | 19 | 54 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7464 | 43307125201 | 2022-05-25 | QTR4 | 21/22 | 2 | 1 | 425 | 478 | 381 | 97 | 0 | 0 | 53 | 0 | 5977271 | 77000 | 5900271 | 5963393 | 5896599 | 0 | 0 | 0 | 5896599 | 5865873 | -30725 | -13878 | 29 | 0 | 0 | 1254 | 0 | 0 | 0 | -31791 | 0 | 0 | 0 | 16658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3612 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-01-20 | QTR3 | 24/25 | 2024-03-06 | QTR3 | 23/24 | 796 | 4795700 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7475 | 43764415201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 260 | 423 | 423 | 0 | 0 | 0 | 104 | 59 | 4773108 | 50000 | 4723108 | 4959207 | 5064114 | 0 | 0 | 0 | 5064114 | 5050016 | 31351 | 186099 | 96 | 0 | 39 | 147305 | 0 | 0 | 0 | 8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18794 | 18794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 174985 | 18794 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-03-12 | QTR3 | 24/25 | 2023-03-31 | QTR3 | 22/23 | 796 | 4701400 |  |  | 20 | 28 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7481 | 44073315201 | 2022-08-31 | QTR1 | 22/23 | 3 | 0 | 225 | 294 | 294 | 0 | 0 | 0 | 69 | 0 | 3304021 | 50000 | 3254021 | 3304021 | 3182990 | 0 | 0 | 0 | 3182990 | 3174072 | -8918 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-11-12 | QTR2 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 796 | 3303500 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7482 | 43983115201 | 2021-10-27 | QTR2 | 21/22 | 1 | 4 | 295 | 369 | 369 | 0 | 0 | 0 | 74 | 0 | 11256386 | 131329 | 11125057 | 10574479 | 10748589 | 0 | 0 | 0 | 10748589 | 11070556 | 331923 | -681906 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 1017154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1709016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | -681906 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 | 2023-11-06 | QTR2 | 23/24 | 796 | 13466700 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7492 | 44024815201 | 2023-02-22 | QTR3 | 22/23 | 1 | 1 | 210 | 250 | 250 | 0 | 0 | 0 | 40 | 0 | 5438332 | 52000 | 5386332 | 5435828 | 5441055 | 0 | 0 | 0 | 5441055 | 5414623 | -26432 | -2504 | 24 | 0 | 0 | -2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2504 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-04 | QTR2 | 24/25 | 2024-08-07 | QTR1 | 24/25 | 799 | 5496384.15 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7497 | 43940115201 | 2022-08-31 | QTR1 | 22/23 | 1 | 3 | 375 | 460 | 460 | 0 | 0 | 0 | 85 | 0 | 7112946 | 50000 | 7062946 | 7172036 | 7363800 | 0 | 0 | 0 | 7363800 | 7320296 | -34413 | 59091 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 48118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 27 | 0 | 61729 | 2100 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 | 2024-07-25 | QTR1 | 24/25 | 799 | 6545800 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7506 | 44549415201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 210 | 273 | 269 | 4 | 0 | 0 | 63 | 0 | 4477908 | 50000 | 4427908 | 4477908 | 4516174 | 0 | 0 | 0 | 4516174 | 4513509 | -2665 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-06-12 | QTR4 | 23/24 | 796 | 4643300 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7518 | 45248755201 | 2023-12-06 | QTR2 | 23/24 | 5 | 0 | 140 | 153 | 142 | 11 | 0 | 0 | 13 | 0 | 908274 | 50000 | 858274 | 908274 | 908491 | 0 | 0 | 0 | 908491 | 908491 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2024-12-30 | QTR2 | 24/25 | 2024-09-16 | QTR1 | 24/25 | 798 | 1515975 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7M37 | 43514215201 | 2019-07-31 | QTR1 | 19/20 | 3 | 12 | 1300 | 1743 | 1717 | 26 | 0 | 0 | 235 | 208 | 80980890 | 298979 | 80681912 | 84381295 | 85235769 | 0 | 0 | 0 | 85235769 | 85499813 | 413658 | 3400405 | 130 | 0 | 0 | 317727 | 24625 | 0 | 208 | 2693729 | 70028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459570 | 443526 | 0 | 0 | 16156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 3612698 | 538180 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2025-01-30 | QTR3 | 24/25 | 2024-07-24 | QTR1 | 24/25 | 798 | 87914529.56 |  |  | 0 | 105 | 0 | 0 | -30396 | 0 |  | DO
07DO | 07 | E7N73 | 43955315201 | 2021-02-10 | QTR3 | 20/21 | 1 | 3 | 240 | 887 | 1039 | -152 | 152 | 0 | 647 | 0 | 6131310 | 61000 | 6070310 | 6338797 | 6305080 | -570912 | 0 | -570912 | 5734168 | 5526680 | 0 | 207487 | 178 | 0 | 0 | 15789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223276 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2024-09-30 | QTR1 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 799 | 6350300 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P11 | 44605115201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 237 | 237 | 0 | 0 | 0 | 57 | 0 | 5505947 | 65000 | 5440947 | 5505947 | 5635303 | 0 | 0 | 0 | 5635303 | 5612523 | -22780 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 26520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26520 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-01-20 | QTR3 | 24/25 | 2024-03-04 | QTR3 | 23/24 | 796 | 5708568 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P19 | 44025415201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 5191258 | 55000 | 5136258 | 5191258 | 5651758 | 0 | 0 | 0 | 5651758 | 5623798 | -27960 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 17807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 17807 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-15 | QTR1 | 24/25 | 2024-04-04 | QTR4 | 23/24 | 799 | 5707113.62 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P32 | 44165215201 | 2022-06-08 | QTR4 | 21/22 | 1 | 3 | 285 | 434 | 434 | 0 | 0 | 0 | 37 | 112 | 6091557 | 50000 | 6041557 | 6416319 | 6316136 | 0 | 0 | 0 | 6316136 | 6124596 | -125432 | 324762 | 127 | 0 | 0 | 46638 | 13259 | 0 | 54 | 314752 | 62190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 361390 | 75450 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 799 | 6992900 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P35 | 44165715201 | 2022-05-11 | QTR4 | 21/22 | 2 | 3 | 400 | 458 | 458 | 0 | 0 | 0 | 58 | 0 | 8986578 | 71000 | 8915578 | 9084687 | 9016111 | 0 | 0 | 0 | 9016111 | 8840279 | -171882 | 98110 | 30 | 0 | 0 | 115777 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-04-18 | QTR4 | 23/24 | 799 | 8393400 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P50 | 41685625201 | 2024-02-14 | QTR3 | 23/24 | 1 | 0 | 40 | 60 | 51 | 9 | 0 | 0 | 20 | 0 | 388968 | 16000 | 372968 | 388968 | 314971 | 0 | 0 | 0 | 314971 | 314971 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2025-01-24 | QTR3 | 24/25 | 2024-08-26 | QTR1 | 24/25 | 796 | 427400 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P81 | 44165615201 | 2023-04-12 | QTR4 | 22/23 | 2 | 4 | 150 | 187 | 187 | 0 | 0 | 0 | 37 | 0 | 2391656 | 50000 | 2341656 | 2492761 | 2474615 | 0 | 0 | 0 | 2474615 | 2474272 | -342 | 101105 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 12946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88159 | 88159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101105 | 88159 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-19 | QTR1 | 24/25 | 2024-03-14 | QTR3 | 23/24 | 799 | 2000400 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P96 | 44378315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 0 | 183 | 232 | 232 | 0 | 0 | 0 | 49 | 0 | 5338647 | 50000 | 5288647 | 5338647 | 5375414 | 0 | 0 | 0 | 5375414 | 5376462 | 1048 | 0 | 40 | 0 | 0 | 3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3833 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-17 | QTR3 | 24/25 | 2024-09-23 | QTR1 | 24/25 | 798 | 5546100 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q14 | 44349215201 | 2023-06-14 | QTR4 | 22/23 | 1 | 0 | 185 | 335 | 335 | 0 | 0 | 0 | 120 | 30 | 2636615 | 50000 | 2586615 | 2636615 | 2586233 | 0 | 0 | 0 | 2586233 | 2586234 | 1 | 0 | 101 | 0 | 0 | 25276 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25276 | 0 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 | 2024-12-02 | QTR2 | 24/25 | 796 | 2170285.15 |  |  | 30 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q20 | 44380615201 | 2023-06-07 | QTR4 | 22/23 | 1 | 2 | 100 | 103 | 101 | 2 | 0 | 0 | 3 | 0 | 1219976 | 50000 | 1169976 | 1219975 | 1270757 | 0 | 0 | 0 | 1270757 | 1271460 | 702 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 13975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46431 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-05-13 | QTR4 | 23/24 | 799 | 1145700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q21 | 44602615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 175 | 201 | 176 | 25 | 0 | 0 | 26 | 0 | 2654159 | 50000 | 2604159 | 2684159 | 2759623 | 0 | 0 | 0 | 2759623 | 2762434 | 2811 | 30000 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29582 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-29 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 796 | 2504300 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q22 | 44165315201 | 2023-06-07 | QTR4 | 22/23 | 1 | 1 | 125 | 162 | 145 | 17 | 0 | 0 | 37 | 0 | 1489626 | 50000 | 1439626 | 1494272 | 1546615 | 0 | 0 | 0 | 1546615 | 1547180 | 565 | 4646 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39202 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-06 | QTR1 | 24/25 | 2024-06-26 | QTR4 | 23/24 | 799 | 1595200 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R09 | 42421335201 | 2020-01-31 | QTR3 | 19/20 | 3 | 1 | 1200 | 1582 | 1572 | 10 | 0 | 0 | 139 | 243 | 38345345 | 150000 | 38195345 | 38534960 | 38424665 | 0 | 0 | 0 | 38424665 | 38424665 | 974984 | 189615 | 163 | 0 | 80 | 230717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 243 | 230717 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-10-25 | QTR2 | 24/25 | 2024-08-18 | QTR1 | 24/25 | 714 | 39771136 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 203 | 86 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R20 | 41075525201 | 2018-05-15 | QTR4 | 17/18 | 3 | 22 | 900 | 1664 | 1664 | 0 | 0 | 0 | 764 | 0 | 56246888 | 150000 | 56096888 | 59724057 | 59409421 | 0 | 0 | 0 | 59409421 | 59100398 | -31871 | 3477169 | 524 | 144 | 0 | 2594782 | 1765728 | 0 | 0 | 629024 | 271987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0 | 181416 | 71647 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 3310615 | 2109363 | F251607500 | AMERICAN BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2024-07-24 | QTR1 | 24/25 | 2023-01-30 | QTR3 | 22/23 | 799 | 60000000 | B0:B8:B8:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 88 | 0 | 0 | -127928 | 0 |  | DO
08DO | 08 | E8R80 | 43554315201 | 2019-06-11 | QTR4 | 18/19 | 1 | 9 | 1810 | 1897 | 1601 | 296 | 0 | 0 | 182 | -95 | 244979349 | 150000 | 244829349 | 251466172 | 255108575 | 0 | 4375439 | 4375439 | 259484014 | 258158459 | 4868615 | 6486824 | 78 | 0 | 0 | 311893 | 0 | 0 | 0 | 9734282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5045376 | 0 | 0 | 0 | 1661009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -95 | 6556771 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-20 | QTR2 | 24/25 | 2024-02-29 | QTR3 | 23/24 | 854 | 217827999.45 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 104 | 0 | -95 | -168828 | 0 |  | DO
08DO | 08 | E8R82 | 43801815201 | 2020-01-16 | QTR3 | 19/20 | 2 | 5 | 1443 | 1673 | 1666 | 7 | 0 | 0 | 230 | 0 | 61180000 | 150000 | 61030000 | 61481136 | 61477229 | 0 | 0 | 0 | 61477229 | 63363328 | 4461679 | 301136 | 133 | 0 | 0 | 40265 | 0 | 0 | 0 | 59694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206332 | 0 | 0 | 0 | 3020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412001 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-02-24 | QTR3 | 24/25 | 2024-10-07 | QTR2 | 24/25 | 854 | 58657847.3 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 97 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S90 | 43945755201 | 2021-04-20 | QTR4 | 20/21 | 5 | 13 | 533 | 998 | 998 | 0 | 0 | 0 | 465 | 0 | 21999573 | 150000 | 21849573 | 23015619 | 24155114 | 0 | 0 | 0 | 24155114 | 24813029 | 1013008 | 1016046 | 287 | 56 | 0 | 446658 | 0 | 0 | 0 | 537731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 32966 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 125872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 1143227 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-11-18 | QTR2 | 24/25 | 2024-05-10 | QTR4 | 23/24 | 854 | 23025803.13 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T40 | 44497815201 | 2021-12-14 | QTR2 | 21/22 | 1 | 4 | 451 | 635 | 633 | 2 | 0 | 0 | 159 | 25 | 3179902 | 50000 | 3129902 | 3285956 | 3273170 | 0 | 0 | 0 | 3273170 | 3273170 | 0 | 106054 | 127 | 0 | 0 | 51083 | 0 | 0 | 25 | 51409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 132422 | 0 | F811490207 | RTECH ENGINEERING LLC | N/A | N/A | N/A | N/A | 2025-03-03 | QTR3 | 24/25 | 2024-11-15 | QTR2 | 24/25 | 854 | 3360453.31 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T67 | 44262415201 | 2022-04-12 | QTR4 | 21/22 | 2 | 5 | 322 | 521 | 518 | 3 | 0 | 0 | 199 | 0 | 12517000 | 119797 | 12397203 | 12877010 | 12203064 | 0 | 0 | 0 | 12203064 | 12123596 | -79468 | 360010 | 133 | 0 | 0 | 108673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796 | 0 | 0 | 0 | 257897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369366 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-10-03 | QTR2 | 24/25 | 2024-03-11 | QTR3 | 23/24 | 854 | 13936524.01 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T77 | 44925315201 | 2022-05-17 | QTR4 | 21/22 | 2 | 4 | 440 | 677 | 666 | 11 | 0 | 0 | 237 | 0 | 5565378 | 50000 | 5515378 | 5757378 | 5730235 | 0 | 0 | 0 | 5730235 | 5763102 | 32867 | 192000 | 120 | 0 | 0 | 33771 | 0 | 0 | 0 | 77369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 62 | 0 | 111140 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-11-14 | QTR2 | 24/25 | 2024-09-11 | QTR1 | 24/25 | 854 | 5213379.79 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T82 | 42897215201 | 2022-09-13 | QTR1 | 22/23 | 2 | 2 | 568 | 619 | 464 | 155 | 0 | 0 | 51 | 0 | 2504148 | 58519 | 2445628 | 2711373 | 2646645 | 0 | 0 | 0 | 2646645 | 2639419 | 0 | 207226 | 9 | 0 | 0 | 227557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234782 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-07-11 | QTR1 | 24/25 | 854 | 4806556.91 |  |  | 0 | 42 | 0 | 0 | 7226 | 0 |  | DO
08DO | 08 | E8T94 | 43578625201 | 2022-10-25 | QTR2 | 22/23 | 1 | 1 | 165 | 221 | 221 | 0 | 0 | 0 | 41 | 15 | 2596848 | 50000 | 2546848 | 2612139 | 2505813 | 0 | 0 | 0 | 2505813 | 2503780 | -2033 | 15291 | 18 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15291 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-04 | QTR2 | 24/25 | 2024-05-17 | QTR4 | 23/24 | 854 | 2699146.4 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T95 | 44171915201 | 2022-10-25 | QTR2 | 22/23 | 3 | 3 | 508 | 651 | 615 | 36 | 0 | 0 | 143 | 0 | 21849074 | 150000 | 21699074 | 22014286 | 22325271 | 0 | 0 | 0 | 22325271 | 22079112 | -230948 | 165212 | 97 | 0 | 0 | 189344 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201 | 0 | 0 | 0 | 11368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225106 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2024-12-09 | QTR2 | 24/25 | 2024-10-17 | QTR2 | 24/25 | 854 | 21254879.86 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U06 | 44262295201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 283 | 429 | 429 | 0 | 0 | 0 | 116 | 30 | 4494080 | 56314 | 4437766 | 4544080 | 4339328 | 0 | 0 | 0 | 4339328 | 4339341 | 13 | 50000 | 67 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 43390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 43390 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2025-02-07 | QTR3 | 24/25 | 2025-01-10 | QTR3 | 24/25 | 854 | 5696150.1 |  |  | 30 | 49 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U07 | 44969215201 | 2023-04-11 | QTR4 | 22/23 | 1 | 2 | 309 | 374 | 360 | 14 | 0 | 0 | 65 | 0 | 3578802 | 48428 | 3530375 | 3752049 | 3491844 | 0 | 0 | 0 | 3491844 | 3491287 | -556 | 173247 | 32 | 0 | 0 | 181887 | 0 | 0 | 0 | 10641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194888 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 | 2024-09-25 | QTR1 | 24/25 | 854 | 2800800.1 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U10 | 44933415201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 200 | 267 | 260 | 7 | 0 | 0 | 67 | 0 | 870362 | 44352 | 826010 | 876241 | 829659 | 0 | 0 | 0 | 829659 | 823780 | 0 | 5880 | 47 | 0 | 0 | 9988 | 0 | 0 | 0 | 9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20747 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2025-02-05 | QTR3 | 24/25 | 2024-12-02 | QTR2 | 24/25 | 854 | 937383.97 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U47 | 43854915201 | 2023-09-12 | QTR1 | 23/24 | 2 | 1 | 357 | 376 | 155 | 221 | 0 | 0 | 19 | 0 | 1133672 | 50000 | 1083672 | 1158672 | 1068668 | 0 | 0 | 0 | 1068668 | 1068668 | 0 | 25000 | 4 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2024-07-31 | QTR1 | 24/25 | 2024-07-08 | QTR1 | 24/25 | 854 | 2868747.02 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U57 | 44942315201 | 2023-09-12 | QTR1 | 23/24 | 1 | 0 | 165 | 196 | 196 | 0 | 0 | 0 | 29 | 2 | 1336393 | 50000 | 1286393 | 1336393 | 1288438 | 0 | 0 | 0 | 1288438 | 1288438 | 0 | 0 | 17 | 0 | 2 | 18473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18473 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2025-01-17 | QTR3 | 24/25 | 2024-09-17 | QTR1 | 24/25 | 854 | 1342593.14 |  |  | 2 | 12 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0