## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 91135261 | 90436273 | 92053858 | 92394187 | -70500 | 92469518 | 2.248% | 100% | 972203 | 1.075% | 918596 | 1.008% | 2825 | 777 | 27.5% | 283 | 10.02% | 29 | 1.027% | 145 | 5.133% | 2999 | 6.159% | 4059 | 3887 | 2827 | 0.0708% | 75%
| District Let | 69426819 | 68752731 | 69922658 | 70843877 | 0 | 70017808 | 1.84% | 100% | 551896 | 0.8027% | 495838 | 0.7142% | 2450 | 468 | 19.1% | 213 | 8.694% | 18 | 0.7347% | 47 | 1.918% | 2515 | 2.653% | 3196 | 3132 | 2451 | 0.04082% | 90%
| All Contracts | 160562080 | 159189004 | 161976516 | 163238064 | -70500 | 162487326 | 2.072% | 100% | 1524099 | 0.9574% | 1414434 | 0.8809% | 5275 | 1245 | 23.6% | 496 | 9.403% | 47 | 0.891% | 192 | 3.64% | 5514 | 4.531% | 7255 | 7019 | 5278 | 0.05687% | 83.33%
2 | Central Let | 165611712 | 164331968 | 170103780 | 174464651 | 0 | 174929796 | 6.449% | 81.25% | 4944714 | 3.009% | 4492068 | 2.712% | 5329 | 1779 | 33.38% | 798 | 14.97% | 608 | 11.41% | 1437 | 26.97% | 7374 | 38.37% | 9365 | 9166 | 6589 | 23.64% | 50%
| District Let | 27954818 | 27684304 | 43117534 | 43762723 | 0 | 43856162 | 58.42% | 33.33% | 15342962 | 55.42% | 15162716 | 54.24% | 1719 | 424 | 24.67% | 268 | 15.59% | 392 | 22.8% | 506 | 29.44% | 2617 | 52.24% | 3206 | 3199 | 2507 | 45.84% | 0%
| All Contracts | 193566530 | 192016272 | 213221314 | 218227374 | 0 | 218785958 | 13.94% | 73.68% | 20287676 | 10.57% | 19654784 | 10.15% | 7048 | 2203 | 31.26% | 1066 | 15.12% | 1000 | 14.19% | 1943 | 27.57% | 9991 | 41.76% | 12571 | 12365 | 9096 | 29.06% | 42.11%
3 | Central Let | 23094727 | 22762261 | 23335522 | 23712535 | 0 | 23663316 | 3.959% | 80% | 355052 | 1.56% | 240795 | 1.043% | 989 | 664 | 67.14% | 266 | 26.9% | 334 | 33.77% | 185 | 18.71% | 1508 | 52.48% | 2443 | 2442 | 1512 | 52.88% | 40%
| District Let | 37290549 | 36836374 | 37868400 | 38170502 | 0 | 38047799 | 3.289% | 100% | 601033 | 1.632% | 577851 | 1.55% | 2067 | 695 | 33.62% | 398 | 19.25% | 172 | 8.321% | 181 | 8.757% | 2420 | 17.08% | 3504 | 3421 | 2328 | 12.63% | 77.78%
| All Contracts | 60385276 | 59598635 | 61203922 | 61883037 | 0 | 61711115 | 3.545% | 92.86% | 956085 | 1.604% | 818646 | 1.356% | 3056 | 1359 | 44.47% | 664 | 21.73% | 506 | 16.56% | 366 | 11.98% | 3928 | 28.53% | 5947 | 5863 | 3840 | 25.65% | 64.29%
4 | Central Let | 21285618 | 20901914 | 21408227 | 20470416 | 0 | 20470615 | -2.063% | 100% | 183430 | 0.8776% | 122609 | 0.576% | 1842 | 380 | 20.63% | 176 | 9.555% | 123 | 6.678% | 30 | 1.629% | 1995 | 8.306% | 2478 | 2448 | 1892 | 2.714% | 100%
| District Let | 65893465 | 65328041 | 69061710 | 67897429 | 0 | 67682936 | 3.605% | 87.5% | 3004295 | 4.599% | 3021620 | 4.586% | 2823 | 597 | 21.15% | 229 | 8.112% | 75 | 2.657% | 48 | 1.7% | 2946 | 4.357% | 3753 | 3538 | 2712 | -3.932% | 100%
| All Contracts | 87179083 | 86229955 | 90469937 | 88367845 | 0 | 88153551 | 2.231% | 92.86% | 3187725 | 3.697% | 3144229 | 3.607% | 4665 | 977 | 20.94% | 405 | 8.682% | 198 | 4.244% | 78 | 1.672% | 4941 | 5.916% | 6231 | 5986 | 4604 | -1.308% | 100%
5 | Central Let | 105686363 | 104937413 | 109965500 | 111351351 | 0 | 110145301 | 4.963% | 100% | 3746611 | 3.57% | 4279137 | 4.049% | 3780 | 751 | 19.87% | 555 | 14.68% | 22 | 0.582% | 161 | 4.259% | 3963 | 4.841% | 5254 | 5115 | 3809 | 0.7672% | 100%
| District Let | 19468420 | 19111568 | 19783422 | 19251620 | 0 | 19131759 | 0.1056% | 100% | 376628 | 1.971% | 315002 | 1.618% | 1437 | 364 | 25.33% | 972 | 67.64% | 0 | 0% | 53 | 3.688% | 1490 | 3.688% | 2828 | 2798 | 1462 | 1.74% | 100%
| All Contracts | 125154783 | 124048981 | 129748922 | 130602971 | 0 | 129277060 | 4.215% | 100% | 4123239 | 3.324% | 4594139 | 3.671% | 5217 | 1115 | 21.37% | 1527 | 29.27% | 22 | 0.4217% | 214 | 4.102% | 5453 | 4.524% | 8082 | 7913 | 5271 | 1.035% | 100%
6 | Central Let | 36546548 | 36157425 | 36692652 | 35830917 | 760000 | 35732341 | -1.176% | 100% | 136939 | 0.3787% | 146104 | 0.3998% | 1660 | 149 | 8.976% | 118 | 7.108% | 22 | 1.325% | 0 | 0% | 1682 | 1.325% | 1949 | 1792 | 1525 | -8.133% | 100%
| District Let | 44236297 | 44036297 | 45938406 | 46029869 | 2100000 | 46060442 | 4.597% | 100% | 1682982 | 3.822% | 1702108 | 3.848% | 1300 | 112 | 8.615% | 75 | 5.769% | 0 | 0% | 89 | 6.846% | 1389 | 6.846% | 1576 | 1475 | 1288 | -0.9231% | 100%
| All Contracts | 80782845 | 80193722 | 82631058 | 81860786 | 2860000 | 81792783 | 1.994% | 100% | 1819921 | 2.269% | 1848212 | 2.288% | 2960 | 261 | 8.818% | 193 | 6.52% | 22 | 0.7432% | 89 | 3.007% | 3071 | 3.75% | 3525 | 3267 | 2813 | -4.966% | 100%
7 | Central Let | 98389555 | 98027357 | 107644265 | 108531073 | 0 | 108310702 | 10.49% | 80% | 8368468 | 8.537% | 9254710 | 9.406% | 1871 | 333 | 17.8% | 163 | 8.712% | 44 | 2.352% | 93 | 4.971% | 2008 | 7.322% | 2435 | 2295 | 1799 | -3.848% | 100%
| District Let | 91174261 | 90751261 | 99662716 | 99051289 | 300000 | 98754019 | 8.818% | 85.71% | 5303973 | 5.845% | 8488455 | 9.31% | 1930 | 377 | 19.53% | 179 | 9.275% | 0 | 0% | 400 | 20.73% | 2330 | 20.73% | 2830 | 2459 | 1903 | -1.399% | 100%
| All Contracts | 189563816 | 188778618 | 207306981 | 207582362 | 300000 | 207064721 | 9.687% | 83.33% | 13672441 | 7.243% | 17743165 | 9.36% | 3801 | 710 | 18.68% | 342 | 8.998% | 44 | 1.158% | 493 | 12.97% | 4338 | 14.13% | 5265 | 4754 | 3702 | -2.605% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 39205058 | 38711062 | 40331929 | 39386605 | 37398 | 39265394 | 1.432% | 100% | 1333224 | 3.444% | 1126871 | 2.874% | 1978 | 249 | 12.59% | 217 | 10.97% | 45 | 2.275% | 50 | 2.528% | 2073 | 4.803% | 2527 | 2193 | 1727 | -12.69% | #VALUE!
| All Contracts | 39205058 | 38711062 | 40331929 | 39386605 | 37398 | 39265394 | 1.432% | 100% | 1333224 | 3.444% | 1126871 | 2.874% | 1978 | 249 | 12.59% | 217 | 10.97% | 45 | 2.275% | 50 | 2.528% | 2073 | 4.803% | 2527 | 2193 | 1727 | -12.69% | 100%
Totals This Qtr | Central Let | 541749784 | 537554611 | 561203804 | 566755130 | 689500 | 565721589 | 5.24% | 90.91% | 18707417 | 3.48% | 19454019 | 3.591% | 18296 | 4833 | 26.42% | 2359 | 12.89% | 1182 | 6.46% | 2051 | 11.21% | 21529 | 17.67% | 27983 | 27145 | 19953 | 9.057% | 76.36%
| District Let | 394649687 | 391211638 | 425686775 | 424393914 | 2437398 | 422816319 | 8.079% | 92.31% | 28196993 | 7.208% | 30890461 | 7.827% | 15704 | 3286 | 20.92% | 2551 | 16.24% | 702 | 4.47% | 1374 | 8.749% | 17780 | 13.22% | 23420 | 22215 | 16378 | 4.292% | 88.46%
| All Contracts | 936399471 | 928766249 | 986890579 | 991149044 | 3126898 | 988537908 | 6.436% | 91.59% | 46904410 | 5.05% | 50344480 | 5.376% | 34000 | 8119 | 23.88% | 4910 | 14.44% | 1884 | 5.541% | 3425 | 10.07% | 39309 | 15.61% | 51403 | 49360 | 36331 | 6.856% | 82.24%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2024/2025 | Central Let | 1279648903 | 1266221414 | 1312978963 | 1321473742 | 2536230 | 1326167192 | 4.734% | 90.72% | 35949687 | 2.839% | 33549474 | 2.622% | 54906 | 16687 | 30.39% | 7064 | 12.87% | 4509 | 8.212% | 6770 | 12.33% | 66185 | 20.54% | 86228 | 84771 | 61020 | 11.14% | 80.93%
| District Let | 1318833837 | 1310154031 | 1361025980 | 1368896349 | 5751239 | 1365653292 | 4.236% | 92.91% | 42375966 | 3.234% | 42720355 | 3.239% | 43619 | 9909 | 22.72% | 5114 | 11.72% | 2675 | 6.133% | 2106 | 4.828% | 48400 | 10.96% | 62882 | 61439 | 46416 | 6.412% | 89.76%
| All Contracts | 2598482740 | 2576375445 | 2674004943 | 2690370091 | 8287469 | 2691820484 | 4.481% | 91.59% | 78325653 | 3.04% | 76269829 | 2.935% | 98525 | 26596 | 26.99% | 12178 | 12.36% | 7184 | 7.292% | 8876 | 9.009% | 114585 | 16.3% | 149110 | 146210 | 107436 | 9.044% | 84.42%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 82.62% | 1 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 102.1% | 1 | 2409623 | 620443 | 176 | 66 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98
| 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 99.67% | 1 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16716202 | 100.7% | 1 | -131944 | 0 | 136 | 36 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58
| 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 107.6% | 1 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | 103.4% | 1 | -56953 | 31648 | 155 | 46 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 |  | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72
| 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 98.29% | 1 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | 101.3% | 1 | -795 | 0 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94
| 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | 143.7% | 0 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11523071 | 103.6% | 1 | 108362 | 84591 | 129 | 47 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29
| 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | 117.8% | 1 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | 98.84% | 1 | -14467 | 132711 | 40 | 25 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39
| 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 128% | 0 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 104.6% | 1 | 0 | 38502 | 57 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56
| 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 108% | 1 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | 106.5% | 1 | -31093 | 10701 | 70 | 24 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 8 | 12 | 27 | 2825 | 4059 | 3887 | 75% | 6 | 172 | 59 | 0 | 1089 | 145 | 91135261 | 698988 | 90436273 | 92053858 | 92394187 | -219920 | -70500 | -290420 | 92103767 | 92469518 | 100% | 8 | 2282733 | 918596 | 777 | 283 | 0 | 42 | 285112 | 0 | 0 | 103 | 396079 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 65721 | 0 | 0 | 0 | 81113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 145 | 972203 | 70927
| 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 86% | 1 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | 100.8% | 1 | -10506 | 70548 | 51 | 23 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78
| 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | 110.3% | 1 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | 96.34% | 1 | -126080 | -565229 | 188 | 42 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94
| 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 111.3% | 1 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 106.2% | 1 | 143 | 103763 | 8 | 19 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 |  | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93
| 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 96.11% | 1 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | 100.1% | 1 | -1029 | -94765 | 25 | 22 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22
| 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 104% | 1 | 199 | -6676 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 |  | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01
| 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | 104.6% | 1 | -480611 | 790067 | 61 | 52 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 |  | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | 125.5% | 0 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | 108.1% | 1 | -22 | 198130 | 44 | 22 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02
| 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 103.1% | 1 | 0 | 0 | 32 | 3 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24
| 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 88.57% | 1 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | 102.3% | 1 | -757 | 0 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2
| 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 81.43% | 1 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | 79.21% | 1 | -1 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 10 | 13 | 28 | 2450 | 3196 | 3132 | 90% | 9 | 64 | 35 | 0 | 674 | 72 | 69426819 | 674088 | 68752731 | 69922658 | 70843877 | -69495 | 0 | -69495 | 70774381 | 70017808 | 100% | 10 | -618664 | 495838 | 468 | 213 | 0 | 26 | -235538 | 0 | 3 | 21 | 918334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 18 | 47 | 551896 | 0
| District 01 Totals |  |  |  |  | 18 | 25 | 55 | 5275 | 7255 | 7019 | 83.33% | 15 | 236 | 94 | 0 | 1763 | 217 | 160562080 | 1373076 | 159189004 | 161976516 | 163238064 | -289415 | -70500 | -359915 | 162878148 | 162487326 | 100% | 18 | 1664069 | 1414434 | 1245 | 496 | 0 | 68 | 49574 | 0 | 3 | 124 | 1314413 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 65721 | 0 | 15 | 0 | 82916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 47 | 192 | 1524099 | 70927
| 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 100% | 1 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 106.8% | 1 | 1493028 | 0 | 244 | 59 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 |  | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12
| 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 136.1% | 0 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | 103.2% | 1 | -345380 | 417407 | 191 | 70 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23
| 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 220% | 0 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | 101.9% | 1 | -330946 | 172500 | 300 | 55 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17
| 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 175.3% | 0 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 117.4% | 0 | 24575 | 1868912 | 57 | 104 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86
| 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 141% | 0 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | 120.5% | 0 | -14114 | 807199 | 68 | 49 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18
| 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 156.8% | 0 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 115.9% | 0 | 0 | 482619 | 107 | 92 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25
| 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 106.7% | 1 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | 108.1% | 1 | -190784 | 275992 | 290 | 29 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41
| 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 98.82% | 1 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | 98.71% | 1 | -3560 | 0 | 137 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85
| 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 123.1% | 0 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | 107.6% | 1 | -105664 | 385943 | 91 | 66 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99
| 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 99.63% | 1 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | 99.05% | 1 | -1654 | 0 | 67 | 36 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6
| 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 87.5% | 1 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | 100.9% | 1 | -957 | 37326 | 19 | 24 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75
| 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 130.6% | 0 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | 100.1% | 1 | -4770 | 0 | 79 | 56 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66
| 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 146.7% | 0 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 102.3% | 1 | 0 | 0 | 34 | 22 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25
| 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 78.55% | 1 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 101.8% | 1 | 0 | 0 | 34 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9
| 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 116.7% | 1 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | 100.6% | 1 | -19104 | 0 | 59 | 31 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02
| 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 79% | 1 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | 103.5% | 1 | -13 | 44170 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 16 | 28 | 35 | 5329 | 9365 | 9166 | 50% | 8 | 199 | 0 | 0 | 2599 | 1437 | 165611712 | 1279743 | 164331968 | 170103780 | 174464651 | 0 | 0 | 0 | 174464651 | 174929796 | 81.25% | 13 | 500657 | 4492068 | 1779 | 798 | 188 | 844 | 3290553 | 11998 | 21 | 195 | 1267869 | 142560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 74192 | 0 | 29 | 90 | 119342 | 0 | 0 | 0 | 0 | 0 | 345 | 190 | 192758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 1437 | 4944714 | 154558
| 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 142.7% | 0 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | 99.22% | 1 | -280479 | 0 | 46 | 77 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 151.1% | 0 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 111.6% | 0 | 0 | 68722 | 137 | 85 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5
| 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 146.4% | 0 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 191.5% | 0 | 498724 | 15093994 | 241 | 106 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 17 | 1719 | 3206 | 3199 | 0% | 0 | 7 | 0 | 0 | 981 | 506 | 27954818 | 270515 | 27684304 | 43117534 | 43762723 | 0 | 0 | 0 | 43762723 | 43856162 | 33.33% | 1 | 218245 | 15162716 | 424 | 268 | 29 | 92 | 264018 | 0 | 56 | 221 | 433928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 506 | 15342962 | 0
| District 02 Totals |  |  |  |  | 19 | 32 | 52 | 7048 | 12571 | 12365 | 42.11% | 8 | 206 | 0 | 0 | 3580 | 1943 | 193566530 | 1550258 | 192016272 | 213221314 | 218227374 | 0 | 0 | 0 | 218227374 | 218785958 | 73.68% | 14 | 718902 | 19654784 | 2203 | 1066 | 217 | 936 | 3554571 | 11998 | 77 | 416 | 1701797 | 142560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 0 | 14682569 | 0 | 29 | 90 | 119342 | 0 | 0 | 0 | 0 | 0 | 345 | 383 | 229397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1943 | 20287676 | 154558
| 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 177.5% | 0 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | 111.8% | 0 | -35209 | 87105 | 260 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26
| 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 109.6% | 1 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | 101.6% | 1 | -13342 | 98995 | 72 | 70 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24
| 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 396.7% | 0 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 98.85% | 1 | 0 | 23011 | 20 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1
| 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 181.1% | 0 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 99.59% | 1 | 0 | 0 | 262 | 51 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67
| 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | 100.2% | 1 | -668 | 31684 | 50 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 5 | 8 | 10 | 989 | 2443 | 2442 | 40% | 2 | 1 | 0 | 0 | 1224 | 230 | 23094727 | 332466 | 22762261 | 23335522 | 23712535 | 0 | 0 | 0 | 23712535 | 23663316 | 80% | 4 | -49219 | 240795 | 664 | 266 | 120 | 3 | 2170 | 0 | 4 | 12 | 64753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 170 | 288129 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 185 | 355052 | 579
| 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 177.7% | 0 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | 107.6% | 1 | -38559 | 222198 | 136 | 62 | 0 | 51 | 147417 | 0 | 0 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25
| 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 106.9% | 1 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 96.1% | 1 | 0 | 0 | 87 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66
| 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 106.5% | 1 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 103% | 1 | 2857 | 141871 | 76 | 52 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36
| 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | 127.5% | 0 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 105.1% | 1 | 297 | 210235 | 157 | 84 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86
| 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 78.33% | 1 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22
| 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 100% | 1 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | 96.96% | 1 | -7350 | 3547 | 133 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48
| 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 98.89% | 1 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 107.3% | 1 | 0 | 0 | 34 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46
| 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 64.44% | 1 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 101.5% | 1 | 0 | 0 | 44 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15
| 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | 103.3% | 1 | -11799 | 0 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 9 | 15 | 7 | 2067 | 3504 | 3421 | 77.78% | 7 | 83 | 18 | 0 | 1259 | 181 | 37290549 | 454174 | 36836374 | 37868400 | 38170502 | -68148 | 0 | -68148 | 38102354 | 38047799 | 100% | 9 | -54554 | 577851 | 695 | 398 | 0 | 57 | 296373 | 0 | 45 | 5 | 245215 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 115 | 49930 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 181 | 601033 | 1539
| District 03 Totals |  |  |  |  | 14 | 23 | 17 | 3056 | 5947 | 5863 | 64.29% | 9 | 84 | 18 | 0 | 2483 | 411 | 60385276 | 786640 | 59598635 | 61203922 | 61883037 | -68148 | 0 | -68148 | 61814889 | 61711115 | 92.86% | 13 | -103773 | 818646 | 1359 | 664 | 120 | 60 | 298543 | 0 | 49 | 17 | 309968 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 285 | 338059 | 579 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 366 | 956085 | 2118
| 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 99.79% | 1 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 101.6% | 1 | 134358 | 0 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 |  | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88
| 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 108.5% | 1 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 101.1% | 1 | 0 | 0 | 84 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32
| 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 104.4% | 1 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 96.71% | 1 | 2250 | 122609 | 65 | 44 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26
| 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 99.52% | 1 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | 98.1% | 1 | -1000 | 0 | 157 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58
| 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 117.4% | 1 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 97.26% | 1 | 0 | 0 | 22 | 19 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17
| 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 87% | 1 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 99.5% | 1 | 0 | 0 | 22 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 6 | 9 | 4 | 1842 | 2478 | 2448 | 100% | 6 | 30 | 0 | 0 | 606 | 30 | 21285618 | 383704 | 20901914 | 21408227 | 20470416 | 0 | 0 | 0 | 20470416 | 20470615 | 100% | 6 | 135608 | 122609 | 380 | 176 | 0 | 0 | 35147 | 0 | 50 | 30 | 147067 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 30 | 183430 | 31860
| 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 110.7% | 1 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 72.58% | 1 | 0 | 6930 | 77 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6
| 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 80.76% | 1 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | 105% | 1 | -1518 | 106590 | 57 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81
| 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 90.84% | 1 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | 105.3% | 1 | -144790 | 1946522 | 57 | 27 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36
| 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 114.5% | 1 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | 112.3% | 0 | -6049 | 459484 | 135 | 44 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25
| 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 100% | 1 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 106% | 1 | 0 | 469019 | 175 | 50 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2
| 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 109.1% | 1 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | 98.27% | 1 | -5116 | 11303 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1
| 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 95.14% | 1 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | 96.73% | 1 | -952 | 0 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705
| 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 98.29% | 1 | 0 | 21772 | 38 | 4 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 34 | 2823 | 3753 | 3538 | 100% | 8 | 215 | 0 | 0 | 882 | 48 | 65893465 | 565423 | 65328041 | 69061710 | 67897429 | 0 | 0 | 0 | 67897429 | 67682936 | 87.5% | 7 | -158425 | 3021620 | 597 | 229 | 30 | 0 | 142626 | 1201843 | 0 | 48 | 2456857 | 34121 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242438 | 3335 | 0 | 0 | 179301 | 22700 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 75 | 48 | 3004295 | 1261998
| District 04 Totals |  |  |  |  | 14 | 22 | 38 | 4665 | 6231 | 5986 | 100% | 14 | 245 | 0 | 0 | 1488 | 78 | 87179083 | 949127 | 86229955 | 90469937 | 88367845 | 0 | 0 | 0 | 88367845 | 88153551 | 92.86% | 13 | -22817 | 3144229 | 977 | 405 | 30 | 0 | 177773 | 1201843 | 50 | 78 | 2603924 | 65981 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242438 | 3335 | 0 | 0 | 180516 | 22700 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 198 | 78 | 3187725 | 1293858
| 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 109.3% | 1 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48288286 | 107.9% | 1 | 2318006 | 2811186 | 343 | 216 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5
| 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 81.23% | 1 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | 100.8% | 1 | -826558 | 767164 | 32 | 51 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT
| 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 99.6% | 1 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | 93.43% | 1 | -632 | 20000 | 119 | 27 | 0 | 0 | 34331 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36784 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6
| 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 113.4% | 1 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | 106.1% | 1 | -490 | 148206 | 43 | 49 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1
| 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 104.2% | 1 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | 107.1% | 1 | -33657 | 423497 | 66 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25
| 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 99.29% | 1 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | 100.1% | 1 | -20420 | 16623 | 41 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87
| 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 98.67% | 1 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | 105.9% | 1 | -58186 | 46835 | 73 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850
| 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 97.63% | 1 | 0 | 0 | 8 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14
| 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 25% | 1 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 93.85% | 1 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52
| 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 107.8% | 1 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 101.2% | 1 | 0 | 49558 | 26 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 10 | 25 | 35 | 3780 | 5254 | 5115 | 100% | 10 | 139 | 0 | 0 | 1331 | 143 | 105686363 | 748950 | 104937413 | 109965500 | 111351351 | 0 | 0 | 0 | 111351351 | 110145301 | 100% | 10 | 1378063 | 4279137 | 751 | 555 | 0 | 59 | 1693372 | 0 | 0 | 102 | 1406171 | 102334 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 248888 | 16623 | 0 | 0 | 26437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 161 | 3746611 | 118957
| 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 101.6% | 1 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | 100.1% | 1 | -6 | 0 | 25 | 18 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5
| 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 110.7% | 1 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | 99.36% | 1 | -472 | 1774 | 46 | 26 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07
| 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 95.38% | 1 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 98.21% | 1 | 0 | 34060 | 38 | 34 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65
| 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 111.9% | 1 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 101.4% | 1 | 0 | 0 | 12 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75
| 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | 101.3% | 1 | -45651 | 207492 | 59 | 37 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59
| 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 100% | 1 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 100% | 1 | 0 | 0 | 141 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | 99.77% | 1 | -4843 | 71676 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 7 | 13 | 10 | 1437 | 2828 | 2798 | 100% | 7 | 30 | 0 | 0 | 1336 | 55 | 19468420 | 356852 | 19111568 | 19783422 | 19251620 | 0 | 0 | 0 | 19251620 | 19131759 | 100% | 7 | -50972 | 315002 | 364 | 972 | 0 | 17 | 174411 | 0 | 0 | 0 | 128561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 376628 | 0
| District 05 Totals |  |  |  |  | 17 | 38 | 45 | 5217 | 8082 | 7913 | 100% | 17 | 169 | 0 | 0 | 2667 | 198 | 125154783 | 1105802 | 124048981 | 129748922 | 130602971 | 0 | 0 | 0 | 130602971 | 129277060 | 100% | 17 | 1327091 | 4594139 | 1115 | 1527 | 0 | 76 | 1867783 | 0 | 0 | 102 | 1534732 | 102334 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15 | 275464 | 16623 | 0 | 0 | 73517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362296 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 214 | 4123239 | 118957
| 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 96.88% | 1 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | 96.37% | 1 | -102 | 704 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75
| 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 96.5% | 1 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | 99.74% | 1 | -7887 | 83991 | 29 | 47 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 86.6% | 1 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | 96.97% | 1 | -460650 | 46466 | 10 | 16 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 82.25% | 1 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | 100.8% | 1 | -342511 | 0 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 |  | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 111% | 1 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | 99.89% | 1 | -2973 | 14943 | 59 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 5 | 21 | 11 | 1660 | 1949 | 1792 | 100% | 5 | 157 | 0 | 0 | 285 | 4 | 36546548 | 389123 | 36157425 | 36692652 | 35830917 | 0 | 760000 | 760000 | 36590917 | 35732341 | 100% | 5 | -814123 | 146104 | 149 | 118 | 0 | 0 | 73666 | 0 | 22 | 0 | 101684 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24744 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 22 | 0 | 136939 | 21158
| 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 103.3% | 1 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | 105% | 1 | -173492 | 1702108 | 104 | 54 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 83.57% | 1 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | 98.52% | 1 | -140063 | 0 | 8 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 2 | 6 | 14 | 1300 | 1576 | 1475 | 100% | 2 | 101 | 0 | 0 | 187 | 89 | 44236297 | 200000 | 44036297 | 45938406 | 46029869 | 0 | 2100000 | 2100000 | 48129869 | 46060442 | 100% | 2 | -313555 | 1702108 | 112 | 75 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 689851 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 89 | 1682982 | 0
| District 06 Totals |  |  |  |  | 7 | 27 | 25 | 2960 | 3525 | 3267 | 100% | 7 | 258 | 0 | 0 | 472 | 93 | 80782845 | 589123 | 80193722 | 82631058 | 81860786 | 0 | 2860000 | 2860000 | 84720786 | 81792783 | 100% | 7 | -1127678 | 1848212 | 261 | 193 | 0 | 0 | 674933 | 0 | 22 | 0 | 488361 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 714595 | 0 | 0 | 0 | 76137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -160309 | 0 | 22 | 89 | 1819921 | 21158
| 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 90.42% | 1 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 112% | 0 | 2218662 | 9203668 | 61 | 77 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 112.9% | 1 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | 98.62% | 1 | -54392 | 30299 | 59 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800
| 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 100% | 1 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | 102.8% | 1 | -1005 | 20743 | 111 | 50 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000
| 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 99.49% | 1 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | 104.9% | 1 | -3017 | 0 | 95 | 25 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840
| 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 115% | 1 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 99.05% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-08 | QTR4 | 24/25 | 799 | 611133
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 5 | 6 | 29 | 1871 | 2435 | 2295 | 100% | 5 | 140 | 0 | 0 | 540 | 24 | 98389555 | 362198 | 98027357 | 107644265 | 108531073 | 0 | 0 | 0 | 108531073 | 108310702 | 80% | 4 | 2160248 | 9254710 | 333 | 163 | 0 | 0 | 493221 | 0 | 15 | 21 | 3112405 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 44 | 93 | 8368468 | 1601156
| 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 118% | 1 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | 101.4% | 1 | -300000 | 126352 | 45 | 25 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | 101.6% | 1 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 84.24% | 1 | 0 | 124000 | 98 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100
| 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 78.26% | 1 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 86.6% | 1 | 0 | 2196 | 17 | 13 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 |  | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163
| 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 110% | 1 | 0 | 85185 | 50 | 21 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805
| 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 86.67% | 1 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 99.58% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 799 | 516283
| 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 100.8% | 1 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 110.2% | 0 | 1620860 | 8138472 | 120 | 64 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -117901 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 94.5% | 1 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | 98.31% | 1 | -4137 | 12250 | 46 | 39 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 7 | 9 | 27 | 1930 | 2830 | 2459 | 100% | 7 | 371 | 2 | 0 | 556 | 344 | 91174261 | 423000 | 90751261 | 99662716 | 99051289 | -3398 | 300000 | 296602 | 99347891 | 98754019 | 85.71% | 6 | 1316723 | 8488455 | 377 | 179 | 0 | 250 | 2763101 | 316345 | 0 | 5 | 1780074 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -117901 | 0 | 0 | 400 | 5303973 | 1011566
| District 07 Totals |  |  |  |  | 12 | 15 | 56 | 3801 | 5265 | 4754 | 100% | 12 | 511 | 2 | 0 | 1096 | 368 | 189563816 | 785198 | 188778618 | 207306981 | 207582362 | -3398 | 300000 | 296602 | 207878964 | 207064721 | 83.33% | 10 | 3476971 | 17743165 | 710 | 342 | 0 | 250 | 3256322 | 316345 | 15 | 26 | 4892479 | 418884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5144147 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 494204 | 368484 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -1452680 | 0 | 44 | 493 | 13672441 | 2612722
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 104.4% | 1 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | 102.1% | 1 | -46667 | 1006123 | 45 | 54 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74
| 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 109.6% | 1 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | 101.7% | 1 | -5101 | 36197 | 122 | 57 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 |  | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59
| 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 109.7% | 1 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 96.26% | 1 | 0 | 24353 | 27 | 32 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34
| 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 41.85% | 1 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 99.42% | 1 | 0 | 0 | 13 | 33 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28
| 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 81.25% | 1 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | 104.2% | 1 | -37398 | 60198 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 97.86% | 1 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 106.9% | 1 | 0 | 0 | 18 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 6 | 10 | 12 | 1978 | 2527 | 2193 | #VALUE! | 6 | 334 | 0 | 0 | 511 | 38 | 39205058 | 493996 | 38711062 | 40331929 | 39386605 | 0 | 37398 | 37398 | 39424003 | 39265394 | 100% | 6 | -89166 | 1126871 | 249 | 217 | 0 | 0 | 234370 | 0 | 0 | 14 | 491862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 531731 | 0 | 0 | 0 | 75263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 1333224 | 0
| District 08 Totals |  |  |  |  | 6 | 10 | 12 | 1978 | 2527 | 2193 | 100% | 6 | 334 | 0 | 0 | 511 | 38 | 39205058 | 493996 | 38711062 | 40331929 | 39386605 | 0 | 37398 | 37398 | 39424003 | 39265394 | 100% | 6 | -89166 | 1126871 | 249 | 217 | 0 | 0 | 234370 | 0 | 0 | 14 | 491862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 36 | 531731 | 0 | 0 | 0 | 75263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 1333224 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 55 | 109 | 151 | 18296 | 27983 | 27145 | 76.36% | 42 | 838 | 59 | 0 | 7674 | 2013 | 541749784 | 4195172 | 537554611 | 561203804 | 566755130 | -219920 | 689500 | 469580 | 567224710 | 565721589 | 90.91% | 50 | 5593967 | 19454019 | 4833 | 2359 | 308 | 948 | 5873241 | 11998 | 112 | 463 | 6496028 | 751863 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 242 | 5734942 | 739087 | 29 | 90 | 1117676 | 335970 | 0 | 0 | 0 | 0 | 418 | 190 | 876770 | 160277 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | -1400687 | 0 | 1182 | 2051 | 18707417 | 1999195
| Statewide District Let Contracts SubTotal |  |  |  |  | 52 | 83 | 149 | 15704 | 23420 | 22215 | 88.46% | 46 | 1205 | 55 | 0 | 6386 | 1333 | 394649687 | 3438048 | 391211638 | 425686775 | 424393914 | -141041 | 2437398 | 2296357 | 426690270 | 422816319 | 92.31% | 48 | 249632 | 30890461 | 3286 | 2551 | 59 | 442 | 4240628 | 1518188 | 104 | 314 | 6841508 | 71520 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 255 | 16259782 | 3335 | 15 | 4 | 386345 | 22700 | 0 | 0 | 0 | 0 | 118 | 193 | 379511 | 208207 | 0 | 0 | 93000 | 0 | 0 | 166 | 451154 | 451154 | 26 | 0 | 0 | 0 | 0 | 0 | -463755 | 0 | 702 | 1374 | 28196993 | 2275103
| Statewide Totals |  |  |  |  | 107 | 192 | 300 | 34000 | 51403 | 49360 | 82.24% | 88 | 2043 | 114 | 0 | 14060 | 3346 | 936399471 | 7633220 | 928766249 | 986890579 | 991149044 | -360961 | 3126898 | 2765937 | 993914980 | 988537908 | 91.59% | 98 | 5843599 | 50344480 | 8119 | 4910 | 367 | 1390 | 10113869 | 1530186 | 216 | 777 | 13337536 | 823383 | 0 | 0 | 18275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 497 | 21994724 | 742422 | 44 | 94 | 1504021 | 358670 | 0 | 0 | 0 | 0 | 536 | 383 | 1256281 | 368484 | 0 | 0 | 93000 | 0 | 60 | 166 | 451154 | 451154 | 26 | 118 | 0 | 0 | 0 | 0 | -1864442 | 0 | 1884 | 3425 | 46904410 | 4274298

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1V08 | 19602265201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-02 | 6226258 | 6296806 | 6274547 | 70547.94 | 0 | 6264042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6274547 | 6264042 | -10506 | 7418504
1 | E1V10 | 44155015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-16 | 14609258 | 14044029 | 14088333 | -565228.69 | -3245 | 13959008 | -3245 | 0 | 0 | 0 | 0 | 0 | -3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3245 | 14085087 | 13959008 | -126080 | 14926350
1 | E1V13 | 44893915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-09-19 | 5289078 | 5392842 | 5545592 | 103763.45 | 0 | 5545735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 5760652
1 | E1V22 | 44620615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-20 | 5142423 | 5047658 | 5138834 | -94764.75 | 0 | 5137805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138834 | 5137805 | -1029 | 4496918
1 | E1V23 | 44743415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-07-20 | 5558710 | 5552034 | 5723019 | -6675.84 | 0 | 5741811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5723019 | 5741811 | 18793 | 5765208
1 | E1V51 | 44743715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-02 | 23141400 | 23931467 | 24545579 | 790066.61 | 0 | 24064967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24545579 | 24064967 | -480611 | 26691037 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1W13 | 44594215201 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2024-02-15 | 2428636 | 2626766 | 2708707 | 198129.96 | -66250 | 2642436 | -66250 | 0 | 0 | 0 | 0 | 0 | -66250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66250 | 2642457 | 2642436 | -22 | 3681296
1 | E1W75 | 44923315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-18 | 2560003 | 2560003 | 2586788 | 0 | 0 | 2586788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 3481659
1 | E1W76 | 44897215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-15 | 3352588 | 3352588 | 3378389 | 0 | 0 | 3377632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 4285958
1 | E1W79 | 44023015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-09-19 | 1118465 | 1118465 | 854089 | 0 | 0 | 854089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854089 | 854089 | -1 | 991704
1 | T1754 | 41924345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-06-10 | 44711727 | 45332170 | 46495372 | 620442.65 | 0 | 47278762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46495372 | 47278762 | 783390 | 49671696
1 | T1833 | 44634515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 16756829 | 16756829 | 16918647 | 0 | -70500 | 16716202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70500 | -70500 | -70500 | 16848147 | 16716202 | -131944 | 17387335
1 | T1843 | 43695525201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-07-27 | 4165582 | 4197230 | 4319692 | 31647.71 | 0 | 4262739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4319692 | 4262739 | -56953 | 3563245
1 | T1852 | 44787215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 3084175 | 3084175 | 3074445 | 0 | 0 | 3073651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 2364266
1 | T1855 | 44547315201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11238774 | 11323365 | 11568463 | 84591.09 | -143070 | 11537149 | -143070 | 0 | 0 | 0 | 0 | 0 | -143070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143070 | 11425393 | 11537149 | 111756 | 12534705
1 | T1866 | 43903215201 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2023-11-15 | 3945642 | 4078353 | 4013289 | 132711.4 | -76850 | 3923705 | -76850 | 0 | 0 | 0 | 0 | 0 | -76850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76850 | 3936439 | 3923705 | -12734 | 5005578
1 | T1868 | 44740215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-02-28 | 1036497 | 1074999 | 1074468 | 38501.79 | 0 | 1074468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074468 | 1074468 | 0 | 1164569
1 | T1881 | 43802715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 6196035 | 6206737 | 6556044 | 10701.34 | 0 | 6524950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 6886951
2 | E20S2 | 21054545201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 8601469 | 8601469 | 8734394 | 0 | 0 | 8453915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 8397276 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20T6 | 44278015201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-02-15 | 1676236 | 1744958 | 1814629 | 68721.9 | 0 | 1814629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 2494428
2 | E2Z53 | 43035245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-02-20 | 17677113 | 32771107 | 33306856 | 15093994.45 | 0 | 33713424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33306856 | 33713424 | 406568 | 14339167
2 | T2839 | 44342115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 31969186 | 31969186 | 32489212 | 0 | 0 | 33982240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 35449756
2 | T2844 | 43935615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 19892956 | 20310363 | 20717832 | 417407.11 | 0 | 20372452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20717832 | 20372452 | -345380 | 16227519
2 | T2854 | 44554515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 10095026 | 10267526 | 10526210 | 172500 | 0 | 10199858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10526210 | 10199858 | -326352 | 10655889
2 | T2863 | 43744115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-01-12 | 14032373 | 15901285 | 16261074 | 1868911.96 | 0 | 16285649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16261074 | 16285649 | 24575 | 15021661
2 | T2865 | 44351715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-11-16 | 7663000 | 8470199 | 9163770 | 807198.83 | 0 | 9151881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163770 | 9151881 | -11890 | 7014633
2 | T2889 | 43575615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3832776 | 4315395 | 4383212 | 482619.04 | 0 | 4383212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 4521037
2 | T2894 | 44540215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 12471547 | 12747539 | 13553931 | 275991.77 | 0 | 13363147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 11980864
2 | T2916 | 43993715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 10398707 | 10398707 | 10268067 | 0 | 0 | 10264664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10268067 | 10264664 | -3403 | 8834994
2 | T2934 | 44331015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 26057502 | 26443445 | 27980036 | 385943.3 | 0 | 27874372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 24163400
2 | T2954 | 44542015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3819110 | 3819110 | 3735111 | 0 | 0 | 3733457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 5040192
2 | T2961 | 43633015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3521000 | 3558326 | 3560864 | 37326.4 | 0 | 3626016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560864 | 3626016 | 65152 | 3765541
2 | T2962 | 44796215201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 7958218 | 7958218 | 7882304 | 0 | 0 | 7877534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 8827614
2 | T2966 | 21086555201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2921783 | 2921783 | 2938946 | 0 | 0 | 2938946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 3224885
2 | T2981 | 45220125201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 2914229 | 2914229 | 2917184 | 0 | 0 | 2917184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 4244876
2 | T2985 | 43761415201 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 7308506 | 7308506 | 7304574 | 0 | 0 | 7285470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 8026688
2 | T9037 | 44627925214 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 755793 | 799963 | 782324 | 44170 | 0 | 782311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782324 | 782311 | -13 | 588438
3 | E3V54 | 44554115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-02-09 | 9981474 | 10203672 | 10678123 | 222197.51 | 0 | 10639564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 10144016
3 | E3V77 | 40919375201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-10-12 | 3075367 | 3075367 | 2907496 | 0 | 0 | 2907496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 4067369
3 | E3V81 | 44563415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-06-08 | 7280451 | 7422322 | 7437743 | 141871 | 0 | 7440600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 6184892
3 | E3W40 | 44374425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6286877 | 6497112 | 6613095 | 210234.99 | -68148 | 6607189 | -68148 | 0 | 0 | 0 | 0 | 0 | -68148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68148 | 6544947 | 6607189 | 62243 | 5983265
3 | E3W68 | 45102815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-13 | 112106 | 112106 | 103639 | 0 | 0 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103639 | 103639 | 0 | 174993
3 | E3W69 | 42696125201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-11-09 | 4685111 | 4688658 | 4492681 | 3546.7 | 0 | 4485331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 5910727
3 | E3W79 | 45109915201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-04-11 | 485265 | 485265 | 487819 | 0 | 0 | 487819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487819 | 487819 | 0 | 555113
3 | E3X08 | 45103115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-07-11 | 1112248 | 1112248 | 1077908 | 0 | 0 | 1077908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 1273505
3 | E3X52 | 43078225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-11 | 4271650 | 4271650 | 4371998 | 0 | 0 | 4360199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 4754953
3 | T3804 | 42697315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 6212045 | 6299150 | 6924822 | 87104.94 | 0 | 6889613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 5759918
3 | T3837 | 22259365201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 11772258 | 11871253 | 11834603 | 98994.59 | 0 | 11821261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 13447557
3 | T3868 | 41344925201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 1298401 | 1321412 | 1234071 | 23011 | 0 | 1234071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 1300164
3 | T3874 | 44188015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 988409 | 988409 | 938135 | 0 | 0 | 938135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938135 | 938135 | 0 | 990879
3 | T3891 | 43467815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2823614 | 2855298 | 2780904 | 31684.39 | 0 | 2780236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 3805810
4 | E4U48 | 44146615201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 2126000 | 2132929 | 1513603 | 6929.94 | 0 | 1513603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513603 | 1513603 | 0 | 2622052
4 | E4U88 | 43999925201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-04-07 | 10631541 | 10738131 | 11100934 | 106590.35 | 0 | 11099417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11100934 | 11099417 | -1518 | 10492575
4 | E4V62 | 43695815201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-18 | 31058595 | 33155117 | 32699199 | 1946522.44 | 0 | 32559543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32699199 | 32559543 | -139657 | 29695111
4 | E4W05 | 44047315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-02 | 3993841 | 4453325 | 4438530 | 459484.36 | 0 | 4433029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438530 | 4433029 | -5501 | 4033616
4 | E4W54 | 44618515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 8153790 | 8619435 | 8570644 | 465645.84 | 0 | 8570644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8570644 | 8570644 | 0 | 7653131
4 | E4W82 | 44610515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-01-05 | 4881711 | 4893014 | 4759434 | 11302.53 | 0 | 4771645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759434 | 4771645 | 12211 | 5716819
4 | E4W93 | 44764815201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-12 | 3198987 | 3198987 | 3046918 | 0 | 0 | 3045966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 3443705
4 | E4X17 | 44655115201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 1849000 | 1870772 | 1768167 | 21772.08 | 0 | 1768167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 2011837
4 | T4560 | 44004315201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2472960 | 2472960 | 2581880 | 0 | 0 | 2588651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581880 | 2588651 | 6772 | 2686958
4 | T4627 | 44384615201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 1831417 | 1831417 | 1800868 | 0 | 0 | 1800868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 2390409
4 | T4645 | 44610215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 12833449 | 12956058 | 12287948 | 122609.04 | 0 | 12290198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12287948 | 12290198 | 2250 | 14351247
4 | T4664 | 44699715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1247247 | 1247247 | 1175544 | 0 | 0 | 1174544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 1347695
4 | T4687 | 45222715201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1600545 | 1600545 | 1508063 | 0 | 0 | 1508063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 2128846
4 | T4708 | 44754315201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-07-31 | 1300000 | 1300000 | 1243700 | 0 | 0 | 1243700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 1369377
5 | E50F1 | 44656815201 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2024-02-06 | 1104118 | 1104118 | 1062935 | 0 | 0 | 1062929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 1174164
5 | E51F2 | 44768815201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-04-02 | 1504656 | 1506430 | 1447570 | 1774.33 | 0 | 1447098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447570 | 1447098 | -472 | 1590260
5 | E51F9 | 43912415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-02 | 4408516 | 4442576 | 4279968 | 34060.07 | 0 | 4279968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279968 | 4279968 | 0 | 6688705
5 | E53F8 | 45022745201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-04 | 1498164 | 1498164 | 1468694 | 0 | 0 | 1468694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 1507975
5 | E54B3 | 44521415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-03 | 6964127 | 7171619 | 7043664 | 207492.45 | 0 | 6998013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7043664 | 6998013 | -45651 | 9627439
5 | E59A5 | 44780715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-06 | 973615 | 973615 | 939263 | 0 | 0 | 939263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939263 | 939263 | 0 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E59B2 | 43986415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-02-06 | 3015224 | 3086900 | 3009526 | 71675.77 | 0 | 3004683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009526 | 3004683 | -4843 | 3337723
5 | T5706 | 42955615201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 44888403 | 47699589 | 50521720 | 2811185.71 | 0 | 50750843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50521720 | 50750843 | 229122 | 37019155
5 | T5777 | 44042425201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 22896706 | 23663870 | 23767312 | 767163.74 | 0 | 22940754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23767312 | 22940754 | -826558 | 28387050 | B10 | ACC - BONUS/INCENT/DISINCENT
5 | T5778 | 44569215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 1617324 | 1637324 | 1467772 | 20000 | 0 | 1467140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 1625739
5 | T5795 | 24259285201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 8347803 | 8496009 | 8830863 | 148205.6 | 0 | 8830373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8830863 | 8830373 | -490 | 8013785
5 | T5799 | 44571615201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 7000000 | 7423497 | 7482575 | 423497.41 | 0 | 7448919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7482575 | 7448919 | -33657 | 8074701
5 | T5805 | 44709215201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 3271306 | 3287930 | 3244926 | 16623.23 | 0 | 3224506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 4597691
5 | T5806 | 44709815201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 9892142 | 9938977 | 10455307 | 46835.26 | 0 | 10397121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10455307 | 10397121 | -58186 | 11922850
5 | T5833 | 44708915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2100000 | 2100000 | 2001416 | 0 | 0 | 2001416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 2701146
5 | T5857 | 45613715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 117123 | 113191 | 103346 | -3931.68 | 0 | 103346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103346 | 103346 | 0 | 180486
5 | T9030 | 44199035223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5555556 | 5605113 | 5565155 | 49557.59 | 0 | 5565155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 5530000
6 | E6M86 | 43351125201 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2021-05-27 | 41366428 | 43068537 | 44950000 | 1702108.31 | 1960000 | 45038064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 160000 | 0 | 1960000 | 1960000 | 46910000 | 45038064 | -1871936 | 33950112 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | E6O12 | 44391925201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 2869869 | 2869869 | 2778313 | 0 | 140000 | 2778250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 2865779 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6466 | 43992315201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 749749 | 750453 | 687268 | 704 | 0 | 687166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687268 | 687166 | -102 | 759571
6 | T6541 | 44390215201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-02-22 | 6112543 | 6196534 | 6055588 | 83991.29 | 0 | 6047700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6055588 | 6047700 | -7887 | 4898503 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6555 | 44598715201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-04-26 | 15230513 | 15276979 | 14673045 | 46466.35 | 440000 | 14652396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 440000 | 440000 | 15113045 | 14652396 | -460650 | 16721998 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6562 | 44393715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 9816354 | 9816354 | 9814725 | 0 | 320000 | 9792214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 10415642 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6575 | 44780615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 4637389 | 4652332 | 4600291 | 14943 | 0 | 4597318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600291 | 4597318 | -2973 | 4247705 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | E7P77 | 44146315201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-05-10 | 3366760 | 3493112 | 3363518 | 126351.52 | 300000 | 3363518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | E7Q31 | 44384115201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-12-13 | 1681476 | 1805476 | 1410753 | 124000 | -3398 | 1407355 | -3398 | 0 | 0 | 0 | 0 | 0 | -3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3398 | 1407355 | 1407355 | 0 | 1673100
7 | E7Q53 | 44583015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-05-08 | 1599000 | 1601196 | 1343560 | 2195.84 | 0 | 1343560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343560 | 1343560 | 0 | 1936163
7 | E7Q75 | 45288915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-12 | 1296714 | 1381899 | 1384246 | 85184.94 | 0 | 1384246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384246 | 1384246 | 0 | 1695805
7 | E7Q94 | 45273615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-11 | 259111 | 259111 | 235124 | 0 | 0 | 235124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235124 | 235124 | 0 | 516283
7 | E7R21 | 42451335201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2021-05-20 | 81649200 | 89787672 | 91076513 | 8138472.09 | 0 | 91676950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91076513 | 91676950 | 600437 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R40 | 44335825201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-07 | 1322000 | 1334250 | 1257998 | 12249.84 | 0 | 1253861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257998 | 1253861 | -4137 | 1543770 | LBDB | LOW BID DESIGN BUILD
7 | T7472 | 43182125201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | 85239705 | 94443373 | 97569383 | 9203668.27 | 0 | 97817624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97569383 | 97817624 | 248241 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7509 | 44588615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 8085082 | 8115381 | 7967342 | 30299.15 | 0 | 7993474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7967342 | 7993474 | 26132 | 9550800
7 | T7514 | 45069315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 2469300 | 2490043 | 2487609 | 20743.16 | 0 | 2486604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 2285000
7 | T7523 | 44697315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 2049777 | 2049777 | 2101379 | 0 | 0 | 2098362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 2385840
7 | T7538 | 44939815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-15 | 545691 | 545691 | 518518 | 0 | 0 | 518518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518518 | 518518 | 0 | 611133
8 | E8U04 | 44602415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-03-21 | 16184460 | 17190583 | 16458548 | 1006122.94 | 0 | 16411881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458548 | 16411881 | -46667 | 18390077
8 | E8U19 | 44588515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-11 | 11226810 | 11263007 | 11344464 | 36197.44 | 0 | 11339363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344464 | 11339363 | -5101 | 11461891
8 | E8U32 | 44925335201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2023-05-09 | 3649071 | 3673424 | 3464348 | 24353 | 0 | 3464348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 4370418
8 | E8U46 | 43854815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-14 | 4734726 | 4734726 | 4628034 | 0 | 0 | 4628034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 8236620
8 | E8U56 | 44942325201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2023-08-22 | 1804313 | 1864511 | 1827419 | 60197.92 | 37398 | 1827419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37398 | 0 | 0 | 0 | 0 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 1786238 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8U95 | 44917535201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-04-09 | 1605678 | 1605678 | 1663792 | 0 | 0 | 1663792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 1739460

## Sheet1 (hidden)
01CO | 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 2409623 | 620443 | 176 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO | 8 | 01co | 1 | 8
01CO | 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16716202 | -131944 | 0 | 136 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO | 10 | 01do | 9 | 18
01CO | 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | -56953 | 31648 | 155 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 16 | 02co | 19 | 34
01CO | 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 3 | 02do | 35 | 37
01CO | 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11523071 | 108362 | 84591 | 129 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO | 5 | 03co | 38 | 42
01CO | 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | -14467 | 132711 | 40 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO | 9 | 03do | 43 | 51
01CO | 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 0 | 38502 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 6 | 04co | 52 | 57
01CO | 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 10701 | 70 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71 |  |  | 16 | 24 | 0 | 0 | 0 | 0 |  | CO | 8 | 04do | 58 | 65
01DO | 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | -10506 | 70548 | 51 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO | 10 | 05co | 66 | 75
01DO | 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | -126080 | -565229 | 188 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94 |  |  | 21 | 42 | 0 | 0 | 0 | 0 | T | DO | 7 | 05do | 76 | 82
01DO | 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 103763 | 8 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO | 5 | 06co | 83 | 87
01DO | 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | -1029 | -94765 | 25 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22 |  |  | 0 | 22 | 0 | 0 | -132703 | 0 |  | DO | 2 | 06do | 88 | 89
01DO | 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 199 | -6676 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO | 5 | 07co | 90 | 94
01DO | 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | -480611 | 790067 | 61 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 52 | 0 | 0 | 0 | 0 |  | DO | 7 | 07do | 95 | 101
01DO | 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | -22 | 198130 | 44 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 102 | 101
01DO | 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 0 | 32 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO | 6 | 08do | 102 | 107
01DO | 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | -1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 0 | 244 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12 |  |  | 120 | 59 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | -345380 | 417407 | 191 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23 |  |  | 113 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | -330946 | 172500 | 300 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17 |  |  | 232 | 55 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 24575 | 1868912 | 57 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86 |  |  | 120 | 104 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | -14114 | 807199 | 68 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 482619 | 107 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25 |  |  | 24 | 92 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 275992 | 290 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41 |  |  | 137 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | -3560 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 385943 | 91 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 0 | 67 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | -957 | 37326 | 19 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 0 | 79 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 0 | 34 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 0 | 59 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02 |  |  | 16 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | -13 | 44170 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 0 | 46 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 260 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 68722 | 137 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5 |  |  | 246 | 85 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 498724 | 15093994 | 241 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 87105 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26 |  |  | 0 | 64 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 98995 | 72 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24 |  |  | 20 | 70 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 23011 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1 |  |  | 118 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 0 | 0 | 262 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 31684 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 222198 | 136 | 0 | 51 | 147417 | 0 | 0 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25 |  |  | 33 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66 |  |  | 0 | 68 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 141871 | 76 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36 |  |  | 4 | 52 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 297 | 210235 | 157 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86 |  |  | 1 | 84 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 3547 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 134358 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32 |  |  | 30 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 2250 | 122609 | 65 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 0 | 6930 | 77 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | -1518 | 106590 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | -144790 | 1946522 | 57 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36 |  |  | 0 | 27 | 0 | 0 | -118750 | 0 |  | DO
04DO | 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | -6049 | 459484 | 135 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 0 | 469019 | 175 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | -5116 | 11303 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 21772 | 38 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48288286 | 2318006 | 2811186 | 343 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5 |  |  | 0 | 216 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | -826558 | 767164 | 32 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 20000 | 119 | 0 | 0 | 34331 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36784 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | -490 | 148206 | 43 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | -33657 | 423497 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 16623 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | -58186 | 46835 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 49558 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 0 | 25 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | -472 | 1774 | 46 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 0 | 34060 | 38 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | -45651 | 207492 | 59 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 0 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 748 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | -4843 | 71676 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | -102 | 704 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | -7887 | 83991 | 29 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | -460650 | 46466 | 10 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | -65908 | 0 |  | CO
06CO | 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | -2973 | 14943 | 59 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | -173492 | 1702108 | 104 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | -94401 | 0 |  | DO
06DO | 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 2218662 | 9203668 | 61 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 77 | 0 | 0 | -1334779 | 0 |  | CO
07CO | 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | -54392 | 30299 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 20743 | 111 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 0 | 95 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-08 | QTR4 | 24/25 | 799 | 611133 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 126352 | 45 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT | 27 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 0 | 124000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 0 | 2196 | 17 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 0 | 85185 | 50 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 | 2025-07-14 | QTR1 | 25/26 | 799 | 516283 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 1620860 | 8138472 | 120 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 64 | 0 | 0 | -117901 | 0 |  | DO
07DO | 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | -4137 | 12250 | 46 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | -46667 | 1006123 | 45 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | -5101 | 36197 | 122 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59 |  |  | 30 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 24353 | 27 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 0 | 13 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 60198 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 0 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0