## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 98566448 | 97771080 | 99591857 | 99867063 | -92500 | 99945726 | 2.224% | 100% | 1097248 | 1.122% | 1025409 | 1.04% | 3250 | 838 | 25.78% | 328 | 10.09% | 29 | 0.8923% | 210 | 6.462% | 3489 | 7.354% | 4655 | 4473 | 3307 | 1.754% | 81.82%
| District Let | 149136125 | 148157748 | 151082902 | 152007145 | 0 | 154306807 | 4.15% | 100% | 2186119 | 1.476% | 1946775 | 1.305% | 4270 | 785 | 18.38% | 373 | 8.735% | 67 | 1.569% | 125 | 2.927% | 4462 | 4.496% | 5571 | 5446 | 4288 | 0.4215% | 92.86%
| All Contracts | 247702573 | 245928828 | 250674759 | 251874208 | -92500 | 254252533 | 3.385% | 100% | 3283367 | 1.335% | 2972184 | 1.2% | 7520 | 1623 | 21.58% | 701 | 9.322% | 96 | 1.277% | 335 | 4.455% | 7951 | 5.731% | 10226 | 9919 | 7595 | 0.9973% | 88%
2 | Central Let | 305299363 | 302726046 | 314089852 | 323267702 | 0 | 323773866 | 6.953% | 81.82% | 9320908 | 3.079% | 8790488 | 2.879% | 9954 | 3275 | 32.9% | 1560 | 15.67% | 1077 | 10.82% | 1919 | 19.28% | 12950 | 30.1% | 16815 | 16241 | 11406 | 14.59% | 63.64%
| District Let | 51508550 | 50988315 | 66671266 | 67764611 | 0 | 67752714 | 32.88% | 66.67% | 15361906 | 30.13% | 15162716 | 29.44% | 2939 | 777 | 26.44% | 407 | 13.85% | 503 | 17.11% | 711 | 24.19% | 4153 | 41.31% | 4964 | 4952 | 3768 | 28.21% | 50%
| All Contracts | 356807913 | 353714361 | 380761118 | 391032313 | 0 | 391526580 | 10.69% | 79.49% | 24682814 | 6.978% | 23953204 | 6.713% | 12893 | 4052 | 31.43% | 1967 | 15.26% | 1580 | 12.25% | 2630 | 20.4% | 17103 | 32.65% | 21779 | 21193 | 15174 | 17.69% | 61.54%
3 | Central Let | 49505616 | 48913150 | 52200754 | 52080270 | 0 | 52071379 | 6.457% | 90% | 2887469 | 5.903% | 2695137 | 5.444% | 2794 | 853 | 30.53% | 404 | 14.46% | 594 | 21.26% | 157 | 5.619% | 3545 | 26.88% | 4563 | 4482 | 3225 | 15.43% | 70%
| District Let | 44922376 | 44166086 | 45178431 | 45238887 | 0 | 44935533 | 1.742% | 100% | 287914 | 0.6519% | 256056 | 0.57% | 3033 | 731 | 24.1% | 506 | 16.68% | 550 | 18.13% | 295 | 9.726% | 3878 | 27.86% | 4931 | 4787 | 3550 | 17.05% | 70.59%
| All Contracts | 94427992 | 93079236 | 97379185 | 97319157 | 0 | 97006912 | 4.22% | 96.3% | 3175383 | 3.411% | 2951193 | 3.125% | 5827 | 1584 | 27.18% | 910 | 15.62% | 1144 | 19.63% | 452 | 7.757% | 7423 | 27.39% | 9494 | 9269 | 6775 | 16.27% | 70.37%
4 | Central Let | 37613460 | 37040378 | 37988658 | 36763240 | 0 | 36740428 | -0.8098% | 100% | 460726 | 1.244% | 375198 | 0.9975% | 2613 | 683 | 26.14% | 251 | 9.606% | 146 | 5.587% | 60 | 2.296% | 2819 | 7.884% | 3680 | 3647 | 2713 | 3.827% | 100%
| District Let | 92304136 | 91424822 | 96213775 | 95250242 | 0 | 94998644 | 3.909% | 92.86% | 3788267 | 4.144% | 3867509 | 4.19% | 4189 | 924 | 22.06% | 340 | 8.116% | 103 | 2.459% | 67 | 1.599% | 4359 | 4.058% | 5587 | 5321 | 4057 | -3.151% | 100%
| All Contracts | 129917596 | 128465200 | 134202433 | 132013482 | 0 | 131739072 | 2.548% | 95.65% | 4248993 | 3.308% | 4242707 | 3.266% | 6802 | 1607 | 23.63% | 591 | 8.689% | 249 | 3.661% | 127 | 1.867% | 7178 | 5.528% | 9267 | 8968 | 6770 | -0.4704% | 100%
5 | Central Let | 197098462 | 195368268 | 205814148 | 208589889 | 0 | 207065779 | 5.987% | 95% | 7551041 | 3.865% | 8715685 | 4.422% | 7070 | 1818 | 25.71% | 1549 | 21.91% | 22 | 0.3112% | 328 | 4.639% | 7420 | 4.95% | 11028 | 10859 | 7492 | 5.969% | 85%
| District Let | 311603166 | 310732314 | 326759822 | 327333572 | 25000 | 327945506 | 5.54% | 100% | 14879076 | 4.788% | 15156655 | 4.864% | 4527 | 949 | 20.96% | 1655 | 36.56% | 0 | 0% | 374 | 8.262% | 4901 | 8.262% | 7523 | 7486 | 4882 | 7.842% | 92.31%
| All Contracts | 508701628 | 506100582 | 532573970 | 535923461 | 25000 | 535011285 | 5.712% | 96.97% | 22430117 | 4.432% | 23872340 | 4.693% | 11597 | 2767 | 23.86% | 3204 | 27.63% | 22 | 0.1897% | 702 | 6.053% | 12321 | 6.243% | 18551 | 18345 | 12374 | 6.7% | 87.88%
6 | Central Let | 47729946 | 47209557 | 48153197 | 47218633 | 1060000 | 47112248 | -0.2061% | 100% | 410022 | 0.8685% | 423251 | 0.8868% | 2300 | 318 | 13.83% | 162 | 7.043% | 22 | 0.9565% | 13 | 0.5652% | 2335 | 1.522% | 2815 | 2589 | 2109 | -8.304% | 100%
| District Let | 52788679 | 52486691 | 54523106 | 54551229 | 2100000 | 46060442 | -12.24% | 100% | 1735150 | 3.306% | 1734426 | 3.286% | 2328 | 277 | 11.9% | 229 | 9.837% | 0 | 0% | 233 | 10.01% | 2561 | 10.01% | 3207 | 3082 | 2576 | 10.65% | 75%
| All Contracts | 100518625 | 99696248 | 102676303 | 101769862 | 3160000 | 93172690 | -6.543% | 100% | 2145172 | 2.152% | 2157677 | 2.147% | 4628 | 595 | 12.86% | 391 | 8.449% | 22 | 0.4754% | 246 | 5.315% | 4896 | 5.791% | 6022 | 5671 | 4685 | 1.232% | 90.91%
7 | Central Let | 183015447 | 181866285 | 193411517 | 194272998 | 875160 | 193442708 | 6.365% | 92.31% | 9419577 | 5.179% | 10396068 | 5.68% | 4318 | 872 | 20.19% | 356 | 8.245% | 105 | 2.432% | 139 | 3.219% | 4562 | 5.651% | 5670 | 5446 | 4218 | -2.316% | 100%
| District Let | 215001574 | 214095924 | 230511627 | 229783397 | 1450000 | 230097421 | 7.474% | 91.67% | 12172470 | 5.686% | 15510054 | 7.214% | 4494 | 943 | 20.98% | 419 | 9.324% | 204 | 4.539% | 568 | 12.64% | 5266 | 17.18% | 6368 | 5974 | 4612 | 2.626% | 100%
| All Contracts | 398017021 | 395962209 | 423923144 | 424056395 | 2325160 | 423540129 | 6.965% | 92% | 21592047 | 5.453% | 25906122 | 6.509% | 8812 | 1815 | 20.6% | 775 | 8.795% | 309 | 3.507% | 707 | 8.023% | 9828 | 11.53% | 12038 | 11420 | 8830 | 0.2043% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 96116791 | 95162449 | 110922526 | 109349313 | 37398 | 109108767 | 14.66% | 90.91% | 15144193 | 15.91% | 14805734 | 15.4% | 3809 | 729 | 19.14% | 489 | 12.84% | 137 | 3.597% | 220 | 5.776% | 4166 | 9.373% | 5280 | 4822 | 3604 | -5.382% | #VALUE!
| All Contracts | 96116791 | 95162449 | 110922526 | 109349313 | 37398 | 109108767 | 14.66% | 90.91% | 15144193 | 15.91% | 14805734 | 15.4% | 3809 | 729 | 19.14% | 489 | 12.84% | 137 | 3.597% | 220 | 5.776% | 4166 | 9.373% | 5280 | 4822 | 3604 | -5.382% | 100%
Totals This Qtr | Central Let | 918828742 | 910894764 | 951249983 | 962059795 | 1842660 | 960152134 | 5.408% | 91.26% | 31146991 | 3.419% | 32421236 | 3.529% | 32299 | 8657 | 26.8% | 4610 | 14.27% | 1995 | 6.177% | 2826 | 8.749% | 37120 | 14.93% | 49226 | 47737 | 34470 | 6.722% | 80.58%
| District Let | 1013381397 | 1007214349 | 1081863455 | 1081278396 | 3612398 | 1075205834 | 6.75% | 94.51% | 65555095 | 6.509% | 68439925 | 6.754% | 29589 | 6115 | 20.67% | 4418 | 14.93% | 1564 | 5.286% | 2593 | 8.763% | 33746 | 14.05% | 43431 | 41870 | 31337 | 5.908% | 87.91%
| All Contracts | 1932210139 | 1918109113 | 2033113438 | 2043338191 | 5455058 | 2035357968 | 6.113% | 92.78% | 96702086 | 5.042% | 100861161 | 5.22% | 61888 | 14772 | 23.87% | 9028 | 14.59% | 3559 | 5.751% | 5419 | 8.756% | 70866 | 14.51% | 92657 | 89607 | 65807 | 6.332% | 84.02%
Totals Previous Quarter | Central Let | 541749784 | 537554611 | 561203804 | 566755130 | 689500 | 565721589 | 5.24% | 90.91% | 18707417 | 3.48% | 19454019 | 3.591% | 18296 | 4833 | 26.42% | 2359 | 12.89% | 1182 | 6.46% | 2051 | 11.21% | 21529 | 17.67% | 27983 | 27145 | 19953 | 9.057% | 76.36%
| District Let | 394649687 | 391211638 | 425686775 | 424393914 | 2437398 | 422816319 | 8.079% | 92.31% | 28196993 | 7.208% | 30890461 | 7.827% | 15704 | 3286 | 20.92% | 2551 | 16.24% | 702 | 4.47% | 1374 | 8.749% | 17780 | 13.22% | 23420 | 22215 | 16378 | 4.292% | 88.46%
| All Contracts | 936399471 | 928766249 | 986890579 | 991149044 | 3126898 | 988537908 | 6.436% | 91.59% | 46904410 | 5.05% | 50344480 | 5.376% | 34000 | 8119 | 23.88% | 4910 | 14.44% | 1884 | 5.541% | 3425 | 10.07% | 39309 | 15.61% | 51403 | 49360 | 36331 | 6.856% | 82.24%
Totals Fiscal Year 2024/2025 | Central Let | 1279648903 | 1266221414 | 1312978963 | 1321473742 | 2536230 | 1326167192 | 4.734% | 90.72% | 35949687 | 2.839% | 33549474 | 2.622% | 54906 | 16687 | 30.39% | 7064 | 12.87% | 4509 | 8.212% | 6770 | 12.33% | 66185 | 20.54% | 86228 | 84771 | 61020 | 11.14% | 80.93%
| District Let | 1318833837 | 1310154031 | 1361025980 | 1368896349 | 5751239 | 1365653292 | 4.236% | 92.91% | 42375966 | 3.234% | 42720355 | 3.239% | 43619 | 9909 | 22.72% | 5114 | 11.72% | 2675 | 6.133% | 2106 | 4.828% | 48400 | 10.96% | 62882 | 61439 | 46416 | 6.412% | 89.76%
| All Contracts | 2598482740 | 2576375445 | 2674004943 | 2690370091 | 8287469 | 2691820484 | 4.481% | 91.59% | 78325653 | 3.04% | 76269829 | 2.935% | 98525 | 26596 | 26.99% | 12178 | 12.36% | 7184 | 7.292% | 8876 | 9.009% | 114585 | 16.3% | 149110 | 146210 | 107436 | 9.044% | 84.42%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 82.62% | 1 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 102.1% | 1 | 2409623 | 620443 | 176 | 66 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98
| 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 99.67% | 1 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | 100.9% | 1 | -99694 | 0 | 136 | 36 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58
| 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 107.6% | 1 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | 103.4% | 1 | -56953 | 31648 | 155 | 46 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 |  | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72
| 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 98.29% | 1 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | 101.3% | 1 | -795 | 0 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94
| 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 108% | 1 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | 98.61% | 1 | -642 | 26799 | 27 | 20 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92
| 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | 143.7% | 0 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11519677 | 103.6% | 1 | 104968 | 84591 | 129 | 47 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29
| 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | 117.8% | 1 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | 98.84% | 1 | -14467 | 132711 | 40 | 25 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39
| 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 128% | 0 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 104.6% | 1 | 0 | 38502 | 57 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56
| 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 108% | 1 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | 106.5% | 1 | -31093 | 10701 | 70 | 24 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71
| 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 112% | 1 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | 101.8% | 1 | -2822 | 44403 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8
| 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 119.2% | 1 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | 103.2% | 1 | -61 | 35611 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 11 | 16 | 32 | 3250 | 4655 | 4473 | 81.82% | 9 | 182 | 59 | 0 | 1195 | 210 | 98566448 | 795368 | 97771080 | 99591857 | 99867063 | -219920 | -92500 | -312420 | 99554643 | 99945726 | 100% | 11 | 2308064 | 1025409 | 838 | 328 | 0 | 62 | 311911 | 0 | 0 | 148 | 481741 | 106538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 65136 | 0 | 0 | 0 | 94281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 210 | 1097248 | 106538
| 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 107% | 1 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 106.3% | 1 | 5571562 | 1174716 | 264 | 101 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 |  | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT
| 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 86% | 1 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | 100.8% | 1 | -10506 | 70548 | 51 | 23 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78
| 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | 110.3% | 1 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | 96.34% | 1 | -126080 | -565229 | 188 | 42 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94
| 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 111.3% | 1 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 106.2% | 1 | 143 | 103763 | 8 | 19 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 |  | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93
| 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 96.11% | 1 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | 100.1% | 1 | -1029 | -94765 | 25 | 22 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22
| 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 104% | 1 | 199 | -6676 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 |  | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01
| 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | 104.6% | 1 | -480611 | 790067 | 61 | 52 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 |  | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | 125.5% | 0 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | 108.1% | 1 | -22 | 198130 | 44 | 22 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02
| 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 85.88% | 1 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | 103.6% | 1 | -4233 | 23853 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68
| 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 97.33% | 1 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | 100.9% | 1 | -264 | 0 | 24 | 33 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT
| 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 103.1% | 1 | 0 | 0 | 32 | 3 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24
| 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 88.57% | 1 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | 102.3% | 1 | -757 | 0 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2
| 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 81.43% | 1 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | 79.21% | 1 | -1 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32
| 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 86.67% | 1 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | 107.2% | 1 | -879 | 252368 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 14 | 18 | 37 | 4270 | 5571 | 5446 | 92.86% | 13 | 125 | 35 | 0 | 1151 | 150 | 149136125 | 978377 | 148157748 | 151082902 | 152007145 | -169495 | 0 | -169495 | 151837649 | 154306807 | 100% | 14 | 4947522 | 1946775 | 785 | 373 | 0 | 30 | -149242 | 0 | 3 | 95 | 2117349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 15 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 67 | 125 | 2186119 | 23853
| District 01 Totals |  |  |  |  | 25 | 34 | 69 | 7520 | 10226 | 9919 | 88% | 22 | 307 | 94 | 0 | 2346 | 360 | 247702573 | 1773745 | 245928828 | 250674759 | 251874208 | -389415 | -92500 | -481915 | 251392292 | 254252533 | 100% | 25 | 7255586 | 2972184 | 1623 | 701 | 0 | 92 | 162669 | 0 | 3 | 243 | 2599090 | 106538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 75433 | 0 | 15 | 0 | 96084 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 458940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 96 | 335 | 3283367 | 130391
| 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 127.2% | 0 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 109.4% | 1 | 329791 | 87098 | 104 | 52 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6
| 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 117.3% | 1 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 120.7% | 0 | 251365 | 3045943 | 306 | 279 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 |  | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57
| 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 100% | 1 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 106.8% | 1 | 1493028 | 0 | 244 | 59 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 |  | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12
| 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 136.1% | 0 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | 103.2% | 1 | -345380 | 417407 | 191 | 70 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23
| 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 177.1% | 0 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | 101.9% | 1 | -330946 | 172500 | 390 | 55 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17
| 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 175.3% | 0 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 117.4% | 0 | 24575 | 1868912 | 57 | 104 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86
| 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 141% | 0 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | 120.5% | 0 | -14114 | 807199 | 68 | 49 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18
| 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 156.8% | 0 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 115.9% | 0 | 0 | 482619 | 107 | 92 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25
| 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 106.7% | 1 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | 108.1% | 1 | -190784 | 275992 | 290 | 29 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41
| 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 118.2% | 1 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | 103.9% | 1 | -3283 | 86004 | 101 | 52 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38
| 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 104.3% | 1 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | 106.5% | 1 | -17213 | 38788 | 301 | 45 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 |  | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13
| 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 98.82% | 1 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | 98.71% | 1 | -3560 | 0 | 137 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85
| 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 130.3% | 0 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | 105.2% | 1 | -5609 | 107690 | 101 | 73 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67
| 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 123.1% | 0 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | 107.6% | 1 | -105664 | 385943 | 91 | 66 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99
| 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 129.3% | 0 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | 103% | 1 | -7392 | 0 | 72 | 41 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02
| 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 94.33% | 1 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | 103.7% | 1 | -21404 | 0 | 93 | 38 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 |  | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61
| 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 92.59% | 1 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | 108% | 1 | -1110 | 73235 | 44 | 29 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64
| 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 99.63% | 1 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | 99.05% | 1 | -1654 | 0 | 67 | 36 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6
| 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 87.5% | 1 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | 100.9% | 1 | -957 | 37326 | 19 | 24 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75
| 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 130.6% | 0 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | 100.1% | 1 | -4770 | 0 | 79 | 56 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66
| 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 146.7% | 0 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 102.3% | 1 | 0 | 0 | 34 | 22 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25
| 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 118.7% | 1 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | 105.2% | 1 | -45883 | -30738 | 23 | 27 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | -30738 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04
| 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 140% | 0 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | 113.1% | 0 | -20654 | 208197 | 91 | 49 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88
| 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 63.89% | 1 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | 108.3% | 1 | -44146 | 397198 | 39 | 27 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 |  | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14
| 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 78.55% | 1 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 101.8% | 1 | 0 | 0 | 34 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9
| 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 116.7% | 1 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | 100.6% | 1 | -19104 | 0 | 59 | 31 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02
| 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 27.78% | 1 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | 113.1% | 0 | -227 | 175589 | 41 | 4 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91
| 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | 99.47% | 1 | -1071 | 74430 | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67
| 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 90.56% | 1 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | 99.32% | 1 | -3091 | 0 | 4 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25
| 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 105.8% | 1 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 100.5% | 1 | 0 | 34986 | 61 | 24 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35
| 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 79% | 1 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | 103.5% | 1 | -13 | 44170 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99
| 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 97.78% | 1 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 99.05% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76
| 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 71.67% | 1 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 99.97% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 208 | 505500
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 33 | 50 | 61 | 9954 | 16815 | 16241 | 63.64% | 21 | 574 | 0 | 0 | 4942 | 1919 | 305299363 | 2573313 | 302726046 | 314089852 | 323267702 | 0 | 0 | 0 | 323267702 | 323773866 | 81.82% | 27 | 910730 | 8790488 | 3275 | 1560 | 208 | 1042 | 5120651 | 111708 | 21 | 329 | 1730303 | 184330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 2054868 | 14607 | 155 | 150 | 249892 | 67137 | 0 | 0 | 0 | 0 | 579 | 250 | 195931 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 148 | 0 | 0 | 0 | 0 | -30738 | 0 | 1077 | 1919 | 9320908 | 378653
| 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 113.9% | 1 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | 103.1% | 1 | -2313 | 0 | 28 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4
| 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 127.9% | 0 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | 99.22% | 1 | -280479 | 0 | 136 | 77 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 151.1% | 0 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 111.6% | 0 | 0 | 68722 | 137 | 85 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5
| 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 116.4% | 1 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | 103.7% | 1 | -38817 | 0 | 27 | 50 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 103.3% | 1 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | 101.4% | 1 | -64205 | 0 | 208 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 146.4% | 0 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 191.5% | 0 | 498724 | 15093994 | 241 | 106 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 6 | 7 | 17 | 2939 | 4964 | 4952 | 50% | 3 | 12 | 0 | 0 | 1404 | 621 | 51508550 | 520236 | 50988315 | 66671266 | 67764611 | 0 | 0 | 0 | 67764611 | 67752714 | 66.67% | 4 | 112910 | 15162716 | 777 | 407 | 29 | 92 | 264018 | 0 | 146 | 221 | 434918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 14608377 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 711 | 15361906 | 0
| District 02 Totals |  |  |  |  | 39 | 57 | 78 | 12893 | 21779 | 21193 | 61.54% | 24 | 586 | 0 | 0 | 6346 | 2540 | 356807913 | 3093549 | 353714361 | 380761118 | 391032313 | 0 | 0 | 0 | 391032313 | 391526580 | 79.49% | 31 | 1023640 | 23953204 | 4052 | 1967 | 237 | 1134 | 5384669 | 111708 | 167 | 550 | 2165221 | 184330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 16663245 | 14607 | 155 | 150 | 267846 | 67137 | 0 | 0 | 0 | 0 | 579 | 648 | 232570 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 148 | 0 | 0 | 0 | 0 | -30738 | 0 | 1580 | 2630 | 24682814 | 378653
| 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 96.35% | 1 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 113% | 0 | 417101 | 2501033 | 111 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02
| 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 98.43% | 1 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | 101.1% | 1 | -1225 | 0 | 66 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95
| 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 109.6% | 1 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | 101.6% | 1 | -13342 | 98995 | 72 | 70 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24
| 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 194.3% | 0 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | 97.4% | 1 | -1 | 0 | 159 | 51 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2
| 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 396.7% | 0 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 98.85% | 1 | 0 | 23011 | 20 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1
| 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 181.1% | 0 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 99.59% | 1 | 0 | 0 | 262 | 51 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67
| 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | 100.2% | 1 | -668 | 31684 | 50 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9
| 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 97.56% | 1 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | 101.6% | 1 | -3611 | 1650 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04
| 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 83.64% | 1 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | 103.7% | 1 | -1439 | 38764 | 59 | 24 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8
| 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 110% | 1 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 98.53% | 1 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 10 | 15 | 15 | 2794 | 4563 | 4482 | 70% | 7 | 81 | 0 | 0 | 1612 | 157 | 49505616 | 592466 | 48913150 | 52200754 | 52080270 | 0 | 0 | 0 | 52080270 | 52071379 | 90% | 9 | 396815 | 2695137 | 853 | 404 | 120 | 3 | 63549 | 16559 | 126 | 14 | 1922447 | 1819753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 140 | 901473 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 157 | 2887469 | 1836891
| 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 177.7% | 0 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | 107.6% | 1 | -38559 | 222198 | 136 | 62 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25
| 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 106.9% | 1 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 96.1% | 1 | 0 | 0 | 87 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66
| 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 120% | 1 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 89.83% | 1 | 0 | -323937 | 5 | 11 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038
| 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 154.8% | 0 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 94.89% | 1 | 0 | 96146 | 18 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55
| 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | 127.5% | 0 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 105.1% | 1 | 297 | 210235 | 157 | 84 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86
| 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | 126.7% | 0 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 102.6% | 1 | 435 | 0 | 104 | 43 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9
| 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 78.33% | 1 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22
| 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 98.89% | 1 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 107.3% | 1 | 0 | 0 | 34 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46
| 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 120% | 1 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 93.69% | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17
| 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 71.11% | 1 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 97.73% | 1 | 0 | 0 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12
| 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 64.44% | 1 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 101.5% | 1 | 0 | 0 | 44 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15
| 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 102.3% | 1 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | 102.1% | 1 | -64 | 26925 | 78 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37
| 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | 103.3% | 1 | -11799 | 0 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2
| 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 90% | 1 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 88.67% | 1 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57
| 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 132.5% | 0 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 100.1% | 1 | 0 | 24489 | 12 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110
| 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 89.17% | 1 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 100.5% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49
| 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 85% | 1 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 99.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 17 | 22 | 10 | 3033 | 4931 | 4787 | 70.59% | 12 | 144 | 67 | 0 | 1606 | 325 | 44922376 | 756289 | 44166086 | 45178431 | 45238887 | -253662 | 0 | -253662 | 44985225 | 44935533 | 100% | 17 | -49690 | 256056 | 731 | 506 | 0 | 72 | 154502 | 0 | 122 | 10 | 265629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 213 | -132217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 295 | 287914 | 0
| District 03 Totals |  |  |  |  | 27 | 37 | 25 | 5827 | 9494 | 9269 | 70.37% | 19 | 225 | 67 | 0 | 3218 | 482 | 94427992 | 1348755 | 93079236 | 97379185 | 97319157 | -253662 | 0 | -253662 | 97065495 | 97006912 | 96.3% | 26 | 347125 | 2951193 | 1584 | 910 | 120 | 75 | 218051 | 16559 | 248 | 24 | 2188076 | 1819753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 353 | 769256 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144 | 452 | 3175383 | 1836891
| 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 99.79% | 1 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 101.6% | 1 | 134358 | 0 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 |  | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88
| 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 108.5% | 1 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 101.1% | 1 | 0 | 0 | 84 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32
| 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 108.7% | 1 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | 101.2% | 1 | -3998 | 262898 | 110 | 27 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 |  | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22
| 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 104.4% | 1 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 96.71% | 1 | 2250 | 122609 | 65 | 44 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26
| 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 111.5% | 1 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | 96.5% | 1 | -16 | -10309 | 123 | 25 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5
| 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 99.52% | 1 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | 98.1% | 1 | -1000 | 0 | 157 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58
| 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 99.59% | 1 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | 102.4% | 1 | -2195 | 0 | 70 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66
| 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 117.4% | 1 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 97.26% | 1 | 0 | 0 | 22 | 19 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17
| 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 87% | 1 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 99.5% | 1 | 0 | 0 | 22 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 9 | 17 | 11 | 2613 | 3680 | 3647 | 100% | 9 | 33 | 0 | 0 | 1007 | 60 | 37613460 | 573083 | 37040378 | 37988658 | 36763240 | 0 | 0 | 0 | 36763240 | 36740428 | 100% | 9 | 129399 | 375198 | 683 | 251 | 0 | 0 | 35958 | 0 | 73 | 60 | 423553 | 159010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 60 | 460726 | 159010
| 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 110.7% | 1 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 72.58% | 1 | 0 | 6930 | 77 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6
| 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 80.76% | 1 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | 105% | 1 | -1518 | 106590 | 57 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81
| 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 90.84% | 1 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | 105.3% | 1 | -144790 | 1946522 | 57 | 27 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36
| 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 114.5% | 1 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | 112.3% | 0 | -6049 | 459484 | 135 | 44 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25
| 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 100% | 1 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 106% | 1 | 0 | 469019 | 175 | 50 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2
| 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 109.8% | 1 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | 104.7% | 1 | -5352 | 104495 | 64 | 29 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06
| 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 108.8% | 1 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | 103.9% | 1 | -9192 | 144713 | 79 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08
| 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 109.1% | 1 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | 98.27% | 1 | -5116 | 11303 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1
| 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 79.4% | 1 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | 103.5% | 1 | -5542 | 169350 | 38 | 17 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9
| 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 98.89% | 1 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | 100.9% | 1 | -5716 | 19752 | 60 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35
| 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 95.14% | 1 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | 96.73% | 1 | -952 | 0 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705
| 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 98.29% | 1 | 0 | 21772 | 38 | 4 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24
| 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 108.4% | 1 | 0 | 199108 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11
| 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 94.27% | 1 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | 108.6% | 1 | -22 | 208471 | 38 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 14 | 23 | 46 | 4189 | 5587 | 5321 | 100% | 14 | 266 | 0 | 0 | 1348 | 50 | 92304136 | 879313 | 91424822 | 96213775 | 95250242 | 0 | 0 | 0 | 95250242 | 94998644 | 92.86% | 13 | -184249 | 3867509 | 924 | 340 | 58 | 0 | 277512 | 1305237 | 0 | 48 | 2638167 | 34121 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423792 | 3335 | 0 | 0 | 179301 | 22700 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 323579 | 0 | 0 | 19 | 55844 | 55844 | 26 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 103 | 67 | 3788267 | 1421236
| District 04 Totals |  |  |  |  | 23 | 40 | 57 | 6802 | 9267 | 8968 | 100% | 23 | 299 | 0 | 0 | 2355 | 110 | 129917596 | 1452396 | 128465200 | 134202433 | 132013482 | 0 | 0 | 0 | 132013482 | 131739072 | 95.65% | 22 | -54850 | 4242707 | 1607 | 591 | 58 | 0 | 313470 | 1305237 | 73 | 108 | 3061720 | 193131 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423792 | 3335 | 0 | 0 | 180516 | 22700 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 323579 | 0 | 0 | 19 | 55844 | 55844 | 26 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 249 | 127 | 4248993 | 1580246
| 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 109.3% | 1 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48288286 | 107.9% | 1 | 2318006 | 2811186 | 343 | 216 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5
| 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 96.52% | 1 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 120.9% | 0 | 155455 | 1728309 | 360 | 314 | 0 | 18 | 529414 | 11401 | 0 | 0 | 879425 | 0 | 0 | 0 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1869865 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79
| 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 147.1% | 0 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 105.6% | 1 | 0 | 445755 | 106 | 50 | 0 | 4 | 102719 | 0 | 0 | 3 | 36135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 152629 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26
| 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 92.94% | 1 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | 103.1% | 1 | -1378 | 125188 | 128 | 302 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57
| 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 108.1% | 1 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | 104.4% | 1 | -1051 | 71079 | 39 | 130 | 0 | 0 | 58672 | 0 | 0 | 0 | 4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62692 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19
| 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 81.23% | 1 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | 100.8% | 1 | -826558 | 767164 | 32 | 51 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT
| 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 99.6% | 1 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | 93.43% | 1 | -632 | 20000 | 119 | 27 | 0 | 0 | 34331 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36784 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6
| 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 100% | 1 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | 101.5% | 1 | -4358 | 25139 | 80 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13
| 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 104.2% | 1 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 104.3% | 1 | 855 | 352308 | 69 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96820 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72
| 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 113.4% | 1 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | 106.1% | 1 | -490 | 148206 | 43 | 49 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1
| 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 104.2% | 1 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | 107.1% | 1 | -33657 | 423497 | 66 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25
| 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | 173% | 0 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | 104.8% | 1 | -69 | 172092 | 61 | 32 | 0 | 4 | 19175 | 31865 | 0 | 9 | 74668 | 34516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 104988 | 66380 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96
| 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 99.29% | 1 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | 100.1% | 1 | -20420 | 16623 | 41 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87
| 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 98.67% | 1 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | 105.9% | 1 | -58186 | 46835 | 73 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850
| 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 91.43% | 1 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | 105.7% | 1 | -74410 | 397272 | 63 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27
| 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 149.6% | 0 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | 109.5% | 1 | -118108 | 1119406 | 124 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43781 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1047592 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21
| 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 97.63% | 1 | 0 | 0 | 8 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14
| 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 102.7% | 1 | 944 | 0 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25
| 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 25% | 1 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 93.85% | 1 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52
| 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 107.8% | 1 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 101.2% | 1 | 0 | 49558 | 26 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 20 | 67 | 85 | 7070 | 11028 | 10859 | 85% | 17 | 169 | 82 | 0 | 3432 | 526 | 197098462 | 1730194 | 195368268 | 205814148 | 208589889 | 0 | 0 | 0 | 208589889 | 207065779 | 95% | 19 | 1335943 | 8715685 | 1818 | 1549 | 0 | 85 | 2391079 | 43266 | 0 | 114 | 3335416 | 190398 | 0 | 0 | 50192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 507494 | 201655 | 0 | 4 | 90635 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 439964 | 0 | 0 | 0 | 355913 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 328 | 7551041 | 1078912
| 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 101.6% | 1 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | 100.1% | 1 | -6 | 0 | 25 | 18 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5
| 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 110.7% | 1 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | 99.36% | 1 | -472 | 1774 | 46 | 26 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07
| 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 108% | 1 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | 106% | 1 | -14889 | 162189 | 89 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 14866 | 12674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14866 | 12674 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48
| 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 95.38% | 1 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 98.21% | 1 | 0 | 34060 | 38 | 34 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65
| 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 102.9% | 1 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 104% | 1 | 3084 | 117838 | 75 | 18 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39
| 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 111.9% | 1 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 101.4% | 1 | 0 | 0 | 12 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75
| 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | 101.3% | 1 | -45651 | 207492 | 59 | 37 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59
| 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 131.7% | 0 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 108.9% | 1 | 0 | 1485 | 141 | 64 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08
| 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 98.81% | 1 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | 105% | 1 | -9 | 181208 | 61 | 52 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 |  | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02
| 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 101.2% | 1 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | 104.5% | 1 | -2602 | 194854 | 81 | 47 | 0 | 0 | 39880 | 0 | 0 | 10 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS
| 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 100% | 1 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 100% | 1 | 0 | 0 | 141 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | 99.77% | 1 | -4843 | 71676 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49
| 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 117.8% | 1 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 106% | 1 | 8560014 | 14184079 | 138 | 461 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497575 | 0 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 13908035 | 7394536 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 13 | 29 | 46 | 4527 | 7523 | 7486 | 92.31% | 12 | 37 | 0 | 0 | 2604 | 392 | 311603166 | 870852 | 310732314 | 326759822 | 327333572 | 0 | 25000 | 25000 | 327358572 | 327945506 | 100% | 13 | 8494626 | 15156655 | 949 | 1655 | 0 | 29 | 3065957 | 0 | 0 | 40 | 2934348 | 108892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 524151 | 0 | 0 | 20 | 105293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 14879076 | 7408892
| District 05 Totals |  |  |  |  | 33 | 96 | 131 | 11597 | 18551 | 18345 | 87.88% | 29 | 206 | 82 | 0 | 6036 | 918 | 508701628 | 2601046 | 506100582 | 532573970 | 535923461 | 0 | 25000 | 25000 | 535948461 | 535011285 | 96.97% | 32 | 9830569 | 23872340 | 2767 | 3204 | 0 | 114 | 5457036 | 43266 | 0 | 154 | 6269764 | 299290 | 0 | 0 | 50192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15 | 1031645 | 201655 | 0 | 24 | 195928 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1389293 | 0 | 0 | 249 | 7655913 | 7300000 | 0 | 136 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 702 | 22430117 | 8487804
| 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 96.88% | 1 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | 96.37% | 1 | -102 | 704 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75
| 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 96.5% | 1 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | 99.74% | 1 | -7887 | 83991 | 29 | 47 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 97.94% | 1 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | 103.4% | 1 | -200821 | 227147 | 146 | 34 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 86.6% | 1 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | 96.97% | 1 | -460650 | 46466 | 10 | 16 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 82.25% | 1 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | 100.8% | 1 | -342511 | 0 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 |  | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 83.67% | 1 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | 102% | 1 | -106988 | 50000 | 23 | 10 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 |  | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 111% | 1 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | 99.89% | 1 | -2973 | 14943 | 59 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 7 | 27 | 19 | 2300 | 2815 | 2589 | 100% | 7 | 226 | 0 | 0 | 498 | 17 | 47729946 | 520389 | 47209557 | 48153197 | 47218633 | 0 | 1060000 | 1060000 | 48278633 | 47112248 | 100% | 7 | -1121932 | 423251 | 318 | 162 | 0 | 13 | 297602 | 0 | 22 | 0 | 129624 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24744 | 0 | 0 | 0 | 23960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 22 | 13 | 410022 | 21158
| 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 103.3% | 1 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | 105% | 1 | -173492 | 1702108 | 104 | 54 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 83.57% | 1 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | 98.52% | 1 | -140063 | 0 | 8 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 143.9% | 0 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | 0% | 1 | -7237180 | 32318 | 121 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 96% | 1 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | 0% | 1 | -1284180 | 0 | 44 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 4 | 10 | 17 | 2328 | 3207 | 3082 | 75% | 3 | 125 | 0 | 0 | 646 | 233 | 52788679 | 301988 | 52486691 | 54523106 | 54551229 | 0 | 2100000 | 2100000 | 56651229 | 46060442 | 100% | 4 | -8834915 | 1734426 | 277 | 229 | 0 | 0 | 601267 | 0 | 0 | 0 | 406527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 722169 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 233 | 1735150 | 0
| District 06 Totals |  |  |  |  | 11 | 37 | 36 | 4628 | 6022 | 5671 | 90.91% | 10 | 351 | 0 | 0 | 1144 | 250 | 100518625 | 822377 | 99696248 | 102676303 | 101769862 | 0 | 3160000 | 3160000 | 104929862 | 93172690 | 100% | 11 | -9956847 | 2157677 | 595 | 391 | 0 | 13 | 898869 | 0 | 22 | 0 | 536151 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 746913 | 0 | 0 | 0 | 97343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -160309 | 0 | 22 | 246 | 2145172 | 21158
| 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 100% | 1 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | 102.1% | 1 | -113501 | 667762 | 87 | 79 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 90.42% | 1 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 112% | 0 | 2218662 | 9203668 | 61 | 77 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 112.9% | 1 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7161112 | 89.57% | 1 | -778302 | 30299 | 59 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800
| 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 112.9% | 1 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | 108.3% | 1 | -125 | 464384 | 209 | 31 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700
| 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 100% | 1 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | 102.8% | 1 | -1005 | 20743 | 111 | 50 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000
| 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 108.3% | 1 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6699170 | 100.4% | 1 | 1257 | 49529 | 152 | 29 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800
| 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 99.49% | 1 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | 104.9% | 1 | -3017 | 0 | 95 | 25 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840
| 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | 98.51% | 1 | -289 | 0 | 41 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132
| 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 115% | 1 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 99.05% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-08 | QTR4 | 24/25 | 799 | 611133
| 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 93.33% | 1 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | 102.8% | 1 | -14790 | -46492 | 13 | 22 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992
| 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 110.3% | 1 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 97.36% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 826944
| 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67.32% | 1 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | 101.8% | 1 | -393 | 835 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150
| 07 | T7573 | 45096915201 | 2025-03-26 | QTR3 | 24/25 | 1 | 2 | 65 | 88 | 87 | 98.46% | 1 | 1 | 0 | 0 | 23 | 0 | 365071 | 21000 | 344071 | 370411 | 359883 | 0 | 0 | 0 | 359883 | 354442 | 103% | 1 | -5442 | 5340 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-29 | QTR1 | 25/26 | 799 | 528390
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 13 | 18 | 51 | 4318 | 5670 | 5446 | 100% | 13 | 224 | 0 | 0 | 1272 | 80 | 183015447 | 1149162 | 181866285 | 193411517 | 194272998 | 0 | 875160 | 875160 | 195148158 | 193442708 | 92.31% | 12 | 1303055 | 10396068 | 872 | 356 | 0 | 20 | 1676714 | 305314 | 15 | 47 | 2803361 | 539295 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5035530 | 721885 | 10 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 51 | 0 | 269711 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 105 | 139 | 9419577 | 2062741
| 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 118% | 1 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | 101.4% | 1 | -300000 | 126352 | 45 | 25 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | 101.6% | 1 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 84.24% | 1 | 0 | 124000 | 98 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100
| 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 98.59% | 1 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 102.4% | 1 | 0 | 0 | 20 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914
| 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 78.26% | 1 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 86.6% | 1 | 0 | 2196 | 17 | 13 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 |  | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163
| 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 119.3% | 1 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | 101.4% | 1 | -92719 | 135750 | 67 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476
| 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 110% | 1 | 0 | 85185 | 50 | 21 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805
| 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 86.67% | 1 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 99.58% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 799 | 516283
| 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 100% | 1 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | 102% | 1 | -335192 | -69440 | 226 | 48 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69440 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 |  | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
| 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 100.8% | 1 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 110.2% | 0 | 1620860 | 8138472 | 120 | 64 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -117901 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 96.9% | 1 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | 101.7% | 1 | -205 | 115220 | 163 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000
| 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 112.5% | 1 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 108.2% | 1 | 1490307 | 6840069 | 90 | 86 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 94.5% | 1 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | 98.31% | 1 | -4137 | 12250 | 46 | 39 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 12 | 22 | 55 | 4494 | 6368 | 5974 | 100% | 12 | 394 | 2 | 0 | 1362 | 512 | 215001574 | 905651 | 214095924 | 230511627 | 229783397 | -48398 | 1450000 | 1401602 | 231184999 | 230097421 | 91.67% | 11 | 2378914 | 15510054 | 943 | 419 | 0 | 369 | 8053750 | 397935 | 0 | 25 | 3165174 | 471806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208316 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 466466 | 208207 | 0 | 0 | 0 | 0 | 0 | 174 | 457795 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -187341 | 0 | 204 | 568 | 12172470 | 1529102
| District 07 Totals |  |  |  |  | 25 | 40 | 106 | 8812 | 12038 | 11420 | 100% | 25 | 618 | 2 | 0 | 2634 | 592 | 398017021 | 2054813 | 395962209 | 423923144 | 424056395 | -48398 | 2325160 | 2276762 | 426333157 | 423540129 | 92% | 23 | 3681969 | 25906122 | 1815 | 775 | 0 | 389 | 9730464 | 703249 | 15 | 72 | 5968535 | 1011101 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5243846 | 721885 | 10 | 0 | 895125 | 335970 | 0 | 0 | 0 | 0 | 255 | 0 | 736177 | 368484 | 0 | 0 | 0 | 0 | 0 | 174 | 457795 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -1522120 | 0 | 309 | 707 | 21592047 | 3591843
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 115.6% | 1 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | 141.7% | 0 | -39220 | 13723361 | 337 | 168 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49
| 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 104.4% | 1 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | 102.1% | 1 | -46667 | 1006123 | 45 | 54 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74
| 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 109.6% | 1 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | 101.7% | 1 | -5101 | 36197 | 122 | 57 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 |  | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59
| 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 109.7% | 1 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 96.26% | 1 | 0 | 24353 | 27 | 32 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34
| 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 41.85% | 1 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 99.42% | 1 | 0 | 0 | 13 | 33 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28
| 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 81.25% | 1 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | 104.2% | 1 | -37398 | 60198 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 106.6% | 1 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 89.4% | 1 | 0 | -257025 | 84 | 49 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -257025 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55
| 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 97.86% | 1 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | 98.18% | 1 | -24020 | 108776 | 20 | 21 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01
| 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 97.52% | 1 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | 101.1% | 1 | -521 | 103751 | 36 | 30 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7
| 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 97.86% | 1 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 106.9% | 1 | 0 | 0 | 18 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6
| 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 50.5% | 1 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | 87.54% | 1 | -52 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 11 | 18 | 44 | 3809 | 5280 | 4822 | #VALUE! | 11 | 458 | 0 | 0 | 1263 | 208 | 96116791 | 954341 | 95162449 | 110922526 | 109349313 | 0 | 37398 | 37398 | 109386711 | 109108767 | 90.91% | 10 | -152979 | 14805734 | 729 | 489 | 0 | 29 | 1034745 | 0 | 0 | 14 | 1003521 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 176 | 11596445 | 0 | 0 | 0 | 1689505 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -257025 | 0 | 137 | 220 | 15144193 | 0
| District 08 Totals |  |  |  |  | 11 | 18 | 44 | 3809 | 5280 | 4822 | 100% | 11 | 458 | 0 | 0 | 1263 | 208 | 96116791 | 954341 | 95162449 | 110922526 | 109349313 | 0 | 37398 | 37398 | 109386711 | 109108767 | 90.91% | 10 | -152979 | 14805734 | 729 | 489 | 0 | 29 | 1034745 | 0 | 0 | 14 | 1003521 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 176 | 11596445 | 0 | 0 | 0 | 1689505 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -257025 | 0 | 137 | 220 | 15144193 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 103 | 210 | 274 | 32299 | 49226 | 47737 | 80.58% | 83 | 1489 | 141 | 0 | 13958 | 2969 | 918828742 | 7933975 | 910894764 | 951249983 | 962059795 | -219920 | 1842660 | 1622740 | 963682535 | 960152134 | 91.26% | 94 | 5262074 | 32421236 | 8657 | 4610 | 328 | 1225 | 9897464 | 476847 | 257 | 712 | 10826445 | 3020482 | 0 | 0 | 132416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 212 | 8589245 | 938726 | 165 | 154 | 1346798 | 403107 | 0 | 0 | 0 | 0 | 841 | 260 | 1049784 | 161149 | 0 | 0 | 355913 | 0 | 60 | 115 | 380350 | 643594 | 89 | 148 | 0 | 0 | 0 | 0 | -1431425 | 0 | 1995 | 2826 | 31146991 | 5643903
| Statewide District Let Contracts SubTotal |  |  |  |  | 91 | 149 | 272 | 29589 | 43431 | 41870 | 87.91% | 80 | 1561 | 104 | 0 | 11384 | 2491 | 1013381397 | 6167047 | 1007214349 | 1081863455 | 1081278396 | -471555 | 3612398 | 3140843 | 1084419238 | 1075205834 | 94.51% | 86 | 6712139 | 68439925 | 6115 | 4418 | 87 | 621 | 13302509 | 1703172 | 271 | 453 | 12965633 | 614819 | 0 | 0 | 10318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | 637 | 27961330 | 3335 | 15 | 20 | 2075549 | 22700 | 0 | 0 | 0 | 0 | 545 | 399 | 1868915 | 208207 | 0 | 249 | 7623579 | 7300000 | 0 | 214 | 537492 | 530851 | 26 | 0 | 0 | 0 | 0 | 0 | -790220 | 0 | 1564 | 2593 | 65555095 | 10383083
| Statewide Totals |  |  |  |  | 194 | 359 | 546 | 61888 | 92657 | 89607 | 84.02% | 163 | 3050 | 245 | 0 | 25342 | 5460 | 1932210139 | 14101022 | 1918109113 | 2033113438 | 2043338191 | -691475 | 5455058 | 4763583 | 2048101773 | 2035357968 | 92.78% | 180 | 11974213 | 100861161 | 14772 | 9028 | 415 | 1846 | 23199973 | 2180019 | 528 | 1165 | 23792078 | 3635301 | 0 | 0 | 142734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875 | 849 | 36550575 | 942061 | 180 | 174 | 3422347 | 425807 | 0 | 0 | 0 | 0 | 1386 | 659 | 2918699 | 369356 | 0 | 249 | 7979492 | 7300000 | 60 | 329 | 917842 | 1174445 | 115 | 148 | 0 | 0 | 0 | 0 | -2221645 | 0 | 3559 | 5419 | 96702086 | 16026986

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1R76 | 20121535201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2020-05-29 | 70460520 | 71635236 | 73663828 | 1174716.35 | -100000 | 77151838 | 0 | 0 | 0 | 0 | 0 | -100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 73563828 | 77151838 | 3588010 | 57230748 | Y | DESIGN/BUILD PROJECT
1 | E1V08 | 19602265201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-02 | 6226258 | 6296806 | 6274547 | 70547.94 | 0 | 6264042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6274547 | 6264042 | -10506 | 7418504
1 | E1V10 | 44155015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-16 | 14609258 | 14044029 | 14088333 | -565228.69 | -3245 | 13959008 | -3245 | 0 | 0 | 0 | 0 | 0 | -3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3245 | 14085087 | 13959008 | -126080 | 14926350
1 | E1V13 | 44893915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-09-19 | 5289078 | 5392842 | 5545592 | 103763.45 | 0 | 5545735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 5760652
1 | E1V22 | 44620615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-20 | 5142423 | 5047658 | 5138834 | -94764.75 | 0 | 5137805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138834 | 5137805 | -1029 | 4496918
1 | E1V23 | 44743415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-07-20 | 5558710 | 5552034 | 5723019 | -6675.84 | 0 | 5741811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5723019 | 5741811 | 18793 | 5765208
1 | E1V51 | 44743715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-02 | 23141400 | 23931467 | 24545579 | 790066.61 | 0 | 24064967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24545579 | 24064967 | -480611 | 26691037 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1W13 | 44594215201 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2024-02-15 | 2428636 | 2626766 | 2708707 | 198129.96 | -66250 | 2642436 | -66250 | 0 | 0 | 0 | 0 | 0 | -66250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66250 | 2642457 | 2642436 | -22 | 3681296
1 | E1W18 | 44743115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-18 | 2506911 | 2530764 | 2550717 | 23853.05 | 0 | 2546483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 2727223
1 | E1W50 | 45279215201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-26 | 2283584 | 2283584 | 2253806 | 0 | 0 | 2253543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 2780605 | Y | DESIGN/BUILD PROJECT
1 | E1W75 | 44923315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-18 | 2560003 | 2560003 | 2586788 | 0 | 0 | 2586788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 3481659
1 | E1W76 | 44897215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-15 | 3352588 | 3352588 | 3378389 | 0 | 0 | 3377632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 4285958
1 | E1W79 | 44023015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-09-19 | 1118465 | 1118465 | 854089 | 0 | 0 | 854089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854089 | 854089 | -1 | 991704
1 | E1W85 | 44893115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-07 | 4458291 | 4710660 | 4720609 | 252368.4 | 0 | 4733331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4720609 | 4733331 | 12722 | 5001199
1 | T1754 | 41924345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-06-10 | 44711727 | 45332170 | 46495372 | 620442.65 | 0 | 47278762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46495372 | 47278762 | 783390 | 49671696
1 | T1833 | 44634515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 16756829 | 16756829 | 16918647 | 0 | -70500 | 16748453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70500 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 17387335
1 | T1843 | 43695525201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-07-27 | 4165582 | 4197230 | 4319692 | 31647.71 | 0 | 4262739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4319692 | 4262739 | -56953 | 3563245
1 | T1852 | 44787215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 3084175 | 3084175 | 3074445 | 0 | 0 | 3073651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 2364266
1 | T1854 | 44480735201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-03-27 | 1273662 | 1300460 | 1232804 | 26798.65 | -22000 | 1210162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | -22000 | -22000 | 1210804 | 1210162 | -642 | 1109605
1 | T1855 | 44547315201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11238774 | 11323365 | 11568463 | 84591.09 | -143070 | 11537149 | -143070 | 0 | 0 | 0 | 0 | 0 | -143070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143070 | 11425393 | 11537149 | 111756 | 12534705
1 | T1866 | 43903215201 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2023-11-15 | 3945642 | 4078353 | 4013289 | 132711.4 | -76850 | 3923705 | -76850 | 0 | 0 | 0 | 0 | 0 | -76850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76850 | 3936439 | 3923705 | -12734 | 5005578
1 | T1868 | 44740215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-02-28 | 1036497 | 1074999 | 1074468 | 38501.79 | 0 | 1074468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074468 | 1074468 | 0 | 1164569
1 | T1881 | 43802715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 6196035 | 6206737 | 6556044 | 10701.34 | 0 | 6524950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 6886951
1 | T1891 | 44743625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 4742624 | 4787027 | 4779994 | 44403.46 | 0 | 4777172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 4605370
1 | T1895 | 44656015201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2024-09-25 | 1414901 | 1450512 | 1460078 | 35610.63 | 0 | 1460017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 1992638
2 | E200W | 44572615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 2930266 | 2930266 | 2970891 | 0 | 0 | 2968577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 2593407
2 | E20S2 | 21054545201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 8601469 | 8601469 | 8734394 | 0 | 0 | 8453915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 8397276 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20T6 | 44278015201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-02-15 | 1676236 | 1744958 | 1814629 | 68721.9 | 0 | 1814629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 2494428
2 | E20X8 | 20840265201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 9409691 | 9409691 | 9709502 | 0 | 0 | 9670685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 8868810 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20X9 | 44707615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 11213775 | 11213775 | 11321495 | 0 | 0 | 11257290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 11190658 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E2Z53 | 43035245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-02-20 | 17677113 | 32771107 | 33306856 | 15093994.45 | 0 | 33713424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33306856 | 33713424 | 406568 | 14339167
2 | T2757 | 43761115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 8709827 | 8796925 | 9281776 | 87098.27 | 0 | 9514074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281776 | 9514074 | 232299 | 10240285
2 | T2790 | 43616815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2021-01-27 | 15444874 | 18490817 | 18667723 | 3045942.89 | 0 | 18710310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18667723 | 18710310 | 42587 | 11733777
2 | T2839 | 44342115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 31969186 | 31969186 | 32489212 | 0 | 0 | 33982240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 35449756
2 | T2844 | 43935615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 19892956 | 20310363 | 20717832 | 417407.11 | 0 | 20372452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20717832 | 20372452 | -345380 | 16227519
2 | T2854 | 44554515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 10095026 | 10267526 | 10526210 | 172500 | 0 | 10199858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10526210 | 10199858 | -326352 | 10655889
2 | T2863 | 43744115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-01-12 | 14032373 | 15901285 | 16261074 | 1868911.96 | 0 | 16285649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16261074 | 16285649 | 24575 | 15021661
2 | T2865 | 44351715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-11-16 | 7663000 | 8470199 | 9163770 | 807198.83 | 0 | 9151881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163770 | 9151881 | -11890 | 7014633
2 | T2889 | 43575615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3832776 | 4315395 | 4383212 | 482619.04 | 0 | 4383212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 4521037
2 | T2894 | 44540215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 12471547 | 12747539 | 13553931 | 275991.77 | 0 | 13363147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 11980864
2 | T2910 | 44535215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 5895675 | 5981679 | 6100547 | 86003.71 | 0 | 6097264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100547 | 6097264 | -3283 | 6680440
2 | T2915 | 44718015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11703806 | 11742594 | 12389230 | 38788.29 | 0 | 12394517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12389230 | 12394517 | 5287 | 10416036
2 | T2916 | 43993715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 10398707 | 10398707 | 10268067 | 0 | 0 | 10264664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10268067 | 10264664 | -3403 | 8834994
2 | T2917 | 44330415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-05-17 | 23947969 | 24055659 | 25032603 | 107690.09 | 0 | 25026994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 21934860
2 | T2934 | 44331015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 26057502 | 26443445 | 27980036 | 385943.3 | 0 | 27874372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 24163400
2 | T2945 | 44542715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 6853255 | 6853255 | 6989283 | 0 | 0 | 6981891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 7614578
2 | T2948 | 44712315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5794236 | 5794236 | 5977965 | 0 | 0 | 5958952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5977965 | 5958952 | -19013 | 5749685
2 | T2949 | 20969745201 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2023-11-15 | 1865813 | 1939049 | 1961474 | 73235.26 | 0 | 1960364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 2230664
2 | T2954 | 44542015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3819110 | 3819110 | 3735111 | 0 | 0 | 3733457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 5040192
2 | T2961 | 43633015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3521000 | 3558326 | 3560864 | 37326.4 | 0 | 3626016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560864 | 3626016 | 65152 | 3765541
2 | T2962 | 44796215201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 7958218 | 7958218 | 7882304 | 0 | 0 | 7877534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 8827614
2 | T2966 | 21086555201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2921783 | 2921783 | 2938946 | 0 | 0 | 2938946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 3224885
2 | T2969 | 44703615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 10923210 | 10892472 | 11424138 | -30738.04 | 0 | 11378255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | 10802904
2 | T2970 | 44712815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 6497196 | 6705393 | 7314719 | 208197.25 | 0 | 7294065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314719 | 7294065 | -20654 | 6729212
2 | T2976 | 44755715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 25893810 | 26291007 | 27924429 | 397197.72 | 0 | 27880284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 21206563
2 | T2981 | 45220125201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 2914229 | 2914229 | 2917184 | 0 | 0 | 2917184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 4244876
2 | T2985 | 43761415201 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 7308506 | 7308506 | 7304574 | 0 | 0 | 7285470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 8026688
2 | T2988 | 44721135201 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2024-04-24 | 1562105 | 1737694 | 1710662 | 175588.73 | 0 | 1710435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 1572772
2 | T2997 | 44984425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2499454 | 2573884 | 2437559 | 74429.6 | 0 | 2436488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 2231403
2 | T2A02 | 43431825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 7419960 | 7419960 | 7285721 | 0 | 0 | 7282630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 8775588
2 | T2A12 | 21071155201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 4071019 | 4106006 | 4039787 | 34986.19 | 0 | 4039787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 4204426
2 | T9037 | 44627925214 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 755793 | 799963 | 782324 | 44170 | 0 | 782311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782324 | 782311 | -13 | 588438
2 | T9041 | 44628015215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 211688 | 211688 | 200166 | 0 | 0 | 200166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200166 | 200166 | 0 | 233430
2 | T9044 | 44628025216 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-01-29 | 393754 | 393754 | 371540 | 0 | 0 | 371540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371540 | 371540 | 0 | 505500
3 | E3V54 | 44554115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-02-09 | 9981474 | 10203672 | 10678123 | 222197.51 | 0 | 10639564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 10144016
3 | E3V77 | 40919375201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-10-12 | 3075367 | 3075367 | 2907496 | 0 | 0 | 2907496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 4067369
3 | E3W12 | 44643355201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-08 | 2949285 | 2625347 | 2604415 | -323937.27 | 0 | 2604415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | 3480038
3 | E3W30 | 44759615201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-06-08 | 4167167 | 4263313 | 3906647 | 96146.41 | 0 | 3906647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 4722892
3 | E3W40 | 44374425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6286877 | 6497112 | 6613095 | 210234.99 | -68148 | 6607189 | -68148 | 0 | 0 | 0 | 0 | 0 | -68148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68148 | 6544947 | 6607189 | 62243 | 5983265
3 | E3W42 | 44559015201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6987787 | 6987787 | 7253303 | 0 | -185514 | 7068223 | -185514 | 0 | 0 | 0 | 0 | 0 | -185514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -185514 | 7067789 | 7068223 | 435 | 10217707
3 | E3W68 | 45102815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-13 | 112106 | 112106 | 103639 | 0 | 0 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103639 | 103639 | 0 | 174993
3 | E3W79 | 45109915201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-04-11 | 485265 | 485265 | 487819 | 0 | 0 | 487819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487819 | 487819 | 0 | 555113
3 | E3X01 | 40619455201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-10-24 | 328567 | 328567 | 291720 | 0 | 0 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291720 | 291720 | 0 | 364798
3 | E3X03 | 40619635201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-03-13 | 169075 | 169075 | 154095 | 0 | 0 | 154095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154095 | 154095 | 0 | 240133
3 | E3X08 | 45103115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-07-11 | 1112248 | 1112248 | 1077908 | 0 | 0 | 1077908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 1273505
3 | E3X17 | 44758915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-13 | 2342678 | 2369603 | 2340433 | 26925.01 | 0 | 2340369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 2975754
3 | E3X52 | 43078225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-11 | 4271650 | 4271650 | 4371998 | 0 | 0 | 4360199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 4754953
3 | E3X72 | 22020225201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-02-13 | 647631 | 647631 | 536583 | 0 | 0 | 536583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536583 | 536583 | 0 | 900233
3 | E3X87 | 45268615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2024-09-12 | 1172775 | 1197264 | 1124063 | 24489.2 | 0 | 1124063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 1445110
3 | E3Y07 | 43937125201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-01-30 | 493247 | 493247 | 468786 | 0 | 0 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468786 | 468786 | 0 | 566683
3 | E3Y28 | 45443415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-04-10 | 339177 | 339177 | 318764 | 0 | 0 | 318764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318764 | 318764 | 0 | 393848
3 | T3705 | 43581615201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 21786584 | 24287618 | 24853167 | 2501033.2 | 0 | 24864564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24853167 | 24864564 | 11396 | 31799900
3 | T3790 | 43748915201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 3547402 | 3547402 | 3587891 | 0 | 0 | 3586665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 4578762
3 | T3837 | 22259365201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 11772258 | 11871253 | 11834603 | 98994.59 | 0 | 11821261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 13447557
3 | T3855 | 44401915201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 958894 | 958894 | 885299 | 0 | 0 | 885298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885299 | 885298 | -1 | 1271778
3 | T3868 | 41344925201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 1298401 | 1321412 | 1234071 | 23011 | 0 | 1234071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 1300164
3 | T3874 | 44188015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 988409 | 988409 | 938135 | 0 | 0 | 938135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938135 | 938135 | 0 | 990879
3 | T3891 | 43467815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2823614 | 2855298 | 2780904 | 31684.39 | 0 | 2780236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 3805810
3 | T3901 | 41342535201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | 3608291 | 3609941 | 3619668 | 1650 | 0 | 3616057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 3187529
3 | T3913 | 21934625201 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2024-08-28 | 2531784 | 2570548 | 2574902 | 38764.2 | 0 | 2573463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 3011929
3 | T9043 | 44628415215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 189979 | 189979 | 177334 | 0 | 0 | 177334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177334 | 177334 | 0 | 237358
4 | E4U48 | 44146615201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 2126000 | 2132929 | 1513603 | 6929.94 | 0 | 1513603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513603 | 1513603 | 0 | 2622052
4 | E4U88 | 43999925201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-04-07 | 10631541 | 10738131 | 11100934 | 106590.35 | 0 | 11099417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11100934 | 11099417 | -1518 | 10492575
4 | E4V62 | 43695815201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-18 | 31058595 | 33155117 | 32699199 | 1946522.44 | 0 | 32559543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32699199 | 32559543 | -139657 | 29695111
4 | E4W05 | 44047315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-02 | 3993841 | 4453325 | 4438530 | 459484.36 | 0 | 4433029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438530 | 4433029 | -5501 | 4033616
4 | E4W54 | 44618515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 8153790 | 8619435 | 8570644 | 465645.84 | 0 | 8570644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8570644 | 8570644 | 0 | 7653131
4 | E4W61 | 44610415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-04 | 5369226 | 5369226 | 5576786 | 0 | 0 | 5571433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 4627615
4 | E4W72 | 44617015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-11-03 | 4285836 | 4430549 | 4413846 | 144712.95 | 0 | 4404654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413846 | 4404654 | -9192 | 4697027
4 | E4W82 | 44610515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-01-05 | 4881711 | 4893014 | 4759434 | 11302.53 | 0 | 4771645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759434 | 4771645 | 12211 | 5716819
4 | E4W88 | 44765415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 6226524 | 6395874 | 6393098 | 169349.93 | 0 | 6387556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6393098 | 6387556 | -5542 | 6625404
4 | E4W89 | 44767415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-07-12 | 3966137 | 3985889 | 3958991 | 19751.98 | 0 | 3953275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 4276093
4 | E4W93 | 44764815201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-12 | 3198987 | 3198987 | 3046918 | 0 | 0 | 3045966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 3443705
4 | E4X17 | 44655115201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 1849000 | 1870772 | 1768167 | 21772.08 | 0 | 1768167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 2011837
4 | E4X24 | 44931815201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-06 | 3983900 | 4183008 | 4262893 | 199107.9 | 0 | 4262893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 5126069
4 | E4X33 | 44359525201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-09-06 | 2579048 | 2787519 | 2747199 | 208471 | 0 | 2747177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 3891911
4 | T4560 | 44004315201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2472960 | 2472960 | 2581880 | 0 | 0 | 2588651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581880 | 2588651 | 6772 | 2686958
4 | T4627 | 44384615201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 1831417 | 1831417 | 1800868 | 0 | 0 | 1800868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 2390409
4 | T4638 | 43580855201 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 8148235 | 8411133 | 8179681 | 262898 | 0 | 8175682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8179681 | 8175682 | -3998 | 8255267
4 | T4645 | 44610215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 12833449 | 12956058 | 12287948 | 122609.04 | 0 | 12290198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12287948 | 12290198 | 2250 | 14351247
4 | T4662 | 44001515201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 2710165 | 2699856 | 2568771 | -10309.35 | 0 | 2568756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568771 | 2568756 | -16 | 3354140
4 | T4664 | 44699715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1247247 | 1247247 | 1175544 | 0 | 0 | 1174544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 1347695
4 | T4679 | 44619615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 5469442 | 5469442 | 5544372 | 0 | 0 | 5542177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 5971109
4 | T4687 | 45222715201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1600545 | 1600545 | 1508063 | 0 | 0 | 1508063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 2128846
4 | T4708 | 44754315201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-07-31 | 1300000 | 1300000 | 1243700 | 0 | 0 | 1243700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 1369377
5 | E50F1 | 44656815201 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2024-02-06 | 1104118 | 1104118 | 1062935 | 0 | 0 | 1062929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 1174164
5 | E51F2 | 44768815201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-04-02 | 1504656 | 1506430 | 1447570 | 1774.33 | 0 | 1447098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447570 | 1447098 | -472 | 1590260
5 | E51F7 | 44530215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-05 | 5562121 | 5724310 | 5880473 | 162189.46 | 0 | 5865584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880473 | 5865584 | -14889 | 6330177
5 | E51F9 | 43912415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-02 | 4408516 | 4442576 | 4279968 | 34060.07 | 0 | 4279968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279968 | 4279968 | 0 | 6688705
5 | E53F2 | 44879115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-01 | 7065614 | 7183452 | 7253477 | 117838 | 0 | 7256561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 8985393
5 | E53F8 | 45022745201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-04 | 1498164 | 1498164 | 1468694 | 0 | 0 | 1468694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 1507975
5 | E54B3 | 44521415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-03 | 6964127 | 7171619 | 7043664 | 207492.45 | 0 | 6998013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7043664 | 6998013 | -45651 | 9627439
5 | E56B6 | 44521115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 3196756 | 3198241 | 3427202 | 1484.92 | 0 | 3427202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 3501358
5 | E57B3 | 24259265201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2023-06-06 | 9899345 | 10080554 | 10364962 | 181208.47 | 0 | 10364953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10364962 | 10364953 | -9 | 8480188
5 | E57B7 | 44708515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-06-06 | 13078910 | 13273764 | 13547486 | 194854.3 | 0 | 13544883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13547486 | 13544883 | -2602 | 13524204 | A5 | ICC - BAM/BONUS
5 | E59A5 | 44780715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-06 | 973615 | 973615 | 939263 | 0 | 0 | 939263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939263 | 939263 | 0 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E59B2 | 43986415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-02-06 | 3015224 | 3086900 | 3009526 | 71675.77 | 0 | 3004683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009526 | 3004683 | -4843 | 3337723
5 | E5Z18 | 24020045201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-08-22 | 253332000 | 267516079 | 275166241 | 14184078.5 | 25000 | 276193366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 275191241 | 276193366 | 1002125 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | T5706 | 42955615201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 44888403 | 47699589 | 50521720 | 2811185.71 | 0 | 50750843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50521720 | 50750843 | 229122 | 37019155
5 | T5718 | 43763415201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 11250000 | 12978309 | 13223828 | 1728309.11 | 0 | 13379283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13223828 | 13379283 | 155455 | 10799983
5 | T5747 | 43366115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 6696978 | 7142732 | 7032054 | 445754.9 | 0 | 7032054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7032054 | 7032054 | 0 | 5918166
5 | T5759 | 44586715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-04-26 | 3865830 | 3991018 | 3937381 | 125187.71 | 0 | 3936003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 3318269
5 | T5760 | 44114515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 9020145 | 9091224 | 9371724 | 71078.78 | 0 | 9370672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9371724 | 9370672 | -1051 | 8000814
5 | T5777 | 44042425201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 22896706 | 23663870 | 23767312 | 767163.74 | 0 | 22940754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23767312 | 22940754 | -826558 | 28387050 | B10 | ACC - BONUS/INCENT/DISINCENT
5 | T5778 | 44569215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 1617324 | 1637324 | 1467772 | 20000 | 0 | 1467140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 1625739
5 | T5786 | 44521715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 10986719 | 11011859 | 11062198 | 25139.3 | 0 | 11057841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11062198 | 11057841 | -4358 | 14985674
5 | T5789 | 43547125201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 8448064 | 8800372 | 8800513 | 352307.8 | 0 | 8801368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800513 | 8801368 | 855 | 8153515
5 | T5795 | 24259285201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 8347803 | 8496009 | 8830863 | 148205.6 | 0 | 8830373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8830863 | 8830373 | -490 | 8013785
5 | T5799 | 44571615201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 7000000 | 7423497 | 7482575 | 423497.41 | 0 | 7448919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7482575 | 7448919 | -33657 | 8074701
5 | T5800 | 44585515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-26 | 3679712 | 3851805 | 3808215 | 172092.45 | 0 | 3808146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3808215 | 3808146 | -69 | 2818722
5 | T5805 | 44709215201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 3271306 | 3287930 | 3244926 | 16623.23 | 0 | 3224506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 4597691
5 | T5806 | 44709815201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 9892142 | 9938977 | 10455307 | 46835.26 | 0 | 10397121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10455307 | 10397121 | -58186 | 11922850
5 | T5809 | 43915615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-27 | 19059007 | 19456279 | 20132774 | 397272.41 | 0 | 20058365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20132774 | 20058365 | -74410 | 20470643
5 | T5811 | 43233215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 15324226 | 16443632 | 16758792 | 1119405.88 | 0 | 16640684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758792 | 16640684 | -118108 | 22228374
5 | T5833 | 44708915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2100000 | 2100000 | 2001416 | 0 | 0 | 2001416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 2701146
5 | T5835 | 44873915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 3081418 | 3081418 | 3111059 | 0 | 0 | 3112003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 3300432
5 | T5857 | 45613715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 117123 | 113191 | 103346 | -3931.68 | 0 | 103346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103346 | 103346 | 0 | 180486
5 | T9030 | 44199035223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5555556 | 5605113 | 5565155 | 49557.59 | 0 | 5565155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 5530000
6 | E6M86 | 43351125201 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2021-05-27 | 41366428 | 43068537 | 44950000 | 1702108.31 | 1960000 | 45038064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 160000 | 0 | 1960000 | 1960000 | 46910000 | 45038064 | -1871936 | 33950112 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | E6O12 | 44391925201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 2869869 | 2869869 | 2778313 | 0 | 140000 | 2778250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 2865779 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6O17 | 43029169201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-13 | 7237000 | 7269318 | 7237180 | 32318.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 5284477 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6P13 | 43029189201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-04-22 | 1315382 | 1315382 | 1284180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 1725000 | Y | DESIGN/BUILD PROJECT
6 | T6466 | 43992315201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 749749 | 750453 | 687268 | 704 | 0 | 687166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687268 | 687166 | -102 | 759571
6 | T6541 | 44390215201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-02-22 | 6112543 | 6196534 | 6055588 | 83991.29 | 0 | 6047700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6055588 | 6047700 | -7887 | 4898503 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6547 | 44392115201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2023-05-24 | 7844825 | 8071972 | 8026073 | 227147.21 | 200000 | 8025252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 8411804 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6555 | 44598715201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-04-26 | 15230513 | 15276979 | 14673045 | 46466.35 | 440000 | 14652396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 440000 | 440000 | 15113045 | 14652396 | -460650 | 16721998 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6562 | 44393715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 9816354 | 9816354 | 9814725 | 0 | 320000 | 9792214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 10415642 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6574 | 44780515201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-10-25 | 3338573 | 3388573 | 3361643 | 50000 | 100000 | 3354655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 3605554 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6575 | 44780615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 4637389 | 4652332 | 4600291 | 14943 | 0 | 4597318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600291 | 4597318 | -2973 | 4247705 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | E7P77 | 44146315201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-05-10 | 3366760 | 3493112 | 3363518 | 126351.52 | 300000 | 3363518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | E7Q31 | 44384115201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-12-13 | 1681476 | 1805476 | 1410753 | 124000 | -3398 | 1407355 | -3398 | 0 | 0 | 0 | 0 | 0 | -3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3398 | 1407355 | 1407355 | 0 | 1673100
7 | E7Q39 | 44582815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | 1714027 | 1714027 | 1704720 | 0 | 0 | 1704720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 3483914
7 | E7Q53 | 44583015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-05-08 | 1599000 | 1601196 | 1343560 | 2195.84 | 0 | 1343560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343560 | 1343560 | 0 | 1936163
7 | E7Q55 | 44165115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-03-13 | 4066019 | 4201769 | 4164473 | 135750.09 | 0 | 4159743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4164473 | 4159743 | -4730 | 4234476
7 | E7Q75 | 45288915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-12 | 1296714 | 1381899 | 1384246 | 85184.94 | 0 | 1384246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384246 | 1384246 | 0 | 1695805
7 | E7Q94 | 45273615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-11 | 259111 | 259111 | 235124 | 0 | 0 | 235124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235124 | 235124 | 0 | 516283
7 | E7R15 | 44138815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-29 | 21358193 | 21288752 | 21393187 | -69440.22 | 1150000 | 21918008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 1150000 | 1150000 | 22543187 | 21918008 | -625179 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
7 | E7R21 | 42451335201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2021-05-20 | 81649200 | 89787672 | 91076513 | 8138472.09 | 0 | 91676950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91076513 | 91676950 | 600437 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R24 | 44132015201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2022-08-04 | 6997500 | 7112720 | 7042786 | 115219.68 | 0 | 7042581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 13119000
7 | E7R26 | 42925115201 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2021-06-17 | 89691574 | 96531643 | 97484006 | 6840069.17 | -45000 | 98162236 | 0 | 0 | 0 | 0 | 0 | -45000 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 97439006 | 98162236 | 723230 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R40 | 44335825201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-07 | 1322000 | 1334250 | 1257998 | 12249.84 | 0 | 1253861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257998 | 1253861 | -4137 | 1543770 | LBDB | LOW BID DESIGN BUILD
7 | T7396 | 41673245201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 55832153 | 56499915 | 56400689 | 667762.03 | 875160 | 56882314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875160 | 0 | 0 | 0 | 0 | 0 | 875160 | 875160 | 57275849 | 56882314 | -393534 | 63202968 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
7 | T7472 | 43182125201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | 85239705 | 94443373 | 97569383 | 9203668.27 | 0 | 97817624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97569383 | 97817624 | 248241 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7509 | 44588615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 8085082 | 8115381 | 7967342 | 30299.15 | 0 | 7993474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7967342 | 7993474 | 26132 | 9550800
7 | T7512 | 44334715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 6290573 | 6754957 | 7072599 | 464384.48 | 0 | 7072474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7072599 | 7072474 | -125 | 6135700
7 | T7514 | 45069315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 2469300 | 2490043 | 2487609 | 20743.16 | 0 | 2486604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 2285000
7 | T7516 | 44006315201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 6730280 | 6779810 | 6697913 | 49529.32 | 0 | 6699170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6697913 | 6699170 | 1257 | 7050800
7 | T7523 | 44697315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 2049777 | 2049777 | 2101379 | 0 | 0 | 2098362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 2385840
7 | T7529 | 44109835201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-03-27 | 1336107 | 1336107 | 1267198 | 0 | 0 | 1266909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 1581132
7 | T7538 | 44939815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-15 | 545691 | 545691 | 518518 | 0 | 0 | 518518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518518 | 518518 | 0 | 611133
7 | T7544 | 44025015201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 7475300 | 7428809 | 7644411 | -46491.53 | 0 | 7629621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | 8386992
7 | T7550 | 45241215201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-15 | 654321 | 654321 | 610593 | 0 | 0 | 610593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610593 | 610593 | 0 | 826944
7 | T7555 | 44794815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 5942087 | 5942922 | 5968673 | 835.12 | 0 | 5968280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 7672150
7 | T7573 | 45096915201 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-26 | 365071 | 370411 | 359883 | 5340 | 0 | 354442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359883 | 354442 | -5442 | 528390
8 | E8R45 | 43799215201 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2018-11-15 | 33928239 | 47651600 | 47969861 | 13723361.4 | 0 | 47904732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47969861 | 47904732 | -65129 | 41184698
8 | E8U04 | 44602415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-03-21 | 16184460 | 17190583 | 16458548 | 1006122.94 | 0 | 16411881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458548 | 16411881 | -46667 | 18390077
8 | E8U19 | 44588515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-11 | 11226810 | 11263007 | 11344464 | 36197.44 | 0 | 11339363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344464 | 11339363 | -5101 | 11461891
8 | E8U32 | 44925335201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2023-05-09 | 3649071 | 3673424 | 3464348 | 24353 | 0 | 3464348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 4370418
8 | E8U46 | 43854815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-14 | 4734726 | 4734726 | 4628034 | 0 | 0 | 4628034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 8236620
8 | E8U56 | 44942325201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2023-08-22 | 1804313 | 1864511 | 1827419 | 60197.92 | 37398 | 1827419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37398 | 0 | 0 | 0 | 0 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 1786238 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8U71 | 41592755201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-02-13 | 2794276 | 2537251 | 2444066 | -257025.06 | 0 | 2444066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | 6003502
8 | E8U73 | 44206215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-03-12 | 13684469 | 13793245 | 13317036 | 108776.05 | 0 | 13293015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13317036 | 13293015 | -24020 | 19932483
8 | E8U91 | 44917545201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-11 | 4804962 | 4908714 | 4813444 | 103751.34 | 0 | 4812923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4813444 | 4812923 | -521 | 4334608
8 | E8U95 | 44917535201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-04-09 | 1605678 | 1605678 | 1663792 | 0 | 0 | 1663792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 1739460
8 | E8V77 | 45211115201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-02-19 | 1699787 | 1699787 | 1444210 | 0 | 0 | 1444159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 1780237

## Sheet1 (hidden)
01CO | 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 2409623 | 620443 | 176 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO | 11 | 01co | 1 | 11
01CO | 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 0 | 136 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO | 14 | 01do | 12 | 25
01CO | 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | -56953 | 31648 | 155 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 33 | 02co | 26 | 58
01CO | 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 6 | 02do | 59 | 64
01CO | 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | -642 | 26799 | 27 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 10 | 03co | 65 | 74
01CO | 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11519677 | 104968 | 84591 | 129 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO | 17 | 03do | 75 | 91
01CO | 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | -14467 | 132711 | 40 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO | 9 | 04co | 92 | 100
01CO | 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 0 | 38502 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 14 | 04do | 101 | 114
01CO | 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 10701 | 70 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71 |  |  | 16 | 24 | 0 | 0 | 0 | 0 |  | CO | 20 | 05co | 115 | 134
01CO | 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 44403 | 18 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8 |  |  | 19 | 21 | 0 | 0 | 0 | 0 | T | CO | 13 | 05do | 135 | 147
01CO | 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 35611 | 16 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 7 | 06co | 148 | 154
01DO | 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 5571562 | 1174716 | 264 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT | 0 | 101 | 0 | 0 | 0 | 0 |  | DO | 4 | 06do | 155 | 158
01DO | 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | -10506 | 70548 | 51 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO | 13 | 07co | 159 | 171
01DO | 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | -126080 | -565229 | 188 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94 |  |  | 21 | 42 | 0 | 0 | 0 | 0 |  | DO | 12 | 07do | 172 | 183
01DO | 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 103763 | 8 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 184 | 183
01DO | 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | -1029 | -94765 | 25 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22 |  |  | 0 | 22 | 0 | 0 | -132703 | 0 |  | DO | 11 | 08do | 184 | 194
01DO | 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 199 | -6676 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | -480611 | 790067 | 61 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | -22 | 198130 | 44 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 23853 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 0 | 24 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT | 4 | 33 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 0 | 32 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | -1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | -879 | 252368 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 329791 | 87098 | 104 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 251365 | 3045943 | 306 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57 |  |  | 0 | 279 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 0 | 244 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12 |  |  | 120 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | -345380 | 417407 | 191 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23 |  |  | 113 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | -330946 | 172500 | 390 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17 |  |  | 232 | 55 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 24575 | 1868912 | 57 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86 |  |  | 120 | 104 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | -14114 | 807199 | 68 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 482619 | 107 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25 |  |  | 24 | 92 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 275992 | 290 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41 |  |  | 137 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | -3283 | 86004 | 101 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38 |  |  | 60 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | -17213 | 38788 | 301 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13 |  |  | 14 | 45 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | -3560 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 107690 | 101 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67 |  |  | 100 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 385943 | 91 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 0 | 72 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02 |  |  | 90 | 41 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | -21404 | 0 | 93 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61 |  |  | 60 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 73235 | 44 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64 |  |  | 1 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 0 | 67 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | -957 | 37326 | 19 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 0 | 79 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 0 | 34 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | -30738 | 23 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04 |  |  | 58 | 27 | 0 | 0 | -30738 | 0 |  | CO
02CO | 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | -20654 | 208197 | 91 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88 |  |  | 2 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 397198 | 39 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14 |  |  | 2 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 0 | 59 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02 |  |  | 16 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 175589 | 41 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 74430 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 0 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 34986 | 61 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | -13 | 44170 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 208 | 505500 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4 |  |  | 25 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 0 | 136 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 260 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 68722 | 137 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5 |  |  | 246 | 85 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 0 | 27 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 90 | 66 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 498724 | 15093994 | 241 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 417101 | 2501033 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 98995 | 72 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24 |  |  | 20 | 70 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | -1 | 0 | 159 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 23011 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1 |  |  | 118 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 0 | 0 | 262 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 31684 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 1650 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 38764 | 59 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 222198 | 136 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25 |  |  | 33 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66 |  |  | 0 | 68 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | -323937 | 5 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038 |  |  | 34 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 96146 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55 |  |  | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 297 | 210235 | 157 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86 |  |  | 1 | 84 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 435 | 0 | 104 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9 |  |  | 3 | 43 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 26925 | 78 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 24489 | 12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110 |  |  | 1 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 134358 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32 |  |  | 30 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | -3998 | 262898 | 110 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 2250 | 122609 | 65 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | -16 | -10309 | 123 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 0 | 6930 | 77 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | -1518 | 106590 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | -144790 | 1946522 | 57 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36 |  |  | 0 | 27 | 0 | 0 | -118750 | 0 |  | DO
04DO | 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | -6049 | 459484 | 135 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 0 | 469019 | 175 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 104495 | 64 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | -9192 | 144713 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | -5116 | 11303 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | -5542 | 169350 | 38 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 19752 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 21772 | 38 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 199108 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 208471 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48288286 | 2318006 | 2811186 | 343 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5 |  |  | 0 | 216 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 155455 | 1728309 | 360 | 0 | 18 | 529414 | 11401 | 0 | 0 | 879425 | 0 | 0 | 0 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1869865 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79 |  |  | 0 | 314 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 0 | 445755 | 106 | 0 | 4 | 102719 | 0 | 0 | 3 | 36135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 152629 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26 |  |  | 5 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 125188 | 128 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57 |  |  | 0 | 302 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | -1051 | 71079 | 39 | 0 | 0 | 58672 | 0 | 0 | 0 | 4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62692 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19 |  |  | 0 | 130 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | -826558 | 767164 | 32 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 20000 | 119 | 0 | 0 | 34331 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36784 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | -4358 | 25139 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 855 | 352308 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96820 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | -490 | 148206 | 43 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | -33657 | 423497 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | -69 | 172092 | 61 | 0 | 4 | 19175 | 31865 | 0 | 9 | 74668 | 34516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 104988 | 66380 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96 |  |  | 15 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 16623 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | -58186 | 46835 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | -74410 | 397272 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | -118108 | 1119406 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43781 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 125 | 1047592 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 49558 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 0 | 25 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | -472 | 1774 | 46 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | -14889 | 162189 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 14866 | 12674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14866 | 12674 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 0 | 34060 | 38 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 117838 | 75 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39 |  |  | 5 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | -45651 | 207492 | 59 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 1485 | 141 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08 |  |  | 57 | 64 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | -9 | 181208 | 61 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | -2602 | 194854 | 81 | 0 | 0 | 39880 | 0 | 0 | 10 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS | 8 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 0 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 748 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | -4843 | 71676 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 8560014 | 14184079 | 138 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497575 | 0 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 13908035 | 7394536 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 461 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | -102 | 704 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | -7887 | 83991 | 29 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 227147 | 146 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | -460650 | 46466 | 10 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | -65908 | 0 |  | CO
06CO | 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 50000 | 23 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | -2973 | 14943 | 59 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | -173492 | 1702108 | 104 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | -94401 | 0 |  | DO
06DO | 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 32318 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 123 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | -113501 | 667762 | 87 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 2218662 | 9203668 | 61 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 77 | 0 | 0 | -1334779 | 0 |  | CO
07CO | 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7161112 | -778302 | 30299 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | -125 | 464384 | 209 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700 |  |  | 25 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 20743 | 111 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6699170 | 1257 | 49529 | 152 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800 |  |  | 19 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 0 | 95 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-08 | QTR4 | 24/25 | 799 | 611133 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | -46492 | 13 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 796 | 826944 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 835 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7573 | 45096915201 | 2025-03-26 | QTR3 | 24/25 | 1 | 2 | 65 | 88 | 87 | 1 | 0 | 0 | 23 | 0 | 365071 | 21000 | 344071 | 370411 | 359883 | 0 | 0 | 0 | 359883 | 354442 | -5442 | 5340 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-08-29 | QTR1 | 25/26 | 799 | 528390 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 126352 | 45 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT | 27 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 0 | 124000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 0 | 2196 | 17 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | -92719 | 135750 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476 |  |  | 29 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 0 | 85185 | 50 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 | 2025-07-14 | QTR1 | 25/26 | 799 | 516283 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | -335192 | -69440 | 226 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT | 0 | 48 | 0 | 0 | -69440 | 0 |  | DO
07DO | 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 1620860 | 8138472 | 120 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 64 | 0 | 0 | -117901 | 0 |  | DO
07DO | 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 115220 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 1490307 | 6840069 | 90 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR | 61 | 86 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | -4137 | 12250 | 46 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | -39220 | 13723361 | 337 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49 |  |  | 0 | 168 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | -46667 | 1006123 | 45 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | -5101 | 36197 | 122 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59 |  |  | 30 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 24353 | 27 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 0 | 13 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 60198 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | -257025 | 84 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55 |  |  | 25 | 49 | 0 | 0 | -257025 | 0 |  | DO
08DO | 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | -24020 | 108776 | 20 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | -521 | 103751 | 36 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 0 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0