## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 202783493 | 201640631 | 205783648 | 204114482 | 4956000 | 196076702 | -2.759% | 100% | 2814785 | 1.396% | 3000154 | 1.479% | 6205 | 931 | 15% | 364 | 5.866% | 0 | 0% | 165 | 2.659% | 6370 | 2.659% | 7674 | 7573 | 6278 | 1.176% | 90%
| District Let | 32306993 | 31905329 | 33884814 | 33375330 | 75000 | 32956111 | 3.293% | 100% | 1628702 | 5.105% | 1577820 | 4.884% | 1976 | 150 | 7.591% | 87 | 4.403% | 498 | 25.2% | 163 | 8.249% | 2637 | 33.45% | 2874 | 2767 | 2530 | 28.04% | 81.82%
| All Contracts | 235090486 | 233545960 | 239668462 | 237489812 | 5031000 | 229032813 | -1.932% | 100% | 4443487 | 1.903% | 4577974 | 1.947% | 8181 | 1081 | 13.21% | 451 | 5.513% | 498 | 6.087% | 328 | 4.009% | 9007 | 10.1% | 10548 | 10340 | 8808 | 7.664% | 87.1%
2 | Central Let | 83025503 | 81738373 | 84785480 | 83061630 | 0 | 81063445 | -0.8257% | 100% | 2362861 | 2.891% | 1759977 | 2.12% | 4630 | 725 | 15.66% | 434 | 9.374% | 18 | 0.3888% | 341 | 7.365% | 4989 | 7.754% | 6148 | 6112 | 4953 | 6.976% | 87.5%
| District Let | 34379704 | 33839646 | 36654663 | 36492201 | 0 | 36646926 | 8.296% | 72.73% | 2366386 | 6.993% | 2274962 | 6.617% | 2655 | 335 | 12.62% | 378 | 14.24% | 0 | 0% | 446 | 16.8% | 3101 | 16.8% | 3814 | 3750 | 3037 | 14.39% | 81.82%
| All Contracts | 117405207 | 115578019 | 121440143 | 119553831 | 0 | 117710371 | 1.845% | 88.89% | 4729247 | 4.092% | 4034939 | 3.437% | 7285 | 1060 | 14.55% | 812 | 11.15% | 18 | 0.2471% | 787 | 10.8% | 8090 | 11.05% | 9962 | 9862 | 7990 | 9.677% | 85.19%
3 | Central Let | 33867739 | 33385937 | 37056899 | 38228615 | 0 | 38333557 | 14.82% | 83.33% | 3223058 | 9.654% | 3189161 | 9.417% | 1995 | 972 | 48.72% | 303 | 15.19% | 560 | 28.07% | 168 | 8.421% | 2723 | 36.49% | 3998 | 3999 | 2724 | 36.54% | 50%
| District Let | 127115898 | 126708404 | 131244367 | 130953809 | 0 | 130064697 | 2.649% | 100% | 4228824 | 3.337% | 4128469 | 3.248% | 1878 | 277 | 14.75% | 138 | 7.348% | 206 | 10.97% | 37 | 1.97% | 2121 | 12.94% | 2536 | 2506 | 2091 | 11.34% | 100%
| All Contracts | 160983637 | 160094341 | 168301266 | 169182424 | 0 | 168398254 | 5.187% | 89.47% | 7451882 | 4.655% | 7317630 | 4.546% | 3873 | 1249 | 32.25% | 441 | 11.39% | 766 | 19.78% | 205 | 5.293% | 4844 | 25.07% | 6534 | 6505 | 4815 | 24.32% | 68.42%
4 | Central Let | 24680818 | 24191588 | 25384651 | 24474028 | 37125 | 24322963 | 0.5431% | 100% | 737319 | 3.048% | 703833 | 2.852% | 2968 | 625 | 21.06% | 251 | 8.457% | 72 | 2.426% | 197 | 6.637% | 3237 | 9.063% | 4113 | 4038 | 3162 | 6.536% | 100%
| District Let | 103680052 | 103136520 | 107638747 | 106621950 | 500000 | 104523191 | 1.345% | 100% | 3863217 | 3.746% | 3958695 | 3.818% | 3379 | 639 | 18.91% | 196 | 5.801% | 26 | 0.7695% | 85 | 2.516% | 3490 | 3.285% | 4325 | 4241 | 3406 | 0.7991% | 100%
| All Contracts | 128360870 | 127328108 | 133023398 | 131095978 | 537125 | 128846154 | 1.192% | 100% | 4600536 | 3.613% | 4662528 | 3.632% | 6347 | 1264 | 19.91% | 447 | 7.043% | 98 | 1.544% | 282 | 4.443% | 6727 | 5.987% | 8438 | 8279 | 6568 | 3.482% | 100%
5 | Central Let | 117630752 | 116873252 | 129008448 | 129321661 | 986200 | 126886969 | 8.568% | 60% | 10459050 | 8.949% | 11377688 | 9.672% | 3800 | 912 | 24% | 327 | 8.605% | 0 | 0% | 587 | 15.45% | 4387 | 15.45% | 5745 | 5556 | 4317 | 13.61% | 60%
| District Let | 30608596 | 30009596 | 31525563 | 30948439 | 0 | 30645983 | 2.121% | 92.86% | 723428 | 2.411% | 916967 | 2.996% | 3800 | 693 | 18.24% | 352 | 9.263% | 0 | 0% | 225 | 5.921% | 4025 | 5.921% | 5070 | 4731 | 3686 | -3% | 100%
| All Contracts | 148239348 | 146882848 | 160534011 | 160270100 | 986200 | 157532952 | 7.251% | 79.17% | 11182478 | 7.613% | 12294655 | 8.294% | 7600 | 1605 | 21.12% | 679 | 8.934% | 0 | 0% | 812 | 10.68% | 8412 | 10.68% | 10815 | 10287 | 8003 | 5.303% | 83.33%
6 | Central Let | 74337666 | 72921472 | 76751207 | 76959548 | 2680000 | 76989213 | 5.578% | 100% | 2758126 | 3.782% | 2413540 | 3.247% | 3339 | 551 | 16.5% | 185 | 5.541% | 127 | 3.804% | 0 | 0% | 3466 | 3.804% | 4202 | 3681 | 2945 | -11.8% | 100%
| District Let | 20210626 | 19824069 | 20526074 | 19575974 | 180000 | 12945510 | -34.7% | 100% | 321047 | 1.619% | 315448 | 1.561% | 2115 | 486 | 22.98% | 175 | 8.274% | 0 | 0% | 14 | 0.6619% | 2129 | 0.6619% | 2828 | 2740 | 2079 | -1.702% | 100%
| All Contracts | 94548292 | 92745541 | 97277281 | 96535522 | 2860000 | 89934723 | -3.031% | 100% | 3079173 | 3.32% | 2728988 | 2.886% | 5454 | 1037 | 19.01% | 360 | 6.601% | 127 | 2.329% | 14 | 0.2567% | 5595 | 2.585% | 7030 | 6421 | 5024 | -7.884% | 100%
7 | Central Let | 126792961 | 125553147 | 131714811 | 132064693 | -400000 | 128304126 | 2.191% | 90% | 5287186 | 4.211% | 4921848 | 3.882% | 4520 | 927 | 20.51% | 366 | 8.097% | 89 | 1.969% | 457 | 10.11% | 5066 | 12.08% | 6359 | 6559 | 5266 | 16.5% | 70%
| District Let | 11495739 | 11225239 | 11978719 | 11787376 | 0 | 11645150 | 3.741% | 87.5% | 468957 | 4.178% | 482980 | 4.201% | 1379 | 412 | 29.88% | 131 | 9.5% | 0 | 0% | 34 | 2.466% | 1413 | 2.466% | 1956 | 1862 | 1319 | -4.351% | 100%
| All Contracts | 138288700 | 136778386 | 143693530 | 143852069 | -400000 | 139949276 | 2.318% | 88.89% | 5756143 | 4.208% | 5404828 | 3.908% | 5899 | 1339 | 22.7% | 497 | 8.425% | 89 | 1.509% | 491 | 8.323% | 6479 | 9.832% | 8315 | 8421 | 6585 | 11.63% | 83.33%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 102419230 | 101817596 | 104762471 | 103870579 | 0 | 101551897.72 | -0.261% | 100% | 2185136 | 2.146% | 2343241 | 2.288% | 2905 | 448 | 15.42% | 218 | 7.504% | 41 | 1.411% | 128 | 4.406% | 3074 | 5.818% | 3740 | 3759 | 3093 | 6.472% | #VALUE!
| All Contracts | 102419230 | 101817596 | 104762471 | 103870579 | 0 | 101551897.72 | -0.261% | 100% | 2185136 | 2.146% | 2343241 | 2.288% | 2905 | 448 | 15.42% | 218 | 7.504% | 41 | 1.411% | 128 | 4.406% | 3074 | 5.818% | 3740 | 3759 | 3093 | 6.472% | 85.71%
Totals This Qtr | Central Let | 663118932 | 656304400 | 690485144 | 688224657 | 8259325 | 671976975 | 2.388% | 92.22% | 27642385 | 4.212% | 27366201 | 4.127% | 27457 | 5643 | 20.55% | 2230 | 8.122% | 866 | 3.154% | 1915 | 6.975% | 30238 | 10.13% | 38239 | 37518 | 29645 | 7.969% | 81.11%
| District Let | 462216838 | 458466399 | 478215418 | 473625658 | 755000 | 460979465.72 | 0.5481% | 93.24% | 15785697 | 3.443% | 15998582 | 3.461% | 20087 | 3440 | 17.13% | 1675 | 8.339% | 771 | 3.838% | 1132 | 5.635% | 21990 | 9.474% | 27143 | 26356 | 21241 | 5.745% | 93.24%
| All Contracts | 1125335770 | 1114770799 | 1168700562 | 1161850315 | 9014325 | 1132956440.72 | 1.631% | 92.68% | 43428082 | 3.896% | 43364783 | 3.853% | 47544 | 9083 | 19.1% | 3905 | 8.213% | 1637 | 3.443% | 3047 | 6.409% | 52228 | 9.852% | 65382 | 63874 | 50886 | 7.029% | 86.59%
Totals Previous Quarter | Central Let | 143695941 | 141621008 | 146862903 | 144533782 | 187125 | 142936574 | 0.9289% | 97.3% | 2338577 | 1.651% | 3166960 | 2.204% | 9272 | 1864 | 20.1% | 756 | 8.154% | 159 | 1.715% | 512 | 5.522% | 9943 | 7.237% | 12671 | 12406 | 9786 | 5.544% | 86.49%
| District Let | 90622297 | 89054613 | 95467568 | 93427417 | 75000 | 92238921.84 | 3.576% | 88.57% | 4390346 | 4.93% | 4845272 | 5.347% | 7423 | 1824 | 24.57% | 874 | 11.77% | 51 | 0.6871% | 549 | 7.396% | 8023 | 8.083% | 10759 | 10408 | 7710 | 3.866% | 97.14%
| All Contracts | 234318238 | 230675621 | 242330471 | 237961199 | 262125 | 235175495.84 | 1.951% | 93.06% | 6728923 | 2.917% | 8012232 | 3.419% | 16695 | 3688 | 22.09% | 1630 | 9.763% | 210 | 1.258% | 1061 | 6.355% | 17966 | 7.613% | 23430 | 22814 | 17496 | 4.798% | 91.67%
Totals Fiscal Year 2017/2018 | Central Let | 922272924 | 912201289 | 950316202 | 949875400 | 5416900 | 923867600 | 1.279% | 94.83% | 30812018 | 3.378% | 27856787 | 3.02% | 42758 | 8500 | 19.88% | 3456 | 8.083% | 1275 | 2.982% | 2225 | 5.204% | 46258 | 8.186% | 58215 | 59077 | 47121 | 10.2% | 87.93%
| District Let | 681923471 | 675586171 | 745680560 | 741535853 | 2689500 | 724953919.61 | 7.307% | 92.62% | 65007580 | 9.622% | 63710371 | 9.343% | 27803 | 4959 | 17.84% | 2334 | 8.395% | 695 | 2.5% | 2601 | 9.355% | 31099 | 11.85% | 38519 | 37890 | 30597 | 10.05% | 85.25%
| All Contracts | 1604196395 | 1587787460 | 1695996762 | 1691411253 | 8106400 | 1648821519.61 | 3.844% | 93.92% | 95819598 | 6.035% | 91567158 | 5.708% | 70561 | 13459 | 19.07% | 5790 | 8.206% | 1970 | 2.792% | 4826 | 6.839% | 77357 | 9.631% | 96734 | 96967 | 77718 | 10.14% | 86.82%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | 107% | 1 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | 95.53% | 1 | -2998654 | 649397 | 175 | 65 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43
| 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 104.9% | 1 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | 96.97% | 1 | -247700 | -332612 | 33 | 25 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 101.1% | 1 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | 98.52% | 1 | -6693381 | 1329652 | 198 | 68 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 95.5% | 1 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | 97.88% | 1 | -109936 | -74498 | 18 | 5 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM
| 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 98.96% | 1 | 4666 | 70668 | 64 | 24 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15
| 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 87.95% | 1 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | 95.18% | 1 | -45614 | 67704 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98
| 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 105.3% | 1 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 103.1% | 1 | 162288 | 192592 | 71 | 21 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28
| 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 69.9% | 1 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | 98.2% | 1 | -627624 | 220362 | 44 | 14 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | 162.4% | 0 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710516 | -83952 | 0 | -83952 | 626564 | 655747 | 92.29% | 1 | 29183 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM
| 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 87.67% | 1 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 101.9% | 1 | 42066 | 48270 | 30 | 23 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35
| 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 97.45% | 1 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 100.1% | 1 | 4205 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79
| 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 100% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59
| 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 138.4% | 0 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 105.7% | 1 | 527 | 16831 | 2 | 15 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 97.33% | 1 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM
| 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 99.13% | 1 | 302 | 0 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 98.96% | 1 | 908 | -6283 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM
| 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 98.89% | 1 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 109.8% | 1 | 92434 | 152724 | 22 | 11 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68
| 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 97.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 52.5% | 1 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 100% | 1 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM
| 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | 117.4% | 1 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | 91.9% | 1 | -1987458 | 665347 | 175 | 36 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 20 | 37 | 68 | 6205 | 7674 | 7573 | 90% | 18 | 101 | 186 | 0 | 1295 | 183 | 202783493 | 1142862 | 201640631 | 205783648 | 204114482 | -200077 | 4956000 | 4755923 | 208870405 | 196076702 | 100% | 20 | -12373788 | 3000154 | 931 | 364 | 0 | 85 | 1870093 | 21454 | 0 | 80 | 1390706 | 107796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -562153 | 0 | 0 | 0 | 95090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 2814785 | 148002
| 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 167.4% | 0 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | 104.4% | 1 | -658099 | 1523947 | 48 | 38 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 145% | 0 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 93.37% | 1 | 0 | 0 | 16 | 3 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09
| 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | 110.9% | 1 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 98.1% | 1 | 0 | 5910 | 22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11
| 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 112.7% | 1 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 101.6% | 1 | 81050 | 33269 | 18 | 6 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66
| 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 99% | 1 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 101.1% | 1 | 94256 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86
| 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 87.37% | 1 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 103.8% | 1 | 88492 | 0 | 11 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM
| 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | 99.62% | 1 | -50000 | 14694 | 8 | 1 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 84.71% | 1 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | 89.77% | 1 | -25000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 69.33% | 1 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 100% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM
| 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 85.33% | 1 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 97.5% | 1 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63
| 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 54.67% | 1 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 90.43% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 11 | 12 | 17 | 1976 | 2874 | 2767 | 81.82% | 9 | 107 | 12 | 0 | 735 | 163 | 32306993 | 401664 | 31905329 | 33884814 | 33375330 | -19008 | 75000 | 55992 | 33431322 | 32956111 | 100% | 11 | -469301 | 1577820 | 150 | 87 | 58 | 0 | 80041 | 0 | 0 | 3 | 17452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 163 | 1628702 | 0
| District 01 Totals |  |  |  |  | 31 | 49 | 85 | 8181 | 10548 | 10340 | 87.1% | 27 | 208 | 198 | 0 | 2030 | 346 | 235090486 | 1544526 | 233545960 | 239668462 | 237489812 | -219085 | 5031000 | 4811915 | 242301727 | 229032813 | 100% | 31 | -12843089 | 4577974 | 1081 | 451 | 58 | 85 | 1950134 | 21454 | 0 | 83 | 1408158 | 107796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -434985 | 0 | 0 | 0 | 95090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 435569 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 328 | 4443487 | 148002
| 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 111.9% | 1 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | 97.1% | 1 | -1247384 | 840958 | 89 | 80 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73
| 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | 141.9% | 0 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | 89.67% | 1 | -62293 | 0 | 12 | 15 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1
| 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 108.8% | 1 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | 100.1% | 1 | -366052 | 96491 | 80 | 54 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97
| 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 112.9% | 1 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | 106.5% | 1 | -214370 | 716585 | 179 | 57 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26
| 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 101.7% | 1 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | 98.56% | 1 | -162193 | 0 | 35 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36
| 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 99.64% | 1 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 91.44% | 1 | 151 | 36072 | 41 | 50 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79
| 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 99.47% | 1 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 100% | 1 | 4 | 0 | 13 | 6 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83
| 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 86.67% | 1 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 103.4% | 1 | 0 | 0 | 21 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13
| 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 100.7% | 1 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 102% | 1 | 44704 | 0 | 28 | 4 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12
| 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 110.6% | 1 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 103.9% | 1 | 26193 | 7048 | 42 | 26 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91
| 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 99.84% | 1 | 89 | 0 | 29 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75
| 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 98.44% | 1 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5815920 | 102.8% | 1 | 87174 | 51929 | 37 | 51 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2
| 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | 144.7% | 0 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1031421 | 97.79% | 1 | 15675 | 6408 | 22 | 24 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32
| 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 105.4% | 1 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 96.89% | 1 | 1714 | 4486 | 74 | 4 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75
| 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 79% | 1 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 95.24% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5
| 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 103.6% | 1 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 103.2% | 1 | 21810 | 0 | 16 | 5 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 16 | 23 | 33 | 4630 | 6148 | 6112 | 87.5% | 14 | 36 | 67 | 0 | 1177 | 341 | 83025503 | 1287129 | 81738373 | 84785480 | 83061630 | -114976 | 0 | -114976 | 82946654 | 81063445 | 100% | 16 | -1854778 | 1759977 | 725 | 434 | 5 | 117 | 1153977 | 16704 | 13 | 127 | 939017 | 20522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 8 | 63758 | 14665 | 0 | 2 | 22214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17449 | 0 | 0 | 44 | 50000 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 18 | 341 | 2362861 | 201848
| 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 164.7% | 0 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | 118.1% | 0 | -412 | 1525306 | 47 | 79 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43
| 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 106.2% | 1 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | 111.7% | 0 | -22727 | 248912 | 44 | 63 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47
| 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 100.7% | 1 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 86.65% | 1 | 35717 | -98576 | 61 | 55 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26
| 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 98.89% | 1 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 100.1% | 1 | 0 | 28412 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894
| 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 99.6% | 1 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 97.73% | 1 | 121 | 4326 | 20 | 40 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23
| 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 97.73% | 1 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 104.5% | 1 | 30133 | 59347 | 55 | 63 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25
| 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 103.1% | 1 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 104.1% | 1 | 66 | 0 | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65
| 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 181.6% | 0 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 127.5% | 0 | 175603 | 494858 | 26 | 20 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55
| 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 103.4% | 1 | 78162 | 0 | 27 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44
| 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 105.6% | 1 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 100.9% | 1 | 0 | 12377 | 10 | 5 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97
| 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 99.77% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 11 | 17 | 24 | 2655 | 3814 | 3750 | 81.82% | 9 | 64 | 0 | 0 | 713 | 446 | 34379704 | 540058 | 33839646 | 36654663 | 36492201 | 0 | 0 | 0 | 36492201 | 36646926 | 72.73% | 8 | 296663 | 2274962 | 335 | 378 | 0 | 127 | 563693 | 0 | 0 | 319 | 1784250 | 322078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446 | 2366386 | 322078
| District 02 Totals |  |  |  |  | 27 | 40 | 57 | 7285 | 9962 | 9862 | 85.19% | 23 | 100 | 67 | 0 | 1890 | 787 | 117405207 | 1827187 | 115578019 | 121440143 | 119553831 | -114976 | 0 | -114976 | 119438855 | 117710371 | 88.89% | 24 | -1558115 | 4034939 | 1060 | 812 | 5 | 244 | 1717670 | 16704 | 13 | 446 | 2723267 | 342600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 8 | 82203 | 14665 | 0 | 2 | 22214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17449 | 0 | 0 | 44 | 50000 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 18 | 787 | 4729247 | 523926
| 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 235.5% | 0 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 125.8% | 0 | 1482 | 446147 | 119 | 44 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15
| 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 112% | 1 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 87% | 1 | 0 | -1624 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM
| 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 173.1% | 0 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | 138.9% | 0 | -25384 | 2617138 | 303 | 81 | 65 | 20 | 532799 | 13449 | 90 | 4 | 491634 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2617725 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94
| 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 127% | 0 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 100% | 1 | 152 | 75332 | 76 | 23 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13
| 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 120.4% | 0 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 107.4% | 1 | 7457 | 20691 | 171 | 28 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24
| 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 109.5% | 1 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 108.2% | 1 | 123160 | 15763 | 77 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43
| 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 98.1% | 1 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 97.03% | 1 | 0 | 1601 | 48 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-03-19 | QTR3 | 17/18 | 308 | 819000
| 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 141.7% | 0 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 102.9% | 1 | 0 | 28099 | 33 | 4 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM
| 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | 122.2% | 0 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 98.39% | 1 | 13058 | -7125 | 22 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54
| 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 98.46% | 1 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 97.09% | 1 | 0 | -21294 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM
| 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 99.26% | 1 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 107% | 1 | 32427 | 14433 | 38 | 21 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46
| 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 119.4% | 1 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 101.4% | 1 | 22904 | 0 | 76 | 16 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 12 | 20 | 50 | 1995 | 3998 | 3999 | 50% | 6 | -1 | 18 | 0 | 1835 | 168 | 33867739 | 481804 | 33385937 | 37056899 | 38228615 | -70312 | 0 | -70312 | 38158303 | 38333557 | 83.33% | 10 | 175256 | 3189161 | 972 | 303 | 65 | 36 | 581183 | 13449 | 317 | 34 | 801366 | 355653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 95 | 1620673 | 428480 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 16052 | 16052 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 168 | 3223058 | 833852
| 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 119.4% | 1 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | 102.6% | 1 | -981850 | 3971426 | 99 | 61 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
| 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 97.78% | 1 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 103.4% | 1 | 130 | 0 | 10 | 0 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000
| 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 118.3% | 1 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 106.1% | 1 | 0 | 26519 | 71 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72
| 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 91.67% | 1 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 106.1% | 1 | 81564 | 0 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17
| 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 99.33% | 1 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 102.1% | 1 | 10099 | 127524 | 43 | 37 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000
| 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 110% | 1 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 101.6% | 1 | 945 | 3000 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64
| 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 95.71% | 1 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 98.08% | 1 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 7 | 8 | 12 | 1878 | 2536 | 2506 | 100% | 7 | 30 | 0 | 0 | 621 | 37 | 127115898 | 407494 | 126708404 | 131244367 | 130953809 | 0 | 0 | 0 | 130953809 | 130064697 | 100% | 7 | -889112 | 4128469 | 277 | 138 | 199 | 6 | -802697 | 236 | 0 | 8 | 168421 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 23 | 66871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 206 | 37 | 4228824 | 4950453
| District 03 Totals |  |  |  |  | 19 | 28 | 62 | 3873 | 6534 | 6505 | 68.42% | 13 | 29 | 18 | 0 | 2456 | 205 | 160983637 | 889298 | 160094341 | 168301266 | 169182424 | -70312 | 0 | -70312 | 169112112 | 168398254 | 89.47% | 17 | -713856 | 7317630 | 1249 | 441 | 264 | 42 | -221514 | 13685 | 317 | 42 | 969787 | 355870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 158 | 118 | 1687544 | 428480 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 231478 | 5684 | 0 | 0 | 4966052 | 4966052 | 20 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 766 | 205 | 7451882 | 5784305
| 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 109.8% | 1 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 88.9% | 1 | 0 | 4802 | 135 | 26 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59
| 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 116% | 1 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | 104.2% | 1 | -14505 | 252534 | 101 | 41 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 116% | 1 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | 107.3% | 1 | -7370 | 325031 | 104 | 27 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4
| 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 105.6% | 1 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 99.1% | 1 | 4036 | 70900 | 32 | 24 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM
| 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 112.1% | 1 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | 96.73% | 1 | -10793 | 15092 | 66 | 22 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97
| 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 118.6% | 1 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 97.21% | 1 | 0 | 0 | 32 | 25 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66
| 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 99.9% | 1 | 985 | 4306 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15
| 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 98.57% | 1 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 93.86% | 1 | 981 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46
| 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 79.2% | 1 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | 105.3% | 1 | -34322 | 31168 | 30 | 14 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 95.84% | 1 | 10 | 0 | 7 | 18 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07
| 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | 104% | 1 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 96.79% | 1 | 0 | 0 | 28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1
| 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 80% | 1 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 94.93% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 12 | 33 | 21 | 2968 | 4113 | 4038 | 100% | 12 | 75 | 4 | 0 | 948 | 197 | 24680818 | 489232 | 24191588 | 25384651 | 24474028 | 0 | 37125 | 37125 | 24511153 | 24322963 | 100% | 12 | -60978 | 703833 | 625 | 251 | 10 | 120 | 457541 | 270087 | 34 | 48 | 249708 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | 0 | 29 | 14562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 72 | 197 | 737319 | 341859
| 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 95.19% | 1 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | 102% | 1 | -2197408 | 3131122 | 99 | 57 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82927 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 102.6% | 1 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | 100% | 1 | -85027 | 475368 | 293 | 39 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75
| 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 117.3% | 1 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 101.6% | 1 | 93460 | 150444 | 82 | 28 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15
| 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 107.2% | 1 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 95.22% | 1 | 26852 | 127760 | 93 | 24 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01
| 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 93.77% | 1 | 1375 | 0 | 46 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29
| 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 96.99% | 1 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 100.1% | 1 | 666 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22
| 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 98.08% | 1 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 98.62% | 1 | 5073 | 0 | 13 | 1 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43
| 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 104.5% | 1 | 42636 | 74001 | 9 | 5 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 8 | 14 | 32 | 3379 | 4325 | 4241 | 100% | 8 | 84 | 0 | 0 | 861 | 85 | 103680052 | 543532 | 103136520 | 107638747 | 106621950 | 0 | 500000 | 500000 | 107121950 | 104523191 | 100% | 8 | -2112373 | 3958695 | 639 | 196 | 0 | 85 | 2195138 | 558253 | 19 | 0 | 1530063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 154579 | 11004 | 0 | 0 | 66256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | -82927 | 0 | 26 | 85 | 3863217 | 569257
| District 04 Totals |  |  |  |  | 20 | 47 | 53 | 6347 | 8438 | 8279 | 100% | 20 | 159 | 4 | 0 | 1809 | 282 | 128360870 | 1032764 | 127328108 | 133023398 | 131095978 | 0 | 537125 | 537125 | 131633103 | 128846154 | 100% | 20 | -2173351 | 4662528 | 1264 | 447 | 10 | 205 | 2652679 | 828340 | 53 | 48 | 1779771 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 171967 | 11004 | 0 | 29 | 80818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | -84809 | 0 | 98 | 282 | 4600536 | 911116
| 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 144.9% | 0 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | 112.7% | 0 | -1059964 | 5141650 | 119 | 57 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -230251 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 124.6% | 0 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | 113.3% | 0 | -1114008 | 4323245 | 93 | 58 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -110308 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55
| 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 79.21% | 1 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | 100.3% | 1 | -956254 | 370838 | 56 | 31 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | -130768 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 105.2% | 1 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 101.9% | 1 | 0 | 56481 | 144 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05
| 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 135.2% | 0 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 97.3% | 1 | 6944 | 115263 | 65 | 40 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47
| 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 110% | 1 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 107.7% | 1 | 13997 | 180307 | 159 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 |  | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12
| 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | 110% | 1 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 100.5% | 1 | 40280 | 52747 | 216 | 28 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772
| 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | 111.3% | 1 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 114% | 0 | 0 | 0 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-07-23 | QTR1 | 18/19 | 514 | 295435
| 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 163.1% | 0 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 190.6% | 0 | 1313 | 1131728 | 26 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65
| 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 89.58% | 1 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 106.4% | 1 | 504 | 5429 | 8 | 13 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 515 | 980597
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 10 | 36 | 76 | 3800 | 5745 | 5556 | 60% | 6 | 189 | 31 | 0 | 1239 | 706 | 117630752 | 757500 | 116873252 | 129008448 | 129321661 | -72092 | 986200 | 914108 | 130235769 | 126886969 | 60% | 6 | -3067188 | 11377688 | 912 | 327 | 0 | 12 | 1829897 | 142753 | 0 | 466 | 6517368 | 2789340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 83 | 1650095 | 5853 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 175105 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 0 | 587 | 10459050 | 2981435
| 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 117.7% | 1 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | 99.18% | 1 | -89138 | 204028 | 174 | 49 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 78.16% | 1 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | 101.7% | 1 | -4400 | 21013 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83
| 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 102.9% | 1 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 108.9% | 1 | 1238 | 76790 | 49 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25
| 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | 105.9% | 1 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 98.88% | 1 | 26994 | 156917 | 98 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03
| 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 111.3% | 1 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 101.3% | 1 | 5094 | 12031 | 26 | 24 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7
| 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 118.3% | 1 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 113.7% | 0 | 64762 | 233345 | 64 | 20 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928
| 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 105.5% | 1 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 103.2% | 1 | 0 | 0 | 60 | 6 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85
| 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 111.6% | 1 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 104.3% | 1 | 0 | 76090 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 98.67% | 1 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 103.6% | 1 | 13589 | 81060 | 48 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27
| 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 102.6% | 1 | 9051 | 55693 | 56 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1
| 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 41.82% | 1 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 78.71% | 1 | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922
| 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 65.88% | 1 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 97.44% | 1 | 1173 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4
| 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 98.33% | 1 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 100% | 1 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2
| 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 99.55% | 1 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 100.6% | 1 | 0 | 0 | 28 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 14 | 24 | 27 | 3800 | 5070 | 4731 | 100% | 14 | 339 | 10 | 0 | 1045 | 225 | 30608596 | 599000 | 30009596 | 31525563 | 30948439 | -15840 | 0 | -15840 | 30932599 | 30645983 | 92.86% | 13 | 28363 | 916967 | 693 | 352 | 0 | 74 | -20189 | 0 | 0 | 63 | 397662 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 319393 | 34307 | 0 | 0 | 26561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 723428 | 35185
| District 05 Totals |  |  |  |  | 24 | 60 | 103 | 7600 | 10815 | 10287 | 83.33% | 20 | 528 | 41 | 0 | 2284 | 931 | 148239348 | 1356500 | 146882848 | 160534011 | 160270100 | -87932 | 986200 | 898268 | 161168368 | 157532952 | 79.17% | 19 | -3038825 | 12294655 | 1605 | 679 | 0 | 86 | 1809708 | 142753 | 0 | 529 | 6915030 | 2790218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 171 | 1969488 | 40160 | 0 | 0 | 34220 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 175105 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 0 | 812 | 11182478 | 3016620
| 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 71.85% | 1 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | 106.2% | 1 | -258037 | 417799 | 96 | 21 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 |  | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 93.9% | 1 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | 104.3% | 1 | -1419938 | 811402 | 61 | 34 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 90.38% | 1 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | 108.1% | 1 | -576452 | 893046 | 79 | 21 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 |  | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 78.57% | 1 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | 103.2% | 1 | -101955 | 0 | 31 | 6 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 62.26% | 1 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | 96.92% | 1 | -136676 | 28195 | 44 | 25 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 118.3% | 1 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | 99.23% | 1 | -29328 | 147817 | 57 | 20 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35
| 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 97.54% | 1 | 5234 | 51632 | 63 | 25 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89
| 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 103.5% | 1 | 5618 | 63649 | 15 | 17 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55
| 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 92.57% | 1 | 69 | 0 | 48 | 8 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 |  | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5
| 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 99.63% | 1 | 2695 | 0 | 57 | 8 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 10 | 42 | 35 | 3339 | 4202 | 3681 | 100% | 10 | 521 | 0 | 0 | 863 | 0 | 74337666 | 1416194 | 72921472 | 76751207 | 76959548 | 0 | 2680000 | 2680000 | 79639548 | 76989213 | 100% | 10 | -2508770 | 2413540 | 551 | 185 | 106 | 0 | 1474314 | 0 | 21 | 0 | 804798 | 18771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415425 | 65328 | 0 | 0 | 63589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 2758126 | 84099
| 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 97.37% | 1 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | 69.81% | 1 | -593229 | 49068 | 214 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069
| 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 115.8% | 1 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 94.72% | 1 | 30910 | 125102 | 67 | 30 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65
| 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 102.9% | 1 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | 0% | 1 | -6008075 | 89950 | 52 | 49 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
| 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 77.23% | 1 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | 100% | 1 | -148006 | 51328 | 26 | 9 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 103.2% | 1 | 1161 | 0 | 13 | 7 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65
| 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 98.89% | 1 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 100% | 1 | 0 | 0 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5
| 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 98.05% | 1 | 9983 | 0 | 44 | 5 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940
| 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 98.89% | 1 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 93.76% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 8 | 23 | 11 | 2115 | 2828 | 2740 | 100% | 8 | 88 | 0 | 0 | 699 | 14 | 20210626 | 386557 | 19824069 | 20526074 | 19575974 | 1584 | 180000 | 181584 | 19757558 | 12945510 | 100% | 8 | -6707256 | 315448 | 486 | 175 | 0 | 0 | 41364 | 4391 | 0 | 0 | 131885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101674 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 321047 | 4391
| District 06 Totals |  |  |  |  | 18 | 65 | 46 | 5454 | 7030 | 6421 | 100% | 18 | 609 | 0 | 0 | 1562 | 14 | 94548292 | 1802751 | 92745541 | 97277281 | 96535522 | 1584 | 2860000 | 2861584 | 99397106 | 89934723 | 100% | 18 | -9216026 | 2728988 | 1037 | 360 | 106 | 0 | 1515678 | 4391 | 21 | 0 | 936683 | 18771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 517099 | 65328 | 0 | 0 | 109713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 14 | 3079173 | 88490
| 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | 128.1% | 0 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | 107.9% | 1 | -544763 | 2295083 | 191 | 91 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14
| 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 105.4% | 1 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | 97.63% | 1 | -758630 | -138845 | 145 | 61 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST
| 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | 124.5% | 0 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | 99.61% | 1 | -887228 | 212174 | 208 | 57 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 |  | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03
| 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 117.4% | 1 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | 102.6% | 1 | -819849 | 1664895 | 92 | 66 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 0 | -113880 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 119.6% | 1 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 107.2% | 1 | 18982 | 298860 | 167 | 33 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22
| 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 120.7% | 0 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 111% | 0 | 25484 | 558900 | 42 | 15 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS
| 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 119.4% | 1 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 105% | 1 | 44854 | 30781 | 47 | 20 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5
| 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 99.68% | 1 | 6464 | 0 | 31 | 18 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000
| 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 98% | 1 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 97.78% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 799 | 446330
| 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 32.5% | 1 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 82.71% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 10 | 45 | 79 | 4520 | 6359 | 6559 | 70% | 7 | -200 | 255 | 0 | 1382 | 457 | 126792961 | 1239815 | 125553147 | 131714811 | 132064693 | -194668 | -400000 | -594668 | 131470025 | 128304126 | 90% | 9 | -2914686 | 4921848 | 927 | 366 | 43 | 40 | 1851561 | 125339 | 14 | 217 | 2918623 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 44209 | 0 | 32 | 0 | 75559 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 409440 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 457 | 5287186 | 947114
| 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 90.54% | 1 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | 103.6% | 1 | -54636 | 367480 | 145 | 40 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000
| 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 90% | 1 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | 94.1% | 1 | -18692 | 37019 | 42 | 23 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200
| 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 115% | 1 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 113.6% | 0 | 25327 | -19 | 20 | 0 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000
| 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 108.1% | 1 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 109% | 1 | 0 | 78500 | 39 | 28 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM
| 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 92.5% | 1 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 94.2% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 |  | 2018-09-12 | QTR1 | 18/19 | 796 | 320000
| 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 94% | 1 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 103.9% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 796 | 310000
| 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 68.33% | 1 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 102.4% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 796 | 225000
| 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | 101.8% | 1 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 98.71% | 1 | 0 | 0 | 155 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 8 | 10 | 6 | 1379 | 1956 | 1862 | 100% | 8 | 94 | 7 | 0 | 543 | 34 | 11495739 | 270500 | 11225239 | 11978719 | 11787376 | -19677 | 0 | -19677 | 11767699 | 11645150 | 87.5% | 7 | -48001 | 482980 | 412 | 131 | 0 | 9 | 366369 | 18033 | 0 | 25 | 96879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 468957 | 18033
| District 07 Totals |  |  |  |  | 18 | 55 | 85 | 5899 | 8315 | 8421 | 83.33% | 15 | -106 | 262 | 0 | 1925 | 491 | 138288700 | 1510315 | 136778386 | 143693530 | 143852069 | -214345 | -400000 | -614345 | 143237724 | 139949276 | 88.89% | 16 | -2962687 | 5404828 | 1339 | 497 | 43 | 49 | 2217930 | 143372 | 14 | 242 | 3015502 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 44190 | 0 | 32 | 0 | 81288 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 409440 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 491 | 5756143 | 965147
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 105.2% | 1 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | 100% | 1 | -1273624 | 1280759 | 147 | 47 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35903 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 99.36% | 1 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | 97.16% | 1 | -695637 | 0 | 56 | 25 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR
| 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 108.6% | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 8969452.72 | 108.2% | 1 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78
| 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 101% | 1 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 99.06% | 1 | 64151 | -44570 | 40 | 28 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104904 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 |  | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64
| 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 258 | 111.9% | 1 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 103% | 1 | 2 | 0 | 78 | 29 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07
| 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | 142.8% | 0 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 99.9% | 1 | 0 | 9613 | 32 | 17 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31
| 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 107.1% | 1 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 92.96% | 1 | 306 | 51808 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 7 | 14 | 28 | 2905 | 3740 | 3759 | #VALUE! | 6 | 16 | 26 | 0 | 707 | 128 | 102419230 | 601634 | 101817596 | 104762471 | 103870579 | -66684 | 0 | -66684 | 103803895 | 101551897.72 | 100% | 7 | -1910910 | 2343241 | 448 | 218 | 0 | 0 | 926490 | 0 | 0 | 38 | 593120 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56 | 516915 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 41 | 128 | 2185136 | 178000
| District 08 Totals |  |  |  |  | 7 | 14 | 28 | 2905 | 3740 | 3759 | 85.71% | 6 | 16 | 26 | 0 | 707 | 128 | 102419230 | 601634 | 101817596 | 104762471 | 103870579 | -66684 | 0 | -66684 | 103803895 | 101551897.72 | 100% | 7 | -1910910 | 2343241 | 448 | 218 | 0 | 0 | 926490 | 0 | 0 | 38 | 593120 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56 | 516915 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 41 | 128 | 2185136 | 178000
| Statewide Central Let Contracts SubTotal |  |  |  |  | 90 | 236 | 362 | 27457 | 38239 | 37518 | 81.11% | 73 | 721 | 561 | 0 | 8739 | 2052 | 663118932 | 6814536 | 656304400 | 690485144 | 688224657 | -652125 | 8259325 | 7607200 | 695831857 | 671976975 | 92.22% | 83 | -22604932 | 27366201 | 5643 | 2230 | 229 | 410 | 9218566 | 589786 | 399 | 972 | 13621586 | 3783453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83150 | 0 | 158 | 208 | 3249395 | 514326 | 32 | 31 | 303888 | 18276 | 0 | 0 | -1650 | 0 | 0 | 47 | 378144 | 49174 | 0 | 44 | 867300 | 16052 | 48 | 213 | 586678 | 567144 | 0 | 0 | -40079 | 0 | 0 | -10 | -624600 | 0 | 866 | 1915 | 27642385 | 5538209
| Statewide District Let Contracts SubTotal |  |  |  |  | 74 | 122 | 157 | 20087 | 27143 | 26356 | 93.24% | 69 | 822 | 55 | 0 | 5924 | 1132 | 462216838 | 3750439 | 458466399 | 478215418 | 473625658 | -119625 | 755000 | 635375 | 474261033 | 460979465.72 | 93.24% | 69 | -11811927 | 15998582 | 3440 | 1675 | 257 | 301 | 3350209 | 580913 | 19 | 456 | 4719732 | 501173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 48 | 181 | 1305026 | 45311 | 0 | 0 | 154242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128121 | 0 | 0 | 34 | 6142750 | 4950000 | 440 | 160 | 416817 | 0 | 7 | 0 | -782 | 0 | 0 | 0 | -440413 | 0 | 771 | 1132 | 15785697 | 6077397
| Statewide Totals |  |  |  |  | 164 | 358 | 519 | 47544 | 65382 | 63874 | 86.59% | 142 | 1543 | 616 | 0 | 14663 | 3184 | 1125335770 | 10564975 | 1114770799 | 1168700562 | 1161850315 | -771750 | 9014325 | 8242575 | 1170092890 | 1132956440.72 | 92.68% | 152 | -34416859 | 43364783 | 9083 | 3905 | 486 | 711 | 12568775 | 1170699 | 418 | 1428 | 18341318 | 4284626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93150 | 0 | 206 | 389 | 4554421 | 559637 | 32 | 31 | 458130 | 18276 | 0 | 0 | -1650 | 0 | 0 | 47 | 506265 | 49174 | 0 | 78 | 7010050 | 4966052 | 488 | 373 | 1003495 | 567144 | 7 | 0 | -40861 | 0 | 0 | -10 | -1065013 | 0 | 1637 | 3047 | 43428082 | 11615606

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1K75 | 20121435201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2012-06-21 | 21206552 | 22730499 | 22650387 | 1523947.09 | 0 | 21992288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1P47 | 43771415201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-10-19 | 161810 | 161810 | 145518 | 0 | 0 | 145518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145518 | 145518 | 0 | 119062
1 | E1Q20 | 43979815201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2017-03-16 | 551623 | 557534 | 539909 | 5910.12 | -19008 | 520901 | -19008 | 0 | 0 | 0 | 0 | 0 | -19008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19008 | 520901 | 520901 | 0 | 682344
1 | E1Q46 | 43659915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-20 | 2486667 | 2519936 | 2394841 | 33269.19 | 0 | 2475891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 2833103
1 | E1Q75 | 43659815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-09-21 | 3257627 | 3257627 | 3147613 | 0 | 0 | 3241869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 3831011
1 | E1Q76 | 43494115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 3162332 | 3162332 | 3141539 | 0 | 0 | 3230031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 3398633 | B0 | ACC - LUMP SUM
1 | E1R00 | 43798415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 399878 | 414572 | 373225 | 14694.4 | 50000 | 373225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 410605 | B1 | ACC - NO EXCUSE BONUS
1 | E1R01 | 43668415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-01-25 | 367307 | 367307 | 318382 | 0 | 25000 | 318382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 312418 | B1 | ACC - NO EXCUSE BONUS
1 | E1R02 | 44026315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-11-16 | 253030 | 253030 | 240240 | 0 | 0 | 240240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240240 | 240240 | 0 | 210004 | B0 | ACC - LUMP SUM
1 | E1R04 | 44035915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-01-18 | 356611 | 356611 | 333569 | 0 | 0 | 333569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333569 | 333569 | 0 | 390669
1 | E1R10 | 44124915201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-04-19 | 103556 | 103556 | 90107 | 0 | 0 | 94096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90107 | 94096 | 3989 | 92976
1 | T1550 | 41304445201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2013-06-19 | 35638696 | 36288093 | 36921189 | 649397.13 | -20000 | 33902534 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 36725854
1 | T1606 | 19801745201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2015-06-17 | 16630324 | 16297713 | 16277472 | -332611.69 | -39000 | 15990772 | 0 | 0 | 0 | 0 | 0 | -39000 | -39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39000 | 16238472 | 15990772 | -247700 | 16471202 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1621 | 20103245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-05-27 | 74506000 | 75835652 | 75066323 | 1329652.15 | 4948000 | 73395413 | 0 | 0 | 0 | 0 | 0 | -52000 | -52000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 4948000 | 80014323 | 73395413 | -6618910 | 93729882 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
1 | T1623 | 43127815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3845363 | 3770865 | 3824811 | -74498 | 0 | 3725877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824811 | 3725877 | -98934 | 4062053 | B0 | ACC - LUMP SUM
1 | T1653 | 43317315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 3821588 | 3892256 | 3742414 | 70667.91 | 0 | 3747080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742414 | 3747080 | 4666 | 2964599
1 | T1660 | 43161915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-09-28 | 2357000 | 2424704 | 2337783 | 67704.15 | 0 | 2292169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337783 | 2292169 | -45614 | 3040685
1 | T1672 | 43660015201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 5457714 | 5650306 | 5444515 | 192591.74 | 0 | 5606803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5444515 | 5606803 | 162288 | 5914612
1 | T1673 | 42063335201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-12-07 | 14067161 | 14287522 | 13878587 | 220361.5 | 550000 | 13800963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000 | 550000 | 14428587 | 13800963 | -627624 | 16781376 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1674 | 43450515201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 739854 | 739854 | 710516 | 0 | -83952 | 655747 | -83952 | 0 | 0 | 0 | 0 | 0 | -83952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83952 | 626564 | 655747 | 29183 | 559471 | B0 | ACC - LUMP SUM
1 | T1678 | 43492915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 7590540 | 7638810 | 7645659 | 48270.16 | 0 | 7687725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7645659 | 7687725 | 42066 | 9127943
1 | T1683 | 43177215201 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1414597 | 1414597 | 1411808 | 0 | 0 | 1416013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 1198143
1 | T1685 | 44011715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 165758 | 165758 | 159130 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159130 | 159130 | 0 | 163746
1 | T1686 | 43318815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 304735 | 321566 | 321566 | 16831.45 | 0 | 322093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321566 | 322093 | 527 | 339200 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1688 | 43498415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 440840 | 440840 | 440840 | 0 | 0 | 440840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440840 | 440840 | 0 | 446099 | B0 | ACC - LUMP SUM
1 | T1692 | 43911115201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 548549 | 548549 | 543483 | 0 | 0 | 543785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543483 | 543785 | 302 | 566923 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1694 | 43513615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 548555 | 542272 | 512417 | -6283.3 | 0 | 513325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512417 | 513325 | 908 | 613009 | B0 | ACC - LUMP SUM
1 | T1698 | 43656715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-10-25 | 3413203 | 3565928 | 3599216 | 152724.34 | 0 | 3691649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 3320587
1 | T1703 | 43668315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 430933 | 430933 | 404140 | 0 | 0 | 404140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404140 | 404140 | 0 | 395408 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1716 | 43506315201 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 172083 | 172083 | 163237 | 0 | 0 | 163237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1A07 | 19389825201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2014-09-24 | 30690000 | 31355347 | 30709376 | 665347.31 | -599125 | 28122793 | 0 | 0 | 0 | 0 | 0 | -5125 | -5125 | 0 | 0 | 0 | 0 | -594000 | 0 | -594000 | -599125 | 30110251 | 28122793 | -1987458 | 31874470 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | E2T36 | 42442415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-05-13 | 10725121 | 12250426 | 12633691 | 1525305.59 | 0 | 12633279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12633691 | 12633279 | -412 | 11100158
2 | E2U34 | 43025815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-20 | 4266548 | 4515459 | 4762225 | 248911.81 | 0 | 4739499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762225 | 4739499 | -22727 | 3812868
2 | E2V29 | 43230815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-21 | 4657688 | 4559112 | 3935337 | -98576.18 | 0 | 3971054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | 3479383
2 | E2V63 | 43860115201 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-05-17 | 1160401 | 1188813 | 1137166 | 28412.16 | 0 | 1137166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 567894
2 | E2V64 | 43075815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 2185756 | 2190082 | 2087115 | 4326.32 | 0 | 2087236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 1534480
2 | E2V65 | 43432315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 3583873 | 3643220 | 3692989 | 59346.81 | 0 | 3723122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3692989 | 3723122 | 30133 | 3819418
2 | E2W07 | 43240515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-15 | 1148442 | 1148442 | 1142933 | 0 | 0 | 1143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 1300556
2 | E2W74 | 43430315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2821185 | 3316043 | 3357671 | 494858.16 | 0 | 3533274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 2864650
2 | E2W87 | 43616615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 2286714 | 2286714 | 2234139 | 0 | 0 | 2316470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2234139 | 2316470 | 82331 | 2718058
2 | E2W97 | 43859915201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 876044 | 888420 | 862161 | 12376.67 | 0 | 862161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862161 | 862161 | 0 | 586122
2 | E2W98 | 43860015201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 667932 | 667932 | 646774 | 0 | 0 | 646774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646774 | 646774 | 0 | 484902
2 | T2534 | 21071235201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 18473682 | 19314640 | 18859990 | 840958.13 | 0 | 17612606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 20202367
2 | T2547 | 42975025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1879929 | 1879929 | 1845519 | 0 | -97552 | 1685674 | -97552 | 0 | 0 | 0 | 0 | 0 | -97552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97552 | 1747967 | 1685674 | -62293 | 1922742
2 | T2568 | 21002845201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 13869804 | 13966295 | 14129834 | 96491.28 | 0 | 13763782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14129834 | 13763782 | -366052 | 14411194
2 | T2569 | 42870115201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 9199000 | 9915585 | 9871416 | 716584.65 | 0 | 9657046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 9784025
2 | T2596 | 43055615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 4955711 | 4955711 | 4972503 | 0 | 0 | 4810311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 4219707
2 | T2624 | 21327285201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 11345332 | 11381404 | 10274352 | 36071.98 | 0 | 10274503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 11100491
2 | T2633 | 42890015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-07-27 | 1780206 | 1780206 | 1730267 | 0 | 0 | 1730271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 1648989
2 | T2643 | 43434015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-12-07 | 1483252 | 1483252 | 1482220 | 0 | 0 | 1482220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 1682912
2 | T2648 | 43231015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1797592 | 1797592 | 1737333 | 0 | 0 | 1782037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 1880670
2 | T2655 | 43231215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 6450313 | 6457361 | 6610843 | 7048 | 0 | 6637036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6610843 | 6637036 | 26193 | 6643070
2 | T2659 | 43432715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | 2042000 | 2042000 | 1988747 | 0 | 0 | 1988836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 2336444
2 | T2665 | 43056015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-05-24 | 5734638 | 5786567 | 5728746 | 51928.64 | 0 | 5815920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5728746 | 5815920 | 87174 | 4851775
2 | T2666 | 43543915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 1101105 | 1107513 | 1035052 | 6407.67 | -17424 | 1033303 | -17424 | 0 | 0 | 0 | 0 | 0 | -17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17424 | 1017628 | 1033303 | 15675 | 969731
2 | T2671 | 43601015201 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 928314 | 932800 | 849315 | 4485.92 | 0 | 851029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 1119164
2 | T2674 | 43335915201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-08-30 | 360929 | 360929 | 343649 | 0 | 0 | 343649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343649 | 343649 | 0 | 413832
2 | T2676 | 43617515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 1623696 | 1623696 | 1601844 | 0 | 0 | 1623655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 1682997
3 | E3L23 | 22066425201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2013-06-06 | 118555712 | 122527138 | 122423398 | 3971426.3 | 0 | 121441548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
3 | E3P21 | 42358825201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 957789 | 957789 | 938474 | 0 | 0 | 938604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938474 | 938604 | 130 | 1276000
3 | E3Q40 | 43375215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 782920 | 809439 | 800466 | 26519.13 | 0 | 800466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800466 | 800466 | 0 | 616285
3 | E3Q60 | 43625715201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 3348662 | 3348662 | 3418381 | 0 | 0 | 3499945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 4130313
3 | E3Q73 | 43966115201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 2101129 | 2228653 | 2084234 | 127524 | 0 | 2094333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 2065000
3 | E3Q80 | 44014815201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-11-09 | 673414 | 676414 | 651186 | 3000 | 0 | 652131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651186 | 652131 | 945 | 670663
3 | E3R24 | 43626915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-08 | 696272 | 696272 | 637670 | 0 | 0 | 637670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637670 | 637670 | 0 | 945342
3 | T3481 | 42884615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-10-28 | 2080005 | 2526152 | 2551459 | 446147.09 | 0 | 2552942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 1782971
3 | T3538 | 43357615201 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2015-06-17 | 90288 | 88663 | 74180 | -1624.32 | 0 | 74180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74180 | 74180 | 0 | 110499 | B0 | ACC - LUMP SUM
3 | T3559 | 22247625201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-03 | 8545785 | 11162923 | 11805411 | 2617137.98 | -19500 | 11760527 | 0 | 0 | 0 | 0 | 0 | -19500 | -19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19500 | 11785911 | 11760527 | -25384 | 7955703
3 | T3565 | 43046915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 2384550 | 2459882 | 2385269 | 75331.94 | 0 | 2385420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 1900106
3 | T3568 | 41347915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-09-28 | 3041965 | 3062656 | 3259199 | 20690.94 | 0 | 3266655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 3211894
3 | T3615 | 42695015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 8847725 | 8863488 | 9356628 | 15762.61 | 0 | 9479788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 8456773
3 | T3636 | 43188325201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 723562 | 725163 | 672253 | 1600.5 | -7800 | 664453 | 0 | 0 | 0 | 0 | 0 | -7800 | -7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7800 | 664453 | 664453 | 0 | 819000
3 | T3641 | 43255115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 526927 | 555025 | 528915 | 28098.65 | -14500 | 514415 | 0 | 0 | 0 | 0 | 0 | -14500 | -14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14500 | 514415 | 514415 | 0 | 561927 | B0 | ACC - LUMP SUM
3 | T3644 | 43671915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1719994 | 1712869 | 1658491 | -7124.92 | -28512 | 1643036 | -28512 | 0 | 0 | 0 | 0 | 0 | -28512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28512 | 1629979 | 1643036 | 13058 | 1688041
3 | T3647 | 43626015201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 741004 | 719710 | 672328 | -21294.4 | 0 | 672328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672328 | 672328 | 0 | 1013516 | B0 | ACC - LUMP SUM
3 | T3650 | 43014645201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3298431 | 3312865 | 3444996 | 14433.44 | 0 | 3477423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 4395538
3 | T3651 | 43014665201 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1867503 | 1867503 | 1819486 | 0 | 0 | 1842390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 2105531
4 | E4N44 | 42170765201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-07-24 | 74960000 | 78091122 | 78080272 | 3131121.83 | 500000 | 76382864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 78580272 | 76382864 | -2197408 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q93 | 43120415201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-04-03 | 9297344 | 9772712 | 9607342 | 475367.61 | 0 | 9522316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9607342 | 9522316 | -85027 | 9241086
4 | E4R63 | 43060215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-05-06 | 9397416 | 9547860 | 9424445 | 150444.28 | 0 | 9517905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9424445 | 9517905 | 93460 | 9034278
4 | E4R89 | 43234915201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2016-09-02 | 4719445 | 4847205 | 4456560 | 127759.9 | 0 | 4483412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4456560 | 4483412 | 26852 | 5266696
4 | E4R95 | 43115625201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | 2267494 | 2267494 | 2078018 | 0 | 0 | 2079393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 2587772
4 | E4S30 | 43111015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-07 | 419035 | 419035 | 393248 | 0 | 0 | 393914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393248 | 393914 | 666 | 602726
4 | E4S37 | 43716515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-05 | 549000 | 549000 | 512495 | 0 | 0 | 517567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 504683
4 | E4S80 | 43609515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 2070318 | 2144319 | 2069570 | 74001.34 | 0 | 2112206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 1656846
4 | T4395 | 42936515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 1928000 | 1932802 | 1674394 | 4801.64 | 0 | 1674394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674394 | 1674394 | 0 | 1544788
4 | T4409 | 43019215201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-05-20 | 4789933 | 5042467 | 4996786 | 252534.18 | 0 | 4982280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4996786 | 4982280 | -14505 | 5274241 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | T4422 | 43257425201 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2016-12-07 | 4613776 | 4938807 | 4932678 | 325030.9 | 0 | 4925308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4932678 | 4925308 | -7370 | 4236194
4 | T4439 | 42872515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 4580758 | 4651658 | 4514932 | 70899.67 | 0 | 4518968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4514932 | 4518968 | 4036 | 4467828 | B0 | ACC - LUMP SUM
4 | T4446 | 43294915201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 2621390 | 2636483 | 2515200 | 15092.34 | 0 | 2504407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515200 | 2504407 | -10793 | 2667038
4 | T4450 | 43288325201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 1867168 | 1867168 | 1766523 | 0 | 0 | 1766523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 2440207
4 | T4453 | 43786615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 741586 | 745892 | 706473 | 4306.13 | 0 | 708943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706473 | 708943 | 2470 | 783049
4 | T4456 | 43509515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 621302 | 621302 | 546893 | 0 | 0 | 547874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546893 | 547874 | 981 | 787751
4 | T4457 | 43436015201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-04-26 | 1472242 | 1503409 | 1494780 | 31167.68 | 37125 | 1497583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37125 | 0 | 0 | 0 | 0 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 1576734 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4460 | 43854615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 932300 | 932300 | 856857 | 0 | 0 | 856867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856857 | 856867 | 10 | 782210
4 | T4463 | 43167215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 312963 | 312963 | 288646 | 0 | 0 | 288646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288646 | 288646 | 0 | 301775
4 | T4468 | 43612415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 199400 | 199400 | 179866 | 0 | 0 | 179866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179866 | 179866 | 0 | 207511
5 | E5W79 | 42404045201 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 10721000 | 10925028 | 10844638 | 204027.69 | 0 | 10755499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10844638 | 10755499 | -89138 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
5 | E5W91 | 40441825201 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2015-08-04 | 648777 | 669790 | 669790 | 21012.5 | 0 | 665390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669790 | 665390 | -4400 | 690160
5 | E5Y56 | 43744715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-02 | 1274655 | 1351445 | 1346112 | 76789.87 | 0 | 1347350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346112 | 1347350 | 1238 | 1669932
5 | E5Y60 | 43474215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-04-04 | 2282739 | 2439656 | 2285278 | 156916.9 | -15840 | 2296432 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 2269438 | 2296432 | 26994 | 2421411
5 | E5Y64 | 41832115201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-09-07 | 1888542 | 1900573 | 1865675 | 12030.51 | 0 | 1870769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865675 | 1870769 | 5094 | 1818886
5 | E5Y73 | 43065115201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 2882444 | 3115789 | 3158796 | 233344.62 | 0 | 3223558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3158796 | 3223558 | 64762 | 3280928
5 | E5Y75 | 43565515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | 576675 | 576675 | 566351 | 0 | 0 | 566351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566351 | 566351 | 0 | 601123
5 | E5Y77 | 43809615201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-04-26 | 1828183 | 1904273 | 1854273 | 76089.71 | 0 | 1854273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y92 | 43243835201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-02 | 2098740 | 2179800 | 2109348 | 81060.22 | 0 | 2122937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 2861396
5 | E5Y96 | 43643415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 3268345 | 3324038 | 3293890 | 55692.68 | 0 | 3302941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 2900877
5 | E5Y98 | 43927215201 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2017-09-06 | 162149 | 162149 | 119762 | 0 | 0 | 119762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119762 | 119762 | 0 | 240922
5 | E5Y99 | 43927615201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2017-10-03 | 596733 | 596733 | 546163 | 0 | 0 | 547337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 946415
5 | E5Z03 | 43612615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-05 | 765000 | 765000 | 715000 | 0 | 0 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000 | 715000 | 0 | 1015761
5 | E5Z15 | 44022215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-09-25 | 1614614 | 1614614 | 1573363 | 0 | 0 | 1573363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
5 | T5313 | 23953535201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-12-03 | 37587579 | 42729229 | 43288413 | 5141649.91 | 0 | 42228448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43288413 | 42228448 | -1059964 | 38177323 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5431 | 23759225201 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2012-12-05 | 29360536 | 33683790 | 34207580 | 4323245.3 | -3800 | 33089772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 29690235
5 | T5558 | 23842215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 37503443 | 37874281 | 37480698 | 370838.06 | 990000 | 37514444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990000 | 0 | 0 | 0 | 0 | 0 | 990000 | 990000 | 38470698 | 37514444 | -956254 | 47475665 | B5 | ACC - INCENTIVE/DISINCENTIVE
5 | T5564 | 43505515201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-05-25 | 2766468 | 2822949 | 2775862 | 56480.73 | 0 | 2775862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775862 | 2775862 | 0 | 3396278
5 | T5578 | 43364815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 3288934 | 3404197 | 3184256 | 115262.79 | -14055 | 3177145 | -14055 | 0 | 0 | 0 | 0 | 0 | -14055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14055 | 3170201 | 3177145 | 6944 | 2864215
5 | T5584 | 43233315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 1998889 | 2179196 | 2210072 | 180307.03 | 0 | 2224069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210072 | 2224069 | 13997 | 2432081
5 | T5585 | 43441715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-02-22 | 2959615 | 3012362 | 2938715 | 52747.39 | -39354 | 2939642 | -39354 | 0 | 0 | 0 | 0 | 0 | -39354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39354 | 2899361 | 2939642 | 40280 | 3119772
5 | T5602 | 44113065203 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 287798 | 287798 | 331937 | 0 | -18683 | 313254 | -18683 | 0 | 0 | 0 | 0 | 0 | -18683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18683 | 313254 | 313254 | 0 | 295435
5 | T5612 | 44113035201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1243505 | 2375233 | 2283435 | 1131727.86 | 0 | 2284747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1351002
5 | T5620 | 43367315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-10-25 | 633985 | 639413 | 620693 | 5428.5 | 0 | 621196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620693 | 621196 | 504 | 980597
6 | E6J51 | 43652415201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 2558857 | 2607925 | 2393750 | 49068.4 | 0 | 1800521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2393750 | 1800521 | -593229 | 3068069
6 | E6J96 | 42918725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-27 | 3292828 | 3417930 | 3052117 | 125102.18 | 0 | 3083026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052117 | 3083026 | 30910 | 3372731
6 | E6K52 | 43029119201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-09-21 | 5967061 | 6057011 | 6008075 | 89950.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
6 | E6K55 | 42527135201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-17 | 4179580 | 4230908 | 4133800 | 51327.99 | 180000 | 4165794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 4313800 | 4165794 | -148006 | 4754512 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6K66 | 43826315201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-26 | 632865 | 632865 | 612839 | 0 | 0 | 614000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 767335
6 | E6K90 | 43653315201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 1534207 | 1534207 | 1484378 | 0 | 0 | 1484378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 1699725
6 | E6L19 | 42848725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-27 | 1469702 | 1469702 | 1379063 | 0 | 1584 | 1390630 | 0 | 0 | 0 | 0 | 1584 | 0 | 1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584 | 1380647 | 1390630 | 9983 | 1648940
6 | E6L32 | 44048515201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-11-30 | 575526 | 575526 | 511952 | 0 | 0 | 511952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511952 | 511952 | 0 | 593410
6 | T6339 | 41463325201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-05-25 | 8785729 | 9203528 | 9138495 | 417798.88 | 250000 | 9130458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 9388495 | 9130458 | -258037 | 8755698 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6347 | 42559815201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 21462766 | 22274168 | 21904850 | 811402.18 | 1200000 | 21684913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 23104850 | 21684913 | -1419938 | 22401464 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6388 | 24961475201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 33267097 | 34160144 | 35419695 | 893046.25 | 960000 | 35803243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 240000 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 37471337 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6411 | 43477615201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2356443 | 2356443 | 2361696 | 0 | 120000 | 2379741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 2737736 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6415 | 43328625201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 2632861 | 2661056 | 2517080 | 28194.94 | 150000 | 2530404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2667080 | 2530404 | -136676 | 3416980 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6416 | 43305925201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1824984 | 1972801 | 1821952 | 147816.92 | 0 | 1792624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821952 | 1792624 | -29328 | 2103857
6 | T6418 | 43274825201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 1730331 | 1781963 | 1633274 | 51631.51 | 0 | 1638508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633274 | 1638508 | 5234 | 2094391
6 | T6426 | 43477115201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1156048 | 1219697 | 1138589 | 63648.67 | 0 | 1144207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 1339225
6 | T6434 | 43792115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 328254 | 328254 | 283998 | 0 | 0 | 284067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283998 | 284067 | 69 | 429367
6 | T6446 | 43631215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 793153 | 793153 | 739919 | 0 | 0 | 742614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 987100
7 | E7L03 | 43656815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-04-13 | 3851530 | 4219010 | 4049852 | 367479.64 | 0 | 3995216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049852 | 3995216 | -54636 | 3798000
7 | E7L45 | 43243515201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-02-08 | 885313 | 922332 | 833142 | 37019.32 | 0 | 814450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833142 | 814450 | -18692 | 1006200
7 | E7L59 | 43070815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2175849 | 2175830 | 2389823 | -19.12 | 0 | 2415150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | 1660000
7 | E7L76 | 43589615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 921000 | 999500 | 949500 | 78500 | 0 | 949500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949500 | 949500 | 0 | 2050000 | B0 | ACC - LUMP SUM
7 | E7L93 | 43402915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 223800 | 223800 | 202343 | 0 | 0 | 202343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202343 | 202343 | 0 | 320000
7 | E7L94 | 43754915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 226571 | 226571 | 223484 | 0 | 0 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223484 | 223484 | 0 | 310000
7 | E7M04 | 43755115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-09 | 240676 | 240676 | 236101 | 0 | 0 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236101 | 236101 | 0 | 225000
7 | E7R00 | 43402615201 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2016-09-15 | 2971000 | 2971000 | 2903131 | 0 | -19677 | 2883454 | -19677 | 0 | 0 | 0 | 0 | 0 | -19677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19677 | 2883454 | 2883454 | 0 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7292 | 40915415201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2011-09-28 | 21468350 | 23763433 | 23633808 | 2295082.97 | -79000 | 23010045 | 0 | 0 | 0 | 0 | 0 | -79000 | -79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -79000 | 23554808 | 23010045 | -544763 | 21183448
7 | T7304 | 40795135201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 39444222 | 39305377 | 38780845 | -138845.42 | -18000 | 38004215 | 0 | 0 | 0 | 0 | 0 | -18000 | -18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 38762845 | 38004215 | -758630 | 44767705 | ARRA | AMERICAN RECOVERY AND REINVEST
7 | T7317 | 41886075201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 25488889 | 25701063 | 26223933 | 212174.36 | -97668 | 25239037 | -97668 | 0 | 0 | 0 | 0 | 0 | -97668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97668 | 26126265 | 25239037 | -887228 | 24112219
7 | T7353 | 25699535201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2014-10-29 | 19306771 | 20971666 | 20689510 | 1664894.68 | 0 | 19869660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20689510 | 19869660 | -819849 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7379 | 42906015202 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 7691624 | 7990485 | 8163052 | 298860.33 | 0 | 8182033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8163052 | 8182033 | 18982 | 9262147
7 | T7382 | 43258615202 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 8465944 | 9024845 | 9722176 | 558900.45 | -400000 | 9347660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | 0 | -400000 | -400000 | 9322176 | 9347660 | 25484 | 9653597 | B7 | ACC - A+B/BONUS
7 | T7390 | 43480715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3002052 | 3032833 | 3060237 | 30780.82 | 0 | 3105091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 3538017
7 | T7394 | 43431715201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1263874 | 1263874 | 1203555 | 0 | 0 | 1210019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 1558000
7 | T7416 | 44030615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 471467 | 471467 | 440953 | 0 | 0 | 440953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440953 | 440953 | 0 | 446330
7 | T7423 | 44269715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-06-13 | 189768 | 189768 | 146624 | 0 | 0 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146624 | 146624 | 0 | 280558
8 | E8N52 | 42935045201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2014-09-30 | 50984589 | 52265348 | 52262125 | 1280759 | -25500 | 50963001 | 0 | 0 | 0 | 0 | 0 | -25500 | -25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25500 | 52236625 | 50963001 | -1273624 | 52446848 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8P06 | 43383015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-23 | 27866200 | 27866200 | 27624496 | 0 | 0 | 26928859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 32476137 | B8 | ACC - DESIGN/BUILD - MAJOR
8 | E8P90 | 43561515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 8378688 | 9424319 | 9142821 | 1045631.46 | 0 | 9136713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9142821 | 9136713 | -6108 | 8835781
8 | E8Q11 | 43715625201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-08-16 | 10316568 | 10271998 | 10116572 | -44570.16 | 0 | 10180724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10116572 | 10180724 | 64151 | 10198096
8 | E8Q46 | 43717015202 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2017-03-14 | 1120173 | 1120173 | 1139075 | 0 | 0 | 1139077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 885798
8 | E8Q48 | 43560815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-13 | 2193386 | 2202999 | 2182384 | 9613.36 | -41184 | 2141200 | -41184 | 0 | 0 | 0 | 0 | 0 | -41184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41184 | 2141200 | 2141200 | 0 | 2074316
8 | E8Q77 | 43905115201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-09-19 | 1559626 | 1611434 | 1403106 | 51808.48 | 0 | 1403413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 1751318

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 649397 | 175 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO | 20 | 01co | 1 | 20
01CO | 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | -247700 | -332612 | 33 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 11 | 01do | 21 | 31
01CO | 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | -6693381 | 1329652 | 198 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 68 | 0 | 0 | 0 | 0 |  | CO | 16 | 02co | 32 | 47
01CO | 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | -109936 | -74498 | 18 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 11 | 02do | 48 | 58
01CO | 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 4666 | 70668 | 64 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO | 12 | 03co | 59 | 70
01CO | 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | -45614 | 67704 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 7 | 03do | 71 | 77
01CO | 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 162288 | 192592 | 71 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 12 | 04co | 78 | 89
01CO | 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | -627624 | 220362 | 44 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO | 8 | 04do | 90 | 97
01CO | 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710516 | -83952 | 0 | -83952 | 626564 | 655747 | 29183 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 10 | 05co | 98 | 107
01CO | 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 42066 | 48270 | 30 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 | T | CO | 14 | 05do | 108 | 121
01CO | 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 10 | 06co | 122 | 131
01CO | 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 8 | 06do | 132 | 139
01CO | 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 527 | 16831 | 2 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 10 | 07co | 140 | 149
01CO | 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 8 | 07do | 150 | 157
01CO | 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 302 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 158 | 157
01CO | 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 908 | -6283 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 7 | 08do | 158 | 164
01CO | 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 152724 | 22 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | -1987458 | 665347 | 175 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE | 11 | 36 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1523947 | 48 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 0 | 0 | 16 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09 |  |  | 3 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 0 | 5910 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 33269 | 18 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 14694 | 8 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 840958 | 89 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73 |  |  | 33 | 80 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | -62293 | 0 | 12 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | -366052 | 96491 | 80 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97 |  |  | 20 | 54 | 0 | 0 | -37511 | 0 |  | CO
02CO | 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 716585 | 179 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26 |  |  | 44 | 57 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36 |  |  | 3 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 36072 | 41 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 0 | 13 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83 |  |  | 2 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 0 | 28 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 26193 | 7048 | 42 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5815920 | 87174 | 51929 | 37 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2 |  |  | 13 | 51 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1031421 | 15675 | 6408 | 22 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32 |  |  | 44 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 4486 | 74 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 0 | 16 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74 |  |  | 4 | 5 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | -412 | 1525306 | 47 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43 |  |  | 14 | 79 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | -22727 | 248912 | 44 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | -98576 | 61 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26 |  |  | 2 | 55 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 28412 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 | 2018-05-09 | QTR4 | 17/18 | 209 | 567894 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 4326 | 20 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 30133 | 59347 | 55 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25 |  |  | 12 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 494858 | 26 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 78162 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 0 | 12377 | 10 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 0 | 0 | 13 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 446147 | 119 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15 |  |  | 2 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 0 | -1624 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | -25384 | 2617138 | 303 | 65 | 20 | 532799 | 13449 | 90 | 4 | 491634 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2617725 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94 |  |  | 17 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 75332 | 76 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 20691 | 171 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 15763 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 0 | 1601 | 48 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 | 2018-03-19 | QTR3 | 17/18 | 308 | 819000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 0 | 28099 | 33 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 13058 | -7125 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 0 | -21294 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 14433 | 38 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83 |  |  | 12 | 16 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 3971426 | 99 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 61 | 0 | 0 | -216679 | 0 |  | DO
03DO | 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 130 | 0 | 10 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000 |  |  | 6 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 0 | 26519 | 71 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 127524 | 43 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 945 | 3000 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64 |  |  | 8 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 0 | 4802 | 135 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | -14505 | 252534 | 101 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | -7370 | 325031 | 104 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 4036 | 70900 | 32 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | -10793 | 15092 | 66 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97 |  |  | 26 | 22 | 0 | 0 | -1882 | 0 |  | CO
04CO | 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 0 | 32 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66 |  |  | 24 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 985 | 4306 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 981 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 31168 | 30 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 10 | 0 | 7 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | -2197408 | 3131122 | 99 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 57 | 0 | 0 | -82927 | 0 |  | DO
04DO | 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | -85027 | 475368 | 293 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75 |  |  | 10 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 93460 | 150444 | 82 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 26852 | 127760 | 93 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 666 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 0 | 13 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 74001 | 9 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | -1059964 | 5141650 | 119 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 7 | 57 | 0 | 30 | -230251 | 0 |  | CO
05CO | 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 4323245 | 93 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55 |  |  | 0 | 58 | 0 | 0 | -110308 | 0 |  | CO
05CO | 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | -956254 | 370838 | 56 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | -40 | -130768 | 0 |  | CO
05CO | 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 0 | 56481 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05 |  |  | 14 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 6944 | 115263 | 65 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 13997 | 180307 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12 |  |  | 8 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 40280 | 52747 | 216 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 | 2018-07-23 | QTR1 | 18/19 | 514 | 295435 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1131728 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 504 | 5429 | 8 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 | 2018-09-17 | QTR1 | 18/19 | 515 | 980597 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | -89138 | 204028 | 174 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 14 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | -4400 | 21013 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 1238 | 76790 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 26994 | 156917 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 5094 | 12031 | 26 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7 |  |  | 26 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 64762 | 233345 | 64 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928 |  |  | 3 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 0 | 0 | 60 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85 |  |  | 8 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 76090 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 81060 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 55693 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-02-07 | QTR3 | 17/18 | 509 | 240922 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | -258037 | 417799 | 96 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | -1419938 | 811402 | 61 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 893046 | 79 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 0 | 31 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | -136676 | 28195 | 44 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | -29328 | 147817 | 57 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 5234 | 51632 | 63 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 63649 | 15 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 69 | 0 | 48 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 0 | 57 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | -593229 | 49068 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 30910 | 125102 | 67 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 89950 | 52 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | -148006 | 51328 | 26 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 0 | 13 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 9983 | 0 | 44 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 0 | 0 | 4 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | -544763 | 2295083 | 191 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14 |  |  | 30 | 91 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | -758630 | -138845 | 145 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST | 16 | 61 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | -887228 | 212174 | 208 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03 |  |  | 2 | 57 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | -819849 | 1664895 | 92 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 66 | 0 | 0 | -113880 | 0 |  | CO
07CO | 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 18982 | 298860 | 167 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22 |  |  | 48 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 25484 | 558900 | 42 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 30781 | 47 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 0 | 31 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 | 2018-06-22 | QTR4 | 17/18 | 799 | 446330 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | -54636 | 367480 | 145 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | -18692 | 37019 | 42 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | -19 | 20 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000 |  |  | 9 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 0 | 78500 | 39 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 | 2018-09-12 | QTR1 | 18/19 | 796 | 320000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 | 2018-09-25 | QTR1 | 18/19 | 796 | 310000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 | 2018-10-08 | QTR2 | 18/19 | 796 | 225000 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | -1273624 | 1280759 | 147 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 47 | 0 | 0 | -35903 | 0 |  | DO
08DO | 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 0 | 56 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | -6108 | 1045631 | 89 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 64151 | -44570 | 40 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64 |  |  | 0 | 28 | 0 | 0 | -104904 | 0 |  | DO
08DO | 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 223 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 0 | 78 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 0 | 9613 | 32 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 51808 | 6 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91 |  |  | 17 | 12 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0