## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 288810850 | 287067988 | 294941520 | 292189110 | 6126000 | 281506517 | -1.937% | 100% | 5831752 | 2.031% | 6130669 | 2.123% | 9012 | 1422 | 15.78% | 587 | 6.514% | 0 | 0% | 402 | 4.461% | 9414 | 4.461% | 11517 | 11288 | 9279 | 2.963% | 83.33%
| District Let | 42928754 | 42334528 | 44524117 | 43810064 | 75000 | 38079239 | -10.05% | 100% | 1667995 | 3.94% | 1595362 | 3.716% | 3431 | 208 | 6.062% | 199 | 5.8% | 498 | 14.51% | 163 | 4.751% | 4092 | 19.27% | 4499 | 4351 | 3944 | 14.95% | 88.24%
| All Contracts | 331739604 | 329402516 | 339465637 | 335999174 | 6201000 | 319585756 | -2.98% | 100% | 7499747 | 2.277% | 7726031 | 2.329% | 12443 | 1630 | 13.1% | 786 | 6.317% | 498 | 4.002% | 565 | 4.541% | 13506 | 8.543% | 16016 | 15639 | 13223 | 6.269% | 85.11%
2 | Central Let | 121859158 | 120100129 | 124739545 | 123226249 | 0 | 121488406 | 1.156% | 100% | 3730460 | 3.106% | 2880387 | 2.364% | 6278 | 1189 | 18.94% | 704 | 11.21% | 44 | 0.7009% | 499 | 7.948% | 6821 | 8.649% | 8714 | 8653 | 6760 | 7.678% | 90.48%
| District Let | 115720609 | 114695452 | 119037897 | 116004379 | 0 | 119256940 | 3.977% | 72.22% | 3254192 | 2.837% | 3317292 | 2.867% | 5014 | 612 | 12.21% | 692 | 13.8% | 21 | 0.4188% | 728 | 14.52% | 5763 | 14.94% | 7067 | 6699 | 5395 | 7.599% | 77.78%
| All Contracts | 237579767 | 234795581 | 243777442 | 239230628 | 0 | 240745346 | 2.534% | 87.18% | 6984652 | 2.975% | 6197679 | 2.609% | 11292 | 1801 | 15.95% | 1396 | 12.36% | 65 | 0.5756% | 1227 | 10.87% | 12584 | 11.44% | 15781 | 15352 | 12155 | 7.643% | 84.62%
3 | Central Let | 81562464 | 80542353 | 86965177 | 89340704 | 0 | 88799864 | 10.25% | 80% | 5645004 | 7.009% | 5402714 | 6.624% | 3944 | 1631 | 41.35% | 498 | 12.63% | 1021 | 25.89% | 259 | 6.567% | 5224 | 32.45% | 7353 | 7357 | 5228 | 32.56% | 60%
| District Let | 147051176 | 146365451 | 151979890 | 151578706 | 0 | 150666016 | 2.938% | 100% | 5141080 | 3.512% | 4928714 | 3.352% | 3002 | 692 | 23.05% | 241 | 8.028% | 226 | 7.528% | 163 | 5.43% | 3391 | 12.96% | 4324 | 4292 | 3359 | 11.89% | 90.91%
| All Contracts | 228613640 | 226907804 | 238945067 | 240919410 | 0 | 239465880 | 5.534% | 87.1% | 10786084 | 4.754% | 10331428 | 4.519% | 6946 | 2323 | 33.44% | 739 | 10.64% | 1247 | 17.95% | 422 | 6.075% | 8615 | 24.03% | 11677 | 11649 | 8587 | 23.63% | 70.97%
4 | Central Let | 53948787 | 53107394 | 54684079 | 52715560 | 37125 | 53781999 | 1.27% | 100% | 902777 | 1.7% | 735292 | 1.363% | 4362 | 877 | 20.11% | 333 | 7.634% | 72 | 1.651% | 158 | 3.622% | 4592 | 5.273% | 5802 | 5657 | 4447 | 1.949% | 100%
| District Let | 286627992 | 285636869 | 307639379 | 306059191 | 300000 | 299102053 | 4.714% | 92.31% | 20484185 | 7.171% | 21011386 | 7.331% | 7012 | 1149 | 16.39% | 476 | 6.788% | 121 | 1.726% | 1335 | 19.04% | 8468 | 20.76% | 10093 | 9668 | 8043 | 14.7% | 92.31%
| All Contracts | 340576779 | 338744263 | 362323458 | 358774751 | 337125 | 352884052 | 4.174% | 96.55% | 21386962 | 6.314% | 21746678 | 6.385% | 11374 | 2026 | 17.81% | 809 | 7.113% | 193 | 1.697% | 1493 | 13.13% | 13060 | 14.82% | 15895 | 15325 | 12490 | 9.812% | 96.55%
5 | Central Let | 149737932 | 148534432 | 162113621 | 162578802 | 986200 | 160280298 | 7.908% | 72.22% | 11206365 | 7.545% | 12375682 | 8.265% | 6465 | 1469 | 22.72% | 561 | 8.677% | 0 | 0% | 600 | 9.281% | 7065 | 9.281% | 9214 | 8978 | 6948 | 7.471% | 77.78%
| District Let | 37779403 | 36932104 | 38953571 | 38173051 | 50000 | 37877122 | 2.559% | 90.48% | 1050601 | 2.845% | 1174167 | 3.108% | 5115 | 978 | 19.12% | 524 | 10.24% | 28 | 0.5474% | 273 | 5.337% | 5416 | 5.885% | 6918 | 6514 | 5012 | -2.014% | 95.24%
| All Contracts | 187517335 | 185466536 | 201067192 | 200751853 | 1036200 | 198157420 | 6.843% | 82.05% | 12256966 | 6.609% | 13549849 | 7.226% | 11580 | 2447 | 21.13% | 1085 | 9.37% | 28 | 0.2418% | 873 | 7.539% | 12481 | 7.781% | 16132 | 15492 | 11960 | 3.282% | 87.18%
6 | Central Let | 101096707 | 99132256 | 103478357 | 103231163 | 3650000 | 103443476 | 4.349% | 94.12% | 2962343 | 2.988% | 2381649 | 2.356% | 5259 | 843 | 16.03% | 304 | 5.781% | 141 | 2.681% | 0 | 0% | 5400 | 2.681% | 6547 | 5849 | 4702 | -10.59% | 100%
| District Let | 26198273 | 25676814 | 26832415 | 25776722 | 180000 | 19131018 | -25.49% | 100% | 655229 | 2.552% | 634141 | 2.421% | 2845 | 755 | 26.54% | 237 | 8.33% | 55 | 1.933% | 14 | 0.4921% | 2914 | 2.425% | 3944 | 3855 | 2863 | 0.6327% | 100%
| All Contracts | 127294980 | 124809070 | 130310772 | 129007885 | 3830000 | 122574494 | -1.79% | 96.43% | 3617572 | 2.898% | 3015790 | 2.369% | 8104 | 1598 | 19.72% | 541 | 6.676% | 196 | 2.419% | 14 | 0.1728% | 8314 | 2.591% | 10491 | 9704 | 7565 | -6.651% | 100%
7 | Central Let | 152548712 | 151058898 | 158266900 | 158714391 | -400000 | 155213776 | 2.751% | 92.31% | 6054553 | 4.008% | 5718186 | 3.748% | 5305 | 1175 | 22.15% | 515 | 9.708% | 89 | 1.678% | 555 | 10.46% | 5949 | 12.14% | 7639 | 7769 | 6079 | 14.59% | 76.92%
| District Let | 17835155 | 17432655 | 18370692 | 17936141 | 0 | 17841725 | 2.347% | 90.91% | 505294 | 2.899% | 535536 | 3.003% | 2047 | 541 | 26.43% | 182 | 8.891% | 0 | 0% | 40 | 1.954% | 2087 | 1.954% | 2810 | 2527 | 1804 | -11.87% | 100%
| All Contracts | 170383867 | 168491553 | 176637592 | 176650532 | -400000 | 173055501 | 2.709% | 91.67% | 6559847 | 3.893% | 6253722 | 3.67% | 7352 | 1716 | 23.34% | 697 | 9.48% | 89 | 1.211% | 595 | 8.093% | 8036 | 9.304% | 10449 | 10296 | 7883 | 7.223% | 87.5%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 112593680 | 111892595 | 115205166 | 114093553 | 0 | 111970226 | 0.06938% | 100% | 2468004 | 2.206% | 2611486 | 2.319% | 3150 | 517 | 16.41% | 262 | 8.317% | 41 | 1.302% | 147 | 4.667% | 3338 | 5.968% | 4117 | 4100 | 3321 | 5.429% | #VALUE!
| All Contracts | 112593680 | 111892595 | 115205166 | 114093553 | 0 | 111970226 | 0.06938% | 100% | 2468004 | 2.206% | 2611486 | 2.319% | 3150 | 517 | 16.41% | 262 | 8.317% | 41 | 1.302% | 147 | 4.667% | 3338 | 5.968% | 4117 | 4100 | 3321 | 5.429% | 87.5%
Totals This Qtr | Central Let | 949564610 | 939543450 | 985189199 | 981995979 | 10399325 | 964514336 | 2.658% | 91.85% | 36333254 | 3.867% | 35624579 | 3.752% | 40625 | 8606 | 21.18% | 3502 | 8.62% | 1367 | 3.365% | 2473 | 6.087% | 44465 | 9.452% | 56786 | 55551 | 43443 | 6.937% | 83.7%
| District Let | 786735042 | 780966468 | 822543127 | 813431807 | 605000 | 793924339 | 1.659% | 91.82% | 35226580 | 4.511% | 35808084 | 4.551% | 31616 | 5452 | 17.24% | 2813 | 8.897% | 990 | 3.131% | 2863 | 9.056% | 35469 | 12.19% | 43772 | 42006 | 33741 | 6.721% | 90.91%
| All Contracts | 1736299652 | 1720509918 | 1807732326 | 1795427786 | 11004325 | 1758438675 | 2.205% | 91.84% | 71559834 | 4.159% | 71432663 | 4.114% | 72241 | 14058 | 19.46% | 6315 | 8.742% | 2357 | 3.263% | 5336 | 7.386% | 79934 | 10.65% | 100558 | 97557 | 77184 | 6.842% | 86.94%
Totals Previous Quarter | Central Let | 663118932 | 656304400 | 690485144 | 688224657 | 8259325 | 671976975 | 2.388% | 92.22% | 27642385 | 4.212% | 27366201 | 4.127% | 27457 | 5643 | 20.55% | 2230 | 8.122% | 866 | 3.154% | 1915 | 6.975% | 30238 | 10.13% | 38239 | 37518 | 29645 | 7.969% | 81.11%
| District Let | 462216838 | 458466399 | 478215418 | 473625658 | 755000 | 460979465.72 | 0.5481% | 93.24% | 15785697 | 3.443% | 15998582 | 3.461% | 20087 | 3440 | 17.13% | 1675 | 8.339% | 771 | 3.838% | 1132 | 5.635% | 21990 | 9.474% | 27143 | 26356 | 21241 | 5.745% | 93.24%
| All Contracts | 1125335770 | 1114770799 | 1168700562 | 1161850315 | 9014325 | 1132956440.72 | 1.631% | 92.68% | 43428082 | 3.896% | 43364783 | 3.853% | 47544 | 9083 | 19.1% | 3905 | 8.213% | 1637 | 3.443% | 3047 | 6.409% | 52228 | 9.852% | 65382 | 63874 | 50886 | 7.029% | 86.59%
Totals Fiscal Year 2017/2018 | Central Let | 922272924 | 912201289 | 950316202 | 949875400 | 5416900 | 923867600 | 1.279% | 94.83% | 30812018 | 3.378% | 27856787 | 3.02% | 42758 | 8500 | 19.88% | 3456 | 8.083% | 1275 | 2.982% | 2225 | 5.204% | 46258 | 8.186% | 58215 | 59077 | 47121 | 10.2% | 87.93%
| District Let | 681923471 | 675586171 | 745680560 | 741535853 | 2689500 | 724953919.61 | 7.307% | 92.62% | 65007580 | 9.622% | 63710371 | 9.343% | 27803 | 4959 | 17.84% | 2334 | 8.395% | 695 | 2.5% | 2601 | 9.355% | 31099 | 11.85% | 38519 | 37890 | 30597 | 10.05% | 85.25%
| All Contracts | 1604196395 | 1587787460 | 1695996762 | 1691411253 | 8106400 | 1648821519.61 | 3.844% | 93.92% | 95819598 | 6.035% | 91567158 | 5.708% | 70561 | 13459 | 19.07% | 5790 | 8.206% | 1970 | 2.792% | 4826 | 6.839% | 77357 | 9.631% | 96734 | 96967 | 77718 | 10.14% | 86.82%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | 107% | 1 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | 95.53% | 1 | -2998654 | 649397 | 175 | 65 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43
| 01 | T1576 | 19690445201 | 2014-04-30 | QTR4 | 13/14 | 2 | 23 | 800 | 1243 | 1197 | 120.8% | 0 | 46 | 0 | 0 | 316 | 127 | 28940681 | 150000 | 28790681 | 30877320 | 31050834 | 0 | 0 | 0 | 31050834 | 28027477 | 97.35% | 1 | -2782025 | 1936639 | 170 | 61 | 0 | 65 | 378653 | 101153 | 0 | 58 | 791125 | 180721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29641 | 5438 | 0 | 2 | 376248 | 114516 | 0 | 0 | 0 | 0 | 0 | 0 | 27196 | 0 | 0 | 2 | 211399 | 94994 | 0 | 0 | 0 | 0 | 0 | 0 | -25911 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1788352 | 496822 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 118 | 36280173.56
| 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 104.9% | 1 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | 96.97% | 1 | -247700 | -332612 | 33 | 25 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 101.1% | 1 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | 98.52% | 1 | -6693381 | 1329652 | 198 | 68 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 95.5% | 1 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | 97.88% | 1 | -109936 | -74498 | 18 | 5 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM
| 01 | T1646 | 43275515202 | 2016-06-15 | QTR4 | 15/16 | 2 | 2 | 340 | 502 | 656 | 152.6% | 0 | -154 | 154 | 0 | 137 | 25 | 3883072 | 50000 | 3833072 | 3988230 | 4003713 | 0 | 0 | 0 | 4003713 | 3893478 | 101.6% | 1 | -55078 | 105158 | 100 | 37 | 0 | 0 | 0 | 0 | 0 | 6 | 34357 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 34559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 68915 | 1520 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 113 | 4572143.2
| 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 98.96% | 1 | 4666 | 70668 | 64 | 24 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15
| 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 87.95% | 1 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | 95.18% | 1 | -45614 | 67704 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98
| 01 | T1666 | 43289715201 | 2017-01-25 | QTR3 | 16/17 | 2 | 5 | 160 | 300 | 300 | 144.4% | 0 | 0 | 0 | 0 | 69 | 71 | 3057226 | 50000 | 3007226 | 3156754 | 3084177 | 0 | 0 | 0 | 3084177 | 3034815 | 100.9% | 1 | 9700 | 99528 | 49 | 20 | 0 | 0 | 13307 | 0 | 0 | 69 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 40465 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-03-15 | QTR3 | 17/18 | 118 | 3786427.28
| 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 105.3% | 1 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 103.1% | 1 | 162288 | 192592 | 71 | 21 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28
| 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 69.9% | 1 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | 98.2% | 1 | -627624 | 220362 | 44 | 14 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | 162.4% | 0 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710515 | -83952 | 0 | -83952 | 626563 | 655747 | 92.29% | 1 | 29184 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-03-05 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM
| 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 87.67% | 1 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 101.9% | 1 | 42066 | 48270 | 30 | 23 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35
| 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 97.45% | 1 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 100.1% | 1 | 4205 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79
| 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 100% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59
| 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 138.4% | 0 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 105.7% | 1 | 527 | 16831 | 2 | 15 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1687 | 41304245201 | 2017-07-26 | QTR1 | 17/18 | 1 | 6 | 429 | 484 | 340 | 66.43% | 1 | 144 | 0 | 0 | 55 | 0 | 28672708 | 150000 | 28522708 | 28693379 | 27612242 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | 99.35% | 1 | -344268 | 20671 | 44 | 11 | 0 | 0 | 46688 | 0 | 0 | 0 | 115877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348392 | 307784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -431102 | 0 | 0 | 0 | 79855 | 307784 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-02 | QTR2 | 18/19 | 106 | 35334896.73 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 97.33% | 1 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM
| 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 99.13% | 1 | 302 | 0 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 98.96% | 1 | 908 | -6283 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM
| 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 98.89% | 1 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 109.8% | 1 | 92434 | 152724 | 22 | 11 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68
| 01 | T1699 | 43698315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 73 | 84 | 84 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 338000 | 0 | 338000 | 345335 | 345335 | 0 | 0 | 0 | 345335 | 345335 | 102.2% | 1 | 0 | 7335 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-28 | QTR1 | 18/19 | 115 | 381548.27
| 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 97.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1710 | 43795915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 170 | 199 | 166 | 80.59% | 1 | 33 | 0 | 0 | 29 | 0 | 1395501 | 50000 | 1345501 | 1395501 | 1301640 | 0 | 100000 | 100000 | 1401640 | 1301762 | 96.75% | 1 | -99878 | 0 | 10 | 19 | 0 | 0 | 30398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30398 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 118 | 1196299.53 | B1 | ACC - NO EXCUSE BONUS
| 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 52.5% | 1 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 100% | 1 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM
| 01 | T1726 | 44016215201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 75 | 81 | 80 | 98.67% | 1 | 1 | 0 | 0 | 6 | 0 | 253590 | 0 | 253590 | 253590 | 253590 | 0 | 0 | 0 | 253590 | 253590 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-12-15 | QTR2 | 18/19 | 113 | 256717.81 | B0 | ACC - LUMP SUM
| 01 | T1728 | 43501715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 75 | 76 | 25 | 32% | 1 | 51 | 0 | 0 | 1 | 0 | 141143 | 0 | 141143 | 141143 | 141143 | 0 | 0 | 0 | 141143 | 141143 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 118 | 128587.62 | B0 | ACC - LUMP SUM
| 01 | T1730 | 43132415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 85 | 103 | 100 | 96.47% | 1 | 3 | 0 | 0 | 18 | 0 | 465432 | 0 | 465432 | 465432 | 465432 | 0 | 0 | 0 | 465432 | 465432 | 100% | 1 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 319733.9 | B0 | ACC - LUMP SUM
| 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | 117.4% | 1 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | 91.9% | 1 | -1987458 | 665347 | 175 | 36 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A16 | 43609215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 9 | 600 | 771 | 767 | 101.7% | 1 | 4 | 0 | 0 | 157 | 14 | 18880004 | 150000 | 18730004 | 19841188 | 19816523 | 0 | 0 | 0 | 19816523 | 19628809 | 104.8% | 1 | -187714 | 961184 | 106 | 51 | 0 | 4 | 154148 | 5054 | 0 | 10 | 279737 | 116375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348400 | 347865 | 0 | 0 | 170559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804 | 48804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1001647 | 518098 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2017-12-08 | QTR2 | 17/18 | 113 | 24424912.84
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 30 | 50 | 114 | 9012 | 11517 | 11288 | 83.33% | 25 | 229 | 340 | 0 | 2094 | 420 | 288810850 | 1742862 | 287067988 | 294941520 | 292189110 | -200077 | 6126000 | 5925923 | 298115033 | 281506517 | 100% | 30 | -15833050 | 6130669 | 1422 | 587 | 0 | 154 | 2493287 | 127661 | 0 | 223 | 2646295 | 411698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164280 | 661087 | 0 | 2 | 641897 | 114516 | 0 | 0 | 0 | 0 | 0 | 21 | 64050 | 0 | 0 | 2 | 211399 | 94994 | 0 | 0 | 67556 | 67556 | 0 | 0 | -25911 | 0 | 0 | 0 | -431102 | 0 | 0 | 402 | 5831752 | 1477512
| 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 167.4% | 0 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | 104.4% | 1 | -658099 | 1523947 | 48 | 38 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 145% | 0 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 93.37% | 1 | 0 | 0 | 16 | 3 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09
| 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | 110.9% | 1 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 98.1% | 1 | 0 | 5910 | 22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11
| 01 | E1Q21 | 41773349201 | 2017-03-22 | QTR3 | 16/17 | 1 | 1 | 500 | 539 | 539 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 5353535 | 55841 | 5297694 | 5368855 | 5313014 | 0 | 0 | 0 | 5313014 | 0 | 0% | 1 | -5313014 | 15320 | 6 | 33 | 0 | 0 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15320 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-03-08 | QTR3 | 18/19 |  | 2018-11-04 | QTR2 | 18/19 | 113 | 5530217.16
| 01 | E1Q22 | 43854515201 | 2017-05-01 | QTR4 | 16/17 | 1 | 1 | 480 | 537 | 537 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 3614066 | 54963 | 3559103 | 3616288 | 3562935 | 0 | 0 | 0 | 3562935 | 3562935 | 100.1% | 1 | 0 | 2222 | 28 | 29 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 108 | 5496030.8
| 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 112.7% | 1 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 101.6% | 1 | 81050 | 33269 | 18 | 6 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66
| 01 | E1Q64 | 43445715201 | 2018-04-19 | QTR4 | 17/18 | 2 | 0 | 140 | 179 | 170 | 93.57% | 1 | 9 | 0 | 0 | 39 | 0 | 429966 | 21462 | 408504 | 429966 | 399604 | 0 | 0 | 0 | 399604 | 399697 | 97.84% | 1 | 94 | 0 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 450406.6
| 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 99% | 1 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 101.1% | 1 | 94256 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86
| 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 87.37% | 1 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 103.8% | 1 | 88492 | 0 | 11 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM
| 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | 99.62% | 1 | -50000 | 14694 | 8 | 1 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 84.71% | 1 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | 89.77% | 1 | -25000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 69.33% | 1 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 100% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM
| 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 85.33% | 1 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 97.5% | 1 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63
| 01 | E1R09 | 43903015201 | 2018-05-17 | QTR4 | 17/18 | 1 | 0 | 90 | 93 | 78 | 83.33% | 1 | 15 | 0 | 0 | 3 | 0 | 279115 | 12207 | 266908 | 279115 | 264760 | 0 | 0 | 0 | 264760 | 264760 | 99.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-07 | QTR2 | 18/19 | 118 | 214242.2
| 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 54.67% | 1 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 90.43% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88
| 01 | E1R47 | 43320215201 | 2018-08-16 | QTR1 | 18/19 | 1 | 0 | 95 | 118 | 118 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 542243 | 28109 | 514134 | 542243 | 514134 | 0 | 0 | 0 | 514134 | 514134 | 100% | 1 | 0 | 0 | 5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-29 | QTR3 | 18/19 |  | 2019-02-28 | QTR3 | 18/19 | 108 | 573290.03 | B0 | ACC - LUMP SUM
| 01 | E1R55 | 43902615201 | 2018-03-15 | QTR3 | 17/18 | 1 | 0 | 150 | 159 | 142 | 88.67% | 1 | 17 | 0 | 0 | 9 | 0 | 402836 | 19980 | 382856 | 402836 | 380287 | 0 | 0 | 0 | 380287 | 381602 | 99.67% | 1 | 1315 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 118 | 497103.38
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 17 | 19 | 19 | 3431 | 4499 | 4351 | 88.24% | 15 | 148 | 12 | 0 | 905 | 163 | 42928754 | 594226 | 42334528 | 44524117 | 43810064 | -19008 | 75000 | 55992 | 43866056 | 38079239 | 100% | 17 | -5780906 | 1595362 | 208 | 199 | 58 | 0 | 101415 | 0 | 0 | 3 | 35371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 163 | 1667995 | 0
| District 01 Totals |  |  |  |  | 47 | 69 | 133 | 12443 | 16016 | 15639 | 85.11% | 40 | 377 | 352 | 0 | 2999 | 583 | 331739604 | 2337088 | 329402516 | 339465637 | 335999174 | -219085 | 6201000 | 5981915 | 341981089 | 319585756 | 100% | 47 | -21613956 | 7726031 | 1630 | 786 | 58 | 154 | 2594702 | 127661 | 0 | 226 | 2681666 | 411698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291448 | 661087 | 0 | 2 | 641897 | 114516 | 0 | 0 | 0 | 0 | 0 | 21 | 64050 | 0 | 0 | 2 | 1198624 | 94994 | 440 | 160 | 484373 | 67556 | 0 | 0 | -25911 | 0 | 0 | 0 | -431102 | 0 | 498 | 565 | 7499747 | 1477512
| 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 111.9% | 1 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | 97.1% | 1 | -1247384 | 840958 | 89 | 80 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73
| 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | 141.9% | 0 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | 89.67% | 1 | -62293 | 0 | 12 | 15 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1
| 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 108.8% | 1 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | 100.1% | 1 | -366052 | 96491 | 80 | 54 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97
| 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 112.9% | 1 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | 106.5% | 1 | -214370 | 716585 | 179 | 57 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26
| 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 101.7% | 1 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | 98.56% | 1 | -162193 | 0 | 35 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36
| 02 | T2611 | 42880415201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 380 | 734 | 731 | 119.5% | 1 | 3 | 0 | 0 | 277 | 77 | 16425368 | 150000 | 16275368 | 17429243 | 17737903 | 0 | 0 | 0 | 17737903 | 17843990 | 109.6% | 1 | 106088 | 1003875 | 186 | 91 | 0 | 7 | 102446 | 43792 | 0 | 70 | 961987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 0 | 0 | 11131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1135125 | 43792 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 214 | 14976802.73
| 02 | T2623 | 42747425201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 588 | 772 | 772 | 104.4% | 1 | 0 | 0 | 0 | 184 | 0 | 12006916 | 125768 | 11881149 | 12006916 | 12019761 | 0 | 0 | 0 | 12019761 | 12020496 | 101.2% | 1 | 735 | 0 | 85 | 73 | 26 | 0 | 18391 | 0 | 0 | 0 | 17909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 43031 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 214 | 12840720.13
| 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 99.64% | 1 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 91.44% | 1 | 151 | 36072 | 41 | 50 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79
| 02 | T2625 | 43091415201 | 2016-06-15 | QTR4 | 15/16 | 2 | 4 | 300 | 495 | 475 | 110.3% | 1 | 20 | 0 | 0 | 144 | 51 | 4913266 | 96132 | 4817134 | 5029801 | 5053902 | 0 | 0 | 0 | 5053902 | 5063705 | 105.1% | 1 | 9803 | 116535 | 75 | 69 | 0 | 11 | 42674 | 0 | 0 | 40 | 83572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 155418 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-01-04 | QTR3 | 17/18 | 208 | 4921245.07
| 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 99.47% | 1 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 100% | 1 | 4 | 0 | 13 | 6 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83
| 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 86.67% | 1 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 103.4% | 1 | 0 | 0 | 21 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13
| 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 100.7% | 1 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 102% | 1 | 44704 | 0 | 28 | 4 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12
| 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 110.6% | 1 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 103.9% | 1 | 26193 | 7048 | 42 | 26 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91
| 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 99.84% | 1 | 89 | 0 | 29 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75
| 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 98.44% | 1 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5836409 | 103.1% | 1 | 107663 | 51929 | 37 | 51 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2
| 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | 144.7% | 0 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1015867 | 96.32% | 1 | 121 | 6408 | 22 | 24 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32
| 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 105.4% | 1 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 96.89% | 1 | 1714 | 4486 | 74 | 4 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75
| 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 79% | 1 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 95.24% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5
| 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 103.6% | 1 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 103.2% | 1 | 21810 | 0 | 16 | 5 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74
| 02 | T2677 | 43616715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 200 | 349 | 347 | 114% | 1 | 2 | 0 | 0 | 119 | 30 | 3488727 | 50000 | 3438727 | 3488727 | 3422691 | 0 | 0 | 0 | 3422691 | 3561473 | 103.6% | 1 | 138781 | 0 | 96 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 216 | 3968191.21
| 02 | T2681 | 43499615201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 180 | 216 | 216 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 1999378 | 50000 | 1949378 | 1999378 | 1930362 | 0 | 0 | 0 | 1930362 | 1930362 | 99.02% | 1 | 0 | 0 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 209 | 2290722.63
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 21 | 30 | 39 | 6278 | 8714 | 8653 | 90.48% | 19 | 61 | 67 | 0 | 1937 | 499 | 121859158 | 1759029 | 120100129 | 124739545 | 123226249 | -114976 | 0 | -114976 | 123111273 | 121488406 | 100% | 21 | -1594436 | 2880387 | 1189 | 704 | 31 | 135 | 1317488 | 60496 | 13 | 267 | 2036510 | 20522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | 0 | 8 | 109412 | 14665 | 0 | 2 | 35313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22211 | 0 | 0 | 44 | 78660 | 0 | 0 | 43 | 163863 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 44 | 499 | 3730460 | 245640
| 02 | E2R81 | 43182025203 | 2014-03-20 | QTR3 | 13/14 | 3 | 0 | 365 | 365 | 0 | 0% | 1 | 365 | 0 | 0 | 0 | 0 | 2916419 | 0 | 2916419 | 2916419 | 0 | 0 | 0 | 0 | 0 | 5517906 | 189.2% | 0 | 5517906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 208 | 1374260.51 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 02 | E2R91 | 41650145201 | 2014-06-26 | QTR4 | 13/14 | 3 | 9 | 900 | 1294 | 1372 | 123.7% | 0 | -78 | 78 | 0 | 259 | 135 | 66725725 | 270345 | 66455380 | 67223879 | 66965314 | -795600 | 0 | -795600 | 66169714 | 64637295 | 97.26% | 1 | -1452887 | 498154 | 134 | 125 | 0 | 0 | 13369 | 0 | 0 | 14 | 196815 | 0 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 301636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202522 | 0 | 0 | 135 | 370894 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-05-30 | QTR4 | 17/18 | 208 | 83530874.22 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 164.7% | 0 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | 118.1% | 0 | -412 | 1525306 | 47 | 79 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43
| 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 106.2% | 1 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | 111.7% | 0 | -22727 | 248912 | 44 | 63 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47
| 02 | E2U40 | 43015815201 | 2016-01-20 | QTR3 | 15/16 | 3 | 2 | 436 | 624 | 622 | 110.1% | 1 | 2 | 0 | 0 | 142 | 46 | 4367770 | 50000 | 4317770 | 4673447 | 4944003 | 0 | 0 | 0 | 4944003 | 4845350 | 112.2% | 0 | -49202 | 305677 | 76 | 66 | 0 | 0 | 3676 | 0 | 0 | 0 | 259099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 262775 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2019-01-09 | QTR3 | 18/19 | 02/17/2018 | 2018-02-17 | QTR3 | 17/18 | 208 | 4165392.78
| 02 | E2U49 | 43074915201 | 2016-05-18 | QTR4 | 15/16 | 3 | 4 | 240 | 409 | 409 | 141.7% | 0 | 0 | 0 | 0 | 69 | 100 | 5878818 | 87141 | 5791677 | 6117316 | 6222842 | 0 | 0 | 0 | 6222842 | 6229444 | 107.6% | 1 | 6601 | 238499 | 41 | 28 | 0 | 100 | 163931 | 148393 | 0 | 0 | 28577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 251507 | 148393 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2017-09-25 | QTR1 | 17/18 | 208 | 7361145.29
| 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 100.7% | 1 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 86.65% | 1 | 35717 | -98576 | 61 | 55 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26
| 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 98.89% | 1 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 100.1% | 1 | 0 | 28412 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894
| 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 99.6% | 1 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 97.73% | 1 | 121 | 4326 | 20 | 40 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23
| 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 97.73% | 1 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 104.5% | 1 | 30133 | 59347 | 55 | 63 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25
| 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 103.1% | 1 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 104.1% | 1 | 66 | 0 | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65
| 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 181.6% | 0 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 127.5% | 0 | 175603 | 494858 | 26 | 20 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55
| 02 | E2W86 | 43239515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 120 | 166 | 166 | 100.8% | 1 | 0 | 0 | 0 | 45 | 1 | 567579 | 25415 | 542163 | 567579 | 542982 | 0 | 0 | 0 | 542982 | 542982 | 100.2% | 1 | 0 | 0 | 9 | 36 | 0 | 1 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2630 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-12-21 | QTR2 | 18/19 | 208 | 529604.74
| 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 103.4% | 1 | 78162 | 0 | 27 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44
| 02 | E2W88 | 42849415201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 138 | 179 | 173 | 95.65% | 1 | 6 | 0 | 0 | 41 | 0 | 290000 | 23311 | 266689 | 290000 | 255859 | 0 | 0 | 0 | 255859 | 255859 | 95.94% | 1 | 0 | 0 | 11 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 208 | 444332.8
| 02 | E2W93 | 43433815201 | 2018-01-17 | QTR3 | 17/18 | 2 | 0 | 160 | 216 | 207 | 107.5% | 1 | 9 | 0 | 0 | 56 | 0 | 594594 | 28886 | 565708 | 594594 | 581178 | 0 | 0 | 0 | 581178 | 581178 | 102.7% | 1 | 0 | 0 | 6 | 29 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-03-15 | QTR3 | 18/19 |  | 2019-02-05 | QTR3 | 18/19 | 208 | 613772.37
| 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 105.6% | 1 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 100.9% | 1 | 0 | 12377 | 10 | 5 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97
| 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 99.77% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 18 | 33 | 39 | 5014 | 7067 | 6699 | 77.78% | 14 | 368 | 78 | 0 | 1325 | 728 | 115720609 | 1025156 | 114695452 | 119037897 | 116004379 | -795600 | 0 | -795600 | 115208779 | 119256940 | 72.22% | 13 | 4319081 | 3317292 | 612 | 692 | 0 | 228 | 747299 | 148393 | 3 | 333 | 2268741 | 322078 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 320081 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 59000 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | -202522 | 0 | 21 | 728 | 3254192 | 470471
| District 02 Totals |  |  |  |  | 39 | 63 | 78 | 11292 | 15781 | 15352 | 84.62% | 33 | 429 | 145 | 0 | 3262 | 1227 | 237579767 | 2784185 | 234795581 | 243777442 | 239230628 | -910576 | 0 | -910576 | 238320052 | 240745346 | 87.18% | 34 | 2724645 | 6197679 | 1801 | 1396 | 31 | 363 | 2064787 | 208889 | 16 | 600 | 4305251 | 342600 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77113 | 0 | 0 | 61 | 429493 | 14665 | 0 | 48 | 35313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22211 | 0 | 0 | 112 | 137660 | 0 | 0 | 43 | 163863 | 149956 | 18 | 0 | 0 | 0 | 0 | 0 | -240033 | 0 | 65 | 1227 | 6984652 | 716111
| 03 | T3417 | 42282315201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 325 | 885 | 885 | 230.2% | 0 | 0 | 0 | 0 | 560 | 0 | 9576952 | 114593 | 9462359 | 11201952 | 11381048 | 0 | 0 | 0 | 11381048 | 11259809 | 119% | 0 | -121240 | 1625000 | 104 | 33 | 0 | 0 | 6816 | 0 | 128 | 0 | 16533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 1672506 | 1625000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2016-03-01 | QTR3 | 15/16 | 321 | 11869074.15
| 03 | T3474 | 41110245201 | 2014-05-21 | QTR4 | 13/14 | 2 | 9 | 560 | 736 | 736 | 105.4% | 1 | 0 | 0 | 0 | 146 | 30 | 13521855 | 125538 | 13396317 | 14023931 | 14165918 | 0 | 0 | 0 | 14165918 | 13122088 | 97.95% | 1 | -1043829 | 502076 | 106 | 40 | 0 | 0 | 37317 | 0 | 0 | 30 | 516186 | 243604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21575 | 21575 | 0 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 618377 | 265179 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | QTR3 | 18/19 |  | 2016-08-26 | QTR1 | 16/17 | 308 | 12749353.07
| 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 235.5% | 0 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 125.8% | 0 | 1482 | 446147 | 119 | 44 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15
| 03 | T3498 | 43178515201 | 2017-01-25 | QTR3 | 16/17 | 4 | 1 | 190 | 384 | 387 | 128.9% | 0 | -3 | 3 | 0 | 172 | 22 | 4274307 | 55980 | 4218327 | 4324307 | 4294029 | -8433 | 0 | -8433 | 4285596 | 4353335 | 103.2% | 1 | 67739 | 50000 | 112 | 30 | 0 | 13 | 40548 | 0 | 15 | 5 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 46278 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 308 | 4281515.77
| 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 112% | 1 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 87% | 1 | 0 | -1624 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM
| 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 173.1% | 0 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | 138.9% | 0 | -25384 | 2617138 | 303 | 81 | 65 | 20 | 532799 | 13449 | 90 | 4 | 490052 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2616143 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94
| 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 127% | 0 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 100% | 1 | 152 | 75332 | 76 | 23 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13
| 03 | T3567 | 43046515201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 165 | 250 | 260 | 115.2% | 1 | -10 | 10 | 0 | 70 | 15 | 1966055 | 0 | 1966055 | 1981055 | 2001427 | -15840 | 0 | -15840 | 1985587 | 1998145 | 101.6% | 1 | 12558 | 15000 | 64 | 6 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 308 | 1970432.78
| 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 120.4% | 0 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 107.4% | 1 | 7457 | 20691 | 171 | 28 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24
| 03 | T3596 | 43274015201 | 2016-09-28 | QTR1 | 16/17 | 2 | 1 | 229 | 350 | 349 | 99.56% | 1 | 1 | 0 | 0 | 121 | 0 | 8173983 | 81645 | 8092338 | 8193029 | 8770491 | -4500 | 0 | -4500 | 8765991 | 8814288 | 108.9% | 1 | 48297 | 19046 | 102 | 19 | 0 | 0 | 6600 | 0 | 0 | 0 | 5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5882 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2017-12-17 | QTR2 | 17/18 | 314 | 8245135.42
| 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 109.5% | 1 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 108.2% | 1 | 123160 | 15763 | 77 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43
| 03 | T3634 | 43256215201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 227 | 227 | 103.3% | 1 | 0 | 0 | 0 | 77 | 0 | 2317459 | 51202 | 2266257 | 2317459 | 2243858 | 0 | 0 | 0 | 2243858 | 2321931 | 102.5% | 1 | 78073 | 0 | 55 | 17 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 308 | 2451817.54
| 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 98.1% | 1 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 97.03% | 1 | 0 | 1601 | 48 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-03-19 | QTR3 | 17/18 | 308 | 819000
| 03 | T3638 | 43461115201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 210 | 364 | 366 | 112.4% | 1 | -2 | 2 | 0 | 133 | 21 | 5256385 | 58075 | 5198309 | 5256385 | 5540831 | -7290 | 0 | -7290 | 5533541 | 5791591 | 111.4% | 0 | 258050 | 0 | 90 | 40 | 0 | 4 | 18750 | 0 | 0 | 3 | 5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8122 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 32453 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 5826402.83
| 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 141.7% | 0 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 102.9% | 1 | 0 | 28099 | 33 | 4 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM
| 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | 122.2% | 0 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 98.39% | 1 | 13058 | -7125 | 22 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54
| 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 98.46% | 1 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 97.09% | 1 | 0 | -21294 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM
| 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 99.26% | 1 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 107% | 1 | 32427 | 14433 | 38 | 21 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46
| 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 119.4% | 1 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 101.4% | 1 | 22904 | 0 | 76 | 16 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83
| 03 | T3677 | 43467515201 | 2018-02-28 | QTR3 | 17/18 | 2 | 1 | 120 | 159 | 148 | 93.33% | 1 | 11 | 0 | 0 | 36 | 3 | 2607729 | 51275 | 2556454 | 2610160 | 2714487 | -7200 | 0 | -7200 | 2707287 | 2805120 | 109.7% | 1 | 97833 | 2431 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 2431 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14394 | 25 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-09-20 | QTR1 | 18/19 | 308 | 3422497.92
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 20 | 36 | 64 | 3944 | 7353 | 7357 | 60% | 12 | -4 | 33 | 0 | 3150 | 259 | 81562464 | 1020112 | 80542353 | 86965177 | 89340704 | -113575 | 0 | -113575 | 89227129 | 88799864 | 80% | 16 | -427263 | 5402714 | 1631 | 498 | 65 | 53 | 691214 | 13449 | 465 | 89 | 1364593 | 599282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 113 | 1681624 | 428480 | 3 | 0 | 31815 | 14535 | 0 | 0 | 0 | 0 | 0 | 4 | 196583 | 5684 | 0 | 0 | 1662627 | 1662627 | 20 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021 | 259 | 5645004 | 2724056
| 03 | E3K83 | 41506725201 | 2012-11-20 | QTR2 | 12/13 | 2 | 8 | 599 | 1108 | 1108 | 120.7% | 0 | 0 | 0 | 0 | 385 | 124 | 13915054 | 150000 | 13765054 | 14699375 | 14628947 | 0 | 0 | 0 | 14628947 | 14470162 | 105.1% | 1 | -158785 | 784321 | 311 | 74 | 0 | 5 | 84488 | 0 | 0 | 12 | 93331 | 1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 107 | 683618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 867013 | 1459 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2016-01-26 | QTR3 | 15/16 | 308 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR
| 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 119.4% | 1 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | 102.6% | 1 | -981850 | 3971426 | 99 | 61 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
| 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 97.78% | 1 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 103.4% | 1 | 130 | 0 | 10 | 0 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000
| 03 | E3P35 | 40674235201 | 2017-11-09 | QTR2 | 17/18 | 1 | 0 | 235 | 281 | 281 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2284367 | 50000 | 2234367 | 2284367 | 2177088 | 0 | 0 | 0 | 2177088 | 2177088 | 97.44% | 1 | 0 | 0 | 40 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 321 | 4068630.6
| 03 | E3P64 | 40747855201 | 2017-10-12 | QTR2 | 17/18 | 1 | 0 | 110 | 153 | 153 | 111.8% | 1 | 0 | 0 | 0 | 43 | 0 | 477560 | 28231 | 449329 | 477560 | 464944 | 0 | 0 | 0 | 464944 | 464944 | 103.5% | 1 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 308 | 607325
| 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 118.3% | 1 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 106.1% | 1 | 0 | 26519 | 71 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72
| 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 91.67% | 1 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 106.1% | 1 | 81564 | 0 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17
| 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 99.33% | 1 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 102.1% | 1 | 10099 | 127524 | 43 | 37 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000
| 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 110% | 1 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 101.6% | 1 | 945 | 3000 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64
| 03 | E3Q91 | 43626815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 3 | 180 | 246 | 244 | 103.9% | 1 | 2 | 0 | 0 | 64 | 2 | 3258297 | 50000 | 3208297 | 3274221 | 3353918 | 0 | 0 | 0 | 3353918 | 3489125 | 108.8% | 1 | 135206 | 15924 | 49 | 8 | 7 | 2 | 16487 | 0 | 0 | 0 | 31396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 45243 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 321 | 4488229.01
| 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 95.71% | 1 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 98.08% | 1 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 11 | 13 | 23 | 3002 | 4324 | 4292 | 90.91% | 10 | 32 | 0 | 0 | 1159 | 163 | 147051176 | 685725 | 146365451 | 151979890 | 151578706 | 0 | 0 | 0 | 151578706 | 150666016 | 100% | 11 | -912691 | 4928714 | 692 | 241 | 206 | 13 | -701722 | 236 | 0 | 20 | 293148 | 1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 13 | 130 | 747849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54484 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 226 | 163 | 5141080 | 4951912
| District 03 Totals |  |  |  |  | 31 | 49 | 87 | 6946 | 11677 | 11649 | 70.97% | 22 | 28 | 33 | 0 | 4309 | 422 | 228613640 | 1705837 | 226907804 | 238945067 | 240919410 | -113575 | 0 | -113575 | 240805835 | 239465880 | 87.1% | 27 | -1339954 | 10331428 | 2323 | 739 | 271 | 66 | -10508 | 13685 | 465 | 109 | 1657741 | 600958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 481 | 243 | 2429473 | 428480 | 3 | 0 | 31815 | 14535 | 0 | 0 | 0 | 0 | 0 | 4 | 251067 | 5684 | 0 | 0 | 6612627 | 6612627 | 20 | 0 | 16549 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 1247 | 422 | 10786084 | 7675968
| 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 109.8% | 1 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 88.9% | 1 | 0 | 4802 | 135 | 26 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59
| 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 116% | 1 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | 104.2% | 1 | -14505 | 252534 | 101 | 41 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 116% | 1 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | 107.3% | 1 | -7370 | 325031 | 104 | 27 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4
| 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 105.6% | 1 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 99.1% | 1 | 4036 | 70900 | 32 | 24 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM
| 04 | T4445 | 43060315201 | 2017-01-25 | QTR3 | 16/17 | 1 | 4 | 365 | 510 | 480 | 94.79% | 1 | 30 | 0 | 0 | 134 | 11 | 8418937 | 102163 | 8316774 | 8403485 | 8476613 | 0 | 0 | 0 | 8476613 | 8700175 | 104.6% | 1 | 251131 | -15452 | 110 | 24 | 0 | 19 | 47250 | 0 | 0 | 0 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | -72293 | 0 | 0 | 11 | 51443 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-28 | QTR3 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 412 | 9837147.69
| 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 112.1% | 1 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | 96.73% | 1 | -10793 | 15092 | 66 | 22 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97
| 04 | T4447 | 43510115201 | 2017-03-29 | QTR3 | 16/17 | 7 | 2 | 364 | 422 | 422 | 86.26% | 1 | 0 | 0 | 0 | 108 | -50 | 3554036 | 50000 | 3504036 | 3574289 | 3278614 | 0 | 0 | 0 | 3278614 | 3266227 | 93.21% | 1 | 4310 | 20253 | 88 | 20 | 0 | 0 | 1981 | 0 | 0 | -50 | 5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 7532 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 409 | 3729070.5
| 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 118.6% | 1 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 97.21% | 1 | 0 | 0 | 32 | 25 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66
| 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 99.9% | 1 | 985 | 4306 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15
| 04 | T4455 | 43442715201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 277 | 316 | 306 | 96.39% | 1 | 10 | 0 | 0 | 39 | 0 | 14081000 | 150000 | 13931000 | 14107664 | 13452505 | 0 | 0 | 0 | 13452505 | 14356886 | 103.1% | 1 | 904380 | 26664 | 31 | 8 | 0 | 0 | 26664 | 0 | 0 | 0 | 9390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11492 | 0 | 0 | 0 | 34538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82084 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-09 | QTR2 | 18/19 | 409 | 15571973.96
| 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 98.57% | 1 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 93.86% | 1 | 981 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46
| 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 79.2% | 1 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | 105.3% | 1 | -34322 | 31168 | 30 | 14 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 95.84% | 1 | 10 | 0 | 7 | 18 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07
| 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | 104% | 1 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 96.79% | 1 | 0 | 0 | 28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1
| 04 | T4466 | 42871815201 | 2017-07-26 | QTR1 | 17/18 | 5 | 1 | 388 | 441 | 411 | 92.27% | 1 | 30 | 0 | 0 | 53 | 0 | 3213996 | 50000 | 3163996 | 3213990 | 3033800 | 0 | 0 | 0 | 3033800 | 3135748 | 99.11% | 1 | 101948 | -6 | 23 | 30 | 0 | 0 | 19551 | 0 | 0 | 0 | 4848 | 8066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24399 | 8066 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-12-20 | QTR2 | 18/19 | 409 | 3457230.6
| 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 80% | 1 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 94.93% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 16 | 47 | 29 | 4362 | 5802 | 5657 | 100% | 16 | 145 | 4 | 0 | 1282 | 158 | 53948787 | 841395 | 53107394 | 54684079 | 52715560 | 0 | 37125 | 37125 | 52752685 | 53781999 | 100% | 16 | 1200791 | 735292 | 877 | 333 | 10 | 139 | 552987 | 270087 | 34 | -2 | 306162 | 79838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28880 | 0 | 0 | 29 | 88921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | -74175 | 0 | 72 | 158 | 902777 | 349925
| 04 | E4K92 | 41248925201 | 2010-11-30 | QTR2 | 10/11 | 7 | 17 | 1303 | 2546 | 2546 | 182.5% | 0 | 0 | 0 | 0 | 228 | 1015 | 94215000 | 150000 | 94065000 | 108647581 | 108420972 | 0 | 0 | 0 | 108420972 | 108204126 | 115% | 0 | -90707 | 14432581 | 86 | 82 | 0 | 288 | 1644087 | 1314542 | 0 | 220 | 2406319 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 60 | 507 | 10129365 | 2700545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1015 | 14293821 | 6446112 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 | 05/08/2018 | 2018-10-04 | QTR2 | 18/19 | 409 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 95.19% | 1 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | 102% | 1 | -2197408 | 3131122 | 99 | 57 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82927 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P08 | 42170755201 | 2014-03-25 | QTR3 | 13/14 | 7 | 23 | 1305 | 1810 | 1471 | 92.03% | 1 | 339 | 0 | 0 | 270 | 235 | 80437734 | 150000 | 80287734 | 82797035 | 82818636 | -283033 | -200000 | -483033 | 82335603 | 78160637 | 97.35% | 1 | -3880669 | 2359301 | 204 | 66 | 0 | 5 | -559751 | 0 | 0 | 27 | 763643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1957639 | 16706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 12319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76704 | 0 | 0 | 235 | 2097146 | 16706 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-06 | QTR3 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 412 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 102.6% | 1 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | 100% | 1 | -85027 | 475368 | 293 | 39 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75
| 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 117.3% | 1 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 101.6% | 1 | 93460 | 150444 | 82 | 28 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15
| 04 | E4R83 | 43482915201 | 2017-05-03 | QTR4 | 16/17 | 1 | 0 | 445 | 586 | 585 | 102.7% | 1 | 1 | 0 | 0 | 141 | 0 | 2949000 | 50000 | 2899000 | 2949000 | 2893000 | 0 | 0 | 0 | 2893000 | 2893000 | 99.79% | 1 | 0 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2019-01-28 | QTR3 | 18/19 | 412 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 107.2% | 1 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 95.22% | 1 | 26852 | 127760 | 93 | 24 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01
| 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 93.77% | 1 | 1375 | 0 | 46 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29
| 04 | E4S29 | 43059325201 | 2017-04-07 | QTR4 | 16/17 | 4 | 2 | 290 | 414 | 414 | 100% | 1 | 0 | 0 | 0 | 124 | 0 | 3060921 | 47591 | 3013330 | 3171379 | 2918996 | 0 | 0 | 0 | 2918996 | 2935462 | 97.42% | 1 | 54722 | 110457 | 74 | 50 | 0 | 0 | 2993 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79649 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 408 | 2506695.34
| 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 96.99% | 1 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 100.1% | 1 | 666 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22
| 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 98.08% | 1 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 98.62% | 1 | 5073 | 0 | 13 | 1 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43
| 04 | E4S43 | 44009015201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 290 | 412 | 411 | 107.2% | 1 | 1 | 0 | 0 | 122 | 0 | 2285285 | 50000 | 2235285 | 2435637 | 2385637 | 0 | 0 | 0 | 2385637 | 2385637 | 106.7% | 1 | 0 | 150352 | 64 | 36 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 150352 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 408 | 2071421.19 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 104.5% | 1 | 42636 | 74001 | 9 | 5 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 13 | 34 | 75 | 7012 | 10093 | 9668 | 92.31% | 12 | 425 | 0 | 0 | 1746 | 1335 | 286627992 | 991123 | 285636869 | 307639379 | 306059191 | -283033 | 300000 | 16967 | 306076158 | 299102053 | 92.31% | 12 | -6029027 | 21011386 | 1149 | 476 | 0 | 378 | 3282467 | 1872795 | 41 | 247 | 4704479 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 67 | 609 | 12391935 | 2728255 | 0 | 0 | 66256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73093 | 0 | 0 | 101 | 12319 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | -159631 | 0 | 121 | 1335 | 20484185 | 7032075
| District 04 Totals |  |  |  |  | 29 | 81 | 104 | 11374 | 15895 | 15325 | 96.55% | 28 | 570 | 4 | 0 | 3028 | 1493 | 340576779 | 1832518 | 338744263 | 362323458 | 358774751 | -283033 | 337125 | 54092 | 358828843 | 352884052 | 96.55% | 28 | -4828236 | 21746678 | 2026 | 809 | 10 | 517 | 3835454 | 2142882 | 75 | 245 | 5010641 | 2510863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 67 | 609 | 12420815 | 2728255 | 0 | 29 | 155177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73093 | 0 | 0 | 101 | 12319 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | -8 | -233806 | 0 | 193 | 1493 | 21386962 | 7382000
| 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 144.9% | 0 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | 112.7% | 0 | -1059964 | 5141650 | 119 | 57 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -230251 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 124.6% | 0 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | 113.3% | 0 | -1114008 | 4323245 | 93 | 58 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -110308 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55
| 05 | T5534 | 42875315201 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 600 | 763 | 765 | 97.83% | 1 | -2 | 2 | 0 | 178 | -15 | 10372492 | 109000 | 10263492 | 10929528 | 10898780 | -15534 | 0 | -15534 | 10883246 | 10869524 | 105.9% | 1 | 280079 | 557037 | 129 | 49 | 0 | 0 | 52612 | 0 | 0 | -26 | 22897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 246070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 321579 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 590 | 11601598.01 | B0 | ACC - LUMP SUM
| 05 | T5555 | 43543315201 | 2016-03-30 | QTR3 | 15/16 | 3 | 2 | 560 | 822 | 815 | 98.75% | 1 | 7 | 0 | 0 | 262 | 0 | 4783671 | 60000 | 4723671 | 4871035 | 5269309 | 0 | 0 | 0 | 5269309 | 5177510 | 109.6% | 1 | -4436 | 87364 | 212 | 50 | 0 | 0 | 19630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19630 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 514 | 6123685
| 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 79.21% | 1 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | 100.3% | 1 | -956254 | 370838 | 56 | 31 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | -130768 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 105.2% | 1 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 101.9% | 1 | 0 | 56481 | 144 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05
| 05 | T5575 | 43505715202 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 290 | 323 | 290 | 88.62% | 1 | 33 | 0 | 0 | 33 | 0 | 3075596 | 50000 | 3025596 | 3075596 | 2961552 | 0 | 0 | 0 | 2961552 | 2961571 | 97.88% | 1 | 19 | 0 | 11 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 13502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40320 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 512 | 4026582.45
| 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 135.2% | 0 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 97.3% | 1 | 6944 | 115263 | 65 | 40 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47
| 05 | T5580 | 43259215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 380 | 517 | 515 | 106.8% | 1 | 2 | 0 | 0 | 109 | 28 | 5833370 | 62000 | 5771370 | 5934096 | 5935419 | 0 | 0 | 0 | 5935419 | 6045029 | 104.7% | 1 | 126318 | 100726 | 78 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-09-13 | QTR1 | 18/19 | 514 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 110% | 1 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 107.7% | 1 | 13997 | 180307 | 159 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 |  | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12
| 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | 110% | 1 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 100.5% | 1 | 40280 | 52747 | 216 | 28 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772
| 05 | T5587 | 43505415201 | 2017-03-29 | QTR3 | 16/17 | 3 | 3 | 380 | 465 | 463 | 99.47% | 1 | 2 | 0 | 0 | 85 | 0 | 3220056 | 50000 | 3170056 | 3323115 | 3265140 | 0 | 0 | 0 | 3265140 | 3262109 | 102.9% | 1 | 0 | 103059 | 63 | 22 | 0 | 0 | 12084 | 0 | 0 | 0 | 87944 | 689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100028 | 689 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 514 | 4249077.7
| 05 | T5598 | 43566115201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 160 | 188 | 188 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 1387781 | 50000 | 1337781 | 1400208 | 1356596 | 0 | 0 | 0 | 1356596 | 1374428 | 102.7% | 1 | 17832 | 12427 | 24 | 4 | 0 | 0 | 1476 | 0 | 0 | 0 | 19164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20640 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 507 | 1627448
| 05 | T5600 | 43691515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 250 | 324 | 324 | 100% | 1 | 0 | 0 | 0 | 74 | 0 | 3294214 | 50000 | 3244214 | 3431595 | 3445345 | 0 | 0 | 0 | 3445345 | 3578158 | 110.3% | 0 | 132813 | 137381 | 30 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-10-23 | QTR2 | 18/19 | 513 | 4280329.25
| 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | 111.3% | 1 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 114% | 0 | 0 | 0 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-07-23 | QTR1 | 18/19 | 514 | 295435
| 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 163.1% | 0 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 190.6% | 0 | 1313 | 1131728 | 26 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65
| 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 89.58% | 1 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 106.4% | 1 | 504 | 5429 | 8 | 13 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 515 | 980597
| 05 | T5627 | 43730215201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 45 | 67 | 62 | 88.89% | 1 | 5 | 0 | 0 | 22 | 0 | 140000 | 15000 | 125000 | 140000 | 125000 | 0 | 0 | 0 | 125000 | 125000 | 100% | 1 | 0 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2019-03-22 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 514 | 315759
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 18 | 54 | 93 | 6465 | 9214 | 8978 | 77.78% | 14 | 236 | 33 | 0 | 2030 | 719 | 149737932 | 1203500 | 148534432 | 162113621 | 162578802 | -87626 | 986200 | 898574 | 163477376 | 160280298 | 72.22% | 13 | -2514563 | 12375682 | 1469 | 561 | 0 | 12 | 1915699 | 142753 | 0 | 440 | 6798256 | 2790029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 122 | 2030720 | 5853 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 175105 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 0 | 600 | 11206365 | 2982124
| 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 117.7% | 1 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | 99.18% | 1 | -89138 | 204028 | 174 | 49 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2019-01-16 | QTR3 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 78.16% | 1 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | 101.7% | 1 | -4400 | 21013 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83
| 05 | E5Y51 | 43832115201 | 2017-06-06 | QTR4 | 16/17 | 1 | 2 | 90 | 194 | 193 | 148.9% | 0 | 1 | 0 | 0 | 87 | 17 | 334599 | 16000 | 318599 | 541800 | 538448 | 0 | 0 | 0 | 538448 | 538448 | 169% | 0 | 0 | 207200 | 34 | 25 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-04-19 | QTR4 | 17/18 | 514 | 346552.2
| 05 | E5Y52 | 43632315201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 270 | 476 | 469 | 97.41% | 1 | 7 | 0 | 0 | 206 | 0 | 745547 | 38000 | 707547 | 745547 | 707547 | 0 | 0 | 0 | 707547 | 707547 | 100% | 1 | 0 | 0 | 167 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | QTR3 | 18/19 |  | 2018-12-14 | QTR2 | 18/19 | 513 | 805051.1
| 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 102.9% | 1 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 108.9% | 1 | 1238 | 76790 | 49 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25
| 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | 105.9% | 1 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 98.88% | 1 | 26994 | 156917 | 98 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03
| 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 111.3% | 1 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 101.3% | 1 | 5094 | 12031 | 26 | 24 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7
| 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 118.3% | 1 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 113.7% | 0 | 64762 | 233345 | 64 | 20 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928
| 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 105.5% | 1 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 103.2% | 1 | 0 | 0 | 60 | 6 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85
| 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 111.6% | 1 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 104.3% | 1 | 0 | 76090 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 98.67% | 1 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 103.6% | 1 | 13589 | 81060 | 48 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27
| 05 | E5Y95 | 43632515201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 380 | 491 | 481 | 105.3% | 1 | 10 | 0 | 0 | 81 | 30 | 2610610 | 50000 | 2560610 | 2610610 | 2553200 | 0 | 0 | 0 | 2553200 | 2553205 | 99.71% | 1 | 5 | 0 | 25 | 56 | 0 | 30 | 23553 | 0 | 0 | 0 | 4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 29994 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-12-26 | QTR2 | 18/19 | 513 | 3377422
| 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 102.6% | 1 | 9051 | 55693 | 56 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1
| 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 41.82% | 1 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 78.71% | 1 | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922
| 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 65.88% | 1 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 97.44% | 1 | 1173 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4
| 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 98.33% | 1 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 100% | 1 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2
| 05 | E5Z04 | 43927115201 | 2018-02-06 | QTR3 | 17/18 | 1 | 0 | 90 | 102 | 87 | 83.33% | 1 | 15 | 0 | 0 | 12 | 0 | 133664 | 5664 | 128000 | 133664 | 128000 | 0 | 0 | 0 | 128000 | 128000 | 100% | 1 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 515 | 123951
| 05 | E5Z05 | 43566615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 1 | 240 | 283 | 262 | 91.67% | 1 | 21 | 0 | 0 | 42 | 1 | 1687883 | 50000 | 1637883 | 1737883 | 1730756 | 0 | 0 | 0 | 1730756 | 1735963 | 106% | 1 | 5207 | 50000 | 23 | 19 | 0 | 0 | 50180 | 0 | 0 | 1 | 30589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 80769 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-12-18 | QTR2 | 18/19 | 512 | 1825766
| 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 99.55% | 1 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 100.6% | 1 | 0 | 0 | 28 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5Z29 | 43926915201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 997135 | 44635 | 952500 | 997135 | 952500 | 0 | 0 | 0 | 952500 | 952500 | 100% | 1 | 0 | 0 | 11 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-01-29 | QTR3 | 18/19 | 513 | 942335
| 05 | E5Z36 | 43987715201 | 2018-01-03 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 128 | 90.83% | 1 | 11 | 0 | 0 | 19 | 0 | 661369 | 44000 | 617369 | 661369 | 614161 | 0 | 50000 | 50000 | 664161 | 615476 | 99.69% | 1 | -48686 | 0 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-07-31 | QTR1 | 18/19 | 513 | 934116.2 | B1 | ACC - NO EXCUSE BONUS
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 21 | 31 | 30 | 5115 | 6918 | 6514 | 95.24% | 20 | 404 | 10 | 0 | 1530 | 273 | 37779403 | 847299 | 36932104 | 38953571 | 38173051 | -15840 | 50000 | 34160 | 38207211 | 37877122 | 90.48% | 19 | -15111 | 1174167 | 978 | 524 | 0 | 104 | 53544 | 0 | 28 | 81 | 649222 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 321273 | 34307 | 0 | 0 | 26561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 273 | 1050601 | 35185
| District 05 Totals |  |  |  |  | 39 | 85 | 123 | 11580 | 16132 | 15492 | 87.18% | 34 | 640 | 43 | 0 | 3560 | 992 | 187517335 | 2050799 | 185466536 | 201067192 | 200751853 | -103466 | 1036200 | 932734 | 201684587 | 198157420 | 82.05% | 32 | -2529674 | 13549849 | 2447 | 1085 | 0 | 116 | 1969243 | 142753 | 28 | 521 | 7447478 | 2790907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 210 | 2351993 | 40160 | 0 | 0 | 34220 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 175105 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 28 | 873 | 12256966 | 3017309
| 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 71.85% | 1 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | 106.2% | 1 | -258037 | 417799 | 96 | 21 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 |  | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 93.9% | 1 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | 104.3% | 1 | -1419938 | 811402 | 61 | 34 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6348 | 41247935201 | 2016-02-24 | QTR3 | 15/16 | 8 | 4 | 740 | 812 | 641 | 76.89% | 1 | 171 | 0 | 0 | 72 | 0 | 18181314 | 296819 | 17884495 | 17828896 | 17896535 | 0 | 800000 | 800000 | 18696535 | 17985610 | 100.6% | 1 | -663461 | -352418 | 36 | 36 | 0 | 0 | 72263 | 0 | 0 | 0 | 245801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464 | 0 | 0 | 0 | 16570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -502098 | 0 | 0 | 0 | -107072 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-22 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 606 | 18130045.8 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 90.38% | 1 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | 108.1% | 1 | -576452 | 893046 | 79 | 21 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 |  | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6390 | 43094915201 | 2017-02-22 | QTR3 | 16/17 | 5 | 6 | 380 | 464 | 460 | 98.95% | 1 | 4 | 0 | 0 | 84 | 0 | 4429507 | 54813 | 4374694 | 4700034 | 4434960 | 0 | 170000 | 170000 | 4604960 | 4569268 | 104.4% | 1 | -15734 | 270527 | 53 | 31 | 0 | 0 | 41640 | 0 | 0 | 0 | 31665 | 12923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171557 | 16087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244862 | 29011 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 606 | 5093915.35 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 78.57% | 1 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | 103.2% | 1 | -101955 | 0 | 31 | 6 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6412 | 43477815201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 120 | 205 | 205 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 292409 | 16584 | 275825 | 292409 | 300085 | 0 | 0 | 0 | 300085 | 304110 | 110.3% | 0 | 4025 | 0 | 70 | 15 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 335871.2
| 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 62.26% | 1 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | 96.92% | 1 | -136676 | 28195 | 44 | 25 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 118.3% | 1 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | 99.23% | 1 | -29328 | 147817 | 57 | 20 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35
| 06 | T6417 | 43476815201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 1228383 | 50000 | 1178383 | 1228383 | 1133929 | 0 | 0 | 0 | 1133929 | 1138502 | 96.62% | 1 | 4573 | 0 | 36 | 10 | 0 | 0 | 9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18218 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-11-19 | QTR2 | 18/19 | 606 | 1258750.05
| 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 97.54% | 1 | 5234 | 51632 | 63 | 25 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89
| 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 103.5% | 1 | 5618 | 63649 | 15 | 17 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55
| 06 | T6428 | 42765125201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 180 | 255 | 255 | 107.8% | 1 | 0 | 0 | 0 | 75 | 0 | 1069876 | 50735 | 1019141 | 1119876 | 1059386 | 0 | 0 | 0 | 1059386 | 1008320 | 98.94% | 1 | -51066 | 50000 | 53 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-09-27 | QTR1 | 18/19 | 606 | 1388000.3
| 06 | T6431 | 43787315201 | 2018-01-31 | QTR3 | 17/18 | 3 | 0 | 150 | 185 | 185 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 929676 | 42743 | 886933 | 929676 | 827030 | 0 | 0 | 0 | 827030 | 827669 | 93.32% | 1 | 639 | 0 | 24 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-22 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 606 | 881390.05
| 06 | T6432 | 43638515201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 178 | 176 | 98.67% | 1 | 2 | 0 | 0 | 28 | 0 | 627876 | 36563 | 591313 | 627876 | 619690 | 0 | 0 | 0 | 619690 | 620784 | 105% | 1 | 1093 | 0 | 20 | 8 | 0 | 0 | 16282 | 0 | 0 | 0 | 14379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31336 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-01 | QTR3 | 18/19 |  | 2018-10-19 | QTR2 | 18/19 | 606 | 756555.75
| 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 92.57% | 1 | 69 | 0 | 48 | 8 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 |  | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5
| 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 99.63% | 1 | 2695 | 0 | 57 | 8 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 17 | 66 | 46 | 5259 | 6547 | 5849 | 100% | 17 | 698 | 0 | 0 | 1288 | 0 | 101096707 | 1964451 | 99132256 | 103478357 | 103231163 | 0 | 3650000 | 3650000 | 106881163 | 103443476 | 94.12% | 16 | -3228701 | 2381649 | 843 | 304 | 106 | 0 | 1614770 | 0 | 21 | 0 | 1096643 | 31694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624265 | 81415 | 14 | 0 | 80834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -502098 | 0 | 141 | 0 | 2962343 | 113110
| 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 97.37% | 1 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | 69.81% | 1 | -593229 | 49068 | 214 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069
| 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 115.8% | 1 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 94.72% | 1 | 30910 | 125102 | 67 | 30 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65
| 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 102.9% | 1 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | 0% | 1 | -6008075 | 89950 | 52 | 49 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
| 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 77.23% | 1 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | 100% | 1 | -148006 | 51328 | 26 | 9 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K60 | 42736945201 | 2017-02-23 | QTR3 | 16/17 | 1 | 0 | 300 | 472 | 471 | 106.3% | 1 | 1 | 0 | 0 | 172 | 0 | 1911584 | 50000 | 1861584 | 1911584 | 1907123 | 0 | 0 | 0 | 1907123 | 1909046 | 102.5% | 1 | 1923 | 0 | 120 | 32 | 20 | 0 | 21089 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 26132 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-12-12 | QTR2 | 18/19 | 606 | 1951851.15
| 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 103.2% | 1 | 1161 | 0 | 13 | 7 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65
| 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 98.89% | 1 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 100% | 1 | 0 | 0 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5
| 06 | E6L12 | 43560115201 | 2017-01-26 | QTR3 | 16/17 | 3 | 6 | 280 | 429 | 429 | 112.5% | 1 | 0 | 0 | 0 | 149 | 0 | 3399874 | 50000 | 3349874 | 3718568 | 3635077 | 0 | 0 | 0 | 3635077 | 3617267 | 108% | 1 | 263 | 318693 | 92 | 22 | 35 | 0 | 25468 | 0 | 0 | 0 | 95370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 308050 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-02-20 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 606 | 3205032.5
| 06 | E6L18 | 43779215201 | 2017-10-26 | QTR2 | 17/18 | 1 | 0 | 150 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 676189 | 34902 | 641287 | 676189 | 658548 | 0 | 0 | 0 | 658548 | 659195 | 102.8% | 1 | 646 | 0 | 57 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-25 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 606 | 719637.75
| 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 98.05% | 1 | 9983 | 0 | 44 | 5 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940
| 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 98.89% | 1 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 93.76% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 11 | 28 | 17 | 2845 | 3944 | 3855 | 100% | 11 | 89 | 0 | 0 | 1085 | 14 | 26198273 | 521459 | 25676814 | 26832415 | 25776722 | 1584 | 180000 | 181584 | 25958306 | 19131018 | 100% | 11 | -6704424 | 634141 | 755 | 237 | 55 | 0 | 87921 | 4391 | 0 | 0 | 232298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 356558 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 14 | 655229 | 4391
| District 06 Totals |  |  |  |  | 28 | 94 | 63 | 8104 | 10491 | 9704 | 100% | 28 | 787 | 0 | 0 | 2373 | 14 | 127294980 | 2485910 | 124809070 | 130310772 | 129007885 | 1584 | 3830000 | 3831584 | 132839469 | 122574494 | 96.43% | 27 | -9933125 | 3015790 | 1598 | 541 | 161 | 0 | 1702691 | 4391 | 21 | 0 | 1328941 | 31694 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 980823 | 81415 | 14 | 0 | 126958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -502098 | 0 | 196 | 14 | 3617572 | 117501
| 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | 128.1% | 0 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | 107.9% | 1 | -544763 | 2295083 | 191 | 91 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14
| 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 105.4% | 1 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | 97.63% | 1 | -758630 | -138845 | 145 | 61 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST
| 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | 124.5% | 0 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | 99.61% | 1 | -887228 | 212174 | 208 | 57 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 |  | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03
| 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 117.4% | 1 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | 102.6% | 1 | -819849 | 1664895 | 92 | 66 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 0 | -113880 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 119.6% | 1 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 107.2% | 1 | 18982 | 298860 | 167 | 33 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22
| 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 120.7% | 0 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 111% | 0 | 25484 | 558900 | 42 | 15 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS
| 07 | T7387 | 42895415201 | 2016-06-15 | QTR4 | 15/16 | 3 | 8 | 435 | 735 | 733 | 117.2% | 1 | 2 | 0 | 0 | 223 | 77 | 17840000 | 150000 | 17690000 | 18339077 | 18567408 | 0 | 0 | 0 | 18567408 | 18654250 | 105.5% | 1 | 128181 | 499077 | 175 | 48 | 0 | 45 | 212755 | 0 | 0 | 28 | 205993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 461583 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 714 | 19115045.32
| 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 119.4% | 1 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 105% | 1 | 44854 | 30781 | 47 | 20 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5
| 07 | T7392 | 43484115202 | 2017-05-24 | QTR4 | 16/17 | 3 | 1 | 210 | 384 | 331 | 84.76% | 1 | 53 | 0 | 0 | 153 | 21 | 5679793 | 50000 | 5629793 | 5828296 | 5798728 | 0 | 0 | 0 | 5798728 | 5859621 | 104.1% | 1 | 60893 | 148503 | 55 | 98 | 0 | 21 | 148503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 148503 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-10-11 | QTR2 | 18/19 | 796 | 4416000
| 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 99.68% | 1 | 6464 | 0 | 31 | 18 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000
| 07 | T7405 | 43649015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 140 | 161 | 146 | 89.29% | 1 | 15 | 0 | 0 | 21 | 0 | 2235958 | 50000 | 2185958 | 2384716 | 2283562 | 0 | 0 | 0 | 2283562 | 2395779 | 109.6% | 1 | 112217 | 148758 | 18 | 3 | 0 | 0 | 58523 | 0 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 798 | 3540000
| 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 98% | 1 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 97.78% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 799 | 446330
| 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 32.5% | 1 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 82.71% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 13 | 52 | 90 | 5305 | 7639 | 7769 | 76.92% | 10 | -130 | 255 | 0 | 1779 | 555 | 152548712 | 1489815 | 151058898 | 158266900 | 158714391 | -194668 | -400000 | -594668 | 158119723 | 155213776 | 92.31% | 12 | -2613395 | 5718186 | 1175 | 515 | 43 | 106 | 2271342 | 125339 | 14 | 245 | 3223374 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 87043 | 0 | 32 | 0 | 75559 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 409440 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 555 | 6054553 | 947114
| 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 90.54% | 1 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | 103.6% | 1 | -54636 | 367480 | 145 | 40 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000
| 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 90% | 1 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | 94.1% | 1 | -18692 | 37019 | 42 | 23 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200
| 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 115% | 1 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 113.6% | 0 | 25327 | -19 | 20 | 0 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000
| 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 108.1% | 1 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 109% | 1 | 0 | 78500 | 39 | 28 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM
| 07 | E7L82 | 43269715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 4 | 280 | 389 | 388 | 101.8% | 1 | 1 | 0 | 0 | 103 | 6 | 4654737 | 50000 | 4604737 | 4707294 | 4587650 | 0 | 0 | 0 | 4587650 | 4635460 | 100.7% | 1 | 47810 | 52556 | 86 | 17 | 0 | 6 | 2664 | 0 | 0 | 0 | 2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12827 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-24 | QTR1 | 18/19 | 798 | 5246589.53
| 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 92.5% | 1 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 94.2% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 |  | 2018-09-12 | QTR1 | 18/19 | 796 | 320000
| 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 94% | 1 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 103.9% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 796 | 310000
| 07 | E7L96 | 43966215201 | 2018-03-14 | QTR3 | 17/18 | 1 | 0 | 300 | 329 | 152 | 41% | 1 | 177 | 0 | 0 | 29 | 0 | 1051194 | 50000 | 1001194 | 1051194 | 908881 | 0 | 0 | 0 | 908881 | 908881 | 90.78% | 1 | 0 | 0 | 11 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-02-13 | QTR3 | 18/19 | 796 | 1997000
| 07 | E7M01 | 43070515201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 88 | 136 | 125 | 87.5% | 1 | 11 | 0 | 0 | 48 | 0 | 633485 | 32000 | 601485 | 633485 | 652234 | 0 | 0 | 0 | 652234 | 652234 | 108.4% | 1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 796 | 643100
| 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 68.33% | 1 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 102.4% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 796 | 225000
| 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | 101.8% | 1 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 98.71% | 1 | 0 | 0 | 155 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 11 | 13 | 10 | 2047 | 2810 | 2527 | 100% | 11 | 283 | 7 | 0 | 723 | 40 | 17835155 | 402500 | 17432655 | 18370692 | 17936141 | -19677 | 0 | -19677 | 17916464 | 17841725 | 90.91% | 10 | -191 | 535536 | 541 | 182 | 0 | 15 | 369033 | 18033 | 0 | 25 | 102400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23606 | 0 | 0 | 0 | 10256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 505294 | 18033
| District 07 Totals |  |  |  |  | 24 | 65 | 100 | 7352 | 10449 | 10296 | 87.5% | 21 | 153 | 262 | 0 | 2502 | 595 | 170383867 | 1892315 | 168491553 | 176637592 | 176650532 | -214345 | -400000 | -614345 | 176036187 | 173055501 | 91.67% | 22 | -2613586 | 6253722 | 1716 | 697 | 43 | 121 | 2640375 | 143372 | 14 | 270 | 3325774 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 110649 | 0 | 32 | 0 | 85815 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 409440 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 595 | 6559847 | 965147
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 105.2% | 1 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | 100% | 1 | -1273624 | 1280759 | 147 | 47 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35903 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 99.36% | 1 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | 97.16% | 1 | -695637 | 0 | 56 | 25 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR
| 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 108.6% | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | 109.2% | 1 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78
| 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 101% | 1 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 99.06% | 1 | 64151 | -44570 | 40 | 28 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104904 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 |  | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64
| 08 | E8Q45 | 43516615201 | 2017-03-28 | QTR3 | 16/17 | 4 | 7 | 245 | 377 | 376 | 107.3% | 1 | 1 | 0 | 0 | 113 | 19 | 10174450 | 99451 | 10074999 | 10442695 | 10222974 | 0 | 0 | 0 | 10222974 | 10331810 | 102.5% | 1 | 132458 | 268245 | 69 | 44 | 0 | 0 | 34793 | 0 | 0 | 12 | 180668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 0 | 0 | 7 | 64962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 282868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 854 | 10340089.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 223 | 85.93% | 1 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 103% | 1 | 2 | 0 | 78 | 29 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07
| 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | 142.8% | 0 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 99.9% | 1 | 0 | 9613 | 32 | 17 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31
| 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 107.1% | 1 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 92.96% | 1 | 306 | 51808 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 8 | 18 | 35 | 3150 | 4117 | 4100 | #VALUE! | 7 | 17 | 26 | 0 | 820 | 147 | 112593680 | 701085 | 111892595 | 115205166 | 114093553 | -66684 | 0 | -66684 | 114026869 | 111970226 | 100% | 8 | -1778452 | 2611486 | 517 | 262 | 0 | 0 | 961283 | 0 | 0 | 50 | 773788 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56 | 519360 | 0 | 0 | 7 | 74534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 41 | 147 | 2468004 | 178000
| District 08 Totals |  |  |  |  | 8 | 18 | 35 | 3150 | 4117 | 4100 | 87.5% | 7 | 17 | 26 | 0 | 820 | 147 | 112593680 | 701085 | 111892595 | 115205166 | 114093553 | -66684 | 0 | -66684 | 114026869 | 111970226 | 100% | 8 | -1778452 | 2611486 | 517 | 262 | 0 | 0 | 961283 | 0 | 0 | 50 | 773788 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56 | 519360 | 0 | 0 | 7 | 74534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 41 | 147 | 2468004 | 178000
| Statewide Central Let Contracts SubTotal |  |  |  |  | 135 | 335 | 475 | 40625 | 56786 | 55551 | 83.7% | 113 | 1235 | 732 | 0 | 13560 | 2610 | 949564610 | 10021164 | 939543450 | 985189199 | 981995979 | -710922 | 10399325 | 9688403 | 991684382 | 964514336 | 91.85% | 124 | -25010617 | 35624579 | 8606 | 3502 | 255 | 599 | 10856787 | 739785 | 547 | 1262 | 17471833 | 4352662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83663 | 0 | 468 | 269 | 4726224 | 1191500 | 49 | 33 | 961998 | 132792 | 0 | 0 | -1650 | 0 | 0 | 69 | 462675 | 49174 | 0 | 46 | 2801861 | 1757621 | 48 | 213 | 665938 | 615948 | 0 | 0 | -65990 | 0 | 0 | -18 | -1630093 | 0 | 1367 | 2473 | 36333254 | 8839481
| Statewide District Let Contracts SubTotal |  |  |  |  | 110 | 189 | 248 | 31616 | 43772 | 42006 | 90.91% | 100 | 1766 | 133 | 0 | 9293 | 2863 | 786735042 | 5768573 | 780966468 | 822543127 | 813431807 | -1198258 | 605000 | -593258 | 812838549 | 793924339 | 91.82% | 101 | -16901721 | 35808084 | 5452 | 2813 | 319 | 738 | 4901240 | 2043848 | 72 | 759 | 9059447 | 2933657 | 0 | 0 | -11004 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 200650 | 0 | 121 | 950 | 14807830 | 2762562 | 0 | 53 | 223731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201897 | 0 | 0 | 203 | 6214069 | 4950000 | 453 | 160 | 416817 | 0 | 25 | 0 | -782 | 0 | 0 | 0 | -719639 | 0 | 990 | 2863 | 35226580 | 12690067
| Statewide Totals |  |  |  |  | 245 | 524 | 723 | 72241 | 100558 | 97557 | 86.94% | 213 | 3001 | 865 | 0 | 22853 | 5473 | 1736299652 | 15789737 | 1720509918 | 1807732326 | 1795427786 | -1909180 | 11004325 | 9095145 | 1804522931 | 1758438675 | 91.84% | 225 | -41912338 | 71432663 | 14058 | 6315 | 574 | 1337 | 15758027 | 2783633 | 619 | 2021 | 26531280 | 7286319 | 0 | 0 | -11004 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 284313 | 0 | 589 | 1219 | 19534054 | 3954062 | 49 | 86 | 1185729 | 132792 | 0 | 0 | -1650 | 0 | 0 | 69 | 664572 | 49174 | 0 | 249 | 9015930 | 6707621 | 501 | 373 | 1082755 | 615948 | 25 | 0 | -66772 | 0 | 0 | -18 | -2349732 | 0 | 2357 | 5336 | 71559834 | 21529548

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1K75 | 20121435201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2012-06-21 | 21206552 | 22730499 | 22650387 | 1523947.09 | 0 | 21992288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1P47 | 43771415201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-10-19 | 161810 | 161810 | 145518 | 0 | 0 | 145518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145518 | 145518 | 0 | 119062
1 | E1Q20 | 43979815201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2017-03-16 | 551623 | 557534 | 539909 | 5910.12 | -19008 | 520901 | -19008 | 0 | 0 | 0 | 0 | 0 | -19008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19008 | 520901 | 520901 | 0 | 682344
1 | E1Q21 | 41773349201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-22 | 5353535 | 5368855 | 5313014 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5313014 | 0 | -5313014 | 5530217
1 | E1Q22 | 43854515201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-05-01 | 3614066 | 3616288 | 3562935 | 2222 | 0 | 3562935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562935 | 3562935 | 0 | 5496031
1 | E1Q46 | 43659915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-20 | 2486667 | 2519936 | 2394841 | 33269.19 | 0 | 2475891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 2833103
1 | E1Q64 | 43445715201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-19 | 429966 | 429966 | 399604 | 0 | 0 | 399697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399604 | 399697 | 94 | 450407
1 | E1Q75 | 43659815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-09-21 | 3257627 | 3257627 | 3147613 | 0 | 0 | 3241869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 3831011
1 | E1Q76 | 43494115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 3162332 | 3162332 | 3141539 | 0 | 0 | 3230031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 3398633 | B0 | ACC - LUMP SUM
1 | E1R00 | 43798415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 399878 | 414572 | 373225 | 14694.4 | 50000 | 373225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 410605 | B1 | ACC - NO EXCUSE BONUS
1 | E1R01 | 43668415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-01-25 | 367307 | 367307 | 318382 | 0 | 25000 | 318382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 312418 | B1 | ACC - NO EXCUSE BONUS
1 | E1R02 | 44026315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-11-16 | 253030 | 253030 | 240240 | 0 | 0 | 240240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240240 | 240240 | 0 | 210004 | B0 | ACC - LUMP SUM
1 | E1R04 | 44035915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-01-18 | 356611 | 356611 | 333569 | 0 | 0 | 333569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333569 | 333569 | 0 | 390669
1 | E1R09 | 43903015201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-05-17 | 279115 | 279115 | 264760 | 0 | 0 | 264760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264760 | 264760 | 0 | 214242
1 | E1R10 | 44124915201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-04-19 | 103556 | 103556 | 90107 | 0 | 0 | 94096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90107 | 94096 | 3989 | 92976
1 | E1R47 | 43320215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 542243 | 542243 | 514134 | 0 | 0 | 514134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514134 | 514134 | 0 | 573290 | B0 | ACC - LUMP SUM
1 | E1R55 | 43902615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-15 | 402836 | 402836 | 380287 | 0 | 0 | 381602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380287 | 381602 | 1315 | 497103
1 | T1550 | 41304445201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2013-06-19 | 35638696 | 36288093 | 36921189 | 649397.13 | -20000 | 33902534 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 36725854
1 | T1576 | 19690445201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 28940681 | 30877320 | 31050834 | 1936639.27 | 0 | 28268809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050834 | 28268809 | -2782025 | 36280174
1 | T1606 | 19801745201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2015-06-17 | 16630324 | 16297713 | 16277472 | -332611.69 | -39000 | 15990772 | 0 | 0 | 0 | 0 | 0 | -39000 | -39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39000 | 16238472 | 15990772 | -247700 | 16471202 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1621 | 20103245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-05-27 | 74506000 | 75835652 | 75066323 | 1329652.15 | 4948000 | 73395413 | 0 | 0 | 0 | 0 | 0 | -52000 | -52000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 4948000 | 80014323 | 73395413 | -6618910 | 93729882 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
1 | T1623 | 43127815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3845363 | 3770865 | 3824811 | -74498 | 0 | 3725877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824811 | 3725877 | -98934 | 4062053 | B0 | ACC - LUMP SUM
1 | T1646 | 43275515202 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 3883072 | 3988230 | 4003713 | 105157.94 | 0 | 3948636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4003713 | 3948636 | -55078 | 4572143
1 | T1653 | 43317315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 3821588 | 3892256 | 3742414 | 70667.91 | 0 | 3747080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742414 | 3747080 | 4666 | 2964599
1 | T1660 | 43161915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-09-28 | 2357000 | 2424704 | 2337783 | 67704.15 | 0 | 2292169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337783 | 2292169 | -45614 | 3040685
1 | T1666 | 43289715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 3057226 | 3156754 | 3084177 | 99527.99 | 0 | 3093877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3084177 | 3093877 | 9700 | 3786427
1 | T1672 | 43660015201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 5457714 | 5650306 | 5444515 | 192591.74 | 0 | 5606803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5444515 | 5606803 | 162288 | 5914612
1 | T1673 | 42063335201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-12-07 | 14067161 | 14287522 | 13878587 | 220361.5 | 550000 | 13800963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000 | 550000 | 14428587 | 13800963 | -627624 | 16781376 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1674 | 43450515201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 739854 | 739854 | 710515 | 0 | -83952 | 655747 | -83952 | 0 | 0 | 0 | 0 | 0 | -83952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83952 | 626563 | 655747 | 29184 | 559471 | B0 | ACC - LUMP SUM
1 | T1678 | 43492915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 7590540 | 7638810 | 7645659 | 48270.16 | 0 | 7687725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7645659 | 7687725 | 42066 | 9127943
1 | T1683 | 43177215201 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1414597 | 1414597 | 1411808 | 0 | 0 | 1416013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 1198143
1 | T1685 | 44011715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 165758 | 165758 | 159130 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159130 | 159130 | 0 | 163746
1 | T1686 | 43318815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 304735 | 321566 | 321566 | 16831.45 | 0 | 322093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321566 | 322093 | 527 | 339200 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1687 | 41304245201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 28672708 | 28693379 | 27612242 | 20670.98 | 1070000 | 28337974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070000 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | -344268 | 35334897 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1688 | 43498415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 440840 | 440840 | 440840 | 0 | 0 | 440840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440840 | 440840 | 0 | 446099 | B0 | ACC - LUMP SUM
1 | T1692 | 43911115201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 548549 | 548549 | 543483 | 0 | 0 | 543785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543483 | 543785 | 302 | 566923 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1694 | 43513615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 548555 | 542272 | 512417 | -6283.3 | 0 | 513325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512417 | 513325 | 908 | 613009 | B0 | ACC - LUMP SUM
1 | T1698 | 43656715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-10-25 | 3413203 | 3565928 | 3599216 | 152724.34 | 0 | 3691649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 3320587
1 | T1699 | 43698315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-01-31 | 338000 | 345335 | 345335 | 7334.62 | 0 | 345335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345335 | 345335 | 0 | 381548
1 | T1703 | 43668315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 430933 | 430933 | 404140 | 0 | 0 | 404140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404140 | 404140 | 0 | 395408 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1710 | 43795915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-03-28 | 1395501 | 1395501 | 1301640 | 0 | 100000 | 1301762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 1401640 | 1301762 | -99878 | 1196300 | B1 | ACC - NO EXCUSE BONUS
1 | T1716 | 43506315201 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 172083 | 172083 | 163237 | 0 | 0 | 163237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1726 | 44016215201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 253590 | 253590 | 253590 | 0 | 0 | 253590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253590 | 253590 | 0 | 256718 | B0 | ACC - LUMP SUM
1 | T1728 | 43501715201 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2018-07-25 | 141143 | 141143 | 141143 | 0 | 0 | 141143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141143 | 141143 | 0 | 128588 | B0 | ACC - LUMP SUM
1 | T1730 | 43132415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-07-25 | 465432 | 465432 | 465432 | 0 | 0 | 465432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465432 | 465432 | 0 | 319734 | B0 | ACC - LUMP SUM
1 | T1A07 | 19389825201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2014-09-24 | 30690000 | 31355347 | 30709376 | 665347.31 | -599125 | 28122793 | 0 | 0 | 0 | 0 | 0 | -5125 | -5125 | 0 | 0 | 0 | 0 | -594000 | 0 | -594000 | -599125 | 30110251 | 28122793 | -1987458 | 31874470 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1A16 | 43609215201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-29 | 18880004 | 19841188 | 19816523 | 961184.32 | 0 | 19628809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19816523 | 19628809 | -187714 | 24424913
2 | E2R81 | 43182025203 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2014-03-20 | 2916419 | 2916419 | 0 | 0 | 0 | 5517906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5517906 | 5517906 | 1374261 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
2 | E2R91 | 41650145201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-06-26 | 66725725 | 67223879 | 66965314 | 498153.71 | -795600 | 64716827 | -795600 | 0 | 0 | 0 | 0 | 0 | -795600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -795600 | 66169714 | 64716827 | -1452887 | 83530874 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2T36 | 42442415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-05-13 | 10725121 | 12250426 | 12633691 | 1525305.59 | 0 | 12633279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12633691 | 12633279 | -412 | 11100158
2 | E2U34 | 43025815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-20 | 4266548 | 4515459 | 4762225 | 248911.81 | 0 | 4739499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762225 | 4739499 | -22727 | 3812868
2 | E2U40 | 43015815201 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2016-01-20 | 4367770 | 4673447 | 4944003 | 305677.35 | 0 | 4894801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4944003 | 4894801 | -49202 | 4165393
2 | E2U49 | 43074915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-18 | 5878818 | 6117316 | 6222842 | 238498.65 | 0 | 6229444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6222842 | 6229444 | 6601 | 7361145
2 | E2V29 | 43230815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-21 | 4657688 | 4559112 | 3935337 | -98576.18 | 0 | 3971054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | 3479383
2 | E2V63 | 43860115201 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-05-17 | 1160401 | 1188813 | 1137166 | 28412.16 | 0 | 1137166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 567894
2 | E2V64 | 43075815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 2185756 | 2190082 | 2087115 | 4326.32 | 0 | 2087236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 1534480
2 | E2V65 | 43432315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 3583873 | 3643220 | 3692989 | 59346.81 | 0 | 3723122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3692989 | 3723122 | 30133 | 3819418
2 | E2W07 | 43240515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-15 | 1148442 | 1148442 | 1142933 | 0 | 0 | 1143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 1300556
2 | E2W74 | 43430315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2821185 | 3316043 | 3357671 | 494858.16 | 0 | 3533274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 2864650
2 | E2W86 | 43239515201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2017-11-30 | 567579 | 567579 | 542982 | 0 | 0 | 542982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542982 | 542982 | 0 | 529605
2 | E2W87 | 43616615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 2286714 | 2286714 | 2234139 | 0 | 0 | 2316470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2234139 | 2316470 | 82331 | 2718058
2 | E2W88 | 42849415201 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2017-12-20 | 290000 | 290000 | 255859 | 0 | 0 | 255859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255859 | 255859 | 0 | 444333
2 | E2W93 | 43433815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-01-17 | 594594 | 594594 | 581178 | 0 | 0 | 581178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581178 | 581178 | 0 | 613772
2 | E2W97 | 43859915201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 876044 | 888420 | 862161 | 12376.67 | 0 | 862161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862161 | 862161 | 0 | 586122
2 | E2W98 | 43860015201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 667932 | 667932 | 646774 | 0 | 0 | 646774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646774 | 646774 | 0 | 484902
2 | T2534 | 21071235201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 18473682 | 19314640 | 18859990 | 840958.13 | 0 | 17612606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 20202367
2 | T2547 | 42975025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1879929 | 1879929 | 1845519 | 0 | -97552 | 1685674 | -97552 | 0 | 0 | 0 | 0 | 0 | -97552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97552 | 1747967 | 1685674 | -62293 | 1922742
2 | T2568 | 21002845201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 13869804 | 13966295 | 14129834 | 96491.28 | 0 | 13763782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14129834 | 13763782 | -366052 | 14411194
2 | T2569 | 42870115201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 9199000 | 9915585 | 9871416 | 716584.65 | 0 | 9657046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 9784025
2 | T2596 | 43055615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 4955711 | 4955711 | 4972503 | 0 | 0 | 4810311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 4219707
2 | T2611 | 42880415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 16425368 | 17429243 | 17737903 | 1003874.73 | 0 | 17879661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17737903 | 17879661 | 141758 | 14976803
2 | T2623 | 42747425201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 12006916 | 12006916 | 12019761 | 0 | 0 | 12020496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12019761 | 12020496 | 735 | 12840720
2 | T2624 | 21327285201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 11345332 | 11381404 | 10274352 | 36071.98 | 0 | 10274503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 11100491
2 | T2625 | 43091415201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 4913266 | 5029801 | 5053902 | 116534.61 | 0 | 5063705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5053902 | 5063705 | 9803 | 4921245
2 | T2633 | 42890015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-07-27 | 1780206 | 1780206 | 1730267 | 0 | 0 | 1730271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 1648989
2 | T2643 | 43434015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-12-07 | 1483252 | 1483252 | 1482220 | 0 | 0 | 1482220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 1682912
2 | T2648 | 43231015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1797592 | 1797592 | 1737333 | 0 | 0 | 1782037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 1880670
2 | T2655 | 43231215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 6450313 | 6457361 | 6610843 | 7048 | 0 | 6637036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6610843 | 6637036 | 26193 | 6643070
2 | T2659 | 43432715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | 2042000 | 2042000 | 1988747 | 0 | 0 | 1988836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 2336444
2 | T2665 | 43056015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-05-24 | 5734638 | 5786567 | 5728746 | 51928.64 | 0 | 5836409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5728746 | 5836409 | 107663 | 4851775
2 | T2666 | 43543915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 1101105 | 1107513 | 1035052 | 6407.67 | -17424 | 1017749 | -17424 | 0 | 0 | 0 | 0 | 0 | -17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17424 | 1017628 | 1017749 | 121 | 969731
2 | T2671 | 43601015201 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 928314 | 932800 | 849315 | 4485.92 | 0 | 851029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 1119164
2 | T2674 | 43335915201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-08-30 | 360929 | 360929 | 343649 | 0 | 0 | 343649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343649 | 343649 | 0 | 413832
2 | T2676 | 43617515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 1623696 | 1623696 | 1601844 | 0 | 0 | 1623655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 1682997
2 | T2677 | 43616715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 3488727 | 3488727 | 3422691 | 0 | 0 | 3561473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3422691 | 3561473 | 138781 | 3968191
2 | T2681 | 43499615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1999378 | 1999378 | 1930362 | 0 | 0 | 1930362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1930362 | 1930362 | 0 | 2290723
3 | E3K83 | 41506725201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2012-11-20 | 13915054 | 14699375 | 14628947 | 784321.33 | 0 | 14470162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14628947 | 14470162 | -158785 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR
3 | E3L23 | 22066425201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2013-06-06 | 118555712 | 122527138 | 122423398 | 3971426.3 | 0 | 121441548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
3 | E3P21 | 42358825201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 957789 | 957789 | 938474 | 0 | 0 | 938604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938474 | 938604 | 130 | 1276000
3 | E3P35 | 40674235201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-11-09 | 2284367 | 2284367 | 2177088 | 0 | 0 | 2177088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177088 | 2177088 | 0 | 4068631
3 | E3P64 | 40747855201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2017-10-12 | 477560 | 477560 | 464944 | 0 | 0 | 464944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464944 | 464944 | 0 | 607325
3 | E3Q40 | 43375215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 782920 | 809439 | 800466 | 26519.13 | 0 | 800466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800466 | 800466 | 0 | 616285
3 | E3Q60 | 43625715201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 3348662 | 3348662 | 3418381 | 0 | 0 | 3499945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 4130313
3 | E3Q73 | 43966115201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 2101129 | 2228653 | 2084234 | 127524 | 0 | 2094333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 2065000
3 | E3Q80 | 44014815201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-11-09 | 673414 | 676414 | 651186 | 3000 | 0 | 652131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651186 | 652131 | 945 | 670663
3 | E3Q91 | 43626815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-09 | 3258297 | 3274221 | 3353918 | 15923.57 | 0 | 3489125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353918 | 3489125 | 135206 | 4488229
3 | E3R24 | 43626915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-08 | 696272 | 696272 | 637670 | 0 | 0 | 637670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637670 | 637670 | 0 | 945342
3 | T3417 | 42282315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 9576952 | 11201952 | 11381048 | 1625000 | 0 | 11259809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11381048 | 11259809 | -121240 | 11869074
3 | T3474 | 41110245201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 13521855 | 14023931 | 14165918 | 502075.52 | 0 | 13122088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14165918 | 13122088 | -1043829 | 12749353
3 | T3481 | 42884615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-10-28 | 2080005 | 2526152 | 2551459 | 446147.09 | 0 | 2552942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 1782971
3 | T3498 | 43178515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 4274307 | 4324307 | 4294029 | 50000 | -8433 | 4353335 | -8433 | 0 | 0 | 0 | 0 | 0 | -8433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8433 | 4285596 | 4353335 | 67739 | 4281516
3 | T3538 | 43357615201 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2015-06-17 | 90288 | 88663 | 74180 | -1624.32 | 0 | 74180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74180 | 74180 | 0 | 110499 | B0 | ACC - LUMP SUM
3 | T3559 | 22247625201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-03 | 8545785 | 11162923 | 11805411 | 2617137.98 | -19500 | 11760527 | 0 | 0 | 0 | 0 | 0 | -19500 | -19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19500 | 11785911 | 11760527 | -25384 | 7955703
3 | T3565 | 43046915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 2384550 | 2459882 | 2385269 | 75331.94 | 0 | 2385420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 1900106
3 | T3567 | 43046515201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1966055 | 1981055 | 2001427 | 15000 | -15840 | 2007278 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 1985587 | 2007278 | 21691 | 1970433
3 | T3568 | 41347915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-09-28 | 3041965 | 3062656 | 3259199 | 20690.94 | 0 | 3266655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 3211894
3 | T3596 | 43274015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 8173983 | 8193029 | 8770491 | 19046.28 | -4500 | 8814288 | 0 | 0 | 0 | 0 | 0 | -4500 | -4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4500 | 8765991 | 8814288 | 48297 | 8245135
3 | T3615 | 42695015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 8847725 | 8863488 | 9356628 | 15762.61 | 0 | 9479788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 8456773
3 | T3634 | 43256215201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 2317459 | 2317459 | 2243858 | 0 | 0 | 2321931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243858 | 2321931 | 78073 | 2451818
3 | T3636 | 43188325201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 723562 | 725163 | 672253 | 1600.5 | -7800 | 664453 | 0 | 0 | 0 | 0 | 0 | -7800 | -7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7800 | 664453 | 664453 | 0 | 819000
3 | T3638 | 43461115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 5256385 | 5256385 | 5540831 | 0 | -7290 | 5791591 | -7290 | 0 | 0 | 0 | 0 | 0 | -7290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7290 | 5533541 | 5791591 | 258050 | 5826403
3 | T3641 | 43255115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 526927 | 555025 | 528915 | 28098.65 | -14500 | 514415 | 0 | 0 | 0 | 0 | 0 | -14500 | -14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14500 | 514415 | 514415 | 0 | 561927 | B0 | ACC - LUMP SUM
3 | T3644 | 43671915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1719994 | 1712869 | 1658491 | -7124.92 | -28512 | 1643036 | -28512 | 0 | 0 | 0 | 0 | 0 | -28512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28512 | 1629979 | 1643036 | 13058 | 1688041
3 | T3647 | 43626015201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 741004 | 719710 | 672328 | -21294.4 | 0 | 672328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672328 | 672328 | 0 | 1013516 | B0 | ACC - LUMP SUM
3 | T3650 | 43014645201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3298431 | 3312865 | 3444996 | 14433.44 | 0 | 3477423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 4395538
3 | T3651 | 43014665201 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1867503 | 1867503 | 1819486 | 0 | 0 | 1842390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 2105531
3 | T3677 | 43467515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2607729 | 2610160 | 2714487 | 2430.66 | -7200 | 2805120 | 0 | 0 | 0 | 0 | 0 | -7200 | -7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7200 | 2707287 | 2805120 | 97833 | 3422498
4 | E4K92 | 41248925201 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2010-11-30 | 94215000 | 108647581 | 108420972 | 14432580.84 | 0 | 108330265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108420972 | 108330265 | -90707 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4N44 | 42170765201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-07-24 | 74960000 | 78091122 | 78080272 | 3131121.83 | 500000 | 76382864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 78580272 | 76382864 | -2197408 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P08 | 42170755201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-03-25 | 80437734 | 82797035 | 82818636 | 2359301.26 | -483033 | 78454934 | -283033 | 0 | 0 | 0 | 0 | 0 | -283033 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -483033 | 82335603 | 78454934 | -3880669 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q93 | 43120415201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-04-03 | 9297344 | 9772712 | 9607342 | 475367.61 | 0 | 9522316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9607342 | 9522316 | -85027 | 9241086
4 | E4R63 | 43060215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-05-06 | 9397416 | 9547860 | 9424445 | 150444.28 | 0 | 9517905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9424445 | 9517905 | 93460 | 9034278
4 | E4R83 | 43482915201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-05-03 | 2949000 | 2949000 | 2893000 | 0 | 0 | 2893000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2893000 | 2893000 | 0 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4R89 | 43234915201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2016-09-02 | 4719445 | 4847205 | 4456560 | 127759.9 | 0 | 4483412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4456560 | 4483412 | 26852 | 5266696
4 | E4R95 | 43115625201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | 2267494 | 2267494 | 2078018 | 0 | 0 | 2079393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 2587772
4 | E4S29 | 43059325201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-04-07 | 3060921 | 3171379 | 2918996 | 110457.34 | 0 | 2973718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2918996 | 2973718 | 54722 | 2506695
4 | E4S30 | 43111015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-07 | 419035 | 419035 | 393248 | 0 | 0 | 393914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393248 | 393914 | 666 | 602726
4 | E4S37 | 43716515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-05 | 549000 | 549000 | 512495 | 0 | 0 | 517567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 504683
4 | E4S43 | 44009015201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 2285285 | 2435637 | 2385637 | 150351.5 | 0 | 2385637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385637 | 2385637 | 0 | 2071421 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4S80 | 43609515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 2070318 | 2144319 | 2069570 | 74001.34 | 0 | 2112206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 1656846
4 | T4395 | 42936515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 1928000 | 1932802 | 1674394 | 4801.64 | 0 | 1674394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674394 | 1674394 | 0 | 1544788
4 | T4409 | 43019215201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-05-20 | 4789933 | 5042467 | 4996786 | 252534.18 | 0 | 4982280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4996786 | 4982280 | -14505 | 5274241 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | T4422 | 43257425201 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2016-12-07 | 4613776 | 4938807 | 4932678 | 325030.9 | 0 | 4925308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4932678 | 4925308 | -7370 | 4236194
4 | T4439 | 42872515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 4580758 | 4651658 | 4514932 | 70899.67 | 0 | 4518968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4514932 | 4518968 | 4036 | 4467828 | B0 | ACC - LUMP SUM
4 | T4445 | 43060315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 8418937 | 8403485 | 8476613 | -15452.13 | 0 | 8727744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8476613 | 8727744 | 251131 | 9837148
4 | T4446 | 43294915201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 2621390 | 2636483 | 2515200 | 15092.34 | 0 | 2504407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515200 | 2504407 | -10793 | 2667038
4 | T4447 | 43510115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 3554036 | 3574289 | 3278614 | 20252.83 | 0 | 3282925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3278614 | 3282925 | 4310 | 3729071
4 | T4450 | 43288325201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 1867168 | 1867168 | 1766523 | 0 | 0 | 1766523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 2440207
4 | T4453 | 43786615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 741586 | 745892 | 706473 | 4306.13 | 0 | 708943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706473 | 708943 | 2470 | 783049
4 | T4455 | 43442715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 14081000 | 14107664 | 13452505 | 26664 | 0 | 14356886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13452505 | 14356886 | 904380 | 15571974
4 | T4456 | 43509515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 621302 | 621302 | 546893 | 0 | 0 | 547874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546893 | 547874 | 981 | 787751
4 | T4457 | 43436015201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-04-26 | 1472242 | 1503409 | 1494780 | 31167.68 | 37125 | 1497583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37125 | 0 | 0 | 0 | 0 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 1576734 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4460 | 43854615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 932300 | 932300 | 856857 | 0 | 0 | 856867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856857 | 856867 | 10 | 782210
4 | T4463 | 43167215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 312963 | 312963 | 288646 | 0 | 0 | 288646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288646 | 288646 | 0 | 301775
4 | T4466 | 42871815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 3213996 | 3213990 | 3033800 | -5.76 | 0 | 3135748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3033800 | 3135748 | 101948 | 3457231
4 | T4468 | 43612415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 199400 | 199400 | 179866 | 0 | 0 | 179866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179866 | 179866 | 0 | 207511
5 | E5W79 | 42404045201 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 10721000 | 10925028 | 10844638 | 204027.69 | 0 | 10755499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10844638 | 10755499 | -89138 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
5 | E5W91 | 40441825201 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2015-08-04 | 648777 | 669790 | 669790 | 21012.5 | 0 | 665390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669790 | 665390 | -4400 | 690160
5 | E5Y51 | 43832115201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2017-06-06 | 334599 | 541800 | 538448 | 207200.3 | 0 | 538448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538448 | 538448 | 0 | 346552
5 | E5Y52 | 43632315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 745547 | 745547 | 707547 | 0 | 0 | 707547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707547 | 707547 | 0 | 805051
5 | E5Y56 | 43744715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-02 | 1274655 | 1351445 | 1346112 | 76789.87 | 0 | 1347350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346112 | 1347350 | 1238 | 1669932
5 | E5Y60 | 43474215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-04-04 | 2282739 | 2439656 | 2285278 | 156916.9 | -15840 | 2296432 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 2269438 | 2296432 | 26994 | 2421411
5 | E5Y64 | 41832115201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-09-07 | 1888542 | 1900573 | 1865675 | 12030.51 | 0 | 1870769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865675 | 1870769 | 5094 | 1818886
5 | E5Y73 | 43065115201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 2882444 | 3115789 | 3158796 | 233344.62 | 0 | 3223558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3158796 | 3223558 | 64762 | 3280928
5 | E5Y75 | 43565515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | 576675 | 576675 | 566351 | 0 | 0 | 566351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566351 | 566351 | 0 | 601123
5 | E5Y77 | 43809615201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-04-26 | 1828183 | 1904273 | 1854273 | 76089.71 | 0 | 1854273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y92 | 43243835201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-02 | 2098740 | 2179800 | 2109348 | 81060.22 | 0 | 2122937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 2861396
5 | E5Y95 | 43632515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 2610610 | 2610610 | 2553200 | 0 | 0 | 2553205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553200 | 2553205 | 5 | 3377422
5 | E5Y96 | 43643415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 3268345 | 3324038 | 3293890 | 55692.68 | 0 | 3302941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 2900877
5 | E5Y98 | 43927215201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2017-09-06 | 162149 | 162149 | 119762 | 0 | 0 | 119762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119762 | 119762 | 0 | 240922
5 | E5Y99 | 43927615201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2017-10-03 | 596733 | 596733 | 546163 | 0 | 0 | 547337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 946415
5 | E5Z03 | 43612615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-05 | 765000 | 765000 | 715000 | 0 | 0 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000 | 715000 | 0 | 1015761
5 | E5Z04 | 43927115201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-06 | 133664 | 133664 | 128000 | 0 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128000 | 128000 | 0 | 123951
5 | E5Z05 | 43566615201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-12-05 | 1687883 | 1737883 | 1730756 | 50000 | 0 | 1735963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730756 | 1735963 | 5207 | 1825766
5 | E5Z15 | 44022215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-09-25 | 1614614 | 1614614 | 1573363 | 0 | 0 | 1573363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5Z29 | 43926915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 997135 | 997135 | 952500 | 0 | 0 | 952500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952500 | 952500 | 0 | 942335
5 | E5Z36 | 43987715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-03 | 661369 | 661369 | 614161 | 0 | 50000 | 615476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 664161 | 615476 | -48686 | 934116 | B1 | ACC - NO EXCUSE BONUS
5 | T5313 | 23953535201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-12-03 | 37587579 | 42729229 | 43288413 | 5141649.91 | 0 | 42228448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43288413 | 42228448 | -1059964 | 38177323 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5431 | 23759225201 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2012-12-05 | 29360536 | 33683790 | 34207580 | 4323245.3 | -3800 | 33089772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 29690235
5 | T5534 | 42875315201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-05-25 | 10372492 | 10929528 | 10898780 | 557036.67 | -15534 | 11163325 | -8434 | 0 | 0 | 0 | 0 | -7100 | -15534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15534 | 10883246 | 11163325 | 280079 | 11601598 | B0 | ACC - LUMP SUM
5 | T5555 | 43543315201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 4783671 | 4871035 | 5269309 | 87363.54 | 0 | 5264873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269309 | 5264873 | -4436 | 6123685
5 | T5558 | 23842215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 37503443 | 37874281 | 37480698 | 370838.06 | 990000 | 37514444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990000 | 0 | 0 | 0 | 0 | 0 | 990000 | 990000 | 38470698 | 37514444 | -956254 | 47475665 | B5 | ACC - INCENTIVE/DISINCENTIVE
5 | T5564 | 43505515201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-05-25 | 2766468 | 2822949 | 2775862 | 56480.73 | 0 | 2775862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775862 | 2775862 | 0 | 3396278
5 | T5575 | 43505715202 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 3075596 | 3075596 | 2961552 | 0 | 0 | 2961571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961552 | 2961571 | 19 | 4026582
5 | T5578 | 43364815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 3288934 | 3404197 | 3184256 | 115262.79 | -14055 | 3177145 | -14055 | 0 | 0 | 0 | 0 | 0 | -14055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14055 | 3170201 | 3177145 | 6944 | 2864215
5 | T5580 | 43259215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 5833370 | 5934096 | 5935419 | 100725.68 | 0 | 6061737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5935419 | 6061737 | 126318 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
5 | T5584 | 43233315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 1998889 | 2179196 | 2210072 | 180307.03 | 0 | 2224069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210072 | 2224069 | 13997 | 2432081
5 | T5585 | 43441715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-02-22 | 2959615 | 3012362 | 2938715 | 52747.39 | -39354 | 2939642 | -39354 | 0 | 0 | 0 | 0 | 0 | -39354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39354 | 2899361 | 2939642 | 40280 | 3119772
5 | T5587 | 43505415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 3220056 | 3323115 | 3265140 | 103059.29 | 0 | 3265140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3265140 | 3265140 | 0 | 4249078
5 | T5598 | 43566115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-10-25 | 1387781 | 1400208 | 1356596 | 12427.32 | 0 | 1374428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356596 | 1374428 | 17832 | 1627448
5 | T5600 | 43691515201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 3294214 | 3431595 | 3445345 | 137381.15 | 0 | 3578158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445345 | 3578158 | 132813 | 4280329
5 | T5602 | 44113065203 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 287798 | 287798 | 331937 | 0 | -18683 | 313254 | -18683 | 0 | 0 | 0 | 0 | 0 | -18683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18683 | 313254 | 313254 | 0 | 295435
5 | T5612 | 44113035201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1243505 | 2375233 | 2283435 | 1131727.86 | 0 | 2284747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1351002
5 | T5620 | 43367315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-10-25 | 633985 | 639413 | 620693 | 5428.5 | 0 | 621196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620693 | 621196 | 504 | 980597
5 | T5627 | 43730215201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 140000 | 140000 | 125000 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 315759
6 | E6J51 | 43652415201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 2558857 | 2607925 | 2393750 | 49068.4 | 0 | 1800521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2393750 | 1800521 | -593229 | 3068069
6 | E6J96 | 42918725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-27 | 3292828 | 3417930 | 3052117 | 125102.18 | 0 | 3083026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052117 | 3083026 | 30910 | 3372731
6 | E6K52 | 43029119201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-09-21 | 5967061 | 6057011 | 6008075 | 89950.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
6 | E6K55 | 42527135201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-17 | 4179580 | 4230908 | 4133800 | 51327.99 | 180000 | 4165794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 4313800 | 4165794 | -148006 | 4754512 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6K60 | 42736945201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2017-02-23 | 1911584 | 1911584 | 1907123 | 0 | 0 | 1909046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907123 | 1909046 | 1923 | 1951851
6 | E6K66 | 43826315201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-26 | 632865 | 632865 | 612839 | 0 | 0 | 614000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 767335
6 | E6K90 | 43653315201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 1534207 | 1534207 | 1484378 | 0 | 0 | 1484378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 1699725
6 | E6L12 | 43560115201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-01-26 | 3399874 | 3718568 | 3635077 | 318693.04 | 0 | 3635340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3635077 | 3635340 | 263 | 3205033
6 | E6L18 | 43779215201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-26 | 676189 | 676189 | 658548 | 0 | 0 | 659195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658548 | 659195 | 646 | 719638
6 | E6L19 | 42848725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-27 | 1469702 | 1469702 | 1379063 | 0 | 1584 | 1390630 | 0 | 0 | 0 | 0 | 1584 | 0 | 1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584 | 1380647 | 1390630 | 9983 | 1648940
6 | E6L32 | 44048515201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-11-30 | 575526 | 575526 | 511952 | 0 | 0 | 511952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511952 | 511952 | 0 | 593410
6 | T6339 | 41463325201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-05-25 | 8785729 | 9203528 | 9138495 | 417798.88 | 250000 | 9130458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 9388495 | 9130458 | -258037 | 8755698 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6347 | 42559815201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 21462766 | 22274168 | 21904850 | 811402.18 | 1200000 | 21684913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 23104850 | 21684913 | -1419938 | 22401464 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6348 | 41247935201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 18181314 | 17828896 | 17896535 | -352417.51 | 800000 | 18033074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 18696535 | 18033074 | -663461 | 18130046 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6388 | 24961475201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 33267097 | 34160144 | 35419695 | 893046.25 | 960000 | 35803243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 240000 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 37471337 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6390 | 43094915201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 4429507 | 4700034 | 4434960 | 270526.65 | 170000 | 4589226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 4604960 | 4589226 | -15734 | 5093915 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6411 | 43477615201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2356443 | 2356443 | 2361696 | 0 | 120000 | 2379741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 2737736 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6412 | 43477815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 292409 | 292409 | 300085 | 0 | 0 | 304110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300085 | 304110 | 4025 | 335871
6 | T6415 | 43328625201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 2632861 | 2661056 | 2517080 | 28194.94 | 150000 | 2530404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2667080 | 2530404 | -136676 | 3416980 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6416 | 43305925201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1824984 | 1972801 | 1821952 | 147816.92 | 0 | 1792624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821952 | 1792624 | -29328 | 2103857
6 | T6417 | 43476815201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1228383 | 1228383 | 1133929 | 0 | 0 | 1138502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133929 | 1138502 | 4573 | 1258750
6 | T6418 | 43274825201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 1730331 | 1781963 | 1633274 | 51631.51 | 0 | 1638508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633274 | 1638508 | 5234 | 2094391
6 | T6426 | 43477115201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1156048 | 1219697 | 1138589 | 63648.67 | 0 | 1144207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 1339225
6 | T6428 | 42765125201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1069876 | 1119876 | 1059386 | 50000 | 0 | 1008320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059386 | 1008320 | -51066 | 1388000
6 | T6431 | 43787315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 929676 | 929676 | 827030 | 0 | 0 | 827669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827030 | 827669 | 639 | 881390
6 | T6432 | 43638515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 627876 | 627876 | 619690 | 0 | 0 | 620784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619690 | 620784 | 1093 | 756556
6 | T6434 | 43792115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 328254 | 328254 | 283998 | 0 | 0 | 284067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283998 | 284067 | 69 | 429367
6 | T6446 | 43631215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 793153 | 793153 | 739919 | 0 | 0 | 742614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 987100
7 | E7L03 | 43656815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-04-13 | 3851530 | 4219010 | 4049852 | 367479.64 | 0 | 3995216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049852 | 3995216 | -54636 | 3798000
7 | E7L45 | 43243515201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-02-08 | 885313 | 922332 | 833142 | 37019.32 | 0 | 814450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833142 | 814450 | -18692 | 1006200
7 | E7L59 | 43070815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2175849 | 2175830 | 2389823 | -19.12 | 0 | 2415150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | 1660000
7 | E7L76 | 43589615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 921000 | 999500 | 949500 | 78500 | 0 | 949500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949500 | 949500 | 0 | 2050000 | B0 | ACC - LUMP SUM
7 | E7L82 | 43269715201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-06-14 | 4654737 | 4707294 | 4587650 | 52556.33 | 0 | 4635460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4587650 | 4635460 | 47810 | 5246590
7 | E7L93 | 43402915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 223800 | 223800 | 202343 | 0 | 0 | 202343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202343 | 202343 | 0 | 320000
7 | E7L94 | 43754915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 226571 | 226571 | 223484 | 0 | 0 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223484 | 223484 | 0 | 310000
7 | E7L96 | 43966215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-03-14 | 1051194 | 1051194 | 908881 | 0 | 0 | 908881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908881 | 908881 | 0 | 1997000
7 | E7M01 | 43070515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 633485 | 633485 | 652234 | 0 | 0 | 652234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652234 | 652234 | 0 | 643100
7 | E7M04 | 43755115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-09 | 240676 | 240676 | 236101 | 0 | 0 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236101 | 236101 | 0 | 225000
7 | E7R00 | 43402615201 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2016-09-15 | 2971000 | 2971000 | 2903131 | 0 | -19677 | 2883454 | -19677 | 0 | 0 | 0 | 0 | 0 | -19677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19677 | 2883454 | 2883454 | 0 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7292 | 40915415201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2011-09-28 | 21468350 | 23763433 | 23633808 | 2295082.97 | -79000 | 23010045 | 0 | 0 | 0 | 0 | 0 | -79000 | -79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -79000 | 23554808 | 23010045 | -544763 | 21183448
7 | T7304 | 40795135201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 39444222 | 39305377 | 38780845 | -138845.42 | -18000 | 38004215 | 0 | 0 | 0 | 0 | 0 | -18000 | -18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 38762845 | 38004215 | -758630 | 44767705 | ARRA | AMERICAN RECOVERY AND REINVEST
7 | T7317 | 41886075201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 25488889 | 25701063 | 26223933 | 212174.36 | -97668 | 25239037 | -97668 | 0 | 0 | 0 | 0 | 0 | -97668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97668 | 26126265 | 25239037 | -887228 | 24112219
7 | T7353 | 25699535201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2014-10-29 | 19306771 | 20971666 | 20689510 | 1664894.68 | 0 | 19869660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20689510 | 19869660 | -819849 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7379 | 42906015202 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 7691624 | 7990485 | 8163052 | 298860.33 | 0 | 8182033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8163052 | 8182033 | 18982 | 9262147
7 | T7382 | 43258615202 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 8465944 | 9024845 | 9722176 | 558900.45 | -400000 | 9347660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | 0 | -400000 | -400000 | 9322176 | 9347660 | 25484 | 9653597 | B7 | ACC - A+B/BONUS
7 | T7387 | 42895415201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 17840000 | 18339077 | 18567408 | 499077.06 | 0 | 18695589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18567408 | 18695589 | 128181 | 19115045
7 | T7390 | 43480715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3002052 | 3032833 | 3060237 | 30780.82 | 0 | 3105091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 3538017
7 | T7392 | 43484115202 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 5679793 | 5828296 | 5798728 | 148502.5 | 0 | 5859621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5798728 | 5859621 | 60893 | 4416000
7 | T7394 | 43431715201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1263874 | 1263874 | 1203555 | 0 | 0 | 1210019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 1558000
7 | T7405 | 43649015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-03-28 | 2235958 | 2384716 | 2283562 | 148758 | 0 | 2395779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283562 | 2395779 | 112217 | 3540000
7 | T7416 | 44030615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 471467 | 471467 | 440953 | 0 | 0 | 440953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440953 | 440953 | 0 | 446330
7 | T7423 | 44269715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-06-13 | 189768 | 189768 | 146624 | 0 | 0 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146624 | 146624 | 0 | 280558
8 | E8N52 | 42935045201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2014-09-30 | 50984589 | 52265348 | 52262125 | 1280759 | -25500 | 50963001 | 0 | 0 | 0 | 0 | 0 | -25500 | -25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25500 | 52236625 | 50963001 | -1273624 | 52446848 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8P06 | 43383015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-23 | 27866200 | 27866200 | 27624496 | 0 | 0 | 26928859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 32476137 | B8 | ACC - DESIGN/BUILD - MAJOR
8 | E8P90 | 43561515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 8378688 | 9424319 | 9142821 | 1045631.46 | 0 | 9136713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9142821 | 9136713 | -6108 | 8835781
8 | E8Q11 | 43715625201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-08-16 | 10316568 | 10271998 | 10116572 | -44570.16 | 0 | 10180724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10116572 | 10180724 | 64151 | 10198096
8 | E8Q45 | 43516615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-03-28 | 10174450 | 10442695 | 10222974 | 268245.15 | 0 | 10355432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10222974 | 10355432 | 132458 | 10340089 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8Q46 | 43717015202 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2017-03-14 | 1120173 | 1120173 | 1139075 | 0 | 0 | 1139077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 885798
8 | E8Q48 | 43560815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-13 | 2193386 | 2202999 | 2182384 | 9613.36 | -41184 | 2141200 | -41184 | 0 | 0 | 0 | 0 | 0 | -41184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41184 | 2141200 | 2141200 | 0 | 2074316
8 | E8Q77 | 43905115201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-09-19 | 1559626 | 1611434 | 1403106 | 51808.48 | 0 | 1403413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 1751318

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [7 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total
01 | 27155.7 | 271175.2 | 0 | 414489.22 | 123667.88 | 752029.74 | 1588517.74 |  | 331739604 | 0.2522% | 836488
02 | 0 | 357670.25 | 0 | 14064.5 | 298349.21 | 295349.87 | 965433.83 |  | 237579767 | 0.282% | 670083.96
03 |  | 500851.63 |  | 0 | 103741.33 | 7162750.04 | 7767343 |  | 228613640 | 0.2645% | 604592.96
04 | 0 | 1502032.29 | 303.46 | 79624.59 | 136268.91 | 6131471.16 | 7849700.41 |  | 340576779 | 0.5045% | 1718229.25
05 | 205.09 | 2780713.13 | 11064.41 | 4334.34 | 75385.67 | 223193.89 | 3094896.53 |  | 187517335 | 1.531% | 2871702.64
06 | 0 | 21227.63 |  | 116082.03 | 17142.54 | 112519.13 | 266971.33 |  | 127294980 | 0.1213% | 154452.2
07 | 20287.88 | 503904.82 | 1155 | 3820.32 | 471663.87 | 198042.83 | 1198874.72 |  | 170383867 | 0.5874% | 1000831.89
08 |  | 178000 |  |  | 0 | 0 | 178000 |  | 112593680 | 0.1581% | 178000
Grand Total | 47648.67 | 6115574.95 | 12522.87 | 632415 | 1226219.41 | 14875356.66 | 22909737.56 |  | 1736299652 | 0.4627% | 8034380.9
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days SA
01 | 0 | 75 | 63 | 20 | 194 | 231 | 583 |  | 352
02 | 0 | 212 | 0 | 18 | 187 | 810 | 1227 |  | 417
03 |  | 40 |  | 3 | 11 | 368 | 422 |  | 54
04 | 2 | 321 | 0 | 30 | 114 | 1026 | 1493 |  | 467
05 | 0 | 362 | 8 | 37 | 21 | 564 | 992 |  | 428
06 | 0 | 0 |  | 0 | 0 | 14 | 14 |  | 0
07 | 0 | 210 | 13 | 6 | 193 | 173 | 595 |  | 422
08 |  | 38 |  |  | 0 | 109 | 147 |  | 38
Grand Total | 2 | 1258 | 84 | 114 | 720 | 3295 | 5473 |  | 2178
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 |  |  |  |  | 440 | 58 | 498 | 440 | 792 | 12443 | 6.365%
02 |  |  |  | 3 | 7 | 55 | 65 | 10 | 427 | 11292 | 3.781%
03 |  | 102 |  | 59 |  | 1086 | 1247 | 161 | 215 | 6946 | 3.095%
04 |  | 60 | 19 | 10 | 41 | 63 | 193 | 130 | 597 | 11374 | 5.249%
05 | [5 empty] | 28 | 28 | 0 | 428 | 11580 | 3.696%
06 |  | 21 |  |  | 14 | 199 | 234 | 35 | 35 | 8104 | 0.4319%
07 |  | 34 |  |  |  | 55 | 89 | 34 | 456 | 7352 | 6.202%
08 | [5 empty] | 41 | 41 | 0 | 38 | 3150 | 1.206%
Grand Total |  | 217 | 19 | 72 | 502 | 1585 | 2395 | 810 | 2988 | 72241 | 4.136%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1K75 | 20121435201 | 001 | 2 |  | 1 | 503 | 163363.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1K75 | 20121435201 | 038 | 2 |  | 1 | 503 | -43457.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1K75 | 20121435201 | 040 | 2 |  | 1 | 005 | 416816.72 | 0 | 5 |  | C | 160 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1K75 | 20121435201 | 059 | 2 |  | 1 | 860 | 437224.73 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1K75 | 20121435201 | 060 | 2 |  | 1 | 860 | 89912.9 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1K75 | 20121435201 | 061 | 2 |  | 1 | 860 | 460087.1 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1Q20 | 43979815201 | 005 | 2 |  | 1 | 919 | 5910.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1Q21 | 41773349201 | 008 | 2 |  | 1 | 004 | 15320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q22 | 43854515201 | 009 | 2 |  | 1 | 004 | 2222 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 004 | 2 | 850 | 1 | 001 | 1258.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 008 | 2 |  | 1 | 004 | -16730.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R00 | 43798415201 | 001 | 2 |  | 1 | 004 | 10240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R00 | 43798415201 | 004 | 2 |  | 1 | 101 | 4454.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1550 | 41304445201 | 008 | 2 |  | 1 | 105 | 1872 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1550 | 41304445201 | 008 | 2 |  | 2 | 113 | -68239.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
01 | T1550 | 41304445201 | 008 | 2 |  | 3 | 115 | -47911.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1550 | 41304445201 | 008 | 2 |  | 4 | 009 | 4289.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | T1550 | 41304445201 | 031 | 2 |  | 1 | 003 | -1353.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1550 | 41304445201 | 031 | 2 |  | 2 | 115 | 832.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1550 | 41304445201 | 031 | 2 |  | 3 | 105 | 4108.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1550 | 41304445201 | 031 | 2 |  | 4 | 105 | -2127.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1550 | 41304445201 | 050 | 2 |  | 1 | 115 | 122.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1550 | 41304445201 | 050 | 2 |  | 2 | 105 | 4252.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1550 | 41304445201 | 065 | 2 |  | 1 | 105 | 5017.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1550 | 41304445201 | 065 | 2 |  | 2 | 503 | 48011.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1550 | 41304445201 | 065 | 2 |  | 3 | 115 | 4861.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1550 | 41304445201 | 065 | 2 |  | 4 | 004 | -2677.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1550 | 41304445201 | 068 | 2 |  | 1 | 004 | 283767.86 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1550 | 41304445201 | 069 | 2 |  | 1 | 113 | 414572.68 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 020 | 2 |  | 1 | 107 | 106799.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 1 | 115 | 5378.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 2 | 115 | 2292.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 3 | 115 | 174.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 4 | 502 | 5438.07 | 5438.07 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate Directions Given | CEI Actions/Inactions | 6
01 | T1576 | 19690445201 | 021 | 2 | 850 | 5 | 107 | 3960 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 6 | 105 | 1686.06 | 1686.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 7 | 112 | 8741.89 | 8741.89 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 8 | 115 | 27654.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 9 | 115 | 4781.17 | 4781.17 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 10 | 107 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 11 | 007 | 18636.46 | 1084.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1576 | 19690445201 | 021 | 2 | 850 | 12 | 105 | 12217.37 | 4626.45 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690445201 | 021 | 2 | 850 | 14 | 503 | 8049.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1576 | 19690445201 | 025 | 2 |  | 1 | 007 | 94228.68 | 12736.97 | 0 |  | N | 31 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1576 | 19690445201 | 026 | 2 |  | 1 | 115 | 87796.33 | 87796.33 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 034 | 2 |  | 1 | 007 | 136899.3 | 34784.17 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1576 | 19690445201 | 035 | 2 |  | 1 | 107 | 121426.14 | 0 | 1 |  | N | 12 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 1 | 115 | 1750.53 | 1750.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 2 | 012 | 8975.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 | 046 | 2 | 850 | 3 | 012 | -8975.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 | 046 | 2 | 850 | 4 | 012 | 1617.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 | 046 | 2 | 850 | 5 | 012 | 7357.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 | 046 | 2 | 850 | 6 | 107 | 396 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 7 | 107 | 6282.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 8 | 503 | 10135.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1576 | 19690445201 | 046 | 2 | 850 | 9 | 503 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1576 | 19690445201 | 046 | 2 | 850 | 10 | 107 | 3816.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 11 | 115 | 16401.31 | 7335.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 12 | 115 | 12182.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 13 | 115 | 3464.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 14 | 115 | -16401.31 | -7335.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 15 | 115 | -3464.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 16 | 115 | 7335.09 | 7335.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 17 | 107 | 13663.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 18 | 115 | 3464.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 19 | 115 | 657.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 20 | 115 | 4690.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 21 | 115 | 1870.88 | 1870.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 22 | 115 | -4690.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 046 | 2 | 850 | 23 | 115 | 2819.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 1 | 503 | 4367.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1576 | 19690445201 | 049 | 2 | 850 | 2 | 112 | 13728 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 3 | 115 | 1540 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 4 | 107 | 8660.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 5 | 107 | 7394.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 6 | 115 | 3024.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 7 | 115 | 3024.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 8 | 107 | 3324.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 9 | 115 | -3024.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 10 | 101 | 20407.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 11 | 122 | 9204.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 12 | 115 | 4365.44 | 4365.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 13 | 107 | 19444.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 14 | 117 | 61.31 | 61.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 15 | 115 | 3598.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 049 | 2 | 850 | 16 | 108 | 880 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1576 | 19690445201 | 053 | 2 |  | 1 | 917 | 15678.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1576 | 19690445201 | 054 | 2 |  | 1 | 105 | 24922.15 | 24922.15 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690445201 | 055 | 2 |  | 1 | 007 | 52547.67 | 52547.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1576 | 19690445201 | 061 | 2 |  | 1 | 001 | 26347.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1576 | 19690445201 | 066 | 2 | 850 | 1 | 115 | 10088.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 066 | 2 | 850 | 2 | 010 | 15155.25 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1576 | 19690445201 | 077 | 2 |  | 1 | 403 | -25911 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
01 | T1576 | 19690445201 | 080 | 2 |  | 1 | 022 | 39782.98 | 39782.98 | 5 |  | N | 2 | Avoidable, Third Party | Material Shortage | Material Shortage | 12
01 | T1576 | 19690445201 | 083 | 2 |  | 1 | 919 | 225653.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
01 | T1576 | 19690445201 | 086 | 2 |  | 1 | 860 | 67838.13 | 67838.13 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | T1576 | 19690445201 | 087 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | T1576 | 19690445201 | 087 | 2 |  | 2 | 013 | 16843 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
01 | T1576 | 19690445201 | 087 | 2 |  | 3 | 860 | 5487 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
01 | T1576 | 19690445201 | 087 | 2 |  | 4 | 107 | 0 | 0 | 1 |  | N | 18 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 087 | 2 |  | 5 | 130 | 0 | 0 | 1 |  | N | 13 | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
01 | T1576 | 19690445201 | 087 | 2 |  | 6 | 115 | 0 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 087 | 2 |  | 7 | 115 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 088 | 2 | 850 | 1 | 117 | 3242.81 | 3242.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1576 | 19690445201 | 088 | 2 | 850 | 2 | 010 | 9982.5 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1576 | 19690445201 | 088 | 2 | 850 | 3 | 115 | 1826.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 088 | 2 | 850 | 4 | 024 | 4671.98 | 4671.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 088 | 2 | 850 | 5 | 012 | 5588.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 | 088 | 2 | 850 | 6 | 107 | 5834.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 088 | 2 | 850 | 7 | 117 | 11654.46 | 11654.46 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1576 | 19690445201 | 091 | 2 |  | 1 | 700 | 235887.48 | 70060.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1576 | 19690445201 | 091 | 2 |  | 2 | 700 | 46624.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Minor Changes | Minor Changes | 7
01 | T1576 | 19690445201 | 091 | 2 |  | 3 | 105 | 17886.72 | 17886.72 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690445201 | 091 | 2 |  | 4 | 115 | 7495.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 091 | 2 |  | 5 | 101 | 4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1576 | 19690445201 | 091 | 2 |  | 6 | 107 | 11440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 092 | 2 |  | 1 | 700 | 49280.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1576 | 19690445201 | 092 | 2 |  | 2 | 107 | 763.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 096 | 2 |  | 1 | 107 | 28345.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 | 097 | 2 |  | 1 | 860 | 110918.5 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
01 | T1576 | 19690445201 | 097 | 2 |  | 2 | 860 | 27155.7 | 27155.7 | 3 |  | C | 0 | Avoidable, CEI Consultant | Claim Settlement | Claim Settlement | 10
01 | T1606 | 19801745201 | 015 | 2 |  | 1 | 007 | 21074.9 | 0 | 5 |  | E | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1606 | 19801745201 | 017 | 2 |  | 1 | 112 | 88710.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1606 | 19801745201 | 022 | 2 |  | 1 | 916 | 10441.1 | 10441.1 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1606 | 19801745201 | 023 | 2 |  | 1 | 503 | -544936.68 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1606 | 19801745201 | 036 | 2 |  | 1 | 130 | 0 | 0 | 5 |  | N | 32 | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
01 | T1606 | 19801745201 | 036 | 2 |  | 2 | 503 | 11346.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1606 | 19801745201 | 036 | 2 |  | 3 | 001 | 11404.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 | 036 | 2 |  | 4 | 128 | 4940.3 | 4940.3 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1606 | 19801745201 | 036 | 2 |  | 5 | 115 | 5125.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1606 | 19801745201 | 036 | 2 |  | 6 | 101 | 2655.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1606 | 19801745201 | 036 | 2 |  | 7 | 001 | 4623.1 | 4623.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 | 036 | 2 |  | 8 | 118 | 6810.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1606 | 19801745201 | 037 | 2 |  | 1 | 015 | 45191.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1621 | 20103245201 | 003 | 2 |  | 1 | 007 | 7100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1621 | 20103245201 | 003 | 2 |  | 2 | 107 | 1595.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 003 | 2 |  | 3 | 105 | 127599.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1621 | 20103245201 | 011 | 2 |  | 1 | 107 | 3541.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 013 | 2 |  | 1 | 503 | -21085.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1621 | 20103245201 | 016 | 2 |  | 1 | 007 | 68182.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1621 | 20103245201 | 017 | 2 |  | 1 | 001 | 616060.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1621 | 20103245201 | 018 | 2 |  | 1 | 126 | 592.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 021 | 2 |  | 1 | 915 | 12609.58 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 031 | 2 |  | 1 | 916 | 25000.04 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 032 | 2 |  | 1 | 917 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 033 | 2 |  | 1 | 101 | 91170.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1621 | 20103245201 | 033 | 2 |  | 2 | 003 | 21697.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1621 | 20103245201 | 033 | 2 |  | 3 | 115 | 1157.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 033 | 2 |  | 4 | 126 | 6170.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 1 | 022 | 3217.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 2 | 118 | 5547.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 3 | 118 | 3014.61 | 3014.61 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 4 | 503 | 275 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1621 | 20103245201 | 036 | 2 | 850 | 5 | 115 | 30804.88 | 30804.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 6 | 115 | 8563.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 7 | 118 | 3014.8 | 3014.8 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1621 | 20103245201 | 036 | 2 | 850 | 8 | 003 | 7581.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1621 | 20103245201 | 037 | 2 | 850 | 1 | 022 | 19367.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1621 | 20103245201 | 037 | 2 | 850 | 2 | 503 | 275 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1621 | 20103245201 | 037 | 2 | 850 | 3 | 115 | 30804.9 | 30804.9 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 039 | 2 |  | 1 | 007 | 4023.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1621 | 20103245201 | 040 | 2 |  | 1 | 106 | -2226 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1621 | 20103245201 | 040 | 2 |  | 2 | 105 | 7789.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1621 | 20103245201 | 040 | 2 |  | 3 | 115 | 4690 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 044 | 2 |  | 1 | 105 | 99597 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1621 | 20103245201 | 044 | 2 |  | 3 | 003 | 23840.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1621 | 20103245201 | 054 | 2 |  | 1 | 101 | 17000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1621 | 20103245201 | 054 | 2 |  | 2 | 115 | 321.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 059 | 2 |  | 1 | 919 | 25669.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1621 | 20103245201 | 064 | 2 |  | 1 | 112 | 37557.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1623 | 43127815201 | 009 | 2 |  | 1 | 503 | -74498 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1646 | 43275515202 | 013 | 2 |  | 1 | 919 | 55157.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1646 | 43275515202 | 019 | 2 | 850 | 1 | 112 | 1519.81 | 1519.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1646 | 43275515202 | 019 | 2 | 850 | 2 | 112 | 8993.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1646 | 43275515202 | 019 | 2 | 850 | 3 | 112 | 269.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1646 | 43275515202 | 019 | 2 | 850 | 4 | 106 | 8132.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1653 | 43317315201 | 016 | 2 |  | 1 | 919 | 14904.5 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1653 | 43317315201 | 017 | 2 |  | 1 | 005 | 18752.37 | 18752.37 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1653 | 43317315201 | 018 | 2 |  | 1 | 001 | 37011.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1660 | 43161915201 | 017 | 2 |  | 1 | 919 | 48877.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1660 | 43161915201 | 018 | 2 |  | 1 | 503 | 14606.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1660 | 43161915201 | 019 | 2 |  | 1 | 101 | 4220.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1666 | 43289715201 | 014 | 2 |  | 1 | 115 | 10071.52 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1666 | 43289715201 | 014 | 2 |  | 2 | 130 | 0 | 0 | 4 |  | N | 63 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | T1666 | 43289715201 | 014 | 2 |  | 3 | 010 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1666 | 43289715201 | 021 | 2 |  | 1 | 001 | 13307.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1666 | 43289715201 | 022 | 2 |  | 1 | 919 | 59062.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1666 | 43289715201 | 023 | 2 |  | 1 | 115 | 8847.95 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1666 | 43289715201 | 024 | 2 |  | 1 | 115 | 8238.43 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1672 | 43660015201 | 012 | 2 |  | 1 | 919 | 49393.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1672 | 43660015201 | 016 | 2 |  | 1 | 130 | 143198.35 | 0 | 2 |  | N | 20 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
01 | T1673 | 42063335201 | 001 | 2 |  | 1 | 101 | 43428.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1673 | 42063335201 | 012 | 2 |  | 1 | 919 | 127259.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1673 | 42063335201 | 015 | 2 |  | 1 | 004 | 49673.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1678 | 43492915201 | 011 | 2 |  | 1 | 919 | 48270.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1686 | 43318815201 | 005 | 2 |  | 1 | 007 | 16831.45 | 16831.45 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1687 | 41304245201 | 004 | 2 |  | 1 | 305 | -431102.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1687 | 41304245201 | 005 | 2 |  | 1 | 105 | 23455.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1687 | 41304245201 | 009 | 2 |  | 1 | 503 | 348392.12 | 307783.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1687 | 41304245201 | 011 | 2 |  | 1 | 105 | 33237.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1687 | 41304245201 | 018 | 2 |  | 1 | 004 | 46688.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1694 | 43513615201 | 009 | 2 |  | 1 | 107 | -6283.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1698 | 43656715201 | 001 | 2 |  | 1 | 101 | 27280.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1698 | 43656715201 | 007 | 2 |  | 1 | 012 | 125444 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1699 | 43698315201 | 005 | 2 |  | 1 | 115 | 7334.62 | 5285.7 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 | 011 | 2 |  | 1 | 015 | 69186.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1A07 | 19389825201 | 012 | 2 |  | 1 | 001 | 14653.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A07 | 19389825201 | 020 | 2 |  | 1 | 101 | 14769.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1A07 | 19389825201 | 021 | 2 |  | 1 | 015 | 68652.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1A07 | 19389825201 | 022 | 2 |  | 1 | 015 | 25324.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1A07 | 19389825201 | 023 | 2 | 850 | 1 | 850 | 100000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
01 | T1A07 | 19389825201 | 024 | 2 | 850 | 1 | 021 | 7245.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
01 | T1A07 | 19389825201 | 027 | 2 |  | 1 | 015 | 8901.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1A07 | 19389825201 | 047 | 2 |  | 1 | 001 | 43686.03 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A07 | 19389825201 | 048 | 2 |  | 1 | 015 | 42079.98 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1A07 | 19389825201 | 051 | 2 |  | 1 | 004 | 85638.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1A07 | 19389825201 | 051 | 2 |  | 2 | 115 | 11635.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 | 051 | 2 |  | 3 | 117 | 23902.7 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1A07 | 19389825201 | 052 | 2 |  | 1 | 128 | 35216.54 | 35216.54 | 1 |  | N | 9 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A07 | 19389825201 | 052 | 2 |  | 2 | 003 | -3433.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A07 | 19389825201 | 052 | 2 |  | 3 | 115 | 55143.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 | 059 | 2 |  | 1 | 919 | 56074.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 | 060 | 2 |  | 1 | 919 | 1414.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A16 | 43609215201 | 009 | 2 |  | 1 | 101 | 75278 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1A16 | 43609215201 | 009 | 2 |  | 3 | 503 | 14999 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 1 | 503 | 8743.77 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 2 | 003 | 17686.29 | 5053.99 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 3 | 022 | 1691.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 4 | 128 | 2937.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 5 | 003 | -17686.29 | -5053.99 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 6 | 022 | 1003.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 7 | 022 | 549.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 8 | 022 | 1735.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 9 | 022 | 774.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 10 | 022 | 2371.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 11 | 003 | 17686.29 | 5053.99 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 12 | 022 | 3278.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 13 | 022 | 108 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 14 | 022 | 3550.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 15 | 022 | 735.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 16 | 022 | 4973.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 17 | 022 | 6033.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 18 | 022 | 2920.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 19 | 022 | 3377.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 20 | 022 | 3060.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 21 | 022 | 2655.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 22 | 022 | 2189.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 23 | 022 | 2411.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 24 | 022 | 2636.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 25 | 503 | 17600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 26 | 022 | 11599.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 27 | 022 | 9270.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 28 | 022 | 14252.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 29 | 022 | 6988.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 30 | 022 | 11686.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 012 | 2 | 850 | 31 | 022 | 3176.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 018 | 2 |  | 1 | 503 | 34300.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 018 | 2 |  | 6 | 022 | 4578.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 018 | 2 |  | 7 | 021 | 6634.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 026 | 2 |  | 1 | 108 | -14585.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1A16 | 43609215201 | 031 | 2 |  | 1 | 503 | -396749.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 1 | 022 | 20647.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 2 | 022 | -20647.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 3 | 022 | 12913.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 4 | 024 | 2865.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 5 | 023 | 4868.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 6 | 022 | 5119.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 7 | 919 | 30940.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 8 | 022 | 10096.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 033 | 2 | 850 | 9 | 024 | 4598.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 040 | 2 |  | 1 | 503 | 27653.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 049 | 2 |  | 1 | 001 | 136461.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A16 | 43609215201 | 049 | 2 |  | 2 | 108 | 116374.52 | 116374.52 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1A16 | 43609215201 | 049 | 2 |  | 3 | 503 | 95342.58 | 95342.58 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 049 | 2 |  | 4 | 700 | 15850.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1A16 | 43609215201 | 049 | 2 |  | 5 | 005 | 48804.02 | 48804.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1A16 | 43609215201 | 050 | 2 |  | 1 | 503 | 243719.23 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 | 050 | 2 |  | 2 | 503 | 252522.69 | 252522.69 | 2 |  | C | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2R91 | 41650145201 | 006 | 2 |  | 1 | 113 | 103080.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 1 | 917 | 53800.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 2 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 3 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 4 | 108 | 39075.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 6 | 108 | 13645.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 007 | 2 | 850 | 7 | 108 | 20379.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 027 | 2 |  | 1 | 305 | -165494.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 041 | 2 |  | 1 | 305 | -37027.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 052 | 2 |  | 1 | 503 | 218063.57 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2R91 | 41650145201 | 064 | 2 | 850 | 1 | 108 | 592.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 064 | 2 | 850 | 2 | 108 | 43100.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 064 | 2 | 850 | 3 | 108 | -12167.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 064 | 2 | 850 | 4 | 208 | -11004.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
02 | E2R91 | 41650145201 | 064 | 2 | 850 | 5 | 108 | -14450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 071 | 2 |  | 1 | 919 | 79532 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 | 072 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | N | 68 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2T36 | 42442415201 | 001 | 2 |  | 1 | 119 | 148758.73 | 6265 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 1 | 108 | 17726.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 2 | 108 | 25088.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 3 | 503 | 18444.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 4 | 108 | 15053.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 5 | 108 | 2247.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 6 | 108 | 7526.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 7 | 108 | 7557.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 8 | 108 | 2355.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 9 | 108 | 944.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 10 | 108 | 2508.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 11 | 108 | 850.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 12 | 012 | 5688.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 13 | 012 | 1165.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T36 | 42442415201 | 005 | 2 | 850 | 14 | 108 | 94.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 009 | 2 |  | 1 | 917 | 34198.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 014 | 2 |  | 1 | 108 | -13200.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 014 | 2 |  | 2 | 108 | 10270.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 014 | 2 |  | 3 | 108 | 1407.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 018 | 2 |  | 1 | 112 | 544616.95 | 289434.68 | 1 |  | N | 126 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 1 | 112 | 4338.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 2 | 131 | 1194.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 3 | 108 | 4168.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 4 | 108 | 4612.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 5 | 108 | 2700.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 6 | 112 | 2710.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 7 | 012 | 4534.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 8 | 108 | 1159.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 9 | 108 | 2926.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 10 | 108 | 2662 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 11 | 108 | 3119.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 12 | 108 | 5339.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 13 | 108 | 6130.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 14 | 108 | 11117.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 027 | 2 | 850 | 15 | 108 | 6075.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 030 | 2 |  | 1 | 108 | 299687.6 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 035 | 2 |  | 1 | 108 | 235835.4 | 0 | 0 |  | N | 73 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 | 038 | 2 |  | 1 | 919 | 49229.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2U34 | 43025815201 | 024 | 2 |  | 1 | 119 | 127048.3 | 26378.27 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U34 | 43025815201 | 026 | 2 |  | 1 | 119 | 44252.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U34 | 43025815201 | 028 | 2 |  | 1 | 919 | 29360.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U34 | 43025815201 | 031 | 2 |  | 1 | 012 | 7336.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2U34 | 43025815201 | 034 | 2 |  | 1 | 105 | 38955.29 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2U34 | 43025815201 | 037 | 2 |  | 1 | 119 | 1958.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U40 | 43015815201 | 024 | 2 |  | 1 | 919 | 49450.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U40 | 43015815201 | 034 | 2 |  | 1 | 105 | 256226.76 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2U49 | 43074915201 | 019 | 2 |  | 1 | 015 | 15537.18 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U49 | 43074915201 | 020 | 2 |  | 1 | 115 | 10812.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2U49 | 43074915201 | 020 | 2 |  | 2 | 107 | 4755.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2U49 | 43074915201 | 024 | 2 |  | 1 | 015 | 148393.32 | 148393.32 | 5 |  | C | 78 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U49 | 43074915201 | 025 | 2 |  | 1 | 860 | 59000 | 0 | 4 |  | C | 0 | Avoidable, In-House CEI | Claim Settlement | Claim Settlement | 10
02 | E2V29 | 43230815201 | 010 | 2 |  | 1 | 012 | -98576.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V63 | 43860115201 | 003 | 2 |  | 1 | 131 | 28412.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
02 | E2V64 | 43075815201 | 008 | 2 |  | 1 | 112 | 4326.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V65 | 43432315201 | 005 | 2 |  | 1 | 919 | 29150.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V65 | 43432315201 | 017 | 2 |  | 1 | 019 | 30196.05 | 0 | 2 |  | N | 3 | Avoidable, In-House Designer | Conflict With Other Contractors | Changed Conditions | 1
02 | E2W74 | 43430315201 | 004 | 2 |  | 1 | 012 | 487661.46 | 0 | 0 |  | N | 102 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W74 | 43430315201 | 007 | 2 |  | 1 | 101 | 2196.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2W74 | 43430315201 | 013 | 2 | 850 | 1 | 012 | 2441.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W74 | 43430315201 | 013 | 2 | 850 | 2 | 012 | 1453.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W97 | 43859915201 | 006 | 2 | 850 | 1 | 850 | 12376.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T2534 | 21071235201 | 005 | 2 |  | 1 | 108 | 13061.1 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2534 | 21071235201 | 005 | 2 |  | 2 | 107 | 63099.02 | 0 | 1 |  | N | 9 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 | 005 | 2 |  | 3 | 001 | 23212.7 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 005 | 2 |  | 4 | 115 | 20460.65 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 | 013 | 2 |  | 1 | 001 | 120738.21 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 1 | 115 | 20953.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 | 015 | 2 | 850 | 2 | 001 | 43774.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 3 | 112 | 35500.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 | 015 | 2 | 850 | 4 | 001 | 18830.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 5 | 003 | 10401.05 | 6957.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 6 | 115 | 4126.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 | 015 | 2 | 850 | 7 | 001 | 7891.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 8 | 001 | 2689.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 9 | 001 | 1889.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 015 | 2 | 850 | 10 | 112 | 3944.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 | 028 | 2 |  | 1 | 001 | 49107.59 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 029 | 2 |  | 1 | 005 | 149955.89 | 149955.89 | 5 |  | N | 43 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2534 | 21071235201 | 034 | 2 | 850 | 1 | 001 | 7211.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 034 | 2 | 850 | 2 | 001 | 2050.5 | 2050.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 034 | 2 | 850 | 3 | 010 | 9014.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2534 | 21071235201 | 034 | 2 | 850 | 4 | 012 | 1380.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2534 | 21071235201 | 034 | 2 | 850 | 5 | 001 | 70064.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 034 | 2 | 850 | 6 | 118 | 2208.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2534 | 21071235201 | 034 | 2 | 850 | 7 | 503 | 25929.7 | 12908.92 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2534 | 21071235201 | 034 | 2 | 850 | 8 | 917 | 11501.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2534 | 21071235201 | 034 | 2 | 850 | 9 | 001 | 14381.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 034 | 2 | 850 | 10 | 021 | 6257.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 037 | 2 |  | 1 | 001 | 10707.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 047 | 2 |  | 1 | 001 | 34707.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 055 | 2 |  | 1 | 001 | 5907.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 060 | 2 | 850 | 1 | 021 | 379 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 | 060 | 2 | 850 | 2 | 503 | 3728.37 | 1756.53 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2534 | 21071235201 | 060 | 2 | 850 | 3 | 101 | -1571.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2534 | 21071235201 | 060 | 2 | 850 | 4 | 004 | 1460.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2534 | 21071235201 | 060 | 2 | 850 | 5 | 101 | 3802.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2534 | 21071235201 | 060 | 2 | 850 | 6 | 118 | 3277.42 | 3277.42 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2534 | 21071235201 | 060 | 2 | 850 | 7 | 007 | 1677.23 | 1677.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2534 | 21071235201 | 060 | 2 | 850 | 8 | 012 | 6019.29 | 6019.29 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2534 | 21071235201 | 060 | 2 | 850 | 9 | 118 | 3656.16 | 97.02 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2568 | 21002845201 | 002 | 2 |  | 1 | 305 | -37510.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2568 | 21002845201 | 003 | 2 |  | 4 | 117 | 35622.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2568 | 21002845201 | 010 | 2 |  | 2 | 117 | 28876.12 | 14064.5 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2568 | 21002845201 | 042 | 2 |  | 1 | 919 | 19502.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2568 | 21002845201 | 044 | 2 |  | 1 | 860 | 50000 | 0 | 0 |  | N | 44 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2569 | 42870115201 | 003 | 2 | 850 | 1 | 015 | 36034.41 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 003 | 2 | 850 | 2 | 015 | 13965.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 009 | 2 |  | 1 | 112 | 232604.65 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2569 | 42870115201 | 023 | 2 | 850 | 1 | 015 | 15763.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 023 | 2 | 850 | 2 | 015 | 21824.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 023 | 2 | 850 | 3 | 015 | 18783.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 023 | 2 | 850 | 4 | 015 | 12486.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 023 | 2 | 850 | 5 | 015 | 21524.82 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 023 | 2 | 850 | 6 | 015 | 1606.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 027 | 2 | 850 | 1 | 015 | 24052.98 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 027 | 2 | 850 | 2 | 015 | 13671.77 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 027 | 2 | 850 | 3 | 015 | 285.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 028 | 2 | 850 | 1 | 107 | 1602.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 | 028 | 2 | 850 | 2 | 007 | 1349.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2569 | 42870115201 | 028 | 2 | 850 | 4 | 115 | 4683.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 | 028 | 2 | 850 | 5 | 003 | 409.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2569 | 42870115201 | 028 | 2 | 850 | 7 | 107 | 6133.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 | 028 | 2 | 850 | 8 | 001 | 17842.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 028 | 2 | 850 | 9 | 112 | 2083.22 | 2083.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2569 | 42870115201 | 028 | 2 | 850 | 10 | 001 | 57885.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 043 | 2 | 850 | 1 | 015 | 15997.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 043 | 2 | 850 | 2 | 015 | 68618.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 043 | 2 | 850 | 3 | 015 | 3256.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 043 | 2 | 850 | 4 | 015 | 4118.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 044 | 2 | 850 | 1 | 015 | 14432.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 1 | 001 | 1768.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 2 | 001 | 14966.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 3 | 001 | 6550.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 4 | 021 | 900.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 5 | 101 | 902.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2569 | 42870115201 | 050 | 2 | 850 | 6 | 003 | 5562.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 7 | 003 | 717.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2569 | 42870115201 | 050 | 2 | 850 | 8 | 107 | 11681.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 | 050 | 2 | 850 | 9 | 107 | 5707.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2611 | 42880415201 | 011 | 2 |  | 1 | 113 | 926314.64 | 0 | 0 |  | N | 70 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2611 | 42880415201 | 015 | 2 |  | 1 | 001 | 77560.09 | 43792 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2624 | 21327285201 | 013 | 2 |  | 1 | 003 | 2490.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2624 | 21327285201 | 013 | 2 |  | 4 | 003 | 33581.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2625 | 43091415201 | 021 | 2 |  | 1 | 112 | 39107 | 0 | 5 |  | C | 25 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2625 | 43091415201 | 024 | 2 |  | 1 | 112 | 22318.05 | 0 | 5 |  | C | 4 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2625 | 43091415201 | 036 | 2 |  | 1 | 015 | 26449.56 | 0 | 5 |  | C | 9 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2625 | 43091415201 | 039 | 2 |  | 1 | 860 | 28660 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2655 | 43231215201 | 010 | 2 |  | 1 | 919 | 7048 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2665 | 43056015201 | 012 | 2 | 850 | 1 | 007 | 22255.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2666 | 43543915201 | 009 | 2 |  | 1 | 919 | 1881.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2666 | 43543915201 | 013 | 2 |  | 1 | 503 | 4525.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2666 | 43543915201 | 016 | 2 |  | 1 | 009 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
02 | T2671 | 43601015201 | 001 | 2 |  | 1 | 107 | 4485.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3K83 | 41506725201 | 005 | 2 |  | 1 | 007 | 55020 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3K83 | 41506725201 | 013 | 2 |  | 1 | 503 | 54904 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 | 048 | 2 |  | 1 | 106 | 2353 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3K83 | 41506725201 | 049 | 2 |  | 1 | 503 | 697684.11 | 0 | 0 |  | N | 100 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 | 053 | 2 |  | 1 | 503 | -98543.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 | 057 | 2 |  | 1 | 503 | -5050.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 | 058 | 2 |  | 1 | 503 | -6135.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 | 078 | 2 |  | 1 | 106 | 84090 | 1459.18 | 5 |  | C | 11 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3L23 | 22066425201 | 012 | 2 |  | 1 | 503 | -84946.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3L23 | 22066425201 | 018 | 2 |  | 1 | 007 | -958804.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3L23 | 22066425201 | 033 | 2 |  | 1 | 305 | -216679.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3L23 | 22066425201 | 036 | 2 |  | 1 | 503 | 131856.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3L23 | 22066425201 | 054 | 2 | 850 | 1 | 012 | 50782.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3L23 | 22066425201 | 054 | 2 | 850 | 2 | 007 | 2722.5 | 235.62 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3L23 | 22066425201 | 070 | 2 |  | 1 | 860 | 4950000 | 4950000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | E3Q40 | 43375215201 | 011 | 2 |  | 1 | 503 | 9222.72 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q40 | 43375215201 | 014 | 2 |  | 1 | 101 | 2415.82 | 217.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q40 | 43375215201 | 018 | 2 |  | 1 | 115 | 14880.59 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3Q73 | 43966115201 | 004 | 2 |  | 1 | 107 | 127524 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3Q80 | 44014815201 | 001 | 2 |  | 1 | 101 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 | 007 | 2 |  | 1 | 101 | 10063.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 | 010 | 2 |  | 1 | 503 | -2639.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q91 | 43626815201 | 018 | 2 |  | 1 | 019 | 8500.07 | 0 | 2 |  | N | 1 | Avoidable, In-House Designer | Conflict With Other Contractors | Changed Conditions | 1
03 | T3417 | 42282315201 | 031 | 2 |  | 1 | 860 | 1625000 | 1625000 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3474 | 41110245201 | 007 | 2 |  | 1 | 101 | 7745 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 | 010 | 2 |  | 1 | 106 | 62650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3474 | 41110245201 | 012 | 2 |  | 1 | 101 | 129126.74 | 118343.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 | 013 | 2 |  | 1 | 503 | 26750.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3474 | 41110245201 | 014 | 2 |  | 1 | 119 | 23219.89 | 23219.89 | 1 |  | N | 11 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3474 | 41110245201 | 014 | 2 |  | 2 | 119 | 22644.3 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3474 | 41110245201 | 016 | 2 |  | 1 | 106 | 63597.74 | 63597.74 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3474 | 41110245201 | 017 | 2 |  | 1 | 101 | 38443.41 | 38443.41 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 | 021 | 2 |  | 1 | 101 | 42898.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 | 044 | 2 |  | 1 | 105 | 63425.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3474 | 41110245201 | 044 | 2 |  | 2 | 860 | 21574.64 | 21574.64 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3481 | 42884615201 | 011 | 2 |  | 1 | 015 | 6950.36 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3481 | 42884615201 | 012 | 2 |  | 1 | 106 | 5075.74 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3481 | 42884615201 | 027 | 2 |  | 1 | 503 | 169489.1 | 169489.1 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 | 031 | 2 |  | 1 | 503 | 32712.06 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 | 032 | 2 |  | 1 | 115 | 17020.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3481 | 42884615201 | 037 | 2 |  | 1 | 115 | 36748.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3481 | 42884615201 | 037 | 2 |  | 2 | 115 | 126812.11 | 126812.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3481 | 42884615201 | 037 | 2 |  | 3 | 860 | 16051.96 | 16051.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
03 | T3481 | 42884615201 | 050 | 2 |  | 1 | 101 | 35285.9 | 4130.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3498 | 43178515201 | 017 | 2 | 850 | 1 | 503 | 818.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3498 | 43178515201 | 017 | 2 | 850 | 2 | 115 | 3200.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3538 | 43357615201 | 004 | 2 |  | 1 | 503 | -1624.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 005 | 2 | 850 | 1 | 023 | 5303.53 | 5303.53 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 005 | 2 | 850 | 2 | 024 | 3079.79 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 005 | 2 | 850 | 3 | 503 | 14973.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 005 | 2 | 850 | 4 | 023 | 9231.04 | 9231.04 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 005 | 2 | 850 | 5 | 010 | 5372.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 005 | 2 | 850 | 6 | 010 | 12546.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 005 | 2 | 850 | 7 | 010 | 21691.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 005 | 2 | 850 | 8 | 012 | 6528.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 015 | 2 |  | 1 | 503 | 488943.9 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 016 | 2 |  | 1 | 012 | 81847.81 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 1 | 012 | 1324.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 2 | 001 | 7596.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 3 | 010 | 5897.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 017 | 2 | 850 | 4 | 012 | 2534.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 5 | 012 | 865.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 6 | 503 | 15001.32 | 3130.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 017 | 2 | 850 | 7 | 010 | 10312.25 | 1535.87 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 017 | 2 | 850 | 8 | 001 | 20193.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 017 | 2 | 850 | 9 | 503 | 15001.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 024 | 2 |  | 1 | 010 | 66157.75 | 4147.75 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 1 | 001 | 9140.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 026 | 2 | 850 | 2 | 107 | 5090.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 3 | 010 | 6757 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 4 | 010 | 4350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 5 | 010 | 942.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 6 | 112 | 8182.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 7 | 010 | 5897.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 8 | 010 | 3626.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 9 | 112 | 4058.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 10 | 010 | 1738.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 11 | 010 | 609 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 12 | 112 | 2321.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 13 | 503 | 1500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 026 | 2 | 850 | 14 | 503 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 026 | 2 | 850 | 15 | 503 | 4942.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 026 | 2 | 850 | 16 | 010 | 1303.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 17 | 118 | 6475.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 18 | 010 | 1841.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 026 | 2 | 850 | 19 | 101 | 398.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 20 | 101 | 162.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 21 | 101 | 81.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 22 | 118 | 4894.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3559 | 22247625201 | 026 | 2 | 850 | 23 | 503 | 1479.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 026 | 2 | 850 | 24 | 010 | 434.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 027 | 2 |  | 1 | 503 | 51469.19 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 033 | 2 |  | 1 | 012 | 250604.2 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 038 | 2 |  | 1 | 503 | 58551.74 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 041 | 2 |  | 1 | 503 | 13448.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 044 | 2 | 850 | 1 | 001 | 27361.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 044 | 2 | 850 | 2 | 118 | 3616.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3559 | 22247625201 | 044 | 2 | 850 | 3 | 010 | 5770.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 044 | 2 | 850 | 4 | 010 | 10238 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 044 | 2 | 850 | 5 | 010 | 4031.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 | 044 | 2 | 850 | 6 | 118 | 1581.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3559 | 22247625201 | 044 | 2 | 850 | 7 | 012 | 439.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 044 | 2 | 850 | 8 | 107 | 1907.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 059 | 2 |  | 1 | 919 | 55940.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 064 | 2 |  | 1 | 001 | 39865 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 067 | 2 |  | 1 | 115 | 26050.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 069 | 2 |  | 1 | 128 | 104838.24 | 50838.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3559 | 22247625201 | 070 | 2 |  | 1 | 107 | 12335.27 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 073 | 2 |  | 1 | 107 | 15286.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 079 | 2 |  | 1 | 001 | 13449.12 | 13449.12 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 080 | 2 |  | 1 | 503 | 149756.98 | 21674.12 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 088 | 2 |  | 1 | 503 | 220020.85 | 8596.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 092 | 2 |  | 1 | 503 | 113628.42 | 17787.6 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 096 | 2 |  | 1 | 012 | 39462.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 | 097 | 2 |  | 1 | 112 | 5852.86 | 1822.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 | 098 | 2 |  | 1 | 101 | 16401.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3559 | 22247625201 | 099 | 2 |  | 1 | 107 | 13449.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 102 | 2 |  | 1 | 115 | 105591.06 | 90275.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 103 | 2 |  | 1 | 107 | 50077.58 | 42755.37 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 105 | 2 |  | 1 | 107 | 101399.6 | 39019.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 106 | 2 |  | 1 | 503 | 207802.29 | 207802.29 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3565 | 43046915201 | 010 | 2 |  | 1 | 919 | 4023.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3565 | 43046915201 | 014 | 2 |  | 1 | 001 | 17692.64 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3565 | 43046915201 | 021 | 2 |  | 1 | 503 | 53615.78 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3567 | 43046515201 | 003 | 2 |  | 1 | 119 | 15000 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3568 | 41347915201 | 012 | 2 |  | 1 | 001 | 20690.94 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3596 | 43274015201 | 020 | 2 |  | 1 | 919 | 19046.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3615 | 42695015201 | 011 | 2 |  | 1 | 919 | 45502.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3615 | 42695015201 | 013 | 2 |  | 1 | 503 | -29739.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3636 | 43188325201 | 009 | 2 |  | 1 | 503 | 1600.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3641 | 43255115201 | 001 | 2 |  | 1 | 108 | 28098.65 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
03 | T3644 | 43671915201 | 012 | 2 |  | 1 | 503 | -7124.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3647 | 43626015201 | 004 | 2 |  | 1 | 503 | -21294.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3650 | 43014645201 | 009 | 2 |  | 1 | 919 | 14433.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3677 | 43467515201 | 005 | 2 |  | 1 | 115 | 2430.66 | 24.98 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4K92 | 41248925201 | 045 | 2 |  | 1 | 503 | 97256.2 | 43337.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 045 | 2 |  | 2 | 503 | 14885.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 045 | 2 |  | 3 | 503 | 27296.5 | 27296.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 045 | 2 |  | 4 | 503 | 153413.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 045 | 2 |  | 5 | 503 | 23180 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 045 | 2 |  | 6 | 131 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
04 | E4K92 | 41248925201 | 045 | 2 |  | 8 | 007 | 20295 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4K92 | 41248925201 | 045 | 2 |  | 9 | 131 | -51900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
04 | E4K92 | 41248925201 | 060 | 2 |  | 1 | 503 | 189819.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 2 | 001 | 30745.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 3 | 503 | 8236.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 4 | 503 | 51981.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 5 | 503 | 19274.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 6 | 503 | 24200.43 | 3493.85 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 061 | 2 | 850 | 8 | 007 | 2939.67 | 2939.67 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4K92 | 41248925201 | 065 | 2 |  | 1 | 116 | 1718798.62 | 1718798.62 | 0 |  | C | 184 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | E4K92 | 41248925201 | 065 | 2 |  | 2 | 116 | 676449.04 | 676449.04 | 0 |  | C | 36 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | E4K92 | 41248925201 | 070 | 2 |  | 1 | 503 | 402707.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 082 | 2 |  | 1 | 350 | 85800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4K92 | 41248925201 | 082 | 2 |  | 2 | 350 | 20000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4K92 | 41248925201 | 082 | 2 |  | 3 | 350 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4K92 | 41248925201 | 102 | 2 |  | 1 | 503 | 2303797.19 | 2303797.19 | 0 |  | C | 177 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 125 | 2 |  | 1 | 503 | 4879271.9 | 0 | 0 |  | C | 242 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 125 | 2 |  | 2 | 503 | 449653.21 | 0 | 0 |  | C | 12 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 125 | 2 |  | 3 | 503 | 211684.72 | 211684.72 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 125 | 2 |  | 4 | 503 | 0 | 0 | 0 |  | C | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 126 | 2 |  | 1 | 503 | 29639.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 139 | 2 |  | 1 | 503 | 1014987.15 | 0 | 0 |  | N | 37 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 141 | 2 |  | 1 | 503 | 110935 | 110935 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 155 | 2 |  | 1 | 503 | 88379.28 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 | 156 | 2 | 850 | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
04 | E4K92 | 41248925201 | 157 | 2 |  | 1 | 917 | 62344.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
04 | E4K92 | 41248925201 | 158 | 2 |  | 1 | 001 | 105952.03 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4K92 | 41248925201 | 158 | 2 |  | 2 | 001 | 76751.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4K92 | 41248925201 | 161 | 2 |  | 1 | 009 | 1238659.93 | 1238659.93 | 1 |  | N | 275 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
04 | E4K92 | 41248925201 | 161 | 2 |  | 2 | 003 | 68145.8 | 68145.8 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4K92 | 41248925201 | 161 | 2 |  | 3 | 009 | 4796.8 | 4796.8 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
04 | E4K92 | 41248925201 | 161 | 2 |  | 4 | 107 | 35777.28 | 35777.28 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
04 | E4K92 | 41248925201 | 169 | 2 |  | 1 | 919 | 63794.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4N44 | 42170765201 | 024 | 2 |  | 1 | 004 | 660997.03 | 116768.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 039 | 2 | 850 | 2 | 503 | 8800 | 8800 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 039 | 2 | 850 | 3 | 503 | 49500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 039 | 2 | 850 | 4 | 004 | 75673.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 039 | 2 | 850 | 5 | 023 | 9173.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 039 | 2 | 850 | 6 | 023 | 6852.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 056 | 2 |  | 1 | 503 | 55813.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 2 | 023 | 6635.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 3 | 023 | 1366.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 4 | 003 | 3054 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 5 | 106 | 1033.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 6 | 023 | 602.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 7 | 023 | 5934.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 8 | 003 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 9 | 003 | 14786.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 10 | 012 | 31434.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 11 | 004 | 32774.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 12 | 108 | 15620.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 13 | 108 | 9064 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 14 | 012 | 18484.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N44 | 42170765201 | 057 | 2 | 850 | 15 | 108 | 5214 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N44 | 42170765201 | 060 | 2 |  | 1 | 003 | 73587.85 | 73587.85 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N44 | 42170765201 | 063 | 2 |  | 1 | 503 | 29393.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 064 | 2 |  | 1 | 004 | -1005821 | -41358.34 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 064 | 2 |  | 2 | 305 | -26314 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 064 | 2 |  | 3 | 118 | -50613 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N44 | 42170765201 | 064 | 2 |  | 4 | 305 | -38820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N44 | 42170765201 | 064 | 2 |  | 5 | 503 | -78432 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 | 064 | 2 |  | 6 | 119 | 1200000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4N44 | 42170765201 | 066 | 2 |  | 1 | 001 | 152171.15 | 59412.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N44 | 42170765201 | 073 | 2 |  | 1 | 004 | 31167.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 075 | 2 |  | 1 | 004 | 462052 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 078 | 2 |  | 1 | 004 | 169692.88 | 124045.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 081 | 2 |  | 1 | 004 | 113269.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 092 | 2 |  | 1 | 917 | 18426.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 093 | 2 |  | 1 | 004 | 84517 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 103 | 2 |  | 1 | 004 | 82187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 106 | 2 |  | 1 | 004 | 412280.41 | 148261.32 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 116 | 2 |  | 1 | 919 | 45960.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 118 | 2 |  | 1 | 001 | 358786.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N44 | 42170765201 | 118 | 2 |  | 2 | 004 | 41213.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N44 | 42170765201 | 118 | 2 |  | 3 | 012 | 57398.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N44 | 42170765201 | 118 | 2 |  | 4 | 305 | -17793.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4P08 | 42170755201 | 023 | 2 |  | 1 | 503 | 97598.5 | 16705.5 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 046 | 2 |  | 1 | 503 | 623042.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 046 | 2 |  | 2 | 004 | 209431.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 049 | 2 |  | 1 | 503 | 14482.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 049 | 2 |  | 2 | 001 | 10918.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P08 | 42170755201 | 049 | 2 |  | 3 | 004 | -21503.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 051 | 2 |  | 1 | 012 | 50557.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4P08 | 42170755201 | 051 | 2 |  | 2 | 305 | -50171.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4P08 | 42170755201 | 052 | 2 |  | 1 | 503 | 895685.6 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 052 | 2 |  | 2 | 004 | -849049.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 053 | 2 |  | 1 | 004 | 33922.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 053 | 2 |  | 2 | 004 | -150744 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 053 | 2 |  | 3 | 004 | 112720.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 063 | 2 |  | 1 | 503 | 99078.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 064 | 2 |  | 1 | 103 | 337202.17 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 | 070 | 2 |  | 1 | 917 | 95646.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 | 070 | 2 |  | 2 | 917 | 1595.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 | 072 | 2 |  | 1 | 503 | 857517 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 073 | 2 |  | 1 | 503 | -857517 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 074 | 2 |  | 1 | 103 | 252451.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 | 076 | 2 |  | 1 | 305 | -26532.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 | 079 | 2 |  | 1 | 118 | 53691.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 | 081 | 2 |  | 1 | 919 | 197055.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 | 089 | 2 | 850 | 1 | 118 | 12353.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 | 089 | 2 | 850 | 2 | 118 | 1174.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 | 089 | 2 | 850 | 3 | 503 | 18614.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 090 | 2 |  | 1 | 004 | 44641.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 091 | 2 |  | 1 | 503 | -44294.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 094 | 2 |  | 1 | 503 | 58581.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 097 | 2 |  | 1 | 503 | 51060.85 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 097 | 2 |  | 2 | 018 | -49935.74 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4P08 | 42170755201 | 100 | 2 |  | 1 | 503 | 143790.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4P08 | 42170755201 | 100 | 2 |  | 2 | 004 | 6060.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 | 110 | 2 |  | 1 | 860 | 12318.85 | 0 | 0 |  | N | 101 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4Q93 | 43120415201 | 013 | 2 |  | 1 | 131 | 66192.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
04 | E4Q93 | 43120415201 | 016 | 2 |  | 1 | 105 | 42065 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4Q93 | 43120415201 | 016 | 2 |  | 2 | 003 | 51450 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q93 | 43120415201 | 051 | 2 |  | 1 | 919 | 315659.86 | 315659.86 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R63 | 43060215201 | 005 | 2 |  | 1 | 101 | 7590.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4R63 | 43060215201 | 017 | 2 | 850 | 1 | 001 | 1145.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4R63 | 43060215201 | 017 | 2 | 850 | 2 | 503 | 2204.4 | 2204.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R63 | 43060215201 | 017 | 2 | 850 | 3 | 023 | 17560.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R63 | 43060215201 | 017 | 2 | 850 | 4 | 105 | 8846.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4R63 | 43060215201 | 021 | 2 |  | 1 | 003 | -31262.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R63 | 43060215201 | 022 | 2 |  | 1 | 919 | 65097.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R63 | 43060215201 | 028 | 2 |  | 1 | 007 | 79019.5 | 77535.8 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4R89 | 43234915201 | 017 | 2 |  | 1 | 502 | 87300 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | E4R89 | 43234915201 | 026 | 2 |  | 1 | 403 | -781.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
04 | E4R89 | 43234915201 | 034 | 2 |  | 1 | 919 | 41241.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
04 | E4S29 | 43059325201 | 005 | 2 |  | 1 | 010 | 72201 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4S29 | 43059325201 | 016 | 2 |  | 1 | 919 | 37845.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4S29 | 43059325201 | 016 | 2 |  | 2 | 919 | 410.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4S43 | 44009015201 | 009 | 2 |  | 1 | 503 | 150351.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S80 | 43609515201 | 009 | 2 |  | 1 | 001 | 74001.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4395 | 42936515201 | 032 | 2 |  | 1 | 919 | 4801.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4409 | 43019215201 | 006 | 2 |  | 1 | 015 | 46200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4409 | 43019215201 | 023 | 2 |  | 1 | 003 | 30000 | 30000 | 5 |  | N | 34 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4409 | 43019215201 | 024 | 2 |  | 1 | 003 | 19550.7 | 19550.7 | 1 |  | N | 30 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4409 | 43019215201 | 031 | 2 |  | 1 | 128 | 56373.97 | 56373.97 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4409 | 43019215201 | 034 | 2 |  | 1 | 107 | 36720 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4409 | 43019215201 | 059 | 2 |  | 1 | 105 | 3695 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4409 | 43019215201 | 062 | 2 |  | 1 | 503 | 1066 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4409 | 43019215201 | 065 | 2 |  | 1 | 919 | 43530.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4409 | 43019215201 | 069 | 2 |  | 1 | 112 | 15398.12 | 15398.12 | 5 |  | N | 30 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4422 | 43257425201 | 011 | 2 |  | 1 | 019 | 31513.91 | 31513.91 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
04 | T4422 | 43257425201 | 011 | 2 |  | 2 | 101 | 6712.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4422 | 43257425201 | 011 | 2 |  | 3 | 101 | 7267.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4422 | 43257425201 | 019 | 2 |  | 1 | 001 | 90269.54 | 28518.04 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4422 | 43257425201 | 021 | 2 |  | 1 | 919 | 28763.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4422 | 43257425201 | 033 | 2 |  | 1 | 001 | 160504.46 | 160504.46 | 1 |  | N | 16 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4439 | 42872515201 | 004 | 2 |  | 1 | 007 | 34090.87 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4439 | 42872515201 | 020 | 2 |  | 1 | 919 | 28836.33 | 28836.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4439 | 42872515201 | 028 | 2 |  | 1 | 001 | 7972.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4445 | 43060315201 | 006 | 2 |  | 1 | 101 | 30329.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4445 | 43060315201 | 009 | 2 |  | 1 | 305 | -72293 | 0 | 0 |  | N | -8 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4445 | 43060315201 | 014 | 2 |  | 1 | 101 | -1058 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4445 | 43060315201 | 021 | 2 |  | 1 | 919 | 27569.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4446 | 43294915201 | 010 | 2 |  | 1 | 305 | -1881.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4446 | 43294915201 | 021 | 2 |  | 1 | 919 | 16974.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4447 | 43510115201 | 010 | 2 |  | 1 | 919 | 16697.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4447 | 43510115201 | 013 | 2 |  | 1 | 101 | 3555.02 | 0 | 0 |  | N | -50 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4453 | 43786615201 | 012 | 2 |  | 1 | 919 | 4306.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4455 | 43442715201 | 005 | 2 |  | 1 | 004 | 26664 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4457 | 43436015201 | 017 | 2 |  | 1 | 919 | 31167.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4466 | 42871815201 | 014 | 2 |  | 1 | 112 | -5.76 | 8066.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5W79 | 42404045201 | 008 | 2 |  | 1 | 917 | 10306.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5W79 | 42404045201 | 017 | 2 |  | 1 | 009 | 0 | 0 | 0 |  | N | 71 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | E5W79 | 42404045201 | 026 | 2 |  | 1 | 919 | 181065.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | E5W79 | 42404045201 | 027 | 2 |  | 1 | 007 | -21651.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W79 | 42404045201 | 041 | 2 |  | 1 | 503 | 34307.26 | 34307.26 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W91 | 40441825201 | 012 | 2 |  | 1 | 917 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W91 | 40441825201 | 013 | 2 |  | 1 | 919 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W91 | 40441825201 | 014 | 2 |  | 1 | 024 | 2700.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W91 | 40441825201 | 014 | 2 |  | 2 | 101 | 6912 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y51 | 43832115201 | 009 | 2 |  | 1 | 107 | 57200.3 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y51 | 43832115201 | 014 | 2 |  | 1 | 105 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y56 | 43744715201 | 001 | 2 |  | 1 | 919 | 14118.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y56 | 43744715201 | 014 | 2 |  | 1 | 107 | 1172.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Y56 | 43744715201 | 014 | 2 |  | 2 | 503 | 5292.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y56 | 43744715201 | 014 | 2 |  | 3 | 503 | 47044.59 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y56 | 43744715201 | 014 | 2 |  | 4 | 503 | 9162.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y60 | 43474215201 | 001 | 2 |  | 1 | 101 | 68217.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y60 | 43474215201 | 006 | 2 |  | 1 | 919 | 88699.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y64 | 41832115201 | 006 | 2 |  | 1 | 007 | -12409.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Y64 | 41832115201 | 006 | 2 |  | 2 | 001 | 6157.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y64 | 41832115201 | 006 | 2 |  | 3 | 115 | 3444.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Y64 | 41832115201 | 009 | 2 |  | 1 | 919 | 7458.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Y64 | 41832115201 | 017 | 2 |  | 1 | 105 | 7379 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 002 | 2 |  | 1 | 919 | 1932.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 003 | 2 |  | 1 | 130 | 66510.99 | 0 | 2 |  | N | 7 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 006 | 2 |  | 1 | 101 | 23458.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 007 | 2 |  | 1 | 503 | 127050.46 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 | 010 | 2 |  | 1 | 503 | -49104 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 | 016 | 2 |  | 1 | 126 | 26339.73 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 016 | 2 |  | 2 | 101 | 22620.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y73 | 43065115201 | 016 | 2 |  | 3 | 503 | 4731.66 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 | 016 | 2 |  | 4 | 126 | 9804 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | E5Y77 | 43809615201 | 002 | 2 |  | 1 | 503 | 60637.04 | 0 | 2 |  | N | 30 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y77 | 43809615201 | 014 | 2 |  | 1 | 112 | 15452.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y92 | 43243835201 | 006 | 2 |  | 1 | 503 | 61439.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y92 | 43243835201 | 006 | 2 |  | 2 | 128 | 6101.65 | 877.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | E5Y92 | 43243835201 | 006 | 2 |  | 3 | 122 | 5739.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Y92 | 43243835201 | 006 | 2 |  | 4 | 122 | 7779.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Y96 | 43643415201 | 009 | 2 |  | 1 | 118 | 10692.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y96 | 43643415201 | 010 | 2 | 850 | 1 | 107 | 16612.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Y96 | 43643415201 | 010 | 2 | 850 | 2 | 122 | 922.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Z05 | 43566615201 | 007 | 2 | 850 | 1 | 001 | 27013.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | E5Z05 | 43566615201 | 007 | 2 | 850 | 2 | 118 | 2626 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Z05 | 43566615201 | 007 | 2 | 850 | 3 | 117 | 1129.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5313 | 23953535201 | 006 | 2 |  | 1 | 118 | 42033.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5313 | 23953535201 | 006 | 2 |  | 2 | 128 | -19696.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5313 | 23953535201 | 013 | 2 |  | 1 | 015 | 22715.07 | 22715.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 1 | 015 | 7984.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 2 | 015 | 4121.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 3 | 015 | 27003.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 4 | 015 | 1803 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 5 | 120 | 10560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5313 | 23953535201 | 014 | 2 | 850 | 6 | 015 | 2225.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 7 | 003 | 2608.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 8 | 015 | 11484.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 9 | 015 | 364.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 10 | 015 | 14127.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 014 | 2 | 850 | 11 | 120 | 3520 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5313 | 23953535201 | 017 | 2 |  | 1 | 305 | -230250.85 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5313 | 23953535201 | 021 | 2 |  | 1 | 015 | 51282.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 026 | 2 |  | 1 | 001 | 74753.04 | 73169.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 1 | 001 | 6690.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 2 | 115 | 21986.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 029 | 2 | 850 | 3 | 112 | 9747.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5313 | 23953535201 | 029 | 2 | 850 | 4 | 001 | 5526.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 5 | 503 | 2132.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5313 | 23953535201 | 029 | 2 | 850 | 6 | 112 | 4728.98 | 4728.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5313 | 23953535201 | 029 | 2 | 850 | 7 | 003 | 4773.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 9 | 503 | 12082.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5313 | 23953535201 | 029 | 2 | 850 | 10 | 012 | 45203.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 11 | 001 | 10817.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 12 | 001 | 1442.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 029 | 2 | 850 | 13 | 107 | 10186.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 029 | 2 | 850 | 14 | 115 | 5756.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 029 | 2 | 850 | 15 | 001 | 8924.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 030 | 2 |  | 1 | 001 | 52554.43 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 031 | 2 |  | 1 | 112 | 215760.48 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5313 | 23953535201 | 044 | 2 |  | 1 | 107 | 52442.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 047 | 2 |  | 1 | 115 | 36047.5 | 14600.39 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 048 | 2 |  | 1 | 105 | 573657.27 | 40099.03 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5313 | 23953535201 | 050 | 2 |  | 1 | 115 | 24598.27 | 16075.89 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 050 | 2 |  | 2 | 700 | 7659.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Minor Changes | Minor Changes | 7
05 | T5313 | 23953535201 | 054 | 2 |  | 1 | 115 | 62800.49 | 62800.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 055 | 2 |  | 1 | 015 | 38995.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 056 | 2 |  | 1 | 115 | 97386.47 | 6907.56 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 065 | 2 |  | 1 | 917 | 17081.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 068 | 2 |  | 1 | 103 | 2048509.98 | 1482235.08 | 1 |  | N | 105 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | T5313 | 23953535201 | 069 | 2 |  | 1 | 106 | 789009.9 | 789009.9 | 1 |  | N | 85 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5313 | 23953535201 | 070 | 2 |  | 1 | 115 | 474342.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 074 | 2 |  | 1 | 115 | 61559 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 086 | 2 | 850 | 1 | 001 | 21468.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 | 086 | 2 | 850 | 2 | 112 | 10690.28 | 8741.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5313 | 23953535201 | 086 | 2 | 850 | 3 | 010 | 6697.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5313 | 23953535201 | 093 | 2 |  | 1 | 919 | 30406.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5313 | 23953535201 | 095 | 2 |  | 1 | 015 | 130524.1 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 | 100 | 2 |  | 1 | 101 | 12000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5313 | 23953535201 | 104 | 2 |  | 1 | 113 | -37995.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5313 | 23953535201 | 108 | 2 |  | 1 | 010 | 113472.27 | 43489.76 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5431 | 23759225201 | 001 | 2 |  | 1 | 350 | 73500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
05 | T5431 | 23759225201 | 010 | 2 |  | 1 | 101 | 39516.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5431 | 23759225201 | 015 | 2 |  | 1 | 101 | 62144.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5431 | 23759225201 | 019 | 2 |  | 1 | 112 | 167476.31 | 167476.31 | 1 |  | N | 17 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 020 | 2 |  | 1 | 305 | -110307.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 021 | 2 |  | 1 | 001 | 375233.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5431 | 23759225201 | 023 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | -17 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 024 | 2 |  | 1 | 112 | 230281.64 | 26881.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 027 | 2 |  | 1 | 503 | 188393.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 027 | 2 |  | 2 | 503 | 305579.57 | 0 | 0 |  | N | -12 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 027 | 2 |  | 3 | 503 | 96334.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 1 | 503 | 1726.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 2 | 503 | 12583.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 3 | 503 | -699.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 4 | 128 | 20059.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 5 | 115 | 10562.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 6 | 503 | 13966.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 7 | 503 | 2563.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 8 | 106 | 11153.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 9 | 115 | 4857.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 10 | 115 | 9532 | 8066.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 11 | 003 | 13294.46 | 12661.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5431 | 23759225201 | 028 | 2 | 850 | 12 | 503 | 13224.46 | 3600.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 13 | 128 | 3209 | 3209 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 14 | 503 | 442.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 028 | 2 | 850 | 15 | 115 | 3756.67 | 2930.06 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 16 | 112 | 11906.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 17 | 115 | 6942.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 18 | 115 | 9572.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 028 | 2 | 850 | 19 | 115 | 1345.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 029 | 2 |  | 1 | 503 | 100000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 032 | 2 |  | 1 | 112 | 189700.21 | 30230.97 | 1 |  | N | 65 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 032 | 2 |  | 2 | 004 | 1650.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5431 | 23759225201 | 032 | 2 |  | 3 | 001 | 121672.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5431 | 23759225201 | 032 | 2 |  | 4 | 007 | 31602.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5431 | 23759225201 | 032 | 2 |  | 5 | 001 | 57416.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5431 | 23759225201 | 033 | 2 |  | 1 | 503 | -6660.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 041 | 2 | 850 | 1 | 106 | 28025.59 | 28025.59 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 | 041 | 2 | 850 | 2 | 007 | 21974.41 | 17251.18 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | T5431 | 23759225201 | 042 | 2 | 850 | 1 | 503 | 1645.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 2 | 503 | 2125.93 | 2018 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 3 | 503 | 3045.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 4 | 115 | 7376.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 5 | 115 | 9183.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 6 | 503 | 16206.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 7 | 115 | 20727.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 8 | 115 | 2460.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 9 | 107 | 16820.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 10 | 115 | 13623.88 | 6332.02 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 11 | 107 | 871.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 12 | 503 | 2389.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 13 | 503 | 398.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 14 | 115 | 2823.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 15 | 115 | 17115.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 16 | 115 | 934 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 17 | 503 | 3469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 18 | 115 | 3014.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 19 | 503 | 17792.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 042 | 2 | 850 | 20 | 112 | 3565.69 | 10262.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 21 | 115 | 1500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 22 | 115 | 2728 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 042 | 2 | 850 | 23 | 503 | 180 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 044 | 2 | 850 | 1 | 007 | 14682.31 | 11526.46 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | T5431 | 23759225201 | 044 | 2 | 850 | 2 | 106 | 4223.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 | 048 | 2 |  | 1 | 108 | 152999.88 | 0 | 1 |  | N | 22 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5431 | 23759225201 | 049 | 2 |  | 1 | 503 | 149914.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 1 | 112 | 6697.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 2 | 128 | 8746.07 | 4791.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 3 | 503 | 4566.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 4 | 503 | 10662.61 | 234.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 5 | 105 | 4445.16 | 3035.73 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 6 | 107 | 1328.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 7 | 503 | 2615.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 8 | 107 | 1100.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 9 | 123 | 1255.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 10 | 128 | 494.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 11 | 503 | 3863.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 12 | 112 | -6697.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 13 | 112 | 6697.04 | 10262.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 14 | 503 | -4566.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 15 | 503 | 4566.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 058 | 2 | 850 | 16 | 123 | -1255.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
05 | T5431 | 23759225201 | 058 | 2 | 850 | 17 | 123 | 5479.92 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
05 | T5431 | 23759225201 | 059 | 2 |  | 1 | 112 | 13049.15 | 13049.15 | 1 |  | N | 23 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 | 069 | 2 |  | 1 | 115 | 49586.77 | 49586.77 | 1 |  | N | 19 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 071 | 2 | 850 | 1 | 106 | 4223.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 | 071 | 2 | 850 | 2 | 503 | 9566.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 071 | 2 | 850 | 3 | 503 | 8844.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 071 | 2 | 850 | 4 | 115 | 652.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 071 | 2 | 850 | 5 | 106 | -4223.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 | 071 | 2 | 850 | 6 | 115 | 1670.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 072 | 2 |  | 1 | 503 | 325667.25 | 0 | 0 |  | N | 104 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 073 | 2 |  | 1 | 115 | 10858.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 073 | 2 |  | 2 | 115 | 8524.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 073 | 2 |  | 3 | 126 | 61344.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 1 | 503 | 121613.68 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 082 | 2 |  | 2 | 126 | 22097.45 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 3 | 115 | 237757.25 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 4 | 107 | 50079.75 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 5 | 503 | 1488.2 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 082 | 2 |  | 6 | 128 | 11953.2 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 7 | 107 | 4554.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5431 | 23759225201 | 082 | 2 |  | 8 | 350 | 5650 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
05 | T5431 | 23759225201 | 082 | 2 |  | 9 | 503 | 40000 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 | 083 | 2 |  | 1 | 860 | 662571.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5534 | 42875315201 | 005 | 2 |  | 1 | 917 | 19973.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5534 | 42875315201 | 019 | 2 |  | 1 | 919 | 273827.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5534 | 42875315201 | 023 | 2 |  | 1 | 107 | 0 | 0 | 0 |  | N | -30 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5534 | 42875315201 | 028 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | T5534 | 42875315201 | 032 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | -15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5534 | 42875315201 | 035 | 2 |  | 1 | 503 | 213235.65 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5555 | 43543315201 | 008 | 2 |  | 1 | 917 | 8436.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5555 | 43543315201 | 020 | 2 |  | 1 | 919 | 78927.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5558 | 23842215201 | 007 | 2 |  | 1 | 305 | -39998.25 | 0 | 0 |  | N | -40 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5558 | 23842215201 | 010 | 2 |  | 1 | 305 | -90770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5558 | 23842215201 | 012 | 2 |  | 1 | 917 | 6604 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5558 | 23842215201 | 018 | 2 |  | 1 | 007 | -2833.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5558 | 23842215201 | 019 | 2 |  | 1 | 001 | 276043.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 | 030 | 2 |  | 1 | 919 | 52480.89 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 | 031 | 2 |  | 1 | 917 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 | 033 | 2 | 850 | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | T5558 | 23842215201 | 037 | 2 |  | 1 | 005 | 8529.64 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5558 | 23842215201 | 039 | 2 |  | 1 | 107 | 10782 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5564 | 43505515201 | 017 | 2 |  | 1 | 503 | 47385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5564 | 43505515201 | 021 | 2 |  | 1 | 919 | 9095.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5578 | 43364815201 | 006 | 2 |  | 1 | 101 | 100000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5578 | 43364815201 | 015 | 2 |  | 1 | 919 | 25759.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5578 | 43364815201 | 021 | 2 |  | 1 | 112 | 0 | 0 | 0 |  | N | 105 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5578 | 43364815201 | 021 | 2 |  | 2 | 015 | -26906.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815201 | 021 | 2 |  | 3 | 015 | 16409.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5580 | 43259215201 | 010 | 2 |  | 1 | 919 | 16708.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5580 | 43259215201 | 020 | 2 |  | 1 | 503 | 96495.61 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5580 | 43259215201 | 028 | 2 |  | 1 | 503 | -12478.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5584 | 43233315201 | 005 | 2 |  | 1 | 919 | 124247.21 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5584 | 43233315201 | 015 | 2 |  | 1 | 010 | 46059.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5584 | 43233315201 | 018 | 2 | 850 | 1 | 128 | 7544.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5585 | 43441715201 | 008 | 2 |  | 1 | 919 | 15934.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5585 | 43441715201 | 016 | 2 |  | 1 | 012 | 36813.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5587 | 43505415201 | 004 | 2 |  | 1 | 919 | 3031.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5587 | 43505415201 | 013 | 2 |  | 1 | 004 | 12084 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5587 | 43505415201 | 021 | 2 |  | 1 | 105 | 87944.25 | 688.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5598 | 43566115201 | 007 | 2 |  | 1 | 107 | -6000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5598 | 43566115201 | 007 | 2 |  | 2 | 105 | 18427.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5600 | 43691515201 | 003 | 2 |  | 1 | 101 | 66510.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5600 | 43691515201 | 009 | 2 |  | 1 | 118 | 70870.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5612 | 44113035201 | 001 | 2 |  | 1 | 919 | 1131727.86 | 0 | 0 |  | N | 84 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5620 | 43367315201 | 011 | 2 |  | 1 | 018 | 5428.5 | 5428.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | E6J51 | 43652415201 | 021 | 2 |  | 1 | 919 | 49068.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | E6J96 | 42918725201 | 001 | 2 |  | 1 | 101 | 94690 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6J96 | 42918725201 | 011 | 2 |  | 1 | 118 | 18426.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6J96 | 42918725201 | 014 | 2 |  | 1 | 919 | 11985.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K52 | 43029119201 | 003 | 2 |  | 1 | 503 | 53543.01 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K52 | 43029119201 | 013 | 2 | 850 | 1 | 503 | 7897.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K52 | 43029119201 | 014 | 2 |  | 1 | 003 | -6552.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6K55 | 42527135201 | 004 | 2 |  | 1 | 004 | -37423.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K55 | 42527135201 | 005 | 2 |  | 1 | 004 | -4986.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K55 | 42527135201 | 014 | 2 | 850 | 1 | 012 | 4390.76 | 4390.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K55 | 42527135201 | 014 | 2 | 850 | 2 | 001 | 16683.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K55 | 42527135201 | 014 | 2 | 850 | 3 | 004 | 17482.93 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K55 | 42527135201 | 017 | 2 |  | 1 | 919 | 43737.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L12 | 43560115201 | 008 | 2 |  | 1 | 919 | 18073.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L12 | 43560115201 | 010 | 2 |  | 1 | 300 | -67672.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
06 | E6L12 | 43560115201 | 018 | 2 | 850 | 1 | 101 | 19537.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L12 | 43560115201 | 021 | 2 |  | 1 | 503 | 244942.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L12 | 43560115201 | 022 | 2 | 850 | 1 | 108 | 9982.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L12 | 43560115201 | 022 | 2 | 850 | 2 | 503 | 9441.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L12 | 43560115201 | 025 | 2 |  | 1 | 108 | 65850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6339 | 41463325201 | 011 | 2 |  | 1 | 001 | 147801.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6339 | 41463325201 | 022 | 2 | 850 | 1 | 001 | 35116.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6339 | 41463325201 | 022 | 2 | 850 | 2 | 115 | 38129.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6339 | 41463325201 | 022 | 2 | 850 | 3 | 118 | 9634.24 | 9634.24 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6339 | 41463325201 | 023 | 2 | 850 | 1 | 503 | 52330.44 | 52330.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 | 023 | 2 | 850 | 2 | 503 | 12997.72 | 12997.72 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 | 023 | 2 | 850 | 3 | 503 | 2195.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 | 023 | 2 | 850 | 4 | 101 | 13184 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6339 | 41463325201 | 025 | 2 |  | 1 | 503 | 79042.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 | 026 | 2 |  | 1 | 919 | 19764.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 | 033 | 2 |  | 1 | 503 | -4524.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 | 011 | 2 |  | 1 | 503 | 10482.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 | 017 | 2 |  | 1 | 015 | 407591.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 | 036 | 2 | 850 | 1 | 001 | 8320.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 | 036 | 2 | 850 | 2 | 115 | 9136.94 | 9136.94 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 | 036 | 2 | 850 | 3 | 101 | 28350.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6347 | 42559815201 | 036 | 2 | 850 | 4 | 003 | 2290.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815201 | 045 | 2 |  | 1 | 113 | 0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6347 | 42559815201 | 048 | 2 |  | 1 | 919 | 37367.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6347 | 42559815201 | 049 | 2 |  | 1 | 503 | 204672.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 | 053 | 2 |  | 1 | 919 | 3864.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 | 054 | 2 |  | 1 | 919 | 16403.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 | 055 | 2 |  | 1 | 113 | -18980.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6348 | 41247935201 | 017 | 2 |  | 1 | 101 | 15951.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6348 | 41247935201 | 018 | 2 | 850 | 1 | 103 | 63078.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6348 | 41247935201 | 018 | 2 | 850 | 2 | 860 | 20427.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
06 | T6348 | 41247935201 | 022 | 2 |  | 1 | 305 | -502097.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
06 | T6348 | 41247935201 | 028 | 2 |  | 1 | 919 | 47463.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
06 | T6388 | 24961475201 | 008 | 2 | 850 | 1 | 850 | 134532.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6388 | 24961475201 | 008 | 2 | 850 | 2 | 115 | 15467.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 014 | 2 | 850 | 1 | 115 | 3121.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 014 | 2 | 850 | 2 | 115 | 36024 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 014 | 2 | 850 | 3 | 115 | 99000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 014 | 2 | 850 | 4 | 101 | 2640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6388 | 24961475201 | 014 | 2 | 850 | 5 | 105 | 9214.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 1 | 105 | 12442.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 2 | 118 | 28996.04 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 3 | 118 | 7680.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 4 | 118 | 18624.29 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 5 | 122 | 24075.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 6 | 115 | 32074.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 016 | 2 | 850 | 7 | 003 | 20421.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6388 | 24961475201 | 016 | 2 | 850 | 8 | 001 | 5685 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
06 | T6388 | 24961475201 | 023 | 2 |  | 1 | 101 | 103061.73 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6388 | 24961475201 | 028 | 2 |  | 1 | 919 | 189984.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6388 | 24961475201 | 034 | 2 | 850 | 1 | 007 | 1502.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6388 | 24961475201 | 034 | 2 | 850 | 2 | 001 | 14549.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6388 | 24961475201 | 034 | 2 | 850 | 3 | 001 | 6835.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6388 | 24961475201 | 034 | 2 | 850 | 5 | 113 | 55558.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6388 | 24961475201 | 034 | 2 | 850 | 6 | 024 | 42750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6390 | 43094915201 | 005 | 2 |  | 1 | 503 | 109500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 009 | 2 |  | 1 | 919 | 1044.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 011 | 2 |  | 1 | 919 | 18913.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 014 | 2 |  | 1 | 850 | 47023 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6390 | 43094915201 | 017 | 2 | 850 | 1 | 012 | 28230.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6390 | 43094915201 | 017 | 2 | 850 | 2 | 503 | 458.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 017 | 2 | 850 | 3 | 503 | 16087.41 | 16087.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 018 | 2 | 850 | 1 | 503 | 27000 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 | 018 | 2 | 850 | 2 | 112 | 12923.3 | 12923.3 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6390 | 43094915201 | 018 | 2 | 850 | 3 | 007 | 3654.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6415 | 43328625201 | 015 | 2 |  | 1 | 919 | 28194.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6416 | 43305925201 | 013 | 2 |  | 1 | 919 | 34457.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6416 | 43305925201 | 014 | 2 |  | 1 | 018 | 74806 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6416 | 43305925201 | 017 | 2 |  | 1 | 018 | 38553.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6418 | 43274825201 | 006 | 2 |  | 1 | 919 | 1512.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6418 | 43274825201 | 011 | 2 |  | 1 | 001 | 30195.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6418 | 43274825201 | 012 | 2 |  | 1 | 106 | 7702 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6418 | 43274825201 | 013 | 2 |  | 1 | 106 | 881.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6418 | 43274825201 | 016 | 2 |  | 1 | 106 | 2475.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6418 | 43274825201 | 023 | 2 |  | 1 | 112 | 4432.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6418 | 43274825201 | 023 | 2 |  | 2 | 112 | 4431.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6426 | 43477115201 | 001 | 2 |  | 1 | 105 | 40670.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6426 | 43477115201 | 014 | 2 |  | 1 | 001 | 22977.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L03 | 43656815201 | 014 | 2 |  | 1 | 001 | 311918.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L03 | 43656815201 | 028 | 2 |  | 1 | 919 | 54768.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L03 | 43656815201 | 028 | 2 |  | 2 | 919 | 793.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L45 | 43243515201 | 015 | 2 |  | 1 | 919 | 18986.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L45 | 43243515201 | 016 | 2 |  | 1 | 012 | 18032.73 | 18032.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L59 | 43070815201 | 005 | 2 |  | 1 | 503 | -19.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L76 | 43589615201 | 005 | 2 |  | 1 | 105 | 78500 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L82 | 43269715201 | 004 | 2 |  | 1 | 101 | 2556.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L82 | 43269715201 | 015 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7292 | 40915415201 | 015 | 2 |  | 1 | 107 | 167134.24 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915415201 | 042 | 2 |  | 1 | 117 | 90308.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7292 | 40915415201 | 043 | 2 |  | 1 | 101 | 74000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7292 | 40915415201 | 046 | 2 |  | 1 | 015 | 93099.55 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 048 | 2 | 850 | 1 | 007 | 697.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915415201 | 049 | 2 | 850 | 1 | 007 | 27002.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 1 | 015 | 4362.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 2 | 015 | 46749.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 3 | 015 | 1305.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 4 | 015 | 20247.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 5 | 015 | 15569.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 6 | 015 | 21673.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 7 | 015 | 15307.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 8 | 015 | 5050.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 055 | 2 |  | 9 | 115 | 1763.45 | 1763.45 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 | 055 | 2 |  | 10 | 115 | 101757.35 | 59368.96 | 1 |  | N | 6 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 | 062 | 2 |  | 1 | 012 | 393335.01 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7292 | 40915415201 | 062 | 2 |  | 2 | 012 | 734589.02 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7292 | 40915415201 | 062 | 2 |  | 3 | 003 | 78014.25 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7292 | 40915415201 | 063 | 2 |  | 1 | 015 | 89013.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 066 | 2 |  | 1 | 015 | -70353.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 080 | 2 |  | 1 | 015 | 29046.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 080 | 2 |  | 2 | 015 | 7495.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 080 | 2 |  | 3 | 015 | 5621.06 | 5621.06 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 080 | 2 |  | 4 | 015 | 16484 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 080 | 2 |  | 5 | 015 | 27636 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 097 | 2 |  | 1 | 106 | 4516.73 | 4516.73 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7292 | 40915415201 | 097 | 2 |  | 2 | 015 | 1468.24 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 097 | 2 |  | 3 | 015 | 3539.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7292 | 40915415201 | 097 | 2 |  | 4 | 112 | 1842.15 | 1842.15 | 1 |  | C | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7292 | 40915415201 | 097 | 2 |  | 5 | 108 | 25831.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7292 | 40915415201 | 101 | 2 |  | 1 | 860 | 138675.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | T7304 | 40795135201 | 037 | 2 |  | 1 | 007 | 58113.3 | 17750.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7304 | 40795135201 | 037 | 2 |  | 2 | 112 | 7627.6 | 7627.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7304 | 40795135201 | 039 | 2 | 850 | 1 | 128 | 23602.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7304 | 40795135201 | 039 | 2 | 850 | 3 | 007 | 3509.27 | 3509.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7304 | 40795135201 | 039 | 2 | 850 | 4 | 105 | 18651.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 | 039 | 2 | 850 | 5 | 105 | 6866.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 | 044 | 2 |  | 1 | 004 | -486194.89 | 44594.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7304 | 40795135201 | 044 | 2 |  | 2 | 503 | 12270.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7304 | 40795135201 | 044 | 2 |  | 3 | 503 | 34416.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7304 | 40795135201 | 055 | 2 |  | 1 | 105 | 37547.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 | 069 | 2 |  | 1 | 007 | 54284.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7304 | 40795135201 | 069 | 2 |  | 2 | 007 | 15557.1 | 744 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7304 | 40795135201 | 069 | 2 |  | 3 | 007 | 13571.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7304 | 40795135201 | 070 | 2 |  | 1 | 105 | 4943 | 3095 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 | 070 | 2 |  | 2 | 003 | 14693.28 | 14693.28 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7304 | 40795135201 | 071 | 2 |  | 1 | 108 | 1007.92 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 | 072 | 2 |  | 1 | 105 | 19566.56 | 19566.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 | 072 | 2 |  | 2 | 105 | 3750.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7317 | 41886075201 | 005 | 2 |  | 1 | 503 | 1256.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7317 | 41886075201 | 006 | 2 |  | 1 | 015 | -6440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 007 | 2 |  | 1 | 015 | -13346.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 011 | 2 |  | 1 | 101 | -5399.61 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7317 | 41886075201 | 029 | 2 |  | 1 | 117 | 30349.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 029 | 2 |  | 2 | 117 | 22749.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 029 | 2 |  | 3 | 117 | 6935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 038 | 2 |  | 1 | 112 | 360582.6 | 34054.78 | 1 |  | N | 88 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7317 | 41886075201 | 057 | 2 |  | 1 | 015 | 18193.98 | 1519.13 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 061 | 2 |  | 1 | 015 | -310000.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 061 | 2 |  | 2 | 015 | 31137.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 061 | 2 |  | 3 | 015 | 9133.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 062 | 2 |  | 1 | 117 | 16968.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 062 | 2 |  | 2 | 117 | 67998.83 | 14342.22 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 062 | 2 |  | 3 | 117 | 1585.1 | 2686 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7317 | 41886075201 | 067 | 2 |  | 1 | 503 | -17918.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7317 | 41886075201 | 067 | 2 |  | 2 | 503 | -1610.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7317 | 41886075201 | 075 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7353 | 25699535201 | 006 | 2 |  | 1 | 015 | -23931.97 | 9855.88 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 014 | 2 |  | 1 | 101 | 905.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7353 | 25699535201 | 014 | 2 |  | 2 | 107 | 108014.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 014 | 2 |  | 3 | 101 | 4174.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7353 | 25699535201 | 014 | 2 |  | 4 | 305 | -113879.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7353 | 25699535201 | 014 | 2 |  | 6 | 001 | 110741.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7353 | 25699535201 | 015 | 2 |  | 1 | 010 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7353 | 25699535201 | 017 | 2 |  | 1 | 015 | 3634.8 | 3634.8 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 033 | 2 |  | 1 | 015 | 5738.57 | 5738.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 034 | 2 |  | 1 | 115 | -2538 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 034 | 2 |  | 2 | 005 | 2755.99 | 2755.99 | 5 |  | C | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7353 | 25699535201 | 034 | 2 |  | 3 | 003 | 2667.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7353 | 25699535201 | 035 | 2 |  | 1 | 107 | 187002.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 036 | 2 |  | 1 | 107 | 138019.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 042 | 2 |  | 1 | 015 | 8243.53 | 4184.03 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 045 | 2 |  | 1 | 107 | 139148.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 048 | 2 |  | 1 | 107 | 89961.19 | 20202.05 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 050 | 2 |  | 1 | 101 | 3692.01 | 3692.01 | 5 |  | C | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7353 | 25699535201 | 050 | 2 |  | 2 | 015 | 5836.32 | 5836.32 | 5 |  | C | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 053 | 2 |  | 1 | 015 | 11569.48 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 055 | 2 |  | 1 | 917 | 2364.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 055 | 2 |  | 2 | 108 | 10818.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7353 | 25699535201 | 055 | 2 |  | 3 | 115 | 20482.43 | 20482.43 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 055 | 2 |  | 4 | 112 | 34741.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7353 | 25699535201 | 055 | 2 |  | 5 | 107 | 26940.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 055 | 2 |  | 6 | 115 | 11834.91 | 11834.91 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 056 | 2 |  | 1 | 005 | 134177.23 | 134177.23 | 5 |  | N | 29 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7353 | 25699535201 | 057 | 2 |  | 1 | 005 | 129858.33 | 129858.33 | 5 |  | N | 40 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7353 | 25699535201 | 058 | 2 |  | 1 | 107 | 48702.08 | 0 | 1 |  | N | 13 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 060 | 2 |  | 1 | 107 | 155571.41 | 0 | 1 |  | N | 45 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7353 | 25699535201 | 062 | 2 |  | 1 | 015 | 124171.01 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 075 | 2 |  | 1 | 015 | 2142.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 079 | 2 |  | 1 | 919 | 28946.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7353 | 25699535201 | 079 | 2 |  | 2 | 403 | -38766.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
07 | T7353 | 25699535201 | 079 | 2 |  | 3 | 024 | 32741.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
07 | T7353 | 25699535201 | 079 | 2 |  | 4 | 105 | 183411.87 | 183411.87 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7379 | 42906015202 | 012 | 2 |  | 1 | 115 | 519.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 012 | 2 |  | 2 | 115 | 3845.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 012 | 2 |  | 3 | 115 | 3665.07 | 3665.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 012 | 2 |  | 4 | 115 | 1281.92 | 1281.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 012 | 2 |  | 6 | 115 | 6764.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 016 | 2 |  | 1 | 115 | 1671.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 016 | 2 |  | 2 | 007 | 35408.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7379 | 42906015202 | 016 | 2 |  | 3 | 115 | 35295.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 016 | 2 |  | 4 | 007 | 35408.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7379 | 42906015202 | 017 | 2 | 850 | 1 | 122 | 2044.12 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 1 | 023 | 3596.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 2 | 115 | 1669.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 3 | 403 | -1312.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
07 | T7379 | 42906015202 | 023 | 2 |  | 4 | 115 | 4444.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 5 | 024 | 8440.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 6 | 001 | 39615.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7379 | 42906015202 | 023 | 2 |  | 7 | 115 | 868.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 8 | 112 | 4211.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7379 | 42906015202 | 023 | 2 |  | 9 | 106 | 6020.27 | 6020.27 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7379 | 42906015202 | 034 | 2 |  | 1 | 919 | 9148.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7379 | 42906015202 | 034 | 2 |  | 2 | 919 | 16351.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7379 | 42906015202 | 035 | 2 |  | 1 | 003 | 684.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7379 | 42906015202 | 035 | 2 |  | 2 | 115 | 21978.62 | 13881.45 | 3 |  | N | 0 | Avoidable, CEI Consultant | Drainage Modification | Plan Modifications | 2
07 | T7379 | 42906015202 | 035 | 2 |  | 3 | 115 | 19282.18 | 5697 | 3 |  | N | 0 | Avoidable, CEI Consultant | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615202 | 003 | 2 |  | 1 | 012 | 28043.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7382 | 43258615202 | 004 | 2 | 850 | 1 | 001 | 3162.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 004 | 2 | 850 | 2 | 012 | 3735.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7382 | 43258615202 | 004 | 2 | 850 | 3 | 115 | 566.64 | 566.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615202 | 004 | 2 | 850 | 4 | 005 | 8481.44 | 8481.44 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 004 | 2 | 850 | 5 | 005 | 3775.57 | 3775.57 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 004 | 2 | 850 | 6 | 001 | 2688.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 004 | 2 | 850 | 7 | 005 | 2233.35 | 2233.35 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 005 | 2 | 850 | 1 | 001 | 40350.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 005 | 2 | 850 | 2 | 001 | 7657.32 | 7657.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 008 | 2 |  | 1 | 004 | 1352.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7382 | 43258615202 | 017 | 2 |  | 1 | 003 | 76532.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7382 | 43258615202 | 020 | 2 |  | 1 | 101 | 10228.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7382 | 43258615202 | 023 | 2 |  | 1 | 101 | 3438.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7382 | 43258615202 | 023 | 2 |  | 2 | 005 | 709.43 | 709.43 | 3 |  | N | 0 | Avoidable, CEI Consultant | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 027 | 2 |  | 2 | 115 | 9382.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615202 | 027 | 2 |  | 3 | 115 | 71390.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615202 | 027 | 2 |  | 4 | 001 | 22185.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 028 | 2 |  | 1 | 005 | 116443.87 | 116443.87 | 5 |  | N | 59 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 028 | 2 |  | 3 | 106 | 83845.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7382 | 43258615202 | 028 | 2 |  | 4 | 005 | 2114.11 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7382 | 43258615202 | 031 | 2 |  | 1 | 101 | 6388.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7382 | 43258615202 | 031 | 2 |  | 2 | 106 | 6388.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7382 | 43258615202 | 031 | 2 |  | 3 | 001 | 3579.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 034 | 2 |  | 1 | 919 | 19377.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615202 | 038 | 2 |  | 1 | 012 | 2500.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 | 015 | 2 |  | 1 | 001 | 2709.61 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7387 | 42895415201 | 017 | 2 | 850 | 1 | 012 | 111011.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 | 017 | 2 | 850 | 2 | 503 | 1220.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 | 017 | 2 | 850 | 3 | 503 | 37768.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 | 024 | 2 |  | 2 | 101 | 79112.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7387 | 42895415201 | 027 | 2 |  | 1 | 101 | 75915.12 | 0 | 1 |  | N | 28 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7387 | 42895415201 | 029 | 2 |  | 1 | 919 | 41339.46 | 41339.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7387 | 42895415201 | 033 | 2 | 850 | 1 | 503 | 3845.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7390 | 43480715201 | 009 | 2 |  | 1 | 023 | 27039.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7390 | 43480715201 | 013 | 2 |  | 1 | 022 | 3740.84 | 3740.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7392 | 43484115202 | 016 | 2 |  | 1 | 007 | 148502.5 | 0 | 0 |  | E | 21 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7405 | 43649015201 | 001 | 2 |  | 1 | 107 | 98758 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7405 | 43649015201 | 007 | 2 | 850 | 1 | 001 | 8523.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 011 | 2 |  | 1 | 305 | -35902.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 028 | 2 |  | 1 | 503 | 25030.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 | 028 | 2 |  | 2 | 106 | 14612.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8N52 | 42935045201 | 036 | 2 |  | 1 | 001 | 35767.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 036 | 2 |  | 2 | 103 | 77840.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8N52 | 42935045201 | 036 | 2 |  | 3 | 001 | 3578.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 036 | 2 |  | 4 | 001 | 8620.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 047 | 2 |  | 1 | 004 | 345655.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N52 | 42935045201 | 047 | 2 |  | 2 | 118 | 128748.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N52 | 42935045201 | 047 | 2 |  | 3 | 012 | 4521.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N52 | 42935045201 | 054 | 2 |  | 1 | 919 | 113213.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 1 | 003 | 246443.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 2 | 915 | 25035.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 3 | 003 | 7100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 4 | 503 | 33802.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 | 060 | 2 |  | 5 | 503 | 19269.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 | 060 | 2 |  | 6 | 003 | 17058.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 7 | 003 | 7361.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N52 | 42935045201 | 060 | 2 |  | 8 | 004 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N52 | 42935045201 | 061 | 2 |  | 1 | 860 | 200000 | 0 | 0 |  | N | 34 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8P90 | 43561515201 | 003 | 2 |  | 1 | 107 | 6049.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P90 | 43561515201 | 010 | 2 |  | 1 | 503 | 75423.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 1 | 503 | 15235.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 2 | 503 | 5132.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 3 | 115 | 1298.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 4 | 115 | 8994.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 5 | 001 | 4952.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 6 | 108 | 2606.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 7 | 503 | 42382.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 8 | 108 | 1574.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 9 | 108 | 13959 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 10 | 115 | 2475 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 11 | 503 | 550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 019 | 2 | 850 | 12 | 101 | 170.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 | 021 | 2 |  | 1 | 919 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 1 | 105 | 14458.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 2 | 503 | 16500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 3 | 001 | 46832.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 4 | 503 | 1911.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 5 | 112 | 8633.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 6 | 115 | 1028.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 7 | 108 | 3317.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 8 | 503 | 2949.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 9 | 101 | 2442 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 | 022 | 2 | 850 | 10 | 503 | 537.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 025 | 2 |  | 1 | 101 | 49252.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 | 026 | 2 |  | 1 | 101 | 3272.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 | 035 | 2 |  | 1 | 105 | 178000 | 178000 | 1 |  | C | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P90 | 43561515201 | 035 | 2 |  | 2 | 010 | 62000 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P90 | 43561515201 | 035 | 2 |  | 3 | 503 | 100000 | 0 | 0 |  | C | 26 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 049 | 2 |  | 1 | 503 | -4261.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 050 | 2 |  | 1 | 919 | 77992.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 1 | 007 | 7726.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 2 | 503 | 2780.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 3 | 503 | 4106.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 4 | 503 | 11500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 5 | 503 | 11000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 6 | 503 | 1366.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 052 | 2 | 850 | 7 | 007 | 744.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8P90 | 43561515201 | 053 | 2 |  | 1 | 503 | 2151.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 | 062 | 2 |  | 1 | 503 | 93000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q11 | 43715625201 | 001 | 2 |  | 1 | 305 | -104904.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q11 | 43715625201 | 017 | 2 |  | 1 | 919 | 60614.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q11 | 43715625201 | 023 | 2 |  | 1 | 101 | -280.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 009 | 2 |  | 1 | 113 | 32152.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 1 | 021 | 1991.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 2 | 023 | 7597.7 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 3 | 023 | 1468.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 4 | 023 | 2361.71 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 5 | 021 | 425.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 6 | 023 | 1349.23 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 7 | 101 | 2750 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 8 | 021 | 1044.71 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 014 | 2 | 850 | 9 | 023 | 3238.49 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 1 | 021 | 2971.32 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 2 | 021 | 17960.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 3 | 021 | 1108.47 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 4 | 023 | 948.48 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 5 | 023 | 1315.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 6 | 023 | 2200.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 7 | 021 | -17960.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 8 | 021 | 17950.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 015 | 2 | 850 | 9 | 021 | 3504.99 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 021 | 2 | 850 | 1 | 503 | 2445.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q45 | 43516615201 | 021 | 2 | 850 | 2 | 115 | 15271.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 024 | 2 |  | 1 | 919 | 23622.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 025 | 2 |  | 1 | 113 | 97470.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 1 | 023 | 4332.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 2 | 101 | 5100 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 3 | 023 | 7491.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 4 | 023 | 879.91 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 5 | 023 | 789.42 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q45 | 43516615201 | 028 | 2 | 850 | 6 | 105 | 157.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q48 | 43560815201 | 008 | 2 |  | 1 | 503 | 4656.12 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q48 | 43560815201 | 013 | 2 |  | 1 | 105 | 4957.24 | 0 | 1 |  | N | 21 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q77 | 43905115201 | 005 | 2 |  | 1 | 113 | 1808.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | E1K75 | 20121435201 |  | 2 | CPI | 1 | 001 | 3420.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1K75 | 20121435201 |  | 2 | CPI | 1 | 003 | 23374.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1K75 | 20121435201 |  | 2 | CPI | 2 | 917 | 12108.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1K75 | 20121435201 |  | 2 | CPI | 1 | 917 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1K75 | 20121435201 |  | 2 | CPI | 1 | 001 | 8477.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P47 | 43771415201 |  | 2 | CPI | 1 | 106 | 5676.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P47 | 43771415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1Q20 | 43979815201 |  | 2 | CPI | 1 | 115 | 2460.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1Q22 | 43854515201 |  | 2 | CPI | 1 | 012 | 3832.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1Q46 | 43659915201 |  | 2 | CPI | 1 | 001 | 48258.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 |  | 2 | CPI | 1 | 001 | 1741.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q75 | 43659815201 |  | 2 | CPI | 1 | 503 | 7261.65 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R01 | 43668415201 |  | 2 | CPI | 1 | 112 | 4859.7 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R55 | 43902615201 |  | 2 | CPI | 1 | 103 | 17919.02 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1550 | 41304445201 |  | 2 | CPI | 1 | 001 | 4573.83 | 4573.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1550 | 41304445201 |  | 2 | CPI | 1 | 012 | 1158.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1550 | 41304445201 |  | 2 | CPI | 1 | 915 | 16545.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1550 | 41304445201 |  | 2 | CPI | 1 | 012 | 2151.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 903 | 2058.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 115 | 805.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 001 | 17303.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 107 | 7080.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 2 | 105 | 1502.6 | 1502.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 3 | 115 | 4148.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 107 | 27669.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 112 | 11249.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 107 | 27669.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 107 | -27669.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 115 | 8272.36 | 2935 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 2 | 115 | 454.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 115 | 2935 | 2935 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 128 | 377.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 112 | 14061.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 105 | 19217.66 | 19217.66 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 115 | 646.25 | 646.25 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 107 | 7080.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 2 | 115 | 4148.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 107 | -7080.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1576 | 19690425201 |  | 2 | CPI | 2 | 115 | -4148.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 012 | 1283.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 |  | 2 | CPI | 2 | 115 | -646.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 115 | 646.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 012 | -1283.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 012 | 1283.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690425201 |  | 2 | CPI | 1 | 112 | 30935.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1576 | 19690445201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | E | 5 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | 4912 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | 1687.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 2 | 105 | 1541.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | 4912 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 2 | 001 | 4912 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | -4912 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745601 |  | 2 | CPI | 1 | 015 | 756.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745601 |  | 2 | CPI | 2 | 015 | 968.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745601 |  | 2 | CPI | 1 | 015 | 3922.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | 4475.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 001 | 6552.24 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 2 | 106 | 4903.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1606 | 19801745601 |  | 2 | CPI | 1 | 015 | 1616.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745601 |  | 2 | CPI | 2 | 015 | 4059.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745601 |  | 2 | CPI | 3 | 015 | 4710.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1606 | 19801745201 |  | 2 | CPI | 1 | 106 | 4625.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 503 | 3852 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 004 | -4430.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1621 | 20127725201 |  | 2 | CPI | 1 | 010 | 2295.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 001 | 7504.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1621 | 20127725201 |  | 2 | CPI | 1 | 012 | 10137.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 101 | 8981.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1621 | 20127725201 |  | 2 | CPI | 1 | 101 | 6503.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1621 | 20127725201 |  | 2 | CPI | 1 | 126 | 11766 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 001 | 28358.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1621 | 20103245201 |  | 2 | CPI | 1 | 022 | 30733.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1621 | 20127725201 |  | 2 | CPI | 1 | 022 | 22701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 1 | 117 | 541.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1623 | 43127815201 |  | 2 | CPI | 1 | 007 | 825.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 2 | 001 | 747.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 3 | 118 | 4448.4 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1623 | 43127815201 |  | 2 | CPI | 4 | 012 | 11969.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 1 | 115 | 5078.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1623 | 43127815201 |  | 2 | CPI | 2 | 115 | 840.49 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1623 | 43127815201 |  | 2 | CPI | 1 | 012 | 471.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 2 | 017 | 3402.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1623 | 43127815201 |  | 2 | CPI | 3 | 015 | 6686.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 101 | 12927.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 101 | 12927.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 101 | -12927.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 105 | 861.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 010 | 34558.5 | 34558.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1646 | 43275515202 |  | 2 | CPI | 2 | 106 | 1033.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 112 | 618.89 | 618.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1646 | 43275515202 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 106 | 4861.03 | 4861.03 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 115 | 5662.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 119 | 4090.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 119 | -4090.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 2 | 003 | 4624.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 119 | 4090.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1653 | 43317315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1672 | 43660015201 |  | 2 | CPI | 1 | 001 | 8386.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1672 | 43660015201 |  | 2 | CPI | 2 | 128 | 8225.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1672 | 43660015201 |  | 2 | CPI | 1 | 101 | 3657.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1678 | 43492915201 |  | 2 | CPI | 1 | 012 | 3465 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1687 | 41304245201 |  | 2 | CPI | 1 | 118 | 48419.33 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1687 | 41304245201 |  | 2 | CPI | 1 | 118 | 10765.13 | 10765.13 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1698 | 43656715201 |  | 2 | CPI | 1 | 012 | 726.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1698 | 43656715201 |  | 2 | CPI | 1 | 001 | 2939 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1710 | 43795915201 |  | 2 | CPI | 1 | 012 | 22798.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1710 | 43795915201 |  | 2 | CPI | 1 | 012 | 7599.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 012 | 708.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 3502.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 2 | 115 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 3 | 115 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 8284.52 | 4142.26 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 001 | 30321.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 001 | 9969.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 2 | 001 | -9969.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 2 | 115 | 8687.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 2 | 007 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1A07 | 42910915201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1A07 | 42910915201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1A07 | 42910915201 |  | 2 | CPI | 3 | 012 | 7921.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1A07 | 42911015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1A07 | 19389825603 |  | 2 | CPI | 1 | 007 | 2243.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 7789.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 42911015201 |  | 2 | CPI | 1 | 003 | 1337.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 7785.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 42911015201 |  | 2 | CPI | 1 | 106 | 8701.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1A07 | 42910915201 |  | 2 | CPI | 1 | 021 | 4578.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1A07 | 42910915201 |  | 2 | CPI | 1 | 021 | 7245.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 6904.07 | 6904.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 6904.07 | 6904.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 012 | 236.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | -6904.07 | -6904.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 6904.07 | 6904.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1A07 | 19389825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | 475.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 2 | 503 | 27769.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 |  | 2 | CPI | 3 | 107 | 34600.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 4 | 101 | 7656 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | 57000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 503 | 22498.8 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | -57000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | 34770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | 22230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1A16 | 43609215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 004 | -1587.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2R91 | 41650145201 |  | 2 | CPI | 2 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2R91 | 41650145201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2R91 | 41650145201 |  | 2 | CPI | 2 | 503 | 10461.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 503 | 73110.91 | 73110.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 004 | 3737.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2R91 | 41650145201 |  | 2 | CPI | 2 | 108 | 3559.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 004 | 3737.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2R91 | 41650145201 |  | 2 | CPI | 2 | 012 | 7480.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2R91 | 41650145201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 112 | 19540.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 2 | 120 | 24755.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 112 | 19540.25 | 6790.56 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 2 | 120 | 24755.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 3 | 112 | 8921.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 112 | -19540.25 | -6790.56 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 2 | 120 | -24755.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 112 | 1574.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 2 | 108 | 3551.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 012 | 14890.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 108 | 26179.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2T36 | 42442415201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2U34 | 43025815201 |  | 2 | CPI | 1 | 119 | 13021.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U34 | 43025815201 |  | 2 | CPI | 1 | 119 | 36978.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U40 | 43015815201 |  | 2 | CPI | 1 | 917 | 3693.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U40 | 43194515201 |  | 2 | CPI | 1 | 012 | 1795 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2U40 | 43194515201 |  | 2 | CPI | 1 | 007 | 1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2U40 | 43194515201 |  | 2 | CPI | 1 | 119 | 2871.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2U40 | 43015815201 |  | 2 | CPI | 1 | 700 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 101 | 1455 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 101 | 145.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 917 | 5773.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 115 | 4370.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 101 | 1754.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 107 | 2897.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2U49 | 43226715201 |  | 2 | CPI | 1 | 115 | 2385.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 106 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 003 | 528 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V29 | 43230815601 |  | 2 | CPI | 1 | 015 | 7639.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 115 | 6895.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 107 | 3465 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 117 | 2622.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V29 | 43230815201 |  | 2 | CPI | 1 | 117 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V64 | 43075815201 |  | 2 | CPI | 1 | 001 | 1573.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V64 | 43075815201 |  | 2 | CPI | 1 | 001 | 1573.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V64 | 43075815201 |  | 2 | CPI | 1 | 001 | -1573.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V64 | 43075815201 |  | 2 | CPI | 1 | 101 | 385.62 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V64 | 43075815201 |  | 2 | CPI | 1 | 012 | 7341.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V64 | 43075815201 |  | 2 | CPI | 2 | 106 | 13555.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V65 | 43432315201 |  | 2 | CPI | 1 | 001 | 4245 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V65 | 43432315201 |  | 2 | CPI | 1 | 001 | 6446.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V65 | 43432315201 |  | 2 | CPI | 1 | 101 | 910.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V65 | 43432315201 |  | 2 | CPI | 2 | 001 | 13999.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V65 | 43432315201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V65 | 43432315201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V65 | 43432315201 |  | 2 | CPI | 1 | 019 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2W07 | 43240515201 |  | 2 | CPI | 1 | 118 | 4409.13 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2W07 | 43240515201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 2 |  | N | 8 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2W74 | 43430315201 |  | 2 | CPI | 1 | 012 | 5101.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W74 | 43430315201 |  | 2 | CPI | 1 | 012 | 44898.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W86 | 43239515201 |  | 2 | CPI | 1 | 009 | 2629.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
02 | E2W86 | 43239515201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
02 | E2W97 | 43859915201 |  | 2 | CPI | 1 | 012 | 6364 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W97 | 43859915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860615201 |  | 2 | CPI | 1 | 012 | 5962 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860015201 |  | 2 | CPI | 1 | 012 | 1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860615201 |  | 2 | CPI | 1 | 012 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860015201 |  | 2 | CPI | 1 | 012 | -1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860015201 |  | 2 | CPI | 2 | 012 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860615201 |  | 2 | CPI | 1 | 012 | -1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W98 | 43860615201 |  | 2 | CPI | 2 | 012 | 1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 112 | 1000 | 1000 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 1937.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 001 | 1518 | 1518 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 112 | 3766 | 3766 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 2314.6 | 714.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 714.63 | 714.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 34100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 108 | 715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 25575.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 115 | 6037.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 001 | 5980.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 3 | 010 | 6610.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2534 | 21071235201 |  | 2 | CPI | 4 | 001 | 659.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 001 | 2852.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 001 | 2342 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 34179.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 001 | 1945.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 023 | 1723.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 112 | 3556.21 | 3556.21 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 573.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 001 | 12689.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 112 | 5660 | 5660 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235601 |  | 2 | CPI | 2 | 015 | 2080 | 2080 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 2 | 015 | 1487.75 | 1487.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 61.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 112 | 35494.74 | 35494.74 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 3390.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 107 | 341 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 775.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 1035.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 262.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 157.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 2 | 107 | -157.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 001 | 3457.54 | 3457.54 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 001 | 1761.16 | 1761.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 1 | 015 | 17253.45 | 17253.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2534 | 21071235601 |  | 2 | CPI | 2 | 015 | 10243.9 | 10243.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 0 | 1000 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2534 | 21071235201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 001 | 6790 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2568 | 21002845201 |  | 2 | CPI | 2 | 115 | 2470.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 917 | 7692.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 14568.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 112 | 5240.91 | 5240.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 105 | 2663.96 | 2663.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 112 | 1105.2 | 1105.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 9127.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 010 | 1824.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 1473.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 2 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 14471.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 20153.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 2 | 115 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2568 | 21002845201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 012 | 3795 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2569 | 42870115601 |  | 2 | CPI | 1 | 015 | 49863 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 2686.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 1375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 115 | 19528.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 2 | 107 | 1649.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 003 | 14826.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 2 | 106 | 28567.06 | 28567.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2569 | 42870115601 |  | 2 | CPI | 1 | 015 | 137 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 6773.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 105 | 895 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 105 | 895 | 895 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 105 | -895 | -895 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 007 | 2125.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 2522.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2569 | 42870115201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 25 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2596 | 43055615201 |  | 2 | CPI | 1 | 023 | 5046.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2596 | 43055615201 |  | 2 | CPI | 2 | 021 | 2860 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2596 | 43055615201 |  | 2 | CPI | 3 | 101 | 11140.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2596 | 43055615201 |  | 2 | CPI | 1 | 502 | 20475 | 20475 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
02 | T2596 | 43055615201 |  | 2 | CPI | 1 | 023 | 5046.75 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
02 | T2596 | 43055615201 |  | 2 | CPI | 2 | 101 | 11140.8 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 101 | 1850.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 101 | 2900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 108 | 1667.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 001 | 8995.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 3 | 105 | 1058.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 4 | 105 | 3984.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 003 | 4540.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 005 | 13907.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 003 | 3004.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 003 | 1429.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 003 | 3265.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 118 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 007 | 3650 | 3650 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 503 | 20872.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 503 | 21651.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 503 | 3130.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 105 | 21461.07 | 21461.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 2 | 024 | 11131.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2611 | 42880415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2623 | 42747425201 |  | 2 | CPI | 1 | 003 | 15391.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2623 | 42747425201 |  | 2 | CPI | 2 | 001 | 1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2623 | 42747425201 |  | 2 | CPI | 1 | 001 | 1300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2623 | 42747425201 |  | 2 | CPI | 2 | 010 | 852.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2623 | 42747425201 |  | 2 | CPI | 3 | 112 | 1119.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2623 | 42747425201 |  | 2 | CPI | 4 | 112 | 16790.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2623 | 42747425201 |  | 2 | CPI | 5 | 022 | 1968 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2623 | 42747425201 |  | 2 | CPI | 6 | 010 | 3910.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2624 | 21327285201 |  | 2 | CPI | 1 | 112 | 10316.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2624 | 21327285201 |  | 2 | CPI | 1 | 003 | 14189.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 115 | 428.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2625 | 43091415601 |  | 2 | CPI | 1 | 015 | 5522.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 107 | 2880.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 115 | 12459.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 2 | 112 | 4489.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2625 | 43091415601 |  | 2 | CPI | 1 | 015 | 3204.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 001 | 1229.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 001 | 2841.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 2 | 001 | 525.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2625 | 43091415601 |  | 2 | CPI | 1 | 015 | 689.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 001 | 2211.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 107 | 1888.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 2 | 920 | 5654.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 920 | 88.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 2 | 325 | 512.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2625 | 43091415201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2633 | 42890015201 |  | 2 | CPI | 1 | 001 | 15400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2633 | 42890015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2643 | 43434015201 |  | 2 | CPI | 1 | 919 | 46522.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2643 | 43434015201 |  | 2 | CPI | 1 | 919 | 130.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 101 | 22855.56 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 115 | 7878.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 012 | 14237.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 2 |  | N | 3 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2648 | 43231015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2655 | 43231215201 |  | 2 | CPI | 1 | 001 | 5448.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2655 | 43231215201 |  | 2 | CPI | 1 | 115 | 47197.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2655 | 43231215201 |  | 2 | CPI | 1 | 115 | 3767.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2655 | 43231215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2655 | 43231215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2659 | 43432715201 |  | 2 | CPI | 1 | 503 | 9098.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 2104.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015601 |  | 2 | CPI | 1 | 007 | 25000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 117 | 3577.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 19042.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 4340.52 | 4340.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 16545.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 2 | 001 | 4380.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2665 | 43056015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2666 | 43543915201 |  | 2 | CPI | 1 | 101 | 5112.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2666 | 43543915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 44 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2676 | 43617515201 |  | 2 | CPI | 1 | 012 | 5574.57 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | T2676 | 43617515201 |  | 2 | CPI | 1 | 108 | 821.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2676 | 43617515201 |  | 2 | CPI | 1 | 112 | 7691.77 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2676 | 43617515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 2 |  | N | 4 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2677 | 43616715201 |  | 2 | CPI | 1 | 115 | 34024.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2677 | 43616715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 2 | 001 | 2416 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3K83 | 41506725201 |  | 2 | CPI | 4 | 012 | 506 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3K83 | 41506725201 |  | 2 | CPI | 5 | 010 | 1575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3K83 | 41506725201 |  | 2 | CPI | 6 | 120 | 4242 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 503 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 503 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 2 | 001 | 26546 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3K83 | 41506725201 |  | 2 | CPI | 3 | 503 | 34760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 107 | 2646.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 120 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3K83 | 41506725201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 1 | 009 | 4158 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 2 | 003 | 4350.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 3 | 010 | 44702.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3L23 | 22066425201 |  | 2 | CPI | 4 | 010 | 8206.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3L23 | 22066425201 |  | 2 | CPI | 5 | 003 | 27578.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 6 | 350 | 10000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | E3L23 | 22066425201 |  | 2 | CPI | 7 | 503 | 1827.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3L23 | 22066425201 |  | 2 | CPI | 8 | 012 | 8123.1 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 1 | 007 | 9802.07 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | E3L23 | 22066425201 |  | 2 | CPI | 1 | 503 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3L23 | 22066425201 |  | 2 | CPI | 2 | 007 | 28501.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3P21 | 42358825201 |  | 2 | CPI | 1 | 001 | 15101.44 | 15101.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3P21 | 42358825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q60 | 43625715201 |  | 2 | CPI | 1 | 115 | 20600.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3Q73 | 43966115201 |  | 2 | CPI | 1 | 001 | 4987.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q80 | 44014815201 |  | 2 | CPI | 1 | 503 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q80 | 44014815201 |  | 2 | CPI | 2 | 503 | 2310 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q80 | 44014815201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q80 | 44014815201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 101 | 5005.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 101 | 226.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 101 | 226.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 004 | 2643.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3Q91 | 43626815201 |  | 2 | CPI | 2 | 001 | 5343.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 101 | 5866.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 2 | 101 | 4015 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 3 | 101 | 1485 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 101 | 4507.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q91 | 43626815201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 010 | 6050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 115 | 1034 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 115 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 107 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 107 | 4788.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 001 | 6816.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 113 | 311.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 1 | 115 | 4624.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3417 | 42282315201 |  | 2 | CPI | 2 | 503 | 18107.27 | 14248.53 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 118 | 1660.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 005 | 16549 | 16549 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 107 | 2764.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 105 | 388.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 115 | 10288 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 012 | 5412.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 019 | 8201.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
03 | T3474 | 41110245201 |  | 2 | CPI | 3 | 107 | 1713.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 4 | 115 | 4643.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 131 | 3064.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 105 | 1165.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 107 | 100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 106 | 6689.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 115 | 12251.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 012 | 21811.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 106 | -6689.5 | -689.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 106 | 6689.5 | 6689.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 118 | 1272.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 115 | 1990.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 101 | 9300 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 101 | 1328.05 | 1328.05 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 115 | -1990.51 | -1990.51 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 2 | 012 | 1891.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3474 | 41110245201 |  | 2 | CPI | 3 | 107 | 3815.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 115 | 1990.51 | 1990.51 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3474 | 41110245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3481 | 42884615201 |  | 2 | CPI | 1 | 503 | 8336 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 |  | 2 | CPI | 1 | 503 | 9732 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 |  | 2 | CPI | 2 | 503 | 6435 | 4685 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3498 | 42884715201 |  | 2 | CPI | 1 | 007 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 001 | 4868.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 2 | 128 | 440 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3498 | 43178525201 |  | 2 | CPI | 1 | 007 | 4950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3498 | 42884715201 |  | 2 | CPI | 1 | 001 | 1930 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3498 | 42884715201 |  | 2 | CPI | 2 | 003 | 9000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3498 | 43178525201 |  | 2 | CPI | 1 | 503 | 1271.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3498 | 43178515201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 009 | 30789 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 503 | 30487.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 010 | 7313.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 010 | 1738.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 |  | 2 | CPI | 2 | 012 | 797.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 023 | 7600.84 | 7600.84 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3596 | 43274015201 |  | 2 | CPI | 1 | 012 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3596 | 43274015201 |  | 2 | CPI | 2 | 503 | 3935.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3596 | 43274015201 |  | 2 | CPI | 3 | 115 | 1885 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3596 | 43274015201 |  | 2 | CPI | 1 | 012 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3596 | 43274015201 |  | 2 | CPI | 1 | 503 | 1947 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3596 | 43274015201 |  | 2 | CPI | 2 | 021 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3596 | 43274015201 |  | 2 | CPI | 1 | 101 | 3553.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3615 | 42695015201 |  | 2 | CPI | 1 | 503 | 1080.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3634 | 43256215201 |  | 2 | CPI | 1 | 921 | 1095.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3636 | 43188325201 |  | 2 | CPI | 1 | 503 | 1348.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3636 | 43188325201 |  | 2 | CPI | 1 | 126 | 5618 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 13595.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 2 | 001 | 2812.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 1560.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 780.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 503 | 8122 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 115 | 3156.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 101 | 2425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3638 | 43461115201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3644 | 43671915201 |  | 2 | CPI | 1 | 115 | 32692.09 | 17176.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3644 | 43671915201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 11 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3647 | 43626015201 |  | 2 | CPI | 1 | 107 | 1134 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3650 | 43014645201 |  | 2 | CPI | 1 | 001 | 3050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3650 | 43014645201 |  | 2 | CPI | 1 | 112 | 5145 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3650 | 43014645201 |  | 2 | CPI | 1 | 503 | 4275.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3650 | 43014655201 |  | 2 | CPI | 1 | 115 | 7400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3650 | 43014645201 |  | 2 | CPI | 1 | 115 | 7400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3650 | 43014655201 |  | 2 | CPI | 1 | 115 | -7400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 503 | 2323 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 115 | 3200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 105 | 5500 | 3330.3 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3651 | 43014665201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3677 | 43467515201 |  | 2 | CPI | 1 | 010 | 11963.81 | 5354.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3677 | 43467515201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 107 | 4946.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 107 | 20289.5 | 198 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4K92 | 41248925201 |  | 2 | CPI | 2 | 007 | 13233.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 107 | 198 | 198 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 012 | 32045.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 012 | 11938.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 012 | 1430 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 004 | 6000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 503 | 9322 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 007 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 001 | 2235.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 001 | 19099.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 007 | 7617.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4K92 | 41248925201 |  | 2 | CPI | 1 | 503 | 19443.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N44 | 42170765201 |  | 2 | CPI | 1 | 007 | 5500 | 5500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N44 | 42170765201 |  | 2 | CPI | 1 | 001 | 10403.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N44 | 42170765201 |  | 2 | CPI | 2 | 103 | 19129.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4N44 | 42170765201 |  | 2 | CPI | 1 | 007 | 12410.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N44 | 42170765201 |  | 2 | CPI | 1 | 106 | 30165.4 | 13506.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 |  | 2 | CPI | 2 | 106 | 41995.76 | 16888.9 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 |  | 2 | CPI | 1 | 106 | 13506.25 | 13506.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N44 | 42170765201 |  | 2 | CPI | 2 | 106 | 16888.9 | 16888.9 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 128 | 33175.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 106 | 1356.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 106 | 3727.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 2 | 018 | 1398.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 107 | 1056 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 2 | 012 | 17040.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 103 | 4323.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 115 | 13331.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 105 | 1877.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 2 | 004 | 14874.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 004 | 7950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 004 | 1966.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P08 | 42170755201 |  | 2 | CPI | 2 | 106 | 3228.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 118 | 22255.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 107 | 1539.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 118 | 7194 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4P08 | 42170755201 |  | 2 | CPI | 1 | 118 | 13705.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 007 | 4027.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 107 | 4009.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 107 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 2 | 012 | 1376 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 012 | 3490.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 2 | 118 | 11547.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 3 | 007 | 2643.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 007 | 2481.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 2 | 106 | 2701.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 128 | 1711.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | E4Q93 | 43120415201 |  | 2 | CPI | 2 | 013 | 1925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 007 | 50024.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 012 | -1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q93 | 43120415201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 004 | 35249.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 013 | 1925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 010 | 891.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 010 | 891.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 010 | -891.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 004 | 35249.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 004 | 2321.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 004 | -35249.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 106 | 3412.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 023 | 760.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 118 | 3016.93 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 101 | 12411.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 101 | 12833.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 012 | 1186.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 024 | 3937.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 2 | 003 | 9563.72 | 0 | 2 |  | E | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 105 | 9013.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4R63 | 43060215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 2 |  | N | 30 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R89 | 43234915201 |  | 2 | CPI | 1 | 107 | 998.75 | 939.75 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | E4R89 | 43234915201 |  | 2 | CPI | 1 | 113 | 3525 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4R89 | 43234915201 |  | 2 | CPI | 2 | 023 | 3831.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4R89 | 43234915201 |  | 2 | CPI | 1 | 115 | 800 | 543.75 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | E4R89 | 43234915201 |  | 2 | CPI | 2 | 023 | 9600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R89 | 43234915201 |  | 2 | CPI | 1 | 118 | 7560 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4S29 | 43059325201 |  | 2 | CPI | 1 | 106 | 2497.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S29 | 43059325201 |  | 2 | CPI | 1 | 112 | 784.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4S29 | 43059325201 |  | 2 | CPI | 2 | 105 | 1172.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4S29 | 43059325201 |  | 2 | CPI | 3 | 012 | 2993.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S30 | 43111015201 |  | 2 | CPI | 1 | 105 | 5446.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4S37 | 43716515201 |  | 2 | CPI | 1 | 106 | 1309.75 | 1309.75 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S37 | 43716515201 |  | 2 | CPI | 2 | 007 | 1154.31 | 1154.31 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4S37 | 43716515201 |  | 2 | CPI | 3 | 118 | 645.29 | 645.29 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4S37 | 43716515201 |  | 2 | CPI | 4 | 105 | 1491.88 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4S80 | 43609515201 |  | 2 | CPI | 1 | 105 | 17849.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4S80 | 43609515201 |  | 2 | CPI | 2 | 007 | 2368.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4395 | 42936515201 |  | 2 | CPI | 1 | 101 | 2588.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4395 | 42936515201 |  | 2 | CPI | 2 | 106 | 8852.96 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 018 | 381.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 107 | 1407.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 2 | 007 | 2873.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 003 | 2355 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4409 | 43019215201 |  | 2 | CPI | 2 | 119 | 1602.13 | 1602.13 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 003 | 1550.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 115 | 6660.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 115 | 3670.45 | 3670.45 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 115 | 874.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 122 | 2805 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4409 | 43019215201 |  | 2 | CPI | 1 | 105 | 3773 | 3773 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4422 | 43257425201 |  | 2 | CPI | 1 | 101 | 3100 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4422 | 43257425201 |  | 2 | CPI | 1 | 105 | 8411.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4422 | 43257425201 |  | 2 | CPI | 2 | 108 | 2870.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4422 | 43257425201 |  | 2 | CPI | 1 | 112 | 3473.17 | 3473.17 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4439 | 42872515201 |  | 2 | CPI | 1 | 105 | 9477.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4439 | 42872515201 |  | 2 | CPI | 2 | 108 | 1055 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4439 | 42872515201 |  | 2 | CPI | 3 | 503 | 4990.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4439 | 42872515201 |  | 2 | CPI | 4 | 503 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4439 | 42872515201 |  | 2 | CPI | 5 | 108 | 4274.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4439 | 42872515201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 108 | 3543.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 021 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4445 | 43060315201 |  | 2 | CPI | 2 | 023 | 255 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 003 | 15962.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 023 | 34175.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 101 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4445 | 43060315201 |  | 2 | CPI | 2 | 007 | 31287.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 3 |  | N | 2 | Avoidable, CEI Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4445 | 43060315201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4446 | 43294915201 |  | 2 | CPI | 1 | 003 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4446 | 43294915201 |  | 2 | CPI | 1 | 101 | 2274.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4446 | 43294915201 |  | 2 | CPI | 1 | 022 | 8885 | 8885 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4446 | 43294915201 |  | 2 | CPI | 2 | 118 | 2574 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4446 | 43294915201 |  | 2 | CPI | 3 | 023 | 1090.84 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4446 | 43294915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 5 |  | N | 26 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4447 | 43510115201 |  | 2 | CPI | 1 | 107 | 1995.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4447 | 43510115201 |  | 2 | CPI | 1 | 007 | 1981.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 007 | 825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 106 | 1780.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 105 | 23199.77 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 2 | 101 | 1400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 022 | 91.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 022 | 1005.16 | 1005.16 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 022 | 0.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 2 | 101 | 4534.92 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 3 | 105 | 1431.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 4 | 007 | 2111.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 021 | 3488.91 | 3488.91 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 |  | 2 | CPI | 2 | 105 | 1469.92 | 1469.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 5 |  | N | 21 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4453 | 43786615201 |  | 2 | CPI | 1 | 101 | 639.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4453 | 43786615201 |  | 2 | CPI | 2 | 101 | 4579.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4453 | 43786615201 |  | 2 | CPI | 3 | 503 | 1222.94 | 1222.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 021 | 7074.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 023 | 2211 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 118 | 9390.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 023 | 3610 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 503 | 3366.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 2 | 503 | 1246.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 021 | 4721 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 2 | 021 | 5365.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 503 | 3864.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 2 | 503 | 3015.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 021 | -4721 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 2 | 021 | 3049.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 1 | 023 | 3949.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 2 | 023 | 852.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 3 | 023 | 577.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4455 | 43442715201 |  | 2 | CPI | 4 | 024 | 7847.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4457 | 43436015201 |  | 2 | CPI | 1 | 115 | 4745.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4457 | 43436015201 |  | 2 | CPI | 1 | 001 | 24127.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4457 | 43436015201 |  | 2 | CPI | 1 | 105 | 3085.88 | 3085.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4460 | 43854615201 |  | 2 | CPI | 1 | 001 | 685.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4460 | 43854615201 |  | 2 | CPI | 1 | 101 | 3459.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4463 | 43167215201 |  | 2 | CPI | 1 | 101 | 1969.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4463 | 43167215201 |  | 2 | CPI | 1 | 503 | 7108.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 001 | 1854.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 001 | 2246.93 | 2246.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 001 | 9827.36 | 9827.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 2 | 009 | 770.55 | 770.55 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 115 | 797.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 2 | 105 | 184.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 105 | 730 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 106 | 446.41 | 446.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 101 | 589.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 108 | 303.46 | 303.46 | 4 |  | N | 0 | Avoidable, In-House CEI | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 118 | 1802.24 | 1802.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 007 | 4851 | 4851 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 001 | -2246.93 | -2246.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4466 | 42871815201 |  | 2 | CPI | 1 | 001 | 2246.93 | 2246.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4468 | 43612415201 |  | 2 | CPI | 1 | 101 | 1500 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5W79 | 42404045201 |  | 2 | CPI | 1 | 105 | 8110 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5W79 | 42404045201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 5 |  | N | 14 | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
05 | E5W91 | 40441825201 |  | 2 | CPI | 1 | 105 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5W91 | 40441825201 |  | 2 | CPI | 2 | 105 | 1600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y56 | 43744715201 |  | 2 | CPI | 1 | 503 | 2635.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y64 | 41832115201 |  | 2 | CPI | 1 | 023 | 23859.92 | 23859.92 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y64 | 41832115201 |  | 2 | CPI | 2 | 001 | 451.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y64 | 41832115201 |  | 2 | CPI | 1 | 007 | 3163.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Y64 | 41832115201 |  | 2 | CPI | 2 | 101 | 2769.86 | 2769.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y64 | 41832115201 |  | 2 | CPI | 1 | 104 | 0 | 0 | 0 |  | N | 26 | Unavoidable, No Remedial Action Required | Pay Item Conflicts | Plan Modifications | 2
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 503 | 15736.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 503 | 15736.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 503 | -15736.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 115 | 6626.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 001 | 1308.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y73 | 43065115201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Y75 | 43565515201 |  | 2 | CPI | 1 | 105 | 5010 | 205.09 | 3 |  | N | 0 | Avoidable, CEI Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y75 | 43565515201 |  | 2 | CPI | 2 | 105 | 7462.75 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y75 | 43565515201 |  | 2 | CPI | 1 | 003 | 2792.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y75 | 43565515201 |  | 2 | CPI | 2 | 106 | 2411.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y75 | 43565515201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y75 | 43565515201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y92 | 43243835201 |  | 2 | CPI | 1 | 118 | 2623.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y92 | 43243835201 |  | 2 | CPI | 1 | 503 | 320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y92 | 43243835201 |  | 2 | CPI | 2 | 122 | 3243.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Y92 | 43243835201 |  | 2 | CPI | 3 | 126 | 495 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | E5Y92 | 43243835201 |  | 2 | CPI | 4 | 503 | 140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y95 | 43632515201 |  | 2 | CPI | 1 | 503 | 1880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y95 | 43632515201 |  | 2 | CPI | 1 | 118 | 4561.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y95 | 43632515201 |  | 2 | CPI | 1 | 003 | 23552.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y95 | 43632515201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y96 | 43643415201 |  | 2 | CPI | 1 | 107 | 24698.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Y96 | 43643415201 |  | 2 | CPI | 1 | 107 | 24698.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Y96 | 43643415201 |  | 2 | CPI | 2 | 115 | 2114.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Y96 | 43643415201 |  | 2 | CPI | 1 | 107 | -24698.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Y96 | 43643415201 |  | 2 | CPI | 1 | 107 | 18187.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z05 | 43566615201 |  | 2 | CPI | 1 | 107 | 920.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z05 | 43566615201 |  | 2 | CPI | 1 | 101 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z05 | 43566615201 |  | 2 | CPI | 2 | 107 | 1177.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z05 | 43566615201 |  | 2 | CPI | 3 | 001 | 10835 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z05 | 43566615201 |  | 2 | CPI | 4 | 105 | 22236.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z05 | 43566615201 |  | 2 | CPI | 1 | 001 | 12331.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | E5Z05 | 43566615201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | E5Z15 | 44022215201 |  | 2 | CPI | 1 | 126 | 8749.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z36 | 43987715201 |  | 2 | CPI | 1 | 115 | 7765.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z36 | 43987715201 |  | 2 | CPI | 2 | 108 | 1445 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 001 | 17305.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 2 | 107 | 6846.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5313 | 43222615201 |  | 2 | CPI | 1 | 128 | 4586.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 107 | 5229.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 7984.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 4121.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 27003.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 118 | 30947.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 1803 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 2 | 120 | 10560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 012 | 31657.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 2 | 001 | 2777.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 3 | 010 | 8874.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 2225.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 003 | 3942.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 2 | 001 | 6905.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 3 | 001 | 29.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 003 | 2608.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 118 | 3090.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5313 | 23953535201 |  | 2 | CPI | 2 | 118 | 3526.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 11484.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 004 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 015 | 364.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 012 | 14127.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 004 | 9065.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5313 | 23953535601 |  | 2 | CPI | 1 | 120 | 3520 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5313 | 23953535201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 7 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 503 | 1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 112 | 24884.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 |  | 2 | CPI | 2 | 503 | -1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 112 | 2105.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 503 | 6152.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 503 | 1300.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225201 |  | 2 | CPI | 2 | 503 | 102255.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225601 |  | 2 | CPI | 1 | 106 | 14679.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225601 |  | 2 | CPI | 2 | 503 | 4006.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5431 | 23759225602 |  | 2 | CPI | 1 | 106 | 23019.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225201 |  | 2 | CPI | 1 | 128 | 13301.84 | 884.02 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5431 | 23759225601 |  | 2 | CPI | 1 | 106 | 3992.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225601 |  | 2 | CPI | 2 | 106 | 4656.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225601 |  | 2 | CPI | 1 | 106 | 4082 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5431 | 23759225601 |  | 2 | CPI | 1 | 106 | 18582.44 | 18582.44 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 003 | 29755.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 122 | 6361.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 2 | 503 | 18072 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5534 | 42875315201 |  | 2 | CPI | 3 | 003 | 4135.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5534 | 42875315201 |  | 2 | CPI | 4 | 003 | 10820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5534 | 42875315201 |  | 2 | CPI | 5 | 503 | 7381 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5534 | 42875315201 |  | 2 | CPI | 6 | 113 | 4224.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 113 | 2625.97 | 2625.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 122 | 1325 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 2 | 003 | 5200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5534 | 42875315201 |  | 2 | CPI | 3 | 115 | 4145 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 503 | 7381 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5534 | 42875315201 |  | 2 | CPI | 2 | 012 | 2701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5534 | 42875315201 |  | 2 | CPI | 3 | 115 | 4215.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5534 | 42875315201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5555 | 43543315201 |  | 2 | CPI | 1 | 012 | 19629.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 001 | 71217.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 007 | 5666.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 001 | 4549.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 2 | 012 | 3155.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 3 | 001 | 2063.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 4 | 105 | 935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5558 | 23842215201 |  | 2 | CPI | 5 | 118 | 1907.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 122 | 4334.34 | 4334.34 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 001 | 20975.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 115 | 4331.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 115 | 5260.42 | 5260.42 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5558 | 23842215201 |  | 2 | CPI | 1 | 503 | 10204.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5564 | 43505515201 |  | 2 | CPI | 1 | 917 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5575 | 43505715201 |  | 2 | CPI | 1 | 503 | 24257.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5575 | 43505715201 |  | 2 | CPI | 1 | 503 | 2559.62 | 2559.62 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5575 | 43505715201 |  | 2 | CPI | 1 | 112 | 11729.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5575 | 43505715201 |  | 2 | CPI | 1 | 112 | 1772.87 | 1772.87 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5578 | 43364815201 |  | 2 | CPI | 1 | 122 | 33111.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5578 | 43364815602 |  | 2 | CPI | 1 | 015 | 17215.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815602 |  | 2 | CPI | 1 | 015 | -17215.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815602 |  | 2 | CPI | 2 | 015 | 17217.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815201 |  | 2 | CPI | 1 | 112 | 16888.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5578 | 43364815601 |  | 2 | CPI | 1 | 015 | 7741.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815602 |  | 2 | CPI | 1 | 015 | 9364.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5578 | 43364815602 |  | 2 | CPI | 2 | 015 | 23418.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5580 | 43244315201 |  | 2 | CPI | 1 | 503 | 1098.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5580 | 43244315201 |  | 2 | CPI | 2 | 503 | 10257.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5580 | 43244315201 |  | 2 | CPI | 3 | 503 | 12364.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5584 | 43233315201 |  | 2 | CPI | 1 | 105 | 33244.48 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5584 | 43233315201 |  | 2 | CPI | 1 | 118 | 2571.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5584 | 43233315201 |  | 2 | CPI | 1 | 502 | 11064.41 | 11064.41 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
05 | T5584 | 43233315201 |  | 2 | CPI | 1 | 128 | 3119.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5584 | 43233315201 |  | 2 | CPI | 1 | 502 | 0 | 0 | 4 |  | N | 8 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
05 | T5585 | 43441715201 |  | 2 | CPI | 1 | 105 | 24999.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5598 | 43566115201 |  | 2 | CPI | 1 | 107 | 6736.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5598 | 43566115201 |  | 2 | CPI | 2 | 003 | 1476.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5620 | 43367315201 |  | 2 | CPI | 1 | 101 | 6988.95 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5620 | 43367315201 |  | 2 | CPI | 1 | 106 | 3669.53 | 3669.53 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5620 | 43367315201 |  | 2 | CPI | 1 | 007 | 1701.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5620 | 43367315201 |  | 2 | CPI | 1 | 007 | 4106.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5620 | 43367315201 |  | 2 | CPI | 2 | 007 | 1687.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5620 | 43367315201 |  | 2 | CPI | 3 | 007 | 3949.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J51 | 43652415201 |  | 2 | CPI | 1 | 503 | 20802.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J96 | 42918725201 |  | 2 | CPI | 1 | 106 | 2515.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6J96 | 42918725201 |  | 2 | CPI | 2 | 115 | 6256.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6J96 | 42918725201 |  | 2 | CPI | 1 | 003 | 4950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6K52 | 43029119202 |  | 2 | CPI | 1 | 023 | 42956.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6K52 | 43029119201 |  | 2 | CPI | 1 | 022 | 3166.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6K52 | 43029119202 |  | 2 | CPI | 1 | 503 | 3.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K55 | 42527135201 |  | 2 | CPI | 1 | 503 | 3318.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K55 | 42527135201 |  | 2 | CPI | 1 | 001 | 20984.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K55 | 42527135201 |  | 2 | CPI | 1 | 012 | 6776.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K55 | 42527135201 |  | 2 | CPI | 1 | 012 | 8620.51 | 8620.51 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K55 | 42527135601 |  | 2 | CPI | 1 | 503 | 6250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K55 | 42919415201 |  | 2 | CPI | 1 | 007 | 4887.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6K60 | 42736945201 |  | 2 | CPI | 1 | 106 | 3189.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K60 | 42736945201 |  | 2 | CPI | 1 | 009 | 10499.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
06 | E6K60 | 42736945201 |  | 2 | CPI | 1 | 106 | 1853.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K60 | 42736945201 |  | 2 | CPI | 2 | 007 | 8180.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6K60 | 42736945201 |  | 2 | CPI | 3 | 007 | 1676.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6K60 | 42736945201 |  | 2 | CPI | 4 | 009 | 732.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
06 | E6K66 | 43826315201 |  | 2 | CPI | 1 | 001 | 627.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K66 | 43826315201 |  | 2 | CPI | 2 | 001 | 959.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K66 | 43826315201 |  | 2 | CPI | 3 | 503 | 927.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K66 | 43826315201 |  | 2 | CPI | 4 | 503 | 3325.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K66 | 43826315201 |  | 2 | CPI | 5 | 503 | 4276.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K66 | 43826315201 |  | 2 | CPI | 6 | 503 | 1331 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K66 | 43826315201 |  | 2 | CPI | 7 | 128 | 3267 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
06 | E6L12 | 43560115203 |  | 2 | CPI | 1 | 015 | 882.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | E6L12 | 43560115203 |  | 2 | CPI | 1 | 015 | 24586.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | E6L12 | 43560115203 |  | 2 | CPI | 1 | 503 | 500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L19 | 42848725201 |  | 2 | CPI | 1 | 115 | 2975.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | E6L19 | 42848725202 |  | 2 | CPI | 1 | 001 | 2600.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | E6L32 | 44048515201 |  | 2 | CPI | 1 | 101 | 1818.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L32 | 44048515201 |  | 2 | CPI | 2 | 107 | 1936 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6L32 | 44048515201 |  | 2 | CPI | 3 | 001 | 1361.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6339 | 41463325201 |  | 2 | CPI | 1 | 503 | 17233.01 | 6650.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 |  | 2 | CPI | 1 | 012 | 9470.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6339 | 41463325201 |  | 2 | CPI | 1 | 503 | -17233.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325201 |  | 2 | CPI | 2 | 917 | 22014.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325601 |  | 2 | CPI | 1 | 503 | 17233.01 | 6550.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325601 |  | 2 | CPI | 2 | 015 | 18201.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6339 | 41463325201 |  | 2 | CPI | 1 | 503 | 27615 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6339 | 41463325601 |  | 2 | CPI | 1 | 015 | 77701.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6339 | 41463325601 |  | 2 | CPI | 2 | 015 | 2115 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6339 | 41463325201 |  | 2 | CPI | 1 | 003 | 10182.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 003 | 15449.61 | 15449.61 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 24089.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 8834.61 | 8834.61 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 9078.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 22405.59 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 19664.82 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 6005.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 934.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 917 | 7399.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 8770.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 1721.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 1498.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 003 | -15449.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 115 | -8834.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 3 | 115 | 2802.38 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 1311.11 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 003 | 15449.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 3 | 115 | 8834.61 | 8834.61 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | -9078.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 9078.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 003 | 3840.93 | 3840.93 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 2885.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 18159.07 | 18159.07 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 34421.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 18159.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 3 | 015 | 19250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 4 | 015 | 11395.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 001 | 6695.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 9960.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 18931.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 001 | 6695.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 001 | -6695.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 115 | 5069.43 | 5069.43 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 14159.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 001 | 46601.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 024 | 1475.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 3 | 115 | 5231.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 003 | 5960.5 | 5960.5 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 9555.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 503 | 3605.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 115 | -5231.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 5231.1 | 5231.1 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 107 | 11550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 503 | 1403.68 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 34421.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 13475 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 3 | 015 | 2227.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 1447.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 82611.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815201 |  | 2 | CPI | 1 | 115 | 1447.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815201 |  | 2 | CPI | 2 | 115 | -1447.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6347 | 42559815601 |  | 2 | CPI | 1 | 015 | 30979.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 2 | 015 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 3 | 015 | -30979.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 4 | 015 | 5.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6347 | 42559815601 |  | 2 | CPI | 5 | 015 | 5775 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 107 | 1336.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 917 | 2931.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 024 | 6121.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 017 | 4716.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 007 | 1617.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 003 | 1340.74 | 1072.1 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 2 | 115 | 11162.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6348 | 41247925201 |  | 2 | CPI | 1 | 115 | 11162.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 115 | -11162.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 112 | 34493.13 | 34493.13 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6348 | 41247935202 |  | 2 | CPI | 1 | 023 | 3013.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6348 | 41247935202 |  | 2 | CPI | 1 | 101 | 1898.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 103 | 63078.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6348 | 41247925201 |  | 2 | CPI | 1 | 001 | 1258.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 112 | 24050.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6348 | 41247935601 |  | 2 | CPI | 1 | 015 | 2955.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247925201 |  | 2 | CPI | 1 | 502 | 1922.34 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate Directions Given | CEI Actions/Inactions | 6
06 | T6348 | 41247925201 |  | 2 | CPI | 2 | 003 | 4950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6348 | 41247925601 |  | 2 | CPI | 1 | 015 | 5916.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247925601 |  | 2 | CPI | 2 | 023 | 4731.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 860 | 20427.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 003 | 268.64 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 003 | -1340.74 | -1072.1 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6348 | 41247935201 |  | 2 | CPI | 2 | 003 | 1072.1 | 1072.1 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6348 | 41247935202 |  | 2 | CPI | 1 | 101 | 5017.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6348 | 41247935202 |  | 2 | CPI | 2 | 108 | 5673.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6348 | 41247935202 |  | 2 | CPI | 1 | 023 | 2702.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6348 | 41247935601 |  | 2 | CPI | 1 | 015 | 6100 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247935601 |  | 2 | CPI | 2 | 015 | 15652.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247935601 |  | 2 | CPI | 3 | 015 | 6025.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247925201 |  | 2 | CPI | 1 | 503 | 7958.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6348 | 41247925201 |  | 2 | CPI | 1 | 106 | 3763.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6348 | 41247935201 |  | 2 | CPI | 1 | 860 | 7072.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
06 | T6348 | 41247935201 |  | 2 | CPI | 2 | 503 | 2583.27 | 2583.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6348 | 41247935202 |  | 2 | CPI | 1 | 112 | 7990.01 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6348 | 41247925601 |  | 2 | CPI | 1 | 106 | 8304.33 | 8304.33 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6348 | 41247935601 |  | 2 | CPI | 1 | 007 | 2735.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6348 | 41247935601 |  | 2 | CPI | 2 | 015 | 17007.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6348 | 41247935601 |  | 2 | CPI | 3 | 015 | 6703.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 123 | 43024.31 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 123 | 4780.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 3 | 118 | 2071.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 2 | 101 | 20955.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 123 | -0.18 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 101 | 6144.56 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 2 | 001 | 19921.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6388 | 24961475201 |  | 2 | CPI | 3 | 113 | 35471.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 022 | 9311.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6388 | 24961475201 |  | 2 | CPI | 1 | 024 | 8319.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6390 | 43094915201 |  | 2 | CPI | 1 | 503 | 2276.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 |  | 2 | CPI | 1 | 503 | 3555.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 |  | 2 | CPI | 2 | 001 | 2156.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6390 | 43094915201 |  | 2 | CPI | 3 | 503 | 4903.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6390 | 43094915201 |  | 2 | CPI | 4 | 001 | 7597.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6390 | 43094915201 |  | 2 | CPI | 6 | 115 | 11544.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6390 | 43094915201 |  | 2 | CPI | 5 | 106 | 7197.08 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6390 | 43094915201 |  | 2 | CPI | 1 | 503 | 7776.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6411 | 43477615202 |  | 2 | CPI | 1 | 001 | 3456.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6411 | 43477615201 |  | 2 | CPI | 1 | 105 | 5834.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6411 | 43477615201 |  | 2 | CPI | 2 | 001 | 3908.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6411 | 43477615201 |  | 2 | CPI | 3 | 101 | 6691.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6411 | 43477615201 |  | 2 | CPI | 1 | 106 | 7508.3 | 7508.3 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6411 | 43477615202 |  | 2 | CPI | 1 | 101 | 2263.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6412 | 43477815201 |  | 2 | CPI | 1 | 503 | 12704.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6412 | 43477815201 |  | 2 | CPI | 2 | 503 | 2133.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6412 | 43477815201 |  | 2 | CPI | 1 | 007 | 1100.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6415 | 43328625201 |  | 2 | CPI | 1 | 105 | 2024.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6415 | 43328625201 |  | 2 | CPI | 2 | 107 | 425.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6415 | 43328625201 |  | 2 | CPI | 3 | 001 | 1901.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6415 | 43328615201 |  | 2 | CPI | 1 | 101 | 605 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6415 | 43328625201 |  | 2 | CPI | 1 | 112 | 350.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6415 | 43328625201 |  | 2 | CPI | 1 | 003 | 3680.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6416 | 43305925201 |  | 2 | CPI | 1 | 001 | 6812.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6416 | 43305925201 |  | 2 | CPI | 2 | 115 | 4641.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6416 | 43305925201 |  | 2 | CPI | 3 | 503 | 550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6416 | 43305925201 |  | 2 | CPI | 1 | 101 | 797.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6416 | 43305925201 |  | 2 | CPI | 2 | 503 | 1425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6416 | 43305925201 |  | 2 | CPI | 3 | 503 | 1245.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6416 | 43305925201 |  | 2 | CPI | 4 | 503 | -1245.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6416 | 43305925201 |  | 2 | CPI | 5 | 503 | 1248.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6416 | 43305925201 |  | 2 | CPI | 1 | 503 | 824.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6417 | 43476815201 |  | 2 | CPI | 1 | 001 | 7829.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6417 | 43476815201 |  | 2 | CPI | 1 | 503 | 2589.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6417 | 43476815201 |  | 2 | CPI | 2 | 001 | 1341.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6417 | 43476815202 |  | 2 | CPI | 1 | 503 | 6458 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6417 | 43476815201 |  | 2 | CPI | 1 | 001 | 7829.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6417 | 43476815201 |  | 2 | CPI | 1 | 001 | -7829.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6418 | 43274825201 |  | 2 | CPI | 1 | 101 | 2877.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6418 | 43274835201 |  | 2 | CPI | 1 | 003 | 2644.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6418 | 43274825201 |  | 2 | CPI | 1 | 118 | 7208.84 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6418 | 43274825202 |  | 2 | CPI | 1 | 012 | 2757.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6418 | 43274835201 |  | 2 | CPI | 1 | 012 | 1380.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6426 | 43477115201 |  | 2 | CPI | 1 | 101 | 5016 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6431 | 43787315202 |  | 2 | CPI | 1 | 503 | 933.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6432 | 43638515201 |  | 2 | CPI | 1 | 001 | 4261.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6432 | 43638515201 |  | 2 | CPI | 2 | 101 | 6324 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6432 | 43638515201 |  | 2 | CPI | 3 | 001 | 12020.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6432 | 43638515201 |  | 2 | CPI | 4 | 101 | 2781.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6432 | 43638515201 |  | 2 | CPI | 1 | 021 | 675.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6432 | 43638515201 |  | 2 | CPI | 1 | 128 | 5273.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
06 | T6434 | 43792115201 |  | 2 | CPI | 1 | 007 | 2300.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6434 | 43792115201 |  | 2 | CPI | 2 | 101 | 3672.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6446 | 43631215201 |  | 2 | CPI | 1 | 001 | 1731.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6446 | 43631215201 |  | 2 | CPI | 1 | 001 | 1445.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6446 | 43631215201 |  | 2 | CPI | 1 | 001 | 5701.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6446 | 43631215201 |  | 2 | CPI | 2 | 503 | 503.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6446 | 43631215201 |  | 2 | CPI | 3 | 503 | 1509.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6446 | 43631215201 |  | 2 | CPI | 4 | 023 | 1732.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6446 | 43631215201 |  | 2 | CPI | 1 | 503 | 2308.08 | 2308.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L03 | 43656815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L03 | 43656815201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L03 | 43656815201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L03 | 43656815201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L03 | 43656815201 |  | 2 | CPI | 1 | 105 | 16606.14 | 16606.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L03 | 43656815201 |  | 2 | CPI | 1 | 024 | 5728.51 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L03 | 43656815201 |  | 2 | CPI | 1 | 101 | 1561 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 007 | 16391.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 001 | 8000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 101 | 211.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L59 | 43070815201 |  | 2 | CPI | 2 | 001 | 277.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 3 | 007 | 10080 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 001 | 1669.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L59 | 43070815201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 2 |  | N | 6 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L82 | 43269715201 |  | 2 | CPI | 1 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L82 | 43269715201 |  | 2 | CPI | 1 | 021 | 4527.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L82 | 43269715201 |  | 2 | CPI | 2 | 007 | 2664 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L82 | 43269715201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L96 | 43966215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M01 | 43070515201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M01 | 43070515201 |  | 2 | CPI | 1 | 503 | 20544.74 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M01 | 43070515201 |  | 2 | CPI | 2 | 130 | 2964.97 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 101 | 3517.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 107 | 7256.49 | 7256.49 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 001 | 2562.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 107 | 4730.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 107 | 2559.63 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 010 | 4726.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 101 | 550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 115 | 672.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 107 | 2574.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 107 | 2676.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 001 | 3976.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 115 | 3678.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 112 | 7069.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 117 | 1577.85 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 115 | 13286.55 | 13286.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 106 | 3413.32 | 3413.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 107 | 8301.48 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 108 | 21525.97 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 105 | 5357.47 | 5357.47 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 001 | 1282.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 005 | 1650 | 1650 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 115 | 4843.09 | 4843.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 001 | 2568.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 001 | 1047.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 001 | 5613.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 005 | 2740.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
07 | T7292 | 40915515201 |  | 2 | CPI | 2 | 115 | 10536.3 | 10536.3 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 004 | 2435.06 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 007 | 11444.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 007 | 5825.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 007 | -11444.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 007 | 11444.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 007 | -5825.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915515201 |  | 2 | CPI | 1 | 007 | 5825.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7292 | 40915415201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 5 |  | N | 30 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 101 | 589.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 101 | 1680.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 107 | 1290.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 107 | 4894.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 2 | 107 | 750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 5233.5 | 5233.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 105 | 3419.54 | 3419.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 107 | 4894.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 112 | 3657.4 | 3657.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 101 | 1825.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7304 | 40795125601 |  | 2 | CPI | 1 | 108 | 1853.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 101 | 1680.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 101 | -1825.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 015 | 2190.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7304 | 40795135601 |  | 2 | CPI | 2 | 108 | 2310 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 004 | 14350.88 | 14350.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 115 | 1498.85 | 1498.85 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7304 | 40795125601 |  | 2 | CPI | 1 | 108 | 185.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 108 | 231 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 112 | 2596.83 | 2596.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 4846.89 | 4846.89 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 105 | 3703.22 | 3703.22 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | -3703.22 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 105 | 3703.22 | 3703.22 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 3820.32 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 108 | 1258.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | -3820.32 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 3820.32 | 3820.32 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 105 | 4945.96 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 2 | 105 | 6109.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 108 | 9424 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 015 | 68383.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 108 | 2628.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795135601 |  | 2 | CPI | 1 | 015 | 7598.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 001 | 13977.58 | 1502.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 128 | 12475.28 | 1502.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 128 | -13977.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 3 | 128 | 1502.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 108 | 1.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 1 | 105 | 3432.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 2 | 105 | 7264.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795125201 |  | 2 | CPI | 3 | 105 | 16810.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 176.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 2 | 105 | 3406.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 42715115201 |  | 2 | CPI | 1 | 105 | 3943.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7304 | 40795135201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 001 | 730.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 112 | 6398.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 001 | 17366.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 007 | 1617.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 007 | 1193.5 | 1193.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 41886095201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 001 | 3661.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 106 | 539 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 41886095201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 107 | 5969.38 | 3245 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 101 | 2090.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7317 | 41886095201 |  | 2 | CPI | 1 | 115 | 1888.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 001 | 1040.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 503 | 1578.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 004 | 3728.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 004 | 7457.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7317 | 42715715201 |  | 2 | CPI | 2 | 503 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7317 | 41886095201 |  | 2 | CPI | 1 | 108 | 901.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7317 | 42715715201 |  | 2 | CPI | 1 | 725 | -1649.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7317 | 41886075201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 115 | 5703.96 | 5703.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 2 | 112 | 44922.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 3 | 106 | 1510.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 009 | 19635.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 115 | 6674.09 | 6674.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 115 | 5862.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 115 | 3216.33 | 3216.33 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 012 | 2179.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 001 | 22184.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 005 | 4500.66 | 4500.66 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 013 | 1155 | 1155 | 4 |  | N | 0 | Avoidable, In-House CEI | Test Projects | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 118 | 12984.29 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 004 | 2439.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 003 | 12928.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7353 | 25699535201 |  | 2 | CPI | 2 | 503 | -770.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 122 | 2524.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7353 | 25699535201 |  | 2 | CPI | 1 | 503 | 770.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7379 | 42906015201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 012 | 4016.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7379 | 42906015201 |  | 2 | CPI | 2 | 101 | 6046.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 003 | 15583.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7379 | 42906015202 |  | 2 | CPI | 1 | 503 | 12565.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 106 | 13795.38 | 634.5 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
07 | T7379 | 42906015202 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7379 | 42906015201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7379 | 42906015202 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 35 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7379 | 42906015202 |  | 2 | CPI | 1 | 130 | 0 | 0 | 4 |  | N | 13 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
07 | T7382 | 43258615202 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7382 | 43258615202 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7382 | 43258615202 |  | 2 | CPI | 3 | 122 | 3907.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7382 | 43258615202 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 013 | 1512 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 128 | 1408.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7382 | 43258615202 |  | 2 | CPI | 1 | 115 | 272.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 013 | -1512 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 2 | 001 | 6628.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 3 | 007 | 2475 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 128 | -1408.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7382 | 43261615201 |  | 2 | CPI | 1 | 013 | 1512 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | T7382 | 43261615201 |  | 2 | CPI | 1 | 128 | 1408.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7382 | 43261615201 |  | 2 | CPI | 2 | 115 | 3780.02 | 3780 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 106 | 1477.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 105 | 1896.88 | 1896.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 2 | 106 | 5850.88 | 5850.88 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 106 | 1477.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 001 | 6628.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 001 | 15654.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 2 | 007 | -2475 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7382 | 43261615201 |  | 2 | CPI | 1 | 128 | 0.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7382 | 43261615201 |  | 2 | CPI | 1 | 001 | 10049.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 001 | 2688.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7382 | 43258615201 |  | 2 | CPI | 1 | 115 | 1195.65 | 1195.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 |  | 2 | CPI | 2 | 012 | 52073.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 2 | 001 | 3351.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 123 | 9178.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 123 | 9178.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 123 | -9178.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 105 | 13972.82 | 13972.82 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 |  | 2 | CPI | 2 | 108 | 1229.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 112 | 6988.83 | 6988.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 112 | 19596.06 | 19596.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 14500.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 3212.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 25896.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 31 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7387 | 42895415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 1 | 007 | 8796 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715202 |  | 2 | CPI | 1 | 007 | 1008.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715202 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 1 | 007 | 0.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7390 | 43480715202 |  | 2 | CPI | 1 | 105 | 723.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7390 | 43480715201 |  | 2 | CPI | 1 | 007 | 3939.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 1 | 122 | 538.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7390 | 43480715201 |  | 2 | CPI | 2 | 007 | 3939.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715201 |  | 2 | CPI | 1 | 007 | -3939.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7390 | 43480715202 |  | 2 | CPI | 1 | 012 | 4334.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7394 | 43431715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7394 | 43431715201 |  | 2 | CPI | 1 | 009 | 7260 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7394 | 43431715201 |  | 2 | CPI | 1 | 105 | 3838 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7405 | 43649015201 |  | 2 | CPI | 1 | 012 | 19582.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7405 | 43649015201 |  | 2 | CPI | 1 | 001 | 30417.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 007 | 1303.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 012 | 10235.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 503 | 2030.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 019 | 12319.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8N52 | 42935045201 |  | 2 | CPI | 2 | 012 | 20740.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N52 | 42935045201 |  | 2 | CPI | 3 | 503 | 2186.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 010 | 12319.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8N52 | 42935045201 |  | 2 | CPI | 2 | 503 | 1311.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N52 | 42935045201 |  | 2 | CPI | 1 | 019 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 1 | 004 | 11040.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 2 | 003 | 34767.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 1 | 003 | 34767.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 1 | 021 | 9571.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 1 | 917 | 36416.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 1 | 917 | -36416.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 2 | 917 | 36419.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 3 | 007 | 1720.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8P06 | 43383015201 |  | 2 | CPI | 4 | 004 | 1296.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 101 | 12900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P90 | 43561515201 |  | 2 | CPI | 2 | 503 | 13673.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 |  | 2 | CPI | 3 | 001 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P90 | 43561545201 |  | 2 | CPI | 1 | 503 | 1849 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 012 | 1700.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P90 | 43561515201 |  | 2 | CPI | 2 | 108 | 576.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561545201 |  | 2 | CPI | 1 | 503 | 28561.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 108 | 2345.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 108 | 4036.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 115 | 1239.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561545201 |  | 2 | CPI | 1 | 115 | 4675 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P90 | 43561545201 |  | 2 | CPI | 2 | 003 | 2475 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P90 | 43561545201 |  | 2 | CPI | 1 | 503 | 2276.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P90 | 43561515201 |  | 2 | CPI | 1 | 115 | 7271.05 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q11 | 43715625201 |  | 2 | CPI | 1 | 003 | 12075.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q11 | 43715625201 |  | 2 | CPI | 2 | 001 | 6066.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q11 | 43715625201 |  | 2 | CPI | 1 | 003 | 10154.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q11 | 43715625201 |  | 2 | CPI | 2 | 001 | 9347.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q11 | 43715625201 |  | 2 | CPI | 1 | 001 | 3215.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q11 | 43715625201 |  | 2 | CPI | 1 | 001 | 4495.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 007 | 12132.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 012 | 22661.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q45 | 43516635201 |  | 2 | CPI | 1 | 021 | 1136.6 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q45 | 43516635201 |  | 2 | CPI | 1 | 021 | 854.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q45 | 43516635201 |  | 2 | CPI | 1 | 105 | 2365 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q45 | 43516835201 |  | 2 | CPI | 1 | 105 | 4730 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 115 | 20538.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 012 | -22661.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q45 | 43516815201 |  | 2 | CPI | 1 | 012 | 22661.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q45 | 43516835201 |  | 2 | CPI | 1 | 105 | 132.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q45 | 43516615201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q46 | 43717015204 |  | 2 | CPI | 1 | 012 | 6101.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q77 | 43905115201 |  | 2 | CPI | 1 | 860 | 5525.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
08 | E8Q77 | 43905115201 |  | 2 | CPI | 1 | 131 | 34856.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q77 | 43905115201 |  | 2 | CPI | 1 | 131 | 0 | 0 | 1 |  | N | 17 | Avoidable, Design Consultant | Architectural Feature Related Issue | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1K75 | 20121435201 | 005 |  | 440 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1P47 | 43771415201 | 007 |  | 33 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 001 |  | 15 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 001 |  | 3 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 001 |  | 1 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q76 | 43494115201 | 018 |  | 6 | 001 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2W93 | 43433815201 | 118 |  | 3 | 007 | 1 | 2 | N | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2W93 | 43433815201 | 404 |  | 18 | 007 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | T2547 | 42975025201 | 113 |  | 6 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2547 | 42975025201 | 007 |  | 5 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2623 | 42747425201 | 004 |  | 26 | 034 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2671 | 43601015201 | 106 |  | 7 | 006 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3L23 | 22066425201 | 009 |  | 199 | 042 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | E3P64 | 40747855201 | 503 |  | 13 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q80 | 44014815201 | 401 |  | 7 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | E3Q91 | 43626815201 | 016 |  | 7 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | T3417 | 42282315201 | 130 |  | 128 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | T3417 | 42282315201 | 503 |  | 295 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 | 503 |  | 8 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3481 | 42884615201 | 106 |  | 24 | 014 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3481 | 42884615201 | 118 |  | 5 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3481 | 42884615201 | 107 |  | 12 | 021 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
03 | T3481 | 42884615201 | 105 |  | 29 | 022 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3481 | 42884615201 | 108 |  | 6 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
03 | T3481 | 42884615201 | 105 |  | 125 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3481 | 42884615201 | 503 |  | 77 | 049 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3498 | 43178515201 | 115 |  | 9 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3498 | 43178515201 | 126 |  | 6 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3498 | 43178515201 | 503 |  | 15 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3538 | 43357615201 | 503 |  | 5 | 003 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3559 | 22247625201 | 016 |  | 37 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | T3559 | 22247625201 | 001 |  | 9 | 054 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 016 |  | 13 | 055 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | T3559 | 22247625201 | 128 |  | 17 | 065 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3559 | 22247625201 | 107 |  | 25 | 074 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 001 |  | 6 | 075 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3559 | 22247625201 | 107 |  | 16 | 076 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 107 |  | 6 | 077 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 115 |  | 12 | 078 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3559 | 22247625201 | 107 |  | 14 | 107 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3568 | 41347915201 | 502 |  | 35 | 015 | 1 | 2 | N | Avoidable, In-House Designer | Inaccurate Directions Given | CEI Actions/Inactions | 6
03 | T3568 | 41347915201 | 502 |  | 13 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
03 | T3615 | 42695015201 | 503 |  | 20 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3634 | 43256215201 | 105 |  | 5 | 006 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3636 | 43188325201 | 126 |  | 1 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3638 | 43461115201 | 023 |  | 3 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3641 | 43255115201 | 130 |  | 24 | 003 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
03 | T3644 | 43671915201 | 105 |  | 1 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3651 | 43014665201 | 005 |  | 14 | 013 | 1 | 1 | N | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
03 | T3651 | 43014665201 | 005 |  | 6 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
04 | E4K92 | 41248925201 | 503 |  | 60 | 121 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R63 | 43060215201 | 503 |  | 7 | 036 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R83 | 43482915201 | 005 |  | 13 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4R89 | 43234915201 | 130 |  | 19 | 016 | 1 | 4 | C | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
04 | E4S43 | 44009015201 | 130 |  | 22 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | T4395 | 42936515201 | 112 |  | 28 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4422 | 43257425201 | 105 |  | 6 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4446 | 43294915201 | 007 |  | 10 | 028 | 1 | 2 | N | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
04 | T4450 | 43288325201 | 005 |  | 28 | 026 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | E5Y51 | 43832115201 | 107 |  | 14 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y51 | 43832115201 | 107 |  | 14 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6J96 | 42918725201 | 919 |  | 38 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6K60 | 42736945201 | 007 |  | 20 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L12 | 43560115201 | 001 |  | 35 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6347 | 42559815201 | 015 |  | 94 | 058 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6416 | 43305925201 | 018 |  | 12 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6416 | 43305925201 | 126 |  | 21 | 022 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | T6428 | 42765125201 | 022 |  | 14 | 012 | 1 | 5 | N | Avoidable, Third Party | Computation Error | Plan Modifications | 2
07 | T7304 | 40795135201 | 003 |  | 20 | 068 | 1 | 1 | N | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7304 | 40795135201 | 105 |  | 14 | 068 | 2 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7317 | 41886075201 | 015 |  | 8 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7317 | 41886075201 | 001 |  | 15 | 069 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7390 | 43480715201 | 023 |  | 32 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N52 | 42935045201 | 503 |  | 21 | 053 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q11 | 43715625201 | 503 |  | 4 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q46 | 43717015202 | 503 |  | 16 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 649397 | 175 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO | 30 | 01co | 1 | 30
01CO | 01 | T1576 | 19690445201 | 2014-04-30 | QTR4 | 13/14 | 2 | 23 | 800 | 1243 | 1197 | 46 | 0 | 0 | 316 | 127 | 28940681 | 150000 | 28790681 | 30877320 | 31050834 | 0 | 0 | 0 | 31050834 | 28027477 | -2782025 | 1936639 | 255 | 0 | 65 | 378653 | 101153 | 0 | 58 | 791125 | 180721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29641 | 5438 | 0 | 2 | 376248 | 114516 | 0 | 0 | 0 | 0 | 0 | 0 | 27196 | 0 | 0 | 2 | 211399 | 94994 | 0 | 0 | 0 | 0 | 0 | 0 | -25911 | 0 | 0 | 127 | 1788352 | 496822 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 118 | 36280173.56 |  |  | 6 | 61 | 0 | 0 | 0 | 0 |  | CO | 17 | 01do | 31 | 47
01CO | 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | -247700 | -332612 | 33 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 21 | 02co | 48 | 68
01CO | 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | -6693381 | 1329652 | 198 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 68 | 0 | 0 | 0 | 0 |  | CO | 18 | 02do | 69 | 86
01CO | 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | -109936 | -74498 | 18 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 20 | 03co | 87 | 106
01CO | 01 | T1646 | 43275515202 | 2016-06-15 | QTR4 | 15/16 | 2 | 2 | 340 | 502 | 656 | -154 | 154 | 0 | 137 | 25 | 3883072 | 50000 | 3833072 | 3988230 | 4003713 | 0 | 0 | 0 | 4003713 | 3893478 | -55078 | 105158 | 100 | 0 | 0 | 0 | 0 | 0 | 6 | 34357 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 34559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 68915 | 1520 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 113 | 4572143.2 |  |  | 25 | 37 | 0 | 0 | 0 | 0 |  | CO | 11 | 03do | 107 | 117
01CO | 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 4666 | 70668 | 64 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO | 16 | 04co | 118 | 133
01CO | 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | -45614 | 67704 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 13 | 04do | 134 | 146
01CO | 01 | T1666 | 43289715201 | 2017-01-25 | QTR3 | 16/17 | 2 | 5 | 160 | 300 | 300 | 0 | 0 | 0 | 69 | 71 | 3057226 | 50000 | 3007226 | 3156754 | 3084177 | 0 | 0 | 0 | 3084177 | 3034815 | 9700 | 99528 | 49 | 0 | 0 | 13307 | 0 | 0 | 69 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 40465 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-03-15 | QTR3 | 17/18 | 118 | 3786427.28 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 18 | 05co | 147 | 164
01CO | 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 162288 | 192592 | 71 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28 |  |  | 0 | 21 | 0 | 0 | 0 | 0 | T | CO | 21 | 05do | 165 | 185
01CO | 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | -627624 | 220362 | 44 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO | 17 | 06co | 186 | 202
01CO | 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710515 | -83952 | 0 | -83952 | 626563 | 655747 | 29184 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-03-05 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 11 | 06do | 203 | 213
01CO | 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 42066 | 48270 | 30 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 13 | 07co | 214 | 226
01CO | 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 11 | 07do | 227 | 237
01CO | 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 238 | 237
01CO | 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 527 | 16831 | 2 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 8 | 08do | 238 | 245
01CO | 01 | T1687 | 41304245201 | 2017-07-26 | QTR1 | 17/18 | 1 | 6 | 429 | 484 | 340 | 144 | 0 | 0 | 55 | 0 | 28672708 | 150000 | 28522708 | 28693379 | 27612242 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | -344268 | 20671 | 44 | 0 | 0 | 46688 | 0 | 0 | 0 | 115877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348392 | 307784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79855 | 307784 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-02 | QTR2 | 18/19 | 106 | 35334896.73 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | -431102 | 0 |  | CO
01CO | 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 302 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 908 | -6283 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 152724 | 22 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1699 | 43698315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 73 | 84 | 84 | 0 | 0 | 0 | 11 | 0 | 338000 | 0 | 338000 | 345335 | 345335 | 0 | 0 | 0 | 345335 | 345335 | 0 | 7335 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-28 | QTR1 | 18/19 | 115 | 381548.27 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1710 | 43795915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 170 | 199 | 166 | 33 | 0 | 0 | 29 | 0 | 1395501 | 50000 | 1345501 | 1395501 | 1301640 | 0 | 100000 | 100000 | 1401640 | 1301762 | -99878 | 0 | 10 | 0 | 0 | 30398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30398 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 118 | 1196299.53 | B1 | ACC - NO EXCUSE BONUS | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1726 | 44016215201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 75 | 81 | 80 | 1 | 0 | 0 | 6 | 0 | 253590 | 0 | 253590 | 253590 | 253590 | 0 | 0 | 0 | 253590 | 253590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-12-15 | QTR2 | 18/19 | 113 | 256717.81 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1728 | 43501715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 75 | 76 | 25 | 51 | 0 | 0 | 1 | 0 | 141143 | 0 | 141143 | 141143 | 141143 | 0 | 0 | 0 | 141143 | 141143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 118 | 128587.62 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1730 | 43132415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 85 | 103 | 100 | 3 | 0 | 0 | 18 | 0 | 465432 | 0 | 465432 | 465432 | 465432 | 0 | 0 | 0 | 465432 | 465432 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 319733.9 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | -1987458 | 665347 | 175 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE | 11 | 36 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A16 | 43609215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 9 | 600 | 771 | 767 | 4 | 0 | 0 | 157 | 14 | 18880004 | 150000 | 18730004 | 19841188 | 19816523 | 0 | 0 | 0 | 19816523 | 19628809 | -187714 | 961184 | 106 | 0 | 4 | 154148 | 5054 | 0 | 10 | 279737 | 116375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348400 | 347865 | 0 | 0 | 170559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804 | 48804 | 0 | 0 | 0 | 0 | 0 | 14 | 1001647 | 518098 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2017-12-08 | QTR2 | 17/18 | 113 | 24424912.84 |  |  | 14 | 51 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1523947 | 48 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 0 | 0 | 16 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09 |  |  | 3 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 0 | 5910 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q21 | 41773349201 | 2017-03-22 | QTR3 | 16/17 | 1 | 1 | 500 | 539 | 539 | 0 | 0 | 0 | 39 | 0 | 5353535 | 55841 | 5297694 | 5368855 | 5313014 | 0 | 0 | 0 | 5313014 | 0 | -5313014 | 15320 | 6 | 0 | 0 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15320 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-03-08 | QTR3 | 18/19 |  | 2018-11-04 | QTR2 | 18/19 | 113 | 5530217.16 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q22 | 43854515201 | 2017-05-01 | QTR4 | 16/17 | 1 | 1 | 480 | 537 | 537 | 0 | 0 | 0 | 57 | 0 | 3614066 | 54963 | 3559103 | 3616288 | 3562935 | 0 | 0 | 0 | 3562935 | 3562935 | 0 | 2222 | 28 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 108 | 5496030.8 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 33269 | 18 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q64 | 43445715201 | 2018-04-19 | QTR4 | 17/18 | 2 | 0 | 140 | 179 | 170 | 9 | 0 | 0 | 39 | 0 | 429966 | 21462 | 408504 | 429966 | 399604 | 0 | 0 | 0 | 399604 | 399697 | 94 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 450406.6 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 14694 | 8 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R09 | 43903015201 | 2018-05-17 | QTR4 | 17/18 | 1 | 0 | 90 | 93 | 78 | 15 | 0 | 0 | 3 | 0 | 279115 | 12207 | 266908 | 279115 | 264760 | 0 | 0 | 0 | 264760 | 264760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-07 | QTR2 | 18/19 | 118 | 214242.2 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R47 | 43320215201 | 2018-08-16 | QTR1 | 18/19 | 1 | 0 | 95 | 118 | 118 | 0 | 0 | 0 | 23 | 0 | 542243 | 28109 | 514134 | 542243 | 514134 | 0 | 0 | 0 | 514134 | 514134 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-29 | QTR3 | 18/19 |  | 2019-02-28 | QTR3 | 18/19 | 108 | 573290.03 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R55 | 43902615201 | 2018-03-15 | QTR3 | 17/18 | 1 | 0 | 150 | 159 | 142 | 17 | 0 | 0 | 9 | 0 | 402836 | 19980 | 382856 | 402836 | 380287 | 0 | 0 | 0 | 380287 | 381602 | 1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 118 | 497103.38 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 840958 | 89 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73 |  |  | 33 | 80 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | -62293 | 0 | 12 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | -366052 | 96491 | 80 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97 |  |  | 20 | 54 | 0 | 0 | -37511 | 0 |  | CO
02CO | 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 716585 | 179 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26 |  |  | 44 | 57 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36 |  |  | 3 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2611 | 42880415201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 380 | 734 | 731 | 3 | 0 | 0 | 277 | 77 | 16425368 | 150000 | 16275368 | 17429243 | 17737903 | 0 | 0 | 0 | 17737903 | 17843990 | 106088 | 1003875 | 186 | 0 | 7 | 102446 | 43792 | 0 | 70 | 961987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 0 | 0 | 11131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13907 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1135125 | 43792 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 214 | 14976802.73 |  |  | 5 | 91 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2623 | 42747425201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 588 | 772 | 772 | 0 | 0 | 0 | 184 | 0 | 12006916 | 125768 | 11881149 | 12006916 | 12019761 | 0 | 0 | 0 | 12019761 | 12020496 | 735 | 0 | 85 | 26 | 0 | 18391 | 0 | 0 | 0 | 17909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 43031 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 214 | 12840720.13 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 36072 | 41 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2625 | 43091415201 | 2016-06-15 | QTR4 | 15/16 | 2 | 4 | 300 | 495 | 475 | 20 | 0 | 0 | 144 | 51 | 4913266 | 96132 | 4817134 | 5029801 | 5053902 | 0 | 0 | 0 | 5053902 | 5063705 | 9803 | 116535 | 75 | 0 | 11 | 42674 | 0 | 0 | 40 | 83572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 155418 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-01-04 | QTR3 | 17/18 | 208 | 4921245.07 |  |  | 13 | 69 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 0 | 13 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83 |  |  | 2 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 0 | 28 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 26193 | 7048 | 42 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5836409 | 107663 | 51929 | 37 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2 |  |  | 13 | 51 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1015867 | 121 | 6408 | 22 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32 |  |  | 44 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 4486 | 74 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 0 | 16 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74 |  |  | 4 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2677 | 43616715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 200 | 349 | 347 | 2 | 0 | 0 | 119 | 30 | 3488727 | 50000 | 3438727 | 3488727 | 3422691 | 0 | 0 | 0 | 3422691 | 3561473 | 138781 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 216 | 3968191.21 |  |  | 30 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2681 | 43499615201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 180 | 216 | 216 | 0 | 0 | 0 | 36 | 0 | 1999378 | 50000 | 1949378 | 1999378 | 1930362 | 0 | 0 | 0 | 1930362 | 1930362 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 209 | 2290722.63 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R81 | 43182025203 | 2014-03-20 | QTR3 | 13/14 | 3 | 0 | 365 | 365 | 0 | 365 | 0 | 0 | 0 | 0 | 2916419 | 0 | 2916419 | 2916419 | 0 | 0 | 0 | 0 | 0 | 5517906 | 5517906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 208 | 1374260.51 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R91 | 41650145201 | 2014-06-26 | QTR4 | 13/14 | 3 | 9 | 900 | 1294 | 1372 | -78 | 78 | 0 | 259 | 135 | 66725725 | 270345 | 66455380 | 67223879 | 66965314 | -795600 | 0 | -795600 | 66169714 | 64637295 | -1452887 | 498154 | 134 | 0 | 0 | 13369 | 0 | 0 | 14 | 196815 | 0 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 301636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 370894 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-05-30 | QTR4 | 17/18 | 208 | 83530874.22 | B8 | ACC - DESIGN/BUILD - MAJOR | 14 | 125 | 0 | 0 | -202522 | 0 |  | DO
02DO | 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | -412 | 1525306 | 47 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43 |  |  | 14 | 79 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | -22727 | 248912 | 44 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U40 | 43015815201 | 2016-01-20 | QTR3 | 15/16 | 3 | 2 | 436 | 624 | 622 | 2 | 0 | 0 | 142 | 46 | 4367770 | 50000 | 4317770 | 4673447 | 4944003 | 0 | 0 | 0 | 4944003 | 4845350 | -49202 | 305677 | 76 | 0 | 0 | 3676 | 0 | 0 | 0 | 259099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 262775 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2019-01-09 | QTR3 | 18/19 | 02/17/2018 | 2018-02-17 | QTR3 | 17/18 | 208 | 4165392.78 |  |  | 46 | 66 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U49 | 43074915201 | 2016-05-18 | QTR4 | 15/16 | 3 | 4 | 240 | 409 | 409 | 0 | 0 | 0 | 69 | 100 | 5878818 | 87141 | 5791677 | 6117316 | 6222842 | 0 | 0 | 0 | 6222842 | 6229444 | 6601 | 238499 | 41 | 0 | 100 | 163931 | 148393 | 0 | 0 | 28577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 251507 | 148393 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2017-09-25 | QTR1 | 17/18 | 208 | 7361145.29 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | -98576 | 61 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26 |  |  | 2 | 55 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 28412 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 4326 | 20 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 30133 | 59347 | 55 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25 |  |  | 12 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 494858 | 26 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W86 | 43239515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 120 | 166 | 166 | 0 | 0 | 0 | 45 | 1 | 567579 | 25415 | 542163 | 567579 | 542982 | 0 | 0 | 0 | 542982 | 542982 | 0 | 0 | 9 | 0 | 1 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2630 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-12-21 | QTR2 | 18/19 | 208 | 529604.74 |  |  | 1 | 36 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 78162 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W88 | 42849415201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 138 | 179 | 173 | 6 | 0 | 0 | 41 | 0 | 290000 | 23311 | 266689 | 290000 | 255859 | 0 | 0 | 0 | 255859 | 255859 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 208 | 444332.8 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W93 | 43433815201 | 2018-01-17 | QTR3 | 17/18 | 2 | 0 | 160 | 216 | 207 | 9 | 0 | 0 | 56 | 0 | 594594 | 28886 | 565708 | 594594 | 581178 | 0 | 0 | 0 | 581178 | 581178 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-03-15 | QTR3 | 18/19 |  | 2019-02-05 | QTR3 | 18/19 | 208 | 613772.37 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 0 | 12377 | 10 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 0 | 0 | 13 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3417 | 42282315201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 325 | 885 | 885 | 0 | 0 | 0 | 560 | 0 | 9576952 | 114593 | 9462359 | 11201952 | 11381048 | 0 | 0 | 0 | 11381048 | 11259809 | -121240 | 1625000 | 104 | 0 | 0 | 6816 | 0 | 128 | 0 | 16533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 1672506 | 1625000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2016-03-01 | QTR3 | 15/16 | 321 | 11869074.15 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3474 | 41110245201 | 2014-05-21 | QTR4 | 13/14 | 2 | 9 | 560 | 736 | 736 | 0 | 0 | 0 | 146 | 30 | 13521855 | 125538 | 13396317 | 14023931 | 14165918 | 0 | 0 | 0 | 14165918 | 13122088 | -1043829 | 502076 | 106 | 0 | 0 | 37317 | 0 | 0 | 30 | 516186 | 243604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21575 | 21575 | 0 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 618377 | 265179 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | QTR3 | 18/19 |  | 2016-08-26 | QTR1 | 16/17 | 308 | 12749353.07 |  |  | 9 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 446147 | 119 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15 |  |  | 2 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3498 | 43178515201 | 2017-01-25 | QTR3 | 16/17 | 4 | 1 | 190 | 384 | 387 | -3 | 3 | 0 | 172 | 22 | 4274307 | 55980 | 4218327 | 4324307 | 4294029 | -8433 | 0 | -8433 | 4285596 | 4353335 | 67739 | 50000 | 112 | 0 | 13 | 40548 | 0 | 15 | 5 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 46278 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 308 | 4281515.77 |  |  | 22 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 0 | -1624 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | -25384 | 2617138 | 303 | 65 | 20 | 532799 | 13449 | 90 | 4 | 490052 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2616143 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94 |  |  | 17 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 75332 | 76 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3567 | 43046515201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 165 | 250 | 260 | -10 | 10 | 0 | 70 | 15 | 1966055 | 0 | 1966055 | 1981055 | 2001427 | -15840 | 0 | -15840 | 1985587 | 1998145 | 12558 | 15000 | 64 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 308 | 1970432.78 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 20691 | 171 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3596 | 43274015201 | 2016-09-28 | QTR1 | 16/17 | 2 | 1 | 229 | 350 | 349 | 1 | 0 | 0 | 121 | 0 | 8173983 | 81645 | 8092338 | 8193029 | 8770491 | -4500 | 0 | -4500 | 8765991 | 8814288 | 48297 | 19046 | 102 | 0 | 0 | 6600 | 0 | 0 | 0 | 5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5882 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2017-12-17 | QTR2 | 17/18 | 314 | 8245135.42 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 15763 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3634 | 43256215201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 227 | 227 | 0 | 0 | 0 | 77 | 0 | 2317459 | 51202 | 2266257 | 2317459 | 2243858 | 0 | 0 | 0 | 2243858 | 2321931 | 78073 | 0 | 55 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 308 | 2451817.54 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 0 | 1601 | 48 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-03-19 | QTR3 | 17/18 | 308 | 819000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3638 | 43461115201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 210 | 364 | 366 | -2 | 2 | 0 | 133 | 21 | 5256385 | 58075 | 5198309 | 5256385 | 5540831 | -7290 | 0 | -7290 | 5533541 | 5791591 | 258050 | 0 | 90 | 0 | 4 | 18750 | 0 | 0 | 3 | 5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8122 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 32453 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 5826402.83 |  |  | 21 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 0 | 28099 | 33 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 13058 | -7125 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 0 | -21294 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 14433 | 38 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83 |  |  | 12 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3677 | 43467515201 | 2018-02-28 | QTR3 | 17/18 | 2 | 1 | 120 | 159 | 148 | 11 | 0 | 0 | 36 | 3 | 2607729 | 51275 | 2556454 | 2610160 | 2714487 | -7200 | 0 | -7200 | 2707287 | 2805120 | 97833 | 2431 | 26 | 0 | 0 | 0 | 0 | 0 | 2 | 2431 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14394 | 25 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-09-20 | QTR1 | 18/19 | 308 | 3422497.92 |  |  | 1 | 10 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K83 | 41506725201 | 2012-11-20 | QTR2 | 12/13 | 2 | 8 | 599 | 1108 | 1108 | 0 | 0 | 0 | 385 | 124 | 13915054 | 150000 | 13765054 | 14699375 | 14628947 | 0 | 0 | 0 | 14628947 | 14470162 | -158785 | 784321 | 311 | 0 | 5 | 84488 | 0 | 0 | 12 | 93331 | 1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 107 | 683618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 867013 | 1459 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2016-01-26 | QTR3 | 15/16 | 308 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR | 8 | 74 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 3971426 | 99 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 61 | 0 | 0 | -216679 | 0 |  | DO
03DO | 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 130 | 0 | 10 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000 |  |  | 6 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P35 | 40674235201 | 2017-11-09 | QTR2 | 17/18 | 1 | 0 | 235 | 281 | 281 | 0 | 0 | 0 | 46 | 0 | 2284367 | 50000 | 2234367 | 2284367 | 2177088 | 0 | 0 | 0 | 2177088 | 2177088 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 321 | 4068630.6 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P64 | 40747855201 | 2017-10-12 | QTR2 | 17/18 | 1 | 0 | 110 | 153 | 153 | 0 | 0 | 0 | 43 | 0 | 477560 | 28231 | 449329 | 477560 | 464944 | 0 | 0 | 0 | 464944 | 464944 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 308 | 607325 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 0 | 26519 | 71 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 127524 | 43 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 945 | 3000 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64 |  |  | 8 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q91 | 43626815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 3 | 180 | 246 | 244 | 2 | 0 | 0 | 64 | 2 | 3258297 | 50000 | 3208297 | 3274221 | 3353918 | 0 | 0 | 0 | 3353918 | 3489125 | 135206 | 15924 | 49 | 7 | 2 | 16487 | 0 | 0 | 0 | 31396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 45243 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 321 | 4488229.01 |  |  | 1 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 0 | 4802 | 135 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | -14505 | 252534 | 101 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | -7370 | 325031 | 104 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 4036 | 70900 | 32 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4445 | 43060315201 | 2017-01-25 | QTR3 | 16/17 | 1 | 4 | 365 | 510 | 480 | 30 | 0 | 0 | 134 | 11 | 8418937 | 102163 | 8316774 | 8403485 | 8476613 | 0 | 0 | 0 | 8476613 | 8700175 | 251131 | -15452 | 110 | 0 | 19 | 47250 | 0 | 0 | 0 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 51443 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-28 | QTR3 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 412 | 9837147.69 |  |  | 19 | 24 | 0 | -8 | -72293 | 0 |  | CO
04CO | 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | -10793 | 15092 | 66 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97 |  |  | 26 | 22 | 0 | 0 | -1882 | 0 |  | CO
04CO | 04 | T4447 | 43510115201 | 2017-03-29 | QTR3 | 16/17 | 7 | 2 | 364 | 422 | 422 | 0 | 0 | 0 | 108 | -50 | 3554036 | 50000 | 3504036 | 3574289 | 3278614 | 0 | 0 | 0 | 3278614 | 3266227 | 4310 | 20253 | 88 | 0 | 0 | 1981 | 0 | 0 | -50 | 5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 7532 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 409 | 3729070.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 0 | 32 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66 |  |  | 24 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 985 | 4306 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4455 | 43442715201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 277 | 316 | 306 | 10 | 0 | 0 | 39 | 0 | 14081000 | 150000 | 13931000 | 14107664 | 13452505 | 0 | 0 | 0 | 13452505 | 14356886 | 904380 | 26664 | 31 | 0 | 0 | 26664 | 0 | 0 | 0 | 9390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11492 | 0 | 0 | 0 | 34538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82084 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-09 | QTR2 | 18/19 | 409 | 15571973.96 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 981 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 31168 | 30 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 10 | 0 | 7 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4466 | 42871815201 | 2017-07-26 | QTR1 | 17/18 | 5 | 1 | 388 | 441 | 411 | 30 | 0 | 0 | 53 | 0 | 3213996 | 50000 | 3163996 | 3213990 | 3033800 | 0 | 0 | 0 | 3033800 | 3135748 | 101948 | -6 | 23 | 0 | 0 | 19551 | 0 | 0 | 0 | 4848 | 8066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24399 | 8066 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-12-20 | QTR2 | 18/19 | 409 | 3457230.6 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4K92 | 41248925201 | 2010-11-30 | QTR2 | 10/11 | 7 | 17 | 1303 | 2546 | 2546 | 0 | 0 | 0 | 228 | 1015 | 94215000 | 150000 | 94065000 | 108647581 | 108420972 | 0 | 0 | 0 | 108420972 | 108204126 | -90707 | 14432581 | 86 | 0 | 288 | 1644087 | 1314542 | 0 | 220 | 2406319 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 60 | 507 | 10129365 | 2700545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1015 | 14293821 | 6446112 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 | 05/08/2018 | 2018-10-04 | QTR2 | 18/19 | 409 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | -2197408 | 3131122 | 99 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 57 | 0 | 0 | -82927 | 0 |  | DO
04DO | 04 | E4P08 | 42170755201 | 2014-03-25 | QTR3 | 13/14 | 7 | 23 | 1305 | 1810 | 1471 | 339 | 0 | 0 | 270 | 235 | 80437734 | 150000 | 80287734 | 82797035 | 82818636 | -283033 | -200000 | -483033 | 82335603 | 78160637 | -3880669 | 2359301 | 204 | 0 | 5 | -559751 | 0 | 0 | 27 | 763643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1957639 | 16706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 12319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 2097146 | 16706 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-06 | QTR3 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 412 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 66 | 0 | 0 | -76704 | 0 |  | DO
04DO | 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | -85027 | 475368 | 293 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75 |  |  | 10 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 93460 | 150444 | 82 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R83 | 43482915201 | 2017-05-03 | QTR4 | 16/17 | 1 | 0 | 445 | 586 | 585 | 1 | 0 | 0 | 141 | 0 | 2949000 | 50000 | 2899000 | 2949000 | 2893000 | 0 | 0 | 0 | 2893000 | 2893000 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2019-01-28 | QTR3 | 18/19 | 412 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 26852 | 127760 | 93 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S29 | 43059325201 | 2017-04-07 | QTR4 | 16/17 | 4 | 2 | 290 | 414 | 414 | 0 | 0 | 0 | 124 | 0 | 3060921 | 47591 | 3013330 | 3171379 | 2918996 | 0 | 0 | 0 | 2918996 | 2935462 | 54722 | 110457 | 74 | 0 | 0 | 2993 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79649 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 408 | 2506695.34 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 666 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 0 | 13 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S43 | 44009015201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 290 | 412 | 411 | 1 | 0 | 0 | 122 | 0 | 2285285 | 50000 | 2235285 | 2435637 | 2385637 | 0 | 0 | 0 | 2385637 | 2385637 | 0 | 150352 | 64 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 150352 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 408 | 2071421.19 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 74001 | 9 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | -1059964 | 5141650 | 119 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 7 | 57 | 0 | 30 | -230251 | 0 |  | CO
05CO | 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 4323245 | 93 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55 |  |  | 0 | 58 | 0 | 0 | -110308 | 0 |  | CO
05CO | 05 | T5534 | 42875315201 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 600 | 763 | 765 | -2 | 2 | 0 | 178 | -15 | 10372492 | 109000 | 10263492 | 10929528 | 10898780 | -15534 | 0 | -15534 | 10883246 | 10869524 | 280079 | 557037 | 129 | 0 | 0 | 52612 | 0 | 0 | -26 | 22897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 246070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 321579 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 590 | 11601598.01 | B0 | ACC - LUMP SUM | 8 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5555 | 43543315201 | 2016-03-30 | QTR3 | 15/16 | 3 | 2 | 560 | 822 | 815 | 7 | 0 | 0 | 262 | 0 | 4783671 | 60000 | 4723671 | 4871035 | 5269309 | 0 | 0 | 0 | 5269309 | 5177510 | -4436 | 87364 | 212 | 0 | 0 | 19630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19630 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 514 | 6123685 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | -956254 | 370838 | 56 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | -40 | -130768 | 0 |  | CO
05CO | 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 0 | 56481 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05 |  |  | 14 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5575 | 43505715202 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 290 | 323 | 290 | 33 | 0 | 0 | 33 | 0 | 3075596 | 50000 | 3025596 | 3075596 | 2961552 | 0 | 0 | 0 | 2961552 | 2961571 | 19 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 13502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40320 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 512 | 4026582.45 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 6944 | 115263 | 65 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5580 | 43259215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 380 | 517 | 515 | 2 | 0 | 0 | 109 | 28 | 5833370 | 62000 | 5771370 | 5934096 | 5935419 | 0 | 0 | 0 | 5935419 | 6045029 | 126318 | 100726 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-09-13 | QTR1 | 18/19 | 514 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 13997 | 180307 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 |  | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12 |  |  | 8 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 40280 | 52747 | 216 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5587 | 43505415201 | 2017-03-29 | QTR3 | 16/17 | 3 | 3 | 380 | 465 | 463 | 2 | 0 | 0 | 85 | 0 | 3220056 | 50000 | 3170056 | 3323115 | 3265140 | 0 | 0 | 0 | 3265140 | 3262109 | 0 | 103059 | 63 | 0 | 0 | 12084 | 0 | 0 | 0 | 87944 | 689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100028 | 689 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 514 | 4249077.7 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5598 | 43566115201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 160 | 188 | 188 | 0 | 0 | 0 | 28 | 0 | 1387781 | 50000 | 1337781 | 1400208 | 1356596 | 0 | 0 | 0 | 1356596 | 1374428 | 17832 | 12427 | 24 | 0 | 0 | 1476 | 0 | 0 | 0 | 19164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20640 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 507 | 1627448 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5600 | 43691515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 250 | 324 | 324 | 0 | 0 | 0 | 74 | 0 | 3294214 | 50000 | 3244214 | 3431595 | 3445345 | 0 | 0 | 0 | 3445345 | 3578158 | 132813 | 137381 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-10-23 | QTR2 | 18/19 | 513 | 4280329.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-07-23 | QTR1 | 18/19 | 514 | 295435 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1131728 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 504 | 5429 | 8 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 515 | 980597 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5627 | 43730215201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 45 | 67 | 62 | 5 | 0 | 0 | 22 | 0 | 140000 | 15000 | 125000 | 140000 | 125000 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2019-03-22 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 514 | 315759 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | -89138 | 204028 | 174 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2019-01-16 | QTR3 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 14 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | -4400 | 21013 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y51 | 43832115201 | 2017-06-06 | QTR4 | 16/17 | 1 | 2 | 90 | 194 | 193 | 1 | 0 | 0 | 87 | 17 | 334599 | 16000 | 318599 | 541800 | 538448 | 0 | 0 | 0 | 538448 | 538448 | 0 | 207200 | 34 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-04-19 | QTR4 | 17/18 | 514 | 346552.2 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y52 | 43632315201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 270 | 476 | 469 | 7 | 0 | 0 | 206 | 0 | 745547 | 38000 | 707547 | 745547 | 707547 | 0 | 0 | 0 | 707547 | 707547 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | QTR3 | 18/19 |  | 2018-12-14 | QTR2 | 18/19 | 513 | 805051.1 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 1238 | 76790 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 26994 | 156917 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 5094 | 12031 | 26 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7 |  |  | 26 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 64762 | 233345 | 64 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928 |  |  | 3 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 0 | 0 | 60 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85 |  |  | 8 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 76090 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 81060 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y95 | 43632515201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 380 | 491 | 481 | 10 | 0 | 0 | 81 | 30 | 2610610 | 50000 | 2560610 | 2610610 | 2553200 | 0 | 0 | 0 | 2553200 | 2553205 | 5 | 0 | 25 | 0 | 30 | 23553 | 0 | 0 | 0 | 4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 29994 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-12-26 | QTR2 | 18/19 | 513 | 3377422 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 55693 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z04 | 43927115201 | 2018-02-06 | QTR3 | 17/18 | 1 | 0 | 90 | 102 | 87 | 15 | 0 | 0 | 12 | 0 | 133664 | 5664 | 128000 | 133664 | 128000 | 0 | 0 | 0 | 128000 | 128000 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 515 | 123951 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z05 | 43566615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 1 | 240 | 283 | 262 | 21 | 0 | 0 | 42 | 1 | 1687883 | 50000 | 1637883 | 1737883 | 1730756 | 0 | 0 | 0 | 1730756 | 1735963 | 5207 | 50000 | 23 | 0 | 0 | 50180 | 0 | 0 | 1 | 30589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 80769 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-12-18 | QTR2 | 18/19 | 512 | 1825766 |  |  | 1 | 19 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z29 | 43926915201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 997135 | 44635 | 952500 | 997135 | 952500 | 0 | 0 | 0 | 952500 | 952500 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-01-29 | QTR3 | 18/19 | 513 | 942335 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z36 | 43987715201 | 2018-01-03 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 128 | 11 | 0 | 0 | 19 | 0 | 661369 | 44000 | 617369 | 661369 | 614161 | 0 | 50000 | 50000 | 664161 | 615476 | -48686 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-07-31 | QTR1 | 18/19 | 513 | 934116.2 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | -258037 | 417799 | 96 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 |  | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | -1419938 | 811402 | 61 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6348 | 41247935201 | 2016-02-24 | QTR3 | 15/16 | 8 | 4 | 740 | 812 | 641 | 171 | 0 | 0 | 72 | 0 | 18181314 | 296819 | 17884495 | 17828896 | 17896535 | 0 | 800000 | 800000 | 18696535 | 17985610 | -663461 | -352418 | 36 | 0 | 0 | 72263 | 0 | 0 | 0 | 245801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464 | 0 | 0 | 0 | 16570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -107072 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-22 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 606 | 18130045.8 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 36 | 0 | 0 | -502098 | 0 |  | CO
06CO | 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 893046 | 79 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 |  | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6390 | 43094915201 | 2017-02-22 | QTR3 | 16/17 | 5 | 6 | 380 | 464 | 460 | 4 | 0 | 0 | 84 | 0 | 4429507 | 54813 | 4374694 | 4700034 | 4434960 | 0 | 170000 | 170000 | 4604960 | 4569268 | -15734 | 270527 | 53 | 0 | 0 | 41640 | 0 | 0 | 0 | 31665 | 12923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171557 | 16087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244862 | 29011 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 606 | 5093915.35 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 0 | 31 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6412 | 43477815201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 120 | 205 | 205 | 0 | 0 | 0 | 85 | 0 | 292409 | 16584 | 275825 | 292409 | 300085 | 0 | 0 | 0 | 300085 | 304110 | 4025 | 0 | 70 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 335871.2 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | -136676 | 28195 | 44 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | -29328 | 147817 | 57 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6417 | 43476815201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 1228383 | 50000 | 1178383 | 1228383 | 1133929 | 0 | 0 | 0 | 1133929 | 1138502 | 4573 | 0 | 36 | 0 | 0 | 9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18218 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-11-19 | QTR2 | 18/19 | 606 | 1258750.05 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 5234 | 51632 | 63 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 63649 | 15 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6428 | 42765125201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 180 | 255 | 255 | 0 | 0 | 0 | 75 | 0 | 1069876 | 50735 | 1019141 | 1119876 | 1059386 | 0 | 0 | 0 | 1059386 | 1008320 | -51066 | 50000 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-09-27 | QTR1 | 18/19 | 606 | 1388000.3 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6431 | 43787315201 | 2018-01-31 | QTR3 | 17/18 | 3 | 0 | 150 | 185 | 185 | 0 | 0 | 0 | 35 | 0 | 929676 | 42743 | 886933 | 929676 | 827030 | 0 | 0 | 0 | 827030 | 827669 | 639 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-22 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 606 | 881390.05 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6432 | 43638515201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 178 | 176 | 2 | 0 | 0 | 28 | 0 | 627876 | 36563 | 591313 | 627876 | 619690 | 0 | 0 | 0 | 619690 | 620784 | 1093 | 0 | 20 | 0 | 0 | 16282 | 0 | 0 | 0 | 14379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31336 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-01 | QTR3 | 18/19 |  | 2018-10-19 | QTR2 | 18/19 | 606 | 756555.75 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 69 | 0 | 48 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 |  | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 0 | 57 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | -593229 | 49068 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 30910 | 125102 | 67 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 89950 | 52 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | -148006 | 51328 | 26 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K60 | 42736945201 | 2017-02-23 | QTR3 | 16/17 | 1 | 0 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 1911584 | 50000 | 1861584 | 1911584 | 1907123 | 0 | 0 | 0 | 1907123 | 1909046 | 1923 | 0 | 120 | 20 | 0 | 21089 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 26132 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-12-12 | QTR2 | 18/19 | 606 | 1951851.15 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 0 | 13 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L12 | 43560115201 | 2017-01-26 | QTR3 | 16/17 | 3 | 6 | 280 | 429 | 429 | 0 | 0 | 0 | 149 | 0 | 3399874 | 50000 | 3349874 | 3718568 | 3635077 | 0 | 0 | 0 | 3635077 | 3617267 | 263 | 318693 | 92 | 35 | 0 | 25468 | 0 | 0 | 0 | 95370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 308050 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-02-20 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 606 | 3205032.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L18 | 43779215201 | 2017-10-26 | QTR2 | 17/18 | 1 | 0 | 150 | 215 | 215 | 0 | 0 | 0 | 65 | 0 | 676189 | 34902 | 641287 | 676189 | 658548 | 0 | 0 | 0 | 658548 | 659195 | 646 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-25 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 606 | 719637.75 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 9983 | 0 | 44 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 0 | 0 | 4 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | -544763 | 2295083 | 191 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14 |  |  | 30 | 91 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | -758630 | -138845 | 145 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST | 16 | 61 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | -887228 | 212174 | 208 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 |  | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03 |  |  | 2 | 57 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | -819849 | 1664895 | 92 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 66 | 0 | 0 | -113880 | 0 |  | CO
07CO | 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 18982 | 298860 | 167 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22 |  |  | 48 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 25484 | 558900 | 42 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7387 | 42895415201 | 2016-06-15 | QTR4 | 15/16 | 3 | 8 | 435 | 735 | 733 | 2 | 0 | 0 | 223 | 77 | 17840000 | 150000 | 17690000 | 18339077 | 18567408 | 0 | 0 | 0 | 18567408 | 18654250 | 128181 | 499077 | 175 | 0 | 45 | 212755 | 0 | 0 | 28 | 205993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 461583 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 714 | 19115045.32 |  |  | 49 | 48 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 30781 | 47 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7392 | 43484115202 | 2017-05-24 | QTR4 | 16/17 | 3 | 1 | 210 | 384 | 331 | 53 | 0 | 0 | 153 | 21 | 5679793 | 50000 | 5629793 | 5828296 | 5798728 | 0 | 0 | 0 | 5798728 | 5859621 | 60893 | 148503 | 55 | 0 | 21 | 148503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 148503 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-10-11 | QTR2 | 18/19 | 796 | 4416000 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 0 | 31 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7405 | 43649015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 140 | 161 | 146 | 15 | 0 | 0 | 21 | 0 | 2235958 | 50000 | 2185958 | 2384716 | 2283562 | 0 | 0 | 0 | 2283562 | 2395779 | 112217 | 148758 | 18 | 0 | 0 | 58523 | 0 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 798 | 3540000 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 799 | 446330 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | -54636 | 367480 | 145 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | -18692 | 37019 | 42 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | -19 | 20 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000 |  |  | 9 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 0 | 78500 | 39 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L82 | 43269715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 4 | 280 | 389 | 388 | 1 | 0 | 0 | 103 | 6 | 4654737 | 50000 | 4604737 | 4707294 | 4587650 | 0 | 0 | 0 | 4587650 | 4635460 | 47810 | 52556 | 86 | 0 | 6 | 2664 | 0 | 0 | 0 | 2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12827 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-24 | QTR1 | 18/19 | 798 | 5246589.53 |  |  | 6 | 17 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 |  | 2018-09-12 | QTR1 | 18/19 | 796 | 320000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 796 | 310000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L96 | 43966215201 | 2018-03-14 | QTR3 | 17/18 | 1 | 0 | 300 | 329 | 152 | 177 | 0 | 0 | 29 | 0 | 1051194 | 50000 | 1001194 | 1051194 | 908881 | 0 | 0 | 0 | 908881 | 908881 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-02-13 | QTR3 | 18/19 | 796 | 1997000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M01 | 43070515201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 88 | 136 | 125 | 11 | 0 | 0 | 48 | 0 | 633485 | 32000 | 601485 | 633485 | 652234 | 0 | 0 | 0 | 652234 | 652234 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 796 | 643100 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 796 | 225000 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GANNETT FLEMING PROJECT DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | -1273624 | 1280759 | 147 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 47 | 0 | 0 | -35903 | 0 |  | DO
08DO | 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 0 | 56 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | -6108 | 1045631 | 89 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 64151 | -44570 | 40 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 |  | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64 |  |  | 0 | 28 | 0 | 0 | -104904 | 0 |  | DO
08DO | 08 | E8Q45 | 43516615201 | 2017-03-28 | QTR3 | 16/17 | 4 | 7 | 245 | 377 | 376 | 1 | 0 | 0 | 113 | 19 | 10174450 | 99451 | 10074999 | 10442695 | 10222974 | 0 | 0 | 0 | 10222974 | 10331810 | 132458 | 268245 | 69 | 0 | 0 | 34793 | 0 | 0 | 12 | 180668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 0 | 0 | 7 | 64962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 282868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 854 | 10340089.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 19 | 44 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 223 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 0 | 78 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 0 | 9613 | 32 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 51808 | 6 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91 |  |  | 17 | 12 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0