## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 348744577 | 346466754 | 359473679 | 356894062 | 6126000 | 346272624 | -0.05603% | 94.74% | 9830322 | 2.837% | 10729101 | 3.076% | 11222 | 1952 | 17.39% | 812 | 7.236% | 267 | 2.379% | 582 | 5.186% | 12071 | 7.565% | 15028 | 14775 | 12011 | 7.031% | 81.58%
| District Let | 56333038 | 55613506 | 57923997 | 57087750 | 75000 | 51627511 | -7.167% | 100% | 1695592 | 3.049% | 1590958 | 2.824% | 4431 | 325 | 7.335% | 290 | 6.545% | 525 | 11.85% | 166 | 3.746% | 5122 | 15.59% | 5737 | 5516 | 4901 | 10.61% | 90%
| All Contracts | 405077615 | 402080260 | 417397676 | 413981812 | 6201000 | 397900135 | -1.04% | 96.55% | 11525914 | 2.867% | 12320059 | 3.041% | 15653 | 2277 | 14.55% | 1102 | 7.04% | 792 | 5.06% | 748 | 4.779% | 17193 | 9.838% | 20765 | 20291 | 16912 | 8.043% | 84.48%
2 | Central Let | 204705560 | 202477935 | 210599382 | 210263394 | 0 | 208371725 | 2.911% | 100% | 6865405 | 3.391% | 5893821 | 2.879% | 8792 | 1756 | 19.97% | 982 | 11.17% | 69 | 0.7848% | 715 | 8.132% | 9576 | 8.917% | 12340 | 12243 | 9505 | 8.11% | 89.29%
| District Let | 121055540 | 119880383 | 124434139 | 124114706 | 0 | 121904996 | 1.689% | 80% | 3323808 | 2.773% | 3378603 | 2.791% | 5339 | 726 | 13.6% | 773 | 14.48% | 21 | 0.3933% | 769 | 14.4% | 6129 | 14.8% | 7630 | 7606 | 6107 | 14.38% | 80%
| All Contracts | 325761100 | 322358318 | 335033521 | 334378100 | 0 | 330276721 | 2.456% | 91.67% | 10189213 | 3.161% | 9272424 | 2.846% | 14131 | 2482 | 17.56% | 1755 | 12.42% | 90 | 0.6369% | 1484 | 10.5% | 15705 | 11.14% | 19970 | 19849 | 15612 | 10.48% | 85.42%
3 | Central Let | 90143823 | 89123712 | 95718718 | 98319809 | 0 | 97797494 | 9.732% | 81.82% | 5781489 | 6.487% | 5574895 | 6.184% | 4724 | 1791 | 37.91% | 563 | 11.92% | 1098 | 23.24% | 331 | 7.007% | 6153 | 30.25% | 8507 | 8392 | 6038 | 27.82% | 59.09%
| District Let | 147808980 | 147062906 | 152751079 | 152268689 | 0 | 151355999 | 2.919% | 100% | 5141080 | 3.496% | 4942099 | 3.344% | 3302 | 759 | 22.99% | 292 | 8.843% | 226 | 6.844% | 163 | 4.936% | 3691 | 11.78% | 4742 | 4697 | 3646 | 10.42% | 92.86%
| All Contracts | 237952803 | 236186618 | 248469797 | 250588498 | 0 | 249153493 | 5.49% | 88.89% | 10922569 | 4.625% | 10516994 | 4.42% | 8026 | 2550 | 31.77% | 855 | 10.65% | 1324 | 16.5% | 494 | 6.155% | 9844 | 22.65% | 13249 | 13089 | 9684 | 20.66% | 72.22%
4 | Central Let | 68833986 | 67708075 | 69682121 | 67559113 | 37125 | 68890181 | 1.746% | 100% | 1102389 | 1.628% | 848135 | 1.232% | 5415 | 1072 | 19.8% | 440 | 8.126% | 173 | 3.195% | 163 | 3.01% | 5751 | 6.205% | 7263 | 7115 | 5603 | 3.472% | 100%
| District Let | 337682436 | 336520111 | 359986864 | 358178690 | 300000 | 347649189 | 3.307% | 93.33% | 21766138 | 6.468% | 22304427 | 6.605% | 8094 | 1549 | 19.14% | 583 | 7.203% | 252 | 3.113% | 1493 | 18.45% | 9839 | 21.56% | 12066 | 11691 | 9559 | 18.1% | 86.67%
| All Contracts | 406516422 | 404228186 | 429668985 | 425737803 | 337125 | 416539370 | 3.046% | 97.14% | 22868527 | 5.657% | 23152562 | 5.695% | 13509 | 2621 | 19.4% | 1023 | 7.573% | 425 | 3.146% | 1656 | 12.26% | 15590 | 15.4% | 19329 | 18806 | 15162 | 12.24% | 94.29%
5 | Central Let | 215587204 | 214043704 | 228714320 | 229682263 | 1761200 | 227799353 | 6.427% | 76.19% | 11892671 | 5.556% | 13053759 | 6.055% | 8645 | 1521 | 17.59% | 685 | 7.924% | 0 | 0% | 628 | 7.264% | 9273 | 7.264% | 11598 | 11108 | 8902 | 2.973% | 80.95%
| District Let | 178304864 | 177039565 | 222559633 | 221707766 | 1050000 | 221182706 | 24.93% | 80.77% | 44292642 | 25.02% | 44254767 | 24.82% | 7125 | 1044 | 14.65% | 680 | 9.544% | 28 | 0.393% | 837 | 11.75% | 7990 | 12.14% | 9714 | 9179 | 7455 | 4.632% | 88.46%
| All Contracts | 393892068 | 391083269 | 451273953 | 451390029 | 2811200 | 448982059 | 14.8% | 78.72% | 56185313 | 14.37% | 57308526 | 14.55% | 15770 | 2565 | 16.27% | 1365 | 8.656% | 28 | 0.1776% | 1465 | 9.29% | 17263 | 9.467% | 21312 | 20287 | 16357 | 3.722% | 85.11%
6 | Central Let | 164291890 | 162055550 | 166918000 | 168407525 | 3830000 | 166962381.08 | 3.028% | 100% | 3214861 | 1.984% | 2626108 | 1.598% | 6867 | 1061 | 15.45% | 402 | 5.854% | 291 | 4.238% | 0 | 0% | 7158 | 4.238% | 8621 | 7939 | 6476 | -5.694% | 100%
| District Let | 36957307 | 36188218 | 37603595 | 36284240 | 180000 | 29687139 | -17.96% | 100% | 761750 | 2.105% | 646286 | 1.749% | 3935 | 902 | 22.92% | 345 | 8.767% | 83 | 2.109% | 14 | 0.3558% | 4032 | 2.465% | 5317 | 5202 | 3955 | 0.5083% | 100%
| All Contracts | 201249197 | 198243768 | 204521595 | 204691765 | 4010000 | 196649520.08 | -0.8042% | 100% | 3976611 | 2.006% | 3272394 | 1.626% | 10802 | 1963 | 18.17% | 747 | 6.915% | 374 | 3.462% | 14 | 0.1296% | 11190 | 3.592% | 13938 | 13141 | 10431 | -3.435% | 100%
7 | Central Let | 153484016 | 151950702 | 159202204 | 159617252 | -400000 | 156117644 | 2.742% | 92.86% | 6056286 | 3.986% | 5718186 | 3.726% | 5405 | 1180 | 21.83% | 533 | 9.861% | 89 | 1.647% | 555 | 10.27% | 6049 | 11.91% | 7762 | 7892 | 6179 | 14.32% | 78.57%
| District Let | 90695120 | 90063420 | 93926110 | 92868993 | 0 | 88149106 | -2.126% | 93.33% | 3007924 | 3.34% | 3230989 | 3.562% | 3514 | 992 | 28.23% | 317 | 9.021% | 0 | 0% | 165 | 4.696% | 3679 | 4.696% | 4988 | 4682 | 3373 | -4.013% | 100%
| All Contracts | 244179136 | 242014122 | 253128314 | 252486245 | -400000 | 244266750 | 0.9308% | 93.1% | 9064210 | 3.745% | 8949175 | 3.665% | 8919 | 2172 | 24.35% | 850 | 9.53% | 89 | 0.9979% | 720 | 8.073% | 9728 | 9.071% | 12750 | 12574 | 9552 | 7.097% | 89.66%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 114699646 | 113906737 | 117284289 | 116086347 | 0 | 113940844 | 0.02994% | 100% | 2463255 | 2.163% | 2584642 | 2.253% | 3415 | 582 | 17.04% | 301 | 8.814% | 55 | 1.611% | 171 | 5.007% | 3641 | 6.618% | 4524 | 4522 | 3639 | 6.559% | 80%
| All Contracts | 114699646 | 113906737 | 117284289 | 116086347 | 0 | 113940844 | 0.02994% | 100% | 2463255 | 2.163% | 2584642 | 2.253% | 3415 | 582 | 17.04% | 301 | 8.814% | 55 | 1.611% | 171 | 5.007% | 3641 | 6.618% | 4524 | 4522 | 3639 | 6.559% | 80%
Totals This Qtr | Central Let | 1245791056 | 1233826432 | 1290308424 | 1290743418 | 11354325 | 1272211402.08 | 3.111% | 92.68% | 44743423 | 3.626% | 44444005 | 3.568% | 51070 | 10333 | 20.23% | 4417 | 8.649% | 1987 | 3.891% | 2974 | 5.823% | 56031 | 9.714% | 71119 | 69464 | 54714 | 7.135% | 84.15%
| District Let | 1083536931 | 1076274846 | 1166469706 | 1158597181 | 1605000 | 1125497490 | 4.573% | 91.97% | 82452189 | 7.661% | 82932771 | 7.654% | 39155 | 6879 | 17.57% | 3581 | 9.146% | 1190 | 3.039% | 3778 | 9.649% | 44123 | 12.69% | 54718 | 53095 | 42635 | 8.888% | 89.78%
| All Contracts | 2329327987 | 2310101278 | 2456778130 | 2449340599 | 12959325 | 2397708892.08 | 3.792% | 92.36% | 127195612 | 5.506% | 127376776 | 5.468% | 90225 | 17212 | 19.08% | 7998 | 8.865% | 3177 | 3.521% | 6752 | 7.484% | 100154 | 11% | 125837 | 122559 | 97349 | 7.896% | 86.71%
Totals Previous Quarter | Central Let | 949564610 | 939543450 | 985189199 | 981995979 | 10399325 | 964514336 | 2.658% | 91.85% | 36333254 | 3.867% | 35624579 | 3.752% | 40625 | 8606 | 21.18% | 3502 | 8.62% | 1367 | 3.365% | 2473 | 6.087% | 44465 | 9.452% | 56786 | 55551 | 43443 | 6.937% | 83.7%
| District Let | 786735042 | 780966468 | 822543127 | 813431807 | 605000 | 793924339 | 1.659% | 91.82% | 35226580 | 4.511% | 35808084 | 4.551% | 31616 | 5452 | 17.24% | 2813 | 8.897% | 990 | 3.131% | 2863 | 9.056% | 35469 | 12.19% | 43772 | 42006 | 33741 | 6.721% | 90.91%
| All Contracts | 1736299652 | 1720509918 | 1807732326 | 1795427786 | 11004325 | 1758438675 | 2.205% | 91.84% | 71559834 | 4.159% | 71432663 | 4.114% | 72241 | 14058 | 19.46% | 6315 | 8.742% | 2357 | 3.263% | 5336 | 7.386% | 79934 | 10.65% | 100558 | 97557 | 77184 | 6.842% | 86.94%
Totals Fiscal Year 2017/2018 | Central Let | 922272924 | 912201289 | 950316202 | 949875400 | 5416900 | 923867600 | 1.279% | 94.83% | 30812018 | 3.378% | 27856787 | 3.02% | 42758 | 8500 | 19.88% | 3456 | 8.083% | 1275 | 2.982% | 2225 | 5.204% | 46258 | 8.186% | 58215 | 59077 | 47121 | 10.2% | 87.93%
| District Let | 681923471 | 675586171 | 745680560 | 741535853 | 2689500 | 724953919.61 | 7.307% | 92.62% | 65007580 | 9.622% | 63710371 | 9.343% | 27803 | 4959 | 17.84% | 2334 | 8.395% | 695 | 2.5% | 2601 | 9.355% | 31099 | 11.85% | 38519 | 37890 | 30597 | 10.05% | 85.25%
| All Contracts | 1604196395 | 1587787460 | 1695996762 | 1691411253 | 8106400 | 1648821519.61 | 3.844% | 93.92% | 95819598 | 6.035% | 91567158 | 5.708% | 70561 | 13459 | 19.07% | 5790 | 8.206% | 1970 | 2.792% | 4826 | 6.839% | 77357 | 9.631% | 96734 | 96967 | 77718 | 10.14% | 86.82%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | 107% | 1 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | 95.53% | 1 | -2998654 | 649397 | 175 | 65 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43
| 01 | T1576 | 19690445201 | 2014-04-30 | QTR4 | 13/14 | 2 | 23 | 800 | 1243 | 1197 | 110.1% | 1 | 46 | 0 | 0 | 316 | 127 | 28940681 | 150000 | 28790681 | 30877320 | 31050834 | 0 | 0 | 0 | 31050834 | 28027477 | 97.35% | 1 | -2782025 | 1936639 | 255 | 61 | 0 | 65 | 378653 | 101153 | 0 | 58 | 791125 | 180721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29641 | 5438 | 0 | 2 | 376248 | 114516 | 0 | 0 | 0 | 0 | 0 | 0 | 27196 | 0 | 0 | 2 | 211399 | 94994 | 0 | 0 | 0 | 0 | 0 | 0 | -25911 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1788352 | 496822 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 118 | 36280173.56
| 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 104.9% | 1 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | 96.97% | 1 | -247700 | -332612 | 33 | 25 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 101.1% | 1 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | 98.52% | 1 | -6693381 | 1329652 | 198 | 68 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 95.5% | 1 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | 97.88% | 1 | -109936 | -74498 | 18 | 5 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM
| 01 | T1627 | 43130615201 | 2015-09-30 | QTR1 | 15/16 | 3 | 22 | 535 | 678 | 677 | 99.81% | 1 | 1 | 0 | 0 | 143 | 0 | 17136343 | 129497 | 17006846 | 19412207 | 20247437 | 0 | 0 | 0 | 20247437 | 20062426 | 118% | 0 | -83418 | 2275864 | 121 | 22 | 0 | 0 | 630929 | 0 | 0 | 0 | 1232145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105785 | 0 | 0 | 0 | 225345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201935 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-18 | QTR4 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 115 | 14213441.36 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1642 | 43131115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 8 | 250 | 592 | 592 | 184% | 0 | 0 | 0 | 0 | 282 | 60 | 6228254 | 58701 | 6169553 | 7299149 | 7284341 | -20000 | 0 | -20000 | 7264341 | 7348123 | 119.1% | 0 | 93161 | 1070895 | 54 | 78 | 150 | 0 | 604769 | 0 | 0 | 60 | 349795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 60 | 956072 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-06-27 | QTR4 | 18/19 |  | 2018-07-12 | QTR1 | 18/19 | 115 | 5212533.98 | B0 | ACC - LUMP SUM
| 01 | T1644 | 20074615201 | 2016-06-15 | QTR4 | 15/16 | 1 | 8 | 450 | 917 | 907 | 176.7% | 0 | 10 | 0 | 0 | 413 | 54 | 10076029 | 85873 | 9990156 | 10805932 | 10804382 | 0 | 0 | 0 | 10804382 | 10809726 | 108.2% | 1 | 34988 | 729903 | 69 | 43 | 0 | 0 | -8714 | 0 | 117 | 54 | 864500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 54 | 855786 | 0 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-28 | QTR4 | 18/19 |  | 2019-04-05 | QTR4 | 18/19 | 113 | 8346217.75
| 01 | T1646 | 43275515202 | 2016-06-15 | QTR4 | 15/16 | 2 | 2 | 340 | 502 | 656 | 152.6% | 0 | -154 | 154 | 0 | 137 | 25 | 3883072 | 50000 | 3833072 | 3988230 | 4003713 | 0 | 0 | 0 | 4003713 | 3893478 | 101.6% | 1 | -55078 | 105158 | 100 | 37 | 0 | 0 | 0 | 0 | 0 | 6 | 34357 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 34559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 68915 | 1520 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 113 | 4572143.2
| 01 | T1650 | 41454715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 13 | 575 | 757 | 756 | 100% | 1 | 1 | 0 | 0 | 181 | 1 | 23457366 | 150000 | 23307366 | 23966925 | 23422232 | 0 | 0 | 0 | 23422232 | 23605126 | 101.3% | 1 | 712036 | 509559 | 144 | 37 | 0 | 0 | 402 | 0 | 0 | 1 | -14585 | 2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -15279 | 2289 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-02 | QTR4 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 118 | 27208050.39 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 98.96% | 1 | 4666 | 70668 | 64 | 24 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15
| 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 87.95% | 1 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | 95.18% | 1 | -45614 | 67704 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98
| 01 | T1666 | 43289715201 | 2017-01-25 | QTR3 | 16/17 | 2 | 5 | 160 | 300 | 300 | 144.4% | 0 | 0 | 0 | 0 | 69 | 71 | 3057226 | 50000 | 3007226 | 3156754 | 3084177 | 0 | 0 | 0 | 3084177 | 3034815 | 100.9% | 1 | 9700 | 99528 | 49 | 20 | 0 | 0 | 13307 | 0 | 0 | 69 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 40465 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-03-15 | QTR3 | 17/18 | 118 | 3786427.28
| 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 105.3% | 1 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 103.1% | 1 | 162288 | 192592 | 71 | 21 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28
| 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 69.9% | 1 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | 98.2% | 1 | -627624 | 220362 | 44 | 14 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | 162.4% | 0 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710515 | -83952 | 0 | -83952 | 626563 | 655747 | 92.29% | 1 | 29184 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-03-05 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM
| 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 87.67% | 1 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 101.9% | 1 | 42066 | 48270 | 30 | 23 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35
| 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 97.45% | 1 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 100.1% | 1 | 4205 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79
| 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 100% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59
| 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 138.4% | 0 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 105.7% | 1 | 527 | 16831 | 2 | 15 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1687 | 41304245201 | 2017-07-26 | QTR1 | 17/18 | 1 | 6 | 429 | 484 | 340 | 66.43% | 1 | 144 | 0 | 0 | 55 | 0 | 28672708 | 150000 | 28522708 | 28693379 | 27612242 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | 99.35% | 1 | -344268 | 20671 | 44 | 11 | 0 | 0 | 46688 | 0 | 0 | 0 | 115877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348392 | 307784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -431102 | 0 | 0 | 0 | 79855 | 307784 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-02 | QTR2 | 18/19 | 106 | 35334896.73 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 97.33% | 1 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM
| 01 | T1690 | 43133915201 | 2017-07-26 | QTR1 | 17/18 | 1 | 2 | 75 | 165 | 165 | 186.7% | 0 | 0 | 0 | 0 | 25 | 65 | 350030 | 10890 | 339140 | 358946 | 348056 | 0 | 0 | 0 | 348056 | 348056 | 102.6% | 1 | 0 | 8916 | 21 | 4 | 0 | 47 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 8916 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-06-05 | QTR4 | 18/19 |  | 2018-08-24 | QTR1 | 18/19 | 118 | 228656.73 | B0 | ACC - LUMP SUM
| 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 99.13% | 1 | 302 | 0 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 98.96% | 1 | 908 | -6283 | 36 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM
| 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 98.89% | 1 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 109.8% | 1 | 92434 | 152724 | 22 | 11 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68
| 01 | T1699 | 43698315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 73 | 84 | 84 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 338000 | 0 | 338000 | 345335 | 345335 | 0 | 0 | 0 | 345335 | 345335 | 102.2% | 1 | 0 | 7335 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-28 | QTR1 | 18/19 | 115 | 381548.27
| 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 97.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1710 | 43795915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 170 | 199 | 166 | 80.59% | 1 | 33 | 0 | 0 | 29 | 0 | 1395501 | 50000 | 1345501 | 1395501 | 1301640 | 0 | 100000 | 100000 | 1401640 | 1301762 | 96.75% | 1 | -99878 | 0 | 10 | 19 | 0 | 0 | 30398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30398 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 118 | 1196299.53 | B1 | ACC - NO EXCUSE BONUS
| 01 | T1715 | 43902715201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 125 | 162 | 150 | 90.4% | 1 | 12 | 0 | 0 | 37 | 0 | 1013907 | 50000 | 963907 | 1013907 | 954583 | 0 | 0 | 0 | 954583 | 948729 | 98.43% | 1 | -5854 | 0 | 23 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2019-05-09 | QTR4 | 18/19 |  | 2019-02-27 | QTR3 | 18/19 | 118 | 844330.15
| 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 52.5% | 1 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 100% | 1 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM
| 01 | T1723 | 43658515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 1 | 120 | 140 | 140 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 1397798 | 50000 | 1347798 | 1388938 | 1357766 | 0 | 0 | 0 | 1357766 | 1357766 | 100.7% | 1 | 0 | -8860 | 4 | 16 | 0 | 0 | -1941 | 0 | 0 | 0 | -4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8860 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-05-28 | QTR4 | 18/19 |  | 2019-04-06 | QTR4 | 18/19 | 113 | 1567497.74 | B0 | ACC - LUMP SUM
| 01 | T1726 | 44016215201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 75 | 81 | 80 | 98.67% | 1 | 1 | 0 | 0 | 6 | 0 | 253590 | 0 | 253590 | 253590 | 253590 | 0 | 0 | 0 | 253590 | 253590 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-12-15 | QTR2 | 18/19 | 113 | 256717.81 | B0 | ACC - LUMP SUM
| 01 | T1728 | 43501715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 75 | 76 | 25 | 32% | 1 | 51 | 0 | 0 | 1 | 0 | 141143 | 0 | 141143 | 141143 | 141143 | 0 | 0 | 0 | 141143 | 141143 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 118 | 128587.62 | B0 | ACC - LUMP SUM
| 01 | T1730 | 43132415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 85 | 103 | 100 | 96.47% | 1 | 3 | 0 | 0 | 18 | 0 | 465432 | 0 | 465432 | 465432 | 465432 | 0 | 0 | 0 | 465432 | 465432 | 100% | 1 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 319733.9 | B0 | ACC - LUMP SUM
| 01 | T1733 | 43536915201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 80 | 100 | 100 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 274000 | 0 | 274000 | 286155 | 286155 | 0 | 0 | 0 | 286155 | 286155 | 104.4% | 1 | 0 | 12155 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-06-24 | QTR4 | 18/19 |  | 2019-03-08 | QTR3 | 18/19 | 115 | 295503.06 | B0 | ACC - LUMP SUM
| 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | 117.4% | 1 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | 91.9% | 1 | -1987458 | 665347 | 175 | 36 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A16 | 43609215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 9 | 600 | 771 | 767 | 101.7% | 1 | 4 | 0 | 0 | 157 | 14 | 18880004 | 150000 | 18730004 | 19841188 | 19816523 | 0 | 0 | 0 | 19816523 | 19628809 | 104.8% | 1 | -187714 | 961184 | 106 | 51 | 0 | 4 | 154148 | 5054 | 0 | 10 | 279737 | 116375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348400 | 347865 | 0 | 0 | 170559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804 | 48804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1001647 | 518098 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2017-12-08 | QTR2 | 17/18 | 113 | 24424912.84
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 38 | 60 | 169 | 11222 | 15028 | 14775 | 81.58% | 31 | 253 | 340 | 0 | 3215 | 600 | 348744577 | 2277823 | 346466754 | 359473679 | 356894062 | -220077 | 6126000 | 5905923 | 362799985 | 346272624 | 94.74% | 36 | -15082137 | 10729101 | 1952 | 812 | 150 | 201 | 3724201 | 127661 | 117 | 338 | 5074085 | 413987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170665 | 661087 | 0 | 2 | 641897 | 114516 | 0 | 0 | -1095 | 0 | 0 | 21 | 64050 | 0 | 0 | 20 | 320631 | 94994 | 0 | 0 | 292901 | 67556 | 0 | 0 | -25911 | 0 | 0 | 0 | -431102 | 0 | 267 | 582 | 9830322 | 1479801
| 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 167.4% | 0 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | 104.4% | 1 | -658099 | 1523947 | 48 | 38 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 145% | 0 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 93.37% | 1 | 0 | 0 | 16 | 3 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09
| 01 | E1P92 | 43493715201 | 2017-06-15 | QTR4 | 16/17 | 1 | 3 | 445 | 534 | 472 | 86.07% | 1 | 62 | 0 | 0 | 89 | 0 | 6312673 | 75306 | 6237367 | 6294987 | 6239240 | 0 | 0 | 0 | 6239240 | 6432013 | 103.1% | 1 | 192773 | -17686 | 45 | 44 | 0 | 0 | 32556 | 0 | 0 | 0 | 120500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -138741 | 0 | 0 | 0 | 14315 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-05-28 | QTR4 | 18/19 |  | 2019-01-30 | QTR3 | 18/19 | 108 | 6900471.09
| 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | 110.9% | 1 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 98.1% | 1 | 0 | 5910 | 22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11
| 01 | E1Q21 | 41773349201 | 2017-03-22 | QTR3 | 16/17 | 1 | 1 | 500 | 539 | 539 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 5353535 | 55841 | 5297694 | 5368855 | 5313014 | 0 | 0 | 0 | 5313014 | 0 | 0% | 1 | -5313014 | 15320 | 6 | 33 | 0 | 0 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15320 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-03-08 | QTR3 | 18/19 |  | 2018-11-04 | QTR2 | 18/19 | 113 | 5530217.16
| 01 | E1Q22 | 43854515201 | 2017-05-01 | QTR4 | 16/17 | 1 | 1 | 480 | 537 | 537 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 3614066 | 54963 | 3559103 | 3616288 | 3562935 | 0 | 0 | 0 | 3562935 | 3562935 | 100.1% | 1 | 0 | 2222 | 28 | 29 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 108 | 5496030.8
| 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 112.7% | 1 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 101.6% | 1 | 81050 | 33269 | 18 | 6 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66
| 01 | E1Q64 | 43445715201 | 2018-04-19 | QTR4 | 17/18 | 2 | 0 | 140 | 179 | 170 | 93.57% | 1 | 9 | 0 | 0 | 39 | 0 | 429966 | 21462 | 408504 | 429966 | 399604 | 0 | 0 | 0 | 399604 | 399697 | 97.84% | 1 | 94 | 0 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 450406.6
| 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 99% | 1 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 101.1% | 1 | 94256 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86
| 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 87.37% | 1 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 103.8% | 1 | 88492 | 0 | 11 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM
| 01 | E1Q77 | 43189515201 | 2017-05-19 | QTR4 | 16/17 | 1 | 1 | 475 | 617 | 617 | 106.3% | 1 | 0 | 0 | 0 | 139 | 3 | 6188743 | 0 | 6188743 | 6202025 | 6184286 | 0 | 0 | 0 | 6184286 | 6262099 | 101.2% | 1 | 77813 | 13282 | 66 | 46 | 0 | 3 | 13282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 3 | 13282 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-05-13 | QTR4 | 18/19 |  | 2019-03-28 | QTR3 | 18/19 | 113 | 7791984 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | 99.62% | 1 | -50000 | 14694 | 8 | 1 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 84.71% | 1 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | 89.77% | 1 | -25000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 69.33% | 1 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 100% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM
| 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 85.33% | 1 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 97.5% | 1 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63
| 01 | E1R09 | 43903015201 | 2018-05-17 | QTR4 | 17/18 | 1 | 0 | 90 | 93 | 78 | 83.33% | 1 | 15 | 0 | 0 | 3 | 0 | 279115 | 12207 | 266908 | 279115 | 264760 | 0 | 0 | 0 | 264760 | 264760 | 99.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-07 | QTR2 | 18/19 | 118 | 214242.2
| 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 54.67% | 1 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 90.43% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88
| 01 | E1R41 | 43806515201 | 2018-10-18 | QTR2 | 18/19 | 1 | 0 | 80 | 87 | 76 | 86.25% | 1 | 11 | 0 | 0 | 7 | 0 | 902868 | 50000 | 852868 | 902868 | 854160 | 0 | 0 | 0 | 854160 | 854160 | 100.2% | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-03-27 | QTR3 | 18/19 | 118 | 1003081.6
| 01 | E1R47 | 43320215201 | 2018-08-16 | QTR1 | 18/19 | 1 | 0 | 95 | 118 | 118 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 542243 | 28109 | 514134 | 542243 | 514134 | 0 | 0 | 0 | 514134 | 514134 | 100% | 1 | 0 | 0 | 5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-29 | QTR3 | 18/19 |  | 2019-02-28 | QTR3 | 18/19 | 108 | 573290.03 | B0 | ACC - LUMP SUM
| 01 | E1R55 | 43902615201 | 2018-03-15 | QTR3 | 17/18 | 1 | 0 | 150 | 159 | 142 | 88.67% | 1 | 17 | 0 | 0 | 9 | 0 | 402836 | 19980 | 382856 | 402836 | 380287 | 0 | 0 | 0 | 380287 | 381602 | 99.67% | 1 | 1315 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 118 | 497103.38
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 20 | 22 | 23 | 4431 | 5737 | 5516 | 90% | 18 | 221 | 12 | 0 | 1140 | 166 | 56333038 | 719532 | 55613506 | 57923997 | 57087750 | -19008 | 75000 | 55992 | 57143742 | 51627511 | 100% | 20 | -5510320 | 1590958 | 325 | 290 | 58 | 3 | 147253 | 0 | 0 | 3 | 155871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127168 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -138741 | 0 | 525 | 166 | 1695592 | 0
| District 01 Totals |  |  |  |  | 58 | 82 | 192 | 15653 | 20765 | 20291 | 84.48% | 49 | 474 | 352 | 0 | 4355 | 766 | 405077615 | 2997355 | 402080260 | 417397676 | 413981812 | -239085 | 6201000 | 5961915 | 419943727 | 397900135 | 96.55% | 56 | -20592457 | 12320059 | 2277 | 1102 | 208 | 204 | 3871454 | 127661 | 117 | 341 | 5229956 | 413987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297833 | 661087 | 27 | 2 | 641897 | 114516 | 0 | 0 | -1095 | 0 | 0 | 21 | 64050 | 0 | 0 | 20 | 1307856 | 94994 | 440 | 160 | 709718 | 67556 | 0 | 0 | -25911 | 0 | 0 | 0 | -569843 | 0 | 792 | 748 | 11525914 | 1479801
| 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 111.9% | 1 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | 97.1% | 1 | -1247384 | 840958 | 89 | 80 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73
| 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | 141.9% | 0 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | 89.67% | 1 | -62293 | 0 | 12 | 15 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1
| 02 | T2563 | 20965935201 | 2015-04-29 | QTR4 | 14/15 | 2 | 15 | 850 | 1201 | 1201 | 107.9% | 1 | 0 | 0 | 0 | 284 | 67 | 45821967 | 150000 | 45671967 | 48044659 | 49578076 | 0 | 0 | 0 | 49578076 | 48432413 | 106% | 1 | -1041379 | 2222691 | 206 | 78 | 0 | 26 | 1231947 | 142755 | 0 | 26 | 292304 | 7606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 471110 | 30796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 2228407 | 181157 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-06-13 | QTR4 | 18/19 |  | 2018-10-18 | QTR2 | 18/19 | 208 | 42314170.17
| 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 108.8% | 1 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | 100.1% | 1 | -366052 | 96491 | 80 | 54 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37511 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97
| 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 112.9% | 1 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | 106.5% | 1 | -214370 | 716585 | 179 | 57 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26
| 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 101.7% | 1 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | 98.56% | 1 | -162193 | 0 | 35 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36
| 02 | T2611 | 42880415201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 380 | 734 | 731 | 119.5% | 1 | 3 | 0 | 0 | 277 | 77 | 16425368 | 150000 | 16275368 | 17429243 | 17737903 | 0 | 0 | 0 | 17737903 | 17843990 | 109.6% | 1 | 106088 | 1003875 | 186 | 91 | 0 | 7 | 102446 | 43792 | 0 | 70 | 961987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 0 | 0 | 11131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1135125 | 43792 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 214 | 14976802.73
| 02 | T2623 | 42747425201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 588 | 772 | 772 | 104.4% | 1 | 0 | 0 | 0 | 184 | 0 | 12006916 | 125768 | 11881149 | 12006916 | 12019761 | 0 | 0 | 0 | 12019761 | 12020496 | 101.2% | 1 | 735 | 0 | 85 | 73 | 26 | 0 | 18391 | 0 | 0 | 0 | 17909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 43031 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 214 | 12840720.13
| 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 99.64% | 1 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 91.44% | 1 | 151 | 36072 | 41 | 50 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79
| 02 | T2625 | 43091415201 | 2016-06-15 | QTR4 | 15/16 | 2 | 4 | 300 | 495 | 475 | 110.3% | 1 | 20 | 0 | 0 | 144 | 51 | 4913266 | 96132 | 4817134 | 5029801 | 5053902 | 0 | 0 | 0 | 5053902 | 5063705 | 105.1% | 1 | 9803 | 116535 | 75 | 69 | 0 | 11 | 42674 | 0 | 0 | 40 | 83572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 155418 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-01-04 | QTR3 | 17/18 | 208 | 4921245.07
| 02 | T2627 | 43035215201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 624 | 813 | 813 | 105.9% | 1 | 0 | 0 | 0 | 161 | 28 | 10750000 | 111180 | 10638820 | 10970043 | 11054481 | 0 | 0 | 0 | 11054481 | 11069654 | 104% | 1 | 71901 | 220043 | 89 | 63 | 0 | 0 | 10095 | 0 | 0 | 28 | 252685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 28 | 266343 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-06-18 | QTR4 | 18/19 |  | 2019-01-22 | QTR3 | 18/19 | 214 | 11199747.1
| 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 99.47% | 1 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 100% | 1 | 4 | 0 | 13 | 6 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83
| 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 86.67% | 1 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 103.4% | 1 | 0 | 0 | 21 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13
| 02 | T2647 | 43230915201 | 2017-03-29 | QTR3 | 16/17 | 3 | 5 | 240 | 446 | 445 | 114.2% | 1 | 1 | 0 | 0 | 171 | 35 | 9199404 | 103815 | 9095588 | 9776200 | 8992961 | 0 | 0 | 0 | 8992961 | 9273619 | 102% | 1 | 280658 | 576796 | 100 | 71 | 0 | 14 | 45192 | 0 | 0 | 0 | 3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 286737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 621897 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-04-23 | QTR4 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 214 | 10410749.13
| 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 100.7% | 1 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 102% | 1 | 44704 | 0 | 28 | 4 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12
| 02 | T2654 | 43434215201 | 2017-02-22 | QTR3 | 16/17 | 1 | 8 | 260 | 451 | 451 | 136.9% | 0 | 0 | 0 | 0 | 111 | 80 | 7099476 | 120 | 7099356 | 6953209 | 7172661 | 0 | 0 | 0 | 7172661 | 7430190 | 104.7% | 1 | 266940 | -146267 | 71 | 24 | 3 | 0 | 25327 | 0 | 10 | 60 | 58126 | 10439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -247097 | 0 | 16 | 60 | -155678 | 10439 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-07 | QTR4 | 18/19 |  | 2018-09-28 | QTR1 | 18/19 | 214 | 7906422.14
| 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 110.6% | 1 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 103.9% | 1 | 26193 | 7048 | 42 | 26 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91
| 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 99.84% | 1 | 89 | 0 | 29 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75
| 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 98.44% | 1 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5836409 | 103.1% | 1 | 107663 | 51929 | 37 | 51 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2
| 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | 144.7% | 0 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1015867 | 96.32% | 1 | 121 | 6408 | 22 | 24 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32
| 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 105.4% | 1 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 96.89% | 1 | 1714 | 4486 | 74 | 4 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75
| 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 79% | 1 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 95.24% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5
| 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 103.6% | 1 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 103.2% | 1 | 21810 | 0 | 16 | 5 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74
| 02 | T2677 | 43616715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 200 | 349 | 347 | 114% | 1 | 2 | 0 | 0 | 119 | 30 | 3488727 | 50000 | 3438727 | 3488727 | 3422691 | 0 | 0 | 0 | 3422691 | 3561473 | 103.6% | 1 | 138781 | 0 | 96 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 216 | 3968191.21
| 02 | T2680 | 43616415201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 160 | 235 | 235 | 109.4% | 1 | 0 | 0 | 0 | 60 | 15 | 4259756 | 53360 | 4206396 | 4352657 | 4324824 | 0 | 0 | 0 | 4324824 | 4574214 | 108.7% | 1 | 249390 | 92901 | 37 | 23 | 0 | 15 | 21638 | 0 | 0 | 0 | 89529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 111167 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2019-04-10 | QTR4 | 18/19 |  | 2019-01-14 | QTR3 | 18/19 | 209 | 4621256.34
| 02 | T2681 | 43499615201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 180 | 216 | 216 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 1999378 | 50000 | 1949378 | 1999378 | 1930362 | 0 | 0 | 0 | 1930362 | 1930362 | 99.02% | 1 | 0 | 0 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 209 | 2290722.63
| 02 | T2684 | 42857315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 200 | 265 | 265 | 108.5% | 1 | 0 | 0 | 0 | 48 | 17 | 1816827 | 120 | 1816707 | 1864097 | 1920891 | 0 | 0 | 0 | 1920891 | 1923439 | 105.9% | 1 | 2549 | 47270 | 40 | 8 | 0 | 5 | 23159 | 0 | 0 | 6 | 24111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 47270 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-04-04 | QTR4 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 209 | 1671760.06
| 02 | T2696 | 43616015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 180 | 215 | 180 | 80.56% | 1 | 35 | 0 | 0 | 35 | 0 | 3898972 | 50000 | 3848972 | 3898972 | 3993251 | 0 | 0 | 0 | 3993251 | 4179790 | 108.6% | 1 | 186539 | 0 | 24 | 11 | 0 | 0 | 11579 | 0 | 0 | 0 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15539 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2018-12-03 | QTR2 | 18/19 | 208 | 4207177.88
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 28 | 40 | 72 | 8792 | 12340 | 12243 | 89.29% | 25 | 97 | 67 | 0 | 2807 | 741 | 204705560 | 2227624 | 202477935 | 210599382 | 210263394 | -114976 | 0 | -114976 | 210148418 | 208371725 | 100% | 28 | -1577838 | 5893821 | 1756 | 982 | 34 | 195 | 2686425 | 203251 | 23 | 387 | 2760456 | 38567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | 0 | 23 | 580522 | 45461 | 3 | 23 | 325614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255257 | 0 | 0 | 44 | 373363 | 0 | 9 | 43 | 163863 | 149956 | 0 | 0 | 0 | 0 | 0 | 0 | -284608 | 0 | 69 | 715 | 6865405 | 437236
| 02 | E2R91 | 41650145201 | 2014-06-26 | QTR4 | 13/14 | 3 | 9 | 900 | 1294 | 1372 | 123.7% | 0 | -78 | 78 | 0 | 259 | 135 | 66725725 | 270345 | 66455380 | 67223879 | 66965314 | -795600 | 0 | -795600 | 66169714 | 64637295 | 97.26% | 1 | -1452887 | 498154 | 134 | 125 | 0 | 0 | 13369 | 0 | 0 | 14 | 196815 | 0 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 301636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202522 | 0 | 0 | 135 | 370894 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-05-30 | QTR4 | 17/18 | 208 | 83530874.22 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 164.7% | 0 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | 118.1% | 0 | -412 | 1525306 | 47 | 79 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43
| 02 | E2T76 | 43055715201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 150 | 201 | 201 | 108.7% | 1 | 0 | 0 | 0 | 38 | 13 | 2328151 | 50000 | 2278151 | 2328151 | 2166539 | 0 | 0 | 0 | 2166539 | 2180708 | 95.72% | 1 | 14169 | 0 | 22 | 16 | 0 | 3 | 1972 | 0 | 0 | 10 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 5492 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-26 | QTR4 | 18/19 |  | 2017-03-08 | QTR3 | 16/17 | 209 | 2144470.22
| 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 106.2% | 1 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | 111.7% | 0 | -22727 | 248912 | 44 | 63 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47
| 02 | E2U40 | 43015815201 | 2016-01-20 | QTR3 | 15/16 | 3 | 2 | 436 | 624 | 622 | 110.1% | 1 | 2 | 0 | 0 | 142 | 46 | 4367770 | 50000 | 4317770 | 4673447 | 4944003 | 0 | 0 | 0 | 4944003 | 4845350 | 112.2% | 0 | -49202 | 305677 | 76 | 66 | 0 | 0 | 3676 | 0 | 0 | 0 | 259099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 262775 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2019-01-09 | QTR3 | 18/19 | 02/17/2018 | 2018-02-17 | QTR3 | 17/18 | 208 | 4165392.78
| 02 | E2U49 | 43074915201 | 2016-05-18 | QTR4 | 15/16 | 3 | 4 | 240 | 409 | 409 | 141.7% | 0 | 0 | 0 | 0 | 69 | 100 | 5878818 | 87141 | 5791677 | 6117316 | 6222842 | 0 | 0 | 0 | 6222842 | 6229444 | 107.6% | 1 | 6601 | 238499 | 41 | 28 | 0 | 100 | 163931 | 148393 | 0 | 0 | 28577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 251507 | 148393 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2017-09-25 | QTR1 | 17/18 | 208 | 7361145.29
| 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 100.7% | 1 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 86.65% | 1 | 35717 | -98576 | 61 | 55 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26
| 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 98.89% | 1 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 100.1% | 1 | 0 | 28412 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894
| 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 99.6% | 1 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 97.73% | 1 | 121 | 4326 | 20 | 40 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23
| 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 97.73% | 1 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 104.5% | 1 | 30133 | 59347 | 55 | 63 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25
| 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 103.1% | 1 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 104.1% | 1 | 66 | 0 | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65
| 02 | E2W33 | 42820235201 | 2017-05-17 | QTR4 | 16/17 | 2 | 2 | 240 | 372 | 372 | 112.5% | 1 | 0 | 0 | 0 | 102 | 30 | 3845000 | 50000 | 3795000 | 3906311 | 3955336 | 0 | 0 | 0 | 3955336 | 3996802 | 105.3% | 1 | 52777 | 61311 | 79 | 23 | 0 | 13 | 18140 | 0 | 0 | 15 | 45984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 64124 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-04-26 | QTR4 | 18/19 |  | 2018-10-22 | QTR2 | 18/19 | 216 | 4211837.31
| 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 181.6% | 0 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 127.5% | 0 | 175603 | 494858 | 26 | 20 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55
| 02 | E2W85 | 43219515201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 300 | 355 | 334 | 93% | 1 | 21 | 0 | 0 | 55 | 0 | 2078199 | 50000 | 2028199 | 2078199 | 1988452 | 0 | 0 | 0 | 1988452 | 1988452 | 98.04% | 1 | 0 | 0 | 13 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-30 | QTR4 | 18/19 |  | 2019-04-05 | QTR4 | 18/19 | 208 | 2082168.77
| 02 | E2W86 | 43239515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 120 | 166 | 166 | 100.8% | 1 | 0 | 0 | 0 | 45 | 1 | 567579 | 25415 | 542163 | 567579 | 542982 | 0 | 0 | 0 | 542982 | 542982 | 100.2% | 1 | 0 | 0 | 9 | 36 | 0 | 1 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2630 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-12-21 | QTR2 | 18/19 | 208 | 529604.74
| 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 103.4% | 1 | 78162 | 0 | 27 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44
| 02 | E2W88 | 42849415201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 138 | 179 | 173 | 95.65% | 1 | 6 | 0 | 0 | 41 | 0 | 290000 | 23311 | 266689 | 290000 | 255859 | 0 | 0 | 0 | 255859 | 255859 | 95.94% | 1 | 0 | 0 | 11 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 208 | 444332.8
| 02 | E2W93 | 43433815201 | 2018-01-17 | QTR3 | 17/18 | 2 | 0 | 160 | 216 | 207 | 107.5% | 1 | 9 | 0 | 0 | 56 | 0 | 594594 | 28886 | 565708 | 594594 | 581178 | 0 | 0 | 0 | 581178 | 581178 | 102.7% | 1 | 0 | 0 | 6 | 29 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-03-15 | QTR3 | 18/19 |  | 2019-02-05 | QTR3 | 18/19 | 208 | 613772.37
| 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 105.6% | 1 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 100.9% | 1 | 0 | 12377 | 10 | 5 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97
| 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 99.77% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 20 | 34 | 41 | 5339 | 7630 | 7606 | 80% | 16 | 24 | 78 | 0 | 1520 | 771 | 121055540 | 1175156 | 119880383 | 124434139 | 124114706 | -795600 | 0 | -795600 | 123319106 | 121904996 | 80% | 16 | -1131879 | 3378603 | 726 | 773 | 0 | 244 | 767411 | 148393 | 3 | 358 | 2318245 | 322078 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 320081 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 59000 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | -202522 | 0 | 21 | 769 | 3323808 | 470471
| District 02 Totals |  |  |  |  | 48 | 74 | 113 | 14131 | 19970 | 19849 | 85.42% | 41 | 121 | 145 | 0 | 4327 | 1512 | 325761100 | 3402780 | 322358318 | 335033521 | 334378100 | -910576 | 0 | -910576 | 333467524 | 330276721 | 91.67% | 44 | -2709717 | 9272424 | 2482 | 1755 | 34 | 439 | 3453836 | 351644 | 26 | 745 | 5078701 | 360645 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77113 | 0 | 0 | 76 | 900603 | 45461 | 3 | 69 | 325614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255257 | 0 | 0 | 112 | 432363 | 0 | 9 | 43 | 163863 | 149956 | 18 | 0 | 0 | 0 | 0 | 0 | -487130 | 0 | 90 | 1484 | 10189213 | 907707
| 03 | T3417 | 42282315201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 325 | 885 | 885 | 230.2% | 0 | 0 | 0 | 0 | 560 | 0 | 9576952 | 114593 | 9462359 | 11201952 | 11381048 | 0 | 0 | 0 | 11381048 | 11259809 | 119% | 0 | -121240 | 1625000 | 104 | 33 | 0 | 0 | 6816 | 0 | 128 | 0 | 16533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 1672506 | 1625000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2016-03-01 | QTR3 | 15/16 | 321 | 11869074.15
| 03 | T3474 | 41110245201 | 2014-05-21 | QTR4 | 13/14 | 2 | 9 | 560 | 736 | 736 | 105.4% | 1 | 0 | 0 | 0 | 146 | 30 | 13521855 | 125538 | 13396317 | 14023931 | 14165918 | 0 | 0 | 0 | 14165918 | 13122088 | 97.95% | 1 | -1043829 | 502076 | 106 | 40 | 0 | 0 | 37317 | 0 | 0 | 30 | 516186 | 243604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21575 | 21575 | 0 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 618377 | 265179 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | QTR3 | 18/19 |  | 2016-08-26 | QTR1 | 16/17 | 308 | 12749353.07
| 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 235.5% | 0 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 125.8% | 0 | 1482 | 446147 | 119 | 44 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15
| 03 | T3498 | 43178515201 | 2017-01-25 | QTR3 | 16/17 | 4 | 1 | 190 | 384 | 387 | 128.9% | 0 | -3 | 3 | 0 | 172 | 22 | 4274307 | 55980 | 4218327 | 4324307 | 4294029 | -8433 | 0 | -8433 | 4285596 | 4353335 | 103.2% | 1 | 67739 | 50000 | 112 | 30 | 0 | 13 | 40548 | 0 | 15 | 5 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 46278 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 308 | 4281515.77
| 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 112% | 1 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 87% | 1 | 0 | -1624 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM
| 03 | T3545 | 43047615201 | 2017-08-30 | QTR1 | 17/18 | 2 | 7 | 485 | 542 | 423 | 69.28% | 1 | 119 | 0 | 0 | 87 | -30 | 4421121 | 0 | 4421121 | 4223806 | 4448093 | 0 | 0 | 0 | 4448093 | 4444910 | 100.5% | 1 | 17887 | -197315 | 53 | 34 | 0 | 0 | 25547 | 0 | 0 | 0 | 7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -306809 | 0 | 0 | -30 | -218385 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-05-09 | QTR4 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 321 | 5512724.17
| 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 173.1% | 0 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | 138.9% | 0 | -25384 | 2617138 | 303 | 81 | 65 | 20 | 532799 | 13449 | 90 | 4 | 490052 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2616143 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94
| 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 127% | 0 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 100% | 1 | 152 | 75332 | 76 | 23 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13
| 03 | T3567 | 43046515201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 165 | 250 | 260 | 115.2% | 1 | -10 | 10 | 0 | 70 | 15 | 1966055 | 0 | 1966055 | 1981055 | 2001427 | -15840 | 0 | -15840 | 1985587 | 1998145 | 101.6% | 1 | 12558 | 15000 | 64 | 6 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 308 | 1970432.78
| 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 120.4% | 0 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 107.4% | 1 | 7457 | 20691 | 171 | 28 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24
| 03 | T3573 | 43046615201 | 2016-12-07 | QTR2 | 16/17 | 1 | 3 | 295 | 612 | 612 | 160.7% | 0 | 0 | 0 | 0 | 215 | 102 | 4160238 | 0 | 4160238 | 4529735 | 4531012 | 0 | 0 | 0 | 4531012 | 4552720 | 109.4% | 1 | 21708 | 369496 | 107 | 31 | 0 | 0 | 0 | 0 | 77 | 102 | 354870 | 121906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 102 | 354870 | 121906 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-04-15 | QTR4 | 18/19 |  | 2018-11-26 | QTR2 | 18/19 | 308 | 3945558.92
| 03 | T3596 | 43274015201 | 2016-09-28 | QTR1 | 16/17 | 2 | 1 | 229 | 350 | 349 | 99.56% | 1 | 1 | 0 | 0 | 121 | 0 | 8173983 | 81645 | 8092338 | 8193029 | 8770491 | -4500 | 0 | -4500 | 8765991 | 8814288 | 108.9% | 1 | 48297 | 19046 | 102 | 19 | 0 | 0 | 6600 | 0 | 0 | 0 | 5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5882 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2017-12-17 | QTR2 | 17/18 | 314 | 8245135.42
| 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 109.5% | 1 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 108.2% | 1 | 123160 | 15763 | 77 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43
| 03 | T3634 | 43256215201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 227 | 227 | 103.3% | 1 | 0 | 0 | 0 | 77 | 0 | 2317459 | 51202 | 2266257 | 2317459 | 2243858 | 0 | 0 | 0 | 2243858 | 2321931 | 102.5% | 1 | 78073 | 0 | 55 | 17 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 308 | 2451817.54
| 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 98.1% | 1 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 97.03% | 1 | 0 | 1601 | 48 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-03-19 | QTR3 | 17/18 | 308 | 819000
| 03 | T3638 | 43461115201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 210 | 364 | 366 | 112.4% | 1 | -2 | 2 | 0 | 133 | 21 | 5256385 | 58075 | 5198309 | 5256385 | 5540831 | -7290 | 0 | -7290 | 5533541 | 5791591 | 111.4% | 0 | 258050 | 0 | 90 | 40 | 0 | 4 | 18750 | 0 | 0 | 3 | 5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8122 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 32453 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 5826402.83
| 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 141.7% | 0 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 102.9% | 1 | 0 | 28099 | 33 | 4 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM
| 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | 122.2% | 0 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 98.39% | 1 | 13058 | -7125 | 22 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54
| 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 98.46% | 1 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 97.09% | 1 | 0 | -21294 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM
| 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 99.26% | 1 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 107% | 1 | 32427 | 14433 | 38 | 21 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46
| 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 119.4% | 1 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 101.4% | 1 | 22904 | 0 | 76 | 16 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83
| 03 | T3677 | 43467515201 | 2018-02-28 | QTR3 | 17/18 | 2 | 1 | 120 | 159 | 148 | 93.33% | 1 | 11 | 0 | 0 | 36 | 3 | 2607729 | 51275 | 2556454 | 2610160 | 2714487 | -7200 | 0 | -7200 | 2707287 | 2805120 | 109.7% | 1 | 97833 | 2431 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 2431 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14394 | 25 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-09-20 | QTR1 | 18/19 | 308 | 3422497.92
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 22 | 39 | 74 | 4724 | 8507 | 8392 | 59.09% | 13 | 115 | 33 | 0 | 3452 | 331 | 90143823 | 1020112 | 89123712 | 95718718 | 98319809 | -113575 | 0 | -113575 | 98206234 | 97797494 | 81.82% | 18 | -387668 | 5574895 | 1791 | 563 | 65 | 53 | 716761 | 13449 | 542 | 191 | 1727129 | 721188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 113 | 1736835 | 428480 | 3 | 0 | 31815 | 14535 | 0 | 0 | 0 | 0 | 0 | 4 | 196583 | 5684 | 0 | 0 | 1662627 | 1662627 | 20 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -306809 | 0 | 1098 | 331 | 5781489 | 2845962
| 03 | E3K83 | 41506725201 | 2012-11-20 | QTR2 | 12/13 | 2 | 8 | 599 | 1108 | 1108 | 120.7% | 0 | 0 | 0 | 0 | 385 | 124 | 13915054 | 150000 | 13765054 | 14699375 | 14628947 | 0 | 0 | 0 | 14628947 | 14470162 | 105.1% | 1 | -158785 | 784321 | 311 | 74 | 0 | 5 | 84488 | 0 | 0 | 12 | 93331 | 1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 107 | 683618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 867013 | 1459 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2016-01-26 | QTR3 | 15/16 | 308 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR
| 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 119.4% | 1 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | 102.6% | 1 | -981850 | 3971426 | 99 | 61 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
| 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 97.78% | 1 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 103.4% | 1 | 130 | 0 | 10 | 0 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000
| 03 | E3P22 | 40619625201 | 2018-08-09 | QTR1 | 18/19 | 1 | 0 | 120 | 135 | 130 | 95.83% | 1 | 5 | 0 | 0 | 15 | 0 | 178163 | 15128 | 163035 | 178163 | 116546 | 0 | 0 | 0 | 116546 | 116546 | 71.49% | 1 | 0 | 0 | 2 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2019-06-06 | QTR4 | 18/19 |  | 2019-04-04 | QTR4 | 18/19 | 308 | 270683.27
| 03 | E3P35 | 40674235201 | 2017-11-09 | QTR2 | 17/18 | 1 | 0 | 235 | 281 | 281 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2284367 | 50000 | 2234367 | 2284367 | 2177088 | 0 | 0 | 0 | 2177088 | 2177088 | 97.44% | 1 | 0 | 0 | 40 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 321 | 4068630.6
| 03 | E3P64 | 40747855201 | 2017-10-12 | QTR2 | 17/18 | 1 | 0 | 110 | 153 | 153 | 111.8% | 1 | 0 | 0 | 0 | 43 | 0 | 477560 | 28231 | 449329 | 477560 | 464944 | 0 | 0 | 0 | 464944 | 464944 | 103.5% | 1 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 308 | 607325
| 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 118.3% | 1 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 106.1% | 1 | 0 | 26519 | 71 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72
| 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 91.67% | 1 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 106.1% | 1 | 81564 | 0 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17
| 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 99.33% | 1 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 102.1% | 1 | 10099 | 127524 | 43 | 37 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000
| 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 110% | 1 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 101.6% | 1 | 945 | 3000 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64
| 03 | E3Q91 | 43626815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 3 | 180 | 246 | 244 | 103.9% | 1 | 2 | 0 | 0 | 64 | 2 | 3258297 | 50000 | 3208297 | 3274221 | 3353918 | 0 | 0 | 0 | 3353918 | 3489125 | 108.8% | 1 | 135206 | 15924 | 49 | 8 | 7 | 2 | 16487 | 0 | 0 | 0 | 31396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 45243 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 321 | 4488229.01
| 03 | E3Q93 | 44107815201 | 2018-07-12 | QTR1 | 18/19 | 2 | 0 | 90 | 139 | 133 | 93.33% | 1 | 6 | 0 | 0 | 49 | 0 | 119741 | 9449 | 110292 | 119741 | 111083 | 0 | 0 | 0 | 111083 | 111083 | 100.7% | 1 | 0 | 0 | 29 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F541769861 | FERROVIAL SERVICES INFRASTRUCTURE INC | N/A | N/A | N/A | N/A | 2019-06-05 | QTR4 | 18/19 |  | 2019-02-11 | QTR3 | 18/19 | 313 | 198799.25
| 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 95.71% | 1 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 98.08% | 1 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61
| 03 | E3R38 | 21869925201 | 2018-06-14 | QTR4 | 17/18 | 1 | 1 | 90 | 144 | 142 | 97.78% | 1 | 2 | 0 | 0 | 54 | 0 | 459900 | 35772 | 424128 | 473285 | 462354 | 0 | 0 | 0 | 462354 | 462354 | 109% | 1 | 0 | 13385 | 36 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-04-18 | QTR4 | 18/19 |  | 2019-02-19 | QTR3 | 18/19 | 321 | 750711.43
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 14 | 17 | 24 | 3302 | 4742 | 4697 | 92.86% | 13 | 45 | 0 | 0 | 1277 | 163 | 147808980 | 746074 | 147062906 | 152751079 | 152268689 | 0 | 0 | 0 | 152268689 | 151355999 | 100% | 14 | -912691 | 4942099 | 759 | 292 | 206 | 13 | -701722 | 236 | 0 | 20 | 293148 | 1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 13 | 130 | 747849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54484 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | -216679 | 0 | 226 | 163 | 5141080 | 4951912
| District 03 Totals |  |  |  |  | 36 | 56 | 98 | 8026 | 13249 | 13089 | 72.22% | 26 | 160 | 33 | 0 | 4729 | 494 | 237952803 | 1766186 | 236186618 | 248469797 | 250588498 | -113575 | 0 | -113575 | 250474923 | 249153493 | 88.89% | 32 | -1300359 | 10516994 | 2550 | 855 | 271 | 66 | 15039 | 13685 | 542 | 211 | 2020277 | 722864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 481 | 243 | 2484684 | 428480 | 3 | 0 | 31815 | 14535 | 0 | 0 | 0 | 0 | 0 | 4 | 251067 | 5684 | 0 | 0 | 6612627 | 6612627 | 20 | 0 | 16549 | 0 | 7 | 0 | 0 | 0 | 0 | -30 | -523488 | 0 | 1324 | 494 | 10922569 | 7797874
| 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 109.8% | 1 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 88.9% | 1 | 0 | 4802 | 135 | 26 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59
| 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 116% | 1 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | 104.2% | 1 | -14505 | 252534 | 101 | 41 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 116% | 1 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | 107.3% | 1 | -7370 | 325031 | 104 | 27 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL C | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4
| 04 | T4438 | 42871915201 | 2016-09-28 | QTR1 | 16/17 | 10 | 6 | 414 | 553 | 553 | 110.9% | 1 | 0 | 0 | 0 | 139 | 0 | 8534546 | 149000 | 8385546 | 8647389 | 8810202 | 0 | 0 | 0 | 8810202 | 8996744 | 107.3% | 1 | 197163 | 112843 | 56 | 38 | 0 | 0 | 147796 | 7419 | 45 | 0 | 59952 | 8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668 | 8668 | 0 | 0 | 3778 | 0 | 0 | 0 | -84397 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 135797 | 25044 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-09 | QTR4 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 409 | 8438874.92
| 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 105.6% | 1 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 99.1% | 1 | 4036 | 70900 | 32 | 24 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM
| 04 | T4445 | 43060315201 | 2017-01-25 | QTR3 | 16/17 | 1 | 4 | 365 | 510 | 480 | 94.79% | 1 | 30 | 0 | 0 | 134 | 11 | 8418937 | 102163 | 8316774 | 8403485 | 8476613 | 0 | 0 | 0 | 8476613 | 8700175 | 104.6% | 1 | 251131 | -15452 | 110 | 24 | 0 | 19 | 47250 | 0 | 0 | 0 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | -72293 | 0 | 0 | 11 | 51443 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-28 | QTR3 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 412 | 9837147.69
| 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 112.1% | 1 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | 96.73% | 1 | -10793 | 15092 | 66 | 22 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97
| 04 | T4447 | 43510115201 | 2017-03-29 | QTR3 | 16/17 | 7 | 2 | 364 | 422 | 422 | 86.26% | 1 | 0 | 0 | 0 | 108 | -50 | 3554036 | 50000 | 3504036 | 3574289 | 3278614 | 0 | 0 | 0 | 3278614 | 3266227 | 93.21% | 1 | 4310 | 20253 | 88 | 20 | 0 | 0 | 1981 | 0 | 0 | -50 | 5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 7532 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 409 | 3729070.5
| 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 118.6% | 1 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 97.21% | 1 | 0 | 0 | 32 | 25 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66
| 04 | T4451 | 43514415201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 167 | 204 | 204 | 103% | 1 | 0 | 0 | 0 | 32 | 5 | 853000 | 35518 | 817482 | 853000 | 762484 | 0 | 0 | 0 | 762484 | 764893 | 93.57% | 1 | 2408 | 0 | 24 | 8 | 0 | 5 | 1628 | 0 | 0 | 0 | 6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8585 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-04-25 | QTR4 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 409 | 757018.39
| 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 99.9% | 1 | 985 | 4306 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15
| 04 | T4455 | 43442715201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 277 | 316 | 306 | 96.39% | 1 | 10 | 0 | 0 | 39 | 0 | 14081000 | 150000 | 13931000 | 14107664 | 13452505 | 0 | 0 | 0 | 13452505 | 14356886 | 103.1% | 1 | 904380 | 26664 | 31 | 8 | 0 | 0 | 26664 | 0 | 0 | 0 | 9390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11492 | 0 | 0 | 0 | 34538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82084 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-09 | QTR2 | 18/19 | 409 | 15571973.96
| 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 98.57% | 1 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 93.86% | 1 | 981 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46
| 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 79.2% | 1 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | 105.3% | 1 | -34322 | 31168 | 30 | 14 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 95.84% | 1 | 10 | 0 | 7 | 18 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07
| 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | 104% | 1 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 96.79% | 1 | 0 | 0 | 28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1
| 04 | T4464 | 23316625201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 291 | 458 | 456 | 112.7% | 1 | 2 | 0 | 0 | 167 | 0 | 3520178 | 50000 | 3470178 | 3520178 | 3370360 | 0 | 0 | 0 | 3370360 | 3385395 | 97.56% | 1 | 15035 | 0 | 87 | 41 | 0 | 0 | 2782 | 0 | 30 | 0 | 40068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 45234 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-05-29 | QTR4 | 18/19 |  | 2019-01-23 | QTR3 | 18/19 | 409 | 3420061.33
| 04 | T4466 | 42871815201 | 2017-07-26 | QTR1 | 17/18 | 5 | 1 | 388 | 441 | 411 | 92.27% | 1 | 30 | 0 | 0 | 53 | 0 | 3213996 | 50000 | 3163996 | 3213990 | 3033800 | 0 | 0 | 0 | 3033800 | 3135748 | 99.11% | 1 | 101948 | -6 | 23 | 30 | 0 | 0 | 19551 | 0 | 0 | 0 | 4848 | 8066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24399 | 8066 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-12-20 | QTR2 | 18/19 | 409 | 3457230.6
| 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 80% | 1 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 94.93% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24
| 04 | T4475 | 43609715201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 181 | 246 | 245 | 108.8% | 1 | 1 | 0 | 0 | 65 | 0 | 1977475 | 50000 | 1927475 | 1977475 | 1900507 | 0 | 0 | 0 | 1900507 | 1961150 | 101.7% | 1 | 60643 | 0 | 28 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 9996 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-05-13 | QTR4 | 18/19 |  | 2019-02-17 | QTR3 | 18/19 | 412 | 2189027.65
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 20 | 61 | 35 | 5415 | 7263 | 7115 | 100% | 20 | 148 | 4 | 0 | 1685 | 163 | 68833986 | 1125913 | 67708075 | 69682121 | 67559113 | 0 | 37125 | 37125 | 67596238 | 68890181 | 100% | 20 | 1476040 | 848135 | 1072 | 440 | 10 | 144 | 705193 | 277506 | 109 | -2 | 413139 | 88795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38876 | 0 | 0 | 29 | 91305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668 | 8668 | 54 | 0 | 3778 | 0 | 0 | 0 | -84397 | 0 | 0 | -8 | -74175 | 0 | 173 | 163 | 1102389 | 374969
| 04 | E4K92 | 41248925201 | 2010-11-30 | QTR2 | 10/11 | 7 | 17 | 1303 | 2546 | 2546 | 182.5% | 0 | 0 | 0 | 0 | 228 | 1015 | 94215000 | 150000 | 94065000 | 108647581 | 108420972 | 0 | 0 | 0 | 108420972 | 108204126 | 115% | 0 | -90707 | 14432581 | 86 | 82 | 0 | 288 | 1644087 | 1314542 | 0 | 220 | 2406319 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 60 | 507 | 10129365 | 2700545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1015 | 14293821 | 6446112 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 | 05/08/2018 | 2018-10-04 | QTR2 | 18/19 | 409 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4M78 | 41304925201 | 2013-03-14 | QTR3 | 12/13 | 1 | 6 | 925 | 1777 | 1831 | 147.4% | 0 | -54 | 54 | 0 | 599 | 253 | 50630000 | 150000 | 50480000 | 51906885 | 51703165 | -514238 | 0 | -514238 | 51188926 | 48130802 | 95.35% | 1 | -2986230 | 1276885 | 382 | 86 | 2 | 4 | 160986 | 0 | 129 | 154 | 1630628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -525817 | 0 | 131 | 158 | 1265797 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-04-22 | QTR4 | 18/19 |  | 2018-06-01 | QTR4 | 17/18 | 408 | 57557685.27 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 95.19% | 1 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | 102% | 1 | -2197408 | 3131122 | 99 | 57 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82927 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P08 | 42170755201 | 2014-03-25 | QTR3 | 13/14 | 7 | 23 | 1305 | 1810 | 1471 | 92.03% | 1 | 339 | 0 | 0 | 270 | 235 | 80437734 | 150000 | 80287734 | 82797035 | 82818636 | -283033 | -200000 | -483033 | 82335603 | 78160637 | 97.35% | 1 | -3880669 | 2359301 | 204 | 66 | 0 | 5 | -559751 | 0 | 0 | 27 | 763643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1957639 | 16706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 12319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76704 | 0 | 0 | 235 | 2097146 | 16706 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-06 | QTR3 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 412 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 102.6% | 1 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | 100% | 1 | -85027 | 475368 | 293 | 39 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75
| 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 117.3% | 1 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 101.6% | 1 | 93460 | 150444 | 82 | 28 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15
| 04 | E4R83 | 43482915201 | 2017-05-03 | QTR4 | 16/17 | 1 | 0 | 445 | 586 | 585 | 102.7% | 1 | 1 | 0 | 0 | 141 | 0 | 2949000 | 50000 | 2899000 | 2949000 | 2893000 | 0 | 0 | 0 | 2893000 | 2893000 | 99.79% | 1 | 0 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2019-01-28 | QTR3 | 18/19 | 412 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 107.2% | 1 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 95.22% | 1 | 26852 | 127760 | 93 | 24 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01
| 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 93.77% | 1 | 1375 | 0 | 46 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29
| 04 | E4S29 | 43059325201 | 2017-04-07 | QTR4 | 16/17 | 4 | 2 | 290 | 414 | 414 | 100% | 1 | 0 | 0 | 0 | 124 | 0 | 3060921 | 47591 | 3013330 | 3171379 | 2918996 | 0 | 0 | 0 | 2918996 | 2935462 | 97.42% | 1 | 54722 | 110457 | 74 | 50 | 0 | 0 | 2993 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79649 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 408 | 2506695.34
| 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 96.99% | 1 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 100.1% | 1 | 666 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22
| 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 98.08% | 1 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 98.62% | 1 | 5073 | 0 | 13 | 1 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43
| 04 | E4S43 | 44009015201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 290 | 412 | 411 | 107.2% | 1 | 1 | 0 | 0 | 122 | 0 | 2285285 | 50000 | 2235285 | 2435637 | 2385637 | 0 | 0 | 0 | 2385637 | 2385637 | 106.7% | 1 | 0 | 150352 | 64 | 36 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 150352 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 408 | 2071421.19 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 104.5% | 1 | 42636 | 74001 | 9 | 5 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48
| 04 | E4S96 | 43215115201 | 2018-02-02 | QTR3 | 17/18 | 1 | 1 | 157 | 196 | 192 | 97.45% | 1 | 4 | 0 | 0 | 39 | 0 | 424444 | 21202 | 403242 | 440600 | 416334 | 0 | 0 | 0 | 416334 | 416334 | 103.2% | 1 | 0 | 16156 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 16153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16156 | 3 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-04-25 | QTR4 | 18/19 |  | 2019-01-16 | QTR3 | 18/19 | 409 | 433731.62
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 15 | 36 | 82 | 8094 | 12066 | 11691 | 86.67% | 13 | 375 | 54 | 0 | 2384 | 1588 | 337682436 | 1162325 | 336520111 | 359986864 | 358178690 | -797271 | 300000 | -497271 | 357681418 | 347649189 | 93.33% | 14 | -9015257 | 22304427 | 1549 | 583 | 2 | 382 | 3443453 | 1872795 | 170 | 401 | 6351260 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 67 | 609 | 12391935 | 2728255 | 0 | 0 | 66256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73093 | 0 | 0 | 101 | 12322 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | -685448 | 0 | 252 | 1493 | 21766138 | 7032078
| District 04 Totals |  |  |  |  | 35 | 97 | 117 | 13509 | 19329 | 18806 | 94.29% | 33 | 523 | 58 | 0 | 4069 | 1751 | 406516422 | 2288238 | 404228186 | 429668985 | 425737803 | -797271 | 337125 | -460146 | 425277656 | 416539370 | 97.14% | 34 | -7539217 | 23152562 | 2621 | 1023 | 12 | 526 | 4148646 | 2150301 | 279 | 399 | 6764399 | 2519820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 67 | 609 | 12430811 | 2728255 | 0 | 29 | 157561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73093 | 0 | 0 | 101 | 20990 | 8671 | 67 | 0 | 3778 | 0 | 0 | 0 | -85179 | 0 | 0 | -8 | -759623 | 0 | 425 | 1656 | 22868527 | 7407047
| 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 144.9% | 0 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | 112.7% | 0 | -1059964 | 5141650 | 119 | 57 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -230251 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 124.6% | 0 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | 113.3% | 0 | -1114008 | 4323245 | 93 | 58 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -110308 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55
| 05 | T5521 | 23926635201 | 2015-03-25 | QTR3 | 14/15 | 9 | 10 | 1300 | 1440 | 1215 | 82.69% | 1 | 225 | 0 | 0 | 140 | 0 | 37089690 | 150000 | 36939690 | 37921259 | 38186961 | 0 | 775000 | 775000 | 38961961 | 37805706 | 102.3% | 1 | -1060568 | 831569 | 71 | 69 | 0 | 0 | 354866 | 0 | 0 | 0 | 395988 | 5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781799 | 5636 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2018-12-06 | QTR2 | 18/19 | 509 | 30786372.89 | B1 | ACC - NO EXCUSE BONUS
| 05 | T5534 | 42875315201 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 600 | 763 | 765 | 97.83% | 1 | -2 | 2 | 0 | 178 | -15 | 10372492 | 109000 | 10263492 | 10929528 | 10898780 | -15534 | 0 | -15534 | 10883246 | 10869524 | 105.9% | 1 | 280079 | 557037 | 129 | 49 | 0 | 0 | 52612 | 0 | 0 | -26 | 22897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 246070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 321579 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 590 | 11601598.01 | B0 | ACC - LUMP SUM
| 05 | T5548 | 24021625201 | 2016-02-24 | QTR3 | 15/16 | 4 | 8 | 860 | 1076 | 1075 | 103.1% | 1 | 1 | 0 | 0 | 188 | 28 | 26475089 | 150000 | 26325089 | 26427125 | 26734528 | -73350 | 0 | -73350 | 26661178 | 27364124 | 103.9% | 1 | 755744 | -121314 | 132 | 56 | 0 | 0 | -667764 | 0 | 0 | 14 | 365473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 128179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | -174112 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-17 | QTR4 | 18/19 |  | 2019-04-18 | QTR4 | 18/19 | 507 | 27928071.89 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 79.21% | 1 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | 100.3% | 1 | -956254 | 370838 | 56 | 31 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | -130768 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 105.2% | 1 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 101.9% | 1 | 0 | 56481 | 144 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05
| 05 | T5575 | 43505715202 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 290 | 323 | 290 | 88.62% | 1 | 33 | 0 | 0 | 33 | 0 | 3075596 | 50000 | 3025596 | 3075596 | 2961552 | 0 | 0 | 0 | 2961552 | 2961571 | 97.88% | 1 | 19 | 0 | 11 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 13502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40320 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 512 | 4026582.45
| 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 135.2% | 0 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 97.3% | 1 | 6944 | 115263 | 65 | 40 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47
| 05 | T5579 | 43240225201 | 2016-10-26 | QTR2 | 16/17 | 2 | 1 | 340 | 409 | 410 | 100.3% | 1 | -1 | 1 | 0 | 69 | 0 | 4191439 | 50000 | 4141439 | 4197665 | 4536952 | 0 | 0 | 0 | 4536952 | 4533228 | 109.5% | 1 | 2502 | 6226 | 43 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26473 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-05-03 | QTR4 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 4646410
| 05 | T5580 | 43259215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 380 | 517 | 515 | 106.8% | 1 | 2 | 0 | 0 | 109 | 28 | 5833370 | 62000 | 5771370 | 5934096 | 5935419 | 0 | 0 | 0 | 5935419 | 6045029 | 104.7% | 1 | 126318 | 100726 | 78 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-09-13 | QTR1 | 18/19 | 514 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 110% | 1 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 107.7% | 1 | 13997 | 180307 | 159 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 |  | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12
| 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | 110% | 1 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 100.5% | 1 | 40280 | 52747 | 216 | 28 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772
| 05 | T5587 | 43505415201 | 2017-03-29 | QTR3 | 16/17 | 3 | 3 | 380 | 465 | 463 | 99.47% | 1 | 2 | 0 | 0 | 85 | 0 | 3220056 | 50000 | 3170056 | 3323115 | 3265140 | 0 | 0 | 0 | 3265140 | 3262109 | 102.9% | 1 | 0 | 103059 | 63 | 22 | 0 | 0 | 12084 | 0 | 0 | 0 | 87944 | 689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100028 | 689 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 514 | 4249077.7
| 05 | T5598 | 43566115201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 160 | 188 | 188 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 1387781 | 50000 | 1337781 | 1400208 | 1356596 | 0 | 0 | 0 | 1356596 | 1374428 | 102.7% | 1 | 17832 | 12427 | 24 | 4 | 0 | 0 | 1476 | 0 | 0 | 0 | 19164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20640 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 507 | 1627448
| 05 | T5600 | 43691515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 250 | 324 | 324 | 100% | 1 | 0 | 0 | 0 | 74 | 0 | 3294214 | 50000 | 3244214 | 3431595 | 3445345 | 0 | 0 | 0 | 3445345 | 3578158 | 110.3% | 0 | 132813 | 137381 | 30 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-10-23 | QTR2 | 18/19 | 513 | 4280329.25
| 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | 111.3% | 1 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 114% | 0 | 0 | 0 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-07-23 | QTR1 | 18/19 | 514 | 295435
| 05 | T5609 | 43441215201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 240 | 281 | 245 | 85% | 1 | 36 | 0 | 0 | 41 | 0 | 2876725 | 50000 | 2826725 | 2925685 | 2914329 | 0 | 0 | 0 | 2914329 | 2993507 | 105.9% | 1 | 79179 | 48960 | 18 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 72816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71776 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-05-21 | QTR4 | 18/19 |  | 2019-03-29 | QTR3 | 18/19 | 507 | 3026652
| 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 163.1% | 0 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 190.6% | 0 | 1313 | 1131728 | 26 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65
| 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 89.58% | 1 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 106.4% | 1 | 504 | 5429 | 8 | 13 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 515 | 980597
| 05 | T5627 | 43730215201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 45 | 67 | 62 | 88.89% | 1 | 5 | 0 | 0 | 22 | 0 | 140000 | 15000 | 125000 | 140000 | 125000 | 0 | 0 | 0 | 125000 | 125000 | 100% | 1 | 0 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2019-03-22 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 514 | 315759
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 21 | 67 | 112 | 8645 | 11598 | 11108 | 80.95% | 17 | 490 | 34 | 0 | 2206 | 747 | 215587204 | 1543500 | 214043704 | 228714320 | 229682263 | -160976 | 1761200 | 1600224 | 231282487 | 227799353 | 76.19% | 16 | -2733270 | 13053759 | 1521 | 685 | 0 | 12 | 1583171 | 142753 | 0 | 454 | 7659006 | 2795665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 136 | 2146795 | 5853 | 0 | 0 | 38604 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 175105 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 19594 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 0 | 628 | 11892671 | 2987760
| 05 | E5W78 | 23869315201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 850 | 1212 | 1210 | 130.6% | 0 | 2 | 0 | 0 | 100 | 262 | 17605644 | 150000 | 17455644 | 20490569 | 20425101 | 0 | 0 | 0 | 20425101 | 20296799 | 116.3% | 0 | -71813 | 2884924 | 32 | 68 | 0 | 0 | 398745 | 0 | 0 | 262 | 2350231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 2941982 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-05-02 | QTR4 | 18/19 |  | 2018-12-19 | QTR2 | 18/19 | 512 | 19539277.05 | A3:B2:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD
| 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 117.7% | 1 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | 99.18% | 1 | -89138 | 204028 | 174 | 49 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2019-01-16 | QTR3 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 78.16% | 1 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | 101.7% | 1 | -4400 | 21013 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83
| 05 | E5W96 | 42344695201 | 2015-10-13 | QTR2 | 15/16 | 17 | 23 | 650 | 1025 | 1007 | 143.7% | 0 | 18 | 0 | 0 | 73 | 302 | 113653294 | 150000 | 113503294 | 153813717 | 153692841 | 0 | 1000000 | 1000000 | 154692841 | 153331926 | 135.1% | 0 | -1183152 | 40160423 | 24 | 49 | 0 | 122 | 2794353 | 121808 | 0 | 0 | 1064932 | 14649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 180 | 36317114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18933 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 40205231 | 155390 | F474365086 | MIDDLESEX-HERZOG II A JOINT VEN | N/A | N/A | N/A | N/A | 2019-06-19 | QTR4 | 18/19 |  | 2019-01-02 | QTR3 | 18/19 | 507 | 113653294 | B1:B5:B8:B:B:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y51 | 43832115201 | 2017-06-06 | QTR4 | 16/17 | 1 | 2 | 90 | 194 | 193 | 148.9% | 0 | 1 | 0 | 0 | 87 | 17 | 334599 | 16000 | 318599 | 541800 | 538448 | 0 | 0 | 0 | 538448 | 538448 | 169% | 0 | 0 | 207200 | 34 | 25 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-04-19 | QTR4 | 17/18 | 514 | 346552.2
| 05 | E5Y52 | 43632315201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 270 | 476 | 469 | 97.41% | 1 | 7 | 0 | 0 | 206 | 0 | 745547 | 38000 | 707547 | 745547 | 707547 | 0 | 0 | 0 | 707547 | 707547 | 100% | 1 | 0 | 0 | 167 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | QTR3 | 18/19 |  | 2018-12-14 | QTR2 | 18/19 | 513 | 805051.1
| 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 102.9% | 1 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 108.9% | 1 | 1238 | 76790 | 49 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25
| 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | 105.9% | 1 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 98.88% | 1 | 26994 | 156917 | 98 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03
| 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 111.3% | 1 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 101.3% | 1 | 5094 | 12031 | 26 | 24 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7
| 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 118.3% | 1 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 113.7% | 0 | 64762 | 233345 | 64 | 20 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928
| 05 | E5Y74 | 43440615201 | 2018-02-06 | QTR3 | 17/18 | 1 | 1 | 330 | 356 | 276 | 75.76% | 1 | 80 | 0 | 0 | 26 | 0 | 8870873 | 91000 | 8779873 | 8896060 | 9038403 | 0 | 0 | 0 | 9038403 | 9298489 | 105.9% | 1 | 260086 | 25187 | 9 | 17 | 0 | 0 | 79152 | 0 | 0 | 0 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84762 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | QTR4 | 18/19 |  | 2019-01-09 | QTR3 | 18/19 | 509 | 9190822
| 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 105.5% | 1 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 103.2% | 1 | 0 | 0 | 60 | 6 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85
| 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 111.6% | 1 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 104.3% | 1 | 0 | 76090 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 98.67% | 1 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 103.6% | 1 | 13589 | 81060 | 48 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27
| 05 | E5Y95 | 43632515201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 380 | 491 | 481 | 105.3% | 1 | 10 | 0 | 0 | 81 | 30 | 2610610 | 50000 | 2560610 | 2610610 | 2553200 | 0 | 0 | 0 | 2553200 | 2553205 | 99.71% | 1 | 5 | 0 | 25 | 56 | 0 | 30 | 23553 | 0 | 0 | 0 | 4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 29994 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-12-26 | QTR2 | 18/19 | 513 | 3377422
| 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 102.6% | 1 | 9051 | 55693 | 56 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1
| 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 41.82% | 1 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 78.71% | 1 | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922
| 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 65.88% | 1 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 97.44% | 1 | 1173 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4
| 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 98.33% | 1 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 100% | 1 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2
| 05 | E5Z04 | 43927115201 | 2018-02-06 | QTR3 | 17/18 | 1 | 0 | 90 | 102 | 87 | 83.33% | 1 | 15 | 0 | 0 | 12 | 0 | 133664 | 5664 | 128000 | 133664 | 128000 | 0 | 0 | 0 | 128000 | 128000 | 100% | 1 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 515 | 123951
| 05 | E5Z05 | 43566615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 1 | 240 | 283 | 262 | 91.67% | 1 | 21 | 0 | 0 | 42 | 1 | 1687883 | 50000 | 1637883 | 1737883 | 1730756 | 0 | 0 | 0 | 1730756 | 1735963 | 106% | 1 | 5207 | 50000 | 23 | 19 | 0 | 0 | 50180 | 0 | 0 | 1 | 30589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 80769 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-12-18 | QTR2 | 18/19 | 512 | 1825766
| 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 99.55% | 1 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 100.6% | 1 | 0 | 0 | 28 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5Z29 | 43926915201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 997135 | 44635 | 952500 | 997135 | 952500 | 0 | 0 | 0 | 952500 | 952500 | 100% | 1 | 0 | 0 | 11 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-01-29 | QTR3 | 18/19 | 513 | 942335
| 05 | E5Z31 | 44116515201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 90 | 101 | 74 | 70% | 1 | 27 | 0 | 0 | 11 | 0 | 79650 | 5000 | 74650 | 89716 | 84370 | 0 | 0 | 0 | 84370 | 84370 | 113% | 0 | 0 | 10066 | 0 | 11 | 0 | 0 | 10066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10066 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-04-02 | QTR4 | 18/19 |  | 2019-02-12 | QTR3 | 18/19 | 509 | 114395.2
| 05 | E5Z36 | 43987715201 | 2018-01-03 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 128 | 90.83% | 1 | 11 | 0 | 0 | 19 | 0 | 661369 | 44000 | 617369 | 661369 | 614161 | 0 | 50000 | 50000 | 664161 | 615476 | 99.69% | 1 | -48686 | 0 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-07-31 | QTR1 | 18/19 | 513 | 934116.2 | B1 | ACC - NO EXCUSE BONUS
| 05 | E5Z38 | 43734615201 | 2018-10-02 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 98 | 95.56% | 1 | 4 | 0 | 0 | 12 | 0 | 316000 | 22000 | 294000 | 316000 | 294000 | 0 | 0 | 0 | 294000 | 294000 | 100% | 1 | 0 | 0 | 1 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-06-07 | QTR4 | 18/19 |  | 2019-04-16 | QTR4 | 18/19 | 513 | 464322
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 26 | 54 | 63 | 7125 | 9714 | 9179 | 88.46% | 23 | 535 | 10 | 0 | 1752 | 837 | 178304864 | 1265299 | 177039565 | 222559633 | 221707766 | -15840 | 1050000 | 1034160 | 222741926 | 221182706 | 80.77% | 21 | -1009990 | 44254767 | 1044 | 680 | 0 | 226 | 3335860 | 121808 | 28 | 343 | 4069995 | 15527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 268 | 36823387 | 34307 | 0 | 0 | 26561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18933 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 837 | 44292642 | 190575
| District 05 Totals |  |  |  |  | 47 | 121 | 175 | 15770 | 21312 | 20287 | 85.11% | 40 | 1025 | 44 | 0 | 3958 | 1584 | 393892068 | 2808799 | 391083269 | 451273953 | 451390029 | -176816 | 2811200 | 2634384 | 454024413 | 448982059 | 78.72% | 37 | -3743260 | 57308526 | 2565 | 1365 | 0 | 238 | 4919031 | 264561 | 28 | 797 | 11729001 | 2811192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89050 | 0 | 0 | 404 | 38970182 | 40160 | 0 | 0 | 65165 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 183111 | 43490 | 0 | 0 | 662572 | 0 | 0 | 7 | 38527 | 18933 | 0 | 0 | 0 | 0 | 0 | -10 | -471327 | 0 | 28 | 1465 | 56185313 | 3178335
| 06 | T6220 | 24961435201 | 2014-12-03 | QTR2 | 14/15 | 2 | 7 | 1028 | 1363 | 1363 | 113.9% | 1 | 0 | 0 | 0 | 335 | 0 | 58841233 | 150000 | 58691233 | 59057286 | 61015817 | 0 | 0 | 0 | 61015817 | 59202394 | 100.9% | 1 | -1584059 | 216053 | 148 | 44 | 83 | 0 | 486798 | 0 | 15 | 0 | 102307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 61141 | 0 | 0 | 0 | 39915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -586234 | 0 | 143 | 0 | 103925 | 0 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-04-11 | QTR4 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 606 | 54079695.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 71.85% | 1 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | 106.2% | 1 | -258037 | 417799 | 96 | 21 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 |  | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 93.9% | 1 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | 104.3% | 1 | -1419938 | 811402 | 61 | 34 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6348 | 41247935201 | 2016-02-24 | QTR3 | 15/16 | 8 | 4 | 740 | 812 | 711 | 86.35% | 1 | 101 | 0 | 0 | 72 | 0 | 18181314 | 296819 | 17884495 | 17828896 | 17896535 | 0 | 800000 | 800000 | 18696535 | 17985610 | 100.6% | 1 | -663461 | -352418 | 36 | 36 | 0 | 0 | 72263 | 0 | 0 | 0 | 245801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464 | 0 | 0 | 0 | 16570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -502098 | 0 | 0 | 0 | -107072 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-22 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 606 | 18130045.8 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 90.38% | 1 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | 108.1% | 1 | -576452 | 893046 | 79 | 21 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 |  | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6390 | 43094915201 | 2017-02-22 | QTR3 | 16/17 | 5 | 6 | 380 | 464 | 460 | 98.95% | 1 | 4 | 0 | 0 | 84 | 0 | 4429507 | 54813 | 4374694 | 4700034 | 4434960 | 0 | 170000 | 170000 | 4604960 | 4569268 | 104.4% | 1 | -15734 | 270527 | 53 | 31 | 0 | 0 | 41640 | 0 | 0 | 0 | 31665 | 12923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171557 | 16087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244862 | 29011 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 606 | 5093915.35 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 78.57% | 1 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | 103.2% | 1 | -101955 | 0 | 31 | 6 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6412 | 43477815201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 120 | 205 | 205 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 292409 | 16584 | 275825 | 292409 | 300085 | 0 | 0 | 0 | 300085 | 300085.08 | 108.8% | 1 | 4025 | 0 | 70 | 15 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 335871.2
| 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 62.26% | 1 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | 96.92% | 1 | -136676 | 28195 | 44 | 25 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 118.3% | 1 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | 99.23% | 1 | -29328 | 147817 | 57 | 20 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35
| 06 | T6417 | 43476815201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 1228383 | 50000 | 1178383 | 1228383 | 1133929 | 0 | 0 | 0 | 1133929 | 1138502 | 96.62% | 1 | 4573 | 0 | 36 | 10 | 0 | 0 | 9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18218 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-11-19 | QTR2 | 18/19 | 606 | 1258750.05
| 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 97.54% | 1 | 5234 | 51632 | 63 | 25 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89
| 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 103.5% | 1 | 5618 | 63649 | 15 | 17 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55
| 06 | T6428 | 42765125201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 180 | 255 | 255 | 107.8% | 1 | 0 | 0 | 0 | 75 | 0 | 1069876 | 50735 | 1019141 | 1119876 | 1059386 | 0 | 0 | 0 | 1059386 | 1065529 | 104.6% | 1 | 6143 | 50000 | 53 | 8 | 0 | 0 | 2426 | 0 | 0 | 0 | 6065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18103 | 0 | 14 | 0 | 28284 | 30284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 54878 | 30284 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-09-27 | QTR1 | 18/19 | 606 | 1388000.3
| 06 | T6430 | 43476915201 | 2017-12-06 | QTR2 | 17/18 | 3 | 1 | 180 | 272 | 271 | 103.3% | 1 | 1 | 0 | 0 | 92 | 0 | 1525970 | 50890 | 1475080 | 1558102 | 1416657 | 0 | 0 | 0 | 1416657 | 1416845 | 96.05% | 1 | 188 | 32132 | 63 | 22 | 0 | 0 | 33094 | 0 | 0 | 0 | 18847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 62968 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-04-26 | QTR4 | 18/19 |  | 2019-03-04 | QTR3 | 18/19 | 606 | 1552449.05
| 06 | T6431 | 43787315201 | 2018-01-31 | QTR3 | 17/18 | 3 | 0 | 150 | 185 | 185 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 929676 | 42743 | 886933 | 929676 | 827030 | 0 | 0 | 0 | 827030 | 827669 | 93.32% | 1 | 639 | 0 | 24 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-22 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 606 | 881390.05
| 06 | T6432 | 43638515201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 178 | 176 | 98.67% | 1 | 2 | 0 | 0 | 28 | 0 | 627876 | 36563 | 591313 | 627876 | 619690 | 0 | 0 | 0 | 619690 | 620784 | 105% | 1 | 1093 | 0 | 20 | 8 | 0 | 0 | 16282 | 0 | 0 | 0 | 14379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31336 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-01 | QTR3 | 18/19 |  | 2018-10-19 | QTR2 | 18/19 | 606 | 756555.75
| 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 92.57% | 1 | 69 | 0 | 48 | 8 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 |  | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5
| 06 | T6435 | 43635515201 | 2017-12-06 | QTR2 | 17/18 | 3 | 1 | 280 | 300 | 249 | 81.79% | 1 | 51 | 0 | 0 | 20 | 0 | 2585379 | 52040 | 2533339 | 2581654 | 2536459 | 0 | 180000 | 180000 | 2716459 | 2639053 | 104.2% | 1 | -77406 | -3726 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20265 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 606 | 3093043.9 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 99.63% | 1 | 2695 | 0 | 57 | 8 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7
| 06 | T6453 | 44018615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 137 | 98.33% | 1 | 2 | 0 | 0 | 19 | 0 | 242601 | 18959 | 223642 | 242601 | 207429 | 0 | 0 | 0 | 207429 | 207429 | 92.75% | 1 | 0 | 0 | 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 10482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10482 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-03-07 | QTR3 | 18/19 | 606 | 374459.25
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 21 | 75 | 55 | 6867 | 8621 | 7939 | 100% | 21 | 682 | 0 | 0 | 1754 | 0 | 164291890 | 2236340 | 162055550 | 166918000 | 168407525 | 0 | 3830000 | 3830000 | 172237525 | 166962381.08 | 100% | 21 | -4832769 | 2626108 | 1061 | 402 | 189 | 0 | 2137088 | 0 | 36 | 0 | 1234344 | 31694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 734800 | 81415 | 14 | 0 | 149033 | 30284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1088332 | 0 | 291 | 0 | 3214861 | 143394
| 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 97.37% | 1 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | 69.81% | 1 | -593229 | 49068 | 214 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069
| 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 115.8% | 1 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 94.72% | 1 | 30910 | 125102 | 67 | 30 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65
| 06 | E6K27 | 43747515201 | 2017-04-27 | QTR4 | 16/17 | 3 | 0 | 300 | 395 | 392 | 108.3% | 1 | 3 | 0 | 0 | 95 | 0 | 2877777 | 51435 | 2826342 | 2877777 | 2846198 | 0 | 0 | 0 | 2846198 | 2850887 | 100.9% | 1 | 4689 | 0 | 37 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 39030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 39030 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-05-01 | QTR4 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 3018097.85 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 102.9% | 1 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | 0% | 1 | -6008075 | 89950 | 52 | 49 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
| 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 77.23% | 1 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | 100% | 1 | -148006 | 51328 | 26 | 9 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K60 | 42736945201 | 2017-02-23 | QTR3 | 16/17 | 1 | 0 | 300 | 472 | 471 | 106.3% | 1 | 1 | 0 | 0 | 172 | 0 | 1911584 | 50000 | 1861584 | 1911584 | 1907123 | 0 | 0 | 0 | 1907123 | 1909046 | 102.5% | 1 | 1923 | 0 | 120 | 32 | 20 | 0 | 21089 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 26132 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-12-12 | QTR2 | 18/19 | 606 | 1951851.15
| 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 103.2% | 1 | 1161 | 0 | 13 | 7 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65
| 06 | E6K67 | 43634415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 1 | 180 | 200 | 200 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 1835317 | 50000 | 1785317 | 1839190 | 1814980 | 0 | 0 | 0 | 1814980 | 1815065 | 101.7% | 1 | 85 | 3872 | 9 | 11 | 0 | 0 | 17996 | 0 | 0 | 0 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29972 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-08 | QTR4 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 606 | 1635399.65
| 06 | E6K70 | 43274345201 | 2018-02-22 | QTR3 | 17/18 | 1 | 0 | 140 | 233 | 233 | 100% | 1 | 0 | 0 | 0 | 93 | 0 | 974367 | 50000 | 924367 | 974367 | 916327 | 0 | 0 | 0 | 916327 | 917824 | 99.29% | 1 | 1497 | 0 | 68 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-04 | QTR4 | 18/19 |  | 2019-01-09 | QTR3 | 18/19 | 606 | 1053303.5
| 06 | E6K75 | 43083725201 | 2018-02-22 | QTR3 | 17/18 | 2 | 1 | 210 | 238 | 238 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 4131134 | 50000 | 4081134 | 4139407 | 4033935 | 0 | 0 | 0 | 4033935 | 4074967 | 99.85% | 1 | 41032 | 8273 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9924 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-06-14 | QTR4 | 18/19 |  | 2019-04-08 | QTR4 | 18/19 | 606 | 4148174.65
| 06 | E6K88 | 43653815201 | 2018-07-26 | QTR1 | 18/19 | 1 | 0 | 120 | 121 | 99 | 81.67% | 1 | 22 | 0 | 0 | 1 | 0 | 366908 | 17371 | 349537 | 366908 | 341677 | 0 | 0 | 0 | 341677 | 341677 | 97.75% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-05-31 | QTR4 | 18/19 |  | 2019-05-06 | QTR4 | 18/19 | 606 | 362295
| 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 98.89% | 1 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 100% | 1 | 0 | 0 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5
| 06 | E6L12 | 43560115201 | 2017-01-26 | QTR3 | 16/17 | 3 | 6 | 280 | 429 | 429 | 112.5% | 1 | 0 | 0 | 0 | 149 | 0 | 3399874 | 50000 | 3349874 | 3718568 | 3635077 | 0 | 0 | 0 | 3635077 | 3617267 | 108% | 1 | 263 | 318693 | 92 | 22 | 35 | 0 | 25468 | 0 | 0 | 0 | 95370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 308050 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS | N/A | N/A | N/A | N/A | 2019-02-20 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 606 | 3205032.5
| 06 | E6L17 | 42847925201 | 2018-03-29 | QTR3 | 17/18 | 2 | 0 | 140 | 186 | 185 | 99.29% | 1 | 1 | 0 | 0 | 46 | 0 | 573531 | 28824 | 544707 | 573531 | 554401 | 0 | 0 | 0 | 554401 | 555701 | 102% | 1 | 1299 | 0 | 24 | 22 | 0 | 0 | 12435 | 0 | 0 | 0 | 15160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27595 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-10 | QTR4 | 18/19 |  | 2019-01-30 | QTR3 | 18/19 | 606 | 585290.75
| 06 | E6L18 | 43779215201 | 2017-10-26 | QTR2 | 17/18 | 1 | 0 | 150 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 676189 | 34902 | 641287 | 676189 | 658548 | 0 | 0 | 0 | 658548 | 659195 | 102.8% | 1 | 646 | 0 | 57 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-25 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 606 | 719637.75
| 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 98.05% | 1 | 9983 | 0 | 44 | 5 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940
| 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 98.89% | 1 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 93.76% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 17 | 38 | 19 | 3935 | 5317 | 5202 | 100% | 17 | 115 | 0 | 0 | 1368 | 14 | 36957307 | 769089 | 36188218 | 37603595 | 36284240 | 1584 | 180000 | 181584 | 36465824 | 29687139 | 100% | 17 | -6655822 | 646286 | 902 | 345 | 55 | 0 | 118352 | 4391 | 0 | 0 | 256187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 28 | 14 | 396613 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12145 | 0 | 0 | 0 | 0 | 0 | 83 | 14 | 761750 | 4391
| District 06 Totals |  |  |  |  | 38 | 113 | 74 | 10802 | 13938 | 13141 | 100% | 38 | 797 | 0 | 0 | 3122 | 14 | 201249197 | 3005429 | 198243768 | 204521595 | 204691765 | 1584 | 4010000 | 4011584 | 208703349 | 196649520.08 | 100% | 38 | -11488591 | 3272394 | 1963 | 747 | 244 | 0 | 2255440 | 4391 | 36 | 0 | 1490531 | 31694 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 80 | 14 | 1131413 | 81415 | 14 | 0 | 195157 | 30284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12145 | 0 | 0 | 0 | -1088332 | 0 | 374 | 14 | 3976611 | 147785
| 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | 128.1% | 0 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | 107.9% | 1 | -544763 | 2295083 | 191 | 91 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14
| 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 105.4% | 1 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | 97.63% | 1 | -758630 | -138845 | 145 | 61 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST
| 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | 124.5% | 0 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | 99.61% | 1 | -887228 | 212174 | 208 | 57 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 |  | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03
| 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 117.4% | 1 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | 102.6% | 1 | -819849 | 1664895 | 92 | 66 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 0 | -113880 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 119.6% | 1 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 107.2% | 1 | 18982 | 298860 | 167 | 33 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22
| 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 120.7% | 0 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 111% | 0 | 25484 | 558900 | 42 | 15 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS
| 07 | T7387 | 42895415201 | 2016-06-15 | QTR4 | 15/16 | 3 | 8 | 435 | 735 | 733 | 117.2% | 1 | 2 | 0 | 0 | 223 | 77 | 17840000 | 150000 | 17690000 | 18339077 | 18567408 | 0 | 0 | 0 | 18567408 | 18654250 | 105.5% | 1 | 128181 | 499077 | 175 | 48 | 0 | 45 | 212755 | 0 | 0 | 28 | 205993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 461583 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 714 | 19115045.32
| 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 119.4% | 1 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 105% | 1 | 44854 | 30781 | 47 | 20 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5
| 07 | T7392 | 43484115202 | 2017-05-24 | QTR4 | 16/17 | 3 | 1 | 210 | 384 | 331 | 84.76% | 1 | 53 | 0 | 0 | 153 | 21 | 5679793 | 50000 | 5629793 | 5828296 | 5798728 | 0 | 0 | 0 | 5798728 | 5859621 | 104.1% | 1 | 60893 | 148503 | 55 | 98 | 0 | 21 | 148503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 148503 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-10-11 | QTR2 | 18/19 | 796 | 4416000
| 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 99.68% | 1 | 6464 | 0 | 31 | 18 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000
| 07 | T7405 | 43649015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 140 | 161 | 146 | 89.29% | 1 | 15 | 0 | 0 | 21 | 0 | 2235958 | 50000 | 2185958 | 2384716 | 2283562 | 0 | 0 | 0 | 2283562 | 2395779 | 109.6% | 1 | 112217 | 148758 | 18 | 3 | 0 | 0 | 58523 | 0 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 798 | 3540000
| 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 98% | 1 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 97.78% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 799 | 446330
| 07 | T7418 | 43648615201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 100 | 123 | 123 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 935304 | 43500 | 891804 | 935304 | 902861 | 0 | 0 | 0 | 902861 | 903868 | 101.4% | 1 | 1007 | 0 | 5 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-05-14 | QTR4 | 18/19 |  | 2019-03-07 | QTR3 | 18/19 | 799 | 985000
| 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 32.5% | 1 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 82.71% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 14 | 53 | 90 | 5405 | 7762 | 7892 | 78.57% | 11 | -130 | 255 | 0 | 1802 | 555 | 153484016 | 1533315 | 151950702 | 159202204 | 159617252 | -194668 | -400000 | -594668 | 159022584 | 156117644 | 92.86% | 13 | -2612388 | 5718186 | 1180 | 533 | 43 | 106 | 2271342 | 125339 | 14 | 245 | 3225107 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 87043 | 0 | 32 | 0 | 75559 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 409440 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 555 | 6056286 | 947114
| 07 | E7I24 | 25873625201 | 2013-07-31 | QTR1 | 13/14 | 2 | 21 | 1080 | 1678 | 1678 | 111.6% | 1 | 0 | 0 | 0 | 473 | 125 | 71245000 | 150000 | 71095000 | 73940453 | 73581395 | 0 | 0 | 0 | 73581395 | 68828499 | 96.81% | 1 | -4536501 | 2695453 | 369 | 104 | 0 | 86 | 1868254 | 0 | 0 | 0 | 502006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91300 | 0 | 0 | 39 | 29919 | 17848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2491479 | 17848 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 714 | 73473000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 90.54% | 1 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | 103.6% | 1 | -54636 | 367480 | 145 | 40 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000
| 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 90% | 1 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | 94.1% | 1 | -18692 | 37019 | 42 | 23 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200
| 07 | E7L56 | 43243425201 | 2017-03-08 | QTR3 | 16/17 | 1 | 0 | 240 | 264 | 248 | 93.33% | 1 | 16 | 0 | 0 | 24 | 0 | 844020 | 45000 | 799020 | 844020 | 653258 | 0 | 0 | 0 | 653258 | 780683 | 97.71% | 1 | 127425 | 0 | 9 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2018-06-26 | QTR4 | 17/18 | 709 | 930000
| 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 115% | 1 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 113.6% | 0 | 25327 | -19 | 20 | 0 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000
| 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 108.1% | 1 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 109% | 1 | 0 | 78500 | 39 | 28 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM
| 07 | E7L82 | 43269715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 4 | 280 | 389 | 388 | 101.8% | 1 | 1 | 0 | 0 | 103 | 6 | 4654737 | 50000 | 4604737 | 4707294 | 4587650 | 0 | 0 | 0 | 4587650 | 4635460 | 100.7% | 1 | 47810 | 52556 | 86 | 17 | 0 | 6 | 2664 | 0 | 0 | 0 | 2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12827 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-24 | QTR1 | 18/19 | 798 | 5246589.53
| 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 92.5% | 1 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 94.2% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 |  | 2018-09-12 | QTR1 | 18/19 | 796 | 320000
| 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 94% | 1 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 103.9% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 796 | 310000
| 07 | E7L96 | 43966215201 | 2018-03-14 | QTR3 | 17/18 | 1 | 0 | 300 | 329 | 152 | 41% | 1 | 177 | 0 | 0 | 29 | 0 | 1051194 | 50000 | 1001194 | 1051194 | 908881 | 0 | 0 | 0 | 908881 | 908881 | 90.78% | 1 | 0 | 0 | 11 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-02-13 | QTR3 | 18/19 | 796 | 1997000
| 07 | E7L97 | 43589415201 | 2018-04-11 | QTR4 | 17/18 | 2 | 0 | 87 | 156 | 155 | 98.85% | 1 | 1 | 0 | 0 | 69 | 0 | 376868 | 19200 | 357668 | 376868 | 346469 | 0 | 0 | 0 | 346469 | 346469 | 96.87% | 1 | 0 | 0 | 53 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2019-03-04 | QTR3 | 18/19 | 796 | 405835
| 07 | E7M01 | 43070515201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 88 | 136 | 125 | 87.5% | 1 | 11 | 0 | 0 | 48 | 0 | 633485 | 32000 | 601485 | 633485 | 652234 | 0 | 0 | 0 | 652234 | 652234 | 108.4% | 1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 796 | 643100
| 07 | E7M02 | 43386215201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 80 | 74 | 90% | 1 | 6 | 0 | 0 | 20 | 0 | 394077 | 15000 | 379077 | 394077 | 351730 | 0 | 0 | 0 | 351730 | 351730 | 92.79% | 1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-05-16 | QTR4 | 18/19 |  | 2019-04-15 | QTR4 | 18/19 | 796 | 405582.5
| 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 68.33% | 1 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 102.4% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 796 | 225000
| 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | 101.8% | 1 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 98.71% | 1 | 0 | 0 | 155 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GA | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 15 | 19 | 31 | 3514 | 4988 | 4682 | 100% | 15 | 306 | 7 | 0 | 1309 | 165 | 90695120 | 631700 | 90063420 | 93926110 | 92868993 | -19677 | 0 | -19677 | 92849316 | 88149106 | 93.33% | 14 | -4409267 | 3230989 | 992 | 317 | 0 | 101 | 2237287 | 18033 | 0 | 25 | 613687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91300 | 0 | 0 | 39 | 53525 | 17848 | 0 | 0 | 10256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 3007924 | 35881
| District 07 Totals |  |  |  |  | 29 | 72 | 121 | 8919 | 12750 | 12574 | 89.66% | 26 | 176 | 262 | 0 | 3111 | 720 | 244179136 | 2165015 | 242014122 | 253128314 | 252486245 | -214345 | -400000 | -614345 | 251871900 | 244266750 | 93.1% | 27 | -7021655 | 8949175 | 2172 | 850 | 43 | 207 | 4508629 | 143372 | 14 | 270 | 3838794 | 419599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91300 | 0 | 0 | 65 | 140568 | 17848 | 32 | 0 | 85815 | 3741 | 0 | 0 | -1650 | 0 | 0 | 15 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 163 | 411310 | 398436 | 0 | 0 | -40079 | 0 | 0 | 0 | -113880 | 0 | 89 | 720 | 9064210 | 982995
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 105.2% | 1 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | 100% | 1 | -1273624 | 1280759 | 147 | 47 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35903 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 99.36% | 1 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | 97.16% | 1 | -695637 | 0 | 56 | 25 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR
| 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 108.6% | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | 109.2% | 1 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78
| 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 101% | 1 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 99.06% | 1 | 64151 | -44570 | 40 | 28 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104904 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 |  | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64
| 08 | E8Q45 | 43516615201 | 2017-03-28 | QTR3 | 16/17 | 4 | 7 | 245 | 377 | 376 | 107.3% | 1 | 1 | 0 | 0 | 113 | 19 | 10174450 | 99451 | 10074999 | 10442695 | 10222974 | 0 | 0 | 0 | 10222974 | 10331810 | 102.5% | 1 | 132458 | 268245 | 69 | 44 | 0 | 0 | 34793 | 0 | 0 | 12 | 180668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 0 | 0 | 7 | 64962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 282868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 854 | 10340089.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 223 | 85.93% | 1 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 103% | 1 | 2 | 0 | 78 | 29 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07
| 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | 142.8% | 0 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 99.9% | 1 | 0 | 9613 | 32 | 17 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31
| 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 107.1% | 1 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 92.96% | 1 | 306 | 51808 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91
| 08 | E8Q84 | 43990115201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 200 | 314 | 329 | 126.5% | 0 | -15 | 15 | 0 | 90 | 24 | 1282157 | 50000 | 1232157 | 1255314 | 1134931 | -22176 | 0 | -22176 | 1112755 | 1112755 | 90.31% | 1 | 0 | -26844 | 40 | 36 | 0 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24 | -18525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24 | -4749 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2019-06-11 | QTR4 | 18/19 |  | 2019-03-01 | QTR3 | 18/19 | 854 | 1036756.94
| 08 | E8R14 | 43716725201 | 2018-09-11 | QTR1 | 18/19 | 1 | 0 | 65 | 93 | 93 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 823809 | 41824 | 781985 | 823809 | 857863 | 0 | 0 | 0 | 857863 | 857863 | 109.7% | 1 | 0 | 0 | 25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-06-25 | QTR4 | 18/19 |  | 2019-04-25 | QTR4 | 18/19 | 854 | 878142.68
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 10 | 20 | 36 | 3415 | 4524 | 4522 | 80% | 8 | 2 | 41 | 0 | 938 | 171 | 114699646 | 792909 | 113906737 | 117284289 | 116086347 | -88860 | 0 | -88860 | 115997487 | 113940844 | 100% | 10 | -1778452 | 2584642 | 582 | 301 | 0 | 0 | 975058 | 0 | 0 | 50 | 773788 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 80 | 500835 | 0 | 0 | 7 | 74534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 55 | 171 | 2463255 | 178000
| District 08 Totals |  |  |  |  | 10 | 20 | 36 | 3415 | 4524 | 4522 | 80% | 8 | 2 | 41 | 0 | 938 | 171 | 114699646 | 792909 | 113906737 | 117284289 | 116086347 | -88860 | 0 | -88860 | 115997487 | 113940844 | 100% | 10 | -1778452 | 2584642 | 582 | 301 | 0 | 0 | 975058 | 0 | 0 | 50 | 773788 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 80 | 500835 | 0 | 0 | 7 | 74534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74320 | 0 | 0 | 34 | 205525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140807 | 0 | 55 | 171 | 2463255 | 178000
| Statewide Central Let Contracts SubTotal |  |  |  |  | 164 | 395 | 607 | 51070 | 71119 | 69464 | 84.15% | 138 | 1655 | 733 | 0 | 16921 | 3137 | 1245791056 | 11964627 | 1233826432 | 1290308424 | 1290743418 | -804272 | 11354325 | 10550053 | 1301293471 | 1272211402.08 | 92.68% | 152 | -25750030 | 44444005 | 10333 | 4417 | 491 | 711 | 13824181 | 889959 | 841 | 1613 | 22093266 | 4509495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83663 | 0 | 520 | 298 | 5495536 | 1222296 | 52 | 54 | 1353827 | 163076 | 0 | 0 | -2745 | 0 | 0 | 69 | 695721 | 49174 | 0 | 64 | 3214464 | 1766289 | 83 | 213 | 906125 | 615948 | 0 | 0 | -150387 | 0 | 0 | -48 | -2770233 | 0 | 1987 | 2974 | 44743423 | 9216236
| Statewide District Let Contracts SubTotal |  |  |  |  | 137 | 240 | 319 | 39155 | 54718 | 53095 | 89.78% | 123 | 1623 | 202 | 0 | 11688 | 3875 | 1083536931 | 7262084 | 1076274846 | 1166469706 | 1158597181 | -1734672 | 1605000 | -129672 | 1158467508 | 1125497490 | 91.97% | 126 | -30423678 | 82932771 | 6879 | 3581 | 321 | 969 | 10322952 | 2165656 | 201 | 1200 | 14832181 | 2948306 | 0 | 0 | -11004 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 301850 | 0 | 163 | 1193 | 51361393 | 2780410 | 27 | 53 | 223731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209903 | 0 | 0 | 203 | 6214072 | 4950003 | 453 | 160 | 437620 | 18933 | 25 | 0 | 11363 | 0 | 0 | 0 | -1384197 | 0 | 1190 | 3778 | 82452189 | 12863308
| Statewide Totals |  |  |  |  | 301 | 635 | 926 | 90225 | 125837 | 122559 | 86.71% | 261 | 3278 | 935 | 0 | 28609 | 7012 | 2329327987 | 19226711 | 2310101278 | 2456778130 | 2449340599 | -2538944 | 12959325 | 10420381 | 2459760979 | 2397708892.08 | 92.36% | 278 | -56173708 | 127376776 | 17212 | 7998 | 812 | 1680 | 24147133 | 3055615 | 1042 | 2813 | 36925447 | 7457801 | 0 | 0 | -11004 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 385513 | 0 | 683 | 1491 | 56856929 | 4002706 | 79 | 107 | 1577558 | 163076 | 0 | 0 | -2745 | 0 | 0 | 69 | 905624 | 49174 | 0 | 267 | 9428536 | 6716292 | 536 | 373 | 1343745 | 634881 | 25 | 0 | -139024 | 0 | 0 | -48 | -4154430 | 0 | 3177 | 6752 | 127195612 | 22079544

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1K75 | 20121435201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2012-06-21 | 21206552 | 22730499 | 22650387 | 1523947.09 | 0 | 21992288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1P47 | 43771415201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-10-19 | 161810 | 161810 | 145518 | 0 | 0 | 145518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145518 | 145518 | 0 | 119062
1 | E1P92 | 43493715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-06-15 | 6312673 | 6294987 | 6239240 | -17685.8 | 0 | 6432013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6239240 | 6432013 | 192773 | 6900471
1 | E1Q20 | 43979815201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2017-03-16 | 551623 | 557534 | 539909 | 5910.12 | -19008 | 520901 | -19008 | 0 | 0 | 0 | 0 | 0 | -19008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19008 | 520901 | 520901 | 0 | 682344
1 | E1Q21 | 41773349201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-22 | 5353535 | 5368855 | 5313014 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5313014 | 0 | -5313014 | 5530217
1 | E1Q22 | 43854515201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-05-01 | 3614066 | 3616288 | 3562935 | 2222 | 0 | 3562935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562935 | 3562935 | 0 | 5496031
1 | E1Q46 | 43659915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-20 | 2486667 | 2519936 | 2394841 | 33269.19 | 0 | 2475891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 2833103
1 | E1Q64 | 43445715201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-19 | 429966 | 429966 | 399604 | 0 | 0 | 399697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399604 | 399697 | 94 | 450407
1 | E1Q75 | 43659815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-09-21 | 3257627 | 3257627 | 3147613 | 0 | 0 | 3241869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 3831011
1 | E1Q76 | 43494115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 3162332 | 3162332 | 3141539 | 0 | 0 | 3230031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 3398633 | B0 | ACC - LUMP SUM
1 | E1Q77 | 43189515201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-05-19 | 6188743 | 6202025 | 6184286 | 13282.48 | 0 | 6262099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6184286 | 6262099 | 77813 | 7791984 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1R00 | 43798415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 399878 | 414572 | 373225 | 14694.4 | 50000 | 373225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 410605 | B1 | ACC - NO EXCUSE BONUS
1 | E1R01 | 43668415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-01-25 | 367307 | 367307 | 318382 | 0 | 25000 | 318382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 312418 | B1 | ACC - NO EXCUSE BONUS
1 | E1R02 | 44026315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-11-16 | 253030 | 253030 | 240240 | 0 | 0 | 240240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240240 | 240240 | 0 | 210004 | B0 | ACC - LUMP SUM
1 | E1R04 | 44035915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-01-18 | 356611 | 356611 | 333569 | 0 | 0 | 333569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333569 | 333569 | 0 | 390669
1 | E1R09 | 43903015201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-05-17 | 279115 | 279115 | 264760 | 0 | 0 | 264760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264760 | 264760 | 0 | 214242
1 | E1R10 | 44124915201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-04-19 | 103556 | 103556 | 90107 | 0 | 0 | 94096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90107 | 94096 | 3989 | 92976
1 | E1R41 | 43806515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-18 | 902868 | 902868 | 854160 | 0 | 0 | 854160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854160 | 854160 | 0 | 1003082
1 | E1R47 | 43320215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 542243 | 542243 | 514134 | 0 | 0 | 514134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514134 | 514134 | 0 | 573290 | B0 | ACC - LUMP SUM
1 | E1R55 | 43902615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-15 | 402836 | 402836 | 380287 | 0 | 0 | 381602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380287 | 381602 | 1315 | 497103
1 | T1550 | 41304445201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2013-06-19 | 35638696 | 36288093 | 36921189 | 649397.13 | -20000 | 33902534 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 36725854
1 | T1576 | 19690445201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 28940681 | 30877320 | 31050834 | 1936639.27 | 0 | 28268809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050834 | 28268809 | -2782025 | 36280174
1 | T1606 | 19801745201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2015-06-17 | 16630324 | 16297713 | 16277472 | -332611.69 | -39000 | 15990772 | 0 | 0 | 0 | 0 | 0 | -39000 | -39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39000 | 16238472 | 15990772 | -247700 | 16471202 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1621 | 20103245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-05-27 | 74506000 | 75835652 | 75066323 | 1329652.15 | 4948000 | 73395413 | 0 | 0 | 0 | 0 | 0 | -52000 | -52000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 4948000 | 80014323 | 73395413 | -6618910 | 93729882 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
1 | T1623 | 43127815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3845363 | 3770865 | 3824811 | -74498 | 0 | 3725877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824811 | 3725877 | -98934 | 4062053 | B0 | ACC - LUMP SUM
1 | T1627 | 43130615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 17136343 | 19412207 | 20247437 | 2275863.7 | 0 | 20164018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20247437 | 20164018 | -83418 | 14213441 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1642 | 43131115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 6228254 | 7299149 | 7284341 | 1070894.52 | -20000 | 7357502 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 7264341 | 7357502 | 93161 | 5212534 | B0 | ACC - LUMP SUM
1 | T1644 | 20074615201 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 10076029 | 10805932 | 10804382 | 729902.77 | 0 | 10839371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10804382 | 10839371 | 34988 | 8346218
1 | T1646 | 43275515202 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 3883072 | 3988230 | 4003713 | 105157.94 | 0 | 3948636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4003713 | 3948636 | -55078 | 4572143
1 | T1650 | 41454715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 23457366 | 23966925 | 23422232 | 509559.16 | 0 | 24134268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23422232 | 24134268 | 712036 | 27208050 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | T1653 | 43317315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 3821588 | 3892256 | 3742414 | 70667.91 | 0 | 3747080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742414 | 3747080 | 4666 | 2964599
1 | T1660 | 43161915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-09-28 | 2357000 | 2424704 | 2337783 | 67704.15 | 0 | 2292169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337783 | 2292169 | -45614 | 3040685
1 | T1666 | 43289715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 3057226 | 3156754 | 3084177 | 99527.99 | 0 | 3093877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3084177 | 3093877 | 9700 | 3786427
1 | T1672 | 43660015201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 5457714 | 5650306 | 5444515 | 192591.74 | 0 | 5606803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5444515 | 5606803 | 162288 | 5914612
1 | T1673 | 42063335201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-12-07 | 14067161 | 14287522 | 13878587 | 220361.5 | 550000 | 13800963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 550000 | 550000 | 14428587 | 13800963 | -627624 | 16781376 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1674 | 43450515201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 739854 | 739854 | 710515 | 0 | -83952 | 655747 | -83952 | 0 | 0 | 0 | 0 | 0 | -83952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83952 | 626563 | 655747 | 29184 | 559471 | B0 | ACC - LUMP SUM
1 | T1678 | 43492915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 7590540 | 7638810 | 7645659 | 48270.16 | 0 | 7687725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7645659 | 7687725 | 42066 | 9127943
1 | T1683 | 43177215201 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1414597 | 1414597 | 1411808 | 0 | 0 | 1416013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 1198143
1 | T1685 | 44011715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 165758 | 165758 | 159130 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159130 | 159130 | 0 | 163746
1 | T1686 | 43318815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 304735 | 321566 | 321566 | 16831.45 | 0 | 322093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321566 | 322093 | 527 | 339200 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1687 | 41304245201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 28672708 | 28693379 | 27612242 | 20670.98 | 1070000 | 28337974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070000 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | -344268 | 35334897 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1688 | 43498415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 440840 | 440840 | 440840 | 0 | 0 | 440840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440840 | 440840 | 0 | 446099 | B0 | ACC - LUMP SUM
1 | T1690 | 43133915201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 350030 | 358946 | 348056 | 8916.28 | 0 | 348056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348056 | 348056 | 0 | 228657 | B0 | ACC - LUMP SUM
1 | T1692 | 43911115201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 548549 | 548549 | 543483 | 0 | 0 | 543785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543483 | 543785 | 302 | 566923 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1694 | 43513615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 548555 | 542272 | 512417 | -6283.3 | 0 | 513325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512417 | 513325 | 908 | 613009 | B0 | ACC - LUMP SUM
1 | T1698 | 43656715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-10-25 | 3413203 | 3565928 | 3599216 | 152724.34 | 0 | 3691649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 3320587
1 | T1699 | 43698315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-01-31 | 338000 | 345335 | 345335 | 7334.62 | 0 | 345335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345335 | 345335 | 0 | 381548
1 | T1703 | 43668315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 430933 | 430933 | 404140 | 0 | 0 | 404140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404140 | 404140 | 0 | 395408 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1710 | 43795915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-03-28 | 1395501 | 1395501 | 1301640 | 0 | 100000 | 1301762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 1401640 | 1301762 | -99878 | 1196300 | B1 | ACC - NO EXCUSE BONUS
1 | T1715 | 43902715201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-06-13 | 1013907 | 1013907 | 954583 | 0 | 0 | 948729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954583 | 948729 | -5854 | 844330
1 | T1716 | 43506315201 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 172083 | 172083 | 163237 | 0 | 0 | 163237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1723 | 43658515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 1397798 | 1388938 | 1357766 | -8859.51 | 0 | 1357766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357766 | 1357766 | 0 | 1567498 | B0 | ACC - LUMP SUM
1 | T1726 | 44016215201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 253590 | 253590 | 253590 | 0 | 0 | 253590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253590 | 253590 | 0 | 256718 | B0 | ACC - LUMP SUM
1 | T1728 | 43501715201 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2018-07-25 | 141143 | 141143 | 141143 | 0 | 0 | 141143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141143 | 141143 | 0 | 128588 | B0 | ACC - LUMP SUM
1 | T1730 | 43132415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-07-25 | 465432 | 465432 | 465432 | 0 | 0 | 465432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465432 | 465432 | 0 | 319734 | B0 | ACC - LUMP SUM
1 | T1733 | 43536915201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-08-29 | 274000 | 286155 | 286155 | 12154.98 | 0 | 286155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286155 | 286155 | 0 | 295503 | B0 | ACC - LUMP SUM
1 | T1A07 | 19389825201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2014-09-24 | 30690000 | 31355347 | 30709376 | 665347.31 | -599125 | 28122793 | 0 | 0 | 0 | 0 | 0 | -5125 | -5125 | 0 | 0 | 0 | 0 | -594000 | 0 | -594000 | -599125 | 30110251 | 28122793 | -1987458 | 31874470 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1A16 | 43609215201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-29 | 18880004 | 19841188 | 19816523 | 961184.32 | 0 | 19628809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19816523 | 19628809 | -187714 | 24424913
2 | E2R91 | 41650145201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-06-26 | 66725725 | 67223879 | 66965314 | 498153.71 | -795600 | 64716827 | -795600 | 0 | 0 | 0 | 0 | 0 | -795600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -795600 | 66169714 | 64716827 | -1452887 | 83530874 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2T36 | 42442415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-05-13 | 10725121 | 12250426 | 12633691 | 1525305.59 | 0 | 12633279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12633691 | 12633279 | -412 | 11100158
2 | E2T76 | 43055715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-20 | 2328151 | 2328151 | 2166539 | 0 | 0 | 2180708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166539 | 2180708 | 14169 | 2144470
2 | E2U34 | 43025815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-20 | 4266548 | 4515459 | 4762225 | 248911.81 | 0 | 4739499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762225 | 4739499 | -22727 | 3812868
2 | E2U40 | 43015815201 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2016-01-20 | 4367770 | 4673447 | 4944003 | 305677.35 | 0 | 4894801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4944003 | 4894801 | -49202 | 4165393
2 | E2U49 | 43074915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-18 | 5878818 | 6117316 | 6222842 | 238498.65 | 0 | 6229444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6222842 | 6229444 | 6601 | 7361145
2 | E2V29 | 43230815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-21 | 4657688 | 4559112 | 3935337 | -98576.18 | 0 | 3971054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | 3479383
2 | E2V63 | 43860115201 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-05-17 | 1160401 | 1188813 | 1137166 | 28412.16 | 0 | 1137166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 567894
2 | E2V64 | 43075815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 2185756 | 2190082 | 2087115 | 4326.32 | 0 | 2087236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 1534480
2 | E2V65 | 43432315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 3583873 | 3643220 | 3692989 | 59346.81 | 0 | 3723122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3692989 | 3723122 | 30133 | 3819418
2 | E2W07 | 43240515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-15 | 1148442 | 1148442 | 1142933 | 0 | 0 | 1143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 1300556
2 | E2W33 | 42820235201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-05-17 | 3845000 | 3906311 | 3955336 | 61310.99 | 0 | 4008113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3955336 | 4008113 | 52777 | 4211837
2 | E2W74 | 43430315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2821185 | 3316043 | 3357671 | 494858.16 | 0 | 3533274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 2864650
2 | E2W85 | 43219515201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 2078199 | 2078199 | 1988452 | 0 | 0 | 1988452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988452 | 1988452 | 0 | 2082169
2 | E2W86 | 43239515201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2017-11-30 | 567579 | 567579 | 542982 | 0 | 0 | 542982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542982 | 542982 | 0 | 529605
2 | E2W87 | 43616615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 2286714 | 2286714 | 2234139 | 0 | 0 | 2316470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2234139 | 2316470 | 82331 | 2718058
2 | E2W88 | 42849415201 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2017-12-20 | 290000 | 290000 | 255859 | 0 | 0 | 255859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255859 | 255859 | 0 | 444333
2 | E2W93 | 43433815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-01-17 | 594594 | 594594 | 581178 | 0 | 0 | 581178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581178 | 581178 | 0 | 613772
2 | E2W97 | 43859915201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 876044 | 888420 | 862161 | 12376.67 | 0 | 862161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862161 | 862161 | 0 | 586122
2 | E2W98 | 43860015201 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 667932 | 667932 | 646774 | 0 | 0 | 646774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646774 | 646774 | 0 | 484902
2 | T2534 | 21071235201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 18473682 | 19314640 | 18859990 | 840958.13 | 0 | 17612606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 20202367
2 | T2547 | 42975025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1879929 | 1879929 | 1845519 | 0 | -97552 | 1685674 | -97552 | 0 | 0 | 0 | 0 | 0 | -97552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97552 | 1747967 | 1685674 | -62293 | 1922742
2 | T2563 | 20965935201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 45821967 | 48044659 | 49578076 | 2222691.32 | 0 | 48536697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49578076 | 48536697 | -1041379 | 42314170
2 | T2568 | 21002845201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 13869804 | 13966295 | 14129834 | 96491.28 | 0 | 13763782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14129834 | 13763782 | -366052 | 14411194
2 | T2569 | 42870115201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 9199000 | 9915585 | 9871416 | 716584.65 | 0 | 9657046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 9784025
2 | T2596 | 43055615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 4955711 | 4955711 | 4972503 | 0 | 0 | 4810311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 4219707
2 | T2611 | 42880415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 16425368 | 17429243 | 17737903 | 1003874.73 | 0 | 17879661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17737903 | 17879661 | 141758 | 14976803
2 | T2623 | 42747425201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 12006916 | 12006916 | 12019761 | 0 | 0 | 12020496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12019761 | 12020496 | 735 | 12840720
2 | T2624 | 21327285201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2016-06-15 | 11345332 | 11381404 | 10274352 | 36071.98 | 0 | 10274503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 11100491
2 | T2625 | 43091415201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 4913266 | 5029801 | 5053902 | 116534.61 | 0 | 5063705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5053902 | 5063705 | 9803 | 4921245
2 | T2627 | 43035215201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-06-15 | 10750000 | 10970043 | 11054481 | 220043.07 | 0 | 11126382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11054481 | 11126382 | 71901 | 11199747
2 | T2633 | 42890015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-07-27 | 1780206 | 1780206 | 1730267 | 0 | 0 | 1730271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 1648989
2 | T2643 | 43434015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-12-07 | 1483252 | 1483252 | 1482220 | 0 | 0 | 1482220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 1682912
2 | T2647 | 43230915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 9199404 | 9776200 | 8992961 | 576796.12 | 0 | 9273619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8992961 | 9273619 | 280658 | 10410749
2 | T2648 | 43231015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1797592 | 1797592 | 1737333 | 0 | 0 | 1782037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 1880670
2 | T2654 | 43434215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 7099476 | 6953209 | 7172661 | -146267.38 | 0 | 7439601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7172661 | 7439601 | 266940 | 7906422
2 | T2655 | 43231215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 6450313 | 6457361 | 6610843 | 7048 | 0 | 6637036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6610843 | 6637036 | 26193 | 6643070
2 | T2659 | 43432715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | 2042000 | 2042000 | 1988747 | 0 | 0 | 1988836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 2336444
2 | T2665 | 43056015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-05-24 | 5734638 | 5786567 | 5728746 | 51928.64 | 0 | 5836409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5728746 | 5836409 | 107663 | 4851775
2 | T2666 | 43543915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 1101105 | 1107513 | 1035052 | 6407.67 | -17424 | 1017749 | -17424 | 0 | 0 | 0 | 0 | 0 | -17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17424 | 1017628 | 1017749 | 121 | 969731
2 | T2671 | 43601015201 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 928314 | 932800 | 849315 | 4485.92 | 0 | 851029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 1119164
2 | T2674 | 43335915201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-08-30 | 360929 | 360929 | 343649 | 0 | 0 | 343649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343649 | 343649 | 0 | 413832
2 | T2676 | 43617515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 1623696 | 1623696 | 1601844 | 0 | 0 | 1623655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 1682997
2 | T2677 | 43616715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 3488727 | 3488727 | 3422691 | 0 | 0 | 3561473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3422691 | 3561473 | 138781 | 3968191
2 | T2680 | 43616415201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 4259756 | 4352657 | 4324824 | 92901.06 | 0 | 4574214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4324824 | 4574214 | 249390 | 4621256
2 | T2681 | 43499615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1999378 | 1999378 | 1930362 | 0 | 0 | 1930362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1930362 | 1930362 | 0 | 2290723
2 | T2684 | 42857315201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 1816827 | 1864097 | 1920891 | 47270 | 0 | 1923439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920891 | 1923439 | 2549 | 1671760
2 | T2696 | 43616015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-03-28 | 3898972 | 3898972 | 3993251 | 0 | 0 | 4179790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3993251 | 4179790 | 186539 | 4207178
3 | E3K83 | 41506725201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2012-11-20 | 13915054 | 14699375 | 14628947 | 784321.33 | 0 | 14470162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14628947 | 14470162 | -158785 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR
3 | E3L23 | 22066425201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2013-06-06 | 118555712 | 122527138 | 122423398 | 3971426.3 | 0 | 121441548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR
3 | E3P21 | 42358825201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 957789 | 957789 | 938474 | 0 | 0 | 938604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938474 | 938604 | 130 | 1276000
3 | E3P22 | 40619625201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-08-09 | 178163 | 178163 | 116546 | 0 | 0 | 116546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116546 | 116546 | 0 | 270683
3 | E3P35 | 40674235201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-11-09 | 2284367 | 2284367 | 2177088 | 0 | 0 | 2177088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177088 | 2177088 | 0 | 4068631
3 | E3P64 | 40747855201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2017-10-12 | 477560 | 477560 | 464944 | 0 | 0 | 464944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464944 | 464944 | 0 | 607325
3 | E3Q40 | 43375215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 782920 | 809439 | 800466 | 26519.13 | 0 | 800466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800466 | 800466 | 0 | 616285
3 | E3Q60 | 43625715201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 3348662 | 3348662 | 3418381 | 0 | 0 | 3499945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 4130313
3 | E3Q73 | 43966115201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-08-10 | 2101129 | 2228653 | 2084234 | 127524 | 0 | 2094333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 2065000
3 | E3Q80 | 44014815201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-11-09 | 673414 | 676414 | 651186 | 3000 | 0 | 652131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651186 | 652131 | 945 | 670663
3 | E3Q91 | 43626815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-09 | 3258297 | 3274221 | 3353918 | 15923.57 | 0 | 3489125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353918 | 3489125 | 135206 | 4488229
3 | E3Q93 | 44107815201 | F541769861 | FERROVIAL SERVICES INFRASTRUCTURE INC | N/A | N/A | N/A | N/A | 2018-07-12 | 119741 | 119741 | 111083 | 0 | 0 | 111083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111083 | 111083 | 0 | 198799
3 | E3R24 | 43626915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-08 | 696272 | 696272 | 637670 | 0 | 0 | 637670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637670 | 637670 | 0 | 945342
3 | E3R38 | 21869925201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2018-06-14 | 459900 | 473285 | 462354 | 13384.87 | 0 | 462354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462354 | 462354 | 0 | 750711
3 | T3417 | 42282315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 9576952 | 11201952 | 11381048 | 1625000 | 0 | 11259809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11381048 | 11259809 | -121240 | 11869074
3 | T3474 | 41110245201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 13521855 | 14023931 | 14165918 | 502075.52 | 0 | 13122088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14165918 | 13122088 | -1043829 | 12749353
3 | T3481 | 42884615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-10-28 | 2080005 | 2526152 | 2551459 | 446147.09 | 0 | 2552942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 1782971
3 | T3498 | 43178515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 4274307 | 4324307 | 4294029 | 50000 | -8433 | 4353335 | -8433 | 0 | 0 | 0 | 0 | 0 | -8433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8433 | 4285596 | 4353335 | 67739 | 4281516
3 | T3538 | 43357615201 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2015-06-17 | 90288 | 88663 | 74180 | -1624.32 | 0 | 74180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74180 | 74180 | 0 | 110499 | B0 | ACC - LUMP SUM
3 | T3545 | 43047615201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-08-30 | 4421121 | 4223806 | 4448093 | -197314.99 | 0 | 4465980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448093 | 4465980 | 17887 | 5512724
3 | T3559 | 22247625201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-03 | 8545785 | 11162923 | 11805411 | 2617137.98 | -19500 | 11760527 | 0 | 0 | 0 | 0 | 0 | -19500 | -19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19500 | 11785911 | 11760527 | -25384 | 7955703
3 | T3565 | 43046915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 2384550 | 2459882 | 2385269 | 75331.94 | 0 | 2385420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 1900106
3 | T3567 | 43046515201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1966055 | 1981055 | 2001427 | 15000 | -15840 | 2007278 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 1985587 | 2007278 | 21691 | 1970433
3 | T3568 | 41347915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-09-28 | 3041965 | 3062656 | 3259199 | 20690.94 | 0 | 3266655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 3211894
3 | T3573 | 43046615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 4160238 | 4529735 | 4531012 | 369496.09 | 0 | 4552720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4531012 | 4552720 | 21708 | 3945559
3 | T3596 | 43274015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 8173983 | 8193029 | 8770491 | 19046.28 | -4500 | 8814288 | 0 | 0 | 0 | 0 | 0 | -4500 | -4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4500 | 8765991 | 8814288 | 48297 | 8245135
3 | T3615 | 42695015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 8847725 | 8863488 | 9356628 | 15762.61 | 0 | 9479788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 8456773
3 | T3634 | 43256215201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 2317459 | 2317459 | 2243858 | 0 | 0 | 2321931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243858 | 2321931 | 78073 | 2451818
3 | T3636 | 43188325201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 723562 | 725163 | 672253 | 1600.5 | -7800 | 664453 | 0 | 0 | 0 | 0 | 0 | -7800 | -7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7800 | 664453 | 664453 | 0 | 819000
3 | T3638 | 43461115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 5256385 | 5256385 | 5540831 | 0 | -7290 | 5791591 | -7290 | 0 | 0 | 0 | 0 | 0 | -7290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7290 | 5533541 | 5791591 | 258050 | 5826403
3 | T3641 | 43255115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 526927 | 555025 | 528915 | 28098.65 | -14500 | 514415 | 0 | 0 | 0 | 0 | 0 | -14500 | -14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14500 | 514415 | 514415 | 0 | 561927 | B0 | ACC - LUMP SUM
3 | T3644 | 43671915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1719994 | 1712869 | 1658491 | -7124.92 | -28512 | 1643036 | -28512 | 0 | 0 | 0 | 0 | 0 | -28512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28512 | 1629979 | 1643036 | 13058 | 1688041
3 | T3647 | 43626015201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 741004 | 719710 | 672328 | -21294.4 | 0 | 672328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672328 | 672328 | 0 | 1013516 | B0 | ACC - LUMP SUM
3 | T3650 | 43014645201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3298431 | 3312865 | 3444996 | 14433.44 | 0 | 3477423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 4395538
3 | T3651 | 43014665201 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1867503 | 1867503 | 1819486 | 0 | 0 | 1842390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 2105531
3 | T3677 | 43467515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2607729 | 2610160 | 2714487 | 2430.66 | -7200 | 2805120 | 0 | 0 | 0 | 0 | 0 | -7200 | -7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7200 | 2707287 | 2805120 | 97833 | 3422498
4 | E4K92 | 41248925201 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2010-11-30 | 94215000 | 108647581 | 108420972 | 14432580.84 | 0 | 108330265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108420972 | 108330265 | -90707 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4M78 | 41304925201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-03-14 | 50630000 | 51906885 | 51703165 | 1276884.65 | -514238 | 48202697 | -507384 | 0 | 0 | 0 | -6854 | 0 | -514238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514238 | 51188926 | 48202697 | -2986230 | 57557685 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4N44 | 42170765201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-07-24 | 74960000 | 78091122 | 78080272 | 3131121.83 | 500000 | 76382864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 78580272 | 76382864 | -2197408 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P08 | 42170755201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-03-25 | 80437734 | 82797035 | 82818636 | 2359301.26 | -483033 | 78454934 | -283033 | 0 | 0 | 0 | 0 | 0 | -283033 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -483033 | 82335603 | 78454934 | -3880669 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q93 | 43120415201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-04-03 | 9297344 | 9772712 | 9607342 | 475367.61 | 0 | 9522316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9607342 | 9522316 | -85027 | 9241086
4 | E4R63 | 43060215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-05-06 | 9397416 | 9547860 | 9424445 | 150444.28 | 0 | 9517905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9424445 | 9517905 | 93460 | 9034278
4 | E4R83 | 43482915201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-05-03 | 2949000 | 2949000 | 2893000 | 0 | 0 | 2893000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2893000 | 2893000 | 0 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4R89 | 43234915201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2016-09-02 | 4719445 | 4847205 | 4456560 | 127759.9 | 0 | 4483412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4456560 | 4483412 | 26852 | 5266696
4 | E4R95 | 43115625201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | 2267494 | 2267494 | 2078018 | 0 | 0 | 2079393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 2587772
4 | E4S29 | 43059325201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-04-07 | 3060921 | 3171379 | 2918996 | 110457.34 | 0 | 2973718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2918996 | 2973718 | 54722 | 2506695
4 | E4S30 | 43111015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-07 | 419035 | 419035 | 393248 | 0 | 0 | 393914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393248 | 393914 | 666 | 602726
4 | E4S37 | 43716515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-05 | 549000 | 549000 | 512495 | 0 | 0 | 517567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 504683
4 | E4S43 | 44009015201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 2285285 | 2435637 | 2385637 | 150351.5 | 0 | 2385637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385637 | 2385637 | 0 | 2071421 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4S80 | 43609515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 2070318 | 2144319 | 2069570 | 74001.34 | 0 | 2112206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 1656846
4 | E4S96 | 43215115201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-02-02 | 424444 | 440600 | 416334 | 16155.68 | 0 | 416334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416334 | 416334 | 0 | 433732
4 | T4395 | 42936515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 1928000 | 1932802 | 1674394 | 4801.64 | 0 | 1674394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674394 | 1674394 | 0 | 1544788
4 | T4409 | 43019215201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-05-20 | 4789933 | 5042467 | 4996786 | 252534.18 | 0 | 4982280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4996786 | 4982280 | -14505 | 5274241 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | T4422 | 43257425201 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL C | N/A | N/A | N/A | N/A | 2016-12-07 | 4613776 | 4938807 | 4932678 | 325030.9 | 0 | 4925308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4932678 | 4925308 | -7370 | 4236194
4 | T4438 | 42871915201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 8534546 | 8647389 | 8810202 | 112842.77 | 0 | 9007365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8810202 | 9007365 | 197163 | 8438875
4 | T4439 | 42872515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 4580758 | 4651658 | 4514932 | 70899.67 | 0 | 4518968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4514932 | 4518968 | 4036 | 4467828 | B0 | ACC - LUMP SUM
4 | T4445 | 43060315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 8418937 | 8403485 | 8476613 | -15452.13 | 0 | 8727744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8476613 | 8727744 | 251131 | 9837148
4 | T4446 | 43294915201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 2621390 | 2636483 | 2515200 | 15092.34 | 0 | 2504407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515200 | 2504407 | -10793 | 2667038
4 | T4447 | 43510115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 3554036 | 3574289 | 3278614 | 20252.83 | 0 | 3282925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3278614 | 3282925 | 4310 | 3729071
4 | T4450 | 43288325201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 1867168 | 1867168 | 1766523 | 0 | 0 | 1766523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 2440207
4 | T4451 | 43514415201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-24 | 853000 | 853000 | 762484 | 0 | 0 | 764893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762484 | 764893 | 2408 | 757018
4 | T4453 | 43786615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 741586 | 745892 | 706473 | 4306.13 | 0 | 708943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706473 | 708943 | 2470 | 783049
4 | T4455 | 43442715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 14081000 | 14107664 | 13452505 | 26664 | 0 | 14356886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13452505 | 14356886 | 904380 | 15571974
4 | T4456 | 43509515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 621302 | 621302 | 546893 | 0 | 0 | 547874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546893 | 547874 | 981 | 787751
4 | T4457 | 43436015201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-04-26 | 1472242 | 1503409 | 1494780 | 31167.68 | 37125 | 1497583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37125 | 0 | 0 | 0 | 0 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 1576734 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4460 | 43854615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-04-26 | 932300 | 932300 | 856857 | 0 | 0 | 856867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856857 | 856867 | 10 | 782210
4 | T4463 | 43167215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 312963 | 312963 | 288646 | 0 | 0 | 288646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288646 | 288646 | 0 | 301775
4 | T4464 | 23316625201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 3520178 | 3520178 | 3370360 | 0 | 0 | 3385395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370360 | 3385395 | 15035 | 3420061
4 | T4466 | 42871815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 3213996 | 3213990 | 3033800 | -5.76 | 0 | 3135748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3033800 | 3135748 | 101948 | 3457231
4 | T4468 | 43612415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 199400 | 199400 | 179866 | 0 | 0 | 179866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179866 | 179866 | 0 | 207511
4 | T4475 | 43609715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 1977475 | 1977475 | 1900507 | 0 | 0 | 1961150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900507 | 1961150 | 60643 | 2189028
5 | E5W78 | 23869315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 17605644 | 20490569 | 20425101 | 2884924.16 | 0 | 20353288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20425101 | 20353288 | -71813 | 19539277 | A3:B2:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD
5 | E5W79 | 42404045201 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 10721000 | 10925028 | 10844638 | 204027.69 | 0 | 10755499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10844638 | 10755499 | -89138 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
5 | E5W91 | 40441825201 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2015-08-04 | 648777 | 669790 | 669790 | 21012.5 | 0 | 665390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669790 | 665390 | -4400 | 690160
5 | E5W96 | 42344695201 | F474365086 | MIDDLESEX-HERZOG II A JOINT VEN | N/A | N/A | N/A | N/A | 2015-10-13 | 113653294 | 153813717 | 153692841 | 40160422.71 | 1000000 | 153509689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 154692841 | 153509689 | -1183152 | 113653294 | B1:B5:B8:B:B:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Y51 | 43832115201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2017-06-06 | 334599 | 541800 | 538448 | 207200.3 | 0 | 538448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538448 | 538448 | 0 | 346552
5 | E5Y52 | 43632315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 745547 | 745547 | 707547 | 0 | 0 | 707547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707547 | 707547 | 0 | 805051
5 | E5Y56 | 43744715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-02 | 1274655 | 1351445 | 1346112 | 76789.87 | 0 | 1347350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346112 | 1347350 | 1238 | 1669932
5 | E5Y60 | 43474215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-04-04 | 2282739 | 2439656 | 2285278 | 156916.9 | -15840 | 2296432 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 2269438 | 2296432 | 26994 | 2421411
5 | E5Y64 | 41832115201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-09-07 | 1888542 | 1900573 | 1865675 | 12030.51 | 0 | 1870769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865675 | 1870769 | 5094 | 1818886
5 | E5Y73 | 43065115201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 2882444 | 3115789 | 3158796 | 233344.62 | 0 | 3223558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3158796 | 3223558 | 64762 | 3280928
5 | E5Y74 | 43440615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-02-06 | 8870873 | 8896060 | 9038403 | 25186.9 | 0 | 9298489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9038403 | 9298489 | 260086 | 9190822
5 | E5Y75 | 43565515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | 576675 | 576675 | 566351 | 0 | 0 | 566351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566351 | 566351 | 0 | 601123
5 | E5Y77 | 43809615201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-04-26 | 1828183 | 1904273 | 1854273 | 76089.71 | 0 | 1854273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y92 | 43243835201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-02 | 2098740 | 2179800 | 2109348 | 81060.22 | 0 | 2122937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 2861396
5 | E5Y95 | 43632515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 2610610 | 2610610 | 2553200 | 0 | 0 | 2553205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553200 | 2553205 | 5 | 3377422
5 | E5Y96 | 43643415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 3268345 | 3324038 | 3293890 | 55692.68 | 0 | 3302941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 2900877
5 | E5Y98 | 43927215201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2017-09-06 | 162149 | 162149 | 119762 | 0 | 0 | 119762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119762 | 119762 | 0 | 240922
5 | E5Y99 | 43927615201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2017-10-03 | 596733 | 596733 | 546163 | 0 | 0 | 547337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 946415
5 | E5Z03 | 43612615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-05 | 765000 | 765000 | 715000 | 0 | 0 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000 | 715000 | 0 | 1015761
5 | E5Z04 | 43927115201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-06 | 133664 | 133664 | 128000 | 0 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128000 | 128000 | 0 | 123951
5 | E5Z05 | 43566615201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-12-05 | 1687883 | 1737883 | 1730756 | 50000 | 0 | 1735963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730756 | 1735963 | 5207 | 1825766
5 | E5Z15 | 44022215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-09-25 | 1614614 | 1614614 | 1573363 | 0 | 0 | 1573363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5Z29 | 43926915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 997135 | 997135 | 952500 | 0 | 0 | 952500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952500 | 952500 | 0 | 942335
5 | E5Z31 | 44116515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-05 | 79650 | 89716 | 84370 | 10066.28 | 0 | 84370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84370 | 84370 | 0 | 114395
5 | E5Z36 | 43987715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-03 | 661369 | 661369 | 614161 | 0 | 50000 | 615476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 664161 | 615476 | -48686 | 934116 | B1 | ACC - NO EXCUSE BONUS
5 | E5Z38 | 43734615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | 316000 | 316000 | 294000 | 0 | 0 | 294000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294000 | 294000 | 0 | 464322
5 | T5313 | 23953535201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-12-03 | 37587579 | 42729229 | 43288413 | 5141649.91 | 0 | 42228448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43288413 | 42228448 | -1059964 | 38177323 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5431 | 23759225201 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2012-12-05 | 29360536 | 33683790 | 34207580 | 4323245.3 | -3800 | 33089772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 29690235
5 | T5521 | 23926635201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-03-25 | 37089690 | 37921259 | 38186961 | 831569.27 | 775000 | 37901392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775000 | 0 | 0 | 0 | 0 | 0 | 775000 | 775000 | 38961961 | 37901392 | -1060568 | 30786373 | B1 | ACC - NO EXCUSE BONUS
5 | T5534 | 42875315201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-05-25 | 10372492 | 10929528 | 10898780 | 557036.67 | -15534 | 11163325 | -8434 | 0 | 0 | 0 | 0 | -7100 | -15534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15534 | 10883246 | 11163325 | 280079 | 11601598 | B0 | ACC - LUMP SUM
5 | T5548 | 24021625201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 26475089 | 26427125 | 26734528 | -121314.05 | -73350 | 27416922 | 0 | 0 | 0 | 0 | -73350 | 0 | -73350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -73350 | 26661178 | 27416922 | 755744 | 27928072 | B5 | ACC - INCENTIVE/DISINCENTIVE
5 | T5558 | 23842215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 37503443 | 37874281 | 37480698 | 370838.06 | 990000 | 37514444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990000 | 0 | 0 | 0 | 0 | 0 | 990000 | 990000 | 38470698 | 37514444 | -956254 | 47475665 | B5 | ACC - INCENTIVE/DISINCENTIVE
5 | T5564 | 43505515201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-05-25 | 2766468 | 2822949 | 2775862 | 56480.73 | 0 | 2775862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775862 | 2775862 | 0 | 3396278
5 | T5575 | 43505715202 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 3075596 | 3075596 | 2961552 | 0 | 0 | 2961571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961552 | 2961571 | 19 | 4026582
5 | T5578 | 43364815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 3288934 | 3404197 | 3184256 | 115262.79 | -14055 | 3177145 | -14055 | 0 | 0 | 0 | 0 | 0 | -14055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14055 | 3170201 | 3177145 | 6944 | 2864215
5 | T5579 | 43240225201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 4191439 | 4197665 | 4536952 | 6226.08 | 0 | 4539454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4536952 | 4539454 | 2502 | 4646410
5 | T5580 | 43259215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 5833370 | 5934096 | 5935419 | 100725.68 | 0 | 6061737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5935419 | 6061737 | 126318 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
5 | T5584 | 43233315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 1998889 | 2179196 | 2210072 | 180307.03 | 0 | 2224069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210072 | 2224069 | 13997 | 2432081
5 | T5585 | 43441715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-02-22 | 2959615 | 3012362 | 2938715 | 52747.39 | -39354 | 2939642 | -39354 | 0 | 0 | 0 | 0 | 0 | -39354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39354 | 2899361 | 2939642 | 40280 | 3119772
5 | T5587 | 43505415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 3220056 | 3323115 | 3265140 | 103059.29 | 0 | 3265140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3265140 | 3265140 | 0 | 4249078
5 | T5598 | 43566115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-10-25 | 1387781 | 1400208 | 1356596 | 12427.32 | 0 | 1374428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356596 | 1374428 | 17832 | 1627448
5 | T5600 | 43691515201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 3294214 | 3431595 | 3445345 | 137381.15 | 0 | 3578158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445345 | 3578158 | 132813 | 4280329
5 | T5602 | 44113065203 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 287798 | 287798 | 331937 | 0 | -18683 | 313254 | -18683 | 0 | 0 | 0 | 0 | 0 | -18683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18683 | 313254 | 313254 | 0 | 295435
5 | T5609 | 43441215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-28 | 2876725 | 2925685 | 2914329 | 48960.2 | 0 | 2993507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914329 | 2993507 | 79179 | 3026652
5 | T5612 | 44113035201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1243505 | 2375233 | 2283435 | 1131727.86 | 0 | 2284747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1351002
5 | T5620 | 43367315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-10-25 | 633985 | 639413 | 620693 | 5428.5 | 0 | 621196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620693 | 621196 | 504 | 980597
5 | T5627 | 43730215201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 140000 | 140000 | 125000 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 315759
6 | E6J51 | 43652415201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 2558857 | 2607925 | 2393750 | 49068.4 | 0 | 1800521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2393750 | 1800521 | -593229 | 3068069
6 | E6J96 | 42918725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-27 | 3292828 | 3417930 | 3052117 | 125102.18 | 0 | 3083026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052117 | 3083026 | 30910 | 3372731
6 | E6K27 | 43747515201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-04-27 | 2877777 | 2877777 | 2846198 | 0 | 0 | 2850887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846198 | 2850887 | 4689 | 3018098 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K52 | 43029119201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-09-21 | 5967061 | 6057011 | 6008075 | 89950.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
6 | E6K55 | 42527135201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-17 | 4179580 | 4230908 | 4133800 | 51327.99 | 180000 | 4165794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 4313800 | 4165794 | -148006 | 4754512 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6K60 | 42736945201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2017-02-23 | 1911584 | 1911584 | 1907123 | 0 | 0 | 1909046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907123 | 1909046 | 1923 | 1951851
6 | E6K66 | 43826315201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-26 | 632865 | 632865 | 612839 | 0 | 0 | 614000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 767335
6 | E6K67 | 43634415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-01-25 | 1835317 | 1839190 | 1814980 | 3872.44 | 0 | 1815065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814980 | 1815065 | 85 | 1635400
6 | E6K70 | 43274345201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 974367 | 974367 | 916327 | 0 | 0 | 917824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 916327 | 917824 | 1497 | 1053304
6 | E6K75 | 43083725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 4131134 | 4139407 | 4033935 | 8272.94 | 0 | 4074967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4033935 | 4074967 | 41032 | 4148175
6 | E6K88 | 43653815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-26 | 366908 | 366908 | 341677 | 0 | 0 | 341677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341677 | 341677 | 0 | 362295
6 | E6K90 | 43653315201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 1534207 | 1534207 | 1484378 | 0 | 0 | 1484378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 1699725
6 | E6L12 | 43560115201 | F812774010 | LEAD ENGINEERING CONTRACTORS | N/A | N/A | N/A | N/A | 2017-01-26 | 3399874 | 3718568 | 3635077 | 318693.04 | 0 | 3635340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3635077 | 3635340 | 263 | 3205033
6 | E6L17 | 42847925201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-03-29 | 573531 | 573531 | 554401 | 0 | 0 | 555701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554401 | 555701 | 1299 | 585291
6 | E6L18 | 43779215201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-26 | 676189 | 676189 | 658548 | 0 | 0 | 659195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658548 | 659195 | 646 | 719638
6 | E6L19 | 42848725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-27 | 1469702 | 1469702 | 1379063 | 0 | 1584 | 1390630 | 0 | 0 | 0 | 0 | 1584 | 0 | 1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584 | 1380647 | 1390630 | 9983 | 1648940
6 | E6L32 | 44048515201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-11-30 | 575526 | 575526 | 511952 | 0 | 0 | 511952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511952 | 511952 | 0 | 593410
6 | T6220 | 24961435201 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 58841233 | 59057286 | 61015817 | 216053.03 | 0 | 59431758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61015817 | 59431758 | -1584059 | 54079696 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6339 | 41463325201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-05-25 | 8785729 | 9203528 | 9138495 | 417798.88 | 250000 | 9130458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 9388495 | 9130458 | -258037 | 8755698 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6347 | 42559815201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 21462766 | 22274168 | 21904850 | 811402.18 | 1200000 | 21684913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 23104850 | 21684913 | -1419938 | 22401464 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6348 | 41247935201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 18181314 | 17828896 | 17896535 | -352417.51 | 800000 | 18033074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 18696535 | 18033074 | -663461 | 18130046 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6388 | 24961475201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 33267097 | 34160144 | 35419695 | 893046.25 | 960000 | 35803243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 240000 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 37471337 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6390 | 43094915201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 4429507 | 4700034 | 4434960 | 270526.65 | 170000 | 4589226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 4604960 | 4589226 | -15734 | 5093915 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6411 | 43477615201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2356443 | 2356443 | 2361696 | 0 | 120000 | 2379741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 2737736 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6412 | 43477815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 292409 | 292409 | 300085 | 0 | 0 | 304110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300085 | 304110 | 4025 | 335871
6 | T6415 | 43328625201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 2632861 | 2661056 | 2517080 | 28194.94 | 150000 | 2530404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2667080 | 2530404 | -136676 | 3416980 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6416 | 43305925201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1824984 | 1972801 | 1821952 | 147816.92 | 0 | 1792624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821952 | 1792624 | -29328 | 2103857
6 | T6417 | 43476815201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1228383 | 1228383 | 1133929 | 0 | 0 | 1138502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133929 | 1138502 | 4573 | 1258750
6 | T6418 | 43274825201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 1730331 | 1781963 | 1633274 | 51631.51 | 0 | 1638508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633274 | 1638508 | 5234 | 2094391
6 | T6426 | 43477115201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1156048 | 1219697 | 1138589 | 63648.67 | 0 | 1144207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 1339225
6 | T6428 | 42765125201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1069876 | 1119876 | 1059386 | 50000 | 0 | 1065529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059386 | 1065529 | 6143 | 1388000
6 | T6430 | 43476915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 1525970 | 1558102 | 1416657 | 32131.52 | 0 | 1416845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1416657 | 1416845 | 188 | 1552449
6 | T6431 | 43787315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 929676 | 929676 | 827030 | 0 | 0 | 827669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827030 | 827669 | 639 | 881390
6 | T6432 | 43638515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 627876 | 627876 | 619690 | 0 | 0 | 620784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619690 | 620784 | 1093 | 756556
6 | T6434 | 43792115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 328254 | 328254 | 283998 | 0 | 0 | 284067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283998 | 284067 | 69 | 429367
6 | T6435 | 43635515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 2585379 | 2581654 | 2536459 | -3725.56 | 180000 | 2639053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 2716459 | 2639053 | -77406 | 3093044 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6446 | 43631215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 793153 | 793153 | 739919 | 0 | 0 | 742614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 987100
6 | T6453 | 44018615201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 242601 | 242601 | 207429 | 0 | 0 | 207429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207429 | 207429 | 0 | 374459
7 | E7I24 | 25873625201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-07-31 | 71245000 | 73940453 | 73581395 | 2695452.65 | 0 | 69044894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73581395 | 69044894 | -4536501 | 73473000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7L03 | 43656815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-04-13 | 3851530 | 4219010 | 4049852 | 367479.64 | 0 | 3995216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049852 | 3995216 | -54636 | 3798000
7 | E7L45 | 43243515201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-02-08 | 885313 | 922332 | 833142 | 37019.32 | 0 | 814450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833142 | 814450 | -18692 | 1006200
7 | E7L56 | 43243425201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-03-08 | 844020 | 844020 | 653258 | 0 | 0 | 780683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653258 | 780683 | 127425 | 930000
7 | E7L59 | 43070815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2175849 | 2175830 | 2389823 | -19.12 | 0 | 2415150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | 1660000
7 | E7L76 | 43589615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 921000 | 999500 | 949500 | 78500 | 0 | 949500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949500 | 949500 | 0 | 2050000 | B0 | ACC - LUMP SUM
7 | E7L82 | 43269715201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-06-14 | 4654737 | 4707294 | 4587650 | 52556.33 | 0 | 4635460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4587650 | 4635460 | 47810 | 5246590
7 | E7L93 | 43402915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 223800 | 223800 | 202343 | 0 | 0 | 202343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202343 | 202343 | 0 | 320000
7 | E7L94 | 43754915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-02-14 | 226571 | 226571 | 223484 | 0 | 0 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223484 | 223484 | 0 | 310000
7 | E7L96 | 43966215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-03-14 | 1051194 | 1051194 | 908881 | 0 | 0 | 908881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908881 | 908881 | 0 | 1997000
7 | E7L97 | 43589415201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-11 | 376868 | 376868 | 346469 | 0 | 0 | 346469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346469 | 346469 | 0 | 405835
7 | E7M01 | 43070515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 633485 | 633485 | 652234 | 0 | 0 | 652234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652234 | 652234 | 0 | 643100
7 | E7M02 | 43386215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-09 | 394077 | 394077 | 351730 | 0 | 0 | 351730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351730 | 351730 | 0 | 405583
7 | E7M04 | 43755115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-09 | 240676 | 240676 | 236101 | 0 | 0 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236101 | 236101 | 0 | 225000
7 | E7R00 | 43402615201 | F232947721 | GA | N/A | N/A | N/A | N/A | 2016-09-15 | 2971000 | 2971000 | 2903131 | 0 | -19677 | 2883454 | -19677 | 0 | 0 | 0 | 0 | 0 | -19677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19677 | 2883454 | 2883454 | 0 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7292 | 40915415201 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2011-09-28 | 21468350 | 23763433 | 23633808 | 2295082.97 | -79000 | 23010045 | 0 | 0 | 0 | 0 | 0 | -79000 | -79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -79000 | 23554808 | 23010045 | -544763 | 21183448
7 | T7304 | 40795135201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 39444222 | 39305377 | 38780845 | -138845.42 | -18000 | 38004215 | 0 | 0 | 0 | 0 | 0 | -18000 | -18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 38762845 | 38004215 | -758630 | 44767705 | ARRA | AMERICAN RECOVERY AND REINVEST
7 | T7317 | 41886075201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 25488889 | 25701063 | 26223933 | 212174.36 | -97668 | 25239037 | -97668 | 0 | 0 | 0 | 0 | 0 | -97668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97668 | 26126265 | 25239037 | -887228 | 24112219
7 | T7353 | 25699535201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2014-10-29 | 19306771 | 20971666 | 20689510 | 1664894.68 | 0 | 19869660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20689510 | 19869660 | -819849 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7379 | 42906015202 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 7691624 | 7990485 | 8163052 | 298860.33 | 0 | 8182033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8163052 | 8182033 | 18982 | 9262147
7 | T7382 | 43258615202 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 8465944 | 9024845 | 9722176 | 558900.45 | -400000 | 9347660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | 0 | -400000 | -400000 | 9322176 | 9347660 | 25484 | 9653597 | B7 | ACC - A+B/BONUS
7 | T7387 | 42895415201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 17840000 | 18339077 | 18567408 | 499077.06 | 0 | 18695589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18567408 | 18695589 | 128181 | 19115045
7 | T7390 | 43480715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3002052 | 3032833 | 3060237 | 30780.82 | 0 | 3105091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 3538017
7 | T7392 | 43484115202 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 5679793 | 5828296 | 5798728 | 148502.5 | 0 | 5859621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5798728 | 5859621 | 60893 | 4416000
7 | T7394 | 43431715201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1263874 | 1263874 | 1203555 | 0 | 0 | 1210019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 1558000
7 | T7405 | 43649015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-03-28 | 2235958 | 2384716 | 2283562 | 148758 | 0 | 2395779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283562 | 2395779 | 112217 | 3540000
7 | T7416 | 44030615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 471467 | 471467 | 440953 | 0 | 0 | 440953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440953 | 440953 | 0 | 446330
7 | T7418 | 43648615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 935304 | 935304 | 902861 | 0 | 0 | 903868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902861 | 903868 | 1007 | 985000
7 | T7423 | 44269715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-06-13 | 189768 | 189768 | 146624 | 0 | 0 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146624 | 146624 | 0 | 280558
8 | E8N52 | 42935045201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2014-09-30 | 50984589 | 52265348 | 52262125 | 1280759 | -25500 | 50963001 | 0 | 0 | 0 | 0 | 0 | -25500 | -25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25500 | 52236625 | 50963001 | -1273624 | 52446848 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8P06 | 43383015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-23 | 27866200 | 27866200 | 27624496 | 0 | 0 | 26928859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 32476137 | B8 | ACC - DESIGN/BUILD - MAJOR
8 | E8P90 | 43561515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 8378688 | 9424319 | 9142821 | 1045631.46 | 0 | 9136713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9142821 | 9136713 | -6108 | 8835781
8 | E8Q11 | 43715625201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-08-16 | 10316568 | 10271998 | 10116572 | -44570.16 | 0 | 10180724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10116572 | 10180724 | 64151 | 10198096
8 | E8Q45 | 43516615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-03-28 | 10174450 | 10442695 | 10222974 | 268245.15 | 0 | 10355432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10222974 | 10355432 | 132458 | 10340089 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8Q46 | 43717015202 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2017-03-14 | 1120173 | 1120173 | 1139075 | 0 | 0 | 1139077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 885798
8 | E8Q48 | 43560815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-13 | 2193386 | 2202999 | 2182384 | 9613.36 | -41184 | 2141200 | -41184 | 0 | 0 | 0 | 0 | 0 | -41184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41184 | 2141200 | 2141200 | 0 | 2074316
8 | E8Q77 | 43905115201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-09-19 | 1559626 | 1611434 | 1403106 | 51808.48 | 0 | 1403413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 1751318
8 | E8Q84 | 43990115201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 1282157 | 1255314 | 1134931 | -26843.84 | -22176 | 1112755 | -22176 | 0 | 0 | 0 | 0 | 0 | -22176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22176 | 1112755 | 1112755 | 0 | 1036757
8 | E8R14 | 43716725201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-09-11 | 823809 | 823809 | 857863 | 0 | 0 | 857863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857863 | 857863 | 0 | 878143

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1550 | 41304445201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 900 | 1169 | 1203 | -34 | 34 | 0 | 240 | 29 | 35638696 | 150000 | 35488696 | 36288093 | 36921189 | -20000 | 0 | -20000 | 36901189 | 33902534 | -2998654 | 649397 | 175 | 0 | 24 | 291910 | 0 | 0 | 5 | 317359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 657281 | 0 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2017-02-11 | QTR3 | 16/17 | 106 | 36725854.43 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO | 38 | 01co | 1 | 38
01CO | 01 | T1576 | 19690445201 | 2014-04-30 | QTR4 | 13/14 | 2 | 23 | 800 | 1243 | 1197 | 46 | 0 | 0 | 316 | 127 | 28940681 | 150000 | 28790681 | 30877320 | 31050834 | 0 | 0 | 0 | 31050834 | 28027477 | -2782025 | 1936639 | 255 | 0 | 65 | 378653 | 101153 | 0 | 58 | 791125 | 180721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29641 | 5438 | 0 | 2 | 376248 | 114516 | 0 | 0 | 0 | 0 | 0 | 0 | 27196 | 0 | 0 | 2 | 211399 | 94994 | 0 | 0 | 0 | 0 | 0 | 0 | -25911 | 0 | 0 | 127 | 1788352 | 496822 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 118 | 36280173.56 |  |  | 6 | 61 | 0 | 0 | 0 | 0 |  | CO | 20 | 01do | 39 | 58
01CO | 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | -247700 | -332612 | 33 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 28 | 02co | 59 | 86
01CO | 01 | T1621 | 20103245201 | 2015-05-27 | QTR4 | 14/15 | 3 | 20 | 745 | 1019 | 1019 | 0 | 0 | 0 | 266 | 8 | 74506000 | 150000 | 74356000 | 75835652 | 75066323 | -52000 | 5000000 | 4948000 | 80014323 | 73257663 | -6693381 | 1329652 | 198 | 0 | 0 | 790055 | 0 | 0 | 0 | 505557 | 67639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16684 | 0 | 0 | 0 | 76020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357244 | 67639 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 106 | 93729881.67 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 68 | 0 | 0 | 0 | 0 |  | CO | 20 | 02do | 87 | 106
01CO | 01 | T1623 | 43127815201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 200 | 223 | 214 | 9 | 0 | 0 | 23 | 0 | 3845363 | 50000 | 3795363 | 3770865 | 3824811 | 0 | 0 | 0 | 3824811 | 3714876 | -109936 | -74498 | 18 | 0 | 0 | 20701 | 0 | 0 | 0 | 10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42887 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2016-09-15 | QTR1 | 16/17 | 108 | 4062053.36 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 22 | 03co | 107 | 128
01CO | 01 | T1627 | 43130615201 | 2015-09-30 | QTR1 | 15/16 | 3 | 22 | 535 | 678 | 677 | 1 | 0 | 0 | 143 | 0 | 17136343 | 129497 | 17006846 | 19412207 | 20247437 | 0 | 0 | 0 | 20247437 | 20062426 | -83418 | 2275864 | 121 | 0 | 0 | 630929 | 0 | 0 | 0 | 1232145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105785 | 0 | 0 | 0 | 225345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201935 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-18 | QTR4 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 115 | 14213441.36 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 14 | 03do | 129 | 142
01CO | 01 | T1642 | 43131115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 8 | 250 | 592 | 592 | 0 | 0 | 0 | 282 | 60 | 6228254 | 58701 | 6169553 | 7299149 | 7284341 | -20000 | 0 | -20000 | 7264341 | 7348123 | 93161 | 1070895 | 54 | 150 | 0 | 604769 | 0 | 0 | 60 | 349795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 60 | 956072 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-06-27 | QTR4 | 18/19 |  | 2018-07-12 | QTR1 | 18/19 | 115 | 5212533.98 | B0 | ACC - LUMP SUM | 0 | 78 | 0 | 0 | 0 | 0 |  | CO | 20 | 04co | 143 | 162
01CO | 01 | T1644 | 20074615201 | 2016-06-15 | QTR4 | 15/16 | 1 | 8 | 450 | 917 | 907 | 10 | 0 | 0 | 413 | 54 | 10076029 | 85873 | 9990156 | 10805932 | 10804382 | 0 | 0 | 0 | 10804382 | 10809726 | 34988 | 729903 | 69 | 0 | 0 | -8714 | 0 | 117 | 54 | 864500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 54 | 855786 | 0 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-28 | QTR4 | 18/19 |  | 2019-04-05 | QTR4 | 18/19 | 113 | 8346217.75 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO | 15 | 04do | 163 | 177
01CO | 01 | T1646 | 43275515202 | 2016-06-15 | QTR4 | 15/16 | 2 | 2 | 340 | 502 | 656 | -154 | 154 | 0 | 137 | 25 | 3883072 | 50000 | 3833072 | 3988230 | 4003713 | 0 | 0 | 0 | 4003713 | 3893478 | -55078 | 105158 | 100 | 0 | 0 | 0 | 0 | 0 | 6 | 34357 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 34559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 68915 | 1520 | F364806784 | VALIANT POWER SOUTH LLC | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 113 | 4572143.2 |  |  | 25 | 37 | 0 | 0 | 0 | 0 |  | CO | 21 | 05co | 178 | 198
01CO | 01 | T1650 | 41454715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 13 | 575 | 757 | 756 | 1 | 0 | 0 | 181 | 1 | 23457366 | 150000 | 23307366 | 23966925 | 23422232 | 0 | 0 | 0 | 23422232 | 23605126 | 712036 | 509559 | 144 | 0 | 0 | 402 | 0 | 0 | 1 | -14585 | 2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -15279 | 2289 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-02 | QTR4 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 118 | 27208050.39 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 37 | 0 | 0 | 0 | 0 | T | CO | 26 | 05do | 199 | 224
01CO | 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 4666 | 70668 | 64 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO | 21 | 06co | 225 | 245
01CO | 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | -45614 | 67704 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 17 | 06do | 246 | 262
01CO | 01 | T1666 | 43289715201 | 2017-01-25 | QTR3 | 16/17 | 2 | 5 | 160 | 300 | 300 | 0 | 0 | 0 | 69 | 71 | 3057226 | 50000 | 3007226 | 3156754 | 3084177 | 0 | 0 | 0 | 3084177 | 3034815 | 9700 | 99528 | 49 | 0 | 0 | 13307 | 0 | 0 | 69 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 40465 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-03-15 | QTR3 | 17/18 | 118 | 3786427.28 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 14 | 07co | 263 | 276
01CO | 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 162288 | 192592 | 71 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 15 | 07do | 277 | 291
01CO | 01 | T1673 | 42063335201 | 2016-12-07 | QTR2 | 16/17 | 3 | 4 | 485 | 534 | 397 | 137 | 0 | 0 | 58 | 0 | 14067161 | 142723 | 13924438 | 14287522 | 13878587 | 0 | 550000 | 550000 | 14428587 | 13673704 | -627624 | 220362 | 44 | 0 | 0 | 49673 | 0 | 0 | 0 | 43429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93102 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-23 | QTR2 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 118 | 16781375.74 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 292 | 291
01CO | 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710515 | -83952 | 0 | -83952 | 626563 | 655747 | 29184 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-03-05 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 10 | 08do | 292 | 301
01CO | 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 42066 | 48270 | 30 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 527 | 16831 | 2 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1687 | 41304245201 | 2017-07-26 | QTR1 | 17/18 | 1 | 6 | 429 | 484 | 340 | 144 | 0 | 0 | 55 | 0 | 28672708 | 150000 | 28522708 | 28693379 | 27612242 | 0 | 1070000 | 1070000 | 28682242 | 28337974 | -344268 | 20671 | 44 | 0 | 0 | 46688 | 0 | 0 | 0 | 115877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348392 | 307784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79855 | 307784 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-02 | QTR2 | 18/19 | 106 | 35334896.73 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | -431102 | 0 |  | CO
01CO | 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1690 | 43133915201 | 2017-07-26 | QTR1 | 17/18 | 1 | 2 | 75 | 165 | 165 | 0 | 0 | 0 | 25 | 65 | 350030 | 10890 | 339140 | 358946 | 348056 | 0 | 0 | 0 | 348056 | 348056 | 0 | 8916 | 21 | 0 | 47 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 8916 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-06-05 | QTR4 | 18/19 |  | 2018-08-24 | QTR1 | 18/19 | 118 | 228656.73 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1692 | 43911115201 | 2018-04-25 | QTR4 | 17/18 | 2 | 0 | 125 | 145 | 145 | 0 | 0 | 0 | 20 | 0 | 548549 | 0 | 548549 | 548549 | 543483 | 0 | 0 | 0 | 543483 | 543785 | 302 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 113 | 566923.18 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1694 | 43513615201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 125 | 165 | 165 | 0 | 0 | 0 | 40 | 0 | 548555 | 29855 | 518700 | 542272 | 512417 | 0 | 0 | 0 | 512417 | 513325 | 908 | -6283 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6283 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 115 | 613008.64 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1698 | 43656715201 | 2017-10-25 | QTR2 | 17/18 | 2 | 2 | 180 | 213 | 211 | 2 | 0 | 0 | 33 | 0 | 3413203 | 50000 | 3363203 | 3565928 | 3599216 | 0 | 0 | 0 | 3599216 | 3691649 | 92434 | 152724 | 22 | 0 | 0 | 129110 | 0 | 0 | 0 | 27280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156390 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 115 | 3320586.68 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1699 | 43698315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 73 | 84 | 84 | 0 | 0 | 0 | 11 | 0 | 338000 | 0 | 338000 | 345335 | 345335 | 0 | 0 | 0 | 345335 | 345335 | 0 | 7335 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 5286 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-28 | QTR1 | 18/19 | 115 | 381548.27 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1703 | 43668315201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 430933 | 17797 | 413136 | 430933 | 404140 | 0 | 0 | 0 | 404140 | 404140 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-11 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 118 | 395408.14 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1710 | 43795915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 170 | 199 | 166 | 33 | 0 | 0 | 29 | 0 | 1395501 | 50000 | 1345501 | 1395501 | 1301640 | 0 | 100000 | 100000 | 1401640 | 1301762 | -99878 | 0 | 10 | 0 | 0 | 30398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30398 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 118 | 1196299.53 | B1 | ACC - NO EXCUSE BONUS | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1715 | 43902715201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 125 | 162 | 150 | 12 | 0 | 0 | 37 | 0 | 1013907 | 50000 | 963907 | 1013907 | 954583 | 0 | 0 | 0 | 954583 | 948729 | -5854 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2019-05-09 | QTR4 | 18/19 |  | 2019-02-27 | QTR3 | 18/19 | 118 | 844330.15 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1716 | 43506315201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 80 | 90 | 52 | 38 | 0 | 0 | 10 | 0 | 172083 | 8846 | 163237 | 172083 | 163237 | 0 | 0 | 0 | 163237 | 163237 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 108 | 0 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1723 | 43658515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 1 | 120 | 140 | 140 | 0 | 0 | 0 | 20 | 0 | 1397798 | 50000 | 1347798 | 1388938 | 1357766 | 0 | 0 | 0 | 1357766 | 1357766 | 0 | -8860 | 4 | 0 | 0 | -1941 | 0 | 0 | 0 | -4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8860 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-05-28 | QTR4 | 18/19 |  | 2019-04-06 | QTR4 | 18/19 | 113 | 1567497.74 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1726 | 44016215201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 75 | 81 | 80 | 1 | 0 | 0 | 6 | 0 | 253590 | 0 | 253590 | 253590 | 253590 | 0 | 0 | 0 | 253590 | 253590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-12-15 | QTR2 | 18/19 | 113 | 256717.81 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1728 | 43501715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 75 | 76 | 25 | 51 | 0 | 0 | 1 | 0 | 141143 | 0 | 141143 | 141143 | 141143 | 0 | 0 | 0 | 141143 | 141143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 118 | 128587.62 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1730 | 43132415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 85 | 103 | 100 | 3 | 0 | 0 | 18 | 0 | 465432 | 0 | 465432 | 465432 | 465432 | 0 | 0 | 0 | 465432 | 465432 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 319733.9 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1733 | 43536915201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 80 | 100 | 100 | 0 | 0 | 0 | 20 | 0 | 274000 | 0 | 274000 | 286155 | 286155 | 0 | 0 | 0 | 286155 | 286155 | 0 | 12155 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-06-24 | QTR4 | 18/19 |  | 2019-03-08 | QTR3 | 18/19 | 115 | 295503.06 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A07 | 19389825201 | 2014-09-24 | QTR1 | 14/15 | 7 | 14 | 760 | 1004 | 1103 | -99 | 99 | 0 | 211 | 33 | 30690000 | 150000 | 30540000 | 31355347 | 30709376 | -5125 | -594000 | -599125 | 30110251 | 28065304 | -1987458 | 665347 | 175 | 0 | 10 | 397459 | 0 | 0 | 23 | 199227 | 35217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 615756 | 35217 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-01-18 | QTR3 | 17/18 | 115 | 31874469.67 | B5 | ACC - INCENTIVE/DISINCENTIVE | 11 | 36 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A16 | 43609215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 9 | 600 | 771 | 767 | 4 | 0 | 0 | 157 | 14 | 18880004 | 150000 | 18730004 | 19841188 | 19816523 | 0 | 0 | 0 | 19816523 | 19628809 | -187714 | 961184 | 106 | 0 | 4 | 154148 | 5054 | 0 | 10 | 279737 | 116375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348400 | 347865 | 0 | 0 | 170559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804 | 48804 | 0 | 0 | 0 | 0 | 0 | 14 | 1001647 | 518098 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2017-12-08 | QTR2 | 17/18 | 113 | 24424912.84 |  |  | 14 | 51 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1K75 | 20121435201 | 2012-06-21 | QTR4 | 11/12 | 1 | 11 | 881 | 1567 | 1561 | 6 | 0 | 0 | 526 | 160 | 21206552 | 150000 | 21056552 | 22730499 | 22650387 | 0 | 0 | 0 | 22650387 | 21992288 | -658099 | 1523947 | 48 | 0 | 0 | 35273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987225 | 0 | 440 | 160 | 416817 | 0 | 0 | 0 | 0 | 0 | 440 | 160 | 1559220 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2017-02-15 | QTR3 | 16/17 | 108 | 1678072 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P47 | 43771415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 80 | 135 | 135 | 0 | 0 | 0 | 52 | 3 | 161810 | 5962 | 155848 | 161810 | 145518 | 0 | 0 | 0 | 145518 | 145518 | 0 | 0 | 16 | 33 | 0 | 0 | 0 | 0 | 3 | 5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 3 | 5677 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 115 | 119062.09 |  |  | 3 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P92 | 43493715201 | 2017-06-15 | QTR4 | 16/17 | 1 | 3 | 445 | 534 | 472 | 62 | 0 | 0 | 89 | 0 | 6312673 | 75306 | 6237367 | 6294987 | 6239240 | 0 | 0 | 0 | 6239240 | 6432013 | 192773 | -17686 | 45 | 0 | 0 | 32556 | 0 | 0 | 0 | 120500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14315 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-05-28 | QTR4 | 18/19 |  | 2019-01-30 | QTR3 | 18/19 | 108 | 6900471.09 |  |  | 0 | 44 | 0 | 0 | -138741 | 0 |  | DO
01DO | 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 0 | 5910 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q21 | 41773349201 | 2017-03-22 | QTR3 | 16/17 | 1 | 1 | 500 | 539 | 539 | 0 | 0 | 0 | 39 | 0 | 5353535 | 55841 | 5297694 | 5368855 | 5313014 | 0 | 0 | 0 | 5313014 | 0 | -5313014 | 15320 | 6 | 0 | 0 | 15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15320 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-03-08 | QTR3 | 18/19 |  | 2018-11-04 | QTR2 | 18/19 | 113 | 5530217.16 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q22 | 43854515201 | 2017-05-01 | QTR4 | 16/17 | 1 | 1 | 480 | 537 | 537 | 0 | 0 | 0 | 57 | 0 | 3614066 | 54963 | 3559103 | 3616288 | 3562935 | 0 | 0 | 0 | 3562935 | 3562935 | 0 | 2222 | 28 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 108 | 5496030.8 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 33269 | 18 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q64 | 43445715201 | 2018-04-19 | QTR4 | 17/18 | 2 | 0 | 140 | 179 | 170 | 9 | 0 | 0 | 39 | 0 | 429966 | 21462 | 408504 | 429966 | 399604 | 0 | 0 | 0 | 399604 | 399697 | 94 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2019-01-15 | QTR3 | 18/19 | 113 | 450406.6 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q75 | 43659815201 | 2017-09-21 | QTR1 | 17/18 | 1 | 0 | 200 | 216 | 214 | 2 | 0 | 0 | 16 | 0 | 3257627 | 50000 | 3207627 | 3257627 | 3147613 | 0 | 0 | 0 | 3147613 | 3241869 | 94256 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 118 | 3831010.86 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q77 | 43189515201 | 2017-05-19 | QTR4 | 16/17 | 1 | 1 | 475 | 617 | 617 | 0 | 0 | 0 | 139 | 3 | 6188743 | 0 | 6188743 | 6202025 | 6184286 | 0 | 0 | 0 | 6184286 | 6262099 | 77813 | 13282 | 66 | 0 | 3 | 13282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 3 | 13282 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-05-13 | QTR4 | 18/19 |  | 2019-03-28 | QTR3 | 18/19 | 113 | 7791984 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 14694 | 8 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R09 | 43903015201 | 2018-05-17 | QTR4 | 17/18 | 1 | 0 | 90 | 93 | 78 | 15 | 0 | 0 | 3 | 0 | 279115 | 12207 | 266908 | 279115 | 264760 | 0 | 0 | 0 | 264760 | 264760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-07 | QTR2 | 18/19 | 118 | 214242.2 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R10 | 44124915201 | 2018-04-19 | QTR4 | 17/18 | 1 | 0 | 75 | 79 | 45 | 34 | 0 | 0 | 4 | 0 | 103556 | 3909 | 99647 | 103556 | 90107 | 0 | 0 | 0 | 90107 | 90107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 115 | 92975.88 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R41 | 43806515201 | 2018-10-18 | QTR2 | 18/19 | 1 | 0 | 80 | 87 | 76 | 11 | 0 | 0 | 7 | 0 | 902868 | 50000 | 852868 | 902868 | 854160 | 0 | 0 | 0 | 854160 | 854160 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-03-27 | QTR3 | 18/19 | 118 | 1003081.6 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R47 | 43320215201 | 2018-08-16 | QTR1 | 18/19 | 1 | 0 | 95 | 118 | 118 | 0 | 0 | 0 | 23 | 0 | 542243 | 28109 | 514134 | 542243 | 514134 | 0 | 0 | 0 | 514134 | 514134 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-29 | QTR3 | 18/19 |  | 2019-02-28 | QTR3 | 18/19 | 108 | 573290.03 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R55 | 43902615201 | 2018-03-15 | QTR3 | 17/18 | 1 | 0 | 150 | 159 | 142 | 17 | 0 | 0 | 9 | 0 | 402836 | 19980 | 382856 | 402836 | 380287 | 0 | 0 | 0 | 380287 | 381602 | 1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-25 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 118 | 497103.38 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2534 | 21071235201 | 2014-06-18 | QTR4 | 13/14 | 2 | 10 | 720 | 990 | 975 | 15 | 0 | 0 | 169 | 101 | 18473682 | 334531 | 18139151 | 19314640 | 18859990 | 0 | 0 | 0 | 18859990 | 17612606 | -1247384 | 840958 | 89 | 0 | 14 | 498373 | 16704 | 0 | 36 | 337859 | 4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29658 | 14665 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 149956 | 149956 | 0 | 0 | 0 | 0 | 0 | 101 | 1039831 | 185700 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2017-05-03 | QTR4 | 16/17 | 208 | 20202366.73 |  |  | 33 | 80 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | -62293 | 0 | 12 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2563 | 20965935201 | 2015-04-29 | QTR4 | 14/15 | 2 | 15 | 850 | 1201 | 1201 | 0 | 0 | 0 | 284 | 67 | 45821967 | 150000 | 45671967 | 48044659 | 49578076 | 0 | 0 | 0 | 49578076 | 48432413 | -1041379 | 2222691 | 206 | 0 | 26 | 1231947 | 142755 | 0 | 26 | 292304 | 7606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 471110 | 30796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 2228407 | 181157 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-06-13 | QTR4 | 18/19 |  | 2018-10-18 | QTR2 | 18/19 | 208 | 42314170.17 |  |  | 32 | 78 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2568 | 21002845201 | 2015-04-29 | QTR4 | 14/15 | 1 | 5 | 730 | 928 | 928 | 0 | 0 | 0 | 134 | 64 | 13869804 | 142439 | 13727364 | 13966295 | 14129834 | 0 | 0 | 0 | 14129834 | 13744279 | -366052 | 96491 | 80 | 0 | 0 | 6790 | 0 | 0 | 20 | 135774 | 14065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 44 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 160878 | 14065 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-02-12 | QTR3 | 17/18 | 216 | 14411193.97 |  |  | 20 | 54 | 0 | 0 | -37511 | 0 |  | CO
02CO | 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 716585 | 179 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26 |  |  | 44 | 57 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2596 | 43055615201 | 2015-08-26 | QTR1 | 15/16 | 2 | 0 | 180 | 223 | 223 | 0 | 0 | 0 | 40 | 3 | 4955711 | 75000 | 4880711 | 4955711 | 4972503 | 0 | 0 | 0 | 4972503 | 4810311 | -162193 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 22282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | 0 | 2 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55710 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2016-09-10 | QTR1 | 16/17 | 209 | 4219707.36 |  |  | 3 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2611 | 42880415201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 380 | 734 | 731 | 3 | 0 | 0 | 277 | 77 | 16425368 | 150000 | 16275368 | 17429243 | 17737903 | 0 | 0 | 0 | 17737903 | 17843990 | 106088 | 1003875 | 186 | 0 | 7 | 102446 | 43792 | 0 | 70 | 961987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 0 | 0 | 11131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13907 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1135125 | 43792 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 214 | 14976802.73 |  |  | 5 | 91 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2623 | 42747425201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 588 | 772 | 772 | 0 | 0 | 0 | 184 | 0 | 12006916 | 125768 | 11881149 | 12006916 | 12019761 | 0 | 0 | 0 | 12019761 | 12020496 | 735 | 0 | 85 | 26 | 0 | 18391 | 0 | 0 | 0 | 17909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 43031 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 214 | 12840720.13 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2624 | 21327285201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 550 | 641 | 639 | 2 | 0 | 0 | 91 | 0 | 11345332 | 108594 | 11236738 | 11381404 | 10274352 | 0 | 0 | 0 | 10274352 | 10274503 | 151 | 36072 | 41 | 0 | 0 | 50261 | 0 | 0 | 0 | 10317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60578 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 209 | 11100490.79 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2625 | 43091415201 | 2016-06-15 | QTR4 | 15/16 | 2 | 4 | 300 | 495 | 475 | 20 | 0 | 0 | 144 | 51 | 4913266 | 96132 | 4817134 | 5029801 | 5053902 | 0 | 0 | 0 | 5053902 | 5063705 | 9803 | 116535 | 75 | 0 | 11 | 42674 | 0 | 0 | 40 | 83572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 155418 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-01-04 | QTR3 | 17/18 | 208 | 4921245.07 |  |  | 13 | 69 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2627 | 43035215201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 624 | 813 | 813 | 0 | 0 | 0 | 161 | 28 | 10750000 | 111180 | 10638820 | 10970043 | 11054481 | 0 | 0 | 0 | 11054481 | 11069654 | 71901 | 220043 | 89 | 0 | 0 | 10095 | 0 | 0 | 28 | 252685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 28 | 266343 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-06-18 | QTR4 | 18/19 |  | 2019-01-22 | QTR3 | 18/19 | 214 | 11199747.1 |  |  | 21 | 63 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2633 | 42890015201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 211 | 208 | 3 | 0 | 0 | 19 | 2 | 1780206 | 50000 | 1730206 | 1780206 | 1730267 | 0 | 0 | 0 | 1730267 | 1730271 | 4 | 0 | 13 | 0 | 2 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15400 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2017-08-22 | QTR1 | 17/18 | 209 | 1648988.83 |  |  | 2 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2647 | 43230915201 | 2017-03-29 | QTR3 | 16/17 | 3 | 5 | 240 | 446 | 445 | 1 | 0 | 0 | 171 | 35 | 9199404 | 103815 | 9095588 | 9776200 | 8992961 | 0 | 0 | 0 | 8992961 | 9273619 | 280658 | 576796 | 100 | 0 | 14 | 45192 | 0 | 0 | 0 | 3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 286737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 621897 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-04-23 | QTR4 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 214 | 10410749.13 |  |  | 14 | 71 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 0 | 28 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2654 | 43434215201 | 2017-02-22 | QTR3 | 16/17 | 1 | 8 | 260 | 451 | 451 | 0 | 0 | 0 | 111 | 80 | 7099476 | 120 | 7099356 | 6953209 | 7172661 | 0 | 0 | 0 | 7172661 | 7430190 | 266940 | -146267 | 71 | 3 | 0 | 25327 | 0 | 10 | 60 | 58126 | 10439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 60 | -155678 | 10439 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-07 | QTR4 | 18/19 |  | 2018-09-28 | QTR1 | 18/19 | 214 | 7906422.14 |  |  | 0 | 24 | 0 | 0 | -247097 | 0 |  | CO
02CO | 02 | T2655 | 43231215201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 160 | 245 | 245 | 0 | 0 | 0 | 68 | 17 | 6450313 | 70313 | 6380000 | 6457361 | 6610843 | 0 | 0 | 0 | 6610843 | 6629988 | 26193 | 7048 | 42 | 0 | 17 | 5448 | 0 | 0 | 0 | 50965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 56414 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-01-11 | QTR3 | 17/18 | 209 | 6643069.91 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2042000 | 50000 | 1992000 | 2042000 | 1988747 | 0 | 0 | 0 | 1988747 | 1988836 | 89 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9099 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-28 | QTR1 | 18/19 | 209 | 2336443.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2665 | 43056015201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 320 | 421 | 403 | 18 | 0 | 0 | 88 | 13 | 5734638 | 75000 | 5659638 | 5786567 | 5728746 | 0 | 0 | 0 | 5728746 | 5836409 | 107663 | 51929 | 37 | 0 | 13 | 93669 | 0 | 0 | 0 | 3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 97246 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-28 | QTR2 | 18/19 |  | 2018-09-29 | QTR1 | 18/19 | 208 | 4851775.2 |  |  | 13 | 51 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2666 | 43543915201 | 2017-04-26 | QTR4 | 16/17 | 2 | 3 | 190 | 310 | 321 | -11 | 11 | 0 | 46 | 74 | 1101105 | 46387 | 1054718 | 1107513 | 1035052 | -17424 | 0 | -17424 | 1017628 | 1015867 | 121 | 6408 | 22 | 0 | 30 | 0 | 0 | 0 | 44 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 9639 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-12-27 | QTR2 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 216 | 969731.32 |  |  | 44 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2671 | 43601015201 | 2017-09-27 | QTR1 | 17/18 | 1 | 1 | 130 | 215 | 215 | 0 | 0 | 0 | 85 | 0 | 928314 | 50000 | 878314 | 932800 | 849315 | 0 | 0 | 0 | 849315 | 851029 | 1714 | 4486 | 74 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 4486 | 0 | F593148142 | A.W.A. CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2018-11-13 | QTR2 | 18/19 |  | 2018-08-10 | QTR1 | 18/19 | 216 | 1119163.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 0 | 16 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74 |  |  | 4 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2677 | 43616715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 200 | 349 | 347 | 2 | 0 | 0 | 119 | 30 | 3488727 | 50000 | 3438727 | 3488727 | 3422691 | 0 | 0 | 0 | 3422691 | 3561473 | 138781 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34025 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-11-15 | QTR2 | 18/19 | 216 | 3968191.21 |  |  | 30 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2680 | 43616415201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 160 | 235 | 235 | 0 | 0 | 0 | 60 | 15 | 4259756 | 53360 | 4206396 | 4352657 | 4324824 | 0 | 0 | 0 | 4324824 | 4574214 | 249390 | 92901 | 37 | 0 | 15 | 21638 | 0 | 0 | 0 | 89529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 111167 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2019-04-10 | QTR4 | 18/19 |  | 2019-01-14 | QTR3 | 18/19 | 209 | 4621256.34 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2681 | 43499615201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 180 | 216 | 216 | 0 | 0 | 0 | 36 | 0 | 1999378 | 50000 | 1949378 | 1999378 | 1930362 | 0 | 0 | 0 | 1930362 | 1930362 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 209 | 2290722.63 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2684 | 42857315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 200 | 265 | 265 | 0 | 0 | 0 | 48 | 17 | 1816827 | 120 | 1816707 | 1864097 | 1920891 | 0 | 0 | 0 | 1920891 | 1923439 | 2549 | 47270 | 40 | 0 | 5 | 23159 | 0 | 0 | 6 | 24111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 47270 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-04-04 | QTR4 | 18/19 |  | 2018-11-17 | QTR2 | 18/19 | 209 | 1671760.06 |  |  | 6 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2696 | 43616015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 0 | 180 | 215 | 180 | 35 | 0 | 0 | 35 | 0 | 3898972 | 50000 | 3848972 | 3898972 | 3993251 | 0 | 0 | 0 | 3993251 | 4179790 | 186539 | 0 | 24 | 0 | 0 | 11579 | 0 | 0 | 0 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15539 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2018-12-03 | QTR2 | 18/19 | 208 | 4207177.88 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R91 | 41650145201 | 2014-06-26 | QTR4 | 13/14 | 3 | 9 | 900 | 1294 | 1372 | -78 | 78 | 0 | 259 | 135 | 66725725 | 270345 | 66455380 | 67223879 | 66965314 | -795600 | 0 | -795600 | 66169714 | 64637295 | -1452887 | 498154 | 134 | 0 | 0 | 13369 | 0 | 0 | 14 | 196815 | 0 | 0 | 0 | -11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72600 | 0 | 0 | 53 | 301636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 370894 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-05-30 | QTR4 | 17/18 | 208 | 83530874.22 | B8 | ACC - DESIGN/BUILD - MAJOR | 14 | 125 | 0 | 0 | -202522 | 0 |  | DO
02DO | 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | -412 | 1525306 | 47 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43 |  |  | 14 | 79 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T76 | 43055715201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 150 | 201 | 201 | 0 | 0 | 0 | 38 | 13 | 2328151 | 50000 | 2278151 | 2328151 | 2166539 | 0 | 0 | 0 | 2166539 | 2180708 | 14169 | 0 | 22 | 0 | 3 | 1972 | 0 | 0 | 10 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 5492 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-26 | QTR4 | 18/19 |  | 2017-03-08 | QTR3 | 16/17 | 209 | 2144470.22 |  |  | 13 | 16 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | -22727 | 248912 | 44 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U40 | 43015815201 | 2016-01-20 | QTR3 | 15/16 | 3 | 2 | 436 | 624 | 622 | 2 | 0 | 0 | 142 | 46 | 4367770 | 50000 | 4317770 | 4673447 | 4944003 | 0 | 0 | 0 | 4944003 | 4845350 | -49202 | 305677 | 76 | 0 | 0 | 3676 | 0 | 0 | 0 | 259099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 262775 | 0 | F411224817 | ABHE & SVOBODA INC. | N/A | N/A | N/A | N/A | 2019-01-09 | QTR3 | 18/19 | 02/17/2018 | 2018-02-17 | QTR3 | 17/18 | 208 | 4165392.78 |  |  | 46 | 66 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U49 | 43074915201 | 2016-05-18 | QTR4 | 15/16 | 3 | 4 | 240 | 409 | 409 | 0 | 0 | 0 | 69 | 100 | 5878818 | 87141 | 5791677 | 6117316 | 6222842 | 0 | 0 | 0 | 6222842 | 6229444 | 6601 | 238499 | 41 | 0 | 100 | 163931 | 148393 | 0 | 0 | 28577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 251507 | 148393 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2017-09-25 | QTR1 | 17/18 | 208 | 7361145.29 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V29 | 43230815201 | 2016-12-21 | QTR2 | 16/17 | 2 | 1 | 300 | 418 | 418 | 0 | 0 | 0 | 116 | 2 | 4657688 | 75000 | 4582688 | 4559112 | 3935337 | 0 | 0 | 0 | 3935337 | 3971054 | 35717 | -98576 | 61 | 0 | 0 | -90408 | 0 | 0 | 2 | 15732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -74676 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 208 | 3479383.26 |  |  | 2 | 55 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 28412 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V64 | 43075815201 | 2017-04-19 | QTR4 | 16/17 | 1 | 1 | 250 | 310 | 309 | 1 | 0 | 0 | 60 | 0 | 2185756 | 50000 | 2135756 | 2190082 | 2087115 | 0 | 0 | 0 | 2087115 | 2087236 | 121 | 4326 | 20 | 0 | 0 | 8915 | 0 | 0 | 0 | 18267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27182 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 208 | 1534480.23 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 30133 | 59347 | 55 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25 |  |  | 12 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W33 | 42820235201 | 2017-05-17 | QTR4 | 16/17 | 2 | 2 | 240 | 372 | 372 | 0 | 0 | 0 | 102 | 30 | 3845000 | 50000 | 3795000 | 3906311 | 3955336 | 0 | 0 | 0 | 3955336 | 3996802 | 52777 | 61311 | 79 | 0 | 13 | 18140 | 0 | 0 | 15 | 45984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 64124 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-04-26 | QTR4 | 18/19 |  | 2018-10-22 | QTR2 | 18/19 | 216 | 4211837.31 |  |  | 28 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W74 | 43430315201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 125 | 273 | 273 | 0 | 0 | 0 | 46 | 102 | 2821185 | 50000 | 2771185 | 3316043 | 3357671 | 0 | 0 | 0 | 3357671 | 3533274 | 175603 | 494858 | 26 | 0 | 102 | 541557 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 543753 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-09-11 | QTR1 | 18/19 | 208 | 2864649.55 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W85 | 43219515201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 300 | 355 | 334 | 21 | 0 | 0 | 55 | 0 | 2078199 | 50000 | 2028199 | 2078199 | 1988452 | 0 | 0 | 0 | 1988452 | 1988452 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-30 | QTR4 | 18/19 |  | 2019-04-05 | QTR4 | 18/19 | 208 | 2082168.77 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W86 | 43239515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 120 | 166 | 166 | 0 | 0 | 0 | 45 | 1 | 567579 | 25415 | 542163 | 567579 | 542982 | 0 | 0 | 0 | 542982 | 542982 | 0 | 0 | 9 | 0 | 1 | 2630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2630 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2018-12-21 | QTR2 | 18/19 | 208 | 529604.74 |  |  | 1 | 36 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W87 | 43616615201 | 2017-11-15 | QTR2 | 17/18 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 2286714 | 50000 | 2236714 | 2286714 | 2234139 | 0 | 0 | 0 | 2234139 | 2312301 | 78162 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-18 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 214 | 2718058.44 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W88 | 42849415201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 138 | 179 | 173 | 6 | 0 | 0 | 41 | 0 | 290000 | 23311 | 266689 | 290000 | 255859 | 0 | 0 | 0 | 255859 | 255859 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473502193 | SOUTHEAST BRIDGE FL CORP | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 208 | 444332.8 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W93 | 43433815201 | 2018-01-17 | QTR3 | 17/18 | 2 | 0 | 160 | 216 | 207 | 9 | 0 | 0 | 56 | 0 | 594594 | 28886 | 565708 | 594594 | 581178 | 0 | 0 | 0 | 581178 | 581178 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-03-15 | QTR3 | 18/19 |  | 2019-02-05 | QTR3 | 18/19 | 208 | 613772.37 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W97 | 43859915201 | 2017-06-14 | QTR4 | 16/17 | 2 | 1 | 180 | 205 | 205 | 0 | 0 | 0 | 15 | 10 | 876044 | 21644 | 854400 | 888420 | 862161 | 0 | 0 | 0 | 862161 | 862161 | 0 | 12377 | 10 | 0 | 10 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6364 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 209 | 586121.97 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W98 | 43860015201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 180 | 198 | 198 | 0 | 0 | 0 | 18 | 0 | 667932 | 19660 | 648272 | 667932 | 646774 | 0 | 0 | 0 | 646774 | 646774 | 0 | 0 | 13 | 0 | 0 | 8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8762 | 0 | F760735258 | OLD WORLD CRAFTSMEN INC. | N/A | N/A | N/A | N/A | 2018-10-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 209 | 484902.31 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3417 | 42282315201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 325 | 885 | 885 | 0 | 0 | 0 | 560 | 0 | 9576952 | 114593 | 9462359 | 11201952 | 11381048 | 0 | 0 | 0 | 11381048 | 11259809 | -121240 | 1625000 | 104 | 0 | 0 | 6816 | 0 | 128 | 0 | 16533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 1672506 | 1625000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2016-03-01 | QTR3 | 15/16 | 321 | 11869074.15 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3474 | 41110245201 | 2014-05-21 | QTR4 | 13/14 | 2 | 9 | 560 | 736 | 736 | 0 | 0 | 0 | 146 | 30 | 13521855 | 125538 | 13396317 | 14023931 | 14165918 | 0 | 0 | 0 | 14165918 | 13122088 | -1043829 | 502076 | 106 | 0 | 0 | 37317 | 0 | 0 | 30 | 516186 | 243604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21575 | 21575 | 0 | 0 | 16549 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 618377 | 265179 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | QTR3 | 18/19 |  | 2016-08-26 | QTR1 | 16/17 | 308 | 12749353.07 |  |  | 9 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3481 | 42884615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 220 | 681 | 681 | 0 | 0 | 0 | 449 | 12 | 2080005 | 50000 | 2030005 | 2526152 | 2551459 | 0 | 0 | 0 | 2551459 | 2552942 | 1482 | 446147 | 119 | 0 | 2 | 6950 | 0 | 201 | 5 | 220944 | 130942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 5 | 226704 | 169489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16052 | 16052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 12 | 470650 | 316483 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-30 | QTR2 | 17/18 | 308 | 1782971.15 |  |  | 2 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3498 | 43178515201 | 2017-01-25 | QTR3 | 16/17 | 4 | 1 | 190 | 384 | 387 | -3 | 3 | 0 | 172 | 22 | 4274307 | 55980 | 4218327 | 4324307 | 4294029 | -8433 | 0 | -8433 | 4285596 | 4353335 | 67739 | 50000 | 112 | 0 | 13 | 40548 | 0 | 15 | 5 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 22 | 46278 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-05-17 | QTR4 | 17/18 | 308 | 4281515.77 |  |  | 22 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 0 | -1624 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3545 | 43047615201 | 2017-08-30 | QTR1 | 17/18 | 2 | 7 | 485 | 542 | 423 | 119 | 0 | 0 | 87 | -30 | 4421121 | 0 | 4421121 | 4223806 | 4448093 | 0 | 0 | 0 | 4448093 | 4444910 | 17887 | -197315 | 53 | 0 | 0 | 25547 | 0 | 0 | 0 | 7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -218385 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-05-09 | QTR4 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 321 | 5512724.17 |  |  | 0 | 34 | 0 | -30 | -306809 | 0 |  | CO
03CO | 03 | T3559 | 22247625201 | 2015-12-03 | QTR2 | 15/16 | 2 | 29 | 305 | 912 | 912 | 0 | 0 | 0 | 539 | 68 | 8545785 | 78727 | 8467058 | 11162923 | 11805411 | -19500 | 0 | -19500 | 11785911 | 11760527 | -25384 | 2617138 | 303 | 65 | 20 | 532799 | 13449 | 90 | 4 | 490052 | 224711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1389507 | 258991 | 0 | 0 | 25215 | 14535 | 0 | 0 | 0 | 0 | 0 | 3 | 178569 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 68 | 2616143 | 517369 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-12-12 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 7955702.94 |  |  | 17 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3565 | 43046915201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 200 | 354 | 353 | 1 | 0 | 0 | 99 | 55 | 2384550 | 0 | 2384550 | 2459882 | 2385269 | 0 | 0 | 0 | 2385269 | 2385420 | 152 | 75332 | 76 | 0 | 7 | 17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 53616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 71308 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-02 | QTR2 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 308 | 1900106.13 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3567 | 43046515201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 165 | 250 | 260 | -10 | 10 | 0 | 70 | 15 | 1966055 | 0 | 1966055 | 1981055 | 2001427 | -15840 | 0 | -15840 | 1985587 | 1998145 | 12558 | 15000 | 64 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15000 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 308 | 1970432.78 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3568 | 41347915201 | 2016-09-28 | QTR1 | 16/17 | 1 | 2 | 245 | 499 | 494 | 5 | 0 | 0 | 247 | 7 | 3041965 | 0 | 3041965 | 3062656 | 3259199 | 0 | 0 | 0 | 3259199 | 3266655 | 7457 | 20691 | 171 | 0 | 7 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 7 | 20691 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-11-15 | QTR2 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 308 | 3211894.24 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3573 | 43046615201 | 2016-12-07 | QTR2 | 16/17 | 1 | 3 | 295 | 612 | 612 | 0 | 0 | 0 | 215 | 102 | 4160238 | 0 | 4160238 | 4529735 | 4531012 | 0 | 0 | 0 | 4531012 | 4552720 | 21708 | 369496 | 107 | 0 | 0 | 0 | 0 | 77 | 102 | 354870 | 121906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 102 | 354870 | 121906 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-04-15 | QTR4 | 18/19 |  | 2018-11-26 | QTR2 | 18/19 | 308 | 3945558.92 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3596 | 43274015201 | 2016-09-28 | QTR1 | 16/17 | 2 | 1 | 229 | 350 | 349 | 1 | 0 | 0 | 121 | 0 | 8173983 | 81645 | 8092338 | 8193029 | 8770491 | -4500 | 0 | -4500 | 8765991 | 8814288 | 48297 | 19046 | 102 | 0 | 0 | 6600 | 0 | 0 | 0 | 5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5882 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2017-12-17 | QTR2 | 17/18 | 314 | 8245135.42 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3615 | 42695015201 | 2017-04-26 | QTR4 | 16/17 | 2 | 2 | 200 | 340 | 339 | 1 | 0 | 0 | 140 | 0 | 8847725 | 83740 | 8763985 | 8863488 | 9356628 | 0 | 0 | 0 | 9356628 | 9479788 | 123160 | 15763 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | -28659 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-06-30 | QTR4 | 17/18 | 314 | 8456773.43 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3634 | 43256215201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 227 | 227 | 0 | 0 | 0 | 77 | 0 | 2317459 | 51202 | 2266257 | 2317459 | 2243858 | 0 | 0 | 0 | 2243858 | 2321931 | 78073 | 0 | 55 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-07 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 308 | 2451817.54 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3636 | 43188325201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 105 | 172 | 169 | 3 | 0 | 0 | 67 | 0 | 723562 | 38779 | 684784 | 725163 | 672253 | -7800 | 0 | -7800 | 664453 | 664453 | 0 | 1601 | 48 | 0 | 0 | 0 | 0 | 1 | 0 | 5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8567 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-03-19 | QTR3 | 17/18 | 308 | 819000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3638 | 43461115201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 210 | 364 | 366 | -2 | 2 | 0 | 133 | 21 | 5256385 | 58075 | 5198309 | 5256385 | 5540831 | -7290 | 0 | -7290 | 5533541 | 5791591 | 258050 | 0 | 90 | 0 | 4 | 18750 | 0 | 0 | 3 | 5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8122 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 32453 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-07 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 308 | 5826402.83 |  |  | 21 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3641 | 43255115201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 60 | 124 | 122 | 2 | 0 | 0 | 61 | 3 | 526927 | 26927 | 500000 | 555025 | 528915 | -14500 | 0 | -14500 | 514415 | 514415 | 0 | 28099 | 33 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 28099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-02 | QTR2 | 18/19 |  | 2018-06-25 | QTR4 | 17/18 | 308 | 561926.52 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3644 | 43671915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 135 | 191 | 209 | -18 | 18 | 0 | 45 | 11 | 1719994 | 50091 | 1669903 | 1712869 | 1658491 | -28512 | 0 | -28512 | 1629979 | 1643036 | 13058 | -7125 | 22 | 0 | 0 | 0 | 0 | 1 | 11 | 32692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 25567 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-12-13 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 308 | 1688040.54 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3647 | 43626015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 65 | 69 | 68 | 1 | 0 | 0 | 4 | 0 | 741004 | 48516 | 692489 | 719710 | 672328 | 0 | 0 | 0 | 672328 | 672328 | 0 | -21294 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20160 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-08-22 | QTR1 | 18/19 | 321 | 1013515.6 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 14433 | 38 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3651 | 43014665201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 165 | 289 | 289 | 0 | 0 | 0 | 112 | 12 | 1867503 | 50000 | 1817503 | 1867503 | 1819486 | 0 | 0 | 0 | 1819486 | 1842390 | 22904 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 11 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 11023 | 0 | F593327393 | NORTH FLORIDA ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-15 | QTR4 | 17/18 | 321 | 2105530.83 |  |  | 12 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3677 | 43467515201 | 2018-02-28 | QTR3 | 17/18 | 2 | 1 | 120 | 159 | 148 | 11 | 0 | 0 | 36 | 3 | 2607729 | 51275 | 2556454 | 2610160 | 2714487 | -7200 | 0 | -7200 | 2707287 | 2805120 | 97833 | 2431 | 26 | 0 | 0 | 0 | 0 | 0 | 2 | 2431 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14394 | 25 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-04 | QTR3 | 18/19 |  | 2018-09-20 | QTR1 | 18/19 | 308 | 3422497.92 |  |  | 1 | 10 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K83 | 41506725201 | 2012-11-20 | QTR2 | 12/13 | 2 | 8 | 599 | 1108 | 1108 | 0 | 0 | 0 | 385 | 124 | 13915054 | 150000 | 13765054 | 14699375 | 14628947 | 0 | 0 | 0 | 14628947 | 14470162 | -158785 | 784321 | 311 | 0 | 5 | 84488 | 0 | 0 | 12 | 93331 | 1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 107 | 683618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 867013 | 1459 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2016-01-26 | QTR3 | 15/16 | 308 | 13915054 | B8 | ACC - DESIGN/BUILD - MAJOR | 8 | 74 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L23 | 22066425201 | 2013-06-06 | QTR4 | 12/13 | 1 | 6 | 1028 | 1387 | 1387 | 0 | 0 | 0 | 359 | 0 | 118555712 | 150000 | 118405712 | 122527138 | 122423398 | 0 | 0 | 0 | 122423398 | 121441548 | -981850 | 3971426 | 99 | 199 | 0 | -822786 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 51488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52909 | 0 | 0 | 0 | 4950000 | 4950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 0 | 4024931 | 4950236 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2017-05-31 | QTR4 | 16/17 | 313 | 118555712 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 61 | 0 | 0 | -216679 | 0 |  | DO
03DO | 03 | E3P21 | 42358825201 | 2017-08-10 | QTR1 | 17/18 | 1 | 0 | 180 | 196 | 186 | 10 | 0 | 0 | 10 | 6 | 957789 | 50000 | 907789 | 957789 | 938474 | 0 | 0 | 0 | 938474 | 938604 | 130 | 0 | 10 | 0 | 6 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15101 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-07-15 | QTR1 | 18/19 | 321 | 1276000 |  |  | 6 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P22 | 40619625201 | 2018-08-09 | QTR1 | 18/19 | 1 | 0 | 120 | 135 | 130 | 5 | 0 | 0 | 15 | 0 | 178163 | 15128 | 163035 | 178163 | 116546 | 0 | 0 | 0 | 116546 | 116546 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2019-06-06 | QTR4 | 18/19 |  | 2019-04-04 | QTR4 | 18/19 | 308 | 270683.27 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P35 | 40674235201 | 2017-11-09 | QTR2 | 17/18 | 1 | 0 | 235 | 281 | 281 | 0 | 0 | 0 | 46 | 0 | 2284367 | 50000 | 2234367 | 2284367 | 2177088 | 0 | 0 | 0 | 2177088 | 2177088 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 321 | 4068630.6 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P64 | 40747855201 | 2017-10-12 | QTR2 | 17/18 | 1 | 0 | 110 | 153 | 153 | 0 | 0 | 0 | 43 | 0 | 477560 | 28231 | 449329 | 477560 | 464944 | 0 | 0 | 0 | 464944 | 464944 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-01-02 | QTR3 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 308 | 607325 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 0 | 26519 | 71 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q60 | 43625715201 | 2017-09-21 | QTR1 | 17/18 | 2 | 1 | 180 | 222 | 207 | 15 | 0 | 0 | 42 | 0 | 3348662 | 50795 | 3297867 | 3348662 | 3418381 | 0 | 0 | 0 | 3418381 | 3499945 | 81564 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20601 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-11-29 | QTR2 | 18/19 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 4130313.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q73 | 43966115201 | 2017-08-10 | QTR1 | 17/18 | 1 | 1 | 150 | 230 | 229 | 1 | 0 | 0 | 80 | 0 | 2101129 | 50000 | 2051129 | 2228653 | 2084234 | 0 | 0 | 0 | 2084234 | 2094333 | 10099 | 127524 | 43 | 0 | 0 | 4988 | 0 | 0 | 0 | 127524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132512 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 314 | 2065000 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q80 | 44014815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 1 | 150 | 182 | 182 | 0 | 0 | 0 | 24 | 8 | 673414 | 31817 | 641597 | 676414 | 651186 | 0 | 0 | 0 | 651186 | 652131 | 945 | 3000 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 8 | 9160 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-08-13 | QTR1 | 18/19 | 321 | 670662.64 |  |  | 8 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q91 | 43626815201 | 2017-11-09 | QTR2 | 17/18 | 1 | 3 | 180 | 246 | 244 | 2 | 0 | 0 | 64 | 2 | 3258297 | 50000 | 3208297 | 3274221 | 3353918 | 0 | 0 | 0 | 3353918 | 3489125 | 135206 | 15924 | 49 | 7 | 2 | 16487 | 0 | 0 | 0 | 31396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 45243 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 321 | 4488229.01 |  |  | 1 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q93 | 44107815201 | 2018-07-12 | QTR1 | 18/19 | 2 | 0 | 90 | 139 | 133 | 6 | 0 | 0 | 49 | 0 | 119741 | 9449 | 110292 | 119741 | 111083 | 0 | 0 | 0 | 111083 | 111083 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F541769861 | FERROVIAL SERVICES INFRASTRUCTURE INC | N/A | N/A | N/A | N/A | 2019-06-05 | QTR4 | 18/19 |  | 2019-02-11 | QTR3 | 18/19 | 313 | 198799.25 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R24 | 43626915201 | 2018-02-08 | QTR3 | 17/18 | 1 | 0 | 70 | 83 | 80 | 3 | 0 | 0 | 13 | 0 | 696272 | 46135 | 650137 | 696272 | 637670 | 0 | 0 | 0 | 637670 | 637670 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-07-19 | QTR1 | 18/19 | 313 | 945341.61 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R38 | 21869925201 | 2018-06-14 | QTR4 | 17/18 | 1 | 1 | 90 | 144 | 142 | 2 | 0 | 0 | 54 | 0 | 459900 | 35772 | 424128 | 473285 | 462354 | 0 | 0 | 0 | 462354 | 462354 | 0 | 13385 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-04-18 | QTR4 | 18/19 |  | 2019-02-19 | QTR3 | 18/19 | 321 | 750711.43 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 0 | 4802 | 135 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | -14505 | 252534 | 101 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | -7370 | 325031 | 104 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL C | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4438 | 42871915201 | 2016-09-28 | QTR1 | 16/17 | 10 | 6 | 414 | 553 | 553 | 0 | 0 | 0 | 139 | 0 | 8534546 | 149000 | 8385546 | 8647389 | 8810202 | 0 | 0 | 0 | 8810202 | 8996744 | 197163 | 112843 | 56 | 0 | 0 | 147796 | 7419 | 45 | 0 | 59952 | 8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668 | 8668 | 0 | 0 | 3778 | 0 | 0 | 0 | -84397 | 0 | 45 | 0 | 135797 | 25044 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-09 | QTR4 | 18/19 |  | 2018-10-03 | QTR2 | 18/19 | 409 | 8438874.92 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 4036 | 70900 | 32 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4445 | 43060315201 | 2017-01-25 | QTR3 | 16/17 | 1 | 4 | 365 | 510 | 480 | 30 | 0 | 0 | 134 | 11 | 8418937 | 102163 | 8316774 | 8403485 | 8476613 | 0 | 0 | 0 | 8476613 | 8700175 | 251131 | -15452 | 110 | 0 | 19 | 47250 | 0 | 0 | 0 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 51443 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-28 | QTR3 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 412 | 9837147.69 |  |  | 19 | 24 | 0 | -8 | -72293 | 0 |  | CO
04CO | 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | -10793 | 15092 | 66 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97 |  |  | 26 | 22 | 0 | 0 | -1882 | 0 |  | CO
04CO | 04 | T4447 | 43510115201 | 2017-03-29 | QTR3 | 16/17 | 7 | 2 | 364 | 422 | 422 | 0 | 0 | 0 | 108 | -50 | 3554036 | 50000 | 3504036 | 3574289 | 3278614 | 0 | 0 | 0 | 3278614 | 3266227 | 4310 | 20253 | 88 | 0 | 0 | 1981 | 0 | 0 | -50 | 5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 7532 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 409 | 3729070.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4450 | 43288325201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 269 | 378 | 376 | 2 | 0 | 0 | 85 | 24 | 1867168 | 50000 | 1817168 | 1867168 | 1766523 | 0 | 0 | 0 | 1766523 | 1766523 | 0 | 0 | 32 | 0 | 21 | 2936 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 41339 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 409 | 2440206.66 |  |  | 24 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4451 | 43514415201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 167 | 204 | 204 | 0 | 0 | 0 | 32 | 5 | 853000 | 35518 | 817482 | 853000 | 762484 | 0 | 0 | 0 | 762484 | 764893 | 2408 | 0 | 24 | 0 | 5 | 1628 | 0 | 0 | 0 | 6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8585 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-04-25 | QTR4 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 409 | 757018.39 |  |  | 5 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 985 | 4306 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4455 | 43442715201 | 2017-07-26 | QTR1 | 17/18 | 1 | 1 | 277 | 316 | 306 | 10 | 0 | 0 | 39 | 0 | 14081000 | 150000 | 13931000 | 14107664 | 13452505 | 0 | 0 | 0 | 13452505 | 14356886 | 904380 | 26664 | 31 | 0 | 0 | 26664 | 0 | 0 | 0 | 9390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11492 | 0 | 0 | 0 | 34538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82084 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-18 | QTR3 | 18/19 |  | 2018-11-09 | QTR2 | 18/19 | 409 | 15571973.96 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 981 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 31168 | 30 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4460 | 43854615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 147 | 172 | 172 | 0 | 0 | 0 | 25 | 0 | 932300 | 38207 | 894094 | 932300 | 856857 | 0 | 0 | 0 | 856857 | 856867 | 10 | 0 | 7 | 0 | 0 | 685 | 0 | 0 | 0 | 3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-04-16 | QTR4 | 17/18 | 408 | 782210.07 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4464 | 23316625201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 291 | 458 | 456 | 2 | 0 | 0 | 167 | 0 | 3520178 | 50000 | 3470178 | 3520178 | 3370360 | 0 | 0 | 0 | 3370360 | 3385395 | 15035 | 0 | 87 | 0 | 0 | 2782 | 0 | 30 | 0 | 40068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 45234 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-05-29 | QTR4 | 18/19 |  | 2019-01-23 | QTR3 | 18/19 | 409 | 3420061.33 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4466 | 42871815201 | 2017-07-26 | QTR1 | 17/18 | 5 | 1 | 388 | 441 | 411 | 30 | 0 | 0 | 53 | 0 | 3213996 | 50000 | 3163996 | 3213990 | 3033800 | 0 | 0 | 0 | 3033800 | 3135748 | 101948 | -6 | 23 | 0 | 0 | 19551 | 0 | 0 | 0 | 4848 | 8066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24399 | 8066 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-12-20 | QTR2 | 18/19 | 409 | 3457230.6 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4475 | 43609715201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 181 | 246 | 245 | 1 | 0 | 0 | 65 | 0 | 1977475 | 50000 | 1927475 | 1977475 | 1900507 | 0 | 0 | 0 | 1900507 | 1961150 | 60643 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 9996 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-05-13 | QTR4 | 18/19 |  | 2019-02-17 | QTR3 | 18/19 | 412 | 2189027.65 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4K92 | 41248925201 | 2010-11-30 | QTR2 | 10/11 | 7 | 17 | 1303 | 2546 | 2546 | 0 | 0 | 0 | 228 | 1015 | 94215000 | 150000 | 94065000 | 108647581 | 108420972 | 0 | 0 | 0 | 108420972 | 108204126 | -90707 | 14432581 | 86 | 0 | 288 | 1644087 | 1314542 | 0 | 220 | 2406319 | 2431025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114050 | 0 | 60 | 507 | 10129365 | 2700545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1015 | 14293821 | 6446112 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-29 | QTR3 | 18/19 | 05/08/2018 | 2018-10-04 | QTR2 | 18/19 | 409 | 97954437 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4M78 | 41304925201 | 2013-03-14 | QTR3 | 12/13 | 1 | 6 | 925 | 1777 | 1831 | -54 | 54 | 0 | 599 | 253 | 50630000 | 150000 | 50480000 | 51906885 | 51703165 | -514238 | 0 | -514238 | 51188926 | 48130802 | -2986230 | 1276885 | 382 | 2 | 4 | 160986 | 0 | 129 | 154 | 1630628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 158 | 1265797 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-04-22 | QTR4 | 18/19 |  | 2018-06-01 | QTR4 | 17/18 | 408 | 57557685.27 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 4 | 86 | 0 | 0 | -525817 | 0 |  | DO
04DO | 04 | E4N44 | 42170765201 | 2013-07-24 | QTR1 | 13/14 | 1 | 20 | 1455 | 1611 | 1541 | 70 | 0 | 0 | 156 | 0 | 74960000 | 150000 | 74810000 | 78091122 | 78080272 | 0 | 500000 | 500000 | 78580272 | 76318477 | -2197408 | 3131122 | 99 | 0 | 0 | 1901047 | 480717 | 0 | 0 | 1302005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65075 | 8800 | 0 | 0 | 30566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3215766 | 489517 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 406 | 85510016 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 57 | 0 | 0 | -82927 | 0 |  | DO
04DO | 04 | E4P08 | 42170755201 | 2014-03-25 | QTR3 | 13/14 | 7 | 23 | 1305 | 1810 | 1471 | 339 | 0 | 0 | 270 | 235 | 80437734 | 150000 | 80287734 | 82797035 | 82818636 | -283033 | -200000 | -483033 | 82335603 | 78160637 | -3880669 | 2359301 | 204 | 0 | 5 | -559751 | 0 | 0 | 27 | 763643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1957639 | 16706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 12319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 2097146 | 16706 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-06 | QTR3 | 18/19 |  | 2018-07-16 | QTR1 | 18/19 | 412 | 106884251 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 66 | 0 | 0 | -76704 | 0 |  | DO
04DO | 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | -85027 | 475368 | 293 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75 |  |  | 10 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 93460 | 150444 | 82 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R83 | 43482915201 | 2017-05-03 | QTR4 | 16/17 | 1 | 0 | 445 | 586 | 585 | 1 | 0 | 0 | 141 | 0 | 2949000 | 50000 | 2899000 | 2949000 | 2893000 | 0 | 0 | 0 | 2893000 | 2893000 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-02-21 | QTR3 | 18/19 |  | 2019-01-28 | QTR3 | 18/19 | 412 | 2699822 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 26852 | 127760 | 93 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S29 | 43059325201 | 2017-04-07 | QTR4 | 16/17 | 4 | 2 | 290 | 414 | 414 | 0 | 0 | 0 | 124 | 0 | 3060921 | 47591 | 3013330 | 3171379 | 2918996 | 0 | 0 | 0 | 2918996 | 2935462 | 54722 | 110457 | 74 | 0 | 0 | 2993 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79649 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 408 | 2506695.34 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 666 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 0 | 13 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S43 | 44009015201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 290 | 412 | 411 | 1 | 0 | 0 | 122 | 0 | 2285285 | 50000 | 2235285 | 2435637 | 2385637 | 0 | 0 | 0 | 2385637 | 2385637 | 0 | 150352 | 64 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 150352 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-01-31 | QTR3 | 18/19 |  | 2019-01-11 | QTR3 | 18/19 | 408 | 2071421.19 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S80 | 43609515201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 140 | 154 | 154 | 0 | 0 | 0 | 14 | 0 | 2070318 | 50000 | 2020318 | 2144319 | 2069570 | 0 | 0 | 0 | 2069570 | 2112206 | 42636 | 74001 | 9 | 0 | 0 | 76370 | 0 | 0 | 0 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94219 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 408 | 1656846.48 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S96 | 43215115201 | 2018-02-02 | QTR3 | 17/18 | 1 | 1 | 157 | 196 | 192 | 4 | 0 | 0 | 39 | 0 | 424444 | 21202 | 403242 | 440600 | 416334 | 0 | 0 | 0 | 416334 | 416334 | 0 | 16156 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 16153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16156 | 3 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-04-25 | QTR4 | 18/19 |  | 2019-01-16 | QTR3 | 18/19 | 409 | 433731.62 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5313 | 23953535201 | 2014-12-03 | QTR2 | 14/15 | 6 | 28 | 643 | 1112 | 1108 | 4 | 0 | 0 | 176 | 293 | 37587579 | 150000 | 37437579 | 42729229 | 43288413 | 0 | 0 | 0 | 43288413 | 42180960 | -1059964 | 5141650 | 119 | 0 | 12 | 710601 | 95885 | 0 | 215 | 4577941 | 2425199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14215 | 0 | 0 | 0 | 7659 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 129045 | 43490 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 5209211 | 2564573 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-03 | QTR2 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 509 | 38177322.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 7 | 57 | 0 | 30 | -230251 | 0 |  | CO
05CO | 05 | T5431 | 23759225201 | 2012-12-05 | QTR2 | 12/13 | 3 | 26 | 900 | 1272 | 1272 | 0 | 0 | 0 | 151 | 221 | 29360536 | 150000 | 29210536 | 33683790 | 34207580 | 0 | -3800 | -3800 | 34203780 | 33089772 | -1114008 | 4323245 | 93 | 0 | 0 | 637527 | 41439 | 0 | 146 | 1679738 | 364141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79150 | 0 | 0 | 75 | 1567226 | 5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 4515905 | 411433 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2016-09-07 | QTR1 | 16/17 | 514 | 29690234.55 |  |  | 0 | 58 | 0 | 0 | -110308 | 0 |  | CO
05CO | 05 | T5521 | 23926635201 | 2015-03-25 | QTR3 | 14/15 | 9 | 10 | 1300 | 1440 | 1215 | 225 | 0 | 0 | 140 | 0 | 37089690 | 150000 | 36939690 | 37921259 | 38186961 | 0 | 775000 | 775000 | 38961961 | 37805706 | -1060568 | 831569 | 71 | 0 | 0 | 354866 | 0 | 0 | 0 | 395988 | 5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781799 | 5636 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2018-12-06 | QTR2 | 18/19 | 509 | 30786372.89 | B1 | ACC - NO EXCUSE BONUS | 0 | 69 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5534 | 42875315201 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 600 | 763 | 765 | -2 | 2 | 0 | 178 | -15 | 10372492 | 109000 | 10263492 | 10929528 | 10898780 | -15534 | 0 | -15534 | 10883246 | 10869524 | 280079 | 557037 | 129 | 0 | 0 | 52612 | 0 | 0 | -26 | 22897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 246070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 321579 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-24 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 590 | 11601598.01 | B0 | ACC - LUMP SUM | 8 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5548 | 24021625201 | 2016-02-24 | QTR3 | 15/16 | 4 | 8 | 860 | 1076 | 1075 | 1 | 0 | 0 | 188 | 28 | 26475089 | 150000 | 26325089 | 26427125 | 26734528 | -73350 | 0 | -73350 | 26661178 | 27364124 | 755744 | -121314 | 132 | 0 | 0 | -667764 | 0 | 0 | 14 | 365473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 128179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | -174112 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-17 | QTR4 | 18/19 |  | 2019-04-18 | QTR4 | 18/19 | 507 | 27928071.89 | B5 | ACC - INCENTIVE/DISINCENTIVE | 14 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5558 | 23842215201 | 2015-10-28 | QTR2 | 15/16 | 3 | 10 | 967 | 1029 | 853 | 176 | 0 | 0 | 87 | -25 | 37503443 | 150000 | 37353443 | 37874281 | 37480698 | 0 | 990000 | 990000 | 38470698 | 37455359 | -956254 | 370838 | 56 | 0 | 0 | 380837 | 0 | 0 | 0 | 27551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8530 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | 296353 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 515 | 47475664.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | -40 | -130768 | 0 |  | CO
05CO | 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 0 | 56481 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05 |  |  | 14 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5575 | 43505715202 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 290 | 323 | 290 | 33 | 0 | 0 | 33 | 0 | 3075596 | 50000 | 3025596 | 3075596 | 2961552 | 0 | 0 | 0 | 2961552 | 2961571 | 19 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 13502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40320 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 512 | 4026582.45 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 6944 | 115263 | 65 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5579 | 43240225201 | 2016-10-26 | QTR2 | 16/17 | 2 | 1 | 340 | 409 | 410 | -1 | 1 | 0 | 69 | 0 | 4191439 | 50000 | 4141439 | 4197665 | 4536952 | 0 | 0 | 0 | 4536952 | 4533228 | 2502 | 6226 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 26473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26473 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-05-03 | QTR4 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 4646410 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5580 | 43259215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 380 | 517 | 515 | 2 | 0 | 0 | 109 | 28 | 5833370 | 62000 | 5771370 | 5934096 | 5935419 | 0 | 0 | 0 | 5935419 | 6045029 | 126318 | 100726 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 107737 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-09-13 | QTR1 | 18/19 | 514 | 6316391 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5584 | 43233315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 3 | 130 | 327 | 326 | 1 | 0 | 0 | 183 | 14 | 1998889 | 50000 | 1948889 | 2179196 | 2210072 | 0 | 0 | 0 | 2210072 | 2099822 | 13997 | 180307 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 46480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11064 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 103605 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-19 | QTR2 | 18/19 |  | 2018-05-31 | QTR4 | 17/18 | 515 | 2432081.12 |  |  | 8 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5585 | 43441715201 | 2017-02-22 | QTR3 | 16/17 | 4 | 2 | 140 | 384 | 398 | -14 | 14 | 0 | 244 | 0 | 2959615 | 50000 | 2909615 | 3012362 | 2938715 | -39354 | 0 | -39354 | 2899361 | 2923708 | 40280 | 52747 | 216 | 0 | 0 | 36813 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61813 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-11-01 | QTR2 | 18/19 |  | 2018-06-21 | QTR4 | 17/18 | 514 | 3119772 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5587 | 43505415201 | 2017-03-29 | QTR3 | 16/17 | 3 | 3 | 380 | 465 | 463 | 2 | 0 | 0 | 85 | 0 | 3220056 | 50000 | 3170056 | 3323115 | 3265140 | 0 | 0 | 0 | 3265140 | 3262109 | 0 | 103059 | 63 | 0 | 0 | 12084 | 0 | 0 | 0 | 87944 | 689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100028 | 689 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-11-05 | QTR2 | 18/19 | 514 | 4249077.7 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5598 | 43566115201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 160 | 188 | 188 | 0 | 0 | 0 | 28 | 0 | 1387781 | 50000 | 1337781 | 1400208 | 1356596 | 0 | 0 | 0 | 1356596 | 1374428 | 17832 | 12427 | 24 | 0 | 0 | 1476 | 0 | 0 | 0 | 19164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20640 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-12-21 | QTR2 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 507 | 1627448 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5600 | 43691515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 250 | 324 | 324 | 0 | 0 | 0 | 74 | 0 | 3294214 | 50000 | 3244214 | 3431595 | 3445345 | 0 | 0 | 0 | 3445345 | 3578158 | 132813 | 137381 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137381 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-10-23 | QTR2 | 18/19 | 513 | 4280329.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5602 | 44113065203 | 2017-08-30 | QTR1 | 17/18 | 3 | 0 | 150 | 205 | 222 | -17 | 17 | 0 | 55 | 0 | 287798 | 13000 | 274798 | 287798 | 331937 | -18683 | 0 | -18683 | 313254 | 313254 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-07-23 | QTR1 | 18/19 | 514 | 295435 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5609 | 43441215201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 240 | 281 | 245 | 36 | 0 | 0 | 41 | 0 | 2876725 | 50000 | 2826725 | 2925685 | 2914329 | 0 | 0 | 0 | 2914329 | 2993507 | 79179 | 48960 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 72816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71776 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-05-21 | QTR4 | 18/19 |  | 2019-03-29 | QTR3 | 18/19 | 507 | 3026652 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1131728 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5620 | 43367315201 | 2017-10-25 | QTR2 | 17/18 | 1 | 1 | 240 | 261 | 236 | 25 | 0 | 0 | 21 | 0 | 633985 | 50000 | 583985 | 639413 | 620693 | 0 | 0 | 0 | 620693 | 621196 | 504 | 5429 | 8 | 0 | 0 | 16874 | 5429 | 0 | 0 | 10658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27533 | 5429 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-11-08 | QTR2 | 18/19 |  | 2018-09-17 | QTR1 | 18/19 | 515 | 980597 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5627 | 43730215201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 45 | 67 | 62 | 5 | 0 | 0 | 22 | 0 | 140000 | 15000 | 125000 | 140000 | 125000 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2019-03-22 | QTR3 | 18/19 |  | 2019-01-24 | QTR3 | 18/19 | 514 | 315759 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W78 | 23869315201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 850 | 1212 | 1210 | 2 | 0 | 0 | 100 | 262 | 17605644 | 150000 | 17455644 | 20490569 | 20425101 | 0 | 0 | 0 | 20425101 | 20296799 | -71813 | 2884924 | 32 | 0 | 0 | 398745 | 0 | 0 | 262 | 2350231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 2941982 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-05-02 | QTR4 | 18/19 |  | 2018-12-19 | QTR2 | 18/19 | 512 | 19539277.05 | A3:B2:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD | 0 | 68 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W79 | 42404045201 | 2015-05-20 | QTR4 | 14/15 | 3 | 5 | 650 | 988 | 988 | 0 | 0 | 0 | 223 | 115 | 10721000 | 70000 | 10651000 | 10925028 | 10844638 | 0 | 0 | 0 | 10844638 | 10564127 | -89138 | 204028 | 174 | 0 | 71 | -21652 | 0 | 0 | 14 | 8110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34307 | 34307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 20766 | 34307 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2019-01-16 | QTR3 | 18/19 |  | 2018-04-02 | QTR4 | 17/18 | 514 | 7403285 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 14 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W91 | 40441825201 | 2015-08-04 | QTR1 | 15/16 | 3 | 4 | 980 | 1000 | 786 | 214 | 0 | 0 | 20 | 0 | 648777 | 6000 | 642777 | 669790 | 669790 | 0 | 0 | 0 | 669790 | 653990 | -4400 | 21013 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613 | 0 | F272068885 | LAFLEUR NURSERIES AND GARDEN CENTER LLC | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-08-17 | QTR1 | 18/19 | 507 | 690159.83 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W96 | 42344695201 | 2015-10-13 | QTR2 | 15/16 | 17 | 23 | 650 | 1025 | 1007 | 18 | 0 | 0 | 73 | 302 | 113653294 | 150000 | 113503294 | 153813717 | 153692841 | 0 | 1000000 | 1000000 | 154692841 | 153331926 | -1183152 | 40160423 | 24 | 0 | 122 | 2794353 | 121808 | 0 | 0 | 1064932 | 14649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 180 | 36317114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18933 | 18933 | 0 | 0 | 0 | 0 | 0 | 302 | 40205231 | 155390 | F474365086 | MIDDLESEX-HERZOG II A JOINT VEN | N/A | N/A | N/A | N/A | 2019-06-19 | QTR4 | 18/19 |  | 2019-01-02 | QTR3 | 18/19 | 507 | 113653294 | B1:B5:B8:B:B:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 69 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y51 | 43832115201 | 2017-06-06 | QTR4 | 16/17 | 1 | 2 | 90 | 194 | 193 | 1 | 0 | 0 | 87 | 17 | 334599 | 16000 | 318599 | 541800 | 538448 | 0 | 0 | 0 | 538448 | 538448 | 0 | 207200 | 34 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17 | 207200 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-01-17 | QTR3 | 18/19 |  | 2018-04-19 | QTR4 | 17/18 | 514 | 346552.2 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y52 | 43632315201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 270 | 476 | 469 | 7 | 0 | 0 | 206 | 0 | 745547 | 38000 | 707547 | 745547 | 707547 | 0 | 0 | 0 | 707547 | 707547 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | QTR3 | 18/19 |  | 2018-12-14 | QTR2 | 18/19 | 513 | 805051.1 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 1238 | 76790 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 26994 | 156917 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y64 | 41832115201 | 2016-09-07 | QTR1 | 16/17 | 2 | 3 | 230 | 306 | 306 | 0 | 0 | 0 | 50 | 26 | 1888542 | 50000 | 1838542 | 1900573 | 1865675 | 0 | 0 | 0 | 1865675 | 1863311 | 5094 | 12031 | 26 | 0 | 0 | -2637 | 0 | 0 | 26 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 34816 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-10-30 | QTR2 | 18/19 |  | 2018-01-13 | QTR3 | 17/18 | 509 | 1818885.7 |  |  | 26 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y73 | 43065115201 | 2017-06-06 | QTR4 | 16/17 | 2 | 6 | 180 | 299 | 297 | 2 | 0 | 0 | 84 | 35 | 2882444 | 50000 | 2832444 | 3115789 | 3158796 | 0 | 0 | 0 | 3158796 | 3221626 | 64762 | 233345 | 64 | 0 | 0 | 1308 | 0 | 0 | 18 | 155360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 98415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 255084 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-07-02 | QTR1 | 18/19 | 515 | 3280928 |  |  | 3 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y74 | 43440615201 | 2018-02-06 | QTR3 | 17/18 | 1 | 1 | 330 | 356 | 276 | 80 | 0 | 0 | 26 | 0 | 8870873 | 91000 | 8779873 | 8896060 | 9038403 | 0 | 0 | 0 | 9038403 | 9298489 | 260086 | 25187 | 9 | 0 | 0 | 79152 | 0 | 0 | 0 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84762 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | QTR4 | 18/19 |  | 2019-01-09 | QTR3 | 18/19 | 509 | 9190822 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 0 | 0 | 60 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85 |  |  | 8 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 76090 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 81060 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y95 | 43632515201 | 2017-06-06 | QTR4 | 16/17 | 1 | 0 | 380 | 491 | 481 | 10 | 0 | 0 | 81 | 30 | 2610610 | 50000 | 2560610 | 2610610 | 2553200 | 0 | 0 | 0 | 2553200 | 2553205 | 5 | 0 | 25 | 0 | 30 | 23553 | 0 | 0 | 0 | 4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 29994 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-12-26 | QTR2 | 18/19 | 513 | 3377422 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 55693 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z03 | 43612615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 120 | 168 | 166 | 2 | 0 | 0 | 48 | 0 | 765000 | 50000 | 715000 | 765000 | 715000 | 0 | 0 | 0 | 715000 | 715000 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-12 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 513 | 1015761.2 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z04 | 43927115201 | 2018-02-06 | QTR3 | 17/18 | 1 | 0 | 90 | 102 | 87 | 15 | 0 | 0 | 12 | 0 | 133664 | 5664 | 128000 | 133664 | 128000 | 0 | 0 | 0 | 128000 | 128000 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-15 | QTR3 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 515 | 123951 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z05 | 43566615201 | 2017-12-05 | QTR2 | 17/18 | 1 | 1 | 240 | 283 | 262 | 21 | 0 | 0 | 42 | 1 | 1687883 | 50000 | 1637883 | 1737883 | 1730756 | 0 | 0 | 0 | 1730756 | 1735963 | 5207 | 50000 | 23 | 0 | 0 | 50180 | 0 | 0 | 1 | 30589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 80769 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-02-27 | QTR3 | 18/19 |  | 2018-12-18 | QTR2 | 18/19 | 512 | 1825766 |  |  | 1 | 19 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z15 | 44022215201 | 2017-09-25 | QTR1 | 17/18 | 1 | 0 | 220 | 284 | 283 | 1 | 0 | 0 | 64 | 0 | 1614614 | 50000 | 1564614 | 1614614 | 1573363 | 0 | 0 | 0 | 1573363 | 1573363 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-11-28 | QTR2 | 18/19 |  | 2018-09-08 | QTR1 | 18/19 | 512 | 1763429 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z29 | 43926915201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 997135 | 44635 | 952500 | 997135 | 952500 | 0 | 0 | 0 | 952500 | 952500 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-01-29 | QTR3 | 18/19 | 513 | 942335 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z31 | 44116515201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 90 | 101 | 74 | 27 | 0 | 0 | 11 | 0 | 79650 | 5000 | 74650 | 89716 | 84370 | 0 | 0 | 0 | 84370 | 84370 | 0 | 10066 | 0 | 0 | 0 | 10066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10066 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-04-02 | QTR4 | 18/19 |  | 2019-02-12 | QTR3 | 18/19 | 509 | 114395.2 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z36 | 43987715201 | 2018-01-03 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 128 | 11 | 0 | 0 | 19 | 0 | 661369 | 44000 | 617369 | 661369 | 614161 | 0 | 50000 | 50000 | 664161 | 615476 | -48686 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-04 | QTR3 | 18/19 |  | 2018-07-31 | QTR1 | 18/19 | 513 | 934116.2 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z38 | 43734615201 | 2018-10-02 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 98 | 4 | 0 | 0 | 12 | 0 | 316000 | 22000 | 294000 | 316000 | 294000 | 0 | 0 | 0 | 294000 | 294000 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-06-07 | QTR4 | 18/19 |  | 2019-04-16 | QTR4 | 18/19 | 513 | 464322 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6220 | 24961435201 | 2014-12-03 | QTR2 | 14/15 | 2 | 7 | 1028 | 1363 | 1363 | 0 | 0 | 0 | 335 | 0 | 58841233 | 150000 | 58691233 | 59057286 | 61015817 | 0 | 0 | 0 | 61015817 | 59202394 | -1584059 | 216053 | 148 | 83 | 0 | 486798 | 0 | 15 | 0 | 102307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 61141 | 0 | 0 | 0 | 39915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 103925 | 0 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-04-11 | QTR4 | 18/19 |  | 2018-11-16 | QTR2 | 18/19 | 606 | 54079695.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | -586234 | 0 |  | CO
06CO | 06 | T6339 | 41463325201 | 2016-05-25 | QTR4 | 15/16 | 5 | 6 | 540 | 657 | 505 | 152 | 0 | 0 | 117 | 0 | 8785729 | 206872 | 8578857 | 9203528 | 9138495 | 0 | 250000 | 250000 | 9388495 | 9110693 | -258037 | 417799 | 96 | 0 | 0 | 300590 | 0 | 0 | 0 | 60947 | 9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186890 | 65328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548427 | 74962 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-11 | QTR2 | 18/19 |  | 2018-01-08 | QTR3 | 17/18 | 606 | 8755698.47 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6347 | 42559815201 | 2015-01-28 | QTR3 | 14/15 | 6 | 11 | 820 | 1009 | 865 | 144 | 0 | 0 | 189 | 0 | 21462766 | 732547 | 20730219 | 22274168 | 21904850 | 0 | 1200000 | 1200000 | 23104850 | 21627277 | -1419938 | 811402 | 61 | 94 | 0 | 900554 | 0 | 0 | 0 | 72913 | 9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220165 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 1195107 | 9137 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-11-20 | QTR2 | 18/19 |  | 2018-03-01 | QTR3 | 17/18 | 606 | 22401464.31 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6348 | 41247935201 | 2016-02-24 | QTR3 | 15/16 | 8 | 4 | 740 | 812 | 711 | 101 | 0 | 0 | 72 | 0 | 18181314 | 296819 | 17884495 | 17828896 | 17896535 | 0 | 800000 | 800000 | 18696535 | 17985610 | -663461 | -352418 | 36 | 0 | 0 | 72263 | 0 | 0 | 0 | 245801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464 | 0 | 0 | 0 | 16570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -107072 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-22 | QTR3 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 606 | 18130045.8 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 36 | 0 | 0 | -502098 | 0 |  | CO
06CO | 06 | T6388 | 24961475201 | 2016-03-30 | QTR3 | 15/16 | 2 | 6 | 499 | 599 | 551 | 48 | 0 | 0 | 100 | 0 | 33267097 | 150000 | 33117097 | 34160144 | 35419695 | 0 | 960000 | 960000 | 36379695 | 35803243 | -576452 | 893046 | 79 | 0 | 0 | 68915 | 0 | 0 | 0 | 560427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689724 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-09 | QTR2 | 18/19 |  | 2018-03-10 | QTR3 | 17/18 | 606 | 37471336.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6390 | 43094915201 | 2017-02-22 | QTR3 | 16/17 | 5 | 6 | 380 | 464 | 460 | 4 | 0 | 0 | 84 | 0 | 4429507 | 54813 | 4374694 | 4700034 | 4434960 | 0 | 170000 | 170000 | 4604960 | 4569268 | -15734 | 270527 | 53 | 0 | 0 | 41640 | 0 | 0 | 0 | 31665 | 12923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171557 | 16087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244862 | 29011 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 606 | 5093915.35 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6411 | 43477615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 280 | 317 | 257 | 60 | 0 | 0 | 37 | 0 | 2356443 | 50820 | 2305623 | 2356443 | 2361696 | 0 | 120000 | 120000 | 2481696 | 2379741 | -101955 | 0 | 31 | 0 | 0 | 7365 | 0 | 0 | 0 | 22298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29663 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-09-21 | QTR1 | 18/19 | 606 | 2737735.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6412 | 43477815201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 120 | 205 | 205 | 0 | 0 | 0 | 85 | 0 | 292409 | 16584 | 275825 | 292409 | 300085 | 0 | 0 | 0 | 300085 | 304110 | 4025 | 0 | 70 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-12 | QTR3 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 335871.2 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | -136676 | 28195 | 44 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | -29328 | 147817 | 57 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6417 | 43476815201 | 2017-06-14 | QTR4 | 16/17 | 3 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 1228383 | 50000 | 1178383 | 1228383 | 1133929 | 0 | 0 | 0 | 1133929 | 1138502 | 4573 | 0 | 36 | 0 | 0 | 9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18218 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-01-25 | QTR3 | 18/19 |  | 2018-11-19 | QTR2 | 18/19 | 606 | 1258750.05 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6418 | 43274825201 | 2017-02-22 | QTR3 | 16/17 | 8 | 6 | 240 | 328 | 328 | 0 | 0 | 0 | 88 | 0 | 1730331 | 52015 | 1678316 | 1781963 | 1633274 | 0 | 0 | 0 | 1633274 | 1636995 | 5234 | 51632 | 63 | 0 | 0 | 36978 | 0 | 0 | 0 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66987 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-26 | QTR2 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 606 | 2094390.89 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6426 | 43477115201 | 2017-07-26 | QTR1 | 17/18 | 3 | 2 | 180 | 212 | 212 | 0 | 0 | 0 | 32 | 0 | 1156048 | 50445 | 1105603 | 1219697 | 1138589 | 0 | 0 | 0 | 1138589 | 1144207 | 5618 | 63649 | 15 | 0 | 0 | 22978 | 0 | 0 | 0 | 45687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68665 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-17 | QTR2 | 18/19 |  | 2018-06-12 | QTR4 | 17/18 | 606 | 1339224.55 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6428 | 42765125201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 180 | 255 | 255 | 0 | 0 | 0 | 75 | 0 | 1069876 | 50735 | 1019141 | 1119876 | 1059386 | 0 | 0 | 0 | 1059386 | 1065529 | 6143 | 50000 | 53 | 0 | 0 | 2426 | 0 | 0 | 0 | 6065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18103 | 0 | 14 | 0 | 28284 | 30284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 54878 | 30284 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-02-14 | QTR3 | 18/19 |  | 2018-09-27 | QTR1 | 18/19 | 606 | 1388000.3 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6430 | 43476915201 | 2017-12-06 | QTR2 | 17/18 | 3 | 1 | 180 | 272 | 271 | 1 | 0 | 0 | 92 | 0 | 1525970 | 50890 | 1475080 | 1558102 | 1416657 | 0 | 0 | 0 | 1416657 | 1416845 | 188 | 32132 | 63 | 0 | 0 | 33094 | 0 | 0 | 0 | 18847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 62968 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-04-26 | QTR4 | 18/19 |  | 2019-03-04 | QTR3 | 18/19 | 606 | 1552449.05 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6431 | 43787315201 | 2018-01-31 | QTR3 | 17/18 | 3 | 0 | 150 | 185 | 185 | 0 | 0 | 0 | 35 | 0 | 929676 | 42743 | 886933 | 929676 | 827030 | 0 | 0 | 0 | 827030 | 827669 | 639 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-22 | QTR3 | 18/19 |  | 2018-11-28 | QTR2 | 18/19 | 606 | 881390.05 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6432 | 43638515201 | 2017-10-25 | QTR2 | 17/18 | 2 | 0 | 150 | 178 | 176 | 2 | 0 | 0 | 28 | 0 | 627876 | 36563 | 591313 | 627876 | 619690 | 0 | 0 | 0 | 619690 | 620784 | 1093 | 0 | 20 | 0 | 0 | 16282 | 0 | 0 | 0 | 14379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31336 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-01 | QTR3 | 18/19 |  | 2018-10-19 | QTR2 | 18/19 | 606 | 756555.75 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6434 | 43792115201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 328254 | 21400 | 306854 | 328254 | 283998 | 0 | 0 | 0 | 283998 | 284067 | 69 | 0 | 48 | 0 | 0 | 2301 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-11-21 | QTR2 | 18/19 |  | 2018-10-10 | QTR2 | 18/19 | 606 | 429366.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6435 | 43635515201 | 2017-12-06 | QTR2 | 17/18 | 3 | 1 | 280 | 300 | 249 | 51 | 0 | 0 | 20 | 0 | 2585379 | 52040 | 2533339 | 2581654 | 2536459 | 0 | 180000 | 180000 | 2716459 | 2639053 | -77406 | -3726 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20265 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 606 | 3093043.9 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6446 | 43631215201 | 2017-04-26 | QTR4 | 16/17 | 2 | 0 | 150 | 215 | 215 | 0 | 0 | 0 | 65 | 0 | 793153 | 47780 | 745373 | 793153 | 739919 | 0 | 0 | 0 | 739919 | 742614 | 2695 | 0 | 57 | 0 | 0 | 8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-10-29 | QTR2 | 18/19 |  | 2018-09-07 | QTR1 | 18/19 | 606 | 987099.7 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6453 | 44018615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 120 | 139 | 137 | 2 | 0 | 0 | 19 | 0 | 242601 | 18959 | 223642 | 242601 | 207429 | 0 | 0 | 0 | 207429 | 207429 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10482 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-15 | QTR4 | 18/19 |  | 2019-03-07 | QTR3 | 18/19 | 606 | 374459.25 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | -593229 | 49068 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 30910 | 125102 | 67 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K27 | 43747515201 | 2017-04-27 | QTR4 | 16/17 | 3 | 0 | 300 | 395 | 392 | 3 | 0 | 0 | 95 | 0 | 2877777 | 51435 | 2826342 | 2877777 | 2846198 | 0 | 0 | 0 | 2846198 | 2850887 | 4689 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 39030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 39030 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-05-01 | QTR4 | 18/19 |  | 2018-11-27 | QTR2 | 18/19 | 606 | 3018097.85 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K52 | 43029119201 | 2016-09-21 | QTR1 | 16/17 | 3 | 3 | 480 | 595 | 595 | 0 | 0 | 0 | 101 | 14 | 5967061 | 60000 | 5907061 | 6057011 | 6008075 | 0 | 0 | 0 | 6008075 | 0 | -6008075 | 89950 | 52 | 0 | 0 | -6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 61444 | 0 | 0 | 0 | 46124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 101015 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-12-14 | QTR2 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 606 | 6418996 | A3:LBDB:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:LOW BID DESIGN BUILD | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K55 | 42527135201 | 2016-11-17 | QTR2 | 16/17 | 5 | 4 | 325 | 360 | 286 | 74 | 0 | 0 | 35 | 0 | 4179580 | 57440 | 4122140 | 4230908 | 4133800 | 0 | 180000 | 180000 | 4313800 | 4122056 | -148006 | 51328 | 26 | 0 | 0 | 37417 | 4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46985 | 4391 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | QTR2 | 18/19 |  | 2017-11-21 | QTR2 | 17/18 | 606 | 4754511.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K60 | 42736945201 | 2017-02-23 | QTR3 | 16/17 | 1 | 0 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 1911584 | 50000 | 1861584 | 1911584 | 1907123 | 0 | 0 | 0 | 1907123 | 1909046 | 1923 | 0 | 120 | 20 | 0 | 21089 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 26132 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-18 | QTR3 | 18/19 |  | 2018-12-12 | QTR2 | 18/19 | 606 | 1951851.15 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K66 | 43826315201 | 2017-10-26 | QTR2 | 17/18 | 2 | 0 | 150 | 170 | 170 | 0 | 0 | 0 | 20 | 0 | 632865 | 37703 | 595162 | 632865 | 612839 | 0 | 0 | 0 | 612839 | 614000 | 1161 | 0 | 13 | 0 | 0 | 1587 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14714 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-17 | QTR2 | 18/19 |  | 2018-11-06 | QTR2 | 18/19 | 606 | 767334.65 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K67 | 43634415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 1 | 180 | 200 | 200 | 0 | 0 | 0 | 20 | 0 | 1835317 | 50000 | 1785317 | 1839190 | 1814980 | 0 | 0 | 0 | 1814980 | 1815065 | 85 | 3872 | 9 | 0 | 0 | 17996 | 0 | 0 | 0 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3872 | 0 | 0 | 0 | 29972 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-08 | QTR4 | 18/19 |  | 2018-12-13 | QTR2 | 18/19 | 606 | 1635399.65 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K70 | 43274345201 | 2018-02-22 | QTR3 | 17/18 | 1 | 0 | 140 | 233 | 233 | 0 | 0 | 0 | 93 | 0 | 974367 | 50000 | 924367 | 974367 | 916327 | 0 | 0 | 0 | 916327 | 917824 | 1497 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-04 | QTR4 | 18/19 |  | 2019-01-09 | QTR3 | 18/19 | 606 | 1053303.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K75 | 43083725201 | 2018-02-22 | QTR3 | 17/18 | 2 | 1 | 210 | 238 | 238 | 0 | 0 | 0 | 28 | 0 | 4131134 | 50000 | 4081134 | 4139407 | 4033935 | 0 | 0 | 0 | 4033935 | 4074967 | 41032 | 8273 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8273 | 0 | 0 | 0 | 9924 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-06-14 | QTR4 | 18/19 |  | 2019-04-08 | QTR4 | 18/19 | 606 | 4148174.65 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K88 | 43653815201 | 2018-07-26 | QTR1 | 18/19 | 1 | 0 | 120 | 121 | 99 | 22 | 0 | 0 | 1 | 0 | 366908 | 17371 | 349537 | 366908 | 341677 | 0 | 0 | 0 | 341677 | 341677 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-05-31 | QTR4 | 18/19 |  | 2019-05-06 | QTR4 | 18/19 | 606 | 362295 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K90 | 43653315201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 270 | 361 | 358 | 3 | 0 | 0 | 91 | 0 | 1534207 | 50000 | 1484207 | 1534207 | 1484378 | 0 | 0 | 0 | 1484378 | 1484378 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-11-19 | QTR2 | 18/19 |  | 2018-10-01 | QTR2 | 18/19 | 606 | 1699724.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L12 | 43560115201 | 2017-01-26 | QTR3 | 16/17 | 3 | 6 | 280 | 429 | 429 | 0 | 0 | 0 | 149 | 0 | 3399874 | 50000 | 3349874 | 3718568 | 3635077 | 0 | 0 | 0 | 3635077 | 3617267 | 263 | 318693 | 92 | 35 | 0 | 25468 | 0 | 0 | 0 | 95370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 308050 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS | N/A | N/A | N/A | N/A | 2019-02-20 | QTR3 | 18/19 |  | 2018-10-30 | QTR2 | 18/19 | 606 | 3205032.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L17 | 42847925201 | 2018-03-29 | QTR3 | 17/18 | 2 | 0 | 140 | 186 | 185 | 1 | 0 | 0 | 46 | 0 | 573531 | 28824 | 544707 | 573531 | 554401 | 0 | 0 | 0 | 554401 | 555701 | 1299 | 0 | 24 | 0 | 0 | 12435 | 0 | 0 | 0 | 15160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27595 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-04-10 | QTR4 | 18/19 |  | 2019-01-30 | QTR3 | 18/19 | 606 | 585290.75 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L18 | 43779215201 | 2017-10-26 | QTR2 | 17/18 | 1 | 0 | 150 | 215 | 215 | 0 | 0 | 0 | 65 | 0 | 676189 | 34902 | 641287 | 676189 | 658548 | 0 | 0 | 0 | 658548 | 659195 | 646 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-25 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 606 | 719637.75 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L19 | 42848725201 | 2017-07-27 | QTR1 | 17/18 | 3 | 0 | 180 | 229 | 229 | 0 | 0 | 0 | 49 | 0 | 1469702 | 51435 | 1418267 | 1469702 | 1379063 | 1584 | 0 | 1584 | 1380647 | 1390630 | 9983 | 0 | 44 | 0 | 0 | 2601 | 0 | 0 | 0 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | QTR2 | 18/19 |  | 2018-08-31 | QTR1 | 18/19 | 606 | 1648940 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 0 | 0 | 4 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7292 | 40915415201 | 2011-09-28 | QTR1 | 11/12 | 11 | 13 | 1150 | 1512 | 1755 | -243 | 243 | 0 | 282 | 80 | 21468350 | 150000 | 21318350 | 23763433 | 23633808 | -79000 | 0 | -79000 | 23554808 | 23010045 | -544763 | 2295083 | 191 | 0 | 39 | 1603710 | 5621 | 0 | 41 | 571281 | 67491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 138676 | 0 | 0 | 0 | 4390 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2322783 | 73112 | Z13-5010440 | CONTINENTAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2016-11-18 | QTR2 | 16/17 | 709 | 21183448.14 |  |  | 30 | 91 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | -758630 | -138845 | 145 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST | 16 | 61 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7317 | 41886075201 | 2013-06-19 | QTR4 | 12/13 | 7 | 13 | 600 | 1000 | 1012 | -12 | 12 | 0 | 288 | 112 | 25488889 | 150000 | 25338889 | 25701063 | 26223933 | -97668 | 0 | -97668 | 26126265 | 25239037 | -887228 | 212174 | 208 | 23 | 1 | -234527 | 1519 | 0 | 89 | 519557 | 51083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -15044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 112 | 268337 | 52602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-14 | QTR2 | 18/19 |  | 2016-08-11 | QTR1 | 16/17 | 714 | 24112219.03 |  |  | 2 | 57 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7353 | 25699535201 | 2014-10-29 | QTR2 | 14/15 | 3 | 23 | 815 | 1115 | 1115 | 0 | 0 | 0 | 158 | 142 | 19306771 | 150000 | 19156771 | 20971666 | 20689510 | 0 | 0 | 0 | 20689510 | 19663327 | -819849 | 1664895 | 92 | 0 | 0 | 311336 | 29250 | 0 | 58 | 1244282 | 239623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32741 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 271292 | 266792 | 0 | 0 | -38766 | 0 | 0 | 142 | 1707005 | 535664 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-12-03 | QTR2 | 18/19 |  | 2018-03-06 | QTR3 | 17/18 | 709 | 20231800 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 66 | 0 | 0 | -113880 | 0 |  | CO
07CO | 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 18982 | 298860 | 167 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22 |  |  | 48 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7382 | 43258615202 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 285 | 401 | 401 | 0 | 0 | 0 | 57 | 59 | 8465944 | 65250 | 8400694 | 9024845 | 9722176 | 0 | -400000 | -400000 | 9322176 | 9328282 | 25484 | 558900 | 42 | 0 | 0 | 234950 | 7657 | 0 | 0 | 212897 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 133758 | 131644 | 0 | 0 | 0 | 0 | 0 | 59 | 581605 | 139868 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2017-10-23 | QTR2 | 17/18 | 709 | 9653597.15 | B7 | ACC - A+B/BONUS | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7387 | 42895415201 | 2016-06-15 | QTR4 | 15/16 | 3 | 8 | 435 | 735 | 733 | 2 | 0 | 0 | 223 | 77 | 17840000 | 150000 | 17690000 | 18339077 | 18567408 | 0 | 0 | 0 | 18567408 | 18654250 | 128181 | 499077 | 175 | 0 | 45 | 212755 | 0 | 0 | 28 | 205993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 461583 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-01-03 | QTR3 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 714 | 19115045.32 |  |  | 49 | 48 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 30781 | 47 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7392 | 43484115202 | 2017-05-24 | QTR4 | 16/17 | 3 | 1 | 210 | 384 | 331 | 53 | 0 | 0 | 153 | 21 | 5679793 | 50000 | 5629793 | 5828296 | 5798728 | 0 | 0 | 0 | 5798728 | 5859621 | 60893 | 148503 | 55 | 0 | 21 | 148503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 148503 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-05 | QTR3 | 18/19 |  | 2018-10-11 | QTR2 | 18/19 | 796 | 4416000 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 0 | 31 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7405 | 43649015201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 140 | 161 | 146 | 15 | 0 | 0 | 21 | 0 | 2235958 | 50000 | 2185958 | 2384716 | 2283562 | 0 | 0 | 0 | 2283562 | 2395779 | 112217 | 148758 | 18 | 0 | 0 | 58523 | 0 | 0 | 0 | 98758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-02-26 | QTR3 | 18/19 |  | 2018-10-29 | QTR2 | 18/19 | 798 | 3540000 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7416 | 44030615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 50 | 55 | 54 | 1 | 0 | 0 | 5 | 0 | 471467 | 20500 | 450967 | 471467 | 440953 | 0 | 0 | 0 | 440953 | 440953 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-24 | QTR2 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 799 | 446330 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7418 | 43648615201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 100 | 123 | 123 | 0 | 0 | 0 | 23 | 0 | 935304 | 43500 | 891804 | 935304 | 902861 | 0 | 0 | 0 | 902861 | 903868 | 1007 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-05-14 | QTR4 | 18/19 |  | 2019-03-07 | QTR3 | 18/19 | 799 | 985000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7423 | 44269715201 | 2018-06-13 | QTR4 | 17/18 | 5 | 0 | 80 | 84 | 30 | 54 | 0 | 0 | 4 | 0 | 189768 | 12500 | 177268 | 189768 | 146624 | 0 | 0 | 0 | 146624 | 146624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 796 | 280558.01 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7I24 | 25873625201 | 2013-07-31 | QTR1 | 13/14 | 2 | 21 | 1080 | 1678 | 1678 | 0 | 0 | 0 | 473 | 125 | 71245000 | 150000 | 71095000 | 73940453 | 73581395 | 0 | 0 | 0 | 73581395 | 68828499 | -4536501 | 2695453 | 369 | 0 | 86 | 1868254 | 0 | 0 | 0 | 502006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91300 | 0 | 0 | 39 | 29919 | 17848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2491479 | 17848 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2018-06-22 | QTR4 | 17/18 | 714 | 73473000 | B8 | ACC - DESIGN/BUILD - MAJOR | 35 | 104 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | -54636 | 367480 | 145 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | -18692 | 37019 | 42 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L56 | 43243425201 | 2017-03-08 | QTR3 | 16/17 | 1 | 0 | 240 | 264 | 248 | 16 | 0 | 0 | 24 | 0 | 844020 | 45000 | 799020 | 844020 | 653258 | 0 | 0 | 0 | 653258 | 780683 | 127425 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2018-06-26 | QTR4 | 17/18 | 709 | 930000 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | -19 | 20 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000 |  |  | 9 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 0 | 78500 | 39 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L82 | 43269715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 4 | 280 | 389 | 388 | 1 | 0 | 0 | 103 | 6 | 4654737 | 50000 | 4604737 | 4707294 | 4587650 | 0 | 0 | 0 | 4587650 | 4635460 | 47810 | 52556 | 86 | 0 | 6 | 2664 | 0 | 0 | 0 | 2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12827 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-01-15 | QTR3 | 18/19 |  | 2018-09-24 | QTR1 | 18/19 | 798 | 5246589.53 |  |  | 6 | 17 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L93 | 43402915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 40 | 55 | 52 | 3 | 0 | 0 | 15 | 0 | 223800 | 9000 | 214800 | 223800 | 202343 | 0 | 0 | 0 | 202343 | 202343 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-16 | QTR2 | 18/19 |  | 2018-09-12 | QTR1 | 18/19 | 796 | 320000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L94 | 43754915201 | 2018-02-14 | QTR3 | 17/18 | 1 | 0 | 50 | 54 | 51 | 3 | 0 | 0 | 4 | 0 | 226571 | 11500 | 215071 | 226571 | 223484 | 0 | 0 | 0 | 223484 | 223484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-05 | QTR2 | 18/19 |  | 2018-09-25 | QTR1 | 18/19 | 796 | 310000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L96 | 43966215201 | 2018-03-14 | QTR3 | 17/18 | 1 | 0 | 300 | 329 | 152 | 177 | 0 | 0 | 29 | 0 | 1051194 | 50000 | 1001194 | 1051194 | 908881 | 0 | 0 | 0 | 908881 | 908881 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-03-07 | QTR3 | 18/19 |  | 2019-02-13 | QTR3 | 18/19 | 796 | 1997000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L97 | 43589415201 | 2018-04-11 | QTR4 | 17/18 | 2 | 0 | 87 | 156 | 155 | 1 | 0 | 0 | 69 | 0 | 376868 | 19200 | 357668 | 376868 | 346469 | 0 | 0 | 0 | 346469 | 346469 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-16 | QTR4 | 18/19 |  | 2019-03-04 | QTR3 | 18/19 | 796 | 405835 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M01 | 43070515201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 88 | 136 | 125 | 11 | 0 | 0 | 48 | 0 | 633485 | 32000 | 601485 | 633485 | 652234 | 0 | 0 | 0 | 652234 | 652234 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | QTR3 | 18/19 |  | 2019-02-08 | QTR3 | 18/19 | 796 | 643100 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M02 | 43386215201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 80 | 74 | 6 | 0 | 0 | 20 | 0 | 394077 | 15000 | 379077 | 394077 | 351730 | 0 | 0 | 0 | 351730 | 351730 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 6505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-05-16 | QTR4 | 18/19 |  | 2019-04-15 | QTR4 | 18/19 | 796 | 405582.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M04 | 43755115201 | 2018-05-09 | QTR4 | 17/18 | 1 | 0 | 60 | 63 | 44 | 19 | 0 | 0 | 3 | 0 | 240676 | 10000 | 230676 | 240676 | 236101 | 0 | 0 | 0 | 236101 | 236101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-11-09 | QTR2 | 18/19 |  | 2018-10-08 | QTR2 | 18/19 | 796 | 225000 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R00 | 43402615201 | 2016-09-15 | QTR1 | 16/17 | 1 | 0 | 390 | 574 | 581 | -7 | 7 | 0 | 184 | 0 | 2971000 | 50000 | 2921000 | 2971000 | 2903131 | -19677 | 0 | -19677 | 2883454 | 2883454 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F232947721 | GA | N/A | N/A | N/A | N/A | 2018-11-07 | QTR2 | 18/19 |  | 2018-08-30 | QTR1 | 18/19 | 717 | 2867514 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N52 | 42935045201 | 2014-09-30 | QTR1 | 14/15 | 1 | 7 | 1050 | 1299 | 1299 | 0 | 0 | 0 | 215 | 34 | 50984589 | 150000 | 50834589 | 52265348 | 52262125 | -25500 | 0 | -25500 | 52236625 | 50849787 | -1273624 | 1280759 | 147 | 0 | 0 | 723707 | 0 | 0 | 0 | 221201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 83632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 0 | 0 | 34 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 34 | 1204957 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-07-26 | QTR1 | 18/19 | 854 | 52446848.15 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 47 | 0 | 0 | -35903 | 0 |  | DO
08DO | 08 | E8P06 | 43383015201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 625 | 706 | 702 | 4 | 0 | 0 | 81 | 0 | 27866200 | 150000 | 27716200 | 27866200 | 27624496 | 0 | 0 | 0 | 27624496 | 26928859 | -695637 | 0 | 56 | 0 | 0 | 83594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93166 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-01 | QTR2 | 18/19 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 32476137.41 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | -6108 | 1045631 | 89 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q11 | 43715625201 | 2016-08-16 | QTR1 | 16/17 | 1 | 3 | 415 | 487 | 487 | 0 | 0 | 0 | 72 | 0 | 10316568 | 100607 | 10215961 | 10271998 | 10116572 | 0 | 0 | 0 | 10116572 | 10120109 | 64151 | -44570 | 40 | 0 | 0 | 45355 | 0 | 0 | 0 | -280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -59830 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-10-15 | QTR2 | 18/19 |  | 2018-06-14 | QTR4 | 17/18 | 854 | 10198095.64 |  |  | 0 | 28 | 0 | 0 | -104904 | 0 |  | DO
08DO | 08 | E8Q45 | 43516615201 | 2017-03-28 | QTR3 | 16/17 | 4 | 7 | 245 | 377 | 376 | 1 | 0 | 0 | 113 | 19 | 10174450 | 99451 | 10074999 | 10442695 | 10222974 | 0 | 0 | 0 | 10222974 | 10331810 | 132458 | 268245 | 69 | 0 | 0 | 34793 | 0 | 0 | 12 | 180668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 0 | 0 | 7 | 64962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 282868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-23 | QTR3 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 854 | 10340089.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 19 | 44 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q46 | 43717015202 | 2017-03-14 | QTR3 | 16/17 | 2 | 0 | 135 | 258 | 223 | 35 | 0 | 0 | 123 | 0 | 1120173 | 14148 | 1106025 | 1120173 | 1139075 | 0 | 0 | 0 | 1139075 | 1139077 | 2 | 0 | 78 | 0 | 0 | 6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 6102 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2018-12-18 | QTR2 | 18/19 |  | 2018-07-30 | QTR1 | 18/19 | 854 | 885798.07 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q48 | 43560815201 | 2017-06-13 | QTR4 | 16/17 | 3 | 2 | 180 | 280 | 306 | -26 | 26 | 0 | 49 | 51 | 2193386 | 50000 | 2143386 | 2202999 | 2182384 | -41184 | 0 | -41184 | 2141200 | 2141200 | 0 | 9613 | 32 | 0 | 0 | 0 | 0 | 0 | 21 | 4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 9613 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-12-19 | QTR2 | 18/19 |  | 2018-10-05 | QTR2 | 18/19 | 854 | 2074316.31 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q77 | 43905115201 | 2017-09-19 | QTR1 | 17/18 | 1 | 2 | 210 | 245 | 243 | 2 | 0 | 0 | 18 | 17 | 1559626 | 50000 | 1509626 | 1611434 | 1403106 | 0 | 0 | 0 | 1403106 | 1403413 | 306 | 51808 | 6 | 0 | 0 | 0 | 0 | 0 | 17 | 36665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42191 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-11-16 | QTR2 | 18/19 |  | 2018-09-14 | QTR1 | 18/19 | 854 | 1751317.91 |  |  | 17 | 12 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q84 | 43990115201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 200 | 314 | 329 | -15 | 15 | 0 | 90 | 24 | 1282157 | 50000 | 1232157 | 1255314 | 1134931 | -22176 | 0 | -22176 | 1112755 | 1112755 | 0 | -26844 | 40 | 0 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24 | -18525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24 | -4749 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2019-06-11 | QTR4 | 18/19 |  | 2019-03-01 | QTR3 | 18/19 | 854 | 1036756.94 |  |  | 24 | 36 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R14 | 43716725201 | 2018-09-11 | QTR1 | 18/19 | 1 | 0 | 65 | 93 | 93 | 0 | 0 | 0 | 28 | 0 | 823809 | 41824 | 781985 | 823809 | 857863 | 0 | 0 | 0 | 857863 | 857863 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-06-25 | QTR4 | 18/19 |  | 2019-04-25 | QTR4 | 18/19 | 854 | 878142.68 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0