## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 44054113 | 43804352 | 45471432 | 45599447 | 2220000 | 46265450 | 5.618% | 100% | 1456501 | 3.325% | 1417319 | 3.217% | 1602 | 157 | 9.8% | 84 | 5.243% | 0 | 0% | 120 | 7.491% | 1722 | 7.491% | 1967 | 1615 | 1374 | -14.23% | 100%
| District Let | 13445742 | 13270989 | 13445742 | 13489614 | 0 | 13837853 | 4.271% | 100% | 26214 | 0.1975% | 0 | 0% | 710 | 59 | 8.31% | 50 | 7.042% | 14 | 1.972% | 0 | 0% | 724 | 1.972% | 833 | 799 | 690 | -2.817% | 100%
| All Contracts | 57499855 | 57075341 | 58917174 | 59089061 | 2220000 | 60103303 | 5.305% | 100% | 1482715 | 2.598% | 1417319 | 2.465% | 2312 | 216 | 9.343% | 134 | 5.796% | 14 | 0.6055% | 120 | 5.19% | 2446 | 5.796% | 2800 | 2414 | 2064 | -10.73% | 100%
2 | Central Let | 33108498 | 32739204 | 33962795 | 34329795 | 0 | 35222491 | 7.585% | 57.14% | 909845 | 2.779% | 854299 | 2.58% | 1759 | 414 | 23.54% | 201 | 11.43% | 67 | 3.809% | 276 | 15.69% | 2102 | 19.5% | 2717 | 2644 | 2029 | 15.35% | 57.14%
| District Let | 243628309 | 242959892 | 260616132 | 260743981 | 0 | 257856309 | 6.131% | 50% | 16989398 | 6.993% | 16987824 | 6.973% | 3869 | 674 | 17.42% | 483 | 12.48% | 54 | 1.396% | 1080 | 27.91% | 5003 | 29.31% | 6160 | 6103 | 4946 | 27.84% | 62.5%
| All Contracts | 276736807 | 275699096 | 294578927 | 295073776 | 0 | 293078800 | 6.304% | 53.33% | 17899243 | 6.492% | 17842123 | 6.447% | 5628 | 1088 | 19.33% | 684 | 12.15% | 121 | 2.15% | 1356 | 24.09% | 7105 | 26.24% | 8877 | 8747 | 6975 | 23.93% | 60%
3 | Central Let | 51575870 | 50870853 | 52553899 | 52753675 | 0 | 51991618 | 2.203% | 83.33% | 1042217 | 2.049% | 978028 | 1.896% | 2404 | 1042 | 43.34% | 348 | 14.48% | 101 | 4.201% | 165 | 6.864% | 2670 | 11.06% | 4060 | 4047 | 2657 | 10.52% | 75%
| District Let | 5198254 | 5059285 | 5197430 | 5199977 | 0 | 5351320 | 5.772% | 100% | 1808 | 0.03574% | -824 | -0.01585% | 455 | 166 | 36.48% | 107 | 23.52% | 21 | 4.615% | 1 | 0.2198% | 477 | 4.835% | 750 | 731 | 458 | 0.6593% | 100%
| All Contracts | 56774124 | 55930138 | 57751329 | 57953652 | 0 | 57342938 | 2.526% | 87.5% | 1044025 | 1.867% | 977204 | 1.721% | 2859 | 1208 | 42.25% | 455 | 15.91% | 122 | 4.267% | 166 | 5.806% | 3147 | 10.07% | 4810 | 4778 | 3115 | 8.954% | 81.25%
4 | Central Let | 30723181 | 30499914 | 31086653 | 29703521 | 0 | 30150825 | -1.145% | 100% | 255243 | 0.8369% | 363471 | 1.183% | 1262 | 211 | 16.72% | 99 | 7.845% | 0 | 0% | 38 | 3.011% | 1300 | 3.011% | 1610 | 1603 | 1293 | 2.456% | 100%
| District Let | 103315567 | 102865567 | 106307171 | 105876033 | -200000 | 101581093 | -1.249% | 100% | 2734404 | 2.658% | 2991604 | 2.896% | 3339 | 408 | 12.22% | 195 | 5.84% | 2 | 0.0599% | 352 | 10.54% | 3693 | 10.6% | 4295 | 3692 | 3089 | -7.487% | 100%
| All Contracts | 134038748 | 133365481 | 137393824 | 135579554 | -200000 | 131731918 | -1.225% | 100% | 2989647 | 2.242% | 3355075 | 2.503% | 4601 | 619 | 13.45% | 294 | 6.39% | 2 | 0.04347% | 390 | 8.476% | 4993 | 8.52% | 5905 | 5295 | 4382 | -4.76% | 100%
5 | Central Let | 79030602 | 78709602 | 82654005 | 82865699 | 14500 | 79744504 | 1.315% | 100% | 3704601 | 4.707% | 3623403 | 4.585% | 2170 | 173 | 7.972% | 192 | 8.848% | 0 | 0% | 56 | 2.581% | 2226 | 2.581% | 2591 | 2397 | 2032 | -6.359% | 100%
| District Let | 5056422 | 4935562 | 5190221 | 5128471 | 0 | 5125274 | 3.844% | 66.67% | 146652 | 2.971% | 133799 | 2.646% | 550 | 58 | 10.55% | 83 | 15.09% | 0 | 0% | 40 | 7.273% | 590 | 7.273% | 731 | 690 | 549 | -0.1818% | 100%
| All Contracts | 84087024 | 83645164 | 87844226 | 87994170 | 14500 | 84869778 | 1.464% | 85.71% | 3851253 | 4.604% | 3757202 | 4.468% | 2720 | 231 | 8.493% | 275 | 10.11% | 0 | 0% | 96 | 3.529% | 2816 | 3.529% | 3322 | 3087 | 2581 | -5.11% | 100%
6 | Central Let | 12805567 | 12507429 | 14988122 | 15120018 | 190000 | 14966941 | 19.66% | 85.71% | 2175974 | 17.4% | 2182555 | 17.04% | 1462 | 344 | 23.53% | 106 | 7.25% | 84 | 5.746% | 199 | 13.61% | 1745 | 19.36% | 2195 | 2102 | 1652 | 13% | 85.71%
| District Let | 90549956 | 90137827 | 95023682 | 94161886 | 400000 | 94334810 | 4.656% | 100% | 2487055 | 2.759% | 2941314 | 3.248% | 2520 | 398 | 15.79% | 132 | 5.238% | 0 | 0% | 28 | 1.111% | 2548 | 1.111% | 3078 | 2941 | 2411 | -4.325% | 100%
| All Contracts | 103355523 | 102645256 | 110011804 | 109281904 | 590000 | 109301751 | 6.485% | 92.31% | 4663029 | 4.543% | 5123869 | 4.958% | 3982 | 742 | 18.63% | 238 | 5.977% | 84 | 2.109% | 227 | 5.701% | 4293 | 7.81% | 5273 | 5043 | 4063 | 2.034% | 92.31%
7 | Central Let | 7911363 | 7656583 | 7929714 | 7571348 | 0 | 7481475 | -2.287% | 100% | 102383 | 1.337% | 18352 | 0.232% | 813 | 177 | 21.77% | 107 | 13.16% | 13 | 1.599% | 57 | 7.011% | 883 | 8.61% | 1167 | 1256 | 972 | 19.56% | 83.33%
| District Let | 46451865 | 46033365 | 48097165 | 47657412 | 250000 | 47409715 | 2.99% | 100% | 1434476 | 3.116% | 1645300 | 3.542% | 1602 | 605 | 37.77% | 191 | 11.92% | 0 | 0% | 77 | 4.806% | 1679 | 4.806% | 2475 | 2463 | 1667 | 4.057% | 100%
| All Contracts | 54363228 | 53689948 | 56026879 | 55228760 | 250000 | 54891190 | 2.237% | 100% | 1536859 | 2.862% | 1663652 | 3.06% | 2415 | 782 | 32.38% | 298 | 12.34% | 13 | 0.5383% | 134 | 5.549% | 2562 | 6.087% | 3642 | 3719 | 2639 | 9.275% | 91.67%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 47534366 | 47220946 | 47452800 | 47199246 | -45000 | 45953310 | -2.684% | 100% | 57760 | 0.1223% | -81566 | -0.1716% | 1337 | 127 | 9.499% | 72 | 5.385% | 84 | 6.283% | 48 | 3.59% | 1469 | 9.873% | 1668 | 1684 | 1485 | 11.07% | #VALUE!
| All Contracts | 47534366 | 47220946 | 47452800 | 47199246 | -45000 | 45953310 | -2.684% | 100% | 57760 | 0.1223% | -81566 | -0.1716% | 1337 | 127 | 9.499% | 72 | 5.385% | 84 | 6.283% | 48 | 3.59% | 1469 | 9.873% | 1668 | 1684 | 1485 | 11.07% | 100%
Totals This Qtr | Central Let | 259209194 | 256787937 | 268646620 | 267943503 | 2424500 | 265823304 | 3.519% | 87.23% | 9646764 | 3.757% | 9437427 | 3.641% | 11472 | 2518 | 21.95% | 1137 | 9.911% | 265 | 2.31% | 911 | 7.941% | 12648 | 10.25% | 16307 | 15664 | 12009 | 4.681% | 82.98%
| District Let | 555180481 | 552483433 | 581330343 | 579456620 | 405000 | 571449684 | 3.433% | 87.5% | 23877767 | 4.322% | 24617451 | 4.434% | 14382 | 2495 | 17.35% | 1313 | 9.129% | 175 | 1.217% | 1626 | 11.31% | 16183 | 12.52% | 19990 | 19103 | 15295 | 6.348% | 92.5%
| All Contracts | 814389675 | 809271370 | 849976963 | 847400123 | 2829500 | 837272988 | 3.46% | 87.36% | 33524531 | 4.143% | 34054878 | 4.182% | 25854 | 5013 | 19.39% | 2450 | 9.476% | 440 | 1.702% | 2537 | 9.813% | 28831 | 11.51% | 36297 | 34767 | 27304 | 5.608% | 87.36%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 100.8% | 1 | 410 | 11598 | 6 | 16 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM
| 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 87.63% | 1 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | 107.6% | 1 | -1499517 | 1891710 | 39 | 35 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 50.62% | 1 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 57.34% | 1 | 6509 | -485989 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 |  | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM
| 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 101.2% | 1 | 0 | 0 | 49 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66
| 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 100.7% | 1 | 0 | 0 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM
| 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 86.36% | 1 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 93.87% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM
| 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 86.15% | 1 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 99.42% | 1 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36
| 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 100% | 1 | 0 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM
| 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 69% | 1 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 100% | 1 | 0 | 0 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 9 | 11 | 26 | 1602 | 1967 | 1615 | 100% | 9 | 352 | 0 | 0 | 241 | 124 | 44054113 | 249761 | 43804352 | 45471432 | 45599447 | 0 | 2220000 | 2220000 | 47819447 | 46265450 | 100% | 9 | -1492598 | 1417319 | 157 | 84 | 0 | 0 | 808394 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -484189 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 0 | 120 | 1456501 | 4958
| 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 103.5% | 1 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 107% | 1 | 361384 | 0 | 43 | 24 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34
| 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 97.6% | 1 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | 101.6% | 1 | -783 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69
| 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 83.24% | 1 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | 98.1% | 1 | -12362 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 0 | 710 | 833 | 799 | 100% | 3 | 34 | 0 | 0 | 123 | 0 | 13445742 | 174753 | 13270989 | 13445742 | 13489614 | 0 | 0 | 0 | 13489614 | 13837853 | 100% | 3 | 348239 | 0 | 59 | 50 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0
| District 01 Totals |  |  |  |  | 12 | 15 | 26 | 2312 | 2800 | 2414 | 100% | 12 | 386 | 0 | 0 | 364 | 124 | 57499855 | 424514 | 57075341 | 58917174 | 59089061 | 0 | 2220000 | 2220000 | 61309061 | 60103303 | 100% | 12 | -1144359 | 1417319 | 216 | 134 | 0 | 0 | 808394 | 0 | 14 | 120 | 1395040 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -474888 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 14 | 120 | 1482715 | 4958
| 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | 135.9% | 0 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 100.6% | 1 | 7440 | 0 | 43 | 36 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45
| 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 126.9% | 0 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 111% | 0 | 45271 | 670366 | 127 | 43 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 |  | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54
| 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 119.8% | 1 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 102.4% | 1 | 15232 | 81763 | 65 | 48 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67
| 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 108.3% | 1 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 112.7% | 0 | 804997 | 8616 | 80 | 27 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07
| 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 130.9% | 0 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 113.6% | 0 | 80901 | 27471 | 62 | 25 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62
| 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 108.3% | 1 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 104.3% | 1 | 0 | 66083 | 30 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 |  | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7
| 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 65% | 1 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | 99.5% | 1 | -29525 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 |  | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 7 | 13 | 19 | 1759 | 2717 | 2644 | 57.14% | 4 | 73 | 13 | 0 | 682 | 276 | 33108498 | 369294 | 32739204 | 33962795 | 34329795 | -20592 | 0 | -20592 | 34309203 | 35222491 | 57.14% | 4 | 924316 | 854299 | 414 | 201 | 14 | 66 | 128634 | 0 | 0 | 121 | 548143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 83869 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 38 | 27471 | 27471 | 53 | 29 | 121338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 276 | 909845 | 27471
| 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 157.7% | 0 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | 110.5% | 0 | -1459708 | 16826383 | 385 | 223 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18219 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | 128.4% | 0 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | 97.09% | 1 | -1251611 | -606983 | 51 | 65 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 116.3% | 1 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 112.2% | 0 | 298956 | 30442 | 44 | 26 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25
| 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 170.6% | 0 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 123.3% | 0 | 110065 | 656701 | 89 | 38 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 |  | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79
| 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 103.5% | 1 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 96.37% | 1 | 2 | -3969 | 52 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60481 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 |  | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46
| 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 99.21% | 1 | 0 | 0 | 20 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 |  | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23
| 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 76.19% | 1 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 98.98% | 1 | 0 | 0 | 14 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 50 | 3869 | 6160 | 6103 | 62.5% | 5 | 57 | 18 | 0 | 1211 | 1080 | 243628309 | 668416 | 242959892 | 260616132 | 260743981 | -229932 | 0 | -229932 | 260514049 | 257856309 | 50% | 4 | -2290618 | 16987824 | 674 | 483 | 54 | 203 | 2278546 | 238783 | 0 | 639 | 14512417 | 1224199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 231 | 163837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78700 | 0 | 54 | 1080 | 16989398 | 1462982
| District 02 Totals |  |  |  |  | 15 | 26 | 69 | 5628 | 8877 | 8747 | 60% | 9 | 130 | 31 | 0 | 1893 | 1356 | 276736807 | 1037710 | 275699096 | 294578927 | 295073776 | -250524 | 0 | -250524 | 294823252 | 293078800 | 53.33% | 8 | -1366302 | 17842123 | 1088 | 684 | 68 | 269 | 2407180 | 238783 | 0 | 760 | 15060560 | 1224199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 233 | 247706 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 38 | 27471 | 27471 | 53 | 29 | 121338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78700 | 0 | 121 | 1356 | 17899243 | 1490453
| 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | 114.3% | 1 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | 90.98% | 1 | -1453386 | 157836 | 188 | 58 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28
| 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | 129.8% | 0 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | 96.12% | 1 | -84026 | 68219 | 39 | 20 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 |  | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84
| 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 121.7% | 0 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 106% | 1 | 8875 | 51756 | 76 | 28 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44
| 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 104.3% | 1 | 373777 | 60427 | 75 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485
| 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 102.1% | 1 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | 98.23% | 1 | -2508 | 0 | 76 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9
| 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 99.04% | 1 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 108.7% | 1 | 334168 | -32998 | 50 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16
| 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 96% | 1 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 98.38% | 1 | 0 | -2208 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43
| 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 104.2% | 1 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 114% | 0 | 321209 | 405998 | 157 | 26 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62
| 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 133.8% | 0 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 105.4% | 1 | 57366 | 27889 | 69 | 25 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76
| 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 100% | 1 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 114% | 0 | 100163 | 31248 | 167 | 43 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49
| 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 94.48% | 1 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | 107.9% | 1 | -464 | 209861 | 112 | 20 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000
| 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 95.56% | 1 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 101.7% | 1 | 0 | 0 | 22 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 12 | 18 | 29 | 2404 | 4060 | 4047 | 75% | 9 | 13 | 34 | 0 | 1491 | 165 | 51575870 | 705016 | 50870853 | 52553899 | 52753675 | -198291 | 0 | -198291 | 52555384 | 51991618 | 83.33% | 10 | -344826 | 978028 | 1042 | 348 | 0 | 62 | 596138 | 15783602 | 87 | 85 | 349417 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15342 | 10742 | 0 | 3 | 57843 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 23475 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 165 | 1042217 | 15812503
| 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 115.7% | 1 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 104.7% | 1 | 52521 | 0 | 13 | 25 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95
| 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 94.44% | 1 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 109.1% | 1 | 148555 | 3908 | 52 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8
| 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 97.78% | 1 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 102.4% | 1 | 0 | -4732 | 101 | 60 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-05-13 | QTR4 | 18/19 | 308 | 795145
| 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 84.44% | 1 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0% | 1 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 4 | 7 | 5 | 455 | 750 | 731 | 100% | 4 | 19 | 0 | 0 | 294 | 1 | 5198254 | 138969 | 5059285 | 5197430 | 5199977 | 0 | 0 | 0 | 5199977 | 5351320 | 100% | 4 | 156076 | -824 | 166 | 107 | 21 | 0 | 1500 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 1808 | 8288
| District 03 Totals |  |  |  |  | 16 | 25 | 34 | 2859 | 4810 | 4778 | 81.25% | 13 | 32 | 34 | 0 | 1785 | 166 | 56774124 | 843985 | 55930138 | 57751329 | 57953652 | -198291 | 0 | -198291 | 57755361 | 57342938 | 87.5% | 14 | -188750 | 977204 | 1208 | 455 | 21 | 62 | 597638 | 15783602 | 87 | 86 | 355281 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9786 | 19030 | 0 | 3 | 57843 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 23475 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 166 | 1044025 | 15820791
| 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 100.2% | 1 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 98.32% | 1 | 442812 | 198133 | 145 | 57 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 |  | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16
| 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 106.6% | 1 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 100.7% | 1 | 189028 | 165338 | 66 | 42 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 |  | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 2 | 6 | 12 | 1262 | 1610 | 1603 | 100% | 2 | 7 | 0 | 0 | 310 | 38 | 30723181 | 223268 | 30499914 | 31086653 | 29703521 | 0 | 0 | 0 | 29703521 | 30150825 | 100% | 2 | 631840 | 363471 | 211 | 99 | 0 | 8 | 236976 | 4956 | 0 | 0 | -147891 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 23912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 255243 | 5856
| 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 102.1% | 1 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | 95.08% | 1 | -417090 | -338192 | 219 | 89 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 95.23% | 1 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | 99.35% | 1 | -3249187 | 3281488 | 165 | 64 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 |  | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 113% | 1 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 99.98% | 1 | 2288 | 48308 | 23 | 34 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 |  | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12
| 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 30.92% | 1 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 100.3% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42
| 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 50.41% | 1 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 99.12% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 5 | 6 | 21 | 3339 | 4295 | 3692 | 100% | 5 | 603 | 0 | 0 | 605 | 351 | 103315567 | 450000 | 102865567 | 106307171 | 105876033 | -66765 | -200000 | -266765 | 105609268 | 101581093 | 100% | 5 | -3663989 | 2991604 | 408 | 195 | 2 | 173 | 2215972 | 7451 | 0 | 60 | 564009 | 73534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 352 | 2734404 | 115578
| District 04 Totals |  |  |  |  | 7 | 12 | 33 | 4601 | 5905 | 5295 | 100% | 7 | 610 | 0 | 0 | 915 | 389 | 134038748 | 673268 | 133365481 | 137393824 | 135579554 | -66765 | -200000 | -266765 | 135312789 | 131731918 | 100% | 7 | -3032149 | 3355075 | 619 | 294 | 2 | 181 | 2452948 | 12407 | 0 | 60 | 416118 | 74039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264874 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 23912 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 390 | 2989647 | 121434
| 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 102.4% | 1 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | 101.4% | 1 | -3056235 | 3576803 | 117 | 48 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 82.37% | 1 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | 100.9% | 1 | -14500 | 0 | 18 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75
| 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 76.58% | 1 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 101.2% | 1 | 0 | 26406 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410
| 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 112.8% | 1 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 99.75% | 1 | 6737 | 20194 | 36 | 48 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 4 | 7 | 42 | 2170 | 2591 | 2397 | 100% | 4 | 194 | 0 | 0 | 365 | 56 | 79030602 | 321000 | 78709602 | 82654005 | 82865699 | -56415 | 14500 | -41915 | 82823784 | 79744504 | 100% | 4 | -3063998 | 3623403 | 173 | 192 | 0 | 39 | 860988 | 25021 | 0 | 17 | 1256962 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322768 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 56 | 3704601 | 66084
| 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 85% | 1 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 100% | 1 | 0 | 0 | 21 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655
| 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 116.1% | 1 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | 109.1% | 1 | -3198 | 133799 | 15 | 33 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25
| 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | 113.3% | 1 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 114.4% | 0 | 0 | 0 | 22 | 3 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 5 | 550 | 731 | 690 | 100% | 3 | 41 | 1 | 0 | 141 | 40 | 5056422 | 120860 | 4935562 | 5190221 | 5128471 | 0 | 0 | 0 | 5128471 | 5125274 | 66.67% | 2 | -3198 | 133799 | 58 | 83 | 0 | 22 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 146652 | 9379
| District 05 Totals |  |  |  |  | 7 | 11 | 47 | 2720 | 3322 | 3087 | 100% | 7 | 235 | 1 | 0 | 506 | 96 | 84087024 | 441860 | 83645164 | 87844226 | 87994170 | -56415 | 14500 | -41915 | 87952255 | 84869778 | 85.71% | 6 | -3067196 | 3757202 | 231 | 275 | 0 | 61 | 912271 | 25021 | 0 | 35 | 1352331 | 50442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322768 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 96 | 3851253 | 75463
| 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 195.7% | 0 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 166% | 0 | 5872 | 2030258 | 59 | 33 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 105.5% | 1 | 21437 | 21903 | 44 | 6 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25
| 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 72.1% | 1 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | 103.4% | 1 | -191642 | 37940 | 56 | 14 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 |  | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 101.3% | 1 | 1476 | 92454 | 90 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 |  | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45
| 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 108.3% | 1 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | 99.99% | 1 | -4122 | 0 | 48 | 19 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 |  | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7
| 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | 92.06% | 1 | -1113 | 0 | 34 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 |  | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25
| 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 97.3% | 1 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | 98.31% | 1 | -24 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 606 | 324690
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 7 | 28 | 20 | 1462 | 2195 | 2102 | 85.71% | 6 | 93 | 0 | 0 | 534 | 199 | 12805567 | 298138 | 12507429 | 14988122 | 15120018 | 0 | 190000 | 190000 | 15310018 | 14966941 | 85.71% | 6 | -168116 | 2182555 | 344 | 106 | 15 | 24 | 843723 | 0 | 0 | 142 | 597552 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132116 | 32700 | 0 | 0 | 18823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 199 | 2175974 | 635053
| 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 95.74% | 1 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 99.71% | 1 | 1013 | 67062 | 142 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1
| 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 103.3% | 1 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 105% | 1 | 649560 | 1806784 | 96 | 54 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 84.26% | 1 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | 109.7% | 1 | -358123 | 1067468 | 84 | 14 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 80% | 1 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 93.85% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 |  | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8
| 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 97.08% | 1 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | 93.08% | 1 | -158 | 0 | 23 | 11 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2
| 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | 96.53% | 1 | -87 | 0 | 51 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 6 | 13 | 19 | 2520 | 3078 | 2941 | 100% | 6 | 137 | 0 | 0 | 530 | 28 | 90549956 | 412129 | 90137827 | 95023682 | 94161886 | 0 | 400000 | 400000 | 94561886 | 94334810 | 100% | 6 | 292205 | 2941314 | 398 | 132 | 0 | 28 | 1385511 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631983 | 48552 | 0 | 0 | 98023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2487055 | 169085
| District 06 Totals |  |  |  |  | 13 | 41 | 39 | 3982 | 5273 | 5043 | 92.31% | 12 | 230 | 0 | 0 | 1064 | 227 | 103355523 | 710267 | 102645256 | 110011804 | 109281904 | 0 | 590000 | 590000 | 109871904 | 109301751 | 92.31% | 12 | 124089 | 5123869 | 742 | 238 | 15 | 52 | 2229234 | 0 | 0 | 142 | 970235 | 152481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764099 | 81252 | 0 | 0 | 116846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 227 | 4663029 | 804138
| 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | 206.2% | 0 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 93.7% | 1 | 11195 | 18352 | 19 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400
| 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 99.3% | 1 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 99.75% | 1 | 69368 | 0 | 68 | 19 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000
| 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 111.1% | 1 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 99.28% | 1 | 6971 | 0 | 61 | 22 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM
| 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 91.82% | 1 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 98.93% | 1 | 0 | 0 | 24 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000
| 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 90.89% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5
| 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 93.17% | 1 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 100.7% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 6 | 10 | 1 | 813 | 1167 | 1256 | 83.33% | 5 | -89 | 112 | 0 | 297 | 57 | 7911363 | 254780 | 7656583 | 7929714 | 7571348 | -177408 | 0 | -177408 | 7393940 | 7481475 | 100% | 6 | 87534 | 18352 | 177 | 107 | 13 | 44 | 52993 | 0 | 0 | 13 | 48317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 57 | 102383 | 0
| 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 111.7% | 1 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | 105.4% | 1 | -265912 | 1412899 | 124 | 53 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 160448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1145625 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 105.5% | 1 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 104.4% | 1 | 301 | 232401 | 76 | 23 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26
| 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | 100.5% | 1 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 100.6% | 1 | 2402 | 0 | 242 | 27 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311
| 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 74% | 1 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 98.67% | 1 | 0 | 0 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000
| 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | 112.1% | 1 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | 98.97% | 1 | -14425 | 0 | 36 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38
| 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 100% | 1 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 90.04% | 1 | 0 | 0 | 106 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 6 | 13 | 12 | 1602 | 2475 | 2463 | 100% | 6 | 12 | 21 | 0 | 796 | 77 | 46451865 | 418500 | 46033365 | 48097165 | 47657412 | -72585 | 250000 | 177415 | 47834827 | 47409715 | 100% | 6 | -277634 | 1645300 | 605 | 191 | 0 | 14 | 1089265 | 51798 | 0 | 5 | 181683 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 163528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1434476 | 56150
| District 07 Totals |  |  |  |  | 12 | 23 | 13 | 2415 | 3642 | 3719 | 91.67% | 11 | -77 | 133 | 0 | 1093 | 134 | 54363228 | 673280 | 53689948 | 56026879 | 55228760 | -249993 | 250000 | 7 | 55228767 | 54891190 | 100% | 12 | -190100 | 1663652 | 782 | 298 | 13 | 58 | 1142258 | 51798 | 0 | 18 | 230000 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 163528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 134 | 1536859 | 56150
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | 114.8% | 1 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | 96.75% | 1 | -965750 | -115989 | 28 | 37 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 119.3% | 1 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 107% | 1 | 2296 | 34423 | 37 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26
| 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 97.14% | 1 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36
| 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 95.28% | 1 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 101.6% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4
| 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 99.33% | 1 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | 99.14% | 1 | -6566 | 0 | 44 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 5 | 5 | 5 | 1337 | 1668 | 1684 | #VALUE! | 5 | -16 | 24 | 0 | 283 | 48 | 47534366 | 313419 | 47220946 | 47452800 | 47199246 | -230916 | -45000 | -275916 | 46923330 | 45953310 | 100% | 5 | -970020 | -81566 | 127 | 72 | 0 | 21 | 191680 | 0 | 68 | 0 | 38539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -238385 | 0 | 0 | 0 | 30403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 48 | 57760 | 34423
| District 08 Totals |  |  |  |  | 5 | 5 | 5 | 1337 | 1668 | 1684 | 100% | 5 | -16 | 24 | 0 | 283 | 48 | 47534366 | 313419 | 47220946 | 47452800 | 47199246 | -230916 | -45000 | -275916 | 46923330 | 45953310 | 100% | 5 | -970020 | -81566 | 127 | 72 | 0 | 21 | 191680 | 0 | 68 | 0 | 38539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -238385 | 0 | 0 | 0 | 30403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 48 | 57760 | 34423
| Statewide Central Let Contracts SubTotal |  |  |  |  | 47 | 93 | 149 | 11472 | 16307 | 15664 | 82.98% | 39 | 643 | 159 | 0 | 3920 | 915 | 259209194 | 2421257 | 256787937 | 268646620 | 267943503 | -452706 | 2424500 | 1971794 | 269915297 | 265823304 | 87.23% | 41 | -3425848 | 9437427 | 2518 | 1137 | 42 | 243 | 3527846 | 15813579 | 87 | 498 | 4030627 | 96633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 212152 | 43837 | 0 | 3 | 86368 | 0 | 0 | 0 | -78086 | 0 | 0 | 53 | 47387 | 0 | 0 | 38 | 1520642 | 27471 | 136 | 62 | 706171 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | -406346 | 0 | 265 | 911 | 9646764 | 16551925
| Statewide District Let Contracts SubTotal |  |  |  |  | 40 | 65 | 117 | 14382 | 19990 | 19103 | 92.5% | 37 | 887 | 64 | 0 | 3983 | 1625 | 555180481 | 2697046 | 552483433 | 581330343 | 579456620 | -600198 | 405000 | -195198 | 579261422 | 571449684 | 87.5% | 35 | -6408939 | 24617451 | 2495 | 1313 | 77 | 461 | 7213757 | 298032 | 82 | 723 | 15787477 | 1431996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114400 | 0 | 16 | 289 | 847336 | 56840 | 0 | 0 | 128426 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | -1146 | 0 | 0 | 119 | 34593 | 34593 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | -281497 | 0 | 175 | 1626 | 23877767 | 1855885
| Statewide Totals |  |  |  |  | 87 | 158 | 266 | 25854 | 36297 | 34767 | 87.36% | 76 | 1530 | 223 | 0 | 7903 | 2540 | 814389675 | 5118303 | 809271370 | 849976963 | 847400123 | -1052904 | 2829500 | 1776596 | 849176719 | 837272988 | 87.36% | 76 | -9834787 | 34054878 | 5013 | 2450 | 119 | 704 | 10741603 | 16111611 | 169 | 1221 | 19818104 | 1528629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114400 | 0 | 16 | 303 | 1059488 | 100677 | 0 | 3 | 214794 | 0 | 0 | 0 | -78086 | 0 | 0 | 60 | 46241 | 0 | 0 | 157 | 1555235 | 62064 | 136 | 89 | 740594 | 604828 | 0 | 0 | 0 | 0 | 0 | 0 | -687843 | 0 | 440 | 2537 | 33524531 | 18407810

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P94 | 43493915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-18 | 9111251 | 9111251 | 9282956 | 0 | 0 | 9644340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 9289725
1 | E1R26 | 43319415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 604486 | 604486 | 584381 | 0 | 0 | 583598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584381 | 583598 | -783 | 489570
1 | E1R46 | 43806315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-19 | 3730005 | 3730005 | 3622277 | 0 | 0 | 3609915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 4986764
1 | T1636 | 43323815201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 1444112 | 1455710 | 1455710 | 11597.86 | 0 | 1456120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 1303711 | B0 | ACC - LUMP SUM
1 | T1664 | 20103265201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-02-22 | 39141064 | 41032774 | 41293102 | 1891709.53 | 2220000 | 42013585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220000 | 0 | 2220000 | 2220000 | 43513102 | 42013585 | -1499517 | 43211573 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1667 | 43494215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-08-31 | 1182957 | 696968 | 671825 | -485989.48 | 0 | 678334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671825 | 678334 | 6509 | 1125231 | B0 | ACC - LUMP SUM
1 | T1704 | 44011615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 211559 | 211559 | 204310 | 0 | 0 | 204310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204310 | 204310 | 0 | 255658
1 | T1714 | 43837615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 270550 | 270550 | 256893 | 0 | 0 | 256893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256893 | 256893 | 0 | 302948 | B0 | ACC - LUMP SUM
1 | T1732 | 43318515201 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2018-07-25 | 140241 | 140241 | 131642 | 0 | 0 | 131642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1734 | 43498815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 545828 | 545828 | 508665 | 0 | 0 | 508665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508665 | 508665 | 0 | 633612
1 | T1736 | 43320515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 789502 | 789502 | 749000 | 0 | 0 | 749000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749000 | 749000 | 0 | 784219 | B0 | ACC - LUMP SUM
1 | T1737 | 43826915201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 328300 | 328300 | 328300 | 0 | 0 | 328300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328300 | 328300 | 0 | 356575 | B0 | ACC - LUMP SUM
2 | E2P14 | 21330435201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2012-05-30 | 148792000 | 165618383 | 165903515 | 16826382.52 | 0 | 164443807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165903515 | 164443807 | -1459708 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2T34 | 43141825201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-04-15 | 79728458 | 79121474 | 78886236 | -606983.36 | -229932 | 77404693 | -229932 | 0 | 0 | 0 | 0 | 0 | -229932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -229932 | 78656304 | 77404693 | -1251611 | 80350658 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2V71 | 43430015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 4908173 | 4938615 | 5152163 | 30442.09 | 0 | 5451119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 4805500
2 | E2V95 | 43617015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 4081125 | 4737826 | 4860165 | 656701.41 | 0 | 4970230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 3223625
2 | E2W51 | 20950355201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1735075 | 1731106 | 1623863 | -3969.01 | 0 | 1623865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | 1877622
2 | E2W53 | 42849715201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1093189 | 1093189 | 1034914 | 0 | 0 | 1034914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 1735598
2 | E2X58 | 43205415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-18 | 1561255 | 1561255 | 1495849 | 0 | 0 | 1495849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 1989213
2 | T2612 | 42360825201 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2241677 | 2241677 | 2217516 | 0 | -20592 | 2204364 | -20592 | 0 | 0 | 0 | 0 | 0 | -20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20592 | 2196924 | 2204364 | 7440 | 1830224
2 | T2618 | 43091015201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 6623070 | 7293436 | 7244868 | 670365.84 | 0 | 7349062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7244868 | 7349062 | 104194 | 5699134
2 | T2658 | 41525215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 7921243 | 8003005 | 8095808 | 81762.66 | 0 | 8111040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 5941070
2 | T2683 | 43616215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 9121503 | 9130119 | 9355463 | 8616 | 0 | 10160460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 10382551
2 | T2686 | 43611815201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2698000 | 2725471 | 2926429 | 27470.55 | 0 | 3007330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 2798351
2 | T2688 | 43500115201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2018-01-31 | 1688461 | 1754543 | 1709557 | 66082.5 | 0 | 1709557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 1908915
2 | T2718 | 43762115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 2814544 | 2814544 | 2780154 | 0 | 0 | 2750630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 3342179
3 | E3P84 | 43625815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 1596199 | 1596199 | 1566048 | 0 | 0 | 1618568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 1614268
3 | E3Q52 | 43626715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 2737547 | 2741455 | 2788497 | 3908.32 | 0 | 2937051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2788497 | 2937051 | 148555 | 3367306
3 | E3R04 | 43627115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-06-14 | 819508 | 814776 | 800432 | -4732.46 | 0 | 800432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800432 | 800432 | 0 | 795145
3 | E3S64 | 4453671H201 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-04-16 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | -45000 | 32990
3 | T3471 | 41110225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-05-07 | 15000000 | 15157836 | 15093755 | 157836.02 | -129472 | 13510897 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 14814542
3 | T3488 | 40979275201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 3595027 | 3663247 | 3527855 | 68219.39 | -36334 | 3407495 | -25884 | 0 | 0 | 0 | 0 | -10450 | -36334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36334 | 3491521 | 3407495 | -84026 | 2839406
3 | T3584 | 42551925201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-09-27 | 4956085 | 5007841 | 5206085 | 51755.66 | 0 | 5214960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206085 | 5214960 | 8875 | 4588109
3 | T3621 | 43626115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 6338519 | 6398946 | 6159928 | 60426.55 | -3625 | 6530080 | 0 | 0 | 0 | 0 | 0 | -3625 | -3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3625 | 6156303 | 6530080 | 373777 | 7711485
3 | T3633 | 43188335201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-07-25 | 874222 | 874222 | 812103 | 0 | 0 | 809595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 1107452
3 | T3639 | 43078915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 5166455 | 5133457 | 5226570 | -32997.52 | 0 | 5560738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5226570 | 5560738 | 334168 | 5944823
3 | T3653 | 43672015201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-08-29 | 628643 | 626435 | 585546 | -2207.95 | 0 | 585546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585546 | 585546 | 0 | 728102
3 | T3655 | 43666315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 7611735 | 8017733 | 8305261 | 405997.54 | 0 | 8626470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8305261 | 8626470 | 321209 | 10033609
3 | T3661 | 43255915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 4168106 | 4195995 | 4262748 | 27889.1 | -3685 | 4316429 | 0 | 0 | 0 | 0 | 0 | -3685 | -3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3685 | 4259063 | 4316429 | 57366 | 3474587
3 | T3662 | 43627215201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 1790850 | 1822098 | 1908732 | 31248.18 | -25175 | 1983720 | 0 | 0 | 0 | 0 | 0 | -25175 | -25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25175 | 1883557 | 1983720 | 100163 | 2014996
3 | T3669 | 43046415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-05-23 | 1257739 | 1467600 | 1481515 | 209861.08 | 0 | 1481051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481515 | 1481051 | -464 | 1150000
3 | T3680 | 43815515201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2018-11-14 | 188489 | 188489 | 183577 | 0 | 0 | 183577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183577 | 183577 | 0 | 165102
4 | E4N95 | 43316515201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2014-04-28 | 15085307 | 14747115 | 14692678 | -338192.13 | 0 | 14275588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14692678 | 14275588 | -417090 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
4 | E4N98 | 42170745201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-01-17 | 85270000 | 88551488 | 88376026 | 3281487.8 | -266765 | 84860074 | -66765 | 0 | 0 | 0 | 0 | 0 | -66765 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -266765 | 88109261 | 84860074 | -3249187 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4T01 | 43630215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1711929 | 1760237 | 1659334 | 48308 | 0 | 1661623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 1640419
4 | E4T47 | 43995915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 874745 | 874745 | 827255 | 0 | 0 | 827255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827255 | 827255 | 0 | 2440132
4 | E4T53 | 44145715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-02-01 | 373586 | 373586 | 320740 | 0 | 0 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320740 | 320740 | 0 | 838047
4 | T4423 | 23033845201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 23950804 | 24148938 | 23087444 | 198133.26 | 0 | 23548540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23087444 | 23548540 | 461096 | 30953648
4 | T4465 | 42793815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 6772377 | 6937715 | 6616077 | 165337.71 | 0 | 6805105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616077 | 6805105 | 189028 | 7354282
5 | E5Z21 | 43927015201 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 3175000 | 3175000 | 3125000 | 0 | 0 | 3125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 2594655
5 | E5Z25 | 43685515201 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-07-03 | 1405000 | 1538799 | 1482098 | 133798.84 | 0 | 1478901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 1340492
5 | E5Z48 | 44096715201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 476422 | 476422 | 521373 | 0 | 0 | 521373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521373 | 521373 | 0 | 443061
5 | T5469 | 23920345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-10-30 | 67881735 | 71458538 | 71806238 | 3576803.2 | -56415 | 68693588 | 0 | 0 | 0 | 0 | 0 | -56415 | -56415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56415 | 71749823 | 68693588 | -3056235 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5588 | 43505915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 5555556 | 5555556 | 5533602 | 0 | 14500 | 5533602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0 | 0 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 7289680
5 | T5617 | 43505815201 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 3824000 | 3850406 | 3817535 | 26405.77 | 0 | 3817535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 4905410
5 | T5619 | 24099275201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-08-30 | 1769311 | 1789505 | 1708324 | 20194.25 | 0 | 1715061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 1940871
6 | E6J52 | 43337815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-06-09 | 8960958 | 9028019 | 8935693 | 67061.69 | 0 | 8936706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8935693 | 8936706 | 1013 | 6643198
6 | E6J69 | 43492215201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2016-04-15 | 69547000 | 72886197 | 72551371 | 1806784.32 | 0 | 73200931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72551371 | 73200931 | 649560 | 125147000 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K59 | 41831225201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-07-28 | 9488820 | 10556288 | 10367176 | 1067467.64 | 400000 | 10409054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 10767176 | 10409054 | -358123 | 9121391 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K87 | 43654015201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2018-11-29 | 342215 | 342215 | 303600 | 0 | 0 | 303600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303600 | 303600 | 0 | 394432
6 | E6L27 | 43081725201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 1584337 | 1584337 | 1427013 | 0 | 0 | 1426855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 1676992
6 | E6L83 | 44124315201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-26 | 626626 | 626626 | 577033 | 0 | 0 | 576947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577033 | 576947 | -87 | 611516
6 | T6401 | 41247395201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-03-29 | 3499047 | 5529305 | 5890497 | 2030258.17 | 0 | 5896369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890497 | 5896369 | 5872 | 3269401 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6403 | 43348915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 2123570 | 2145473 | 2165968 | 21903 | 0 | 2187405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 2459954
6 | T6406 | 42902215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-04-25 | 3211923 | 3249863 | 3270531 | 37940 | 190000 | 3268888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 3370172 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6436 | 43631115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1387410 | 1479864 | 1353258 | 92453.79 | 0 | 1354735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 1750082
6 | T6437 | 43634215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 1789134 | 1789134 | 1742305 | 0 | 0 | 1738184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 2085360
6 | T6451 | 42563725201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-31 | 666806 | 666806 | 585572 | 0 | 0 | 584459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 654200
6 | T6467 | 44289715201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-10-31 | 127677 | 127677 | 111887 | 0 | 0 | 111863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111887 | 111863 | -24 | 324690
7 | E7L26 | 40552525201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-08 | 25833397 | 27246296 | 27221715 | 1412898.86 | 250000 | 27205803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 27471715 | 27205803 | -265912 | 23085355 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7L58 | 43243415201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-10 | 5500000 | 5732401 | 5687839 | 232401.07 | 0 | 5688140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 4546054
7 | E7L77 | 42292935201 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2017-09-19 | 5595578 | 5595578 | 5582332 | 0 | -3645 | 5581090 | -3645 | 0 | 0 | 0 | 0 | 0 | -3645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3645 | 5578687 | 5581090 | 2402 | 3505311
7 | E7L98 | 43763715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 2248889 | 2248889 | 2169580 | 0 | 0 | 2169580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 2125000
7 | E7M06 | 44033815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 5327001 | 5327001 | 5287802 | 0 | -68940 | 5204437 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5218862 | 5204437 | -14425 | 6993269
7 | E7R06 | 44008915201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-08-22 | 1947000 | 1947000 | 1708144 | 0 | 0 | 1708144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7391 | 43269815201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 1680691 | 1699042 | 1672177 | 18351.56 | -177408 | 1505964 | -177408 | 0 | 0 | 0 | 0 | 0 | -177408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -177408 | 1494769 | 1505964 | 11195 | 1603400
7 | T7398 | 43473015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-25 | 2979236 | 2979236 | 2852469 | 0 | 0 | 2921837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 3840000
7 | T7404 | 43642015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1081175 | 1081175 | 1016734 | 0 | 0 | 1023706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 1150000 | B0 | ACC - LUMP SUM
7 | T7409 | 43649115202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-23 | 1575996 | 1575996 | 1509644 | 0 | 0 | 1509644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 1415000
7 | T7415 | 43982935201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 497590 | 497590 | 430440 | 0 | 0 | 430440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430440 | 430440 | 0 | 590001
7 | T7422 | 44275215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 96675 | 96675 | 89884 | 0 | 0 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89884 | 89884 | 0 | 182731
8 | E8N19 | 42935015201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-05-14 | 42645454 | 42529465 | 42335775 | -115989.17 | -256416 | 41113609 | -188916 | 0 | 0 | 0 | 0 | -22500 | -211416 | -45000 | 0 | 0 | 0 | 0 | 0 | -45000 | -256416 | 42079359 | 41113609 | -965750 | 44879640 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8Q91 | 43915315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 1568431 | 1602854 | 1622457 | 34422.76 | 0 | 1624753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 1431341
8 | E8R56 | 44290165201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-16 | 994137 | 994137 | 967509 | 0 | 0 | 967509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967509 | 967509 | 0 | 805668
8 | E8R57 | 44290175201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 679823 | 679823 | 674133 | 0 | -9500 | 664633 | 0 | 0 | 0 | 0 | 0 | -9500 | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9500 | 664633 | 664633 | 0 | 820726
8 | E8R59 | 44290185201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1646521 | 1646521 | 1599372 | 0 | -10000 | 1582806 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 1589372 | 1582806 | -6566 | 1947436

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [7 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total
01 |  | 4957.55 |  | 16346.31 | 0 | 0 | 21303.86 |  | 57499855 | 0.03705% | 21303.86
02 |  | 34970.19 |  | 107016.17 | 17083.6 | 1388072.94 | 1547142.9 |  | 276736807 | 0.05748% | 159069.96
03 |  | 10902.79 |  | 8287.64 | 15866927 | 19643.2 | 15905760.63 |  | 56774124 | 27.98% | 15886117.43
04 |  | 3827.94 |  |  | 48308 | 72620.86 | 124756.8 |  | 134038748 | 0.0389% | 52135.94
05 |  | 88278.04 |  |  | 0 | 2935.89 | 91213.93 |  | 84087024 | 0.105% | 88278.04
06 |  | 152646.91 |  | 0 | 482793.17 | 202677.5 | 838117.58 |  | 103355523 | 0.6148% | 635440.08
07 |  | 36742.37 |  | 0 | 0 | 19757.2 | 56499.57 |  | 54363228 | 0.06759% | 36742.37
08 |  | 0 |  |  | 34422.76 | 0 | 34422.76 |  | 47534366 | 0.07242% | 34422.76
Grand Total |  | 332325.79 |  | 131650.12 | 16449534.53 | 1705707.59 | 18619218.03 |  | 814389675 | 2.077% | 16913510.44
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days SA
01 |  | 120 |  | 0 | 0 | 4 | 124 |  | 120
02 |  | 38 |  | 64 | 83 | 1171 | 1356 |  | 185
03 |  | 16 |  | 0 | 59 | 91 | 166 |  | 75
04 |  | 0 |  |  | 30 | 359 | 389 |  | 30
05 |  | 18 |  |  | 0 | 78 | 96 |  | 18
06 |  | 0 |  | 0 | 0 | 227 | 227 |  | 0
07 |  | 13 |  | 0 | 0 | 121 | 134 |  | 13
08 |  | 0 |  |  | 27 | 21 | 48 |  | 27
Grand Total |  | 205 |  | 64 | 199 | 2072 | 2540 |  | 468
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
1 | 17 | 215 | 14 | 46 | 109 | 560 | 961 | 401 | 521 | 2312 | 22.53%
2 | 46 | 471 | 29 | 52 | 348 | 2968 | 3914 | 946 | 1131 | 5628 | 20.1%
3 | 10 | 577 |  | 271 | 455 | 4327 | 5640 | 1313 | 1388 | 2859 | 48.55%
4 |  | 263 | 48 | 168 | 522 | 1825 | 2826 | 1001 | 1031 | 4601 | 22.41%
5 |  | 35 |  |  | 27 | 288 | 350 | 62 | 80 | 2720 | 2.941%
6 | 24 | 150 | 3 | 77 | 233 | 3542 | 4029 | 487 | 487 | 3982 | 12.23%
7 |  | 253 |  | 61 | 16 | 471 | 801 | 330 | 343 | 2415 | 14.2%
8 |  | 49 |  |  | 112 | 971 | 1132 | 161 | 188 | 1337 | 14.06%
01 |  | 84 | 13 | 90 | 876 | 1345 | 2408 | 1063 | 1531 | 25854 | 5.922%
02
03
04
05
06
07
08
Grand Total | 97 | 2097 | 107 | 765 | 2698 | 16297 | 22061

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | T1636 | 43323815201 | 008 | 2 |  | 1 | 001 | 11597.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | [13 empty] | Avoidable, In-House CEI
01 | [13 empty] | Avoidable, CEI Consultant
01 | T1664 | 20103265201 | 005 | 2 |  | 1 | 112 | 5550 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 005 | 2 |  | 2 | 007 | -6645.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1664 | 20103265201 | 010 | 2 |  | 1 | 101 | 12870 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 015 | 2 |  | 1 | 919 | 61398.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 017 | 2 |  | 1 | 305 | -250655.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 1 | 012 | 11241.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 | 018 | 2 | 850 | 2 | 101 | 3746.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 3 | 107 | 5928.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 4 | 107 | 1619.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 5 | 112 | 1162.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 6 | 107 | 1619.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 7 | 022 | 4823.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 8 | 105 | 23626.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 9 | 115 | 9747.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 10 | 101 | 4544.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 11 | 101 | 721.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 1 | 105 | 82510 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 2 | 112 | 531.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 3 | 115 | 264.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 025 | 2 |  | 1 | 001 | 127697.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 026 | 2 |  | 1 | 001 | 97037.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 029 | 2 |  | 1 | 001 | 106486.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 030 | 2 |  | 1 | 001 | 74476.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 035 | 2 |  | 1 | 001 | 45733.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 036 | 2 |  | 1 | 922 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 037 | 2 |  | 1 | 001 | 14686.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 039 | 2 |  | 1 | 107 | 962861.32 | 0 | 1 |  | N | 120 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 1 | 105 | 33305.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 2 | 112 | 35452.32 | 4957.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 041 | 2 |  | 1 | 103 | 89278.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1664 | 20103265201 | 042 | 2 |  | 1 | 001 | 53578.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 046 | 2 |  | 1 | 004 | 21015.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1664 | 20103265201 | 047 | 2 |  | 1 | 001 | 10243.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 048 | 2 |  | 1 | 015 | -82748.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 049 | 2 |  | 1 | 015 | 293617.71 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 050 | 2 |  | 1 | 101 | 3163.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1667 | 43494215201 | 003 | 2 |  | 1 | 503 | -485989.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 001 | 2 |  | 1 | 119 | 9007933 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 002 | 2 |  | 1 | 008 | 34432.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 003 | 2 |  | 1 | 107 | 335329.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 004 | 2 |  | 1 | 008 | 35852.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 005 | 2 |  | 1 | 008 | 1018305.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 1 | 008 | 24819.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 2 | 350 | 16500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 3 | 119 | 107859.75 | 107859.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 4 | 008 | 769.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 5 | 008 | 51.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 007 | 2 |  | 1 | 008 | 91959.33 | 50678.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 008 | 2 |  | 1 | 119 | 240297.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 009 | 2 |  | 1 | 012 | 82871.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 1 | 119 | 134858.4 | 134858.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 2 | 012 | 15141.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 041 | 2 |  | 1 | 107 | 71091.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 048 | 2 |  | 1 | 008 | 234097.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 057 | 2 |  | 1 | 106 | 378046.76 | 378046.76 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 4 | 107 | 9637.19 | 9637.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 5 | 004 | 68634.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 6 | 012 | 26194.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 7 | 107 | 2623.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 8 | 008 | 7646.81 | 7646.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 9 | 012 | 2190.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 10 | 012 | 2491.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 11 | 350 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 12 | 012 | 935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 13 | 016 | 9846.33 | 9846.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 1 | 116 | 50933.24 | 50933.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 2 | 001 | 11645.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 3 | 018 | 14242.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 4 | 107 | 1378.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 5 | 008 | 4106.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 6 | 107 | 3916.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 7 | 107 | 2167.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 8 | 107 | 1355.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 9 | 119 | 52255.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 10 | 350 | 7998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 088 | 2 |  | 1 | 107 | 328688.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 094 | 2 |  | 1 | 107 | 2920117.97 | 0 | 0 |  | N | 152 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 098 | 2 |  | 1 | 012 | 28016.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 099 | 2 |  | 1 | 018 | 66169.53 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 102 | 2 |  | 1 | 917 | 54727.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 115 | 2 |  | 1 | 107 | 28829.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 115 | 2 |  | 2 | 003 | -10699.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 118 | 2 |  | 1 | 107 | 41480.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 119 | 2 |  | 1 | 116 | 149447.45 | 149447.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 1 | 350 | 5201.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 2 | 107 | 19858.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 3 | 107 | 9972.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 4 | 107 | 33966.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 5 | 012 | 17083.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 6 | 012 | 22540.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 7 | 122 | 3442.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 8 | 012 | 517.91 | 517.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 9 | 107 | -425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 10 | 120 | 2758.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 11 | 107 | 2156.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 12 | 107 | 2183.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 13 | 008 | 18841.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 14 | 012 | 11900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 122 | 2 |  | 1 | 019 | 180676.52 | 35226.03 | 0 |  | N | 110 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 1 | 008 | 185154.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 2 | 004 | -65070.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 132 | 2 |  | 1 | 919 | 153275.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 138 | 2 |  | 1 | 503 | 106762.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 138 | 2 |  | 2 | 305 | -18218.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 141 | 2 |  | 1 | 116 | 103438.51 | 0 | 0 |  | N | 132 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 1 | 350 | 26400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 2 | 107 | 6699.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 3 | 115 | 14880.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 4 | 003 | 2019.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 1 | 012 | 74208.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 2 | 008 | 191599.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 3 | 107 | 4680.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 4 | 107 | 1368.26 | 1368.26 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 5 | 107 | -252327.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 6 | 113 | -20345.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 1 | 003 | 5488.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 2 | 012 | 17083.6 | 17083.6 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 3 | 012 | 5886.77 | 5886.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 4 | 503 | 561.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 5 | 107 | 1642.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 6 | 012 | 4880.88 | 4880.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 158 | 2 |  | 1 | 115 | 194183.28 | 76566.34 | 0 |  | N | 138 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 1 | 004 | 11904.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 2 | 012 | 34522.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T34 | 43141825201 | 012 | 2 |  | 1 | 007 | -992697 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2T34 | 43141825201 | 016 | 2 |  | 1 | 015 | 28348.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 021 | 2 |  | 1 | 917 | 63655.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 023 | 2 |  | 1 | 015 | 48247.54 | 0 | 5 |  | N | 7 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 029 | 2 |  | 1 | 919 | 95462.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 038 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 231 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2U38 | 43226615201 | 007 | 2 |  | 1 | 015 | 35250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 | 012 | 2 | 850 | 1 | 015 | 40303.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V71 | 43430015201 | 005 | 2 |  | 1 | 101 | 11273.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 1 | 115 | 13591.19 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 2 | 107 | 5577 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 005 | 2 |  | 1 | 001 | 65939 | 0 | 2 |  | N | 5 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 1 | 012 | 25041.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 2 | 122 | 12630.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 3 | 012 | 7092.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 4 | 105 | 5236 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 1 | 105 | 11908.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 2 | 012 | 16133.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 4 | 107 | 6033.41 | 6033.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 5 | 105 | 4141.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 6 | 001 | 8937.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 7 | 105 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 023 | 2 |  | 1 | 001 | 174752.34 | 107016.17 | 2 |  | N | 59 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 023 | 2 |  | 2 | 119 | 135900.42 | 135900.42 | 0 |  | N | 37 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 1 | 119 | 163953.52 | 163953.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 2 | 119 | 10521.77 | 3960 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 3 | 122 | 5634.36 | 5634.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 1 | 305 | -60481.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 2 | 503 | 41803.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 3 | 503 | -17432.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 4 | 503 | 32141.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 003 | 2 | 850 | 1 | 113 | 13643.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 2 | 105 | 660.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 3 | 115 | 4338.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 4 | 001 | 622.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 5 | 001 | 5688.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 6 | 107 | 9211.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 9 | 503 | 1452 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 003 | 2 | 850 | 10 | 115 | 4987.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 11 | 008 | 370.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 12 | 115 | 4714.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 13 | 115 | 7179.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 15 | 001 | 559.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 16 | 107 | 187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 17 | 107 | 2238.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 18 | 001 | 3913.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 19 | 022 | 390.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 20 | 503 | 2249.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 022 | 2 | 850 | 1 | 015 | 10219.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 2 | 015 | 3509.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 3 | 015 | 2785.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 4 | 015 | 12807.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 028 | 2 |  | 1 | 101 | 319.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2618 | 43091015201 | 028 | 2 |  | 2 | 107 | 25124.74 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 029 | 2 |  | 1 | 001 | 29366.68 | 0 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 030 | 2 |  | 1 | 107 | 10312.9 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 2 | 107 | -2434.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 3 | 105 | -5067.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 4 | 005 | -4526.1 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 030 | 2 |  | 5 | 107 | 24915.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 6 | 107 | 155316.69 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 7 | 105 | 26397.58 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 8 | 105 | -11156.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 9 | 105 | 49750.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 10 | 012 | 5251.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 035 | 2 |  | 1 | 919 | 11029.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 036 | 2 |  | 1 | 005 | 58922.5 | 0 | 5 |  | C | 16 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 037 | 2 |  | 1 | 112 | 58922.5 | 0 | 5 |  | C | 17 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 | 040 | 2 | 850 | 1 | 850 | 66230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T2618 | 43091015201 | 042 | 2 |  | 1 | 106 | 4926.75 | 0 | 5 |  | C | 1 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2618 | 43091015201 | 044 | 2 |  | 1 | 005 | 65531.51 | 0 | 5 |  | C | 12 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2658 | 41525215201 | 002 | 2 |  | 1 | 119 | 6298.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 018 | 2 |  | 1 | 119 | 2847.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 029 | 2 |  | 1 | 106 | 5831.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2658 | 41525215201 | 030 | 2 |  | 1 | 108 | 66785.91 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2683 | 43616215201 | 001 | 2 |  | 1 | 101 | 8616 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 | 021 | 2 |  | 1 | 860 | 27470.55 | 27470.55 | 1 |  | N | 38 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
02 | T2688 | 43500115201 | 012 | 2 |  | 1 | 503 | 66082.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3Q52 | 43626715201 | 015 | 2 |  | 1 | 922 | 3908.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 012 | 2 |  | 1 | 503 | 19445.17 | 8287.64 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 013 | 2 |  | 1 | 503 | -25001.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 016 | 2 |  | 1 | 922 | 823.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3471 | 41110225201 | 038 | 2 |  | 1 | 009 | 157836.02 | 15783602 | 5 |  | N | 50 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
03 | T3488 | 40979275201 | 014 | 2 |  | 1 | 106 | 27272.89 | 9260.48 | 1 |  | N | 8 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 023 | 2 |  | 1 | 126 | 34898.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3488 | 40979275201 | 036 | 2 |  | 1 | 106 | 6047.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3584 | 42551925201 | 022 | 2 |  | 1 | 922 | 14487.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3584 | 42551925201 | 025 | 2 |  | 1 | 106 | 37268.2 | 0 | 5 |  | N | 9 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3621 | 43626115201 | 005 | 2 |  | 1 | 101 | 4400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 011 | 2 |  | 1 | 115 | 20856 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3621 | 43626115201 | 020 | 2 |  | 1 | 101 | 4107.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 026 | 2 |  | 1 | 503 | 31063.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3639 | 43078915201 | 005 | 2 |  | 1 | 503 | -51677.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3639 | 43078915201 | 016 | 2 |  | 1 | 922 | 18680.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3653 | 43672015201 | 004 | 2 |  | 1 | 503 | -2207.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 001 | 2 |  | 1 | 004 | 20837.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3655 | 43666315201 | 006 | 2 |  | 1 | 101 | 8408.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3655 | 43666315201 | 016 | 2 |  | 1 | 115 | -3179.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 017 | 2 |  | 1 | 113 | 24270.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 023 | 2 |  | 1 | 003 | 50951.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3655 | 43666315201 | 028 | 2 |  | 1 | 012 | 194848.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 | 029 | 2 |  | 1 | 503 | -1841.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 030 | 2 | 850 | 1 | 022 | 32893.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 038 | 2 |  | 1 | 922 | 61701.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3661 | 43255915201 | 019 | 2 |  | 1 | 115 | 27889.1 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 010 | 2 |  | 1 | 113 | -27605.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 019 | 2 |  | 1 | 113 | 48112.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 022 | 2 |  | 1 | 503 | 10741.57 | 10741.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3669 | 43046415201 | 014 | 2 |  | 1 | 922 | 124069.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3669 | 43046415201 | 016 | 2 |  | 1 | 119 | 85791.18 | 8898.63 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4N95 | 43316515201 | 038 | 2 |  | 1 | 108 | 80927.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N95 | 43316515201 | 045 | 2 |  | 1 | 007 | -501039.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 059 | 2 |  | 1 | 007 | -175009.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 066 | 2 |  | 1 | 007 | 139723.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 074 | 2 |  | 1 | 919 | 74739.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 1 | 004 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 2 | 003 | 42467.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 1 | 004 | 512217.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 2 | 004 | 80912.86 | 2099.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 3 | 004 | 27828.57 | 1135.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 4 | 004 | 25222.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 5 | 305 | -405594 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 6 | 305 | 202797 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 1 | 001 | 76519.47 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 2 | 001 | 58964.66 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 3 | 001 | 13868.01 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 4 | 001 | 26812.22 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 5 | 003 | 109945.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 6 | 004 | 103082.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 7 | 004 | 18931.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 8 | 004 | -37863.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 9 | 004 | -4121.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 10 | 001 | 8728.52 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 049 | 2 |  | 1 | 004 | 698225.65 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 057 | 2 |  | 1 | 917 | 51319.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 062 | 2 |  | 1 | 004 | 135891.29 | 1035.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 065 | 2 |  | 1 | 103 | 367136.55 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4N98 | 42170745201 | 066 | 2 |  | 1 | 019 | 3180 | 3180 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 2 | 019 | 25950.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 3 | 019 | 89627 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 071 | 2 |  | 1 | 004 | 323503.61 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 1 | 004 | 76630.3 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 2 | 001 | 15446.73 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 3 | 003 | 85830 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 089 | 2 |  | 1 | 919 | 238128.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 119 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4N98 | 42170745201 | 096 | 2 |  | 2 | 118 | 16352 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N98 | 42170745201 | 096 | 2 |  | 3 | 012 | 126196 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 4 | 105 | 25226.19 | 25226.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4N98 | 42170745201 | 097 | 2 |  | 1 | 860 | 34592.78 | 34592.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4T01 | 43630215201 | 012 | 2 |  | 1 | 106 | 48308 | 48308 | 5 |  | C | 30 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4423 | 23033845201 | 008 | 2 |  | 1 | 007 | 28826.31 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4423 | 23033845201 | 011 | 2 |  | 1 | 101 | 25597.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 1 | 503 | 3586.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 2 | 115 | 7175.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 3 | 115 | 1488.38 | 505.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 4 | 503 | 19932.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 5 | 001 | 1687.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 | 016 | 2 | 850 | 6 | 503 | 2621.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 7 | 107 | 9470.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 8 | 101 | 1925.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 9 | 503 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 10 | 107 | 2080.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 11 | 503 | 5106.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 12 | 503 | 2116.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 13 | 503 | 3540.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 14 | 108 | 44871.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 15 | 503 | 395.23 | 395.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 16 | 004 | 30502.97 | 4955.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 023 | 2 |  | 1 | 126 | -472515.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 023 | 2 |  | 3 | 107 | 7822.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 041 | 2 |  | 1 | 107 | 89275.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 1 | 919 | 100340.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 2 | 919 | 15399.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 3 | 919 | 12587.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 057 | 2 | 850 | 1 | 004 | 1998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 2 | 503 | 1656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 3 | 503 | 15643.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 4 | 503 | 18711.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 5 | 004 | 7497.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 6 | 503 | 2425.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 7 | 003 | 3067.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 8 | 503 | 4152.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 9 | 101 | 320.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 1 | 103 | 3849.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 2 | 126 | 11834.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 3 | 126 | 72235.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 4 | 126 | 2880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4465 | 42793815201 | 011 | 2 |  | 1 | 919 | 56207.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4465 | 42793815201 | 016 | 2 |  | 1 | 003 | 59130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 006 | 2 |  | 1 | 001 | 8350 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 009 | 2 |  | 1 | 001 | 42152.24 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 014 | 2 |  | 1 | 106 | 30026.4 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 014 | 2 |  | 2 | 107 | 14436.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 016 | 2 |  | 1 | 003 | 780.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 018 | 2 |  | 1 | 106 | 38052.85 | 9378.86 | 1 |  | N | 13 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 002 | 2 |  | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | T5469 | 23920345201 | 007 | 2 |  | 1 | 105 | -85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 2 | 105 | 90 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 3 | 101 | 2532.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345201 | 008 | 2 |  | 1 | 012 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 018 | 2 |  | 1 | 305 | -118789.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 037 | 2 |  | 1 | 305 | -36900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 1 | 015 | -140666.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 2 | 015 | 140177.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 1 | 015 | 14511.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 2 | 015 | 7737.37 | 7737.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 3 | 015 | 4467.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 4 | 015 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 5 | 015 | 7753.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 6 | 015 | 4425.24 | 4425.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 7 | 015 | -4878.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 053 | 2 |  | 1 | 115 | 4253.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 065 | 2 |  | 1 | 001 | 7824.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 084 | 2 |  | 1 | 001 | 47862.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 1 | 115 | 29323.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 2 | 128 | 4418.68 | 5852.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 3 | 118 | 3512.15 | 3512.15 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 4 | 115 | 1368.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 5 | 012 | 755.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 6 | 115 | 1412.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 7 | 001 | 3427.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 8 | 115 | 4195.68 | 1448.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 9 | 007 | 3053.54 | 3053.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 10 | 003 | 4367.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 11 | 003 | 3359.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 12 | 115 | 4926.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 13 | 003 | 648.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 14 | 115 | 414.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 15 | 105 | 3486.32 | 3941.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 16 | 115 | 3507.28 | 2981.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 17 | 115 | 2745.01 | 6459.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 18 | 115 | 4842.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 19 | 115 | 3329.19 | 3329.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 20 | 107 | 5539 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 21 | 107 | 656.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 22 | 003 | 2491.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 23 | 003 | 2506.76 | 2506.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 24 | 503 | 8499.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 085 | 2 | 850 | 25 | 118 | 8165.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 26 | 003 | 1134.64 | 1246 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 27 | 003 | 8500 | 6052.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 28 | 003 | 11812.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 29 | 118 | 6266.79 | 6266.79 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 30 | 118 | 2859.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 31 | 003 | 6571.65 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 1 | 003 | 7984.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 2 | 107 | 2621.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 101 | 2 |  | 1 | 107 | 13803.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 105 | 2 |  | 1 | 128 | 18863.98 | 3772.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 117 | 2 |  | 1 | 107 | 68509.21 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 118 | 2 |  | 1 | 003 | 63585.28 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 119 | 2 |  | 1 | 917 | 15282.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 121 | 2 |  | 1 | 503 | 308974.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 123 | 2 |  | 1 | 106 | 858359.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 124 | 2 |  | 1 | 012 | 5109.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 132 | 2 |  | 1 | 015 | 162028.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 133 | 2 |  | 1 | 725 | -78085.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
05 | T5469 | 23920345201 | 134 | 2 |  | 1 | 012 | 97231.95 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 135 | 2 |  | 1 | 106 | 8472.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 2 | 115 | 3500 | 3500 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 3 | 003 | 64550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 1 | 003 | 865 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 2 | 118 | 4609 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 138 | 2 |  | 1 | 003 | 71010.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 139 | 2 |  | 1 | 105 | 35202 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 140 | 2 |  | 1 | 860 | 1485000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5617 | 43505815201 | 002 | 2 |  | 1 | 106 | 18234.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 | 012 | 2 |  | 1 | 860 | 8171.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5619 | 24099275201 | 009 | 2 |  | 1 | 115 | -1091.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 | 011 | 2 |  | 1 | 003 | 21286.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099275201 | 022 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6J52 | 43337815201 | 018 | 2 |  | 1 | 919 | 67061.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6J69 | 43492215201 | 022 | 2 |  | 1 | 919 | 350222.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6J69 | 43492215201 | 024 | 2 |  | 1 | 007 | 765311 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 1 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 2 | 022 | 47165.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 3 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 041 | 2 | 850 | 1 | 003 | 58696.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 042 | 2 |  | 1 | 503 | 202835.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J69 | 43492215201 | 043 | 2 |  | 1 | 012 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 | 043 | 2 |  | 2 | 003 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 046 | 2 |  | 1 | 503 | 69191.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 011 | 2 |  | 1 | 503 | 132107.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 016 | 2 |  | 1 | 919 | 101999.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 026 | 2 |  | 1 | 001 | 108531.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 027 | 2 |  | 1 | 001 | 96922.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 1 | 503 | 2628.98 | 2628.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 2 | 106 | 18274.76 | 18274.76 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 3 | 001 | 5096.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 4 | 001 | 6472.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 5 | 106 | 10476.52 | 10476.52 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 6 | 903 | -2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 7 | 903 | 1482.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 8 | 004 | 51700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 1 | 503 | 45923.49 | 45923.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 2 | 503 | 24333.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 3 | 503 | 2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 4 | 503 | 11861.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 5 | 503 | 5012.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 035 | 2 |  | 1 | 105 | 148644.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | E6K59 | 41831225201 | 035 | 2 |  | 2 | 503 | -11623.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 1 | 503 | 5614.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 2 | 118 | 17005.68 | 17005.68 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 3 | 118 | 70879.02 | 70879.02 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 1 | 118 | 3896.81 | 3896.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 2 | 503 | 1750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 3 | 503 | 17040.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 4 | 115 | 12183.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 | 039 | 2 |  | 1 | 503 | 111333 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 008 | 2 |  | 1 | 001 | 75198.42 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 2 | 015 | 46947.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 3 | 101 | 5581.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6401 | 41247395201 | 008 | 2 |  | 4 | 103 | 21097.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 011 | 2 |  | 1 | 919 | 47416.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 1 | 001 | 30840.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 2 | 115 | 5055 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 3 | 103 | 4060.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 4 | 012 | 2608.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 5 | 118 | 7435.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 1 | 118 | 7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 2 | 503 | 32700 | 32700 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 014 | 2 | 850 | 3 | 118 | -7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 4 | 118 | 7311.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 5 | 503 | 8987.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 016 | 2 |  | 1 | 001 | 143032.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 019 | 2 |  | 1 | 001 | 105307.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 020 | 2 |  | 1 | 005 | 134857.01 | 134857.01 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 024 | 2 |  | 1 | 001 | 22284.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 024 | 2 |  | 2 | 115 | 67637.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 024 | 2 |  | 3 | 503 | 30856.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 024 | 2 |  | 4 | 005 | 8035.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 026 | 2 |  | 1 | 005 | 277982.41 | 277982.41 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 027 | 2 |  | 1 | 001 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 027 | 2 |  | 2 | 007 | 198705 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 1 | 919 | 87170.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 2 | 005 | 40374.14 | 40374.14 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 032 | 2 |  | 1 | 005 | 24196.79 | 24196.79 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 033 | 2 |  | 1 | 001 | 59302.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 033 | 2 |  | 2 | 115 | 1461.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 033 | 2 |  | 3 | 005 | 5320.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 034 | 2 |  | 1 | 018 | 62435.91 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6401 | 41247395201 | 035 | 2 |  | 1 | 115 | 97151.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 036 | 2 |  | 1 | 001 | 6366.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 036 | 2 |  | 2 | 005 | 92994.54 | 92994.54 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 3 | 023 | 16568.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 4 | 115 | 238476 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6403 | 43348915201 | 015 | 2 |  | 1 | 001 | 21903 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 | 015 | 2 |  | 1 | 101 | 3440 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6406 | 42902215201 | 019 | 2 | 850 | 1 | 503 | 12484.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6436 | 43631115201 | 013 | 2 |  | 1 | 103 | 92453.79 | 31947.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7L26 | 40552525201 | 002 | 2 |  | 1 | 001 | 318367.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 011 | 2 |  | 1 | 001 | 35650.27 | 35650.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 012 | 2 |  | 1 | 003 | 16147.9 | 16147.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 1 | 503 | 15055.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 2 | 101 | 836 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 3 | 115 | 6134.96 | 742.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 5 | 503 | 1936.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 6 | 503 | 2047.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 7 | 503 | 24254.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 8 | 503 | 13714.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 10 | 503 | 22226.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 12 | 503 | 13795.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 021 | 2 |  | 1 | 115 | 124417.08 | 3609.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 025 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 026 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 027 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 029 | 2 |  | 1 | 003 | 396759.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 030 | 2 |  | 1 | 919 | 147479.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 045 | 2 | 850 | 1 | 850 | 124077.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L58 | 43243415201 | 005 | 2 |  | 1 | 012 | 88378.63 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 2 | 105 | 3660.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 3 | 012 | 15290.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 4 | 012 | 4306.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 5 | 001 | 15518.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 6 | 105 | 3108.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 7 | 003 | 12716.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 8 | 012 | 333.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 9 | 012 | 61531.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 10 | 003 | 24948.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 11 | 012 | 2608.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7391 | 43269815201 | 010 | 2 |  | 1 | 012 | 18351.56 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N19 | 42935015201 | 001 | 2 |  | 1 | 503 | -350000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 002 | 2 |  | 1 | 004 | 106869.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 | 024 | 2 |  | 1 | 003 | 29393.56 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 | 039 | 2 |  | 1 | 503 | 97747.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q91 | 43915315201 | 008 | 2 |  | 1 | 005 | 34422.76 | 34422.76 | 5 |  | N | 27 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 105 | 9801.38 | 9801.38 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 503 | 7821.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 503 | 1480.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 112 | 6544.93 | 6544.93 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 3 | 118 | 566.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 4445.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 62.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 56.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 98.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 14.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 84655.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 107 | 7100.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 3 | 101 | 84.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 28.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 1317.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 126.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 012 | 22495.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 012 | 7879.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 253.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 239.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 70.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 324.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 0.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 464.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | -225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1714 | 43837615201 |  | 2 | CPI | 1 | 503 | 1800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 35948 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2554.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 2122.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 3638.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 1419 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7378 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 14045.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 11000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7898.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 18667.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 11283.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 2729.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2256.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 1092.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 1128.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | -32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 436.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 95245.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 115 | 4293.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 115 | 16649.6 | 16649.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 003 | 31147.2 | 31147.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 2664.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825601 |  | 2 | CPI | 1 | 015 | 18416.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 105 | 13024 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 015 | 2816 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 001 | 6260.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 001 | 16656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 2 | 015 | 29397.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 8419.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 8320.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 118 | 17550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 1072.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 2 | 007 | 1393.67 | 1393.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 2319.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 7371.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 003 | 4771.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 3434.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 32103.81 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W51 | 20950355201 |  | 2 | CPI | 1 | 108 | 5910.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W53 | 42849715201 |  | 2 | CPI | 1 | 120 | 18271.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 1633.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 2534.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 101 | 3882.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 005 | 1410 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 3 | 001 | 1284.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 4 | 103 | 2706.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 1022.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 299.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 3340.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 11250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 112 | 22753.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 718.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 126 | 629.64 | 629.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 7570 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 012 | 2008.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 113 | 7913.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 5215.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 7342.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 2658.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | -8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 007 | 4719.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 3686.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 115 | 4440.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 13120.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 3762 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 5 |  | N | 25 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 4949.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 2 | 101 | 6664.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 3 | 101 | 2542.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 4 | 012 | 5379.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 6870 | 6870 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43671715201 |  | 2 | CPI | 1 | 101 | 862.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 5001.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R04 | 43627115201 |  | 2 | CPI | 1 | 004 | 1500 | 336 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 3716.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 001 | 7581.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 010 | 2008.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | -41662.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 023 | 1485 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 115 | 4510.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3471 | 41110225201 |  | 2 | CPI | 3 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 1281.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 12642.28 | 1306.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3584 | 42551925201 |  | 2 | CPI | 1 | 922 | 4452.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3621 | 43626115201 |  | 2 | CPI | 1 | 115 | 5375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 1084.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 2 | 503 | 7987.77 | 3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 101 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 8667.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 4880.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 2 | 115 | 5064 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 3 | 128 | 7675.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 128 | 9900 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 6550.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 35155.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 17711.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 2 | 010 | 16468.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 23464.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 6938.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 686.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 2 | 101 | 2225 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 3 | 101 | 697.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 4 | 015 | 7220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 1 | 007 | 1598.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 2 | 007 | 12350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 3250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 2 | 503 | 4300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 012 | 10230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 24665 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 22703.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 2 | 503 | 14825.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 3 | 503 | 27357.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 917 | 8455.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 12345.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 503 | 41494.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 001 | 32335.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 18563.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 8321.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 31709.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 7017.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 105 | 22758.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T47 | 43995915201 |  | 2 | CPI | 1 | 012 | 10355.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T53 | 44145715201 |  | 2 | CPI | 1 | 503 | 3899.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 1150.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 107 | 655.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 107 | 705.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 001 | 11760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 001 | 43721.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 012 | 2194.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 010 | 15343.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 22000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 115 | 3322.8 | 3322.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 20881.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 001 | 21724.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 004 | 1713.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 503 | 4826.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 4427.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 112 | 14368.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 15261.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 2 | 112 | 2979.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 3 | 112 | 4392.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 17253 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 2112 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 1468.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 8568.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | E | 30 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 115 | 7195.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 009 | 32447.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 117 | 3295.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3266.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 3359.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 7003.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 3053.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3531 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 012 | 14850.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 53568.73 | 14060.7 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 29101.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 2716.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 120 | 22876.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 21177.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 101 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 25020.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 4011.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 4374.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 1210 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 001 | 986.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 1434.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 6514.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 004 | 1689.89 | 1689.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 107 | 17747.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 10206.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 811.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 008 | 9339.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 8726.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 004 | 1158.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 503 | -460.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 8490.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 3714.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 7694.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 503 | 3372.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 6632.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 2 | 107 | 5618.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | -2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | -1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 503 | 2382.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 023 | 3653.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 6054.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 024 | 834.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 001 | 5764.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 003 | 311.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 115 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 106 | 3337.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 3 | 007 | 15653.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 007 | 5217.8 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | -1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | -536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 9340.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 1478.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 82125.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 24530.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 003 | 5805.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 2156.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 101 | 51824.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 115 | 18518.16 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 106 | 20980.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 503 | 9886.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 007 | 23363.88 | 23363.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 004 | 3883.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 023 | 1648.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725202 |  | 2 | CPI | 1 | 503 | 1459.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 |  | 2 | CPI | 1 | 001 | 17895 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395602 |  | 2 | CPI | 1 | 001 | 925.87 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247375202 |  | 2 | CPI | 1 | 001 | 2139.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395202 |  | 2 | CPI | 1 | 503 | 3600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6403 | 43348915201 |  | 2 | CPI | 1 | 105 | 5280 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 3 | 123 | 6410.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 4 | 001 | 16985.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 6 | 007 | 2554.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 2 | 024 | 2255.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 5 | 115 | 16061.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 1 | 001 | 2882.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 |  | 2 | CPI | 2 | 118 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 3 | 503 | 14596.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902215201 |  | 2 | CPI | 4 | 503 | 9515 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 1 | 503 | 2610.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 2 | 503 | 6811.21 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 003 | 1293.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 123 | 16438.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 007 | 1775.31 | 1775.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 2 | 007 | 8840.65 | 8840.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6451 | 42563725201 |  | 2 | CPI | 1 | 503 | 9954.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 37275.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 007 | 3039.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 3 | 503 | 7920.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 12425.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 32302.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 17997.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2565 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 1 | 007 | 1821.18 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 40552525601 |  | 2 | CPI | 2 | 503 | 962.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 3 | 503 | 484.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2779.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7L77 | 42292935201 |  | 2 | CPI | 1 | 012 | 9843.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L77 | 42292935201 |  | 2 | CPI | 2 | 115 | 33659.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 6160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L98 | 43763715201 |  | 2 | CPI | 2 | 101 | 3707 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 3 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7R06 | 44008915201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Test Projects | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 15807.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 118 | 18795.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 4250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 1116 | 350 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 012 | 4040.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 657.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 101 | 3039.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 13157.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 007 | 9885.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 3521.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 3 | 101 | 4052.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 3371.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 2 | 113 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 3 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7415 | 43982935201 |  | 2 | CPI | 4 | 005 | 1072.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7422 | 44275215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 3 | 112 | 1263 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 021 | 3245 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 19190.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 003 | 26337.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 003 | 3174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 120.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 82.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 503 | 99.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 4653 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 5.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 3 | 118 | 5702.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 4 | 012 | 2061.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 5 | 503 | 113 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 6 | 503 | 6060.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 350 | 1100 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 171.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 118 | 11649.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 101 | 3459.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 106 | 7996.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 023 | 3567.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 022 | 23590.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 886.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 441.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 1513.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 4753.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 115 | 7181.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 107 | 1701.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1D88 | 41284415201 | 901 |  | 8 | 009 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | [9 empty] | Unavoidable, No Remedial Action Required
07 | [9 empty] | Unavoidable, No Remedial Action Required
06 | [9 empty] | Unavoidable, No Remedial Action Required
05 | [9 empty] | Avoidable, Third Party
04 | [9 empty] | Avoidable, In-House Designer
03 | [9 empty] | Avoidable, In-House CEI
02 | [9 empty] | Avoidable, Design Consultant
01 | E1D88 | 41284415201 | 503 |  | 7 | 009 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1F04 | 41284815201 | 119 |  | 7 | 020 | 1 | 2 | N | Avoidable, In-House Designer | Major Sturctural Component Changes | Plan Modifications | 2
01 | E1F04 | 41284815201 | 130 |  | 20 | 020 | 2 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
01 | E1F77 | 42098315201 | 009 |  | 46 | 002 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1F94 | 42149055201 | 001 |  | 23 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1F94 | 42149055201 | 128 |  | 30 | 008 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1G13 | 42174015201 | 005 |  | 2 | 002 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1G56 | 42314915201 | 012 |  | 7 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1G63 | 19794225201 | 001 |  | 7 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1G81 | 41473815201 | 012 |  | 16 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1H20 | 42378915201 | 019 |  | 3 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | E1H23 | 19801045201 | 009 |  | 22 | 029 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1H23 | 19801045201 | 012 |  | 93 | 034 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1H23 | 19801045201 | 012 |  | 29 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1H53 | 42674015201 | 405 |  | 1 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1H60 | 42513615201 | 007 |  | 5 | 010 | 1 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | E1H76 | 41103615201 | 503 |  | 2 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1H79 | 42240415201 | 019 |  | 8 | 005 | 1 | 5 | N | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
01 | E1H79 | 42240415201 | 007 |  | 42 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1H79 | 42240415201 | 005 |  | 11 | 019 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1H79 | 42240415201 | 005 |  | 7 | 020 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1H79 | 42240415201 | 018 |  | 1 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | E1H79 | 42240415201 | 005 |  | 16 | 022 | 1 | 5 | C | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1H79 | 42240415201 | 005 |  | 64 | 025 | 1 | 5 | C | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1H79 | 42240415201 | 012 |  | 2 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1H79 | 42240415201 | 001 |  | 40 | 036 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1H99 | 40546245201 | 007 |  | 73 | 013 | 1 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | E1I17 | 42800415201 | 009 |  | 45 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1I19 | 42812615201 | 503 |  | 20 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1I41 | 19533825201 | 130 |  | 40 | 004 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
01 | E1J08 | 42343715201 | 130 |  | 15 | 008 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
01 | E1J13 | 42740815201 | 112 |  | 44 | 009 | 1 | 1 | C | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1J50 | 42977515201 | 115 |  | 16 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1J52 | 42977615201 | 106 |  | 37 | 015 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1J61 | 41394325201 | 007 |  | 18 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1J61 | 41394325201 | 001 |  | 5 | 007 | 1 | 1 | N | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1J63 | 42735115201 | 115 |  | 19 | 002 | 1 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
01 | E1J68 | 42522815201 | 001 |  | 2 | 002 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1J68 | 42522815201 | 115 |  | 3 | 002 | 2 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1J68 | 42522815201 | 001 |  | 5 | 002 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1J69 | 20074625201 | 009 |  | 9 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1K74 | 42893715201 | 503 |  | 16 | 023 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1K75 | 20121435201 | 005 |  | 440 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1L18 | 42987915201 | 106 |  | 5 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1L19 | 42334015201 | 019 |  | 7 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | E1L39 | 42997815201 | 130 |  | 13 | 014 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | E1L58 | 19753445201 | 009 |  | 129 | 065 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1L60 | 43134415201 | 115 |  | 1 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1L80 | 43000515201 | 012 |  | 1 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1M02 | 43266015201 | 005 |  | 21 | 015 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1M72 | 43385115201 | 106 |  | 21 | 008 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1M90 | 43193715201 | 106 |  | 1 | 007 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1N06 | 43193915201 | 106 |  | 9 | 014 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1N08 | 42347115201 | 106 |  | 7 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1N67 | 43121315201 | 106 |  | 7 | 008 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1N91 | 43526915201 | 130 |  | 21 | 008 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
01 | E1O46 | 43654515201 | 022 |  | 14 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
01 | E1O48 | 43129415201 | 503 |  | 9 | 018 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1O53 | 43486515201 | 012 |  | 14 | 011 | 1 | 1 | N | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
01 | E1P47 | 43771415201 | 007 |  | 33 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1P86 | 43496115201 | 503 |  | 1 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 | 118 |  | 14 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q46 | 43659915201 | 001 |  | 15 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 001 |  | 3 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q46 | 43659915201 | 001 |  | 1 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q76 | 43494115201 | 018 |  | 6 | 001 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | E1Q77 | 43189515201 | 024 |  | 27 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | T1012 | 19573615201 | 019 |  | 1 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | T1022 | 19573715201 | 503 |  | 10 | 059 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1032 | 19753315201 | 115 |  | 7 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1032 | 19753315201 | 115 |  | 9 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1032 | 19753315201 | 115 |  | -6 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1055 | 20073215201 | 901 |  | 4 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 902 |  | 6 | 007 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 903 |  | 4 | 007 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 904 |  | 4 | 007 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 905 |  | 6 | 027 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 906 |  | 6 | 027 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 907 |  | 4 | 027 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 908 |  | 6 | 027 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1055 | 20073215201 | 909 |  | 3 | 028 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | T1108 | 20096615201 | 001 |  | 3 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1108 | 20096615201 | 003 |  | 3 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1108 | 20096615201 | 015 |  | 3 | 026 | 1 | 1 | N | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1108 | 20096615201 | 015 |  | 2 | 027 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1108 | 20096615201 | 001 |  | 5 | 028 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1108 | 20096615201 | 700 |  | 30 | 036 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1108 | 20096615201 | 123 |  | 2 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
01 | T1108 | 20096615201 | 007 |  | 3 | 037 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1108 | 20096615201 | 007 |  | 4 | 037 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1108 | 20096615201 | 007 |  | 13 | 046 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1110 | 19539925201 | 001 |  | 2 | 003 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1110 | 19539925201 | 007 |  | 21 | 005 | 1 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1110 | 19539925201 | 005 |  | 18 | 005 | 2 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1110 | 19539925201 | 503 |  | 27 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1110 | 19539925201 | 007 |  | 2 | 009 | 1 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1110 | 19539925201 | 001 |  | 4 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1112 | 19375025201 | 503 |  | 46 | 002 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1112 | 19375025201 | 403 |  | 28 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
01 | T1124 | 19733225201 | 001 |  | 63 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1124 | 19733225201 | 018 |  | 6 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | T1124 | 19733225201 | 007 |  | 2 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1192 | 41724815201 | 018 |  | 2 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | T1195 | 41712915201 | 122 |  | 52 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1197 | 41723815201 | 103 |  | 50 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1204 | 19847815201 | 001 |  | 1 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1209 | 19576615201 | 007 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1224 | 41544915201 | 130 |  | 17 | 006 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
01 | T1224 | 41544915201 | 007 |  | 4 | 006 | 2 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1224 | 41544915201 | 007 |  | 50 | 007 | 1 | 5 | N | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1227 | 19602235201 | 405 |  | 2 | 059 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1227 | 19602235201 | 405 |  | 12 | 060 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1238 | 41724415201 | 016 |  | 98 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
01 | T1242 | 40818525201 | 018 |  | 2 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
01 | T1255 | 41734215201 | 003 |  | 24 | 015 | 1 | 0 | E | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1255 | 41734215201 | 122 |  | 5 | 015 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1265 | 19607625201 | 001 |  | 8 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1288 | 19596825201 | 010 |  | 4 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
1 | T1288 | 19596825201 | 115 |  | 4 | 22 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 115 |  | 1 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 115 |  | 6 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 3 |  | 6 | 25 | 900 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 115 |  | 5 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 12 |  | 7 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 115 |  | 5 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1288 | 19596825201 | 108 |  | 3 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1299 | 19420125201 | 9 |  | 11 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1315 | 19748525201 | 128 |  | 21 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
1 | T1326 | 19553635201 | 5 |  | 24 | 7 | 1 | 5 | N | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
1 | T1331 | 42240115201 | 115 |  | 31 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1359 | 42249515201 | 405 |  | 4 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1368 | 41994715201 | 5 |  | 11 | 4 | 1 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
1 | T1373 | 40631435201 | 450 |  | 1 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
1 | T1373 | 40631435201 | 503 |  | 2 | 36 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1373 | 40631435201 | 18 |  | 1 | 47 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1373 | 40631435201 | 503 |  | 2 | 54 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1373 | 40631435201 | 18 |  | 1 | 61 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1379 | 42239615201 | 105 |  | 10 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
1 | T1399 | 41103715201 | 503 |  | 2 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1402 | 19756225201 | 112 |  | 49 | 18 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1403 | 19448515201 | 13 |  | 23 | 35 | 1 | 5 | N | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1411 | 40826865201 | 9 |  | 17 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1417 | 41612015201 | 115 |  | 3 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1417 | 41612015201 | 1 |  | 6 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1417 | 41612015201 | 115 |  | 5 | 39 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
1 | T1417 | 41612015201 | 112 |  | 6 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1417 | 41612015201 | 112 |  | 6 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1417 | 41612015201 | 7 |  | 4 | 50 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1429 | 42728715201 | 108 |  | 4 | 2 | 1 | 2 | N | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1430 | 42063315201 | 8 |  | 16 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1454 | 20074115201 | 9 |  | 3 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1454 | 20074115201 | 108 |  | 19 | 20 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1454 | 20074115201 | 7 |  | 8 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1458 | 42730615201 | 12 |  | 1 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
1 | T1461 | 42584315201 | 112 |  | 5 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1463 | 41736515201 | 106 |  | 5 | 4 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
1 | T1471 | 42524115201 | 503 |  | 1 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1471 | 42524115201 | 503 |  | 11 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1474 | 42525515201 | 107 |  | 5 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
1 | T1476 | 42522215201 | 105 |  | 8 | 11 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
1 | T1477 | 19541645201 | 19 |  | 27 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
1 | T1477 | 19541645201 | 106 |  | 7 | 33 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
1 | T1477 | 19541645201 | 128 |  | 3 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
1 | T1477 | 19541645201 | 1 |  | 1 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
1 | T1488 | 42923915201 | 112 |  | 5 | 3 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1488 | 42923915201 | 112 |  | 3 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1495 | 42524815201 | 7 |  | 1 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1497 | 43003715201 | 3 |  | 4 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1500 | 42794615201 | 7 |  | 14 | 8 | 1 | 5 | N | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1505 | 42523415201 | 3 |  | 37 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1506 | 40828625201 | 106 |  | 10 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
1 | T1531 | 42952615201 | 130 |  | 17 | 1 | 1 | 3 | N | Avoidable, CEI Consultant | Indecision/Delayed Response | Plan Modifications | 2
1 | T1544 | 43008415201 | 15 |  | 1 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
1 | T1546 | 42910415201 | 130 |  | 11 | 14 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
1 | T1552 | 40631475201 | 5 |  | 2 | 6 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
1 | T1557 | 42928415201 | 503 |  | 3 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1569 | 42911415201 | 503 |  | 18 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1570 | 42584615201 | 115 |  | 30 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1619 | 43365815201 | 15 |  | 2 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
1 | T1619 | 43365815201 | 112 |  | 14 | 8 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1620 | 43494315201 | 130 |  | 14 | 9 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
1 | T1625 | 42988315201 | 503 |  | 14 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1627 | 43130615201 | 16 |  | 30 | 1 | 1 | 3 | N | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1627 | 43130615201 | 16 |  | -30 | 43 | 1 | 3 | N | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1631 | 43327215201 | 5 |  | 12 | 11 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
1 | T1631 | 43327215201 | 126 |  | 5 | 12 | 1 | 2 | N | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
1 | T1631 | 43327215201 | 112 |  | 8 | 13 | 1 | 2 | N | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1631 | 43327215201 | 5 |  | 5 | 18 | 1 | 5 | N | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
1 | T1631 | 43327215201 | 116 |  | 21 | 22 | 1 | 2 | N | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
1 | T1642 | 43131115201 | 7 |  | 150 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
1 | T1644 | 20074615201 | 105 |  | 117 | 46 | 1 | 1 | C | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
1 | T1996 | 43086115201 | 130 |  | 16 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
1 | T9013 | 43700115201 | 131 |  | 26 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
2 | E2I87 | 20940925201 | 5 |  | 7 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
2 | E2J62 | 21025235201 | 108 |  | 30 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2J62 | 21025235201 | 9 |  | 60 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2K32 | 20950625201 | 502 |  | 22 | 6 | 1 | 4 | N | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | E2K79 | 21070535201 | 3 |  | 21 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | E2K79 | 21070535201 | 3 |  | 21 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | E2L41 | 20823635201 | 5 |  | 5 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | E2L99 | 20950345201 | 108 |  | 7 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2L99 | 20950345201 | 108 |  | 48 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2L99 | 20950345201 | 108 |  | 4 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2L99 | 20950345201 | 105 |  | 63 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2L99 | 20950345201 | 105 |  | 19 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2M33 | 21045835201 | 130 |  | 59 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | E2M36 | 42473115201 | 7 |  | 2 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | E2M46 | 42442315201 | 503 |  | 56 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2N01 | 20954345201 | 1 |  | 7 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2N01 | 20954345201 | 130 |  | 9 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | E2N06 | 42598815201 | 5 |  | 10 | 11 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
2 | E2N06 | 42598815201 | 7 |  | 30 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | E2N35 | 20929325201 | 503 |  | 34 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2N36 | 21068735201 | 19 |  | 1 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2N36 | 21068735201 | 18 |  | 1 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2N37 | 20816625201 | 107 |  | 3 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
2 | E2N64 | 42633315201 | 106 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2N64 | 42633315201 | 106 |  | 2 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2N64 | 42633315201 | 1 |  | 2 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2N66 | 42639225201 | 9 |  | 145 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2O41 | 42742915201 | 9 |  | 58 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2O41 | 42742915201 | 115 |  | 6 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | E2O59 | 42443915201 | 108 |  | 34 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O65 | 42831015201 | 16 |  | 71 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O73 | 42598615201 | 7 |  | 21 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O76 | 42802515201 | 4 |  | 21 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O77 | 42600015201 | 5 |  | 151 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O79 | 42830915201 | 7 |  | 7 | 6 | 1 | 5 | N | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2O91 | 42830715201 | 208 |  | 34 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
2 | E2O92 | 42886815201 | 12 |  | 5 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
2 | E2P91 | 42974915201 | 3 |  | 30 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
2 | E2Q64 | 20972045201 | 103 |  | 47 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | E2Q76 | 42931315201 | 130 |  | 27 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | E2Q78 | 20820745201 | 105 |  | 28 | 13 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2Q83 | 21355725201 | 10 |  | 23 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2Q83 | 21355725201 | 10 |  | 5 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2Q84 | 20957435201 | 5 |  | 5 | 13 | 1 | 5 | C | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2R04 | 21066125201 | 1 |  | 2 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2R04 | 21066125201 | 1 |  | 1 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2R09 | 20970515201 | 1 |  | 38 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2R10 | 20967615201 | 5 |  | 16 | 2 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | E2R15 | 42878315201 | 113 |  | 10 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
2 | E2R15 | 42878315201 | 108 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R19 | 20960715201 | 1 |  | 34 | 50 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R19 | 20960715201 | 1 |  | 27 | 52 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R73 | 43048015201 | 700 |  | 26 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
2 | E2R75 | 43122415201 | 108 |  | 101 | 10 | 1 | 5 | N | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R75 | 43122415201 | 108 |  | 32 | 13 | 1 | 5 | N | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R90 | 20971015201 | 1 |  | 5 | 5 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R90 | 20971015201 | 1 |  | 3 | 5 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R93 | 42607215201 | 12 |  | 26 | 1 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R93 | 42607215201 | 12 |  | 10 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2R93 | 42607215201 | 12 |  | 6 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2T03 | 42871115201 | 117 |  | 7 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
2 | E2T18 | 43071815201 | 128 |  | 207 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
2 | E2T30 | 42339815201 | 22 |  | 4 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
2 | E2U50 | 20968615201 | 19 |  | 21 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
2 | E2U50 | 20968615201 | 130 |  | 46 | 6 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
2 | E2U50 | 20968615201 | 503 |  | 1 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | E2U50 | 20968615201 | 108 |  | 10 | 10 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2U50 | 20968615201 | 24 |  | 6 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | E2U50 | 20968615201 | 106 |  | 45 | 13 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2U52 | 43075015201 | 106 |  | 12 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2V71 | 43430015201 | 7 |  | 42 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2W51 | 20950355201 | 12 |  | 12 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | E2W93 | 43433815201 | 118 |  | 3 | 7 | 1 | 2 | N | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
2 | E2W93 | 43433815201 | 404 |  | 18 | 7 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2091 | 21025515201 | 503 |  | 74 | 108 | 900 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2097 | 20996915201 | 5 |  | 10 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2119 | 20927815201 | 3 |  | 6 | 48 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2174 | 20927825201 | 1 |  | 1 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2174 | 20927825201 | 123 |  | 25 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
2 | T2206 | 21332345201 | 108 |  | 28 | 83 | 900 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2208 | 20972245201 | 18 |  | 12 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2217 | 21257725201 | 7 |  | 2 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2217 | 21257725201 | 5 |  | 5 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2217 | 21257725201 | 7 |  | -7 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2252 | 42302815201 | 113 |  | 21 | 25 | 1 | 1 | N | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
2 | T2252 | 42302815201 | 113 |  | 38 | 26 | 1 | 3 | N | Avoidable, CEI Consultant | Pavement Design Modification | Plan Modifications | 2
2 | T2262 | 20823015201 | 10 |  | 11 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
2 | T2280 | 21311325201 | 108 |  | 1 | 54 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2281 | 21327455201 | 130 |  | 60 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | T2285 | 21040435201 | 106 |  | 79 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2321 | 20783785201 | 12 |  | 7 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2329 | 21236745201 | 16 |  | 26 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2330 | 21259415201 | 130 |  | 1 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | T2330 | 21259415201 | 1 |  | 2 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | T2330 | 21259415201 | 1 |  | 2 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
2 | T2330 | 21259415201 | 502 |  | 7 | 21 | 1 | 4 | N | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2330 | 21259415201 | 1 |  | 1 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2330 | 21259415201 | 1 |  | 1 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2330 | 21259415201 | 115 |  | 27 | 26 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
2 | T2340 | 21324525201 | 4 |  | 8 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | T2340 | 21324525201 | 5 |  | 8 | 13 | 1 | 2 | N | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
2 | T2341 | 21323835201 | 860 |  | 95 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
2 | T2360 | 21307435201 | 16 |  | 32 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
2 | T2387 | 21039465201 | 503 |  | 6 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2389 | 42447215201 | 12 |  | 10 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2395 | 21350525201 | 1 |  | 28 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2396 | 42340715201 | 7 |  | 31 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2404 | 42695915201 | 503 |  | 7 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2409 | 43006515201 | 5 |  | 10 | 1 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2415 | 42884215201 | 106 |  | 30 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2418 | 42340815201 | 113 |  | 83 | 20 | 1 | 1 | C | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
2 | T2426 | 20837325201 | 450 |  | 20 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
2 | T2426 | 20837325201 | 5 |  | 6 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
2 | T2429 | 42342515201 | 503 |  | 4 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2432 | 42743015201 | 128 |  | 21 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
2 | T2432 | 42743015201 | 123 |  | 4 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
2 | T2437 | 42696415201 | 1 |  | 125 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
2 | T2448 | 42732715201 | 7 |  | 5 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
2 | T2454 | 42732915201 | 105 |  | 8 | 4 | 1 | 3 | N | Avoidable, CEI Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2454 | 42732915201 | 105 |  | 12 | 7 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2457 | 42430815201 | 5 |  | 10 | 19 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2464 | 21053845201 | 5 |  | 6 | 4 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2464 | 21053845201 | 12 |  | 5 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2476 | 43091625201 | 4 |  | 35 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
2 | T2476 | 43091625201 | 122 |  | 35 | 8 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
2 | T2476 | 43091625201 | 115 |  | 7 | 8 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | T2476 | 43091625201 | 7 |  | 13 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | T2495 | 42870815201 | 130 |  | 10 | 19 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
2 | T2496 | 43351015201 | 5 |  | 60 | 21 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
2 | T2496 | 43351015201 | 5 |  | 45 | 24 | 1 | 1 | C | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
2 | T2497 | 43091915201 | 115 |  | 15 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | T2499 | 42975015201 | 16 |  | 29 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
2 | T2514 | 42445415201 | 112 |  | 139 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
2 | T2515 | 21325915201 | 12 |  | 1 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
2 | T2515 | 21325915201 | 103 |  | 14 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | T2517 | 41695325201 | 22 |  | 6 | 15 | 1 | 1 | N | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | T2525 | 42476715201 | 5 |  | 2 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | T2528 | 42870615201 | 106 |  | 20 | 26 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2529 | 42871215201 | 403 |  | 85 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2529 | 42871215201 | 126 |  | 3 | 15 | 1 | 2 | N | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
2 | T2529 | 42871215201 | 403 |  | 12 | 15 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2530 | 21156035201 | 403 |  | 38 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2538 | 42696315201 | 1 |  | 3 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2538 | 42696315201 | 12 |  | 1 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
2 | T2542 | 21300425201 | 130 |  | 26 | 9 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
2 | T2546 | 42889615201 | 106 |  | 13 | 18 | 1 | 1 | E | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2547 | 42975025201 | 113 |  | 6 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
2 | T2547 | 42975025201 | 7 |  | 5 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
2 | T2557 | 21028695201 | 503 |  | 8 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
2 | T2572 | 43061415201 | 122 |  | 3 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
2 | T2588 | 21237925201 | 108 |  | 5 | 5 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2588 | 21237925201 | 112 |  | 5 | 5 | 2 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
2 | T2588 | 21237925201 | 3 |  | 4 | 5 | 3 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
2 | T2588 | 21237925201 | 101 |  | 3 | 5 | 4 | 1 | N | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
2 | T2588 | 21237925201 | 108 |  | 5 | 5 | 5 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2588 | 21237925201 | 108 |  | -5 | 7 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2590 | 42880515201 | 19 |  | 60 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2612 | 42360825201 | 5 |  | 23 | 25 | 1 | 5 | N | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2623 | 42747425201 | 4 |  | 26 | 34 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
2 | T2626 | 43055215201 | 103 |  | 7 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | T2627 | 43035215201 | 5 |  | 9 | 42 | 1 | 1 | N | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
2 | T2631 | 43808515201 | 106 |  | 11 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2634 | 43225615201 | 130 |  | 8 | 12 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
2 | T2634 | 43225615201 | 502 |  | 7 | 12 | 2 | 1 | N | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2634 | 43225615201 | 9 |  | 13 | 12 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2654 | 43434215201 | 12 |  | 3 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2654 | 43434215201 | 21 |  | 3 | 21 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
2 | T2654 | 43434215201 | 115 |  | 10 | 21 | 3 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
2 | T2671 | 43601015201 | 106 |  | 7 | 6 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2672 | 43964035201 | 12 |  | 4 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2686 | 43611815201 | 5 |  | 30 | 9 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
2 | T2688 | 43500115201 | 16 |  | 14 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | E3A44 | 40862315201 | 16 |  | 90 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | E3E93 | 41767315201 | 16 |  | 40 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | E3G29 | 41956925201 | 113 |  | 30 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
3 | E3G29 | 41956925201 | 9 |  | 70 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
3 | E3G29 | 41956925201 | 113 |  | 30 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
3 | E3G96 | 41956935201 | 700 |  | 17 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3I54 | 42839715201 | 9 |  | 5 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3I67 | 21877225201 | 1 |  | 49 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3I93 | 41767835201 | 18 |  | 1 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3I93 | 41767835201 | 18 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3I93 | 41767835201 | 18 |  | 1 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3J55 | 43027715201 | 3 |  | 10 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
3 | E3L08 | 43006115201 | 101 |  | 7 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
3 | E3L08 | 43006115201 | 16 |  | 7 | 20 | 1 | 5 | N | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
3 | E3L08 | 43006115201 | 5 |  | 11 | 21 | 1 | 5 | N | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
3 | E3L08 | 43006115201 | 5 |  | 23 | 24 | 1 | 5 | C | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
3 | E3L23 | 22066425201 | 9 |  | 199 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
3 | E3L68 | 42874015201 | 503 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3L90 | 42840315201 | 130 |  | 20 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | E3L90 | 42840315201 | 5 |  | 55 | 46 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
3 | E3M24 | 42693315201 | 503 |  | 8 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3M55 | 42805825201 | 503 |  | 108 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3N16 | 42902475201 | 9 |  | 54 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3N39 | 43078815201 | 503 |  | 7 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3N41 | 42016125201 | 9 |  | 7 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3N73 | 43078715201 | 503 |  | 5 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3N80 | 42577825201 | 123 |  | 2 | 4 | 1 | 2 | N | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
3 | E3N84 | 21876225201 | 16 |  | 25 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
3 | E3N84 | 21876225201 | 1 |  | 10 | 9 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
3 | E3N95 | 42820815201 | 9 |  | 15 | 1 | 1 | 2 | N | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
3 | E3N95 | 42820815201 | 106 |  | 14 | 11 | 1 | 2 | N | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | E3O04 | 41768345201 | 16 |  | 21 | 6 | 1 | 2 | N | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | E3O04 | 41768345201 | 130 |  | 51 | 12 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | E3O14 | 41040925201 | 503 |  | 1 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3O14 | 41040925201 | 503 |  | 1 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P09 | 41767745201 | 12 |  | 30 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P11 | 43257215201 | 115 |  | 7 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | E3P12 | 43255515201 | 107 |  | 14 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | E3P64 | 40747855201 | 503 |  | 13 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P75 | 43078615201 | 18 |  | 2 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P75 | 43078615201 | 3 |  | 2 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P75 | 43078615201 | 7 |  | 69 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | E3P75 | 43078615201 | 107 |  | 4 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | E3P84 | 43625815201 | 16 |  | 21 | 9 | 1 | 2 | N | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
3 | E3P91 | 43460615201 | 105 |  | 12 | 4 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | E3Q80 | 44014815201 | 401 |  | 7 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
3 | E3Q91 | 43626815201 | 16 |  | 7 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
3 | T3042 | 22044235201 | 103 |  | 33 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3042 | 22044235201 | 112 |  | 30 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3042 | 22044235201 | 117 |  | 15 | 48 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3063 | 41170215201 | 18 |  | -2 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3067 | 22159715201 | 107 |  | 8 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3087 | 41466315201 | 15 |  | 6 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3089 | 40716715201 | 115 |  | 32 | 49 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3089 | 40716715201 | 117 |  | 7 | 68 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3116 | 22017215201 | 5 |  | 92 | 19 | 1 | 1 | N | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3116 | 22017215201 | 18 |  | 3 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3116 | 22017215201 | 18 |  | -2 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3116 | 22017215201 | 106 |  | 30 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3116 | 22017215201 | 106 |  | 1 | 45 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3116 | 22017215201 | 106 |  | -6 | 51 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3153 | 21791155201 | 910 |  | 8 | 39 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
3 | T3153 | 21791155201 | 911 |  | 1 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
3 | T3155 | 22066415201 | 103 |  | 11 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3157 | 41170515201 | 18 |  | 1 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3157 | 41170515201 | 18 |  | 1 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3158 | 41343415201 | 18 |  | 17 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3159 | 41344015201 | 18 |  | 1 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3162 | 41345015201 | 12 |  | 24 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3164 | 41525715201 | 910 |  | 2 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
3 | T3166 | 41537015201 | 13 |  | 37 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
3 | T3173 | 41538215201 | 106 |  | 40 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3176 | 41544115201 | 115 |  | 7 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3181 | 41624015201 | 503 |  | 31 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3203 | 41690915201 | 18 |  | 1 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3204 | 21791135201 | 112 |  | 14 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3207 | 22049915201 | 105 |  | 24 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3207 | 22049915201 | 1 |  | 2 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3208 | 41537615201 | 18 |  | 15 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3213 | 41691715201 | 450 |  | 17 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
3 | T3219 | 41693715201 | 115 |  | 3 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3222 | 41538115201 | 18 |  | 1 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3222 | 41538115201 | 120 |  | 19 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3222 | 41538115201 | 115 |  | 4 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3222 | 41538115201 | 18 |  | 1 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3222 | 41538115201 | 120 |  | 10 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3222 | 41538115201 | 18 |  | 1 | 33 | 1 | 1 | N | Avoidable, Design Consultant | Hazardous Materials | Plan Modifications | 2
3 | T3231 | 41343315201 | 18 |  | 17 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3238 | 41111815201 | 3 |  | 4 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3260 | 41929215201 | 18 |  | 2 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3269 | 41929115201 | 12 |  | 10 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3272 | 41935015201 | 18 |  | 1 | 1 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3293 | 42306425201 | 107 |  | 212 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3299 | 41930915201 | 503 |  | 7 | 14 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3301 | 41930415201 | 126 |  | 36 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3308 | 42410815201 | 18 |  | 2 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3319 | 42290015201 | 1 |  | 11 | 6 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
3 | T3321 | 42667315201 | 126 |  | 5 | 3 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
3 | T3325 | 41931515201 | 3 |  | 8 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3325 | 41931515201 | 12 |  | 7 | 10 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3326 | 42306115201 | 18 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3333 | 41931315201 | 503 |  | 8 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3333 | 41931315201 | 503 |  | 6 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3344 | 41537815201 | 503 |  | 2 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3347 | 40804915202 | 18 |  | 1 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3347 | 40804915202 | 18 |  | 3 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3347 | 40804915202 | 18 |  | 5 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3349 | 22041285201 | 860 |  | 97 | 118 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
3 | T3350 | 40716815201 | 106 |  | 92 | 39 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3360 | 42527725201 | 115 |  | 5 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3380 | 22067915201 | 503 |  | 7 | 77 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3380 | 22067915201 | 1 |  | 5 | 81 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3380 | 22067915201 | 106 |  | 28 | 85 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3380 | 22067915201 | 107 |  | 9 | 91 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3394 | 42461115201 | 12 |  | 7 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 107 |  | 5 | 18 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 15 |  | 17 | 19 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 15 |  | 4 | 20 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 15 |  | 6 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 10 |  | 18 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3398 | 22016225201 | 503 |  | 163 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3399 | 42306015201 | 18 |  | 3 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3400 | 22247715201 | 112 |  | 178 | 81 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3406 | 42693215201 | 503 |  | 16 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3412 | 42462325201 | 115 |  | 46 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3416 | 42450815201 | 5 |  | 8 | 51 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
3 | T3417 | 42282315201 | 130 |  | 128 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3417 | 42282315201 | 503 |  | 295 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3422 | 42306515201 | 503 |  | 47 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3422 | 42306515201 | 503 |  | 38 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3422 | 42306515201 | 503 |  | 9 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3424 | 41343515201 | 130 |  | 10 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3424 | 41343515201 | 130 |  | 15 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3424 | 41343515201 | 115 |  | 14 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3427 | 42164415201 | 503 |  | 13 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3428 | 42623315201 | 16 |  | 16 | 12 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3428 | 42623315201 | 503 |  | 3 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3428 | 42623315201 | 503 |  | 8 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3428 | 42623315201 | 15 |  | 2 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3429 | 42445815201 | 503 |  | 1 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3429 | 42445815201 | 130 |  | 10 | 17 | 1 | 3 | N | Avoidable, CEI Consultant | Indecision/Delayed Response | Plan Modifications | 2
3 | T3432 | 42696115201 | 18 |  | 3 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3432 | 42696115201 | 18 |  | 8 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3432 | 42696115201 | 503 |  | 7 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 12 |  | 10 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 18 |  | 9 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 18 |  | 2 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 18 |  | 2 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 18 |  | 2 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3432 | 42696115201 | 118 |  | -2 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
3 | T3435 | 42290715201 | 5 |  | 115 | 53 | 1 | 5 | C | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
3 | T3435 | 42290715201 | 3 |  | 21 | 63 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
3 | T3435 | 42290715201 | 117 |  | 21 | 68 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3443 | 42693415201 | 18 |  | 7 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3443 | 42693415201 | 12 |  | 6 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
3 | T3443 | 42693415201 | 122 |  | 3 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
3 | T3456 | 42986515201 | 105 |  | 7 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3462 | 41694115201 | 503 |  | 35 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3464 | 43000315201 | 9 |  | 21 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3464 | 43000315201 | 18 |  | 1 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3464 | 43000315201 | 105 |  | 13 | 21 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3464 | 43000315201 | 106 |  | 12 | 33 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3464 | 43000315201 | 18 |  | -1 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3467 | 42893915201 | 503 |  | 4 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3467 | 42893915201 | 503 |  | 2 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3468 | 42696515201 | 503 |  | 8 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3468 | 42696515201 | 503 |  | 8 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3468 | 42696515201 | 503 |  | 9 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3468 | 42696515201 | 503 |  | 4 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3469 | 42697115201 | 105 |  | 3 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3469 | 42697115201 | 503 |  | 38 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3470 | 42893815201 | 18 |  | 3 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3470 | 42893815201 | 18 |  | 3 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3470 | 42893815201 | 18 |  | 3 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3470 | 42893815201 | 18 |  | 3 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 4 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 2 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 503 |  | 2 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 2 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 2 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 2 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 18 |  | 2 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3478 | 42693115201 | 450 |  | 2 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
3 | T3478 | 42693115201 | 450 |  | 2 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
3 | T3478 | 42693115201 | 108 |  | 2 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 39 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 108 |  | 2 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3478 | 42693115201 | 18 |  | 2 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3481 | 42884615201 | 503 |  | 8 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3481 | 42884615201 | 106 |  | 24 | 14 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3481 | 42884615201 | 118 |  | 5 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
3 | T3481 | 42884615201 | 107 |  | 12 | 21 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3481 | 42884615201 | 105 |  | 29 | 22 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3481 | 42884615201 | 108 |  | 6 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
3 | T3481 | 42884615201 | 105 |  | 125 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3481 | 42884615201 | 503 |  | 77 | 49 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3483 | 43077715201 | 106 |  | 1 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3483 | 43077715201 | 3 |  | 12 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3484 | 43000215201 | 22 |  | 60 | 22 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3484 | 43000215201 | 22 |  | 13 | 39 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3484 | 43000215201 | 503 |  | 88 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3484 | 43000215201 | 22 |  | 26 | 41 | 1 | 5 | C | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3484 | 43000215201 | 22 |  | 6 | 42 | 1 | 5 | C | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3488 | 40979275201 | 106 |  | 1 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3488 | 40979275201 | 5 |  | 14 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3488 | 40979275201 | 106 |  | 1 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3488 | 40979275201 | 120 |  | 18 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
3 | T3488 | 40979275201 | 106 |  | 1 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3488 | 40979275201 | 126 |  | 6 | 27 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
3 | T3488 | 40979275201 | 105 |  | 10 | 33 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3491 | 43078015201 | 503 |  | 18 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3491 | 43078015201 | 503 |  | 29 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3497 | 43178715201 | 105 |  | 2 | 7 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3498 | 43178515201 | 115 |  | 9 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3498 | 43178515201 | 126 |  | 6 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3498 | 43178515201 | 503 |  | 15 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3502 | 42764915201 | 10 |  | 7 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 18 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 8 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 2 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 9 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 9 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 8 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 7 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 9 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 6 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 10 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 6 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 6 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 11 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 12 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 12 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 13 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 11 | 47 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | 3 | 48 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3515 | 43090835201 | 503 |  | -2 | 50 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3521 | 43078515201 | 122 |  | 3 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
3 | T3521 | 43078515201 | 113 |  | 10 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
3 | T3521 | 43078515201 | 106 |  | 16 | 12 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3521 | 43078515201 | 105 |  | 20 | 19 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3521 | 43078515201 | 106 |  | 11 | 22 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3521 | 43078515201 | 112 |  | 5 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3521 | 43078515201 | 503 |  | 3 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3521 | 43078515201 | 106 |  | 8 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3521 | 43078515201 | 12 |  | 8 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3524 | 22251815201 | 10 |  | 11 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3528 | 22281815201 | 107 |  | 1 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3528 | 22281815201 | 130 |  | 8 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3538 | 43357615201 | 503 |  | 5 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3539 | 22243945201 | 105 |  | 12 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3544 | 43090825201 | 503 |  | 34 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3544 | 43090825201 | 23 |  | 6 | 25 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3544 | 43090825201 | 503 |  | 91 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3551 | 42873915201 | 12 |  | 22 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3551 | 42873915201 | 130 |  | 7 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3551 | 42873915201 | 112 |  | 4 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3557 | 43047215201 | 1 |  | 49 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
3 | T3557 | 43047215201 | 103 |  | 5 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3559 | 22247625201 | 16 |  | 37 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3559 | 22247625201 | 1 |  | 9 | 54 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3559 | 22247625201 | 16 |  | 13 | 55 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
3 | T3559 | 22247625201 | 128 |  | 17 | 65 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
3 | T3559 | 22247625201 | 107 |  | 25 | 74 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3559 | 22247625201 | 1 |  | 6 | 75 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3559 | 22247625201 | 107 |  | 16 | 76 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3559 | 22247625201 | 107 |  | 6 | 77 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3559 | 22247625201 | 115 |  | 12 | 78 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
3 | T3559 | 22247625201 | 107 |  | 14 | 107 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
3 | T3568 | 41347915201 | 502 |  | 35 | 15 | 1 | 2 | N | Avoidable, In-House Designer | Inaccurate Directions Given | CEI Actions/Inactions | 6
3 | T3568 | 41347915201 | 502 |  | 13 | 32 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
3 | T3573 | 43046615201 | 115 |  | 77 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
3 | T3577 | 43047515201 | 130 |  | 18 | 9 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | T3583 | 43047415201 | 16 |  | 21 | 8 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | T3584 | 42551925201 | 101 |  | 38 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
3 | T3584 | 42551925201 | 101 |  | 5 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
3 | T3588 | 43390415201 | 503 |  | 14 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3590 | 43273815201 | 917 |  | 3 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3591 | 43047815201 | 130 |  | 18 | 14 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | T3592 | 43466715201 | 19 |  | 14 | 14 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | T3593 | 43356915201 | 16 |  | 17 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
3 | T3600 | 42695115201 | 107 |  | 4 | 19 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3600 | 42695115201 | 107 |  | 11 | 20 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
3 | T3615 | 42695015201 | 503 |  | 20 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3620 | 43278725201 | 12 |  | 1 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3625 | 43188315201 | 503 |  | 15 | 9 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T3625 | 43188315201 | 106 |  | 6 | 11 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T3634 | 43256215201 | 105 |  | 5 | 6 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3636 | 43188325201 | 126 |  | 1 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3638 | 43461115201 | 23 |  | 3 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
3 | T3641 | 43255115201 | 130 |  | 24 | 3 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
3 | T3644 | 43671915201 | 105 |  | 1 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3651 | 43014665201 | 5 |  | 14 | 13 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3651 | 43014665201 | 5 |  | 6 | 18 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
3 | T3661 | 43255915201 | 106 |  | 7 | 20 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T9002 | 42607115202 | 503 |  | 3 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T9002 | 42607115202 | 16 |  | 105 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
3 | T9009 | 43035625201 | 106 |  | 14 | 11 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
3 | T9009 | 43035625201 | 4 |  | 30 | 16 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4C97 | 23174015201 | 105 |  | 15 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | E4H07 | 23173935201 | 130 |  | 85 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4H07 | 23173935201 | 130 |  | -85 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4H07 | 23173935201 | 130 |  | 85 | 8 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
4 | E4H07 | 23173935201 | 19 |  | 73 | 27 | 1 | 5 | C | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
4 | E4H07 | 23173935201 | 5 |  | 46 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4J55 | 41248615201 | 16 |  | 44 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4J71 | 41742815201 | 16 |  | 16 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4K01 | 41641815201 | 106 |  | 2 | 8 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K01 | 41641815201 | 130 |  | 13 | 12 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
4 | E4K01 | 41641815201 | 106 |  | 7 | 14 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K01 | 41641815201 | 502 |  | 6 | 16 | 1 | 4 | N | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
4 | E4K36 | 41902215201 | 106 |  | 7 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K36 | 41902215201 | 9 |  | 43 | 58 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K48 | 23097815201 | 9 |  | 337 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K48 | 23097815201 | 9 |  | 116 | 62 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K48 | 23097815201 | 18 |  | 3 | 77 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K68 | 42648215201 | 18 |  | 1 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K87 | 41456115201 | 12 |  | 7 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K88 | 41750615201 | 9 |  | 53 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4K92 | 41248925201 | 503 |  | 60 | 121 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | E4L76 | 41304615201 | 12 |  | 2 | 80 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | E4L94 | 41304715201 | 130 |  | 10 | 40 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L95 | 41304815201 | 9 |  | 11 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L95 | 41304815201 | 18 |  | 2 | 73 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L95 | 41304815201 | 18 |  | 1 | 76 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L95 | 41304815201 | 18 |  | 1 | 81 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L97 | 42593215201 | 9 |  | 32 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4L97 | 42593215201 | 107 |  | 13 | 17 | 2 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4L97 | 42593215201 | 13 |  | 6 | 17 | 3 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4L97 | 42593215201 | 450 |  | 2 | 17 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | E4L97 | 42593215201 | 450 |  | 6 | 17 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | E4M26 | 42797115201 | 5 |  | 87 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | E4M26 | 42797115201 | 5 |  | 6 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | E4M26 | 42797115201 | 106 |  | 19 | 59 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4M33 | 42844915201 | 130 |  | 29 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | E4M33 | 42844915201 | 130 |  | 13 | 35 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
4 | E4M52 | 42300015201 | 106 |  | 16 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4M78 | 41304925201 | 7 |  | 2 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4M78 | 41304925201 | 107 |  | 129 | 82 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4N30 | 23071725201 | 1 |  | 20 | 82 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4N30 | 23071725201 | 7 |  | 17 | 82 | 2 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4N98 | 42170745201 | 4 |  | 2 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4P15 | 43270715201 | 12 |  | 1 | 48 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4P28 | 43053415201 | 12 |  | 45 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
4 | E4P38 | 43270415201 | 503 |  | 5 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | E4Q13 | 43060515201 | 106 |  | 21 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | E4Q22 | 42990515201 | 108 |  | 45 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
4 | E4R47 | 42840015201 | 128 |  | 56 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
4 | E4R63 | 43060215201 | 503 |  | 7 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | E4R83 | 43482915201 | 5 |  | 13 | 25 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | E4R89 | 43234915201 | 130 |  | 19 | 16 | 1 | 4 | C | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
4 | E4S43 | 44009015201 | 130 |  | 22 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
4 | T4016 | 23191825201 | 402 |  | 1 | 105 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
4 | T4032 | 23191935201 | 5 |  | 4 | 139 | 1 | 5 | N | Avoidable, Third Party | Material Shortage | Material Shortage | 12
4 | T4039 | 23191815201 | 860 |  | 118 | 41 | 1 | 5 | C | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
4 | T4041 | 23192015201 | 16 |  | 1 | 82 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
4 | T4041 | 23192015201 | 12 |  | 1 | 91 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
4 | T4088 | 23028825201 | 7 |  | 39 | 69 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
4 | T4088 | 23028825201 | 503 |  | 5 | 73 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4133 | 40361715201 | 12 |  | 6 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4161 | 41143115201 | 115 |  | 2 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
4 | T4161 | 41143115201 | 123 |  | 14 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
4 | T4161 | 41143115201 | 106 |  | 7 | 26 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4162 | 22989715201 | 7 |  | 10 | 57 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4175 | 41383715201 | 503 |  | 6 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4181 | 22858355201 | 106 |  | 68 | 56 | 1 | 2 | N | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4183 | 41384415201 | 105 |  | 19 | 15 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4193 | 22862715201 | 5 |  | 4 | 21 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4194 | 40651515201 | 7 |  | 9 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4195 | 41384015201 | 18 |  | 5 | 16 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4196 | 41384215201 | 113 |  | 14 | 17 | 1 | 1 | N | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
4 | T4196 | 41384215201 | 502 |  | 6 | 41 | 1 | 1 | N | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
4 | T4197 | 41379515201 | 5 |  | 20 | 24 | 1 | 5 | N | Avoidable, Third Party | Inaccurate Directions Given | CEI Actions/Inactions | 6
4 | T4206 | 41383815201 | 503 |  | 14 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4208 | 41531815201 | 5 |  | 28 | 26 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4208 | 41531815201 | 450 |  | 4 | 26 | 2 | 5 | N | Avoidable, Third Party | Holiday Time Extension | Holiday Time Extension | 14
4 | T4228 | 40359625201 | 5 |  | 10 | 2 | 1 | 5 | N | Avoidable, Third Party | Holiday Time Extension | Holiday Time Extension | 14
4 | T4231 | 23026225201 | 7 |  | 5 | 86 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | T4231 | 23026225201 | 12 |  | 1 | 86 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
4 | T4236 | 41688315201 | 5 |  | 10 | 22 | 1 | 5 | N | Avoidable, Third Party | Holiday Time Extension | Holiday Time Extension | 14
4 | T4246 | 41965215201 | 112 |  | 12 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4251 | 42648015201 | 106 |  | 3 | 19 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4251 | 42648015201 | 115 |  | 11 | 19 | 2 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
4 | T4251 | 42648015201 | 115 |  | 11 | 19 | 3 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
4 | T4251 | 42648015201 | 105 |  | 2 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4252 | 42284215201 | 5 |  | 8 | 9 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4256 | 41539515201 | 12 |  | 5 | 20 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4270 | 41379525201 | 106 |  | 20 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4275 | 42165615201 | 7 |  | 3 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4277 | 42300215201 | 7 |  | 35 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4287 | 42238715201 | 112 |  | 28 | 17 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4292 | 42581615201 | 1 |  | 13 | 15 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4292 | 42581615201 | 16 |  | 58 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4303 | 42295615201 | 115 |  | 20 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
4 | T4312 | 42165915201 | 16 |  | 14 | 21 | 1 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
4 | T4319 | 42761115201 | 118 |  | 7 | 9 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
4 | T4321 | 42301815201 | 5 |  | 4 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
4 | T4323 | 42295715201 | 112 |  | 5 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4325 | 42303115201 | 7 |  | 10 | 23 | 1 | 5 | N | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4334 | 42463915201 | 123 |  | 10 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
4 | T4340 | 42865115201 | 7 |  | 8 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
4 | T4341 | 23073015201 | 5 |  | 39 | 50 | 1 | 5 | N | Avoidable, Third Party | Landscaping Changes | Plan Modifications | 2
4 | T4341 | 23073015201 | 113 |  | 4 | 60 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
4 | T4342 | 42476215201 | 12 |  | 3 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
4 | T4345 | 40836215201 | 18 |  | 14 | 39 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
4 | T4357 | 42701415201 | 118 |  | 5 | 17 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
4 | T4359 | 42467115201 | 503 |  | 10 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4360 | 40691915201 | 503 |  | 34 | 78 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4360 | 40691915201 | 1 |  | 35 | 85 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4367 | 23072415201 | 5 |  | 67 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4 | T4376 | 42701215201 | 122 |  | 11 | 25 | 1 | 1 | N | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4376 | 42701215201 | 7 |  | 8 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4386 | 42872715201 | 24 |  | 10 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4387 | 42924625201 | 24 |  | 19 | 42 | 1 | 5 | N | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4387 | 42924625201 | 22 |  | 15 | 44 | 1 | 5 | N | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4393 | 42872215201 | 12 |  | 5 | 27 | 1 | 2 | N | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4395 | 42936515201 | 112 |  | 28 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4396 | 42873215201 | 22 |  | 16 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
4 | T4406 | 42872615201 | 122 |  | 18 | 18 | 1 | 5 | N | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
4 | T4422 | 43257425201 | 105 |  | 6 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4426 | 43060815201 | 1 |  | 18 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4431 | 43509315201 | 115 |  | 10 | 8 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
4 | T4438 | 42871915201 | 105 |  | 45 | 35 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4446 | 43294915201 | 7 |  | 10 | 28 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4450 | 43288325201 | 5 |  | 28 | 26 | 1 | 5 | N | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
4 | T4464 | 23316625201 | 106 |  | 30 | 22 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4464 | 23316625201 | 5 |  | 9 | 32 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
4 | T4475 | 43609715201 | 5 |  | 17 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
5 | E5L81 | 42065325201 | 5 |  | 13 | 7 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
5 | E5N44 | 41098315201 | 503 |  | 6 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5N44 | 41098315201 | 503 |  | 39 | 47 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5R16 | 40846415201 | 503 |  | 1 | 153 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5R53 | 42474415201 | 503 |  | 27 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5R53 | 42474415201 | 503 |  | 33 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5R83 | 23930415201 | 15 |  | 13 | 17 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | E5W10 | 24262625201 | 113 |  | 32 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
5 | E5Y06 | 43544325201 | 17 |  | 35 | 9 | 1 | 1 | N | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
5 | E5Y51 | 43832115201 | 107 |  | 14 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
5 | E5Y51 | 43832115201 | 107 |  | 14 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
5 | E5Z24 | 43565115201 | 404 |  | 23 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
5 | T5059 | 23831515201 | 503 |  | 86 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | T5059 | 23831515201 | 503 |  | -86 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | T5060 | 24253115201 | 503 |  | 18 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
5 | T5060 | 24253115201 | 403 |  | 18 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
5 | T5508 | 24041825201 | 5 |  | 10 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
5 | T5508 | 24041825201 | 115 |  | 9 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
5 | T5514 | 43065815201 | 130 |  | 2 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
5 | T5546 | 43234215201 | 108 |  | 20 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
5 | T9017 | 43730315201 | 108 |  | 23 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6C67 | 41475415201 | 16 |  | 25 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6D94 | 25168615201 | 16 |  | 20 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6D94 | 25168615201 | 12 |  | 22 | 23 | 1 | 5 | N | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6D94 | 25168615201 | 4 |  | 37 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6E32 | 25023875201 | 16 |  | 42 | 53 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6E88 | 41067995201 | 3 |  | 62 | 26 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | E6E89 | 42303615201 | 503 |  | 18 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6F11 | 42382915201 | 15 |  | 22 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6F60 | 24994135201 | 3 |  | 5 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6G53 | 42560075201 | 130 |  | 3 | 4 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
6 | E6G56 | 42611915201 | 10 |  | 28 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | E6G64 | 42976115201 | 106 |  | 14 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | E6G64 | 42976115201 | 115 |  | 15 | 13 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | E6G64 | 42976115201 | 106 |  | -14 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | E6G64 | 42976115201 | 115 |  | -15 | 22 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | E6G64 | 42976115201 | 503 |  | -20 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6H34 | 42560035201 | 4 |  | 32 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6H34 | 42560035201 | 106 |  | 23 | 29 | 2 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | E6H34 | 42560035201 | 1 |  | 72 | 29 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | E6H35 | 41809425201 | 4 |  | 7 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | E6H35 | 41809425201 | 118 |  | 14 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | E6H35 | 41809425201 | 105 |  | 14 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | E6H36 | 42848815201 | 122 |  | 2 | 3 | 1 | 1 | N | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6H42 | 42999715201 | 18 |  | 2 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6H58 | 42616715201 | 18 |  | 2 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6H89 | 42934715201 | 7 |  | 5 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6I06 | 42914315201 | 18 |  | 3 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6I14 | 43209815201 | 9 |  | 24 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6I20 | 43117715201 | 1 |  | 5 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6I20 | 43117715201 | 16 |  | 5 | 13 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
6 | E6I31 | 42848315201 | 503 |  | 8 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I58 | 43119415201 | 12 |  | 21 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I74 | 43119315201 | 18 |  | 1 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I74 | 43119315201 | 503 |  | 30 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I74 | 43119315201 | 12 |  | 28 | 52 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I81 | 43305915201 | 503 |  | 33 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6I85 | 41774079201 | 130 |  | 24 | 9 | 1 | 3 | N | Avoidable, CEI Consultant | Indecision/Delayed Response | Plan Modifications | 2
6 | E6I89 | 43117815201 | 12 |  | 42 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | E6I91 | 42918715201 | 5 |  | 9 | 3 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
6 | E6J12 | 43274215201 | 1 |  | 14 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | E6J21 | 43584215201 | 503 |  | 4 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6J96 | 42918725201 | 919 |  | 38 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6K27 | 43747515201 | 503 |  | 28 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6K60 | 42736945201 | 7 |  | 20 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | E6L12 | 43560115201 | 1 |  | 35 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6045 | 24994015201 | 4 |  | 654 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6091 | 41463615201 | 503 |  | 29 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6091 | 41463615201 | 503 |  | 40 | 21 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6091 | 41463615201 | 12 |  | 15 | 21 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6091 | 41463615201 | 1 |  | 18 | 21 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6091 | 41463615201 | 12 |  | 3 | 21 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6109 | 41611715201 | 503 |  | 16 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6109 | 41611715201 | 108 |  | 12 | 19 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6109 | 41611715201 | 105 |  | 28 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6114 | 40558265201 | 118 |  | 65 | 24 | 1 | 0 | E | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6122 | 41463515201 | 503 |  | 30 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6146 | 41807115201 | 115 |  | 33 | 16 | 1 | 5 | N | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
6 | T6146 | 41807115201 | 115 |  | 22 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6169 | 42355315201 | 503 |  | 2 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6177 | 42269915201 | 101 |  | 21 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
6 | T6177 | 42269915201 | 105 |  | 9 | 13 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6177 | 42269915201 | 105 |  | 33 | 14 | 1 | 2 | N | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6183 | 41506025201 | 503 |  | 60 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6183 | 41506025201 | 503 |  | 30 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6187 | 41809515201 | 115 |  | 50 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6188 | 25168445201 | 503 |  | 20 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6189 | 41808915201 | 503 |  | 113 | 39 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6190 | 41247315201 | 15 |  | 97 | 46 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6190 | 41247315201 | 5 |  | 21 | 46 | 2 | 5 | C | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6190 | 41247315201 | 7 |  | 23 | 46 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6190 | 41247315201 | 503 |  | 46 | 46 | 4 | 0 | C | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6194 | 40561225201 | 503 |  | 7 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6198 | 41985915201 | 12 |  | 36 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6199 | 41984915201 | 503 |  | 2 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6207 | 41984815201 | 12 |  | 10 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6211 | 42508115201 | 503 |  | 25 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6216 | 41985415201 | 106 |  | 12 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | T6216 | 41985415201 | 106 |  | 3 | 17 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | T6216 | 41985415201 | 105 |  | 4 | 17 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6216 | 41985415201 | 105 |  | 1 | 17 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6216 | 41985415201 | 19 |  | 3 | 17 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6216 | 41985415201 | 12 |  | 4 | 17 | 6 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6216 | 41985415201 | 12 |  | 2 | 17 | 7 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6216 | 41985415201 | 128 |  | 20 | 17 | 8 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6216 | 41985415201 | 18 |  | 5 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6220 | 24961435201 | 1 |  | 13 | 60 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6220 | 24961435201 | 16 |  | 70 | 61 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6220 | 24961435201 | 503 |  | 45 | 73 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6220 | 24961435201 | 130 |  | 15 | 76 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | T6226 | 42313415201 | 4 |  | 58 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | T6227 | 42313515201 | 18 |  | 5 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | T6229 | 41809415201 | 119 |  | 56 | 13 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
6 | T6231 | 42261215201 | 503 |  | 10 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6231 | 42261215201 | 503 |  | 3 | 17 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6231 | 42261215201 | 108 |  | 6 | 17 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6232 | 25054835201 | 18 |  | 5 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6236 | 42420715201 | 503 |  | 30 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6236 | 42420715201 | 123 |  | 16 | 21 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
6 | T6238 | 42261415201 | 115 |  | 40 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6239 | 42454415201 | 3 |  | 35 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6240 | 41842325201 | 503 |  | 37 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6241 | 41982515201 | 120 |  | 20 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
6 | T6241 | 41982515201 | 115 |  | 50 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6241 | 41982515201 | 115 |  | 81 | 31 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6242 | 42272315201 | 128 |  | 38 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6242 | 42272315201 | 118 |  | 4 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6243 | 42513915201 | 106 |  | 21 | 5 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
6 | T6247 | 24964825201 | 123 |  | 24 | 6 | 1 | 1 | N | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
6 | T6249 | 42345225201 | 12 |  | 14 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
6 | T6252 | 40763335201 | 116 |  | 37 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
6 | T6254 | 42559725201 | 7 |  | 5 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
6 | T6256 | 42551315201 | 7 |  | 7 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
6 | T6257 | 42514515201 | 503 |  | 74 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6257 | 42514515201 | 503 |  | 29 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6258 | 42550415201 | 503 |  | 27 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6258 | 42550415201 | 9 |  | 3 | 21 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6258 | 42550415201 | 115 |  | 5 | 21 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6267 | 42534815201 | 7 |  | 4 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6276 | 42345215201 | 123 |  | 21 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
6 | T6277 | 41247355201 | 450 |  | 1 | 26 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
6 | T6285 | 42848515201 | 108 |  | 8 | 5 | 1 | 1 | N | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6290 | 24991115201 | 22 |  | 2 | 70 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6290 | 24991115201 | 18 |  | 4 | 71 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
6 | T6292 | 42527115201 | 118 |  | 6 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6294 | 25023635201 | 18 |  | 2 | 21 | 1 | 5 | N | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6294 | 25023635201 | 18 |  | 7 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6294 | 25023635201 | 503 |  | 5 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6294 | 25023635201 | 503 |  | 1 | 34 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6298 | 25168835201 | 117 |  | 14 | 29 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
6 | T6299 | 42560015201 | 118 |  | 45 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6304 | 40557555201 | 128 |  | 21 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6308 | 42751315201 | 5 |  | 9 | 22 | 1 | 5 | N | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
6 | T6308 | 42751315201 | 103 |  | 14 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 5 |  | 8 | 8 | 1 | 5 | N | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 1 |  | 1 | 8 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 1 |  | 8 | 8 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 1 |  | 1 | 8 | 4 | 1 | N | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 5 |  | 2 | 8 | 5 | 5 | N | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6309 | 42272325201 | 1 |  | 2 | 8 | 6 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
6 | T6310 | 42848415201 | 115 |  | 3 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6310 | 42848415201 | 12 |  | 5 | 14 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6310 | 42848415201 | 118 |  | 2 | 14 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6322 | 42750525201 | 115 |  | 42 | 27 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
6 | T6324 | 42913615201 | 115 |  | 30 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6325 | 25055425201 | 18 |  | 2 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6347 | 42559815201 | 15 |  | 94 | 58 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6350 | 43080315201 | 1 |  | 30 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
6 | T6352 | 43083715201 | 115 |  | 35 | 16 | 1 | 2 | N | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
6 | T6363 | 42751515201 | 105 |  | 34 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6373 | 43080915201 | 3 |  | 31 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6374 | 43118015201 | 1 |  | 22 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
6 | T6374 | 43118015201 | 503 |  | 12 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6374 | 43118015201 | 12 |  | 7 | 23 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6380 | 41462435201 | 118 |  | 40 | 19 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6401 | 41247395201 | 5 |  | 69 | 25 | 1 | 5 | N | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6416 | 43305925201 | 18 |  | 12 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
6 | T6416 | 43305925201 | 126 |  | 21 | 22 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
6 | T6428 | 42765125201 | 22 |  | 14 | 12 | 1 | 5 | N | Avoidable, Third Party | Computation Error | Plan Modifications | 2
6 | T6430 | 43476915201 | 503 |  | 7 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
6 | T6437 | 43634215201 | 7 |  | 15 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | E7E55 | 40372615201 | 115 |  | 36 | 14 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
7 | E7F82 | 41683715201 | 116 |  | 4 | 7 | 900 | 1 | N | Avoidable, Design Consultant | Inadequate R/W Provided for Construction | Plan Modifications | 2
7 | E7F84 | 41684715201 | 5 |  | 3 | 9 | 900 | 1 | N | Avoidable, Design Consultant | Inadequate R/W Provided for Construction | Plan Modifications | 2
7 | E7F94 | 41683415201 | 405 |  | 29 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
7 | E7G19 | 41684225201 | 9 |  | 29 | 12 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate R/W Provided for Construction | Plan Modifications | 2
7 | E7H56 | 25690315201 | 503 |  | 4 | 1 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | E7H89 | 42472515201 | 1 |  | 5 | 3 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | E7I96 | 40625565201 | 7 |  | 47 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | E7J03 | 41090965201 | 130 |  | 21 | 8 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
7 | E7J99 | 42715515201 | 106 |  | 30 | 16 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
7 | E7K04 | 43066015201 | 503 |  | 15 | 33 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | E7K09 | 43376015201 | 503 |  | 12 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7095 | 41523315201 | 122 |  | 39 | 4 | 1 | 1 | N | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7159 | 41685815201 | 12 |  | 10 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7168 | 25559915201 | 12 |  | 75 | 85 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7170 | 41520115201 | 12 |  | 4 | 42 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7192 | 25729825201 | 3 |  | 5 | 36 | 900 | 1 | N | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7209 | 25841515201 | 7 |  | 15 | 111 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
7 | T7209 | 25841515201 | 112 |  | 1 | 111 | 2 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7209 | 25841515201 | 7 |  | 7 | 111 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7231 | 41684415201 | 3 |  | 3 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7231 | 41684415201 | 3 |  | 2 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7231 | 41684415201 | 113 |  | 11 | 21 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
7 | T7231 | 41684415201 | 118 |  | 5 | 22 | 1 | 5 | N | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
7 | T7231 | 41684415201 | 3 |  | 3 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
7 | T7241 | 41683815201 | 503 |  | 11 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7253 | 41886025201 | 12 |  | 16 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7253 | 41886025201 | 115 |  | 6 | 26 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
7 | T7253 | 41886025201 | 503 |  | 81 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7254 | 41684515201 | 3 |  | 6 | 10 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7275 | 41683615201 | 1 |  | 45 | 18 | 1 | 1 | N | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7285 | 42821915201 | 503 |  | 10 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7299 | 42456115201 | 503 |  | 13 | 34 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
7 | T7300 | 42470515201 | 106 |  | 6 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
7 | T7304 | 40795135201 | 3 |  | 20 | 68 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
7 | T7304 | 40795135201 | 105 |  | 14 | 68 | 2 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
7 | T7307 | 42715215201 | 12 |  | 2 | 37 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
7 | T7311 | 25579315201 | 112 |  | 40 | 31 | 1 | 2 | N | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7317 | 41886075201 | 15 |  | 8 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7317 | 41886075201 | 1 |  | 15 | 69 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7349 | 43124315201 | 3 |  | 6 | 40 | 1 | 1 | N | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7390 | 43480715201 | 23 |  | 32 | 10 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T7391 | 43269815201 | 7 |  | 13 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
7 | T9014 | 43482515201 | 131 |  | 21 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
7 | T9014 | 43482515201 | 13 |  | 15 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
7 | T9019 | 44030915201 | 108 |  | 6 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
8 | E8G09 | 41153335201 | 19 |  | 34 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
8 | E8G79 | 41897615201 | 503 |  | 60 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8G91 | 41590515201 | 503 |  | 1 | 71 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H03 | 41702215201 | 18 |  | 30 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H03 | 41702215201 | 18 |  | 14 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H33 | 40612045201 | 16 |  | 114 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H33 | 40612045201 | 18 |  | 112 | 38 | 1 | 5 | N | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H66 | 40612315201 | 503 |  | 7 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H66 | 40612315201 | 503 |  | 14 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H66 | 40612315201 | 503 |  | 30 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H67 | 40612415201 | 503 |  | 50 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H72 | 40611925201 | 105 |  | 42 | 14 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
8 | E8H76 | 41542915201 | 503 |  | 3 | 35 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H76 | 41542915201 | 503 |  | 4 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H76 | 41542915201 | 18 |  | 2 | 37 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H76 | 41542915201 | 113 |  | 2 | 38 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
8 | E8H76 | 41542915201 | 18 |  | 4 | 43 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
8 | E8H76 | 41542915201 | 503 |  | 1 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H91 | 40609085201 | 9 |  | 41 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8H91 | 40609085201 | 9 |  | -1 | 4 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8I16 | 40614835201 | 503 |  | 3 | 92 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8I60 | 41957015201 | 503 |  | 8 | 7 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8J31 | 42227715201 | 108 |  | 2 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
8 | E8J31 | 42227715201 | 107 |  | 14 | 15 | 2 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
8 | E8J31 | 42227715201 | 112 |  | 5 | 15 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
8 | E8J31 | 42227715201 | 108 |  | 24 | 15 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
8 | E8J31 | 42227715201 | 860 |  | 29 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
8 | E8J36 | 42073515201 | 101 |  | 5 | 23 | 1 | 1 | N | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
8 | E8J36 | 42073515201 | 107 |  | 2 | 23 | 2 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
8 | E8J36 | 42073515201 | 115 |  | 3 | 23 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
8 | E8J36 | 42073515201 | 112 |  | 5 | 23 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
8 | E8J36 | 42073515201 | 107 |  | 26 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
8 | E8J36 | 42073515201 | 107 |  | 28 | 27 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
8 | E8J79 | 41653715201 | 503 |  | 6 | 33 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8J83 | 41960315201 | 4 |  | 30 | 5 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8M60 | 43127515201 | 10 |  | 2 | 83 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8M60 | 43127515201 | 10 |  | 2 | 84 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8M61 | 42815415201 | 503 |  | 23 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8M62 | 40615115201 | 115 |  | 10 | 92 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
8 | E8M63 | 40615215201 | 105 |  | 7 | 76 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
8 | E8M76 | 41548815201 | 108 |  | 21 | 77 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
8 | E8M76 | 41548815201 | 503 |  | 36 | 77 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N19 | 42935015201 | 103 |  | 29 | 36 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
8 | E8N19 | 42935015201 | 118 |  | 14 | 36 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
8 | E8N19 | 42935015201 | 503 |  | 7 | 36 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N19 | 42935015201 | 503 |  | 2 | 36 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N19 | 42935015201 | 113 |  | 3 | 36 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
8 | E8N19 | 42935015201 | 115 |  | 11 | 36 | 6 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
8 | E8N19 | 42935015201 | 105 |  | 11 | 36 | 7 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
8 | E8N19 | 42935015201 | 503 |  | 7 | 36 | 8 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N52 | 42935045201 | 503 |  | 21 | 53 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N60 | 41546265201 | 503 |  | 1 | 28 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N68 | 24301715201 | 105 |  | 14 | 41 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
8 | E8N68 | 24301715201 | 101 |  | 15 | 43 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
8 | E8N68 | 24301715201 | 503 |  | 56 | 44 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8P07 | 43560915201 | 503 |  | 35 | 20 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q11 | 43715625201 | 503 |  | 4 | 24 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q46 | 43717015202 | 503 |  | 16 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q55 | 43914515201 | 503 |  | 10 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q55 | 43914515201 | 503 |  | 7 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q84 | 43990115201 | 503 |  | 14 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 11598 | 6 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 9 | 01co | 1 | 9
01CO | 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | -1499517 | 1891710 | 39 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | -250656 | 0 |  | CO | 3 | 01do | 10 | 12
01CO | 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 6509 | -485989 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 7 | 02co | 13 | 19
01CO | 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 8 | 02do | 20 | 27
01CO | 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 12 | 03co | 28 | 39
01CO | 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 4 | 03do | 40 | 43
01CO | 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 2 | 04co | 44 | 45
01CO | 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 5 | 04do | 46 | 50
01CO | 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 4 | 05co | 51 | 54
01DO | 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 0 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34 |  |  | 0 | 24 | 0 | 0 | 0 | 0 | T | DO | 3 | 05do | 55 | 57
01DO | 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | -783 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO | 7 | 06co | 58 | 64
01DO | 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO | 6 | 06do | 65 | 70
02CO | 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 7440 | 0 | 43 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45 |  |  | 25 | 36 | 0 | 0 | 0 | 0 |  | CO | 6 | 07co | 71 | 76
02CO | 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 45271 | 670366 | 127 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54 |  |  | 33 | 43 | 0 | 0 | 0 | 0 |  | CO | 6 | 07do | 77 | 82
02CO | 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 81763 | 65 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67 |  |  | 50 | 48 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 83 | 82
02CO | 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 8616 | 80 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07 |  |  | 25 | 27 | 0 | 0 | 0 | 0 |  | CO | 5 | 08do | 83 | 87
02CO | 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 27471 | 62 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 66083 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO |  | 0
02DO | 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | -1459708 | 16826383 | 385 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 223 | 0 | 0 | -18219 | 0 |  | DO
02DO | 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | -1251611 | -606983 | 51 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 30442 | 44 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25 |  |  | 7 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 656701 | 89 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79 |  |  | 27 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | -3969 | 52 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46 |  |  | 0 | 37 | 0 | 0 | -60481 | 0 |  | DO
02DO | 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 157836 | 188 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | -84026 | 68219 | 39 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 8875 | 51756 | 76 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 373777 | 60427 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9 |  |  | 3 | 41 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 334168 | -32998 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 0 | -2208 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 321209 | 405998 | 157 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62 |  |  | 13 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 57366 | 27889 | 69 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76 |  |  | 7 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 100163 | 31248 | 167 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | -464 | 209861 | 112 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 0 | 13 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95 |  |  | 1 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 148555 | 3908 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 0 | -4732 | 101 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-05-13 | QTR4 | 18/19 | 308 | 795145 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 442812 | 198133 | 145 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16 |  |  | 8 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 189028 | 165338 | 66 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18 |  |  | 30 | 42 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | -417090 | -338192 | 219 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 89 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | -3249187 | 3281488 | 165 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 64 | 0 | 0 | -202797 | 0 |  | DO
04DO | 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 48308 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 0 | 0 | 1 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | -3056235 | 3576803 | 117 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 3 | 48 | 0 | 0 | -155690 | 0 |  | CO
05CO | 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 26406 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 20194 | 36 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871 |  |  | 17 | 48 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 133799 | 15 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25 |  |  | 1 | 33 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 0 | 0 | 22 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5 |  |  | 11 | 3 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 5872 | 2030258 | 59 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 21903 | 44 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 37940 | 56 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 92454 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 0 | 48 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | -24 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 606 | 324690 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 1013 | 67062 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 649560 | 1806784 | 96 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | -358123 | 1067468 | 84 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 0 | 23 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | -87 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 11195 | 18352 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400 |  |  | 10 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 0 | 68 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM | 12 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | -265912 | 1412899 | 124 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 160448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1145625 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 56 | 53 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 232401 | 76 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 2402 | 0 | 242 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000 |  |  | 7 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | -14425 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | -965750 | -115989 | 28 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 34423 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | -6566 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0