## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 60976282 | 60430300 | 63185265 | 63297001 | 2220000 | 64219762 | 6.271% | 88.89% | 2098691 | 3.473% | 2208983 | 3.623% | 3142 | 503 | 16.01% | 204 | 6.493% | 1 | 0.03183% | 180 | 5.729% | 3323 | 5.761% | 4034 | 3611 | 2904 | -7.575% | 100%
| District Let | 13445742 | 13270989 | 13445742 | 13489614 | 0 | 13837853 | 4.271% | 100% | 26214 | 0.1975% | 0 | 0% | 710 | 59 | 8.31% | 50 | 7.042% | 14 | 1.972% | 0 | 0% | 724 | 1.972% | 833 | 799 | 690 | -2.817% | 100%
| All Contracts | 74422024 | 73701289 | 76631007 | 76786615 | 2220000 | 78057615 | 5.911% | 90.48% | 2124905 | 2.883% | 2208983 | 2.968% | 3852 | 562 | 14.59% | 254 | 6.594% | 15 | 0.3894% | 180 | 4.673% | 4047 | 5.062% | 4867 | 4410 | 3594 | -6.698% | 100%
2 | Central Let | 96454129 | 95382493 | 98274843 | 98997704 | 0 | 100256792 | 5.11% | 66.67% | 2004714 | 2.102% | 1820716 | 1.888% | 4024 | 857 | 21.3% | 514 | 12.77% | 97 | 2.411% | 805 | 20% | 4926 | 22.42% | 6297 | 6130 | 4759 | 18.27% | 60%
| District Let | 256905983 | 256040519 | 273893806 | 273848981 | 0 | 270960379 | 5.827% | 63.64% | 17034996 | 6.653% | 16987824 | 6.612% | 5019 | 788 | 15.7% | 586 | 11.68% | 54 | 1.076% | 1080 | 21.52% | 6153 | 22.59% | 7527 | 7279 | 5905 | 17.65% | 72.73%
| All Contracts | 353360112 | 351423012 | 372168649 | 372846685 | 0 | 371217171 | 5.633% | 65.38% | 19039710 | 5.418% | 18808540 | 5.323% | 9043 | 1645 | 18.19% | 1100 | 12.16% | 151 | 1.67% | 1885 | 20.84% | 11079 | 22.51% | 13824 | 13409 | 10664 | 17.93% | 65.38%
3 | Central Let | 60698812 | 59843795 | 61710000 | 61875762 | 0 | 61250418 | 2.35% | 81.25% | 1064910 | 1.779% | 1011186 | 1.666% | 3069 | 1236 | 40.27% | 428 | 13.95% | 128 | 4.171% | 170 | 5.539% | 3367 | 9.71% | 5031 | 5017 | 3353 | 9.254% | 81.25%
| District Let | 8217756 | 8028787 | 8293859 | 8391088 | 0 | 8589117 | 6.979% | 100% | 62978 | 0.7844% | 76103 | 0.9261% | 770 | 207 | 26.88% | 131 | 17.01% | 39 | 5.065% | 1 | 0.1299% | 810 | 5.195% | 1148 | 1128 | 790 | 2.597% | 100%
| All Contracts | 68916568 | 67872582 | 70003859 | 70266850 | 0 | 69839535 | 2.898% | 85.71% | 1127888 | 1.662% | 1087289 | 1.578% | 3839 | 1443 | 37.59% | 559 | 14.56% | 167 | 4.35% | 171 | 4.454% | 4177 | 8.804% | 6179 | 6145 | 4143 | 7.919% | 85.71%
4 | Central Let | 66035972 | 65416361 | 67370505 | 63687577 | 0 | 64742017 | -1.031% | 88.89% | 1211595 | 1.852% | 1334532 | 2.021% | 3387 | 790 | 23.32% | 293 | 8.651% | 0 | 0% | 250 | 7.381% | 3637 | 7.381% | 4720 | 4692 | 3609 | 6.554% | 88.89%
| District Let | 383970392 | 382828510 | 391522472 | 390422121 | 1420000 | 380453855 | -0.6203% | 92.31% | 7035005 | 1.838% | 7552080 | 1.967% | 8480 | 973 | 11.47% | 470 | 5.542% | 2 | 0.02358% | 443 | 5.224% | 8925 | 5.248% | 10367 | 9704 | 8261 | -2.583% | 92.31%
| All Contracts | 450006364 | 448244871 | 458892977 | 454109698 | 1420000 | 445195872 | -0.6802% | 90.91% | 8246600 | 1.84% | 8886612 | 1.975% | 11867 | 1763 | 14.86% | 763 | 6.43% | 2 | 0.01685% | 693 | 5.84% | 12562 | 5.857% | 15087 | 14396 | 11870 | 0.02528% | 90.91%
5 | Central Let | 92536512 | 91980512 | 96340686 | 96437102 | 44500 | 93576376 | 1.735% | 100% | 3981692 | 4.329% | 3804174 | 4.111% | 3480 | 259 | 7.443% | 326 | 9.368% | 0 | 0% | 84 | 2.414% | 3564 | 2.414% | 4149 | 3757 | 3172 | -8.851% | 100%
| District Let | 24118166 | 23572665 | 25315119 | 24604453 | 0 | 24113307 | 2.294% | 83.33% | 1232914 | 5.23% | 1196953 | 4.963% | 2624 | 334 | 12.73% | 289 | 11.01% | 11 | 0.4192% | 494 | 18.83% | 3129 | 19.25% | 3752 | 3805 | 3182 | 21.27% | 83.33%
| All Contracts | 116654678 | 115553177 | 121655805 | 121041555 | 44500 | 117689683 | 1.849% | 89.47% | 5214606 | 4.513% | 5001127 | 4.287% | 6104 | 593 | 9.715% | 615 | 10.08% | 11 | 0.1802% | 578 | 9.469% | 6693 | 9.649% | 7901 | 7562 | 6354 | 4.096% | 89.47%
6 | Central Let | 70161573 | 68218814 | 73526152 | 72331768 | 1300000 | 72087527 | 5.671% | 90.91% | 3787699 | 5.552% | 3364577 | 4.795% | 3612 | 541 | 14.98% | 194 | 5.371% | 113 | 3.128% | 235 | 6.506% | 3960 | 9.635% | 4695 | 4364 | 3629 | 0.4707% | 90.91%
| District Let | 93531576 | 93000112 | 98029302 | 96981540 | 400000 | 97154112 | 4.467% | 100% | 2519430 | 2.709% | 2965314 | 3.17% | 3030 | 430 | 14.19% | 152 | 5.017% | 0 | 0% | 28 | 0.9241% | 3058 | 0.9241% | 3640 | 3498 | 2916 | -3.762% | 100%
| All Contracts | 163693149 | 161218926 | 171555454 | 169313308 | 1700000 | 169241639 | 4.976% | 95% | 6307129 | 3.912% | 6329891 | 3.867% | 6642 | 971 | 14.62% | 346 | 5.209% | 113 | 1.701% | 263 | 3.96% | 7018 | 5.661% | 8335 | 7862 | 6545 | -1.46% | 95%
7 | Central Let | 10843926 | 10539146 | 10869005 | 10430457 | 0 | 10406096 | -1.262% | 100% | 109282 | 1.037% | 25080 | 0.2313% | 968 | 218 | 22.52% | 128 | 13.22% | 13 | 1.343% | 57 | 5.888% | 1038 | 7.231% | 1384 | 1473 | 1127 | 16.43% | 85.71%
| District Let | 133382387 | 132757062 | 137613096 | 137004362 | 250000 | 135203807 | 1.843% | 100% | 4090620 | 3.081% | 4230709 | 3.172% | 2806 | 1111 | 39.59% | 305 | 10.87% | 0 | 0% | 292 | 10.41% | 3098 | 10.41% | 4514 | 4481 | 3065 | 9.23% | 100%
| All Contracts | 144226313 | 143296208 | 148482101 | 147434819 | 250000 | 145609903 | 1.615% | 100% | 4199902 | 2.931% | 4255789 | 2.951% | 3774 | 1329 | 35.21% | 433 | 11.47% | 13 | 0.3445% | 349 | 9.247% | 4136 | 9.592% | 5898 | 5954 | 4192 | 11.08% | 93.75%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 108352586 | 107675027 | 110765548 | 111615019 | 2385000 | 111113005 | 3.193% | 100% | 2571858 | 2.389% | 2412962 | 2.227% | 2737 | 276 | 10.08% | 193 | 7.052% | 84 | 3.069% | 80 | 2.923% | 2901 | 5.992% | 3370 | 3069 | 2600 | -5.005% | #VALUE!
| All Contracts | 108352586 | 107675027 | 110765548 | 111615019 | 2385000 | 111113005 | 3.193% | 100% | 2571858 | 2.389% | 2412962 | 2.227% | 2737 | 276 | 10.08% | 193 | 7.052% | 84 | 3.069% | 80 | 2.923% | 2901 | 5.992% | 3370 | 3069 | 2600 | -5.005% | 100%
Totals This Qtr | Central Let | 457707206 | 451811421 | 471276456 | 467057371 | 3564500 | 466538988 | 3.26% | 85.54% | 14258583 | 3.156% | 13569248 | 2.965% | 21682 | 4404 | 20.31% | 2087 | 9.625% | 352 | 1.623% | 1781 | 8.214% | 23815 | 9.838% | 30310 | 29044 | 22553 | 4.017% | 85.54%
| District Let | 1021924588 | 1017173671 | 1058878944 | 1056357178 | 4455000 | 1041425435 | 2.384% | 90.14% | 34574015 | 3.399% | 35421945 | 3.466% | 26176 | 4178 | 15.96% | 2176 | 8.313% | 204 | 0.7793% | 2418 | 9.237% | 28798 | 10.02% | 35151 | 33763 | 27409 | 4.71% | 91.55%
| All Contracts | 1479631794 | 1468985092 | 1530155400 | 1523414549 | 8019500 | 1507964423 | 2.653% | 87.66% | 48832598 | 3.324% | 48991193 | 3.311% | 47858 | 8582 | 17.93% | 4263 | 8.908% | 556 | 1.162% | 4199 | 8.774% | 52613 | 9.936% | 65461 | 62807 | 49962 | 4.396% | 88.31%
Totals Previous Quarter | Central Let | 259209194 | 256787937 | 268646620 | 267943503 | 2424500 | 265823304 | 3.519% | 87.23% | 9646764 | 3.757% | 9437427 | 3.641% | 11472 | 2518 | 21.95% | 1137 | 9.911% | 265 | 2.31% | 911 | 7.941% | 12648 | 10.25% | 16307 | 15664 | 12009 | 4.681% | 82.98%
| District Let | 555180481 | 552483433 | 581330343 | 579456620 | 405000 | 571449684 | 3.433% | 87.5% | 23877767 | 4.322% | 24617451 | 4.434% | 14382 | 2495 | 17.35% | 1313 | 9.129% | 175 | 1.217% | 1626 | 11.31% | 16183 | 12.52% | 19990 | 19103 | 15295 | 6.348% | 92.5%
| All Contracts | 814389675 | 809271370 | 849976963 | 847400123 | 2829500 | 837272988 | 3.46% | 87.36% | 33524531 | 4.143% | 34054878 | 4.182% | 25854 | 5013 | 19.39% | 2450 | 9.476% | 440 | 1.702% | 2537 | 9.813% | 28831 | 11.51% | 36297 | 34767 | 27304 | 5.608% | 87.36%
Totals Fiscal Year 2018/2019 | Central Let | 1245791056 | 1233826432 | 1290308424 | 1290743418 | 11354325 | 1272211402.08 | 3.111% | 92.68% | 44743423 | 3.626% | 44444005 | 3.568% | 51070 | 10333 | 20.23% | 4417 | 8.649% | 1987 | 3.891% | 2974 | 5.823% | 56031 | 9.714% | 71119 | 69464 | 54714 | 7.135% | 84.15%
| District Let | 1083536931 | 1076274846 | 1166469706 | 1158597181 | 1605000 | 1125497490 | 4.573% | 91.97% | 82452189 | 7.661% | 82932771 | 7.654% | 39155 | 6879 | 17.57% | 3581 | 9.146% | 1190 | 3.039% | 3778 | 9.649% | 44123 | 12.69% | 54718 | 53095 | 42635 | 8.888% | 89.78%
| All Contracts | 2329327987 | 2310101278 | 2456778130 | 2449340599 | 12959325 | 2397708892.08 | 3.792% | 92.36% | 127195612 | 5.506% | 127376776 | 5.468% | 90225 | 17212 | 19.08% | 7998 | 8.865% | 3177 | 3.521% | 6752 | 7.484% | 100154 | 11% | 125837 | 122559 | 97349 | 7.896% | 86.71%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 100.8% | 1 | 410 | 11598 | 6 | 16 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM
| 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 87.63% | 1 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | 107.6% | 1 | -1499517 | 1891710 | 39 | 35 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 50.62% | 1 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 57.34% | 1 | 6509 | -485989 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 |  | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM
| 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 101.8% | 1 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 108.5% | 1 | 300819 | 240997 | 138 | 47 | 0 | 7 | 201334 | 0 | 0 | 0 | 15623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 229783 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73
| 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 113.2% | 1 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 115.3% | 0 | 795 | 374249 | 101 | 25 | 0 | 33 | 244703 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 274622 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS
| 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 91.5% | 1 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | 104.6% | 1 | -889 | 49336 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 |  | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61
| 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 101.2% | 1 | 0 | 0 | 49 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66
| 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 99.09% | 1 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 98.36% | 1 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82
| 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 73.6% | 1 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | 105.9% | 1 | -6 | 7262 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93
| 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 100.7% | 1 | 0 | 0 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM
| 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | 106.4% | 1 | -485 | 59543 | 17 | 5 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM
| 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 86.36% | 1 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 93.87% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM
| 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 86.15% | 1 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 99.42% | 1 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36
| 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 100% | 1 | 0 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM
| 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 69% | 1 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 100% | 1 | 0 | 0 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM
| 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 98.34% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52
| 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 101% | 1 | 0 | 0 | 11 | 5 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM
| 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 115.9% | 0 | 0 | 60277 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 18 | 34 | 47 | 3142 | 4034 | 3611 | 100% | 18 | 423 | 0 | 0 | 708 | 184 | 60976282 | 545982 | 60430300 | 63185265 | 63297001 | 0 | 2220000 | 2220000 | 65517001 | 64219762 | 88.89% | 16 | -1192364 | 2208983 | 503 | 204 | 0 | 40 | 1256356 | 0 | 0 | 140 | 1549882 | 6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -484189 | 0 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 1 | 180 | 2098691 | 6308
| 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 103.5% | 1 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 107% | 1 | 361384 | 0 | 43 | 24 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34
| 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 97.6% | 1 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | 101.6% | 1 | -783 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69
| 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 83.24% | 1 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | 98.1% | 1 | -12362 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 0 | 710 | 833 | 799 | 100% | 3 | 34 | 0 | 0 | 123 | 0 | 13445742 | 174753 | 13270989 | 13445742 | 13489614 | 0 | 0 | 0 | 13489614 | 13837853 | 100% | 3 | 348239 | 0 | 59 | 50 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0
| District 01 Totals |  |  |  |  | 21 | 38 | 47 | 3852 | 4867 | 4410 | 100% | 21 | 457 | 0 | 0 | 831 | 184 | 74422024 | 720735 | 73701289 | 76631007 | 76786615 | 0 | 2220000 | 2220000 | 79006615 | 78057615 | 90.48% | 19 | -844125 | 2208983 | 562 | 254 | 0 | 40 | 1256356 | 0 | 14 | 140 | 1566795 | 6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -474888 | 0 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 15 | 180 | 2124905 | 6308
| 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 120.6% | 0 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | 98.56% | 1 | -354944 | 150000 | 87 | 47 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74
| 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | 171.9% | 0 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | 100.5% | 1 | -191646 | 313457 | 83 | 110 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88
| 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | 135.9% | 0 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 100.6% | 1 | 7440 | 0 | 43 | 36 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45
| 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 126.9% | 0 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 111% | 0 | 45271 | 670366 | 127 | 43 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 |  | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54
| 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 119.8% | 1 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 102.4% | 1 | 15232 | 81763 | 65 | 48 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67
| 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 198.9% | 0 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 114.5% | 0 | 9762 | 362855 | 62 | 30 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92
| 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 108.3% | 1 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 112.7% | 0 | 804997 | 8616 | 80 | 27 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07
| 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 130.9% | 0 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 113.6% | 0 | 80901 | 27471 | 62 | 25 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62
| 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 86.07% | 1 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 106.1% | 1 | 354385 | 0 | 54 | 40 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27
| 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 108.3% | 1 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 104.3% | 1 | 0 | 66083 | 30 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 |  | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7
| 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14534510 | 0 | 0 | 0 | 14534510 | 15189271 | 111.2% | 0 | 654761 | 0 | 94 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57
| 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 108.1% | 1 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3729852 | 98.55% | 1 | 38471 | 53332 | 27 | 37 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59
| 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 86.04% | 1 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | 104.5% | 1 | -21380 | 86773 | 31 | 24 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39
| 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 65% | 1 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | 99.5% | 1 | -29525 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 |  | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85
| 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 74.29% | 1 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 99.5% | 1 | 6452 | 0 | 5 | 3 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 15 | 25 | 38 | 4024 | 6297 | 6130 | 60% | 9 | 167 | 41 | 0 | 1468 | 805 | 96454129 | 1071635 | 95382493 | 98274843 | 98997704 | -150064 | 0 | -150064 | 98847640 | 100256792 | 66.67% | 10 | 1420177 | 1820716 | 857 | 514 | 44 | 203 | 612762 | 57134 | 0 | 253 | 1053416 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 84857 | 0 | 0 | 1 | 24070 | 5643 | 0 | 0 | 0 | 0 | 0 | 20 | 8988 | 0 | 0 | 292 | 27471 | 27471 | 53 | 34 | 193150 | 70550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 805 | 2004714 | 196632
| 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 157.7% | 0 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | 110.5% | 0 | -1459708 | 16826383 | 385 | 223 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18219 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | 128.4% | 0 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | 97.09% | 1 | -1251611 | -606983 | 51 | 65 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 116.3% | 1 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 112.2% | 0 | 298956 | 30442 | 44 | 26 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25
| 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 170.6% | 0 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 123.3% | 0 | 110065 | 656701 | 89 | 38 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 |  | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79
| 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 85.78% | 1 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 100.6% | 1 | 2 | 0 | 67 | 39 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25
| 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 103.5% | 1 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 96.37% | 1 | 2 | -3969 | 52 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60481 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 |  | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46
| 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 99.21% | 1 | 0 | 0 | 20 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 |  | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23
| 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | 99.4% | 1 | -932 | 0 | 21 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46
| 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 74.6% | 1 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 100.3% | 1 | 0 | 0 | 26 | 39 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 |  | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17
| 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 76.19% | 1 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 98.98% | 1 | 0 | 0 | 14 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 11 | 16 | 50 | 5019 | 7527 | 7279 | 72.73% | 8 | 248 | 18 | 0 | 1428 | 1080 | 256905983 | 865463 | 256040519 | 273893806 | 273848981 | -229932 | 0 | -229932 | 273619049 | 270960379 | 63.64% | 7 | -2291548 | 16987824 | 788 | 586 | 54 | 203 | 2308253 | 238783 | 0 | 639 | 14528308 | 1224199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 231 | 163837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78700 | 0 | 54 | 1080 | 17034996 | 1462982
| District 02 Totals |  |  |  |  | 26 | 41 | 88 | 9043 | 13824 | 13409 | 65.38% | 17 | 415 | 59 | 0 | 2896 | 1885 | 353360112 | 1937098 | 351423012 | 372168649 | 372846685 | -379996 | 0 | -379996 | 372466689 | 371217171 | 65.38% | 17 | -871371 | 18808540 | 1645 | 1100 | 98 | 406 | 2921015 | 295917 | 0 | 892 | 15581724 | 1260033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 233 | 248694 | 0 | 0 | 1 | 24070 | 5643 | 0 | 0 | 0 | 0 | 0 | 27 | 8988 | 0 | 0 | 292 | 27471 | 27471 | 53 | 34 | 193150 | 70550 | 0 | 0 | 0 | 0 | 0 | 0 | -78700 | 0 | 151 | 1885 | 19039710 | 1659614
| 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | 114.3% | 1 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | 90.98% | 1 | -1453386 | 157836 | 188 | 58 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28
| 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | 129.8% | 0 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | 96.12% | 1 | -84026 | 68219 | 39 | 20 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 |  | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84
| 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 121.7% | 0 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 106% | 1 | 8875 | 51756 | 76 | 28 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44
| 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 104.8% | 1 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | 95.32% | 1 | -6959 | 0 | 66 | 24 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75
| 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 104.3% | 1 | 373777 | 60427 | 75 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485
| 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | 100.6% | 1 | -2578 | 6645 | 68 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65
| 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 102.1% | 1 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | 98.23% | 1 | -2508 | 0 | 76 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9
| 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 118.3% | 1 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 113.7% | 0 | 168914 | 26513 | 52 | 23 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2019-01-11 | QTR3 | 18/19 | 308 | 0
| 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 99.04% | 1 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 108.7% | 1 | 334168 | -32998 | 50 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16
| 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 96% | 1 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 98.38% | 1 | 0 | -2208 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43
| 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 104.2% | 1 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 114% | 0 | 321209 | 405998 | 157 | 26 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62
| 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 133.8% | 0 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 105.4% | 1 | 57366 | 27889 | 69 | 25 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76
| 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 100% | 1 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 114% | 0 | 100163 | 31248 | 167 | 43 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49
| 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 94.48% | 1 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | 107.9% | 1 | -464 | 209861 | 112 | 20 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000
| 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 95.56% | 1 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 101.7% | 1 | 0 | 0 | 22 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24
| 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 98.89% | 1 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 99.76% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 16 | 22 | 34 | 3069 | 5031 | 5017 | 81.25% | 13 | 14 | 34 | 0 | 1792 | 170 | 60698812 | 855016 | 59843795 | 61710000 | 61875762 | -198291 | 0 | -198291 | 61677471 | 61250418 | 81.25% | 13 | -185449 | 1011186 | 1236 | 428 | 0 | 62 | 596138 | 15783602 | 97 | 90 | 365465 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15342 | 10742 | 17 | 3 | 57843 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 23475 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 0 | 0 | 128 | 170 | 1064910 | 15812503
| 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 115.7% | 1 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 104.7% | 1 | 52521 | 0 | 13 | 25 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95
| 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 94.44% | 1 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 109.1% | 1 | 148555 | 3908 | 52 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8
| 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 97.78% | 1 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 102.4% | 1 | 0 | -4732 | 101 | 60 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-05-13 | QTR4 | 18/19 | 308 | 795145
| 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 105.4% | 1 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 109% | 1 | 63342 | 76927 | 41 | 24 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46
| 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 84.44% | 1 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0% | 1 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 5 | 9 | 8 | 770 | 1148 | 1128 | 100% | 5 | 20 | 0 | 0 | 377 | 1 | 8217756 | 188969 | 8028787 | 8293859 | 8391088 | -1871 | 0 | -1871 | 8389217 | 8589117 | 100% | 5 | 219418 | 76103 | 207 | 131 | 21 | 0 | 2415 | 0 | 18 | 1 | 66119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 62978 | 8288
| District 03 Totals |  |  |  |  | 21 | 31 | 42 | 3839 | 6179 | 6145 | 85.71% | 18 | 34 | 34 | 0 | 2169 | 171 | 68916568 | 1043985 | 67872582 | 70003859 | 70266850 | -200162 | 0 | -200162 | 70066688 | 69839535 | 85.71% | 18 | 33969 | 1087289 | 1443 | 559 | 21 | 62 | 598553 | 15783602 | 115 | 91 | 431584 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9786 | 19030 | 17 | 3 | 57843 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 23475 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 0 | 0 | 167 | 171 | 1127888 | 15820791
| 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 100.2% | 1 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 98.32% | 1 | 442812 | 198133 | 145 | 57 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 |  | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16
| 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | 119.4% | 1 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 91.7% | 1 | 855652 | 75851 | 215 | 58 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 |  | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 106.6% | 1 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 100.7% | 1 | 189028 | 165338 | 66 | 42 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 |  | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18
| 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 132.6% | 0 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7145526 | 115.4% | 0 | 130865 | 533617 | 55 | 41 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 107.8% | 1 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | 99.64% | 1 | -156 | -6176 | 89 | 27 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55
| 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 109.5% | 1 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 104.4% | 1 | 83036 | 308276 | 109 | 33 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 |  | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96
| 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 99.32% | 1 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | 100.4% | 1 | -4859 | 47624 | 74 | 22 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18
| 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 64.44% | 1 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 96.63% | 1 | 4043 | 0 | 6 | 5 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05
| 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 103.1% | 1 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 99.63% | 1 | 1280 | 11869 | 31 | 8 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 9 | 17 | 36 | 3387 | 4720 | 4692 | 88.89% | 8 | 28 | 91 | 0 | 1083 | 250 | 66035972 | 619612 | 65416361 | 67370505 | 63687577 | -427518 | 0 | -427518 | 63260059 | 64742017 | 88.89% | 8 | 1701701 | 1334532 | 790 | 293 | 0 | 36 | 540685 | 4956 | 0 | 156 | 387310 | 7698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 28 | 159605 | 395 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 1211595 | 13049
| 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 100.9% | 1 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | 98.74% | 1 | -6213797 | 2243984 | 183 | 45 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -404828 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 102.1% | 1 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | 95.08% | 1 | -417090 | -338192 | 219 | 89 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 95.23% | 1 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | 99.35% | 1 | -3249187 | 3281488 | 165 | 64 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 |  | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | 101.9% | 1 | -500000 | 58245 | 22 | 76 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | 109.7% | 1 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | 99.01% | 1 | -4739 | 364238 | 220 | 71 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 97.73% | 1 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 114.7% | 0 | 167827 | 1860107 | 73 | 34 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | 151.3% | 0 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 99.55% | 1 | 172641 | 33902 | 24 | 21 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1
| 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 113% | 1 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 99.98% | 1 | 2288 | 48308 | 23 | 34 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 |  | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12
| 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 101.4% | 1 | 2719 | 0 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33
| 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 101.7% | 1 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 |  | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67
| 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 30.92% | 1 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 100.3% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42
| 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 48.93% | 1 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 99.58% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28
| 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 50.41% | 1 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 99.12% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 13 | 27 | 69 | 8480 | 10367 | 9704 | 92.31% | 12 | 663 | 98 | 0 | 1445 | 442 | 383970392 | 1141882 | 382828510 | 391522472 | 390422121 | -665094 | 1420000 | 754906 | 391177027 | 380453855 | 92.31% | 12 | -10039338 | 7552080 | 973 | 470 | 2 | 194 | 3209999 | 7451 | 0 | 68 | 1369609 | 139319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 27 | 1468575 | 37471 | 0 | 35 | 201633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1355416 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -607625 | 0 | 2 | 443 | 7035005 | 218834
| District 04 Totals |  |  |  |  | 22 | 44 | 105 | 11867 | 15087 | 14396 | 90.91% | 20 | 691 | 189 | 0 | 2528 | 692 | 450006364 | 1761494 | 448244871 | 458892977 | 454109698 | -1092612 | 1420000 | 327388 | 454437086 | 445195872 | 90.91% | 20 | -8337637 | 8886612 | 1763 | 763 | 2 | 230 | 3750684 | 12407 | 0 | 224 | 1756919 | 147017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40400 | 0 | 0 | 55 | 1628180 | 37866 | 0 | 35 | 288376 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34253 | 0 | 0 | 119 | 1355416 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -607625 | 0 | 2 | 693 | 8246600 | 231883
| 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 102.4% | 1 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | 101.4% | 1 | -3056235 | 3576803 | 117 | 48 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 76% | 1 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | 101.8% | 1 | -30000 | 19031 | 14 | 56 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 82.37% | 1 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | 100.9% | 1 | -14500 | 0 | 18 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75
| 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 107.7% | 1 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 108% | 1 | 265414 | 161314 | 43 | 47 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492
| 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 76.58% | 1 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 101.2% | 1 | 0 | 26406 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410
| 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 112.8% | 1 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 99.75% | 1 | 6737 | 20194 | 36 | 48 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871
| 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 88.85% | 1 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | 103.2% | 1 | -4945 | 426 | 29 | 31 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 7 | 16 | 50 | 3480 | 4149 | 3757 | 100% | 7 | 392 | 0 | 0 | 585 | 84 | 92536512 | 556000 | 91980512 | 96340686 | 96437102 | -56415 | 44500 | -11915 | 96425187 | 93576376 | 100% | 7 | -2833529 | 3804174 | 259 | 326 | 0 | 39 | 994931 | 25021 | 0 | 45 | 1382116 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316475 | 0 | 0 | 0 | 28774 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 84 | 3981692 | 66084
| 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | 128.3% | 0 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10738882 | 92.02% | 1 | -80694 | -387154 | 69 | 35 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | 226% | 0 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 180.3% | 0 | 1451 | 1363962 | 39 | 51 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842
| 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 99.29% | 1 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 82.89% | 1 | 1940 | -10 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 |  | 2017-05-14 | QTR4 | 16/17 | 509 | 843684
| 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 111.3% | 1 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | 105.8% | 1 | -795 | 50000 | 60 | 28 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169
| 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 85% | 1 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 100% | 1 | 0 | 0 | 21 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655
| 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 116.1% | 1 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | 109.1% | 1 | -3198 | 133799 | 15 | 33 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25
| 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | 107.5% | 1 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 105.8% | 1 | 0 | 33356 | 25 | 41 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-07-22 | QTR1 | 19/20 | 513 | 480184
| 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 98.18% | 1 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 100% | 1 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 |  | 2019-07-18 | QTR1 | 19/20 | 509 | 441431
| 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | 113.3% | 1 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 114.4% | 0 | 0 | 0 | 22 | 3 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5
| 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 115% | 1 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 97.22% | 1 | 0 | 0 | 29 | 10 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2
| 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 97% | 1 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 100.2% | 1 | 0 | 3000 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75
| 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 93.82% | 1 | 0 | 0 | 22 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 513 | 554880
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 12 | 14 | 16 | 2624 | 3752 | 3805 | 83.33% | 10 | -53 | 101 | 0 | 634 | 494 | 24118166 | 545501 | 23572665 | 25315119 | 24604453 | -391436 | 0 | -391436 | 24213017 | 24113307 | 83.33% | 10 | -81296 | 1196953 | 334 | 289 | 11 | 142 | 144638 | 0 | 0 | 192 | 907853 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 179432 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 494 | 1232914 | 9379
| District 05 Totals |  |  |  |  | 19 | 30 | 66 | 6104 | 7901 | 7562 | 89.47% | 17 | 339 | 101 | 0 | 1219 | 578 | 116654678 | 1101501 | 115553177 | 121655805 | 121041555 | -447851 | 44500 | -403351 | 120638204 | 117689683 | 89.47% | 17 | -2914825 | 5001127 | 593 | 615 | 11 | 181 | 1139569 | 25021 | 0 | 237 | 2289969 | 50442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 495907 | 0 | 0 | 0 | 29774 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493161 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 11 | 578 | 5214606 | 75463
| 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 98.35% | 1 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | 100.4% | 1 | -436405 | 725324 | 52 | 25 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 82.12% | 1 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | 104.4% | 1 | -622662 | 376451 | 74 | 40 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 195.7% | 0 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 166% | 0 | 5872 | 2030258 | 59 | 33 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 105.5% | 1 | 21437 | 21903 | 44 | 6 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25
| 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 72.1% | 1 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | 103.4% | 1 | -191642 | 37940 | 56 | 14 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 |  | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 88.67% | 1 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | 98.77% | 1 | -61063 | 80247 | 31 | 18 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 101.3% | 1 | 1476 | 92454 | 90 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 |  | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45
| 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 108.3% | 1 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | 99.99% | 1 | -4122 | 0 | 48 | 19 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 |  | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7
| 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 118% | 1 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | 93.91% | 1 | -1279 | 0 | 40 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85
| 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | 92.06% | 1 | -1113 | 0 | 34 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 |  | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25
| 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 97.3% | 1 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | 98.31% | 1 | -24 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 606 | 324690
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 11 | 44 | 41 | 3612 | 4695 | 4364 | 90.91% | 10 | 331 | 0 | 0 | 848 | 235 | 70161573 | 1942759 | 68218814 | 73526152 | 72331768 | 0 | 1300000 | 1300000 | 73631768 | 72087527 | 90.91% | 10 | -1289525 | 3364577 | 541 | 194 | 15 | 24 | 1707512 | 130000 | 0 | 178 | 1487299 | 344658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 504355 | 39656 | 0 | 0 | 18823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 113 | 235 | 3787699 | 1084719
| 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 95.74% | 1 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 99.71% | 1 | 1013 | 67062 | 142 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1
| 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 103.3% | 1 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 105% | 1 | 649560 | 1806784 | 96 | 54 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 84.26% | 1 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | 109.7% | 1 | -358123 | 1067468 | 84 | 14 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 80% | 1 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 93.85% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 |  | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8
| 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 96% | 1 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 104.9% | 1 | 0 | 24000 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 606 | 404500
| 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 92.75% | 1 | 0 | 0 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 |  | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218
| 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 97.08% | 1 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | 93.08% | 1 | -158 | 0 | 23 | 11 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2
| 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | 96.53% | 1 | -87 | 0 | 51 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5
| 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 99.5% | 1 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | 99.55% | 1 | -352 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 9 | 16 | 20 | 3030 | 3640 | 3498 | 100% | 9 | 142 | 0 | 0 | 582 | 28 | 93531576 | 531464 | 93000112 | 98029302 | 96981540 | 0 | 400000 | 400000 | 97381540 | 97154112 | 100% | 9 | 291853 | 2965314 | 430 | 152 | 0 | 28 | 1385511 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664358 | 48552 | 0 | 0 | 98023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2519430 | 169085
| District 06 Totals |  |  |  |  | 20 | 60 | 61 | 6642 | 8335 | 7862 | 95% | 19 | 473 | 0 | 0 | 1430 | 263 | 163693149 | 2474223 | 161218926 | 171555454 | 169313308 | 0 | 1700000 | 1700000 | 171013308 | 169241639 | 95% | 19 | -997672 | 6329891 | 971 | 346 | 15 | 52 | 3093023 | 130000 | 0 | 178 | 1859982 | 465191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 1168713 | 88208 | 0 | 0 | 116846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 113 | 263 | 6307129 | 1253804
| 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | 206.2% | 0 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 93.7% | 1 | 11195 | 18352 | 19 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400
| 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 99.3% | 1 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 99.75% | 1 | 69368 | 0 | 68 | 19 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000
| 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 101.5% | 1 | 65512 | 6728 | 41 | 21 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300
| 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 111.1% | 1 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 99.28% | 1 | 6971 | 0 | 61 | 22 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM
| 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 91.82% | 1 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 98.93% | 1 | 0 | 0 | 24 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000
| 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 90.89% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5
| 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 93.17% | 1 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 100.7% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 7 | 11 | 2 | 968 | 1384 | 1473 | 85.71% | 6 | -89 | 112 | 0 | 359 | 57 | 10843926 | 304780 | 10539146 | 10869005 | 10430457 | -177408 | 0 | -177408 | 10253049 | 10406096 | 100% | 7 | 153046 | 25080 | 218 | 128 | 13 | 44 | 59721 | 0 | 0 | 13 | 48488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 57 | 109282 | 0
| 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 119.1% | 1 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | 101% | 1 | -1461417 | 2388357 | 330 | 85 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 111.7% | 1 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | 105.4% | 1 | -265912 | 1412899 | 124 | 53 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 105.5% | 1 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 104.4% | 1 | 301 | 232401 | 76 | 23 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26
| 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | 100.5% | 1 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 100.6% | 1 | 2402 | 0 | 242 | 27 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311
| 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 74% | 1 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 98.67% | 1 | 0 | 0 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000
| 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 117.1% | 1 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | 106.5% | 1 | -5930 | 197052 | 173 | 25 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65
| 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | 112.1% | 1 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | 98.97% | 1 | -14425 | 0 | 36 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38
| 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 69.7% | 1 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 84.89% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 798 | 175000
| 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 100% | 1 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 90.04% | 1 | 0 | 0 | 106 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 9 | 16 | 27 | 2806 | 4514 | 4481 | 100% | 9 | 33 | 21 | 0 | 1416 | 292 | 133382387 | 625325 | 132757062 | 137613096 | 137004362 | -72585 | 250000 | 177415 | 137181777 | 135203807 | 100% | 9 | -1744981 | 4230709 | 1111 | 305 | 0 | 92 | 2618687 | 721481 | 0 | 142 | 1021734 | 38621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 58 | 331759 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 4090620 | 822970
| District 07 Totals |  |  |  |  | 16 | 27 | 29 | 3774 | 5898 | 5954 | 93.75% | 15 | -56 | 133 | 0 | 1775 | 349 | 144226313 | 930105 | 143296208 | 148482101 | 147434819 | -249993 | 250000 | 7 | 147434826 | 145609903 | 100% | 16 | -1591935 | 4255789 | 1329 | 433 | 13 | 136 | 2678408 | 721481 | 0 | 155 | 1070222 | 38621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 58 | 331759 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23812 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 349 | 4199902 | 822970
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | 114.8% | 1 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | 96.75% | 1 | -965750 | -115989 | 28 | 37 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 107.4% | 1 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 102.2% | 1 | 5194 | 40000 | 34 | 22 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53
| 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 68.9% | 1 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | 108.3% | 1 | -1735624 | 1811802 | 56 | 35 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2915 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 119.3% | 1 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 107% | 1 | 2296 | 34423 | 37 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26
| 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 102.8% | 1 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 106.9% | 1 | 176726 | 494166 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24
| 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 97.14% | 1 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36
| 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 95.28% | 1 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 101.6% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4
| 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 99.33% | 1 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | 99.14% | 1 | -6566 | 0 | 44 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04
| 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 78% | 1 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | 108.2% | 1 | -1354 | 148560 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 9 | 13 | 39 | 2737 | 3370 | 3069 | #VALUE! | 9 | 301 | 24 | 0 | 553 | 80 | 108352586 | 677558 | 107675027 | 110765548 | 111615019 | -250916 | 2385000 | 2134084 | 113749103 | 111113005 | 100% | 9 | -2525078 | 2412962 | 276 | 193 | 0 | 21 | 1083865 | 0 | 68 | 24 | 1362057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 8 | -16020 | 0 | 0 | 0 | 101062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36877 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 2915 | 0 | 84 | 80 | 2571858 | 34423
| District 08 Totals |  |  |  |  | 9 | 13 | 39 | 2737 | 3370 | 3069 | 100% | 9 | 301 | 24 | 0 | 553 | 80 | 108352586 | 677558 | 107675027 | 110765548 | 111615019 | -250916 | 2385000 | 2134084 | 113749103 | 111113005 | 100% | 9 | -2525078 | 2412962 | 276 | 193 | 0 | 21 | 1083865 | 0 | 68 | 24 | 1362057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 8 | -16020 | 0 | 0 | 0 | 101062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36877 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 2915 | 0 | 84 | 80 | 2571858 | 34423
| Statewide Central Let Contracts SubTotal |  |  |  |  | 83 | 169 | 248 | 21682 | 30310 | 29044 | 85.54% | 71 | 1266 | 278 | 0 | 6843 | 1785 | 457707206 | 5895784 | 451811421 | 471276456 | 467057371 | -1009696 | 3564500 | 2554804 | 469612175 | 466538988 | 85.54% | 71 | -2225943 | 13569248 | 4404 | 2087 | 72 | 448 | 5768105 | 16000713 | 97 | 875 | 6273976 | 453720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 30 | 42 | 596445 | 50793 | 17 | 4 | 243550 | 5643 | 0 | 0 | -78086 | 0 | 0 | 53 | 66716 | 0 | 0 | 292 | 1520642 | 27471 | 136 | 67 | 777983 | 640955 | 0 | 0 | 6645 | 0 | 0 | 0 | -920398 | 0 | 352 | 1781 | 14258583 | 17179295
| Statewide District Let Contracts SubTotal |  |  |  |  | 71 | 115 | 229 | 26176 | 35151 | 33763 | 91.55% | 65 | 1388 | 262 | 0 | 6558 | 2417 | 1021924588 | 4750915 | 1017173671 | 1058878944 | 1056357178 | -1611834 | 4455000 | 2843166 | 1059200344 | 1041425435 | 90.14% | 64 | -15822731 | 35421945 | 4178 | 2176 | 88 | 680 | 10753368 | 967715 | 100 | 1066 | 19645276 | 1532051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247500 | 0 | 16 | 473 | 2795686 | 138465 | 0 | 35 | 401718 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | -1146 | 0 | 0 | 119 | 1355406 | 34593 | 0 | 38 | 59616 | 53136 | 0 | 0 | 0 | 0 | 0 | 0 | -683410 | 0 | 204 | 2418 | 34574015 | 2725961
| Statewide Totals |  |  |  |  | 154 | 284 | 477 | 47858 | 65461 | 62807 | 88.31% | 136 | 2654 | 540 | 0 | 13401 | 4202 | 1479631794 | 10646699 | 1468985092 | 1530155400 | 1523414549 | -2621530 | 8019500 | 5397970 | 1528812519 | 1507964423 | 87.66% | 135 | -18048674 | 48991193 | 8582 | 4263 | 160 | 1128 | 16521473 | 16968428 | 197 | 1941 | 25919252 | 1985771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250500 | 0 | 46 | 515 | 3392131 | 189258 | 17 | 39 | 645268 | 5643 | 0 | 0 | -78086 | 0 | 0 | 60 | 65570 | 0 | 0 | 411 | 2876048 | 62064 | 136 | 105 | 837599 | 694091 | 0 | 0 | 6645 | 0 | 0 | 0 | -1603808 | 0 | 556 | 4199 | 48832598 | 19905256

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P94 | 43493915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-18 | 9111251 | 9111251 | 9282956 | 0 | 0 | 9644340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 9289725
1 | E1R26 | 43319415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 604486 | 604486 | 584381 | 0 | 0 | 583598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584381 | 583598 | -783 | 489570
1 | E1R46 | 43806315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-19 | 3730005 | 3730005 | 3622277 | 0 | 0 | 3609915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 4986764
1 | T1636 | 43323815201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 1444112 | 1455710 | 1455710 | 11597.86 | 0 | 1456120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 1303711 | B0 | ACC - LUMP SUM
1 | T1664 | 20103265201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-02-22 | 39141064 | 41032774 | 41293102 | 1891709.53 | 2220000 | 42013585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220000 | 0 | 2220000 | 2220000 | 43513102 | 42013585 | -1499517 | 43211573 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1667 | 43494215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-08-31 | 1182957 | 696968 | 671825 | -485989.48 | 0 | 678334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671825 | 678334 | 6509 | 1125231 | B0 | ACC - LUMP SUM
1 | T1671 | 43560615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-07 | 8453536 | 8694533 | 8807307 | 240997 | 0 | 9108126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8807307 | 9108126 | 300819 | 8498514
1 | T1693 | 43450215201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2535000 | 2909249 | 2922189 | 374249.35 | 0 | 2922984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 2562824 | B1 | ACC - NO EXCUSE BONUS
1 | T1697 | 43534915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2532999 | 2582335 | 2599237 | 49336.16 | 0 | 2598348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 2201661
1 | T1704 | 44011615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 211559 | 211559 | 204310 | 0 | 0 | 204310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204310 | 204310 | 0 | 255658
1 | T1705 | 44013315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 448245 | 448245 | 415980 | 0 | 0 | 415980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415980 | 415980 | 0 | 498435
1 | T1707 | 44013815201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 394057 | 401319 | 389400 | 7262.13 | 0 | 389394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 389394 | -6 | 500275
1 | T1714 | 43837615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 270550 | 270550 | 256893 | 0 | 0 | 256893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256893 | 256893 | 0 | 302948 | B0 | ACC - LUMP SUM
1 | T1729 | 43837415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-08-29 | 985800 | 1045343 | 996037 | 59542.75 | 0 | 995552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996037 | 995552 | -485 | 952403 | B0 | ACC - LUMP SUM
1 | T1732 | 43318515201 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2018-07-25 | 140241 | 140241 | 131642 | 0 | 0 | 131642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1734 | 43498815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 545828 | 545828 | 508665 | 0 | 0 | 508665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508665 | 508665 | 0 | 633612
1 | T1736 | 43320515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 789502 | 789502 | 749000 | 0 | 0 | 749000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749000 | 749000 | 0 | 784219 | B0 | ACC - LUMP SUM
1 | T1737 | 43826915201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 328300 | 328300 | 328300 | 0 | 0 | 328300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328300 | 328300 | 0 | 356575 | B0 | ACC - LUMP SUM
1 | T1738 | 43837115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 870522 | 870522 | 829068 | 0 | 0 | 829068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829068 | 829068 | 0 | 590611
1 | T1741 | 44067415201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 366031 | 366031 | 355572 | 0 | 0 | 355572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355572 | 355572 | 0 | 396011 | B0 | ACC - LUMP SUM
1 | T1749 | 44319925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 335979 | 396256 | 382764 | 60277.25 | 0 | 382764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382764 | 382764 | 0 | 263307
2 | E2P14 | 21330435201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2012-05-30 | 148792000 | 165618383 | 165903515 | 16826382.52 | 0 | 164443807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165903515 | 164443807 | -1459708 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2T34 | 43141825201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-04-15 | 79728458 | 79121474 | 78886236 | -606983.36 | -229932 | 77404693 | -229932 | 0 | 0 | 0 | 0 | 0 | -229932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -229932 | 78656304 | 77404693 | -1251611 | 80350658 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2V71 | 43430015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 4908173 | 4938615 | 5152163 | 30442.09 | 0 | 5451119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 4805500
2 | E2V95 | 43617015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 4081125 | 4737826 | 4860165 | 656701.41 | 0 | 4970230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 3223625
2 | E2W35 | 42849115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 2815327 | 2815327 | 2782011 | 0 | 0 | 2782013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 4173997
2 | E2W51 | 20950355201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1735075 | 1731106 | 1623863 | -3969.01 | 0 | 1623865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | 1877622
2 | E2W53 | 42849715201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1093189 | 1093189 | 1034914 | 0 | 0 | 1034914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 1735598
2 | E2W95 | 43402815201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2018-02-21 | 2722348 | 2722348 | 2657208 | 0 | 0 | 2656276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 2383751
2 | E2X15 | 20961685201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-12-20 | 7739999 | 7739999 | 7665781 | 0 | 0 | 7665781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 9122595
2 | E2X58 | 43205415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-18 | 1561255 | 1561255 | 1495849 | 0 | 0 | 1495849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 1989213
2 | T2562 | 20821175201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-05-20 | 15887487 | 16037487 | 15865517 | 150000 | 0 | 15510573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 16006484
2 | T2577 | 43245215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-17 | 13015506 | 13328963 | 13247968 | 313457.41 | -129472 | 12926851 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 13118496 | 12926851 | -191646 | 11330021
2 | T2612 | 42360825201 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2241677 | 2241677 | 2217516 | 0 | -20592 | 2204364 | -20592 | 0 | 0 | 0 | 0 | 0 | -20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20592 | 2196924 | 2204364 | 7440 | 1830224
2 | T2618 | 43091015201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 6623070 | 7293436 | 7244868 | 670365.84 | 0 | 7349062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7244868 | 7349062 | 104194 | 5699134
2 | T2658 | 41525215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 7921243 | 8003005 | 8095808 | 81762.66 | 0 | 8111040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 5941070
2 | T2661 | 43433715201 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2017-06-14 | 3381935 | 3744790 | 3805039 | 362855.46 | 0 | 3814801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 2832771
2 | T2683 | 43616215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 9121503 | 9130119 | 9355463 | 8616 | 0 | 10160460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 10382551
2 | T2686 | 43611815201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2698000 | 2725471 | 2926429 | 27470.55 | 0 | 3007330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 2798351
2 | T2687 | 43617315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 5141768 | 5141768 | 5033451 | 0 | 0 | 5387836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 6618371
2 | T2688 | 43500115201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2018-01-31 | 1688461 | 1754543 | 1709557 | 66082.5 | 0 | 1709557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 1908915
2 | T2691 | 43617215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 13785287 | 13785287 | 14534510 | 0 | 0 | 15189271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14534510 | 15189271 | 654761 | 13297955
2 | T2695 | 43615815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 3836183 | 3889514 | 3691380 | 53331.63 | 0 | 3729852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691380 | 3729852 | 38471 | 3655365
2 | T2704 | 43761615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | 6663346 | 6750120 | 6920369 | 86773.43 | 0 | 6898990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 6878488
2 | T2718 | 43762115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 2814544 | 2814544 | 2780154 | 0 | 0 | 2750630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 3342179
2 | T2727 | 43761215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1634119 | 1634119 | 1569675 | 0 | 0 | 1576127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 1717974
3 | E3P84 | 43625815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 1596199 | 1596199 | 1566048 | 0 | 0 | 1618568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 1614268
3 | E3Q52 | 43626715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 2737547 | 2741455 | 2788497 | 3908.32 | 0 | 2937051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2788497 | 2937051 | 148555 | 3367306
3 | E3R04 | 43627115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-06-14 | 819508 | 814776 | 800432 | -4732.46 | 0 | 800432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800432 | 800432 | 0 | 795145
3 | E3R73 | 43672615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 3019502 | 3096429 | 3191111 | 76927.34 | -1871 | 3252581 | 0 | 0 | 0 | 0 | 0 | -1871 | -1871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1871 | 3189240 | 3252581 | 63342 | 3561779
3 | E3S64 | 4453671H201 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-04-16 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | -45000 | 32990
3 | T3471 | 41110225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-05-07 | 15000000 | 15157836 | 15093755 | 157836.02 | -129472 | 13510897 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 14814542
3 | T3488 | 40979275201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 3595027 | 3663247 | 3527855 | 68219.39 | -36334 | 3407495 | -25884 | 0 | 0 | 0 | 0 | -10450 | -36334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36334 | 3491521 | 3407495 | -84026 | 2839406
3 | T3584 | 42551925201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-09-27 | 4956085 | 5007841 | 5206085 | 51755.66 | 0 | 5214960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206085 | 5214960 | 8875 | 4588109
3 | T3605 | 43390515201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-09-26 | 2727550 | 2727550 | 2606882 | 0 | 0 | 2599923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 2910808
3 | T3621 | 43626115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 6338519 | 6398946 | 6159928 | 60426.55 | -3625 | 6530080 | 0 | 0 | 0 | 0 | 0 | -3625 | -3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3625 | 6156303 | 6530080 | 373777 | 7711485
3 | T3622 | 43403415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-07-25 | 2343362 | 2350008 | 2309974 | 6645.2 | 0 | 2307395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 1958564
3 | T3633 | 43188335201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-07-25 | 874222 | 874222 | 812103 | 0 | 0 | 809595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 1107452
3 | T3637 | 43626515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 2991030 | 3017543 | 3196659 | 26512.73 | 0 | 3365573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196659 | 3365573 | 168914 | 0
3 | T3639 | 43078915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 5166455 | 5133457 | 5226570 | -32997.52 | 0 | 5560738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5226570 | 5560738 | 334168 | 5944823
3 | T3653 | 43672015201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-08-29 | 628643 | 626435 | 585546 | -2207.95 | 0 | 585546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585546 | 585546 | 0 | 728102
3 | T3655 | 43666315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 7611735 | 8017733 | 8305261 | 405997.54 | 0 | 8626470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8305261 | 8626470 | 321209 | 10033609
3 | T3661 | 43255915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 4168106 | 4195995 | 4262748 | 27889.1 | -3685 | 4316429 | 0 | 0 | 0 | 0 | 0 | -3685 | -3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3685 | 4259063 | 4316429 | 57366 | 3474587
3 | T3662 | 43627215201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 1790850 | 1822098 | 1908732 | 31248.18 | -25175 | 1983720 | 0 | 0 | 0 | 0 | 0 | -25175 | -25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25175 | 1883557 | 1983720 | 100163 | 2014996
3 | T3669 | 43046415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-05-23 | 1257739 | 1467600 | 1481515 | 209861.08 | 0 | 1481051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481515 | 1481051 | -464 | 1150000
3 | T3680 | 43815515201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2018-11-14 | 188489 | 188489 | 183577 | 0 | 0 | 183577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183577 | 183577 | 0 | 165102
3 | T3683 | 43774515201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1061000 | 1061000 | 1008572 | 0 | 0 | 1008572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 1142404 | B0 | ACC - LUMP SUM
4 | E4N84 | 42170735201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-30 | 233756400 | 236000384 | 235981625 | 2243984.17 | 1120000 | 230888919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120000 | 0 | 0 | 0 | 0 | 0 | 1120000 | 1120000 | 237101625 | 230888919 | -6212706 | 224173038 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4N95 | 43316515201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2014-04-28 | 15085307 | 14747115 | 14692678 | -338192.13 | 0 | 14275588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14692678 | 14275588 | -417090 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
4 | E4N98 | 42170745201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-01-17 | 85270000 | 88551488 | 88376026 | 3281487.8 | -266765 | 84860074 | -66765 | 0 | 0 | 0 | 0 | 0 | -66765 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -266765 | 88109261 | 84860074 | -3249187 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q16 | 42170795201 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 5426234 | 5484479 | 5462490 | 58244.76 | 500000 | 5462490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
4 | E4Q35 | 42264135201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-05-06 | 20830000 | 21194238 | 21031285 | 364237.59 | -452157 | 20574388 | -452157 | 0 | 0 | 0 | 0 | 0 | -452157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452157 | 20579128 | 20574388 | -4739 | 20036622 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4S21 | 43661715201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-03-03 | 13456789 | 15316896 | 15094846 | 1860106.93 | 0 | 15262674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 15931024 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4S85 | 43609615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-12-01 | 4027310 | 4061212 | 3932814 | 33902.45 | -146172 | 3959283 | -146172 | 0 | 0 | 0 | 0 | 0 | -146172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -146172 | 3786642 | 3959283 | 172641 | 4151810
4 | E4T01 | 43630215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1711929 | 1760237 | 1659334 | 48308 | 0 | 1661623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 1640419
4 | E4T06 | 43977615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1095456 | 1095456 | 1057178 | 0 | 0 | 1059897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 1077515
4 | E4T43 | 43686915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-02-01 | 483248 | 483248 | 462927 | 0 | 0 | 462927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462927 | 462927 | 0 | 584334
4 | E4T47 | 43995915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 874745 | 874745 | 827255 | 0 | 0 | 827255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827255 | 827255 | 0 | 2440132
4 | E4T48 | 43215315201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 1579388 | 1579388 | 1522923 | 0 | 0 | 1522923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 1500208
4 | E4T53 | 44145715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-02-01 | 373586 | 373586 | 320740 | 0 | 0 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320740 | 320740 | 0 | 838047
4 | T4423 | 23033845201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 23950804 | 24148938 | 23087444 | 198133.26 | 0 | 23548540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23087444 | 23548540 | 461096 | 30953648
4 | T4454 | 43427315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 17184517 | 17260367 | 15228075 | 75850.52 | -427518 | 15656209 | -427518 | 0 | 0 | 0 | 0 | 0 | -427518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -427518 | 14800557 | 15656209 | 855652 | 16678233 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4465 | 42793815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 6772377 | 6937715 | 6616077 | 165337.71 | 0 | 6805105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616077 | 6805105 | 189028 | 7354282
4 | T4467 | 42872815201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 6194382 | 6727999 | 7014661 | 533617.21 | 0 | 7145526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7014661 | 7145526 | 130865 | 6773142 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4470 | 43467915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2654817 | 2648641 | 2595600 | -6176.03 | 0 | 2595444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | 2954451
4 | T4474 | 43516015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4025071 | 4333347 | 4067792 | 308276.21 | 0 | 4150827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 3559044
4 | T4478 | 43206645201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 3159876 | 3207501 | 3126761 | 47624.42 | 0 | 3121903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 3633553
4 | T4492 | 43783715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 1180804 | 1180804 | 1088706 | 0 | 0 | 1092749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 1254760
4 | T4493 | 43622615201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 913324 | 925193 | 862461 | 11868.69 | 0 | 863741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 983072
5 | E5W31 | 43360715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-08-04 | 11820000 | 11432846 | 11217159 | -387153.56 | -379168 | 10757297 | -379168 | 0 | 0 | 0 | 0 | 0 | -379168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -379168 | 10837991 | 10757297 | -80694 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y33 | 43693715201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2016-09-07 | 1750000 | 3113962 | 3063962 | 1363961.88 | 0 | 3065413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1325842
5 | E5Y34 | 43744415201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | 793972 | 793962 | 623055 | -9.51 | 0 | 624995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623055 | 624995 | 1940 | 843684
5 | E5Z02 | 43365415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-02-06 | 1457258 | 1507258 | 1490649 | 50000 | -1099 | 1488755 | 0 | 0 | 0 | 0 | 0 | -1099 | -1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1099 | 1489550 | 1488755 | -795 | 1508169
5 | E5Z21 | 43927015201 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 3175000 | 3175000 | 3125000 | 0 | 0 | 3125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 2594655
5 | E5Z25 | 43685515201 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-07-03 | 1405000 | 1538799 | 1482098 | 133798.84 | 0 | 1478901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 1340492
5 | E5Z44 | 43945315201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-06 | 406627 | 439983 | 417356 | 33356.49 | -11169 | 406187 | -11169 | 0 | 0 | 0 | 0 | 0 | -11169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11169 | 406187 | 406187 | 0 | 480184
5 | E5Z47 | 43759915201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2018-12-04 | 490000 | 490000 | 469000 | 0 | 0 | 469000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469000 | 469000 | 0 | 441431
5 | E5Z48 | 44096715201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 476422 | 476422 | 521373 | 0 | 0 | 521373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521373 | 521373 | 0 | 443061
5 | E5Z49 | 44255515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-12-04 | 1193299 | 1193299 | 1111517 | 0 | 0 | 1111517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 1054473
5 | E5Z52 | 44116715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-10-02 | 679222 | 682222 | 665592 | 3000 | 0 | 665592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665592 | 665592 | 0 | 321983
5 | E5Z60 | 44096815201 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 471366 | 471366 | 417692 | 0 | 0 | 417692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417692 | 417692 | 0 | 554880
5 | T5469 | 23920345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-10-30 | 67881735 | 71458538 | 71806238 | 3576803.2 | -56415 | 68693588 | 0 | 0 | 0 | 0 | 0 | -56415 | -56415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56415 | 71749823 | 68693588 | -3056235 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5572 | 43505615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 6749945 | 6768976 | 6749146 | 19031.04 | 30000 | 6749146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
5 | T5588 | 43505915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 5555556 | 5555556 | 5533602 | 0 | 14500 | 5533602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0 | 0 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 7289680
5 | T5601 | 43565815201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4858677 | 5019991 | 4911820 | 161313.66 | 0 | 5177234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 6733492
5 | T5617 | 43505815201 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 3824000 | 3850406 | 3817535 | 26405.77 | 0 | 3817535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 4905410
5 | T5619 | 24099275201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-08-30 | 1769311 | 1789505 | 1708324 | 20194.25 | 0 | 1715061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 1940871
5 | T5623 | 43239915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-07-25 | 1897288 | 1897714 | 1910437 | 426.04 | 0 | 1905492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 2057026
6 | E6J52 | 43337815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-06-09 | 8960958 | 9028019 | 8935693 | 67061.69 | 0 | 8936706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8935693 | 8936706 | 1013 | 6643198
6 | E6J69 | 43492215201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2016-04-15 | 69547000 | 72886197 | 72551371 | 1806784.32 | 0 | 73200931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72551371 | 73200931 | 649560 | 125147000 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K59 | 41831225201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-07-28 | 9488820 | 10556288 | 10367176 | 1067467.64 | 400000 | 10409054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 10767176 | 10409054 | -358123 | 9121391 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K87 | 43654015201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2018-11-29 | 342215 | 342215 | 303600 | 0 | 0 | 303600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303600 | 303600 | 0 | 394432
6 | E6K89 | 43653615201 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 512803 | 536803 | 517303 | 24000 | 0 | 517303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517303 | 517303 | 0 | 404500
6 | E6L26 | 43653515201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-29 | 878038 | 878038 | 768146 | 0 | 0 | 768146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768146 | 768146 | 0 | 1044218
6 | E6L27 | 43081725201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 1584337 | 1584337 | 1427013 | 0 | 0 | 1426855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 1676992
6 | E6L83 | 44124315201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-26 | 626626 | 626626 | 577033 | 0 | 0 | 576947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577033 | 576947 | -87 | 611516
6 | E6L91 | 44203915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 1590779 | 1590779 | 1534205 | 0 | 0 | 1533853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 1335462
6 | T6344 | 24994145201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2014-06-25 | 20865766 | 21591091 | 20515283 | 725324.32 | 0 | 20078878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 22059625 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6382 | 40561535201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 32827940 | 33204392 | 33258885 | 376451.27 | 1000000 | 33636224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 34258885 | 33636224 | -622662 | 32661597 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6401 | 41247395201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-03-29 | 3499047 | 5529305 | 5890497 | 2030258.17 | 0 | 5896369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890497 | 5896369 | 5872 | 3269401 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6403 | 43348915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 2123570 | 2145473 | 2165968 | 21903 | 0 | 2187405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 2459954
6 | T6406 | 42902215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-04-25 | 3211923 | 3249863 | 3270531 | 37940 | 190000 | 3268888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 3370172 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6419 | 42827825201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 2865340 | 2945587 | 2727466 | 80246.87 | 110000 | 2776404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 2918720 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6436 | 43631115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1387410 | 1479864 | 1353258 | 92453.79 | 0 | 1354735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 1750082
6 | T6437 | 43634215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 1789134 | 1789134 | 1742305 | 0 | 0 | 1738184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 2085360
6 | T6448 | 43792015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-07-25 | 796960 | 796960 | 710116 | 0 | 0 | 708837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 867454
6 | T6451 | 42563725201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-31 | 666806 | 666806 | 585572 | 0 | 0 | 584459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 654200
6 | T6467 | 44289715201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-10-31 | 127677 | 127677 | 111887 | 0 | 0 | 111863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111887 | 111863 | -24 | 324690
7 | E7H90 | 25693125201 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2012-11-01 | 82889000 | 85277357 | 85130335 | 2388356.86 | 0 | 83668918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85130335 | 83668918 | -1461417 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7L26 | 40552525201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-08 | 25833397 | 27246296 | 27221715 | 1412898.86 | 250000 | 27205803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 27471715 | 27205803 | -265912 | 23085355 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7L58 | 43243415201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-10 | 5500000 | 5732401 | 5687839 | 232401.07 | 0 | 5688140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 4546054
7 | E7L77 | 42292935201 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2017-09-19 | 5595578 | 5595578 | 5582332 | 0 | -3645 | 5581090 | -3645 | 0 | 0 | 0 | 0 | 0 | -3645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3645 | 5578687 | 5581090 | 2402 | 3505311
7 | E7L98 | 43763715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 2248889 | 2248889 | 2169580 | 0 | 0 | 2169580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 2125000
7 | E7M00 | 42292945201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-05-09 | 3873725 | 4070777 | 4079959 | 197052.15 | 0 | 4074029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 5390437
7 | E7M06 | 44033815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 5327001 | 5327001 | 5287802 | 0 | -68940 | 5204437 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5218862 | 5204437 | -14425 | 6993269
7 | E7M30 | 43755215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-13 | 167797 | 167797 | 136656 | 0 | 0 | 136656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136656 | 136656 | 0 | 175000
7 | E7R06 | 44008915201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-08-22 | 1947000 | 1947000 | 1708144 | 0 | 0 | 1708144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7391 | 43269815201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 1680691 | 1699042 | 1672177 | 18351.56 | -177408 | 1505964 | -177408 | 0 | 0 | 0 | 0 | 0 | -177408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -177408 | 1494769 | 1505964 | 11195 | 1603400
7 | T7398 | 43473015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-25 | 2979236 | 2979236 | 2852469 | 0 | 0 | 2921837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 3840000
7 | T7401 | 43480615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-03-28 | 2932563 | 2939291 | 2859109 | 6728.39 | 0 | 2924621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 3343300
7 | T7404 | 43642015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1081175 | 1081175 | 1016734 | 0 | 0 | 1023706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 1150000 | B0 | ACC - LUMP SUM
7 | T7409 | 43649115202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-23 | 1575996 | 1575996 | 1509644 | 0 | 0 | 1509644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 1415000
7 | T7415 | 43982935201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 497590 | 497590 | 430440 | 0 | 0 | 430440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430440 | 430440 | 0 | 590001
7 | T7422 | 44275215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 96675 | 96675 | 89884 | 0 | 0 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89884 | 89884 | 0 | 182731
8 | E8N19 | 42935015201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-05-14 | 42645454 | 42529465 | 42335775 | -115989.17 | -256416 | 41113609 | -188916 | 0 | 0 | 0 | 0 | -22500 | -211416 | -45000 | 0 | 0 | 0 | 0 | 0 | -45000 | -256416 | 42079359 | 41113609 | -965750 | 44879640 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8P81 | 43561415201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-05-10 | 2564262 | 2604262 | 2577346 | 40000 | 0 | 2582540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 2264808
8 | E8Q39 | 43730015201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-04-11 | 42528000 | 44339802 | 45313329 | 1811801.94 | 2430000 | 46007705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430000 | 0 | 0 | 0 | 0 | 0 | 2430000 | 2430000 | 47743329 | 46007705 | -1735624 | 52100636 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8Q91 | 43915315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 1568431 | 1602854 | 1622457 | 34422.76 | 0 | 1624753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 1431341
8 | E8R18 | 43652115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-05-31 | 11208613 | 11702780 | 11690102 | 494166.31 | -20000 | 11846829 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 11670102 | 11846829 | 176726 | 12719348
8 | E8R56 | 44290165201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-16 | 994137 | 994137 | 967509 | 0 | 0 | 967509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967509 | 967509 | 0 | 805668
8 | E8R57 | 44290175201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 679823 | 679823 | 674133 | 0 | -9500 | 664633 | 0 | 0 | 0 | 0 | 0 | -9500 | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9500 | 664633 | 664633 | 0 | 820726
8 | E8R59 | 44290185201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1646521 | 1646521 | 1599372 | 0 | -10000 | 1582806 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 1589372 | 1582806 | -6566 | 1947436
8 | E8R64 | 44263115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4517345 | 4665904 | 4834996 | 148559.58 | 0 | 4833642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 1860603

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 11598 | 6 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 18 | 01co | 1 | 18
01CO | 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | -1499517 | 1891710 | 39 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | -250656 | 0 |  | CO | 3 | 01do | 19 | 21
01CO | 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 6509 | -485989 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 15 | 02co | 22 | 36
01CO | 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 300819 | 240997 | 138 | 0 | 7 | 201334 | 0 | 0 | 0 | 15623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 229783 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73 |  |  | 2 | 47 | 0 | 0 | 0 | 0 |  | CO | 11 | 02do | 37 | 47
01CO | 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 374249 | 101 | 0 | 33 | 244703 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 274622 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 16 | 03co | 48 | 63
01CO | 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 49336 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 5 | 03do | 64 | 68
01CO | 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 9 | 04co | 69 | 77
01CO | 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 13 | 04do | 78 | 90
01CO | 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | -6 | 7262 | 17 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93 |  |  | 20 | 5 | 0 | 0 | 0 | 0 |  | CO | 7 | 05co | 91 | 97
01CO | 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 | T | CO | 12 | 05do | 98 | 109
01CO | 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | -485 | 59543 | 17 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 11 | 06co | 110 | 120
01CO | 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 9 | 06do | 121 | 129
01CO | 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 7 | 07co | 130 | 136
01CO | 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 9 | 07do | 137 | 145
01CO | 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 146 | 145
01CO | 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 9 | 08do | 146 | 154
01CO | 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 0 | 0 | 11 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 0 | 60277 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 0 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | -783 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 150000 | 87 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74 |  |  | 44 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | -191646 | 313457 | 83 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88 |  |  | 37 | 110 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 7440 | 0 | 43 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45 |  |  | 25 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 45271 | 670366 | 127 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54 |  |  | 33 | 43 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 81763 | 65 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67 |  |  | 50 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 362855 | 62 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92 |  |  | 55 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 8616 | 80 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07 |  |  | 25 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 27471 | 62 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 0 | 54 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 66083 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14534510 | 0 | 0 | 0 | 14534510 | 15189271 | 654761 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3729852 | 38471 | 53332 | 27 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59 |  |  | 22 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 86773 | 31 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39 |  |  | 10 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 0 | 5 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | -1459708 | 16826383 | 385 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 223 | 0 | 0 | -18219 | 0 |  | DO
02DO | 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | -1251611 | -606983 | 51 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 30442 | 44 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25 |  |  | 7 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 656701 | 89 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79 |  |  | 27 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 0 | 67 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | -3969 | 52 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46 |  |  | 0 | 37 | 0 | 0 | -60481 | 0 |  | DO
02DO | 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 0 | 26 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 157836 | 188 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | -84026 | 68219 | 39 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 8875 | 51756 | 76 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 0 | 66 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 373777 | 60427 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 6645 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9 |  |  | 3 | 41 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 168914 | 26513 | 52 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 | 2019-01-11 | QTR3 | 18/19 | 308 | 0 |  |  | 5 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 334168 | -32998 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 0 | -2208 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 321209 | 405998 | 157 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62 |  |  | 13 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 57366 | 27889 | 69 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76 |  |  | 7 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 100163 | 31248 | 167 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | -464 | 209861 | 112 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 0 | 13 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95 |  |  | 1 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 148555 | 3908 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 0 | -4732 | 101 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-05-13 | QTR4 | 18/19 | 308 | 795145 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 63342 | 76927 | 41 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 442812 | 198133 | 145 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16 |  |  | 8 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 855652 | 75851 | 215 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 189028 | 165338 | 66 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18 |  |  | 30 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7145526 | 130865 | 533617 | 55 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | -6176 | 89 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55 |  |  | 28 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 308276 | 109 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 47624 | 74 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 0 | 6 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 11869 | 31 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95 |  |  | 6 | 8 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | -6213797 | 2243984 | 183 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 45 | 0 | 0 | -404828 | 0 |  | DO
04DO | 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | -417090 | -338192 | 219 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 89 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | -3249187 | 3281488 | 165 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 64 | 0 | 0 | -202797 | 0 |  | DO
04DO | 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 58245 | 22 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 76 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | -4739 | 364238 | 220 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR | 6 | 71 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 1860107 | 73 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 172641 | 33902 | 24 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 48308 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 0 | 0 | 1 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | -3056235 | 3576803 | 117 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 3 | 48 | 0 | 0 | -155690 | 0 |  | CO
05CO | 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 19031 | 14 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 161314 | 43 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 26406 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 20194 | 36 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871 |  |  | 17 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 426 | 29 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10738882 | -80694 | -387154 | 69 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1363962 | 39 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842 |  |  | 60 | 51 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 1940 | -10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 | 2017-05-14 | QTR4 | 16/17 | 509 | 843684 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | -795 | 50000 | 60 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 133799 | 15 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25 |  |  | 1 | 33 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 0 | 33356 | 25 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-07-22 | QTR1 | 19/20 | 513 | 480184 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 | 2019-07-18 | QTR1 | 19/20 | 509 | 441431 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 0 | 0 | 22 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5 |  |  | 11 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2 |  |  | 18 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 0 | 3000 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 513 | 554880 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 725324 | 52 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | -622662 | 376451 | 74 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 40 | 0 | 0 | -514052 | 0 |  | CO
06CO | 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 5872 | 2030258 | 59 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 21903 | 44 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 37940 | 56 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 80247 | 31 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 92454 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 0 | 48 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | -24 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 606 | 324690 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 1013 | 67062 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 649560 | 1806784 | 96 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | -358123 | 1067468 | 84 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 0 | 24000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 | 2019-10-04 | QTR2 | 19/20 | 606 | 404500 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 0 | 23 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | -87 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 11195 | 18352 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400 |  |  | 10 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 0 | 68 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 6728 | 41 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM | 12 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | -1461417 | 2388357 | 330 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR | 76 | 85 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | -265912 | 1412899 | 124 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 56 | 53 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 232401 | 76 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 2402 | 0 | 242 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000 |  |  | 7 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 197052 | 173 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | -14425 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 798 | 175000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | -965750 | -115989 | 28 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 40000 | 34 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53 |  |  | 10 | 22 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | -1735624 | 1811802 | 56 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | 2915 | 0 |  | DO
08DO | 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 34423 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 176726 | 494166 | 44 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24 |  |  | 14 | 52 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | -6566 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 148560 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0