## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 81466406 | 80643404 | 83543315 | 83003532 | 2790000 | 83828953 | 3.95% | 91.3% | 2242936 | 2.781% | 2076909 | 2.549% | 4548 | 747 | 16.42% | 291 | 6.398% | 29 | 0.6376% | 180 | 3.958% | 4757 | 4.595% | 5799 | 5112 | 4074 | -10.42% | 100%
| District Let | 86011830 | 85323526 | 88275347 | 87093370 | 2565000 | 88618765 | 3.862% | 100% | 2337755 | 2.74% | 2263517 | 2.632% | 2955 | 380 | 12.86% | 193 | 6.531% | 41 | 1.387% | 354 | 11.98% | 3350 | 13.37% | 3923 | 3524 | 2951 | -0.1354% | 90.91%
| All Contracts | 167478236 | 165966930 | 171818662 | 170096902 | 5355000 | 172447718 | 3.905% | 94.12% | 4580691 | 2.76% | 4340426 | 2.592% | 7503 | 1127 | 15.02% | 484 | 6.451% | 70 | 0.933% | 534 | 7.117% | 8107 | 8.05% | 9722 | 8636 | 7025 | -6.371% | 97.06%
2 | Central Let | 134461236 | 132940484 | 137784208 | 139120990 | 0 | 140559709 | 5.731% | 72.73% | 3533373 | 2.658% | 3322974 | 2.471% | 5904 | 1122 | 19% | 707 | 11.97% | 97 | 1.643% | 1129 | 19.12% | 7130 | 20.77% | 8965 | 8801 | 6972 | 18.09% | 68.18%
| District Let | 358069946 | 356676055 | 376456987 | 375473662 | 0 | 366514131 | 2.758% | 75% | 18495824 | 5.186% | 18387041 | 5.135% | 7662 | 1017 | 13.27% | 829 | 10.82% | 232 | 3.028% | 1327 | 17.32% | 9221 | 20.35% | 11067 | 11631 | 9785 | 27.71% | 70%
| All Contracts | 492531182 | 489616539 | 514241195 | 514594652 | 0 | 507073840 | 3.566% | 73.81% | 22029197 | 4.499% | 21710015 | 4.408% | 13566 | 2139 | 15.77% | 1536 | 11.32% | 329 | 2.425% | 2456 | 18.1% | 16351 | 20.53% | 20032 | 20432 | 16757 | 23.52% | 69.05%
3 | Central Let | 111267758 | 110061177 | 118699154 | 119993387 | 0 | 119378768 | 8.466% | 78.26% | 7519106 | 6.832% | 7431394 | 6.679% | 5039 | 1784 | 35.4% | 629 | 12.48% | 210 | 4.167% | 286 | 5.676% | 5535 | 9.843% | 7948 | 7920 | 5507 | 9.288% | 78.26%
| District Let | 11547141 | 11214103 | 11628979 | 11466653 | 0 | 11671565 | 4.079% | 100% | 78377 | 0.6989% | 81838 | 0.7087% | 1250 | 342 | 27.36% | 175 | 14% | 80 | 6.4% | 2 | 0.16% | 1332 | 6.56% | 1849 | 1817 | 1300 | 4% | 88.89%
| All Contracts | 122814899 | 121275280 | 130328133 | 131460040 | 0 | 131050333 | 8.06% | 84.38% | 7597483 | 6.265% | 7513232 | 6.118% | 6289 | 2126 | 33.81% | 804 | 12.78% | 290 | 4.611% | 288 | 4.579% | 6867 | 9.191% | 9797 | 9737 | 6807 | 8.237% | 81.25%
4 | Central Let | 135678236 | 134458625 | 139467923 | 133749649 | -64000 | 135387720 | 0.691% | 93.33% | 3672397 | 2.731% | 3789687 | 2.793% | 6866 | 1426 | 20.77% | 511 | 7.442% | 0 | 0% | 389 | 5.666% | 7255 | 5.666% | 9188 | 8982 | 7045 | 2.607% | 93.33%
| District Let | 570427971 | 568986089 | 587816437 | 586928695 | 5140000 | 576175531 | 1.264% | 93.33% | 16512307 | 2.902% | 17388466 | 3.048% | 10859 | 1255 | 11.56% | 591 | 5.442% | 2 | 0.01842% | 742 | 6.833% | 11603 | 6.851% | 13448 | 12880 | 11034 | 1.612% | 86.67%
| All Contracts | 706106207 | 703444714 | 727284360 | 720678344 | 5076000 | 711563251 | 1.154% | 93.33% | 20184704 | 2.869% | 21178153 | 2.999% | 17725 | 2681 | 15.13% | 1102 | 6.217% | 2 | 0.01128% | 1131 | 6.381% | 18858 | 6.392% | 22636 | 21862 | 18079 | 1.997% | 90%
5 | Central Let | 114182351 | 113423351 | 118263085 | 117896642 | 44500 | 115399242 | 1.742% | 100% | 4360798 | 3.845% | 4080734 | 3.574% | 4520 | 387 | 8.562% | 441 | 9.757% | 0 | 0% | 131 | 2.898% | 4651 | 2.898% | 5479 | 4953 | 4125 | -8.739% | 100%
| District Let | 107101329 | 106062390 | 112014596 | 111259119 | 0 | 107945348 | 1.775% | 88.89% | 5079484 | 4.789% | 4913268 | 4.587% | 5146 | 889 | 17.28% | 509 | 9.891% | 11 | 0.2138% | 655 | 12.73% | 5812 | 12.94% | 7210 | 7095 | 5697 | 10.71% | 88.89%
| All Contracts | 221283680 | 219485741 | 230277681 | 229155761 | 44500 | 223344590 | 1.758% | 92.86% | 9440282 | 4.301% | 8994002 | 4.064% | 9666 | 1276 | 13.2% | 950 | 9.828% | 11 | 0.1138% | 786 | 8.132% | 10463 | 8.245% | 12689 | 12048 | 9822 | 1.614% | 92.86%
6 | Central Let | 99861827 | 97322827 | 107399002 | 106810570 | 2050000 | 106693114 | 9.628% | 80% | 8069565 | 8.292% | 7537173 | 7.548% | 5252 | 875 | 16.66% | 336 | 6.398% | 391 | 7.445% | 536 | 10.21% | 6179 | 17.65% | 7390 | 6989 | 5778 | 10.02% | 80%
| District Let | 96123506 | 95489467 | 100764065 | 99585824 | 560000 | 99741423 | 4.453% | 100% | 2672150 | 2.798% | 3108147 | 3.233% | 3430 | 475 | 13.85% | 172 | 5.015% | 0 | 0% | 28 | 0.8163% | 3458 | 0.8163% | 4105 | 3902 | 3255 | -5.102% | 100%
| All Contracts | 195985333 | 192812294 | 208163067 | 206396394 | 2610000 | 206434537 | 7.065% | 88.46% | 10741715 | 5.571% | 10645320 | 5.432% | 8682 | 1350 | 15.55% | 508 | 5.851% | 391 | 4.504% | 564 | 6.496% | 9637 | 11% | 11495 | 10891 | 9033 | 4.043% | 88.46%
7 | Central Let | 27982195 | 27418415 | 28907434 | 28480006 | 0 | 28477451 | 3.862% | 100% | 856444 | 3.124% | 925240 | 3.307% | 1743 | 435 | 24.96% | 180 | 10.33% | 23 | 1.32% | 92 | 5.278% | 1858 | 6.598% | 2473 | 2516 | 1901 | 9.065% | 90.91%
| District Let | 281614476 | 280468176 | 312569395 | 310864313 | 280000 | 308289115 | 9.919% | 93.75% | 30397410 | 10.84% | 30954919 | 10.99% | 6551 | 1527 | 23.31% | 607 | 9.266% | 2 | 0.03053% | 787 | 12.01% | 7340 | 12.04% | 9474 | 9424 | 7290 | 11.28% | 93.75%
| All Contracts | 309596671 | 307886591 | 341476829 | 339344319 | 280000 | 336766566 | 9.38% | 96.3% | 31253854 | 10.15% | 31880159 | 10.3% | 8294 | 1962 | 23.66% | 787 | 9.489% | 25 | 0.3014% | 879 | 10.6% | 9198 | 10.9% | 11947 | 11940 | 9191 | 10.82% | 92.59%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 141708875 | 140786166 | 145071462 | 144823490 | 2385000 | 145706523 | 3.495% | 100% | 3300268 | 2.344% | 3362586 | 2.373% | 3457 | 506 | 14.64% | 372 | 10.76% | 84 | 2.43% | 202 | 5.843% | 3743 | 8.273% | 4623 | 4394 | 3516 | 1.707% | #VALUE!
| All Contracts | 141708875 | 140786166 | 145071462 | 144823490 | 2385000 | 145706523 | 3.495% | 100% | 3300268 | 2.344% | 3362586 | 2.373% | 3457 | 506 | 14.64% | 372 | 10.76% | 84 | 2.43% | 202 | 5.843% | 3743 | 8.273% | 4623 | 4394 | 3516 | 1.707% | 91.67%
Totals This Qtr | Central Let | 704900009 | 696268283 | 734064121 | 729054776 | 4820500 | 729724957 | 4.805% | 85.71% | 30254619 | 4.345% | 29164111 | 4.137% | 33872 | 6776 | 20% | 3095 | 9.137% | 750 | 2.214% | 2743 | 8.098% | 37365 | 10.31% | 47242 | 45273 | 35402 | 4.517% | 85.71%
| District Let | 1652605074 | 1645005972 | 1734597268 | 1727495126 | 10930000 | 1704662401 | 3.627% | 91.96% | 78873575 | 4.795% | 80459782 | 4.869% | 41310 | 6391 | 15.47% | 3448 | 8.347% | 452 | 1.094% | 4097 | 9.918% | 45859 | 11.01% | 55699 | 54667 | 44828 | 8.516% | 87.5%
| All Contracts | 2357505083 | 2341274255 | 2468661389 | 2456549902 | 15750500 | 2434387358 | 3.977% | 88.74% | 109128194 | 4.661% | 109623893 | 4.65% | 75182 | 13167 | 17.51% | 6543 | 8.703% | 1202 | 1.599% | 6840 | 9.098% | 83224 | 10.7% | 102941 | 99940 | 80230 | 6.714% | 86.58%
Totals Previous Quarter | Central Let | 457707206 | 451811421 | 471276456 | 467057371 | 3564500 | 466538988 | 3.26% | 85.54% | 14258583 | 3.156% | 13569248 | 2.965% | 21682 | 4404 | 20.31% | 2087 | 9.625% | 352 | 1.623% | 1781 | 8.214% | 23815 | 9.838% | 30310 | 29044 | 22553 | 4.017% | 85.54%
| District Let | 1021924588 | 1017173671 | 1058878944 | 1056357178 | 4455000 | 1041425435 | 2.384% | 90.14% | 34574015 | 3.399% | 35421945 | 3.466% | 26176 | 4178 | 15.96% | 2176 | 8.313% | 204 | 0.7793% | 2418 | 9.237% | 28798 | 10.02% | 35151 | 33763 | 27409 | 4.71% | 91.55%
| All Contracts | 1479631794 | 1468985092 | 1530155400 | 1523414549 | 8019500 | 1507964423 | 2.653% | 87.66% | 48832598 | 3.324% | 48991193 | 3.311% | 47858 | 8582 | 17.93% | 4263 | 8.908% | 556 | 1.162% | 4199 | 8.774% | 52613 | 9.936% | 65461 | 62807 | 49962 | 4.396% | 88.31%
Totals Fiscal Year 2018/2019 | Central Let | 1245791056 | 1233826432 | 1290308424 | 1290743418 | 11354325 | 1272211402.08 | 3.111% | 92.68% | 44743423 | 3.626% | 44444005 | 3.568% | 51070 | 10333 | 20.23% | 4417 | 8.649% | 1987 | 3.891% | 2974 | 5.823% | 56031 | 9.714% | 71119 | 69464 | 54714 | 7.135% | 84.15%
| District Let | 1083536931 | 1076274846 | 1166469706 | 1158597181 | 1605000 | 1125497490 | 4.573% | 91.97% | 82452189 | 7.661% | 82932771 | 7.654% | 39155 | 6879 | 17.57% | 3581 | 9.146% | 1190 | 3.039% | 3778 | 9.649% | 44123 | 12.69% | 54718 | 53095 | 42635 | 8.888% | 89.78%
| All Contracts | 2329327987 | 2310101278 | 2456778130 | 2449340599 | 12959325 | 2397708892.08 | 3.792% | 92.36% | 127195612 | 5.506% | 127376776 | 5.468% | 90225 | 17212 | 19.08% | 7998 | 8.865% | 3177 | 3.521% | 6752 | 7.484% | 100154 | 11% | 125837 | 122559 | 97349 | 7.896% | 86.71%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 100.8% | 1 | 410 | 11598 | 6 | 16 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM
| 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 87.63% | 1 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | 107.6% | 1 | -1499517 | 1891710 | 39 | 35 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 50.62% | 1 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 57.34% | 1 | 6509 | -485989 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 |  | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM
| 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 101.8% | 1 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 108.5% | 1 | 300819 | 240997 | 138 | 47 | 0 | 7 | 224121 | 0 | 0 | 0 | 24860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 261807 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73
| 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 113.2% | 1 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 115.3% | 0 | 795 | 374249 | 101 | 25 | 0 | 33 | 344330 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 374249 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS
| 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 91.5% | 1 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | 104.6% | 1 | -889 | 49336 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 |  | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61
| 01 | T1701 | 43498615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 3 | 580 | 635 | 485 | 74.14% | 1 | 150 | 0 | 0 | 55 | 0 | 8087167 | 75299 | 8011868 | 8023343 | 7632042 | 0 | 570000 | 570000 | 8202042 | 7675787 | 95.81% | 1 | -516267 | -63824 | 40 | 15 | 0 | 0 | 37019 | 0 | 0 | 0 | -73677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29433 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 118 | 8094281.54 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 101.2% | 1 | 0 | 0 | 49 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66
| 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 99.09% | 1 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 98.36% | 1 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82
| 01 | T1706 | 43658615201 | 2018-06-13 | QTR4 | 17/18 | 2 | 1 | 325 | 397 | 374 | 92.92% | 1 | 23 | 0 | 0 | 72 | 0 | 7786066 | 101721 | 7684345 | 7543630 | 7286083 | 0 | 0 | 0 | 7286083 | 7247442 | 94.31% | 1 | -38640 | -242436 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -242436 | 0 | 0 | 0 | -242436 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2019-11-04 | QTR2 | 19/20 | 108 | 9348245.16
| 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 73.6% | 1 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | 105.9% | 1 | -6 | 7262 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93
| 01 | T1713 | 43355215201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 230 | 408 | 407 | 111.7% | 1 | 1 | 0 | 0 | 178 | 0 | 2526300 | 50000 | 2476300 | 2681334 | 2687161 | 0 | 0 | 0 | 2687161 | 2585403 | 104.4% | 1 | -101758 | 155034 | 128 | 22 | 28 | 0 | 74449 | 0 | 0 | 0 | 130585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 205034 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-10-30 | QTR2 | 19/20 | 115 | 2797558.23 | B0 | ACC - LUMP SUM
| 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 100.7% | 1 | 0 | 0 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM
| 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | 106.4% | 1 | -485 | 59543 | 17 | 5 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM
| 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 86.36% | 1 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 93.87% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM
| 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 86.15% | 1 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 99.42% | 1 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36
| 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 100% | 1 | 0 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM
| 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 69% | 1 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 100% | 1 | 0 | 0 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM
| 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 98.34% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52
| 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 101% | 1 | 0 | 0 | 11 | 5 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM
| 01 | T1743 | 43800415201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 71 | 107 | 99 | 88.73% | 1 | 8 | 0 | 0 | 36 | 0 | 138436 | 0 | 138436 | 138436 | 138436 | 0 | 0 | 0 | 138436 | 138436 | 100% | 1 | 0 | 0 | 30 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 108 | 179132.62 | B0 | ACC - LUMP SUM
| 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 115.9% | 0 | 0 | 60277 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07
| 01 | T1753 | 43943215201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 200 | 218 | 136 | 59% | 1 | 82 | 0 | 0 | 18 | 0 | 1952155 | 50000 | 1902155 | 1971307 | 1962809 | 0 | 0 | 0 | 1962809 | 1962123 | 103.2% | 1 | -686 | 19152 | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2020-02-24 | QTR3 | 19/20 | 108 | 2489141.93 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 23 | 41 | 54 | 4548 | 5799 | 5112 | 100% | 23 | 687 | 0 | 0 | 1067 | 184 | 81466406 | 823002 | 80643404 | 83543315 | 83003532 | 0 | 2790000 | 2790000 | 85793532 | 83828953 | 91.3% | 21 | -1849715 | 2076909 | 747 | 291 | 28 | 40 | 1490238 | 0 | 0 | 140 | 1695456 | 6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -476964 | 0 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -493092 | 0 | 29 | 180 | 2242936 | 6308
| 01 | E1P56 | 41968815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 150 | 180 | 180 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1109997 | 50000 | 1059997 | 1109997 | 793278 | 0 | 0 | 0 | 793278 | 793278 | 74.84% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2017-10-27 | QTR2 | 17/18 | 115 | 2383057.05
| 01 | E1P91 | 42271055201 | 2017-04-20 | QTR4 | 16/17 | 1 | 7 | 560 | 729 | 725 | 101.1% | 1 | 4 | 0 | 0 | 169 | 0 | 10071503 | 104026 | 9967477 | 10247666 | 9983254 | 0 | 0 | 0 | 9983254 | 10164043 | 102% | 1 | 198791 | 176163 | 120 | 39 | 5 | 0 | 55015 | 0 | 5 | 0 | 112805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 179808 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 115 | 11091792.08 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 103.5% | 1 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 107% | 1 | 361384 | 0 | 43 | 24 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34
| 01 | E1Q23 | 43665015201 | 2018-02-13 | QTR3 | 17/18 | 1 | 0 | 340 | 462 | 525 | 127.9% | 0 | -63 | 63 | 0 | 90 | 32 | 918123 | 50000 | 868123 | 918123 | 868123 | -104895 | 0 | -104895 | 763228 | 763228 | 87.92% | 1 | 0 | 0 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 108 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 01 | E1Q29 | 42584115201 | 2017-04-20 | QTR4 | 16/17 | 2 | 15 | 650 | 1043 | 726 | 100.8% | 1 | 317 | 0 | 0 | 71 | 322 | 54145606 | 150000 | 53995606 | 56232960 | 55752280 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | 105.4% | 1 | -1366994 | 2087354 | 38 | 33 | 0 | 208 | 2137914 | 84393 | 0 | 114 | 329014 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27149 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -383908 | 0 | 0 | 322 | 2110169 | 103094 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 113 | 61229521.11 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R12 | 43668215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 0 | 175 | 188 | 123 | 62.86% | 1 | 65 | 0 | 0 | 13 | 0 | 1472083 | 50000 | 1422083 | 1472083 | 1445724 | 0 | 65000 | 65000 | 1510724 | 1446603 | 101.7% | 1 | -64121 | 0 | 4 | 9 | 0 | 0 | 15380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15380 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2019-09-16 | QTR1 | 19/20 | 115 | 1181939.29 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 97.6% | 1 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | 101.6% | 1 | -783 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69
| 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 83.24% | 1 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | 98.1% | 1 | -12362 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37
| 01 | E1R51 | 43800815201 | 2018-09-20 | QTR1 | 18/19 | 1 | 0 | 165 | 233 | 232 | 103% | 1 | 1 | 0 | 0 | 68 | 0 | 2579000 | 50000 | 2529000 | 2579000 | 2523711 | 0 | 0 | 0 | 2523711 | 2514757 | 99.44% | 1 | -8954 | 0 | 53 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-10-31 | QTR2 | 19/20 | 113 | 2698176.21 | B0 | ACC - LUMP SUM
| 01 | E1R80 | 43771615201 | 2019-04-18 | QTR4 | 18/19 | 1 | 1 | 65 | 96 | 96 | 116.9% | 1 | 0 | 0 | 0 | 31 | 0 | 157000 | 9525 | 147475 | 157000 | 148434 | 0 | 0 | 0 | 148434 | 148434 | 100.7% | 1 | 0 | 0 | 16 | 4 | 0 | 0 | 6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 6184 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 108 | 169094.28
| 01 | E1S00 | 43943515201 | 2019-05-23 | QTR4 | 18/19 | 2 | 0 | 140 | 159 | 118 | 70.71% | 1 | 41 | 0 | 0 | 19 | 0 | 2112776 | 50000 | 2062776 | 2112776 | 2088952 | 0 | 0 | 0 | 2088952 | 2065283 | 100.1% | 1 | -23668 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 108 | 3162692.93 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 11 | 14 | 23 | 2955 | 3923 | 3524 | 90.91% | 10 | 399 | 63 | 0 | 614 | 354 | 86011830 | 688304 | 85323526 | 88275347 | 87093370 | -104895 | 2565000 | 2460105 | 89553475 | 88618765 | 100% | 11 | -916707 | 2263517 | 380 | 193 | 5 | 208 | 2214493 | 84393 | 19 | 114 | 458732 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 36450 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -383908 | 0 | 41 | 354 | 2337755 | 103094
| District 01 Totals |  |  |  |  | 34 | 55 | 77 | 7503 | 9722 | 8636 | 97.06% | 33 | 1086 | 63 | 0 | 1681 | 538 | 167478236 | 1511306 | 165966930 | 171818662 | 170096902 | -104895 | 5355000 | 5250105 | 175347007 | 172447718 | 94.12% | 32 | -2766422 | 4340426 | 1127 | 484 | 33 | 248 | 3704731 | 84393 | 19 | 254 | 2154188 | 10696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | -440514 | 14314 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -877000 | 0 | 70 | 534 | 4580691 | 109402
| 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 120.6% | 0 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | 98.56% | 1 | -354944 | 150000 | 87 | 47 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74
| 02 | T2576 | 43091115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 13 | 340 | 624 | 717 | 192.1% | 0 | -93 | 93 | 0 | 64 | 220 | 7004346 | 70466 | 6933880 | 8247072 | 8273395 | -350610 | 0 | -350610 | 7922785 | 7815365 | 112.7% | 0 | -95677 | 1242726 | 29 | 35 | 0 | 4 | 33738 | 1648 | 0 | 98 | 237085 | 153271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 898427 | 0 | 0 | 5 | 38629 | 32695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 1207879 | 187614 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2017-12-20 | QTR2 | 17/18 | 208 | 5694356.97
| 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | 171.9% | 0 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | 100.5% | 1 | -191646 | 313457 | 83 | 110 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88
| 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | 135.9% | 0 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 100.6% | 1 | 7440 | 0 | 43 | 36 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45
| 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 126.9% | 0 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 111% | 0 | 45271 | 670366 | 127 | 43 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 |  | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54
| 02 | T2657 | 20781825201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 560 | 749 | 748 | 107.3% | 1 | 1 | 0 | 0 | 147 | 42 | 13545525 | 150000 | 13395525 | 13574913 | 13974107 | 0 | 0 | 0 | 13974107 | 14346429 | 107.1% | 1 | 400515 | 29388 | 101 | 46 | 0 | 30 | 66698 | 0 | 0 | 12 | 26717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 99695 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-12 | QTR3 | 19/20 |  | 2019-08-17 | QTR1 | 19/20 | 214 | 16380282.85 | B6 | ACC - LIQUIDATED SAVINGS
| 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 119.8% | 1 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 102.4% | 1 | 15232 | 81763 | 65 | 48 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67
| 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 198.9% | 0 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 114.5% | 0 | 9762 | 362855 | 62 | 30 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92
| 02 | T2679 | 43617415201 | 2017-12-06 | QTR2 | 17/18 | 2 | 2 | 350 | 518 | 518 | 119.4% | 1 | 0 | 0 | 0 | 100 | 68 | 10753984 | 78530 | 10675454 | 10978696 | 11000190 | 0 | 0 | 0 | 11000190 | 11198057 | 104.9% | 1 | 197867 | 224712 | 67 | 33 | 0 | 12 | 149047 | 0 | 0 | 56 | 21709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 170756 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-21 | QTR3 | 19/20 |  | 2019-09-19 | QTR1 | 19/20 | 208 | 7872133.21
| 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 108.3% | 1 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 112.7% | 0 | 804997 | 8616 | 80 | 27 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07
| 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 130.9% | 0 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 113.6% | 0 | 80901 | 27471 | 62 | 25 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62
| 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 86.07% | 1 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 106.1% | 1 | 354385 | 0 | 54 | 40 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27
| 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 108.3% | 1 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 104.3% | 1 | 0 | 66083 | 30 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 |  | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7
| 02 | T2689 | 43616115201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 270 | 351 | 331 | 92.59% | 1 | 20 | 0 | 0 | 81 | 0 | 1995665 | 50000 | 1945665 | 1995665 | 2049720 | 0 | 0 | 0 | 2049720 | 2101020 | 108% | 1 | 51299 | 0 | 22 | 59 | 0 | 0 | 24965 | 0 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28054 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | QTR3 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 216 | 2153022.57
| 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14546489 | 0 | 0 | 0 | 14546489 | 15202892 | 111.3% | 0 | 656402 | 0 | 94 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57
| 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 108.1% | 1 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3743642 | 98.92% | 1 | 52262 | 53332 | 27 | 37 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59
| 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 86.04% | 1 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | 104.5% | 1 | -21380 | 86773 | 31 | 24 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39
| 02 | T2708 | 44216935201 | 2019-04-24 | QTR4 | 18/19 | 1 | 3 | 120 | 139 | 75 | 46.67% | 1 | 64 | 0 | 0 | 19 | 0 | 368985 | 120 | 368865 | 374417 | 391272 | 0 | 0 | 0 | 391272 | 387389 | 105% | 1 | 0 | 5432 | 9 | 10 | 0 | 0 | 1160 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-25 | QTR2 | 19/20 | 208 | 334520.6
| 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 65% | 1 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | 99.5% | 1 | -29525 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 |  | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85
| 02 | T2723 | 43762015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 120 | 143 | 143 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 1658214 | 50000 | 1608214 | 1658214 | 1598015 | 0 | 0 | 0 | 1598015 | 1602638 | 99.65% | 1 | 4623 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 214 | 2124298.79
| 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 74.29% | 1 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 99.5% | 1 | 6452 | 0 | 5 | 3 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8
| 02 | T2730 | 43429715201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 144 | 139 | 95.83% | 1 | 5 | 0 | 0 | 24 | 0 | 2680388 | 50000 | 2630388 | 2680388 | 2824608 | 0 | 0 | 0 | 2824608 | 2824608 | 107.4% | 1 | 0 | 0 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-10-15 | QTR2 | 19/20 | 209 | 3620026.94
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 22 | 34 | 58 | 5904 | 8965 | 8801 | 68.18% | 15 | 164 | 134 | 0 | 1926 | 1135 | 134461236 | 1520751 | 132940484 | 137784208 | 139120990 | -500674 | 0 | -500674 | 138620316 | 140559709 | 72.73% | 16 | 1994236 | 3322974 | 1122 | 707 | 44 | 249 | 888370 | 58782 | 0 | 419 | 1360627 | 189105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 93641 | 0 | 0 | 1 | 24070 | 5643 | 0 | 0 | 0 | 0 | 0 | 20 | 8988 | 0 | 0 | 399 | 925898 | 27471 | 53 | 39 | 231779 | 103245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1129 | 3533373 | 384246
| 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 157.7% | 0 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | 110.5% | 0 | -1459708 | 16826383 | 385 | 223 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18219 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 11 | 798 | 1068 | 1998 | 234.5% | 0 | -930 | 930 | 0 | 127 | 143 | 84850000 | 175000 | 84675000 | 85372612 | 84851152 | -10428635 | 0 | -10428635 | 74422517 | 78818095 | 93.08% | 1 | 4395578 | 522612 | 82 | 45 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271502 | 0 | 0 | 143 | 564185 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | 128.4% | 0 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | 97.09% | 1 | -1251611 | -606983 | 51 | 65 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2V70 | 42747515201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 350 | 579 | 577 | 131.1% | 0 | 2 | 0 | 0 | 229 | 0 | 4483000 | 51665 | 4431335 | 4642146 | 4688789 | 0 | 0 | 0 | 4688789 | 4688881 | 105.8% | 1 | 92 | 159146 | 25 | 93 | 0 | 0 | 18680 | 0 | 0 | 0 | 40938 | 1341 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 166914 | 1341 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 5283434.02
| 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 116.3% | 1 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 112.2% | 0 | 298956 | 30442 | 44 | 26 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25
| 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 170.6% | 0 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 123.3% | 0 | 110065 | 656701 | 89 | 38 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 |  | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79
| 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 85.78% | 1 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 100.6% | 1 | 2 | 0 | 67 | 39 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25
| 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 103.5% | 1 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 96.37% | 1 | 2 | -3969 | 52 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60481 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 |  | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46
| 02 | E2W52 | 42849815201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 300 | 324 | 261 | 79% | 1 | 63 | 0 | 0 | 24 | 0 | 730881 | 39951 | 690930 | 756196 | 713128 | 0 | 0 | 0 | 713128 | 713129 | 103.2% | 1 | 0 | 25315 | 9 | 15 | 0 | 0 | 53237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53237 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-14 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 208 | 752277.84
| 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 99.21% | 1 | 0 | 0 | 20 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 |  | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23
| 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | 99.4% | 1 | -932 | 0 | 21 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46
| 02 | E2W96 | 43307515201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 350 | 401 | 349 | 85.14% | 1 | 52 | 0 | 0 | 51 | 0 | 4411000 | 50000 | 4361000 | 4455781 | 4414330 | 0 | 0 | 0 | 4414330 | 4414364 | 101.2% | 1 | 34 | 44781 | 28 | 23 | 0 | 0 | 16525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61306 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-16 | QTR2 | 19/20 | 208 | 4144135.21
| 02 | E2X07 | 20956525201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 60 | 72 | 72 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 327059 | 16215 | 310844 | 327059 | 288640 | 0 | 0 | 0 | 288640 | 288640 | 92.86% | 1 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 208 | 337947.23
| 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 74.6% | 1 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 100.3% | 1 | 0 | 0 | 26 | 39 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 |  | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17
| 02 | E2X44 | 42879715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 200 | 428 | 428 | 182.5% | 0 | 0 | 0 | 0 | 130 | 98 | 1990108 | 50000 | 1940108 | 2637472 | 2547298 | 0 | 0 | 0 | 2547298 | 2542607 | 131.1% | 0 | -4691 | 647363 | 37 | 26 | 60 | 95 | 608011 | 0 | 0 | 3 | 4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 98 | 612548 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-05 | QTR2 | 19/20 | 216 | 2271972.07
| 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 76.19% | 1 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 98.98% | 1 | 0 | 0 | 14 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97
| 02 | E2X60 | 43025915201 | 2018-08-15 | QTR1 | 18/19 | 1 | 0 | 280 | 326 | 325 | 101.8% | 1 | 1 | 0 | 0 | 40 | 6 | 1328017 | 50000 | 1278017 | 1328017 | 1207862 | 0 | 0 | 0 | 1207862 | 1207862 | 94.51% | 1 | 0 | 0 | 18 | 22 | 0 | 6 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 875 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 208 | 1798375.14
| 02 | E2X61 | 43496915201 | 2018-08-15 | QTR1 | 18/19 | 2 | 0 | 180 | 210 | 230 | 111.1% | 1 | -20 | 20 | 0 | 30 | 0 | 2118153 | 50000 | 2068153 | 2118153 | 2024485 | -33300 | 0 | -33300 | 1991185 | 1991185 | 96.28% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-01-22 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 209 | 2333869.85
| 02 | E2X68 | 43500015201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 125 | 132 | 112 | 84% | 1 | 20 | 0 | 0 | 7 | 0 | 925745 | 45595 | 880149 | 925745 | 888997 | 0 | 0 | 0 | 888997 | 888989 | 101% | 1 | -8 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 209 | 952358.87
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 20 | 30 | 69 | 7662 | 11067 | 11631 | 70% | 14 | -564 | 968 | 0 | 2078 | 1327 | 358069946 | 1393889 | 356676055 | 376456987 | 375473662 | -10691867 | 0 | -10691867 | 364781795 | 366514131 | 75% | 15 | 2099457 | 18387041 | 1017 | 829 | 114 | 342 | 3576277 | 238783 | 0 | 747 | 14665873 | 1225540 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273900 | 0 | 7 | 231 | 222682 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350202 | 0 | 232 | 1327 | 18495824 | 1464323
| District 02 Totals |  |  |  |  | 42 | 64 | 127 | 13566 | 20032 | 20432 | 69.05% | 29 | -400 | 1102 | 0 | 4004 | 2462 | 492531182 | 2914640 | 489616539 | 514241195 | 514594652 | -11192541 | 0 | -11192541 | 503402111 | 507073840 | 73.81% | 31 | 4093693 | 21710015 | 2139 | 1536 | 158 | 591 | 4464647 | 297565 | 0 | 1166 | 16026500 | 1414645 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273900 | 0 | 7 | 233 | 316323 | 0 | 111 | 1 | 24070 | 5643 | 0 | 0 | 0 | 0 | 0 | 27 | 8988 | 0 | 0 | 399 | 1030731 | 27471 | 53 | 39 | 231779 | 103245 | 0 | 0 | 0 | 0 | 0 | 0 | -350202 | 0 | 329 | 2456 | 22029197 | 1848569
| 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | 114.3% | 1 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | 90.98% | 1 | -1453386 | 157836 | 188 | 58 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28
| 03 | T3485 | 42695315201 | 2016-04-27 | QTR4 | 15/16 | 2 | 1 | 200 | 314 | 351 | 139% | 0 | -37 | 37 | 0 | 113 | 1 | 3574230 | 50000 | 3524230 | 3575445 | 3569976 | -104007 | 0 | -104007 | 3465969 | 3477125 | 98.66% | 1 | 11156 | 1215 | 52 | 21 | 0 | 1 | 1215 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 6091 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2017-06-30 | QTR4 | 16/17 | 308 | 3028499.48
| 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | 129.8% | 0 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | 96.12% | 1 | -84026 | 68219 | 39 | 20 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 |  | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84
| 03 | T3543 | 22044275201 | 2015-09-30 | QTR1 | 15/16 | 1 | 18 | 830 | 1304 | 1304 | 106.1% | 1 | 0 | 0 | 0 | 435 | 39 | 29686177 | 150000 | 29536177 | 35844062 | 36589864 | 0 | 0 | 0 | 36589864 | 36787330 | 124.6% | 0 | 244313 | 6157885 | 342 | 81 | 12 | 14 | 166013 | 0 | 0 | 15 | 229697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 578955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 224474 | 0 | 0 | 0 | 4978544 | 83847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41801 | 0 | 12 | 39 | 6135882 | 83847 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-07-29 | QTR1 | 19/20 | 308 | 37447263.92
| 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 121.7% | 0 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 106% | 1 | 8875 | 51756 | 76 | 28 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44
| 03 | T3586 | 42862415201 | 2018-06-13 | QTR4 | 17/18 | 1 | 4 | 340 | 451 | 449 | 108.2% | 1 | 2 | 0 | 0 | 111 | 0 | 4214542 | 0 | 4214542 | 4293135 | 4297521 | 0 | 0 | 0 | 4297521 | 4255328 | 101% | 1 | -5203 | 78594 | 50 | 31 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13328 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 41604 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-13 | QTR2 | 19/20 | 321 | 3958245.51
| 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 104.8% | 1 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | 95.32% | 1 | -6959 | 0 | 66 | 24 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75
| 03 | T3614 | 43228815201 | 2018-08-29 | QTR1 | 18/19 | 1 | 2 | 120 | 238 | 238 | 133.3% | 0 | 0 | 0 | 0 | 78 | 40 | 776874 | 0 | 776874 | 1103417 | 1178529 | 0 | 0 | 0 | 1178529 | 1178529 | 151.7% | 0 | 0 | 326542 | 62 | 16 | 0 | 40 | 326542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326542 | 0 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 308 | 825049.02
| 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 104.3% | 1 | 373777 | 60427 | 75 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485
| 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | 100.6% | 1 | -2578 | 6645 | 68 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65
| 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 102.1% | 1 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | 98.23% | 1 | -2508 | 0 | 76 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9
| 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 118.3% | 1 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 113.7% | 0 | 168914 | 26513 | 52 | 23 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2019-01-11 | QTR3 | 18/19 | 308 | 0
| 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 99.04% | 1 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 108.7% | 1 | 334168 | -32998 | 50 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16
| 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 96% | 1 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 98.38% | 1 | 0 | -2208 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43
| 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 104.2% | 1 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 114% | 0 | 321209 | 405998 | 157 | 26 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62
| 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 133.8% | 0 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 105.4% | 1 | 57366 | 27889 | 69 | 25 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76
| 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 100% | 1 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 114% | 0 | 100163 | 31248 | 167 | 43 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49
| 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 94.48% | 1 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | 107.9% | 1 | -464 | 209861 | 112 | 20 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000
| 03 | T3673 | 43774415201 | 2018-09-26 | QTR1 | 18/19 | 1 | 4 | 180 | 268 | 262 | 116.7% | 1 | 6 | 0 | 0 | 52 | 36 | 7942048 | 83065 | 7858983 | 7802040 | 7940568 | 0 | 0 | 0 | 7940568 | 7896410 | 100.5% | 1 | -44158 | -140008 | 28 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -140008 | 0 | 0 | 0 | 49174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -90833 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-09-05 | QTR1 | 19/20 | 321 | 8459567.2
| 03 | T3678 | 43627015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 180 | 208 | 179 | 83.89% | 1 | 29 | 0 | 0 | 28 | 0 | 4020176 | 50000 | 3970176 | 4016156 | 4196886 | 0 | 0 | 0 | 4196886 | 4189347 | 105.5% | 1 | -7539 | -4020 | 13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 32860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28840 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2019-12-06 | QTR2 | 19/20 | 321 | 4510561.96
| 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 95.56% | 1 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 101.7% | 1 | 0 | 0 | 22 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24
| 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 98.89% | 1 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 99.76% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM
| 03 | T3688 | 44038315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 134 | 120 | 88.33% | 1 | 14 | 0 | 0 | 14 | 0 | 354899 | 18499 | 336400 | 354899 | 344281 | 0 | 0 | 0 | 344281 | 344281 | 102.3% | 1 | 0 | 0 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 321 | 390454.14
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 23 | 30 | 64 | 5039 | 7948 | 7920 | 78.26% | 18 | 28 | 71 | 0 | 2623 | 286 | 111267758 | 1206580 | 110061177 | 118699154 | 119993387 | -302298 | 0 | -302298 | 119691089 | 119378768 | 78.26% | 18 | 13120 | 7431394 | 1784 | 629 | 12 | 117 | 1089908 | 15783602 | 167 | 105 | 634092 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 455145 | 10742 | 17 | 3 | 107017 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 276225 | 0 | 0 | 0 | 4978544 | 83847 | 14 | 0 | 0 | 0 | 0 | 0 | 19973 | 0 | 0 | 0 | -41801 | 0 | 210 | 286 | 7519106 | 15896350
| 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 115.7% | 1 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 104.7% | 1 | 52521 | 0 | 13 | 25 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95
| 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 94.44% | 1 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 109.1% | 1 | 148555 | 3908 | 52 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8
| 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 97.78% | 1 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 102.4% | 1 | 0 | -4732 | 101 | 60 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-05-13 | QTR4 | 18/19 | 308 | 795145
| 03 | E3R15 | 43730715201 | 2018-04-12 | QTR4 | 17/18 | 2 | 0 | 120 | 195 | 199 | 125% | 0 | -4 | 4 | 0 | 75 | 0 | 847761 | 42761 | 805000 | 847761 | 805000 | -6660 | 0 | -6660 | 798340 | 805000 | 100% | 1 | 6660 | 0 | 44 | 5 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 308 | 968822.89 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 03 | E3R27 | 40410835201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 90 | 121 | 119 | 97.78% | 1 | 2 | 0 | 0 | 31 | 0 | 497771 | 26481 | 471290 | 497771 | 462232 | 0 | 0 | 0 | 462232 | 462232 | 98.08% | 1 | 0 | 0 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-19 | QTR2 | 19/20 | 314 | 568464.05
| 03 | E3R52 | 43627225201 | 2019-01-10 | QTR3 | 18/19 | 1 | 1 | 180 | 215 | 203 | 93.89% | 1 | 12 | 0 | 0 | 34 | 1 | 1432597 | 50000 | 1382597 | 1438332 | 1321040 | 0 | 0 | 0 | 1321040 | 1327923 | 96.05% | 1 | 6884 | 5735 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 308 | 1931230.61
| 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 105.4% | 1 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 109% | 1 | 63342 | 76927 | 41 | 24 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46
| 03 | E3S52 | 41767755201 | 2019-05-09 | QTR4 | 18/19 | 1 | 0 | 90 | 170 | 168 | 114.4% | 1 | 2 | 0 | 0 | 80 | 0 | 551256 | 24827 | 526429 | 551256 | 487293 | 0 | 0 | 0 | 487293 | 487293 | 92.57% | 1 | 0 | 0 | 43 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2020-01-16 | QTR3 | 19/20 | 314 | 525116.42
| 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 84.44% | 1 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0% | 1 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 9 | 14 | 9 | 1250 | 1849 | 1817 | 88.89% | 8 | 32 | 4 | 0 | 597 | 2 | 11547141 | 333038 | 11214103 | 11628979 | 11466653 | -8531 | 0 | -8531 | 11458122 | 11671565 | 100% | 9 | 232962 | 81838 | 342 | 175 | 21 | 0 | 2415 | 0 | 36 | 1 | 66119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 9843 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2 | 78377 | 8796
| District 03 Totals |  |  |  |  | 32 | 44 | 73 | 6289 | 9797 | 9737 | 81.25% | 26 | 60 | 75 | 0 | 3220 | 288 | 122814899 | 1539618 | 121275280 | 130328133 | 131460040 | -310829 | 0 | -310829 | 131149211 | 131050333 | 84.38% | 27 | 246082 | 7513232 | 2126 | 804 | 33 | 117 | 1092323 | 15783602 | 203 | 106 | 700211 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 57 | 464988 | 19538 | 17 | 3 | 107017 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 276225 | 0 | 0 | 0 | 4978544 | 83847 | 14 | 0 | 0 | 0 | 0 | 0 | 19973 | 0 | 0 | 0 | -41801 | 0 | 290 | 288 | 7597483 | 15905146
| 04 | T4418 | 22989615201 | 2015-07-29 | QTR1 | 15/16 | 7 | 5 | 1005 | 1118 | 1118 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 17423228 | 150000 | 17273228 | 17585616 | 15704340 | 0 | 0 | 0 | 15704340 | 15605066 | 90.34% | 1 | -82422 | 162388 | 51 | 62 | 0 | 0 | -39118 | 0 | 0 | 0 | 189822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11593 | 11593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162297 | 11593 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-01-25 | QTR3 | 18/19 | 409 | 22527836.07
| 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 100.2% | 1 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 98.32% | 1 | 442812 | 198133 | 145 | 57 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 |  | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16
| 04 | T4433 | 42872415201 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 601 | 960 | 974 | 111.8% | 1 | -14 | 14 | 0 | 302 | 61 | 16224277 | 150000 | 16074277 | 17235975 | 16795691 | -46980 | -64000 | -110980 | 16684711 | 16774147 | 104.4% | 1 | 140685 | 1011698 | 254 | 48 | 0 | 0 | 284349 | 0 | 0 | 58 | 769055 | 15997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1059392 | 20397 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-02-25 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 412 | 14991647.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4444 | 43270515201 | 2016-12-07 | QTR2 | 16/17 | 4 | 8 | 910 | 1190 | 1005 | 81.98% | 1 | 185 | 0 | 0 | 259 | 21 | 27999900 | 150000 | 27849900 | 28775420 | 29356382 | 0 | 0 | 0 | 29356382 | 30041255 | 107.9% | 1 | 725124 | 775520 | 216 | 43 | 0 | 21 | 446126 | 0 | 0 | 0 | 206370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 683157 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-02-11 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 408 | 34103305.86
| 04 | T4452 | 43166615201 | 2017-01-25 | QTR3 | 16/17 | 2 | 4 | 396 | 484 | 478 | 98.48% | 1 | 6 | 0 | 0 | 88 | 0 | 3407245 | 50000 | 3357245 | 3524212 | 3504637 | 0 | 0 | 0 | 3504637 | 3537514 | 105.4% | 1 | 69412 | 116967 | 67 | 21 | 0 | 0 | 52621 | 51166 | 0 | 0 | 68491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126406 | 51166 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-06 | QTR3 | 19/20 |  | 2018-10-02 | QTR2 | 18/19 | 412 | 3478134.48
| 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | 119.4% | 1 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 91.7% | 1 | 855652 | 75851 | 215 | 58 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 |  | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 106.6% | 1 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 100.7% | 1 | 189028 | 165338 | 66 | 42 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 |  | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18
| 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 132.6% | 0 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7138333 | 115.2% | 0 | 123672 | 533617 | 55 | 41 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 107.8% | 1 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | 99.64% | 1 | -156 | -6176 | 89 | 27 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55
| 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 109.5% | 1 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 104.4% | 1 | 83036 | 308276 | 109 | 33 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 |  | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96
| 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 99.32% | 1 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | 100.4% | 1 | -4859 | 47624 | 74 | 22 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18
| 04 | T4480 | 43166515201 | 2018-04-25 | QTR4 | 17/18 | 2 | 1 | 214 | 274 | 273 | 105.1% | 1 | 1 | 0 | 0 | 48 | 12 | 1327221 | 50000 | 1277221 | 1366521 | 1298578 | 0 | 0 | 0 | 1298578 | 1298125 | 101.6% | 1 | -453 | 39300 | 29 | 19 | 0 | 0 | 0 | 0 | 0 | 12 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42392 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 412 | 1330304.19
| 04 | T4486 | 43165715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 10 | 353 | 442 | 442 | 112.7% | 1 | 0 | 0 | 0 | 44 | 45 | 3260393 | 50000 | 3210393 | 3609674 | 3402444 | 0 | 0 | 0 | 3402444 | 3396789 | 105.8% | 1 | -5656 | 349282 | 19 | 25 | 0 | 45 | 162960 | 125042 | 0 | 0 | 157599 | 106623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 387158 | 231666 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-10-28 | QTR2 | 19/20 | 412 | 3504742.12
| 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 64.44% | 1 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 96.63% | 1 | 4043 | 0 | 6 | 5 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05
| 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 103.1% | 1 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 99.63% | 1 | 1280 | 11869 | 31 | 8 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 15 | 39 | 76 | 6866 | 9188 | 8982 | 93.33% | 14 | 206 | 105 | 0 | 1937 | 389 | 135678236 | 1219612 | 134458625 | 139467923 | 133749649 | -474498 | -64000 | -538498 | 133211151 | 135387720 | 93.33% | 14 | 2541198 | 3789687 | 1426 | 511 | 0 | 102 | 1447623 | 181164 | 0 | 226 | 1780909 | 130318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 28 | 266334 | 395 | 0 | 3 | 121804 | 4400 | 0 | 0 | 0 | 0 | 0 | 30 | 34253 | 0 | 0 | 0 | 11593 | 11593 | 0 | 0 | 6882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389 | 3672397 | 327871
| 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 100.9% | 1 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | 98.74% | 1 | -6213797 | 2243984 | 183 | 45 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -404828 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 102.1% | 1 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | 95.08% | 1 | -417090 | -338192 | 219 | 89 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 95.23% | 1 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | 99.35% | 1 | -3249187 | 3281488 | 165 | 64 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 |  | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P04 | 23193225201 | 2014-04-16 | QTR4 | 13/14 | 7 | 11 | 979 | 1575 | 1811 | 154.6% | 0 | -236 | 236 | 0 | 297 | 299 | 32540300 | 150000 | 32390300 | 33830739 | 33682875 | -2003878 | 0 | -2003878 | 31678997 | 33229430 | 102.6% | 1 | 1655512 | 1290439 | 225 | 72 | 0 | 299 | 1014970 | 0 | 0 | 0 | 128450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -960 | 0 | 0 | 299 | 1187254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-12 | QTR1 | 19/20 | 409 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | 101.9% | 1 | -500000 | 58245 | 22 | 76 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | 109.7% | 1 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | 99.01% | 1 | -4739 | 364238 | 220 | 71 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4Q64 | 43310855201 | 2015-05-29 | QTR4 | 14/15 | 1 | 30 | 1400 | 1506 | 1365 | 89.93% | 1 | 141 | 0 | 0 | 106 | 0 | 153917279 | 150000 | 153767279 | 162463226 | 162823699 | 0 | 3720000 | 3720000 | 166543699 | 162492246 | 105.7% | 1 | -3709579 | 8545947 | 57 | 49 | 0 | 0 | 1603424 | 0 | 0 | 0 | 2717641 | 75013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480038 | 468544 | 0 | 0 | 1150398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -669018 | 0 | 0 | 0 | 8290048 | 543557 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-03 | QTR2 | 19/20 | 406 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 97.73% | 1 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 114.7% | 0 | 167827 | 1860107 | 73 | 34 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | 151.3% | 0 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 99.55% | 1 | 172641 | 33902 | 24 | 21 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1
| 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 113% | 1 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 99.98% | 1 | 2288 | 48308 | 23 | 34 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 |  | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12
| 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 101.4% | 1 | 2719 | 0 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33
| 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 101.7% | 1 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 |  | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67
| 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 30.92% | 1 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 100.3% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42
| 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 48.93% | 1 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 99.58% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28
| 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 50.41% | 1 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 99.12% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 15 | 35 | 110 | 10859 | 13448 | 12880 | 86.67% | 13 | 568 | 334 | 0 | 1848 | 741 | 570427971 | 1441882 | 568986089 | 587816437 | 586928695 | -2668972 | 5140000 | 2471028 | 589399723 | 576175531 | 93.33% | 14 | -12093405 | 17388466 | 1255 | 591 | 2 | 493 | 5828393 | 7451 | 0 | 68 | 4215700 | 214332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80300 | 0 | 0 | 27 | 4948613 | 506015 | 0 | 35 | 1353925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 119 | 1355416 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1277603 | 0 | 2 | 742 | 16512307 | 762391
| District 04 Totals |  |  |  |  | 30 | 74 | 186 | 17725 | 22636 | 21862 | 90% | 27 | 774 | 439 | 0 | 3785 | 1130 | 706106207 | 2661494 | 703444714 | 727284360 | 720678344 | -3143470 | 5076000 | 1932530 | 722610874 | 711563251 | 93.33% | 28 | -9552207 | 21178153 | 2681 | 1102 | 2 | 595 | 7276016 | 188615 | 0 | 294 | 5996609 | 344650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83300 | 0 | 0 | 55 | 5214947 | 506410 | 0 | 38 | 1475729 | 4400 | 0 | 0 | 0 | 0 | 0 | 30 | 41818 | 0 | 0 | 119 | 1367009 | 46186 | 0 | 0 | 6882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1277603 | 0 | 2 | 1131 | 20184704 | 1090262
| 05 | BE626 | 43787225201 | 2018-05-24 | QTR4 | 17/18 | 1 | 0 | 280 | 344 | 213 | 53.21% | 1 | 131 | 0 | 0 | 64 | 0 | 720000 | 0 | 720000 | 720000 | 720000 | 0 | 0 | 0 | 720000 | 720000 | 100% | 1 | 0 | 0 | 41 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-01-17 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 507 | 720000
| 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 102.4% | 1 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | 101.4% | 1 | -3056235 | 3576803 | 117 | 48 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 76% | 1 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | 101.8% | 1 | -30000 | 19031 | 14 | 56 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 82.37% | 1 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | 100.9% | 1 | -14500 | 0 | 18 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75
| 05 | T5591 | 42823815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 500 | 652 | 649 | 107.4% | 1 | 3 | 0 | 0 | 112 | 40 | 16694356 | 150000 | 16544356 | 16972569 | 16490950 | 0 | 0 | 0 | 16490950 | 16700809 | 100.9% | 1 | 209859 | 278213 | 41 | 71 | 0 | 40 | 16791 | 0 | 0 | 0 | 143061 | 49425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137620 | 132029 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 332991 | 181454 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-13 | QTR3 | 19/20 |  | 2019-08-15 | QTR1 | 19/20 | 514 | 15183626.94
| 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 107.7% | 1 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 108% | 1 | 265414 | 161314 | 43 | 47 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492
| 05 | T5616 | 43065515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 260 | 334 | 334 | 102.7% | 1 | 0 | 0 | 0 | 67 | 7 | 4231483 | 53000 | 4178483 | 4229830 | 4248590 | 0 | 0 | 0 | 4248590 | 4402057 | 105.4% | 1 | 153467 | -1653 | 46 | 21 | 0 | 0 | -14065 | 0 | 0 | 2 | 5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 54377 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 46115 | 2422 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-04 | QTR3 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 512 | 5394340.01
| 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 76.58% | 1 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 101.2% | 1 | 0 | 26406 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410
| 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 112.8% | 1 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 99.75% | 1 | 6737 | 20194 | 36 | 48 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871
| 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 88.85% | 1 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | 103.2% | 1 | -4945 | 426 | 29 | 31 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 10 | 19 | 53 | 4520 | 5479 | 4953 | 100% | 10 | 526 | 0 | 0 | 828 | 131 | 114182351 | 759000 | 113423351 | 118263085 | 117896642 | -56415 | 44500 | -11915 | 117884727 | 115399242 | 100% | 10 | -2470203 | 4080734 | 387 | 441 | 0 | 79 | 997657 | 25021 | 0 | 47 | 1530981 | 90488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 508472 | 134451 | 0 | 0 | 30094 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 1493171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 131 | 4360798 | 249960
| 05 | E5W11 | 24262635201 | 2014-11-21 | QTR2 | 14/15 | 3 | 6 | 900 | 1229 | 1229 | 104.6% | 1 | 0 | 0 | 0 | 288 | 41 | 43150089 | 150000 | 43000089 | 45682181 | 45886261 | 0 | 0 | 0 | 45886261 | 43227195 | 100.5% | 1 | -2633738 | 2532092 | 232 | 56 | 0 | 41 | 2571393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 2600543 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2018-07-08 | QTR1 | 18/19 | 515 | 48952301.58 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | 128.3% | 0 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10359714 | 88.77% | 1 | -459862 | -387154 | 69 | 35 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y20 | 42690435201 | 2016-11-04 | QTR2 | 16/17 | 2 | 5 | 547 | 928 | 921 | 117.9% | 1 | 7 | 0 | 0 | 276 | 105 | 26771800 | 150000 | 26621800 | 27777188 | 27684932 | 0 | 0 | 0 | 27684932 | 28031909 | 105.3% | 1 | 444186 | 1005388 | 215 | 61 | 0 | 14 | 243217 | 16025 | 0 | 91 | 756982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1000199 | 16025 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-01-08 | QTR3 | 19/20 |  | 2019-08-02 | QTR1 | 19/20 | 514 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | 226% | 0 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 180.3% | 0 | 1451 | 1363962 | 39 | 51 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842
| 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 99.29% | 1 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 82.89% | 1 | 1940 | -10 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 |  | 2017-05-14 | QTR4 | 16/17 | 509 | 843684
| 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 111.3% | 1 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | 105.8% | 1 | -795 | 50000 | 60 | 28 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169
| 05 | E5Z09 | 41299445214 | 2017-12-14 | QTR2 | 17/18 | 1 | 1 | 515 | 551 | 514 | 92.82% | 1 | 37 | 0 | 0 | 36 | 0 | 5757000 | 50000 | 5707000 | 5860741 | 5841571 | 0 | 0 | 0 | 5841571 | 5844608 | 102.4% | 1 | 3037 | 103741 | 7 | 29 | 0 | 0 | 77312 | 77312 | 0 | 0 | 26429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134571 | 77312 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 507 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 85% | 1 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 100% | 1 | 0 | 0 | 21 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655
| 05 | E5Z23 | 43564715201 | 2018-05-01 | QTR4 | 17/18 | 1 | 1 | 240 | 281 | 281 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 1013390 | 50000 | 963390 | 1008318 | 958318 | -736 | 0 | -736 | 957582 | 957220 | 99.36% | 1 | -362 | -5072 | 16 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-03-02 | QTR3 | 19/20 |  | 2019-07-10 | QTR1 | 19/20 | 514 | 1052401
| 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 116.1% | 1 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | 109.1% | 1 | -3198 | 133799 | 15 | 33 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25
| 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | 107.5% | 1 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 105.8% | 1 | 0 | 33356 | 25 | 41 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-07-22 | QTR1 | 19/20 | 513 | 480184
| 05 | E5Z45 | 43733915201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 230 | 343 | 343 | 106.5% | 1 | 0 | 0 | 0 | 98 | 15 | 6123814 | 81000 | 6042814 | 6203979 | 6135165 | 0 | 0 | 0 | 6135165 | 6001858 | 99.32% | 1 | -114476 | 80166 | 64 | 34 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-18 | QTR3 | 19/20 |  | 2020-01-30 | QTR3 | 19/20 | 512 | 8194285
| 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 98.18% | 1 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 100% | 1 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 |  | 2019-07-18 | QTR1 | 19/20 | 509 | 441431
| 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | 113.3% | 1 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 114.4% | 0 | 0 | 0 | 22 | 3 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5
| 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 115% | 1 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 97.22% | 1 | 0 | 0 | 29 | 10 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2
| 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 97% | 1 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 100.2% | 1 | 0 | 3000 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75
| 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 93.82% | 1 | 0 | 0 | 22 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 513 | 554880
| 05 | E5Z76 | 44097015201 | 2019-06-04 | QTR4 | 18/19 | 1 | 0 | 90 | 126 | 2 | -37.78% | 1 | 124 | 0 | 0 | 36 | 0 | 167070 | 12438 | 154632 | 167070 | 148419 | 0 | 0 | 0 | 148419 | 148419 | 95.98% | 1 | 0 | 0 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2020-01-06 | QTR3 | 19/20 | 507 | 271247.25
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 18 | 24 | 31 | 5146 | 7210 | 7095 | 88.89% | 16 | 115 | 101 | 0 | 1409 | 655 | 107101329 | 1038939 | 106062390 | 112014596 | 111259119 | -392172 | 0 | -392172 | 110866947 | 107945348 | 88.89% | 16 | -2761817 | 4913268 | 889 | 509 | 11 | 197 | 3036560 | 93337 | 0 | 298 | 1807593 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 205190 | 1753 | 0 | 0 | 30150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 655 | 5079484 | 104469
| District 05 Totals |  |  |  |  | 28 | 43 | 84 | 9666 | 12689 | 12048 | 92.86% | 26 | 641 | 101 | 0 | 2237 | 786 | 221283680 | 1797939 | 219485741 | 230277681 | 229155761 | -448587 | 44500 | -404087 | 228751674 | 223344590 | 92.86% | 26 | -5232020 | 8994002 | 1276 | 950 | 11 | 276 | 4034217 | 118358 | 0 | 345 | 3338574 | 99867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 713662 | 136204 | 0 | 0 | 60244 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 1493161 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 11 | 786 | 9440282 | 354429
| 06 | T6337 | 41809115201 | 2015-10-28 | QTR2 | 15/16 | 7 | 22 | 600 | 1055 | 1055 | 141.8% | 0 | 0 | 0 | 0 | 324 | 131 | 14239526 | 267180 | 13972346 | 16636939 | 16898897 | 0 | 500000 | 500000 | 17398897 | 16914510 | 121.1% | 0 | -453877 | 2397413 | 147 | 57 | 0 | 87 | 1404877 | 434699 | 120 | 44 | 573331 | 258449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573254 | 54307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 131 | 2554384 | 747455 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-02-15 | QTR3 | 18/19 | 606 | 13498168.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6338 | 41463315201 | 2016-01-27 | QTR3 | 15/16 | 4 | 11 | 560 | 1082 | 1082 | 158.6% | 0 | 0 | 0 | 0 | 352 | 170 | 11118409 | 242209 | 10876200 | 12716281 | 13284136 | 0 | 0 | 0 | 13284136 | 13366087 | 122.9% | 0 | 119047 | 1597872 | 138 | 56 | 7 | 170 | 1133148 | 332615 | 137 | 0 | 119548 | 25682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 276565 | 23432 | 0 | 0 | 8312 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 170 | 1537573 | 390040 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-05-23 | QTR4 | 18/19 | 606 | 10197839.36 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 98.35% | 1 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | 100.4% | 1 | -436405 | 725324 | 52 | 25 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 82.12% | 1 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | 104.4% | 1 | -622662 | 376451 | 74 | 40 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 195.7% | 0 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 166% | 0 | 5872 | 2030258 | 59 | 33 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 105.5% | 1 | 21437 | 21903 | 44 | 6 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25
| 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 72.1% | 1 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | 103.4% | 1 | -191642 | 37940 | 56 | 14 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 |  | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 88.67% | 1 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | 98.77% | 1 | -61063 | 80247 | 31 | 18 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 101.3% | 1 | 1476 | 92454 | 90 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 |  | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45
| 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 108.3% | 1 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | 99.99% | 1 | -4122 | 0 | 48 | 19 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 |  | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7
| 06 | T6438 | 43117015201 | 2018-05-23 | QTR4 | 17/18 | 6 | 2 | 320 | 363 | 295 | 78.75% | 1 | 68 | 0 | 0 | 43 | 0 | 3669797 | 51765 | 3618032 | 3847108 | 3668181 | 0 | 250000 | 250000 | 3918181 | 3697899 | 102.2% | 1 | -220283 | 177311 | 23 | 20 | 0 | 0 | 82758 | 0 | 0 | 0 | 14636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16895 | 16211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189909 | 16211 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 606 | 4444325.03 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 118% | 1 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | 93.91% | 1 | -1279 | 0 | 40 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85
| 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | 92.06% | 1 | -1113 | 0 | 34 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 |  | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25
| 06 | T6462 | 43792215201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 160 | 195 | 193 | 98.75% | 1 | 2 | 0 | 0 | 35 | 0 | 672522 | 35087 | 637435 | 672522 | 627588 | 0 | 0 | 0 | 627588 | 627091 | 98.38% | 1 | -497 | 0 | 26 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 606 | 724071.25
| 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 97.3% | 1 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | 98.31% | 1 | -24 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 606 | 324690
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 15 | 62 | 76 | 5252 | 7390 | 6989 | 80% | 12 | 401 | 0 | 0 | 1602 | 536 | 99861827 | 2539000 | 97322827 | 107399002 | 106810570 | 0 | 2050000 | 2050000 | 108860570 | 106693114 | 80% | 12 | -1845135 | 7537173 | 875 | 336 | 22 | 281 | 4328295 | 897314 | 257 | 222 | 2194814 | 628789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 1429794 | 117395 | 0 | 0 | 27135 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 603576 | 586616 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 391 | 536 | 8069565 | 2238425
| 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 95.74% | 1 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 99.71% | 1 | 1013 | 67062 | 142 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1
| 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 103.3% | 1 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 105% | 1 | 649560 | 1806784 | 96 | 54 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K58 | 43081315201 | 2019-01-31 | QTR3 | 18/19 | 3 | 1 | 200 | 224 | 186 | 81% | 1 | 38 | 0 | 0 | 24 | 0 | 1100030 | 52315 | 1047715 | 1101649 | 1024191 | 0 | 100000 | 100000 | 1124191 | 1025137 | 97.85% | 1 | -97435 | 1619 | 16 | 8 | 0 | 0 | 557 | 0 | 0 | 0 | 16202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17525 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-11-30 | QTR2 | 19/20 | 606 | 1216039.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 84.26% | 1 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | 109.7% | 1 | -358123 | 1067468 | 84 | 14 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 80% | 1 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 93.85% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 |  | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8
| 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 96% | 1 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 104.9% | 1 | 0 | 24000 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 606 | 404500
| 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 92.75% | 1 | 0 | 0 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 |  | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218
| 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 97.08% | 1 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | 93.08% | 1 | -158 | 0 | 23 | 11 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2
| 06 | E6L37 | 42919325201 | 2018-01-25 | QTR3 | 17/18 | 4 | 3 | 200 | 241 | 218 | 88.5% | 1 | 23 | 0 | 0 | 41 | 0 | 1491900 | 50260 | 1441640 | 1633114 | 1580093 | 0 | 60000 | 60000 | 1640093 | 1562174 | 108.4% | 1 | -60174 | 141214 | 29 | 12 | 0 | 0 | 4537 | 0 | 0 | 0 | 82537 | 9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48121 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135195 | 14309 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 606 | 1421302.2 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | 96.53% | 1 | -87 | 0 | 51 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5
| 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 99.5% | 1 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | 99.55% | 1 | -352 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 11 | 23 | 24 | 3430 | 4105 | 3902 | 100% | 11 | 203 | 0 | 0 | 647 | 28 | 96123506 | 634039 | 95489467 | 100764065 | 99585824 | 0 | 560000 | 560000 | 100145824 | 99741423 | 100% | 11 | 134244 | 3108147 | 475 | 172 | 0 | 28 | 1390605 | 0 | 0 | 0 | 471422 | 129545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713245 | 53849 | 0 | 0 | 98023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2672150 | 183394
| District 06 Totals |  |  |  |  | 26 | 85 | 100 | 8682 | 11495 | 10891 | 88.46% | 23 | 604 | 0 | 0 | 2249 | 564 | 195985333 | 3173039 | 192812294 | 208163067 | 206396394 | 0 | 2610000 | 2610000 | 209006394 | 206434537 | 88.46% | 23 | -1710891 | 10645320 | 1350 | 508 | 22 | 309 | 5718900 | 897314 | 257 | 222 | 2666236 | 758334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 2143039 | 171244 | 0 | 0 | 125158 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 603576 | 586616 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 391 | 564 | 10741715 | 2421819
| 07 | T7389 | 43272015201 | 2017-01-25 | QTR3 | 16/17 | 4 | 11 | 350 | 542 | 542 | 100% | 1 | 0 | 0 | 0 | 192 | 0 | 12988889 | 109000 | 12879889 | 13889049 | 13996342 | 0 | 0 | 0 | 13996342 | 14019355 | 108.8% | 1 | 112797 | 900160 | 162 | 30 | 0 | 0 | 619080 | 0 | 0 | 0 | 112343 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 0 | 0 | 677937 | 2775 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2018-10-03 | QTR2 | 18/19 | 798 | 14634544.46
| 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | 206.2% | 0 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 93.7% | 1 | 11195 | 18352 | 19 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400
| 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 99.3% | 1 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 99.75% | 1 | 69368 | 0 | 68 | 19 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000
| 07 | T7399 | 43653015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 145 | 210 | 211 | 119.3% | 1 | -1 | 1 | 0 | 48 | 17 | 1314062 | 50000 | 1264062 | 1314062 | 1279715 | -1665 | 0 | -1665 | 1278050 | 1277840 | 101.1% | 1 | -210 | 0 | 29 | 9 | 0 | 0 | 0 | 0 | 10 | 12 | 15865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 21855 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 796 | 1374960.82
| 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 101.5% | 1 | 65512 | 6728 | 41 | 21 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300
| 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 111.1% | 1 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 99.28% | 1 | 6971 | 0 | 61 | 22 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM
| 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 91.82% | 1 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 98.93% | 1 | 0 | 0 | 24 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000
| 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 90.89% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5
| 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 93.17% | 1 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 100.7% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91
| 07 | T7427 | 43704015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 160 | 205 | 189 | 101.2% | 1 | 16 | 0 | 0 | 27 | 18 | 1130856 | 50000 | 1080856 | 1130856 | 1101423 | 0 | 0 | 0 | 1101423 | 1102091 | 102% | 1 | 668 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-12-16 | QTR2 | 19/20 | 799 | 1234500
| 07 | T7429 | 43753015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 120 | 132 | 101 | 74.17% | 1 | 31 | 0 | 0 | 12 | 0 | 1704462 | 50000 | 1654462 | 1704462 | 1672069 | 0 | 0 | 0 | 1672069 | 1672069 | 101.1% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-17 | QTR2 | 19/20 | 796 | 2200000
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 11 | 18 | 14 | 1743 | 2473 | 2516 | 90.91% | 10 | -43 | 113 | 0 | 638 | 92 | 27982195 | 563780 | 27418415 | 28907434 | 28480006 | -179073 | 0 | -179073 | 28300933 | 28477451 | 100% | 11 | 266301 | 925240 | 435 | 180 | 13 | 44 | 678801 | 0 | 10 | 43 | 224066 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 23 | 92 | 856444 | 2775
| 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 119.1% | 1 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | 101% | 1 | -1461417 | 2388357 | 330 | 85 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7K19 | 43476515201 | 2014-10-20 | QTR2 | 14/15 | 2 | 16 | 1200 | 1842 | 1829 | 134.9% | 0 | 13 | 0 | 0 | 210 | 432 | 35360313 | 120000 | 35240313 | 59863754 | 59642810 | 0 | 0 | 0 | 59642810 | 59439123 | 168.7% | 0 | 0 | 24503441 | 97 | 113 | 0 | 362 | 23073894 | 0 | 0 | 0 | 379221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 901989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 24357946 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 714 | 35360312.5
| 07 | E7K24 | 41101145201 | 2015-04-09 | QTR4 | 14/15 | 3 | 20 | 1100 | 1320 | 1320 | 103.1% | 1 | 0 | 0 | 0 | 188 | 32 | 94976100 | 150000 | 94826100 | 96934830 | 96454835 | 0 | 0 | 0 | 96454835 | 95867383 | 101.1% | 1 | -259483 | 1958730 | 108 | 78 | 2 | 30 | 982160 | 90496 | 0 | 0 | 91279 | 4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567939 | 0 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 1718138 | 127398 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 714 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 111.7% | 1 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | 105.4% | 1 | -265912 | 1412899 | 124 | 53 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 105.5% | 1 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 104.4% | 1 | 301 | 232401 | 76 | 23 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26
| 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | 100.5% | 1 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 100.6% | 1 | 2402 | 0 | 242 | 27 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311
| 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 74% | 1 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 98.67% | 1 | 0 | 0 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000
| 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 117.1% | 1 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | 106.5% | 1 | -5930 | 197052 | 173 | 25 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65
| 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | 112.1% | 1 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | 98.97% | 1 | -14425 | 0 | 36 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38
| 07 | E7M26 | 25839935201 | 2018-12-12 | QTR2 | 18/19 | 2 | 0 | 90 | 194 | 194 | 118.9% | 1 | 0 | 0 | 0 | 87 | 17 | 1194104 | 30000 | 1164104 | 1194104 | 1177035 | 0 | 0 | 0 | 1177035 | 1177035 | 101.1% | 1 | 0 | 0 | 78 | 9 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-06 | QTR2 | 19/20 | 796 | 850000
| 07 | E7M27 | 43648015201 | 2018-12-12 | QTR2 | 18/19 | 1 | 2 | 150 | 180 | 180 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1274649 | 45000 | 1229649 | 1382195 | 1318471 | 0 | 0 | 0 | 1318471 | 1320688 | 107.4% | 1 | 2217 | 107546 | 21 | 9 | 0 | 0 | 93140 | 0 | 0 | 0 | 22511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115651 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-09-10 | QTR1 | 19/20 | 798 | 980000
| 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 69.7% | 1 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 84.89% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 798 | 175000
| 07 | E7M32 | 43751815201 | 2019-03-13 | QTR3 | 18/19 | 1 | 0 | 165 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 852730 | 40000 | 812730 | 852730 | 751999 | 0 | 0 | 0 | 751999 | 752000 | 92.53% | 1 | 1 | 0 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2020-02-14 | QTR3 | 19/20 | 796 | 850000
| 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 100% | 1 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 90.04% | 1 | 0 | 0 | 106 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R07 | 43845015201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 500 | 572 | 572 | 100% | 1 | 0 | 0 | 0 | 72 | 0 | 2568748 | 50000 | 2518748 | 2568748 | 2497748 | 0 | 0 | 0 | 2497748 | 2497782 | 99.17% | 1 | 34 | 0 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-01-29 | QTR3 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 796 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R60 | 43920615201 | 2017-09-07 | QTR1 | 17/18 | 1 | 2 | 540 | 637 | 633 | 101.9% | 1 | 4 | 0 | 0 | 83 | 14 | 12005445 | 85975 | 11919470 | 12159938 | 12017053 | 0 | 30000 | 30000 | 12047053 | 12031297 | 100.9% | 1 | 38737 | 154493 | 48 | 35 | 0 | 0 | 9573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 115055 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 714 | 11747696.43 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 16 | 27 | 67 | 6551 | 9474 | 9424 | 93.75% | 15 | 50 | 21 | 0 | 2136 | 787 | 281614476 | 1146300 | 280468176 | 312569395 | 310864313 | -72585 | 280000 | 207415 | 311071728 | 308289115 | 93.75% | 15 | -1963475 | 30954919 | 1527 | 607 | 2 | 484 | 26777454 | 811977 | 0 | 159 | 1514745 | 43157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 142 | 1852677 | 44154 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 57335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 787 | 30397410 | 950368
| District 07 Totals |  |  |  |  | 27 | 45 | 81 | 8294 | 11947 | 11940 | 92.59% | 25 | 7 | 134 | 0 | 2774 | 879 | 309596671 | 1710080 | 307886591 | 341476829 | 339344319 | -251658 | 280000 | 28342 | 339372661 | 336766566 | 96.3% | 26 | -1697174 | 31880159 | 1962 | 787 | 15 | 528 | 27456255 | 811977 | 10 | 202 | 1738811 | 45932 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 142 | 1852677 | 44154 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 57335 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 29802 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 25 | 879 | 31253854 | 953143
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | 114.8% | 1 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | 96.75% | 1 | -965750 | -115989 | 28 | 37 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 107.4% | 1 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 102.2% | 1 | 5194 | 40000 | 34 | 22 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53
| 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 68.9% | 1 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | 108.3% | 1 | -1735624 | 1811802 | 56 | 35 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q41 | 43516515201 | 2017-02-14 | QTR3 | 16/17 | 4 | 6 | 280 | 520 | 520 | 118.9% | 1 | 0 | 0 | 0 | 187 | 53 | 15839502 | 62339 | 15777163 | 16427426 | 16013444 | -22000 | 0 | -22000 | 15991444 | 16637324 | 105.5% | 1 | 657394 | 587924 | 130 | 57 | 0 | 20 | 279691 | 0 | 0 | 33 | 128973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 463933 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2018-10-31 | QTR2 | 18/19 | 854 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q54 | 43517115201 | 2017-06-06 | QTR4 | 16/17 | 4 | 9 | 315 | 573 | 645 | 144.8% | 0 | -72 | 72 | 0 | 189 | 69 | 16868340 | 150000 | 16718340 | 17223693 | 16580725 | -451756 | 0 | -451756 | 16128969 | 17348378 | 103.8% | 1 | 1219409 | 355352 | 93 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 175352 | 0 | 0 | 0 | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 264477 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-30 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 854 | 18298995
| 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 119.3% | 1 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 107% | 1 | 2296 | 34423 | 37 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26
| 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 102.8% | 1 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 106.9% | 1 | 176726 | 494166 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24
| 08 | E8R46 | 44154915201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 125 | 160 | 160 | 101.6% | 1 | 0 | 0 | 0 | 33 | 2 | 648447 | 32811 | 615636 | 654795 | 614302 | 0 | 0 | 0 | 614302 | 607816 | 98.73% | 1 | -137 | 6348 | 7 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2020-01-10 | QTR3 | 19/20 | 854 | 709931.87
| 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 97.14% | 1 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36
| 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 95.28% | 1 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 101.6% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4
| 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 99.33% | 1 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | 99.14% | 1 | -6566 | 0 | 44 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04
| 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 78% | 1 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | 108.2% | 1 | -1354 | 148560 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 12 | 22 | 55 | 3457 | 4623 | 4394 | #VALUE! | 11 | 229 | 96 | 0 | 962 | 204 | 141708875 | 922708 | 140786166 | 145071462 | 144823490 | -724672 | 2385000 | 1660328 | 146483818 | 145706523 | 100% | 12 | -648412 | 3362586 | 506 | 372 | 0 | 41 | 1363556 | 0 | 68 | 57 | 1491030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 77 | 162246 | 0 | 0 | 0 | 245455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36877 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 202 | 3300268 | 34423
| District 08 Totals |  |  |  |  | 12 | 22 | 55 | 3457 | 4623 | 4394 | 91.67% | 11 | 229 | 96 | 0 | 962 | 204 | 141708875 | 922708 | 140786166 | 145071462 | 144823490 | -724672 | 2385000 | 1660328 | 146483818 | 145706523 | 100% | 12 | -648412 | 3362586 | 506 | 372 | 0 | 41 | 1363556 | 0 | 68 | 57 | 1491030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 77 | 162246 | 0 | 0 | 0 | 245455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 36877 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 202 | 3300268 | 34423
| Statewide Central Let Contracts SubTotal |  |  |  |  | 119 | 243 | 395 | 33872 | 47242 | 45273 | 85.71% | 102 | 1969 | 423 | 0 | 10621 | 2753 | 704900009 | 8631725 | 696268283 | 734064121 | 729054776 | -1512958 | 4820500 | 3307542 | 732362318 | 729724957 | 85.71% | 102 | -1350198 | 29164111 | 6776 | 3095 | 119 | 912 | 10920892 | 16945883 | 434 | 1202 | 9420945 | 1065942 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 44 | 91 | 2276422 | 262983 | 17 | 7 | 337417 | 18355 | 0 | 0 | -78086 | 0 | 0 | 55 | 353666 | 0 | 0 | 399 | 7409206 | 122911 | 136 | 77 | 849300 | 689861 | 0 | 0 | 19973 | 0 | 0 | 0 | -1288956 | 0 | 750 | 2743 | 30254619 | 19105935
| Statewide District Let Contracts SubTotal |  |  |  |  | 112 | 189 | 388 | 41310 | 55699 | 54667 | 87.5% | 98 | 1032 | 1587 | 0 | 10291 | 4098 | 1652605074 | 7599099 | 1645005972 | 1734597268 | 1727495126 | -14663694 | 10930000 | -3733694 | 1723761432 | 1704662401 | 91.96% | 103 | -15917153 | 80459782 | 6391 | 3448 | 155 | 1793 | 44189753 | 1235941 | 123 | 1444 | 24691214 | 1626341 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451000 | 0 | 48 | 627 | 8150946 | 628881 | 111 | 37 | 1804312 | 32366 | 0 | 0 | 0 | 0 | 15 | 7 | 63754 | 0 | 0 | 119 | 1460239 | 34593 | 0 | 38 | 71603 | 53136 | 0 | 32 | 0 | 0 | 0 | 0 | -2011713 | 0 | 452 | 4097 | 78873575 | 3611258
| Statewide Totals |  |  |  |  | 231 | 432 | 783 | 75182 | 102941 | 99940 | 86.58% | 200 | 3001 | 2010 | 0 | 20912 | 6851 | 2357505083 | 16230824 | 2341274255 | 2468661389 | 2456549902 | -16176652 | 15750500 | -426152 | 2456123750 | 2434387358 | 88.74% | 205 | -17267351 | 109623893 | 13167 | 6543 | 274 | 2705 | 55110645 | 18181824 | 557 | 2646 | 34112159 | 2692283 | 0 | 0 | 33297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454000 | 0 | 92 | 718 | 10427368 | 891864 | 128 | 44 | 2141729 | 50721 | 0 | 0 | -78086 | 0 | 15 | 62 | 417420 | 0 | 0 | 518 | 8869445 | 157504 | 136 | 115 | 920903 | 742997 | 0 | 32 | 19973 | 0 | 0 | 0 | -3300669 | 0 | 1202 | 6840 | 109128194 | 22717193

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P56 | 41968815201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-01-19 | 1109997 | 1109997 | 793278 | 0 | 0 | 793278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793278 | 793278 | 0 | 2383057
1 | E1P91 | 42271055201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-04-20 | 10071503 | 10247666 | 9983254 | 176162.86 | 0 | 10182044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9983254 | 10182044 | 198791 | 11091792 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1P94 | 43493915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-18 | 9111251 | 9111251 | 9282956 | 0 | 0 | 9644340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 9289725
1 | E1Q23 | 43665015201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-02-13 | 918123 | 918123 | 868123 | 0 | -104895 | 851629 | -104895 | 0 | 0 | 0 | 0 | 0 | -104895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104895 | 763228 | 851629 | 88401 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
1 | E1Q29 | 42584115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-04-20 | 54145606 | 56232960 | 55752280 | 2087354.08 | 2500000 | 56885286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | -1366994 | 61229521 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R12 | 43668215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-21 | 1472083 | 1472083 | 1445724 | 0 | 65000 | 1446603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 1510724 | 1446603 | -64121 | 1181939 | B1 | ACC - NO EXCUSE BONUS
1 | E1R26 | 43319415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 604486 | 604486 | 584381 | 0 | 0 | 583598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584381 | 583598 | -783 | 489570
1 | E1R46 | 43806315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-19 | 3730005 | 3730005 | 3622277 | 0 | 0 | 3609915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 4986764
1 | E1R51 | 43800815201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-09-20 | 2579000 | 2579000 | 2523711 | 0 | 0 | 2514757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523711 | 2514757 | -8954 | 2698176 | B0 | ACC - LUMP SUM
1 | E1R80 | 43771615201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-04-18 | 157000 | 157000 | 148434 | 0 | 0 | 148434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148434 | 148434 | 0 | 169094
1 | E1S00 | 43943515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-23 | 2112776 | 2112776 | 2088952 | 0 | 0 | 2065283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088952 | 2065283 | -23668 | 3162693 | B0 | ACC - LUMP SUM
1 | T1636 | 43323815201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 1444112 | 1455710 | 1455710 | 11597.86 | 0 | 1456120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 1303711 | B0 | ACC - LUMP SUM
1 | T1664 | 20103265201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-02-22 | 39141064 | 41032774 | 41293102 | 1891709.53 | 2220000 | 42013585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220000 | 0 | 2220000 | 2220000 | 43513102 | 42013585 | -1499517 | 43211573 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1667 | 43494215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-08-31 | 1182957 | 696968 | 671825 | -485989.48 | 0 | 678334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671825 | 678334 | 6509 | 1125231 | B0 | ACC - LUMP SUM
1 | T1671 | 43560615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-07 | 8453536 | 8694533 | 8807307 | 240997 | 0 | 9108126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8807307 | 9108126 | 300819 | 8498514
1 | T1693 | 43450215201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2535000 | 2909249 | 2922189 | 374249.35 | 0 | 2922984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 2562824 | B1 | ACC - NO EXCUSE BONUS
1 | T1697 | 43534915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2532999 | 2582335 | 2599237 | 49336.16 | 0 | 2598348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 2201661
1 | T1701 | 43498615201 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2018-02-28 | 8087167 | 8023343 | 7632042 | -63824.06 | 570000 | 7685776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 0 | 570000 | 570000 | 8202042 | 7685776 | -516267 | 8094282 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1704 | 44011615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 211559 | 211559 | 204310 | 0 | 0 | 204310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204310 | 204310 | 0 | 255658
1 | T1705 | 44013315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 448245 | 448245 | 415980 | 0 | 0 | 415980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415980 | 415980 | 0 | 498435
1 | T1706 | 43658615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 7786066 | 7543630 | 7286083 | -242435.65 | 0 | 7247442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7286083 | 7247442 | -38640 | 9348245
1 | T1707 | 44013815201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 394057 | 401319 | 389400 | 7262.13 | 0 | 389394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 389394 | -6 | 500275
1 | T1713 | 43355215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 2526300 | 2681334 | 2687161 | 155034.01 | 0 | 2585403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2687161 | 2585403 | -101758 | 2797558 | B0 | ACC - LUMP SUM
1 | T1714 | 43837615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 270550 | 270550 | 256893 | 0 | 0 | 256893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256893 | 256893 | 0 | 302948 | B0 | ACC - LUMP SUM
1 | T1729 | 43837415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-08-29 | 985800 | 1045343 | 996037 | 59542.75 | 0 | 995552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996037 | 995552 | -485 | 952403 | B0 | ACC - LUMP SUM
1 | T1732 | 43318515201 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2018-07-25 | 140241 | 140241 | 131642 | 0 | 0 | 131642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1734 | 43498815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 545828 | 545828 | 508665 | 0 | 0 | 508665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508665 | 508665 | 0 | 633612
1 | T1736 | 43320515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 789502 | 789502 | 749000 | 0 | 0 | 749000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749000 | 749000 | 0 | 784219 | B0 | ACC - LUMP SUM
1 | T1737 | 43826915201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 328300 | 328300 | 328300 | 0 | 0 | 328300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328300 | 328300 | 0 | 356575 | B0 | ACC - LUMP SUM
1 | T1738 | 43837115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 870522 | 870522 | 829068 | 0 | 0 | 829068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829068 | 829068 | 0 | 590611
1 | T1741 | 44067415201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 366031 | 366031 | 355572 | 0 | 0 | 355572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355572 | 355572 | 0 | 396011 | B0 | ACC - LUMP SUM
1 | T1743 | 43800415201 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2019-02-27 | 138436 | 138436 | 138436 | 0 | 0 | 138436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138436 | 138436 | 0 | 179133 | B0 | ACC - LUMP SUM
1 | T1749 | 44319925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 335979 | 396256 | 382764 | 60277.25 | 0 | 382764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382764 | 382764 | 0 | 263307
1 | T1753 | 43943215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 1952155 | 1971307 | 1962809 | 19151.94 | 0 | 1962123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962809 | 1962123 | -686 | 2489142 | B0 | ACC - LUMP SUM
2 | E2P14 | 21330435201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2012-05-30 | 148792000 | 165618383 | 165903515 | 16826382.52 | 0 | 164443807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165903515 | 164443807 | -1459708 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2Q20 | 43056515201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-10-10 | 84850000 | 85372612 | 84851152 | 522611.78 | -10428635 | 78818095 | -10329510 | 0 | 0 | 0 | -99125 | 0 | -10428635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10428635 | 74422517 | 78818095 | 4395578 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
2 | E2T34 | 43141825201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-04-15 | 79728458 | 79121474 | 78886236 | -606983.36 | -229932 | 77404693 | -229932 | 0 | 0 | 0 | 0 | 0 | -229932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -229932 | 78656304 | 77404693 | -1251611 | 80350658 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2V70 | 42747515201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-06-14 | 4483000 | 4642146 | 4688789 | 159146.16 | 0 | 4688881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688789 | 4688881 | 92 | 5283434
2 | E2V71 | 43430015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 4908173 | 4938615 | 5152163 | 30442.09 | 0 | 5451119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 4805500
2 | E2V95 | 43617015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 4081125 | 4737826 | 4860165 | 656701.41 | 0 | 4970230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 3223625
2 | E2W35 | 42849115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 2815327 | 2815327 | 2782011 | 0 | 0 | 2782013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 4173997
2 | E2W51 | 20950355201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1735075 | 1731106 | 1623863 | -3969.01 | 0 | 1623865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | 1877622
2 | E2W52 | 42849815201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-03-21 | 730881 | 756196 | 713128 | 25315 | 0 | 713129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713128 | 713129 | 0 | 752278
2 | E2W53 | 42849715201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1093189 | 1093189 | 1034914 | 0 | 0 | 1034914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 1735598
2 | E2W95 | 43402815201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2018-02-21 | 2722348 | 2722348 | 2657208 | 0 | 0 | 2656276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 2383751
2 | E2W96 | 43307515201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-21 | 4411000 | 4455781 | 4414330 | 44781.29 | 0 | 4414364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4414330 | 4414364 | 34 | 4144135
2 | E2X07 | 20956525201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 327059 | 327059 | 288640 | 0 | 0 | 288640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288640 | 288640 | 0 | 337947
2 | E2X15 | 20961685201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-12-20 | 7739999 | 7739999 | 7665781 | 0 | 0 | 7665781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 9122595
2 | E2X44 | 42879715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 1990108 | 2637472 | 2547298 | 647363.36 | 0 | 2542607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2547298 | 2542607 | -4691 | 2271972
2 | E2X58 | 43205415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-18 | 1561255 | 1561255 | 1495849 | 0 | 0 | 1495849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 1989213
2 | E2X60 | 43025915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-08-15 | 1328017 | 1328017 | 1207862 | 0 | 0 | 1207862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207862 | 1207862 | 0 | 1798375
2 | E2X61 | 43496915201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-08-15 | 2118153 | 2118153 | 2024485 | 0 | -33300 | 1991185 | -33300 | 0 | 0 | 0 | 0 | 0 | -33300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33300 | 1991185 | 1991185 | 0 | 2333870
2 | E2X68 | 43500015201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-11-14 | 925745 | 925745 | 888997 | 0 | 0 | 888989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 888997 | 888989 | -8 | 952359
2 | T2562 | 20821175201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-05-20 | 15887487 | 16037487 | 15865517 | 150000 | 0 | 15510573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 16006484
2 | T2576 | 43091115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-17 | 7004346 | 8247072 | 8273395 | 1242726.05 | -350610 | 7827108 | -350610 | 0 | 0 | 0 | 0 | 0 | -350610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350610 | 7922785 | 7827108 | -95677 | 5694357
2 | T2577 | 43245215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-17 | 13015506 | 13328963 | 13247968 | 313457.41 | -129472 | 12926851 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 13118496 | 12926851 | -191646 | 11330021
2 | T2612 | 42360825201 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2241677 | 2241677 | 2217516 | 0 | -20592 | 2204364 | -20592 | 0 | 0 | 0 | 0 | 0 | -20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20592 | 2196924 | 2204364 | 7440 | 1830224
2 | T2618 | 43091015201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 6623070 | 7293436 | 7244868 | 670365.84 | 0 | 7349062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7244868 | 7349062 | 104194 | 5699134
2 | T2657 | 20781825201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 13545525 | 13574913 | 13974107 | 29387.52 | 0 | 14374623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13974107 | 14374623 | 400515 | 16380283 | B6 | ACC - LIQUIDATED SAVINGS
2 | T2658 | 41525215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 7921243 | 8003005 | 8095808 | 81762.66 | 0 | 8111040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 5941070
2 | T2661 | 43433715201 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2017-06-14 | 3381935 | 3744790 | 3805039 | 362855.46 | 0 | 3814801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 2832771
2 | T2679 | 43617415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 10753984 | 10978696 | 11000190 | 224711.7 | 0 | 11198057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000190 | 11198057 | 197867 | 7872133
2 | T2683 | 43616215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 9121503 | 9130119 | 9355463 | 8616 | 0 | 10160460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 10382551
2 | T2686 | 43611815201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2698000 | 2725471 | 2926429 | 27470.55 | 0 | 3007330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 2798351
2 | T2687 | 43617315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 5141768 | 5141768 | 5033451 | 0 | 0 | 5387836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 6618371
2 | T2688 | 43500115201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2018-01-31 | 1688461 | 1754543 | 1709557 | 66082.5 | 0 | 1709557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 1908915
2 | T2689 | 43616115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1995665 | 1995665 | 2049720 | 0 | 0 | 2101020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049720 | 2101020 | 51299 | 2153023
2 | T2691 | 43617215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 13785287 | 13785287 | 14546489 | 0 | 0 | 15202892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14546489 | 15202892 | 656402 | 13297955
2 | T2695 | 43615815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 3836183 | 3889514 | 3691380 | 53331.63 | 0 | 3743642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691380 | 3743642 | 52262 | 3655365
2 | T2704 | 43761615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | 6663346 | 6750120 | 6920369 | 86773.43 | 0 | 6898990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 6878488
2 | T2708 | 44216935201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 368985 | 374417 | 391272 | 5431.58 | 0 | 391272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391272 | 391272 | 0 | 334521
2 | T2718 | 43762115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 2814544 | 2814544 | 2780154 | 0 | 0 | 2750630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 3342179
2 | T2723 | 43762015201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1658214 | 1658214 | 1598015 | 0 | 0 | 1602638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1598015 | 1602638 | 4623 | 2124299
2 | T2727 | 43761215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1634119 | 1634119 | 1569675 | 0 | 0 | 1576127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 1717974
2 | T2730 | 43429715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2680388 | 2680388 | 2824608 | 0 | 0 | 2824608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824608 | 2824608 | 0 | 3620027
3 | E3P84 | 43625815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 1596199 | 1596199 | 1566048 | 0 | 0 | 1618568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 1614268
3 | E3Q52 | 43626715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 2737547 | 2741455 | 2788497 | 3908.32 | 0 | 2937051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2788497 | 2937051 | 148555 | 3367306
3 | E3R04 | 43627115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-06-14 | 819508 | 814776 | 800432 | -4732.46 | 0 | 800432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800432 | 800432 | 0 | 795145
3 | E3R15 | 43730715201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2018-04-12 | 847761 | 847761 | 805000 | 0 | -6660 | 805000 | -6660 | 0 | 0 | 0 | 0 | 0 | -6660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6660 | 798340 | 805000 | 6660 | 968823 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
3 | E3R27 | 40410835201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-04-11 | 497771 | 497771 | 462232 | 0 | 0 | 462232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462232 | 462232 | 0 | 568464
3 | E3R52 | 43627225201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-01-10 | 1432597 | 1438332 | 1321040 | 5734.8 | 0 | 1327923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1321040 | 1327923 | 6884 | 1931231
3 | E3R73 | 43672615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 3019502 | 3096429 | 3191111 | 76927.34 | -1871 | 3252581 | 0 | 0 | 0 | 0 | 0 | -1871 | -1871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1871 | 3189240 | 3252581 | 63342 | 3561779
3 | E3S52 | 41767755201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-05-09 | 551256 | 551256 | 487293 | 0 | 0 | 487293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487293 | 487293 | 0 | 525116
3 | E3S64 | 4453671H201 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-04-16 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | -45000 | 32990
3 | T3471 | 41110225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-05-07 | 15000000 | 15157836 | 15093755 | 157836.02 | -129472 | 13510897 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 14814542
3 | T3485 | 42695315201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 3574230 | 3575445 | 3569976 | 1215 | -104007 | 3477125 | -104007 | 0 | 0 | 0 | 0 | 0 | -104007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104007 | 3465969 | 3477125 | 11156 | 3028499
3 | T3488 | 40979275201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 3595027 | 3663247 | 3527855 | 68219.39 | -36334 | 3407495 | -25884 | 0 | 0 | 0 | 0 | -10450 | -36334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36334 | 3491521 | 3407495 | -84026 | 2839406
3 | T3543 | 22044275201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-30 | 29686177 | 35844062 | 36589864 | 6157885.47 | 0 | 36834177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36589864 | 36834177 | 244313 | 37447264
3 | T3584 | 42551925201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-09-27 | 4956085 | 5007841 | 5206085 | 51755.66 | 0 | 5214960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206085 | 5214960 | 8875 | 4588109
3 | T3586 | 42862415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-06-13 | 4214542 | 4293135 | 4297521 | 78593.87 | 0 | 4292318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4297521 | 4292318 | -5203 | 3958246
3 | T3605 | 43390515201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-09-26 | 2727550 | 2727550 | 2606882 | 0 | 0 | 2599923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 2910808
3 | T3614 | 43228815201 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 776874 | 1103417 | 1178529 | 326542.39 | 0 | 1178529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178529 | 1178529 | 0 | 825049
3 | T3621 | 43626115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 6338519 | 6398946 | 6159928 | 60426.55 | -3625 | 6530080 | 0 | 0 | 0 | 0 | 0 | -3625 | -3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3625 | 6156303 | 6530080 | 373777 | 7711485
3 | T3622 | 43403415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-07-25 | 2343362 | 2350008 | 2309974 | 6645.2 | 0 | 2307395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 1958564
3 | T3633 | 43188335201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-07-25 | 874222 | 874222 | 812103 | 0 | 0 | 809595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 1107452
3 | T3637 | 43626515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 2991030 | 3017543 | 3196659 | 26512.73 | 0 | 3365573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196659 | 3365573 | 168914 | 0
3 | T3639 | 43078915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 5166455 | 5133457 | 5226570 | -32997.52 | 0 | 5560738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5226570 | 5560738 | 334168 | 5944823
3 | T3653 | 43672015201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-08-29 | 628643 | 626435 | 585546 | -2207.95 | 0 | 585546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585546 | 585546 | 0 | 728102
3 | T3655 | 43666315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 7611735 | 8017733 | 8305261 | 405997.54 | 0 | 8626470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8305261 | 8626470 | 321209 | 10033609
3 | T3661 | 43255915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 4168106 | 4195995 | 4262748 | 27889.1 | -3685 | 4316429 | 0 | 0 | 0 | 0 | 0 | -3685 | -3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3685 | 4259063 | 4316429 | 57366 | 3474587
3 | T3662 | 43627215201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 1790850 | 1822098 | 1908732 | 31248.18 | -25175 | 1983720 | 0 | 0 | 0 | 0 | 0 | -25175 | -25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25175 | 1883557 | 1983720 | 100163 | 2014996
3 | T3669 | 43046415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-05-23 | 1257739 | 1467600 | 1481515 | 209861.08 | 0 | 1481051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481515 | 1481051 | -464 | 1150000
3 | T3673 | 43774415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 7942048 | 7802040 | 7940568 | -140007.62 | 0 | 7896410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7940568 | 7896410 | -44158 | 8459567
3 | T3678 | 43627015201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 4020176 | 4016156 | 4196886 | -4020 | 0 | 4189347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196886 | 4189347 | -7539 | 4510562
3 | T3680 | 43815515201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2018-11-14 | 188489 | 188489 | 183577 | 0 | 0 | 183577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183577 | 183577 | 0 | 165102
3 | T3683 | 43774515201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1061000 | 1061000 | 1008572 | 0 | 0 | 1008572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 1142404 | B0 | ACC - LUMP SUM
3 | T3688 | 44038315201 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2019-02-27 | 354899 | 354899 | 344281 | 0 | 0 | 344281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344281 | 344281 | 0 | 390454
4 | E4N84 | 42170735201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-30 | 233756400 | 236000384 | 235981625 | 2243984.17 | 1120000 | 230888919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120000 | 0 | 0 | 0 | 0 | 0 | 1120000 | 1120000 | 237101625 | 230888919 | -6212706 | 224173038 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4N95 | 43316515201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2014-04-28 | 15085307 | 14747115 | 14692678 | -338192.13 | 0 | 14275588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14692678 | 14275588 | -417090 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
4 | E4N98 | 42170745201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-01-17 | 85270000 | 88551488 | 88376026 | 3281487.8 | -266765 | 84860074 | -66765 | 0 | 0 | 0 | 0 | 0 | -66765 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -266765 | 88109261 | 84860074 | -3249187 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P04 | 23193225201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-04-16 | 32540300 | 33830739 | 33682875 | 1290438.6 | -2003878 | 33334508 | -2003878 | 0 | 0 | 0 | 0 | 0 | -2003878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2003878 | 31678997 | 33334508 | 1655512 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q16 | 42170795201 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 5426234 | 5484479 | 5462490 | 58244.76 | 500000 | 5462490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
4 | E4Q35 | 42264135201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-05-06 | 20830000 | 21194238 | 21031285 | 364237.59 | -452157 | 20574388 | -452157 | 0 | 0 | 0 | 0 | 0 | -452157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452157 | 20579128 | 20574388 | -4739 | 20036622 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4Q64 | 43310855201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-05-29 | 153917279 | 162463226 | 162823699 | 8545946.77 | 3720000 | 162834119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3720000 | 0 | 0 | 0 | 0 | 0 | 3720000 | 3720000 | 166543699 | 162834119 | -3709579 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4S21 | 43661715201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-03-03 | 13456789 | 15316896 | 15094846 | 1860106.93 | 0 | 15262674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 15931024 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4S85 | 43609615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-12-01 | 4027310 | 4061212 | 3932814 | 33902.45 | -146172 | 3959283 | -146172 | 0 | 0 | 0 | 0 | 0 | -146172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -146172 | 3786642 | 3959283 | 172641 | 4151810
4 | E4T01 | 43630215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1711929 | 1760237 | 1659334 | 48308 | 0 | 1661623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 1640419
4 | E4T06 | 43977615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1095456 | 1095456 | 1057178 | 0 | 0 | 1059897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 1077515
4 | E4T43 | 43686915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-02-01 | 483248 | 483248 | 462927 | 0 | 0 | 462927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462927 | 462927 | 0 | 584334
4 | E4T47 | 43995915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 874745 | 874745 | 827255 | 0 | 0 | 827255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827255 | 827255 | 0 | 2440132
4 | E4T48 | 43215315201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 1579388 | 1579388 | 1522923 | 0 | 0 | 1522923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 1500208
4 | E4T53 | 44145715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-02-01 | 373586 | 373586 | 320740 | 0 | 0 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320740 | 320740 | 0 | 838047
4 | T4418 | 22989615201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-07-29 | 17423228 | 17585616 | 15704340 | 162388.39 | 0 | 15621918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15704340 | 15621918 | -82422 | 22527836
4 | T4423 | 23033845201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 23950804 | 24148938 | 23087444 | 198133.26 | 0 | 23548540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23087444 | 23548540 | 461096 | 30953648
4 | T4433 | 42872415201 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2016-04-27 | 16224277 | 17235975 | 16795691 | 1011697.84 | -110980 | 16825397 | -46980 | 0 | 0 | 0 | 0 | 0 | -46980 | -64000 | 0 | 0 | 0 | 0 | 0 | -64000 | -110980 | 16684711 | 16825397 | 140685 | 14991648 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4444 | 43270515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 27999900 | 28775420 | 29356382 | 775520.05 | 0 | 30081989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29356382 | 30081989 | 725606 | 34103306
4 | T4452 | 43166615201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-25 | 3407245 | 3524212 | 3504637 | 116966.98 | 0 | 3574050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504637 | 3574050 | 69412 | 3478134
4 | T4454 | 43427315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 17184517 | 17260367 | 15228075 | 75850.52 | -427518 | 15656209 | -427518 | 0 | 0 | 0 | 0 | 0 | -427518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -427518 | 14800557 | 15656209 | 855652 | 16678233 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4465 | 42793815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 6772377 | 6937715 | 6616077 | 165337.71 | 0 | 6805105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616077 | 6805105 | 189028 | 7354282
4 | T4467 | 42872815201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 6194382 | 6727999 | 7014661 | 533617.21 | 0 | 7145526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7014661 | 7145526 | 130865 | 6773142 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4470 | 43467915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2654817 | 2648641 | 2595600 | -6176.03 | 0 | 2595444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | 2954451
4 | T4474 | 43516015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4025071 | 4333347 | 4067792 | 308276.21 | 0 | 4150827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 3559044
4 | T4478 | 43206645201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 3159876 | 3207501 | 3126761 | 47624.42 | 0 | 3121903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 3633553
4 | T4480 | 43166515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 1327221 | 1366521 | 1298578 | 39300 | 0 | 1298125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1298578 | 1298125 | -453 | 1330304
4 | T4486 | 43165715201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 3260393 | 3609674 | 3402444 | 349281.5 | 0 | 3396789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3402444 | 3396789 | -5656 | 3504742
4 | T4492 | 43783715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 1180804 | 1180804 | 1088706 | 0 | 0 | 1092749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 1254760
4 | T4493 | 43622615201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 913324 | 925193 | 862461 | 11868.69 | 0 | 863741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 983072
5 | BE626 | 43787225201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-05-24 | 720000 | 720000 | 720000 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 720000 | 0 | 720000
5 | E5W11 | 24262635201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-11-21 | 43150089 | 45682181 | 45886261 | 2532092.15 | 0 | 43252523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45886261 | 43252523 | -2633738 | 48952302 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
5 | E5W31 | 43360715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-08-04 | 11820000 | 11432846 | 11217159 | -387153.56 | -379168 | 10378129 | -379168 | 0 | 0 | 0 | 0 | 0 | -379168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -379168 | 10837991 | 10378129 | -459862 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y20 | 42690435201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-11-04 | 26771800 | 27777188 | 27684932 | 1005388.19 | 0 | 28129118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27684932 | 28129118 | 444186 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Y33 | 43693715201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2016-09-07 | 1750000 | 3113962 | 3063962 | 1363961.88 | 0 | 3065413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1325842
5 | E5Y34 | 43744415201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | 793972 | 793962 | 623055 | -9.51 | 0 | 624995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623055 | 624995 | 1940 | 843684
5 | E5Z02 | 43365415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-02-06 | 1457258 | 1507258 | 1490649 | 50000 | -1099 | 1488755 | 0 | 0 | 0 | 0 | 0 | -1099 | -1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1099 | 1489550 | 1488755 | -795 | 1508169
5 | E5Z09 | 41299445214 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-12-14 | 5757000 | 5860741 | 5841571 | 103740.91 | 0 | 5844608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841571 | 5844608 | 3037 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Z21 | 43927015201 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 3175000 | 3175000 | 3125000 | 0 | 0 | 3125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 2594655
5 | E5Z23 | 43564715201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-01 | 1013390 | 1008318 | 958318 | -5071.91 | -736 | 957220 | 0 | 0 | 0 | 0 | 0 | -736 | -736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -736 | 957582 | 957220 | -362 | 1052401
5 | E5Z25 | 43685515201 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-07-03 | 1405000 | 1538799 | 1482098 | 133798.84 | 0 | 1478901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 1340492
5 | E5Z44 | 43945315201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-06 | 406627 | 439983 | 417356 | 33356.49 | -11169 | 406187 | -11169 | 0 | 0 | 0 | 0 | 0 | -11169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11169 | 406187 | 406187 | 0 | 480184
5 | E5Z45 | 43733915201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-11-06 | 6123814 | 6203979 | 6135165 | 80165.9 | 0 | 6020689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6135165 | 6020689 | -114476 | 8194285
5 | E5Z47 | 43759915201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2018-12-04 | 490000 | 490000 | 469000 | 0 | 0 | 469000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469000 | 469000 | 0 | 441431
5 | E5Z48 | 44096715201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 476422 | 476422 | 521373 | 0 | 0 | 521373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521373 | 521373 | 0 | 443061
5 | E5Z49 | 44255515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-12-04 | 1193299 | 1193299 | 1111517 | 0 | 0 | 1111517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 1054473
5 | E5Z52 | 44116715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-10-02 | 679222 | 682222 | 665592 | 3000 | 0 | 665592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665592 | 665592 | 0 | 321983
5 | E5Z60 | 44096815201 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 471366 | 471366 | 417692 | 0 | 0 | 417692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417692 | 417692 | 0 | 554880
5 | E5Z76 | 44097015201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2019-06-04 | 167070 | 167070 | 148419 | 0 | 0 | 148419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148419 | 148419 | 0 | 271247
5 | T5469 | 23920345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-10-30 | 67881735 | 71458538 | 71806238 | 3576803.2 | -56415 | 68693588 | 0 | 0 | 0 | 0 | 0 | -56415 | -56415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56415 | 71749823 | 68693588 | -3056235 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5572 | 43505615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 6749945 | 6768976 | 6749146 | 19031.04 | 30000 | 6749146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
5 | T5588 | 43505915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 5555556 | 5555556 | 5533602 | 0 | 14500 | 5533602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0 | 0 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 7289680
5 | T5591 | 42823815201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 16694356 | 16972569 | 16490950 | 278213.07 | 0 | 16700809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16490950 | 16700809 | 209859 | 15183627
5 | T5601 | 43565815201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4858677 | 5019991 | 4911820 | 161313.66 | 0 | 5177234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 6733492
5 | T5616 | 43065515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 4231483 | 4229830 | 4248590 | -1652.68 | 0 | 4402057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4248590 | 4402057 | 153467 | 5394340
5 | T5617 | 43505815201 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 3824000 | 3850406 | 3817535 | 26405.77 | 0 | 3817535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 4905410
5 | T5619 | 24099275201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-08-30 | 1769311 | 1789505 | 1708324 | 20194.25 | 0 | 1715061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 1940871
5 | T5623 | 43239915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-07-25 | 1897288 | 1897714 | 1910437 | 426.04 | 0 | 1905492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 2057026
6 | E6J52 | 43337815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-06-09 | 8960958 | 9028019 | 8935693 | 67061.69 | 0 | 8936706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8935693 | 8936706 | 1013 | 6643198
6 | E6J69 | 43492215201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2016-04-15 | 69547000 | 72886197 | 72551371 | 1806784.32 | 0 | 73200931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72551371 | 73200931 | 649560 | 125147000 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K58 | 43081315201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-31 | 1100030 | 1101649 | 1024191 | 1618.97 | 100000 | 1026756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1124191 | 1026756 | -97435 | 1216039 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K59 | 41831225201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-07-28 | 9488820 | 10556288 | 10367176 | 1067467.64 | 400000 | 10409054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 10767176 | 10409054 | -358123 | 9121391 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K87 | 43654015201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2018-11-29 | 342215 | 342215 | 303600 | 0 | 0 | 303600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303600 | 303600 | 0 | 394432
6 | E6K89 | 43653615201 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 512803 | 536803 | 517303 | 24000 | 0 | 517303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517303 | 517303 | 0 | 404500
6 | E6L26 | 43653515201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-29 | 878038 | 878038 | 768146 | 0 | 0 | 768146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768146 | 768146 | 0 | 1044218
6 | E6L27 | 43081725201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 1584337 | 1584337 | 1427013 | 0 | 0 | 1426855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 1676992
6 | E6L37 | 42919325201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-01-25 | 1491900 | 1633114 | 1580093 | 141214.05 | 60000 | 1579918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 1640093 | 1579918 | -60174 | 1421302 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6L83 | 44124315201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-26 | 626626 | 626626 | 577033 | 0 | 0 | 576947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577033 | 576947 | -87 | 611516
6 | E6L91 | 44203915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 1590779 | 1590779 | 1534205 | 0 | 0 | 1533853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 1335462
6 | T6337 | 41809115201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 14239526 | 16636939 | 16898897 | 2397413.06 | 500000 | 16945020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 17398897 | 16945020 | -453877 | 13498168 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6338 | 41463315201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 11118409 | 12716281 | 13284136 | 1597872.07 | 0 | 13403183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284136 | 13403183 | 119047 | 10197839 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6344 | 24994145201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2014-06-25 | 20865766 | 21591091 | 20515283 | 725324.32 | 0 | 20078878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 22059625 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6382 | 40561535201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 32827940 | 33204392 | 33258885 | 376451.27 | 1000000 | 33636224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 34258885 | 33636224 | -622662 | 32661597 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6401 | 41247395201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-03-29 | 3499047 | 5529305 | 5890497 | 2030258.17 | 0 | 5896369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890497 | 5896369 | 5872 | 3269401 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6403 | 43348915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 2123570 | 2145473 | 2165968 | 21903 | 0 | 2187405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 2459954
6 | T6406 | 42902215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-04-25 | 3211923 | 3249863 | 3270531 | 37940 | 190000 | 3268888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 3370172 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6419 | 42827825201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 2865340 | 2945587 | 2727466 | 80246.87 | 110000 | 2776404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 2918720 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6436 | 43631115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1387410 | 1479864 | 1353258 | 92453.79 | 0 | 1354735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 1750082
6 | T6437 | 43634215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 1789134 | 1789134 | 1742305 | 0 | 0 | 1738184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 2085360
6 | T6438 | 43117015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 3669797 | 3847108 | 3668181 | 177311.22 | 250000 | 3697899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 3918181 | 3697899 | -220283 | 4444325 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6448 | 43792015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-07-25 | 796960 | 796960 | 710116 | 0 | 0 | 708837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 867454
6 | T6451 | 42563725201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-31 | 666806 | 666806 | 585572 | 0 | 0 | 584459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 654200
6 | T6462 | 43792215201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-07-25 | 672522 | 672522 | 627588 | 0 | 0 | 627091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627588 | 627091 | -497 | 724071
6 | T6467 | 44289715201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-10-31 | 127677 | 127677 | 111887 | 0 | 0 | 111863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111887 | 111863 | -24 | 324690
7 | E7H90 | 25693125201 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2012-11-01 | 82889000 | 85277357 | 85130335 | 2388356.86 | 0 | 83668918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85130335 | 83668918 | -1461417 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7K19 | 43476515201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-10-20 | 35360313 | 59863754 | 59642810 | 24503441.21 | 0 | 59642810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59642810 | 59642810 | 0 | 35360313
7 | E7K24 | 41101145201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-04-09 | 94976100 | 96934830 | 96454835 | 1958729.51 | 0 | 96195352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96454835 | 96195352 | -259483 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | E7L26 | 40552525201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-08 | 25833397 | 27246296 | 27221715 | 1412898.86 | 250000 | 27205803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 27471715 | 27205803 | -265912 | 23085355 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7L58 | 43243415201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-10 | 5500000 | 5732401 | 5687839 | 232401.07 | 0 | 5688140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 4546054
7 | E7L77 | 42292935201 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2017-09-19 | 5595578 | 5595578 | 5582332 | 0 | -3645 | 5581090 | -3645 | 0 | 0 | 0 | 0 | 0 | -3645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3645 | 5578687 | 5581090 | 2402 | 3505311
7 | E7L98 | 43763715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 2248889 | 2248889 | 2169580 | 0 | 0 | 2169580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 2125000
7 | E7M00 | 42292945201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-05-09 | 3873725 | 4070777 | 4079959 | 197052.15 | 0 | 4074029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 5390437
7 | E7M06 | 44033815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 5327001 | 5327001 | 5287802 | 0 | -68940 | 5204437 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5218862 | 5204437 | -14425 | 6993269
7 | E7M26 | 25839935201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-12-12 | 1194104 | 1194104 | 1177035 | 0 | 0 | 1177035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177035 | 1177035 | 0 | 850000
7 | E7M27 | 43648015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-12 | 1274649 | 1382195 | 1318471 | 107546.16 | 0 | 1320688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318471 | 1320688 | 2217 | 980000
7 | E7M30 | 43755215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-13 | 167797 | 167797 | 136656 | 0 | 0 | 136656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136656 | 136656 | 0 | 175000
7 | E7M32 | 43751815201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-03-13 | 852730 | 852730 | 751999 | 0 | 0 | 752000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751999 | 752000 | 1 | 850000
7 | E7R06 | 44008915201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-08-22 | 1947000 | 1947000 | 1708144 | 0 | 0 | 1708144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R07 | 43845015201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-05 | 2568748 | 2568748 | 2497748 | 0 | 0 | 2497782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497748 | 2497782 | 34 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R60 | 43920615201 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2017-09-07 | 12005445 | 12159938 | 12017053 | 154492.99 | 30000 | 12085790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 12047053 | 12085790 | 38737 | 11747696 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
7 | T7389 | 43272015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 12988889 | 13889049 | 13996342 | 900160.08 | 0 | 14109139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13996342 | 14109139 | 112797 | 14634544
7 | T7391 | 43269815201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 1680691 | 1699042 | 1672177 | 18351.56 | -177408 | 1505964 | -177408 | 0 | 0 | 0 | 0 | 0 | -177408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -177408 | 1494769 | 1505964 | 11195 | 1603400
7 | T7398 | 43473015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-25 | 2979236 | 2979236 | 2852469 | 0 | 0 | 2921837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 3840000
7 | T7399 | 43653015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-01-31 | 1314062 | 1314062 | 1279715 | 0 | -1665 | 1277840 | -1665 | 0 | 0 | 0 | 0 | 0 | -1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1665 | 1278050 | 1277840 | -210 | 1374961
7 | T7401 | 43480615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-03-28 | 2932563 | 2939291 | 2859109 | 6728.39 | 0 | 2924621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 3343300
7 | T7404 | 43642015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1081175 | 1081175 | 1016734 | 0 | 0 | 1023706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 1150000 | B0 | ACC - LUMP SUM
7 | T7409 | 43649115202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-23 | 1575996 | 1575996 | 1509644 | 0 | 0 | 1509644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 1415000
7 | T7415 | 43982935201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 497590 | 497590 | 430440 | 0 | 0 | 430440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430440 | 430440 | 0 | 590001
7 | T7422 | 44275215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 96675 | 96675 | 89884 | 0 | 0 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89884 | 89884 | 0 | 182731
7 | T7427 | 43704015201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1130856 | 1130856 | 1101423 | 0 | 0 | 1102091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101423 | 1102091 | 668 | 1234500
7 | T7429 | 43753015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-03-27 | 1704462 | 1704462 | 1672069 | 0 | 0 | 1672069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1672069 | 1672069 | 0 | 2200000
8 | E8N19 | 42935015201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-05-14 | 42645454 | 42529465 | 42335775 | -115989.17 | -256416 | 41113609 | -188916 | 0 | 0 | 0 | 0 | -22500 | -211416 | -45000 | 0 | 0 | 0 | 0 | 0 | -45000 | -256416 | 42079359 | 41113609 | -965750 | 44879640 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8P81 | 43561415201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-05-10 | 2564262 | 2604262 | 2577346 | 40000 | 0 | 2582540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 2264808
8 | E8Q39 | 43730015201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-04-11 | 42528000 | 44339802 | 45313329 | 1811801.94 | 2430000 | 46007705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430000 | 0 | 0 | 0 | 0 | 0 | 2430000 | 2430000 | 47743329 | 46007705 | -1735624 | 52100636 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8Q41 | 43516515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-02-14 | 15839502 | 16427426 | 16013444 | 587923.78 | -22000 | 16648838 | 0 | 0 | 0 | 0 | 0 | -22000 | -22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | 15991444 | 16648838 | 657394 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8Q54 | 43517115201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-06-06 | 16868340 | 17223693 | 16580725 | 355352.22 | -451756 | 17348378 | -338256 | 0 | 0 | 0 | 0 | -113500 | -451756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -451756 | 16128969 | 17348378 | 1219409 | 18298995
8 | E8Q91 | 43915315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 1568431 | 1602854 | 1622457 | 34422.76 | 0 | 1624753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 1431341
8 | E8R18 | 43652115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-05-31 | 11208613 | 11702780 | 11690102 | 494166.31 | -20000 | 11846829 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 11670102 | 11846829 | 176726 | 12719348
8 | E8R46 | 44154915201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-03-12 | 648447 | 654795 | 614302 | 6348.32 | 0 | 614165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614302 | 614165 | -137 | 709932
8 | E8R56 | 44290165201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-16 | 994137 | 994137 | 967509 | 0 | 0 | 967509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967509 | 967509 | 0 | 805668
8 | E8R57 | 44290175201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 679823 | 679823 | 674133 | 0 | -9500 | 664633 | 0 | 0 | 0 | 0 | 0 | -9500 | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9500 | 664633 | 664633 | 0 | 820726
8 | E8R59 | 44290185201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1646521 | 1646521 | 1599372 | 0 | -10000 | 1582806 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 1589372 | 1582806 | -6566 | 1947436
8 | E8R64 | 44263115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4517345 | 4665904 | 4834996 | 148559.58 | 0 | 4833642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 1860603

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [7 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total
01 |  | 113818.45 | 0 | 20912.84 | 0 | 7360.64 | 142091.93 |  | 167478236 | 0.08045% | 134731.29
02 |  | 172292.4 |  | 127257.02 | 121590.05 | 1566114.94 | 1987254.41 |  | 492531182 | 0.08551% | 421139.47
03 |  | 10902.79 |  | 8287.64 | 15866927 | 106861.34 | 15992978.77 |  | 122814899 | 12.94% | 15886117.43
04 | 1760 | 254283.42 | 43243.5 | 18170.9 | 163668.68 | 724213.36 | 1205339.86 |  | 706106207 | 0.06814% | 481126.5
05 |  | 185508.25 | 2422 | 24707.31 | 12617.83 | 275555.47 | 500810.86 |  | 221283680 | 0.1018% | 225255.39
06 |  | 1087789.16 |  | 11499.52 | 911286.69 | 462922.85 | 2473498.22 |  | 195985333 | 1.026% | 2010575.37
07 |  | 36742.37 | 27282.91 | 106098.17 | 858180.72 | 195151.58 | 1223455.75 |  | 309596671 | 0.3321% | 1028304.17
08 |  | 0 |  |  | 34422.76 | 0 | 34422.76 |  | 141708875 | 0.02429% | 34422.76
Grand Total | 1760 | 1861336.84 | 72948.41 | 316933.4 | 17968693.73 | 3338180.18 | 23559852.56 |  | 2357505083 | 0.8578% | 20221672.38
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days SA
01 |  | 173 | 0 | 0 | 0 | 365 | 538 |  | 173
02 |  | 273 |  | 67 | 119 | 2003 | 2462 |  | 459
03 |  | 16 |  | 0 | 59 | 213 | 288 |  | 75
04 | 5 | 45 | 43 | 33 | 30 | 974 | 1130 |  | 156
05 |  | 28 | 0 | 2 | 10 | 746 | 786 |  | 40
06 |  | 82 |  | 0 | 81 | 401 | 564 |  | 163
07 |  | 39 | 0 | 96 | 53 | 691 | 879 |  | 188
08 |  | 10 |  |  | 27 | 167 | 204 |  | 37
Grand Total | 5 | 666 | 43 | 198 | 379 | 5560 | 6851 |  | 1291
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 |  | 28 |  | 5 |  | 37 | 70 | 33 | 206 | 7503 | 2.746%
02 |  |  |  |  | 53 | 276 | 329 | 53 | 512 | 13566 | 3.774%
03 |  | 45 |  | 39 | 10 | 196 | 290 | 94 | 169 | 6289 | 2.687%
04 | [5 empty] | 2 | 2 | 0 | 156 | 17725 | 0.8801%
05 | [5 empty] | 11 | 11 | 0 | 40 | 9666 | 0.4138%
06 |  | 264 |  |  | 69 | 58 | 391 | 333 | 496 | 8682 | 5.713%
07 | [5 empty] | 25 | 25 | 0 | 188 | 8294 | 2.267%
08 | [5 empty] | 84 | 84 | 0 | 37 | 3457 | 1.07%
Grand Total |  | 337 |  | 44 | 132 | 689 | 1202 | 513 | 1804 | 75182 | 2.4%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P91 | 42271055201 | 009 | 2 |  | 1 | 919 | 18000.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required
01 | E1P91 | 42271055201 | 016 | 2 |  | 1 | 108 | 17200.74 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1P91 | 42271055201 | 036 | 2 |  | 1 | 001 | 24038.17 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1P91 | 42271055201 | 038 | 2 |  | 1 | 106 | 3792.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P91 | 42271055201 | 038 | 2 |  | 2 | 128 | 3792.02 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 | 046 | 2 |  | 1 | 001 | 30647.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1P91 | 42271055201 | 047 | 2 |  | 1 | 126 | 78691.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 001 | 2 |  | 1 | 305 | -383908.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 006 | 2 |  | 1 | 001 | 405680 | 84392.56 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 007 | 2 |  | 1 | 101 | -292.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 013 | 2 |  | 1 | 003 | 1373071.3 | 0 | 0 |  | N | 208 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 1 | 115 | 11250.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 2 | 128 | 37364.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 3 | 107 | 13430.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 4 | 101 | 42999 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 5 | 105 | 4377.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 6 | 003 | 13393.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 024 | 2 |  | 1 | 001 | 125640.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 026 | 2 |  | 1 | 007 | 13725.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 029 | 2 |  | 1 | 503 | 18962.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 029 | 2 |  | 2 | 118 | 16897.85 | 4387.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 033 | 2 |  | 1 | 004 | 167069.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 036 | 2 |  | 1 | 103 | 41332.83 | 0 | 0 |  | N | 114 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 037 | 2 |  | 1 | 118 | 41926.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 039 | 2 |  | 1 | 502 | 14313.64 | 14313.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 039 | 2 |  | 2 | 112 | 14693.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 039 | 2 |  | 3 | 503 | -6126.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 039 | 2 |  | 4 | 007 | 4379.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 039 | 2 |  | 5 | 007 | 14989.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1636 | 43323815201 | 008 | 2 |  | 1 | 001 | 11597.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 005 | 2 |  | 1 | 112 | 5550 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 005 | 2 |  | 2 | 007 | -6645.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1664 | 20103265201 | 010 | 2 |  | 1 | 101 | 12870 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 015 | 2 |  | 1 | 919 | 61398.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 017 | 2 |  | 1 | 305 | -250655.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 1 | 012 | 11241.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 | 018 | 2 | 850 | 2 | 101 | 3746.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 3 | 107 | 5928.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 4 | 107 | 1619.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 5 | 112 | 1162.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 6 | 107 | 1619.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 7 | 022 | 4823.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 8 | 105 | 23626.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 9 | 115 | 9747.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 10 | 101 | 4544.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 11 | 101 | 721.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 1 | 105 | 82510 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 2 | 112 | 531.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 3 | 115 | 264.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 025 | 2 |  | 1 | 001 | 127697.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 026 | 2 |  | 1 | 001 | 97037.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 029 | 2 |  | 1 | 001 | 106486.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 030 | 2 |  | 1 | 001 | 74476.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 035 | 2 |  | 1 | 001 | 45733.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 036 | 2 |  | 1 | 922 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 037 | 2 |  | 1 | 001 | 14686.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 039 | 2 |  | 1 | 107 | 962861.32 | 0 | 1 |  | N | 120 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 1 | 105 | 33305.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 2 | 112 | 35452.32 | 4957.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 041 | 2 |  | 1 | 103 | 89278.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1664 | 20103265201 | 042 | 2 |  | 1 | 001 | 53578.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 046 | 2 |  | 1 | 004 | 21015.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1664 | 20103265201 | 047 | 2 |  | 1 | 001 | 10243.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 048 | 2 |  | 1 | 015 | -82748.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 049 | 2 |  | 1 | 015 | 293617.71 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 050 | 2 |  | 1 | 101 | 3163.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1667 | 43494215201 | 003 | 2 |  | 1 | 503 | -485989.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 011 | 2 |  | 1 | 919 | 42077.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 012 | 2 |  | 1 | 918 | 1398.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 015 | 2 |  | 1 | 004 | 7230.22 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1671 | 43560615201 | 020 | 2 |  | 1 | 001 | 8178.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 025 | 2 |  | 1 | 115 | 11373.34 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 029 | 2 | 850 | 1 | 023 | 220.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 029 | 2 | 850 | 2 | 001 | 52335.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 033 | 2 |  | 1 | 001 | 66893.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 040 | 2 |  | 1 | 004 | 11821.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1671 | 43560615201 | 043 | 2 |  | 1 | 115 | 9237.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 043 | 2 |  | 2 | 001 | 22786.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1693 | 43450215201 | 011 | 2 |  | 1 | 117 | 2919.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1693 | 43450215201 | 014 | 2 |  | 1 | 115 | 17352.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1693 | 43450215201 | 014 | 2 |  | 2 | 700 | 9647 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1693 | 43450215201 | 023 | 2 |  | 1 | 009 | 49706.91 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 024 | 2 |  | 1 | 007 | 2400 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1693 | 43450215201 | 028 | 2 |  | 1 | 009 | 97115.34 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 029 | 2 |  | 1 | 001 | 83565.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1693 | 43450215201 | 030 | 2 |  | 1 | 009 | 95480.95 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 031 | 2 |  | 1 | 001 | 16061.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1697 | 43534915201 | 011 | 2 |  | 1 | 101 | -2580.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1697 | 43534915201 | 011 | 2 |  | 2 | 105 | 51917.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1701 | 43498615201 | 007 | 2 |  | 1 | 113 | -81037.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | T1701 | 43498615201 | 011 | 2 |  | 1 | 503 | 7224.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1701 | 43498615201 | 019 | 2 |  | 1 | 923 | 9988.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1706 | 43658615201 | 003 | 2 |  | 1 | 305 | -242435.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1707 | 44013815201 | 002 | 2 |  | 1 | 101 | 7262.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1713 | 43355215201 | 018 | 2 |  | 1 | 003 | 58401.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1713 | 43355215201 | 021 | 2 |  | 1 | 115 | 96632.78 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Drainage Modification | Plan Modifications | 2
01 | T1729 | 43837415201 | 002 | 2 |  | 1 | 117 | 59542.75 | 1350 | 1 |  | N | 0 | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1749 | 44319925201 | 005 | 2 |  | 1 | 103 | 60277.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1753 | 43943215201 | 004 | 2 |  | 1 | 126 | 19151.94 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
02 | E2P14 | 21330435201 | 001 | 2 |  | 1 | 119 | 9007933 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 002 | 2 |  | 1 | 008 | 34432.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 003 | 2 |  | 1 | 107 | 335329.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 004 | 2 |  | 1 | 008 | 35852.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 005 | 2 |  | 1 | 008 | 1018305.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 1 | 008 | 24819.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 2 | 350 | 16500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 3 | 119 | 107859.75 | 107859.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 4 | 008 | 769.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 5 | 008 | 51.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 007 | 2 |  | 1 | 008 | 91959.33 | 50678.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 008 | 2 |  | 1 | 119 | 240297.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 009 | 2 |  | 1 | 012 | 82871.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 1 | 119 | 134858.4 | 134858.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 2 | 012 | 15141.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 041 | 2 |  | 1 | 107 | 71091.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 048 | 2 |  | 1 | 008 | 234097.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 057 | 2 |  | 1 | 106 | 378046.76 | 378046.76 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 4 | 107 | 9637.19 | 9637.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 5 | 004 | 68634.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 6 | 012 | 26194.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 7 | 107 | 2623.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 8 | 008 | 7646.81 | 7646.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 9 | 012 | 2190.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 10 | 012 | 2491.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 11 | 350 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 12 | 012 | 935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 13 | 016 | 9846.33 | 9846.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 1 | 116 | 50933.24 | 50933.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 2 | 001 | 11645.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 3 | 018 | 14242.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 4 | 107 | 1378.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 5 | 008 | 4106.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 6 | 107 | 3916.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 7 | 107 | 2167.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 8 | 107 | 1355.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 9 | 119 | 52255.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 10 | 350 | 7998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 088 | 2 |  | 1 | 107 | 328688.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 094 | 2 |  | 1 | 107 | 2920117.97 | 0 | 0 |  | N | 152 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 098 | 2 |  | 1 | 012 | 28016.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 099 | 2 |  | 1 | 018 | 66169.53 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 102 | 2 |  | 1 | 917 | 54727.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 115 | 2 |  | 1 | 107 | 28829.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 115 | 2 |  | 2 | 003 | -10699.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 118 | 2 |  | 1 | 107 | 41480.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 119 | 2 |  | 1 | 116 | 149447.45 | 149447.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 1 | 350 | 5201.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 2 | 107 | 19858.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 3 | 107 | 9972.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 4 | 107 | 33966.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 5 | 012 | 17083.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 6 | 012 | 22540.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 7 | 122 | 3442.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 8 | 012 | 517.91 | 517.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 9 | 107 | -425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 10 | 120 | 2758.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 11 | 107 | 2156.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 12 | 107 | 2183.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 13 | 008 | 18841.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 14 | 012 | 11900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 122 | 2 |  | 1 | 019 | 180676.52 | 35226.03 | 0 |  | N | 110 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 1 | 008 | 185154.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 2 | 004 | -65070.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 132 | 2 |  | 1 | 919 | 153275.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 138 | 2 |  | 1 | 503 | 106762.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 138 | 2 |  | 2 | 305 | -18218.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 141 | 2 |  | 1 | 116 | 103438.51 | 0 | 0 |  | N | 132 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 1 | 350 | 26400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 2 | 107 | 6699.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 3 | 115 | 14880.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 4 | 003 | 2019.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 1 | 012 | 74208.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 2 | 008 | 191599.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 3 | 107 | 4680.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 4 | 107 | 1368.26 | 1368.26 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 5 | 107 | -252327.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 6 | 113 | -20345.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 1 | 003 | 5488.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 2 | 012 | 17083.6 | 17083.6 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 3 | 012 | 5886.77 | 5886.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 4 | 503 | 561.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 5 | 107 | 1642.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 6 | 012 | 4880.88 | 4880.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 158 | 2 |  | 1 | 115 | 194183.28 | 76566.34 | 0 |  | N | 138 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 1 | 305 | -18243.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 2 | 305 | -202219.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 3 | 305 | -43521.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 4 | 305 | -7517.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 027 | 2 |  | 1 | 007 | 332736.87 | 0 | 5 |  | N | 28 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 1 | 350 | 448.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 3 | 007 | 47220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 8 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 10 | 007 | 5912.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 14 | 007 | 3585.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 15 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 16 | 004 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 19 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 20 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 21 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 22 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 23 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 24 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 25 | 350 | 226.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 26 | 013 | 2714.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 27 | 004 | 22282.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 28 | 107 | 3810.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 035 | 2 |  | 1 | 004 | -60081.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 041 | 2 |  | 1 | 105 | 14220.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 048 | 2 |  | 1 | 503 | -16004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 1 | 350 | 1973.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 3 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 4 | 350 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 8 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 10 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 050 | 2 |  | 1 | 503 | 30068.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 051 | 2 |  | 1 | 007 | 120878.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 053 | 2 |  | 1 | 115 | 72295.4 | 0 | 0 |  | N | 105 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 1 | 004 | 11904.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 2 | 012 | 34522.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T34 | 43141825201 | 012 | 2 |  | 1 | 007 | -992697 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2T34 | 43141825201 | 016 | 2 |  | 1 | 015 | 28348.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 021 | 2 |  | 1 | 917 | 63655.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 023 | 2 |  | 1 | 015 | 48247.54 | 0 | 5 |  | N | 7 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 029 | 2 |  | 1 | 919 | 95462.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 038 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 231 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2U38 | 43226615201 | 007 | 2 |  | 1 | 015 | 35250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 | 012 | 2 | 850 | 1 | 015 | 40303.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V70 | 42747515201 | 016 | 2 |  | 1 | 004 | 4312.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V70 | 42747515201 | 022 | 2 | 850 | 1 | 112 | 4761.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 | 022 | 2 | 850 | 2 | 112 | 1341.48 | 1341.48 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 | 033 | 2 |  | 2 | 860 | 41531.42 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | E2V70 | 42747515201 | 033 | 2 |  | 3 | 860 | 63301.94 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | E2V71 | 43430015201 | 005 | 2 |  | 1 | 101 | 11273.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 1 | 115 | 13591.19 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 2 | 107 | 5577 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 005 | 2 |  | 1 | 001 | 65939 | 0 | 2 |  | N | 5 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 1 | 012 | 25041.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 2 | 122 | 12630.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 3 | 012 | 7092.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 4 | 105 | 5236 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 1 | 105 | 11908.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 2 | 012 | 16133.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 4 | 107 | 6033.41 | 6033.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 5 | 105 | 4141.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 6 | 001 | 8937.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 7 | 105 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 023 | 2 |  | 1 | 001 | 174752.34 | 107016.17 | 2 |  | N | 59 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 023 | 2 |  | 2 | 119 | 135900.42 | 135900.42 | 0 |  | N | 37 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 1 | 119 | 163953.52 | 163953.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 2 | 119 | 10521.77 | 3960 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 3 | 122 | 5634.36 | 5634.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 1 | 305 | -60481.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 2 | 503 | 41803.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 3 | 503 | -17432.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 4 | 503 | 32141.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W52 | 42849815201 | 005 | 2 | 850 | 1 | 012 | 13286.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 | 008 | 2 |  | 1 | 503 | 44781.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X44 | 42879715201 | 003 | 2 |  | 1 | 015 | 139617.91 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 007 | 2 |  | 1 | 015 | 461586.77 | 0 | 0 |  | N | 65 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 008 | 2 | 850 | 1 | 007 | 6806.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2562 | 20821175201 | 022 | 2 | 850 | 1 | 105 | 13055.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 3 | 105 | 13281.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 4 | 106 | 13933.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 5 | 105 | 6068.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 6 | 105 | 3660.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 036 | 2 | 850 | 1 | 105 | 3306.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 047 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 67 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2576 | 43091115201 | 001 | 2 |  | 1 | 101 | 36502.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2576 | 43091115201 | 010 | 2 |  | 1 | 101 | 13117.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2576 | 43091115201 | 014 | 2 |  | 1 | 105 | 15494.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 024 | 2 |  | 1 | 917 | 7554.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 028 | 2 |  | 1 | 112 | 70867.44 | 70867.44 | 1 |  | C | 43 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2576 | 43091115201 | 029 | 2 |  | 1 | 106 | 11536.56 | 11536.56 | 1 |  | C | 7 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2576 | 43091115201 | 035 | 2 |  | 1 | 917 | 4188.21 | 4188.21 | 0 |  | C | 6 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2576 | 43091115201 | 040 | 2 |  | 1 | 105 | 65923.25 | 65923.25 | 0 |  | C | 40 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 041 | 2 |  | 1 | 005 | 32694.52 | 32694.52 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 | 044 | 2 |  | 1 | 001 | 10379.07 | 1648.08 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 | 045 | 2 |  | 1 | 113 | 6984.76 | 4944.24 | 1 |  | C | 7 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
02 | T2576 | 43091115201 | 048 | 2 |  | 1 | 860 | 898427.26 | 0 | 0 |  | N | 107 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2577 | 43245215201 | 009 | 2 |  | 1 | 001 | 67803.45 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 1 | 001 | 15603.45 | 9281.13 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 2 | 001 | 5103.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 3 | 001 | 2662.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 4 | 015 | 14574.71 | 512.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 033 | 2 | 850 | 1 | 015 | 34984.01 | 34984.01 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 1 | 005 | 70550.44 | 70550.44 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 | 034 | 2 | 850 | 2 | 001 | 10184.91 | 10184.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 3 | 108 | 11169.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2577 | 43245215201 | 034 | 2 | 850 | 4 | 023 | 418.84 | 418.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2577 | 43245215201 | 034 | 2 | 850 | 5 | 001 | 2170.66 | 2170.66 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 6 | 021 | 5224.24 | 5224.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 7 | 004 | 440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 8 | 004 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 9 | 012 | 9423.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 10 | 021 | 9966.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 11 | 004 | -44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 042 | 2 |  | 1 | 015 | 8111.5 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 051 | 2 |  | 1 | 015 | 2113.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 052 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 187 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2618 | 43091015201 | 003 | 2 | 850 | 1 | 113 | 13643.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 2 | 105 | 660.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 3 | 115 | 4338.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 4 | 001 | 622.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 5 | 001 | 5688.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 6 | 107 | 9211.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 9 | 503 | 1452 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 003 | 2 | 850 | 10 | 115 | 4987.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 11 | 008 | 370.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 12 | 115 | 4714.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 13 | 115 | 7179.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 15 | 001 | 559.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 16 | 107 | 187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 17 | 107 | 2238.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 18 | 001 | 3913.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 19 | 022 | 390.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 20 | 503 | 2249.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 022 | 2 | 850 | 1 | 015 | 10219.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 2 | 015 | 3509.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 3 | 015 | 2785.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 4 | 015 | 12807.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 028 | 2 |  | 1 | 101 | 319.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2618 | 43091015201 | 028 | 2 |  | 2 | 107 | 25124.74 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 029 | 2 |  | 1 | 001 | 29366.68 | 0 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 030 | 2 |  | 1 | 107 | 10312.9 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 2 | 107 | -2434.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 3 | 105 | -5067.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 4 | 005 | -4526.1 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 030 | 2 |  | 5 | 107 | 24915.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 6 | 107 | 155316.69 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 7 | 105 | 26397.58 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 8 | 105 | -11156.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 9 | 105 | 49750.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 10 | 012 | 5251.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 035 | 2 |  | 1 | 919 | 11029.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 036 | 2 |  | 1 | 005 | 58922.5 | 0 | 5 |  | C | 16 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 037 | 2 |  | 1 | 112 | 58922.5 | 0 | 5 |  | C | 17 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 | 040 | 2 | 850 | 1 | 850 | 66230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T2618 | 43091015201 | 042 | 2 |  | 1 | 106 | 4926.75 | 0 | 5 |  | C | 1 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2618 | 43091015201 | 044 | 2 |  | 1 | 005 | 65531.51 | 0 | 5 |  | C | 12 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2657 | 20781825201 | 008 | 2 |  | 1 | 919 | 28193.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2657 | 20781825201 | 035 | 2 |  | 1 | 107 | 1194.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2658 | 41525215201 | 002 | 2 |  | 1 | 119 | 6298.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 018 | 2 |  | 1 | 119 | 2847.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 029 | 2 |  | 1 | 106 | 5831.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2658 | 41525215201 | 030 | 2 |  | 1 | 108 | 66785.91 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2661 | 43433715201 | 011 | 2 |  | 1 | 019 | 49601.71 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2661 | 43433715201 | 011 | 2 |  | 2 | 012 | 0 | 0 | 1 |  | N | 13 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 014 | 2 |  | 1 | 112 | 163253.75 | 0 | 1 |  | N | 50 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 | 016 | 2 | 850 | 1 | 001 | 46630.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 | 016 | 2 | 850 | 2 | 012 | 3369.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 023 | 2 | 850 | 1 | 012 | 14165.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 023 | 2 | 850 | 2 | 112 | 35834.47 | 35834.47 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 | 028 | 2 | 850 | 1 | 101 | 1614.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2661 | 43433715201 | 028 | 2 | 850 | 2 | 503 | 987.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2661 | 43433715201 | 028 | 2 | 850 | 3 | 013 | 4419.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | T2679 | 43617415201 | 004 | 2 |  | 1 | 015 | 117171.86 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 | 007 | 2 | 850 | 1 | 105 | 13341.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2679 | 43617415201 | 007 | 2 | 850 | 2 | 015 | 3910.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 | 007 | 2 | 850 | 3 | 015 | 575.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2683 | 43616215201 | 001 | 2 |  | 1 | 101 | 8616 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 | 021 | 2 |  | 1 | 860 | 27470.55 | 27470.55 | 1 |  | N | 38 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
02 | T2688 | 43500115201 | 012 | 2 |  | 1 | 503 | 66082.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2695 | 43615815201 | 012 | 2 |  | 1 | 019 | -77219.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2695 | 43615815201 | 017 | 2 | 850 | 1 | 106 | 798.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 | 017 | 2 | 850 | 2 | 106 | 931.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 1 | 115 | 21134.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 2 | 001 | 3774.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2704 | 43761615201 | 017 | 2 |  | 3 | 106 | 7438.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 4 | 115 | 49969.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 5 | 012 | 1226.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2704 | 43761615201 | 017 | 2 |  | 6 | 003 | 3231.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2708 | 44216935201 | 004 | 2 |  | 1 | 018 | 1160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2708 | 44216935201 | 005 | 2 |  | 1 | 923 | 3883.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2708 | 44216935201 | 006 | 2 |  | 1 | 101 | 388.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3Q52 | 43626715201 | 015 | 2 |  | 1 | 922 | 3908.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R04 | 43627115201 | 012 | 2 |  | 1 | 503 | 19445.17 | 8287.64 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 013 | 2 |  | 1 | 503 | -25001.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 016 | 2 |  | 1 | 922 | 823.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R52 | 43627225201 | 008 | 2 |  | 1 | 503 | 5734.8 | 507.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R73 | 43672615201 | 016 | 2 |  | 1 | 101 | 31189.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 | 019 | 2 |  | 1 | 922 | 14784.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3471 | 41110225201 | 038 | 2 |  | 1 | 009 | 157836.02 | 15783602 | 5 |  | N | 50 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
03 | T3485 | 42695315201 | 006 | 2 |  | 1 | 012 | 1215 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3488 | 40979275201 | 014 | 2 |  | 1 | 106 | 27272.89 | 9260.48 | 1 |  | N | 8 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 023 | 2 |  | 1 | 126 | 34898.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3488 | 40979275201 | 036 | 2 |  | 1 | 106 | 6047.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3543 | 22044275201 | 005 | 2 |  | 1 | 115 | 33978.2 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 008 | 2 |  | 1 | 305 | -41800.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 012 | 2 |  | 1 | 007 | 8111.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3543 | 22044275201 | 025 | 2 | 850 | 1 | 503 | 4965.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 2 | 503 | 1948.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 3 | 107 | 8470 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 4 | 503 | 9846.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 5 | 503 | 17045.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 6 | 503 | 26136 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 7 | 503 | 12458.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 8 | 503 | 4066.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 9 | 503 | 12089.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 10 | 107 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 11 | 503 | 2970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 12 | 107 | 1161.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 13 | 503 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 14 | 503 | 451.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 15 | 503 | 1357.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 16 | 503 | 11682.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 17 | 001 | 25599.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3543 | 22044275201 | 025 | 2 | 850 | 18 | 503 | 3120.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 19 | 503 | 2175.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 030 | 2 |  | 1 | 115 | 62520.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 030 | 2 |  | 2 | 860 | 38746.54 | 38746.54 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 033 | 2 |  | 1 | 503 | 72600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 042 | 2 |  | 1 | 010 | 126961.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 042 | 2 |  | 2 | 860 | 10682.09 | 10682.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 047 | 2 |  | 1 | 919 | 81171.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 050 | 2 |  | 1 | 503 | 40858.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 1 | 001 | 29819.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3543 | 22044275201 | 053 | 2 | 850 | 2 | 503 | 40150.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 3 | 107 | 2695 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 053 | 2 | 850 | 4 | 503 | 6326.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 5 | 503 | 33481.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 6 | 503 | 33481.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 7 | 503 | 1958.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 8 | 503 | 1037.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 9 | 503 | 1050.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 057 | 2 |  | 1 | 860 | 34418.57 | 34418.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 061 | 2 |  | 1 | 003 | 51134.75 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3543 | 22044275201 | 061 | 2 |  | 2 | 117 | 73599.9 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | T3543 | 22044275201 | 069 | 2 | 850 | 1 | 503 | 8123.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 069 | 2 | 850 | 2 | 101 | 29590 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3543 | 22044275201 | 069 | 2 | 850 | 3 | 503 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 069 | 2 | 850 | 4 | 003 | 51347.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3543 | 22044275201 | 069 | 2 | 850 | 5 | 010 | 11629.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 069 | 2 | 850 | 6 | 107 | 925.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 071 | 2 |  | 1 | 922 | 46846.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 072 | 2 |  | 1 | 010 | 85883.21 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 080 | 2 |  | 1 | 860 | 44696.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 086 | 2 |  | 1 | 503 | 87475.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 087 | 2 |  | 1 | 860 | 4850000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3584 | 42551925201 | 022 | 2 |  | 1 | 922 | 14487.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3584 | 42551925201 | 025 | 2 |  | 1 | 106 | 37268.2 | 0 | 5 |  | N | 9 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3586 | 42862415201 | 010 | 2 |  | 1 | 402 | 13328 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3586 | 42862415201 | 013 | 2 |  | 1 | 010 | 28275.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3586 | 42862415201 | 017 | 2 |  | 1 | 922 | 36990.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3614 | 43228815201 | 009 | 2 |  | 1 | 001 | 305542.39 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3614 | 43228815201 | 016 | 2 |  | 1 | 001 | 21000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3621 | 43626115201 | 005 | 2 |  | 1 | 101 | 4400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 011 | 2 |  | 1 | 115 | 20856 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3621 | 43626115201 | 020 | 2 |  | 1 | 101 | 4107.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 026 | 2 |  | 1 | 503 | 31063.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3622 | 43403415201 | 010 | 2 |  | 1 | 402 | 6645.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3637 | 43626515201 | 007 | 2 |  | 1 | 101 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3637 | 43626515201 | 017 | 2 |  | 1 | 922 | 22662.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3639 | 43078915201 | 005 | 2 |  | 1 | 503 | -51677.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3639 | 43078915201 | 016 | 2 |  | 1 | 922 | 18680.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3653 | 43672015201 | 004 | 2 |  | 1 | 503 | -2207.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 001 | 2 |  | 1 | 004 | 20837.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3655 | 43666315201 | 006 | 2 |  | 1 | 101 | 8408.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3655 | 43666315201 | 016 | 2 |  | 1 | 115 | -3179.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 017 | 2 |  | 1 | 113 | 24270.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 023 | 2 |  | 1 | 003 | 50951.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3655 | 43666315201 | 028 | 2 |  | 1 | 012 | 194848.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 | 029 | 2 |  | 1 | 503 | -1841.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 030 | 2 | 850 | 1 | 022 | 32893.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 038 | 2 |  | 1 | 922 | 61701.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3661 | 43255915201 | 019 | 2 |  | 1 | 115 | 27889.1 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 010 | 2 |  | 1 | 113 | -27605.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 019 | 2 |  | 1 | 113 | 48112.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 022 | 2 |  | 1 | 503 | 10741.57 | 10741.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3669 | 43046415201 | 014 | 2 |  | 1 | 922 | 124069.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3669 | 43046415201 | 016 | 2 |  | 1 | 119 | 85791.18 | 8898.63 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3673 | 43774415201 | 004 | 2 |  | 1 | 503 | -384821.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 005 | 2 |  | 1 | 503 | 11920.36 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 008 | 2 |  | 1 | 503 | 10256.95 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 010 | 2 |  | 1 | 503 | 222636.82 | 0 | 0 |  | E | 35 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3678 | 43627015201 | 007 | 2 |  | 1 | 503 | -4020 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 004 | 2 |  | 1 | 007 | 67279.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N84 | 42170735201 | 007 | 2 |  | 1 | 503 | 39656.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 026 | 2 |  | 1 | 003 | 9246.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 026 | 2 |  | 2 | 004 | 54638.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 026 | 2 |  | 3 | 305 | -229803 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 1 | 003 | 13651 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 2 | 004 | -803702.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 3 | 118 | 277064.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N84 | 42170735201 | 036 | 2 |  | 4 | 123 | 66140.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | E4N84 | 42170735201 | 036 | 2 |  | 5 | 108 | 105133.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N84 | 42170735201 | 039 | 2 |  | 1 | 503 | 59956 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 044 | 2 |  | 1 | 305 | -16958 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 044 | 2 |  | 2 | 001 | 24890.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170735201 | 049 | 2 |  | 1 | 503 | 18150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 2 | 503 | 10124.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 3 | 023 | 18920.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 4 | 001 | 8519.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170735201 | 053 | 2 |  | 1 | 003 | 1081752.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 054 | 2 |  | 1 | 023 | 21036.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 054 | 2 |  | 2 | 503 | 12375.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 054 | 2 |  | 3 | 503 | 1731.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 1 | 917 | 3222.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 2 | 917 | 861.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 3 | 917 | 891.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 4 | 917 | 861.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 5 | 917 | 457.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 6 | 917 | 3222.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 7 | 917 | 2608.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 8 | 917 | 15673.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 9 | 917 | 3775.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 10 | 917 | 4972.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 11 | 917 | 467.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 12 | 917 | 2576.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 13 | 917 | 861.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 1 | 503 | 5610 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 2 | 503 | 3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 3 | 023 | 277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 4 | 023 | 1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 5 | 503 | 2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 6 | 023 | 3067.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 7 | 003 | 1716 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 8 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 9 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 10 | 503 | 2950.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 1 | 023 | 1366.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 2 | 503 | 14179.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 3 | 503 | 80290.89 | 6037.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 4 | 503 | 11900.52 | 699.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 5 | 503 | 11184.99 | 1399.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 1 | 503 | 635855.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 2 | 503 | 22157.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 3 | 503 | -237035.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 1 | 503 | 72372.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 2 | 503 | 32749.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 3 | 503 | 80099.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 076 | 2 |  | 1 | 503 | 20332.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 076 | 2 |  | 2 | 503 | 33887.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 082 | 2 |  | 1 | 503 | -420676.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 1 | 919 | 22100.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 2 | 919 | 18619.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 3 | 919 | 139540.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 1 | 503 | -43656.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 2 | 004 | 59400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 3 | 007 | -15255.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 4 | 350 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 098 | 2 |  | 5 | 503 | -24072.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 6 | 004 | 45540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 7 | 503 | 33899.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 8 | 004 | 45540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 101 | 2 |  | 1 | 305 | -158066.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 101 | 2 |  | 2 | 503 | 158066.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 1 | 003 | 2566.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 2 | 503 | 4103.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 3 | 503 | 3329.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 1 | 503 | -5375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 2 | 503 | 75715.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 3 | 503 | -3505.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 110 | 2 |  | 1 | 503 | 451695.03 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 116 | 2 |  | 1 | 503 | 11147.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 116 | 2 |  | 2 | 503 | 5232.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 1 | 503 | 11390.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 2 | 023 | 2285.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 3 | 503 | 4537.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 4 | 004 | 32080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 128 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 | 038 | 2 |  | 1 | 108 | 80927.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N95 | 43316515201 | 045 | 2 |  | 1 | 007 | -501039.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 059 | 2 |  | 1 | 007 | -175009.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 066 | 2 |  | 1 | 007 | 139723.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 074 | 2 |  | 1 | 919 | 74739.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 1 | 004 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 2 | 003 | 42467.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 1 | 004 | 512217.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 2 | 004 | 80912.86 | 2099.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 3 | 004 | 27828.57 | 1135.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 4 | 004 | 25222.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 5 | 305 | -405594 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 6 | 305 | 202797 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 1 | 001 | 76519.47 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 2 | 001 | 58964.66 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 3 | 001 | 13868.01 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 4 | 001 | 26812.22 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 5 | 003 | 109945.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 6 | 004 | 103082.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 7 | 004 | 18931.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 8 | 004 | -37863.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 9 | 004 | -4121.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 10 | 001 | 8728.52 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 049 | 2 |  | 1 | 004 | 698225.65 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 057 | 2 |  | 1 | 917 | 51319.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 062 | 2 |  | 1 | 004 | 135891.29 | 1035.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 065 | 2 |  | 1 | 103 | 367136.55 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4N98 | 42170745201 | 066 | 2 |  | 1 | 019 | 3180 | 3180 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 2 | 019 | 25950.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 3 | 019 | 89627 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 071 | 2 |  | 1 | 004 | 323503.61 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 1 | 004 | 76630.3 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 2 | 001 | 15446.73 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 3 | 003 | 85830 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 089 | 2 |  | 1 | 919 | 238128.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 119 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4N98 | 42170745201 | 096 | 2 |  | 2 | 118 | 16352 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N98 | 42170745201 | 096 | 2 |  | 3 | 012 | 126196 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 4 | 105 | 25226.19 | 25226.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4N98 | 42170745201 | 097 | 2 |  | 1 | 860 | 34592.78 | 34592.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4P04 | 23193225201 | 010 | 2 |  | 1 | 105 | 76769.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4P04 | 23193225201 | 019 | 2 |  | 1 | 305 | -960.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4P04 | 23193225201 | 021 | 2 |  | 1 | 003 | 279116.67 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4P04 | 23193225201 | 024 | 2 |  | 1 | 122 | 51680 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4P04 | 23193225201 | 034 | 2 |  | 1 | 004 | 2579.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 2 | 004 | 3868.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 3 | 004 | 2579.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 4 | 004 | 644.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 051 | 2 |  | 1 | 350 | 36300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 064 | 2 |  | 1 | 007 | 67639 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4P04 | 23193225201 | 065 | 2 |  | 1 | 007 | 4543 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4P04 | 23193225201 | 077 | 2 |  | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 083 | 2 |  | 1 | 919 | 105078.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 088 | 2 |  | 1 | 001 | 201068.13 | 0 | 0 |  | C | 225 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 2 | 001 | 246776.95 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 3 | 001 | 106851.88 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 4 | 001 | 99303.04 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q16 | 42170795201 | 019 | 2 |  | 1 | 101 | 23100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4Q16 | 42170795201 | 019 | 2 |  | 2 | 503 | -23742.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 1 | 023 | 19264.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 2 | 023 | 2921.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 3 | 503 | 29133.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q35 | 42264135201 | 008 | 2 |  | 1 | 008 | 111519.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 040 | 2 |  | 1 | 007 | 96140.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 044 | 2 |  | 1 | 919 | 98935.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 067 | 2 |  | 1 | 113 | -51691.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 | 077 | 2 |  | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 077 | 2 |  | 2 | 502 | 29333.85 | 29333.85 | 4 |  | N | 15 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | E4Q35 | 42264135201 | 077 | 2 |  | 3 | 115 | 80000 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 010 | 2 |  | 1 | 004 | 155870.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 1 | 023 | 16668.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 2 | 023 | 38135.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 3 | 023 | 11492.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 4 | 023 | 59070.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 5 | 023 | -59070.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 6 | 023 | -7227.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 7 | 023 | 7227.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 8 | 023 | 14777.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 9 | 023 | 38837.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 10 | 023 | 30087.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 019 | 2 |  | 1 | 503 | 450075.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 026 | 2 |  | 1 | 305 | -362189.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 031 | 2 |  | 1 | 113 | 1587117.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 1 | 023 | 34410.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 2 | 023 | 44342.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 3 | 023 | 38001.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 4 | 023 | 21406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 5 | 023 | 11839.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 036 | 2 |  | 1 | 305 | -306828.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 038 | 2 |  | 1 | 503 | 132656.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 045 | 2 |  | 1 | 503 | 1384692 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 045 | 2 |  | 2 | 007 | 190992.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 045 | 2 |  | 3 | 503 | 199697.35 | 199697.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 056 | 2 |  | 1 | 919 | 341873.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 059 | 2 |  | 1 | 004 | 223000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 1 | 023 | 5933.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 2 | 023 | 19724.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 3 | 023 | 43582.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 4 | 023 | 38735.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 5 | 023 | 27207.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 6 | 023 | 14816.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 061 | 2 |  | 1 | 007 | 366965.52 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 066 | 2 |  | 1 | 001 | 289695.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 072 | 2 |  | 1 | 119 | 1100007.98 | 75013 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 1 | 023 | 20170.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 2 | 023 | 13403.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 3 | 019 | 9814.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 4 | 023 | 15957.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 5 | 001 | 21979.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 6 | 012 | 9842 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 7 | 001 | 5319.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 8 | 106 | 30515.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 9 | 001 | 14852.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 10 | 023 | 361.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 11 | 503 | 7783.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 079 | 2 |  | 1 | 004 | -796.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 086 | 2 |  | 1 | 021 | 253024.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 087 | 2 |  | 1 | 503 | 1478731.02 | 157636.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 089 | 2 |  | 1 | 012 | 111530.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 090 | 2 |  | 1 | 503 | -280593.96 | 26930.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 093 | 2 |  | 1 | 503 | 509643.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 1 | 023 | 31730.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 2 | 023 | 23189.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 3 | 023 | 39927.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 4 | 023 | -361.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 5 | 023 | 24947.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 6 | 012 | 30565.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 095 | 2 |  | 1 | 004 | 89200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 096 | 2 |  | 1 | 503 | -611125.02 | 84278.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 2 | 503 | 52683.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 3 | 503 | 100808.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 4 | 503 | 37144.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 5 | 503 | 46304.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 099 | 2 |  | 1 | 503 | -44237 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 1 | 012 | 27013.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 2 | 023 | 38796.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 3 | 023 | 34858.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 4 | 010 | 7565.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 5 | 012 | 41766.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 1 | 012 | 15812.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 2 | 023 | 63239.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 3 | 024 | 27576.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 4 | 503 | 15772.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S21 | 43661715201 | 005 | 2 |  | 1 | 118 | 56590.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4S21 | 43661715201 | 015 | 2 |  | 1 | 115 | 112689.99 | 50384.32 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 | 017 | 2 |  | 1 | 919 | 150098.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 | 019 | 2 |  | 1 | 004 | 16112 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4S21 | 43661715201 | 034 | 2 | 850 | 1 | 001 | 2273.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 | 049 | 2 |  | 1 | 101 | 39305.91 | 15400.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4S21 | 43661715201 | 050 | 2 |  | 1 | 503 | 64487.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S21 | 43661715201 | 058 | 2 |  | 1 | 860 | 1320823.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4S85 | 43609615201 | 020 | 2 |  | 1 | 503 | -10712.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S85 | 43609615201 | 024 | 2 |  | 1 | 004 | 33180 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4S85 | 43609615201 | 024 | 2 |  | 2 | 022 | 11435 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T01 | 43630215201 | 012 | 2 |  | 1 | 106 | 48308 | 48308 | 5 |  | C | 30 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4418 | 22989615201 | 022 | 2 |  | 1 | 001 | 131337.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 | 046 | 2 |  | 1 | 919 | 16851.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 | 072 | 2 |  | 1 | 126 | 178646 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4418 | 22989615201 | 072 | 2 |  | 2 | 007 | -176040 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4418 | 22989615201 | 072 | 2 |  | 3 | 860 | 11593.28 | 11593.28 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4423 | 23033845201 | 008 | 2 |  | 1 | 007 | 28826.31 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4423 | 23033845201 | 011 | 2 |  | 1 | 101 | 25597.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 1 | 503 | 3586.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 2 | 115 | 7175.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 3 | 115 | 1488.38 | 505.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 4 | 503 | 19932.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 5 | 001 | 1687.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 | 016 | 2 | 850 | 6 | 503 | 2621.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 7 | 107 | 9470.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 8 | 101 | 1925.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 9 | 503 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 10 | 107 | 2080.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 11 | 503 | 5106.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 12 | 503 | 2116.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 13 | 503 | 3540.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 14 | 108 | 44871.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 15 | 503 | 395.23 | 395.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 16 | 004 | 30502.97 | 4955.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 023 | 2 |  | 1 | 126 | -472515.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 023 | 2 |  | 3 | 107 | 7822.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 041 | 2 |  | 1 | 107 | 89275.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 1 | 919 | 100340.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 2 | 919 | 15399.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 3 | 919 | 12587.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 057 | 2 | 850 | 1 | 004 | 1998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 2 | 503 | 1656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 3 | 503 | 15643.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 4 | 503 | 18711.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 5 | 004 | 7497.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 6 | 503 | 2425.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 7 | 003 | 3067.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 8 | 503 | 4152.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 9 | 101 | 320.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 1 | 103 | 3849.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 2 | 126 | 11834.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 3 | 126 | 72235.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 4 | 126 | 2880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4433 | 42872415201 | 012 | 2 |  | 1 | 107 | 307679.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4433 | 42872415201 | 013 | 2 |  | 1 | 015 | 151854.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4433 | 42872415201 | 014 | 2 |  | 1 | 106 | 174333.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 022 | 2 |  | 1 | 004 | 36151.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4433 | 42872415201 | 026 | 2 |  | 1 | 122 | 50236.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4433 | 42872415201 | 028 | 2 |  | 1 | 919 | 51249.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4433 | 42872415201 | 044 | 2 |  | 1 | 106 | 32217 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 049 | 2 |  | 1 | 003 | 31880.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4433 | 42872415201 | 049 | 2 |  | 2 | 106 | 14616.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 049 | 2 |  | 3 | 101 | 11622.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 050 | 2 |  | 1 | 106 | 31143.44 | 15997.02 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 051 | 2 |  | 1 | 101 | 2614.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 067 | 2 |  | 1 | 101 | 86237.54 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 067 | 2 |  | 2 | 101 | 21464.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 1 | 118 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 2 | 024 | 4399.58 | 4399.58 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 3 | 115 | 3355.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 4 | 101 | 641.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4444 | 43270515201 | 010 | 2 |  | 1 | 001 | 397026.5 | 0 | 2 |  | N | 21 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
04 | T4444 | 43270515201 | 018 | 2 |  | 1 | 919 | 29064.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4444 | 43270515201 | 023 | 2 |  | 1 | 118 | 159742.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4444 | 43270515201 | 024 | 2 |  | 1 | 113 | -20599.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4444 | 43270515201 | 025 | 2 |  | 1 | 004 | 1302 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4444 | 43270515201 | 034 | 2 |  | 1 | 003 | 47797.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4444 | 43270515201 | 063 | 2 |  | 1 | 923 | 11186.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4452 | 43166615201 | 011 | 2 |  | 1 | 101 | 3096.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4452 | 43166615201 | 016 | 2 |  | 1 | 919 | 36535.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4452 | 43166615201 | 018 | 2 |  | 1 | 123 | 26168.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4452 | 43166615201 | 029 | 2 |  | 1 | 019 | 51166.08 | 51166.08 | 5 |  | C | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
04 | T4454 | 43427315201 | 017 | 2 |  | 1 | 919 | 35207.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4454 | 43427315201 | 018 | 2 |  | 1 | 004 | 74685 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4454 | 43427315201 | 028 | 2 | 850 | 1 | 101 | 3327.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 028 | 2 | 850 | 2 | 024 | 3376.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 028 | 2 | 850 | 3 | 023 | 22503.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 038 | 2 |  | 1 | 128 | -113348.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4454 | 43427315201 | 043 | 2 |  | 1 | 118 | -693 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4465 | 42793815201 | 011 | 2 |  | 1 | 919 | 56207.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4465 | 42793815201 | 016 | 2 |  | 1 | 003 | 59130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 1 | 001 | 1789.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 2 | 325 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | T4467 | 42872815201 | 003 | 2 | 850 | 3 | 115 | 20297.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 003 | 2 | 850 | 4 | 001 | 7615.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 5 | 118 | 7220.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4467 | 42872815201 | 003 | 2 | 850 | 6 | 001 | 21076.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 006 | 2 |  | 1 | 115 | 40000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 008 | 2 | 850 | 1 | 001 | 24549.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 2 | 001 | 9238.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 3 | 115 | 3193.12 | 3193.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 008 | 2 | 850 | 4 | 012 | 5999.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 5 | 010 | 10340 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4467 | 42872815201 | 008 | 2 | 850 | 6 | 012 | 1695.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 7 | 012 | 3155.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 014 | 2 |  | 1 | 101 | -12188.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4467 | 42872815201 | 015 | 2 |  | 1 | 115 | 99377.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 015 | 2 |  | 2 | 115 | 4000 | 4000 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 029 | 2 |  | 1 | 001 | 6213.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 030 | 2 |  | 1 | 001 | 3213.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 037 | 2 |  | 1 | 115 | 210000 | 0 | 0 |  | N | 150 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 050 | 2 |  | 1 | 010 | 1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4470 | 43467915201 | 007 | 2 |  | 1 | 007 | -6176.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 1 | 003 | -11311.7 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 2 | 126 | 85795.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4474 | 43516015201 | 010 | 2 |  | 3 | 007 | -221337.66 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 4 | 007 | -548.96 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 5 | 007 | 836.35 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 6 | 001 | 237589.74 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 7 | 007 | -177217.57 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 8 | 107 | 282.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4474 | 43516015201 | 010 | 2 |  | 9 | 112 | 85912.05 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 7 | 126 | -13048.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 10 | 107 | 7321.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 11 | 112 | 1157.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 12 | 112 | 3846.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 030 | 2 |  | 1 | 007 | 309000 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4478 | 43206645201 | 013 | 2 | 850 | 1 | 106 | 18283.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4480 | 43166515201 | 018 | 2 |  | 1 | 503 | 39300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 008 | 2 |  | 1 | 115 | -93585.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 1 | 106 | 12083.33 | 4247.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 2 | 112 | 28176.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 3 | 106 | 1710.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 4 | 106 | 4241.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 5 | 118 | 255.47 | 255.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 6 | 106 | 1063.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 7 | 503 | 2425.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 1 | 503 | 15042.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 2 | 503 | 8428.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 3 | 503 | 4128.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 4 | 106 | 2392.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 5 | 001 | 1692.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 014 | 2 | 850 | 6 | 118 | 555.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 7 | 503 | 1092.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 8 | 001 | 1524.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 014 | 2 | 850 | 9 | 118 | 9424.53 | 9424.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 10 | 503 | 2185 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 11 | 503 | 603.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 12 | 118 | 2929.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 015 | 2 |  | 1 | 007 | 13006.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 1 | 118 | 1118.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 2 | 503 | 9477.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 017 | 2 | 850 | 3 | 503 | 2185 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 017 | 2 | 850 | 4 | 108 | 14102.24 | 14102.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 5 | 007 | 3277.48 | 3277.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 6 | 118 | 4210.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 7 | 115 | 5755.6 | 5755.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 8 | 118 | 1027.9 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 9 | 115 | 992.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 10 | 007 | 3239.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 11 | 115 | 449.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 12 | 106 | 1169.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 13 | 001 | 2993.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 020 | 2 | 850 | 1 | 001 | 2909.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 020 | 2 | 850 | 2 | 118 | 2231.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 3 | 118 | 500.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 4 | 112 | 2855.4 | 2855.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 5 | 115 | 17520.51 | 17520.51 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 6 | 101 | 5820.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 7 | 106 | 4881.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 8 | 106 | 4881.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 021 | 2 |  | 1 | 118 | 40508.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 023 | 2 |  | 1 | 118 | 52462.28 | 52462.28 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 029 | 2 |  | 1 | 007 | 121764.98 | 121764.98 | 1 |  | N | 45 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 036 | 2 |  | 1 | 126 | 15124.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4493 | 43622615201 | 006 | 2 |  | 2 | 101 | 11868.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5W11 | 24262635201 | 038 | 2 |  | 1 | 917 | 7889 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5W11 | 24262635201 | 039 | 2 |  | 1 | 004 | -5501.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 | 046 | 2 |  | 1 | 001 | 30979.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5W11 | 24262635201 | 046 | 2 |  | 2 | 007 | 127468.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 | 061 | 2 |  | 1 | 919 | 25327.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 | 073 | 2 |  | 1 | 004 | 12915 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 | 082 | 2 |  | 1 | 004 | 2333013.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 | 049 | 2 |  | 1 | 503 | -405567.71 | 0 | 0 |  | N | 96 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W31 | 43360715201 | 052 | 2 |  | 1 | 917 | 18414.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y20 | 42690435201 | 011 | 2 |  | 1 | 919 | 97208.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y20 | 42690435201 | 021 | 2 |  | 1 | 004 | 18140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 031 | 2 |  | 1 | 106 | 54606.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y20 | 42690435201 | 047 | 2 |  | 1 | 003 | 124328.53 | 4877.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 047 | 2 |  | 2 | 105 | 575469.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 | 057 | 2 |  | 1 | 004 | 20475.52 | 6334.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 057 | 2 |  | 2 | 003 | 57948.74 | 4812.4 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 057 | 2 |  | 3 | 105 | 57211.1 | 0 | 0 |  | N | 91 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 014 | 2 |  | 1 | 001 | 52749.45 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y33 | 43693715201 | 018 | 2 |  | 1 | 112 | 311017.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 026 | 2 |  | 1 | 112 | 415194.77 | 0 | 0 |  | N | 103 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 037 | 2 |  | 1 | 503 | 19504.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y33 | 43693715201 | 037 | 2 |  | 2 | 503 | 368119.52 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y33 | 43693715201 | 037 | 2 |  | 3 | 503 | 197375.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y34 | 43744415201 | 006 | 2 |  | 1 | 860 | -9.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 1 | 105 | 4590 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 2 | 105 | 1144.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 3 | 105 | 23568.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 4 | 012 | 6473.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z02 | 43365415201 | 026 | 2 |  | 1 | 005 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | E5Z02 | 43365415201 | 026 | 2 |  | 2 | 130 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
05 | E5Z09 | 41299445214 | 003 | 2 |  | 1 | 018 | 77311.99 | 77311.99 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | E5Z09 | 41299445214 | 003 | 2 |  | 2 | 115 | 26428.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z23 | 43564715201 | 013 | 2 |  | 1 | 503 | 843.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 2 | 503 | -4331.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 3 | 503 | -1449.13 | 1753.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 4 | 503 | -135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z25 | 43685515201 | 006 | 2 |  | 1 | 001 | 8350 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 009 | 2 |  | 1 | 001 | 42152.24 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 014 | 2 |  | 1 | 106 | 30026.4 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 014 | 2 |  | 2 | 107 | 14436.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 016 | 2 |  | 1 | 003 | 780.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 018 | 2 |  | 1 | 106 | 38052.85 | 9378.86 | 1 |  | N | 13 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z44 | 43945315201 | 013 | 2 |  | 1 | 105 | 33356.49 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z44 | 43945315201 | 013 | 2 |  | 2 | 108 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z45 | 43733915201 | 010 | 2 |  | 1 | 923 | 18830.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z45 | 43733915201 | 016 | 2 |  | 1 | 113 | 61335.2 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | E5Z52 | 44116715201 | 007 | 2 |  | 1 | 105 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 002 | 2 |  | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | T5469 | 23920345201 | 007 | 2 |  | 1 | 105 | -85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 2 | 105 | 90 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 3 | 101 | 2532.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345201 | 008 | 2 |  | 1 | 012 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 018 | 2 |  | 1 | 305 | -118789.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 037 | 2 |  | 1 | 305 | -36900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 1 | 015 | -140666.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 2 | 015 | 140177.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 1 | 015 | 14511.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 2 | 015 | 7737.37 | 7737.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 3 | 015 | 4467.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 4 | 015 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 5 | 015 | 7753.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 6 | 015 | 4425.24 | 4425.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 7 | 015 | -4878.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 053 | 2 |  | 1 | 115 | 4253.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 065 | 2 |  | 1 | 001 | 7824.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 084 | 2 |  | 1 | 001 | 47862.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 1 | 115 | 29323.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 2 | 128 | 4418.68 | 5852.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 3 | 118 | 3512.15 | 3512.15 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 4 | 115 | 1368.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 5 | 012 | 755.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 6 | 115 | 1412.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 7 | 001 | 3427.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 8 | 115 | 4195.68 | 1448.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 9 | 007 | 3053.54 | 3053.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 10 | 003 | 4367.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 11 | 003 | 3359.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 12 | 115 | 4926.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 13 | 003 | 648.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 14 | 115 | 414.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 15 | 105 | 3486.32 | 3941.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 16 | 115 | 3507.28 | 2981.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 17 | 115 | 2745.01 | 6459.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 18 | 115 | 4842.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 19 | 115 | 3329.19 | 3329.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 20 | 107 | 5539 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 21 | 107 | 656.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 22 | 003 | 2491.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 23 | 003 | 2506.76 | 2506.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 24 | 503 | 8499.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 085 | 2 | 850 | 25 | 118 | 8165.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 26 | 003 | 1134.64 | 1246 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 27 | 003 | 8500 | 6052.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 28 | 003 | 11812.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 29 | 118 | 6266.79 | 6266.79 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 30 | 118 | 2859.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 31 | 003 | 6571.65 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 1 | 003 | 7984.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 2 | 107 | 2621.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 101 | 2 |  | 1 | 107 | 13803.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 105 | 2 |  | 1 | 128 | 18863.98 | 3772.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 117 | 2 |  | 1 | 107 | 68509.21 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 118 | 2 |  | 1 | 003 | 63585.28 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 119 | 2 |  | 1 | 917 | 15282.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 121 | 2 |  | 1 | 503 | 308974.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 123 | 2 |  | 1 | 106 | 858359.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 124 | 2 |  | 1 | 012 | 5109.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 132 | 2 |  | 1 | 015 | 162028.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 133 | 2 |  | 1 | 725 | -78085.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
05 | T5469 | 23920345201 | 134 | 2 |  | 1 | 012 | 97231.95 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 135 | 2 |  | 1 | 106 | 8472.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 2 | 115 | 3500 | 3500 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 3 | 003 | 64550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 1 | 003 | 865 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 2 | 118 | 4609 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 138 | 2 |  | 1 | 003 | 71010.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 139 | 2 |  | 1 | 105 | 35202 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 140 | 2 |  | 1 | 860 | 1485000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5572 | 43505615201 | 007 | 2 |  | 1 | 004 | 19031.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5591 | 42823815201 | 031 | 2 |  | 1 | 503 | 132028.9 | 132028.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5591 | 42823815201 | 031 | 2 |  | 2 | 012 | 16790.52 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5591 | 42823815201 | 031 | 2 |  | 3 | 115 | 11239.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 4 | 122 | 32390.38 | 32390.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 5 | 115 | 24542.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 6 | 023 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 7 | 503 | 5590.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5591 | 42823815201 | 031 | 2 |  | 8 | 101 | 3077.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 9 | 010 | 34199.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5591 | 42823815201 | 031 | 2 |  | 10 | 115 | 17034.41 | 17034.41 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43565815201 | 004 | 2 |  | 1 | 107 | 23208.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5601 | 43565815201 | 011 | 2 |  | 1 | 012 | 13095.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43565815201 | 015 | 2 |  | 1 | 012 | 44000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43565815201 | 021 | 2 |  | 1 | 115 | 61010.4 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5616 | 43065515201 | 006 | 2 |  | 1 | 003 | -14065.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5616 | 43065515201 | 026 | 2 |  | 1 | 502 | 12412.65 | 2422 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 | 002 | 2 |  | 1 | 106 | 18234.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 | 012 | 2 |  | 1 | 860 | 8171.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5619 | 24099275201 | 009 | 2 |  | 1 | 115 | -1091.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 | 011 | 2 |  | 1 | 003 | 21286.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099275201 | 022 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5623 | 43239915201 | 010 | 2 |  | 1 | 012 | 7254.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5623 | 43239915201 | 010 | 2 |  | 2 | 122 | 2443.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5623 | 43239915201 | 010 | 2 |  | 3 | 503 | -9272.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J52 | 43337815201 | 018 | 2 |  | 1 | 919 | 67061.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J69 | 43492215201 | 022 | 2 |  | 1 | 919 | 350222.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J69 | 43492215201 | 024 | 2 |  | 1 | 007 | 765311 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 1 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 2 | 022 | 47165.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 3 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 041 | 2 | 850 | 1 | 003 | 58696.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 042 | 2 |  | 1 | 503 | 202835.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J69 | 43492215201 | 043 | 2 |  | 1 | 012 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 | 043 | 2 |  | 2 | 003 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 046 | 2 |  | 1 | 503 | 69191.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K58 | 43081315201 | 011 | 2 |  | 1 | 923 | 1618.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 011 | 2 |  | 1 | 503 | 132107.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 016 | 2 |  | 1 | 919 | 101999.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 026 | 2 |  | 1 | 001 | 108531.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 027 | 2 |  | 1 | 001 | 96922.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 1 | 503 | 2628.98 | 2628.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 2 | 106 | 18274.76 | 18274.76 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 3 | 001 | 5096.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 4 | 001 | 6472.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 5 | 106 | 10476.52 | 10476.52 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 6 | 903 | -2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 7 | 903 | 1482.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 8 | 004 | 51700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 1 | 503 | 45923.49 | 45923.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 2 | 503 | 24333.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 3 | 503 | 2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 4 | 503 | 11861.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 5 | 503 | 5012.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 035 | 2 |  | 1 | 105 | 148644.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | E6K59 | 41831225201 | 035 | 2 |  | 2 | 503 | -11623.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 1 | 503 | 5614.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 2 | 118 | 17005.68 | 17005.68 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 3 | 118 | 70879.02 | 70879.02 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 1 | 118 | 3896.81 | 3896.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 2 | 503 | 1750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 3 | 503 | 17040.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 4 | 115 | 12183.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 | 039 | 2 |  | 1 | 503 | 111333 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K89 | 43653615201 | 001 | 2 |  | 1 | 503 | 24000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 010 | 2 | 850 | 1 | 503 | 9455.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 010 | 2 | 850 | 2 | 503 | 5296.5 | 5296.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 012 | 2 |  | 1 | 923 | 17744.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 016 | 2 |  | 1 | 115 | 75469.28 | 9012.21 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 015 | 2 |  | 1 | 015 | 30556.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 015 | 2 |  | 2 | 015 | 17120.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 015 | 2 |  | 3 | 115 | 14129.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 1 | 106 | 19746.84 | 19746.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 2 | 503 | 19943.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 016 | 2 | 850 | 3 | 107 | 7912.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 4 | 101 | 74925.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 5 | 106 | 8693.81 | 8693.81 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 6 | 503 | 8359.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 017 | 2 |  | 1 | 503 | 49204.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 017 | 2 |  | 2 | 106 | 53003.95 | 53003.95 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 017 | 2 |  | 3 | 115 | 17155.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 022 | 2 |  | 1 | 108 | 6057.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 | 022 | 2 |  | 2 | 503 | 3904.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 022 | 2 |  | 3 | 001 | 3905.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 035 | 2 | 850 | 1 | 015 | 1032.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 035 | 2 | 850 | 2 | 015 | 43743.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 039 | 2 |  | 1 | 919 | 30510.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 045 | 2 |  | 1 | 503 | 190324.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 047 | 2 |  | 1 | 015 | 63756.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 049 | 2 |  | 1 | 015 | 339873.87 | 0 | 0 |  | C | 75 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 051 | 2 |  | 1 | 115 | 160126.13 | 115639.22 | 1 |  | C | 44 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 052 | 2 |  | 1 | 503 | 110000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 054 | 2 | 850 | 1 | 503 | 20627.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 054 | 2 | 850 | 2 | 115 | 15287.83 | 15287.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 3 | 115 | 4985.78 | 4985.78 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 4 | 003 | 8741.56 | 8741.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 5 | 115 | 17993.07 | 17993.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 6 | 115 | 3463.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 7 | 115 | 2781.84 | 2781.84 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 8 | 003 | 3130.27 | 3130.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 9 | 108 | 2552.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 10 | 015 | 14640 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 11 | 115 | 10122.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 12 | 115 | -10122.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 13 | 115 | 10122.13 | 10122.13 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 14 | 115 | -31561.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 15 | 115 | 33108.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 16 | 115 | 31561.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 055 | 2 | 850 | 1 | 001 | 7752.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 055 | 2 | 850 | 2 | 503 | 1974.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 055 | 2 | 850 | 3 | 115 | 2115.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 1 | 101 | 17729.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 2 | 503 | 30451.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 3 | 503 | 3367.05 | 3367.05 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 4 | 503 | 11969.64 | 11969.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 5 | 101 | 668.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 6 | 122 | 3864.9 | 3864.9 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 7 | 115 | 1278.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 10 | 106 | 3842.37 | 3842.37 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 11 | 503 | 24046.83 | 24046.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 13 | 003 | 6004.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 056 | 2 | 850 | 14 | 503 | 5703.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 15 | 503 | 966.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 16 | 503 | 2468.83 | 2468.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 17 | 503 | 12940.11 | 7397.55 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 18 | 003 | 12682.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 1 | 015 | 12902.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 2 | 015 | 2084.29 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 3 | 503 | 12701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 1 | 503 | 4886.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 2 | 001 | 1396.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 072 | 2 | 850 | 3 | 503 | 5057.2 | 5057.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 4 | 107 | 2774.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 072 | 2 | 850 | 5 | 503 | 642.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 6 | 503 | 6575.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 7 | 503 | 29389.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 8 | 503 | 5962.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 9 | 009 | 13901.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6337 | 41809115201 | 073 | 2 | 850 | 1 | 115 | 11915 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 074 | 2 |  | 1 | 015 | 565313.05 | 422827.05 | 1 |  | N | 12 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 076 | 2 |  | 1 | 015 | 59055.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 077 | 2 | 850 | 1 | 118 | 2487.31 | 2487.31 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6337 | 41809115201 | 077 | 2 | 850 | 2 | 503 | 3980.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 077 | 2 | 850 | 3 | 503 | 5349.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 078 | 2 |  | 1 | 015 | 13390.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 019 | 2 |  | 1 | 015 | 118644.76 | 0 | 0 |  | N | 42 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 019 | 2 |  | 2 | 015 | 330801.43 | 0 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 1 | 503 | 7900.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 023 | 2 | 850 | 2 | 106 | 9096.47 | 9096.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 3 | 106 | 16585.16 | 16585.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 4 | 115 | 4709.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 5 | 003 | 5271.49 | 5271.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 6 | 003 | 5271.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 7 | 003 | -5271.49 | -5271.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 8 | 001 | 23589.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 9 | 001 | 13047.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 10 | 001 | 4765.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 028 | 2 |  | 1 | 015 | 128232.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 029 | 2 |  | 1 | 503 | 234906.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 033 | 2 |  | 1 | 919 | 37096.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 040 | 2 |  | 1 | 015 | 45962.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 1 | 115 | 40460.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 043 | 2 | 850 | 2 | 001 | 13851.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 3 | 001 | 3765.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 4 | 503 | 15279.65 | 15279.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 5 | 503 | 8152.36 | 8152.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 6 | 503 | 4344.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 7 | 503 | 6224.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 8 | 001 | 4318.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 9 | 115 | 14226.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 050 | 2 |  | 1 | 015 | 331264.21 | 331264.21 | 5 |  | C | 81 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 064 | 2 |  | 1 | 503 | 4198.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 064 | 2 |  | 2 | 007 | 6671.59 | 1350.66 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6338 | 41463315201 | 064 | 2 |  | 3 | 122 | 13854.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 4 | 024 | 8311.62 | 8311.62 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 5 | 007 | 5844.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6338 | 41463315201 | 064 | 2 |  | 6 | 122 | 2024.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 7 | 503 | -15606.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 064 | 2 |  | 8 | 001 | 12112.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 005 | 2 |  | 1 | 101 | 98804.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 006 | 2 |  | 1 | 101 | 3879.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 025 | 2 |  | 1 | 101 | 5135.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 030 | 2 |  | 1 | 107 | 124618.46 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 1 | 115 | 15978.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 2 | 004 | -6712.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 | 037 | 2 | 850 | 3 | 106 | 7487.7 | 7487.7 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 4 | 503 | 10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 037 | 2 | 850 | 5 | 503 | -10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 038 | 2 |  | 1 | 103 | 300000 | 300000 | 1 |  | C | 26 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 1 | 007 | 7664.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 2 | 004 | -14085.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 3 | 503 | 9900.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 4 | 003 | 1694.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 5 | 503 | 9810.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 6 | 115 | 2466.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 7 | 118 | 3125.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 8 | 503 | 6956.25 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 9 | 112 | 6982.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 10 | 001 | 10200.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 11 | 001 | 21465.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 12 | 503 | 6956.25 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 13 | 001 | 26438.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 14 | 503 | -6956.25 | 6956.25 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 044 | 2 | 850 | 1 | 503 | 10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 044 | 2 | 850 | 2 | 106 | 1111.38 | 1111.38 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 | 044 | 2 | 850 | 3 | 012 | 5187.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6344 | 24994145201 | 052 | 2 | 850 | 1 | 012 | 13428.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6382 | 40561535201 | 009 | 2 |  | 1 | 101 | 53086 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 009 | 2 |  | 2 | 101 | 12768.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 019 | 2 |  | 1 | 919 | 79756.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 1 | 007 | 60790 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 2 | 118 | 3740.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 3 | 118 | 8966.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 4 | 004 | 39929.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 5 | 001 | 2130.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 6 | 001 | 7757.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 7 | 001 | 4355.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 8 | 004 | 6049.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 9 | 003 | 16281.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 027 | 2 |  | 1 | 305 | -514052 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 031 | 2 | 850 | 1 | 003 | 8941.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 031 | 2 | 850 | 2 | 112 | 37957.83 | 2952.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6382 | 40561535201 | 031 | 2 | 850 | 3 | 112 | 1159.07 | 1159.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6382 | 40561535201 | 031 | 2 | 850 | 4 | 004 | 859.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 034 | 2 |  | 1 | 503 | 246786.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561535201 | 039 | 2 |  | 1 | 101 | 68105.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 042 | 2 |  | 1 | 001 | 130000 | 130000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 1 | 001 | 75198.42 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 2 | 015 | 46947.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 3 | 101 | 5581.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6401 | 41247395201 | 008 | 2 |  | 4 | 103 | 21097.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 011 | 2 |  | 1 | 919 | 47416.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 1 | 001 | 30840.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 2 | 115 | 5055 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 3 | 103 | 4060.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 4 | 012 | 2608.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 5 | 118 | 7435.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 1 | 118 | 7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 2 | 503 | 32700 | 32700 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 014 | 2 | 850 | 3 | 118 | -7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 4 | 118 | 7311.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 5 | 503 | 8987.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 016 | 2 |  | 1 | 001 | 143032.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 019 | 2 |  | 1 | 001 | 105307.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 020 | 2 |  | 1 | 005 | 134857.01 | 134857.01 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 024 | 2 |  | 1 | 001 | 22284.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 024 | 2 |  | 2 | 115 | 67637.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 024 | 2 |  | 3 | 503 | 30856.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 024 | 2 |  | 4 | 005 | 8035.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 026 | 2 |  | 1 | 005 | 277982.41 | 277982.41 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 027 | 2 |  | 1 | 001 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 027 | 2 |  | 2 | 007 | 198705 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 1 | 919 | 87170.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 2 | 005 | 40374.14 | 40374.14 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 032 | 2 |  | 1 | 005 | 24196.79 | 24196.79 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 033 | 2 |  | 1 | 001 | 59302.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 033 | 2 |  | 2 | 115 | 1461.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 033 | 2 |  | 3 | 005 | 5320.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 034 | 2 |  | 1 | 018 | 62435.91 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6401 | 41247395201 | 035 | 2 |  | 1 | 115 | 97151.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 036 | 2 |  | 1 | 001 | 6366.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 036 | 2 |  | 2 | 005 | 92994.54 | 92994.54 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 3 | 023 | 16568.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 4 | 115 | 238476 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6403 | 43348915201 | 015 | 2 |  | 1 | 001 | 21903 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 | 015 | 2 |  | 1 | 101 | 3440 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6406 | 42902215201 | 019 | 2 | 850 | 1 | 503 | 12484.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6419 | 42827825201 | 009 | 2 |  | 1 | 503 | 80246.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6436 | 43631115201 | 013 | 2 |  | 1 | 103 | 92453.79 | 31947.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6438 | 43117015201 | 007 | 2 |  | 1 | 001 | 2862.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 007 | 2 |  | 2 | 001 | 3736.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 007 | 2 |  | 3 | 503 | 38500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 007 | 2 |  | 4 | 503 | 16102.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 007 | 2 |  | 5 | 001 | 29344.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 1 | 001 | 3414.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 2 | 001 | 4469.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 4 | 001 | 4493.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 5 | 001 | 2174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 6 | 001 | 3692.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 7 | 001 | 4049.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 8 | 001 | 7352.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 9 | 001 | 6065.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 10 | 503 | 14320.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 008 | 2 |  | 11 | 009 | 1458.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 12 | 001 | 2644.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 13 | 005 | 16210.58 | 16210.58 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6438 | 43117015201 | 008 | 2 |  | 14 | 001 | 6228.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 15 | 115 | 10190.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 1 | 350 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 2 | 005 | 18713.22 | 18713.22 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 8 | 001 | 14244.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 9 | 113 | 14026.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 14 | 126 | 1349.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 16 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 17 | 007 | 58766.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 014 | 2 |  | 1 | 012 | 594363.95 | 594363.95 | 5 |  | N | 48 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 1 | 503 | 44154 | 44154 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7H90 | 25693125201 | 028 | 2 |  | 2 | 001 | 4205.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 3 | 001 | 790.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 4 | 113 | 174768.35 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7H90 | 25693125201 | 028 | 2 |  | 5 | 003 | -245320.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 6 | 004 | 89787.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 7 | 004 | -114716.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 8 | 007 | 593095.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 3 | 007 | 7356.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 4 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 5 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 6 | 122 | 50825.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 7 | 004 | 75318.55 | 75318.55 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 045 | 2 |  | 1 | 001 | 7848.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 045 | 2 |  | 2 | 128 | 32697.5 | 32697.5 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 | 055 | 2 |  | 1 | 003 | 284434.96 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 055 | 2 |  | 2 | 003 | 101651.94 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 2 | 122 | 123363.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 3 | 001 | 5283.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 4 | 122 | 18053.01 | 1572.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 062 | 2 | 850 | 1 | 122 | 687.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 062 | 2 | 850 | 2 | 118 | 5337.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7H90 | 25693125201 | 064 | 2 |  | 1 | 001 | 1581.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 2 | 001 | 1392.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 3 | 917 | 14304.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 4 | 122 | 21584.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 074 | 2 |  | 1 | 118 | 77797.15 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7H90 | 25693125201 | 074 | 2 |  | 4 | 106 | 10430.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7H90 | 25693125201 | 086 | 2 |  | 1 | 919 | 85510.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7H90 | 25693125201 | 087 | 2 |  | 1 | 105 | 7994.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K19 | 43476515201 | 002 | 2 |  | 1 | 003 | 22750000 | 0 | 0 |  | N | 313 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K19 | 43476515201 | 010 | 2 |  | 1 | 113 | 379220.64 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7K19 | 43476515201 | 014 | 2 |  | 1 | 007 | 103456 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 017 | 2 |  | 1 | 503 | 242505.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 025 | 2 |  | 1 | 919 | 203686.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 036 | 2 | 850 | 1 | 503 | 59458.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 036 | 2 | 850 | 2 | 503 | 60541.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 038 | 2 |  | 1 | 503 | -318434.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 043 | 2 |  | 1 | 503 | 646286.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 1 | 018 | 66991.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 2 | 007 | 17366.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 3 | 018 | 18842.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 4 | 503 | 16028.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 5 | 503 | 770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 1 | 503 | 19483.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 2 | 007 | 3956.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 3 | 018 | 5654.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 4 | 012 | 90904.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K19 | 43476515201 | 054 | 2 | 850 | 1 | 503 | 58191.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 063 | 2 |  | 1 | 018 | 16720.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 1 | 023 | 736.78 | 736.78 | 5 |  | N | 0 | Avoidable, Third Party | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 2 | 021 | 8384.71 | 8384.71 | 5 |  | N | 0 | Avoidable, Third Party | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 3 | 007 | 14157.34 | 14157.34 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 4 | 122 | 4536.2 | 4536.2 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 5 | 024 | 852.11 | 852.11 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 6 | 024 | 2856.67 | 2856.67 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 7 | 004 | 4041.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 8 | 012 | 11795.05 | 4259.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 9 | 024 | 1200.72 | 1200.72 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 10 | 105 | 11174.47 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 11 | 012 | 2363.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 13 | 503 | 28363.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 14 | 131 | 5627.06 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 15 | 007 | 5716.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 16 | 004 | 5654.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 17 | 122 | 9919.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 18 | 004 | 2618.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 014 | 2 |  | 1 | 503 | 275627.95 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 015 | 2 |  | 1 | 003 | 86679.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K24 | 41101145201 | 016 | 2 |  | 1 | 004 | 72079.03 | 72079.03 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 1 | 503 | 11051.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 2 | 023 | 3126.49 | 3126.49 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 3 | 021 | 938.79 | 938.79 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 4 | 004 | 14883.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 023 | 2 |  | 1 | 015 | 65907.47 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | E7K24 | 41101145201 | 027 | 2 |  | 1 | 004 | 27090.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 1 | 021 | 14269.63 | 14269.63 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 2 | 012 | 6481.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 3 | 503 | 9248.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 035 | 2 |  | 1 | 004 | 322004.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 036 | 2 |  | 2 | 101 | 51802.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 2 | 004 | 6977.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 3 | 008 | 55167.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 6 | 107 | 2591.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7K24 | 41101145201 | 039 | 2 | 850 | 1 | 503 | 30000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 1 | 503 | 31920.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 2 | 012 | 4637.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 3 | 131 | 5627.06 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 4 | 503 | 38694.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 5 | 012 | 11760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 044 | 2 |  | 1 | 919 | 327968.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 049 | 2 |  | 1 | 503 | 64689.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 059 | 2 |  | 1 | 004 | 160331.5 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 066 | 2 |  | 1 | 503 | 44144.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 075 | 2 |  | 1 | 503 | 15544.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 076 | 2 |  | 1 | 001 | 14858.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 002 | 2 |  | 1 | 001 | 318367.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 011 | 2 |  | 1 | 001 | 35650.27 | 35650.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 012 | 2 |  | 1 | 003 | 16147.9 | 16147.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 1 | 503 | 15055.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 2 | 101 | 836 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 3 | 115 | 6134.96 | 742.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 5 | 503 | 1936.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 6 | 503 | 2047.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 7 | 503 | 24254.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 8 | 503 | 13714.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 10 | 503 | 22226.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 12 | 503 | 13795.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 021 | 2 |  | 1 | 115 | 124417.08 | 3609.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 025 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 026 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 027 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 029 | 2 |  | 1 | 003 | 396759.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 030 | 2 |  | 1 | 919 | 147479.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 045 | 2 | 850 | 1 | 503 | 124077.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L58 | 43243415201 | 005 | 2 |  | 1 | 012 | 88378.63 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 2 | 105 | 3660.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 3 | 012 | 15290.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 4 | 012 | 4306.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 5 | 001 | 15518.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 6 | 105 | 3108.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 7 | 003 | 12716.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 8 | 012 | 333.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 9 | 012 | 61531.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 10 | 003 | 24948.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 11 | 012 | 2608.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M00 | 42292945201 | 006 | 2 |  | 1 | 103 | 147052.15 | 0 | 1 |  | N | 12 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 1 | 103 | 17713.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 2 | 106 | 2632.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 3 | 003 | 19444.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 4 | 001 | 657.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M27 | 43648015201 | 002 | 2 |  | 1 | 115 | 17309.8 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | E7M27 | 43648015201 | 008 | 2 |  | 1 | 001 | 90236.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7R60 | 43920615201 | 020 | 2 | 850 | 1 | 850 | 100000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7R60 | 43920615201 | 025 | 2 |  | 1 | 010 | 54492.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7389 | 43272015201 | 001 | 2 |  | 1 | 015 | -1034.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7389 | 43272015201 | 006 | 2 |  | 1 | 101 | 51809.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7389 | 43272015201 | 007 | 2 |  | 1 | 850 | 46698 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7389 | 43272015201 | 008 | 2 |  | 1 | 850 | 129888 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7389 | 43272015201 | 024 | 2 |  | 2 | 107 | 17100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 | 026 | 2 |  | 1 | 007 | 549567.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 027 | 2 |  | 1 | 919 | 89783.7 | 89783.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 036 | 2 |  | 1 | 305 | -84321.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 040 | 2 |  | 1 | 106 | 1815 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 | 040 | 2 |  | 2 | 106 | 2774.79 | 2774.79 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 | 040 | 2 |  | 3 | 007 | 1725.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 040 | 2 |  | 4 | 208 | 883.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015201 | 041 | 2 |  | 1 | 113 | 2470.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7391 | 43269815201 | 010 | 2 |  | 1 | 012 | 18351.56 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7401 | 43480615201 | 011 | 2 |  | 1 | 012 | 6728.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N19 | 42935015201 | 001 | 2 |  | 1 | 503 | -350000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 002 | 2 |  | 1 | 004 | 106869.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 | 024 | 2 |  | 1 | 003 | 29393.56 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 | 039 | 2 |  | 1 | 503 | 97747.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 1 | 023 | 8927.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 2 | 023 | 1963.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 3 | 126 | 6144.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 006 | 2 |  | 1 | 101 | 27300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 007 | 2 |  | 1 | 131 | -94332.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 008 | 2 |  | 1 | 003 | 387833.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 012 | 2 |  | 1 | 009 | 115671.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 016 | 2 |  | 1 | 919 | 111021.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 019 | 2 |  | 1 | 003 | 119709.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 020 | 2 |  | 1 | 106 | 24515.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 023 | 2 |  | 1 | 003 | 26483.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 027 | 2 |  | 1 | 131 | 9747.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 1 | 001 | 3461.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 2 | 003 | 17118.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 3 | 108 | 3244.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 4 | 108 | 3244.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 5 | 503 | 7334.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 6 | 503 | 6958.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 7 | 108 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 8 | 105 | 1633.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 9 | 003 | 7004.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 1 | 105 | 26354.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 2 | 131 | 8072.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 3 | 131 | 8072.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 4 | 131 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 5 | 131 | 8576.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 6 | 131 | 6615.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 7 | 131 | 3047.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 8 | 131 | 2914.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 9 | 131 | 12864.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 10 | 131 | 1927.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 11 | 131 | 2566.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 12 | 131 | 16084.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 13 | 131 | -2566.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 14 | 131 | 2556.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 15 | 503 | 2914.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 032 | 2 |  | 1 | 131 | 241133.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 033 | 2 |  | 1 | 131 | 128800.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 037 | 2 |  | 1 | 108 | 89554.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 041 | 2 |  | 1 | 131 | 93527.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 042 | 2 |  | 1 | 003 | 141830.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 045 | 2 |  | 1 | 101 | 86350.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 049 | 2 |  | 1 | 003 | 16580.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 1 | 003 | 11197.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 2 | 003 | 4265.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 3 | 003 | 2419.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 1 | 131 | 27985.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 2 | 131 | 547.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 3 | 131 | 3116.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 4 | 131 | 4875.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 5 | 131 | 8462.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 6 | 131 | 3525.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 7 | 131 | 10 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 054 | 2 |  | 1 | 105 | 15323.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 055 | 2 |  | 1 | 503 | 10479.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 056 | 2 |  | 1 | 503 | 270 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q41 | 43516515201 | 028 | 2 |  | 1 | 113 | 120025.2 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 034 | 2 |  | 1 | 919 | 11513.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 037 | 2 | 850 | 1 | 021 | 38344.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 043 | 2 |  | 1 | 012 | 278427.21 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q41 | 43516515201 | 051 | 2 |  | 1 | 101 | 7958.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 010 | 2 | 850 | 1 | 023 | 17890.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 010 | 2 | 850 | 2 | 023 | 2109.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 011 | 2 | 850 | 1 | 023 | 6986.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 011 | 2 | 850 | 2 | 023 | 13013.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 026 | 2 | 850 | 1 | 023 | 7429.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 026 | 2 | 850 | 2 | 021 | 12570.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 027 | 2 | 850 | 1 | 023 | 11737.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 041 | 2 |  | 1 | 503 | 7314.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 042 | 2 |  | 1 | 503 | -4792.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 043 | 2 | 850 | 1 | 023 | 6888.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 044 | 2 |  | 1 | 503 | 172830.5 | 0 | 0 |  | C | 69 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q91 | 43915315201 | 008 | 2 |  | 1 | 005 | 34422.76 | 34422.76 | 5 |  | N | 27 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 1 | 101 | 125000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 2 | 024 | 14708.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 3 | 101 | 3685.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 019 | 2 |  | 1 | 503 | 94166.31 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R18 | 43652115201 | 020 | 2 | 850 | 1 | 101 | 24700.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 020 | 2 | 850 | 2 | 101 | 10874.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 021 | 2 | 850 | 1 | 101 | 37000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 021 | 2 | 850 | 2 | 101 | 5408.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 1 | 101 | 23227.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 2 | 021 | 33471.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 3 | 021 | 11589.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R46 | 44154915201 | 006 | 2 |  | 1 | 923 | 6348.32 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 | 002 | 2 |  | 1 | 101 | 5477.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 | 004 | 2 |  | 1 | 112 | 97924.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R64 | 44263115201 | 009 | 2 |  | 1 | 503 | 55503.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R64 | 44263115201 | 009 | 2 |  | 2 | 503 | -10346.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 3 | 009 | 330 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 005 | 11987.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P91 | 42271055201 |  | 2 | CPI | 2 | 112 | 5590.53 | 316.53 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 128 | 3948.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 128 | 2585 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 112 | -2795.26 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 105 | 9801.38 | 9801.38 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 503 | 7821.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 503 | 1480.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 112 | 6544.93 | 6544.93 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 3 | 118 | 566.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q23 | 43665015201 |  | 2 | CPI | 1 | 401 | 0 | 0 | 0 |  | N | 32 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 13167 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 2516.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 825 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 27300.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 107 | 3855.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 2 | 107 | 4072.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 6591.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 004 | 19965 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 108 | 16108.78 | 3167.05 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 12829.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 115 | 8562.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 9206.11 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R12 | 43668215201 |  | 2 | CPI | 1 | 003 | 14025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R12 | 43668215201 |  | 2 | CPI | 2 | 007 | 1354.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R80 | 43771615201 |  | 2 | CPI | 1 | 001 | 6183.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 4445.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 62.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 56.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 98.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 14.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 84655.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 107 | 7100.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 3 | 101 | 84.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 28.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 1317.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 126.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 012 | 22495.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 012 | 7879.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 253.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 239.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 70.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 324.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 0.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 464.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | -225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 4585.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 128 | 4250 | 4250 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 7146.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 8971.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 2 | 001 | 34170.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 3 | 023 | 6197.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 023 | 6407.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1697 | 43534915201 |  | 2 | CPI | 1 | 112 | 1241.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 001 | 18048.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 001 | 18048.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 115 | 7360.64 | 7360.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1701 | 43498615201 |  | 2 | CPI | 2 | 007 | 923.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1705 | 44013315201 |  | 2 | CPI | 1 | 112 | 296.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1705 | 44013715201 |  | 2 | CPI | 1 | 112 | 1195.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44012515201 |  | 2 | CPI | 1 | 112 | 1490.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44012515201 |  | 2 | CPI | 1 | 112 | 1250 | 1250 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44013815201 |  | 2 | CPI | 1 | 106 | 11902.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1707 | 44013815201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 101 | 16973.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 115 | 16978.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1713 | 43355215201 |  | 2 | CPI | 2 | 001 | 7539.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 003 | 8508.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1714 | 43837615201 |  | 2 | CPI | 1 | 503 | 1800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1729 | 43837415201 |  | 2 | CPI | 1 | 012 | 694.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1741 | 44067415201 |  | 2 | CPI | 1 | 122 | 2342.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1741 | 44067415201 |  | 2 | CPI | 1 | 007 | 1230.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 35948 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2554.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 2122.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 3638.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 1419 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7378 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 14045.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 11000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7898.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 18667.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 11283.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 2729.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2256.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 1092.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 1128.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | -32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 436.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 007 | 715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 2255.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 007 | 6699.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 5 | 007 | 5671.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 6 | 003 | 7500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 3 | 007 | 10049.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 007 | 4192.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 350 | 2851.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 013 | 8285 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 003 | 26121.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 013 | 21757.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 95245.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 115 | 4293.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 115 | 16649.6 | 16649.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 003 | 31147.2 | 31147.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 2664.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825601 |  | 2 | CPI | 1 | 015 | 18416.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 105 | 13024 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 015 | 2816 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 001 | 6260.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 001 | 16656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 2 | 015 | 29397.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 8419.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 503 | 31698.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 5013.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 105 | 23233.91 | 0 | 2 |  | C | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 105 | 3451.33 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 503 | -31698.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 1891.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 1102.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 208 | 2461.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 112 | 1017.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | 3993.73 | 3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | 3310.46 | 3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | 1792.67 | 1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 112 | 1049.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 112 | 980.49 | 980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | 3993.73 | 3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | 3310.46 | 3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | 1792.67 | 1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 5 | 112 | 980.49 | 980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | -2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | -3993.73 | -3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | -3310.46 | -3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | -1792.67 | -1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 5 | 112 | -980.49 | -980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 8320.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 118 | 17550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 1072.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 2 | 007 | 1393.67 | 1393.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 2319.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 7371.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 003 | 4771.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 3434.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 32103.81 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W35 | 42849115201 |  | 2 | CPI | 1 | 012 | 10399.78 | 1722.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W51 | 20950355201 |  | 2 | CPI | 1 | 108 | 5910.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W52 | 42849815201 |  | 2 | CPI | 1 | 012 | 39951.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W53 | 42849715201 |  | 2 | CPI | 1 | 120 | 18271.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 4386 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 3607.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 1694.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 003 | 2961.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 8032.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 003 | 229.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X15 | 20961685201 |  | 2 | CPI | 1 | 106 | 8172.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X15 | 20961685201 |  | 2 | CPI | 1 | 012 | 19307.27 | 7485.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X44 | 42879715201 |  | 2 | CPI | 1 | 118 | 4536.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2X44 | 42879715201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2X60 | 43025915201 |  | 2 | CPI | 1 | 001 | 874.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X60 | 43025915201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X68 | 43500015201 |  | 2 | CPI | 1 | 101 | 1762.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 003 | 19823.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 003 | 30530.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 115 | 3842.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 6564.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 4526.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 47514.67 | 20240.85 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 37197.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 019 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 003 | 3792.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 2 | 005 | 5934 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 001 | 19566.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 122 | 1265.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 105 | 15392.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 126 | 6987.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 105 | 3946.98 | 3946.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 5593.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1924.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 118 | 2043.71 | 2043.71 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 7470.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 012 | 17090.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 5000 | 5000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 012 | 5500 | 5500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 012 | 2673 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 001 | 1210.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 2 | 120 | 3556.89 | 3556.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1163.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 5161.2 | 5160.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 120 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 3932.5 | 3932.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 001 | 42560.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 14997.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 10975.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 2024.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 005 | 1261.49 | 1261.49 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1521.89 | 1521.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 126 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 1633.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 2534.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 101 | 3882.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 005 | 1410 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 3 | 001 | 1284.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 4 | 103 | 2706.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 1022.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 299.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 3340.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 11250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 112 | 22753.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 718.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 126 | 629.64 | 629.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 7570 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 012 | 2008.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 113 | 7913.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 5215.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 7342.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 2658.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | -8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 007 | 4719.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 3686.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 503 | 3200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 101 | 3616 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 2 | 101 | 1604.48 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 3 | 101 | 4627.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 4 | 101 | 3600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 5 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 101 | 890.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 25449.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 115 | 11184.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 11263.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 2 | 001 | 29984.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 1453.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 6356.14 | 6356.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 5220.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 2 | 001 | 1452.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 34018.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 33 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2679 | 43617415601 |  | 2 | CPI | 1 | 015 | 10643.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415601 |  | 2 | CPI | 1 | 015 | 8746.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 7199.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 799.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 1075.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 2 | 108 | 1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | -1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 716.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 2 | 923 | 1421.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 3 | 108 | 633.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 118 | 4447.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 33 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 115 | 4440.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 13120.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 3762 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 5 |  | N | 25 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 4949.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 2 | 101 | 6664.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 3 | 101 | 2542.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 4 | 012 | 5379.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 6870 | 6870 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2687 | 43617315201 |  | 2 | CPI | 1 | 001 | 8532.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2687 | 43617315201 |  | 2 | CPI | 1 | 113 | 17379 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 101 | 1706.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 001 | 11752.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2689 | 43616115201 |  | 2 | CPI | 2 | 112 | 1382.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 001 | 13212.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2691 | 43617215201 |  | 2 | CPI | 1 | 115 | 3409.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2691 | 43617215201 |  | 2 | CPI | 1 | 101 | 916.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 010 | 8988.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 001 | 980.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 012 | 3959.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 2 | 107 | 7825.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615915201 |  | 2 | CPI | 1 | 115 | 1082.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2695 | 43615915201 |  | 2 | CPI | 2 | 012 | 839.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 003 | 4190.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 003 | 1394.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2695 | 43615915201 |  | 2 | CPI | 1 | 001 | 639.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 1455.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 801.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 106 | 3675.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 024 | 728.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 1 |  | N | 17 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 3 | 024 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 2 |  | N | 1 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2704 | 43761615201 |  | 2 | CPI | 1 | 007 | 15471.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2704 | 43761615201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2723 | 43762015201 |  | 2 | CPI | 1 | 503 | 2504.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2723 | 43762015201 |  | 2 | CPI | 2 | 101 | 1526.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 003 | 1894.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 001 | 838 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 116 | 353.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 024 | 7341.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | T2730 | 43429715201 |  | 2 | CPI | 1 | 105 | 16696.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3P84 | 43671715201 |  | 2 | CPI | 1 | 101 | 862.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 5001.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R04 | 43627115201 |  | 2 | CPI | 1 | 004 | 1500 | 336 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3R52 | 43627225201 |  | 2 | CPI | 1 | 503 | 9663.81 | 1845.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R52 | 43627225201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 101 | 540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 115 | 26048 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | 914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | 914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | -914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 118 | 624 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 2 | 101 | 853.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 3 | 105 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 3716.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 001 | 7581.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 010 | 2008.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | -41662.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 023 | 1485 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 115 | 4510.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3471 | 41110225201 |  | 2 | CPI | 3 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 1281.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3485 | 42695315201 |  | 2 | CPI | 1 | 503 | 4876.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 12642.28 | 1306.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 107 | 980.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 2903.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 7700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 11246.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 5580.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 4 | 503 | 2709.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 107 | 7081.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 107 | 1017.5 | 1017.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 7678.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 1665.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 2054.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 123 | 4541.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4583.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 11388.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 2711.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 1399.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 7265.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 38524.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 6481.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 7409.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 1355.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 206.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | -4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 451.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3584 | 42551925201 |  | 2 | CPI | 1 | 922 | 4452.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3621 | 43626115201 |  | 2 | CPI | 1 | 115 | 5375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 1084.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 2 | 503 | 7987.77 | 3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 101 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3637 | 43626515201 |  | 2 | CPI | 1 | 115 | 12197.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3637 | 43626515201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 8667.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 4880.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 2 | 115 | 5064 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 3 | 128 | 7675.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 128 | 9900 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 6550.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 35155.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 17711.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 2 | 010 | 16468.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 23464.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 6938.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 686.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 2 | 101 | 2225 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 3 | 101 | 697.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 4 | 015 | 7220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 1 | 007 | 1598.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 2 | 007 | 12350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 3250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 2 | 503 | 4300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 012 | 10230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 24665 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3673 | 43774415201 |  | 2 | CPI | 1 | 022 | 49174.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3678 | 43627015201 |  | 2 | CPI | 1 | 107 | 24960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3678 | 43627015201 |  | 2 | CPI | 1 | 115 | 7900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3688 | 44038315201 |  | 2 | CPI | 1 | 118 | 6070 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 6211.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 7520.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 6000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 5229.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 3991.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 2224.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 10052.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 1735.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1203.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 4029.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | -1043.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1053.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1010.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 792.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 023 | 1173.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1403.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 023 | 2093.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 300.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 2135.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1121.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1790.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 471.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 003 | 3146 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 11489.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 726.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1564.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 001 | 4652.37 | 4652.37 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 2564.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | 2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 3320.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 023 | 257.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 3 | 023 | 277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 4 | 023 | 1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 503 | 3466.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 2978.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 10330.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 2751.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 023 | 1575.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 3 | 023 | 1604.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 4 | 023 | 1313.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 5 | 023 | 3308.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 6 | 023 | 439.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | 3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 003 | 4160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 3586.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | -3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | -1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 503 | -2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | -277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 503 | 6794.6 | 6794.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 503 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | -1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 003 | 10865.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1583.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 003 | 440.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 22703.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 2 | 503 | 14825.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 3 | 503 | 27357.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 917 | 8455.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 12345.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 503 | 41494.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 001 | 32335.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 18563.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 8321.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 31709.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 7017.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 42978515201 |  | 2 | CPI | 1 | 023 | 1369.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41325725201 |  | 2 | CPI | 1 | 023 | 524.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 |  | 2 | CPI | 1 | 917 | 1930.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41273325201 |  | 2 | CPI | 1 | 917 | 2422.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41325725201 |  | 2 | CPI | 1 | 917 | 1166.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 42978515201 |  | 2 | CPI | 1 | 917 | 534.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 43093215201 |  | 2 | CPI | 1 | 917 | 4064.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 503 | 2987.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 2 | 503 | 1290.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 503 | 9195.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 2 | 503 | 2869.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 013 | 4879.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 023 | 37664.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 917 | 822.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 115 | 9299 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 003 | 9062.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 3 |  | N | 5 | Avoidable, CEI Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 16653.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 3321.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 19230.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 2529.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 13123.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 6037.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 43188.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 6639.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 917 | 36426.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 2848.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 106 | 5981.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 107 | 13699.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 106 | 5981.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 012 | 4728.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 3 | 001 | 12658.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 115 | 8976.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 107 | 6974.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 115 | 24954.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 013 | 33647.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 001 | 12408.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 107 | 13699.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 001 | 6289.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S85 | 43609615201 |  | 2 | CPI | 1 | 106 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S85 | 43609615201 |  | 2 | CPI | 1 | 502 | 2750 | 2750 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 105 | 22758.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T43 | 43686915201 |  | 2 | CPI | 1 | 118 | 2200 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T47 | 43995915201 |  | 2 | CPI | 1 | 012 | 10355.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T53 | 44145715201 |  | 2 | CPI | 1 | 503 | 3899.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 001 | 4492.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 003 | 1091.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4418 | 22989615201 |  | 2 | CPI | 2 | 106 | 3076.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 106 | 8100 | 8100 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 1150.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 107 | 655.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 107 | 705.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 001 | 11760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 001 | 43721.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 012 | 2194.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 010 | 15343.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 22000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 115 | 3322.8 | 3322.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 20881.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 001 | 21724.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 004 | 1713.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 503 | 4826.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 123 | 4014.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 2 | 001 | 28714.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 001 | 3321 | 3321 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 106 | 809.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 106 | 3547.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415203 |  | 2 | CPI | 1 | 106 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 012 | 4395.55 | 4395.55 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 119 | 1760 | 1760 | 3 |  | N | 0 | Avoidable, CEI Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 001 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 005 | 1588.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Utility Adjustments | Utility Delays | 11
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 015 | 3200.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4433 | 42995815601 |  | 2 | CPI | 2 | 012 | 1816.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 734.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 5587.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 106 | 18684.88 | 18684.88 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 003 | 12222.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 106 | 1074.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 009 | 1697.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 003 | 2002 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 7345.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 112 | 7655.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 4560.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 7852.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 4560.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 8643.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 2380.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 2 | 118 | 3289 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 112 | 20938.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 022 | 30661.2 | 30661.2 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 115 | 1024 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 005 | 5294.02 | 5294.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4452 | 43166615201 |  | 2 | CPI | 2 | 001 | 1454.5 | 1454.5 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4452 | 43166615201 |  | 2 | CPI | 3 | 115 | 11036.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 4 | 122 | 2071.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 107 | 708.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 2 | 115 | 8270.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 106 | 1144.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 108 | 11268.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 105 | 3701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 023 | 7396.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 18153.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 9815.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 023 | 18346.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 101 | 5435.27 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 101 | 4257.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 7150.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 4427.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 112 | 14368.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 15261.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 2 | 112 | 2979.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 3 | 112 | 4392.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 17253 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 2112 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 1468.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 8568.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | E | 30 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 6199.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 101 | 8773.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 11159.65 | 11159.65 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 4 |  | N | 28 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 3889.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 2457.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 2 | 003 | 1854.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 3476.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 108 | 15045.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 106 | 15703.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4478 | 43206645201 |  | 2 | CPI | 2 | 106 | 4651.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4480 | 43166515201 |  | 2 | CPI | 1 | 503 | 830.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4480 | 43166515201 |  | 2 | CPI | 2 | 118 | 2261.88 | 2261.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4480 | 43166515201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 2 |  | N | 12 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 105 | 1931.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 001 | 3267.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 001 | 2273.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 001 | 5233.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 503 | 9121.11 | 2173.88 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 503 | 4044.19 | 4044.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 503 | 1019.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 106 | 2500.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 3 | 007 | 251.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 4 | 106 | 3055.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 5 | 001 | 1524.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 6 | 503 | 1721.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 7 | 503 | 755.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 8 | 503 | 4370 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 9 | 106 | 4870.47 | 3868.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 106 | 379 | 379 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4492 | 43783715201 |  | 2 | CPI | 1 | 003 | 1964.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4492 | 43783715201 |  | 2 | CPI | 2 | 118 | 375 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 107 | 1456.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 118 | 16897.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 3899.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 2 | 023 | 11026.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 022 | 9416.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 1023 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 024 | 8706.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 007 | 39069.83 | 12617.83 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 001 | 15531.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 2 | 007 | 12994.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 5 |  | N | 10 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 |  | 2 | CPI | 1 | 021 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 |  | 2 | CPI | 1 | 003 | 4745.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 20030 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 26484.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 9000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 8984 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 3136.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 003 | 22324.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 2060.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y33 | 43693715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y33 | 43693715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 105 | 5734 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 2 | 106 | 4585.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 012 | 5993.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z02 | 43365415201 |  | 2 | CPI | 2 | 105 | 10293.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 007 | 23393.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Z09 | 41299445214 |  | 2 | CPI | 1 | 503 | 4205.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z09 | 41299445214 |  | 2 | CPI | 1 | 503 | 26624.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 115 | 7195.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 101 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 2 | 126 | 1450 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 2670.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 2 | 115 | 13133.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 34740.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z49 | 44255515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 009 | 32447.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 117 | 3295.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3266.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 3359.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 7003.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 3053.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3531 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 012 | 14850.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 53568.73 | 14060.7 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 29101.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 2716.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 120 | 22876.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 21177.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 101 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 25020.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 4011.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 4374.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 1210 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 001 | 986.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 1434.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 6514.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 004 | 1689.89 | 1689.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 107 | 17747.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 10206.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 811.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 008 | 9339.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 8726.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 004 | 1158.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 503 | -460.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 001 | 6777.6 | 7272.52 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505315201 |  | 2 | CPI | 2 | 107 | 2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615201 |  | 2 | CPI | 1 | 112 | 1968.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 107 | 2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615201 |  | 2 | CPI | 1 | 107 | 4444 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615202 |  | 2 | CPI | 1 | 107 | 4642 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 107 | -2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 2 | 001 | 6777.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505315201 |  | 2 | CPI | 3 | 001 | 13394.97 | 12577.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505615202 |  | 2 | CPI | 1 | 118 | 844.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 503 | 2978.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 8490.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 3714.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 7694.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 503 | 3372.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 6632.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 2 | 107 | 5618.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 101 | 3600 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | 48898.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | -48898.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 2 | 115 | 48395.15 | 48395.15 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | 2782.4 | 2782.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 023 | 6497 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43239815201 |  | 2 | CPI | 1 | 101 | 1207.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 001 | 2111.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5601 | 43565815201 |  | 2 | CPI | 1 | 012 | 21500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 108 | 4097.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 023 | 1050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43565815201 |  | 2 | CPI | 1 | 023 | 2650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43565815201 |  | 2 | CPI | 2 | 021 | 2650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 503 | 13110.33 | 13110.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 101 | 5603.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 2 | 503 | 25738.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 3 | 503 | 3115 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 118 | 200 | 24707.31 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | -2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | -1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 503 | 2382.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 023 | 3653.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 6054.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 024 | 834.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 001 | 5764.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 003 | 311.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 115 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 106 | 3337.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 782.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 023 | 11439.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 115 | 7972.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5623 | 43618735201 |  | 2 | CPI | 1 | 122 | 6180.35 | 6180.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 1272.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 2987.62 | 2987.62 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 3 | 007 | 15653.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 007 | 5217.8 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | -1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | -536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 9340.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 1478.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 82125.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 24530.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 003 | 5805.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 2156.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 122 | 1966.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | E6K58 | 43081315201 |  | 2 | CPI | 2 | 001 | 556.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 101 | 14235.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 503 | 85.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K58 | 43081315201 |  | 2 | CPI | 2 | 503 | 680.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 101 | 51824.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 115 | 18518.16 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 106 | 20980.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6L26 | 43653515201 |  | 2 | CPI | 1 | 503 | 8375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 503 | 9886.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 007 | 23363.88 | 23363.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 004 | 3883.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 023 | 1648.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725202 |  | 2 | CPI | 1 | 503 | 1459.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 1 | 001 | 4537.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | E6L37 | 42919325201 |  | 2 | CPI | 1 | 503 | 10279.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 2 | 503 | 23090.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 3 | 101 | 7067.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 001 | 10601.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 001 | 15982.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 103 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 118 | 56166.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6337 | 41809115601 |  | 2 | CPI | 1 | 015 | 17517.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 2 | 015 | 5102.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 3 | 015 | 70280.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 4 | 015 | 11584.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 123 | 2722.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 2442.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115601 |  | 2 | CPI | 1 | 015 | 40722.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 107 | 617.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 108 | 598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 003 | 1674.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 3 | 503 | 2456.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 005 | 2921.21 | 2921.21 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 115 | 652.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 43328315201 |  | 2 | CPI | 1 | 001 | 10425.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 115 | 2984.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 123 | 1455.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | -598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 3 | 108 | -299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 108 | 598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 43349115201 |  | 2 | CPI | 1 | 118 | 2268.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 503 | 11165 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 107 | 3812.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6338 | 41463315201 |  | 2 | CPI | 2 | 001 | 12218.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 26037.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 13551.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 115 | 14778.48 | 14778.48 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | -32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 1056 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 115 | 14639.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 123 | 2368.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 112 | 3844 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 007 | 3590 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 105 | 1054.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 917 | 4717.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 003 | 7409.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 1 | 107 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 107 | 858 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 004 | 11636.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 003 | 35891.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 503 | 4397.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 503 | 2040.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 |  | 2 | CPI | 3 | 003 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 4 | 001 | 614.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 1 | 004 | 4231.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 2 | 115 | 9497.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 115 | 1495.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 42901415601 |  | 2 | CPI | 1 | 001 | 18706.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 2 | 001 | 5616.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 106 | -1495.63 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 007 | 7194 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 3 | 007 | 4539.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 4 | 115 | 14130.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 106 | 1495.63 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145601 |  | 2 | CPI | 1 | 015 | 3672.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 1 | 112 | 17868.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 42901415601 |  | 2 | CPI | 2 | 001 | 12983.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 3 | 001 | 8342.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 4 | 015 | 17050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 001 | 3222.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 001 | 1235.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 009 | 5490 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 63609.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 3180.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 5129.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 015 | 10379.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 2 | 007 | 6330.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 503 | 480.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 1939.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 2 | 503 | 1164.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 647.74 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 001 | 2811.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 2 | 007 | 2136.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 004 | 6555.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 105 | 17007.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 118 | 20481.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 160823.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 2198.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 6327 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 004 | 2594.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 7126.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 9720 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 5750 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 007 | 4886.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | -5750 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 5750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 41705.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 007 | 2856.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 2 | 007 | 761.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 21412.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 |  | 2 | CPI | 1 | 001 | 17895 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395602 |  | 2 | CPI | 1 | 001 | 925.87 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247375202 |  | 2 | CPI | 1 | 001 | 2139.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395202 |  | 2 | CPI | 1 | 503 | 3600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6403 | 43348915201 |  | 2 | CPI | 1 | 105 | 5280 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 3 | 123 | 6410.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 4 | 001 | 16985.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 6 | 007 | 2554.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 2 | 024 | 2255.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 5 | 115 | 16061.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 1 | 001 | 2882.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 |  | 2 | CPI | 2 | 118 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 3 | 503 | 14596.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902215201 |  | 2 | CPI | 4 | 503 | 9515 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 1 | 503 | 2610.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 2 | 503 | 6811.21 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 101 | 2786.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 001 | 2069.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6419 | 42827825201 |  | 2 | CPI | 2 | 101 | 18916.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 001 | 4441.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 003 | 1293.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 123 | 16438.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 007 | 1775.31 | 1775.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 2 | 007 | 8840.65 | 8840.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117015201 |  | 2 | CPI | 1 | 503 | 564.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 |  | 2 | CPI | 2 | 005 | 684.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6438 | 43117015201 |  | 2 | CPI | 3 | 007 | 385.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117015202 |  | 2 | CPI | 1 | 503 | 1880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 503 | 4252.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 101 | 564.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 101 | 1601.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6438 | 43117025201 |  | 2 | CPI | 2 | 007 | 385.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117055202 |  | 2 | CPI | 1 | 101 | 2280 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6451 | 42563725201 |  | 2 | CPI | 1 | 503 | 9954.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 44211.51 | 44211.51 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 10470.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 15291.34 | 29983.01 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 28309.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 2 | 005 | 4025.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 8815 | 8815 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 005 | -4025.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 005 | 4025.86 | 4025.86 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | -38779.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 38779.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | -8815 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 14691.67 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 55 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 1584 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 010 | 2842.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 99990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 2 | 503 | 15583.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 2 |  | N | 49 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 70 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 6001.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 004 | 3842.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 3 | 003 | 6982.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 3850 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 021 | 16357.31 | 16357.31 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 023 | 3282.09 | 3282.09 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 2 | 023 | 3517.7 | 3517.7 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 3 | 023 | 1144.67 | 1144.67 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 023 | 3394.17 | 3394.17 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 21764.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 3850 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | -3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 021 | 16697.4 | 16697.4 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3940.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 503 | 1963.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 15708.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 503 | 16688.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 840 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 20173.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 37275.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 007 | 3039.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 3 | 503 | 7920.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 12425.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 32302.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 17997.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2565 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 1 | 007 | 1821.18 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 40552525601 |  | 2 | CPI | 2 | 503 | 962.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 3 | 503 | 484.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2779.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7L77 | 42292935201 |  | 2 | CPI | 1 | 012 | 9843.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L77 | 42292935201 |  | 2 | CPI | 2 | 115 | 33659.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 6160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L98 | 43763715201 |  | 2 | CPI | 2 | 101 | 3707 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 3 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 103 | 20764.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7M26 | 25839935201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 2 |  | N | 17 | Avoidable, In-House Designer | Major Sturctural Component Changes | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 122 | 2195.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 115 | 3005.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 012 | 2903.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R06 | 44008915201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Test Projects | Changed Conditions | 1
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 20501.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 001 | 9572.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 30487.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 2420 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 1188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 17264.22 | 17264.22 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 1695.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 3145.56 | 3145.56 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 012 | 22476.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 4098.34 | 4098.34 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 6561.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 208 | 27990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015201 |  | 2 | CPI | 2 | 725 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 208 | 1962 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015602 |  | 2 | CPI | 1 | 007 | 46344.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 15807.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 118 | 18795.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 4250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 1116 | 350 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 012 | 4040.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 657.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 101 | 3039.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 13157.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 007 | 9885.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 3521.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 3 | 101 | 4052.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 005 | 5990.38 | 5990.38 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 108 | 5311.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 101 | 2094.46 | 2094.46 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 4 | 106 | 7000 | 7000 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 5 | 112 | 1458.67 | 1458.67 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 6 | 101 | -2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 112 | 1458.67 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | 2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 112 | -1458.67 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 101 | 2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | -2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 2 |  | N | 3 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 2 |  | N | 7 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7401 | 43480615201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7401 | 43480615201 |  | 2 | CPI | 4 | 101 | 493.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 1 | 101 | -323.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 3371.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 2 | 113 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 3 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7415 | 43982935201 |  | 2 | CPI | 4 | 005 | 1072.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7422 | 44275215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 3 | 112 | 1263 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 106 | 20830.53 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 2 | 106 | 1343 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 923 | 1076.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 2 | 115 | 204.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 115 | 24992.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 2 |  | N | 10 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 2 |  | N | 8 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7429 | 43753015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 021 | 3245 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 19190.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 003 | 26337.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 003 | 3174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 120.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 82.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 503 | 99.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 4653 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 5.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 3 | 118 | 5702.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 4 | 012 | 2061.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 5 | 503 | 113 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 6 | 503 | 6060.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 350 | 1100 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 171.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 118 | 11649.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 105 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P81 | 43561415201 |  | 2 | CPI | 2 | 101 | 25914 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 101 | 4871.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 2 | 101 | 2527 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 106 | 10401.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 2 | 005 | 2454.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
08 | E8Q39 | 43730015201 |  | 2 | CPI | 3 | 117 | 815.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 012 | 2755.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q39 | 43730015201 |  | 2 | CPI | 2 | 012 | 32754.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q39 | 43730015201 |  | 2 | CPI | 3 | 503 | 17485.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 4126.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 8507.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 2 | 131 | 5730.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 003 | 3099.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 6519.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 2 | 105 | 12264.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 503 | 40513.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q41 | 43516715201 |  | 2 | CPI | 1 | 009 | 1264.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q41 | 43516535201 |  | 2 | CPI | 1 | 021 | 2916.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
08 | E8Q41 | 43516715201 |  | 2 | CPI | 1 | 118 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q41 | 43516535201 |  | 2 | CPI | 1 | 021 | 14007.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517235201 |  | 2 | CPI | 1 | 023 | 704.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517135201 |  | 2 | CPI | 1 | 023 | 1630.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517235201 |  | 2 | CPI | 1 | 023 | 1778.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517135201 |  | 2 | CPI | 1 | 023 | 6384.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 101 | 3459.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 106 | 7996.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 023 | 3567.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 022 | 23590.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 11880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 1048.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 26920.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 17650.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 4237.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 12350.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 3 | 101 | 18506.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | -12350.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 14585.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 5334.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 1 | 101 | 2193.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 2 | 101 | 3758.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 3 | 101 | 14643.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 4 | 101 | 1980 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 886.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 441.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 1513.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 4753.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 115 | 7181.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 107 | 1701.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R64 | 44263115201 |  | 2 | CPI | 1 | 101 | 456 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 |  | 2 | CPI | 2 | 101 | 550 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P91 | 42271055201 | 012 |  | 5 | 044 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1P91 | 42271055201 | 115 |  | 5 | 044 | 2 | 2 | N | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P94 | 43493915201 | 118 |  | 14 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1R51 | 43800815201 | 503 |  | 6 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R80 | 43771615201 | 503 |  | 11 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 503 |  | 1 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1713 | 43355215201 | 007 |  | 28 | 015 | 1 | 1 | N | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V70 | 42747515201 | 024 |  | 60 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V70 | 42747515201 | 022 |  | 51 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V71 | 43430015201 | 007 |  | 42 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2W51 | 20950355201 | 012 |  | 12 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X44 | 42879715201 | 015 |  | 45 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 007 |  | 15 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X44 | 42879715201 | 503 |  | 7 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2577 | 43245215201 | 012 |  | 3 | 049 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2612 | 42360825201 | 005 |  | 23 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2661 | 43433715201 | 001 |  | 27 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2686 | 43611815201 | 005 |  | 30 | 009 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2688 | 43500115201 | 016 |  | 14 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3P84 | 43625815201 | 016 |  | 21 | 009 | 1 | 2 | N | Avoidable, In-House Designer | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3R15 | 43730715201 | 503 |  | 8 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R15 | 43730715201 | 116 |  | 18 | 011 | 1 | 2 | N | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3R73 | 43672615201 | 107 |  | 18 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3S52 | 41767755201 | 010 |  | 15 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3485 | 42695315201 | 106 |  | 3 | 004 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3485 | 42695315201 | 106 |  | 26 | 017 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 2 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3488 | 40979275201 | 106 |  | 1 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 005 |  | 14 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
03 | T3488 | 40979275201 | 106 |  | 1 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 120 |  | 18 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | T3488 | 40979275201 | 106 |  | 1 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 126 |  | 6 | 027 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3488 | 40979275201 | 105 |  | 10 | 033 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3543 | 22044275201 | 015 |  | 12 | 079 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3584 | 42551925201 | 101 |  | 38 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3584 | 42551925201 | 101 |  | 5 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3586 | 42862415201 | 119 |  | 30 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3605 | 43390515201 | 106 |  | 10 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3637 | 43626515201 | 700 |  | 17 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3661 | 43255915201 | 106 |  | 7 | 020 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N98 | 42170745201 | 004 |  | 2 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Z02 | 43365415201 | 012 |  | 11 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6337 | 41809115201 | 115 |  | 120 | 064 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 003 |  | 7 | 054 | 1 | 1 | N | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 503 |  | 14 | 054 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 118 |  | 137 | 061 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 005 |  | 69 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6437 | 43634215201 | 007 |  | 15 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6448 | 43792015201 | 503 |  | 29 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 018 |  | 2 | 069 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | T7391 | 43269815201 | 007 |  | 13 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7399 | 43653015201 | 108 |  | 10 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N19 | 42935015201 | 103 |  | 29 | 036 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8N19 | 42935015201 | 118 |  | 14 | 036 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N19 | 42935015201 | 503 |  | 7 | 036 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 503 |  | 2 | 036 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 113 |  | 3 | 036 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 | 115 |  | 11 | 036 | 6 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 | 105 |  | 11 | 036 | 7 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N19 | 42935015201 | 503 |  | 7 | 036 | 8 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 11598 | 6 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 23 | 01co | 1 | 23
01CO | 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | -1499517 | 1891710 | 39 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | -250656 | 0 |  | CO | 11 | 01do | 24 | 34
01CO | 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 6509 | -485989 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 22 | 02co | 35 | 56
01CO | 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 300819 | 240997 | 138 | 0 | 7 | 224121 | 0 | 0 | 0 | 24860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 261807 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73 |  |  | 2 | 47 | 0 | 0 | 0 | 0 |  | CO | 20 | 02do | 57 | 76
01CO | 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 374249 | 101 | 0 | 33 | 344330 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 374249 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 23 | 03co | 77 | 99
01CO | 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 49336 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 9 | 03do | 100 | 108
01CO | 01 | T1701 | 43498615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 3 | 580 | 635 | 485 | 150 | 0 | 0 | 55 | 0 | 8087167 | 75299 | 8011868 | 8023343 | 7632042 | 0 | 570000 | 570000 | 8202042 | 7675787 | -516267 | -63824 | 40 | 0 | 0 | 37019 | 0 | 0 | 0 | -73677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29433 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 | 2019-10-01 | QTR2 | 19/20 | 118 | 8094281.54 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 15 | 04co | 109 | 123
01CO | 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 15 | 04do | 124 | 138
01CO | 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 10 | 05co | 139 | 148
01CO | 01 | T1706 | 43658615201 | 2018-06-13 | QTR4 | 17/18 | 2 | 1 | 325 | 397 | 374 | 23 | 0 | 0 | 72 | 0 | 7786066 | 101721 | 7684345 | 7543630 | 7286083 | 0 | 0 | 0 | 7286083 | 7247442 | -38640 | -242436 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -242436 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 | 2019-11-04 | QTR2 | 19/20 | 108 | 9348245.16 |  |  | 0 | 27 | 0 | 0 | -242436 | 0 | T | CO | 18 | 05do | 149 | 166
01CO | 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | -6 | 7262 | 17 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93 |  |  | 20 | 5 | 0 | 0 | 0 | 0 |  | CO | 15 | 06co | 167 | 181
01CO | 01 | T1713 | 43355215201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 230 | 408 | 407 | 1 | 0 | 0 | 178 | 0 | 2526300 | 50000 | 2476300 | 2681334 | 2687161 | 0 | 0 | 0 | 2687161 | 2585403 | -101758 | 155034 | 128 | 28 | 0 | 74449 | 0 | 0 | 0 | 130585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 205034 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 | 2019-10-30 | QTR2 | 19/20 | 115 | 2797558.23 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 11 | 06do | 182 | 192
01CO | 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 11 | 07co | 193 | 203
01CO | 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | -485 | 59543 | 17 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 16 | 07do | 204 | 219
01CO | 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 220 | 219
01CO | 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 12 | 08do | 220 | 231
01CO | 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 0 | 0 | 11 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1743 | 43800415201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 71 | 107 | 99 | 8 | 0 | 0 | 36 | 0 | 138436 | 0 | 138436 | 138436 | 138436 | 0 | 0 | 0 | 138436 | 138436 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-09-30 | QTR1 | 19/20 | 108 | 179132.62 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 0 | 60277 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1753 | 43943215201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 200 | 218 | 136 | 82 | 0 | 0 | 18 | 0 | 1952155 | 50000 | 1902155 | 1971307 | 1962809 | 0 | 0 | 0 | 1962809 | 1962123 | -686 | 19152 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 | 2020-02-24 | QTR3 | 19/20 | 108 | 2489141.93 | B0 | ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1P56 | 41968815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 150 | 180 | 180 | 0 | 0 | 0 | 30 | 0 | 1109997 | 50000 | 1059997 | 1109997 | 793278 | 0 | 0 | 0 | 793278 | 793278 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 | 2017-10-27 | QTR2 | 17/18 | 115 | 2383057.05 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P91 | 42271055201 | 2017-04-20 | QTR4 | 16/17 | 1 | 7 | 560 | 729 | 725 | 4 | 0 | 0 | 169 | 0 | 10071503 | 104026 | 9967477 | 10247666 | 9983254 | 0 | 0 | 0 | 9983254 | 10164043 | 198791 | 176163 | 120 | 5 | 0 | 55015 | 0 | 5 | 0 | 112805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 179808 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 | 2019-07-03 | QTR1 | 19/20 | 115 | 11091792.08 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 0 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q23 | 43665015201 | 2018-02-13 | QTR3 | 17/18 | 1 | 0 | 340 | 462 | 525 | -63 | 63 | 0 | 90 | 32 | 918123 | 50000 | 868123 | 918123 | 868123 | -104895 | 0 | -104895 | 763228 | 763228 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 | 2019-10-01 | QTR2 | 19/20 | 108 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 32 | 30 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q29 | 42584115201 | 2017-04-20 | QTR4 | 16/17 | 2 | 15 | 650 | 1043 | 726 | 317 | 0 | 0 | 71 | 322 | 54145606 | 150000 | 53995606 | 56232960 | 55752280 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | -1366994 | 2087354 | 38 | 0 | 208 | 2137914 | 84393 | 0 | 114 | 329014 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27149 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322 | 2110169 | 103094 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-10-11 | QTR2 | 19/20 | 113 | 61229521.11 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | -383908 | 0 |  | DO
01DO | 01 | E1R12 | 43668215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 0 | 175 | 188 | 123 | 65 | 0 | 0 | 13 | 0 | 1472083 | 50000 | 1422083 | 1472083 | 1445724 | 0 | 65000 | 65000 | 1510724 | 1446603 | -64121 | 0 | 4 | 0 | 0 | 15380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15380 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 | 2019-09-16 | QTR1 | 19/20 | 115 | 1181939.29 | B1 | ACC - NO EXCUSE BONUS | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | -783 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R51 | 43800815201 | 2018-09-20 | QTR1 | 18/19 | 1 | 0 | 165 | 233 | 232 | 1 | 0 | 0 | 68 | 0 | 2579000 | 50000 | 2529000 | 2579000 | 2523711 | 0 | 0 | 0 | 2523711 | 2514757 | -8954 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 | 2019-10-31 | QTR2 | 19/20 | 113 | 2698176.21 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R80 | 43771615201 | 2019-04-18 | QTR4 | 18/19 | 1 | 1 | 65 | 96 | 96 | 0 | 0 | 0 | 31 | 0 | 157000 | 9525 | 147475 | 157000 | 148434 | 0 | 0 | 0 | 148434 | 148434 | 0 | 0 | 16 | 0 | 0 | 6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 6184 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 | 2019-10-11 | QTR2 | 19/20 | 108 | 169094.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S00 | 43943515201 | 2019-05-23 | QTR4 | 18/19 | 2 | 0 | 140 | 159 | 118 | 41 | 0 | 0 | 19 | 0 | 2112776 | 50000 | 2062776 | 2112776 | 2088952 | 0 | 0 | 0 | 2088952 | 2065283 | -23668 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 | 2019-12-02 | QTR2 | 19/20 | 108 | 3162692.93 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 150000 | 87 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74 |  |  | 44 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2576 | 43091115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 13 | 340 | 624 | 717 | -93 | 93 | 0 | 64 | 220 | 7004346 | 70466 | 6933880 | 8247072 | 8273395 | -350610 | 0 | -350610 | 7922785 | 7815365 | -95677 | 1242726 | 29 | 0 | 4 | 33738 | 1648 | 0 | 98 | 237085 | 153271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 898427 | 0 | 0 | 5 | 38629 | 32695 | 0 | 0 | 0 | 0 | 0 | 214 | 1207879 | 187614 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 | 2017-12-20 | QTR2 | 17/18 | 208 | 5694356.97 |  |  | 6 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | -191646 | 313457 | 83 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88 |  |  | 37 | 110 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 7440 | 0 | 43 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45 |  |  | 25 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 45271 | 670366 | 127 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54 |  |  | 33 | 43 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2657 | 20781825201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 560 | 749 | 748 | 1 | 0 | 0 | 147 | 42 | 13545525 | 150000 | 13395525 | 13574913 | 13974107 | 0 | 0 | 0 | 13974107 | 14346429 | 400515 | 29388 | 101 | 0 | 30 | 66698 | 0 | 0 | 12 | 26717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 99695 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-12 | QTR3 | 19/20 | 2019-08-17 | QTR1 | 19/20 | 214 | 16380282.85 | B6 | ACC - LIQUIDATED SAVINGS | 42 | 46 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 81763 | 65 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67 |  |  | 50 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 362855 | 62 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92 |  |  | 55 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2679 | 43617415201 | 2017-12-06 | QTR2 | 17/18 | 2 | 2 | 350 | 518 | 518 | 0 | 0 | 0 | 100 | 68 | 10753984 | 78530 | 10675454 | 10978696 | 11000190 | 0 | 0 | 0 | 11000190 | 11198057 | 197867 | 224712 | 67 | 0 | 12 | 149047 | 0 | 0 | 56 | 21709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 170756 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-21 | QTR3 | 19/20 | 2019-09-19 | QTR1 | 19/20 | 208 | 7872133.21 |  |  | 62 | 33 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 8616 | 80 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07 |  |  | 25 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 27471 | 62 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 0 | 54 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 66083 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2689 | 43616115201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 270 | 351 | 331 | 20 | 0 | 0 | 81 | 0 | 1995665 | 50000 | 1945665 | 1995665 | 2049720 | 0 | 0 | 0 | 2049720 | 2101020 | 51299 | 0 | 22 | 0 | 0 | 24965 | 0 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28054 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | QTR3 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 216 | 2153022.57 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14546489 | 0 | 0 | 0 | 14546489 | 15202892 | 656402 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3743642 | 52262 | 53332 | 27 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59 |  |  | 22 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 86773 | 31 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39 |  |  | 10 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2708 | 44216935201 | 2019-04-24 | QTR4 | 18/19 | 1 | 3 | 120 | 139 | 75 | 64 | 0 | 0 | 19 | 0 | 368985 | 120 | 368865 | 374417 | 391272 | 0 | 0 | 0 | 391272 | 387389 | 0 | 5432 | 9 | 0 | 0 | 1160 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 | 2019-10-25 | QTR2 | 19/20 | 208 | 334520.6 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2723 | 43762015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 120 | 143 | 143 | 0 | 0 | 0 | 23 | 0 | 1658214 | 50000 | 1608214 | 1658214 | 1598015 | 0 | 0 | 0 | 1598015 | 1602638 | 4623 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 | 2019-07-16 | QTR1 | 19/20 | 214 | 2124298.79 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 0 | 5 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2730 | 43429715201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 144 | 139 | 5 | 0 | 0 | 24 | 0 | 2680388 | 50000 | 2630388 | 2680388 | 2824608 | 0 | 0 | 0 | 2824608 | 2824608 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 | 2019-10-15 | QTR2 | 19/20 | 209 | 3620026.94 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | -1459708 | 16826383 | 385 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 223 | 0 | 0 | -18219 | 0 |  | DO
02DO | 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 11 | 798 | 1068 | 1998 | -930 | 930 | 0 | 127 | 143 | 84850000 | 175000 | 84675000 | 85372612 | 84851152 | -10428635 | 0 | -10428635 | 74422517 | 78818095 | 4395578 | 522612 | 82 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 564185 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 10 | 45 | 0 | 0 | -271502 | 0 |  | DO
02DO | 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | -1251611 | -606983 | 51 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V70 | 42747515201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 350 | 579 | 577 | 2 | 0 | 0 | 229 | 0 | 4483000 | 51665 | 4431335 | 4642146 | 4688789 | 0 | 0 | 0 | 4688789 | 4688881 | 92 | 159146 | 25 | 0 | 0 | 18680 | 0 | 0 | 0 | 40938 | 1341 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 166914 | 1341 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 208 | 5283434.02 |  |  | 0 | 93 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 30442 | 44 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25 |  |  | 7 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 656701 | 89 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79 |  |  | 27 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 0 | 67 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | -3969 | 52 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46 |  |  | 0 | 37 | 0 | 0 | -60481 | 0 |  | DO
02DO | 02 | E2W52 | 42849815201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 300 | 324 | 261 | 63 | 0 | 0 | 24 | 0 | 730881 | 39951 | 690930 | 756196 | 713128 | 0 | 0 | 0 | 713128 | 713129 | 0 | 25315 | 9 | 0 | 0 | 53237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53237 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-14 | QTR3 | 19/20 | 2019-10-29 | QTR2 | 19/20 | 208 | 752277.84 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W96 | 43307515201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 350 | 401 | 349 | 52 | 0 | 0 | 51 | 0 | 4411000 | 50000 | 4361000 | 4455781 | 4414330 | 0 | 0 | 0 | 4414330 | 4414364 | 34 | 44781 | 28 | 0 | 0 | 16525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61306 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-10-16 | QTR2 | 19/20 | 208 | 4144135.21 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X07 | 20956525201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 60 | 72 | 72 | 0 | 0 | 0 | 12 | 0 | 327059 | 16215 | 310844 | 327059 | 288640 | 0 | 0 | 0 | 288640 | 288640 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 | 2019-11-26 | QTR2 | 19/20 | 208 | 337947.23 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 0 | 26 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X44 | 42879715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 200 | 428 | 428 | 0 | 0 | 0 | 130 | 98 | 1990108 | 50000 | 1940108 | 2637472 | 2547298 | 0 | 0 | 0 | 2547298 | 2542607 | -4691 | 647363 | 37 | 60 | 95 | 608011 | 0 | 0 | 3 | 4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 98 | 612548 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 | 2019-12-05 | QTR2 | 19/20 | 216 | 2271972.07 |  |  | 3 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X60 | 43025915201 | 2018-08-15 | QTR1 | 18/19 | 1 | 0 | 280 | 326 | 325 | 1 | 0 | 0 | 40 | 6 | 1328017 | 50000 | 1278017 | 1328017 | 1207862 | 0 | 0 | 0 | 1207862 | 1207862 | 0 | 0 | 18 | 0 | 6 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 875 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 | 2019-12-04 | QTR2 | 19/20 | 208 | 1798375.14 |  |  | 6 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X61 | 43496915201 | 2018-08-15 | QTR1 | 18/19 | 2 | 0 | 180 | 210 | 230 | -20 | 20 | 0 | 30 | 0 | 2118153 | 50000 | 2068153 | 2118153 | 2024485 | -33300 | 0 | -33300 | 1991185 | 1991185 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-01-22 | QTR3 | 19/20 | 2019-10-01 | QTR2 | 19/20 | 209 | 2333869.85 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X68 | 43500015201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 125 | 132 | 112 | 20 | 0 | 0 | 7 | 0 | 925745 | 45595 | 880149 | 925745 | 888997 | 0 | 0 | 0 | 888997 | 888989 | -8 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-09-23 | QTR1 | 19/20 | 209 | 952358.87 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 157836 | 188 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3485 | 42695315201 | 2016-04-27 | QTR4 | 15/16 | 2 | 1 | 200 | 314 | 351 | -37 | 37 | 0 | 113 | 1 | 3574230 | 50000 | 3524230 | 3575445 | 3569976 | -104007 | 0 | -104007 | 3465969 | 3477125 | 11156 | 1215 | 52 | 0 | 1 | 1215 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 6091 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 | 2017-06-30 | QTR4 | 16/17 | 308 | 3028499.48 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | -84026 | 68219 | 39 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3543 | 22044275201 | 2015-09-30 | QTR1 | 15/16 | 1 | 18 | 830 | 1304 | 1304 | 0 | 0 | 0 | 435 | 39 | 29686177 | 150000 | 29536177 | 35844062 | 36589864 | 0 | 0 | 0 | 36589864 | 36787330 | 244313 | 6157885 | 342 | 12 | 14 | 166013 | 0 | 0 | 15 | 229697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 578955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 224474 | 0 | 0 | 0 | 4978544 | 83847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 39 | 6135882 | 83847 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-07-29 | QTR1 | 19/20 | 308 | 37447263.92 |  |  | 12 | 81 | 0 | 0 | -41801 | 0 |  | CO
03CO | 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 8875 | 51756 | 76 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3586 | 42862415201 | 2018-06-13 | QTR4 | 17/18 | 1 | 4 | 340 | 451 | 449 | 2 | 0 | 0 | 111 | 0 | 4214542 | 0 | 4214542 | 4293135 | 4297521 | 0 | 0 | 0 | 4297521 | 4255328 | -5203 | 78594 | 50 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13328 | 0 | 30 | 0 | 41604 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-11-13 | QTR2 | 19/20 | 321 | 3958245.51 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 0 | 66 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3614 | 43228815201 | 2018-08-29 | QTR1 | 18/19 | 1 | 2 | 120 | 238 | 238 | 0 | 0 | 0 | 78 | 40 | 776874 | 0 | 776874 | 1103417 | 1178529 | 0 | 0 | 0 | 1178529 | 1178529 | 0 | 326542 | 62 | 0 | 40 | 326542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326542 | 0 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 | 2019-07-03 | QTR1 | 19/20 | 308 | 825049.02 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 373777 | 60427 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 6645 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9 |  |  | 3 | 41 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 168914 | 26513 | 52 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 | 2019-01-11 | QTR3 | 18/19 | 308 | 0 |  |  | 5 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 334168 | -32998 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 0 | -2208 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 321209 | 405998 | 157 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62 |  |  | 13 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 57366 | 27889 | 69 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76 |  |  | 7 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 100163 | 31248 | 167 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | -464 | 209861 | 112 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3673 | 43774415201 | 2018-09-26 | QTR1 | 18/19 | 1 | 4 | 180 | 268 | 262 | 6 | 0 | 0 | 52 | 36 | 7942048 | 83065 | 7858983 | 7802040 | 7940568 | 0 | 0 | 0 | 7940568 | 7896410 | -44158 | -140008 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -140008 | 0 | 0 | 0 | 49174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -90833 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 | 2019-09-05 | QTR1 | 19/20 | 321 | 8459567.2 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3678 | 43627015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 180 | 208 | 179 | 29 | 0 | 0 | 28 | 0 | 4020176 | 50000 | 3970176 | 4016156 | 4196886 | 0 | 0 | 0 | 4196886 | 4189347 | -7539 | -4020 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 32860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28840 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 | 2019-12-06 | QTR2 | 19/20 | 321 | 4510561.96 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3688 | 44038315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 134 | 120 | 14 | 0 | 0 | 14 | 0 | 354899 | 18499 | 336400 | 354899 | 344281 | 0 | 0 | 0 | 344281 | 344281 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 321 | 390454.14 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 0 | 13 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95 |  |  | 1 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 148555 | 3908 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 0 | -4732 | 101 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 | 2019-05-13 | QTR4 | 18/19 | 308 | 795145 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R15 | 43730715201 | 2018-04-12 | QTR4 | 17/18 | 2 | 0 | 120 | 195 | 199 | -4 | 4 | 0 | 75 | 0 | 847761 | 42761 | 805000 | 847761 | 805000 | -6660 | 0 | -6660 | 798340 | 805000 | 6660 | 0 | 44 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 308 | 968822.89 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R27 | 40410835201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 90 | 121 | 119 | 2 | 0 | 0 | 31 | 0 | 497771 | 26481 | 471290 | 497771 | 462232 | 0 | 0 | 0 | 462232 | 462232 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 | 2019-11-19 | QTR2 | 19/20 | 314 | 568464.05 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R52 | 43627225201 | 2019-01-10 | QTR3 | 18/19 | 1 | 1 | 180 | 215 | 203 | 12 | 0 | 0 | 34 | 1 | 1432597 | 50000 | 1382597 | 1438332 | 1321040 | 0 | 0 | 0 | 1321040 | 1327923 | 6884 | 5735 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 | 2019-10-29 | QTR2 | 19/20 | 308 | 1931230.61 |  |  | 1 | 12 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 63342 | 76927 | 41 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S52 | 41767755201 | 2019-05-09 | QTR4 | 18/19 | 1 | 0 | 90 | 170 | 168 | 2 | 0 | 0 | 80 | 0 | 551256 | 24827 | 526429 | 551256 | 487293 | 0 | 0 | 0 | 487293 | 487293 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 | 2020-01-16 | QTR3 | 19/20 | 314 | 525116.42 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4418 | 22989615201 | 2015-07-29 | QTR1 | 15/16 | 7 | 5 | 1005 | 1118 | 1118 | 0 | 0 | 0 | 113 | 0 | 17423228 | 150000 | 17273228 | 17585616 | 15704340 | 0 | 0 | 0 | 15704340 | 15605066 | -82422 | 162388 | 51 | 0 | 0 | -39118 | 0 | 0 | 0 | 189822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11593 | 11593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162297 | 11593 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 | 2019-01-25 | QTR3 | 18/19 | 409 | 22527836.07 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 442812 | 198133 | 145 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16 |  |  | 8 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4433 | 42872415201 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 601 | 960 | 974 | -14 | 14 | 0 | 302 | 61 | 16224277 | 150000 | 16074277 | 17235975 | 16795691 | -46980 | -64000 | -110980 | 16684711 | 16774147 | 140685 | 1011698 | 254 | 0 | 0 | 284349 | 0 | 0 | 58 | 769055 | 15997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1059392 | 20397 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-02-25 | QTR3 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 412 | 14991647.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4444 | 43270515201 | 2016-12-07 | QTR2 | 16/17 | 4 | 8 | 910 | 1190 | 1005 | 185 | 0 | 0 | 259 | 21 | 27999900 | 150000 | 27849900 | 28775420 | 29356382 | 0 | 0 | 0 | 29356382 | 30041255 | 725124 | 775520 | 216 | 0 | 21 | 446126 | 0 | 0 | 0 | 206370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 683157 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-02-11 | QTR3 | 19/20 | 2019-11-26 | QTR2 | 19/20 | 408 | 34103305.86 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4452 | 43166615201 | 2017-01-25 | QTR3 | 16/17 | 2 | 4 | 396 | 484 | 478 | 6 | 0 | 0 | 88 | 0 | 3407245 | 50000 | 3357245 | 3524212 | 3504637 | 0 | 0 | 0 | 3504637 | 3537514 | 69412 | 116967 | 67 | 0 | 0 | 52621 | 51166 | 0 | 0 | 68491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126406 | 51166 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-06 | QTR3 | 19/20 | 2018-10-02 | QTR2 | 18/19 | 412 | 3478134.48 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 855652 | 75851 | 215 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 189028 | 165338 | 66 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18 |  |  | 30 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7138333 | 123672 | 533617 | 55 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | -6176 | 89 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55 |  |  | 28 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 308276 | 109 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 47624 | 74 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4480 | 43166515201 | 2018-04-25 | QTR4 | 17/18 | 2 | 1 | 214 | 274 | 273 | 1 | 0 | 0 | 48 | 12 | 1327221 | 50000 | 1277221 | 1366521 | 1298578 | 0 | 0 | 0 | 1298578 | 1298125 | -453 | 39300 | 29 | 0 | 0 | 0 | 0 | 0 | 12 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42392 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 | 2019-06-30 | QTR4 | 18/19 | 412 | 1330304.19 |  |  | 12 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4486 | 43165715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 10 | 353 | 442 | 442 | 0 | 0 | 0 | 44 | 45 | 3260393 | 50000 | 3210393 | 3609674 | 3402444 | 0 | 0 | 0 | 3402444 | 3396789 | -5656 | 349282 | 19 | 0 | 45 | 162960 | 125042 | 0 | 0 | 157599 | 106623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 387158 | 231666 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 | 2019-10-28 | QTR2 | 19/20 | 412 | 3504742.12 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 0 | 6 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 11869 | 31 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95 |  |  | 6 | 8 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | -6213797 | 2243984 | 183 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 45 | 0 | 0 | -404828 | 0 |  | DO
04DO | 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | -417090 | -338192 | 219 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 89 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | -3249187 | 3281488 | 165 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 64 | 0 | 0 | -202797 | 0 |  | DO
04DO | 04 | E4P04 | 23193225201 | 2014-04-16 | QTR4 | 13/14 | 7 | 11 | 979 | 1575 | 1811 | -236 | 236 | 0 | 297 | 299 | 32540300 | 150000 | 32390300 | 33830739 | 33682875 | -2003878 | 0 | -2003878 | 31678997 | 33229430 | 1655512 | 1290439 | 225 | 0 | 299 | 1014970 | 0 | 0 | 0 | 128450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299 | 1187254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 | 2019-07-12 | QTR1 | 19/20 | 409 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 72 | 0 | 0 | -960 | 0 |  | DO
04DO | 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 58245 | 22 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 76 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | -4739 | 364238 | 220 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR | 6 | 71 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q64 | 43310855201 | 2015-05-29 | QTR4 | 14/15 | 1 | 30 | 1400 | 1506 | 1365 | 141 | 0 | 0 | 106 | 0 | 153917279 | 150000 | 153767279 | 162463226 | 162823699 | 0 | 3720000 | 3720000 | 166543699 | 162492246 | -3709579 | 8545947 | 57 | 0 | 0 | 1603424 | 0 | 0 | 0 | 2717641 | 75013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480038 | 468544 | 0 | 0 | 1150398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8290048 | 543557 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 | 2019-10-03 | QTR2 | 19/20 | 406 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 49 | 0 | 0 | -669018 | 0 |  | DO
04DO | 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 1860107 | 73 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 172641 | 33902 | 24 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 48308 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 0 | 0 | 1 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BE626 | 43787225201 | 2018-05-24 | QTR4 | 17/18 | 1 | 0 | 280 | 344 | 213 | 131 | 0 | 0 | 64 | 0 | 720000 | 0 | 720000 | 720000 | 720000 | 0 | 0 | 0 | 720000 | 720000 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-01-17 | QTR3 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 507 | 720000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | -3056235 | 3576803 | 117 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 3 | 48 | 0 | 0 | -155690 | 0 |  | CO
05CO | 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 19031 | 14 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5591 | 42823815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 500 | 652 | 649 | 3 | 0 | 0 | 112 | 40 | 16694356 | 150000 | 16544356 | 16972569 | 16490950 | 0 | 0 | 0 | 16490950 | 16700809 | 209859 | 278213 | 41 | 0 | 40 | 16791 | 0 | 0 | 0 | 143061 | 49425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137620 | 132029 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 332991 | 181454 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-13 | QTR3 | 19/20 | 2019-08-15 | QTR1 | 19/20 | 514 | 15183626.94 |  |  | 0 | 71 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 161314 | 43 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5616 | 43065515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 260 | 334 | 334 | 0 | 0 | 0 | 67 | 7 | 4231483 | 53000 | 4178483 | 4229830 | 4248590 | 0 | 0 | 0 | 4248590 | 4402057 | 153467 | -1653 | 46 | 0 | 0 | -14065 | 0 | 0 | 2 | 5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 54377 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 46115 | 2422 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-04 | QTR3 | 19/20 | 2019-05-17 | QTR4 | 18/19 | 512 | 5394340.01 |  |  | 7 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 26406 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 20194 | 36 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871 |  |  | 17 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 426 | 29 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W11 | 24262635201 | 2014-11-21 | QTR2 | 14/15 | 3 | 6 | 900 | 1229 | 1229 | 0 | 0 | 0 | 288 | 41 | 43150089 | 150000 | 43000089 | 45682181 | 45886261 | 0 | 0 | 0 | 45886261 | 43227195 | -2633738 | 2532092 | 232 | 0 | 41 | 2571393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 2600543 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 | 2018-07-08 | QTR1 | 18/19 | 515 | 48952301.58 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 41 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10359714 | -459862 | -387154 | 69 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y20 | 42690435201 | 2016-11-04 | QTR2 | 16/17 | 2 | 5 | 547 | 928 | 921 | 7 | 0 | 0 | 276 | 105 | 26771800 | 150000 | 26621800 | 27777188 | 27684932 | 0 | 0 | 0 | 27684932 | 28031909 | 444186 | 1005388 | 215 | 0 | 14 | 243217 | 16025 | 0 | 91 | 756982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1000199 | 16025 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-01-08 | QTR3 | 19/20 | 2019-08-02 | QTR1 | 19/20 | 514 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1363962 | 39 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842 |  |  | 60 | 51 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 1940 | -10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 | 2017-05-14 | QTR4 | 16/17 | 509 | 843684 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | -795 | 50000 | 60 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z09 | 41299445214 | 2017-12-14 | QTR2 | 17/18 | 1 | 1 | 515 | 551 | 514 | 37 | 0 | 0 | 36 | 0 | 5757000 | 50000 | 5707000 | 5860741 | 5841571 | 0 | 0 | 0 | 5841571 | 5844608 | 3037 | 103741 | 7 | 0 | 0 | 77312 | 77312 | 0 | 0 | 26429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134571 | 77312 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 | 2019-07-17 | QTR1 | 19/20 | 507 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z23 | 43564715201 | 2018-05-01 | QTR4 | 17/18 | 1 | 1 | 240 | 281 | 281 | 0 | 0 | 0 | 41 | 0 | 1013390 | 50000 | 963390 | 1008318 | 958318 | -736 | 0 | -736 | 957582 | 957220 | -362 | -5072 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-03-02 | QTR3 | 19/20 | 2019-07-10 | QTR1 | 19/20 | 514 | 1052401 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 133799 | 15 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25 |  |  | 1 | 33 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 0 | 33356 | 25 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-07-22 | QTR1 | 19/20 | 513 | 480184 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z45 | 43733915201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 230 | 343 | 343 | 0 | 0 | 0 | 98 | 15 | 6123814 | 81000 | 6042814 | 6203979 | 6135165 | 0 | 0 | 0 | 6135165 | 6001858 | -114476 | 80166 | 64 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-18 | QTR3 | 19/20 | 2020-01-30 | QTR3 | 19/20 | 512 | 8194285 |  |  | 10 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 | 2019-07-18 | QTR1 | 19/20 | 509 | 441431 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 0 | 0 | 22 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5 |  |  | 11 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2 |  |  | 18 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 0 | 3000 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 513 | 554880 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z76 | 44097015201 | 2019-06-04 | QTR4 | 18/19 | 1 | 0 | 90 | 126 | 2 | 124 | 0 | 0 | 36 | 0 | 167070 | 12438 | 154632 | 167070 | 148419 | 0 | 0 | 0 | 148419 | 148419 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 | 2020-01-06 | QTR3 | 19/20 | 507 | 271247.25 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6337 | 41809115201 | 2015-10-28 | QTR2 | 15/16 | 7 | 22 | 600 | 1055 | 1055 | 0 | 0 | 0 | 324 | 131 | 14239526 | 267180 | 13972346 | 16636939 | 16898897 | 0 | 500000 | 500000 | 17398897 | 16914510 | -453877 | 2397413 | 147 | 0 | 87 | 1404877 | 434699 | 120 | 44 | 573331 | 258449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573254 | 54307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 0 | 0 | 120 | 131 | 2554384 | 747455 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 | 2019-02-15 | QTR3 | 18/19 | 606 | 13498168.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6338 | 41463315201 | 2016-01-27 | QTR3 | 15/16 | 4 | 11 | 560 | 1082 | 1082 | 0 | 0 | 0 | 352 | 170 | 11118409 | 242209 | 10876200 | 12716281 | 13284136 | 0 | 0 | 0 | 13284136 | 13366087 | 119047 | 1597872 | 138 | 7 | 170 | 1133148 | 332615 | 137 | 0 | 119548 | 25682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 276565 | 23432 | 0 | 0 | 8312 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 170 | 1537573 | 390040 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 | 2019-05-23 | QTR4 | 18/19 | 606 | 10197839.36 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 725324 | 52 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | -622662 | 376451 | 74 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 40 | 0 | 0 | -514052 | 0 |  | CO
06CO | 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 5872 | 2030258 | 59 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 21903 | 44 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 37940 | 56 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 80247 | 31 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 92454 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 0 | 48 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6438 | 43117015201 | 2018-05-23 | QTR4 | 17/18 | 6 | 2 | 320 | 363 | 295 | 68 | 0 | 0 | 43 | 0 | 3669797 | 51765 | 3618032 | 3847108 | 3668181 | 0 | 250000 | 250000 | 3918181 | 3697899 | -220283 | 177311 | 23 | 0 | 0 | 82758 | 0 | 0 | 0 | 14636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16895 | 16211 | 0 | 0 | 0 | 0 | 0 | 0 | 189909 | 16211 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 | 2019-08-07 | QTR1 | 19/20 | 606 | 4444325.03 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6462 | 43792215201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 160 | 195 | 193 | 2 | 0 | 0 | 35 | 0 | 672522 | 35087 | 637435 | 672522 | 627588 | 0 | 0 | 0 | 627588 | 627091 | -497 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 | 2019-11-25 | QTR2 | 19/20 | 606 | 724071.25 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | -24 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 | 2019-07-19 | QTR1 | 19/20 | 606 | 324690 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 1013 | 67062 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 649560 | 1806784 | 96 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K58 | 43081315201 | 2019-01-31 | QTR3 | 18/19 | 3 | 1 | 200 | 224 | 186 | 38 | 0 | 0 | 24 | 0 | 1100030 | 52315 | 1047715 | 1101649 | 1024191 | 0 | 100000 | 100000 | 1124191 | 1025137 | -97435 | 1619 | 16 | 0 | 0 | 557 | 0 | 0 | 0 | 16202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17525 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 | 2019-11-30 | QTR2 | 19/20 | 606 | 1216039.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | -358123 | 1067468 | 84 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 0 | 24000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 | 2019-10-04 | QTR2 | 19/20 | 606 | 404500 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 0 | 23 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L37 | 42919325201 | 2018-01-25 | QTR3 | 17/18 | 4 | 3 | 200 | 241 | 218 | 23 | 0 | 0 | 41 | 0 | 1491900 | 50260 | 1441640 | 1633114 | 1580093 | 0 | 60000 | 60000 | 1640093 | 1562174 | -60174 | 141214 | 29 | 0 | 0 | 4537 | 0 | 0 | 0 | 82537 | 9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48121 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135195 | 14309 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 | 2019-12-04 | QTR2 | 19/20 | 606 | 1421302.2 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | -87 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7389 | 43272015201 | 2017-01-25 | QTR3 | 16/17 | 4 | 11 | 350 | 542 | 542 | 0 | 0 | 0 | 192 | 0 | 12988889 | 109000 | 12879889 | 13889049 | 13996342 | 0 | 0 | 0 | 13996342 | 14019355 | 112797 | 900160 | 162 | 0 | 0 | 619080 | 0 | 0 | 0 | 112343 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677937 | 2775 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 | 2018-10-03 | QTR2 | 18/19 | 798 | 14634544.46 |  |  | 0 | 30 | 0 | 0 | -84321 | 0 |  | CO
07CO | 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 11195 | 18352 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400 |  |  | 10 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 0 | 68 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7399 | 43653015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 145 | 210 | 211 | -1 | 1 | 0 | 48 | 17 | 1314062 | 50000 | 1264062 | 1314062 | 1279715 | -1665 | 0 | -1665 | 1278050 | 1277840 | -210 | 0 | 29 | 0 | 0 | 0 | 0 | 10 | 12 | 15865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5990 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 21855 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 | 2019-10-29 | QTR2 | 19/20 | 796 | 1374960.82 |  |  | 17 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 6728 | 41 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM | 12 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7427 | 43704015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 160 | 205 | 189 | 16 | 0 | 0 | 27 | 18 | 1130856 | 50000 | 1080856 | 1130856 | 1101423 | 0 | 0 | 0 | 1101423 | 1102091 | 668 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 | 2019-12-16 | QTR2 | 19/20 | 799 | 1234500 |  |  | 18 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7429 | 43753015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 120 | 132 | 101 | 31 | 0 | 0 | 12 | 0 | 1704462 | 50000 | 1654462 | 1704462 | 1672069 | 0 | 0 | 0 | 1672069 | 1672069 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 | 2019-10-17 | QTR2 | 19/20 | 796 | 2200000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | -1461417 | 2388357 | 330 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR | 76 | 85 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K19 | 43476515201 | 2014-10-20 | QTR2 | 14/15 | 2 | 16 | 1200 | 1842 | 1829 | 13 | 0 | 0 | 210 | 432 | 35360313 | 120000 | 35240313 | 59863754 | 59642810 | 0 | 0 | 0 | 59642810 | 59439123 | 0 | 24503441 | 97 | 0 | 362 | 23073894 | 0 | 0 | 0 | 379221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 901989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 24357946 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 | 2019-11-25 | QTR2 | 19/20 | 714 | 35360312.5 |  |  | 119 | 113 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K24 | 41101145201 | 2015-04-09 | QTR4 | 14/15 | 3 | 20 | 1100 | 1320 | 1320 | 0 | 0 | 0 | 188 | 32 | 94976100 | 150000 | 94826100 | 96934830 | 96454835 | 0 | 0 | 0 | 96454835 | 95867383 | -259483 | 1958730 | 108 | 2 | 30 | 982160 | 90496 | 0 | 0 | 91279 | 4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567939 | 0 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 1718138 | 127398 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 | 2019-09-30 | QTR1 | 19/20 | 714 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 2 | 78 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | -265912 | 1412899 | 124 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 56 | 53 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 232401 | 76 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 2402 | 0 | 242 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000 |  |  | 7 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 197052 | 173 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | -14425 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M26 | 25839935201 | 2018-12-12 | QTR2 | 18/19 | 2 | 0 | 90 | 194 | 194 | 0 | 0 | 0 | 87 | 17 | 1194104 | 30000 | 1164104 | 1194104 | 1177035 | 0 | 0 | 0 | 1177035 | 1177035 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 | 2019-11-06 | QTR2 | 19/20 | 796 | 850000 |  |  | 17 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M27 | 43648015201 | 2018-12-12 | QTR2 | 18/19 | 1 | 2 | 150 | 180 | 180 | 0 | 0 | 0 | 30 | 0 | 1274649 | 45000 | 1229649 | 1382195 | 1318471 | 0 | 0 | 0 | 1318471 | 1320688 | 2217 | 107546 | 21 | 0 | 0 | 93140 | 0 | 0 | 0 | 22511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115651 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 | 2019-09-10 | QTR1 | 19/20 | 798 | 980000 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 | 2019-09-12 | QTR1 | 19/20 | 798 | 175000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M32 | 43751815201 | 2019-03-13 | QTR3 | 18/19 | 1 | 0 | 165 | 215 | 215 | 0 | 0 | 0 | 50 | 0 | 852730 | 40000 | 812730 | 852730 | 751999 | 0 | 0 | 0 | 751999 | 752000 | 1 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 | 2020-02-14 | QTR3 | 19/20 | 796 | 850000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R07 | 43845015201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 500 | 572 | 572 | 0 | 0 | 0 | 72 | 0 | 2568748 | 50000 | 2518748 | 2568748 | 2497748 | 0 | 0 | 0 | 2497748 | 2497782 | 34 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-01-29 | QTR3 | 19/20 | 2019-09-24 | QTR1 | 19/20 | 796 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R60 | 43920615201 | 2017-09-07 | QTR1 | 17/18 | 1 | 2 | 540 | 637 | 633 | 4 | 0 | 0 | 83 | 14 | 12005445 | 85975 | 11919470 | 12159938 | 12017053 | 0 | 30000 | 30000 | 12047053 | 12031297 | 38737 | 154493 | 48 | 0 | 0 | 9573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 115055 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 | 2019-07-03 | QTR1 | 19/20 | 714 | 11747696.43 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT | 14 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | -965750 | -115989 | 28 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 40000 | 34 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53 |  |  | 10 | 22 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | -1735624 | 1811802 | 56 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q41 | 43516515201 | 2017-02-14 | QTR3 | 16/17 | 4 | 6 | 280 | 520 | 520 | 0 | 0 | 0 | 187 | 53 | 15839502 | 62339 | 15777163 | 16427426 | 16013444 | -22000 | 0 | -22000 | 15991444 | 16637324 | 657394 | 587924 | 130 | 0 | 20 | 279691 | 0 | 0 | 33 | 128973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 463933 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 | 2018-10-31 | QTR2 | 18/19 | 854 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q54 | 43517115201 | 2017-06-06 | QTR4 | 16/17 | 4 | 9 | 315 | 573 | 645 | -72 | 72 | 0 | 189 | 69 | 16868340 | 150000 | 16718340 | 17223693 | 16580725 | -451756 | 0 | -451756 | 16128969 | 17348378 | 1219409 | 355352 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 175352 | 0 | 0 | 0 | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 264477 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-30 | QTR3 | 19/20 | 2019-06-28 | QTR4 | 18/19 | 854 | 18298995 |  |  | 0 | 96 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 34423 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 176726 | 494166 | 44 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24 |  |  | 14 | 52 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R46 | 44154915201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 125 | 160 | 160 | 0 | 0 | 0 | 33 | 2 | 648447 | 32811 | 615636 | 654795 | 614302 | 0 | 0 | 0 | 614302 | 607816 | -137 | 6348 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 | 2020-01-10 | QTR3 | 19/20 | 854 | 709931.87 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | -6566 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 148560 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0