## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 96142836 | 95047630 | 98823314 | 97882780 | 2790000 | 98636611 | 3.776% | 93.55% | 2891925 | 3.043% | 2680479 | 2.788% | 5671 | 999 | 17.62% | 391 | 6.895% | 59 | 1.04% | 295 | 5.202% | 6025 | 6.242% | 7405 | 6686 | 5296 | -6.613% | 93.55%
| District Let | 91476004 | 90725195 | 93821301 | 92165641 | 2405000 | 93257361 | 2.791% | 100% | 2429074 | 2.677% | 2345297 | 2.564% | 3115 | 403 | 12.94% | 199 | 6.388% | 41 | 1.316% | 369 | 11.85% | 3525 | 13.16% | 4127 | 3779 | 3177 | 1.99% | 84.62%
| All Contracts | 187618840 | 185772825 | 192644615 | 190048421 | 5195000 | 191893972 | 3.295% | 95.45% | 5320999 | 2.864% | 5025776 | 2.679% | 8786 | 1402 | 15.96% | 590 | 6.715% | 100 | 1.138% | 664 | 7.557% | 9550 | 8.696% | 11532 | 10465 | 8473 | -3.562% | 90.91%
2 | Central Let | 253561011 | 251562460 | 257631649 | 259123712 | 0 | 263699998 | 4.825% | 75% | 4341216 | 1.726% | 4070639 | 1.605% | 8824 | 1655 | 18.76% | 1051 | 11.91% | 127 | 1.439% | 1397 | 15.83% | 10348 | 17.27% | 13060 | 12850 | 10144 | 14.96% | 67.86%
| District Let | 363629244 | 362071638 | 382350490 | 381303153 | 0 | 372343437 | 2.837% | 79.17% | 18876090 | 5.213% | 18721246 | 5.148% | 8447 | 1097 | 12.99% | 940 | 11.13% | 249 | 2.948% | 1445 | 17.11% | 10141 | 20.05% | 12178 | 12680 | 10643 | 26% | 75%
| All Contracts | 617190255 | 613634098 | 639982139 | 640426865 | 0 | 636043435 | 3.652% | 76.92% | 23217306 | 3.784% | 22791885 | 3.693% | 17271 | 2752 | 15.93% | 1991 | 11.53% | 376 | 2.177% | 2842 | 16.46% | 20489 | 18.63% | 25238 | 25530 | 20787 | 20.36% | 71.15%
3 | Central Let | 148813412 | 147156148 | 156383733 | 157501907 | 0 | 157247853 | 6.858% | 85.29% | 7671013 | 5.213% | 7570319 | 5.087% | 7339 | 2659 | 36.23% | 979 | 13.34% | 369 | 5.028% | 350 | 4.769% | 8058 | 9.797% | 11696 | 11570 | 7932 | 8.08% | 79.41%
| District Let | 12655191 | 12284414 | 12774768 | 12605871 | 0 | 12417706 | 1.085% | 100% | 116116 | 0.9452% | 119577 | 0.9449% | 1495 | 379 | 25.35% | 227 | 15.18% | 80 | 5.351% | 2 | 0.1338% | 1577 | 5.485% | 2183 | 2104 | 1498 | 0.2007% | 91.67%
| All Contracts | 161468603 | 159440562 | 169158501 | 170107778 | 0 | 169665559 | 6.413% | 89.13% | 7787129 | 4.884% | 7689896 | 4.762% | 8834 | 3038 | 34.39% | 1206 | 13.65% | 449 | 5.083% | 352 | 3.985% | 9635 | 9.067% | 13879 | 13674 | 9430 | 6.747% | 82.61%
4 | Central Let | 189565763 | 187772333 | 193460495 | 185013361 | -239000 | 185522333 | -1.198% | 96.15% | 3900242 | 2.077% | 3894731 | 2.055% | 10844 | 1976 | 18.22% | 808 | 7.451% | 47 | 0.4334% | 792 | 7.304% | 11683 | 7.737% | 14463 | 14192 | 11408 | 5.201% | 96.15%
| District Let | 583834589 | 582137863 | 603399359 | 602357366 | 5140000 | 589552390 | 1.274% | 90% | 18773169 | 3.225% | 19564768 | 3.351% | 12306 | 1440 | 11.7% | 758 | 6.16% | 9 | 0.07314% | 779 | 6.33% | 13094 | 6.403% | 15291 | 14703 | 12505 | 1.617% | 90%
| All Contracts | 773400352 | 769910196 | 796859854 | 787370727 | 4901000 | 775074723 | 0.6708% | 93.48% | 22673411 | 2.945% | 23459499 | 3.033% | 23150 | 3416 | 14.76% | 1566 | 6.765% | 56 | 0.2419% | 1571 | 6.786% | 24777 | 7.028% | 29754 | 28895 | 23913 | 3.296% | 93.48%
5 | Central Let | 165724925 | 164440402 | 172275351 | 172656156 | 1044500 | 170217134 | 3.513% | 89.47% | 6657102 | 4.048% | 6550426 | 3.953% | 7110 | 691 | 9.719% | 739 | 10.39% | 91 | 1.28% | 505 | 7.103% | 7706 | 8.383% | 9136 | 8607 | 7177 | 0.9423% | 89.47%
| District Let | 113199019 | 112022556 | 118277882 | 117158640 | 0 | 113800380 | 1.587% | 90.91% | 5295378 | 4.727% | 5078864 | 4.487% | 5816 | 1003 | 17.25% | 589 | 10.13% | 11 | 0.1891% | 693 | 11.92% | 6520 | 12.1% | 8112 | 7945 | 6353 | 9.233% | 86.36%
| All Contracts | 278923944 | 276462958 | 290553233 | 289814796 | 1044500 | 284017514 | 2.733% | 90.24% | 11952480 | 4.323% | 11629290 | 4.169% | 12926 | 1694 | 13.11% | 1328 | 10.27% | 102 | 0.7891% | 1198 | 9.268% | 14226 | 10.06% | 17248 | 16552 | 13530 | 4.673% | 87.8%
6 | Central Let | 103986628 | 101267723 | 111623807 | 110549611 | 2050000 | 110421384 | 9.039% | 84.21% | 8333626 | 8.229% | 7637178 | 7.344% | 6069 | 1093 | 18.01% | 430 | 7.085% | 403 | 6.64% | 536 | 8.832% | 7008 | 15.47% | 8531 | 8037 | 6514 | 7.332% | 84.21%
| District Let | 102097670 | 101372779 | 106778069 | 105498997 | 560000 | 100097176 | -1.258% | 100% | 2756336 | 2.719% | 3147987 | 3.083% | 4110 | 518 | 12.6% | 254 | 6.18% | 28 | 0.6813% | 28 | 0.6813% | 4166 | 1.363% | 4938 | 4729 | 3957 | -3.723% | 100%
| All Contracts | 206084298 | 202640502 | 218401876 | 216048608 | 2610000 | 210518560 | 3.888% | 90.62% | 11089962 | 5.473% | 10785165 | 5.233% | 10179 | 1611 | 15.83% | 684 | 6.72% | 431 | 4.234% | 564 | 5.541% | 11174 | 9.775% | 13469 | 12766 | 10471 | 2.869% | 90.62%
7 | Central Let | 31197084 | 30533304 | 32144668 | 31686207 | 0 | 31684042 | 3.769% | 100% | 936455 | 3.067% | 947585 | 3.037% | 2023 | 486 | 24.02% | 215 | 10.63% | 23 | 1.137% | 92 | 4.548% | 2138 | 5.685% | 2850 | 2892 | 2191 | 8.304% | 92.31%
| District Let | 300331964 | 298760664 | 331336899 | 329462590 | 280000 | 326665741 | 9.34% | 96% | 30501990 | 10.21% | 31004937 | 10.32% | 8566 | 1763 | 20.58% | 800 | 9.339% | 2 | 0.02335% | 861 | 10.05% | 9429 | 10.07% | 11992 | 11836 | 9273 | 8.254% | 92%
| All Contracts | 331529048 | 329293968 | 363481567 | 361148797 | 280000 | 358349783 | 8.824% | 97.37% | 31438445 | 9.547% | 31952522 | 9.638% | 10589 | 2249 | 21.24% | 1015 | 9.585% | 25 | 0.2361% | 953 | 9% | 11567 | 9.236% | 14842 | 14728 | 11464 | 8.263% | 92.11%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 235925419 | 234601603 | 248393690 | 247004621 | 2385000 | 247569647 | 5.528% | 93.33% | 12267831 | 5.229% | 12468270 | 5.285% | 5269 | 729 | 13.84% | 524 | 9.945% | 239 | 4.536% | 892 | 16.93% | 6400 | 21.47% | 7655 | 7416 | 6163 | 16.97% | #VALUE!
| All Contracts | 235925419 | 234601603 | 248393690 | 247004621 | 2385000 | 247569647 | 5.528% | 93.33% | 12267831 | 5.229% | 12468270 | 5.285% | 5269 | 729 | 13.84% | 524 | 9.945% | 239 | 4.536% | 892 | 16.93% | 6400 | 21.47% | 7655 | 7416 | 6163 | 16.97% | 80%
Totals This Qtr | Central Let | 988991659 | 977780000 | 1022343017 | 1014413734 | 5645500 | 1017429355 | 4.055% | 88.24% | 34731579 | 3.552% | 33351357 | 3.372% | 47880 | 9559 | 19.96% | 4613 | 9.635% | 1119 | 2.337% | 3967 | 8.285% | 52966 | 10.62% | 67141 | 64834 | 50662 | 5.81% | 85.29%
| District Let | 1803149100 | 1793976712 | 1897132458 | 1887556879 | 10770000 | 1855703838 | 3.441% | 92.36% | 91015984 | 5.073% | 92450946 | 5.127% | 49124 | 7332 | 14.93% | 4291 | 8.735% | 659 | 1.342% | 5069 | 10.32% | 54852 | 11.66% | 66476 | 65192 | 53569 | 9.049% | 86.81%
| All Contracts | 2792140759 | 2771756712 | 2919475475 | 2901970613 | 16415500 | 2873133193 | 3.657% | 90.13% | 125747563 | 4.537% | 125802303 | 4.506% | 97004 | 16891 | 17.41% | 8904 | 9.179% | 1778 | 1.833% | 9036 | 9.315% | 107818 | 11.15% | 133617 | 130026 | 104231 | 7.45% | 85.99%
Totals Previous Quarter | Central Let | 457707206 | 451811421 | 471276456 | 467057371 | 3564500 | 466538988 | 3.26% | 85.54% | 14258583 | 3.156% | 13569248 | 2.965% | 21682 | 4404 | 20.31% | 2087 | 9.625% | 352 | 1.623% | 1781 | 8.214% | 23815 | 9.838% | 30310 | 29044 | 22553 | 4.017% | 85.54%
| District Let | 1021924588 | 1017173671 | 1058878944 | 1056357178 | 4455000 | 1041425435 | 2.384% | 90.14% | 34574015 | 3.399% | 35421945 | 3.466% | 26176 | 4178 | 15.96% | 2176 | 8.313% | 204 | 0.7793% | 2418 | 9.237% | 28798 | 10.02% | 35151 | 33763 | 27409 | 4.71% | 91.55%
| All Contracts | 1479631794 | 1468985092 | 1530155400 | 1523414549 | 8019500 | 1507964423 | 2.653% | 87.66% | 48832598 | 3.324% | 48991193 | 3.311% | 47858 | 8582 | 17.93% | 4263 | 8.908% | 556 | 1.162% | 4199 | 8.774% | 52613 | 9.936% | 65461 | 62807 | 49962 | 4.396% | 88.31%
Totals Fiscal Year 2018/2019 | Central Let | 1245791056 | 1233826432 | 1290308424 | 1290743418 | 11354325 | 1272211402.08 | 3.111% | 92.68% | 44743423 | 3.626% | 44444005 | 3.568% | 51070 | 10333 | 20.23% | 4417 | 8.649% | 1987 | 3.891% | 2974 | 5.823% | 56031 | 9.714% | 71119 | 69464 | 54714 | 7.135% | 84.15%
| District Let | 1083536931 | 1076274846 | 1166469706 | 1158597181 | 1605000 | 1125497490 | 4.573% | 91.97% | 82452189 | 7.661% | 82932771 | 7.654% | 39155 | 6879 | 17.57% | 3581 | 9.146% | 1190 | 3.039% | 3778 | 9.649% | 44123 | 12.69% | 54718 | 53095 | 42635 | 8.888% | 89.78%
| All Contracts | 2329327987 | 2310101278 | 2456778130 | 2449340599 | 12959325 | 2397708892.08 | 3.792% | 92.36% | 127195612 | 5.506% | 127376776 | 5.468% | 90225 | 17212 | 19.08% | 7998 | 8.865% | 3177 | 3.521% | 6752 | 7.484% | 100154 | 11% | 125837 | 122559 | 97349 | 7.896% | 86.71%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1634 | 43137315201 | 2015-10-28 | QTR2 | 15/16 | 2 | 4 | 325 | 500 | 500 | 108.6% | 1 | 0 | 0 | 0 | 147 | 28 | 8177462 | 97126 | 8080336 | 8672530 | 8450258 | 0 | 0 | 0 | 8450258 | 8318044 | 102.9% | 1 | -132214 | 495068 | 113 | 34 | 0 | 28 | 357778 | 0 | 0 | 0 | 41850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 537929 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2017-12-29 | QTR2 | 17/18 | 115 | 9745220.76
| 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 100.8% | 1 | 410 | 11598 | 6 | 16 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM
| 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 87.63% | 1 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | 107.6% | 1 | -1499517 | 1891710 | 39 | 35 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250656 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 50.62% | 1 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 57.34% | 1 | 6509 | -485989 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 |  | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM
| 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 101.8% | 1 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 108.5% | 1 | 300819 | 240997 | 138 | 47 | 0 | 7 | 224121 | 0 | 0 | 0 | 24860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 261807 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73
| 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 113.2% | 1 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 115.3% | 0 | 795 | 374249 | 101 | 25 | 0 | 33 | 344330 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 374249 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS
| 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 91.5% | 1 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | 104.6% | 1 | -889 | 49336 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 |  | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61
| 01 | T1701 | 43498615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 3 | 580 | 635 | 485 | 74.14% | 1 | 150 | 0 | 0 | 55 | 0 | 8087167 | 75299 | 8011868 | 8023343 | 7632042 | 0 | 570000 | 570000 | 8202042 | 7675787 | 95.81% | 1 | -516267 | -63824 | 40 | 15 | 0 | 0 | 37019 | 0 | 0 | 0 | -73677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29433 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 118 | 8094281.54 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 101.2% | 1 | 0 | 0 | 49 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66
| 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 99.09% | 1 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 98.36% | 1 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82
| 01 | T1706 | 43658615201 | 2018-06-13 | QTR4 | 17/18 | 2 | 1 | 325 | 397 | 374 | 92.92% | 1 | 23 | 0 | 0 | 72 | 0 | 7786066 | 101721 | 7684345 | 7543630 | 7286083 | 0 | 0 | 0 | 7286083 | 7247442 | 94.31% | 1 | -38640 | -242436 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -242436 | 0 | 0 | 0 | -242436 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2019-11-04 | QTR2 | 19/20 | 108 | 9348245.16
| 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 73.6% | 1 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | 105.9% | 1 | -6 | 7262 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93
| 01 | T1711 | 43121915201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 125 | 199 | 213 | 143.2% | 0 | -14 | 14 | 0 | 34 | 40 | 719941 | 34577 | 685364 | 719941 | 689498 | -24975 | 0 | -24975 | 664523 | 663884 | 96.87% | 1 | -639 | 0 | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8973 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-05-27 | QTR4 | 19/20 |  | 2019-12-17 | QTR2 | 19/20 | 113 | 651945.49
| 01 | T1713 | 43355215201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 230 | 408 | 407 | 111.7% | 1 | 1 | 0 | 0 | 178 | 0 | 2526300 | 50000 | 2476300 | 2681334 | 2687161 | 0 | 0 | 0 | 2687161 | 2682036 | 108.3% | 1 | -5125 | 155034 | 128 | 22 | 28 | 0 | 74449 | 0 | 0 | 0 | 130585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 205034 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-10-30 | QTR2 | 19/20 | 115 | 2797558.23 | B0 | ACC - LUMP SUM
| 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 100.7% | 1 | 0 | 0 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM
| 01 | T1725 | 43501515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 0 | 100 | 159 | 159 | 116% | 1 | 0 | 0 | 0 | 59 | 0 | 984573 | 29273 | 955300 | 984573 | 955300 | 0 | 0 | 0 | 955300 | 955300 | 100% | 1 | 0 | 0 | 33 | 10 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-19 | QTR4 | 19/20 |  | 2020-02-21 | QTR3 | 19/20 | 118 | 713682.23 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1727 | 43800715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 175 | 317 | 317 | 126.9% | 0 | 0 | 0 | 0 | 95 | 47 | 2658381 | 50000 | 2608381 | 2763353 | 2697261 | 0 | 0 | 0 | 2697261 | 2689819 | 103.1% | 1 | -4557 | 104972 | 67 | 28 | 0 | 0 | 0 | 0 | 0 | 47 | 96037 | 56605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 102087 | 56605 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-06-08 | QTR4 | 19/20 |  | 2020-01-28 | QTR3 | 19/20 | 113 | 2768479.93
| 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | 106.4% | 1 | -485 | 59543 | 17 | 5 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM
| 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 86.36% | 1 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 93.87% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM
| 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 86.15% | 1 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 99.42% | 1 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36
| 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 100% | 1 | 0 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM
| 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 69% | 1 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 100% | 1 | 0 | 0 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM
| 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 98.34% | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52
| 01 | T1739 | 43837815201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 120 | 148 | 148 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 1095691 | 43494 | 1052197 | 1099220 | 1055726 | 0 | 0 | 0 | 1055726 | 1052773 | 100.1% | 1 | 576 | 3530 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 113 | 979242.1 | B0 | ACC - LUMP SUM
| 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 101% | 1 | 0 | 0 | 11 | 5 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM
| 01 | T1743 | 43800415201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 71 | 107 | 99 | 88.73% | 1 | 8 | 0 | 0 | 36 | 0 | 138436 | 0 | 138436 | 138436 | 138436 | 0 | 0 | 0 | 138436 | 138436 | 100% | 1 | 0 | 0 | 30 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 108 | 179132.62 | B0 | ACC - LUMP SUM
| 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 115.9% | 0 | 0 | 60277 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07
| 01 | T1753 | 43943215201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 200 | 218 | 136 | 59% | 1 | 82 | 0 | 0 | 18 | 0 | 1952155 | 50000 | 1902155 | 1971307 | 1962809 | 0 | 0 | 0 | 1962809 | 1962123 | 103.2% | 1 | -686 | 19152 | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2020-02-24 | QTR3 | 19/20 | 108 | 2489141.93 | B0 | ACC - LUMP SUM
| 01 | T1765 | 43698215201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 90 | 94 | 94 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 371018 | 0 | 371018 | 371018 | 371018 | 0 | 0 | 0 | 371018 | 371018 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 115 | 262342.57
| 01 | T1766 | 44248515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 98 | 99 | 53 | 53.06% | 1 | 46 | 0 | 0 | 1 | 0 | 305000 | 0 | 305000 | 305000 | 305000 | 0 | 0 | 0 | 305000 | 305000 | 100% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-03-26 | QTR3 | 19/20 | 118 | 267579.22 | B0 | ACC - LUMP SUM
| 01 | T1769 | 44012315201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 90 | 90 | 90 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 364364 | 17734 | 346630 | 364364 | 355187 | 0 | 0 | 0 | 355187 | 355187 | 102.5% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-06-23 | QTR4 | 19/20 |  | 2020-04-27 | QTR4 | 19/20 | 113 | 367495.83
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 31 | 52 | 61 | 5671 | 7405 | 6686 | 93.55% | 29 | 719 | 14 | 0 | 1435 | 299 | 96142836 | 1095206 | 95047630 | 98823314 | 97882780 | -24975 | 2790000 | 2765025 | 100647805 | 98636611 | 93.55% | 29 | -1889916 | 2680479 | 999 | 391 | 28 | 68 | 1848016 | 0 | 30 | 187 | 1833343 | 62913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 40 | -329690 | 0 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -493092 | 0 | 59 | 295 | 2891925 | 62913
| 01 | E1P56 | 41968815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 150 | 180 | 180 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1109997 | 50000 | 1059997 | 1109997 | 793278 | 0 | 0 | 0 | 793278 | 793278 | 74.84% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2017-10-27 | QTR2 | 17/18 | 115 | 2383057.05
| 01 | E1P91 | 42271055201 | 2017-04-20 | QTR4 | 16/17 | 1 | 7 | 560 | 729 | 725 | 101.1% | 1 | 4 | 0 | 0 | 169 | 0 | 10071503 | 104026 | 9967477 | 10247666 | 9983254 | 0 | 0 | 0 | 9983254 | 10164043 | 102% | 1 | 198791 | 176163 | 120 | 39 | 5 | 0 | 55015 | 0 | 5 | 0 | 112805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 179808 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 115 | 11091792.08 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 103.5% | 1 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 107% | 1 | 361384 | 0 | 43 | 24 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34
| 01 | E1Q23 | 43665015201 | 2018-02-13 | QTR3 | 17/18 | 1 | 0 | 340 | 462 | 525 | 127.9% | 0 | -63 | 63 | 0 | 90 | 32 | 918123 | 50000 | 868123 | 918123 | 868123 | -104895 | 0 | -104895 | 763228 | 763228 | 87.92% | 1 | 0 | 0 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 108 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 01 | E1Q29 | 42584115201 | 2017-04-20 | QTR4 | 16/17 | 2 | 15 | 650 | 1043 | 726 | 100.8% | 1 | 317 | 0 | 0 | 71 | 322 | 54145606 | 150000 | 53995606 | 56232960 | 55752280 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | 105.4% | 1 | -1366994 | 2087354 | 38 | 33 | 0 | 208 | 2137914 | 84393 | 0 | 114 | 329014 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27149 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -383908 | 0 | 0 | 322 | 2110169 | 103094 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 113 | 61229521.11 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R12 | 43668215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 0 | 175 | 188 | 123 | 62.86% | 1 | 65 | 0 | 0 | 13 | 0 | 1472083 | 50000 | 1422083 | 1472083 | 1445724 | 0 | 65000 | 65000 | 1510724 | 1446603 | 101.7% | 1 | -64121 | 0 | 4 | 9 | 0 | 0 | 15380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15380 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2019-09-16 | QTR1 | 19/20 | 115 | 1181939.29 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 97.6% | 1 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | 101.6% | 1 | -783 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69
| 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 83.24% | 1 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | 98.1% | 1 | -12362 | 0 | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37
| 01 | E1R51 | 43800815201 | 2018-09-20 | QTR1 | 18/19 | 1 | 0 | 165 | 233 | 232 | 103% | 1 | 1 | 0 | 0 | 68 | 0 | 2579000 | 50000 | 2529000 | 2579000 | 2523711 | 0 | 0 | 0 | 2523711 | 2514757 | 99.44% | 1 | -8954 | 0 | 53 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-10-31 | QTR2 | 19/20 | 113 | 2698176.21 | B0 | ACC - LUMP SUM
| 01 | E1R66 | 43641515201 | 2019-02-21 | QTR3 | 18/19 | 1 | 2 | 80 | 124 | 200 | 213.8% | 0 | -76 | 76 | 0 | 29 | 15 | 5199494 | 50000 | 5149494 | 5281274 | 4820096 | -261972 | -160000 | -421972 | 4398124 | 4386421 | 85.18% | 1 | 0 | 81780 | 23 | 6 | 0 | 0 | 1940 | 0 | 0 | 0 | 19302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 91319 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-16 | QTR4 | 19/20 |  | 2019-12-26 | QTR2 | 19/20 | 115 | 3837739.52 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R80 | 43771615201 | 2019-04-18 | QTR4 | 18/19 | 1 | 1 | 65 | 96 | 96 | 116.9% | 1 | 0 | 0 | 0 | 31 | 0 | 157000 | 9525 | 147475 | 157000 | 148434 | 0 | 0 | 0 | 148434 | 148434 | 100.7% | 1 | 0 | 0 | 16 | 4 | 0 | 0 | 6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 6184 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 108 | 169094.28
| 01 | E1S00 | 43943515201 | 2019-05-23 | QTR4 | 18/19 | 2 | 0 | 140 | 159 | 118 | 70.71% | 1 | 41 | 0 | 0 | 19 | 0 | 2112776 | 50000 | 2062776 | 2112776 | 2088952 | 0 | 0 | 0 | 2088952 | 2065283 | 100.1% | 1 | -23668 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 108 | 3162692.93 | B0 | ACC - LUMP SUM
| 01 | E1S90 | 43506515201 | 2019-12-05 | QTR2 | 19/20 | 1 | 0 | 80 | 80 | 55 | 68.75% | 1 | 25 | 0 | 0 | 0 | 0 | 264680 | 12505 | 252175 | 264680 | 252175 | 0 | 0 | 0 | 252175 | 252175 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2020-04-21 | QTR4 | 19/20 | 118 | 235218.96 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 13 | 16 | 25 | 3115 | 4127 | 3779 | 84.62% | 11 | 348 | 139 | 0 | 643 | 369 | 91476004 | 750809 | 90725195 | 93821301 | 92165641 | -366867 | 2405000 | 2038133 | 94203774 | 93257361 | 100% | 13 | -916707 | 2345297 | 403 | 199 | 5 | 208 | 2216433 | 84393 | 19 | 114 | 478034 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 106527 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -383908 | 0 | 41 | 369 | 2429074 | 103094
| District 01 Totals |  |  |  |  | 44 | 68 | 86 | 8786 | 11532 | 10465 | 90.91% | 40 | 1067 | 153 | 0 | 2078 | 668 | 187618840 | 1846015 | 185772825 | 192644615 | 190048421 | -391842 | 5195000 | 4803158 | 194851579 | 191893972 | 95.45% | 42 | -2806623 | 5025776 | 1402 | 590 | 33 | 276 | 4064449 | 84393 | 49 | 301 | 2311377 | 67301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 40 | -223163 | 14314 | 0 | 0 | 27297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 18037 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -877000 | 0 | 100 | 664 | 5320999 | 166007
| 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 120.6% | 0 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | 98.56% | 1 | -354944 | 150000 | 87 | 47 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74
| 02 | T2576 | 43091115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 13 | 340 | 624 | 717 | 192.1% | 0 | -93 | 93 | 0 | 64 | 220 | 7004346 | 70466 | 6933880 | 8247072 | 8273395 | -350610 | 0 | -350610 | 7922785 | 7815365 | 112.7% | 0 | -95677 | 1242726 | 29 | 35 | 0 | 4 | 33738 | 1648 | 0 | 98 | 237085 | 153271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 898427 | 0 | 0 | 5 | 38629 | 32695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 1207879 | 187614 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2017-12-20 | QTR2 | 17/18 | 208 | 5694356.97
| 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | 171.9% | 0 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | 100.5% | 1 | -191646 | 313457 | 83 | 110 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88
| 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | 135.9% | 0 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 100.6% | 1 | 7440 | 0 | 43 | 36 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45
| 02 | T2616 | 20800155201 | 2016-03-30 | QTR3 | 15/16 | 4 | 5 | 950 | 1229 | 1165 | 93.26% | 1 | 64 | 0 | 0 | 279 | 0 | 48935291 | 150000 | 48785291 | 48562222 | 47847275 | 0 | 0 | 0 | 47847275 | 49825494 | 102.1% | 1 | 2046752 | -373069 | 148 | 131 | 0 | 0 | 17383 | 0 | 0 | 0 | 134983 | 29037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -576584 | 0 | 0 | 0 | -424218 | 29037 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-04-27 | QTR4 | 19/20 |  | 2019-10-17 | QTR2 | 19/20 | 214 | 61148938.06
| 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 126.9% | 0 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 111% | 0 | 45271 | 670366 | 127 | 43 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 |  | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54
| 02 | T2621 | 20800145201 | 2016-06-20 | QTR4 | 15/16 | 2 | 6 | 800 | 1156 | 1156 | 107.9% | 1 | 0 | 0 | 0 | 323 | 33 | 49402252 | 150000 | 49252252 | 49868003 | 50029395 | 0 | 0 | 0 | 50029395 | 51188630 | 103.9% | 1 | 1252856 | 465751 | 181 | 112 | 21 | 0 | 163493 | 8734 | 0 | 33 | 200593 | 141476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78316 | 0 | 9 | 0 | 74599 | 22488 | 0 | 0 | 0 | 0 | 0 | 0 | 21607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 33 | 538607 | 172699 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 214 | 50264622.68
| 02 | T2657 | 20781825201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 560 | 749 | 748 | 107.3% | 1 | 1 | 0 | 0 | 147 | 42 | 13545525 | 150000 | 13395525 | 13574913 | 13974107 | 0 | 0 | 0 | 13974107 | 14346429 | 107.1% | 1 | 400515 | 29388 | 101 | 46 | 0 | 30 | 66698 | 0 | 0 | 12 | 26717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 99695 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-12 | QTR3 | 19/20 |  | 2019-08-17 | QTR1 | 19/20 | 214 | 16380282.85 | B6 | ACC - LIQUIDATED SAVINGS
| 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 119.8% | 1 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 102.4% | 1 | 15232 | 81763 | 65 | 48 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67
| 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 198.9% | 0 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 114.5% | 0 | 9762 | 362855 | 62 | 30 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92
| 02 | T2678 | 21028685201 | 2017-05-24 | QTR4 | 16/17 | 4 | 4 | 330 | 470 | 470 | 106.7% | 1 | 0 | 0 | 0 | 118 | 22 | 5834914 | 50000 | 5784914 | 5935993 | 6210758 | 0 | 0 | 0 | 6210758 | 6236655 | 107.8% | 1 | 28928 | 101079 | 87 | 31 | 0 | 22 | 115529 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 117937 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2018-12-18 | QTR2 | 18/19 | 216 | 5533447.16
| 02 | T2679 | 43617415201 | 2017-12-06 | QTR2 | 17/18 | 2 | 2 | 350 | 518 | 518 | 119.4% | 1 | 0 | 0 | 0 | 100 | 68 | 10753984 | 78530 | 10675454 | 10978696 | 11000190 | 0 | 0 | 0 | 11000190 | 11198057 | 104.9% | 1 | 197867 | 224712 | 67 | 33 | 0 | 12 | 149047 | 0 | 0 | 56 | 21709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 170756 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-21 | QTR3 | 19/20 |  | 2019-09-19 | QTR1 | 19/20 | 208 | 7872133.21
| 02 | T2682 | 43201215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 3 | 350 | 548 | 548 | 136% | 0 | 0 | 0 | 0 | 72 | 126 | 3548288 | 50000 | 3498288 | 3732180 | 3999294 | 0 | 0 | 0 | 3999294 | 4055594 | 115.9% | 0 | 56300 | 183891 | 40 | 32 | 0 | 74 | 112571 | 0 | 0 | 27 | 67449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7145 | 0 | 0 | 0 | 18339 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 205504 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-06-05 | QTR4 | 19/20 |  | 2019-10-15 | QTR2 | 19/20 | 214 | 3940432.98
| 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 108.3% | 1 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 112.7% | 0 | 804997 | 8616 | 80 | 27 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07
| 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 130.9% | 0 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 113.6% | 0 | 80901 | 27471 | 62 | 25 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62
| 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 86.07% | 1 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 106.1% | 1 | 354385 | 0 | 54 | 40 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27
| 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 108.3% | 1 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 104.3% | 1 | 0 | 66083 | 30 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 |  | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7
| 02 | T2689 | 43616115201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 270 | 351 | 331 | 92.59% | 1 | 20 | 0 | 0 | 81 | 0 | 1995665 | 50000 | 1945665 | 1995665 | 2049720 | 0 | 0 | 0 | 2049720 | 2101020 | 108% | 1 | 51299 | 0 | 22 | 59 | 0 | 0 | 24965 | 0 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28054 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | QTR3 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 216 | 2153022.57
| 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14546489 | 0 | 0 | 0 | 14546489 | 15202892 | 111.3% | 0 | 656402 | 0 | 94 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57
| 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 108.1% | 1 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3743642 | 98.92% | 1 | 52262 | 53332 | 27 | 37 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59
| 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 86.04% | 1 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | 104.5% | 1 | -21380 | 86773 | 31 | 24 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39
| 02 | T2708 | 44216935201 | 2019-04-24 | QTR4 | 18/19 | 1 | 3 | 120 | 139 | 75 | 46.67% | 1 | 64 | 0 | 0 | 19 | 0 | 368985 | 120 | 368865 | 374417 | 391272 | 0 | 0 | 0 | 391272 | 387389 | 105% | 1 | 0 | 5432 | 9 | 10 | 0 | 0 | 1160 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-25 | QTR2 | 19/20 | 208 | 334520.6
| 02 | T2710 | 40926715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 4 | 320 | 384 | 383 | 102.8% | 1 | 1 | 0 | 0 | 54 | 10 | 3168954 | 0 | 3168954 | 3211208 | 3216929 | 0 | 0 | 0 | 3216929 | 3215797 | 101.5% | 1 | -1132 | 42254 | 31 | 23 | 0 | 7 | 5327 | 1815 | 0 | 3 | 36151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42254 | 1815 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2019-10-14 | QTR2 | 19/20 | 208 | 1926903.62
| 02 | T2714 | 43761815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 3 | 170 | 308 | 327 | 156.5% | 0 | -19 | 19 | 0 | 61 | 77 | 8210076 | 77799 | 8132277 | 8537835 | 8699071 | -65493 | 0 | -65493 | 8633578 | 8618119 | 106% | 1 | -15459 | 327759 | 46 | 15 | 0 | 3 | 112357 | 0 | 0 | 74 | 215402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 327759 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-05 | QTR4 | 19/20 |  | 2019-12-27 | QTR2 | 19/20 | 209 | 8052869.27
| 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 65% | 1 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | 99.5% | 1 | -29525 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 |  | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85
| 02 | T2723 | 43762015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 120 | 143 | 143 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 1658214 | 50000 | 1608214 | 1658214 | 1598015 | 0 | 0 | 0 | 1598015 | 1602638 | 99.65% | 1 | 4623 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 214 | 2124298.79
| 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 74.29% | 1 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 99.5% | 1 | 6452 | 0 | 5 | 3 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8
| 02 | T2730 | 43429715201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 144 | 139 | 95.83% | 1 | 5 | 0 | 0 | 24 | 0 | 2680388 | 50000 | 2630388 | 2680388 | 2824608 | 0 | 0 | 0 | 2824608 | 2824608 | 107.4% | 1 | 0 | 0 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-10-15 | QTR2 | 19/20 | 209 | 3620026.94
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 28 | 48 | 83 | 8824 | 13060 | 12850 | 67.86% | 19 | 210 | 153 | 0 | 2833 | 1403 | 253561011 | 1998550 | 251562460 | 257631649 | 259123712 | -566167 | 0 | -566167 | 258557545 | 263699998 | 75% | 21 | 5362481 | 4070639 | 1655 | 1051 | 65 | 355 | 1415030 | 69331 | 0 | 556 | 2017613 | 359618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 179878 | 0 | 9 | 1 | 117008 | 28131 | 0 | 0 | 0 | 0 | 0 | 24 | 30595 | 0 | 0 | 399 | 925898 | 27471 | 53 | 39 | 231779 | 103245 | 0 | 0 | 0 | 0 | 0 | 0 | -576584 | 0 | 127 | 1397 | 4341216 | 587797
| 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 157.7% | 0 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | 110.5% | 0 | -1459708 | 16826383 | 385 | 223 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18219 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 12 | 798 | 1129 | 1998 | 234.5% | 0 | -869 | 869 | 0 | 127 | 204 | 84850000 | 175000 | 84675000 | 85626817 | 85105357 | -9751108 | 0 | -9751108 | 75354249 | 79072300 | 93.38% | 1 | 3718051 | 776817 | 82 | 45 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 254205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271502 | 0 | 0 | 204 | 818390 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 | 06/04/2020 | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | 128.4% | 0 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | 97.09% | 1 | -1251611 | -606983 | 51 | 65 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2V70 | 42747515201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 350 | 579 | 577 | 131.1% | 0 | 2 | 0 | 0 | 229 | 0 | 4483000 | 51665 | 4431335 | 4642146 | 4688789 | 0 | 0 | 0 | 4688789 | 4688881 | 105.8% | 1 | 92 | 159146 | 25 | 93 | 0 | 0 | 18680 | 0 | 0 | 0 | 40938 | 1341 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 166914 | 1341 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 5283434.02
| 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 116.3% | 1 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 112.2% | 0 | 298956 | 30442 | 44 | 26 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25
| 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 170.6% | 0 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 123.3% | 0 | 110065 | 656701 | 89 | 38 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 |  | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79
| 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 85.78% | 1 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 100.6% | 1 | 2 | 0 | 67 | 39 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25
| 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 103.5% | 1 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 96.37% | 1 | 2 | -3969 | 52 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60481 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING CO. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 |  | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46
| 02 | E2W52 | 42849815201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 300 | 324 | 261 | 79% | 1 | 63 | 0 | 0 | 24 | 0 | 730881 | 39951 | 690930 | 756196 | 713128 | 0 | 0 | 0 | 713128 | 713129 | 103.2% | 1 | 0 | 25315 | 9 | 15 | 0 | 0 | 53237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53237 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-14 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 208 | 752277.84
| 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 99.21% | 1 | 0 | 0 | 20 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 |  | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23
| 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | 99.4% | 1 | -932 | 0 | 21 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46
| 02 | E2W96 | 43307515201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 350 | 401 | 349 | 85.14% | 1 | 52 | 0 | 0 | 51 | 0 | 4411000 | 50000 | 4361000 | 4455781 | 4414330 | 0 | 0 | 0 | 4414330 | 4414364 | 101.2% | 1 | 34 | 44781 | 28 | 23 | 0 | 0 | 16525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61306 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-16 | QTR2 | 19/20 | 208 | 4144135.21
| 02 | E2X07 | 20956525201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 60 | 72 | 72 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 327059 | 16215 | 310844 | 327059 | 288640 | 0 | 0 | 0 | 288640 | 288640 | 92.86% | 1 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 208 | 337947.23
| 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 74.6% | 1 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 100.3% | 1 | 0 | 0 | 26 | 39 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 |  | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17
| 02 | E2X44 | 42879715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 200 | 428 | 428 | 182.5% | 0 | 0 | 0 | 0 | 130 | 98 | 1990108 | 50000 | 1940108 | 2637472 | 2547298 | 0 | 0 | 0 | 2547298 | 2542607 | 131.1% | 0 | -4691 | 647363 | 37 | 26 | 60 | 95 | 608011 | 0 | 0 | 3 | 4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 98 | 612548 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-05 | QTR2 | 19/20 | 216 | 2271972.07
| 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 76.19% | 1 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 98.98% | 1 | 0 | 0 | 14 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97
| 02 | E2X60 | 43025915201 | 2018-08-15 | QTR1 | 18/19 | 1 | 0 | 280 | 326 | 325 | 101.8% | 1 | 1 | 0 | 0 | 40 | 6 | 1328017 | 50000 | 1278017 | 1328017 | 1207862 | 0 | 0 | 0 | 1207862 | 1207862 | 94.51% | 1 | 0 | 0 | 18 | 22 | 0 | 6 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 875 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 208 | 1798375.14
| 02 | E2X61 | 43496915201 | 2018-08-15 | QTR1 | 18/19 | 2 | 0 | 180 | 210 | 230 | 111.1% | 1 | -20 | 20 | 0 | 30 | 0 | 2118153 | 50000 | 2068153 | 2118153 | 2024485 | -33300 | 0 | -33300 | 1991185 | 1991185 | 96.28% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-01-22 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 209 | 2333869.85
| 02 | E2X62 | 43044925201 | 2018-08-15 | QTR1 | 18/19 | 1 | 2 | 320 | 447 | 446 | 104.7% | 1 | 1 | 0 | 0 | 111 | 16 | 3108597 | 50000 | 3058597 | 3188597 | 3259002 | 0 | 0 | 0 | 3259002 | 3258817 | 106.5% | 1 | -185 | 80000 | 48 | 63 | 0 | 0 | 0 | 0 | 0 | 16 | 117118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 117118 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 216 | 2739647.8
| 02 | E2X63 | 43391215201 | 2018-09-19 | QTR1 | 18/19 | 1 | 0 | 250 | 342 | 342 | 116.4% | 1 | 0 | 0 | 0 | 51 | 41 | 1149152 | 50000 | 1099152 | 1149152 | 1082839 | 0 | 0 | 0 | 1082839 | 1082839 | 98.52% | 1 | 0 | 0 | 18 | 33 | 0 | 6 | 8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 8943 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2020-01-21 | QTR3 | 19/20 | 208 | 1278581.91
| 02 | E2X68 | 43500015201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 125 | 132 | 112 | 84% | 1 | 20 | 0 | 0 | 7 | 0 | 925745 | 45595 | 880149 | 925745 | 888997 | 0 | 0 | 0 | 888997 | 888989 | 101% | 1 | -8 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 209 | 952358.87
| 02 | E2Y23 | 43500215201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 125 | 165 | 165 | 111.2% | 1 | 0 | 0 | 0 | 40 | 0 | 891797 | 43663 | 848134 | 891797 | 842389 | 0 | 0 | 0 | 842389 | 842389 | 99.32% | 1 | 0 | 0 | 11 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-04-16 | QTR4 | 19/20 |  | 2020-02-23 | QTR3 | 19/20 | 209 | 906381.04
| 02 | E2Y77 | 43606615201 | 2019-07-17 | QTR1 | 19/20 | 1 | 0 | 90 | 96 | 96 | 103.3% | 1 | 0 | 0 | 0 | 6 | 0 | 409752 | 20052 | 389700 | 409752 | 391056 | 0 | 0 | 0 | 391056 | 391056 | 100.3% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-06-15 | QTR4 | 19/20 |  | 2020-04-10 | QTR4 | 19/20 | 208 | 431103.15
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 24 | 34 | 72 | 8447 | 12178 | 12680 | 75% | 18 | -502 | 907 | 0 | 2286 | 1445 | 363629244 | 1557604 | 362071638 | 382350490 | 381303153 | -10014340 | 0 | -10014340 | 371288813 | 372343437 | 79.17% | 19 | 1421745 | 18721246 | 1097 | 940 | 128 | 348 | 3585220 | 238783 | 0 | 763 | 14782991 | 1225540 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273900 | 0 | 10 | 231 | 222682 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 254205 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -350202 | 0 | 249 | 1445 | 18876090 | 1464323
| District 02 Totals |  |  |  |  | 52 | 82 | 155 | 17271 | 25238 | 25530 | 71.15% | 37 | -292 | 1060 | 0 | 5119 | 2848 | 617190255 | 3556154 | 613634098 | 639982139 | 640426865 | -10580507 | 0 | -10580507 | 629846358 | 636043435 | 76.92% | 40 | 6784226 | 22791885 | 2752 | 1991 | 193 | 703 | 5000250 | 308114 | 0 | 1319 | 16800604 | 1585158 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273900 | 0 | 10 | 254 | 402560 | 0 | 120 | 1 | 117008 | 28131 | 0 | 0 | 0 | 0 | 0 | 92 | 284800 | 0 | 0 | 399 | 1030731 | 27471 | 53 | 39 | 231779 | 103245 | 0 | 35 | 0 | 0 | 0 | 0 | -926786 | 0 | 376 | 2842 | 23217306 | 2052120
| 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | 114.3% | 1 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | 90.98% | 1 | -1453386 | 157836 | 188 | 58 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28
| 03 | T3485 | 42695315201 | 2016-04-27 | QTR4 | 15/16 | 2 | 1 | 200 | 314 | 351 | 139% | 0 | -37 | 37 | 0 | 113 | 1 | 3574230 | 50000 | 3524230 | 3575445 | 3569976 | -104007 | 0 | -104007 | 3465969 | 3477125 | 98.66% | 1 | 11156 | 1215 | 52 | 21 | 0 | 1 | 1215 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 6091 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2017-06-30 | QTR4 | 16/17 | 308 | 3028499.48
| 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | 129.8% | 0 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | 96.12% | 1 | -84026 | 68219 | 39 | 20 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 |  | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84
| 03 | T3543 | 22044275201 | 2015-09-30 | QTR1 | 15/16 | 1 | 18 | 830 | 1304 | 1304 | 106.1% | 1 | 0 | 0 | 0 | 435 | 39 | 29686177 | 150000 | 29536177 | 35844062 | 36589864 | 0 | 0 | 0 | 36589864 | 36787330 | 124.6% | 0 | 244313 | 6157885 | 342 | 81 | 12 | 14 | 166013 | 0 | 0 | 15 | 229697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 578955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 224474 | 0 | 0 | 0 | 4978544 | 83847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41801 | 0 | 12 | 39 | 6135882 | 83847 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-07-29 | QTR1 | 19/20 | 308 | 37447263.92
| 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 121.7% | 0 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 106% | 1 | 8875 | 51756 | 76 | 28 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44
| 03 | T3586 | 42862415201 | 2018-06-13 | QTR4 | 17/18 | 1 | 4 | 340 | 451 | 449 | 108.2% | 1 | 2 | 0 | 0 | 111 | 0 | 4214542 | 0 | 4214542 | 4293135 | 4297521 | 0 | 0 | 0 | 4297521 | 4255328 | 101% | 1 | -5203 | 78594 | 50 | 31 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13328 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 41604 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-13 | QTR2 | 19/20 | 321 | 3958245.51
| 03 | T3594 | 42884415201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 210 | 720 | 720 | 126.7% | 0 | 0 | 0 | 0 | 454 | 56 | 5851220 | 61859 | 5789362 | 5885580 | 5664882 | 0 | 0 | 0 | 5664882 | 5780265 | 99.84% | 1 | 115384 | 34359 | 395 | 59 | 0 | 0 | 0 | 0 | 0 | 56 | 49348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 49348 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2020-06-06 | QTR4 | 19/20 |  | 2020-04-08 | QTR4 | 19/20 | 314 | 6081166.5
| 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 104.8% | 1 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | 95.32% | 1 | -6959 | 0 | 66 | 24 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75
| 03 | T3614 | 43228815201 | 2018-08-29 | QTR1 | 18/19 | 1 | 2 | 120 | 238 | 238 | 133.3% | 0 | 0 | 0 | 0 | 78 | 40 | 776874 | 0 | 776874 | 1103417 | 1178529 | 0 | 0 | 0 | 1178529 | 1178529 | 151.7% | 0 | 0 | 326542 | 62 | 16 | 0 | 40 | 326542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326542 | 0 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 308 | 825049.02
| 03 | T3617 | 43228615201 | 2018-11-14 | QTR2 | 18/19 | 1 | 3 | 290 | 425 | 425 | 124.8% | 0 | 0 | 0 | 0 | 135 | 0 | 1583516 | 0 | 1583516 | 1621356 | 1660818 | 0 | 0 | 0 | 1660818 | 1656916 | 104.6% | 1 | -3903 | 37840 | 34 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 37840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 37840 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-06-10 | QTR4 | 19/20 |  | 2020-03-30 | QTR3 | 19/20 | 308 | 1384281.38
| 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 104.3% | 1 | 373777 | 60427 | 75 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485
| 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | 100.6% | 1 | -2578 | 6645 | 68 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65
| 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 102.1% | 1 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | 98.23% | 1 | -2508 | 0 | 76 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9
| 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 118.3% | 1 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 113.7% | 0 | 168914 | 26513 | 52 | 23 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2019-01-11 | QTR3 | 18/19 | 308 | 0
| 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 99.04% | 1 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 108.7% | 1 | 334168 | -32998 | 50 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16
| 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 96% | 1 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 98.38% | 1 | 0 | -2208 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43
| 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 104.2% | 1 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 114% | 0 | 321209 | 405998 | 157 | 26 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62
| 03 | T3656 | 42817125201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 168 | 168 | 100% | 1 | 0 | 0 | 0 | 48 | 0 | 483492 | 23492 | 460000 | 483492 | 460000 | 0 | 0 | 0 | 460000 | 460000 | 100% | 1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-01-13 | QTR3 | 19/20 | 314 | 489801.84 | B0 | ACC - LUMP SUM
| 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 133.8% | 0 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 105.4% | 1 | 57366 | 27889 | 69 | 25 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76
| 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 100% | 1 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 114% | 0 | 100163 | 31248 | 167 | 43 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49
| 03 | T3666 | 43578215201 | 2019-07-31 | QTR1 | 19/20 | 1 | 1 | 120 | 139 | 128 | 90.83% | 1 | 11 | 0 | 0 | 19 | 0 | 552204 | 0 | 552204 | 552204 | 493444 | 0 | 0 | 0 | 493444 | 493444 | 89.36% | 1 | 0 | 0 | 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-05-28 | QTR4 | 19/20 |  | 2020-02-18 | QTR3 | 19/20 | 321 | 621266.47
| 03 | T3667 | 43273835201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 325 | 639 | 639 | 109.8% | 1 | 0 | 0 | 0 | 312 | 2 | 10109835 | 112126 | 9997709 | 10121496 | 9985893 | 0 | 0 | 0 | 9985893 | 10290483 | 102.9% | 1 | 339141 | 11661 | 190 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2 | -17331 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2020-01-10 | QTR3 | 19/20 | 313 | 11327401.22
| 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 94.48% | 1 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | 107.9% | 1 | -464 | 209861 | 112 | 20 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000
| 03 | T3673 | 43774415201 | 2018-09-26 | QTR1 | 18/19 | 1 | 4 | 180 | 268 | 262 | 116.7% | 1 | 6 | 0 | 0 | 52 | 36 | 7942048 | 83065 | 7858983 | 7802040 | 7940568 | 0 | 0 | 0 | 7940568 | 7896410 | 100.5% | 1 | -44158 | -140008 | 28 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -140008 | 0 | 0 | 0 | 49174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -90833 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-09-05 | QTR1 | 19/20 | 321 | 8459567.2
| 03 | T3678 | 43627015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 180 | 208 | 179 | 83.89% | 1 | 29 | 0 | 0 | 28 | 0 | 4020176 | 50000 | 3970176 | 4016156 | 4196886 | 0 | 0 | 0 | 4196886 | 4189347 | 105.5% | 1 | -7539 | -4020 | 13 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 32860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28840 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2019-12-06 | QTR2 | 19/20 | 321 | 4510561.96
| 03 | T3679 | 43388415201 | 2018-12-05 | QTR2 | 18/19 | 2 | 0 | 365 | 403 | 378 | 93.15% | 1 | 25 | 0 | 0 | 38 | 0 | 1634280 | 0 | 1634280 | 1634280 | 1650177 | 0 | 0 | 0 | 1650177 | 1651949 | 101.1% | 1 | 1772 | 0 | 11 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-03-10 | QTR3 | 19/20 | 313 | 2275667.74
| 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 95.56% | 1 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 101.7% | 1 | 0 | 0 | 22 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24
| 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 98.89% | 1 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 99.76% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM
| 03 | T3684 | 43774815201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 210 | 249 | 239 | 95.24% | 1 | 10 | 0 | 0 | 39 | 0 | 5394287 | 67888 | 5326399 | 5398247 | 5475266 | 0 | 0 | 0 | 5475266 | 5462989 | 102.6% | 1 | -12278 | 3960 | 21 | 18 | 0 | 0 | 24710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3960 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 28670 | 279 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2019-12-03 | QTR2 | 19/20 | 321 | 6845122.25
| 03 | T3688 | 44038315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 134 | 120 | 88.33% | 1 | 14 | 0 | 0 | 14 | 0 | 354899 | 18499 | 336400 | 354899 | 344281 | 0 | 0 | 0 | 344281 | 344281 | 102.3% | 1 | 0 | 0 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 321 | 390454.14
| 03 | T3693 | 43776515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 210 | 369 | 362 | 115.2% | 1 | 7 | 0 | 0 | 159 | 0 | 9424063 | 103994 | 9320069 | 9424063 | 9590716 | 0 | 0 | 0 | 9590716 | 9547583 | 102.4% | 1 | -43133 | 0 | 93 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-29 | QTR4 | 19/20 |  | 2020-02-20 | QTR3 | 19/20 | 313 | 10485495.93
| 03 | T3713 | 42985635201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 180 | 277 | 277 | 103.3% | 1 | 0 | 0 | 0 | 91 | 6 | 1053341 | 0 | 1053341 | 1099610 | 1118223 | 0 | 0 | 0 | 1118223 | 1117591 | 106.1% | 1 | -632 | 46269 | 67 | 24 | 0 | 0 | 0 | 0 | 0 | 6 | 46269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46269 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-08 | QTR4 | 19/20 |  | 2020-03-12 | QTR3 | 19/20 | 321 | 1301273.03
| 03 | T3715 | 43827215201 | 2019-05-22 | QTR4 | 18/19 | 2 | 1 | 150 | 159 | 118 | 72.67% | 1 | 41 | 0 | 0 | 9 | 0 | 649114 | 50000 | 599114 | 653949 | 611340 | 0 | 0 | 0 | 611340 | 610104 | 101.8% | 1 | -1235 | 4836 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 321 | 755587.05
| 03 | T3726 | 43551825201 | 2019-06-12 | QTR4 | 18/19 | 1 | 1 | 120 | 200 | 196 | 111.7% | 1 | 4 | 0 | 0 | 80 | 0 | 810302 | 31325 | 778977 | 810302 | 797761 | 0 | 0 | 0 | 797761 | 797761 | 102.4% | 1 | 0 | 0 | 23 | 39 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-06-29 | QTR4 | 19/20 |  | 2020-04-20 | QTR4 | 19/20 | 314 | 663447.16
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 34 | 46 | 79 | 7339 | 11696 | 11570 | 79.41% | 27 | 126 | 71 | 0 | 4007 | 350 | 148813412 | 1657264 | 147156148 | 156383733 | 157501907 | -302298 | 0 | -302298 | 157199609 | 157247853 | 85.29% | 29 | 408236 | 7570319 | 2659 | 979 | 12 | 117 | 1114618 | 15783602 | 185 | 167 | 750397 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 56 | 456518 | 10742 | 17 | 3 | 107017 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 281784 | 0 | 0 | 0 | 4978544 | 83847 | 14 | 0 | 0 | 0 | 69 | 0 | 23933 | 279 | 0 | 0 | -41801 | 0 | 369 | 350 | 7671013 | 15896629
| 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 115.7% | 1 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 104.7% | 1 | 52521 | 0 | 13 | 25 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95
| 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 94.44% | 1 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 109.1% | 1 | 148555 | 3908 | 52 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8
| 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 97.78% | 1 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 102.4% | 1 | 0 | -4732 | 101 | 60 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-05-13 | QTR4 | 18/19 | 308 | 795145
| 03 | E3R15 | 43730715201 | 2018-04-12 | QTR4 | 17/18 | 2 | 0 | 120 | 195 | 199 | 125% | 0 | -4 | 4 | 0 | 75 | 0 | 847761 | 42761 | 805000 | 847761 | 805000 | -6660 | 0 | -6660 | 798340 | 798340 | 99.17% | 1 | 0 | 0 | 44 | 5 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 308 | 968822.89 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 03 | E3R27 | 40410835201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 90 | 121 | 119 | 97.78% | 1 | 2 | 0 | 0 | 31 | 0 | 497771 | 26481 | 471290 | 497771 | 462232 | 0 | 0 | 0 | 462232 | 462232 | 98.08% | 1 | 0 | 0 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-19 | QTR2 | 19/20 | 314 | 568464.05
| 03 | E3R52 | 43627225201 | 2019-01-10 | QTR3 | 18/19 | 1 | 1 | 180 | 215 | 203 | 93.89% | 1 | 12 | 0 | 0 | 34 | 1 | 1432597 | 50000 | 1382597 | 1438332 | 1321040 | 0 | 0 | 0 | 1321040 | 1327923 | 96.05% | 1 | 6884 | 5735 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 308 | 1931230.61
| 03 | E3R71 | 41557325201 | 2019-06-13 | QTR4 | 18/19 | 1 | 1 | 150 | 197 | 155 | 72% | 1 | 42 | 0 | 0 | 47 | 0 | 726199 | 37739 | 688460 | 763938 | 752801 | 0 | 0 | 0 | 752801 | 752801 | 109.3% | 1 | 0 | 37739 | 11 | 36 | 0 | 0 | 37739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37739 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-31 | QTR3 | 19/20 | 314 | 735823.85
| 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 105.4% | 1 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 109% | 1 | 63342 | 76927 | 41 | 24 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46
| 03 | E3S52 | 41767755201 | 2019-05-09 | QTR4 | 18/19 | 1 | 0 | 90 | 170 | 168 | 114.4% | 1 | 2 | 0 | 0 | 80 | 0 | 551256 | 24827 | 526429 | 551256 | 487293 | 0 | 0 | 0 | 487293 | 487293 | 92.57% | 1 | 0 | 0 | 43 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2020-01-16 | QTR3 | 19/20 | 314 | 525116.42
| 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 84.44% | 1 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0% | 1 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34
| 03 | E3S65 | 4453681E201 | 2019-04-26 | QTR4 | 18/19 | 1 | 0 | 45 | 86 | 84 | 95.56% | 1 | 2 | 0 | 0 | 41 | 0 | 290951 | 0 | 290951 | 290951 | 295907 | 0 | 0 | 0 | 295907 | 0 | 0% | 1 | -295907 | 0 | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-01-07 | QTR3 | 19/20 | 314 | 223300
| 03 | E3T17 | 4458601G201 | 2019-10-14 | QTR2 | 19/20 | 1 | 0 | 50 | 51 | 48 | 94% | 1 | 3 | 0 | 0 | 1 | 0 | 90900 | 0 | 90900 | 90900 | 90510 | 0 | 0 | 0 | 90510 | 0 | 0% | 1 | -90510 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208255780 | T & M LAWN-FENCE SERVICE INC | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2020-02-28 | QTR3 | 19/20 | 314 | 98690
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 12 | 17 | 10 | 1495 | 2183 | 2104 | 91.67% | 11 | 79 | 4 | 0 | 686 | 2 | 12655191 | 370777 | 12284414 | 12774768 | 12605871 | -8531 | 0 | -8531 | 12597340 | 12417706 | 100% | 12 | -160115 | 119577 | 379 | 227 | 21 | 0 | 40154 | 0 | 36 | 1 | 66119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 9843 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2 | 116116 | 8796
| District 03 Totals |  |  |  |  | 46 | 63 | 89 | 8834 | 13879 | 13674 | 82.61% | 38 | 205 | 75 | 0 | 4693 | 352 | 161468603 | 2028041 | 159440562 | 169158501 | 170107778 | -310829 | 0 | -310829 | 169796949 | 169665559 | 89.13% | 41 | 248121 | 7689896 | 3038 | 1206 | 33 | 117 | 1154772 | 15783602 | 221 | 168 | 816516 | 18159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 57 | 466361 | 19538 | 17 | 3 | 107017 | 0 | 0 | 0 | 0 | 0 | 15 | 7 | 281784 | 0 | 0 | 0 | 4978544 | 83847 | 14 | 0 | 0 | 0 | 69 | 0 | 23933 | 279 | 0 | 0 | -41801 | 0 | 449 | 352 | 7787129 | 15905425
| 04 | T4400 | 22777415201 | 2014-05-21 | QTR4 | 13/14 | 3 | 8 | 1100 | 1532 | 1532 | 115.2% | 1 | 0 | 0 | 0 | 312 | 120 | 30674813 | 150000 | 30524813 | 30018004 | 28121407 | 0 | -175000 | -175000 | 27946407 | 26867570 | 88.02% | 1 | -1001159 | -656809 | 210 | 55 | 43 | 0 | 96338 | 15944 | 4 | 21 | 174318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | -96939 | 43113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -972544 | 0 | 47 | 120 | -653022 | 59057 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-04-30 | QTR4 | 19/20 |  | 2019-03-16 | QTR3 | 18/19 | 412 | 31615938.89 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
| 04 | T4412 | 42873315201 | 2016-08-31 | QTR1 | 16/17 | 2 | 4 | 661 | 899 | 898 | 117.4% | 1 | 1 | 0 | 0 | 122 | 116 | 6616134 | 55250 | 6560884 | 6744078 | 6260985 | 0 | 0 | 0 | 6260985 | 6337789 | 96.6% | 1 | 102908 | 127944 | 73 | 49 | 0 | 2 | 50042 | 0 | 0 | 53 | 88966 | 18492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 12210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 152254 | 18492 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2019-06-19 | QTR4 | 18/19 | 412 | 5635993.18
| 04 | T4418 | 22989615201 | 2015-07-29 | QTR1 | 15/16 | 7 | 5 | 1005 | 1118 | 1118 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 17423228 | 150000 | 17273228 | 17585616 | 15704340 | 0 | 0 | 0 | 15704340 | 15605066 | 90.34% | 1 | -82422 | 162388 | 51 | 62 | 0 | 0 | -39118 | 0 | 0 | 0 | 189822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11593 | 11593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162297 | 11593 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-01-25 | QTR3 | 18/19 | 409 | 22527836.07
| 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 100.2% | 1 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 98.32% | 1 | 442812 | 198133 | 145 | 57 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 |  | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16
| 04 | T4433 | 42872415201 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 601 | 960 | 974 | 111.8% | 1 | -14 | 14 | 0 | 302 | 61 | 16224277 | 150000 | 16074277 | 17235975 | 16795691 | -46980 | -64000 | -110980 | 16684711 | 16774147 | 104.4% | 1 | 140685 | 1011698 | 254 | 48 | 0 | 0 | 284349 | 0 | 0 | 58 | 769055 | 15997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1059392 | 20397 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-02-25 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 412 | 14991647.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4444 | 43270515201 | 2016-12-07 | QTR2 | 16/17 | 4 | 8 | 910 | 1190 | 1005 | 81.98% | 1 | 185 | 0 | 0 | 259 | 21 | 27999900 | 150000 | 27849900 | 28775420 | 29356382 | 0 | 0 | 0 | 29356382 | 30041255 | 107.9% | 1 | 725124 | 775520 | 216 | 43 | 0 | 21 | 446126 | 0 | 0 | 0 | 206370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 683157 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-02-11 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 408 | 34103305.86
| 04 | T4449 | 43466615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 4 | 625 | 913 | 912 | 118.7% | 1 | 1 | 0 | 0 | 170 | 118 | 7667258 | 81519 | 7585739 | 7990322 | 8156412 | 0 | 0 | 0 | 8156412 | 8213679 | 108.3% | 1 | 84466 | 323063 | 101 | 69 | 0 | 0 | 2309 | 0 | 0 | 61 | 169260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 148044 | 0 | 0 | 0 | 17025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 336638 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-09 | QTR4 | 19/20 |  | 2020-01-07 | QTR3 | 19/20 | 412 | 7671793.67
| 04 | T4452 | 43166615201 | 2017-01-25 | QTR3 | 16/17 | 2 | 4 | 396 | 484 | 478 | 98.48% | 1 | 6 | 0 | 0 | 88 | 0 | 3407245 | 50000 | 3357245 | 3524212 | 3504637 | 0 | 0 | 0 | 3504637 | 3537514 | 105.4% | 1 | 69412 | 116967 | 67 | 21 | 0 | 0 | 52621 | 51166 | 0 | 0 | 68491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126406 | 51166 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-06 | QTR3 | 19/20 |  | 2018-10-02 | QTR2 | 18/19 | 412 | 3478134.48
| 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | 119.4% | 1 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 91.7% | 1 | 855652 | 75851 | 215 | 58 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 |  | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 106.6% | 1 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 100.7% | 1 | 189028 | 165338 | 66 | 42 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 |  | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18
| 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 132.6% | 0 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7138333 | 115.2% | 0 | 123672 | 533617 | 55 | 41 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 107.8% | 1 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | 99.64% | 1 | -156 | -6176 | 89 | 27 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55
| 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 109.5% | 1 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 104.4% | 1 | 83036 | 308276 | 109 | 33 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 |  | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96
| 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 99.32% | 1 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | 100.4% | 1 | -4859 | 47624 | 74 | 22 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18
| 04 | T4480 | 43166515201 | 2018-04-25 | QTR4 | 17/18 | 2 | 1 | 214 | 274 | 273 | 105.1% | 1 | 1 | 0 | 0 | 48 | 12 | 1327221 | 50000 | 1277221 | 1366521 | 1298578 | 0 | 0 | 0 | 1298578 | 1298125 | 101.6% | 1 | -453 | 39300 | 29 | 19 | 0 | 0 | 0 | 0 | 0 | 12 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42392 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 412 | 1330304.19
| 04 | T4481 | 43177025201 | 2018-04-25 | QTR4 | 17/18 | 2 | 3 | 274 | 395 | 395 | 116.4% | 1 | 0 | 0 | 0 | 76 | 45 | 2295900 | 50000 | 2245900 | 2421717 | 2381617 | 0 | 0 | 0 | 2381617 | 2380490 | 106% | 1 | -1127 | 125817 | 52 | 24 | 0 | 0 | 15551 | 0 | 0 | 39 | 132589 | 42865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 161617 | 42865 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-04-23 | QTR4 | 19/20 |  | 2019-10-09 | QTR2 | 19/20 | 412 | 2164418.85
| 04 | T4482 | 44007915201 | 2018-05-23 | QTR4 | 17/18 | 2 | 3 | 253 | 284 | 283 | 99.6% | 1 | 1 | 0 | 0 | 31 | 0 | 398299 | 25300 | 372999 | 443873 | 390019 | 0 | 0 | 0 | 390019 | 390013 | 104.6% | 1 | -6 | 45574 | 11 | 20 | 0 | 0 | 634 | 0 | 0 | 0 | 49025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49659 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-04-20 | QTR4 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 409 | 523214.25
| 04 | T4484 | 43169815201 | 2018-05-23 | QTR4 | 17/18 | 2 | 2 | 180 | 228 | 228 | 100% | 1 | 0 | 0 | 0 | 48 | 0 | 1436281 | 50000 | 1386281 | 1518265 | 1430265 | 0 | 0 | 0 | 1430265 | 1427633 | 103% | 1 | -2632 | 81984 | 33 | 15 | 0 | 0 | 23051 | 0 | 0 | 0 | 9060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94344 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-04-23 | QTR4 | 19/20 |  | 2019-12-03 | QTR2 | 19/20 | 412 | 1552637.32
| 04 | T4486 | 43165715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 10 | 353 | 442 | 442 | 112.7% | 1 | 0 | 0 | 0 | 44 | 45 | 3260393 | 50000 | 3210393 | 3609674 | 3402444 | 0 | 0 | 0 | 3402444 | 3396789 | 105.8% | 1 | -5656 | 349282 | 19 | 25 | 0 | 45 | 162960 | 125042 | 0 | 0 | 157599 | 106623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 387158 | 231666 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-10-28 | QTR2 | 19/20 | 412 | 3504742.12
| 04 | T4487 | 43060825201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 207 | 231 | 193 | 81.64% | 1 | 38 | 0 | 0 | 24 | 0 | 755191 | 32732 | 722458 | 755191 | 655187 | 0 | 0 | 0 | 655187 | 654702 | 90.62% | 1 | -486 | 0 | 6 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-30 | QTR3 | 19/20 | 409 | 684674.32
| 04 | T4490 | 43467415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 246 | 309 | 309 | 101.6% | 1 | 0 | 0 | 0 | 59 | 4 | 1487250 | 50000 | 1437250 | 1501835 | 1498981 | 0 | 0 | 0 | 1498981 | 1501750 | 104.5% | 1 | 8264 | 14585 | 40 | 19 | 0 | 4 | 10639 | 9090 | 0 | 0 | 31779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42418 | 9090 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-06-11 | QTR4 | 19/20 |  | 2020-02-03 | QTR3 | 19/20 | 412 | 1612250.71
| 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 64.44% | 1 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 96.63% | 1 | 4043 | 0 | 6 | 5 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05
| 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 103.1% | 1 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 99.63% | 1 | 1280 | 11869 | 31 | 8 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95
| 04 | T4515 | 43783515201 | 2019-03-27 | QTR3 | 18/19 | 2 | 2 | 269 | 310 | 289 | 92.19% | 1 | 21 | 0 | 0 | 41 | 0 | 1965071 | 50000 | 1915071 | 1985843 | 1788610 | 0 | 0 | 0 | 1788610 | 1780758 | 92.99% | 1 | -7851 | 20773 | 16 | 25 | 0 | 0 | 689 | 0 | 0 | 0 | 21135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21824 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2020-03-25 | QTR3 | 19/20 | 409 | 1803197.14
| 04 | T4532 | 43838815201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 80 | 80 | 77 | 96.25% | 1 | 3 | 0 | 0 | 0 | 0 | 291936 | 14514 | 277423 | 291936 | 271767 | 0 | 0 | 0 | 271767 | 271767 | 97.96% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-05-26 | QTR4 | 19/20 |  | 2020-04-28 | QTR4 | 19/20 | 409 | 289117.3
| 04 | T4533 | 43689915201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 83 | 94 | 94 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 299394 | 14505 | 284890 | 321508 | 308462 | 0 | 0 | 0 | 308462 | 308462 | 108.3% | 1 | 0 | 22113 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 22113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22113 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-06-23 | QTR4 | 19/20 |  | 2020-05-29 | QTR4 | 19/20 | 409 | 308306.81
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 26 | 59 | 105 | 10844 | 14463 | 14192 | 96.15% | 25 | 271 | 105 | 0 | 2831 | 792 | 189565763 | 1793432 | 187772333 | 193460495 | 185013361 | -474498 | -239000 | -713498 | 184299863 | 185522333 | 96.15% | 25 | 1723575 | 3894731 | 1976 | 808 | 43 | 108 | 1646876 | 206198 | 4 | 400 | 2479154 | 191675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 85 | 560184 | 395 | 0 | 70 | 164517 | 4400 | 0 | 0 | 0 | 0 | 0 | 30 | 37553 | 0 | 0 | 99 | -85346 | 54706 | 0 | 0 | 7918 | 0 | 0 | 0 | 58933 | 0 | 0 | 0 | -972544 | 0 | 47 | 792 | 3900242 | 457375
| 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 100.9% | 1 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | 98.74% | 1 | -6213797 | 2243984 | 183 | 45 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -404828 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 102.1% | 1 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | 95.08% | 1 | -417090 | -338192 | 219 | 89 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 95.23% | 1 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | 99.35% | 1 | -3249187 | 3281488 | 165 | 64 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -202797 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 |  | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P04 | 23193225201 | 2014-04-16 | QTR4 | 13/14 | 7 | 11 | 979 | 1575 | 1811 | 154.6% | 0 | -236 | 236 | 0 | 297 | 299 | 32540300 | 150000 | 32390300 | 33830739 | 33682875 | -2003878 | 0 | -2003878 | 31678997 | 31225551 | 96.4% | 1 | -348367 | 1290439 | 225 | 72 | 0 | 299 | 1014970 | 0 | 0 | 0 | 128450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -960 | 0 | 0 | 299 | 1187254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-12 | QTR1 | 19/20 | 409 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | 101.9% | 1 | -500000 | 58245 | 22 | 76 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | 109.7% | 1 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | 99.01% | 1 | -4739 | 364238 | 220 | 71 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4Q64 | 43310855201 | 2015-05-29 | QTR4 | 14/15 | 1 | 30 | 1400 | 1506 | 1365 | 89.93% | 1 | 141 | 0 | 0 | 106 | 0 | 153917279 | 150000 | 153767279 | 162463226 | 162823699 | 0 | 3720000 | 3720000 | 166543699 | 162492246 | 105.7% | 1 | -3709579 | 8545947 | 57 | 49 | 0 | 0 | 1603424 | 0 | 0 | 0 | 2717641 | 75013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480038 | 468544 | 0 | 0 | 1150398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -669018 | 0 | 0 | 0 | 8290048 | 543557 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-03 | QTR2 | 19/20 | 406 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4S19 | 43215415201 | 2019-01-04 | QTR3 | 18/19 | 1 | 1 | 150 | 217 | 214 | 101.3% | 1 | 3 | 0 | 0 | 62 | 5 | 2497568 | 50000 | 2447568 | 2505758 | 2398176 | 0 | 0 | 0 | 2398176 | 2389987 | 97.65% | 1 | 0 | 8189 | 37 | 25 | 0 | 5 | 13102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 13102 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-12 | QTR3 | 19/20 | 409 | 3078159.73
| 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 97.73% | 1 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 114.7% | 0 | 167827 | 1860107 | 73 | 34 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4S38 | 42684015201 | 2017-05-05 | QTR4 | 16/17 | 1 | 4 | 732 | 868 | 868 | 101.9% | 1 | 0 | 0 | 0 | 122 | 14 | 7933333 | 75464 | 7857869 | 10078503 | 10162546 | 0 | 0 | 0 | 10162546 | 10130655 | 128.9% | 0 | 5251 | 2145170 | 54 | 68 | 0 | 14 | 3468 | 0 | 0 | 0 | 2024646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22168 | 0 | 0 | 0 | 83382 | 2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2133664 | 2563 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2020-03-01 | QTR3 | 19/20 | 408 | 6966383.46
| 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | 151.3% | 0 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 99.55% | 1 | 172641 | 33902 | 24 | 21 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1
| 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 113% | 1 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 99.98% | 1 | 2288 | 48308 | 23 | 34 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 |  | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12
| 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 101.4% | 1 | 2719 | 0 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33
| 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 101.7% | 1 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 |  | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67
| 04 | E4T45 | 44145415201 | 2018-12-07 | QTR2 | 18/19 | 1 | 0 | 264 | 303 | 286 | 93.56% | 1 | 17 | 0 | 0 | 39 | 0 | 1195515 | 50000 | 1145515 | 1195515 | 1144992 | 0 | 0 | 0 | 1144992 | 1144992 | 99.95% | 1 | 0 | 0 | 13 | 26 | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-02-29 | QTR3 | 19/20 | 412 | 1552783.3
| 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 30.92% | 1 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 100.3% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42
| 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 48.93% | 1 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 99.58% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28
| 04 | E4T52 | 43784715201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 182 | 248 | 248 | 103.8% | 1 | 0 | 0 | 0 | 66 | 0 | 1344115 | 50000 | 1294115 | 1351758 | 1279142 | 0 | 0 | 0 | 1279142 | 1271289 | 98.24% | 1 | -209 | 7643 | 34 | 25 | 0 | 0 | 4800 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 30930 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-04 | QTR4 | 19/20 |  | 2020-01-27 | QTR3 | 19/20 | 412 | 1455182.8
| 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 50.41% | 1 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 99.12% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4
| 04 | E4T55 | 43388915201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 119 | 207 | 207 | 115.1% | 1 | 0 | 0 | 0 | 70 | 18 | 436087 | 29381 | 406707 | 451388 | 443815 | 0 | 0 | 0 | 443815 | 443815 | 109.1% | 1 | 0 | 15300 | 47 | 23 | 0 | 0 | 0 | 0 | 0 | 18 | 44166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 44166 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-06 | QTR3 | 19/20 | 412 | 589902.2
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 20 | 40 | 117 | 12306 | 15291 | 14703 | 90% | 18 | 588 | 334 | 0 | 2207 | 778 | 583834589 | 1696727 | 582137863 | 603399359 | 602357366 | -2668972 | 5140000 | 2471028 | 604828394 | 589552390 | 90% | 18 | -14092242 | 19564768 | 1440 | 758 | 2 | 512 | 5888763 | 7451 | 0 | 86 | 6285537 | 214332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80300 | 0 | 0 | 27 | 4995886 | 506015 | 0 | 35 | 1437307 | 2563 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 119 | 1355416 | 34593 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1277603 | 0 | 9 | 779 | 18773169 | 764954
| District 04 Totals |  |  |  |  | 46 | 99 | 222 | 23150 | 29754 | 28895 | 93.48% | 43 | 859 | 439 | 0 | 5038 | 1570 | 773400352 | 3490159 | 769910196 | 796859854 | 787370727 | -3143470 | 4901000 | 1757530 | 789128257 | 775074723 | 93.48% | 43 | -12368667 | 23459499 | 3416 | 1566 | 45 | 620 | 7535639 | 213649 | 4 | 486 | 8764691 | 406007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83300 | 0 | 0 | 112 | 5556070 | 506410 | 0 | 105 | 1601824 | 6963 | 0 | 0 | 0 | 0 | 0 | 30 | 45118 | 0 | 0 | 218 | 1270070 | 89299 | 7 | 0 | 7918 | 0 | 0 | 0 | 58933 | 0 | 0 | 0 | -2250147 | 0 | 56 | 1571 | 22673411 | 1222329
| 05 | BE626 | 43787225201 | 2018-05-24 | QTR4 | 17/18 | 1 | 0 | 280 | 344 | 213 | 53.21% | 1 | 131 | 0 | 0 | 64 | 0 | 720000 | 0 | 720000 | 720000 | 720000 | 0 | 0 | 0 | 720000 | 720000 | 100% | 1 | 0 | 0 | 41 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-01-17 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 507 | 720000
| 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 102.4% | 1 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | 101.4% | 1 | -3056235 | 3576803 | 117 | 48 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -155690 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5506 | 41840325201 | 2015-06-17 | QTR4 | 14/15 | 4 | 18 | 800 | 1180 | 1181 | 130% | 0 | -1 | 1 | 0 | 232 | 148 | 12348616 | 73000 | 12275616 | 13716737 | 13601127 | 0 | 0 | 0 | 13601127 | 13641534 | 111.1% | 0 | 107227 | 1368121 | 86 | 55 | 0 | 21 | 799701 | 22020 | 91 | 30 | 336757 | 232158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80666 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 114786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19902 | 0 | 0 | 0 | 0 | 0 | 91 | 148 | 1319075 | 254178 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2019-02-06 | QTR3 | 18/19 | 509 | 11281111.5
| 05 | T5569 | 43442615201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 180 | 235 | 235 | 107.8% | 1 | 0 | 0 | 0 | 41 | 14 | 1957429 | 50000 | 1907429 | 2177504 | 2168249 | 0 | 0 | 0 | 2168249 | 2060853 | 108% | 1 | 8636 | 220075 | 26 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 112214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 112539 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | QTR4 | 19/20 |  | 2017-12-21 | QTR2 | 17/18 | 509 | 2248770.95
| 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 76% | 1 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | 101.8% | 1 | -30000 | 19031 | 14 | 56 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
| 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 82.37% | 1 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | 100.9% | 1 | -14500 | 0 | 18 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75
| 05 | T5591 | 42823815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 500 | 652 | 649 | 107.4% | 1 | 3 | 0 | 0 | 112 | 40 | 16694356 | 150000 | 16544356 | 16972569 | 16490950 | 0 | 0 | 0 | 16490950 | 16700809 | 100.9% | 1 | 209859 | 278213 | 41 | 71 | 0 | 40 | 16791 | 0 | 0 | 0 | 143061 | 49425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137620 | 132029 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 332991 | 181454 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-13 | QTR3 | 19/20 |  | 2019-08-15 | QTR1 | 19/20 | 514 | 15183626.94
| 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 107.7% | 1 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 108% | 1 | 265414 | 161314 | 43 | 47 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492
| 05 | T5606 | 43803815201 | 2018-01-31 | QTR3 | 17/18 | 4 | 10 | 390 | 508 | 508 | 105.1% | 1 | 0 | 0 | 0 | 98 | 20 | 8022650 | 95000 | 7927650 | 8458736 | 8268967 | 0 | 0 | 0 | 8268967 | 8611040 | 108.6% | 1 | 346762 | 436086 | 41 | 57 | 0 | 0 | 435190 | 0 | 0 | 20 | 91027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 467173 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-13 | QTR4 | 19/20 |  | 2019-10-24 | QTR2 | 19/20 | 513 | 9588756
| 05 | T5616 | 43065515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 260 | 334 | 334 | 102.7% | 1 | 0 | 0 | 0 | 67 | 7 | 4231483 | 53000 | 4178483 | 4229830 | 4248590 | 0 | 0 | 0 | 4248590 | 4402057 | 105.4% | 1 | 153467 | -1653 | 46 | 21 | 0 | 0 | -14065 | 0 | 0 | 2 | 5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 54377 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 46115 | 2422 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-04 | QTR3 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 512 | 5394340.01
| 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 76.58% | 1 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 101.2% | 1 | 0 | 26406 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410
| 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 112.8% | 1 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 99.75% | 1 | 6737 | 20194 | 36 | 48 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871
| 05 | T5621 | 43623715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 330 | 435 | 435 | 111.2% | 1 | 0 | 0 | 0 | 68 | 37 | 1704711 | 50000 | 1654711 | 1714508 | 1599483 | 0 | 0 | 0 | 1599483 | 1590886 | 96.14% | 1 | -4841 | 9797 | 27 | 41 | 0 | 17 | 5837 | 0 | 0 | 20 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 6040 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-06-01 | QTR4 | 19/20 |  | 2020-01-15 | QTR3 | 19/20 | 514 | 1787643.5
| 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 88.85% | 1 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | 103.2% | 1 | -4945 | 426 | 29 | 31 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026
| 05 | T5635 | 43733015202 | 2018-10-31 | QTR2 | 18/19 | 2 | 2 | 290 | 377 | 377 | 110.3% | 1 | 0 | 0 | 0 | 57 | 30 | 2923010 | 50000 | 2873010 | 2973010 | 2925571 | 0 | 0 | 0 | 2925571 | 2880657 | 100.3% | 1 | -44914 | 50000 | 31 | 26 | 0 | 30 | 10356 | 0 | 0 | 0 | 47588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 57944 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-02-17 | QTR3 | 19/20 | 509 | 3429127
| 05 | T5641 | 44055775201 | 2018-09-26 | QTR1 | 18/19 | 6 | 5 | 300 | 363 | 362 | 105% | 1 | 1 | 0 | 0 | 47 | 16 | 22429705 | 150000 | 22279705 | 22800571 | 23719308 | 0 | 1000000 | 1000000 | 24719308 | 23561852 | 105.8% | 1 | -1020828 | 370866 | 25 | 22 | 0 | 0 | 178586 | 0 | 0 | 6 | 46819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 32848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 280355 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2020-01-31 | QTR3 | 19/20 | 513 | 27275444.74 | B5:B7:B5:B7 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS
| 05 | T5644 | 43988325201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 60 | 124 | 122 | 96.67% | 1 | 2 | 0 | 0 | 64 | 0 | 61969 | 3000 | 58969 | 61969 | 61131 | 0 | 0 | 0 | 61131 | 61131 | 103.7% | 1 | 0 | 0 | 34 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2020-04-24 | QTR4 | 19/20 |  | 2020-03-20 | QTR3 | 19/20 | 514 | 70243.95
| 05 | T5646 | 43988715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 1 | 90 | 208 | 207 | 196.7% | 0 | 1 | 0 | 0 | 30 | 88 | 85394 | 4523 | 80871 | 85394 | 71417 | 0 | 0 | 0 | 71417 | 71417 | 88.31% | 1 | 0 | 0 | 1 | 29 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2020-02-21 | QTR3 | 19/20 | 512 | 99982.5
| 05 | T5647 | 44106615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 3 | 150 | 227 | 227 | 114% | 1 | 0 | 0 | 0 | 56 | 21 | 2009090 | 50000 | 1959090 | 2023837 | 2344261 | 0 | 0 | 0 | 2344261 | 2338522 | 119.4% | 0 | -200 | 14747 | 33 | 23 | 0 | 0 | 0 | 0 | 0 | 21 | 53178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 53178 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-06-24 | QTR4 | 19/20 |  | 2020-02-04 | QTR3 | 19/20 | 509 | 1775243.2
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 19 | 45 | 98 | 7110 | 9136 | 8607 | 89.47% | 17 | 529 | 1 | 0 | 1521 | 505 | 165724925 | 1284523 | 164440402 | 172275351 | 172656156 | -56415 | 1044500 | 988085 | 173644241 | 170217134 | 89.47% | 17 | -3078361 | 6550426 | 691 | 739 | 0 | 147 | 2427327 | 47041 | 91 | 232 | 2107007 | 322646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 562812 | 134451 | 0 | 0 | 37161 | 0 | 0 | 0 | -78086 | 0 | 0 | 14 | 168516 | 0 | 0 | 97 | 1607957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19902 | 0 | 0 | 0 | -155690 | 0 | 91 | 505 | 6657102 | 504138
| 05 | E5W11 | 24262635201 | 2014-11-21 | QTR2 | 14/15 | 3 | 6 | 900 | 1229 | 1229 | 104.6% | 1 | 0 | 0 | 0 | 288 | 41 | 43150089 | 150000 | 43000089 | 45682181 | 45886261 | 0 | 0 | 0 | 45886261 | 43227195 | 100.5% | 1 | -2633738 | 2532092 | 232 | 56 | 0 | 41 | 2571393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 2600543 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2018-07-08 | QTR1 | 18/19 | 515 | 48952301.58 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | 128.3% | 0 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10359714 | 88.77% | 1 | -459862 | -387154 | 69 | 35 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y20 | 42690435201 | 2016-11-04 | QTR2 | 16/17 | 2 | 5 | 547 | 928 | 921 | 117.9% | 1 | 7 | 0 | 0 | 276 | 105 | 26771800 | 150000 | 26621800 | 27777188 | 27684932 | 0 | 0 | 0 | 27684932 | 28031909 | 105.3% | 1 | 444186 | 1005388 | 215 | 61 | 0 | 14 | 243217 | 16025 | 0 | 91 | 756982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1000199 | 16025 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-01-08 | QTR3 | 19/20 |  | 2019-08-02 | QTR1 | 19/20 | 514 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | 226% | 0 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 180.3% | 0 | 1451 | 1363962 | 39 | 51 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842
| 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 99.29% | 1 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 82.89% | 1 | 1940 | -10 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 |  | 2017-05-14 | QTR4 | 16/17 | 509 | 843684
| 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 111.3% | 1 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | 105.8% | 1 | -795 | 50000 | 60 | 28 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169
| 05 | E5Z09 | 41299445214 | 2017-12-14 | QTR2 | 17/18 | 1 | 1 | 515 | 551 | 514 | 92.82% | 1 | 37 | 0 | 0 | 36 | 0 | 5757000 | 50000 | 5707000 | 5860741 | 5841571 | 0 | 0 | 0 | 5841571 | 5844608 | 102.4% | 1 | 3037 | 103741 | 7 | 29 | 0 | 0 | 77312 | 77312 | 0 | 0 | 26429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134571 | 77312 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 507 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 85% | 1 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 100% | 1 | 0 | 0 | 21 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655
| 05 | E5Z23 | 43564715201 | 2018-05-01 | QTR4 | 17/18 | 1 | 1 | 240 | 281 | 281 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 1013390 | 50000 | 963390 | 1008318 | 958318 | -736 | 0 | -736 | 957582 | 957220 | 99.36% | 1 | -362 | -5072 | 16 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-02 | QTR3 | 19/20 |  | 2019-07-10 | QTR1 | 19/20 | 514 | 1052401
| 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 116.1% | 1 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | 109.1% | 1 | -3198 | 133799 | 15 | 33 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25
| 05 | E5Z27 | 43733815201 | 2018-06-05 | QTR4 | 17/18 | 2 | 4 | 420 | 557 | 554 | 101.7% | 1 | 3 | 0 | 0 | 127 | 10 | 4978323 | 57000 | 4921323 | 5143919 | 4848769 | 0 | 0 | 0 | 4848769 | 4804280 | 97.62% | 1 | -25189 | 165596 | 78 | 49 | 0 | 0 | 7576 | 0 | 0 | 0 | 76771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 89547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 173894 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-05 | QTR3 | 19/20 | 507 | 5765157.09
| 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | 107.5% | 1 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 105.8% | 1 | 0 | 33356 | 25 | 41 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-07-22 | QTR1 | 19/20 | 513 | 480184
| 05 | E5Z45 | 43733915201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 230 | 343 | 343 | 106.5% | 1 | 0 | 0 | 0 | 98 | 15 | 6123814 | 81000 | 6042814 | 6203979 | 6135165 | 0 | 0 | 0 | 6135165 | 6001858 | 99.32% | 1 | -114476 | 80166 | 64 | 34 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-06-01 | QTR4 | 19/20 |  | 2020-01-30 | QTR3 | 19/20 | 512 | 8194285
| 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 98.18% | 1 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 100% | 1 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 |  | 2019-07-18 | QTR1 | 19/20 | 509 | 441431
| 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | 113.3% | 1 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 114.4% | 0 | 0 | 0 | 22 | 3 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5
| 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 115% | 1 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 97.22% | 1 | 0 | 0 | 29 | 10 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2
| 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 97% | 1 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 100.2% | 1 | 0 | 3000 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75
| 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 93.82% | 1 | 0 | 0 | 22 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 513 | 554880
| 05 | E5Z73 | 44096615201 | 2019-04-02 | QTR4 | 18/19 | 1 | 0 | 80 | 161 | 161 | 135% | 0 | 0 | 0 | 0 | 53 | 28 | 648932 | 49732 | 599200 | 648932 | 638000 | 0 | 0 | 0 | 638000 | 638000 | 106.5% | 1 | 0 | 0 | 28 | 25 | 0 | 0 | 0 | 0 | 0 | 28 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 42000 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-20 | QTR4 | 19/20 |  | 2020-01-17 | QTR3 | 19/20 | 513 | 1049373.9
| 05 | E5Z75 | 44180415201 | 2019-05-07 | QTR4 | 18/19 | 1 | 0 | 90 | 100 | 100 | 100% | 1 | 0 | 0 | 0 | 10 | 0 | 176561 | 13561 | 163000 | 176561 | 146000 | 0 | 0 | 0 | 146000 | 146000 | 89.57% | 1 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2019-12-16 | QTR2 | 19/20 | 514 | 287786
| 05 | E5Z76 | 44097015201 | 2019-06-04 | QTR4 | 18/19 | 1 | 0 | 90 | 126 | 2 | -37.78% | 1 | 124 | 0 | 0 | 36 | 0 | 167070 | 12438 | 154632 | 167070 | 148419 | 0 | 0 | 0 | 148419 | 148419 | 95.98% | 1 | 0 | 0 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2020-01-06 | QTR3 | 19/20 | 507 | 271247.25
| 05 | E5Z99 | 44326715201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 80 | 84 | 35 | 38.75% | 1 | 49 | 0 | 0 | 4 | 0 | 293874 | 17231 | 276643 | 293874 | 266752 | 0 | 0 | 0 | 266752 | 266752 | 96.42% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-06-12 | QTR4 | 19/20 |  | 2020-04-30 | QTR4 | 19/20 | 513 | 366851
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 22 | 29 | 35 | 5816 | 8112 | 7945 | 86.36% | 19 | 167 | 101 | 0 | 1603 | 693 | 113199019 | 1176463 | 112022556 | 118277882 | 117158640 | -392172 | 0 | -392172 | 116766468 | 113800380 | 90.91% | 20 | -2787006 | 5078864 | 1003 | 589 | 11 | 197 | 3044136 | 93337 | 0 | 326 | 1926364 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 294737 | 1753 | 0 | 0 | 30150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 693 | 5295378 | 104469
| District 05 Totals |  |  |  |  | 41 | 74 | 133 | 12926 | 17248 | 16552 | 87.8% | 36 | 696 | 102 | 0 | 3124 | 1198 | 278923944 | 2460986 | 276462958 | 290553233 | 289814796 | -448587 | 1044500 | 595913 | 290410709 | 284017514 | 90.24% | 37 | -5865367 | 11629290 | 1694 | 1328 | 11 | 344 | 5471463 | 140378 | 91 | 558 | 4033371 | 332025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 857549 | 136204 | 0 | 0 | 67311 | 0 | 0 | 0 | -78086 | 0 | 0 | 14 | 168516 | 0 | 0 | 97 | 1607947 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | -19902 | 0 | 0 | 0 | -155690 | 0 | 102 | 1198 | 11952480 | 608607
| 06 | T6337 | 41809115201 | 2015-10-28 | QTR2 | 15/16 | 7 | 22 | 600 | 1055 | 1055 | 141.8% | 0 | 0 | 0 | 0 | 324 | 131 | 14239526 | 267180 | 13972346 | 16636939 | 16898897 | 0 | 500000 | 500000 | 17398897 | 16914510 | 121.1% | 0 | -453877 | 2397413 | 147 | 57 | 0 | 87 | 1404877 | 434699 | 120 | 44 | 573331 | 258449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573254 | 54307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 131 | 2554384 | 747455 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-02-15 | QTR3 | 18/19 | 606 | 13498168.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6338 | 41463315201 | 2016-01-27 | QTR3 | 15/16 | 4 | 11 | 560 | 1082 | 1082 | 158.6% | 0 | 0 | 0 | 0 | 352 | 170 | 11118409 | 242209 | 10876200 | 12716281 | 13284136 | 0 | 0 | 0 | 13284136 | 13366087 | 122.9% | 0 | 119047 | 1597872 | 138 | 56 | 7 | 170 | 1172291 | 332615 | 137 | 0 | 139746 | 40433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 320742 | 32961 | 0 | 0 | 8312 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 170 | 1641090 | 414320 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-05-23 | QTR4 | 18/19 | 606 | 10197839.36 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 98.35% | 1 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | 100.4% | 1 | -436405 | 725324 | 52 | 25 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 82.12% | 1 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | 104.4% | 1 | -622662 | 376451 | 74 | 40 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 195.7% | 0 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 166% | 0 | 5872 | 2030258 | 59 | 33 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 105.5% | 1 | 21437 | 21903 | 44 | 6 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25
| 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 72.1% | 1 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | 103.4% | 1 | -191642 | 37940 | 56 | 14 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 |  | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 88.67% | 1 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | 98.77% | 1 | -61063 | 80247 | 31 | 18 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 101.3% | 1 | 1476 | 92454 | 90 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 |  | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45
| 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 108.3% | 1 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | 99.99% | 1 | -4122 | 0 | 48 | 19 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 |  | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7
| 06 | T6438 | 43117015201 | 2018-05-23 | QTR4 | 17/18 | 6 | 2 | 320 | 363 | 295 | 78.75% | 1 | 68 | 0 | 0 | 43 | 0 | 3669797 | 51765 | 3618032 | 3847108 | 3668181 | 0 | 250000 | 250000 | 3918181 | 3697899 | 102.2% | 1 | -220283 | 177311 | 23 | 20 | 0 | 0 | 82758 | 0 | 0 | 0 | 14636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16895 | 16211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189909 | 16211 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 606 | 4444325.03 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6444 | 43640415201 | 2018-07-25 | QTR1 | 18/19 | 2 | 1 | 180 | 271 | 264 | 96.11% | 1 | 7 | 0 | 0 | 91 | 0 | 1113869 | 48941 | 1064928 | 1119160 | 1084619 | 0 | 0 | 0 | 1084619 | 1078347 | 101.3% | 1 | -981 | 5291 | 65 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-06-04 | QTR4 | 19/20 |  | 2020-02-07 | QTR3 | 19/20 | 606 | 1006236.05
| 06 | T6445 | 42611315201 | 2019-01-30 | QTR3 | 18/19 | 2 | 1 | 297 | 349 | 268 | 72.73% | 1 | 81 | 0 | 0 | 52 | 0 | 1196727 | 50260 | 1146467 | 1200684 | 1179569 | 0 | 0 | 0 | 1179569 | 1176527 | 102.6% | 1 | 914 | 3957 | 30 | 22 | 0 | 0 | 15008 | 0 | 0 | 0 | 10372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27799 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2020-03-10 | QTR3 | 19/20 | 606 | 1242692.5
| 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 118% | 1 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | 93.91% | 1 | -1279 | 0 | 40 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85
| 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | 92.06% | 1 | -1113 | 0 | 34 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 |  | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25
| 06 | T6455 | 43791715201 | 2018-08-29 | QTR1 | 18/19 | 2 | 1 | 140 | 203 | 202 | 99.29% | 1 | 1 | 0 | 0 | 63 | 0 | 564205 | 30704 | 533501 | 565127 | 533205 | 0 | 0 | 0 | 533205 | 531866 | 99.69% | 1 | -417 | 923 | 48 | 15 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11222 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 606 | 617376.5
| 06 | T6458 | 44019115201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 200 | 318 | 314 | 104% | 1 | 4 | 0 | 0 | 118 | 0 | 1250000 | 50000 | 1200000 | 1339834 | 941648 | 0 | 0 | 0 | 941648 | 941530 | 78.46% | 1 | -118 | 89834 | 75 | 31 | 12 | 0 | 0 | 0 | 0 | 0 | 3393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 119247 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-23 | QTR3 | 19/20 | 606 | 1429145
| 06 | T6462 | 43792215201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 160 | 195 | 193 | 98.75% | 1 | 2 | 0 | 0 | 35 | 0 | 672522 | 35087 | 637435 | 672522 | 627588 | 0 | 0 | 0 | 627588 | 627091 | 98.38% | 1 | -497 | 0 | 26 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 606 | 724071.25
| 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 97.3% | 1 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | 98.31% | 1 | -24 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 606 | 324690
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 19 | 70 | 81 | 6069 | 8531 | 8037 | 84.21% | 16 | 494 | 0 | 0 | 1926 | 536 | 103986628 | 2718905 | 101267723 | 111623807 | 110549611 | 0 | 2050000 | 2050000 | 112599611 | 110421384 | 84.21% | 16 | -1845737 | 7637178 | 1093 | 430 | 34 | 281 | 4389935 | 897314 | 257 | 222 | 2228777 | 643540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 1592101 | 126924 | 0 | 0 | 30868 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 605995 | 586616 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 403 | 536 | 8333626 | 2262705
| 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 95.74% | 1 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 99.71% | 1 | 1013 | 67062 | 142 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1
| 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 103.3% | 1 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 105% | 1 | 649560 | 1806784 | 96 | 54 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K58 | 43081315201 | 2019-01-31 | QTR3 | 18/19 | 3 | 1 | 200 | 224 | 186 | 81% | 1 | 38 | 0 | 0 | 24 | 0 | 1100030 | 52315 | 1047715 | 1101649 | 1024191 | 0 | 100000 | 100000 | 1124191 | 1025137 | 97.85% | 1 | -97435 | 1619 | 16 | 8 | 0 | 0 | 557 | 0 | 0 | 0 | 16202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17525 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-11-30 | QTR2 | 19/20 | 606 | 1216039.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 84.26% | 1 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | 109.7% | 1 | -358123 | 1067468 | 84 | 14 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 80% | 1 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 93.85% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 |  | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8
| 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 96% | 1 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 104.9% | 1 | 0 | 24000 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 606 | 404500
| 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 92.75% | 1 | 0 | 0 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 |  | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218
| 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 97.08% | 1 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | 93.08% | 1 | -158 | 0 | 23 | 11 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2
| 06 | E6L37 | 42919325201 | 2018-01-25 | QTR3 | 17/18 | 4 | 3 | 200 | 241 | 218 | 88.5% | 1 | 23 | 0 | 0 | 41 | 0 | 1491900 | 50260 | 1441640 | 1633114 | 1580093 | 0 | 60000 | 60000 | 1640093 | 1562174 | 108.4% | 1 | -60174 | 141214 | 29 | 12 | 0 | 0 | 4537 | 0 | 0 | 0 | 82537 | 9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48121 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135195 | 14309 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 606 | 1421302.2 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6L51 | 43029129201 | 2017-12-04 | QTR2 | 17/18 | 2 | 1 | 600 | 723 | 720 | 104.2% | 1 | 3 | 0 | 0 | 123 | 0 | 5545538 | 70946 | 5474592 | 5585378 | 5557420 | 0 | 0 | 0 | 5557420 | 0 | 0% | 1 | -5557420 | 39840 | 31 | 64 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 77248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 82828 | 0 | F301004760 | RTECH HEC JV | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2020-02-17 | QTR3 | 19/20 | 606 | 7161526 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6L72 | 44183315201 | 2019-08-29 | QTR1 | 19/20 | 1 | 0 | 80 | 110 | 107 | 96.25% | 1 | 3 | 0 | 0 | 30 | 0 | 428626 | 19906 | 408720 | 428626 | 355753 | 0 | 0 | 0 | 355753 | 355753 | 87.04% | 1 | 0 | 0 | 12 | 18 | 0 | 0 | 1358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1358 | 0 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2020-05-07 | QTR4 | 19/20 |  | 2020-03-05 | QTR3 | 19/20 | 636 | 412463.45
| 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | 96.53% | 1 | -87 | 0 | 51 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5
| 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 99.5% | 1 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | 99.55% | 1 | -352 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 13 | 26 | 25 | 4110 | 4938 | 4729 | 100% | 13 | 209 | 0 | 0 | 800 | 28 | 102097670 | 724891 | 101372779 | 106778069 | 105498997 | 0 | 560000 | 560000 | 106058997 | 100097176 | 100% | 13 | -5423176 | 3147987 | 518 | 254 | 0 | 28 | 1397543 | 0 | 0 | 0 | 471422 | 129545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 790493 | 53849 | 0 | 0 | 98023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 2756336 | 183394
| District 06 Totals |  |  |  |  | 32 | 96 | 106 | 10179 | 13469 | 12766 | 90.62% | 29 | 703 | 0 | 0 | 2726 | 564 | 206084298 | 3443796 | 202640502 | 218401876 | 216048608 | 0 | 2610000 | 2610000 | 218658608 | 210518560 | 90.62% | 29 | -7268913 | 10785165 | 1611 | 684 | 34 | 309 | 5787478 | 897314 | 257 | 222 | 2700199 | 773085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 2382594 | 180773 | 0 | 0 | 128891 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 605995 | 586616 | 0 | 0 | 0 | 0 | 0 | 0 | -514052 | 0 | 431 | 564 | 11089962 | 2446099
| 07 | T7389 | 43272015201 | 2017-01-25 | QTR3 | 16/17 | 4 | 11 | 350 | 542 | 542 | 100% | 1 | 0 | 0 | 0 | 192 | 0 | 12988889 | 109000 | 12879889 | 13889049 | 13996342 | 0 | 0 | 0 | 13996342 | 14019355 | 108.8% | 1 | 112797 | 900160 | 162 | 30 | 0 | 0 | 619080 | 0 | 0 | 0 | 112343 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 0 | 0 | 677937 | 2775 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2018-10-03 | QTR2 | 18/19 | 798 | 14634544.46
| 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | 206.2% | 0 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 93.7% | 1 | 11195 | 18352 | 19 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400
| 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 99.3% | 1 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 99.75% | 1 | 69368 | 0 | 68 | 19 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000
| 07 | T7399 | 43653015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 145 | 210 | 211 | 119.3% | 1 | -1 | 1 | 0 | 48 | 17 | 1314062 | 50000 | 1264062 | 1314062 | 1279715 | -1665 | 0 | -1665 | 1278050 | 1277840 | 101.1% | 1 | -210 | 0 | 29 | 9 | 0 | 0 | 0 | 0 | 10 | 12 | 15865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 21855 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 796 | 1374960.82
| 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 101.5% | 1 | 65512 | 6728 | 41 | 21 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300
| 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 111.1% | 1 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 99.28% | 1 | 6971 | 0 | 61 | 22 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM
| 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 91.82% | 1 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 98.93% | 1 | 0 | 0 | 24 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000
| 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 90.89% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5
| 07 | T7421 | 43648115201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 120 | 196 | 195 | 108.3% | 1 | 1 | 0 | 0 | 76 | 0 | 1160445 | 50000 | 1110445 | 1160445 | 1174720 | 0 | 0 | 0 | 1174720 | 1174720 | 105.8% | 1 | 0 | 0 | 43 | 22 | 0 | 0 | 12711 | 0 | 0 | 0 | 35671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48382 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-19 | QTR4 | 19/20 |  | 2020-03-06 | QTR3 | 19/20 | 796 | 1200000
| 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 93.17% | 1 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 100.7% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91
| 07 | T7427 | 43704015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 160 | 205 | 189 | 101.2% | 1 | 16 | 0 | 0 | 27 | 18 | 1130856 | 50000 | 1080856 | 1130856 | 1101423 | 0 | 0 | 0 | 1101423 | 1102091 | 102% | 1 | 668 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-12-16 | QTR2 | 19/20 | 799 | 1234500
| 07 | T7429 | 43753015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 120 | 132 | 101 | 74.17% | 1 | 31 | 0 | 0 | 12 | 0 | 1704462 | 50000 | 1654462 | 1704462 | 1672069 | 0 | 0 | 0 | 1672069 | 1672069 | 101.1% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-17 | QTR2 | 19/20 | 796 | 2200000
| 07 | T7430 | 42907525201 | 2019-02-27 | QTR3 | 18/19 | 1 | 1 | 160 | 181 | 181 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 2054444 | 50000 | 2004444 | 2076789 | 2031481 | 0 | 0 | 0 | 2031481 | 2031871 | 101.4% | 1 | 390 | 22345 | 8 | 13 | 0 | 0 | 16576 | 0 | 0 | 0 | 11397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3656 | 3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31629 | 3656 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-13 | QTR4 | 19/20 |  | 2019-12-14 | QTR2 | 19/20 | 798 | 2450000
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 13 | 20 | 15 | 2023 | 2850 | 2892 | 92.31% | 12 | -42 | 113 | 0 | 735 | 92 | 31197084 | 663780 | 30533304 | 32144668 | 31686207 | -179073 | 0 | -179073 | 31507134 | 31684042 | 100% | 13 | 266691 | 947585 | 486 | 215 | 13 | 44 | 708088 | 0 | 10 | 43 | 271134 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10719 | 3656 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 23 | 92 | 936455 | 6431
| 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 119.1% | 1 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | 101% | 1 | -1461417 | 2388357 | 330 | 85 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7K19 | 43476515201 | 2014-10-20 | QTR2 | 14/15 | 2 | 16 | 1200 | 1842 | 1829 | 134.9% | 0 | 13 | 0 | 0 | 210 | 432 | 35360313 | 120000 | 35240313 | 59863754 | 59642810 | 0 | 0 | 0 | 59642810 | 59439123 | 168.7% | 0 | 0 | 24503441 | 97 | 113 | 0 | 362 | 23073894 | 0 | 0 | 0 | 379221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 901989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 24357946 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 714 | 35360312.5
| 07 | E7K24 | 41101145201 | 2015-04-09 | QTR4 | 14/15 | 3 | 20 | 1100 | 1320 | 1320 | 103.1% | 1 | 0 | 0 | 0 | 188 | 32 | 94976100 | 150000 | 94826100 | 96934830 | 96454835 | 0 | 0 | 0 | 96454835 | 95867383 | 101.1% | 1 | -259483 | 1958730 | 108 | 78 | 2 | 30 | 982160 | 90496 | 0 | 0 | 91279 | 4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567939 | 0 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 1718138 | 127398 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 714 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 111.7% | 1 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | 105.4% | 1 | -265912 | 1412899 | 124 | 53 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 105.5% | 1 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 104.4% | 1 | 301 | 232401 | 76 | 23 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26
| 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | 100.5% | 1 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 100.6% | 1 | 2402 | 0 | 242 | 27 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311
| 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 74% | 1 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 98.67% | 1 | 0 | 0 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000
| 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 117.1% | 1 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | 106.5% | 1 | -5930 | 197052 | 173 | 25 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65
| 07 | E7M05 | 43954615201 | 2018-05-30 | QTR4 | 17/18 | 1 | 1 | 360 | 374 | 219 | 56.94% | 1 | 155 | 0 | 0 | 14 | 0 | 2278000 | 50000 | 2228000 | 2281910 | 2448836 | 0 | 0 | 0 | 2448836 | 2448834 | 109.9% | 1 | -1 | 3910 | 9 | 5 | 0 | 0 | 3910 | 0 | 0 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5967 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-04-09 | QTR4 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 799 | 1751000
| 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | 112.1% | 1 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | 98.97% | 1 | -14425 | 0 | 36 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38
| 07 | E7M24 | 43649415201 | 2019-03-13 | QTR3 | 18/19 | 2 | 0 | 125 | 182 | 179 | 100% | 1 | 3 | 0 | 0 | 54 | 3 | 2316390 | 50000 | 2266390 | 2316390 | 2260239 | 0 | 0 | 0 | 2260239 | 2257824 | 99.62% | 1 | -2415 | 0 | 35 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 24120 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-25 | QTR4 | 19/20 |  | 2020-03-13 | QTR3 | 19/20 | 796 | 1445000
| 07 | E7M25 | 43386415201 | 2019-04-10 | QTR4 | 18/19 | 2 | 1 | 110 | 123 | 112 | 90% | 1 | 11 | 0 | 0 | 13 | 0 | 354276 | 10000 | 344276 | 375176 | 357381 | 0 | 0 | 0 | 357381 | 336481 | 97.74% | 1 | 0 | 20901 | 3 | 10 | 0 | 0 | 3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3553 | 0 | F842663349 | CHEYENNE ASSOCIATES LLC | N/A | N/A | N/A | N/A | 2020-06-03 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 798 | 264999.9
| 07 | E7M26 | 25839935201 | 2018-12-12 | QTR2 | 18/19 | 2 | 0 | 90 | 194 | 194 | 118.9% | 1 | 0 | 0 | 0 | 87 | 17 | 1194104 | 30000 | 1164104 | 1194104 | 1177035 | 0 | 0 | 0 | 1177035 | 1177035 | 101.1% | 1 | 0 | 0 | 78 | 9 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-06 | QTR2 | 19/20 | 796 | 850000
| 07 | E7M27 | 43648015201 | 2018-12-12 | QTR2 | 18/19 | 1 | 2 | 150 | 180 | 180 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1274649 | 45000 | 1229649 | 1382195 | 1318471 | 0 | 0 | 0 | 1318471 | 1320688 | 107.4% | 1 | 2217 | 107546 | 21 | 9 | 0 | 0 | 93140 | 0 | 0 | 0 | 22511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115651 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-09-10 | QTR1 | 19/20 | 798 | 980000
| 07 | E7M28 | 43754115201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 175 | 201 | 162 | 77.71% | 1 | 39 | 0 | 0 | 26 | 0 | 870000 | 50000 | 820000 | 870000 | 820000 | 0 | 0 | 0 | 820000 | 820000 | 100% | 1 | 0 | 0 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 796 | 1950395 | B0 | ACC - LUMP SUM
| 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 69.7% | 1 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 84.89% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 798 | 175000
| 07 | E7M32 | 43751815201 | 2019-03-13 | QTR3 | 18/19 | 1 | 0 | 165 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 852730 | 40000 | 812730 | 852730 | 751999 | 0 | 0 | 0 | 751999 | 752000 | 92.53% | 1 | 1 | 0 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2020-02-14 | QTR3 | 19/20 | 796 | 850000
| 07 | E7M33 | 43764915201 | 2019-03-13 | QTR3 | 18/19 | 1 | 1 | 220 | 286 | 286 | 102.7% | 1 | 0 | 0 | 0 | 60 | 6 | 2477868 | 50000 | 2427868 | 2501292 | 2443200 | 0 | 0 | 0 | 2443200 | 2437101 | 100.4% | 1 | -6099 | 23425 | 28 | 32 | 0 | 3 | 20944 | 0 | 0 | 3 | 7381 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 28325 | 3875 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-21 | QTR4 | 19/20 |  | 2020-03-18 | QTR3 | 19/20 | 798 | 2667000
| 07 | E7M34 | 41918235201 | 2018-09-12 | QTR1 | 18/19 | 1 | 0 | 120 | 181 | 180 | 115.8% | 1 | 1 | 0 | 0 | 41 | 20 | 1124875 | 40000 | 1084875 | 1124875 | 1167653 | 0 | 0 | 0 | 1167653 | 1167653 | 107.6% | 1 | 0 | 0 | 32 | 9 | 0 | 0 | 8918 | 0 | 0 | 20 | 14048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-21 | QTR4 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 798 | 1030000
| 07 | E7M36 | 43648815201 | 2019-04-10 | QTR4 | 18/19 | 1 | 1 | 135 | 168 | 168 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1604974 | 50000 | 1554974 | 1606756 | 1564847 | 0 | 0 | 0 | 1564847 | 1550744 | 99.73% | 1 | -14103 | 1782 | 6 | 27 | 0 | 0 | 996 | 0 | 0 | 0 | 6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7665 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-04 | QTR4 | 19/20 |  | 2020-02-24 | QTR3 | 19/20 | 799 | 2102050
| 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 100% | 1 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 90.04% | 1 | 0 | 0 | 106 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R07 | 43845015201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 500 | 572 | 572 | 100% | 1 | 0 | 0 | 0 | 72 | 0 | 2568748 | 50000 | 2518748 | 2568748 | 2497748 | 0 | 0 | 0 | 2497748 | 2497782 | 99.17% | 1 | 34 | 0 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-01-29 | QTR3 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 796 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R08 | 43402515201 | 2018-03-16 | QTR3 | 17/18 | 1 | 0 | 520 | 644 | 643 | 99.81% | 1 | 1 | 0 | 0 | 124 | 0 | 5832000 | 75000 | 5757000 | 5832000 | 5747984 | 0 | 0 | 0 | 5747984 | 5747984 | 99.84% | 1 | 0 | 0 | 75 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-04-01 | QTR4 | 19/20 |  | 2020-02-19 | QTR3 | 19/20 | 796 | 8500000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R16 | 44255215201 | 2018-07-24 | QTR1 | 18/19 | 1 | 1 | 250 | 359 | 463 | 159.6% | 0 | -104 | 104 | 0 | 64 | 45 | 1859105 | 50000 | 1809105 | 1859105 | 1788137 | -173160 | 0 | -173160 | 1614977 | 1610005 | 88.99% | 1 | -4972 | 0 | 41 | 23 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2019-12-30 | QTR2 | 19/20 | 799 | 3000566 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R60 | 43920615201 | 2017-09-07 | QTR1 | 17/18 | 1 | 2 | 540 | 637 | 633 | 101.9% | 1 | 4 | 0 | 0 | 83 | 14 | 12005445 | 85975 | 11919470 | 12159938 | 12017053 | 0 | 30000 | 30000 | 12047053 | 12031297 | 100.9% | 1 | 38737 | 154493 | 48 | 35 | 0 | 0 | 9573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 115055 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 714 | 11747696.43 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 25 | 38 | 72 | 8566 | 11992 | 11836 | 92% | 23 | 156 | 125 | 0 | 2565 | 861 | 300331964 | 1571300 | 298760664 | 331336899 | 329462590 | -245745 | 280000 | 34255 | 329496845 | 326665741 | 96% | 24 | -1991065 | 31004937 | 1763 | 800 | 2 | 487 | 26815775 | 811977 | 0 | 227 | 1544899 | 47032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 142 | 1864661 | 44154 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 57335 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 46859 | 18713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 861 | 30501990 | 954243
| District 07 Totals |  |  |  |  | 38 | 58 | 87 | 10589 | 14842 | 14728 | 92.11% | 35 | 114 | 238 | 0 | 3300 | 953 | 331529048 | 2235080 | 329293968 | 363481567 | 361148797 | -424818 | 280000 | -144818 | 361003979 | 358349783 | 97.37% | 37 | -1724374 | 31952522 | 2249 | 1015 | 15 | 531 | 27523863 | 811977 | 10 | 270 | 1816033 | 49807 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 142 | 1864661 | 44154 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 57335 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 57578 | 22369 | 0 | 0 | 0 | 0 | 0 | 0 | -84321 | 0 | 25 | 953 | 31438445 | 960674
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | 114.8% | 1 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | 96.75% | 1 | -965750 | -115989 | 28 | 37 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8N92 | 42337225201 | 2015-05-07 | QTR4 | 14/15 | 6 | 18 | 875 | 1607 | 1607 | 163.2% | 0 | 0 | 0 | 0 | 334 | 398 | 69954000 | 150000 | 69804000 | 73801707 | 73879251 | -35000 | 0 | -35000 | 73844251 | 73217932 | 104.9% | 1 | -587478 | 3847707 | 114 | 65 | 0 | 0 | 265519 | 0 | 0 | 0 | 1597547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | -1019642 | 0 | 0 | 0 | 327117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52381 | 0 | 155 | 398 | 3718160 | 0 | F471943651 | DE MOYA REDLAND HEFT JV | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-02-28 | QTR3 | 19/20 | 854 | 67972638.7 | B8 | ACC - DESIGN/BUILD - MAJOR
| 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 107.4% | 1 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 102.2% | 1 | 5194 | 40000 | 34 | 22 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53
| 08 | E8P89 | 43546215201 | 2016-06-02 | QTR4 | 15/16 | 6 | 8 | 622 | 985 | 975 | 139.5% | 0 | 10 | 0 | 0 | 107 | 256 | 14923655 | 150000 | 14773655 | 18836210 | 18823730 | -19000 | 0 | -19000 | 18804730 | 19033852 | 128.8% | 0 | 314158 | 3912555 | 66 | 41 | 0 | 0 | 195633 | 0 | 0 | 23 | 80550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807 | 0 | 0 | 147 | 3553990 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 3854332 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 854 | 23170861.47 | B8 | ACC - DESIGN/BUILD - MAJOR
| 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 68.9% | 1 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | 108.3% | 1 | -1735624 | 1811802 | 56 | 35 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q41 | 43516515201 | 2017-02-14 | QTR3 | 16/17 | 4 | 6 | 280 | 520 | 520 | 118.9% | 1 | 0 | 0 | 0 | 187 | 53 | 15839502 | 62339 | 15777163 | 16427426 | 16013444 | -22000 | 0 | -22000 | 15991444 | 16637324 | 105.5% | 1 | 657394 | 587924 | 130 | 57 | 0 | 20 | 279691 | 0 | 0 | 33 | 128973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 463933 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2018-10-31 | QTR2 | 18/19 | 854 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8Q54 | 43517115201 | 2017-06-06 | QTR4 | 16/17 | 4 | 9 | 315 | 573 | 645 | 144.8% | 0 | -72 | 72 | 0 | 189 | 69 | 16868340 | 150000 | 16718340 | 17223693 | 16580725 | -451756 | 0 | -451756 | 16128969 | 17010121 | 101.7% | 1 | 1219409 | 355352 | 93 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 175352 | 0 | 0 | 0 | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 264477 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-30 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 854 | 18298995
| 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 119.3% | 1 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 107% | 1 | 2296 | 34423 | 37 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26
| 08 | E8Q92 | 43798815201 | 2018-01-23 | QTR3 | 17/18 | 3 | 3 | 315 | 440 | 440 | 111.4% | 1 | 0 | 0 | 0 | 89 | 36 | 9338889 | 101107 | 9237782 | 10684311 | 9478150 | 0 | 0 | 0 | 9478150 | 9949597 | 107.7% | 1 | 471447 | 1345422 | 43 | 46 | 0 | 0 | 653762 | 0 | 0 | 0 | 31212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 677701 | 0 | 0 | 1 | 32396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1395071 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-24 | QTR4 | 19/20 |  | 2019-08-08 | QTR1 | 19/20 | 854 | 10469556.31
| 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 102.8% | 1 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 106.9% | 1 | 176726 | 494166 | 44 | 52 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24
| 08 | E8R46 | 44154915201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 125 | 160 | 160 | 101.6% | 1 | 0 | 0 | 0 | 33 | 2 | 648447 | 32811 | 615636 | 654795 | 614302 | 0 | 0 | 0 | 614302 | 607816 | 98.73% | 1 | -137 | 6348 | 7 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2020-01-10 | QTR3 | 19/20 | 854 | 709931.87
| 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 97.14% | 1 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36
| 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 95.28% | 1 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 101.6% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4
| 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 99.33% | 1 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | 99.14% | 1 | -6566 | 0 | 44 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04
| 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 78% | 1 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | 108.2% | 1 | -1354 | 148560 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 15 | 37 | 84 | 5269 | 7655 | 7416 | #VALUE! | 12 | 239 | 96 | 0 | 1492 | 894 | 235925419 | 1323815 | 234601603 | 248393690 | 247004621 | -778672 | 2385000 | 1606328 | 248610949 | 247569647 | 93.33% | 14 | -450285 | 12468270 | 729 | 524 | 0 | 41 | 2478470 | 0 | 68 | 80 | 3200339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 171 | 112 | -179695 | 0 | 0 | 1 | 625321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807 | 0 | 0 | 545 | 6153990 | 0 | 0 | 27 | 36877 | 34423 | 0 | 86 | 0 | 0 | 0 | 0 | -52381 | 0 | 239 | 892 | 12267831 | 34423
| District 08 Totals |  |  |  |  | 15 | 37 | 84 | 5269 | 7655 | 7416 | 80% | 12 | 239 | 96 | 0 | 1492 | 894 | 235925419 | 1323815 | 234601603 | 248393690 | 247004621 | -778672 | 2385000 | 1606328 | 248610949 | 247569647 | 93.33% | 14 | -450285 | 12468270 | 729 | 524 | 0 | 41 | 2478470 | 0 | 68 | 80 | 3200339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 171 | 112 | -179695 | 0 | 0 | 1 | 625321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807 | 0 | 0 | 545 | 6153990 | 0 | 0 | 27 | 36877 | 34423 | 0 | 86 | 0 | 0 | 0 | 0 | -52381 | 0 | 239 | 892 | 12267831 | 34423
| Statewide Central Let Contracts SubTotal |  |  |  |  | 170 | 340 | 522 | 47880 | 67141 | 64834 | 85.29% | 145 | 2307 | 457 | 0 | 15288 | 3977 | 988991659 | 11211660 | 977780000 | 1022343017 | 1014413734 | -1603426 | 5645500 | 4042074 | 1018455808 | 1017429355 | 88.24% | 150 | 946969 | 33351357 | 9559 | 4613 | 195 | 1120 | 13549890 | 17003486 | 577 | 1807 | 11687425 | 1601326 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 116 | 219 | 3021803 | 272512 | 26 | 74 | 483868 | 40843 | 0 | 0 | -78086 | 0 | 0 | 75 | 518448 | 0 | 0 | 595 | 7427053 | 166024 | 136 | 77 | 862461 | 693517 | 69 | 0 | 62964 | 279 | 0 | 0 | -2838084 | 0 | 1119 | 3967 | 34731579 | 19777988
| Statewide District Let Contracts SubTotal |  |  |  |  | 144 | 237 | 440 | 49124 | 66476 | 65192 | 86.81% | 125 | 1284 | 1706 | 0 | 12282 | 5070 | 1803149100 | 9172386 | 1793976712 | 1897132458 | 1887556879 | -14475299 | 10770000 | -3705299 | 1883851580 | 1855703838 | 92.36% | 133 | -24398851 | 92450946 | 7332 | 4291 | 169 | 1821 | 45466494 | 1235941 | 123 | 1597 | 28755705 | 1630216 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451000 | 0 | 234 | 672 | 8105134 | 628881 | 111 | 38 | 2267560 | 34929 | 0 | 0 | 0 | 0 | 15 | 68 | 321766 | 0 | 0 | 679 | 7614229 | 34593 | 7 | 41 | 95723 | 53136 | 0 | 153 | 0 | 0 | 0 | 0 | -2064094 | 0 | 659 | 5069 | 91015984 | 3617696
| Statewide Totals |  |  |  |  | 314 | 577 | 962 | 97004 | 133617 | 130026 | 85.99% | 270 | 3591 | 2163 | 0 | 27570 | 9047 | 2792140759 | 20384046 | 2771756712 | 2919475475 | 2901970613 | -16078725 | 16415500 | 336775 | 2902307388 | 2873133193 | 90.13% | 283 | -23451882 | 125802303 | 16891 | 8904 | 364 | 2941 | 59016384 | 18239427 | 700 | 3404 | 40443130 | 3231542 | 0 | 0 | 33297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454000 | 0 | 350 | 891 | 11126937 | 901393 | 137 | 112 | 2751428 | 75772 | 0 | 0 | -78086 | 0 | 15 | 143 | 840214 | 0 | 0 | 1274 | 15041282 | 200617 | 143 | 118 | 958184 | 746653 | 69 | 153 | 62964 | 279 | 0 | 0 | -4902178 | 0 | 1778 | 9036 | 125747563 | 23395684

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P56 | 41968815201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-01-19 | 1109997 | 1109997 | 793278 | 0 | 0 | 793278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793278 | 793278 | 0 | 2383057
1 | E1P91 | 42271055201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-04-20 | 10071503 | 10247666 | 9983254 | 176162.86 | 0 | 10182044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9983254 | 10182044 | 198791 | 11091792 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1P94 | 43493915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-18 | 9111251 | 9111251 | 9282956 | 0 | 0 | 9644340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 9289725
1 | E1Q23 | 43665015201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-02-13 | 918123 | 918123 | 868123 | 0 | -104895 | 851629 | -104895 | 0 | 0 | 0 | 0 | 0 | -104895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104895 | 763228 | 851629 | 88401 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
1 | E1Q29 | 42584115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-04-20 | 54145606 | 56232960 | 55752280 | 2087354.08 | 2500000 | 56885286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | -1366994 | 61229521 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R12 | 43668215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-21 | 1472083 | 1472083 | 1445724 | 0 | 65000 | 1446603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 1510724 | 1446603 | -64121 | 1181939 | B1 | ACC - NO EXCUSE BONUS
1 | E1R26 | 43319415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-16 | 604486 | 604486 | 584381 | 0 | 0 | 583598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584381 | 583598 | -783 | 489570
1 | E1R46 | 43806315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-19 | 3730005 | 3730005 | 3622277 | 0 | 0 | 3609915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 4986764
1 | E1R51 | 43800815201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-09-20 | 2579000 | 2579000 | 2523711 | 0 | 0 | 2514757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523711 | 2514757 | -8954 | 2698176 | B0 | ACC - LUMP SUM
1 | E1R66 | 43641515201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-02-21 | 5199494 | 5281274 | 4820096 | 81779.62 | -421972 | 4398124 | -261972 | 0 | 0 | 0 | 0 | 0 | -261972 | 0 | 0 | 0 | 0 | -160000 | 0 | -160000 | -421972 | 4398124 | 4398124 | 0 | 3837740 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R80 | 43771615201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-04-18 | 157000 | 157000 | 148434 | 0 | 0 | 148434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148434 | 148434 | 0 | 169094
1 | E1S00 | 43943515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-23 | 2112776 | 2112776 | 2088952 | 0 | 0 | 2065283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088952 | 2065283 | -23668 | 3162693 | B0 | ACC - LUMP SUM
1 | E1S90 | 43506515201 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2019-12-05 | 264680 | 264680 | 252175 | 0 | 0 | 252175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252175 | 252175 | 0 | 235219 | B0 | ACC - LUMP SUM
1 | T1634 | 43137315201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 8177462 | 8672530 | 8450258 | 495067.74 | 0 | 8318044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8450258 | 8318044 | -132214 | 9745221
1 | T1636 | 43323815201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 1444112 | 1455710 | 1455710 | 11597.86 | 0 | 1456120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 1303711 | B0 | ACC - LUMP SUM
1 | T1664 | 20103265201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-02-22 | 39141064 | 41032774 | 41293102 | 1891709.53 | 2220000 | 42013585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220000 | 0 | 2220000 | 2220000 | 43513102 | 42013585 | -1499517 | 43211573 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1667 | 43494215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-08-31 | 1182957 | 696968 | 671825 | -485989.48 | 0 | 678334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671825 | 678334 | 6509 | 1125231 | B0 | ACC - LUMP SUM
1 | T1671 | 43560615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-07 | 8453536 | 8694533 | 8807307 | 240997 | 0 | 9108126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8807307 | 9108126 | 300819 | 8498514
1 | T1693 | 43450215201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2535000 | 2909249 | 2922189 | 374249.35 | 0 | 2922984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 2562824 | B1 | ACC - NO EXCUSE BONUS
1 | T1697 | 43534915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2532999 | 2582335 | 2599237 | 49336.16 | 0 | 2598348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 2201661
1 | T1701 | 43498615201 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2018-02-28 | 8087167 | 8023343 | 7632042 | -63824.06 | 570000 | 7685776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 0 | 570000 | 570000 | 8202042 | 7685776 | -516267 | 8094282 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1704 | 44011615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-03-28 | 211559 | 211559 | 204310 | 0 | 0 | 204310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204310 | 204310 | 0 | 255658
1 | T1705 | 44013315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 448245 | 448245 | 415980 | 0 | 0 | 415980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415980 | 415980 | 0 | 498435
1 | T1706 | 43658615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 7786066 | 7543630 | 7286083 | -242435.65 | 0 | 7247442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7286083 | 7247442 | -38640 | 9348245
1 | T1707 | 44013815201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 394057 | 401319 | 389400 | 7262.13 | 0 | 389394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 389394 | -6 | 500275
1 | T1711 | 43121915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-07-25 | 719941 | 719941 | 689498 | 0 | -24975 | 663884 | -24975 | 0 | 0 | 0 | 0 | 0 | -24975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24975 | 664523 | 663884 | -639 | 651945
1 | T1713 | 43355215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-05-23 | 2526300 | 2681334 | 2687161 | 155034.01 | 0 | 2682036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2687161 | 2682036 | -5125 | 2797558 | B0 | ACC - LUMP SUM
1 | T1714 | 43837615201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 270550 | 270550 | 256893 | 0 | 0 | 256893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256893 | 256893 | 0 | 302948 | B0 | ACC - LUMP SUM
1 | T1725 | 43501515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 984573 | 984573 | 955300 | 0 | 0 | 955300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955300 | 955300 | 0 | 713682 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1727 | 43800715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 2658381 | 2763353 | 2697261 | 104971.55 | 0 | 2692704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2697261 | 2692704 | -4557 | 2768480
1 | T1729 | 43837415201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-08-29 | 985800 | 1045343 | 996037 | 59542.75 | 0 | 995552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996037 | 995552 | -485 | 952403 | B0 | ACC - LUMP SUM
1 | T1732 | 43318515201 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2018-07-25 | 140241 | 140241 | 131642 | 0 | 0 | 131642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | B0 | ACC - LUMP SUM
1 | T1734 | 43498815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 545828 | 545828 | 508665 | 0 | 0 | 508665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508665 | 508665 | 0 | 633612
1 | T1736 | 43320515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 789502 | 789502 | 749000 | 0 | 0 | 749000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749000 | 749000 | 0 | 784219 | B0 | ACC - LUMP SUM
1 | T1737 | 43826915201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 328300 | 328300 | 328300 | 0 | 0 | 328300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328300 | 328300 | 0 | 356575 | B0 | ACC - LUMP SUM
1 | T1738 | 43837115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 870522 | 870522 | 829068 | 0 | 0 | 829068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829068 | 829068 | 0 | 590611
1 | T1739 | 43837815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 1095691 | 1099220 | 1055726 | 3529.61 | 0 | 1056303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1055726 | 1056303 | 576 | 979242 | B0 | ACC - LUMP SUM
1 | T1741 | 44067415201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 366031 | 366031 | 355572 | 0 | 0 | 355572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355572 | 355572 | 0 | 396011 | B0 | ACC - LUMP SUM
1 | T1743 | 43800415201 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2019-02-27 | 138436 | 138436 | 138436 | 0 | 0 | 138436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138436 | 138436 | 0 | 179133 | B0 | ACC - LUMP SUM
1 | T1749 | 44319925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 335979 | 396256 | 382764 | 60277.25 | 0 | 382764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382764 | 382764 | 0 | 263307
1 | T1753 | 43943215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 1952155 | 1971307 | 1962809 | 19151.94 | 0 | 1962123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962809 | 1962123 | -686 | 2489142 | B0 | ACC - LUMP SUM
1 | T1765 | 43698215201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 371018 | 371018 | 371018 | 0 | 0 | 371018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371018 | 371018 | 0 | 262343
1 | T1766 | 44248515201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-09-25 | 305000 | 305000 | 305000 | 0 | 0 | 305000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305000 | 305000 | 0 | 267579 | B0 | ACC - LUMP SUM
1 | T1769 | 44012315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 364364 | 364364 | 355187 | 0 | 0 | 355187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355187 | 355187 | 0 | 367496
2 | E2P14 | 21330435201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2012-05-30 | 148792000 | 165618383 | 165903515 | 16826382.52 | 0 | 164443807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165903515 | 164443807 | -1459708 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2Q20 | 43056515201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-10-10 | 84850000 | 85626817 | 85105357 | 776816.8 | -9751108 | 79072300 | -9651983 | 0 | 0 | 0 | -99125 | 0 | -9751108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9751108 | 75354249 | 79072300 | 3718051 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
2 | E2T34 | 43141825201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-04-15 | 79728458 | 79121474 | 78886236 | -606983.36 | -229932 | 77404693 | -229932 | 0 | 0 | 0 | 0 | 0 | -229932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -229932 | 78656304 | 77404693 | -1251611 | 80350658 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2V70 | 42747515201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-06-14 | 4483000 | 4642146 | 4688789 | 159146.16 | 0 | 4688881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688789 | 4688881 | 92 | 5283434
2 | E2V71 | 43430015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 4908173 | 4938615 | 5152163 | 30442.09 | 0 | 5451119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 4805500
2 | E2V95 | 43617015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 4081125 | 4737826 | 4860165 | 656701.41 | 0 | 4970230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 3223625
2 | E2W35 | 42849115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-09-20 | 2815327 | 2815327 | 2782011 | 0 | 0 | 2782013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 4173997
2 | E2W51 | 20950355201 | F561918615 | ASTRON GENERAL CONTRACTING CO. | N/A | N/A | N/A | N/A | 2017-08-16 | 1735075 | 1731106 | 1623863 | -3969.01 | 0 | 1623865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | 1877622
2 | E2W52 | 42849815201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-03-21 | 730881 | 756196 | 713128 | 25315 | 0 | 713129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713128 | 713129 | 0 | 752278
2 | E2W53 | 42849715201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1093189 | 1093189 | 1034914 | 0 | 0 | 1034914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 1735598
2 | E2W95 | 43402815201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2018-02-21 | 2722348 | 2722348 | 2657208 | 0 | 0 | 2656276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 2383751
2 | E2W96 | 43307515201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-21 | 4411000 | 4455781 | 4414330 | 44781.29 | 0 | 4414364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4414330 | 4414364 | 34 | 4144135
2 | E2X07 | 20956525201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 327059 | 327059 | 288640 | 0 | 0 | 288640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288640 | 288640 | 0 | 337947
2 | E2X15 | 20961685201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-12-20 | 7739999 | 7739999 | 7665781 | 0 | 0 | 7665781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 9122595
2 | E2X44 | 42879715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 1990108 | 2637472 | 2547298 | 647363.36 | 0 | 2542607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2547298 | 2542607 | -4691 | 2271972
2 | E2X58 | 43205415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-18 | 1561255 | 1561255 | 1495849 | 0 | 0 | 1495849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 1989213
2 | E2X60 | 43025915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-08-15 | 1328017 | 1328017 | 1207862 | 0 | 0 | 1207862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207862 | 1207862 | 0 | 1798375
2 | E2X61 | 43496915201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-08-15 | 2118153 | 2118153 | 2024485 | 0 | -33300 | 1991185 | -33300 | 0 | 0 | 0 | 0 | 0 | -33300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33300 | 1991185 | 1991185 | 0 | 2333870
2 | E2X62 | 43044925201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2018-08-15 | 3108597 | 3188597 | 3259002 | 80000 | 0 | 3258817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259002 | 3258817 | -185 | 2739648
2 | E2X63 | 43391215201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2018-09-19 | 1149152 | 1149152 | 1082839 | 0 | 0 | 1082839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082839 | 1082839 | 0 | 1278582
2 | E2X68 | 43500015201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-11-14 | 925745 | 925745 | 888997 | 0 | 0 | 888989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 888997 | 888989 | -8 | 952359
2 | E2Y23 | 43500215201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 891797 | 891797 | 842389 | 0 | 0 | 842389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842389 | 842389 | 0 | 906381
2 | E2Y77 | 43606615201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | 409752 | 409752 | 391056 | 0 | 0 | 391056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391056 | 391056 | 0 | 431103
2 | T2562 | 20821175201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-05-20 | 15887487 | 16037487 | 15865517 | 150000 | 0 | 15510573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 16006484
2 | T2576 | 43091115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-17 | 7004346 | 8247072 | 8273395 | 1242726.05 | -350610 | 7827108 | -350610 | 0 | 0 | 0 | 0 | 0 | -350610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350610 | 7922785 | 7827108 | -95677 | 5694357
2 | T2577 | 43245215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-17 | 13015506 | 13328963 | 13247968 | 313457.41 | -129472 | 12926851 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 13118496 | 12926851 | -191646 | 11330021
2 | T2612 | 42360825201 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2241677 | 2241677 | 2217516 | 0 | -20592 | 2204364 | -20592 | 0 | 0 | 0 | 0 | 0 | -20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20592 | 2196924 | 2204364 | 7440 | 1830224
2 | T2616 | 20800155201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 48935291 | 48562222 | 47847275 | -373068.54 | 0 | 49894026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47847275 | 49894026 | 2046752 | 61148938
2 | T2618 | 43091015201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 6623070 | 7293436 | 7244868 | 670365.84 | 0 | 7349062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7244868 | 7349062 | 104194 | 5699134
2 | T2621 | 20800145201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-06-20 | 49402252 | 49868003 | 50029395 | 465751.14 | 0 | 51282251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50029395 | 51282251 | 1252856 | 50264623
2 | T2657 | 20781825201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 13545525 | 13574913 | 13974107 | 29387.52 | 0 | 14374623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13974107 | 14374623 | 400515 | 16380283 | B6 | ACC - LIQUIDATED SAVINGS
2 | T2658 | 41525215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 7921243 | 8003005 | 8095808 | 81762.66 | 0 | 8111040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 5941070
2 | T2661 | 43433715201 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2017-06-14 | 3381935 | 3744790 | 3805039 | 362855.46 | 0 | 3814801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 2832771
2 | T2678 | 21028685201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-05-24 | 5834914 | 5935993 | 6210758 | 101079.18 | 0 | 6239687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6210758 | 6239687 | 28928 | 5533447
2 | T2679 | 43617415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 10753984 | 10978696 | 11000190 | 224711.7 | 0 | 11198057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000190 | 11198057 | 197867 | 7872133
2 | T2682 | 43201215201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-12-06 | 3548288 | 3732180 | 3999294 | 183891.07 | 0 | 4055594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999294 | 4055594 | 56300 | 3940433
2 | T2683 | 43616215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 9121503 | 9130119 | 9355463 | 8616 | 0 | 10160460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 10382551
2 | T2686 | 43611815201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2698000 | 2725471 | 2926429 | 27470.55 | 0 | 3007330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 2798351
2 | T2687 | 43617315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 5141768 | 5141768 | 5033451 | 0 | 0 | 5387836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 6618371
2 | T2688 | 43500115201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2018-01-31 | 1688461 | 1754543 | 1709557 | 66082.5 | 0 | 1709557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 1908915
2 | T2689 | 43616115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1995665 | 1995665 | 2049720 | 0 | 0 | 2101020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049720 | 2101020 | 51299 | 2153023
2 | T2691 | 43617215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 13785287 | 13785287 | 14546489 | 0 | 0 | 15202892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14546489 | 15202892 | 656402 | 13297955
2 | T2695 | 43615815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 3836183 | 3889514 | 3691380 | 53331.63 | 0 | 3743642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691380 | 3743642 | 52262 | 3655365
2 | T2704 | 43761615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | 6663346 | 6750120 | 6920369 | 86773.43 | 0 | 6898990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 6878488
2 | T2708 | 44216935201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 368985 | 374417 | 391272 | 5431.58 | 0 | 391272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391272 | 391272 | 0 | 334521
2 | T2710 | 40926715201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 3168954 | 3211208 | 3216929 | 42254.21 | 0 | 3215797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3216929 | 3215797 | -1132 | 1926904
2 | T2714 | 43761815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 8210076 | 8537835 | 8699071 | 327759.11 | -65493 | 8618119 | -65493 | 0 | 0 | 0 | 0 | 0 | -65493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65493 | 8633578 | 8618119 | -15459 | 8052869
2 | T2718 | 43762115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 2814544 | 2814544 | 2780154 | 0 | 0 | 2750630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 3342179
2 | T2723 | 43762015201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1658214 | 1658214 | 1598015 | 0 | 0 | 1602638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1598015 | 1602638 | 4623 | 2124299
2 | T2727 | 43761215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1634119 | 1634119 | 1569675 | 0 | 0 | 1576127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 1717974
2 | T2730 | 43429715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2680388 | 2680388 | 2824608 | 0 | 0 | 2824608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824608 | 2824608 | 0 | 3620027
3 | E3P84 | 43625815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-09-21 | 1596199 | 1596199 | 1566048 | 0 | 0 | 1618568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 1614268
3 | E3Q52 | 43626715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 2737547 | 2741455 | 2788497 | 3908.32 | 0 | 2937051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2788497 | 2937051 | 148555 | 3367306
3 | E3R04 | 43627115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-06-14 | 819508 | 814776 | 800432 | -4732.46 | 0 | 800432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800432 | 800432 | 0 | 795145
3 | E3R15 | 43730715201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2018-04-12 | 847761 | 847761 | 805000 | 0 | -6660 | 798340 | -6660 | 0 | 0 | 0 | 0 | 0 | -6660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6660 | 798340 | 798340 | 0 | 968823 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
3 | E3R27 | 40410835201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-04-11 | 497771 | 497771 | 462232 | 0 | 0 | 462232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462232 | 462232 | 0 | 568464
3 | E3R52 | 43627225201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-01-10 | 1432597 | 1438332 | 1321040 | 5734.8 | 0 | 1327923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1321040 | 1327923 | 6884 | 1931231
3 | E3R71 | 41557325201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2019-06-13 | 726199 | 763938 | 752801 | 37738.85 | 0 | 752801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752801 | 752801 | 0 | 735824
3 | E3R73 | 43672615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-03-08 | 3019502 | 3096429 | 3191111 | 76927.34 | -1871 | 3252581 | 0 | 0 | 0 | 0 | 0 | -1871 | -1871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1871 | 3189240 | 3252581 | 63342 | 3561779
3 | E3S52 | 41767755201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-05-09 | 551256 | 551256 | 487293 | 0 | 0 | 487293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487293 | 487293 | 0 | 525116
3 | E3S64 | 4453671H201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2019-04-16 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | -45000 | 32990
3 | E3S65 | 4.4537e+207 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2019-04-26 | 290951 | 290951 | 295907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295907 | 0 | -295907 | 223300
3 | E3T17 | 4458601G201 | F208255780 | T & M LAWN-FENCE SERVICE INC | N/A | N/A | N/A | N/A | 2019-10-14 | 90900 | 90900 | 90510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90510 | 0 | -90510 | 98690
3 | T3471 | 41110225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-05-07 | 15000000 | 15157836 | 15093755 | 157836.02 | -129472 | 13510897 | -129472 | 0 | 0 | 0 | 0 | 0 | -129472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 14814542
3 | T3485 | 42695315201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 3574230 | 3575445 | 3569976 | 1215 | -104007 | 3477125 | -104007 | 0 | 0 | 0 | 0 | 0 | -104007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104007 | 3465969 | 3477125 | 11156 | 3028499
3 | T3488 | 40979275201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 3595027 | 3663247 | 3527855 | 68219.39 | -36334 | 3407495 | -25884 | 0 | 0 | 0 | 0 | -10450 | -36334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36334 | 3491521 | 3407495 | -84026 | 2839406
3 | T3543 | 22044275201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-30 | 29686177 | 35844062 | 36589864 | 6157885.47 | 0 | 36834177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36589864 | 36834177 | 244313 | 37447264
3 | T3584 | 42551925201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-09-27 | 4956085 | 5007841 | 5206085 | 51755.66 | 0 | 5214960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206085 | 5214960 | 8875 | 4588109
3 | T3586 | 42862415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-06-13 | 4214542 | 4293135 | 4297521 | 78593.87 | 0 | 4292318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4297521 | 4292318 | -5203 | 3958246
3 | T3594 | 42884415201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 5851220 | 5885580 | 5664882 | 34359.48 | 0 | 5780265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5664882 | 5780265 | 115384 | 6081167
3 | T3605 | 43390515201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-09-26 | 2727550 | 2727550 | 2606882 | 0 | 0 | 2599923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 2910808
3 | T3614 | 43228815201 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 776874 | 1103417 | 1178529 | 326542.39 | 0 | 1178529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178529 | 1178529 | 0 | 825049
3 | T3617 | 43228615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-11-14 | 1583516 | 1621356 | 1660818 | 37840.09 | 0 | 1656916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660818 | 1656916 | -3903 | 1384281
3 | T3621 | 43626115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 6338519 | 6398946 | 6159928 | 60426.55 | -3625 | 6530080 | 0 | 0 | 0 | 0 | 0 | -3625 | -3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3625 | 6156303 | 6530080 | 373777 | 7711485
3 | T3622 | 43403415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-07-25 | 2343362 | 2350008 | 2309974 | 6645.2 | 0 | 2307395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 1958564
3 | T3633 | 43188335201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-07-25 | 874222 | 874222 | 812103 | 0 | 0 | 809595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 1107452
3 | T3637 | 43626515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 2991030 | 3017543 | 3196659 | 26512.73 | 0 | 3365573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196659 | 3365573 | 168914 | 0
3 | T3639 | 43078915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 5166455 | 5133457 | 5226570 | -32997.52 | 0 | 5560738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5226570 | 5560738 | 334168 | 5944823
3 | T3653 | 43672015201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2018-08-29 | 628643 | 626435 | 585546 | -2207.95 | 0 | 585546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585546 | 585546 | 0 | 728102
3 | T3655 | 43666315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 7611735 | 8017733 | 8305261 | 405997.54 | 0 | 8626470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8305261 | 8626470 | 321209 | 10033609
3 | T3656 | 42817125201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 483492 | 483492 | 460000 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 460000 | 0 | 489802 | B0 | ACC - LUMP SUM
3 | T3661 | 43255915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 4168106 | 4195995 | 4262748 | 27889.1 | -3685 | 4316429 | 0 | 0 | 0 | 0 | 0 | -3685 | -3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3685 | 4259063 | 4316429 | 57366 | 3474587
3 | T3662 | 43627215201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 1790850 | 1822098 | 1908732 | 31248.18 | -25175 | 1983720 | 0 | 0 | 0 | 0 | 0 | -25175 | -25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25175 | 1883557 | 1983720 | 100163 | 2014996
3 | T3666 | 43578215201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 552204 | 552204 | 493444 | 0 | 0 | 493444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493444 | 493444 | 0 | 621266
3 | T3667 | 43273835201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 10109835 | 10121496 | 9985893 | 11660.92 | 0 | 10325034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9985893 | 10325034 | 339141 | 11327401
3 | T3669 | 43046415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-05-23 | 1257739 | 1467600 | 1481515 | 209861.08 | 0 | 1481051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481515 | 1481051 | -464 | 1150000
3 | T3673 | 43774415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 7942048 | 7802040 | 7940568 | -140007.62 | 0 | 7896410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7940568 | 7896410 | -44158 | 8459567
3 | T3678 | 43627015201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 4020176 | 4016156 | 4196886 | -4020 | 0 | 4189347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196886 | 4189347 | -7539 | 4510562
3 | T3679 | 43388415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-12-05 | 1634280 | 1634280 | 1650177 | 0 | 0 | 1651949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650177 | 1651949 | 1772 | 2275668
3 | T3680 | 43815515201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2018-11-14 | 188489 | 188489 | 183577 | 0 | 0 | 183577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183577 | 183577 | 0 | 165102
3 | T3683 | 43774515201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1061000 | 1061000 | 1008572 | 0 | 0 | 1008572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 1142404 | B0 | ACC - LUMP SUM
3 | T3684 | 43774815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 5394287 | 5398247 | 5475266 | 3960 | 0 | 5462989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5475266 | 5462989 | -12278 | 6845122
3 | T3688 | 44038315201 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2019-02-27 | 354899 | 354899 | 344281 | 0 | 0 | 344281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344281 | 344281 | 0 | 390454
3 | T3693 | 43776515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 9424063 | 9424063 | 9590716 | 0 | 0 | 9547583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9590716 | 9547583 | -43133 | 10485496
3 | T3713 | 42985635201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1053341 | 1099610 | 1118223 | 46269.22 | 0 | 1117591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118223 | 1117591 | -632 | 1301273
3 | T3715 | 43827215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 649114 | 653949 | 611340 | 4835.6 | 0 | 610104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611340 | 610104 | -1235 | 755587
3 | T3726 | 43551825201 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 810302 | 810302 | 797761 | 0 | 0 | 797761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797761 | 797761 | 0 | 663447
4 | E4N84 | 42170735201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-30 | 233756400 | 236000384 | 235981625 | 2243984.17 | 1120000 | 230888919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120000 | 0 | 0 | 0 | 0 | 0 | 1120000 | 1120000 | 237101625 | 230888919 | -6212706 | 224173038 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4N95 | 43316515201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2014-04-28 | 15085307 | 14747115 | 14692678 | -338192.13 | 0 | 14275588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14692678 | 14275588 | -417090 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
4 | E4N98 | 42170745201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-01-17 | 85270000 | 88551488 | 88376026 | 3281487.8 | -266765 | 84860074 | -66765 | 0 | 0 | 0 | 0 | 0 | -66765 | -200000 | 0 | 0 | 0 | 0 | 0 | -200000 | -266765 | 88109261 | 84860074 | -3249187 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P04 | 23193225201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-04-16 | 32540300 | 33830739 | 33682875 | 1290438.6 | -2003878 | 31330630 | -2003878 | 0 | 0 | 0 | 0 | 0 | -2003878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2003878 | 31678997 | 31330630 | -348367 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q16 | 42170795201 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 5426234 | 5484479 | 5462490 | 58244.76 | 500000 | 5462490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
4 | E4Q35 | 42264135201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-05-06 | 20830000 | 21194238 | 21031285 | 364237.59 | -452157 | 20574388 | -452157 | 0 | 0 | 0 | 0 | 0 | -452157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452157 | 20579128 | 20574388 | -4739 | 20036622 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4Q64 | 43310855201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-05-29 | 153917279 | 162463226 | 162823699 | 8545946.77 | 3720000 | 162834119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3720000 | 0 | 0 | 0 | 0 | 0 | 3720000 | 3720000 | 166543699 | 162834119 | -3709579 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4S19 | 43215415201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2019-01-04 | 2497568 | 2505758 | 2398176 | 8189.24 | 0 | 2398176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2398176 | 2398176 | 0 | 3078160
4 | E4S21 | 43661715201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-03-03 | 13456789 | 15316896 | 15094846 | 1860106.93 | 0 | 15262674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 15931024 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4S38 | 42684015201 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2017-05-05 | 7933333 | 10078503 | 10162546 | 2145169.7 | 0 | 10167797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10162546 | 10167797 | 5251 | 6966383
4 | E4S85 | 43609615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-12-01 | 4027310 | 4061212 | 3932814 | 33902.45 | -146172 | 3959283 | -146172 | 0 | 0 | 0 | 0 | 0 | -146172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -146172 | 3786642 | 3959283 | 172641 | 4151810
4 | E4T01 | 43630215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1711929 | 1760237 | 1659334 | 48308 | 0 | 1661623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 1640419
4 | E4T06 | 43977615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | 1095456 | 1095456 | 1057178 | 0 | 0 | 1059897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 1077515
4 | E4T43 | 43686915201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-02-01 | 483248 | 483248 | 462927 | 0 | 0 | 462927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462927 | 462927 | 0 | 584334
4 | E4T45 | 44145415201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-12-07 | 1195515 | 1195515 | 1144992 | 0 | 0 | 1144992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144992 | 1144992 | 0 | 1552783
4 | E4T47 | 43995915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 874745 | 874745 | 827255 | 0 | 0 | 827255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827255 | 827255 | 0 | 2440132
4 | E4T48 | 43215315201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-01-04 | 1579388 | 1579388 | 1522923 | 0 | 0 | 1522923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 1500208
4 | E4T52 | 43784715201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-08 | 1344115 | 1351758 | 1279142 | 7643.32 | 0 | 1278932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279142 | 1278932 | -209 | 1455183
4 | E4T53 | 44145715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-02-01 | 373586 | 373586 | 320740 | 0 | 0 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320740 | 320740 | 0 | 838047
4 | E4T55 | 43388915201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-03-08 | 436087 | 451388 | 443815 | 15300.23 | 0 | 443815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443815 | 443815 | 0 | 589902
4 | T4400 | 22777415201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 30674813 | 30018004 | 28121407 | -656809.26 | -175000 | 26945248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175000 | 0 | 0 | 0 | 0 | 0 | -175000 | -175000 | 27946407 | 26945248 | -1001159 | 31615939 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
4 | T4412 | 42873315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-31 | 6616134 | 6744078 | 6260985 | 127944.06 | 0 | 6363893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6260985 | 6363893 | 102908 | 5635993
4 | T4418 | 22989615201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-07-29 | 17423228 | 17585616 | 15704340 | 162388.39 | 0 | 15621918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15704340 | 15621918 | -82422 | 22527836
4 | T4423 | 23033845201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 23950804 | 24148938 | 23087444 | 198133.26 | 0 | 23548540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23087444 | 23548540 | 461096 | 30953648
4 | T4433 | 42872415201 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2016-04-27 | 16224277 | 17235975 | 16795691 | 1011697.84 | -110980 | 16825397 | -46980 | 0 | 0 | 0 | 0 | 0 | -46980 | -64000 | 0 | 0 | 0 | 0 | 0 | -64000 | -110980 | 16684711 | 16825397 | 140685 | 14991648 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4444 | 43270515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 27999900 | 28775420 | 29356382 | 775520.05 | 0 | 30081989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29356382 | 30081989 | 725606 | 34103306
4 | T4449 | 43466615201 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 7667258 | 7990322 | 8156412 | 323063.28 | 0 | 8240877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8156412 | 8240877 | 84466 | 7671794
4 | T4452 | 43166615201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-25 | 3407245 | 3524212 | 3504637 | 116966.98 | 0 | 3574050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504637 | 3574050 | 69412 | 3478134
4 | T4454 | 43427315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 17184517 | 17260367 | 15228075 | 75850.52 | -427518 | 15656209 | -427518 | 0 | 0 | 0 | 0 | 0 | -427518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -427518 | 14800557 | 15656209 | 855652 | 16678233 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4465 | 42793815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 6772377 | 6937715 | 6616077 | 165337.71 | 0 | 6805105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616077 | 6805105 | 189028 | 7354282
4 | T4467 | 42872815201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 6194382 | 6727999 | 7014661 | 533617.21 | 0 | 7145526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7014661 | 7145526 | 130865 | 6773142 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4470 | 43467915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 2654817 | 2648641 | 2595600 | -6176.03 | 0 | 2595444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | 2954451
4 | T4474 | 43516015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4025071 | 4333347 | 4067792 | 308276.21 | 0 | 4150827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 3559044
4 | T4478 | 43206645201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 3159876 | 3207501 | 3126761 | 47624.42 | 0 | 3121903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 3633553
4 | T4480 | 43166515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 1327221 | 1366521 | 1298578 | 39300 | 0 | 1298125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1298578 | 1298125 | -453 | 1330304
4 | T4481 | 43177025201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 2295900 | 2421717 | 2381617 | 125817.34 | 0 | 2380490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381617 | 2380490 | -1127 | 2164419
4 | T4482 | 44007915201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-05-23 | 398299 | 443873 | 390019 | 45574.25 | 0 | 400857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390019 | 400857 | 10839 | 523214
4 | T4484 | 43169815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 1436281 | 1518265 | 1430265 | 81984 | 0 | 1427633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430265 | 1427633 | -2632 | 1552637
4 | T4486 | 43165715201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 3260393 | 3609674 | 3402444 | 349281.5 | 0 | 3396789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3402444 | 3396789 | -5656 | 3504742
4 | T4487 | 43060825201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 755191 | 755191 | 655187 | 0 | 0 | 654702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655187 | 654702 | -486 | 684674
4 | T4490 | 43467415201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 1487250 | 1501835 | 1498981 | 14585.25 | 0 | 1507245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498981 | 1507245 | 8264 | 1612251
4 | T4492 | 43783715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 1180804 | 1180804 | 1088706 | 0 | 0 | 1092749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 1254760
4 | T4493 | 43622615201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 913324 | 925193 | 862461 | 11868.69 | 0 | 863741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 983072
4 | T4515 | 43783515201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1965071 | 1985843 | 1788610 | 20772.52 | 0 | 1780758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788610 | 1780758 | -7851 | 1803197
4 | T4532 | 43838815201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-12-04 | 291936 | 291936 | 271767 | 0 | 0 | 271767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271767 | 271767 | 0 | 289117
4 | T4533 | 43689915201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 299394 | 321508 | 308462 | 22113.24 | 0 | 308462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308462 | 308462 | 0 | 308307
5 | BE626 | 43787225201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-05-24 | 720000 | 720000 | 720000 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 720000 | 0 | 720000
5 | E5W11 | 24262635201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-11-21 | 43150089 | 45682181 | 45886261 | 2532092.15 | 0 | 43252523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45886261 | 43252523 | -2633738 | 48952302 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
5 | E5W31 | 43360715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-08-04 | 11820000 | 11432846 | 11217159 | -387153.56 | -379168 | 10378129 | -379168 | 0 | 0 | 0 | 0 | 0 | -379168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -379168 | 10837991 | 10378129 | -459862 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y20 | 42690435201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-11-04 | 26771800 | 27777188 | 27684932 | 1005388.19 | 0 | 28129118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27684932 | 28129118 | 444186 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Y33 | 43693715201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2016-09-07 | 1750000 | 3113962 | 3063962 | 1363961.88 | 0 | 3065413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1325842
5 | E5Y34 | 43744415201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | 793972 | 793962 | 623055 | -9.51 | 0 | 624995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623055 | 624995 | 1940 | 843684
5 | E5Z02 | 43365415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-02-06 | 1457258 | 1507258 | 1490649 | 50000 | -1099 | 1488755 | 0 | 0 | 0 | 0 | 0 | -1099 | -1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1099 | 1489550 | 1488755 | -795 | 1508169
5 | E5Z09 | 41299445214 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-12-14 | 5757000 | 5860741 | 5841571 | 103740.91 | 0 | 5844608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841571 | 5844608 | 3037 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Z21 | 43927015201 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2018-05-01 | 3175000 | 3175000 | 3125000 | 0 | 0 | 3125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 2594655
5 | E5Z23 | 43564715201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-05-01 | 1013390 | 1008318 | 958318 | -5071.91 | -736 | 957220 | 0 | 0 | 0 | 0 | 0 | -736 | -736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -736 | 957582 | 957220 | -362 | 1052401
5 | E5Z25 | 43685515201 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-07-03 | 1405000 | 1538799 | 1482098 | 133798.84 | 0 | 1478901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 1340492
5 | E5Z27 | 43733815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-05 | 4978323 | 5143919 | 4848769 | 165595.61 | 0 | 4823580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4848769 | 4823580 | -25189 | 5765157
5 | E5Z44 | 43945315201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-06 | 406627 | 439983 | 417356 | 33356.49 | -11169 | 406187 | -11169 | 0 | 0 | 0 | 0 | 0 | -11169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11169 | 406187 | 406187 | 0 | 480184
5 | E5Z45 | 43733915201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-11-06 | 6123814 | 6203979 | 6135165 | 80165.9 | 0 | 6020689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6135165 | 6020689 | -114476 | 8194285
5 | E5Z47 | 43759915201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2018-12-04 | 490000 | 490000 | 469000 | 0 | 0 | 469000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469000 | 469000 | 0 | 441431
5 | E5Z48 | 44096715201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 476422 | 476422 | 521373 | 0 | 0 | 521373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521373 | 521373 | 0 | 443061
5 | E5Z49 | 44255515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-12-04 | 1193299 | 1193299 | 1111517 | 0 | 0 | 1111517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 1054473
5 | E5Z52 | 44116715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-10-02 | 679222 | 682222 | 665592 | 3000 | 0 | 665592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665592 | 665592 | 0 | 321983
5 | E5Z60 | 44096815201 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2018-12-04 | 471366 | 471366 | 417692 | 0 | 0 | 417692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417692 | 417692 | 0 | 554880
5 | E5Z73 | 44096615201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-04-02 | 648932 | 648932 | 638000 | 0 | 0 | 638000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638000 | 638000 | 0 | 1049374
5 | E5Z75 | 44180415201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-05-07 | 176561 | 176561 | 146000 | 0 | 0 | 146000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146000 | 146000 | 0 | 287786
5 | E5Z76 | 44097015201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2019-06-04 | 167070 | 167070 | 148419 | 0 | 0 | 148419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148419 | 148419 | 0 | 271247
5 | E5Z99 | 44326715201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-01-07 | 293874 | 293874 | 266752 | 0 | 0 | 266752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266752 | 266752 | 0 | 366851
5 | T5469 | 23920345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-10-30 | 67881735 | 71458538 | 71806238 | 3576803.2 | -56415 | 68693588 | 0 | 0 | 0 | 0 | 0 | -56415 | -56415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56415 | 71749823 | 68693588 | -3056235 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5506 | 41840325201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-06-17 | 12348616 | 13716737 | 13601127 | 1368120.68 | 0 | 13708354 | -402297 | 0 | 0 | 0 | 402297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13601127 | 13708354 | 107227 | 11281112
5 | T5569 | 43442615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-02-22 | 1957429 | 2177504 | 2168249 | 220074.99 | 0 | 2176885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168249 | 2176885 | 8636 | 2248771
5 | T5572 | 43505615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 6749945 | 6768976 | 6749146 | 19031.04 | 30000 | 6749146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS
5 | T5588 | 43505915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 5555556 | 5555556 | 5533602 | 0 | 14500 | 5533602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0 | 0 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 7289680
5 | T5591 | 42823815201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 16694356 | 16972569 | 16490950 | 278213.07 | 0 | 16700809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16490950 | 16700809 | 209859 | 15183627
5 | T5601 | 43565815201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 4858677 | 5019991 | 4911820 | 161313.66 | 0 | 5177234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 6733492
5 | T5606 | 43803815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-31 | 8022650 | 8458736 | 8268967 | 436086.29 | 0 | 8615728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8268967 | 8615728 | 346762 | 9588756
5 | T5616 | 43065515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 4231483 | 4229830 | 4248590 | -1652.68 | 0 | 4402057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4248590 | 4402057 | 153467 | 5394340
5 | T5617 | 43505815201 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 3824000 | 3850406 | 3817535 | 26405.77 | 0 | 3817535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 4905410
5 | T5619 | 24099275201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-08-30 | 1769311 | 1789505 | 1708324 | 20194.25 | 0 | 1715061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 1940871
5 | T5621 | 43623715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-13 | 1704711 | 1714508 | 1599483 | 9796.81 | 0 | 1594642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599483 | 1594642 | -4841 | 1787644
5 | T5623 | 43239915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-07-25 | 1897288 | 1897714 | 1910437 | 426.04 | 0 | 1905492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 2057026
5 | T5635 | 43733015202 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-31 | 2923010 | 2973010 | 2925571 | 50000 | 0 | 2880657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2925571 | 2880657 | -44914 | 3429127
5 | T5641 | 44055775201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-09-26 | 22429705 | 22800571 | 23719308 | 370865.55 | 1000000 | 23698480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000 | 1000000 | 24719308 | 23698480 | -1020828 | 27275445 | B5:B7:B5:B7 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS
5 | T5644 | 43988325201 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 61969 | 61969 | 61131 | 0 | 0 | 61131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61131 | 61131 | 0 | 70244
5 | T5646 | 43988715201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 85394 | 85394 | 71417 | 0 | 0 | 71417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71417 | 71417 | 0 | 99983
5 | T5647 | 44106615201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-03-27 | 2009090 | 2023837 | 2344261 | 14747.02 | 0 | 2344061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2344261 | 2344061 | -200 | 1775243
6 | E6J52 | 43337815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-06-09 | 8960958 | 9028019 | 8935693 | 67061.69 | 0 | 8936706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8935693 | 8936706 | 1013 | 6643198
6 | E6J69 | 43492215201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2016-04-15 | 69547000 | 72886197 | 72551371 | 1806784.32 | 0 | 73200931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72551371 | 73200931 | 649560 | 125147000 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K58 | 43081315201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-31 | 1100030 | 1101649 | 1024191 | 1618.97 | 100000 | 1026756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1124191 | 1026756 | -97435 | 1216039 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K59 | 41831225201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-07-28 | 9488820 | 10556288 | 10367176 | 1067467.64 | 400000 | 10409054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 10767176 | 10409054 | -358123 | 9121391 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6K87 | 43654015201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2018-11-29 | 342215 | 342215 | 303600 | 0 | 0 | 303600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303600 | 303600 | 0 | 394432
6 | E6K89 | 43653615201 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 512803 | 536803 | 517303 | 24000 | 0 | 517303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517303 | 517303 | 0 | 404500
6 | E6L26 | 43653515201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-29 | 878038 | 878038 | 768146 | 0 | 0 | 768146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768146 | 768146 | 0 | 1044218
6 | E6L27 | 43081725201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-22 | 1584337 | 1584337 | 1427013 | 0 | 0 | 1426855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 1676992
6 | E6L37 | 42919325201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-01-25 | 1491900 | 1633114 | 1580093 | 141214.05 | 60000 | 1579918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 1640093 | 1579918 | -60174 | 1421302 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6L51 | 43029129201 | F301004760 | RTECH HEC JV | N/A | N/A | N/A | N/A | 2017-12-04 | 5545538 | 5585378 | 5557420 | 39840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5557420 | 0 | -5557420 | 7161526 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6L72 | 44183315201 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2019-08-29 | 428626 | 428626 | 355753 | 0 | 0 | 355753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355753 | 355753 | 0 | 412463
6 | E6L83 | 44124315201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-26 | 626626 | 626626 | 577033 | 0 | 0 | 576947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577033 | 576947 | -87 | 611516
6 | E6L91 | 44203915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | 1590779 | 1590779 | 1534205 | 0 | 0 | 1533853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 1335462
6 | T6337 | 41809115201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 14239526 | 16636939 | 16898897 | 2397413.06 | 500000 | 16945020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 17398897 | 16945020 | -453877 | 13498168 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6338 | 41463315201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 11118409 | 12716281 | 13284136 | 1597872.07 | 0 | 13403183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284136 | 13403183 | 119047 | 10197839 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6344 | 24994145201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2014-06-25 | 20865766 | 21591091 | 20515283 | 725324.32 | 0 | 20078878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 22059625 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6382 | 40561535201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 32827940 | 33204392 | 33258885 | 376451.27 | 1000000 | 33636224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 34258885 | 33636224 | -622662 | 32661597 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6401 | 41247395201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-03-29 | 3499047 | 5529305 | 5890497 | 2030258.17 | 0 | 5896369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890497 | 5896369 | 5872 | 3269401 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6403 | 43348915201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 2123570 | 2145473 | 2165968 | 21903 | 0 | 2187405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 2459954
6 | T6406 | 42902215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-04-25 | 3211923 | 3249863 | 3270531 | 37940 | 190000 | 3268888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 3370172 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6419 | 42827825201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 2865340 | 2945587 | 2727466 | 80246.87 | 110000 | 2776404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 2918720 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6436 | 43631115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 1387410 | 1479864 | 1353258 | 92453.79 | 0 | 1354735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 1750082
6 | T6437 | 43634215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-31 | 1789134 | 1789134 | 1742305 | 0 | 0 | 1738184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 2085360
6 | T6438 | 43117015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 3669797 | 3847108 | 3668181 | 177311.22 | 250000 | 3697899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 3918181 | 3697899 | -220283 | 4444325 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6444 | 43640415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 1113869 | 1119160 | 1084619 | 5290.56 | 0 | 1083638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084619 | 1083638 | -981 | 1006236
6 | T6445 | 42611315201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 1196727 | 1200684 | 1179569 | 3956.79 | 0 | 1180484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179569 | 1180484 | 914 | 1242693
6 | T6448 | 43792015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-07-25 | 796960 | 796960 | 710116 | 0 | 0 | 708837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 867454
6 | T6451 | 42563725201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2018-10-31 | 666806 | 666806 | 585572 | 0 | 0 | 584459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 654200
6 | T6455 | 43791715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 564205 | 565127 | 533205 | 922.57 | 0 | 532789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533205 | 532789 | -417 | 617377
6 | T6458 | 44019115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 1250000 | 1339834 | 941648 | 89834.15 | 0 | 941530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941648 | 941530 | -118 | 1429145
6 | T6462 | 43792215201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-07-25 | 672522 | 672522 | 627588 | 0 | 0 | 627091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627588 | 627091 | -497 | 724071
6 | T6467 | 44289715201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2018-10-31 | 127677 | 127677 | 111887 | 0 | 0 | 111863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111887 | 111863 | -24 | 324690
7 | E7H90 | 25693125201 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2012-11-01 | 82889000 | 85277357 | 85130335 | 2388356.86 | 0 | 83668918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85130335 | 83668918 | -1461417 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7K19 | 43476515201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-10-20 | 35360313 | 59863754 | 59642810 | 24503441.21 | 0 | 59642810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59642810 | 59642810 | 0 | 35360313
7 | E7K24 | 41101145201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-04-09 | 94976100 | 96934830 | 96454835 | 1958729.51 | 0 | 96195352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96454835 | 96195352 | -259483 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | E7L26 | 40552525201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2017-03-08 | 25833397 | 27246296 | 27221715 | 1412898.86 | 250000 | 27205803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 27471715 | 27205803 | -265912 | 23085355 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7L58 | 43243415201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-10 | 5500000 | 5732401 | 5687839 | 232401.07 | 0 | 5688140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 4546054
7 | E7L77 | 42292935201 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2017-09-19 | 5595578 | 5595578 | 5582332 | 0 | -3645 | 5581090 | -3645 | 0 | 0 | 0 | 0 | 0 | -3645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3645 | 5578687 | 5581090 | 2402 | 3505311
7 | E7L98 | 43763715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-04-11 | 2248889 | 2248889 | 2169580 | 0 | 0 | 2169580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 2125000
7 | E7M00 | 42292945201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-05-09 | 3873725 | 4070777 | 4079959 | 197052.15 | 0 | 4074029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 5390437
7 | E7M05 | 43954615201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-30 | 2278000 | 2281910 | 2448836 | 3910.26 | 0 | 2448834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2448836 | 2448834 | -1 | 1751000
7 | E7M06 | 44033815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 5327001 | 5327001 | 5287802 | 0 | -68940 | 5204437 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5218862 | 5204437 | -14425 | 6993269
7 | E7M24 | 43649415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-03-13 | 2316390 | 2316390 | 2260239 | 0 | 0 | 2257824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2260239 | 2257824 | -2415 | 1445000
7 | E7M25 | 43386415201 | F842663349 | CHEYENNE ASSOCIATES LLC | N/A | N/A | N/A | N/A | 2019-04-10 | 354276 | 375176 | 357381 | 20900.5 | 0 | 357381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357381 | 357381 | 0 | 265000
7 | E7M26 | 25839935201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-12-12 | 1194104 | 1194104 | 1177035 | 0 | 0 | 1177035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177035 | 1177035 | 0 | 850000
7 | E7M27 | 43648015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-12-12 | 1274649 | 1382195 | 1318471 | 107546.16 | 0 | 1320688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318471 | 1320688 | 2217 | 980000
7 | E7M28 | 43754115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-01-09 | 870000 | 870000 | 820000 | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 820000 | 0 | 1950395 | B0 | ACC - LUMP SUM
7 | E7M30 | 43755215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-02-13 | 167797 | 167797 | 136656 | 0 | 0 | 136656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136656 | 136656 | 0 | 175000
7 | E7M32 | 43751815201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2019-03-13 | 852730 | 852730 | 751999 | 0 | 0 | 752000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751999 | 752000 | 1 | 850000
7 | E7M33 | 43764915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-03-13 | 2477868 | 2501292 | 2443200 | 23424.79 | 0 | 2437101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443200 | 2437101 | -6099 | 2667000
7 | E7M34 | 41918235201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-12 | 1124875 | 1124875 | 1167653 | 0 | 0 | 1167653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167653 | 1167653 | 0 | 1030000
7 | E7M36 | 43648815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-10 | 1604974 | 1606756 | 1564847 | 1782 | 0 | 1550744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564847 | 1550744 | -14103 | 2102050
7 | E7R06 | 44008915201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-08-22 | 1947000 | 1947000 | 1708144 | 0 | 0 | 1708144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R07 | 43845015201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-12-05 | 2568748 | 2568748 | 2497748 | 0 | 0 | 2497782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497748 | 2497782 | 34 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R08 | 43402515201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-03-16 | 5832000 | 5832000 | 5747984 | 0 | 0 | 5747984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5747984 | 5747984 | 0 | 8500000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R16 | 44255215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-07-24 | 1859105 | 1859105 | 1788137 | 0 | -173160 | 1610005 | -173160 | 0 | 0 | 0 | 0 | 0 | -173160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173160 | 1614977 | 1610005 | -4972 | 3000566 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R60 | 43920615201 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2017-09-07 | 12005445 | 12159938 | 12017053 | 154492.99 | 30000 | 12085790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 12047053 | 12085790 | 38737 | 11747696 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
7 | T7389 | 43272015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 12988889 | 13889049 | 13996342 | 900160.08 | 0 | 14109139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13996342 | 14109139 | 112797 | 14634544
7 | T7391 | 43269815201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 1680691 | 1699042 | 1672177 | 18351.56 | -177408 | 1505964 | -177408 | 0 | 0 | 0 | 0 | 0 | -177408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -177408 | 1494769 | 1505964 | 11195 | 1603400
7 | T7398 | 43473015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-25 | 2979236 | 2979236 | 2852469 | 0 | 0 | 2921837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 3840000
7 | T7399 | 43653015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-01-31 | 1314062 | 1314062 | 1279715 | 0 | -1665 | 1277840 | -1665 | 0 | 0 | 0 | 0 | 0 | -1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1665 | 1278050 | 1277840 | -210 | 1374961
7 | T7401 | 43480615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-03-28 | 2932563 | 2939291 | 2859109 | 6728.39 | 0 | 2924621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 3343300
7 | T7404 | 43642015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 1081175 | 1081175 | 1016734 | 0 | 0 | 1023706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 1150000 | B0 | ACC - LUMP SUM
7 | T7409 | 43649115202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-23 | 1575996 | 1575996 | 1509644 | 0 | 0 | 1509644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 1415000
7 | T7415 | 43982935201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-04-25 | 497590 | 497590 | 430440 | 0 | 0 | 430440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430440 | 430440 | 0 | 590001
7 | T7421 | 43648115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | 1160445 | 1160445 | 1174720 | 0 | 0 | 1174720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174720 | 1174720 | 0 | 1200000
7 | T7422 | 44275215201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 96675 | 96675 | 89884 | 0 | 0 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89884 | 89884 | 0 | 182731
7 | T7427 | 43704015201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1130856 | 1130856 | 1101423 | 0 | 0 | 1102091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101423 | 1102091 | 668 | 1234500
7 | T7429 | 43753015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-03-27 | 1704462 | 1704462 | 1672069 | 0 | 0 | 1672069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1672069 | 1672069 | 0 | 2200000
7 | T7430 | 42907525201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2054444 | 2076789 | 2031481 | 22344.94 | 0 | 2031871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031481 | 2031871 | 390 | 2450000
8 | E8N19 | 42935015201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-05-14 | 42645454 | 42529465 | 42335775 | -115989.17 | -256416 | 41113609 | -188916 | 0 | 0 | 0 | 0 | -22500 | -211416 | -45000 | 0 | 0 | 0 | 0 | 0 | -45000 | -256416 | 42079359 | 41113609 | -965750 | 44879640 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8N92 | 42337225201 | F471943651 | DE MOYA REDLAND HEFT JV | N/A | N/A | N/A | N/A | 2015-05-07 | 69954000 | 73801707 | 73879251 | 3847707.46 | -35000 | 73256773 | 0 | 0 | 0 | 0 | 0 | -35000 | -35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | 73844251 | 73256773 | -587478 | 67972639 | B8 | ACC - DESIGN/BUILD - MAJOR
8 | E8P81 | 43561415201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-05-10 | 2564262 | 2604262 | 2577346 | 40000 | 0 | 2582540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 2264808
8 | E8P89 | 43546215201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2016-06-02 | 14923655 | 18836210 | 18823730 | 3912554.94 | -19000 | 19118888 | 0 | 0 | 0 | 0 | 0 | -19000 | -19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19000 | 18804730 | 19118888 | 314158 | 23170861 | B8 | ACC - DESIGN/BUILD - MAJOR
8 | E8Q39 | 43730015201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-04-11 | 42528000 | 44339802 | 45313329 | 1811801.94 | 2430000 | 46007705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430000 | 0 | 0 | 0 | 0 | 0 | 2430000 | 2430000 | 47743329 | 46007705 | -1735624 | 52100636 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8Q41 | 43516515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-02-14 | 15839502 | 16427426 | 16013444 | 587923.78 | -22000 | 16648838 | 0 | 0 | 0 | 0 | 0 | -22000 | -22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | 15991444 | 16648838 | 657394 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8Q54 | 43517115201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-06-06 | 16868340 | 17223693 | 16580725 | 355352.22 | -451756 | 17348378 | -338256 | 0 | 0 | 0 | 0 | -113500 | -451756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -451756 | 16128969 | 17348378 | 1219409 | 18298995
8 | E8Q91 | 43915315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 1568431 | 1602854 | 1622457 | 34422.76 | 0 | 1624753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 1431341
8 | E8Q92 | 43798815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-01-23 | 9338889 | 10684311 | 9478150 | 1345422.43 | 0 | 9949597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9478150 | 9949597 | 471447 | 10469556
8 | E8R18 | 43652115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-05-31 | 11208613 | 11702780 | 11690102 | 494166.31 | -20000 | 11846829 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 11670102 | 11846829 | 176726 | 12719348
8 | E8R46 | 44154915201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-03-12 | 648447 | 654795 | 614302 | 6348.32 | 0 | 614165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614302 | 614165 | -137 | 709932
8 | E8R56 | 44290165201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-10-16 | 994137 | 994137 | 967509 | 0 | 0 | 967509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967509 | 967509 | 0 | 805668
8 | E8R57 | 44290175201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 679823 | 679823 | 674133 | 0 | -9500 | 664633 | 0 | 0 | 0 | 0 | 0 | -9500 | -9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9500 | 664633 | 664633 | 0 | 820726
8 | E8R59 | 44290185201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1646521 | 1646521 | 1599372 | 0 | -10000 | 1582806 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 1589372 | 1582806 | -6566 | 1947436
8 | E8R64 | 44263115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4517345 | 4665904 | 4834996 | 148559.58 | 0 | 4833642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 1860603

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 | 0 | 113818.45 | 0 | 77517.58 | 14834.52 | 7360.64 |  | 213531.19 |  | 187618840 | 0.1099% | 206170.55
02 |  | 345913.81 |  | 127257.02 | 130324.45 | 1590418.36 |  | 2193913.64 |  | 617190255 | 0.09778% | 603495.28
03 |  | 10902.79 |  | 8287.64 | 15866927 | 107140.34 |  | 15993257.77 |  | 161468603 | 9.839% | 15886117.43
04 | 1760 | 289523.36 | 43243.5 | 32847.76 | 230042.61 | 823763 |  | 1421180.23 |  | 773400352 | 0.07725% | 597417.23
05 |  | 425694.05 | 2422 | 24707.31 | 12617.83 | 297575.68 |  | 763016.87 |  | 278923944 | 0.1669% | 465441.19
06 |  | 1102540.74 |  | 11499.52 | 913705.41 | 472451.6 |  | 2500197.27 |  | 206084298 | 0.9839% | 2027745.67
07 |  | 50790.35 | 27282.91 | 109973.1 | 885957.21 | 195151.58 |  | 1269155.15 |  | 331529048 | 0.324% | 1074003.57
08 | 0 | 0 | 0 |  | 34422.76 | 0 |  | 34422.76 |  | 235925419 | 0.01459% | 34422.76
4OTY3Liw0MzYwODYuMjksMC4sODYxNTcyOC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sODI2ODk2Ny4sODYxNTcyOC4sMzQ2NzYyLiw5NTg4NzU2LiwiIiwiIiwiIg0KIjA1IiwiVDU2MTYiLCI0MzA2NTUxNTIwMSIsIkY1OTI4NzE5MzUiLCJBTkRFUlNPTiBDT0xVTUJJQSBDTy4gSU5DLiIsIk4vQS | [9 empty] | 2792140759 | 0% | 0
RU5FUkFMIEFTUEhBTFQgQ08uIElOQy4iLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwNS8yMy8yMDE4IiwxNDM2MjgxLiwxNTE4MjY1LiwxNDMwMjY1Liw4MTk4NC4wMCwwLiwxNDI3NjMzLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwxNDMwMjY1LiwxNDI3NjMzLiwtMjYzMi4sMTU1MjYzNy4sIiI
Grand Total | 1760 | 2339183.55 | 72948.41 | 392089.93 | 18088831.79 | 3493861.2 |  | 24388674.88
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 | 0 | 201 | 40 | 47 | 0 | 380 |  | 668 |  | 288
02 |  | 327 |  | 154 | 119 | 2248 |  | 2848 |  | 600
03 |  | 16 |  | 0 | 59 | 277 |  | 352 |  | 75
04 | 9 | 128 | 43 | 98 | 49 | 1243 |  | 1570 |  | 327
05 |  | 78 | 0 | 90 | 40 | 990 |  | 1198 |  | 208
06 |  | 82 |  | 0 | 81 | 401 |  | 564 |  | 163
07 |  | 59 | 0 | 99 | 56 | 739 |  | 953 |  | 214
08 | 0 | 10 | 0 |  | 27 | 857 |  | 894 |  | 37
4OTY3Liw0MzYwODYuMjksMC4sODYxNTcyOC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sODI2ODk2Ny4sODYxNTcyOC4sMzQ2NzYyLiw5NTg4NzU2LiwiIiwiIiwiIg0KIjA1IiwiVDU2MTYiLCI0MzA2NTUxNTIwMSIsIkY1OTI4NzE5MzUiLCJBTkRFUlNPTiBDT0xVTUJJQSBDTy4gSU5DLiIsIk4vQS | [9 empty] | 0
RU5FUkFMIEFTUEhBTFQgQ08uIElOQy4iLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwNS8yMy8yMDE4IiwxNDM2MjgxLiwxNTE4MjY1LiwxNDMwMjY1Liw4MTk4NC4wMCwwLiwxNDI3NjMzLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwxNDMwMjY1LiwxNDI3NjMzLiwtMjYzMi4sMTU1MjYzNy4sIiI
Grand Total | 9 | 901 | 83 | 488 | 431 | 7135 |  | 9047
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
€€€€endefaulttablestyle.sty@Ùš?€èv (øTHenpurple_medium1.styeNEÙŸo@€èv (øathuid_default.sty“€€€€€€€€€€ZÙ€A€èv (ø€€€€ukid_default.sty€€€€€€€€€€€€€€_Ù•€B€èv (ø€€€€enteal_medium2.sty€€€€€€€€€€TÙŽ€C€èv (ø€€€€itid_default.sty€€€€€€€€€€€€ | [8 empty] | 0 | 288 | 8786 | 3.278%
€èv (øÜØ[€èv (øtnoid_default.styhemegÑØ n\€èv (øuiruid_default.styÖØ ]€èv (øjaid_default.styëØ^€èv (øtwid_default.styàØ:_€èv (øroid_default.styåØ?`€contracts_not_reported_active.fexúØ0a€eocfm025_bidder_opportuni.acxÿØ5db€èv (ø | [8 empty] | 0 | 600 | 17271 | 3.474%
01 |  | 28 |  | 5 |  | 67 |  | 100 | 33 | 108 | 8834 | 1.223%
02 |  |  |  |  | 53 | 323 |  | 376 | 53 | 380 | 23150 | 1.641%
03 |  | 45 |  | 39 | 10 | 355 |  | 449 | 94 | 302 | 12926 | 2.336%
04 | [5 empty] | 56 |  | 56 | 0 | 163 | 10179 | 1.601%
05 | [5 empty] | 102 |  | 102 | 0 | 214 | 10589 | 2.021%
06 |  | 264 |  |  | 69 | 98 |  | 431 | 333 | 370 | 5269 | 7.022%
07 | [5 empty] | 36 |  | 36 | 0 | 0 | 97004 | 0%
08 | [5 empty] | 239 |  | 239
Grand Total |  | 337 |  | 44 | 132 | 1276 |  | 1789

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P91 | 42271055201 | 009 | 2 |  | 1 | 919 | 18000.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required
01 | E1P91 | 42271055201 | 016 | 2 |  | 1 | 108 | 17200.74 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1P91 | 42271055201 | 036 | 2 |  | 1 | 001 | 24038.17 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1P91 | 42271055201 | 038 | 2 |  | 1 | 106 | 3792.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P91 | 42271055201 | 038 | 2 |  | 2 | 128 | 3792.02 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 | 046 | 2 |  | 1 | 001 | 30647.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1P91 | 42271055201 | 047 | 2 |  | 1 | 126 | 78691.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 001 | 2 |  | 1 | 305 | -383908.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 006 | 2 |  | 1 | 001 | 405680 | 84392.56 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 007 | 2 |  | 1 | 101 | -292.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 013 | 2 |  | 1 | 003 | 1373071.3 | 0 | 0 |  | N | 208 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 1 | 115 | 11250.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 2 | 128 | 37364.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 3 | 107 | 13430.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 4 | 101 | 42999 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 5 | 105 | 4377.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 021 | 2 | 850 | 6 | 003 | 13393.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 024 | 2 |  | 1 | 001 | 125640.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 026 | 2 |  | 1 | 007 | 13725.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 029 | 2 |  | 1 | 503 | 18962.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 029 | 2 |  | 2 | 118 | 16897.85 | 4387.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 033 | 2 |  | 1 | 004 | 167069.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 036 | 2 |  | 1 | 103 | 41332.83 | 0 | 0 |  | N | 114 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 037 | 2 |  | 1 | 118 | 41926.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 039 | 2 |  | 1 | 502 | 14313.64 | 14313.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 039 | 2 |  | 2 | 112 | 14693.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1Q29 | 42584115201 | 039 | 2 |  | 3 | 503 | -6126.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q29 | 42584115201 | 039 | 2 |  | 4 | 007 | 4379.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q29 | 42584115201 | 039 | 2 |  | 5 | 007 | 14989.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R66 | 43641515201 | 006 | 2 |  | 1 | 923 | 11702.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R66 | 43641515201 | 007 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1R66 | 43641515201 | 007 | 2 |  | 2 | 503 | 70076.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1634 | 43137315201 | 012 | 2 |  | 1 | 503 | 136124.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1634 | 43137315201 | 012 | 2 |  | 2 | 101 | 3575 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1634 | 43137315201 | 013 | 2 |  | 1 | 001 | 305367.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1634 | 43137315201 | 017 | 2 | 850 | 1 | 007 | 8389.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1634 | 43137315201 | 017 | 2 | 850 | 2 | 101 | 2673 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1634 | 43137315201 | 023 | 2 |  | 1 | 001 | 0 | 0 | 1 |  | N | 28 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1636 | 43323815201 | 008 | 2 |  | 1 | 001 | 11597.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 005 | 2 |  | 1 | 112 | 5550 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 005 | 2 |  | 2 | 007 | -6645.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1664 | 20103265201 | 010 | 2 |  | 1 | 101 | 12870 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 015 | 2 |  | 1 | 919 | 61398.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 017 | 2 |  | 1 | 305 | -250655.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 1 | 012 | 11241.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 | 018 | 2 | 850 | 2 | 101 | 3746.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 3 | 107 | 5928.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 4 | 107 | 1619.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 5 | 112 | 1162.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 6 | 107 | 1619.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 7 | 022 | 4823.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 8 | 105 | 23626.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 9 | 115 | 9747.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 10 | 101 | 4544.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 018 | 2 | 850 | 11 | 101 | 721.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 1 | 105 | 82510 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 2 | 112 | 531.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 020 | 2 |  | 3 | 115 | 264.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 025 | 2 |  | 1 | 001 | 127697.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 026 | 2 |  | 1 | 001 | 97037.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 029 | 2 |  | 1 | 001 | 106486.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 030 | 2 |  | 1 | 001 | 74476.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 035 | 2 |  | 1 | 001 | 45733.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 036 | 2 |  | 1 | 922 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 037 | 2 |  | 1 | 001 | 14686.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 039 | 2 |  | 1 | 107 | 962861.32 | 0 | 1 |  | N | 120 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 1 | 105 | 33305.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1664 | 20103265201 | 040 | 2 |  | 2 | 112 | 35452.32 | 4957.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1664 | 20103265201 | 041 | 2 |  | 1 | 103 | 89278.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1664 | 20103265201 | 042 | 2 |  | 1 | 001 | 53578.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 046 | 2 |  | 1 | 004 | 21015.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1664 | 20103265201 | 047 | 2 |  | 1 | 001 | 10243.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1664 | 20103265201 | 048 | 2 |  | 1 | 015 | -82748.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 049 | 2 |  | 1 | 015 | 293617.71 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1664 | 20103265201 | 050 | 2 |  | 1 | 101 | 3163.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1667 | 43494215201 | 003 | 2 |  | 1 | 503 | -485989.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 011 | 2 |  | 1 | 919 | 42077.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 012 | 2 |  | 1 | 918 | 1398.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 015 | 2 |  | 1 | 004 | 7230.22 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1671 | 43560615201 | 020 | 2 |  | 1 | 001 | 8178.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 025 | 2 |  | 1 | 115 | 11373.34 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 029 | 2 | 850 | 1 | 023 | 220.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 029 | 2 | 850 | 2 | 001 | 52335.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 033 | 2 |  | 1 | 001 | 66893.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 | 040 | 2 |  | 1 | 004 | 11821.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1671 | 43560615201 | 043 | 2 |  | 1 | 115 | 9237.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1671 | 43560615201 | 043 | 2 |  | 2 | 001 | 22786.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1693 | 43450215201 | 011 | 2 |  | 1 | 117 | 2919.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1693 | 43450215201 | 014 | 2 |  | 1 | 115 | 17352.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1693 | 43450215201 | 014 | 2 |  | 2 | 700 | 9647 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | T1693 | 43450215201 | 023 | 2 |  | 1 | 009 | 49706.91 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 024 | 2 |  | 1 | 007 | 2400 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1693 | 43450215201 | 028 | 2 |  | 1 | 009 | 97115.34 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 029 | 2 |  | 1 | 001 | 83565.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1693 | 43450215201 | 030 | 2 |  | 1 | 009 | 95480.95 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | T1693 | 43450215201 | 031 | 2 |  | 1 | 001 | 16061.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1697 | 43534915201 | 011 | 2 |  | 1 | 101 | -2580.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1697 | 43534915201 | 011 | 2 |  | 2 | 105 | 51917.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1701 | 43498615201 | 007 | 2 |  | 1 | 113 | -81037.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | T1701 | 43498615201 | 011 | 2 |  | 1 | 503 | 7224.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1701 | 43498615201 | 019 | 2 |  | 1 | 923 | 9988.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1706 | 43658615201 | 003 | 2 |  | 1 | 305 | -242435.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1707 | 44013815201 | 002 | 2 |  | 1 | 101 | 7262.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1713 | 43355215201 | 018 | 2 |  | 1 | 003 | 58401.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1713 | 43355215201 | 021 | 2 |  | 1 | 115 | 96632.78 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Drainage Modification | Plan Modifications | 2
01 | T1727 | 43800715201 | 015 | 2 |  | 1 | 923 | 2884.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1727 | 43800715201 | 019 | 2 |  | 1 | 101 | -6456.05 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1727 | 43800715201 | 019 | 2 |  | 2 | 005 | 6050 | 0 | 3 |  | C | 0 | Avoidable, CEI Consultant | Utility Adjustments | Utility Delays | 11
01 | T1727 | 43800715201 | 019 | 2 |  | 3 | 118 | 102492.79 | 56604.74 | 2 |  | N | 47 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1729 | 43837415201 | 002 | 2 |  | 1 | 117 | 59542.75 | 1350 | 1 |  | N | 0 | Avoidable, Design Consultant | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1739 | 43837815201 | 008 | 2 |  | 1 | 923 | 3529.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1749 | 44319925201 | 005 | 2 |  | 1 | 103 | 60277.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1753 | 43943215201 | 004 | 2 |  | 1 | 126 | 19151.94 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
02 | E2P14 | 21330435201 | 001 | 2 |  | 1 | 119 | 9007933 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 002 | 2 |  | 1 | 008 | 34432.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 003 | 2 |  | 1 | 107 | 335329.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 004 | 2 |  | 1 | 008 | 35852.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 005 | 2 |  | 1 | 008 | 1018305.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 1 | 008 | 24819.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 2 | 350 | 16500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 3 | 119 | 107859.75 | 107859.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 4 | 008 | 769.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 006 | 2 | 850 | 5 | 008 | 51.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 007 | 2 |  | 1 | 008 | 91959.33 | 50678.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 008 | 2 |  | 1 | 119 | 240297.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 009 | 2 |  | 1 | 012 | 82871.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 1 | 119 | 134858.4 | 134858.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 040 | 2 | 850 | 2 | 012 | 15141.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 041 | 2 |  | 1 | 107 | 71091.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 048 | 2 |  | 1 | 008 | 234097.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 057 | 2 |  | 1 | 106 | 378046.76 | 378046.76 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 4 | 107 | 9637.19 | 9637.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 5 | 004 | 68634.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 6 | 012 | 26194.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 7 | 107 | 2623.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 8 | 008 | 7646.81 | 7646.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 9 | 012 | 2190.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 10 | 012 | 2491.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 11 | 350 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 12 | 012 | 935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 066 | 2 | 850 | 13 | 016 | 9846.33 | 9846.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 1 | 116 | 50933.24 | 50933.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 2 | 001 | 11645.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 3 | 018 | 14242.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 4 | 107 | 1378.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 5 | 008 | 4106.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 6 | 107 | 3916.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 7 | 107 | 2167.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 8 | 107 | 1355.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 9 | 119 | 52255.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 077 | 2 | 850 | 10 | 350 | 7998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 088 | 2 |  | 1 | 107 | 328688.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 094 | 2 |  | 1 | 107 | 2920117.97 | 0 | 0 |  | N | 152 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 098 | 2 |  | 1 | 012 | 28016.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 099 | 2 |  | 1 | 018 | 66169.53 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 102 | 2 |  | 1 | 917 | 54727.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | E2P14 | 21330435201 | 115 | 2 |  | 1 | 107 | 28829.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 115 | 2 |  | 2 | 003 | -10699.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 118 | 2 |  | 1 | 107 | 41480.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 119 | 2 |  | 1 | 116 | 149447.45 | 149447.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 1 | 350 | 5201.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 2 | 107 | 19858.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 3 | 107 | 9972.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 4 | 107 | 33966.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 5 | 012 | 17083.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 6 | 012 | 22540.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 7 | 122 | 3442.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 8 | 012 | 517.91 | 517.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 9 | 107 | -425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 10 | 120 | 2758.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 11 | 107 | 2156.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 12 | 107 | 2183.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 13 | 008 | 18841.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 120 | 2 | 850 | 14 | 012 | 11900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 122 | 2 |  | 1 | 019 | 180676.52 | 35226.03 | 0 |  | N | 110 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 1 | 008 | 185154.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 123 | 2 |  | 2 | 004 | -65070.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 132 | 2 |  | 1 | 919 | 153275.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 | 138 | 2 |  | 1 | 503 | 106762.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 138 | 2 |  | 2 | 305 | -18218.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 141 | 2 |  | 1 | 116 | 103438.51 | 0 | 0 |  | N | 132 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 1 | 350 | 26400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 2 | 107 | 6699.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 3 | 115 | 14880.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 146 | 2 | 850 | 4 | 003 | 2019.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 1 | 012 | 74208.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 2 | 008 | 191599.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 | 151 | 2 |  | 3 | 107 | 4680.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 4 | 107 | 1368.26 | 1368.26 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 5 | 107 | -252327.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 151 | 2 |  | 6 | 113 | -20345.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 1 | 003 | 5488.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 2 | 012 | 17083.6 | 17083.6 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 3 | 012 | 5886.77 | 5886.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 4 | 503 | 561.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 5 | 107 | 1642.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 | 155 | 2 | 850 | 6 | 012 | 4880.88 | 4880.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2P14 | 21330435201 | 158 | 2 |  | 1 | 115 | 194183.28 | 76566.34 | 0 |  | N | 138 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 1 | 305 | -18243.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 2 | 305 | -202219.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 3 | 305 | -43521.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 006 | 2 |  | 4 | 305 | -7517.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 027 | 2 |  | 1 | 007 | 332736.87 | 0 | 5 |  | N | 28 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 1 | 350 | 448.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 3 | 007 | 47220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 8 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 10 | 007 | 5912.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 14 | 007 | 3585.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 15 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 16 | 004 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 19 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 20 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 21 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 22 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 23 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 24 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 25 | 350 | 226.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 26 | 013 | 2714.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 27 | 004 | 22282.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 28 | 107 | 3810.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 035 | 2 |  | 1 | 004 | -60081.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 041 | 2 |  | 1 | 105 | 14220.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 048 | 2 |  | 1 | 503 | -16004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 1 | 350 | 1973.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 3 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 4 | 350 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 8 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 10 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 050 | 2 |  | 1 | 503 | 30068.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 051 | 2 |  | 1 | 007 | 120878.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 053 | 2 |  | 1 | 115 | 72295.4 | 0 | 0 |  | N | 105 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 054 | 2 |  | 1 | 010 | 254205.02 | 0 | 0 |  | N | 61 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 1 | 004 | 11904.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 | 007 | 2 | 850 | 2 | 012 | 34522.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2T34 | 43141825201 | 012 | 2 |  | 1 | 007 | -992697 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2T34 | 43141825201 | 016 | 2 |  | 1 | 015 | 28348.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 021 | 2 |  | 1 | 917 | 63655.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 023 | 2 |  | 1 | 015 | 48247.54 | 0 | 5 |  | N | 7 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 029 | 2 |  | 1 | 919 | 95462.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2T34 | 43141825201 | 038 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 231 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2U38 | 43226615201 | 007 | 2 |  | 1 | 015 | 35250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 | 012 | 2 | 850 | 1 | 015 | 40303.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V70 | 42747515201 | 016 | 2 |  | 1 | 004 | 4312.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V70 | 42747515201 | 022 | 2 | 850 | 1 | 112 | 4761.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 | 022 | 2 | 850 | 2 | 112 | 1341.48 | 1341.48 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 | 033 | 2 |  | 2 | 860 | 41531.42 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | E2V70 | 42747515201 | 033 | 2 |  | 3 | 860 | 63301.94 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | E2V71 | 43430015201 | 005 | 2 |  | 1 | 101 | 11273.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 1 | 115 | 13591.19 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2V71 | 43430015201 | 016 | 2 |  | 2 | 107 | 5577 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 005 | 2 |  | 1 | 001 | 65939 | 0 | 2 |  | N | 5 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 1 | 012 | 25041.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 2 | 122 | 12630.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 3 | 012 | 7092.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 010 | 2 | 850 | 4 | 105 | 5236 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 1 | 105 | 11908.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 2 | 012 | 16133.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 4 | 107 | 6033.41 | 6033.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 5 | 105 | 4141.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 6 | 001 | 8937.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 011 | 2 | 850 | 7 | 105 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V95 | 43617015201 | 023 | 2 |  | 1 | 001 | 174752.34 | 107016.17 | 2 |  | N | 59 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 | 023 | 2 |  | 2 | 119 | 135900.42 | 135900.42 | 0 |  | N | 37 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 1 | 119 | 163953.52 | 163953.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 2 | 119 | 10521.77 | 3960 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 | 031 | 2 |  | 3 | 122 | 5634.36 | 5634.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 1 | 305 | -60481.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2W51 | 20950355201 | 016 | 2 |  | 2 | 503 | 41803.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 3 | 503 | -17432.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W51 | 20950355201 | 016 | 2 |  | 4 | 503 | 32141.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W52 | 42849815201 | 005 | 2 | 850 | 1 | 012 | 13286.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 | 008 | 2 |  | 1 | 503 | 44781.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X44 | 42879715201 | 003 | 2 |  | 1 | 015 | 139617.91 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 007 | 2 |  | 1 | 015 | 461586.77 | 0 | 0 |  | N | 65 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 008 | 2 | 850 | 1 | 007 | 6806.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X62 | 43044925201 | 013 | 2 | 850 | 1 | 119 | 26250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 | 013 | 2 | 850 | 2 | 119 | 17955.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 | 013 | 2 | 850 | 3 | 923 | 5794.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 | 026 | 2 | 850 | 1 | 923 | 18403.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 1 | 105 | 13055.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 3 | 105 | 13281.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 4 | 106 | 13933.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 5 | 105 | 6068.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 022 | 2 | 850 | 6 | 105 | 3660.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 036 | 2 | 850 | 1 | 105 | 3306.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 | 047 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 67 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2576 | 43091115201 | 001 | 2 |  | 1 | 101 | 36502.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2576 | 43091115201 | 010 | 2 |  | 1 | 101 | 13117.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2576 | 43091115201 | 014 | 2 |  | 1 | 105 | 15494.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 024 | 2 |  | 1 | 917 | 7554.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 028 | 2 |  | 1 | 112 | 70867.44 | 70867.44 | 1 |  | C | 43 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2576 | 43091115201 | 029 | 2 |  | 1 | 106 | 11536.56 | 11536.56 | 1 |  | C | 7 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2576 | 43091115201 | 035 | 2 |  | 1 | 917 | 4188.21 | 4188.21 | 0 |  | C | 6 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2576 | 43091115201 | 040 | 2 |  | 1 | 105 | 65923.25 | 65923.25 | 0 |  | C | 40 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 | 041 | 2 |  | 1 | 005 | 32694.52 | 32694.52 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 | 044 | 2 |  | 1 | 001 | 10379.07 | 1648.08 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 | 045 | 2 |  | 1 | 113 | 6984.76 | 4944.24 | 1 |  | C | 7 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
02 | T2576 | 43091115201 | 048 | 2 |  | 1 | 860 | 898427.26 | 0 | 0 |  | N | 107 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2577 | 43245215201 | 009 | 2 |  | 1 | 001 | 67803.45 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 1 | 001 | 15603.45 | 9281.13 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 2 | 001 | 5103.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 3 | 001 | 2662.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 025 | 2 | 850 | 4 | 015 | 14574.71 | 512.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 033 | 2 | 850 | 1 | 015 | 34984.01 | 34984.01 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 1 | 005 | 70550.44 | 70550.44 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 | 034 | 2 | 850 | 2 | 001 | 10184.91 | 10184.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 3 | 108 | 11169.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2577 | 43245215201 | 034 | 2 | 850 | 4 | 023 | 418.84 | 418.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2577 | 43245215201 | 034 | 2 | 850 | 5 | 001 | 2170.66 | 2170.66 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 6 | 021 | 5224.24 | 5224.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 7 | 004 | 440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 8 | 004 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 9 | 012 | 9423.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 10 | 021 | 9966.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 | 034 | 2 | 850 | 11 | 004 | -44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2577 | 43245215201 | 042 | 2 |  | 1 | 015 | 8111.5 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 051 | 2 |  | 1 | 015 | 2113.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2577 | 43245215201 | 052 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 187 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2616 | 20800155201 | 018 | 2 |  | 1 | 305 | -576565.5 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2616 | 20800155201 | 032 | 2 |  | 1 | 919 | 68532.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2616 | 20800155201 | 044 | 2 |  | 1 | 305 | -18.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2616 | 20800155201 | 048 | 2 |  | 1 | 101 | 46194.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2616 | 20800155201 | 049 | 2 |  | 1 | 101 | 88788.54 | 29036.53 | 1 |  | C | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 1 | 113 | 13643.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 2 | 105 | 660.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 3 | 115 | 4338.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 4 | 001 | 622.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 5 | 001 | 5688.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 6 | 107 | 9211.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 9 | 503 | 1452 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 003 | 2 | 850 | 10 | 115 | 4987.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 11 | 008 | 370.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 12 | 115 | 4714.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 13 | 115 | 7179.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 15 | 001 | 559.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 16 | 107 | 187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 17 | 107 | 2238.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 003 | 2 | 850 | 18 | 001 | 3913.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 19 | 022 | 390.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 003 | 2 | 850 | 20 | 503 | 2249.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2618 | 43091015201 | 022 | 2 | 850 | 1 | 015 | 10219.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 2 | 015 | 3509.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 3 | 015 | 2785.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 022 | 2 | 850 | 4 | 015 | 12807.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 | 028 | 2 |  | 1 | 101 | 319.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2618 | 43091015201 | 028 | 2 |  | 2 | 107 | 25124.74 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 029 | 2 |  | 1 | 001 | 29366.68 | 0 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 | 030 | 2 |  | 1 | 107 | 10312.9 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 2 | 107 | -2434.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 3 | 105 | -5067.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 4 | 005 | -4526.1 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 030 | 2 |  | 5 | 107 | 24915.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 6 | 107 | 155316.69 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 7 | 105 | 26397.58 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 8 | 105 | -11156.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 9 | 105 | 49750.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2618 | 43091015201 | 030 | 2 |  | 10 | 012 | 5251.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 035 | 2 |  | 1 | 919 | 11029.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 | 036 | 2 |  | 1 | 005 | 58922.5 | 0 | 5 |  | C | 16 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2618 | 43091015201 | 037 | 2 |  | 1 | 112 | 58922.5 | 0 | 5 |  | C | 17 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 | 040 | 2 | 850 | 1 | 850 | 66230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T2618 | 43091015201 | 042 | 2 |  | 1 | 106 | 4926.75 | 0 | 5 |  | C | 1 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2618 | 43091015201 | 044 | 2 |  | 1 | 005 | 65531.51 | 0 | 5 |  | C | 12 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2621 | 20800145201 | 003 | 2 |  | 1 | 007 | 13940.09 | 8734.4 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2621 | 20800145201 | 003 | 2 |  | 2 | 007 | 74157.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2621 | 20800145201 | 013 | 2 |  | 1 | 503 | 42557.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 | 022 | 2 |  | 1 | 919 | 72013.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 | 030 | 2 |  | 1 | 112 | 141476.3 | 141476.3 | 1 |  | N | 33 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2621 | 20800145201 | 041 | 2 | 850 | 1 | 107 | 25503.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 | 041 | 2 | 850 | 2 | 023 | 8023.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 | 041 | 2 | 850 | 3 | 008 | 10440.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 | 041 | 2 | 850 | 4 | 023 | 4430.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 | 041 | 2 | 850 | 5 | 003 | 7654.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2621 | 20800145201 | 041 | 2 | 850 | 6 | 007 | 17417.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2621 | 20800145201 | 041 | 2 | 850 | 7 | 023 | 5455.56 | 5455.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2621 | 20800145201 | 041 | 2 | 850 | 8 | 023 | 17032.88 | 17032.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2621 | 20800145201 | 073 | 2 |  | 1 | 010 | 21606.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2657 | 20781825201 | 008 | 2 |  | 1 | 919 | 28193.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2657 | 20781825201 | 035 | 2 |  | 1 | 107 | 1194.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2658 | 41525215201 | 002 | 2 |  | 1 | 119 | 6298.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 018 | 2 |  | 1 | 119 | 2847.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2658 | 41525215201 | 029 | 2 |  | 1 | 106 | 5831.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2658 | 41525215201 | 030 | 2 |  | 1 | 108 | 66785.91 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2661 | 43433715201 | 011 | 2 |  | 1 | 019 | 49601.71 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2661 | 43433715201 | 011 | 2 |  | 2 | 012 | 0 | 0 | 1 |  | N | 13 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 014 | 2 |  | 1 | 112 | 163253.75 | 0 | 1 |  | N | 50 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 | 016 | 2 | 850 | 1 | 001 | 46630.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 | 016 | 2 | 850 | 2 | 012 | 3369.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 023 | 2 | 850 | 1 | 012 | 14165.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2661 | 43433715201 | 023 | 2 | 850 | 2 | 112 | 35834.47 | 35834.47 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 | 028 | 2 | 850 | 1 | 101 | 1614.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2661 | 43433715201 | 028 | 2 | 850 | 2 | 503 | 987.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2661 | 43433715201 | 028 | 2 | 850 | 3 | 013 | 4419.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | T2678 | 21028685201 | 005 | 2 |  | 1 | 919 | 3031.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | T2678 | 21028685201 | 013 | 2 |  | 1 | 001 | 20879.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2678 | 21028685201 | 020 | 2 |  | 1 | 007 | 12014.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2678 | 21028685201 | 026 | 2 |  | 1 | 001 | 65153.95 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2679 | 43617415201 | 004 | 2 |  | 1 | 015 | 117171.86 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 | 007 | 2 | 850 | 1 | 105 | 13341.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2679 | 43617415201 | 007 | 2 | 850 | 2 | 015 | 3910.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 | 007 | 2 | 850 | 3 | 015 | 575.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2682 | 43201215201 | 017 | 2 |  | 1 | 112 | 64175.15 | 0 | 2 |  | N | 27 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2682 | 43201215201 | 024 | 2 |  | 1 | 001 | 112571.21 | 0 | 0 |  | N | 52 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2682 | 43201215201 | 025 | 2 |  | 1 | 503 | 7144.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2683 | 43616215201 | 001 | 2 |  | 1 | 101 | 8616 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 | 021 | 2 |  | 1 | 860 | 27470.55 | 27470.55 | 1 |  | N | 38 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
02 | T2688 | 43500115201 | 012 | 2 |  | 1 | 503 | 66082.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2695 | 43615815201 | 012 | 2 |  | 1 | 019 | -77219.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2695 | 43615815201 | 017 | 2 | 850 | 1 | 106 | 798.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 | 017 | 2 | 850 | 2 | 106 | 931.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 1 | 115 | 21134.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 2 | 001 | 3774.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2704 | 43761615201 | 017 | 2 |  | 3 | 106 | 7438.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 4 | 115 | 49969.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2704 | 43761615201 | 017 | 2 |  | 5 | 012 | 1226.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2704 | 43761615201 | 017 | 2 |  | 6 | 003 | 3231.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2708 | 44216935201 | 004 | 2 |  | 1 | 018 | 1160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2708 | 44216935201 | 005 | 2 |  | 1 | 923 | 3883.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2708 | 44216935201 | 006 | 2 |  | 1 | 101 | 388.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2710 | 40926715201 | 004 | 2 |  | 1 | 105 | 12963.09 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2710 | 40926715201 | 017 | 2 |  | 1 | 113 | 23187.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2710 | 40926715201 | 017 | 2 |  | 2 | 502 | 776.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate Directions Given | CEI Actions/Inactions | 6
02 | T2710 | 40926715201 | 018 | 2 |  | 1 | 001 | 1814.98 | 1814.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2710 | 40926715201 | 018 | 2 |  | 2 | 001 | 3512.44 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2714 | 43761815201 | 003 | 2 |  | 1 | 101 | 215401.85 | 0 | 2 |  | N | 60 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2714 | 43761815201 | 007 | 2 |  | 1 | 001 | 87764.04 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2714 | 43761815201 | 011 | 2 |  | 1 | 001 | 24593.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q52 | 43626715201 | 015 | 2 |  | 1 | 922 | 3908.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R04 | 43627115201 | 012 | 2 |  | 1 | 503 | 19445.17 | 8287.64 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 013 | 2 |  | 1 | 503 | -25001.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R04 | 43627115201 | 016 | 2 |  | 1 | 922 | 823.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R52 | 43627225201 | 008 | 2 |  | 1 | 503 | 5734.8 | 507.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R71 | 41557325201 | 011 | 2 |  | 1 | 016 | 37738.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3R73 | 43672615201 | 016 | 2 |  | 1 | 101 | 31189.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 | 019 | 2 |  | 1 | 922 | 14784.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3471 | 41110225201 | 038 | 2 |  | 1 | 009 | 157836.02 | 157836.02 | 5 |  | N | 50 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
03 | T3485 | 42695315201 | 006 | 2 |  | 1 | 012 | 1215 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3488 | 40979275201 | 014 | 2 |  | 1 | 106 | 27272.89 | 9260.48 | 1 |  | N | 8 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 023 | 2 |  | 1 | 126 | 34898.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3488 | 40979275201 | 036 | 2 |  | 1 | 106 | 6047.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3543 | 22044275201 | 005 | 2 |  | 1 | 115 | 33978.2 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 008 | 2 |  | 1 | 305 | -41800.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 012 | 2 |  | 1 | 007 | 8111.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3543 | 22044275201 | 025 | 2 | 850 | 1 | 503 | 4965.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 2 | 503 | 1948.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 3 | 107 | 8470 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 4 | 503 | 9846.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 5 | 503 | 17045.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 6 | 503 | 26136 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 7 | 503 | 12458.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 8 | 503 | 4066.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 9 | 503 | 12089.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 10 | 107 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 11 | 503 | 2970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 12 | 107 | 1161.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 025 | 2 | 850 | 13 | 503 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 14 | 503 | 451.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 15 | 503 | 1357.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 16 | 503 | 11682.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 17 | 001 | 25599.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3543 | 22044275201 | 025 | 2 | 850 | 18 | 503 | 3120.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 025 | 2 | 850 | 19 | 503 | 2175.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 030 | 2 |  | 1 | 115 | 62520.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 030 | 2 |  | 2 | 860 | 38746.54 | 38746.54 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 033 | 2 |  | 1 | 503 | 72600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 042 | 2 |  | 1 | 010 | 126961.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 042 | 2 |  | 2 | 860 | 10682.09 | 10682.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 047 | 2 |  | 1 | 919 | 81171.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 050 | 2 |  | 1 | 503 | 40858.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 1 | 001 | 29819.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3543 | 22044275201 | 053 | 2 | 850 | 2 | 503 | 40150.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 3 | 107 | 2695 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 053 | 2 | 850 | 4 | 503 | 6326.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 5 | 503 | 33481.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 6 | 503 | 33481.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 7 | 503 | 1958.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 8 | 503 | 1037.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 053 | 2 | 850 | 9 | 503 | 1050.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 057 | 2 |  | 1 | 860 | 34418.57 | 34418.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 061 | 2 |  | 1 | 003 | 51134.75 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3543 | 22044275201 | 061 | 2 |  | 2 | 117 | 73599.9 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | T3543 | 22044275201 | 069 | 2 | 850 | 1 | 503 | 8123.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 069 | 2 | 850 | 2 | 101 | 29590 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3543 | 22044275201 | 069 | 2 | 850 | 3 | 503 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 069 | 2 | 850 | 4 | 003 | 51347.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3543 | 22044275201 | 069 | 2 | 850 | 5 | 010 | 11629.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 069 | 2 | 850 | 6 | 107 | 925.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 071 | 2 |  | 1 | 922 | 46846.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 | 072 | 2 |  | 1 | 010 | 85883.21 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3543 | 22044275201 | 080 | 2 |  | 1 | 860 | 44696.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3543 | 22044275201 | 086 | 2 |  | 1 | 503 | 87475.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 | 087 | 2 |  | 1 | 860 | 4850000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3584 | 42551925201 | 022 | 2 |  | 1 | 922 | 14487.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
03 | T3584 | 42551925201 | 025 | 2 |  | 1 | 106 | 37268.2 | 0 | 5 |  | N | 9 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3586 | 42862415201 | 010 | 2 |  | 1 | 402 | 13328 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3586 | 42862415201 | 013 | 2 |  | 1 | 010 | 28275.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3586 | 42862415201 | 017 | 2 |  | 1 | 922 | 36990.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3594 | 42884415201 | 024 | 2 |  | 1 | 115 | 34359.48 | 0 | 0 |  | N | 56 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3614 | 43228815201 | 009 | 2 |  | 1 | 001 | 305542.39 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3614 | 43228815201 | 016 | 2 |  | 1 | 001 | 21000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3617 | 43228615201 | 019 | 2 |  | 1 | 503 | 37840.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3621 | 43626115201 | 005 | 2 |  | 1 | 101 | 4400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 011 | 2 |  | 1 | 115 | 20856 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3621 | 43626115201 | 020 | 2 |  | 1 | 101 | 4107.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3621 | 43626115201 | 026 | 2 |  | 1 | 503 | 31063.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3622 | 43403415201 | 010 | 2 |  | 1 | 402 | 6645.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3637 | 43626515201 | 007 | 2 |  | 1 | 101 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3637 | 43626515201 | 017 | 2 |  | 1 | 922 | 22662.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3639 | 43078915201 | 005 | 2 |  | 1 | 503 | -51677.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3639 | 43078915201 | 016 | 2 |  | 1 | 922 | 18680.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3653 | 43672015201 | 004 | 2 |  | 1 | 503 | -2207.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 001 | 2 |  | 1 | 004 | 20837.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3655 | 43666315201 | 006 | 2 |  | 1 | 101 | 8408.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3655 | 43666315201 | 016 | 2 |  | 1 | 115 | -3179.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 017 | 2 |  | 1 | 113 | 24270.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3655 | 43666315201 | 023 | 2 |  | 1 | 003 | 50951.67 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3655 | 43666315201 | 028 | 2 |  | 1 | 012 | 194848.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 | 029 | 2 |  | 1 | 503 | -1841.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 030 | 2 | 850 | 1 | 022 | 32893.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3655 | 43666315201 | 038 | 2 |  | 1 | 922 | 61701.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3661 | 43255915201 | 019 | 2 |  | 1 | 115 | 27889.1 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 010 | 2 |  | 1 | 113 | -27605.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 019 | 2 |  | 1 | 113 | 48112.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3662 | 43627215201 | 022 | 2 |  | 1 | 503 | 10741.57 | 10741.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3667 | 43273835201 | 020 | 2 |  | 1 | 922 | 34550.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3667 | 43273835201 | 025 | 2 |  | 1 | 503 | -38741.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3667 | 43273835201 | 029 | 2 |  | 1 | 126 | 15851.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3669 | 43046415201 | 014 | 2 |  | 1 | 922 | 124069.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | T3669 | 43046415201 | 016 | 2 |  | 1 | 119 | 85791.18 | 8898.63 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3673 | 43774415201 | 004 | 2 |  | 1 | 503 | -384821.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 005 | 2 |  | 1 | 503 | 11920.36 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 008 | 2 |  | 1 | 503 | 10256.95 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3673 | 43774415201 | 010 | 2 |  | 1 | 503 | 222636.82 | 0 | 0 |  | E | 35 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3678 | 43627015201 | 007 | 2 |  | 1 | 503 | -4020 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3684 | 43774815201 | 002 | 2 |  | 1 | 402 | 3960 | 279 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3713 | 42985635201 | 004 | 2 |  | 1 | 115 | 6200 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3713 | 42985635201 | 010 | 2 |  | 1 | 115 | 2500 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3713 | 42985635201 | 018 | 2 |  | 1 | 115 | 34586.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3713 | 42985635201 | 023 | 2 |  | 1 | 115 | 2983.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3715 | 43827215201 | 001 | 2 |  | 1 | 107 | 4835.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4N84 | 42170735201 | 004 | 2 |  | 1 | 007 | 67279.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N84 | 42170735201 | 007 | 2 |  | 1 | 503 | 39656.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 026 | 2 |  | 1 | 003 | 9246.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 026 | 2 |  | 2 | 004 | 54638.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 026 | 2 |  | 3 | 305 | -229803 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 1 | 003 | 13651 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 2 | 004 | -803702.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 036 | 2 |  | 3 | 118 | 277064.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N84 | 42170735201 | 036 | 2 |  | 4 | 123 | 66140.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | E4N84 | 42170735201 | 036 | 2 |  | 5 | 108 | 105133.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N84 | 42170735201 | 039 | 2 |  | 1 | 503 | 59956 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 044 | 2 |  | 1 | 305 | -16958 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 044 | 2 |  | 2 | 001 | 24890.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170735201 | 049 | 2 |  | 1 | 503 | 18150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 2 | 503 | 10124.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 3 | 023 | 18920.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 049 | 2 |  | 4 | 001 | 8519.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170735201 | 053 | 2 |  | 1 | 003 | 1081752.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 054 | 2 |  | 1 | 023 | 21036.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 054 | 2 |  | 2 | 503 | 12375.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 054 | 2 |  | 3 | 503 | 1731.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 1 | 917 | 3222.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 2 | 917 | 861.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 3 | 917 | 891.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 4 | 917 | 861.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 5 | 917 | 457.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 6 | 917 | 3222.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 7 | 917 | 2608.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 8 | 917 | 15673.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 9 | 917 | 3775.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 10 | 917 | 4972.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 11 | 917 | 467.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 12 | 917 | 2576.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 059 | 2 |  | 13 | 917 | 861.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 1 | 503 | 5610 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 2 | 503 | 3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 3 | 023 | 277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 4 | 023 | 1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 5 | 503 | 2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 6 | 023 | 3067.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 7 | 003 | 1716 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 8 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 9 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 062 | 2 | 850 | 10 | 503 | 2950.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 1 | 023 | 1366.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 2 | 503 | 14179.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 3 | 503 | 80290.89 | 6037.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 4 | 503 | 11900.52 | 699.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 063 | 2 |  | 5 | 503 | 11184.99 | 1399.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 1 | 503 | 635855.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 2 | 503 | 22157.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 069 | 2 |  | 3 | 503 | -237035.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 1 | 503 | 72372.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 2 | 503 | 32749.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 070 | 2 |  | 3 | 503 | 80099.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 076 | 2 |  | 1 | 503 | 20332.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 076 | 2 |  | 2 | 503 | 33887.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 082 | 2 |  | 1 | 503 | -420676.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 1 | 919 | 22100.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 2 | 919 | 18619.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 090 | 2 |  | 3 | 919 | 139540.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 1 | 503 | -43656.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 2 | 004 | 59400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 3 | 007 | -15255.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 4 | 350 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4N84 | 42170735201 | 098 | 2 |  | 5 | 503 | -24072.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 6 | 004 | 45540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 098 | 2 |  | 7 | 503 | 33899.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 098 | 2 |  | 8 | 004 | 45540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 101 | 2 |  | 1 | 305 | -158066.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 101 | 2 |  | 2 | 503 | 158066.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 1 | 003 | 2566.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 2 | 503 | 4103.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 102 | 2 | 850 | 3 | 503 | 3329.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 1 | 503 | -5375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 2 | 503 | 75715.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 106 | 2 |  | 3 | 503 | -3505.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 110 | 2 |  | 1 | 503 | 451695.03 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 116 | 2 |  | 1 | 503 | 11147.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 116 | 2 |  | 2 | 503 | 5232.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 1 | 503 | 11390.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 2 | 023 | 2285.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 3 | 503 | 4537.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 | 121 | 2 | 850 | 4 | 004 | 32080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N84 | 42170735201 | 128 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 | 038 | 2 |  | 1 | 108 | 80927.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4N95 | 43316515201 | 045 | 2 |  | 1 | 007 | -501039.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 059 | 2 |  | 1 | 007 | -175009.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 066 | 2 |  | 1 | 007 | 139723.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 074 | 2 |  | 1 | 919 | 74739.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 1 | 004 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N95 | 43316515201 | 101 | 2 |  | 2 | 003 | 42467.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 1 | 004 | 512217.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 2 | 004 | 80912.86 | 2099.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 3 | 004 | 27828.57 | 1135.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 4 | 004 | 25222.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 5 | 305 | -405594 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 006 | 2 |  | 6 | 305 | 202797 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 1 | 001 | 76519.47 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 2 | 001 | 58964.66 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 3 | 001 | 13868.01 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 4 | 001 | 26812.22 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 5 | 003 | 109945.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 6 | 004 | 103082.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 7 | 004 | 18931.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 8 | 004 | -37863.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 9 | 004 | -4121.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 047 | 2 |  | 10 | 001 | 8728.52 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 049 | 2 |  | 1 | 004 | 698225.65 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 057 | 2 |  | 1 | 917 | 51319.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 062 | 2 |  | 1 | 004 | 135891.29 | 1035.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 065 | 2 |  | 1 | 103 | 367136.55 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4N98 | 42170745201 | 066 | 2 |  | 1 | 019 | 3180 | 3180 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 2 | 019 | 25950.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 066 | 2 |  | 3 | 019 | 89627 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4N98 | 42170745201 | 071 | 2 |  | 1 | 004 | 323503.61 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 1 | 004 | 76630.3 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 2 | 001 | 15446.73 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 | 084 | 2 |  | 3 | 003 | 85830 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 089 | 2 |  | 1 | 919 | 238128.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 1 | 860 | 0 | 0 | 0 |  | C | 119 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4N98 | 42170745201 | 096 | 2 |  | 2 | 118 | 16352 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4N98 | 42170745201 | 096 | 2 |  | 3 | 012 | 126196 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N98 | 42170745201 | 096 | 2 |  | 4 | 105 | 25226.19 | 25226.19 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4N98 | 42170745201 | 097 | 2 |  | 1 | 860 | 34592.78 | 34592.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4P04 | 23193225201 | 010 | 2 |  | 1 | 105 | 76769.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4P04 | 23193225201 | 019 | 2 |  | 1 | 305 | -960.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4P04 | 23193225201 | 021 | 2 |  | 1 | 003 | 279116.67 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4P04 | 23193225201 | 024 | 2 |  | 1 | 122 | 51680 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4P04 | 23193225201 | 034 | 2 |  | 1 | 004 | 2579.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 2 | 004 | 3868.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 3 | 004 | 2579.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 034 | 2 |  | 4 | 004 | 644.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 | 051 | 2 |  | 1 | 350 | 36300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 064 | 2 |  | 1 | 007 | 67639 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4P04 | 23193225201 | 065 | 2 |  | 1 | 007 | 4543 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4P04 | 23193225201 | 077 | 2 |  | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 083 | 2 |  | 1 | 919 | 105078.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4P04 | 23193225201 | 088 | 2 |  | 1 | 001 | 201068.13 | 0 | 0 |  | C | 225 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 2 | 001 | 246776.95 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 3 | 001 | 106851.88 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4P04 | 23193225201 | 088 | 2 |  | 4 | 001 | 99303.04 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q16 | 42170795201 | 019 | 2 |  | 1 | 101 | 23100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4Q16 | 42170795201 | 019 | 2 |  | 2 | 503 | -23742.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 1 | 023 | 19264.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 2 | 023 | 2921.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170795201 | 060 | 2 | 850 | 3 | 503 | 29133.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q35 | 42264135201 | 008 | 2 |  | 1 | 008 | 111519.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 040 | 2 |  | 1 | 007 | 96140.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 044 | 2 |  | 1 | 919 | 98935.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 067 | 2 |  | 1 | 113 | -51691.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 | 077 | 2 |  | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q35 | 42264135201 | 077 | 2 |  | 2 | 502 | 29333.85 | 29333.85 | 4 |  | N | 15 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | E4Q35 | 42264135201 | 077 | 2 |  | 3 | 115 | 80000 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 010 | 2 |  | 1 | 004 | 155870.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 1 | 023 | 16668.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 2 | 023 | 38135.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 3 | 023 | 11492.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 4 | 023 | 59070.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 5 | 023 | -59070.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 6 | 023 | -7227.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 7 | 023 | 7227.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 8 | 023 | 14777.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 9 | 023 | 38837.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 018 | 2 | 850 | 10 | 023 | 30087.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 019 | 2 |  | 1 | 503 | 450075.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 026 | 2 |  | 1 | 305 | -362189.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 031 | 2 |  | 1 | 113 | 1587117.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 1 | 023 | 34410.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 2 | 023 | 44342.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 3 | 023 | 38001.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 4 | 023 | 21406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 034 | 2 | 850 | 5 | 023 | 11839.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 036 | 2 |  | 1 | 305 | -306828.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 038 | 2 |  | 1 | 503 | 132656.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 045 | 2 |  | 1 | 503 | 1384692 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 045 | 2 |  | 2 | 007 | 190992.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 045 | 2 |  | 3 | 503 | 199697.35 | 199697.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 056 | 2 |  | 1 | 919 | 341873.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 059 | 2 |  | 1 | 004 | 223000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 1 | 023 | 5933.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 2 | 023 | 19724.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 3 | 023 | 43582.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 4 | 023 | 38735.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 5 | 023 | 27207.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 060 | 2 | 850 | 6 | 023 | 14816.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 061 | 2 |  | 1 | 007 | 366965.52 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 066 | 2 |  | 1 | 001 | 289695.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 072 | 2 |  | 1 | 119 | 1100007.98 | 75013 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 1 | 023 | 20170.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 2 | 023 | 13403.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 3 | 019 | 9814.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 4 | 023 | 15957.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 5 | 001 | 21979.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 6 | 012 | 9842 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 7 | 001 | 5319.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 8 | 106 | 30515.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 9 | 001 | 14852.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 10 | 023 | 361.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 077 | 2 | 850 | 11 | 503 | 7783.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 079 | 2 |  | 1 | 004 | -796.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 086 | 2 |  | 1 | 021 | 253024.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 087 | 2 |  | 1 | 503 | 1478731.02 | 157636.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 089 | 2 |  | 1 | 012 | 111530.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 090 | 2 |  | 1 | 503 | -280593.96 | 26930.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 093 | 2 |  | 1 | 503 | 509643.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 1 | 023 | 31730.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 2 | 023 | 23189.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 3 | 023 | 39927.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 4 | 023 | -361.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 5 | 023 | 24947.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 094 | 2 | 850 | 6 | 012 | 30565.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 095 | 2 |  | 1 | 004 | 89200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 096 | 2 |  | 1 | 503 | -611125.02 | 84278.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 2 | 503 | 52683.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 3 | 503 | 100808.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 4 | 503 | 37144.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 096 | 2 |  | 5 | 503 | 46304.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 099 | 2 |  | 1 | 503 | -44237 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 1 | 012 | 27013.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 2 | 023 | 38796.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 3 | 023 | 34858.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 4 | 010 | 7565.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4Q64 | 43310855201 | 106 | 2 | 850 | 5 | 012 | 41766.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 1 | 012 | 15812.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 2 | 023 | 63239.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 3 | 024 | 27576.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4Q64 | 43310855201 | 113 | 2 | 850 | 4 | 503 | 15772.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S19 | 43215415201 | 008 | 2 |  | 1 | 923 | 8189.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S21 | 43661715201 | 005 | 2 |  | 1 | 118 | 56590.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4S21 | 43661715201 | 015 | 2 |  | 1 | 115 | 112689.99 | 50384.32 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 | 017 | 2 |  | 1 | 919 | 150098.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 | 019 | 2 |  | 1 | 004 | 16112 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4S21 | 43661715201 | 034 | 2 | 850 | 1 | 001 | 2273.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 | 049 | 2 |  | 1 | 101 | 39305.91 | 15400.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4S21 | 43661715201 | 050 | 2 |  | 1 | 503 | 64487.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S21 | 43661715201 | 058 | 2 |  | 1 | 860 | 1320823.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4S38 | 42684015201 | 009 | 2 |  | 1 | 105 | 2024287.49 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4S38 | 42684015201 | 015 | 2 |  | 1 | 101 | 358.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4S38 | 42684015201 | 032 | 2 |  | 1 | 023 | 83381.7 | 2563.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4S38 | 42684015201 | 044 | 2 |  | 1 | 923 | 37141.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4S85 | 43609615201 | 020 | 2 |  | 1 | 503 | -10712.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S85 | 43609615201 | 024 | 2 |  | 1 | 004 | 33180 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4S85 | 43609615201 | 024 | 2 |  | 2 | 022 | 11435 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T01 | 43630215201 | 012 | 2 |  | 1 | 106 | 48308 | 48308 | 5 |  | C | 30 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T52 | 43784715201 | 016 | 2 |  | 1 | 923 | 7643.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T55 | 43388915201 | 014 | 2 |  | 1 | 119 | 15300.23 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4400 | 22777415201 | 006 | 2 |  | 1 | 305 | -271148.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4400 | 22777415201 | 021 | 2 |  | 1 | 305 | -701395.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4400 | 22777415201 | 040 | 2 |  | 1 | 503 | 141276.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4400 | 22777415201 | 054 | 2 |  | 1 | 015 | 15943.66 | 15943.66 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4400 | 22777415201 | 068 | 2 |  | 1 | 919 | 77677.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4400 | 22777415201 | 084 | 2 |  | 1 | 860 | 76323.89 | 26085.09 | 0 |  | N | 86 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4400 | 22777415201 | 084 | 2 |  | 2 | 860 | 22896.63 | 17028.01 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4400 | 22777415201 | 092 | 2 |  | 1 | 015 | 37480.85 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4400 | 22777415201 | 102 | 2 |  | 1 | 860 | -200000 | 0 | 0 |  | C | 9 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4400 | 22777415201 | 102 | 2 |  | 2 | 860 | 0 | 0 | 3 |  | C | 4 | Avoidable, CEI Consultant | Claim Settlement | Claim Settlement | 10
04 | T4400 | 22777415201 | 102 | 2 |  | 3 | 118 | 0 | 0 | 1 |  | C | 17 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4400 | 22777415201 | 102 | 2 |  | 4 | 860 | 3840.44 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
04 | T4400 | 22777415201 | 102 | 2 |  | 5 | 126 | 11574.3 | 0 | 3 |  | C | 0 | Avoidable, CEI Consultant | Computation Error | Plan Modifications | 2
04 | T4400 | 22777415201 | 102 | 2 |  | 6 | 126 | 128721 | 0 | 3 |  | C | 0 | Avoidable, CEI Consultant | Computation Error | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 1 | 106 | 362.18 | 362.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 3 | 005 | 1035.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4412 | 42873315201 | 017 | 2 | 850 | 4 | 106 | 1937.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 6 | 106 | 6484.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 7 | 122 | 2229.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 8 | 001 | 6872.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4412 | 42873315201 | 017 | 2 | 850 | 9 | 106 | 6591.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 10 | 106 | 4663.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 11 | 106 | 6484.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 | 017 | 2 | 850 | 12 | 108 | 2730 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4412 | 42873315201 | 032 | 2 |  | 1 | 919 | 26103.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4412 | 42873315201 | 048 | 2 |  | 1 | 023 | 2743.43 | 0 | 0 |  | N | 31 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4412 | 42873315201 | 048 | 2 |  | 2 | 003 | 3318.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4412 | 42873315201 | 048 | 2 |  | 3 | 022 | 3805.91 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4412 | 42873315201 | 048 | 2 |  | 4 | 115 | 18129.74 | 18129.74 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4412 | 42873315201 | 048 | 2 |  | 5 | 700 | 5660.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
04 | T4412 | 42873315201 | 053 | 2 |  | 1 | 105 | 4664.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4412 | 42873315201 | 053 | 2 |  | 2 | 126 | 8266.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4418 | 22989615201 | 022 | 2 |  | 1 | 001 | 131337.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 | 046 | 2 |  | 1 | 919 | 16851.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 | 072 | 2 |  | 1 | 126 | 178646 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4418 | 22989615201 | 072 | 2 |  | 2 | 007 | -176040 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4418 | 22989615201 | 072 | 2 |  | 3 | 860 | 11593.28 | 11593.28 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4423 | 23033845201 | 008 | 2 |  | 1 | 007 | 28826.31 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4423 | 23033845201 | 011 | 2 |  | 1 | 101 | 25597.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 1 | 503 | 3586.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 2 | 115 | 7175.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 3 | 115 | 1488.38 | 505.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 4 | 503 | 19932.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 5 | 001 | 1687.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 | 016 | 2 | 850 | 6 | 503 | 2621.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 7 | 107 | 9470.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 8 | 101 | 1925.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 9 | 503 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 10 | 107 | 2080.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 11 | 503 | 5106.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 12 | 503 | 2116.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 13 | 503 | 3540.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 14 | 108 | 44871.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4423 | 23033845201 | 016 | 2 | 850 | 15 | 503 | 395.23 | 395.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 016 | 2 | 850 | 16 | 004 | 30502.97 | 4955.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 023 | 2 |  | 1 | 126 | -472515.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 023 | 2 |  | 3 | 107 | 7822.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 041 | 2 |  | 1 | 107 | 89275.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 1 | 919 | 100340.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 2 | 919 | 15399.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 045 | 2 |  | 3 | 919 | 12587.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 | 057 | 2 | 850 | 1 | 004 | 1998.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 2 | 503 | 1656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 3 | 503 | 15643.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 4 | 503 | 18711.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 5 | 004 | 7497.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 6 | 503 | 2425.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 7 | 003 | 3067.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4423 | 23033845201 | 057 | 2 | 850 | 8 | 503 | 4152.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 | 057 | 2 | 850 | 9 | 101 | 320.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 1 | 103 | 3849.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 2 | 126 | 11834.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 3 | 126 | 72235.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4423 | 23033845201 | 068 | 2 |  | 4 | 126 | 2880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4433 | 42872415201 | 012 | 2 |  | 1 | 107 | 307679.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4433 | 42872415201 | 013 | 2 |  | 1 | 015 | 151854.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4433 | 42872415201 | 014 | 2 |  | 1 | 106 | 174333.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 022 | 2 |  | 1 | 004 | 36151.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4433 | 42872415201 | 026 | 2 |  | 1 | 122 | 50236.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4433 | 42872415201 | 028 | 2 |  | 1 | 919 | 51249.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4433 | 42872415201 | 044 | 2 |  | 1 | 106 | 32217 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 049 | 2 |  | 1 | 003 | 31880.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4433 | 42872415201 | 049 | 2 |  | 2 | 106 | 14616.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 049 | 2 |  | 3 | 101 | 11622.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 050 | 2 |  | 1 | 106 | 31143.44 | 15997.02 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 | 051 | 2 |  | 1 | 101 | 2614.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 067 | 2 |  | 1 | 101 | 86237.54 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 067 | 2 |  | 2 | 101 | 21464.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 1 | 118 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 2 | 024 | 4399.58 | 4399.58 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 3 | 115 | 3355.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4433 | 42872415201 | 104 | 2 |  | 4 | 101 | 641.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4444 | 43270515201 | 010 | 2 |  | 1 | 001 | 397026.5 | 0 | 2 |  | N | 21 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
04 | T4444 | 43270515201 | 018 | 2 |  | 1 | 919 | 29064.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4444 | 43270515201 | 023 | 2 |  | 1 | 118 | 159742.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4444 | 43270515201 | 024 | 2 |  | 1 | 113 | -20599.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4444 | 43270515201 | 025 | 2 |  | 1 | 004 | 1302 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4444 | 43270515201 | 034 | 2 |  | 1 | 003 | 47797.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4444 | 43270515201 | 063 | 2 |  | 1 | 923 | 11186.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4449 | 43466615201 | 018 | 2 |  | 1 | 919 | 27198.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4449 | 43466615201 | 032 | 2 |  | 1 | 107 | 157031.66 | 0 | 2 |  | N | 61 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | T4449 | 43466615201 | 041 | 2 |  | 1 | 101 | -9210.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4449 | 43466615201 | 045 | 2 |  | 1 | 503 | 148044.26 | 0 | 0 |  | N | 57 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4452 | 43166615201 | 011 | 2 |  | 1 | 101 | 3096.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4452 | 43166615201 | 016 | 2 |  | 1 | 919 | 36535.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4452 | 43166615201 | 018 | 2 |  | 1 | 123 | 26168.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4452 | 43166615201 | 029 | 2 |  | 1 | 019 | 51166.08 | 51166.08 | 5 |  | C | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
04 | T4454 | 43427315201 | 017 | 2 |  | 1 | 919 | 35207.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4454 | 43427315201 | 018 | 2 |  | 1 | 004 | 74685 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4454 | 43427315201 | 028 | 2 | 850 | 1 | 101 | 3327.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 028 | 2 | 850 | 2 | 024 | 3376.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 028 | 2 | 850 | 3 | 023 | 22503.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 | 038 | 2 |  | 1 | 128 | -113348.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4454 | 43427315201 | 043 | 2 |  | 1 | 118 | -693 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4465 | 42793815201 | 011 | 2 |  | 1 | 919 | 56207.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4465 | 42793815201 | 016 | 2 |  | 1 | 003 | 59130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 1 | 001 | 1789.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 2 | 325 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | T4467 | 42872815201 | 003 | 2 | 850 | 3 | 115 | 20297.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 003 | 2 | 850 | 4 | 001 | 7615.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 003 | 2 | 850 | 5 | 118 | 7220.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4467 | 42872815201 | 003 | 2 | 850 | 6 | 001 | 21076.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 006 | 2 |  | 1 | 115 | 40000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 008 | 2 | 850 | 1 | 001 | 24549.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 2 | 001 | 9238.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 3 | 115 | 3193.12 | 3193.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 008 | 2 | 850 | 4 | 012 | 5999.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 5 | 010 | 10340 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4467 | 42872815201 | 008 | 2 | 850 | 6 | 012 | 1695.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 008 | 2 | 850 | 7 | 012 | 3155.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4467 | 42872815201 | 014 | 2 |  | 1 | 101 | -12188.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4467 | 42872815201 | 015 | 2 |  | 1 | 115 | 99377.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 015 | 2 |  | 2 | 115 | 4000 | 4000 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 029 | 2 |  | 1 | 001 | 6213.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 030 | 2 |  | 1 | 001 | 3213.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4467 | 42872815201 | 037 | 2 |  | 1 | 115 | 210000 | 0 | 0 |  | N | 150 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4467 | 42872815201 | 050 | 2 |  | 1 | 010 | 1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4470 | 43467915201 | 007 | 2 |  | 1 | 007 | -6176.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 1 | 003 | -11311.7 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 2 | 126 | 85795.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4474 | 43516015201 | 010 | 2 |  | 3 | 007 | -221337.66 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 4 | 007 | -548.96 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 5 | 007 | 836.35 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 6 | 001 | 237589.74 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 7 | 007 | -177217.57 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4474 | 43516015201 | 010 | 2 |  | 8 | 107 | 282.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4474 | 43516015201 | 010 | 2 |  | 9 | 112 | 85912.05 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 7 | 126 | -13048.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 10 | 107 | 7321.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 11 | 112 | 1157.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 023 | 2 |  | 12 | 112 | 3846.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4474 | 43516015201 | 030 | 2 |  | 1 | 007 | 309000 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4478 | 43206645201 | 013 | 2 | 850 | 1 | 106 | 18283.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4480 | 43166515201 | 018 | 2 |  | 1 | 503 | 39300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4481 | 43177025201 | 015 | 2 |  | 1 | 106 | 45057.58 | 5864.36 | 1 |  | N | 24 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 | 022 | 2 | 850 | 1 | 105 | 21790.48 | 6931.48 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 | 022 | 2 | 850 | 2 | 106 | 20138 | 20138 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 | 034 | 2 |  | 1 | 923 | 6128.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 | 034 | 2 |  | 2 | 106 | 2000 | 2000 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 | 034 | 2 |  | 3 | 105 | 19771.04 | 5071 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 | 034 | 2 |  | 4 | 118 | 2860 | 2860 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4482 | 44007915201 | 009 | 2 |  | 1 | 108 | 3031.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4482 | 44007915201 | 009 | 2 |  | 2 | 108 | 7578.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4482 | 44007915201 | 009 | 2 |  | 3 | 101 | 4271.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4482 | 44007915201 | 009 | 2 |  | 4 | 101 | 10678.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4482 | 44007915201 | 014 | 2 |  | 1 | 108 | 3354.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4482 | 44007915201 | 014 | 2 |  | 2 | 108 | 8386.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4482 | 44007915201 | 022 | 2 |  | 1 | 126 | 8273.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4484 | 43169815201 | 015 | 2 |  | 1 | 405 | 58933 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4484 | 43169815201 | 027 | 2 |  | 1 | 007 | 23051 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 008 | 2 |  | 1 | 115 | -93585.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 1 | 106 | 12083.33 | 4247.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 2 | 112 | 28176.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 3 | 106 | 1710.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 4 | 106 | 4241.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 5 | 118 | 255.47 | 255.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 6 | 106 | 1063.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 011 | 2 | 850 | 7 | 503 | 2425.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 1 | 503 | 15042.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 2 | 503 | 8428.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 3 | 503 | 4128.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 4 | 106 | 2392.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 5 | 001 | 1692.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 014 | 2 | 850 | 6 | 118 | 555.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 7 | 503 | 1092.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 8 | 001 | 1524.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 014 | 2 | 850 | 9 | 118 | 9424.53 | 9424.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 014 | 2 | 850 | 10 | 503 | 2185 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 11 | 503 | 603.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 014 | 2 | 850 | 12 | 118 | 2929.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 015 | 2 |  | 1 | 007 | 13006.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 1 | 118 | 1118.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 2 | 503 | 9477.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 017 | 2 | 850 | 3 | 503 | 2185 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 | 017 | 2 | 850 | 4 | 108 | 14102.24 | 14102.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 5 | 007 | 3277.48 | 3277.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 6 | 118 | 4210.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 7 | 115 | 5755.6 | 5755.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 8 | 118 | 1027.9 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 9 | 115 | 992.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 10 | 007 | 3239.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 017 | 2 | 850 | 11 | 115 | 449.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 12 | 106 | 1169.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 017 | 2 | 850 | 13 | 001 | 2993.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 020 | 2 | 850 | 1 | 001 | 2909.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 | 020 | 2 | 850 | 2 | 118 | 2231.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 3 | 118 | 500.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 4 | 112 | 2855.4 | 2855.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 5 | 115 | 17520.51 | 17520.51 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 6 | 101 | 5820.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 7 | 106 | 4881.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 020 | 2 | 850 | 8 | 106 | 4881.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 | 021 | 2 |  | 1 | 118 | 40508.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 023 | 2 |  | 1 | 118 | 52462.28 | 52462.28 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4486 | 43165715201 | 029 | 2 |  | 1 | 007 | 121764.98 | 121764.98 | 1 |  | N | 45 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 | 036 | 2 |  | 1 | 126 | 15124.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | T4490 | 43467415201 | 019 | 2 |  | 1 | 007 | 9090.39 | 9090.39 | 5 |  | N | 4 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4490 | 43467415201 | 020 | 2 |  | 1 | 923 | 5494.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4493 | 43622615201 | 006 | 2 |  | 2 | 101 | 11868.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4515 | 43783515201 | 009 | 2 |  | 1 | 113 | -14.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4515 | 43783515201 | 009 | 2 |  | 2 | 101 | 5522.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4515 | 43783515201 | 017 | 2 |  | 1 | 101 | 15264.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4533 | 43689915201 | 004 | 2 |  | 1 | 128 | 22113.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | E5W11 | 24262635201 | 038 | 2 |  | 1 | 917 | 7889 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | E5W11 | 24262635201 | 039 | 2 |  | 1 | 004 | -5501.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 | 046 | 2 |  | 1 | 001 | 30979.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5W11 | 24262635201 | 046 | 2 |  | 2 | 007 | 127468.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 | 061 | 2 |  | 1 | 919 | 25327.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 | 073 | 2 |  | 1 | 004 | 12915 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 | 082 | 2 |  | 1 | 004 | 2333013.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 | 049 | 2 |  | 1 | 503 | -405567.71 | 0 | 0 |  | N | 96 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W31 | 43360715201 | 052 | 2 |  | 1 | 917 | 18414.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y20 | 42690435201 | 011 | 2 |  | 1 | 919 | 97208.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y20 | 42690435201 | 021 | 2 |  | 1 | 004 | 18140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 031 | 2 |  | 1 | 106 | 54606.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y20 | 42690435201 | 047 | 2 |  | 1 | 003 | 124328.53 | 4877.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 047 | 2 |  | 2 | 105 | 575469.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 | 057 | 2 |  | 1 | 004 | 20475.52 | 6334.81 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 057 | 2 |  | 2 | 003 | 57948.74 | 4812.4 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 | 057 | 2 |  | 3 | 105 | 57211.1 | 0 | 0 |  | N | 91 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 014 | 2 |  | 1 | 001 | 52749.45 | 0 | 0 |  | N | 90 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y33 | 43693715201 | 018 | 2 |  | 1 | 112 | 311017.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 026 | 2 |  | 1 | 112 | 415194.77 | 0 | 0 |  | N | 103 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y33 | 43693715201 | 037 | 2 |  | 1 | 503 | 19504.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y33 | 43693715201 | 037 | 2 |  | 2 | 503 | 368119.52 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y33 | 43693715201 | 037 | 2 |  | 3 | 503 | 197375.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y34 | 43744415201 | 006 | 2 |  | 1 | 860 | -9.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 1 | 105 | 4590 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 2 | 105 | 1144.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 3 | 105 | 23568.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 | 012 | 2 | 850 | 4 | 012 | 6473.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z02 | 43365415201 | 026 | 2 |  | 1 | 005 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | E5Z02 | 43365415201 | 026 | 2 |  | 2 | 130 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
05 | E5Z09 | 41299445214 | 003 | 2 |  | 1 | 018 | 77311.99 | 77311.99 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | E5Z09 | 41299445214 | 003 | 2 |  | 2 | 115 | 26428.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z23 | 43564715201 | 013 | 2 |  | 1 | 503 | 843.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 2 | 503 | -4331.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 3 | 503 | -1449.13 | 1753.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z23 | 43564715201 | 013 | 2 |  | 4 | 503 | -135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z25 | 43685515201 | 006 | 2 |  | 1 | 001 | 8350 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 009 | 2 |  | 1 | 001 | 42152.24 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 014 | 2 |  | 1 | 106 | 30026.4 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 014 | 2 |  | 2 | 107 | 14436.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 | 016 | 2 |  | 1 | 003 | 780.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z25 | 43685515201 | 018 | 2 |  | 1 | 106 | 38052.85 | 9378.86 | 1 |  | N | 13 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z27 | 43733815201 | 009 | 2 |  | 1 | 101 | 6750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z27 | 43733815201 | 016 | 2 |  | 1 | 923 | 19299.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z27 | 43733815201 | 024 | 2 | 850 | 2 | 101 | 13021.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z27 | 43733815201 | 024 | 2 | 850 | 3 | 012 | 7575.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z27 | 43733815201 | 028 | 2 |  | 1 | 503 | 89546.58 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z44 | 43945315201 | 013 | 2 |  | 1 | 105 | 33356.49 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z44 | 43945315201 | 013 | 2 |  | 2 | 108 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z45 | 43733915201 | 010 | 2 |  | 1 | 923 | 18830.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z45 | 43733915201 | 016 | 2 |  | 1 | 113 | 61335.2 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | E5Z52 | 44116715201 | 007 | 2 |  | 1 | 105 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 002 | 2 |  | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | T5469 | 23920345201 | 007 | 2 |  | 1 | 105 | -85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 2 | 105 | 90 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 007 | 2 |  | 3 | 101 | 2532.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345201 | 008 | 2 |  | 1 | 012 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 018 | 2 |  | 1 | 305 | -118789.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 037 | 2 |  | 1 | 305 | -36900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 1 | 015 | -140666.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 050 | 2 |  | 2 | 015 | 140177.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 1 | 015 | 14511.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 2 | 015 | 7737.37 | 7737.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 3 | 015 | 4467.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 4 | 015 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 5 | 015 | 7753.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 6 | 015 | 4425.24 | 4425.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 051 | 2 | 850 | 7 | 015 | -4878.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 053 | 2 |  | 1 | 115 | 4253.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 065 | 2 |  | 1 | 001 | 7824.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 084 | 2 |  | 1 | 001 | 47862.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 1 | 115 | 29323.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 2 | 128 | 4418.68 | 5852.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 3 | 118 | 3512.15 | 3512.15 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 4 | 115 | 1368.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 5 | 012 | 755.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 6 | 115 | 1412.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 7 | 001 | 3427.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 8 | 115 | 4195.68 | 1448.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 9 | 007 | 3053.54 | 3053.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 10 | 003 | 4367.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 11 | 003 | 3359.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 12 | 115 | 4926.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 13 | 003 | 648.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 14 | 115 | 414.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 15 | 105 | 3486.32 | 3941.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 16 | 115 | 3507.28 | 2981.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 17 | 115 | 2745.01 | 6459.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 18 | 115 | 4842.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 19 | 115 | 3329.19 | 3329.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 20 | 107 | 5539 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 21 | 107 | 656.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 22 | 003 | 2491.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 23 | 003 | 2506.76 | 2506.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 24 | 503 | 8499.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 085 | 2 | 850 | 25 | 118 | 8165.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 26 | 003 | 1134.64 | 1246 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 27 | 003 | 8500 | 6052.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 28 | 003 | 11812.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 085 | 2 | 850 | 29 | 118 | 6266.79 | 6266.79 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 30 | 118 | 2859.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 085 | 2 | 850 | 31 | 003 | 6571.65 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 1 | 003 | 7984.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 094 | 2 |  | 2 | 107 | 2621.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 101 | 2 |  | 1 | 107 | 13803.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 105 | 2 |  | 1 | 128 | 18863.98 | 3772.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5469 | 23920345201 | 117 | 2 |  | 1 | 107 | 68509.21 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 118 | 2 |  | 1 | 003 | 63585.28 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 119 | 2 |  | 1 | 917 | 15282.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 121 | 2 |  | 1 | 503 | 308974.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 | 123 | 2 |  | 1 | 106 | 858359.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 124 | 2 |  | 1 | 012 | 5109.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 132 | 2 |  | 1 | 015 | 162028.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 | 133 | 2 |  | 1 | 725 | -78085.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
05 | T5469 | 23920345201 | 134 | 2 |  | 1 | 012 | 97231.95 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 | 135 | 2 |  | 1 | 106 | 8472.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 2 | 115 | 3500 | 3500 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 | 135 | 2 |  | 3 | 003 | 64550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 1 | 003 | 865 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 137 | 2 |  | 2 | 118 | 4609 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5469 | 23920345201 | 138 | 2 |  | 1 | 003 | 71010.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 | 139 | 2 |  | 1 | 105 | 35202 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 | 140 | 2 |  | 1 | 860 | 1485000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5506 | 41840325201 | 002 | 2 |  | 1 | 105 | 43051.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5506 | 41840325201 | 005 | 2 |  | 1 | 106 | 212501.23 | 116078.9 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 009 | 2 |  | 1 | 106 | 0 | 116078.9 | 1 |  | N | 30 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 010 | 2 |  | 1 | 015 | 191075 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 1 | 106 | 10191.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 018 | 2 | 850 | 2 | 015 | 14838.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 3 | 015 | 14233.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 4 | 015 | 28147.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 5 | 015 | 2858.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 6 | 015 | 3269.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 018 | 2 | 850 | 7 | 015 | 1460.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 023 | 2 |  | 1 | 917 | 9403.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 024 | 2 | 850 | 1 | 021 | 1734.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 024 | 2 | 850 | 2 | 503 | 586.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 | 024 | 2 | 850 | 3 | 021 | -1734.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 | 024 | 2 | 850 | 4 | 106 | 16738.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 024 | 2 | 850 | 5 | 023 | 5331.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 024 | 2 | 850 | 6 | 105 | 3754.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5506 | 41840325201 | 025 | 2 | 850 | 1 | 015 | 4872.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 2 | 015 | 8452.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 3 | 015 | 632.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 4 | 015 | 1460.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 5 | 015 | 31818.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 6 | 015 | 13069.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 7 | 015 | -632.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 8 | 015 | 632.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 9 | 015 | -1460.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 025 | 2 | 850 | 10 | 015 | 10970.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 028 | 2 | 850 | 1 | 015 | 9363.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 028 | 2 | 850 | 2 | 106 | 7927.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 028 | 2 | 850 | 3 | 015 | 10572.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 028 | 2 | 850 | 4 | 106 | 817.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 | 028 | 2 | 850 | 5 | 015 | 10662.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 028 | 2 | 850 | 6 | 015 | 4049.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 029 | 2 |  | 1 | 015 | 151031.29 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 030 | 2 |  | 1 | 015 | 39245.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 043 | 2 |  | 1 | 919 | 57416.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 049 | 2 |  | 1 | 001 | 61486.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5506 | 41840325201 | 049 | 2 |  | 2 | 503 | 77604.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 | 049 | 2 |  | 3 | 403 | -19902.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
05 | T5506 | 41840325201 | 058 | 2 |  | 1 | 015 | 127784.82 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 062 | 2 |  | 1 | 015 | 1235.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 073 | 2 |  | 1 | 015 | 31554.61 | 22020.21 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 | 074 | 2 |  | 1 | 860 | 114786.17 | 0 | 0 |  | N | 97 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5569 | 43442615201 | 005 | 2 |  | 1 | 113 | -8171.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5569 | 43442615201 | 005 | 2 |  | 2 | 010 | 112213.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5569 | 43442615201 | 009 | 2 |  | 1 | 919 | 116032.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5572 | 43505615201 | 007 | 2 |  | 1 | 004 | 19031.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5591 | 42823815201 | 031 | 2 |  | 1 | 503 | 132028.9 | 132028.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5591 | 42823815201 | 031 | 2 |  | 2 | 012 | 16790.52 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5591 | 42823815201 | 031 | 2 |  | 3 | 115 | 11239.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 4 | 122 | 32390.38 | 32390.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 5 | 115 | 24542.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 6 | 023 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 7 | 503 | 5590.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5591 | 42823815201 | 031 | 2 |  | 8 | 101 | 3077.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5591 | 42823815201 | 031 | 2 |  | 9 | 010 | 34199.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5591 | 42823815201 | 031 | 2 |  | 10 | 115 | 17034.41 | 17034.41 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43565815201 | 004 | 2 |  | 1 | 107 | 23208.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5601 | 43565815201 | 011 | 2 |  | 1 | 012 | 13095.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43565815201 | 015 | 2 |  | 1 | 012 | 44000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43565815201 | 021 | 2 |  | 1 | 115 | 61010.4 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5606 | 43803815201 | 002 | 2 |  | 1 | 004 | 26190 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5606 | 43803815201 | 003 | 2 |  | 1 | 113 | -27812.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5606 | 43803815201 | 006 | 2 |  | 1 | 113 | -11579.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5606 | 43803815201 | 010 | 2 |  | 1 | 503 | -72472 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5606 | 43803815201 | 015 | 2 |  | 1 | 001 | 304000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5606 | 43803815201 | 016 | 2 |  | 1 | 112 | 180634.35 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5606 | 43803815201 | 023 | 2 |  | 1 | 105 | 192.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5606 | 43803815201 | 023 | 2 |  | 2 | 128 | 16958.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5606 | 43803815201 | 026 | 2 |  | 1 | 128 | -89714.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5606 | 43803815201 | 029 | 2 |  | 1 | 923 | 4688.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5606 | 43803815201 | 036 | 2 |  | 1 | 004 | 105000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5616 | 43065515201 | 006 | 2 |  | 1 | 003 | -14065.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5616 | 43065515201 | 026 | 2 |  | 1 | 502 | 12412.65 | 2422 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 | 002 | 2 |  | 1 | 106 | 18234.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 | 012 | 2 |  | 1 | 860 | 8171.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5619 | 24099275201 | 009 | 2 |  | 1 | 115 | -1091.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 | 011 | 2 |  | 1 | 003 | 21286.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099275201 | 022 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5621 | 43623715201 | 005 | 2 |  | 1 | 503 | -128.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5621 | 43623715201 | 012 | 2 |  | 1 | 007 | 5836.96 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5621 | 43623715201 | 012 | 2 |  | 2 | 101 | 6559.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5621 | 43623715201 | 012 | 2 |  | 4 | 106 | -6227.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5621 | 43623715201 | 012 | 2 |  | 5 | 106 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5621 | 43623715201 | 013 | 2 |  | 1 | 923 | 3756.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5623 | 43239915201 | 010 | 2 |  | 1 | 012 | 7254.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5623 | 43239915201 | 010 | 2 |  | 2 | 122 | 2443.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5623 | 43239915201 | 010 | 2 |  | 3 | 503 | -9272.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5635 | 43733015202 | 008 | 2 | 850 | 1 | 115 | 2606.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5635 | 43733015202 | 008 | 2 | 850 | 2 | 009 | 5337.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
05 | T5641 | 44055775201 | 011 | 2 |  | 1 | 923 | 136627.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | T5641 | 44055775201 | 018 | 2 | 850 | 1 | 003 | 27682 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5641 | 44055775201 | 018 | 2 | 850 | 2 | 503 | 11856.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5641 | 44055775201 | 021 | 2 | 850 | 1 | 106 | 5153.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5641 | 44055775201 | 021 | 2 | 850 | 2 | 503 | 1425 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5641 | 44055775201 | 026 | 2 |  | 1 | 012 | 150904.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
05 | T5646 | 43988715201 | 005 | 2 |  | 2 | 112 | 0 | 0 | 2 |  | N | 88 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5647 | 44106615201 | 003 | 2 |  | 1 | 101 | 7470 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5647 | 44106615201 | 004 | 2 |  | 1 | 923 | 5539.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5647 | 44106615201 | 020 | 2 |  | 1 | 126 | 1738 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | E6J52 | 43337815201 | 018 | 2 |  | 1 | 919 | 67061.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
06 | E6J69 | 43492215201 | 022 | 2 |  | 1 | 919 | 350222.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
06 | E6J69 | 43492215201 | 024 | 2 |  | 1 | 007 | 765311 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 1 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 2 | 022 | 47165.56 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 033 | 2 | 850 | 3 | 022 | 23582.78 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 | 041 | 2 | 850 | 1 | 003 | 58696.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 042 | 2 |  | 1 | 503 | 202835.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J69 | 43492215201 | 043 | 2 |  | 1 | 012 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 | 043 | 2 |  | 2 | 003 | 59611.68 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 | 046 | 2 |  | 1 | 503 | 69191.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K58 | 43081315201 | 011 | 2 |  | 1 | 923 | 1618.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 011 | 2 |  | 1 | 503 | 132107.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 016 | 2 |  | 1 | 919 | 101999.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 026 | 2 |  | 1 | 001 | 108531.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 027 | 2 |  | 1 | 001 | 96922.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 1 | 503 | 2628.98 | 2628.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 2 | 106 | 18274.76 | 18274.76 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 3 | 001 | 5096.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 4 | 001 | 6472.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 5 | 106 | 10476.52 | 10476.52 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 6 | 903 | -2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 7 | 903 | 1482.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K59 | 41831225201 | 028 | 2 | 850 | 8 | 004 | 51700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 1 | 503 | 45923.49 | 45923.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 2 | 503 | 24333.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 3 | 503 | 2628.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 4 | 503 | 11861.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 032 | 2 | 850 | 5 | 503 | 5012.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 035 | 2 |  | 1 | 105 | 148644.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | E6K59 | 41831225201 | 035 | 2 |  | 2 | 503 | -11623.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 1 | 503 | 5614.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 2 | 118 | 17005.68 | 17005.68 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 036 | 2 | 850 | 3 | 118 | 70879.02 | 70879.02 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 1 | 118 | 3896.81 | 3896.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 2 | 503 | 1750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 3 | 503 | 17040.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 | 038 | 2 | 850 | 4 | 115 | 12183.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 | 039 | 2 |  | 1 | 503 | 111333 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K89 | 43653615201 | 001 | 2 |  | 1 | 503 | 24000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 010 | 2 | 850 | 1 | 503 | 9455.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 010 | 2 | 850 | 2 | 503 | 5296.5 | 5296.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 012 | 2 |  | 1 | 923 | 17744.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 | 016 | 2 |  | 1 | 115 | 75469.28 | 9012.21 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | E6L51 | 43029129201 | 010 | 2 | 850 | 1 | 503 | 34909.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L51 | 43029129201 | 010 | 2 | 850 | 2 | 503 | 2498.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 015 | 2 |  | 1 | 015 | 30556.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 015 | 2 |  | 2 | 015 | 17120.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 015 | 2 |  | 3 | 115 | 14129.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 1 | 106 | 19746.84 | 19746.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 2 | 503 | 19943.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 016 | 2 | 850 | 3 | 107 | 7912.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 4 | 101 | 74925.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 5 | 106 | 8693.81 | 8693.81 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 016 | 2 | 850 | 6 | 503 | 8359.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 017 | 2 |  | 1 | 503 | 49204.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 017 | 2 |  | 2 | 106 | 53003.95 | 53003.95 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 017 | 2 |  | 3 | 115 | 17155.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 022 | 2 |  | 1 | 108 | 6057.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 | 022 | 2 |  | 2 | 503 | 3904.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 022 | 2 |  | 3 | 001 | 3905.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 035 | 2 | 850 | 1 | 015 | 1032.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 035 | 2 | 850 | 2 | 015 | 43743.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 039 | 2 |  | 1 | 919 | 30510.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 045 | 2 |  | 1 | 503 | 190324.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 047 | 2 |  | 1 | 015 | 63756.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 049 | 2 |  | 1 | 015 | 339873.87 | 0 | 0 |  | C | 75 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 051 | 2 |  | 1 | 115 | 160126.13 | 115639.22 | 1 |  | C | 44 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 052 | 2 |  | 1 | 503 | 110000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 054 | 2 | 850 | 1 | 503 | 20627.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 054 | 2 | 850 | 2 | 115 | 15287.83 | 15287.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 3 | 115 | 4985.78 | 4985.78 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 4 | 003 | 8741.56 | 8741.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 5 | 115 | 17993.07 | 17993.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 6 | 115 | 3463.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 7 | 115 | 2781.84 | 2781.84 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 8 | 003 | 3130.27 | 3130.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 9 | 108 | 2552.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 10 | 015 | 14640 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 054 | 2 | 850 | 11 | 115 | 10122.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 12 | 115 | -10122.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 13 | 115 | 10122.13 | 10122.13 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 14 | 115 | -31561.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 15 | 115 | 33108.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 054 | 2 | 850 | 16 | 115 | 31561.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 055 | 2 | 850 | 1 | 001 | 7752.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 055 | 2 | 850 | 2 | 503 | 1974.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 055 | 2 | 850 | 3 | 115 | 2115.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 1 | 101 | 17729.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 2 | 503 | 30451.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 3 | 503 | 3367.05 | 3367.05 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 4 | 503 | 11969.64 | 11969.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 5 | 101 | 668.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 6 | 122 | 3864.9 | 3864.9 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 7 | 115 | 1278.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 10 | 106 | 3842.37 | 3842.37 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6337 | 41809115201 | 056 | 2 | 850 | 11 | 503 | 24046.83 | 24046.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 13 | 003 | 6004.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 056 | 2 | 850 | 14 | 503 | 5703.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 15 | 503 | 966.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 16 | 503 | 2468.83 | 2468.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 17 | 503 | 12940.11 | 7397.55 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 056 | 2 | 850 | 18 | 003 | 12682.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 1 | 015 | 12902.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 2 | 015 | 2084.29 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 070 | 2 |  | 3 | 503 | 12701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 1 | 503 | 4886.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 2 | 001 | 1396.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 | 072 | 2 | 850 | 3 | 503 | 5057.2 | 5057.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 4 | 107 | 2774.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 072 | 2 | 850 | 5 | 503 | 642.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 6 | 503 | 6575.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 7 | 503 | 29389.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 8 | 503 | 5962.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 072 | 2 | 850 | 9 | 009 | 13901.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6337 | 41809115201 | 073 | 2 | 850 | 1 | 115 | 11915 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 | 074 | 2 |  | 1 | 015 | 565313.05 | 422827.05 | 1 |  | N | 12 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 076 | 2 |  | 1 | 015 | 59055.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 | 077 | 2 | 850 | 1 | 118 | 2487.31 | 2487.31 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6337 | 41809115201 | 077 | 2 | 850 | 2 | 503 | 3980.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 077 | 2 | 850 | 3 | 503 | 5349.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 078 | 2 |  | 1 | 015 | 13390.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 019 | 2 |  | 1 | 015 | 118644.76 | 0 | 0 |  | N | 42 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 019 | 2 |  | 2 | 015 | 330801.43 | 0 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 1 | 503 | 7900.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 023 | 2 | 850 | 2 | 106 | 9096.47 | 9096.47 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 3 | 106 | 16585.16 | 16585.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 4 | 115 | 4709.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 023 | 2 | 850 | 5 | 003 | 5271.49 | 5271.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 6 | 003 | 5271.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 7 | 003 | -5271.49 | -5271.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 8 | 001 | 23589.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 9 | 001 | 13047.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 023 | 2 | 850 | 10 | 001 | 4765.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 028 | 2 |  | 1 | 015 | 128232.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 029 | 2 |  | 1 | 503 | 234906.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 033 | 2 |  | 1 | 919 | 37096.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 040 | 2 |  | 1 | 015 | 45962.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 1 | 115 | 40460.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 043 | 2 | 850 | 2 | 001 | 13851.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 3 | 001 | 3765.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 4 | 503 | 15279.65 | 15279.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 5 | 503 | 8152.36 | 8152.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 6 | 503 | 4344.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 7 | 503 | 6224.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 043 | 2 | 850 | 8 | 001 | 4318.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 043 | 2 | 850 | 9 | 115 | 14226.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 050 | 2 |  | 1 | 015 | 331264.21 | 331264.21 | 5 |  | C | 81 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 | 060 | 2 | 850 | 1 | 108 | 408.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 2 | 503 | 9616.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 3 | 107 | 715.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 4 | 001 | 1649.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 | 060 | 2 | 850 | 5 | 003 | 13289.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 060 | 2 | 850 | 6 | 503 | 5116.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 7 | 503 | 5260.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 8 | 503 | 16264.11 | 6561.74 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 9 | 503 | 3509.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 10 | 503 | 1443.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 060 | 2 | 850 | 11 | 122 | 2316.11 | 2316.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 12 | 115 | 3450.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 13 | 115 | 871.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 14 | 115 | 12435.47 | 12435.47 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 060 | 2 | 850 | 15 | 503 | 2967.01 | 2967.01 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 064 | 2 |  | 1 | 503 | 4198.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 064 | 2 |  | 2 | 007 | 6671.59 | 1350.66 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6338 | 41463315201 | 064 | 2 |  | 3 | 122 | 13854.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 4 | 024 | 8311.62 | 8311.62 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 5 | 007 | 5844.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6338 | 41463315201 | 064 | 2 |  | 6 | 122 | 2024.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6338 | 41463315201 | 064 | 2 |  | 7 | 503 | -15606.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 064 | 2 |  | 8 | 001 | 12112.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 005 | 2 |  | 1 | 101 | 98804.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 006 | 2 |  | 1 | 101 | 3879.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 025 | 2 |  | 1 | 101 | 5135.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6344 | 24994145201 | 030 | 2 |  | 1 | 107 | 124618.46 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 1 | 115 | 15978.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 2 | 004 | -6712.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 | 037 | 2 | 850 | 3 | 106 | 7487.7 | 7487.7 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 | 037 | 2 | 850 | 4 | 503 | 10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 037 | 2 | 850 | 5 | 503 | -10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 038 | 2 |  | 1 | 103 | 300000 | 300000 | 1 |  | C | 26 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 1 | 007 | 7664.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 2 | 004 | -14085.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 3 | 503 | 9900.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 4 | 003 | 1694.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 5 | 503 | 9810.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 6 | 115 | 2466.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 7 | 118 | 3125.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 8 | 503 | 6956.25 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 9 | 112 | 6982.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 24994145201 | 043 | 2 | 850 | 10 | 001 | 10200.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 11 | 001 | 21465.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 12 | 503 | 6956.25 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 043 | 2 | 850 | 13 | 001 | 26438.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 | 043 | 2 | 850 | 14 | 503 | -6956.25 | 6956.25 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 044 | 2 | 850 | 1 | 503 | 10455.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 | 044 | 2 | 850 | 2 | 106 | 1111.38 | 1111.38 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 | 044 | 2 | 850 | 3 | 012 | 5187.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6344 | 24994145201 | 052 | 2 | 850 | 1 | 012 | 13428.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6382 | 40561535201 | 009 | 2 |  | 1 | 101 | 53086 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 009 | 2 |  | 2 | 101 | 12768.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 019 | 2 |  | 1 | 919 | 79756.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 1 | 007 | 60790 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 2 | 118 | 3740.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 3 | 118 | 8966.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535201 | 020 | 2 | 850 | 4 | 004 | 39929.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 5 | 001 | 2130.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 6 | 001 | 7757.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 7 | 001 | 4355.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 8 | 004 | 6049.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 020 | 2 | 850 | 9 | 003 | 16281.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 027 | 2 |  | 1 | 305 | -514052 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 031 | 2 | 850 | 1 | 003 | 8941.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6382 | 40561535201 | 031 | 2 | 850 | 2 | 112 | 37957.83 | 2952.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6382 | 40561535201 | 031 | 2 | 850 | 3 | 112 | 1159.07 | 1159.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6382 | 40561535201 | 031 | 2 | 850 | 4 | 004 | 859.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 | 034 | 2 |  | 1 | 503 | 246786.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561535201 | 039 | 2 |  | 1 | 101 | 68105.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6382 | 40561535201 | 042 | 2 |  | 1 | 001 | 130000 | 130000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 1 | 001 | 75198.42 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 2 | 015 | 46947.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6401 | 41247395201 | 008 | 2 |  | 3 | 101 | 5581.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6401 | 41247395201 | 008 | 2 |  | 4 | 103 | 21097.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 011 | 2 |  | 1 | 919 | 47416.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 1 | 001 | 30840.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 2 | 115 | 5055 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 3 | 103 | 4060.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6401 | 41247395201 | 012 | 2 | 850 | 4 | 012 | 2608.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6401 | 41247395201 | 012 | 2 | 850 | 5 | 118 | 7435.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 1 | 118 | 7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 2 | 503 | 32700 | 32700 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 014 | 2 | 850 | 3 | 118 | -7311.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 4 | 118 | 7311.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 014 | 2 | 850 | 5 | 503 | 8987.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 016 | 2 |  | 1 | 001 | 143032.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 019 | 2 |  | 1 | 001 | 105307.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 020 | 2 |  | 1 | 005 | 134857.01 | 134857.01 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 024 | 2 |  | 1 | 001 | 22284.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 024 | 2 |  | 2 | 115 | 67637.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 024 | 2 |  | 3 | 503 | 30856.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6401 | 41247395201 | 024 | 2 |  | 4 | 005 | 8035.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 026 | 2 |  | 1 | 005 | 277982.41 | 277982.41 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 027 | 2 |  | 1 | 001 | 13500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 027 | 2 |  | 2 | 007 | 198705 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 1 | 919 | 87170.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 | 031 | 2 |  | 2 | 005 | 40374.14 | 40374.14 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 032 | 2 |  | 1 | 005 | 24196.79 | 24196.79 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 033 | 2 |  | 1 | 001 | 59302.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 033 | 2 |  | 2 | 115 | 1461.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 033 | 2 |  | 3 | 005 | 5320.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 034 | 2 |  | 1 | 018 | 62435.91 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | T6401 | 41247395201 | 035 | 2 |  | 1 | 115 | 97151.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6401 | 41247395201 | 036 | 2 |  | 1 | 001 | 6366.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395201 | 036 | 2 |  | 2 | 005 | 92994.54 | 92994.54 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 3 | 023 | 16568.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6401 | 41247395201 | 036 | 2 |  | 4 | 115 | 238476 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6403 | 43348915201 | 015 | 2 |  | 1 | 001 | 21903 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 | 015 | 2 |  | 1 | 101 | 3440 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6406 | 42902215201 | 019 | 2 | 850 | 1 | 503 | 12484.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6419 | 42827825201 | 009 | 2 |  | 1 | 503 | 80246.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6436 | 43631115201 | 013 | 2 |  | 1 | 103 | 92453.79 | 31947.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6438 | 43117015201 | 007 | 2 |  | 1 | 001 | 2862.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 007 | 2 |  | 2 | 001 | 3736.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 007 | 2 |  | 3 | 503 | 38500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 007 | 2 |  | 4 | 503 | 16102.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 007 | 2 |  | 5 | 001 | 29344.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 1 | 001 | 3414.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 2 | 001 | 4469.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 4 | 001 | 4493.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 5 | 001 | 2174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 6 | 001 | 3692.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 7 | 001 | 4049.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 8 | 001 | 7352.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 9 | 001 | 6065.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 10 | 503 | 14320.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 | 008 | 2 |  | 11 | 009 | 1458.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 12 | 001 | 2644.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 13 | 005 | 16210.58 | 16210.58 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6438 | 43117015201 | 008 | 2 |  | 14 | 001 | 6228.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6438 | 43117015201 | 008 | 2 |  | 15 | 115 | 10190.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6444 | 43640415201 | 013 | 2 |  | 1 | 923 | 5290.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6445 | 42611315201 | 015 | 2 |  | 1 | 923 | 3956.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6455 | 43791715201 | 010 | 2 |  | 1 | 923 | 922.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6458 | 44019115201 | 011 | 2 |  | 1 | 503 | 77816.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6458 | 44019115201 | 018 | 2 |  | 1 | 503 | 12017.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 1 | 350 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 2 | 005 | 18713.22 | 18713.22 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 8 | 001 | 14244.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 9 | 113 | 14026.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 14 | 126 | 1349.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 16 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 006 | 2 | 850 | 17 | 007 | 58766.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 014 | 2 |  | 1 | 012 | 594363.95 | 594363.95 | 5 |  | N | 48 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 1 | 503 | 44154 | 44154 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7H90 | 25693125201 | 028 | 2 |  | 2 | 001 | 4205.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 3 | 001 | 790.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 4 | 113 | 174768.35 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7H90 | 25693125201 | 028 | 2 |  | 5 | 003 | -245320.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 6 | 004 | 89787.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 7 | 004 | -114716.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 028 | 2 |  | 8 | 007 | 593095.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 3 | 007 | 7356.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 4 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 5 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 6 | 122 | 50825.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 032 | 2 | 850 | 7 | 004 | 75318.55 | 75318.55 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 | 045 | 2 |  | 1 | 001 | 7848.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 045 | 2 |  | 2 | 128 | 32697.5 | 32697.5 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 | 055 | 2 |  | 1 | 003 | 284434.96 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 055 | 2 |  | 2 | 003 | 101651.94 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 2 | 122 | 123363.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 3 | 001 | 5283.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 060 | 2 | 850 | 4 | 122 | 18053.01 | 1572.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 062 | 2 | 850 | 1 | 122 | 687.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 062 | 2 | 850 | 2 | 118 | 5337.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7H90 | 25693125201 | 064 | 2 |  | 1 | 001 | 1581.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 2 | 001 | 1392.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 3 | 917 | 14304.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7H90 | 25693125201 | 064 | 2 |  | 4 | 122 | 21584.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 | 074 | 2 |  | 1 | 118 | 77797.15 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7H90 | 25693125201 | 074 | 2 |  | 4 | 106 | 10430.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7H90 | 25693125201 | 086 | 2 |  | 1 | 919 | 85510.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7H90 | 25693125201 | 087 | 2 |  | 1 | 105 | 7994.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K19 | 43476515201 | 002 | 2 |  | 1 | 003 | 22750000 | 0 | 0 |  | N | 313 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K19 | 43476515201 | 010 | 2 |  | 1 | 113 | 379220.64 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | E7K19 | 43476515201 | 014 | 2 |  | 1 | 007 | 103456 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 017 | 2 |  | 1 | 503 | 242505.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 025 | 2 |  | 1 | 919 | 203686.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 036 | 2 | 850 | 1 | 503 | 59458.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 036 | 2 | 850 | 2 | 503 | 60541.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 038 | 2 |  | 1 | 503 | -318434.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 043 | 2 |  | 1 | 503 | 646286.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 1 | 018 | 66991.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 2 | 007 | 17366.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 3 | 018 | 18842.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 4 | 503 | 16028.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 048 | 2 | 850 | 5 | 503 | 770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 1 | 503 | 19483.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 2 | 007 | 3956.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 3 | 018 | 5654.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K19 | 43476515201 | 052 | 2 | 850 | 4 | 012 | 90904.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K19 | 43476515201 | 054 | 2 | 850 | 1 | 503 | 58191.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 | 063 | 2 |  | 1 | 018 | 16720.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 1 | 023 | 736.78 | 736.78 | 5 |  | N | 0 | Avoidable, Third Party | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 2 | 021 | 8384.71 | 8384.71 | 5 |  | N | 0 | Avoidable, Third Party | Special Events or Excessive Traffic | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 3 | 007 | 14157.34 | 14157.34 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 4 | 122 | 4536.2 | 4536.2 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 5 | 024 | 852.11 | 852.11 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 6 | 024 | 2856.67 | 2856.67 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 7 | 004 | 4041.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 8 | 012 | 11795.05 | 4259.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 9 | 024 | 1200.72 | 1200.72 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 10 | 105 | 11174.47 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 11 | 012 | 2363.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 13 | 503 | 28363.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 14 | 131 | 5627.06 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 15 | 007 | 5716.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 16 | 004 | 5654.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 17 | 122 | 9919.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K24 | 41101145201 | 012 | 2 | 850 | 18 | 004 | 2618.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 014 | 2 |  | 1 | 503 | 275627.95 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 015 | 2 |  | 1 | 003 | 86679.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K24 | 41101145201 | 016 | 2 |  | 1 | 004 | 72079.03 | 72079.03 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 1 | 503 | 11051.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 2 | 023 | 3126.49 | 3126.49 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 3 | 021 | 938.79 | 938.79 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 022 | 2 | 850 | 4 | 004 | 14883.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 023 | 2 |  | 1 | 015 | 65907.47 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | E7K24 | 41101145201 | 027 | 2 |  | 1 | 004 | 27090.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 1 | 021 | 14269.63 | 14269.63 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 2 | 012 | 6481.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 028 | 2 | 850 | 3 | 503 | 9248.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 035 | 2 |  | 1 | 004 | 322004.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 036 | 2 |  | 2 | 101 | 51802.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 2 | 004 | 6977.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 3 | 008 | 55167.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
07 | E7K24 | 41101145201 | 038 | 2 | 850 | 6 | 107 | 2591.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7K24 | 41101145201 | 039 | 2 | 850 | 1 | 503 | 30000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 1 | 503 | 31920.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 2 | 012 | 4637.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 3 | 131 | 5627.06 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 4 | 503 | 38694.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 042 | 2 | 850 | 5 | 012 | 11760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 044 | 2 |  | 1 | 919 | 327968.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7K24 | 41101145201 | 049 | 2 |  | 1 | 503 | 64689.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 059 | 2 |  | 1 | 004 | 160331.5 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 | 066 | 2 |  | 1 | 503 | 44144.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 075 | 2 |  | 1 | 503 | 15544.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 | 076 | 2 |  | 1 | 001 | 14858.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 002 | 2 |  | 1 | 001 | 318367.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 011 | 2 |  | 1 | 001 | 35650.27 | 35650.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 | 012 | 2 |  | 1 | 003 | 16147.9 | 16147.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 1 | 503 | 15055.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 2 | 101 | 836 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 3 | 115 | 6134.96 | 742.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 5 | 503 | 1936.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 6 | 503 | 2047.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 7 | 503 | 24254.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 8 | 503 | 13714.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 10 | 503 | 22226.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 016 | 2 | 850 | 12 | 503 | 13795.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 | 021 | 2 |  | 1 | 115 | 124417.08 | 3609.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 | 025 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 026 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 027 | 2 |  | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L26 | 40552525201 | 029 | 2 |  | 1 | 003 | 396759.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 030 | 2 |  | 1 | 919 | 147479.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L26 | 40552525201 | 045 | 2 | 850 | 1 | 503 | 124077.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L58 | 43243415201 | 005 | 2 |  | 1 | 012 | 88378.63 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 2 | 105 | 3660.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 3 | 012 | 15290.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 4 | 012 | 4306.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 5 | 001 | 15518.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 6 | 105 | 3108.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L58 | 43243415201 | 005 | 2 |  | 7 | 003 | 12716.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 8 | 012 | 333.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 9 | 012 | 61531.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 10 | 003 | 24948.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7L58 | 43243415201 | 005 | 2 |  | 11 | 012 | 2608.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M00 | 42292945201 | 006 | 2 |  | 1 | 103 | 147052.15 | 0 | 1 |  | N | 12 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 1 | 103 | 17713.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 2 | 106 | 2632.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 3 | 003 | 19444.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7M00 | 42292945201 | 008 | 2 | 850 | 4 | 001 | 657.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M05 | 43954615201 | 008 | 2 |  | 1 | 012 | 3910.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M25 | 43386415201 | 007 | 2 |  | 1 | 923 | 20900.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M27 | 43648015201 | 002 | 2 |  | 1 | 115 | 17309.8 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | E7M27 | 43648015201 | 008 | 2 |  | 1 | 001 | 90236.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M33 | 43764915201 | 012 | 2 |  | 1 | 007 | 16043.55 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M33 | 43764915201 | 012 | 2 |  | 2 | 115 | 3874.93 | 3874.93 | 2 |  | N | 3 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | E7M33 | 43764915201 | 012 | 2 |  | 3 | 115 | 3506.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7M36 | 43648815201 | 001 | 2 |  | 1 | 101 | 1782 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7R60 | 43920615201 | 020 | 2 | 850 | 1 | 850 | 100000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7R60 | 43920615201 | 025 | 2 |  | 1 | 010 | 54492.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7389 | 43272015201 | 001 | 2 |  | 1 | 015 | -1034.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7389 | 43272015201 | 006 | 2 |  | 1 | 101 | 51809.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7389 | 43272015201 | 007 | 2 |  | 1 | 850 | 46698 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7389 | 43272015201 | 008 | 2 |  | 1 | 850 | 129888 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7389 | 43272015201 | 024 | 2 |  | 2 | 107 | 17100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 | 026 | 2 |  | 1 | 007 | 549567.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 027 | 2 |  | 1 | 919 | 89783.7 | 89783.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 036 | 2 |  | 1 | 305 | -84321.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 040 | 2 |  | 1 | 106 | 1815 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 | 040 | 2 |  | 2 | 106 | 2774.79 | 2774.79 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 | 040 | 2 |  | 3 | 007 | 1725.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7389 | 43272015201 | 040 | 2 |  | 4 | 208 | 883.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015201 | 041 | 2 |  | 1 | 113 | 2470.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7391 | 43269815201 | 010 | 2 |  | 1 | 012 | 18351.56 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7401 | 43480615201 | 011 | 2 |  | 1 | 012 | 6728.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7430 | 42907525201 | 011 | 2 |  | 1 | 115 | 11396.94 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7430 | 42907525201 | 011 | 2 |  | 2 | 005 | 2830.01 | 2830.01 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7430 | 42907525201 | 011 | 2 |  | 3 | 001 | 7291.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7430 | 42907525201 | 011 | 2 |  | 4 | 005 | 826.34 | 826.34 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
08 | E8N19 | 42935015201 | 001 | 2 |  | 1 | 503 | -350000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 002 | 2 |  | 1 | 004 | 106869.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 | 024 | 2 |  | 1 | 003 | 29393.56 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 | 039 | 2 |  | 1 | 503 | 97747.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 009 | 2 |  | 1 | 123 | 148940 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8N92 | 42337225201 | 016 | 2 |  | 1 | 305 | -51439.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8N92 | 42337225201 | 020 | 2 |  | 1 | 105 | 582970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 | 020 | 2 |  | 2 | 503 | -898953.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 1 | 021 | 8108.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 2 | 021 | 10547.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 3 | 023 | 820.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 4 | 021 | 15787.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 5 | 023 | 7782.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 6 | 021 | 3422.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 7 | 023 | 5051.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 8 | 021 | 12350.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 9 | 023 | 8561.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 10 | 503 | 53245.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 11 | 023 | -1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 12 | 108 | 2178 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 13 | 021 | 15257.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 14 | 023 | 3123.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N92 | 42337225201 | 023 | 2 | 850 | 15 | 108 | 5082 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N92 | 42337225201 | 026 | 2 |  | 1 | 108 | 286049.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N92 | 42337225201 | 027 | 2 |  | 1 | 118 | 554997.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N92 | 42337225201 | 039 | 2 |  | 1 | 503 | -260053.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 1 | 023 | 15674.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 2 | 021 | 4690.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 3 | 023 | 6654.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 4 | 021 | 5988.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 5 | 023 | 7295.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 6 | 012 | 3776.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 7 | 012 | 4463.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 8 | 021 | 10863.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 9 | 023 | 8906.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 10 | 021 | 9579.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 11 | 023 | 7052.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 12 | 021 | 5803.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 13 | 023 | 3117.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 14 | 012 | 4838.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 15 | 021 | 5449.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 16 | 001 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 17 | 503 | 5282.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 18 | 023 | 7136.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 19 | 021 | 20959.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 20 | 012 | 5098.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 049 | 2 | 850 | 21 | 021 | 768.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 050 | 2 |  | 1 | 919 | 130614.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 055 | 2 |  | 1 | 305 | -942.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 | 056 | 2 |  | 1 | 009 | 81617.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N92 | 42337225201 | 060 | 2 |  | 1 | 009 | 67117.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N92 | 42337225201 | 064 | 2 |  | 1 | 001 | 74952.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N92 | 42337225201 | 067 | 2 |  | 1 | 860 | 2600000 | 0 | 0 |  | N | 398 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8N92 | 42337225201 | 087 | 2 | 850 | 1 | 021 | 1574.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8N92 | 42337225201 | 087 | 2 | 850 | 2 | 023 | 803 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8N92 | 42337225201 | 087 | 2 | 850 | 3 | 503 | 3332.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 087 | 2 | 850 | 4 | 021 | 10408.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 087 | 2 | 850 | 5 | 023 | 1733.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 096 | 2 |  | 1 | 923 | 15610.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 098 | 2 |  | 1 | 503 | 66225.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 1 | 023 | 8927.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 2 | 023 | 1963.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P81 | 43561415201 | 012 | 2 | 850 | 3 | 126 | 6144.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8P89 | 43546215201 | 014 | 2 |  | 1 | 919 | 49021.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8P89 | 43546215201 | 015 | 2 |  | 1 | 919 | 85035.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8P89 | 43546215201 | 016 | 2 |  | 1 | 003 | 172790.9 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P89 | 43546215201 | 028 | 2 |  | 1 | 106 | 23974.61 | 0 | 0 |  | C | 23 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P89 | 43546215201 | 028 | 2 |  | 2 | 404 | 0 | 0 | 0 |  | N | 86 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
08 | E8P89 | 43546215201 | 037 | 2 |  | 1 | 118 | 27741.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P89 | 43546215201 | 038 | 2 |  | 1 | 860 | 3553990 | 0 | 0 |  | N | 147 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q39 | 43730015201 | 006 | 2 |  | 1 | 101 | 27300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 007 | 2 |  | 1 | 131 | -94332.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 008 | 2 |  | 1 | 003 | 387833.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 012 | 2 |  | 1 | 009 | 115671.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 016 | 2 |  | 1 | 919 | 111021.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 019 | 2 |  | 1 | 003 | 119709.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 020 | 2 |  | 1 | 106 | 24515.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 023 | 2 |  | 1 | 003 | 26483.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 027 | 2 |  | 1 | 131 | 9747.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 1 | 001 | 3461.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 2 | 003 | 17118.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 3 | 108 | 3244.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 4 | 108 | 3244.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 5 | 503 | 7334.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 6 | 503 | 6958.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 7 | 108 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 8 | 105 | 1633.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 030 | 2 | 850 | 9 | 003 | 7004.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 1 | 105 | 26354.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 2 | 131 | 8072.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 3 | 131 | 8072.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 4 | 131 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 5 | 131 | 8576.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 6 | 131 | 6615.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 7 | 131 | 3047.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 8 | 131 | 2914.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 9 | 131 | 12864.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 10 | 131 | 1927.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 11 | 131 | 2566.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 12 | 131 | 16084.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 13 | 131 | -2566.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 14 | 131 | 2556.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 031 | 2 | 850 | 15 | 503 | 2914.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 032 | 2 |  | 1 | 131 | 241133.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 033 | 2 |  | 1 | 131 | 128800.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 037 | 2 |  | 1 | 108 | 89554.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 041 | 2 |  | 1 | 131 | 93527.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 042 | 2 |  | 1 | 003 | 141830.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 045 | 2 |  | 1 | 101 | 86350.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 049 | 2 |  | 1 | 003 | 16580.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 1 | 003 | 11197.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 2 | 003 | 4265.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 051 | 2 | 850 | 3 | 003 | 2419.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 1 | 131 | 27985.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 2 | 131 | 547.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 3 | 131 | 3116.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 4 | 131 | 4875.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 5 | 131 | 8462.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 6 | 131 | 3525.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 052 | 2 | 850 | 7 | 131 | 10 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 054 | 2 |  | 1 | 105 | 15323.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 | 055 | 2 |  | 1 | 503 | 10479.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730015201 | 056 | 2 |  | 1 | 503 | 270 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q41 | 43516515201 | 028 | 2 |  | 1 | 113 | 120025.2 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 034 | 2 |  | 1 | 919 | 11513.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 037 | 2 | 850 | 1 | 021 | 38344.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Pavement Design Modification | Plan Modifications | 2
08 | E8Q41 | 43516515201 | 043 | 2 |  | 1 | 012 | 278427.21 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q41 | 43516515201 | 051 | 2 |  | 1 | 101 | 7958.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 010 | 2 | 850 | 1 | 023 | 17890.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 010 | 2 | 850 | 2 | 023 | 2109.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 011 | 2 | 850 | 1 | 023 | 6986.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 011 | 2 | 850 | 2 | 023 | 13013.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 026 | 2 | 850 | 1 | 023 | 7429.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 026 | 2 | 850 | 2 | 021 | 12570.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 027 | 2 | 850 | 1 | 023 | 11737.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q54 | 43517115201 | 041 | 2 |  | 1 | 503 | 7314.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 042 | 2 |  | 1 | 503 | -4792.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 043 | 2 | 850 | 1 | 023 | 6888.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q54 | 43517115201 | 044 | 2 |  | 1 | 503 | 172830.5 | 0 | 0 |  | C | 69 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q91 | 43915315201 | 008 | 2 |  | 1 | 005 | 34422.76 | 34422.76 | 5 |  | N | 27 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
08 | E8Q92 | 43798815201 | 002 | 2 |  | 1 | 503 | 477052.92 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q92 | 43798815201 | 006 | 2 |  | 1 | 503 | 200000 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q92 | 43798815201 | 028 | 2 |  | 1 | 001 | 616978.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q92 | 43798815201 | 028 | 2 |  | 2 | 105 | 31212 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q92 | 43798815201 | 028 | 2 |  | 3 | 503 | 648.24 | 0 | 3 |  | C | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q92 | 43798815201 | 028 | 2 |  | 4 | 004 | 17661.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q92 | 43798815201 | 028 | 2 |  | 5 | 023 | 1870 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 1 | 101 | 125000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 2 | 024 | 14708.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 014 | 2 | 850 | 3 | 101 | 3685.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 019 | 2 |  | 1 | 503 | 94166.31 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R18 | 43652115201 | 020 | 2 | 850 | 1 | 101 | 24700.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 020 | 2 | 850 | 2 | 101 | 10874.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 021 | 2 | 850 | 1 | 101 | 37000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 021 | 2 | 850 | 2 | 101 | 5408.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 1 | 101 | 23227.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 2 | 021 | 33471.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 | 027 | 2 | 850 | 3 | 021 | 11589.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R46 | 44154915201 | 006 | 2 |  | 1 | 923 | 6348.32 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 | 002 | 2 |  | 1 | 101 | 5477.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 | 004 | 2 |  | 1 | 112 | 97924.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R64 | 44263115201 | 009 | 2 |  | 1 | 503 | 55503.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R64 | 44263115201 | 009 | 2 |  | 2 | 503 | -10346.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
4OTY3Liw0MzYwODYuMjksMC4sODYxNTcyOC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sODI2ODk2Ny4sODYxNTcyOC4sMzQ2NzYyLiw5NTg4NzU2LiwiIiwiIiwiIg0KIjA1IiwiVDU2MTYiLCI0MzA2NTUxNTIwMSIsIkY1OTI4NzE5MzUiLCJBTkRFUlNPTiBDT0xVTUJJQSBDTy4gSU5DLiIsIk4vQSIsIk4vQSIsIk4vQSIsIk4vQSIsIjAzLzI4LzIwMTgiLDQyMzE0ODMuLDQyMjk4MzAuLDQyNDg1OTAuLC0xNjUyLjY4LDAuLDQ0MDIwNTcuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDQyNDg1OTAuLDQ0MDIwNTcuLDE1MzQ2Ny4sNTM5NDM0MC4sIiIsIiIsIiINCiIwNSIsIlQ1NjE3IiwiNDM1MDU4MTUyMDEiLCJGNTkzMzUwNjQ5IiwiVU5JVEVEIFNJR05TICYgU0lHTkFMUyBJTkMuIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMDQvMjUvMjAxOCIsMzgyNDAwMC4sMzg1MDQwNi4sMzgxNzUzNS4sMjY0MDUuNzcsMC4sMzgxNzUzNS4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMC4sMzgxNzUzNS4sMzgxNzUzNS4sMC4sNDkwNTQxMC4sIiIsIiIsIiINCiIwNSIsIlQ1NjE5IiwiMjQwOTkyNzUyMDEiLCJGMjAyMDQ1ODAwIiwiTUFTQ0kgR0VORVJBTCBDT05UUkFDVE9SUyBJTkMiLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwOC8zMC8yMDE3IiwxNzY5MzExLiwxNzg5NTA1LiwxNzA4MzI0LiwyMDE5NC4yNSwwLiwxNzE1MDYxLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwxNzA4MzI0LiwxNzE1MDYxLiw2NzM3LiwxOTQwODcx
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 3 | 009 | 330 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 005 | 11987.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P91 | 42271055201 |  | 2 | CPI | 2 | 112 | 5590.53 | 316.53 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 128 | 3948.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 128 | 2585 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P91 | 42271055201 |  | 2 | CPI | 1 | 112 | -2795.26 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 105 | 9801.38 | 9801.38 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 503 | 7821.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 1 | 503 | 1480.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P94 | 43493915201 |  | 2 | CPI | 2 | 112 | 6544.93 | 6544.93 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P94 | 43493915201 |  | 2 | CPI | 3 | 118 | 566.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1Q23 | 43665015201 |  | 2 | CPI | 1 | 401 | 0 | 0 | 0 |  | N | 32 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 13167 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 2516.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 825 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 27300.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 107 | 3855.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 2 | 107 | 4072.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 6591.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 004 | 19965 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 108 | 16108.78 | 3167.05 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 12829.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 115 | 8562.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1Q29 | 42584115201 |  | 2 | CPI | 1 | 101 | 9206.11 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R12 | 43668215201 |  | 2 | CPI | 1 | 003 | 14025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R12 | 43668215201 |  | 2 | CPI | 2 | 007 | 1354.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R66 | 43641515201 |  | 2 | CPI | 1 | 105 | 3850.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R66 | 43641515201 |  | 2 | CPI | 1 | 007 | 880.46 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R66 | 43641515201 |  | 2 | CPI | 1 | 108 | 15452.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1R66 | 43641515201 |  | 2 | CPI | 1 | 012 | 1059.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R80 | 43771615201 |  | 2 | CPI | 1 | 001 | 6183.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 106 | 5217 | 5217 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1634 | 43120715201 |  | 2 | CPI | 1 | 101 | 8863.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 101 | 2954.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 106 | 9617.52 | 9617.52 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1634 | 43120715201 |  | 2 | CPI | 1 | 007 | 8198.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 007 | 1604.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1634 | 43120715201 |  | 2 | CPI | 1 | 503 | 2176 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1634 | 43120715201 |  | 2 | CPI | 2 | 007 | 9776.79 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1634 | 43120715201 |  | 2 | CPI | 3 | 003 | 6917.8 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1634 | 43120715201 |  | 2 | CPI | 1 | 007 | 14067.21 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1634 | 43137315201 |  | 2 | CPI | 2 | 004 | 3455.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1634 | 43137315201 |  | 2 | CPI | 1 | 115 | 8949.46 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Drainage Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 4445.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 62.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 56.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 98.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 14.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 84655.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 107 | 7100.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 3 | 101 | 84.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 28.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 1317.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 126.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 012 | 22495.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 012 | 7879.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 253.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 239.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 70.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 324.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 141 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | 225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 107 | 0.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 2 | 101 | 464.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1664 | 20103265201 |  | 2 | CPI | 1 | 101 | -225.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 4585.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 128 | 4250 | 4250 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 7146.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 8971.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 2 | 001 | 34170.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 3 | 023 | 6197.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 023 | 6407.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1671 | 43560615201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1697 | 43534915201 |  | 2 | CPI | 1 | 112 | 1241.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 001 | 18048.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 001 | 18048.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1701 | 43498615201 |  | 2 | CPI | 1 | 115 | 7360.64 | 7360.64 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1701 | 43498615201 |  | 2 | CPI | 2 | 007 | 923.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1705 | 44013315201 |  | 2 | CPI | 1 | 112 | 296.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1705 | 44013715201 |  | 2 | CPI | 1 | 112 | 1195.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44012515201 |  | 2 | CPI | 1 | 112 | 1490.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44012515201 |  | 2 | CPI | 1 | 112 | 1250 | 1250 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1707 | 44013815201 |  | 2 | CPI | 1 | 106 | 11902.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1707 | 44013815201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1711 | 43121915201 |  | 2 | CPI | 1 | 503 | 8972.89 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1711 | 43121915201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 4 |  | N | 40 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 101 | 16973.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 115 | 16978.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1713 | 43355215201 |  | 2 | CPI | 2 | 001 | 7539.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1713 | 43355215201 |  | 2 | CPI | 1 | 003 | 8508.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1714 | 43837615201 |  | 2 | CPI | 1 | 503 | 1800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1729 | 43837415201 |  | 2 | CPI | 1 | 012 | 694.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1741 | 44067415201 |  | 2 | CPI | 1 | 122 | 2342.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1741 | 44067415201 |  | 2 | CPI | 1 | 007 | 1230.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 35948 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2554.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 2122.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 3638.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 1419 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7378 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 14045.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 350 | 11000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 7898.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 18667.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 11283.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | 2729.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 2256.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 350 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 1092.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 1128.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | 32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 008 | -32.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 107 | 436.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2P14 | 21330435201 |  | 2 | CPI | 1 | 004 | 0.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2P14 | 21330435201 |  | 2 | CPI | 2 | 107 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 007 | 715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 2255.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 007 | 6699.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 5 | 007 | 5671.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 6 | 003 | 7500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 3 | 007 | 10049.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 007 | 4192.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 350 | 2851.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 013 | 8285 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 003 | 26121.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 013 | 21757.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 95245.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 115 | 4293.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 115 | 16649.6 | 16649.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2T34 | 43141825201 |  | 2 | CPI | 2 | 003 | 31147.2 | 31147.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2T34 | 43141825201 |  | 2 | CPI | 1 | 004 | 2664.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2T34 | 43141825601 |  | 2 | CPI | 1 | 015 | 18416.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 105 | 13024 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 015 | 2816 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 001 | 6260.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 1 | 001 | 16656.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2U38 | 43226615601 |  | 2 | CPI | 2 | 015 | 29397.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 8419.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2U38 | 43226615201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 503 | 31698.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 5013.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 105 | 23233.91 | 0 | 2 |  | C | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 105 | 3451.33 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 503 | -31698.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 1891.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 1102.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 208 | 2461.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 112 | 1017.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | 3993.73 | 3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | 3310.46 | 3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | 1792.67 | 1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 112 | 1049.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 112 | 980.49 | 980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | 2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | 3993.73 | 3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | 3310.46 | 3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | 1792.67 | 1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 5 | 112 | 980.49 | 980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 1 | 003 | -2366.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 2 | 003 | -3993.73 | -3993.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V70 | 42747515201 |  | 2 | CPI | 3 | 117 | -3310.46 | -3310.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 4 | 112 | -1792.67 | -1792.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V70 | 42747515201 |  | 2 | CPI | 5 | 112 | -980.49 | -980.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 8320.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 118 | 17550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 012 | 1072.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 2 | 007 | 1393.67 | 1393.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V71 | 43430015201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 2319.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 7371.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 003 | 4771.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 107 | 3434.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 32103.81 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2V95 | 43617015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V95 | 43617015201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W35 | 42849115201 |  | 2 | CPI | 1 | 012 | 10399.78 | 1722.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W51 | 20950355201 |  | 2 | CPI | 1 | 108 | 5910.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W52 | 42849815201 |  | 2 | CPI | 1 | 012 | 39951.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W53 | 42849715201 |  | 2 | CPI | 1 | 120 | 18271.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 4386 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W95 | 43402815201 |  | 2 | CPI | 1 | 108 | 833 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 3607.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 1694.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 003 | 2961.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 012 | 8032.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W96 | 43307515201 |  | 2 | CPI | 1 | 003 | 229.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X15 | 20961685201 |  | 2 | CPI | 1 | 106 | 8172.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X15 | 20961685201 |  | 2 | CPI | 1 | 012 | 19307.27 | 7485.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X44 | 42879715201 |  | 2 | CPI | 1 | 118 | 4536.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2X44 | 42879715201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2X60 | 43025915201 |  | 2 | CPI | 1 | 001 | 874.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X60 | 43025915201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X62 | 43044925201 |  | 2 | CPI | 1 | 119 | 22912.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 |  | 2 | CPI | 1 | 119 | 22912.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 |  | 2 | CPI | 1 | 119 | 27087.5 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X62 | 43044925201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 001 | 1760.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 923 | 2402.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 001 | 7182.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 404 | 0 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 401 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | E2X63 | 43391215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X68 | 43500015201 |  | 2 | CPI | 1 | 101 | 1762.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 003 | 19823.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 003 | 30530.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 115 | 3842.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 6564.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 4526.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 47514.67 | 20240.85 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 37197.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 019 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2562 | 20821175201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 003 | 3792.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 2 | 005 | 5934 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 001 | 19566.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 122 | 1265.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 105 | 15392.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2576 | 43091115201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 126 | 6987.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 105 | 3946.98 | 3946.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 5593.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1924.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 118 | 2043.71 | 2043.71 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 7470.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 012 | 17090.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 5000 | 5000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 012 | 5500 | 5500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 012 | 2673 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 001 | 1210.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 2 | 120 | 3556.89 | 3556.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1163.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 5161.2 | 5160.2 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 120 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 3932.5 | 3932.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215601 |  | 2 | CPI | 1 | 001 | 42560.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 14997.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 10975.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 2024.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 005 | 1261.49 | 1261.49 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 007 | 1521.89 | 1521.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 126 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2577 | 43245215201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 1633.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 2534.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 101 | 3882.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 005 | 1410 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 3 | 001 | 1284.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 4 | 103 | 2706.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 1022.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 299.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 3340.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 11250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2612 | 42360825201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2616 | 20800155201 |  | 2 | CPI | 1 | 007 | 17383.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 112 | 22753.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 718.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 126 | 629.64 | 629.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 7570 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 012 | 2008.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 113 | 7913.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 5215.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 7342.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015601 |  | 2 | CPI | 1 | 015 | 2658.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | -8406.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 007 | 4719.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 3686.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2618 | 43091015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2618 | 43091015201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 021 | 26233.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 119 | 2531.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 024 | 2669.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 008 | 13116.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 3 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 503 | 32079 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 503 | 3679.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 008 | 16872.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 2 | 503 | 3679.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 3 | 008 | 9893.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 503 | 3679.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 2 | 008 | 16872.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 3 | 008 | 9893.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 503 | -3679.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 2 | 503 | -3679.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2621 | 20800145201 |  | 2 | CPI | 3 | 008 | -16872.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 4 | 008 | -9893.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 115 | 5103.59 | 3108.58 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 107 | 4356 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 024 | 10754.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2621 | 20800145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2621 | 20800145201 |  | 2 | CPI | 2 | 117 | 21622.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 503 | 3200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 101 | 3616 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 2 | 101 | 1604.48 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 3 | 101 | 4627.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 4 | 101 | 3600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 5 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 101 | 890.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 25449.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 115 | 11184.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 11263.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 2 | 001 | 29984.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2657 | 20781825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2658 | 41525215201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 1453.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 6356.14 | 6356.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 5220.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 2 | 001 | 1452.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 34018.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2661 | 43433715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 33 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2678 | 21028685201 |  | 2 | CPI | 1 | 001 | 8119.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2678 | 43579615201 |  | 2 | CPI | 1 | 001 | 3760.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2678 | 21028685201 |  | 2 | CPI | 1 | 106 | 2407.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2678 | 21028685201 |  | 2 | CPI | 1 | 007 | 4226.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2678 | 43579615201 |  | 2 | CPI | 1 | 007 | 1374.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2678 | 21028685201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415601 |  | 2 | CPI | 1 | 015 | 10643.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415601 |  | 2 | CPI | 1 | 015 | 8746.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 7199.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 799.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 1075.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 2 | 108 | 1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | -1494.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 716.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 2 | 923 | 1421.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 3 | 108 | 633.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 118 | 4447.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2679 | 43617415201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 33 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 115 | 3586.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 115 | -3586.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 101 | 3273.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2682 | 43201215201 |  | 2 | CPI | 2 | 021 | 18339.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 21 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2682 | 43201215201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 115 | 4440.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 13120.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 3762 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2683 | 43616215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 5 |  | N | 25 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 4949.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 2 | 101 | 6664.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 3 | 101 | 2542.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2686 | 43611815201 |  | 2 | CPI | 4 | 012 | 5379.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2686 | 43611815201 |  | 2 | CPI | 1 | 101 | 6870 | 6870 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2687 | 43617315201 |  | 2 | CPI | 1 | 001 | 8532.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2687 | 43617315201 |  | 2 | CPI | 1 | 113 | 17379 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 101 | 1706.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 001 | 11752.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2689 | 43616115201 |  | 2 | CPI | 2 | 112 | 1382.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2689 | 43616115201 |  | 2 | CPI | 1 | 001 | 13212.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2691 | 43617215201 |  | 2 | CPI | 1 | 115 | 3409.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2691 | 43617215201 |  | 2 | CPI | 1 | 101 | 916.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 010 | 8988.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 001 | 980.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 012 | 3959.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 2 | 107 | 7825.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615915201 |  | 2 | CPI | 1 | 115 | 1082.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2695 | 43615915201 |  | 2 | CPI | 2 | 012 | 839.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 003 | 4190.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 003 | 1394.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2695 | 43615915201 |  | 2 | CPI | 1 | 001 | 639.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 1455.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 801.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 106 | 3675.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 024 | 728.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 1 |  | N | 17 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 3 | 024 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2695 | 43615815201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 2 |  | N | 1 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2704 | 43761615201 |  | 2 | CPI | 1 | 007 | 15471.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2704 | 43761615201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2714 | 43761815201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2714 | 43761815201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2723 | 43762015201 |  | 2 | CPI | 1 | 503 | 2504.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2723 | 43762015201 |  | 2 | CPI | 2 | 101 | 1526.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 003 | 1894.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 001 | 838 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 116 | 353.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | T2727 | 43761215201 |  | 2 | CPI | 1 | 024 | 7341.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
02 | T2730 | 43429715201 |  | 2 | CPI | 1 | 105 | 16696.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3P84 | 43671715201 |  | 2 | CPI | 1 | 101 | 862.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 5001.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3P84 | 43625815201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R04 | 43627115201 |  | 2 | CPI | 1 | 004 | 1500 | 336 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3R52 | 43627225201 |  | 2 | CPI | 1 | 503 | 9663.81 | 1845.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R52 | 43627225201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 101 | 540 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 115 | 26048 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | 914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | 914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 001 | -914.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R73 | 43672615201 |  | 2 | CPI | 1 | 118 | 624 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 2 | 101 | 853.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R73 | 43672615201 |  | 2 | CPI | 3 | 105 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 3716.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 001 | 7581.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 010 | 2008.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 007 | -41662.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 023 | 1485 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 2 | 115 | 4510.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3471 | 41110225201 |  | 2 | CPI | 3 | 007 | 41662.5 | 41662.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
03 | T3471 | 41110225201 |  | 2 | CPI | 1 | 010 | 1281.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3485 | 42695315201 |  | 2 | CPI | 1 | 503 | 4876.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 12642.28 | 1306.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3488 | 40979275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 107 | 980.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 2903.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 7700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 11246.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 5580.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 4 | 503 | 2709.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 107 | 7081.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 107 | 1017.5 | 1017.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 7678.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 1665.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 2054.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 123 | 4541.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4583.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 11388.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 2711.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 1399.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 4355.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 3 | 503 | 7265.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 38524.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 6481.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 2 | 503 | 7409.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 1355.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 206.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | -4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 451.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3543 | 22044275201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3584 | 42551925201 |  | 2 | CPI | 1 | 922 | 4452.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3594 | 42884415201 |  | 2 | CPI | 1 | 115 | 14988.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3621 | 43626115201 |  | 2 | CPI | 1 | 115 | 5375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 1084.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 2 | 503 | 7987.77 | 3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 101 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3633 | 43188335201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3637 | 43626515201 |  | 2 | CPI | 1 | 115 | 12197.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3637 | 43626515201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 8667.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 115 | 4880.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 2 | 115 | 5064 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 3 | 128 | 7675.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3639 | 43078915201 |  | 2 | CPI | 1 | 128 | 9900 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 6550.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 35155.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 17711.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 2 | 010 | 16468.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 23464.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3655 | 43666315201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 6938.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 686.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 2 | 101 | 2225 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 3 | 101 | 697.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 4 | 015 | 7220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 1 | 007 | 1598.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915204 |  | 2 | CPI | 2 | 007 | 12350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3661 | 43255915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 3250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 2 | 503 | 4300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 012 | 10230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 24665 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3662 | 43627215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3667 | 43273835201 |  | 2 | CPI | 1 | 010 | 5558.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3667 | 43273835201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3673 | 43774415201 |  | 2 | CPI | 1 | 022 | 49174.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3678 | 43627015201 |  | 2 | CPI | 1 | 107 | 24960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3678 | 43627015201 |  | 2 | CPI | 1 | 115 | 7900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3684 | 43774815201 |  | 2 | CPI | 1 | 923 | 900.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3684 | 43774815201 |  | 2 | CPI | 2 | 001 | 4590.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3684 | 43774815201 |  | 2 | CPI | 1 | 001 | 7362.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3684 | 43774815201 |  | 2 | CPI | 2 | 001 | 12757.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3688 | 44038315201 |  | 2 | CPI | 1 | 118 | 6070 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3715 | 43827225201 |  | 2 | CPI | 1 | 503 | 2275 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 6211.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 7520.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 6000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 5229.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 3991.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 2224.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 10052.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 1735.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1203.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 4029.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | -1043.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1053.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1010.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 792.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 023 | 1173.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1403.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 023 | 2093.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 300.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 2135.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1121.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 1790.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 471.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 003 | 3146 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 11489.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 726.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1564.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 001 | 4652.37 | 4652.37 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 2564.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | 2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | 3320.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 023 | 257.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 3 | 023 | 277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 4 | 023 | 1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 503 | 3466.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 2978.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 10330.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 2751.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 023 | 1575.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 3 | 023 | 1604.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 4 | 023 | 1313.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 5 | 023 | 3308.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 6 | 023 | 439.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | 3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 003 | 4160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 023 | 3586.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 503 | -3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | -1317.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 2 | 503 | -2072.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170725201 |  | 2 | CPI | 1 | 023 | -277.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 503 | 6794.6 | 6794.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | 1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 2 | 503 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 503 | -1881 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N84 | 42170785201 |  | 2 | CPI | 1 | 003 | 10865.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 023 | 1583.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N84 | 42170735201 |  | 2 | CPI | 1 | 003 | 440.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 22703.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 2 | 503 | 14825.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 3 | 503 | 27357.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 917 | 8455.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N95 | 43316515201 |  | 2 | CPI | 1 | 503 | 12345.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 503 | 41494.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 001 | 32335.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 18563.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 8321.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 2 | 004 | 31709.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N98 | 42170745201 |  | 2 | CPI | 1 | 004 | 7017.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 42978515201 |  | 2 | CPI | 1 | 023 | 1369.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41325725201 |  | 2 | CPI | 1 | 023 | 524.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 23193225201 |  | 2 | CPI | 1 | 917 | 1930.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41273325201 |  | 2 | CPI | 1 | 917 | 2422.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 41325725201 |  | 2 | CPI | 1 | 917 | 1166.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 42978515201 |  | 2 | CPI | 1 | 917 | 534.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4P04 | 43093215201 |  | 2 | CPI | 1 | 917 | 4064.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 503 | 2987.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 2 | 503 | 1290.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 503 | 9195.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 2 | 503 | 2869.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 013 | 4879.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q16 | 42170775201 |  | 2 | CPI | 1 | 023 | 37664.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 917 | 822.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 115 | 9299 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 003 | 9062.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4Q35 | 42264135201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 3 |  | N | 5 | Avoidable, CEI Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 16653.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 3321.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 19230.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 2529.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 13123.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 6037.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 43188.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 6639.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 917 | 36426.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4Q64 | 43310855201 |  | 2 | CPI | 1 | 023 | 2848.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4S19 | 43215415201 |  | 2 | CPI | 2 | 012 | 13102.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S19 | 43215415201 |  | 2 | CPI | 1 | 012 | -13102.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S19 | 43215415201 |  | 2 | CPI | 1 | 012 | 13102.42 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S19 | 43215415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 106 | 5981.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 107 | 13699.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 106 | 5981.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 012 | 4728.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 3 | 001 | 12658.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 115 | 8976.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 107 | 6974.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 115 | 24954.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 2 | 013 | 33647.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 001 | 12408.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 107 | 13699.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4S21 | 43661715201 |  | 2 | CPI | 1 | 001 | 6289.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4S38 | 42684015201 |  | 2 | CPI | 1 | 012 | 3468.12 | 3468.12 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S38 | 42684015201 |  | 2 | CPI | 2 | 503 | 20397.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S38 | 42684015201 |  | 2 | CPI | 3 | 503 | 1770.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4S38 | 42684015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4S85 | 43609615201 |  | 2 | CPI | 1 | 106 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4S85 | 43609615201 |  | 2 | CPI | 1 | 502 | 2750 | 2750 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 105 | 22758.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T01 | 43630215201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T43 | 43686915201 |  | 2 | CPI | 1 | 118 | 2200 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T45 | 44145415201 |  | 2 | CPI | 1 | 012 | 19500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T45 | 44145415201 |  | 2 | CPI | 2 | 012 | 19500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T47 | 43995915201 |  | 2 | CPI | 1 | 012 | 10355.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T52 | 43784715201 |  | 2 | CPI | 1 | 106 | 1025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T52 | 43784715201 |  | 2 | CPI | 1 | 004 | 4800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T52 | 43784715201 |  | 2 | CPI | 2 | 503 | 25105.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T53 | 44145715201 |  | 2 | CPI | 1 | 503 | 3899.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T55 | 43388915201 |  | 2 | CPI | 1 | 105 | 28866.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T55 | 43388915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 001 | 21089.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 503 | 4529.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 115 | 21974.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 115 | 3438.66 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 115 | 8609.37 | 8609.37 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 004 | 20400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4400 | 22777415602 |  | 2 | CPI | 1 | 015 | 750 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4400 | 22777415602 |  | 2 | CPI | 2 | 015 | 673.32 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4400 | 22777415201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 2 |  | N | 4 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 001 | 12902.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4412 | 42873315201 |  | 2 | CPI | 2 | 101 | 6859.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 115 | 1404.48 | 1404.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 2 | 001 | 25669.74 | 25669.74 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4412 | 42873315202 |  | 2 | CPI | 1 | 101 | 4565 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 643.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315202 |  | 2 | CPI | 1 | 004 | 1278.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 1692.44 | 1692.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 28 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 6591.69 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4412 | 42873315201 |  | 2 | CPI | 1 | 106 | 4663.91 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 001 | 4492.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 003 | 1091.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4418 | 22989615201 |  | 2 | CPI | 2 | 106 | 3076.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4418 | 22989615201 |  | 2 | CPI | 1 | 106 | 8100 | 8100 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 1150.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 107 | 655.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 107 | 705.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 001 | 11760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 001 | 43721.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 012 | 2194.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 010 | 15343.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 22000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 115 | 3322.8 | 3322.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 503 | 20881.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 2 | 001 | 21724.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 3 | 004 | 1713.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4423 | 23033845201 |  | 2 | CPI | 4 | 503 | 4826.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4423 | 23033845201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 123 | 4014.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 2 | 001 | 28714.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 001 | 3321 | 3321 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 106 | 809.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 106 | 3547.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415203 |  | 2 | CPI | 1 | 106 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 012 | 4395.55 | 4395.55 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 119 | 1760 | 1760 | 3 |  | N | 0 | Avoidable, CEI Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 001 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 005 | 1588.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Utility Adjustments | Utility Delays | 11
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 015 | 3200.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4433 | 42995815601 |  | 2 | CPI | 2 | 012 | 1816.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 734.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42872415201 |  | 2 | CPI | 1 | 001 | 5587.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 106 | 18684.88 | 18684.88 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 003 | 12222.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 106 | 1074.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4433 | 42995815601 |  | 2 | CPI | 1 | 009 | 1697.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | T4433 | 42995815201 |  | 2 | CPI | 1 | 003 | 2002 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 7345.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 112 | 7655.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 4560.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 7852.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 4560.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 8643.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 115 | 2380.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 2 | 118 | 3289 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 112 | 20938.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4444 | 43270515201 |  | 2 | CPI | 1 | 022 | 30661.2 | 30661.2 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 117 | 633.6 | 633.6 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 024 | 1066.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 018 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 024 | 2846.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 126 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 024 | 6085.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Computation Error | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 108 | 11379.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 2 | 115 | 1398.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 001 | 2308.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 115 | 4202.02 | 4202.02 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 2 | 115 | 2123.65 | 1231.87 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 122 | 1701.77 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4449 | 43466615201 |  | 2 | CPI | 1 | 023 | 7026.98 | 7026.98 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 115 | 1024 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 005 | 5294.02 | 5294.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4452 | 43166615201 |  | 2 | CPI | 2 | 001 | 1454.5 | 1454.5 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4452 | 43166615201 |  | 2 | CPI | 3 | 115 | 11036.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 4 | 122 | 2071.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 107 | 708.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 2 | 115 | 8270.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 106 | 1144.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 108 | 11268.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4452 | 43166615201 |  | 2 | CPI | 1 | 105 | 3701.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 023 | 7396.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 18153.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 9815.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 023 | 18346.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 101 | 5435.27 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427325201 |  | 2 | CPI | 1 | 101 | 4257.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4454 | 43427315201 |  | 2 | CPI | 1 | 023 | 7150.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 4427.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 112 | 14368.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 15261.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 2 | 112 | 2979.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 3 | 112 | 4392.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 17253 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 115 | 2112 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 003 | 1468.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 8568.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4465 | 42793815201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | E | 30 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 6199.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 101 | 8773.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 11159.65 | 11159.65 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4470 | 43467915201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 4 |  | N | 28 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 3889.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 2457.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 2 | 003 | 1854.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 001 | 3476.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 108 | 15045.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4478 | 43206645201 |  | 2 | CPI | 1 | 106 | 15703.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4478 | 43206645201 |  | 2 | CPI | 2 | 106 | 4651.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4480 | 43166515201 |  | 2 | CPI | 1 | 503 | 830.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4480 | 43166515201 |  | 2 | CPI | 2 | 118 | 2261.88 | 2261.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4480 | 43166515201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 2 |  | N | 12 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 001 | 1525.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4481 | 43177025201 |  | 2 | CPI | 2 | 001 | 14025.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 105 | 6916.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 105 | 1880.48 | 1880.48 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 024 | 6830.78 | 6830.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 024 | 6646.85 | 6646.85 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 2 | 106 | 12174.9 | 12174.9 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4481 | 43177025201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4482 | 44008015201 |  | 2 | CPI | 1 | 012 | 634.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4482 | 44008015201 |  | 2 | CPI | 1 | 106 | 3450.78 | 1938.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4482 | 44008015201 |  | 2 | CPI | 1 | 106 | -3450.78 | -1938.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4482 | 44008015201 |  | 2 | CPI | 2 | 106 | 1511.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4482 | 44008015201 |  | 2 | CPI | 1 | 106 | 1938.88 | 1938.88 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4484 | 43169815201 |  | 2 | CPI | 1 | 101 | 896.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4484 | 43169815201 |  | 2 | CPI | 1 | 106 | 3678.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4484 | 43169815201 |  | 2 | CPI | 2 | 101 | -896.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4484 | 43169815201 |  | 2 | CPI | 1 | 106 | 4484.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4484 | 43169815201 |  | 2 | CPI | 2 | 010 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4484 | 43169815202 |  | 2 | CPI | 1 | 101 | 896.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 105 | 1931.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 001 | 3267.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 001 | 2273.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 001 | 5233.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 503 | 9121.11 | 2173.88 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 503 | 4044.19 | 4044.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 503 | 1019.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 2 | 106 | 2500.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 3 | 007 | 251.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 4 | 106 | 3055.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 5 | 001 | 1524.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4486 | 43165715201 |  | 2 | CPI | 6 | 503 | 1721.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 7 | 503 | 755.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 8 | 503 | 4370 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4486 | 43165715201 |  | 2 | CPI | 9 | 106 | 4870.47 | 3868.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4486 | 43165715201 |  | 2 | CPI | 1 | 106 | 379 | 379 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4490 | 43467415201 |  | 2 | CPI | 1 | 107 | 2070.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4490 | 43469915201 |  | 2 | CPI | 1 | 107 | 1035.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4490 | 43467415201 |  | 2 | CPI | 1 | 118 | 3146 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4490 | 43469915201 |  | 2 | CPI | 1 | 003 | 1548.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4490 | 43469915201 |  | 2 | CPI | 1 | 112 | 939.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4490 | 43467415201 |  | 2 | CPI | 1 | 118 | 3080 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4490 | 43467415201 |  | 2 | CPI | 2 | 123 | 21507.11 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Landscaping Changes | Plan Modifications | 2
04 | T4492 | 43783715201 |  | 2 | CPI | 1 | 003 | 1964.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4492 | 43783715201 |  | 2 | CPI | 2 | 118 | 375 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 107 | 1456.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 118 | 16897.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4493 | 43622615201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4515 | 43783515201 |  | 2 | CPI | 1 | 001 | 688.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4515 | 43783515201 |  | 2 | CPI | 1 | 118 | 362.48 | 362.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 3899.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 2 | 023 | 11026.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 022 | 9416.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 1023 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 024 | 8706.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 007 | 39069.83 | 12617.83 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 001 | 15531.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 2 | 007 | 12994.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 5 |  | N | 10 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W11 | 24262635201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 |  | 2 | CPI | 1 | 021 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W31 | 43360715201 |  | 2 | CPI | 1 | 003 | 4745.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 20030 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 26484.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 9000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 8984 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 3136.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 003 | 22324.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y20 | 42690435201 |  | 2 | CPI | 1 | 105 | 2060.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Y33 | 43693715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y33 | 43693715201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 105 | 5734 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 2 | 106 | 4585.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 012 | 5993.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z02 | 43365415201 |  | 2 | CPI | 2 | 105 | 10293.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z02 | 43365415201 |  | 2 | CPI | 1 | 007 | 23393.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Z09 | 41299445214 |  | 2 | CPI | 1 | 503 | 4205.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z09 | 41299445214 |  | 2 | CPI | 1 | 503 | 26624.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 115 | 7195.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 2828.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z25 | 43685515201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z27 | 43733815201 |  | 2 | CPI | 1 | 115 | 21077.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z27 | 43733815201 |  | 2 | CPI | 1 | 115 | 9563.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z27 | 43733815201 |  | 2 | CPI | 1 | 101 | 26358.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 101 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 2 | 126 | 1450 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 2670.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 2 | 115 | 13133.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 34740.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z45 | 43733915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z48 | 44096715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z49 | 44255515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z73 | 44096615201 |  | 2 | CPI | 1 | 105 | 42000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z73 | 44096615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 009 | 32447.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 117 | 3295.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3266.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 3359.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 7003.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 3053.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 012 | 3531 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 012 | 14850.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 53568.73 | 14060.7 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 29101.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 3 | 015 | 2716.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 120 | 22876.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 21177.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345601 |  | 2 | CPI | 2 | 015 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 101 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5469 | 23920345601 |  | 2 | CPI | 1 | 015 | 25020.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 4011.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 4374.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 1210 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 001 | 986.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 1434.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 115 | 6514.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 004 | 1689.89 | 1689.89 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 107 | 17747.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 10206.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 003 | 811.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 008 | 9339.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 115 | 8726.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 004 | 1158.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5469 | 23920345201 |  | 2 | CPI | 2 | 503 | -460.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5469 | 23920345201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 165 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 115 | 2603.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 106 | 8619 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 106 | 4906.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325601 |  | 2 | CPI | 2 | 015 | 16188.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 106 | 1905.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 001 | 4250.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 3 | 503 | 165 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 4 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 5 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 6 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 7 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 8 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 9 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | -165 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 3 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 4 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 5 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 6 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 7 | 503 | -82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 115 | 2603.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 503 | 247.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 3 | 118 | 15770.49 | 8028 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 4 | 503 | 82.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 115 | -2603.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 503 | -247.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 106 | 4906.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 106 | -4906.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 503 | 1237.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 007 | 3736.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 007 | 2839.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 106 | 7970.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 2 | 021 | 1734.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 3 | 106 | 8619 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 106 | -8619 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 015 | 16188.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325601 |  | 2 | CPI | 1 | 015 | -16188.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5506 | 41840325201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5569 | 43442615201 |  | 2 | CPI | 1 | 108 | 8496.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5569 | 43442615201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5569 | 43442615201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 001 | 6777.6 | 7272.52 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505315201 |  | 2 | CPI | 2 | 107 | 2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615201 |  | 2 | CPI | 1 | 112 | 1968.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 107 | 2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615201 |  | 2 | CPI | 1 | 107 | 4444 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505615202 |  | 2 | CPI | 1 | 107 | 4642 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 107 | -2091.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 2 | 001 | 6777.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505315201 |  | 2 | CPI | 3 | 001 | 13394.97 | 12577.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5572 | 43505615202 |  | 2 | CPI | 1 | 118 | 844.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5572 | 43505315201 |  | 2 | CPI | 1 | 503 | 2978.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 8490.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 3714.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 7694.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 503 | 3372.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5588 | 43505915201 |  | 2 | CPI | 1 | 107 | 6632.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5588 | 43505915201 |  | 2 | CPI | 2 | 107 | 5618.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 101 | 3600 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | 48898.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | -48898.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 2 | 115 | 48395.15 | 48395.15 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5591 | 42823815201 |  | 2 | CPI | 1 | 115 | 2782.4 | 2782.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 023 | 6497 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5601 | 43239815201 |  | 2 | CPI | 1 | 101 | 1207.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 001 | 2111.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5601 | 43565815201 |  | 2 | CPI | 1 | 012 | 21500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 108 | 4097.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43440415201 |  | 2 | CPI | 1 | 023 | 1050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43565815201 |  | 2 | CPI | 1 | 023 | 2650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5601 | 43565815201 |  | 2 | CPI | 2 | 021 | 2650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5606 | 44107015201 |  | 2 | CPI | 1 | 115 | 4934.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5606 | 43803815201 |  | 2 | CPI | 1 | 503 | 13427.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5606 | 43803815201 |  | 2 | CPI | 1 | 105 | 7513.32 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5606 | 43803815201 |  | 2 | CPI | 2 | 105 | 9900 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 503 | 13110.33 | 13110.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 101 | 5603.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 2 | 503 | 25738.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 3 | 503 | 3115 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 118 | 200 | 24707.31 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5616 | 43065515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | 1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | -2295.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 2 | 101 | -1909.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 503 | 2382.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 023 | 3653.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 106 | 6054.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5617 | 43505815201 |  | 2 | CPI | 1 | 024 | 834.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 001 | 5764.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 003 | 311.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5619 | 24099285201 |  | 2 | CPI | 1 | 115 | 1200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 106 | 3337.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5619 | 24099275201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 782.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 023 | 11439.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 115 | 7972.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5623 | 43618735201 |  | 2 | CPI | 1 | 122 | 6180.35 | 6180.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 1272.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5623 | 43239915201 |  | 2 | CPI | 1 | 118 | 2987.62 | 2987.62 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5635 | 43733015201 |  | 2 | CPI | 1 | 001 | 5018.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5635 | 43733015201 |  | 2 | CPI | 2 | 112 | 8901.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5635 | 43733015201 |  | 2 | CPI | 1 | 105 | 18287.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5635 | 43733015201 |  | 2 | CPI | 2 | 115 | 17792.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5635 | 43733015201 |  | 2 | CPI | 1 | 105 | 0.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5635 | 43733015202 |  | 2 | CPI | 1 | 009 | 0 | 0 | 5 |  | N | 30 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
05 | T5641 | 44055765201 |  | 2 | CPI | 1 | 106 | 41666 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5641 | 44055775201 |  | 2 | CPI | 1 | 010 | 22101.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5641 | 44055775201 |  | 2 | CPI | 1 | 503 | 19566.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5641 | 44055775201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5641 | 44055775201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5647 | 44106615201 |  | 2 | CPI | 1 | 122 | 2750 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5647 | 44106615201 |  | 2 | CPI | 1 | 106 | 18288.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5647 | 44106615201 |  | 2 | CPI | 1 | 108 | 4642.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5647 | 44106615201 |  | 2 | CPI | 1 | 106 | 18288.55 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 3 | 007 | 15653.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 007 | 5217.8 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | -1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | -536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 023 | 1506.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 2 | 023 | 536.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 9340.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 1478.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 82125.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 24530.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 003 | 5805.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | E6J69 | 43492215201 |  | 2 | CPI | 1 | 012 | 2156.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 122 | 1966.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | E6K58 | 43081315201 |  | 2 | CPI | 2 | 001 | 556.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 101 | 14235.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K58 | 43081315201 |  | 2 | CPI | 1 | 503 | 85.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K58 | 43081315201 |  | 2 | CPI | 2 | 503 | 680.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 101 | 51824.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 115 | 18518.16 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | E6K59 | 41831225201 |  | 2 | CPI | 1 | 106 | 20980.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6L26 | 43653515201 |  | 2 | CPI | 1 | 503 | 8375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 503 | 9886.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 007 | 23363.88 | 23363.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 004 | 3883.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725201 |  | 2 | CPI | 1 | 023 | 1648.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6L27 | 43081725202 |  | 2 | CPI | 1 | 503 | 1459.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 1 | 001 | 4537.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | E6L37 | 42919325201 |  | 2 | CPI | 1 | 503 | 10279.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 2 | 503 | 23090.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L37 | 42919325201 |  | 2 | CPI | 3 | 101 | 7067.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L51 | 43029129201 |  | 2 | CPI | 1 | 012 | 4989.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L51 | 43029129202 |  | 2 | CPI | 1 | 503 | 29648.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L51 | 43029129201 |  | 2 | CPI | 1 | 012 | 590 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L51 | 43029129202 |  | 2 | CPI | 1 | 503 | 5816.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L51 | 43029129202 |  | 2 | CPI | 2 | 503 | 4375.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L72 | 44183315201 |  | 2 | CPI | 1 | 003 | 1357.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 001 | 10601.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 001 | 15982.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 103 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 118 | 56166.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6337 | 41809115601 |  | 2 | CPI | 1 | 015 | 17517.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 2 | 015 | 5102.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 3 | 015 | 70280.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115601 |  | 2 | CPI | 4 | 015 | 11584.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 123 | 2722.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 2442.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115601 |  | 2 | CPI | 1 | 015 | 40722.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 107 | 617.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 108 | 598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 003 | 1674.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 3 | 503 | 2456.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 005 | 2921.21 | 2921.21 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 115 | 652.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 43328315201 |  | 2 | CPI | 1 | 001 | 10425.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 115 | 2984.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 123 | 1455.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | -598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 3 | 108 | -299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 1 | 108 | 598.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 41809115201 |  | 2 | CPI | 2 | 108 | 299.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6337 | 43349115201 |  | 2 | CPI | 1 | 118 | 2268.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 503 | 11165 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 107 | 3812.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6338 | 41463315201 |  | 2 | CPI | 2 | 001 | 12218.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 26037.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 13551.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 115 | 14778.48 | 14778.48 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | -32141.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315201 |  | 2 | CPI | 1 | 001 | 1056 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 22392.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6338 | 41463315601 |  | 2 | CPI | 1 | 015 | 1811.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 115 | 14639.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 123 | 2368.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 112 | 3844 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 007 | 3590 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 105 | 1054.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 917 | 4717.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 003 | 7409.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 1 | 107 | 3025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 107 | 858 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 004 | 11636.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 003 | 35891.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 503 | 4397.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 503 | 2040.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6344 | 24994145201 |  | 2 | CPI | 3 | 003 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 4 | 001 | 614.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 1 | 004 | 4231.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6344 | 42901415201 |  | 2 | CPI | 2 | 115 | 9497.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 115 | 1495.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 42901415601 |  | 2 | CPI | 1 | 001 | 18706.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 2 | 001 | 5616.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 106 | -1495.63 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 007 | 7194 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 3 | 007 | 4539.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 4 | 115 | 14130.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 106 | 1495.63 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6344 | 24994145601 |  | 2 | CPI | 1 | 015 | 3672.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 1 | 112 | 17868.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6344 | 42901415601 |  | 2 | CPI | 2 | 001 | 12983.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 3 | 001 | 8342.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 42901415601 |  | 2 | CPI | 4 | 015 | 17050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 1 | 001 | 3222.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6344 | 24994145201 |  | 2 | CPI | 2 | 001 | 1235.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 009 | 5490 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 63609.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 3180.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 5129.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 015 | 10379.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 2 | 007 | 6330.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 503 | 480.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 001 | 1939.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 2 | 503 | 1164.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 647.74 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 001 | 2811.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 2 | 007 | 2136.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 004 | 6555.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 105 | 17007.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6382 | 40561535201 |  | 2 | CPI | 1 | 118 | 20481.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 160823.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 2198.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 6327 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 004 | 2594.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 7126.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535602 |  | 2 | CPI | 1 | 007 | 9720 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 5750 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 007 | 4886.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | -5750 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 106 | 5750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 41705.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 1 | 007 | 2856.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561545201 |  | 2 | CPI | 2 | 007 | 761.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6382 | 40561535601 |  | 2 | CPI | 1 | 007 | 21412.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6401 | 41247395201 |  | 2 | CPI | 1 | 001 | 17895 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395602 |  | 2 | CPI | 1 | 001 | 925.87 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247375202 |  | 2 | CPI | 1 | 001 | 2139.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6401 | 41247395202 |  | 2 | CPI | 1 | 503 | 3600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6403 | 43348915201 |  | 2 | CPI | 1 | 105 | 5280 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 3 | 123 | 6410.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6403 | 43348915201 |  | 2 | CPI | 4 | 001 | 16985.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 6 | 007 | 2554.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 2 | 024 | 2255.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6403 | 43348915201 |  | 2 | CPI | 5 | 115 | 16061.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 1 | 001 | 2882.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6406 | 42902215201 |  | 2 | CPI | 2 | 118 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6406 | 42902215201 |  | 2 | CPI | 3 | 503 | 14596.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902215201 |  | 2 | CPI | 4 | 503 | 9515 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 1 | 503 | 2610.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6406 | 42902225201 |  | 2 | CPI | 2 | 503 | 6811.21 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 101 | 2786.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 001 | 2069.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6419 | 42827825201 |  | 2 | CPI | 2 | 101 | 18916.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6419 | 42827825201 |  | 2 | CPI | 1 | 001 | 4441.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 003 | 1293.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 123 | 16438.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
06 | T6437 | 43634215201 |  | 2 | CPI | 1 | 007 | 1775.31 | 1775.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6437 | 43634215201 |  | 2 | CPI | 2 | 007 | 8840.65 | 8840.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117015201 |  | 2 | CPI | 1 | 503 | 564.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117015201 |  | 2 | CPI | 2 | 005 | 684.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6438 | 43117015201 |  | 2 | CPI | 3 | 007 | 385.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117015202 |  | 2 | CPI | 1 | 503 | 1880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 503 | 4252.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 101 | 564.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6438 | 43117025201 |  | 2 | CPI | 1 | 101 | 1601.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6438 | 43117025201 |  | 2 | CPI | 2 | 007 | 385.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6438 | 43117055202 |  | 2 | CPI | 1 | 101 | 2280 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6444 | 43640415201 |  | 2 | CPI | 1 | 503 | 2275.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 005 | 2418.72 | 2418.72 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 001 | 1021.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6445 | 42611315201 |  | 2 | CPI | 2 | 001 | 1695 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6445 | 42611315201 |  | 2 | CPI | 3 | 001 | 4074.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 130 | 3240.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 001 | 1170.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 001 | 7046.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6445 | 42611315201 |  | 2 | CPI | 1 | 104 | 7131.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pay Item Conflicts | Plan Modifications | 2
06 | T6451 | 42563725201 |  | 2 | CPI | 1 | 503 | 9954.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6455 | 43791715201 |  | 2 | CPI | 1 | 012 | 5357.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6455 | 43791715201 |  | 2 | CPI | 1 | 001 | 1690.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6455 | 43791715201 |  | 2 | CPI | 2 | 023 | 3733.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6455 | 43791715201 |  | 2 | CPI | 3 | 009 | 440.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6458 | 44019115201 |  | 2 | CPI | 1 | 503 | 17669.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6458 | 44018915201 |  | 2 | CPI | 1 | 106 | 3393.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6458 | 44019115201 |  | 2 | CPI | 1 | 503 | 8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 44211.51 | 44211.51 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 10470.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 15291.34 | 29983.01 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 28309.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 2 | 005 | 4025.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 8815 | 8815 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 005 | -4025.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 005 | 4025.86 | 4025.86 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | -38779.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 38779.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | -8815 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 14691.67 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 55 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7H90 | 25693125201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 1584 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 010 | 2842.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 99990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 2 | 503 | 15583.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 2 |  | N | 49 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
07 | E7K19 | 43476515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 70 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 6001.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 004 | 3842.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 3 | 003 | 6982.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 3850 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 021 | 16357.31 | 16357.31 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 023 | 3282.09 | 3282.09 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 2 | 023 | 3517.7 | 3517.7 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 3 | 023 | 1144.67 | 1144.67 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 023 | 3394.17 | 3394.17 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 21764.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 3850 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | -3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 021 | 16697.4 | 16697.4 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 007 | 3940.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K24 | 41101225201 |  | 2 | CPI | 1 | 503 | 1963.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 15708.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 503 | 16688.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 840 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 004 | 20173.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K24 | 41101145201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 37275.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 007 | 3039.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 43473815201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 3 | 503 | 7920.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 12425.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 001 | 32302.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L26 | 40552525201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 17997.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2565 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 1 | 007 | 1821.18 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L26 | 40552525601 |  | 2 | CPI | 2 | 503 | 962.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525601 |  | 2 | CPI | 3 | 503 | 484.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525605 |  | 2 | CPI | 1 | 503 | 17355.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 43473815201 |  | 2 | CPI | 1 | 503 | 2779.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L26 | 40552525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L58 | 43243415201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7L77 | 42292935201 |  | 2 | CPI | 1 | 012 | 9843.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L77 | 42292935201 |  | 2 | CPI | 2 | 115 | 33659.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 6160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L98 | 43763715201 |  | 2 | CPI | 2 | 101 | 3707 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L98 | 43763715201 |  | 2 | CPI | 3 | 503 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L98 | 43763715201 |  | 2 | CPI | 1 | 131 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 103 | 20764.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | -29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 29235.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M00 | 42292945201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | E7M05 | 43954615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M05 | 43954615201 |  | 2 | CPI | 2 | 105 | 532.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M05 | 43954615201 |  | 2 | CPI | 1 | 128 | 1524.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | E7M24 | 43649415201 |  | 2 | CPI | 1 | 005 | 24120.14 | 24120.14 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7M24 | 43649415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M24 | 43649415201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7M25 | 43386415201 |  | 2 | CPI | 1 | 001 | 3552.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M26 | 25839935201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 2 |  | N | 17 | Avoidable, In-House Designer | Major Sturctural Component Changes | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 122 | 2195.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 115 | 3005.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7M27 | 43648015201 |  | 2 | CPI | 1 | 012 | 2903.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M28 | 43754115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M28 | 43754115201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M33 | 43764915201 |  | 2 | CPI | 1 | 012 | 4900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M34 | 41918235201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M34 | 41918235201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M34 | 41918235201 |  | 2 | CPI | 1 | 923 | 3551.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M34 | 41918235201 |  | 2 | CPI | 2 | 001 | 8917.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M34 | 41918235201 |  | 2 | CPI | 1 | 115 | 14047.98 | 14047.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7M34 | 41918235201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 20 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7M36 | 43648815201 |  | 2 | CPI | 1 | 106 | 4886.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7M36 | 43648815201 |  | 2 | CPI | 1 | 001 | 996.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7R06 | 44008915201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Test Projects | Changed Conditions | 1
07 | E7R08 | 43402515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R08 | 43402515201 |  | 2 | CPI | 1 | 503 | 11984.37 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R16 | 44255215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7R16 | 44255215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 20501.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 001 | 9572.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 30487.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R60 | 43920615201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 2420 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 1188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 17264.22 | 17264.22 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 107 | 1695.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 3145.56 | 3145.56 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 012 | 22476.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 4098.34 | 4098.34 | 4 |  | N | 0 | Avoidable, In-House CEI | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 106 | 6561.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 208 | 27990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015201 |  | 2 | CPI | 2 | 725 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
07 | T7389 | 43272015201 |  | 2 | CPI | 1 | 208 | 1962 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
07 | T7389 | 43272015602 |  | 2 | CPI | 1 | 007 | 46344.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 15807.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 118 | 18795.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 4250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 1116 | 350 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7391 | 43269815201 |  | 2 | CPI | 2 | 012 | 4040.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 007 | 657.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7391 | 43269815201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 101 | 3039.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 13157.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 1 | 007 | 9885.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7398 | 43473015201 |  | 2 | CPI | 2 | 101 | 3521.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 3 | 101 | 4052.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7398 | 43473015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 005 | 5990.38 | 5990.38 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 108 | 5311.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 101 | 2094.46 | 2094.46 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 4 | 106 | 7000 | 7000 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 5 | 112 | 1458.67 | 1458.67 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 6 | 101 | -2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 112 | 1458.67 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | 2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 2 | 112 | -1458.67 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 3 | 101 | 2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | -2094.46 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 2 |  | N | 3 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7399 | 43653015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 2 |  | N | 7 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7401 | 43480615201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7401 | 43480615201 |  | 2 | CPI | 4 | 101 | 493.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7401 | 43480615201 |  | 2 | CPI | 1 | 101 | -323.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 3371.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 2 | 113 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 3 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7404 | 43642015201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7415 | 43982935201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7415 | 43982935201 |  | 2 | CPI | 4 | 005 | 1072.73 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | T7421 | 43648115201 |  | 2 | CPI | 1 | 012 | 12711.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7421 | 43648115201 |  | 2 | CPI | 2 | 118 | 35670.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7422 | 44275215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7422 | 44275215201 |  | 2 | CPI | 3 | 112 | 1263 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 106 | 20830.53 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 2 | 106 | 1343 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 923 | 1076.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 2 | 115 | 204.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 115 | 24992.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 2 |  | N | 10 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7427 | 43704015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 2 |  | N | 8 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7429 | 43753015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7430 | 42907525201 |  | 2 | CPI | 1 | 007 | 869.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7430 | 42907525201 |  | 2 | CPI | 1 | 007 | 8414.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 021 | 3245 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 19190.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 003 | 26337.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 003 | 3174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 120.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 86.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 104.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 82.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 503 | 99.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 004 | 4653 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 107 | 5.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 3 | 118 | 5702.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 4 | 012 | 2061.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N19 | 42935015201 |  | 2 | CPI | 5 | 503 | 113 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 6 | 503 | 6060.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 350 | 1100 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8N19 | 42935015201 |  | 2 | CPI | 1 | 107 | 171.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 |  | 2 | CPI | 2 | 118 | 11649.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 105 | 17330.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 021 | 20983.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 2 | 023 | 4278.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 021 | 20586.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 2 | 023 | 8417.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 3 | 021 | 8511.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N92 | 42337225201 |  | 2 | CPI | 4 | 012 | 1970.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N92 | 42337225201 |  | 2 | CPI | 5 | 503 | 7228.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 6 | 503 | 4050.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 7 | 917 | 1173.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 021 | 5454.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 2 | 023 | 2527.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 022 | 14433.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 2 | 022 | 2607 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 |  | 2 | CPI | 1 | 009 | 15083.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N92 | 42337225201 |  | 2 | CPI | 2 | 023 | 6483.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N92 | 42337225201 |  | 2 | CPI | 3 | 021 | 8879.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 105 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P81 | 43561415201 |  | 2 | CPI | 2 | 101 | 25914 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 101 | 4871.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 2 | 101 | 2527 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P81 | 43561415201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 107 | 935 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 021 | 3899.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 2 | 003 | 5478.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 108 | 2851.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 021 | 13242.05 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 2 | 023 | 2208.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 108 | 1716.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 2 | 503 | -7606.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P89 | 43546215201 |  | 2 | CPI | 3 | 115 | 23330.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 4 | 023 | 1002.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 503 | 7606.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P89 | 43546215201 |  | 2 | CPI | 2 | 004 | 17363.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P89 | 43546215201 |  | 2 | CPI | 3 | 010 | 3806.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P89 | 43546215201 |  | 2 | CPI | 1 | 919 | 7643.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 106 | 10401.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 2 | 005 | 2454.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
08 | E8Q39 | 43730015201 |  | 2 | CPI | 3 | 117 | 815.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 012 | 2755.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q39 | 43730015201 |  | 2 | CPI | 2 | 012 | 32754.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q39 | 43730015201 |  | 2 | CPI | 3 | 503 | 17485.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 4126.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 8507.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 2 | 131 | 5730.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 003 | 3099.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q39 | 43730025201 |  | 2 | CPI | 1 | 131 | 6519.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q39 | 43730025201 |  | 2 | CPI | 2 | 105 | 12264.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q39 | 43730015201 |  | 2 | CPI | 1 | 503 | 40513.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q41 | 43516715201 |  | 2 | CPI | 1 | 009 | 1264.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8Q41 | 43516535201 |  | 2 | CPI | 1 | 021 | 2916.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
08 | E8Q41 | 43516715201 |  | 2 | CPI | 1 | 118 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q41 | 43516535201 |  | 2 | CPI | 1 | 021 | 14007.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517235201 |  | 2 | CPI | 1 | 023 | 704.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517135201 |  | 2 | CPI | 1 | 023 | 1630.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517235201 |  | 2 | CPI | 1 | 023 | 1778.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q54 | 43517135201 |  | 2 | CPI | 1 | 023 | 6384.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 101 | 3459.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 106 | 7996.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 1 | 023 | 3567.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q91 | 43915315201 |  | 2 | CPI | 2 | 022 | 23590.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q92 | 43798815201 |  | 2 | CPI | 1 | 012 | 9229.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798815201 |  | 2 | CPI | 1 | 023 | 3866.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798835201 |  | 2 | CPI | 1 | 012 | 9893.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798815201 |  | 2 | CPI | 1 | 023 | 10090.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798815201 |  | 2 | CPI | 1 | 023 | 1658.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798815201 |  | 2 | CPI | 2 | 023 | 14909.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q92 | 43798815201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 11880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 1048.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 26920.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 17650.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 4237.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 12350.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 3 | 101 | 18506.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | -12350.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 2 | 101 | 14585.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 5334.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 1 | 101 | 2193.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 2 | 101 | 3758.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 3 | 101 | 14643.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652135201 |  | 2 | CPI | 4 | 101 | 1980 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R18 | 43652115201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 886.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 441.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 1 | 503 | 1513.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R57 | 44290175201 |  | 2 | CPI | 2 | 503 | 4753.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 115 | 7181.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R59 | 44290185201 |  | 2 | CPI | 1 | 107 | 1701.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R64 | 44263115201 |  | 2 | CPI | 1 | 101 | 456 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R64 | 44263115201 |  | 2 | CPI | 2 | 101 | 550 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
RU5FUkFMIEFTUEhBTFQgQ08uIElOQy4iLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwNS8yMy8yMDE4IiwxNDM2MjgxLiwxNTE4MjY1LiwxNDMwMjY1Liw4MTk4NC4wMCwwLiwxNDI3NjMzLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwxNDMwMjY1LiwxNDI3NjMzLiwtMjYzMi4sMTU1MjYzNy4sIiIsIiIsIiINCiIwNCIsIlQ0NDg2IiwiNDMxNjU3MTUyMDEiLCJGNDU0NzY3MzE0IiwiUk9BRFdBWSBDT05TVFJVQ1RJT04gTExDIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMDYvMTMvMjAxOCIsMzI2MDM5My4sMzYwOTY3NC4sMzQwMjQ0NC4sMzQ5MjgxLjUwLDAuLDMzOTY3ODkuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDM0MDI0NDQuLDMzOTY3ODkuLC01NjU2LiwzNTA0NzQyLiwiIiwiIiwiIg0KIjA0IiwiVDQ0ODciLCI0MzA2MDgyNTIwMSIsIkY1OTA3NTMwMzkiLCJXRUVLTEVZIEFTUEhBTFQgUEFWSU5HIElOQy4iLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwMi8yNy8yMDE5Iiw3NTUxOTEuLDc1NTE5MS4sNjU1MTg3LiwuMDAsMC4sNjU0NzAyLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiw2NTUxODcuLDY1NDcwMi4sLTQ4Ni4sNjg0Njc0LiwiIiwiIiwiIg0KIjA0IiwiVDQ0OTAiLCI0MzQ2NzQxNTIwMSIsIkY0NTQ3NjczMTQiLCJST0FEV0FZIENPTlNUUlVDVElPTiBMTEMiLCJOL0EiLCJOL0EiLCJOL0EiLCJOL0EiLCIwMS8zMC8yMDE5IiwxNDg3MjUwLiwxNTAxODM1LiwxNDk4OTgxLiwxNDU4NS4yNSwwLiwxNTA3MjQ1LiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwxNDk4OTgxLiwxNTA3MjQ1Liw4MjY0LiwxNjEyMjUxLiwiIiwiIiwiIg0KIjA0IiwiVDQ0OTIiLCI0Mzc4MzcxNTIwMSIsIkYyMDE5Mjg0NzkiLCJKLlcuIENIRUFUSEFNIExMQyIsIk4vQSIsIk4vQSIsIk4vQSIsIk4vQSIsIjEyLzA1LzIwMTgiLDExODA4MDQuLDExODA4MDQuLDEwODg3MDYuLC4wMCwwLiwxMDkyNzQ5LiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiwwLiw

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P91 | 42271055201 | 012 |  | 5 | 044 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1P91 | 42271055201 | 115 |  | 5 | 044 | 2 | 2 | N | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P94 | 43493915201 | 118 |  | 14 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1R51 | 43800815201 | 503 |  | 6 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R80 | 43771615201 | 503 |  | 11 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1671 | 43560615201 | 503 |  | 1 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1713 | 43355215201 | 007 |  | 28 | 015 | 1 | 1 | N | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1725 | 43501515201 | 131 |  | 30 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
02 | E2V70 | 42747515201 | 024 |  | 60 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
02 | E2V70 | 42747515201 | 022 |  | 51 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
02 | E2V71 | 43430015201 | 007 |  | 42 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2W51 | 20950355201 | 012 |  | 12 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X44 | 42879715201 | 015 |  | 45 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2X44 | 42879715201 | 007 |  | 15 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X44 | 42879715201 | 503 |  | 7 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y23 | 43500215201 | 016 |  | 14 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | E2Y77 | 43606615201 | 503 |  | 3 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2577 | 43245215201 | 012 |  | 3 | 049 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2612 | 42360825201 | 005 |  | 23 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2621 | 20800145201 | 003 |  | 21 | 065 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2621 | 20800145201 | 023 |  | 8 | 079 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2621 | 20800145201 | 023 |  | 1 | 080 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2661 | 43433715201 | 001 |  | 27 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2686 | 43611815201 | 005 |  | 30 | 009 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2688 | 43500115201 | 016 |  | 14 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3P84 | 43625815201 | 016 |  | 21 | 009 | 1 | 2 | N | Avoidable, In-House Designer | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3R15 | 43730715201 | 503 |  | 8 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R15 | 43730715201 | 116 |  | 18 | 011 | 1 | 2 | N | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3R73 | 43672615201 | 107 |  | 18 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3S52 | 41767755201 | 010 |  | 15 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3485 | 42695315201 | 106 |  | 3 | 004 | 1 | 5 | C | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3485 | 42695315201 | 106 |  | 26 | 017 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 2 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3485 | 42695315201 | 105 |  | 3 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3488 | 40979275201 | 106 |  | 1 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 005 |  | 14 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
03 | T3488 | 40979275201 | 106 |  | 1 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 120 |  | 18 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | T3488 | 40979275201 | 106 |  | 1 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3488 | 40979275201 | 126 |  | 6 | 027 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3488 | 40979275201 | 105 |  | 10 | 033 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3543 | 22044275201 | 015 |  | 12 | 079 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3584 | 42551925201 | 101 |  | 38 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3584 | 42551925201 | 101 |  | 5 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3586 | 42862415201 | 119 |  | 30 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
03 | T3605 | 43390515201 | 106 |  | 10 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3617 | 43228615201 | 503 |  | 72 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3637 | 43626515201 | 700 |  | 17 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3661 | 43255915201 | 106 |  | 7 | 020 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3667 | 43273835201 | 402 |  | 30 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3693 | 43776515201 | 402 |  | 39 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
03 | T3726 | 43551825201 | 115 |  | 18 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4N98 | 42170745201 | 004 |  | 2 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T52 | 43784715201 | 005 |  | 7 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4400 | 22777415201 | 120 |  | 2 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
04 | T4400 | 22777415201 | 106 |  | 2 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4400 | 22777415201 | 001 |  | 5 | 079 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4400 | 22777415201 | 009 |  | 38 | 080 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
05 | E5Z02 | 43365415201 | 012 |  | 11 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5506 | 41840325201 | 106 |  | 91 | 056 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6L51 | 43029129201 | 503 |  | 28 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6337 | 41809115201 | 115 |  | 120 | 064 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6338 | 41463315201 | 003 |  | 7 | 054 | 1 | 1 | N | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6338 | 41463315201 | 503 |  | 14 | 054 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6338 | 41463315201 | 118 |  | 137 | 061 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6401 | 41247395201 | 005 |  | 69 | 025 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6437 | 43634215201 | 007 |  | 15 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6448 | 43792015201 | 503 |  | 29 | 008 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6458 | 44019115201 | 016 |  | 12 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7K24 | 41101145201 | 018 |  | 2 | 069 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
07 | T7391 | 43269815201 | 007 |  | 13 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7399 | 43653015201 | 108 |  | 10 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7421 | 43648115201 | 450 |  | 11 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
08 | E8N19 | 42935015201 | 103 |  | 29 | 036 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8N19 | 42935015201 | 118 |  | 14 | 036 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8N19 | 42935015201 | 503 |  | 7 | 036 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 503 |  | 2 | 036 | 4 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N19 | 42935015201 | 113 |  | 3 | 036 | 5 | 0 | N | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 | 115 |  | 11 | 036 | 6 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N19 | 42935015201 | 105 |  | 11 | 036 | 7 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N19 | 42935015201 | 503 |  | 7 | 036 | 8 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N92 | 42337225201 | 503 |  | 155 | 097 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
€€€€endefaulttablestyle.sty@Ùš?€èv (øTHenpurple_medium1.styeNEÙŸo@€èv (øathuid_default.sty“€€€€€€€€€€ZÙ€A€èv (ø€€€€ukid_default.sty€€€€€€€€€€€€€€_Ù•€B€èv (ø€€€€enteal_medium2.sty€€€€€€€€€€TÙŽ€C€èv (ø€€€€itid_default.sty€€€€€€€€€€€€€€iÙƒ€D€èv (ø€€€€nlid_default.sty€€€€€€€€€€€€€€nÙ„€E€contract_profile_commitments.fexcÙ¹F€contract_profile_report_periods.fexxÙ²oG€eocfm902_contract_summary.acx}Ù·øH€eocfm902_contract_summary.masrÙ¨“I€eocfm024_bidder_opportuni.acxwÙ­‹J€eocfm903_contract_dollars.acxŒØ¦‹K€èv (ø‹iwid_default.sty€€€€€€Ø[L€èv (ø“ptid_default.sty_‹ €èv (ø†Ø\M€èv (ø¦¦š2`ørö“gtö“_default.sty2ing›ØQnN€contract_profile_prime_details.fexØJO€eocfm024_bidder_opportunity.mas•ØOP€eocfm024_bidder_opportunity.acxªØ@Q€èv (øfiid_default.styy¯ØER€èv (øfrid_default.sty¤Ø~S€èv (øhrid_default.sty.styø¹ØsT€èv (øTMsvid_default.styintl/EN¾ØtoU€èv (øatkoid_default.sty€€€€€€€€€€€€€€³Øi€V€contract_profile_sub_payments.fexÈØb€W€èv (ø€€€€enturquoise_theme.sty€€€€ÍØg€X€eocfm024_bidder_opportuni.masÂØY€eocfm025_bidder_opportuni.masÇØ øZ€èv (øøesid_default.sty€
€èv (øÜØ[€èv (øtnoid_default.styhemegÑØ n\€èv (øuiruid_default.styÖØ ]€èv (øjaid_default.styëØ^€èv (øtwid_default.styàØ:_€èv (øroid_default.styåØ?`€contracts_not_reported_active.fexúØ0a€eocfm025_bidder_opportuni.acxÿØ5db€èv (ø plid_default.styí‹@H¹õ“ôØ.“c€contract_profile_cont_detail.fex Ø#‹d€èv (øøfcid_default.sty]o‘j°…°í‹179770C4

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
Áí‹P°yö“ ˜ÕàÅ=UT €˜¾í‹þÿÿÿÿÿÿ title=We¤^—U€ PàOÐ ê:i¢Ø+00/C:\x1ƒO Usersd ï¾sN¬$ƒO .ãa[:£ú€Users@shell32.dll
08 | [13 empty] | Unavoidable, No Remedial Action Required
07 | [13 empty] | Unavoidable, No Remedial Action Required
06 | [13 empty] | Unavoidable, No Remedial Action Required
05 | [13 empty] | Avoidable, Third Party
04 | [13 empty] | Avoidable, In-House Designer
03 | [13 empty] | Avoidable, In-House CEI
02 | [13 empty] | Avoidable, Design Consultant
01 | [13 empty] | Unavoidable, No Remedial Action Required
01 | [13 empty] | Avoidable, Third Party
01 | [13 empty] | Avoidable, In-House Designer
01 | [13 empty] | Avoidable, In-House CEI
01 | [13 empty] | Avoidable, Design Consultant
01 | [13 empty] | Avoidable, CEI Consultant
Áí‹P°yö“ ˜ÕàÅ=UT €˜¾í‹þÿÿÿÿÿÿ title=We¤^—U€ PàOÐ ê:i¢Ø+00/C:\x1ƒO Usersd ï¾sN¬$ƒO .ãa[:£ú€Users@shell32.dll

## Card 2 TE Data - PPP
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
Áí‹P°yö“ ˜ÕàÅ=UT €˜¾í‹þÿÿÿÿÿÿ title=We¤^—U€ PàOÐ ê:i¢Ø+00/C:\x1ƒO Usersd ï¾sN¬$ƒO .ãa[:£ú€Users@shell32.dll
08 | [9 empty] | Unavoidable, No Remedial Action Required
07 | [9 empty] | Unavoidable, No Remedial Action Required
06 | [9 empty] | Unavoidable, No Remedial Action Required
05 | [9 empty] | Avoidable, Third Party
04 | [9 empty] | Avoidable, In-House Designer
03 | [9 empty] | Avoidable, In-House CEI
02 | [9 empty] | Avoidable, Design Consultant
01 | [9 empty] | Unavoidable, No Remedial Action Required
01 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, In-House Designer
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, Design Consultant
01 | [9 empty] | Avoidable, CEI Consultant

## Sheet1 (hidden)
01CO | 01 | T1634 | 43137315201 | 2015-10-28 | QTR2 | 15/16 | 2 | 4 | 325 | 500 | 500 | 0 | 0 | 0 | 147 | 28 | 8177462 | 97126 | 8080336 | 8672530 | 8450258 | 0 | 0 | 0 | 8450258 | 8318044 | -132214 | 495068 | 113 | 0 | 28 | 357778 | 0 | 0 | 0 | 41850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 537929 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2017-12-29 | QTR2 | 17/18 | 115 | 9745220.76 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO | 31 | 01co | 1 | 31
01CO | 01 | T1636 | 43323815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 125 | 147 | 147 | 0 | 0 | 0 | 22 | 0 | 1444112 | 0 | 1444112 | 1455710 | 1455710 | 0 | 0 | 0 | 1455710 | 1456120 | 410 | 11598 | 6 | 0 | 0 | 11598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11598 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2017-03-11 | QTR3 | 16/17 | 113 | 1303710.84 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 13 | 01do | 32 | 44
01CO | 01 | T1664 | 20103265201 | 2017-02-22 | QTR3 | 16/17 | 2 | 24 | 687 | 885 | 676 | 209 | 0 | 0 | 74 | 124 | 39141064 | 150000 | 38991064 | 41032774 | 41293102 | 0 | 2220000 | 2220000 | 43513102 | 41952186 | -1499517 | 1891710 | 39 | 0 | 0 | 796796 | 0 | 0 | 120 | 1378127 | 4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1929092 | 4958 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2019-04-15 | QTR4 | 18/19 | 106 | 43211572.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | -250656 | 0 |  | CO | 28 | 02co | 45 | 72
01CO | 01 | T1667 | 43494215201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 160 | 167 | 88 | 79 | 0 | 0 | 7 | 0 | 1182957 | 0 | 1182957 | 696968 | 671825 | 0 | 0 | 0 | 671825 | 678334 | 6509 | -485989 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485989 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-07-03 | QTR1 | 19/20 |  | 2017-03-31 | QTR3 | 16/17 | 108 | 1125231.13 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 24 | 02do | 73 | 96
01CO | 01 | T1671 | 43560615201 | 2016-12-07 | QTR2 | 16/17 | 2 | 9 | 435 | 628 | 628 | 0 | 0 | 0 | 186 | 7 | 8453536 | 97171 | 8356365 | 8694533 | 8807307 | 0 | 0 | 0 | 8807307 | 9064650 | 300819 | 240997 | 138 | 0 | 7 | 224121 | 0 | 0 | 0 | 24860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 261807 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 108 | 8498513.73 |  |  | 2 | 47 | 0 | 0 | 0 | 0 |  | CO | 34 | 03co | 97 | 130
01CO | 01 | T1693 | 43450215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 8 | 250 | 409 | 409 | 0 | 0 | 0 | 126 | 33 | 2535000 | 0 | 2535000 | 2909249 | 2922189 | 0 | 0 | 0 | 2922189 | 2922984 | 795 | 374249 | 101 | 0 | 33 | 344330 | 0 | 0 | 0 | 20272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 374249 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 108 | 2562824.24 | B1 | ACC - NO EXCUSE BONUS | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 12 | 03do | 131 | 142
01CO | 01 | T1697 | 43534915201 | 2018-01-31 | QTR3 | 17/18 | 5 | 1 | 200 | 238 | 221 | 17 | 0 | 0 | 38 | 0 | 2532999 | 50000 | 2482999 | 2582335 | 2599237 | 0 | 0 | 0 | 2599237 | 2598348 | -889 | 49336 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50578 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-12-05 | QTR2 | 19/20 |  | 2019-03-11 | QTR3 | 18/19 | 115 | 2201660.61 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 26 | 04co | 143 | 168
01CO | 01 | T1701 | 43498615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 3 | 580 | 635 | 485 | 150 | 0 | 0 | 55 | 0 | 8087167 | 75299 | 8011868 | 8023343 | 7632042 | 0 | 570000 | 570000 | 8202042 | 7675787 | -516267 | -63824 | 40 | 0 | 0 | 37019 | 0 | 0 | 0 | -73677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29433 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 118 | 8094281.54 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 20 | 04do | 169 | 188
01CO | 01 | T1704 | 44011615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 0 | 100 | 165 | 165 | 0 | 0 | 0 | 65 | 0 | 211559 | 9615 | 201944 | 211559 | 204310 | 0 | 0 | 0 | 204310 | 204310 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-07 | QTR3 | 18/19 | 113 | 255657.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 19 | 05co | 189 | 207
01CO | 01 | T1705 | 44013315201 | 2018-05-23 | QTR4 | 17/18 | 3 | 0 | 110 | 133 | 132 | 1 | 0 | 0 | 23 | 0 | 448245 | 25313 | 422932 | 448245 | 415980 | 0 | 0 | 0 | 415980 | 415980 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-17 | QTR2 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 115 | 498434.82 |  |  | 0 | 5 | 0 | 0 | 0 | 0 | T | CO | 22 | 05do | 208 | 229
01CO | 01 | T1706 | 43658615201 | 2018-06-13 | QTR4 | 17/18 | 2 | 1 | 325 | 397 | 374 | 23 | 0 | 0 | 72 | 0 | 7786066 | 101721 | 7684345 | 7543630 | 7286083 | 0 | 0 | 0 | 7286083 | 7247442 | -38640 | -242436 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -242436 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2019-11-04 | QTR2 | 19/20 | 108 | 9348245.16 |  |  | 0 | 27 | 0 | 0 | -242436 | 0 |  | CO | 19 | 06co | 230 | 248
01CO | 01 | T1707 | 44013815201 | 2018-06-13 | QTR4 | 17/18 | 4 | 1 | 125 | 167 | 114 | 53 | 0 | 0 | 22 | 20 | 394057 | 26456 | 367601 | 401319 | 389400 | 0 | 0 | 0 | 389400 | 389394 | -6 | 7262 | 17 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21906 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-19 | QTR2 | 19/20 |  | 2019-07-09 | QTR1 | 19/20 | 108 | 500274.93 |  |  | 20 | 5 | 0 | 0 | 0 | 0 |  | CO | 13 | 06do | 249 | 261
01CO | 01 | T1711 | 43121915201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 125 | 199 | 213 | -14 | 14 | 0 | 34 | 40 | 719941 | 34577 | 685364 | 719941 | 689498 | -24975 | 0 | -24975 | 664523 | 663884 | -639 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8973 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-05-27 | QTR4 | 19/20 |  | 2019-12-17 | QTR2 | 19/20 | 113 | 651945.49 |  |  | 40 | 14 | 0 | 0 | 0 | 0 |  | CO | 13 | 07co | 262 | 274
01CO | 01 | T1713 | 43355215201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 230 | 408 | 407 | 1 | 0 | 0 | 178 | 0 | 2526300 | 50000 | 2476300 | 2681334 | 2687161 | 0 | 0 | 0 | 2687161 | 2682036 | -5125 | 155034 | 128 | 28 | 0 | 74449 | 0 | 0 | 0 | 130585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 205034 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-10-30 | QTR2 | 19/20 | 115 | 2797558.23 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 25 | 07do | 275 | 299
01CO | 01 | T1714 | 43837615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 90 | 107 | 107 | 0 | 0 | 0 | 17 | 0 | 270550 | 15457 | 255093 | 270550 | 256893 | 0 | 0 | 0 | 256893 | 256893 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 118 | 302948.32 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 300 | 299
01CO | 01 | T1725 | 43501515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 0 | 100 | 159 | 159 | 0 | 0 | 0 | 59 | 0 | 984573 | 29273 | 955300 | 984573 | 955300 | 0 | 0 | 0 | 955300 | 955300 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-19 | QTR4 | 19/20 |  | 2020-02-21 | QTR3 | 19/20 | 118 | 713682.23 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 15 | 08do | 300 | 314
01CO | 01 | T1727 | 43800715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 175 | 317 | 317 | 0 | 0 | 0 | 95 | 47 | 2658381 | 50000 | 2608381 | 2763353 | 2697261 | 0 | 0 | 0 | 2697261 | 2689819 | -4557 | 104972 | 67 | 0 | 0 | 0 | 0 | 0 | 47 | 96037 | 56605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 102087 | 56605 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-06-08 | QTR4 | 19/20 |  | 2020-01-28 | QTR3 | 19/20 | 113 | 2768479.93 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1729 | 43837415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 140 | 162 | 162 | 0 | 0 | 0 | 22 | 0 | 985800 | 50000 | 935800 | 1045343 | 996037 | 0 | 0 | 0 | 996037 | 995552 | -485 | 59543 | 17 | 0 | 0 | 694 | 0 | 0 | 0 | 59543 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60237 | 1350 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 115 | 952402.62 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1732 | 43318515201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 110 | 115 | 100 | 15 | 0 | 0 | 5 | 0 | 140241 | 0 | 140241 | 140241 | 131642 | 0 | 0 | 0 | 131642 | 131642 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264688872 | SOUTHERN STIRPING SOLUTIONS LL | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-16 | QTR4 | 18/19 | 113 | 0 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1734 | 43498815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 130 | 141 | 123 | 18 | 0 | 0 | 11 | 0 | 545828 | 34187 | 511641 | 545828 | 508665 | 0 | 0 | 0 | 508665 | 508665 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 113 | 633612.36 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1736 | 43320515201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 100 | 112 | 112 | 0 | 0 | 0 | 12 | 0 | 789502 | 40502 | 749000 | 789502 | 749000 | 0 | 0 | 0 | 749000 | 749000 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 118 | 784219.14 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1737 | 43826915201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 100 | 128 | 97 | 31 | 0 | 0 | 28 | 0 | 328300 | 0 | 328300 | 328300 | 328300 | 0 | 0 | 0 | 328300 | 328300 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-09-04 | QTR1 | 19/20 | 108 | 356575.21 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1738 | 43837115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 108 | 108 | 0 | 0 | 0 | 18 | 0 | 870522 | 27435 | 843087 | 870522 | 829068 | 0 | 0 | 0 | 829068 | 829068 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 115 | 590610.52 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1739 | 43837815201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 120 | 148 | 148 | 0 | 0 | 0 | 28 | 0 | 1095691 | 43494 | 1052197 | 1099220 | 1055726 | 0 | 0 | 0 | 1055726 | 1052773 | 576 | 3530 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 113 | 979242.1 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1741 | 44067415201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 80 | 96 | 96 | 0 | 0 | 0 | 16 | 0 | 366031 | 14031 | 352000 | 366031 | 355572 | 0 | 0 | 0 | 355572 | 355572 | 0 | 0 | 11 | 0 | 0 | 1231 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-11-07 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 115 | 396011.31 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1743 | 43800415201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 71 | 107 | 99 | 8 | 0 | 0 | 36 | 0 | 138436 | 0 | 138436 | 138436 | 138436 | 0 | 0 | 0 | 138436 | 138436 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 108 | 179132.62 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1749 | 44319925201 | 2019-01-30 | QTR3 | 18/19 | 4 | 1 | 110 | 126 | 126 | 0 | 0 | 0 | 16 | 0 | 335979 | 5815 | 330164 | 396256 | 382764 | 0 | 0 | 0 | 382764 | 382764 | 0 | 60277 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60277 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-10 | QTR2 | 19/20 |  | 2019-08-16 | QTR1 | 19/20 | 118 | 263307.07 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1753 | 43943215201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 200 | 218 | 136 | 82 | 0 | 0 | 18 | 0 | 1952155 | 50000 | 1902155 | 1971307 | 1962809 | 0 | 0 | 0 | 1962809 | 1962123 | -686 | 19152 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19152 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2020-02-24 | QTR3 | 19/20 | 108 | 2489141.93 | B0 | ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1765 | 43698215201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 90 | 94 | 94 | 0 | 0 | 0 | 4 | 0 | 371018 | 0 | 371018 | 371018 | 371018 | 0 | 0 | 0 | 371018 | 371018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 115 | 262342.57 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1766 | 44248515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 98 | 99 | 53 | 46 | 0 | 0 | 1 | 0 | 305000 | 0 | 305000 | 305000 | 305000 | 0 | 0 | 0 | 305000 | 305000 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-03-26 | QTR3 | 19/20 | 118 | 267579.22 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1769 | 44012315201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 364364 | 17734 | 346630 | 364364 | 355187 | 0 | 0 | 0 | 355187 | 355187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-06-23 | QTR4 | 19/20 |  | 2020-04-27 | QTR4 | 19/20 | 113 | 367495.83 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1P56 | 41968815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 150 | 180 | 180 | 0 | 0 | 0 | 30 | 0 | 1109997 | 50000 | 1059997 | 1109997 | 793278 | 0 | 0 | 0 | 793278 | 793278 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2017-10-27 | QTR2 | 17/18 | 115 | 2383057.05 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P91 | 42271055201 | 2017-04-20 | QTR4 | 16/17 | 1 | 7 | 560 | 729 | 725 | 4 | 0 | 0 | 169 | 0 | 10071503 | 104026 | 9967477 | 10247666 | 9983254 | 0 | 0 | 0 | 9983254 | 10164043 | 198791 | 176163 | 120 | 5 | 0 | 55015 | 0 | 5 | 0 | 112805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11987 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 179808 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 115 | 11091792.08 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P94 | 43493915201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 400 | 481 | 481 | 0 | 0 | 0 | 81 | 0 | 9111251 | 94944 | 9016307 | 9111251 | 9282956 | 0 | 0 | 0 | 9282956 | 9644340 | 361384 | 0 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 16913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 26214 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 113 | 9289725.34 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q23 | 43665015201 | 2018-02-13 | QTR3 | 17/18 | 1 | 0 | 340 | 462 | 525 | -63 | 63 | 0 | 90 | 32 | 918123 | 50000 | 868123 | 918123 | 868123 | -104895 | 0 | -104895 | 763228 | 763228 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 108 | 1567525 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 32 | 30 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q29 | 42584115201 | 2017-04-20 | QTR4 | 16/17 | 2 | 15 | 650 | 1043 | 726 | 317 | 0 | 0 | 71 | 322 | 54145606 | 150000 | 53995606 | 56232960 | 55752280 | 0 | 2500000 | 2500000 | 58252280 | 56885286 | -1366994 | 2087354 | 38 | 0 | 208 | 2137914 | 84393 | 0 | 114 | 329014 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27149 | 14314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322 | 2110169 | 103094 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 113 | 61229521.11 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | -383908 | 0 |  | DO
01DO | 01 | E1R12 | 43668215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 0 | 175 | 188 | 123 | 65 | 0 | 0 | 13 | 0 | 1472083 | 50000 | 1422083 | 1472083 | 1445724 | 0 | 65000 | 65000 | 1510724 | 1446603 | -64121 | 0 | 4 | 0 | 0 | 15380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15380 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2019-09-16 | QTR1 | 19/20 | 115 | 1181939.29 | B1 | ACC - NO EXCUSE BONUS | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R26 | 43319415201 | 2018-08-16 | QTR1 | 18/19 | 2 | 0 | 125 | 144 | 141 | 3 | 0 | 0 | 19 | 0 | 604486 | 29809 | 574677 | 604486 | 584381 | 0 | 0 | 0 | 584381 | 583598 | -783 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-06 | QTR4 | 18/19 | 108 | 489569.69 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R46 | 43806315201 | 2018-07-19 | QTR1 | 18/19 | 1 | 0 | 185 | 208 | 177 | 31 | 0 | 0 | 23 | 0 | 3730005 | 50000 | 3680005 | 3730005 | 3622277 | 0 | 0 | 0 | 3622277 | 3609915 | -12362 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-03-26 | QTR3 | 18/19 | 118 | 4986764.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R51 | 43800815201 | 2018-09-20 | QTR1 | 18/19 | 1 | 0 | 165 | 233 | 232 | 1 | 0 | 0 | 68 | 0 | 2579000 | 50000 | 2529000 | 2579000 | 2523711 | 0 | 0 | 0 | 2523711 | 2514757 | -8954 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-10-31 | QTR2 | 19/20 | 113 | 2698176.21 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R66 | 43641515201 | 2019-02-21 | QTR3 | 18/19 | 1 | 2 | 80 | 124 | 200 | -76 | 76 | 0 | 29 | 15 | 5199494 | 50000 | 5149494 | 5281274 | 4820096 | -261972 | -160000 | -421972 | 4398124 | 4386421 | 0 | 81780 | 23 | 0 | 0 | 1940 | 0 | 0 | 0 | 19302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 91319 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-16 | QTR4 | 19/20 |  | 2019-12-26 | QTR2 | 19/20 | 115 | 3837739.52 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R80 | 43771615201 | 2019-04-18 | QTR4 | 18/19 | 1 | 1 | 65 | 96 | 96 | 0 | 0 | 0 | 31 | 0 | 157000 | 9525 | 147475 | 157000 | 148434 | 0 | 0 | 0 | 148434 | 148434 | 0 | 0 | 16 | 0 | 0 | 6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 6184 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 108 | 169094.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S00 | 43943515201 | 2019-05-23 | QTR4 | 18/19 | 2 | 0 | 140 | 159 | 118 | 41 | 0 | 0 | 19 | 0 | 2112776 | 50000 | 2062776 | 2112776 | 2088952 | 0 | 0 | 0 | 2088952 | 2065283 | -23668 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-02-27 | QTR3 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 108 | 3162692.93 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S90 | 43506515201 | 2019-12-05 | QTR2 | 19/20 | 1 | 0 | 80 | 80 | 55 | 25 | 0 | 0 | 0 | 0 | 264680 | 12505 | 252175 | 264680 | 252175 | 0 | 0 | 0 | 252175 | 252175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2020-04-21 | QTR4 | 19/20 | 118 | 235218.96 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2562 | 20821175201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 540 | 785 | 785 | 0 | 0 | 0 | 134 | 111 | 15887487 | 150000 | 15737487 | 16037487 | 15865517 | 0 | 0 | 0 | 15865517 | 15510573 | -354944 | 150000 | 87 | 0 | 38 | 50354 | 0 | 0 | 6 | 152953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 203307 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2017-09-29 | QTR1 | 17/18 | 214 | 16006483.74 |  |  | 44 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2576 | 43091115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 13 | 340 | 624 | 717 | -93 | 93 | 0 | 64 | 220 | 7004346 | 70466 | 6933880 | 8247072 | 8273395 | -350610 | 0 | -350610 | 7922785 | 7815365 | -95677 | 1242726 | 29 | 0 | 4 | 33738 | 1648 | 0 | 98 | 237085 | 153271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 898427 | 0 | 0 | 5 | 38629 | 32695 | 0 | 0 | 0 | 0 | 0 | 214 | 1207879 | 187614 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2017-12-20 | QTR2 | 17/18 | 208 | 5694356.97 |  |  | 6 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2577 | 43245215201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 370 | 801 | 829 | -28 | 28 | 0 | 196 | 235 | 13015506 | 146980 | 12868525 | 13328963 | 13247968 | -129472 | 0 | -129472 | 13118496 | 12926851 | -191646 | 313457 | 83 | 3 | 41 | 303690 | 57134 | 0 | 2 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15609 | 5643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 5 | 71812 | 70550 | 0 | 0 | 0 | 0 | 3 | 235 | 419201 | 133327 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2018-03-07 | QTR3 | 17/18 | 208 | 11330020.88 |  |  | 37 | 110 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2612 | 42360825201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 170 | 297 | 310 | -13 | 13 | 0 | 102 | 25 | 2241677 | 50000 | 2191677 | 2241677 | 2217516 | -20592 | 0 | -20592 | 2196924 | 2204364 | 7440 | 0 | 43 | 0 | 2 | 5647 | 0 | 0 | 20 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 1410 | 0 | 0 | 0 | 0 | 0 | 23 | 25 | 29364 | 0 | F650108710 | R.E. ARNOLD CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2017-03-04 | QTR3 | 16/17 | 214 | 1830224.45 |  |  | 25 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2616 | 20800155201 | 2016-03-30 | QTR3 | 15/16 | 4 | 5 | 950 | 1229 | 1165 | 64 | 0 | 0 | 279 | 0 | 48935291 | 150000 | 48785291 | 48562222 | 47847275 | 0 | 0 | 0 | 47847275 | 49825494 | 2046752 | -373069 | 148 | 0 | 0 | 17383 | 0 | 0 | 0 | 134983 | 29037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -424218 | 29037 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-04-27 | QTR4 | 19/20 |  | 2019-10-17 | QTR2 | 19/20 | 214 | 61148938.06 |  |  | 0 | 131 | 0 | 0 | -576584 | 0 |  | CO
02CO | 02 | T2618 | 43091015201 | 2016-06-15 | QTR4 | 15/16 | 3 | 11 | 320 | 599 | 576 | 23 | 0 | 0 | 170 | 109 | 6623070 | 65216 | 6557854 | 7293436 | 7244868 | 0 | 0 | 0 | 7244868 | 7279110 | 45271 | 670366 | 127 | 0 | 39 | 100725 | 0 | 0 | 42 | 424074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 119928 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 648819 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-08 | QTR1 | 19/20 |  | 2018-08-13 | QTR1 | 18/19 | 208 | 5699133.54 |  |  | 33 | 43 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2621 | 20800145201 | 2016-06-20 | QTR4 | 15/16 | 2 | 6 | 800 | 1156 | 1156 | 0 | 0 | 0 | 323 | 33 | 49402252 | 150000 | 49252252 | 49868003 | 50029395 | 0 | 0 | 0 | 50029395 | 51188630 | 1252856 | 465751 | 181 | 21 | 0 | 163493 | 8734 | 0 | 33 | 200593 | 141476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78316 | 0 | 9 | 0 | 74599 | 22488 | 0 | 0 | 0 | 0 | 0 | 0 | 21607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 33 | 538607 | 172699 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 214 | 50264622.68 |  |  | 0 | 112 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2657 | 20781825201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 560 | 749 | 748 | 1 | 0 | 0 | 147 | 42 | 13545525 | 150000 | 13395525 | 13574913 | 13974107 | 0 | 0 | 0 | 13974107 | 14346429 | 400515 | 29388 | 101 | 0 | 30 | 66698 | 0 | 0 | 12 | 26717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 99695 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-12 | QTR3 | 19/20 |  | 2019-08-17 | QTR1 | 19/20 | 214 | 16380282.85 | B6 | ACC - LIQUIDATED SAVINGS | 42 | 46 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2658 | 41525215201 | 2017-04-26 | QTR4 | 16/17 | 4 | 5 | 400 | 592 | 592 | 0 | 0 | 0 | 113 | 79 | 7921243 | 480 | 7920763 | 8003005 | 8095808 | 0 | 0 | 0 | 8095808 | 8111040 | 15232 | 81763 | 65 | 0 | 0 | 0 | 0 | 0 | 59 | 81763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 81763 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-23 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 214 | 5941069.67 |  |  | 50 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2661 | 43433715201 | 2017-06-14 | QTR4 | 16/17 | 2 | 5 | 180 | 450 | 450 | 0 | 0 | 0 | 119 | 151 | 3381935 | 50000 | 3331935 | 3744790 | 3805039 | 0 | 0 | 0 | 3805039 | 3814801 | 9762 | 362855 | 62 | 27 | 48 | 160331 | 0 | 0 | 103 | 207059 | 35834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 151 | 368378 | 35834 | F201668768 | CAPPS LAND MANAGEMENT AND MATER | N/A | N/A | N/A | N/A | 2019-10-28 | QTR2 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 208 | 2832770.92 |  |  | 55 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2678 | 21028685201 | 2017-05-24 | QTR4 | 16/17 | 4 | 4 | 330 | 470 | 470 | 0 | 0 | 0 | 118 | 22 | 5834914 | 50000 | 5784914 | 5935993 | 6210758 | 0 | 0 | 0 | 6210758 | 6236655 | 28928 | 101079 | 87 | 0 | 22 | 115529 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 117937 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2018-12-18 | QTR2 | 18/19 | 216 | 5533447.16 |  |  | 8 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2679 | 43617415201 | 2017-12-06 | QTR2 | 17/18 | 2 | 2 | 350 | 518 | 518 | 0 | 0 | 0 | 100 | 68 | 10753984 | 78530 | 10675454 | 10978696 | 11000190 | 0 | 0 | 0 | 11000190 | 11198057 | 197867 | 224712 | 67 | 0 | 12 | 149047 | 0 | 0 | 56 | 21709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 170756 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-21 | QTR3 | 19/20 |  | 2019-09-19 | QTR1 | 19/20 | 208 | 7872133.21 |  |  | 62 | 33 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2682 | 43201215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 3 | 350 | 548 | 548 | 0 | 0 | 0 | 72 | 126 | 3548288 | 50000 | 3498288 | 3732180 | 3999294 | 0 | 0 | 0 | 3999294 | 4055594 | 56300 | 183891 | 40 | 0 | 74 | 112571 | 0 | 0 | 27 | 67449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7145 | 0 | 0 | 0 | 18339 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 205504 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-06-05 | QTR4 | 19/20 |  | 2019-10-15 | QTR2 | 19/20 | 214 | 3940432.98 |  |  | 47 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2683 | 43616215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 300 | 432 | 432 | 0 | 0 | 0 | 107 | 25 | 9121503 | 103598 | 9017905 | 9130119 | 9355463 | 0 | 0 | 0 | 9355463 | 10160460 | 804997 | 8616 | 80 | 0 | 25 | 16882 | 0 | 0 | 0 | 13056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 29939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 208 | 10382551.07 |  |  | 25 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2686 | 43611815201 | 2018-01-31 | QTR3 | 17/18 | 1 | 1 | 220 | 375 | 375 | 0 | 0 | 0 | 117 | 38 | 2698000 | 50000 | 2648000 | 2725471 | 2926429 | 0 | 0 | 0 | 2926429 | 3007330 | 80901 | 27471 | 62 | 0 | 0 | 5380 | 0 | 0 | 0 | 21027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 27471 | 27471 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38 | 53877 | 27471 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 216 | 2798350.62 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2687 | 43617315201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 280 | 374 | 335 | 39 | 0 | 0 | 94 | 0 | 5141768 | 65349 | 5076419 | 5141768 | 5033451 | 0 | 0 | 0 | 5033451 | 5387836 | 354385 | 0 | 54 | 0 | 0 | 8533 | 0 | 0 | 0 | 17379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25912 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 214 | 6618371.27 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2688 | 43500115201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 169 | 232 | 232 | 0 | 0 | 0 | 63 | 0 | 1688461 | 50000 | 1638461 | 1754543 | 1709557 | 0 | 0 | 0 | 1709557 | 1709557 | 0 | 66083 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 66083 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2019-07-31 | QTR1 | 19/20 |  | 2019-04-09 | QTR4 | 18/19 | 209 | 1908914.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2689 | 43616115201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 270 | 351 | 331 | 20 | 0 | 0 | 81 | 0 | 1995665 | 50000 | 1945665 | 1995665 | 2049720 | 0 | 0 | 0 | 2049720 | 2101020 | 51299 | 0 | 22 | 0 | 0 | 24965 | 0 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28054 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | QTR3 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 216 | 2153022.57 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2691 | 43617215201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 220 | 336 | 336 | 0 | 0 | 0 | 116 | 0 | 13785287 | 125571 | 13659716 | 13785287 | 14546489 | 0 | 0 | 0 | 14546489 | 15202892 | 656402 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 209 | 13297954.57 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2695 | 43615815201 | 2018-03-28 | QTR3 | 17/18 | 3 | 2 | 270 | 356 | 356 | 0 | 0 | 0 | 64 | 22 | 3836183 | 51520 | 3784663 | 3889514 | 3691380 | 0 | 0 | 0 | 3691380 | 3743642 | 52262 | 53332 | 27 | 0 | 0 | -65216 | 0 | 0 | 21 | 16571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -38928 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 3655364.59 |  |  | 22 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2704 | 43761615201 | 2018-06-13 | QTR4 | 17/18 | 1 | 1 | 265 | 330 | 283 | 47 | 0 | 0 | 55 | 10 | 6663346 | 62921 | 6600425 | 6750120 | 6920369 | 0 | 0 | 0 | 6920369 | 6898990 | -21380 | 86773 | 31 | 0 | 10 | 23703 | 0 | 0 | 0 | 78542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102245 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 208 | 6878488.39 |  |  | 10 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2708 | 44216935201 | 2019-04-24 | QTR4 | 18/19 | 1 | 3 | 120 | 139 | 75 | 64 | 0 | 0 | 19 | 0 | 368985 | 120 | 368865 | 374417 | 391272 | 0 | 0 | 0 | 391272 | 387389 | 0 | 5432 | 9 | 0 | 0 | 1160 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-25 | QTR2 | 19/20 | 208 | 334520.6 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2710 | 40926715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 4 | 320 | 384 | 383 | 1 | 0 | 0 | 54 | 10 | 3168954 | 0 | 3168954 | 3211208 | 3216929 | 0 | 0 | 0 | 3216929 | 3215797 | -1132 | 42254 | 31 | 0 | 7 | 5327 | 1815 | 0 | 3 | 36151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42254 | 1815 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2019-10-14 | QTR2 | 19/20 | 208 | 1926903.62 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2714 | 43761815201 | 2018-09-26 | QTR1 | 18/19 | 1 | 3 | 170 | 308 | 327 | -19 | 19 | 0 | 61 | 77 | 8210076 | 77799 | 8132277 | 8537835 | 8699071 | -65493 | 0 | -65493 | 8633578 | 8618119 | -15459 | 327759 | 46 | 0 | 3 | 112357 | 0 | 0 | 74 | 215402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 327759 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-05 | QTR4 | 19/20 |  | 2019-12-27 | QTR2 | 19/20 | 209 | 8052869.27 |  |  | 17 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2718 | 43762115201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 180 | 190 | 127 | 63 | 0 | 0 | 10 | 0 | 2814544 | 50000 | 2764544 | 2814544 | 2780154 | 0 | 0 | 0 | 2780154 | 2750630 | -29525 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-23 | QTR1 | 19/20 |  | 2019-05-31 | QTR4 | 18/19 | 214 | 3342178.85 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2723 | 43762015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 120 | 143 | 143 | 0 | 0 | 0 | 23 | 0 | 1658214 | 50000 | 1608214 | 1658214 | 1598015 | 0 | 0 | 0 | 1598015 | 1602638 | 4623 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-24 | QTR3 | 19/20 |  | 2019-07-16 | QTR1 | 19/20 | 214 | 2124298.79 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2727 | 43761215201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 140 | 148 | 112 | 36 | 0 | 0 | 8 | 0 | 1634119 | 50000 | 1584119 | 1634119 | 1569675 | 0 | 0 | 0 | 1569675 | 1576127 | 6452 | 0 | 5 | 0 | 0 | 2733 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-11-25 | QTR2 | 19/20 |  | 2019-06-20 | QTR4 | 18/19 | 208 | 1717973.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2730 | 43429715201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 144 | 139 | 5 | 0 | 0 | 24 | 0 | 2680388 | 50000 | 2630388 | 2680388 | 2824608 | 0 | 0 | 0 | 2824608 | 2824608 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16696 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-10-15 | QTR2 | 19/20 | 209 | 3620026.94 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P14 | 21330435201 | 2012-05-30 | QTR4 | 11/12 | 4 | 33 | 1165 | 2447 | 2445 | 2 | 0 | 0 | 608 | 674 | 148792000 | 150000 | 148642000 | 165618383 | 165903515 | 0 | 0 | 0 | 165903515 | 164235803 | -1459708 | 16826383 | 385 | 0 | 115 | 2517134 | 131767 | 0 | 559 | 14034384 | 908717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113300 | 0 | 0 | 0 | 107325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 16753923 | 1040484 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 208 | 156768132 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 223 | 0 | 0 | -18219 | 0 |  | DO
02DO | 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 12 | 798 | 1129 | 1998 | -869 | 869 | 0 | 127 | 204 | 84850000 | 175000 | 84675000 | 85626817 | 85105357 | -9751108 | 0 | -9751108 | 75354249 | 79072300 | 3718051 | 776817 | 82 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 254205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 818390 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 | 06/04/2020 | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 10 | 45 | 0 | 0 | -271502 | 0 |  | DO
02DO | 02 | E2T34 | 43141825201 | 2015-04-15 | QTR4 | 14/15 | 2 | 7 | 900 | 1254 | 1272 | -18 | 18 | 0 | 116 | 238 | 79728458 | 168416 | 79560041 | 79121474 | 78886236 | -229932 | 0 | -229932 | 78656304 | 77245575 | -1251611 | -606983 | 51 | 0 | 7 | -722201 | 0 | 0 | 0 | 20943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | -701258 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-07 | QTR3 | 18/19 | 216 | 80350657.67 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-19 | QTR1 | 19/20 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V70 | 42747515201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 350 | 579 | 577 | 2 | 0 | 0 | 229 | 0 | 4483000 | 51665 | 4431335 | 4642146 | 4688789 | 0 | 0 | 0 | 4688789 | 4688881 | 92 | 159146 | 25 | 0 | 0 | 18680 | 0 | 0 | 0 | 40938 | 1341 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 166914 | 1341 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 208 | 5283434.02 |  |  | 0 | 93 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V71 | 43430015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 2 | 320 | 442 | 442 | 0 | 0 | 0 | 112 | 10 | 4908173 | 50000 | 4858173 | 4938615 | 5152163 | 0 | 0 | 0 | 5152163 | 5451119 | 298956 | 30442 | 44 | 42 | 0 | 10787 | 0 | 0 | 3 | 47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 10 | 58779 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-03-20 | QTR3 | 18/19 | 208 | 4805500.25 |  |  | 7 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V95 | 43617015201 | 2017-09-20 | QTR1 | 17/18 | 1 | 5 | 180 | 435 | 434 | 1 | 0 | 0 | 127 | 128 | 4081125 | 50000 | 4031125 | 4737826 | 4860165 | 0 | 0 | 0 | 4860165 | 4970230 | 110065 | 656701 | 89 | 0 | 75 | 342142 | 107016 | 0 | 53 | 363473 | 315482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 705615 | 422498 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-07-05 | QTR1 | 19/20 |  | 2019-03-12 | QTR3 | 18/19 | 208 | 3223624.79 |  |  | 27 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W35 | 42849115201 | 2017-09-20 | QTR1 | 17/18 | 1 | 0 | 450 | 556 | 492 | 64 | 0 | 0 | 106 | 0 | 2815327 | 50000 | 2765327 | 2815327 | 2782011 | 0 | 0 | 0 | 2782011 | 2782013 | 2 | 0 | 67 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 208 | 4173997.25 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W51 | 20950355201 | 2017-08-16 | QTR1 | 17/18 | 1 | 1 | 340 | 441 | 441 | 0 | 0 | 0 | 101 | 0 | 1735075 | 50000 | 1685075 | 1731106 | 1623863 | 0 | 0 | 0 | 1623863 | 1623865 | 2 | -3969 | 52 | 12 | 0 | 0 | 0 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1941 | 0 | F561918615 | ASTRON GENERAL CONTRACTING CO. | N/A | N/A | N/A | N/A | 2019-07-26 | QTR1 | 19/20 |  | 2019-03-31 | QTR3 | 18/19 | 208 | 1877622.46 |  |  | 0 | 37 | 0 | 0 | -60481 | 0 |  | DO
02DO | 02 | E2W52 | 42849815201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 300 | 324 | 261 | 63 | 0 | 0 | 24 | 0 | 730881 | 39951 | 690930 | 756196 | 713128 | 0 | 0 | 0 | 713128 | 713129 | 0 | 25315 | 9 | 0 | 0 | 53237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53237 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-14 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 208 | 752277.84 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W53 | 42849715201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 440 | 519 | 519 | 0 | 0 | 0 | 79 | 0 | 1093189 | 50000 | 1043189 | 1093189 | 1034914 | 0 | 0 | 0 | 1034914 | 1034914 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18271 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-08-30 | QTR1 | 19/20 |  | 2019-06-25 | QTR4 | 18/19 | 208 | 1735598.23 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W95 | 43402815201 | 2018-02-21 | QTR3 | 17/18 | 1 | 0 | 200 | 246 | 246 | 0 | 0 | 0 | 46 | 0 | 2722348 | 50000 | 2672348 | 2722348 | 2657208 | 0 | 0 | 0 | 2657208 | 2656276 | -932 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7718 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2019-10-25 | QTR2 | 19/20 |  | 2019-04-24 | QTR4 | 18/19 | 208 | 2383751.46 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W96 | 43307515201 | 2018-03-21 | QTR3 | 17/18 | 1 | 1 | 350 | 401 | 349 | 52 | 0 | 0 | 51 | 0 | 4411000 | 50000 | 4361000 | 4455781 | 4414330 | 0 | 0 | 0 | 4414330 | 4414364 | 34 | 44781 | 28 | 0 | 0 | 16525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61306 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-10-16 | QTR2 | 19/20 | 208 | 4144135.21 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X07 | 20956525201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 60 | 72 | 72 | 0 | 0 | 0 | 12 | 0 | 327059 | 16215 | 310844 | 327059 | 288640 | 0 | 0 | 0 | 288640 | 288640 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-03-31 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 208 | 337947.23 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X15 | 20961685201 | 2017-12-20 | QTR2 | 17/18 | 1 | 0 | 500 | 565 | 438 | 127 | 0 | 0 | 65 | 0 | 7739999 | 97047 | 7642952 | 7739999 | 7665781 | 0 | 0 | 0 | 7665781 | 7665781 | 0 | 0 | 26 | 0 | 0 | 19307 | 0 | 0 | 0 | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27480 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-10-17 | QTR2 | 19/20 |  | 2019-07-25 | QTR1 | 19/20 | 208 | 9122595.17 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X44 | 42879715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 200 | 428 | 428 | 0 | 0 | 0 | 130 | 98 | 1990108 | 50000 | 1940108 | 2637472 | 2547298 | 0 | 0 | 0 | 2547298 | 2542607 | -4691 | 647363 | 37 | 60 | 95 | 608011 | 0 | 0 | 3 | 4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 98 | 612548 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-05 | QTR2 | 19/20 | 216 | 2271972.07 |  |  | 3 | 26 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X58 | 43205415201 | 2018-07-18 | QTR1 | 18/19 | 1 | 0 | 294 | 325 | 255 | 70 | 0 | 0 | 31 | 0 | 1561255 | 50000 | 1511255 | 1561255 | 1495849 | 0 | 0 | 0 | 1495849 | 1495849 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-09-19 | QTR1 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 209 | 1989212.97 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X60 | 43025915201 | 2018-08-15 | QTR1 | 18/19 | 1 | 0 | 280 | 326 | 325 | 1 | 0 | 0 | 40 | 6 | 1328017 | 50000 | 1278017 | 1328017 | 1207862 | 0 | 0 | 0 | 1207862 | 1207862 | 0 | 0 | 18 | 0 | 6 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 875 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 208 | 1798375.14 |  |  | 6 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X61 | 43496915201 | 2018-08-15 | QTR1 | 18/19 | 2 | 0 | 180 | 210 | 230 | -20 | 20 | 0 | 30 | 0 | 2118153 | 50000 | 2068153 | 2118153 | 2024485 | -33300 | 0 | -33300 | 1991185 | 1991185 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-01-22 | QTR3 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 209 | 2333869.85 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X62 | 43044925201 | 2018-08-15 | QTR1 | 18/19 | 1 | 2 | 320 | 447 | 446 | 1 | 0 | 0 | 111 | 16 | 3108597 | 50000 | 3058597 | 3188597 | 3259002 | 0 | 0 | 0 | 3259002 | 3258817 | -185 | 80000 | 48 | 0 | 0 | 0 | 0 | 0 | 16 | 117118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 117118 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 216 | 2739647.8 |  |  | 16 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X63 | 43391215201 | 2018-09-19 | QTR1 | 18/19 | 1 | 0 | 250 | 342 | 342 | 0 | 0 | 0 | 51 | 41 | 1149152 | 50000 | 1099152 | 1149152 | 1082839 | 0 | 0 | 0 | 1082839 | 1082839 | 0 | 0 | 18 | 0 | 6 | 8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 41 | 8943 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2020-01-21 | QTR3 | 19/20 | 208 | 1278581.91 |  |  | 41 | 33 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X68 | 43500015201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 125 | 132 | 112 | 20 | 0 | 0 | 7 | 0 | 925745 | 45595 | 880149 | 925745 | 888997 | 0 | 0 | 0 | 888997 | 888989 | -8 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 209 | 952358.87 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y23 | 43500215201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 125 | 165 | 165 | 0 | 0 | 0 | 40 | 0 | 891797 | 43663 | 848134 | 891797 | 842389 | 0 | 0 | 0 | 842389 | 842389 | 0 | 0 | 11 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-04-16 | QTR4 | 19/20 |  | 2020-02-23 | QTR3 | 19/20 | 209 | 906381.04 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y77 | 43606615201 | 2019-07-17 | QTR1 | 19/20 | 1 | 0 | 90 | 96 | 96 | 0 | 0 | 0 | 6 | 0 | 409752 | 20052 | 389700 | 409752 | 391056 | 0 | 0 | 0 | 391056 | 391056 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-06-15 | QTR4 | 19/20 |  | 2020-04-10 | QTR4 | 19/20 | 208 | 431103.15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3471 | 41110225201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 545 | 841 | 869 | -28 | 28 | 0 | 246 | 50 | 15000000 | 150000 | 14850000 | 15157836 | 15093755 | -129472 | 0 | -129472 | 14964283 | 13510897 | -1453386 | 157836 | 188 | 0 | 50 | 207080 | 15783602 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 220081 | 15783602 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-17 | QTR1 | 19/20 |  | 2017-02-15 | QTR3 | 16/17 | 308 | 14814542.28 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3485 | 42695315201 | 2016-04-27 | QTR4 | 15/16 | 2 | 1 | 200 | 314 | 351 | -37 | 37 | 0 | 113 | 1 | 3574230 | 50000 | 3524230 | 3575445 | 3569976 | -104007 | 0 | -104007 | 3465969 | 3477125 | 11156 | 1215 | 52 | 0 | 1 | 1215 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 6091 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2017-06-30 | QTR4 | 16/17 | 308 | 3028499.48 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3488 | 40979275201 | 2015-05-20 | QTR4 | 14/15 | 1 | 4 | 245 | 371 | 377 | -6 | 6 | 0 | 110 | 16 | 3595027 | 50000 | 3545027 | 3663247 | 3527855 | -36334 | 0 | -36334 | 3491521 | 3407495 | -84026 | 68219 | 39 | 0 | 0 | 0 | 0 | 37 | 8 | 68219 | 9260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 16 | 80862 | 9260 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | QTR1 | 19/20 |  | 2016-11-11 | QTR2 | 16/17 | 308 | 2839405.84 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3543 | 22044275201 | 2015-09-30 | QTR1 | 15/16 | 1 | 18 | 830 | 1304 | 1304 | 0 | 0 | 0 | 435 | 39 | 29686177 | 150000 | 29536177 | 35844062 | 36589864 | 0 | 0 | 0 | 36589864 | 36787330 | 244313 | 6157885 | 342 | 12 | 14 | 166013 | 0 | 0 | 15 | 229697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 578955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 224474 | 0 | 0 | 0 | 4978544 | 83847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 39 | 6135882 | 83847 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-07-29 | QTR1 | 19/20 | 308 | 37447263.92 |  |  | 12 | 81 | 0 | 0 | -41801 | 0 |  | CO
03CO | 03 | T3584 | 42551925201 | 2017-09-27 | QTR1 | 17/18 | 1 | 2 | 240 | 396 | 396 | 0 | 0 | 0 | 147 | 9 | 4956085 | 50000 | 4906085 | 5007841 | 5206085 | 0 | 0 | 0 | 5206085 | 5200473 | 8875 | 51756 | 76 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 9 | 37268 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-02-01 | QTR3 | 18/19 | 308 | 4588109.44 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3586 | 42862415201 | 2018-06-13 | QTR4 | 17/18 | 1 | 4 | 340 | 451 | 449 | 2 | 0 | 0 | 111 | 0 | 4214542 | 0 | 4214542 | 4293135 | 4297521 | 0 | 0 | 0 | 4297521 | 4255328 | -5203 | 78594 | 50 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13328 | 0 | 30 | 0 | 41604 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-13 | QTR2 | 19/20 | 321 | 3958245.51 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3594 | 42884415201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 210 | 720 | 720 | 0 | 0 | 0 | 454 | 56 | 5851220 | 61859 | 5789362 | 5885580 | 5664882 | 0 | 0 | 0 | 5664882 | 5780265 | 115384 | 34359 | 395 | 0 | 0 | 0 | 0 | 0 | 56 | 49348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 49348 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2020-06-06 | QTR4 | 19/20 |  | 2020-04-08 | QTR4 | 19/20 | 314 | 6081166.5 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3605 | 43390515201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 210 | 310 | 310 | 0 | 0 | 0 | 100 | 0 | 2727550 | 0 | 2727550 | 2727550 | 2606882 | 0 | 0 | 0 | 2606882 | 2599923 | -6959 | 0 | 66 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-10-01 | QTR2 | 19/20 | 308 | 2910807.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3614 | 43228815201 | 2018-08-29 | QTR1 | 18/19 | 1 | 2 | 120 | 238 | 238 | 0 | 0 | 0 | 78 | 40 | 776874 | 0 | 776874 | 1103417 | 1178529 | 0 | 0 | 0 | 1178529 | 1178529 | 0 | 326542 | 62 | 0 | 40 | 326542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326542 | 0 | F593638214 | J. MILLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 308 | 825049.02 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3617 | 43228615201 | 2018-11-14 | QTR2 | 18/19 | 1 | 3 | 290 | 425 | 425 | 0 | 0 | 0 | 135 | 0 | 1583516 | 0 | 1583516 | 1621356 | 1660818 | 0 | 0 | 0 | 1660818 | 1656916 | -3903 | 37840 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 37840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 37840 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-06-10 | QTR4 | 19/20 |  | 2020-03-30 | QTR3 | 19/20 | 308 | 1384281.38 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3621 | 43626115201 | 2018-01-31 | QTR3 | 17/18 | 3 | 4 | 240 | 344 | 344 | 0 | 0 | 0 | 104 | 0 | 6338519 | 76410 | 6262109 | 6398946 | 6159928 | -3625 | 0 | -3625 | 6156303 | 6530080 | 373777 | 60427 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 34738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65802 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-04-22 | QTR4 | 18/19 | 321 | 7711485 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3622 | 43403415201 | 2018-07-25 | QTR1 | 18/19 | 1 | 2 | 245 | 342 | 342 | 0 | 0 | 0 | 97 | 0 | 2343362 | 50000 | 2293362 | 2350008 | 2309974 | 0 | 0 | 0 | 2309974 | 2307395 | -2578 | 6645 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6645 | 0 | 0 | 0 | 6645 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-11-26 | QTR2 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 321 | 1958563.65 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3633 | 43188335201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 140 | 260 | 260 | 0 | 0 | 0 | 117 | 3 | 874222 | 50000 | 824222 | 874222 | 812103 | 0 | 0 | 0 | 812103 | 809595 | -2508 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10272 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-08-07 | QTR1 | 19/20 |  | 2019-06-24 | QTR4 | 18/19 | 308 | 1107451.9 |  |  | 3 | 41 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3637 | 43626515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 120 | 217 | 217 | 0 | 0 | 0 | 92 | 5 | 2991030 | 50000 | 2941030 | 3017543 | 3196659 | 0 | 0 | 0 | 3196659 | 3342910 | 168914 | 26513 | 52 | 0 | 0 | 0 | 0 | 0 | 5 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 5 | 16048 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2019-01-11 | QTR3 | 18/19 | 308 | 0 |  |  | 5 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3639 | 43078915201 | 2018-02-28 | QTR3 | 17/18 | 1 | 2 | 209 | 280 | 278 | 2 | 0 | 0 | 71 | 0 | 5166455 | 66461 | 5099994 | 5133457 | 5226570 | 0 | 0 | 0 | 5226570 | 5542057 | 334168 | -32998 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 36187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15491 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2019-03-08 | QTR3 | 18/19 | 314 | 5944823.16 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3653 | 43672015201 | 2018-08-29 | QTR1 | 18/19 | 1 | 1 | 100 | 131 | 127 | 4 | 0 | 0 | 31 | 0 | 628643 | 33472 | 595170 | 626435 | 585546 | 0 | 0 | 0 | 585546 | 585546 | 0 | -2208 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2208 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-09-04 | QTR1 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 308 | 728102.43 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3655 | 43666315201 | 2017-12-06 | QTR2 | 17/18 | 1 | 9 | 215 | 413 | 407 | 6 | 0 | 0 | 183 | 15 | 7611735 | 99352 | 7512383 | 8017733 | 8305261 | 0 | 0 | 0 | 8305261 | 8564768 | 321209 | 405998 | 157 | 0 | 9 | 326056 | 0 | 0 | 0 | 29499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1841 | 0 | 0 | 3 | 56358 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 426541 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-09 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 321 | 10033608.62 |  |  | 13 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3656 | 42817125201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 168 | 168 | 0 | 0 | 0 | 48 | 0 | 483492 | 23492 | 460000 | 483492 | 460000 | 0 | 0 | 0 | 460000 | 460000 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-01-13 | QTR3 | 19/20 | 314 | 489801.84 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3661 | 43255915201 | 2018-04-25 | QTR4 | 17/18 | 4 | 1 | 160 | 308 | 308 | 0 | 0 | 0 | 101 | 47 | 4168106 | 71094 | 4097012 | 4195995 | 4262748 | -3685 | 0 | -3685 | 4259063 | 4316429 | 57366 | 27889 | 69 | 0 | 4 | 28107 | 0 | 7 | 43 | 31498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 47 | 59606 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-30 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 321 | 3474586.76 |  |  | 7 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3662 | 43627215201 | 2018-01-31 | QTR3 | 17/18 | 2 | 3 | 120 | 330 | 330 | 0 | 0 | 0 | 210 | 0 | 1790850 | 50327 | 1740523 | 1822098 | 1908732 | -25175 | 0 | -25175 | 1883557 | 1983720 | 100163 | 31248 | 167 | 0 | -1 | 34895 | 0 | 0 | 0 | 20507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18292 | 10742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73693 | 10742 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-01 | QTR1 | 19/20 |  | 2019-04-01 | QTR4 | 18/19 | 308 | 2014996.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3666 | 43578215201 | 2019-07-31 | QTR1 | 19/20 | 1 | 1 | 120 | 139 | 128 | 11 | 0 | 0 | 19 | 0 | 552204 | 0 | 552204 | 552204 | 493444 | 0 | 0 | 0 | 493444 | 493444 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-05-28 | QTR4 | 19/20 |  | 2020-02-18 | QTR3 | 19/20 | 321 | 621266.47 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3667 | 43273835201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 325 | 639 | 639 | 0 | 0 | 0 | 312 | 2 | 10109835 | 112126 | 9997709 | 10121496 | 9985893 | 0 | 0 | 0 | 9985893 | 10290483 | 339141 | 11661 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 2 | -17331 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2020-01-10 | QTR3 | 19/20 | 313 | 11327401.22 |  |  | 2 | 92 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3669 | 43046415201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 145 | 302 | 269 | 33 | 0 | 0 | 132 | 25 | 1257739 | 0 | 1257739 | 1467600 | 1481515 | 0 | 0 | 0 | 1481515 | 1356981 | -464 | 209861 | 112 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 85791 | 8899 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 314 | 1150000 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3673 | 43774415201 | 2018-09-26 | QTR1 | 18/19 | 1 | 4 | 180 | 268 | 262 | 6 | 0 | 0 | 52 | 36 | 7942048 | 83065 | 7858983 | 7802040 | 7940568 | 0 | 0 | 0 | 7940568 | 7896410 | -44158 | -140008 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -140008 | 0 | 0 | 0 | 49174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -90833 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-09-05 | QTR1 | 19/20 | 321 | 8459567.2 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3678 | 43627015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 180 | 208 | 179 | 29 | 0 | 0 | 28 | 0 | 4020176 | 50000 | 3970176 | 4016156 | 4196886 | 0 | 0 | 0 | 4196886 | 4189347 | -7539 | -4020 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 32860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28840 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2019-12-06 | QTR2 | 19/20 | 321 | 4510561.96 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3679 | 43388415201 | 2018-12-05 | QTR2 | 18/19 | 2 | 0 | 365 | 403 | 378 | 25 | 0 | 0 | 38 | 0 | 1634280 | 0 | 1634280 | 1634280 | 1650177 | 0 | 0 | 0 | 1650177 | 1651949 | 1772 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-03-10 | QTR3 | 19/20 | 313 | 2275667.74 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3680 | 43815515201 | 2018-11-14 | QTR2 | 18/19 | 1 | 0 | 45 | 84 | 82 | 2 | 0 | 0 | 39 | 0 | 188489 | 7900 | 180589 | 188489 | 183577 | 0 | 0 | 0 | 183577 | 183577 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 313 | 165102.24 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3683 | 43774515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 90 | 102 | 101 | 1 | 0 | 0 | 12 | 0 | 1061000 | 50000 | 1011000 | 1061000 | 1008572 | 0 | 0 | 0 | 1008572 | 1008572 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-12-03 | QTR2 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 321 | 1142403.59 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3684 | 43774815201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 210 | 249 | 239 | 10 | 0 | 0 | 39 | 0 | 5394287 | 67888 | 5326399 | 5398247 | 5475266 | 0 | 0 | 0 | 5475266 | 5462989 | -12278 | 3960 | 21 | 0 | 0 | 24710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3960 | 279 | 0 | 0 | 28670 | 279 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2019-12-03 | QTR2 | 19/20 | 321 | 6845122.25 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3688 | 44038315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 134 | 120 | 14 | 0 | 0 | 14 | 0 | 354899 | 18499 | 336400 | 354899 | 344281 | 0 | 0 | 0 | 344281 | 344281 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6070 | 0 | F593715775 | PYRAMID EXCAVATION INC | N/A | N/A | N/A | N/A | 2020-03-03 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 321 | 390454.14 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3693 | 43776515201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 210 | 369 | 362 | 7 | 0 | 0 | 159 | 0 | 9424063 | 103994 | 9320069 | 9424063 | 9590716 | 0 | 0 | 0 | 9590716 | 9547583 | -43133 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-29 | QTR4 | 19/20 |  | 2020-02-20 | QTR3 | 19/20 | 313 | 10485495.93 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3713 | 42985635201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 180 | 277 | 277 | 0 | 0 | 0 | 91 | 6 | 1053341 | 0 | 1053341 | 1099610 | 1118223 | 0 | 0 | 0 | 1118223 | 1117591 | -632 | 46269 | 67 | 0 | 0 | 0 | 0 | 0 | 6 | 46269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46269 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-08 | QTR4 | 19/20 |  | 2020-03-12 | QTR3 | 19/20 | 321 | 1301273.03 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3715 | 43827215201 | 2019-05-22 | QTR4 | 18/19 | 2 | 1 | 150 | 159 | 118 | 41 | 0 | 0 | 9 | 0 | 649114 | 50000 | 599114 | 653949 | 611340 | 0 | 0 | 0 | 611340 | 610104 | -1235 | 4836 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 321 | 755587.05 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3726 | 43551825201 | 2019-06-12 | QTR4 | 18/19 | 1 | 1 | 120 | 200 | 196 | 4 | 0 | 0 | 80 | 0 | 810302 | 31325 | 778977 | 810302 | 797761 | 0 | 0 | 0 | 797761 | 797761 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-06-29 | QTR4 | 19/20 |  | 2020-04-20 | QTR4 | 19/20 | 314 | 663447.16 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3P84 | 43625815201 | 2017-09-21 | QTR1 | 17/18 | 2 | 0 | 140 | 200 | 200 | 0 | 0 | 0 | 59 | 1 | 1596199 | 50000 | 1546199 | 1596199 | 1566048 | 0 | 0 | 0 | 1566048 | 1618568 | 52521 | 0 | 13 | 21 | 0 | 0 | 0 | 0 | 1 | 5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 5864 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-06 | QTR1 | 19/20 |  | 2018-07-20 | QTR1 | 18/19 | 308 | 1614267.95 |  |  | 1 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q52 | 43626715201 | 2018-03-08 | QTR3 | 17/18 | 2 | 1 | 180 | 254 | 244 | 10 | 0 | 0 | 74 | 0 | 2737547 | 50000 | 2687547 | 2741455 | 2788497 | 0 | 0 | 0 | 2788497 | 2933143 | 148555 | 3908 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-07-16 | QTR1 | 19/20 |  | 2019-01-27 | QTR3 | 18/19 | 313 | 3367305.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R04 | 43627115201 | 2018-06-14 | QTR4 | 17/18 | 2 | 3 | 90 | 251 | 249 | 2 | 0 | 0 | 161 | 0 | 819508 | 38969 | 780539 | 814776 | 800432 | 0 | 0 | 0 | 800432 | 799609 | 0 | -4732 | 101 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5556 | 8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4056 | 8288 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-07-11 | QTR1 | 19/20 |  | 2019-05-13 | QTR4 | 18/19 | 308 | 795145 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R15 | 43730715201 | 2018-04-12 | QTR4 | 17/18 | 2 | 0 | 120 | 195 | 199 | -4 | 4 | 0 | 75 | 0 | 847761 | 42761 | 805000 | 847761 | 805000 | -6660 | 0 | -6660 | 798340 | 798340 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | QTR3 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 308 | 968822.89 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R27 | 40410835201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 90 | 121 | 119 | 2 | 0 | 0 | 31 | 0 | 497771 | 26481 | 471290 | 497771 | 462232 | 0 | 0 | 0 | 462232 | 462232 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-23 | QTR3 | 19/20 |  | 2019-11-19 | QTR2 | 19/20 | 314 | 568464.05 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R52 | 43627225201 | 2019-01-10 | QTR3 | 18/19 | 1 | 1 | 180 | 215 | 203 | 12 | 0 | 0 | 34 | 1 | 1432597 | 50000 | 1382597 | 1438332 | 1321040 | 0 | 0 | 0 | 1321040 | 1327923 | 6884 | 5735 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15399 | 508 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-01-30 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 308 | 1931230.61 |  |  | 1 | 12 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R71 | 41557325201 | 2019-06-13 | QTR4 | 18/19 | 1 | 1 | 150 | 197 | 155 | 42 | 0 | 0 | 47 | 0 | 726199 | 37739 | 688460 | 763938 | 752801 | 0 | 0 | 0 | 752801 | 752801 | 0 | 37739 | 11 | 0 | 0 | 37739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37739 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-31 | QTR3 | 19/20 | 314 | 735823.85 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R73 | 43672615201 | 2018-03-08 | QTR3 | 17/18 | 2 | 3 | 315 | 398 | 397 | 1 | 0 | 0 | 83 | 0 | 3019502 | 50000 | 2969502 | 3096429 | 3191111 | -1871 | 0 | -1871 | 3189240 | 3237797 | 63342 | 76927 | 41 | 0 | 0 | 915 | 0 | 18 | 0 | 60255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 61170 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-16 | QTR2 | 19/20 |  | 2019-07-02 | QTR1 | 19/20 | 321 | 3561779.46 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S52 | 41767755201 | 2019-05-09 | QTR4 | 18/19 | 1 | 0 | 90 | 170 | 168 | 2 | 0 | 0 | 80 | 0 | 551256 | 24827 | 526429 | 551256 | 487293 | 0 | 0 | 0 | 487293 | 487293 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-03-16 | QTR3 | 19/20 |  | 2020-01-16 | QTR3 | 19/20 | 314 | 525116.42 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S64 | 4453671H201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 45 | 45 | 38 | 7 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 0 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2019-09-24 | QTR1 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 321 | 32990.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S65 | 4453681E201 | 2019-04-26 | QTR4 | 18/19 | 1 | 0 | 45 | 86 | 84 | 2 | 0 | 0 | 41 | 0 | 290951 | 0 | 290951 | 290951 | 295907 | 0 | 0 | 0 | 295907 | 0 | -295907 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-04-14 | QTR4 | 19/20 |  | 2020-01-07 | QTR3 | 19/20 | 314 | 223300 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T17 | 4458601G201 | 2019-10-14 | QTR2 | 19/20 | 1 | 0 | 50 | 51 | 48 | 3 | 0 | 0 | 1 | 0 | 90900 | 0 | 90900 | 90900 | 90510 | 0 | 0 | 0 | 90510 | 0 | -90510 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208255780 | T & M LAWN-FENCE SERVICE INC | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2020-02-28 | QTR3 | 19/20 | 314 | 98690 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4400 | 22777415201 | 2014-05-21 | QTR4 | 13/14 | 3 | 8 | 1100 | 1532 | 1532 | 0 | 0 | 0 | 312 | 120 | 30674813 | 150000 | 30524813 | 30018004 | 28121407 | 0 | -175000 | -175000 | 27946407 | 26867570 | -1001159 | -656809 | 210 | 43 | 0 | 96338 | 15944 | 4 | 21 | 174318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | -96939 | 43113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 120 | -653022 | 59057 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-04-30 | QTR4 | 19/20 |  | 2019-03-16 | QTR3 | 18/19 | 412 | 31615938.89 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE | 4 | 55 | 0 | 0 | -972544 | 0 |  | CO
04CO | 04 | T4412 | 42873315201 | 2016-08-31 | QTR1 | 16/17 | 2 | 4 | 661 | 899 | 898 | 1 | 0 | 0 | 122 | 116 | 6616134 | 55250 | 6560884 | 6744078 | 6260985 | 0 | 0 | 0 | 6260985 | 6337789 | 102908 | 127944 | 73 | 0 | 2 | 50042 | 0 | 0 | 53 | 88966 | 18492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 12210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 152254 | 18492 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2019-06-19 | QTR4 | 18/19 | 412 | 5635993.18 |  |  | 38 | 49 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4418 | 22989615201 | 2015-07-29 | QTR1 | 15/16 | 7 | 5 | 1005 | 1118 | 1118 | 0 | 0 | 0 | 113 | 0 | 17423228 | 150000 | 17273228 | 17585616 | 15704340 | 0 | 0 | 0 | 15704340 | 15605066 | -82422 | 162388 | 51 | 0 | 0 | -39118 | 0 | 0 | 0 | 189822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11593 | 11593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162297 | 11593 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-01-25 | QTR3 | 18/19 | 409 | 22527836.07 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4423 | 23033845201 | 2016-02-24 | QTR3 | 15/16 | 4 | 9 | 824 | 1034 | 1028 | 6 | 0 | 0 | 202 | 8 | 23950804 | 150000 | 23800804 | 24148938 | 23087444 | 0 | 0 | 0 | 23087444 | 23401928 | 442812 | 198133 | 145 | 0 | 8 | 154696 | 4956 | 0 | 0 | -187005 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142246 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 125280 | 5856 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-08-26 | QTR1 | 19/20 |  | 2019-02-23 | QTR3 | 18/19 | 408 | 30953648.16 |  |  | 8 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4433 | 42872415201 | 2016-04-27 | QTR4 | 15/16 | 4 | 12 | 601 | 960 | 974 | -14 | 14 | 0 | 302 | 61 | 16224277 | 150000 | 16074277 | 17235975 | 16795691 | -46980 | -64000 | -110980 | 16684711 | 16774147 | 140685 | 1011698 | 254 | 0 | 0 | 284349 | 0 | 0 | 58 | 769055 | 15997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1059392 | 20397 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-02-25 | QTR3 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 412 | 14991647.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4444 | 43270515201 | 2016-12-07 | QTR2 | 16/17 | 4 | 8 | 910 | 1190 | 1005 | 185 | 0 | 0 | 259 | 21 | 27999900 | 150000 | 27849900 | 28775420 | 29356382 | 0 | 0 | 0 | 29356382 | 30041255 | 725124 | 775520 | 216 | 0 | 21 | 446126 | 0 | 0 | 0 | 206370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 683157 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-02-11 | QTR3 | 19/20 |  | 2019-11-26 | QTR2 | 19/20 | 408 | 34103305.86 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4449 | 43466615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 4 | 625 | 913 | 912 | 1 | 0 | 0 | 170 | 118 | 7667258 | 81519 | 7585739 | 7990322 | 8156412 | 0 | 0 | 0 | 8156412 | 8213679 | 84466 | 323063 | 101 | 0 | 0 | 2309 | 0 | 0 | 61 | 169260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 148044 | 0 | 0 | 0 | 17025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 336638 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-09 | QTR4 | 19/20 |  | 2020-01-07 | QTR3 | 19/20 | 412 | 7671793.67 |  |  | 0 | 69 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4452 | 43166615201 | 2017-01-25 | QTR3 | 16/17 | 2 | 4 | 396 | 484 | 478 | 6 | 0 | 0 | 88 | 0 | 3407245 | 50000 | 3357245 | 3524212 | 3504637 | 0 | 0 | 0 | 3504637 | 3537514 | 69412 | 116967 | 67 | 0 | 0 | 52621 | 51166 | 0 | 0 | 68491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126406 | 51166 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-06 | QTR3 | 19/20 |  | 2018-10-02 | QTR2 | 18/19 | 412 | 3478134.48 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4454 | 43427315201 | 2017-02-22 | QTR3 | 16/17 | 2 | 8 | 469 | 742 | 833 | -91 | 91 | 0 | 273 | 0 | 17184517 | 150000 | 17034517 | 17260367 | 15228075 | -427518 | 0 | -427518 | 14800557 | 15621002 | 855652 | 75851 | 215 | 0 | 0 | 74685 | 0 | 0 | 0 | -101021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60406 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-26 | QTR2 | 19/20 |  | 2019-08-19 | QTR1 | 19/20 | 408 | 16678233.17 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4465 | 42793815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 3 | 438 | 576 | 575 | 1 | 0 | 0 | 108 | 30 | 6772377 | 73268 | 6699110 | 6937715 | 6616077 | 0 | 0 | 0 | 6616077 | 6748897 | 189028 | 165338 | 66 | 0 | 0 | 82280 | 0 | 0 | 0 | 39114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 129963 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-09 | QTR1 | 19/20 |  | 2019-03-01 | QTR3 | 18/19 | 412 | 7354282.18 |  |  | 30 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4467 | 42872815201 | 2017-09-27 | QTR1 | 17/18 | 1 | 10 | 380 | 626 | 600 | 26 | 0 | 0 | 96 | 150 | 6194382 | 0 | 6194382 | 6727999 | 7014661 | 0 | 0 | 0 | 7014661 | 7138333 | 123672 | 533617 | 55 | 0 | 0 | 84548 | 0 | 0 | 150 | 371900 | 7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 469789 | 7193 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-12 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 408 | 6773142.32 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4470 | 43467915201 | 2018-01-31 | QTR3 | 17/18 | 2 | 1 | 334 | 478 | 476 | 2 | 0 | 0 | 116 | 28 | 2654817 | 50000 | 2604817 | 2648641 | 2595600 | 0 | 0 | 0 | 2595600 | 2595444 | -156 | -6176 | 89 | 0 | 0 | -6176 | 0 | 0 | 0 | 8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 17359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19957 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-23 | QTR1 | 19/20 | 412 | 2954450.55 |  |  | 28 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4474 | 43516015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 3 | 294 | 464 | 464 | 0 | 0 | 0 | 142 | 28 | 4025071 | 50000 | 3975071 | 4333347 | 4067792 | 0 | 0 | 0 | 4067792 | 4150827 | 83036 | 308276 | 109 | 0 | 28 | 137010 | 0 | 0 | 0 | 171266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 308276 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-12-09 | QTR2 | 19/20 |  | 2019-07-26 | QTR1 | 19/20 | 409 | 3559043.96 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4478 | 43206645201 | 2018-05-23 | QTR4 | 17/18 | 3 | 1 | 293 | 389 | 387 | 2 | 0 | 0 | 96 | 0 | 3159876 | 50000 | 3109876 | 3207501 | 3126761 | 0 | 0 | 0 | 3126761 | 3121903 | -4859 | 47624 | 74 | 0 | 0 | 11677 | 0 | 0 | 0 | 53684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65361 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 412 | 3633553.18 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4480 | 43166515201 | 2018-04-25 | QTR4 | 17/18 | 2 | 1 | 214 | 274 | 273 | 1 | 0 | 0 | 48 | 12 | 1327221 | 50000 | 1277221 | 1366521 | 1298578 | 0 | 0 | 0 | 1298578 | 1298125 | -453 | 39300 | 29 | 0 | 0 | 0 | 0 | 0 | 12 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42392 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-06-30 | QTR4 | 18/19 | 412 | 1330304.19 |  |  | 12 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4481 | 43177025201 | 2018-04-25 | QTR4 | 17/18 | 2 | 3 | 274 | 395 | 395 | 0 | 0 | 0 | 76 | 45 | 2295900 | 50000 | 2245900 | 2421717 | 2381617 | 0 | 0 | 0 | 2381617 | 2380490 | -1127 | 125817 | 52 | 0 | 0 | 15551 | 0 | 0 | 39 | 132589 | 42865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 161617 | 42865 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-04-23 | QTR4 | 19/20 |  | 2019-10-09 | QTR2 | 19/20 | 412 | 2164418.85 |  |  | 21 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4482 | 44007915201 | 2018-05-23 | QTR4 | 17/18 | 2 | 3 | 253 | 284 | 283 | 1 | 0 | 0 | 31 | 0 | 398299 | 25300 | 372999 | 443873 | 390019 | 0 | 0 | 0 | 390019 | 390013 | -6 | 45574 | 11 | 0 | 0 | 634 | 0 | 0 | 0 | 49025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49659 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-04-20 | QTR4 | 19/20 |  | 2019-09-11 | QTR1 | 19/20 | 409 | 523214.25 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4484 | 43169815201 | 2018-05-23 | QTR4 | 17/18 | 2 | 2 | 180 | 228 | 228 | 0 | 0 | 0 | 48 | 0 | 1436281 | 50000 | 1386281 | 1518265 | 1430265 | 0 | 0 | 0 | 1430265 | 1427633 | -2632 | 81984 | 33 | 0 | 0 | 23051 | 0 | 0 | 0 | 9060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58933 | 0 | 0 | 0 | 94344 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-04-23 | QTR4 | 19/20 |  | 2019-12-03 | QTR2 | 19/20 | 412 | 1552637.32 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4486 | 43165715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 10 | 353 | 442 | 442 | 0 | 0 | 0 | 44 | 45 | 3260393 | 50000 | 3210393 | 3609674 | 3402444 | 0 | 0 | 0 | 3402444 | 3396789 | -5656 | 349282 | 19 | 0 | 45 | 162960 | 125042 | 0 | 0 | 157599 | 106623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 387158 | 231666 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-10-28 | QTR2 | 19/20 | 412 | 3504742.12 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4487 | 43060825201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 207 | 231 | 193 | 38 | 0 | 0 | 24 | 0 | 755191 | 32732 | 722458 | 755191 | 655187 | 0 | 0 | 0 | 655187 | 654702 | -486 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-30 | QTR3 | 19/20 | 409 | 684674.32 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4490 | 43467415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 246 | 309 | 309 | 0 | 0 | 0 | 59 | 4 | 1487250 | 50000 | 1437250 | 1501835 | 1498981 | 0 | 0 | 0 | 1498981 | 1501750 | 8264 | 14585 | 40 | 0 | 4 | 10639 | 9090 | 0 | 0 | 31779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 42418 | 9090 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-06-11 | QTR4 | 19/20 |  | 2020-02-03 | QTR3 | 19/20 | 412 | 1612250.71 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4492 | 43783715201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 225 | 236 | 156 | 80 | 0 | 0 | 11 | 0 | 1180804 | 50000 | 1130804 | 1180804 | 1088706 | 0 | 0 | 0 | 1088706 | 1092749 | 4043 | 0 | 6 | 0 | 0 | 1965 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-07-23 | QTR1 | 19/20 | 409 | 1254760.05 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4493 | 43622615201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 130 | 175 | 173 | 2 | 0 | 0 | 39 | 6 | 913324 | 46344 | 866980 | 925193 | 862461 | 0 | 0 | 0 | 862461 | 863741 | 1280 | 11869 | 31 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30223 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-09-20 | QTR1 | 19/20 | 412 | 983071.95 |  |  | 6 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4515 | 43783515201 | 2019-03-27 | QTR3 | 18/19 | 2 | 2 | 269 | 310 | 289 | 21 | 0 | 0 | 41 | 0 | 1965071 | 50000 | 1915071 | 1985843 | 1788610 | 0 | 0 | 0 | 1788610 | 1780758 | -7851 | 20773 | 16 | 0 | 0 | 689 | 0 | 0 | 0 | 21135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21824 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2020-03-25 | QTR3 | 19/20 | 409 | 1803197.14 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4532 | 43838815201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 80 | 80 | 77 | 3 | 0 | 0 | 0 | 0 | 291936 | 14514 | 277423 | 291936 | 271767 | 0 | 0 | 0 | 271767 | 271767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-05-26 | QTR4 | 19/20 |  | 2020-04-28 | QTR4 | 19/20 | 409 | 289117.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4533 | 43689915201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 83 | 94 | 94 | 0 | 0 | 0 | 11 | 0 | 299394 | 14505 | 284890 | 321508 | 308462 | 0 | 0 | 0 | 308462 | 308462 | 0 | 22113 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 22113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22113 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-06-23 | QTR4 | 19/20 |  | 2020-05-29 | QTR4 | 19/20 | 409 | 308306.81 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N84 | 42170735201 | 2014-06-30 | QTR4 | 13/14 | 13 | 27 | 1350 | 1590 | 1590 | 0 | 0 | 0 | 228 | 12 | 233756400 | 150000 | 233606400 | 236000384 | 235981625 | 0 | 1120000 | 1120000 | 237101625 | 230667115 | -6213797 | 2243984 | 183 | 0 | 0 | 651127 | 0 | 0 | 0 | 448339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37400 | 0 | 0 | 12 | 1238353 | 8137 | 0 | 0 | 130348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2100740 | 8137 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-05-10 | QTR4 | 18/19 | 406 | 224173038.41 | B5:B8:B5::Y:B::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 45 | 0 | 0 | -404828 | 0 |  | DO
04DO | 04 | E4N95 | 43316515201 | 2014-04-28 | QTR4 | 13/14 | 1 | 6 | 1339 | 1677 | 1675 | 2 | 0 | 0 | 308 | 30 | 15085307 | 150000 | 14935307 | 14747115 | 14692678 | 0 | 0 | 0 | 14692678 | 14200849 | -417090 | -338192 | 219 | 0 | 30 | -493859 | 0 | 0 | 0 | 80928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -335699 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-03-28 | QTR3 | 18/19 | 412 | 15641980 | B8:LBDB:Y | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 89 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N98 | 42170745201 | 2014-01-17 | QTR3 | 13/14 | 2 | 14 | 1385 | 1907 | 1548 | 359 | 0 | 0 | 231 | 291 | 85270000 | 150000 | 85120000 | 88551488 | 88376026 | -66765 | -200000 | -266765 | 88109261 | 84570626 | -3249187 | 3281488 | 165 | 2 | 143 | 2699476 | 7451 | 0 | 30 | 408715 | 25226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 34593 | 34593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 292 | 2981482 | 67270 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-29 | QTR1 | 19/20 |  | 2018-07-16 | QTR1 | 18/19 | 406 | 101668874 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 64 | 0 | 0 | -202797 | 0 |  | DO
04DO | 04 | E4P04 | 23193225201 | 2014-04-16 | QTR4 | 13/14 | 7 | 11 | 979 | 1575 | 1811 | -236 | 236 | 0 | 297 | 299 | 32540300 | 150000 | 32390300 | 33830739 | 33682875 | -2003878 | 0 | -2003878 | 31678997 | 31225551 | -348367 | 1290439 | 225 | 0 | 299 | 1014970 | 0 | 0 | 0 | 128450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299 | 1187254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-02-26 | QTR3 | 19/20 |  | 2019-07-12 | QTR1 | 19/20 | 409 | 33267451 | B8:Y:B:Y::Y::Y::Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 72 | 0 | 0 | -960 | 0 |  | DO
04DO | 04 | E4Q16 | 42170795201 | 2015-03-11 | QTR3 | 14/15 | 2 | 3 | 1500 | 1598 | 1598 | 0 | 0 | 0 | 98 | 0 | 5426234 | 64008 | 5362226 | 5484479 | 5462490 | 0 | 500000 | 500000 | 5962490 | 5462490 | -500000 | 58245 | 22 | 0 | 0 | 4879 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21735 | 0 | 0 | 0 | 59850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109563 | 0 | F593057681 | PRECISION CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-10-11 | QTR2 | 19/20 | 406 | 6421653 | B5:B8:Y:B:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 76 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q35 | 42264135201 | 2015-05-06 | QTR4 | 14/15 | 1 | 7 | 790 | 1112 | 1158 | -46 | 46 | 0 | 291 | 31 | 20830000 | 150000 | 20680000 | 21194238 | 21031285 | -452157 | 0 | -452157 | 20579128 | 20475453 | -4739 | 364238 | 220 | 0 | 8 | 216722 | 0 | 0 | 8 | 37608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 29334 | 29334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 283664 | 29334 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-06-21 | QTR4 | 18/19 | 408 | 20036622.16 | B8 | ACC - DESIGN/BUILD - MAJOR | 6 | 71 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q64 | 43310855201 | 2015-05-29 | QTR4 | 14/15 | 1 | 30 | 1400 | 1506 | 1365 | 141 | 0 | 0 | 106 | 0 | 153917279 | 150000 | 153767279 | 162463226 | 162823699 | 0 | 3720000 | 3720000 | 166543699 | 162492246 | -3709579 | 8545947 | 57 | 0 | 0 | 1603424 | 0 | 0 | 0 | 2717641 | 75013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480038 | 468544 | 0 | 0 | 1150398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8290048 | 543557 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-10-03 | QTR2 | 19/20 | 406 | 152035431 | B5:B8:Y | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 49 | 0 | 0 | -669018 | 0 |  | DO
04DO | 04 | E4S19 | 43215415201 | 2019-01-04 | QTR3 | 18/19 | 1 | 1 | 150 | 217 | 214 | 3 | 0 | 0 | 62 | 5 | 2497568 | 50000 | 2447568 | 2505758 | 2398176 | 0 | 0 | 0 | 2398176 | 2389987 | 0 | 8189 | 37 | 0 | 5 | 13102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 13102 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-12 | QTR3 | 19/20 | 409 | 3078159.73 |  |  | 5 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S21 | 43661715201 | 2017-03-03 | QTR3 | 16/17 | 1 | 8 | 660 | 767 | 752 | 15 | 0 | 0 | 107 | 0 | 13456789 | 150000 | 13306789 | 15316896 | 15094846 | 0 | 0 | 0 | 15094846 | 15262674 | 167827 | 1860107 | 73 | 0 | 0 | 88119 | 0 | 0 | 0 | 288853 | 65785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762282 | 65785 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-10-02 | QTR2 | 19/20 |  | 2019-07-31 | QTR1 | 19/20 | 408 | 15931023.83 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S38 | 42684015201 | 2017-05-05 | QTR4 | 16/17 | 1 | 4 | 732 | 868 | 868 | 0 | 0 | 0 | 122 | 14 | 7933333 | 75464 | 7857869 | 10078503 | 10162546 | 0 | 0 | 0 | 10162546 | 10130655 | 5251 | 2145170 | 54 | 0 | 14 | 3468 | 0 | 0 | 0 | 2024646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22168 | 0 | 0 | 0 | 83382 | 2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2133664 | 2563 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2020-03-01 | QTR3 | 19/20 | 408 | 6966383.46 |  |  | 14 | 68 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S85 | 43609615201 | 2017-12-01 | QTR2 | 17/18 | 1 | 3 | 195 | 288 | 340 | -52 | 52 | 0 | 45 | 48 | 4027310 | 50000 | 3977310 | 4061212 | 3932814 | -146172 | 0 | -146172 | 3786642 | 3959283 | 172641 | 33902 | 24 | 0 | 13 | 33180 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7963 | 0 | 0 | 35 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 42152 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-12-30 | QTR2 | 19/20 |  | 2019-06-13 | QTR4 | 18/19 | 408 | 4151810.1 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T01 | 43630215201 | 2018-03-09 | QTR3 | 17/18 | 1 | 1 | 230 | 317 | 317 | 0 | 0 | 0 | 57 | 30 | 1711929 | 50000 | 1661929 | 1760237 | 1659334 | 0 | 0 | 0 | 1659334 | 1661623 | 2288 | 48308 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 74366 | 48308 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-10 | QTR1 | 19/20 |  | 2019-03-29 | QTR3 | 18/19 | 409 | 1640419.12 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T06 | 43977615201 | 2018-03-09 | QTR3 | 17/18 | 1 | 0 | 251 | 293 | 293 | 0 | 0 | 0 | 42 | 0 | 1095456 | 50000 | 1045456 | 1095456 | 1057178 | 0 | 0 | 0 | 1057178 | 1059897 | 2719 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-12 | QTR2 | 19/20 |  | 2019-03-30 | QTR3 | 18/19 | 412 | 1077515.33 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T43 | 43686915201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 115 | 129 | 129 | 0 | 0 | 0 | 14 | 0 | 483248 | 27874 | 455374 | 483248 | 462927 | 0 | 0 | 0 | 462927 | 462927 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2019-10-01 | QTR2 | 19/20 |  | 2019-08-28 | QTR1 | 19/20 | 408 | 584333.67 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T45 | 44145415201 | 2018-12-07 | QTR2 | 18/19 | 1 | 0 | 264 | 303 | 286 | 17 | 0 | 0 | 39 | 0 | 1195515 | 50000 | 1145515 | 1195515 | 1144992 | 0 | 0 | 0 | 1144992 | 1144992 | 0 | 0 | 13 | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-02-29 | QTR3 | 19/20 | 412 | 1552783.3 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T47 | 43995915201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 262 | 266 | 85 | 181 | 0 | 0 | 4 | 0 | 874745 | 50000 | 824745 | 874745 | 827255 | 0 | 0 | 0 | 827255 | 827255 | 0 | 0 | 1 | 0 | 0 | 10355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10355 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-06-18 | QTR4 | 18/19 | 412 | 2440132.42 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T48 | 43215315201 | 2019-01-04 | QTR3 | 18/19 | 1 | 0 | 280 | 295 | 152 | 143 | 0 | 0 | 15 | 0 | 1579388 | 50000 | 1529388 | 1579388 | 1522923 | 0 | 0 | 0 | 1522923 | 1522923 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-10-07 | QTR2 | 19/20 |  | 2019-08-30 | QTR1 | 19/20 | 412 | 1500208.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T52 | 43784715201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 182 | 248 | 248 | 0 | 0 | 0 | 66 | 0 | 1344115 | 50000 | 1294115 | 1351758 | 1279142 | 0 | 0 | 0 | 1279142 | 1271289 | -209 | 7643 | 34 | 0 | 0 | 4800 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 30930 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-04 | QTR4 | 19/20 |  | 2020-01-27 | QTR3 | 19/20 | 412 | 1455182.8 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T53 | 44145715201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 123 | 128 | 67 | 61 | 0 | 0 | 5 | 0 | 373586 | 50000 | 323586 | 373586 | 320740 | 0 | 0 | 0 | 320740 | 320740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-07-11 | QTR1 | 19/20 | 409 | 838047.4 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T55 | 43388915201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 119 | 207 | 207 | 0 | 0 | 0 | 70 | 18 | 436087 | 29381 | 406707 | 451388 | 443815 | 0 | 0 | 0 | 443815 | 443815 | 0 | 15300 | 47 | 0 | 0 | 0 | 0 | 0 | 18 | 44166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 44166 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-06 | QTR3 | 19/20 | 412 | 589902.2 |  |  | 14 | 23 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BE626 | 43787225201 | 2018-05-24 | QTR4 | 17/18 | 1 | 0 | 280 | 344 | 213 | 131 | 0 | 0 | 64 | 0 | 720000 | 0 | 720000 | 720000 | 720000 | 0 | 0 | 0 | 720000 | 720000 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-01-17 | QTR3 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 507 | 720000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5469 | 23920345201 | 2013-10-30 | QTR2 | 13/14 | 3 | 36 | 950 | 1139 | 1138 | 1 | 0 | 0 | 165 | 24 | 67881735 | 150000 | 67731735 | 71458538 | 71806238 | -56415 | 0 | -56415 | 71749823 | 68678306 | -3056235 | 3576803 | 117 | 0 | 22 | 833627 | 25021 | 0 | 2 | 1192872 | 41063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3594736 | 66084 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2017-03-03 | QTR3 | 16/17 | 507 | 60257622 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 3 | 48 | 0 | 0 | -155690 | 0 |  | CO
05CO | 05 | T5506 | 41840325201 | 2015-06-17 | QTR4 | 14/15 | 4 | 18 | 800 | 1180 | 1181 | -1 | 1 | 0 | 232 | 148 | 12348616 | 73000 | 12275616 | 13716737 | 13601127 | 0 | 0 | 0 | 13601127 | 13641534 | 107227 | 1368121 | 86 | 0 | 21 | 799701 | 22020 | 91 | 30 | 336757 | 232158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80666 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 114786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19902 | 0 | 91 | 148 | 1319075 | 254178 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2019-02-06 | QTR3 | 18/19 | 509 | 11281111.5 |  |  | 7 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5569 | 43442615201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 180 | 235 | 235 | 0 | 0 | 0 | 41 | 14 | 1957429 | 50000 | 1907429 | 2177504 | 2168249 | 0 | 0 | 0 | 2168249 | 2060853 | 8636 | 220075 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 112214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 112539 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | QTR4 | 19/20 |  | 2017-12-21 | QTR2 | 17/18 | 509 | 2248770.95 |  |  | 14 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5572 | 43505615201 | 2017-06-14 | QTR4 | 16/17 | 3 | 2 | 700 | 770 | 602 | 168 | 0 | 0 | 70 | 0 | 6749945 | 119000 | 6630945 | 6768976 | 6749146 | 0 | 30000 | 30000 | 6779146 | 6749146 | -30000 | 19031 | 14 | 0 | 0 | 45981 | 0 | 0 | 0 | 13991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62951 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2019-08-05 | QTR1 | 19/20 | 513 | 8840212 | B1:B1 | ACC - NO EXCUSE BONUS:ACC - NO EXCUSE BONUS | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5588 | 43505915201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 590 | 671 | 567 | 104 | 0 | 0 | 81 | 0 | 5555556 | 71000 | 5484556 | 5555556 | 5533602 | 0 | 14500 | 14500 | 5548102 | 5533602 | -14500 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 32150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35523 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 513 | 7289679.75 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5591 | 42823815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 500 | 652 | 649 | 3 | 0 | 0 | 112 | 40 | 16694356 | 150000 | 16544356 | 16972569 | 16490950 | 0 | 0 | 0 | 16490950 | 16700809 | 209859 | 278213 | 41 | 0 | 40 | 16791 | 0 | 0 | 0 | 143061 | 49425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137620 | 132029 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 332991 | 181454 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-03-13 | QTR3 | 19/20 |  | 2019-08-15 | QTR1 | 19/20 | 514 | 15183626.94 |  |  | 0 | 71 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5601 | 43565815201 | 2018-01-31 | QTR3 | 17/18 | 3 | 5 | 350 | 468 | 467 | 1 | 0 | 0 | 90 | 28 | 4858677 | 66000 | 4792677 | 5019991 | 4911820 | 0 | 0 | 0 | 4911820 | 5177234 | 265414 | 161314 | 43 | 0 | 0 | 80707 | 0 | 0 | 28 | 89524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 183078 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-11 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 6733492 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5606 | 43803815201 | 2018-01-31 | QTR3 | 17/18 | 4 | 10 | 390 | 508 | 508 | 0 | 0 | 0 | 98 | 20 | 8022650 | 95000 | 7927650 | 8458736 | 8268967 | 0 | 0 | 0 | 8268967 | 8611040 | 346762 | 436086 | 41 | 0 | 0 | 435190 | 0 | 0 | 20 | 91027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 467173 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-13 | QTR4 | 19/20 |  | 2019-10-24 | QTR2 | 19/20 | 513 | 9588756 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5616 | 43065515201 | 2018-03-28 | QTR3 | 17/18 | 1 | 2 | 260 | 334 | 334 | 0 | 0 | 0 | 67 | 7 | 4231483 | 53000 | 4178483 | 4229830 | 4248590 | 0 | 0 | 0 | 4248590 | 4402057 | 153467 | -1653 | 46 | 0 | 0 | -14065 | 0 | 0 | 2 | 5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 54377 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 46115 | 2422 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-04 | QTR3 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 512 | 5394340.01 |  |  | 7 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5617 | 43505815201 | 2018-04-25 | QTR4 | 17/18 | 1 | 2 | 380 | 415 | 326 | 89 | 0 | 0 | 35 | 0 | 3824000 | 50000 | 3774000 | 3850406 | 3817535 | 0 | 0 | 0 | 3817535 | 3817535 | 0 | 26406 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 28494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43535 | 0 | F593350649 | UNITED SIGNS & SIGNALS INC. | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 4905410 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5619 | 24099275201 | 2017-08-30 | QTR1 | 17/18 | 2 | 3 | 250 | 366 | 366 | 0 | 0 | 0 | 84 | 32 | 1769311 | 50000 | 1719311 | 1789505 | 1708324 | 0 | 0 | 0 | 1708324 | 1715061 | 6737 | 20194 | 36 | 0 | 17 | 27361 | 0 | 0 | 15 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30807 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-07-25 | QTR1 | 19/20 |  | 2019-03-19 | QTR3 | 18/19 | 513 | 1940871 |  |  | 17 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5621 | 43623715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 330 | 435 | 435 | 0 | 0 | 0 | 68 | 37 | 1704711 | 50000 | 1654711 | 1714508 | 1599483 | 0 | 0 | 0 | 1599483 | 1590886 | -4841 | 9797 | 27 | 0 | 17 | 5837 | 0 | 0 | 20 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 6040 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-06-01 | QTR4 | 19/20 |  | 2020-01-15 | QTR3 | 19/20 | 514 | 1787643.5 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5623 | 43239915201 | 2018-07-25 | QTR1 | 18/19 | 3 | 1 | 260 | 320 | 291 | 29 | 0 | 0 | 60 | 0 | 1897288 | 50000 | 1847288 | 1897714 | 1910437 | 0 | 0 | 0 | 1910437 | 1905492 | -4945 | 426 | 29 | 0 | 0 | 7255 | 0 | 0 | 0 | 21639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9272 | 0 | 0 | 0 | 11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31062 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-10-14 | QTR2 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 514 | 2057026 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5635 | 43733015202 | 2018-10-31 | QTR2 | 18/19 | 2 | 2 | 290 | 377 | 377 | 0 | 0 | 0 | 57 | 30 | 2923010 | 50000 | 2873010 | 2973010 | 2925571 | 0 | 0 | 0 | 2925571 | 2880657 | -44914 | 50000 | 31 | 0 | 30 | 10356 | 0 | 0 | 0 | 47588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 57944 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-02-17 | QTR3 | 19/20 | 509 | 3429127 |  |  | 30 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5641 | 44055775201 | 2018-09-26 | QTR1 | 18/19 | 6 | 5 | 300 | 363 | 362 | 1 | 0 | 0 | 47 | 16 | 22429705 | 150000 | 22279705 | 22800571 | 23719308 | 0 | 1000000 | 1000000 | 24719308 | 23561852 | -1020828 | 370866 | 25 | 0 | 0 | 178586 | 0 | 0 | 6 | 46819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 32848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 280355 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-04-15 | QTR4 | 19/20 |  | 2020-01-31 | QTR3 | 19/20 | 513 | 27275444.74 | B5:B7:B5:B7 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS | 16 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5644 | 43988325201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 60 | 124 | 122 | 2 | 0 | 0 | 64 | 0 | 61969 | 3000 | 58969 | 61969 | 61131 | 0 | 0 | 0 | 61131 | 61131 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2020-04-24 | QTR4 | 19/20 |  | 2020-03-20 | QTR3 | 19/20 | 514 | 70243.95 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5646 | 43988715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 1 | 90 | 208 | 207 | 1 | 0 | 0 | 30 | 88 | 85394 | 4523 | 80871 | 85394 | 71417 | 0 | 0 | 0 | 71417 | 71417 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2020-02-21 | QTR3 | 19/20 | 512 | 99982.5 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5647 | 44106615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 3 | 150 | 227 | 227 | 0 | 0 | 0 | 56 | 21 | 2009090 | 50000 | 1959090 | 2023837 | 2344261 | 0 | 0 | 0 | 2344261 | 2338522 | -200 | 14747 | 33 | 0 | 0 | 0 | 0 | 0 | 21 | 53178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 53178 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-06-24 | QTR4 | 19/20 |  | 2020-02-04 | QTR3 | 19/20 | 509 | 1775243.2 |  |  | 21 | 23 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W11 | 24262635201 | 2014-11-21 | QTR2 | 14/15 | 3 | 6 | 900 | 1229 | 1229 | 0 | 0 | 0 | 288 | 41 | 43150089 | 150000 | 43000089 | 45682181 | 45886261 | 0 | 0 | 0 | 45886261 | 43227195 | -2633738 | 2532092 | 232 | 0 | 41 | 2571393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 2600543 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-13 | QTR3 | 19/20 |  | 2018-07-08 | QTR1 | 18/19 | 515 | 48952301.58 | B2:B5:B8:LBDB | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 41 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W31 | 43360715201 | 2014-08-04 | QTR1 | 14/15 | 2 | 2 | 629 | 829 | 911 | -82 | 82 | 0 | 104 | 96 | 11820000 | 150000 | 11670000 | 11432846 | 11217159 | -379168 | 0 | -379168 | 10837991 | 10359714 | -459862 | -387154 | 69 | 0 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -405568 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | -399823 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2017-04-28 | QTR4 | 16/17 | 507 | 12144516 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y20 | 42690435201 | 2016-11-04 | QTR2 | 16/17 | 2 | 5 | 547 | 928 | 921 | 7 | 0 | 0 | 276 | 105 | 26771800 | 150000 | 26621800 | 27777188 | 27684932 | 0 | 0 | 0 | 27684932 | 28031909 | 444186 | 1005388 | 215 | 0 | 14 | 243217 | 16025 | 0 | 91 | 756982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1000199 | 16025 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-01-08 | QTR3 | 19/20 |  | 2019-08-02 | QTR1 | 19/20 | 514 | 26771800 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y33 | 43693715201 | 2016-09-07 | QTR1 | 16/17 | 1 | 4 | 250 | 646 | 655 | -9 | 9 | 0 | 90 | 306 | 1750000 | 50000 | 1700000 | 3113962 | 3063962 | 0 | 0 | 0 | 3063962 | 3065413 | 1451 | 1363962 | 39 | 0 | 120 | 52749 | 0 | 0 | 133 | 726212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1363962 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2019-10-31 | QTR2 | 19/20 |  | 2018-12-13 | QTR2 | 18/19 | 513 | 1325842 |  |  | 60 | 51 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 1 | 140 | 153 | 152 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793962 | 623055 | 0 | 0 | 0 | 623055 | 624995 | 1940 | -10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | QTR2 | 19/20 |  | 2017-05-14 | QTR4 | 16/17 | 509 | 843684 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z02 | 43365415201 | 2018-02-06 | QTR3 | 17/18 | 1 | 2 | 265 | 383 | 383 | 0 | 0 | 0 | 99 | 19 | 1457258 | 50000 | 1407258 | 1507258 | 1490649 | -1099 | 0 | -1099 | 1489550 | 1488755 | -795 | 50000 | 60 | 11 | 0 | 35861 | 0 | 0 | 8 | 49916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 19 | 85777 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-11-15 | QTR2 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 514 | 1508169 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z09 | 41299445214 | 2017-12-14 | QTR2 | 17/18 | 1 | 1 | 515 | 551 | 514 | 37 | 0 | 0 | 36 | 0 | 5757000 | 50000 | 5707000 | 5860741 | 5841571 | 0 | 0 | 0 | 5841571 | 5844608 | 3037 | 103741 | 7 | 0 | 0 | 77312 | 77312 | 0 | 0 | 26429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134571 | 77312 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-07 | QTR3 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 507 | 5200000 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z21 | 43927015201 | 2018-05-01 | QTR4 | 17/18 | 1 | 0 | 280 | 348 | 306 | 42 | 0 | 0 | 68 | 0 | 3175000 | 50000 | 3125000 | 3175000 | 3125000 | 0 | 0 | 0 | 3125000 | 3125000 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F611201949 | INTECH CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-06-07 | QTR4 | 18/19 | 513 | 2594655 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z23 | 43564715201 | 2018-05-01 | QTR4 | 17/18 | 1 | 1 | 240 | 281 | 281 | 0 | 0 | 0 | 41 | 0 | 1013390 | 50000 | 963390 | 1008318 | 958318 | -736 | 0 | -736 | 957582 | 957220 | -362 | -5072 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5072 | 1753 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-02 | QTR3 | 19/20 |  | 2019-07-10 | QTR1 | 19/20 | 514 | 1052401 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z25 | 43685515201 | 2018-07-03 | QTR1 | 18/19 | 2 | 5 | 180 | 257 | 257 | 0 | 0 | 0 | 48 | 29 | 1405000 | 50000 | 1355000 | 1538799 | 1482098 | 0 | 0 | 0 | 1482098 | 1478901 | -3198 | 133799 | 15 | 0 | 11 | 51283 | 0 | 0 | 18 | 95369 | 9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 146652 | 9379 | F823777772 | GPS CIVIL CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-06-04 | QTR4 | 18/19 | 513 | 1340492.25 |  |  | 1 | 33 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z27 | 43733815201 | 2018-06-05 | QTR4 | 17/18 | 2 | 4 | 420 | 557 | 554 | 3 | 0 | 0 | 127 | 10 | 4978323 | 57000 | 4921323 | 5143919 | 4848769 | 0 | 0 | 0 | 4848769 | 4804280 | -25189 | 165596 | 78 | 0 | 0 | 7576 | 0 | 0 | 0 | 76771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 89547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 173894 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-03-05 | QTR3 | 19/20 | 507 | 5765157.09 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z44 | 43945315201 | 2018-03-06 | QTR3 | 17/18 | 1 | 1 | 320 | 401 | 410 | -9 | 9 | 0 | 66 | 15 | 406627 | 22627 | 384000 | 439983 | 417356 | -11169 | 0 | -11169 | 406187 | 406187 | 0 | 33356 | 25 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 33356 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-07-22 | QTR1 | 19/20 | 513 | 480184 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z45 | 43733915201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 230 | 343 | 343 | 0 | 0 | 0 | 98 | 15 | 6123814 | 81000 | 6042814 | 6203979 | 6135165 | 0 | 0 | 0 | 6135165 | 6001858 | -114476 | 80166 | 64 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 116329 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-06-01 | QTR4 | 19/20 |  | 2020-01-30 | QTR3 | 19/20 | 512 | 8194285 |  |  | 10 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z47 | 43759915201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 110 | 129 | 127 | 2 | 0 | 0 | 19 | 0 | 490000 | 21000 | 469000 | 490000 | 469000 | 0 | 0 | 0 | 469000 | 469000 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-12-06 | QTR2 | 19/20 |  | 2019-07-18 | QTR1 | 19/20 | 509 | 441431 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z48 | 44096715201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 90 | 126 | 127 | -1 | 1 | 0 | 25 | 11 | 476422 | 20860 | 455562 | 476422 | 521373 | 0 | 0 | 0 | 521373 | 521373 | 0 | 0 | 22 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-01 | QTR1 | 19/20 | 509 | 443060.5 |  |  | 11 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z49 | 44255515201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 120 | 177 | 177 | 0 | 0 | 0 | 39 | 18 | 1193299 | 49974 | 1143325 | 1193299 | 1111517 | 0 | 0 | 0 | 1111517 | 1111517 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-29 | QTR2 | 19/20 |  | 2019-09-14 | QTR1 | 19/20 | 513 | 1054473.2 |  |  | 18 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z52 | 44116715201 | 2018-10-02 | QTR2 | 18/19 | 1 | 1 | 100 | 120 | 117 | 3 | 0 | 0 | 20 | 0 | 679222 | 14856 | 664366 | 682222 | 665592 | 0 | 0 | 0 | 665592 | 665592 | 0 | 3000 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-10-10 | QTR2 | 19/20 |  | 2019-07-30 | QTR1 | 19/20 | 515 | 321982.75 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z60 | 44096815201 | 2018-12-04 | QTR2 | 18/19 | 1 | 0 | 140 | 183 | 183 | 0 | 0 | 0 | 43 | 0 | 471366 | 26184 | 445182 | 471366 | 417692 | 0 | 0 | 0 | 417692 | 417692 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593118880 | INTRON TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 513 | 554880 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z73 | 44096615201 | 2019-04-02 | QTR4 | 18/19 | 1 | 0 | 80 | 161 | 161 | 0 | 0 | 0 | 53 | 28 | 648932 | 49732 | 599200 | 648932 | 638000 | 0 | 0 | 0 | 638000 | 638000 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 28 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 42000 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-20 | QTR4 | 19/20 |  | 2020-01-17 | QTR3 | 19/20 | 513 | 1049373.9 |  |  | 28 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z75 | 44180415201 | 2019-05-07 | QTR4 | 18/19 | 1 | 0 | 90 | 100 | 100 | 0 | 0 | 0 | 10 | 0 | 176561 | 13561 | 163000 | 176561 | 146000 | 0 | 0 | 0 | 146000 | 146000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-04-21 | QTR4 | 19/20 |  | 2019-12-16 | QTR2 | 19/20 | 514 | 287786 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z76 | 44097015201 | 2019-06-04 | QTR4 | 18/19 | 1 | 0 | 90 | 126 | 2 | 124 | 0 | 0 | 36 | 0 | 167070 | 12438 | 154632 | 167070 | 148419 | 0 | 0 | 0 | 148419 | 148419 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-02-24 | QTR3 | 19/20 |  | 2020-01-06 | QTR3 | 19/20 | 507 | 271247.25 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z99 | 44326715201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 80 | 84 | 35 | 49 | 0 | 0 | 4 | 0 | 293874 | 17231 | 276643 | 293874 | 266752 | 0 | 0 | 0 | 266752 | 266752 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-06-12 | QTR4 | 19/20 |  | 2020-04-30 | QTR4 | 19/20 | 513 | 366851 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6337 | 41809115201 | 2015-10-28 | QTR2 | 15/16 | 7 | 22 | 600 | 1055 | 1055 | 0 | 0 | 0 | 324 | 131 | 14239526 | 267180 | 13972346 | 16636939 | 16898897 | 0 | 500000 | 500000 | 17398897 | 16914510 | -453877 | 2397413 | 147 | 0 | 87 | 1404877 | 434699 | 120 | 44 | 573331 | 258449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573254 | 54307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 0 | 0 | 120 | 131 | 2554384 | 747455 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-02-20 | QTR3 | 19/20 |  | 2019-02-15 | QTR3 | 18/19 | 606 | 13498168.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6338 | 41463315201 | 2016-01-27 | QTR3 | 15/16 | 4 | 11 | 560 | 1082 | 1082 | 0 | 0 | 0 | 352 | 170 | 11118409 | 242209 | 10876200 | 12716281 | 13284136 | 0 | 0 | 0 | 13284136 | 13366087 | 119047 | 1597872 | 138 | 7 | 170 | 1172291 | 332615 | 137 | 0 | 139746 | 40433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 320742 | 32961 | 0 | 0 | 8312 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 170 | 1641090 | 414320 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-03-20 | QTR3 | 19/20 |  | 2019-05-23 | QTR4 | 18/19 | 606 | 10197839.36 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6344 | 24994145201 | 2014-06-25 | QTR4 | 13/14 | 4 | 10 | 850 | 963 | 913 | 50 | 0 | 0 | 77 | 36 | 20865766 | 857583 | 20008183 | 21591091 | 20515283 | 0 | 0 | 0 | 20515283 | 20078878 | -436405 | 725324 | 52 | 0 | 0 | 212210 | 0 | 0 | 36 | 638372 | 308599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 894143 | 315555 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2019-10-24 | QTR2 | 19/20 |  | 2017-07-05 | QTR1 | 17/18 | 606 | 22059624.95 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6382 | 40561535201 | 2016-12-07 | QTR2 | 16/17 | 7 | 9 | 850 | 964 | 812 | 152 | 0 | 0 | 114 | 0 | 32827940 | 690477 | 32137463 | 33204392 | 33258885 | 0 | 1000000 | 1000000 | 34258885 | 33556467 | -622662 | 376451 | 74 | 0 | 0 | 645068 | 130000 | 0 | 0 | 229672 | 4111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609120 | 134111 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-07-21 | QTR1 | 19/20 | 606 | 32661596.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 40 | 0 | 0 | -514052 | 0 |  | CO
06CO | 06 | T6401 | 41247395201 | 2017-03-29 | QTR3 | 16/17 | 9 | 16 | 280 | 640 | 640 | 0 | 0 | 0 | 161 | 199 | 3499047 | 51510 | 3447537 | 5529305 | 5890497 | 0 | 0 | 0 | 5890497 | 5721407 | 5872 | 2030258 | 59 | 0 | 24 | 787490 | 0 | 0 | 142 | 455267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76144 | 32700 | 0 | 0 | 16568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33 | 583760 | 570405 | 0 | 0 | 0 | 0 | 69 | 199 | 1919229 | 603105 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 606 | 3269401.1 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6403 | 43348915201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 200 | 250 | 250 | 0 | 0 | 0 | 50 | 0 | 2123570 | 50000 | 2073570 | 2145473 | 2165968 | 0 | 0 | 0 | 2165968 | 2187405 | 21437 | 21903 | 44 | 0 | 0 | 41442 | 0 | 0 | 0 | 27753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71450 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2018-11-02 | QTR2 | 18/19 | 606 | 2459954.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6406 | 42902215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 2 | 319 | 389 | 300 | 89 | 0 | 0 | 70 | 0 | 3211923 | 50000 | 3161923 | 3249863 | 3270531 | 0 | 190000 | 190000 | 3460531 | 3268888 | -191642 | 37940 | 56 | 0 | 0 | 2882 | 0 | 0 | 0 | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54540 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-09-27 | QTR1 | 19/20 |  | 2019-07-27 | QTR1 | 19/20 | 606 | 3370171.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6419 | 42827825201 | 2018-04-25 | QTR4 | 17/18 | 3 | 2 | 300 | 349 | 315 | 34 | 0 | 0 | 49 | 0 | 2865340 | 54440 | 2810900 | 2945587 | 2727466 | 0 | 110000 | 110000 | 2837466 | 2776404 | -61063 | 80247 | 31 | 0 | 0 | 6511 | 0 | 0 | 0 | 21703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108462 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 606 | 2918719.6 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6436 | 43631115201 | 2017-10-25 | QTR2 | 17/18 | 3 | 1 | 210 | 325 | 325 | 0 | 0 | 0 | 115 | 0 | 1387410 | 50000 | 1337410 | 1479864 | 1353258 | 0 | 0 | 0 | 1353258 | 1354735 | 1476 | 92454 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92454 | 31948 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-08 | QTR1 | 19/20 |  | 2019-03-14 | QTR3 | 18/19 | 606 | 1750082.45 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6437 | 43634215201 | 2018-01-31 | QTR3 | 17/18 | 4 | 0 | 180 | 262 | 262 | 0 | 0 | 0 | 82 | 0 | 1789134 | 50795 | 1738339 | 1789134 | 1742305 | 0 | 0 | 0 | 1742305 | 1738184 | -4122 | 0 | 48 | 15 | 0 | 11909 | 0 | 0 | 0 | 16438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28347 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-07-18 | QTR1 | 19/20 |  | 2019-04-05 | QTR4 | 18/19 | 606 | 2085359.7 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6438 | 43117015201 | 2018-05-23 | QTR4 | 17/18 | 6 | 2 | 320 | 363 | 295 | 68 | 0 | 0 | 43 | 0 | 3669797 | 51765 | 3618032 | 3847108 | 3668181 | 0 | 250000 | 250000 | 3918181 | 3697899 | -220283 | 177311 | 23 | 0 | 0 | 82758 | 0 | 0 | 0 | 14636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16895 | 16211 | 0 | 0 | 0 | 0 | 0 | 0 | 189909 | 16211 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-08-07 | QTR1 | 19/20 | 606 | 4444325.03 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6444 | 43640415201 | 2018-07-25 | QTR1 | 18/19 | 2 | 1 | 180 | 271 | 264 | 7 | 0 | 0 | 91 | 0 | 1113869 | 48941 | 1064928 | 1119160 | 1084619 | 0 | 0 | 0 | 1084619 | 1078347 | -981 | 5291 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-06-04 | QTR4 | 19/20 |  | 2020-02-07 | QTR3 | 19/20 | 606 | 1006236.05 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6445 | 42611315201 | 2019-01-30 | QTR3 | 18/19 | 2 | 1 | 297 | 349 | 268 | 81 | 0 | 0 | 52 | 0 | 1196727 | 50260 | 1146467 | 1200684 | 1179569 | 0 | 0 | 0 | 1179569 | 1176527 | 914 | 3957 | 30 | 0 | 0 | 15008 | 0 | 0 | 0 | 10372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27799 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2020-04-17 | QTR4 | 19/20 |  | 2020-03-10 | QTR3 | 19/20 | 606 | 1242692.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6448 | 43792015201 | 2018-07-25 | QTR1 | 18/19 | 2 | 0 | 150 | 224 | 222 | 2 | 0 | 0 | 74 | 0 | 796960 | 42121 | 754839 | 796960 | 710116 | 0 | 0 | 0 | 710116 | 708837 | -1279 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-08-23 | QTR1 | 19/20 | 606 | 867453.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6451 | 42563725201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 125 | 163 | 163 | 0 | 0 | 0 | 38 | 0 | 666806 | 31943 | 634863 | 666806 | 585572 | 0 | 0 | 0 | 585572 | 584459 | -1113 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9954 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-08-27 | QTR1 | 19/20 |  | 2019-07-05 | QTR1 | 19/20 | 606 | 654200.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6455 | 43791715201 | 2018-08-29 | QTR1 | 18/19 | 2 | 1 | 140 | 203 | 202 | 1 | 0 | 0 | 63 | 0 | 564205 | 30704 | 533501 | 565127 | 533205 | 0 | 0 | 0 | 533205 | 531866 | -417 | 923 | 48 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11222 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-02 | QTR4 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 606 | 617376.5 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6458 | 44019115201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 200 | 318 | 314 | 4 | 0 | 0 | 118 | 0 | 1250000 | 50000 | 1200000 | 1339834 | 941648 | 0 | 0 | 0 | 941648 | 941530 | -118 | 89834 | 75 | 12 | 0 | 0 | 0 | 0 | 0 | 3393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 119247 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2020-03-23 | QTR3 | 19/20 | 606 | 1429145 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6462 | 43792215201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 160 | 195 | 193 | 2 | 0 | 0 | 35 | 0 | 672522 | 35087 | 637435 | 672522 | 627588 | 0 | 0 | 0 | 627588 | 627091 | -497 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-01-14 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 606 | 724071.25 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6467 | 44289715201 | 2018-10-31 | QTR2 | 18/19 | 5 | 0 | 148 | 166 | 162 | 4 | 0 | 0 | 18 | 0 | 127677 | 13890 | 113787 | 127677 | 111887 | 0 | 0 | 0 | 111887 | 111863 | -24 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-09-06 | QTR1 | 19/20 |  | 2019-07-19 | QTR1 | 19/20 | 606 | 324690 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J52 | 43337815201 | 2016-06-09 | QTR4 | 15/16 | 2 | 2 | 680 | 867 | 838 | 29 | 0 | 0 | 187 | 0 | 8960958 | 65774 | 8895184 | 9028019 | 8935693 | 0 | 0 | 0 | 8935693 | 8869645 | 1013 | 67062 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-07-12 | QTR1 | 19/20 |  | 2019-04-26 | QTR4 | 18/19 | 606 | 6643198.1 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J69 | 43492215201 | 2016-04-15 | QTR4 | 15/16 | 2 | 7 | 840 | 1018 | 1018 | 0 | 0 | 0 | 150 | 28 | 69547000 | 150000 | 69397000 | 72886197 | 72551371 | 0 | 0 | 0 | 72551371 | 72850709 | 649560 | 1806784 | 96 | 0 | 28 | 1089539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272027 | 0 | 0 | 0 | 96375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1457941 | 0 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2019-05-29 | QTR4 | 18/19 | 606 | 125146999.99 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K58 | 43081315201 | 2019-01-31 | QTR3 | 18/19 | 3 | 1 | 200 | 224 | 186 | 38 | 0 | 0 | 24 | 0 | 1100030 | 52315 | 1047715 | 1101649 | 1024191 | 0 | 100000 | 100000 | 1124191 | 1025137 | -97435 | 1619 | 16 | 0 | 0 | 557 | 0 | 0 | 0 | 16202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17525 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2019-11-30 | QTR2 | 19/20 | 606 | 1216039.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K59 | 41831225201 | 2016-07-28 | QTR1 | 16/17 | 4 | 10 | 540 | 638 | 553 | 85 | 0 | 0 | 98 | 0 | 9488820 | 97328 | 9391492 | 10556288 | 10367176 | 0 | 400000 | 400000 | 10767176 | 10307054 | -358123 | 1067468 | 84 | 0 | 0 | 268724 | 0 | 0 | 0 | 372683 | 120533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348610 | 48552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988871 | 169085 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-07-24 | QTR1 | 19/20 |  | 2018-07-12 | QTR1 | 18/19 | 606 | 9121390.75 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K87 | 43654015201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 80 | 85 | 69 | 16 | 0 | 0 | 5 | 0 | 342215 | 18735 | 323480 | 342215 | 303600 | 0 | 0 | 0 | 303600 | 303600 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2019-08-22 | QTR1 | 19/20 |  | 2019-07-08 | QTR1 | 19/20 | 606 | 394431.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K89 | 43653615201 | 2018-08-30 | QTR1 | 18/19 | 1 | 1 | 100 | 111 | 107 | 4 | 0 | 0 | 11 | 0 | 512803 | 19500 | 493303 | 536803 | 517303 | 0 | 0 | 0 | 517303 | 517303 | 0 | 24000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | F650946504 | FLORIDA DRAWBRIDGES INC. | N/A | N/A | N/A | N/A | 2019-11-14 | QTR2 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 606 | 404500 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L26 | 43653515201 | 2018-11-29 | QTR2 | 18/19 | 1 | 0 | 210 | 233 | 233 | 0 | 0 | 0 | 23 | 0 | 878038 | 49835 | 828203 | 878038 | 768146 | 0 | 0 | 0 | 768146 | 768146 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-22 | QTR2 | 19/20 |  | 2019-10-23 | QTR2 | 19/20 | 606 | 1044218 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L27 | 43081725201 | 2018-02-22 | QTR3 | 17/18 | 3 | 0 | 240 | 274 | 267 | 7 | 0 | 0 | 34 | 0 | 1584337 | 51335 | 1533002 | 1584337 | 1427013 | 0 | 0 | 0 | 1427013 | 1426855 | -158 | 0 | 23 | 0 | 0 | 27248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40243 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-14 | QTR1 | 19/20 |  | 2019-06-12 | QTR4 | 18/19 | 606 | 1676992.2 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L37 | 42919325201 | 2018-01-25 | QTR3 | 17/18 | 4 | 3 | 200 | 241 | 218 | 23 | 0 | 0 | 41 | 0 | 1491900 | 50260 | 1441640 | 1633114 | 1580093 | 0 | 60000 | 60000 | 1640093 | 1562174 | -60174 | 141214 | 29 | 0 | 0 | 4537 | 0 | 0 | 0 | 82537 | 9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48121 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135195 | 14309 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-02-10 | QTR3 | 19/20 |  | 2019-12-04 | QTR2 | 19/20 | 606 | 1421302.2 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L51 | 43029129201 | 2017-12-04 | QTR2 | 17/18 | 2 | 1 | 600 | 723 | 720 | 3 | 0 | 0 | 123 | 0 | 5545538 | 70946 | 5474592 | 5585378 | 5557420 | 0 | 0 | 0 | 5557420 | 0 | -5557420 | 39840 | 31 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 77248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 82828 | 0 | F301004760 | RTECH HEC JV | N/A | N/A | N/A | N/A | 2020-04-08 | QTR4 | 19/20 |  | 2020-02-17 | QTR3 | 19/20 | 606 | 7161526 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 64 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L72 | 44183315201 | 2019-08-29 | QTR1 | 19/20 | 1 | 0 | 80 | 110 | 107 | 3 | 0 | 0 | 30 | 0 | 428626 | 19906 | 408720 | 428626 | 355753 | 0 | 0 | 0 | 355753 | 355753 | 0 | 0 | 12 | 0 | 0 | 1358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1358 | 0 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2020-05-07 | QTR4 | 19/20 |  | 2020-03-05 | QTR3 | 19/20 | 636 | 412463.45 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L83 | 44124315201 | 2018-04-26 | QTR4 | 17/18 | 1 | 0 | 140 | 196 | 196 | 0 | 0 | 0 | 56 | 0 | 626626 | 28957 | 597669 | 626626 | 577033 | 0 | 0 | 0 | 577033 | 576947 | -87 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-08-05 | QTR1 | 19/20 |  | 2019-07-17 | QTR1 | 19/20 | 606 | 611515.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L91 | 44203915201 | 2018-08-30 | QTR1 | 18/19 | 1 | 0 | 200 | 218 | 217 | 1 | 0 | 0 | 18 | 0 | 1590779 | 50000 | 1540779 | 1590779 | 1534205 | 0 | 0 | 0 | 1534205 | 1533853 | -352 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-09-27 | QTR1 | 19/20 | 606 | 1335461.5 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7389 | 43272015201 | 2017-01-25 | QTR3 | 16/17 | 4 | 11 | 350 | 542 | 542 | 0 | 0 | 0 | 192 | 0 | 12988889 | 109000 | 12879889 | 13889049 | 13996342 | 0 | 0 | 0 | 13996342 | 14019355 | 112797 | 900160 | 162 | 0 | 0 | 619080 | 0 | 0 | 0 | 112343 | 2775 | 0 | 0 | 30835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677937 | 2775 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-01-21 | QTR3 | 19/20 |  | 2018-10-03 | QTR2 | 18/19 | 798 | 14634544.46 |  |  | 0 | 30 | 0 | 0 | -84321 | 0 |  | CO
07CO | 07 | T7391 | 43269815201 | 2017-05-24 | QTR4 | 16/17 | 2 | 1 | 160 | 256 | 368 | -112 | 112 | 0 | 51 | 45 | 1680691 | 73400 | 1607291 | 1699042 | 1672177 | -177408 | 0 | -177408 | 1494769 | 1505964 | 11195 | 18352 | 19 | 13 | 44 | 43107 | 0 | 0 | 1 | 19911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 45 | 63018 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2018-10-18 | QTR2 | 18/19 | 799 | 1603400 |  |  | 10 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7398 | 43473015201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 142 | 229 | 228 | 1 | 0 | 0 | 87 | 0 | 2979236 | 50000 | 2929236 | 2979236 | 2852469 | 0 | 0 | 0 | 2852469 | 2921837 | 69368 | 0 | 68 | 0 | 0 | 9886 | 0 | 0 | 0 | 23772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33658 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-22 | QTR1 | 19/20 |  | 2019-04-11 | QTR4 | 18/19 | 796 | 3840000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7399 | 43653015201 | 2018-01-31 | QTR3 | 17/18 | 1 | 0 | 145 | 210 | 211 | -1 | 1 | 0 | 48 | 17 | 1314062 | 50000 | 1264062 | 1314062 | 1279715 | -1665 | 0 | -1665 | 1278050 | 1277840 | -210 | 0 | 29 | 0 | 0 | 0 | 0 | 10 | 12 | 15865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5990 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 21855 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2019-10-29 | QTR2 | 19/20 | 796 | 1374960.82 |  |  | 17 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7401 | 43480615201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 155 | 217 | 217 | 0 | 0 | 0 | 62 | 0 | 2932563 | 50000 | 2882563 | 2939291 | 2859109 | 0 | 0 | 0 | 2859109 | 2924621 | 65512 | 6728 | 41 | 0 | 0 | 6728 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-04-08 | QTR4 | 18/19 | 799 | 3343300 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7404 | 43642015201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 90 | 185 | 183 | 2 | 0 | 0 | 83 | 12 | 1081175 | 50000 | 1031175 | 1081175 | 1016734 | 0 | 0 | 0 | 1016734 | 1023706 | 6971 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3371 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-08-13 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1150000 | B0 | ACC - LUMP SUM | 12 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7409 | 43649115202 | 2018-05-23 | QTR4 | 17/18 | 2 | 0 | 110 | 167 | 158 | 9 | 0 | 0 | 57 | 0 | 1575996 | 50000 | 1525996 | 1575996 | 1509644 | 0 | 0 | 0 | 1509644 | 1509644 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-08-15 | QTR1 | 19/20 |  | 2019-01-24 | QTR3 | 18/19 | 796 | 1415000 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7415 | 43982935201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 150 | 158 | 158 | 0 | 0 | 0 | 8 | 0 | 497590 | 24000 | 473590 | 497590 | 430440 | 0 | 0 | 0 | 430440 | 430440 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-06-09 | QTR4 | 18/19 | 799 | 590000.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7421 | 43648115201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 120 | 196 | 195 | 1 | 0 | 0 | 76 | 0 | 1160445 | 50000 | 1110445 | 1160445 | 1174720 | 0 | 0 | 0 | 1174720 | 1174720 | 0 | 0 | 43 | 0 | 0 | 12711 | 0 | 0 | 0 | 35671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48382 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-19 | QTR4 | 19/20 |  | 2020-03-06 | QTR3 | 19/20 | 796 | 1200000 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7422 | 44275215201 | 2018-06-13 | QTR4 | 17/18 | 3 | 0 | 161 | 172 | 161 | 11 | 0 | 0 | 11 | 0 | 96675 | 7380 | 89295 | 96675 | 89884 | 0 | 0 | 0 | 89884 | 89884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-15 | QTR1 | 19/20 |  | 2019-05-17 | QTR4 | 18/19 | 799 | 182730.91 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7427 | 43704015201 | 2018-12-05 | QTR2 | 18/19 | 1 | 1 | 160 | 205 | 189 | 16 | 0 | 0 | 27 | 18 | 1130856 | 50000 | 1080856 | 1130856 | 1101423 | 0 | 0 | 0 | 1101423 | 1102091 | 668 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 47370 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-31 | QTR3 | 19/20 |  | 2019-12-16 | QTR2 | 19/20 | 799 | 1234500 |  |  | 18 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7429 | 43753015201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 120 | 132 | 101 | 31 | 0 | 0 | 12 | 0 | 1704462 | 50000 | 1654462 | 1704462 | 1672069 | 0 | 0 | 0 | 1672069 | 1672069 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-27 | QTR3 | 19/20 |  | 2019-10-17 | QTR2 | 19/20 | 796 | 2200000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7430 | 42907525201 | 2019-02-27 | QTR3 | 18/19 | 1 | 1 | 160 | 181 | 181 | 0 | 0 | 0 | 21 | 0 | 2054444 | 50000 | 2004444 | 2076789 | 2031481 | 0 | 0 | 0 | 2031481 | 2031871 | 390 | 22345 | 8 | 0 | 0 | 16576 | 0 | 0 | 0 | 11397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3656 | 3656 | 0 | 0 | 0 | 0 | 0 | 0 | 31629 | 3656 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-13 | QTR4 | 19/20 |  | 2019-12-14 | QTR2 | 19/20 | 798 | 2450000 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7H90 | 25693125201 | 2012-11-01 | QTR2 | 12/13 | 1 | 13 | 968 | 1568 | 1568 | 0 | 0 | 0 | 415 | 185 | 82889000 | 150000 | 82739000 | 85277357 | 85130335 | 0 | 0 | 0 | 85130335 | 83583407 | -1461417 | 2388357 | 330 | 0 | 64 | 1480085 | 669683 | 0 | 121 | 651888 | 34270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95700 | 0 | 0 | 0 | 44154 | 44154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22739 | 18713 | 0 | 0 | 0 | 0 | 0 | 185 | 2294567 | 766820 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2019-11-19 | QTR2 | 19/20 |  | 2018-04-22 | QTR4 | 17/18 | 714 | 90180000 | B8 | ACC - DESIGN/BUILD - MAJOR | 76 | 85 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K19 | 43476515201 | 2014-10-20 | QTR2 | 14/15 | 2 | 16 | 1200 | 1842 | 1829 | 13 | 0 | 0 | 210 | 432 | 35360313 | 120000 | 35240313 | 59863754 | 59642810 | 0 | 0 | 0 | 59642810 | 59439123 | 0 | 24503441 | 97 | 0 | 362 | 23073894 | 0 | 0 | 0 | 379221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 901989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 24357946 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-25 | QTR2 | 19/20 | 714 | 35360312.5 |  |  | 119 | 113 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K24 | 41101145201 | 2015-04-09 | QTR4 | 14/15 | 3 | 20 | 1100 | 1320 | 1320 | 0 | 0 | 0 | 188 | 32 | 94976100 | 150000 | 94826100 | 96934830 | 96454835 | 0 | 0 | 0 | 96454835 | 95867383 | -259483 | 1958730 | 108 | 2 | 30 | 982160 | 90496 | 0 | 0 | 91279 | 4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567939 | 0 | 0 | 2 | 76759 | 32366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32 | 1718138 | 127398 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-02-28 | QTR3 | 19/20 |  | 2019-09-30 | QTR1 | 19/20 | 714 | 102853500 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 2 | 78 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L26 | 40552525201 | 2017-03-08 | QTR3 | 16/17 | 8 | 11 | 478 | 711 | 711 | 0 | 0 | 0 | 177 | 56 | 25833397 | 150000 | 25683397 | 27246296 | 27221715 | 0 | 250000 | 250000 | 27471715 | 27058324 | -265912 | 1412899 | 124 | 0 | 0 | 853789 | 51798 | 0 | 0 | 131388 | 4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 284525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1269702 | 56150 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-08-19 | QTR1 | 19/20 |  | 2019-04-25 | QTR4 | 18/19 | 714 | 23085355.33 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 56 | 53 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L58 | 43243415201 | 2017-05-10 | QTR4 | 16/17 | 1 | 1 | 255 | 368 | 368 | 0 | 0 | 0 | 99 | 14 | 5500000 | 50000 | 5450000 | 5732401 | 5687839 | 0 | 0 | 0 | 5687839 | 5688140 | 301 | 232401 | 76 | 0 | 14 | 225632 | 0 | 0 | 0 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 232401 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-06 | QTR4 | 18/19 | 709 | 4546054.26 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L77 | 42292935201 | 2017-09-19 | QTR1 | 17/18 | 1 | 0 | 204 | 473 | 474 | -1 | 1 | 0 | 269 | 0 | 5595578 | 50000 | 5545578 | 5595578 | 5582332 | -3645 | 0 | -3645 | 5578687 | 5581090 | 2402 | 0 | 242 | 0 | 0 | 9844 | 0 | 0 | 0 | 33659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43503 | 0 | F222382970 | CRISDEL GROUP INC | N/A | N/A | N/A | N/A | 2019-08-20 | QTR1 | 19/20 |  | 2019-04-23 | QTR4 | 18/19 | 796 | 3505311 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L98 | 43763715201 | 2018-04-11 | QTR4 | 17/18 | 1 | 0 | 100 | 138 | 105 | 33 | 0 | 0 | 31 | 7 | 2248889 | 50000 | 2198889 | 2248889 | 2169580 | 0 | 0 | 0 | 2169580 | 2169580 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 5 | 9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12947 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-04-19 | QTR4 | 18/19 | 796 | 2125000 |  |  | 7 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M00 | 42292945201 | 2018-05-09 | QTR4 | 17/18 | 1 | 2 | 170 | 398 | 397 | 1 | 0 | 0 | 198 | 30 | 3873725 | 50000 | 3823725 | 4070777 | 4079959 | 0 | 0 | 0 | 4079959 | 4074029 | -5930 | 197052 | 173 | 0 | 14 | 49337 | 0 | 0 | 16 | 188163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 237500 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2019-12-20 | QTR2 | 19/20 |  | 2019-11-15 | QTR2 | 19/20 | 796 | 5390436.65 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M05 | 43954615201 | 2018-05-30 | QTR4 | 17/18 | 1 | 1 | 360 | 374 | 219 | 155 | 0 | 0 | 14 | 0 | 2278000 | 50000 | 2228000 | 2281910 | 2448836 | 0 | 0 | 0 | 2448836 | 2448834 | -1 | 3910 | 9 | 0 | 0 | 3910 | 0 | 0 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5967 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-04-09 | QTR4 | 19/20 |  | 2019-08-20 | QTR1 | 19/20 | 799 | 1751000 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M06 | 44033815201 | 2018-06-13 | QTR4 | 17/18 | 1 | 0 | 165 | 235 | 255 | -20 | 20 | 0 | 70 | 0 | 5327001 | 68500 | 5258501 | 5327001 | 5287802 | -68940 | 0 | -68940 | 5218862 | 5204437 | -14425 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-11 | QTR1 | 19/20 |  | 2019-06-26 | QTR4 | 18/19 | 796 | 6993269.38 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M24 | 43649415201 | 2019-03-13 | QTR3 | 18/19 | 2 | 0 | 125 | 182 | 179 | 3 | 0 | 0 | 54 | 3 | 2316390 | 50000 | 2266390 | 2316390 | 2260239 | 0 | 0 | 0 | 2260239 | 2257824 | -2415 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 24120 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-25 | QTR4 | 19/20 |  | 2020-03-13 | QTR3 | 19/20 | 796 | 1445000 |  |  | 3 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M25 | 43386415201 | 2019-04-10 | QTR4 | 18/19 | 2 | 1 | 110 | 123 | 112 | 11 | 0 | 0 | 13 | 0 | 354276 | 10000 | 344276 | 375176 | 357381 | 0 | 0 | 0 | 357381 | 336481 | 0 | 20901 | 3 | 0 | 0 | 3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3553 | 0 | F842663349 | CHEYENNE ASSOCIATES LLC | N/A | N/A | N/A | N/A | 2020-06-03 | QTR4 | 19/20 |  | 2019-12-02 | QTR2 | 19/20 | 798 | 264999.9 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M26 | 25839935201 | 2018-12-12 | QTR2 | 18/19 | 2 | 0 | 90 | 194 | 194 | 0 | 0 | 0 | 87 | 17 | 1194104 | 30000 | 1164104 | 1194104 | 1177035 | 0 | 0 | 0 | 1177035 | 1177035 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-11-06 | QTR2 | 19/20 | 796 | 850000 |  |  | 17 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M27 | 43648015201 | 2018-12-12 | QTR2 | 18/19 | 1 | 2 | 150 | 180 | 180 | 0 | 0 | 0 | 30 | 0 | 1274649 | 45000 | 1229649 | 1382195 | 1318471 | 0 | 0 | 0 | 1318471 | 1320688 | 2217 | 107546 | 21 | 0 | 0 | 93140 | 0 | 0 | 0 | 22511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115651 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-28 | QTR3 | 19/20 |  | 2019-09-10 | QTR1 | 19/20 | 798 | 980000 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M28 | 43754115201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 175 | 201 | 162 | 39 | 0 | 0 | 26 | 0 | 870000 | 50000 | 820000 | 870000 | 820000 | 0 | 0 | 0 | 820000 | 820000 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-06-17 | QTR4 | 19/20 |  | 2020-04-03 | QTR4 | 19/20 | 796 | 1950395 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M30 | 43755215201 | 2019-02-13 | QTR3 | 18/19 | 1 | 0 | 66 | 73 | 53 | 20 | 0 | 0 | 7 | 0 | 167797 | 6825 | 160972 | 167797 | 136656 | 0 | 0 | 0 | 136656 | 136656 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-10-23 | QTR2 | 19/20 |  | 2019-09-12 | QTR1 | 19/20 | 798 | 175000 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M32 | 43751815201 | 2019-03-13 | QTR3 | 18/19 | 1 | 0 | 165 | 215 | 215 | 0 | 0 | 0 | 50 | 0 | 852730 | 40000 | 812730 | 852730 | 751999 | 0 | 0 | 0 | 751999 | 752000 | 1 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2020-02-14 | QTR3 | 19/20 | 796 | 850000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M33 | 43764915201 | 2019-03-13 | QTR3 | 18/19 | 1 | 1 | 220 | 286 | 286 | 0 | 0 | 0 | 60 | 6 | 2477868 | 50000 | 2427868 | 2501292 | 2443200 | 0 | 0 | 0 | 2443200 | 2437101 | -6099 | 23425 | 28 | 0 | 3 | 20944 | 0 | 0 | 3 | 7381 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 28325 | 3875 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-21 | QTR4 | 19/20 |  | 2020-03-18 | QTR3 | 19/20 | 798 | 2667000 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M34 | 41918235201 | 2018-09-12 | QTR1 | 18/19 | 1 | 0 | 120 | 181 | 180 | 1 | 0 | 0 | 41 | 20 | 1124875 | 40000 | 1084875 | 1124875 | 1167653 | 0 | 0 | 0 | 1167653 | 1167653 | 0 | 0 | 32 | 0 | 0 | 8918 | 0 | 0 | 20 | 14048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-21 | QTR4 | 19/20 |  | 2019-10-04 | QTR2 | 19/20 | 798 | 1030000 |  |  | 20 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M36 | 43648815201 | 2019-04-10 | QTR4 | 18/19 | 1 | 1 | 135 | 168 | 168 | 0 | 0 | 0 | 33 | 0 | 1604974 | 50000 | 1554974 | 1606756 | 1564847 | 0 | 0 | 0 | 1564847 | 1550744 | -14103 | 1782 | 6 | 0 | 0 | 996 | 0 | 0 | 0 | 6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7665 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-04 | QTR4 | 19/20 |  | 2020-02-24 | QTR3 | 19/20 | 799 | 2102050 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R06 | 44008915201 | 2017-08-22 | QTR1 | 17/18 | 1 | 0 | 400 | 550 | 550 | 0 | 0 | 0 | 150 | 0 | 1947000 | 50000 | 1897000 | 1947000 | 1708144 | 0 | 0 | 0 | 1708144 | 1708144 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-07-30 | QTR1 | 19/20 |  | 2019-04-29 | QTR4 | 18/19 | 796 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R07 | 43845015201 | 2017-12-05 | QTR2 | 17/18 | 1 | 0 | 500 | 572 | 572 | 0 | 0 | 0 | 72 | 0 | 2568748 | 50000 | 2518748 | 2568748 | 2497748 | 0 | 0 | 0 | 2497748 | 2497782 | 34 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-01-29 | QTR3 | 19/20 |  | 2019-09-24 | QTR1 | 19/20 | 796 | 4000000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R08 | 43402515201 | 2018-03-16 | QTR3 | 17/18 | 1 | 0 | 520 | 644 | 643 | 1 | 0 | 0 | 124 | 0 | 5832000 | 75000 | 5757000 | 5832000 | 5747984 | 0 | 0 | 0 | 5747984 | 5747984 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-04-01 | QTR4 | 19/20 |  | 2020-02-19 | QTR3 | 19/20 | 796 | 8500000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R16 | 44255215201 | 2018-07-24 | QTR1 | 18/19 | 1 | 1 | 250 | 359 | 463 | -104 | 104 | 0 | 64 | 45 | 1859105 | 50000 | 1809105 | 1859105 | 1788137 | -173160 | 0 | -173160 | 1614977 | 1610005 | -4972 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-04-28 | QTR4 | 19/20 |  | 2019-12-30 | QTR2 | 19/20 | 799 | 3000566 | A3 | ICC - DESIGN/BUILD - MINOR | 45 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R60 | 43920615201 | 2017-09-07 | QTR1 | 17/18 | 1 | 2 | 540 | 637 | 633 | 4 | 0 | 0 | 83 | 14 | 12005445 | 85975 | 11919470 | 12159938 | 12017053 | 0 | 30000 | 30000 | 12047053 | 12031297 | 38737 | 154493 | 48 | 0 | 0 | 9573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 50990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 115055 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2020-01-10 | QTR3 | 19/20 |  | 2019-07-03 | QTR1 | 19/20 | 714 | 11747696.43 | A3:B10 | ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT | 14 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N19 | 42935015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 4 | 871 | 1041 | 1065 | -24 | 24 | 0 | 149 | 21 | 42645454 | 150000 | 42495454 | 42529465 | 42335775 | -211416 | -45000 | -256416 | 42079359 | 41113609 | -965750 | -115989 | 28 | 0 | 21 | 191680 | 0 | 68 | 0 | 18199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 16 | 0 | -245979 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 21 | -31754 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-10 | QTR1 | 19/20 |  | 2017-06-14 | QTR4 | 16/17 | 854 | 44879640.02 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N92 | 42337225201 | 2015-05-07 | QTR4 | 14/15 | 6 | 18 | 875 | 1607 | 1607 | 0 | 0 | 0 | 334 | 398 | 69954000 | 150000 | 69804000 | 73801707 | 73879251 | -35000 | 0 | -35000 | 73844251 | 73110548 | -587478 | 3847707 | 114 | 0 | 0 | 265519 | 0 | 0 | 0 | 1597547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | -1019642 | 0 | 0 | 0 | 327117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 398 | 3718160 | 0 | F471943651 | DE MOYA REDLAND HEFT JV | N/A | N/A | N/A | N/A | 2020-06-09 | QTR4 | 19/20 |  | 2020-02-28 | QTR3 | 19/20 | 854 | 67972638.7 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 65 | 0 | 0 | -52381 | 0 |  | DO
08DO | 08 | E8P81 | 43561415201 | 2016-05-10 | QTR4 | 15/16 | 1 | 1 | 135 | 201 | 201 | 0 | 0 | 0 | 56 | 10 | 2564262 | 37836 | 2526426 | 2604262 | 2577346 | 0 | 0 | 0 | 2577346 | 2582540 | 5194 | 40000 | 34 | 0 | 0 | 0 | 0 | 0 | 10 | 42457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 53348 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2017-05-30 | QTR4 | 16/17 | 854 | 2264807.53 |  |  | 10 | 22 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P89 | 43546215201 | 2016-06-02 | QTR4 | 15/16 | 6 | 8 | 622 | 985 | 975 | 10 | 0 | 0 | 107 | 256 | 14923655 | 150000 | 14773655 | 18836210 | 18823730 | -19000 | 0 | -19000 | 18804730 | 18984830 | 314158 | 3912555 | 66 | 0 | 0 | 195633 | 0 | 0 | 23 | 80550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807 | 0 | 0 | 147 | 3553990 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 256 | 3854332 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2020-05-11 | QTR4 | 19/20 |  | 2019-04-27 | QTR4 | 18/19 | 854 | 23170861.47 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q39 | 43730015201 | 2017-04-11 | QTR4 | 16/17 | 3 | 25 | 865 | 956 | 687 | 269 | 0 | 0 | 91 | 0 | 42528000 | 150000 | 42378000 | 44339802 | 45313329 | 0 | 2430000 | 2430000 | 47743329 | 45896684 | -1735624 | 1811802 | 56 | 0 | 0 | 892185 | 0 | 0 | 0 | 824018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804615 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-09-18 | QTR1 | 19/20 |  | 2019-05-02 | QTR4 | 18/19 | 854 | 52100635.87 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q41 | 43516515201 | 2017-02-14 | QTR3 | 16/17 | 4 | 6 | 280 | 520 | 520 | 0 | 0 | 0 | 187 | 53 | 15839502 | 62339 | 15777163 | 16427426 | 16013444 | -22000 | 0 | -22000 | 15991444 | 16637324 | 657394 | 587924 | 130 | 0 | 20 | 279691 | 0 | 0 | 33 | 128973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 463933 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-19 | QTR3 | 19/20 |  | 2018-10-31 | QTR2 | 18/19 | 854 | 15350000 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q54 | 43517115201 | 2017-06-06 | QTR4 | 16/17 | 4 | 9 | 315 | 573 | 645 | -72 | 72 | 0 | 189 | 69 | 16868340 | 150000 | 16718340 | 17223693 | 16580725 | -451756 | 0 | -451756 | 16128969 | 17348378 | 1219409 | 355352 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 175352 | 0 | 0 | 0 | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 264477 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-03-30 | QTR3 | 19/20 |  | 2019-06-28 | QTR4 | 18/19 | 854 | 18298995 |  |  | 0 | 96 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q91 | 43915315201 | 2017-12-12 | QTR2 | 17/18 | 1 | 1 | 140 | 222 | 222 | 0 | 0 | 0 | 55 | 27 | 1568431 | 50000 | 1518431 | 1602854 | 1622457 | 0 | 0 | 0 | 1622457 | 1624753 | 2296 | 34423 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 34423 | 34423 | 0 | 0 | 0 | 0 | 0 | 27 | 73037 | 34423 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-01-18 | QTR3 | 18/19 | 854 | 1431341.26 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q92 | 43798815201 | 2018-01-23 | QTR3 | 17/18 | 3 | 3 | 315 | 440 | 440 | 0 | 0 | 0 | 89 | 36 | 9338889 | 101107 | 9237782 | 10684311 | 9478150 | 0 | 0 | 0 | 9478150 | 9949597 | 471447 | 1345422 | 43 | 0 | 0 | 653762 | 0 | 0 | 0 | 31212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 677701 | 0 | 0 | 1 | 32396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1395071 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-04-24 | QTR4 | 19/20 |  | 2019-08-08 | QTR1 | 19/20 | 854 | 10469556.31 |  |  | 1 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R18 | 43652115201 | 2018-05-31 | QTR4 | 17/18 | 3 | 5 | 250 | 368 | 353 | 15 | 0 | 0 | 96 | 22 | 11208613 | 126303 | 11082310 | 11702780 | 11690102 | -20000 | 0 | -20000 | 11670102 | 11846829 | 176726 | 494166 | 44 | 0 | 0 | 0 | 0 | 0 | 14 | 352634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 94166 | 0 | 0 | 0 | 59769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 506569 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-13 | QTR2 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 12719348.24 |  |  | 14 | 52 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R46 | 44154915201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 125 | 160 | 160 | 0 | 0 | 0 | 33 | 2 | 648447 | 32811 | 615636 | 654795 | 614302 | 0 | 0 | 0 | 614302 | 607816 | -137 | 6348 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-03-23 | QTR3 | 19/20 |  | 2020-01-10 | QTR3 | 19/20 | 854 | 709931.87 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R56 | 44290165201 | 2018-10-16 | QTR2 | 18/19 | 1 | 0 | 70 | 84 | 82 | 2 | 0 | 0 | 14 | 0 | 994137 | 38015 | 956121 | 994137 | 967509 | 0 | 0 | 0 | 967509 | 967509 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-03 | QTR4 | 18/19 | 854 | 805668.36 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R57 | 44290175201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 106 | 116 | 111 | 5 | 0 | 0 | 10 | 0 | 679823 | 25404 | 654419 | 679823 | 674133 | -9500 | 0 | -9500 | 664633 | 664633 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-07-17 | QTR1 | 19/20 |  | 2019-05-21 | QTR4 | 18/19 | 854 | 820726.4 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R59 | 44290185201 | 2018-11-15 | QTR2 | 18/19 | 1 | 0 | 150 | 205 | 204 | 1 | 0 | 0 | 55 | 0 | 1646521 | 50000 | 1596521 | 1646521 | 1599372 | -10000 | 0 | -10000 | 1589372 | 1582806 | -6566 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-09-26 | QTR1 | 19/20 |  | 2019-07-24 | QTR1 | 19/20 | 854 | 1947436.04 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R64 | 44263115201 | 2018-11-15 | QTR2 | 18/19 | 1 | 3 | 150 | 177 | 144 | 33 | 0 | 0 | 27 | 0 | 4517345 | 50000 | 4467345 | 4665904 | 4834996 | 0 | 0 | 0 | 4834996 | 4833642 | -1354 | 148560 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 104409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149566 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-11-21 | QTR2 | 19/20 |  | 2019-08-14 | QTR1 | 19/20 | 854 | 1860602.62 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
BIiwiMDEvMzEvMjAxOSIsMTEwMDAzMC4sMTEwMTY0OS4sMTAyNDE5MS4sMTYxOC45NywxMDAwMDAuLDEwMjY3NTYuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDEwMDAwMC4sMC4sMC4sMC4sMC4sMC4sMTAwMDAwLiwxMDAwMDAuLDExMjQxOTEuLDEwMjY3NTYuLC05NzQzNS4sMTIxNjAzOS4sIkI1IiwiQUNDIC0gSU5DRU5USVZFL0RJU0lOQ0VOVElWRSIsIiINCiIwNiIsIkU2SzU5IiwiNDE4MzEyMjUyMDEiLCJGNDgxMjc3Njg1IiwiSlZBIEVOR0lORUVSSU5HIENPTlRSQUNUT1IgSU5DIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMDcvMjgvMjAxNiIsOTQ4ODgyMC4sMTA1NTYyODguLDEwMzY3MTc2LiwxMDY3NDY3LjY0LDQwMDAwMC4sMTA0MDkwNTQuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDQwMDAwMC4sMC4sMC4sMC4sMC4sMC4sNDAwMDAwLiw0MDAwMDAuLDEwNzY3MTc2LiwxMDQwOTA1NC4sLTM1ODEyMy4sOTEyMTM5MS4sIkI1IiwiQUNDIC0gSU5DRU5USVZFL0RJU0lOQ0VOVElWRSIsIiINCiIwNiIsIkU2Szg3IiwiNDM2NTQwMTUyMDEiLCJGNTIyMDg0MDg5IiwiR0VNU1RPTkUgTExDIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMTEvMjkvMjAxOCIsMzQyMjE1LiwzNDIyMTUuLDMwMzYwMC4sLjAwLDAuLDMwMzYwCO | BIiwiMDEvMzEvMjAxOSIsMTEwMDAzMC4sMTEwMTY0OS4sMTAyNDE5MS4sMTYxOC45NywxMDAwMDAuLDEwMjY3NTYuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDEwMDAwMC4sMC4sMC4sMC4sMC4sMC4sMTAwMDAwLiwxMDAwMDAuLDExMjQxOTEuLDEwMjY3NTYuLC05NzQzNS4sMTIxNjAzOS4sIkI1IiwiQUNDIC0gSU5DRU5USVZFL0RJU0lOQ0VOVElWRSIsIiINCiIwNiIsIkU2SzU5IiwiNDE4MzEyMjUyMDEiLCJGNDgxMjc3Njg1IiwiSlZBIEVOR0lORUVSSU5HIENPTlRSQUNUT1IgSU5DIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMDcvMjgvMjAxNiIsOTQ4ODgyMC4sMTA1NTYyODguLDEwMzY3MTc2LiwxMDY3NDY3LjY0LDQwMDAwMC4sMTA0MDkwNTQuLDAuLDAuLDAuLDAuLDAuLDAuLDAuLDQwMDAwMC4sMC4sMC4sMC4sMC4sMC4sNDAwMDAwLiw0MDAwMDAuLDEwNzY3MTc2LiwxMDQwOTA1NC4sLTM1ODEyMy4sOTEyMTM5MS4sIkI1IiwiQUNDIC0gSU5DRU5USVZFL0RJU0lOQ0VOVElWRSIsIiINCiIwNiIsIkU2Szg3IiwiNDM2NTQwMTUyMDEiLCJGNTIyMDg0MDg5IiwiR0VNU1RPTkUgTExDIiwiTi9BIiwiTi9BIiwiTi9BIiwiTi9BIiwiMTEvMjkvMjAxOCIsMzQyMjE1LiwzNDIyMTUuLDMwMzYwMC4sLjAwLDAuLDMwMzYw | [104 empty] | CO

## Sheet2 (hidden)
Áí‹P°yö“ ˜ÕàÅ=UT €˜¾í‹þÿÿÿÿÿÿ title=We¤^—U€ PàOÐ ê:i¢Ø+00/C:\x1ƒO Usersd ï¾sN¬$ƒO .ãa[:£ú€Users@shell32.dllCO | Áí‹P°yö“ ˜ÕàÅ=UT €˜¾í‹þÿÿÿÿÿÿ title=We¤^—U€ PàOÐ ê:i¢Ø+00/C:\x1ƒO Usersd ï¾sN¬$ƒO .ãa[:£ú€Users@shell32.dll |  | CO | 0 | 01co | 1 | 0
CO |  |  | CO | 0 | 01do | 1 | 0
CO |  |  | CO | 0 | 02co | 1 | 0
CO |  |  | CO | 0 | 02do | 1 | 0
CO |  |  | CO | 0 | 03co | 1 | 0
CO |  |  | CO | 0 | 03do | 1 | 0
CO |  |  | CO | 0 | 04co | 1 | 0
CO |  |  | CO | 0 | 04do | 1 | 0
CO |  |  | CO | 0 | 05co | 1 | 0
CO |  | T | CO | 0 | 05do | 1 | 0
CO |  |  | CO | 0 | 06co | 1 | 0
CO |  |  | CO | 0 | 06do | 1 | 0
CO |  |  | CO | 0 | 07co | 1 | 0
CO |  |  | CO | 0 | 07do | 1 | 0
CO |  |  | CO | 0 | 08co | 1 | 0
CO |  |  | CO | 0 | 08do | 1 | 0
CO |  |  | CO
CO |  |  | CO
CO |  |  | CO |  | 0