## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 76419019 | 75933207 | 77383599 | 76717702 | 0 | 77653989 | 2.266% | 100% | 923295 | 1.216% | 964579 | 1.262% | 2680 | 240 | 8.955% | 192 | 7.164% | 0 | 0% | 93 | 3.47% | 2773 | 3.47% | 3202 | 3116 | 2684 | 0.1493% | 77.78%
| District Let | 38419626 | 37744459 | 39416821 | 39094801 | 0 | 39081317 | 3.542% | 91.67% | 1063690 | 2.818% | 997197 | 2.596% | 2580 | 484 | 18.76% | 197 | 7.636% | 112 | 4.341% | 385 | 14.92% | 3077 | 19.26% | 3760 | 3652 | 2971 | 15.16% | 75%
| All Contracts | 114838645 | 113677666 | 116800420 | 115812503 | 0 | 116735306 | 2.69% | 95.24% | 1986985 | 1.748% | 1961776 | 1.708% | 5260 | 724 | 13.76% | 389 | 7.395% | 112 | 2.129% | 478 | 9.087% | 5850 | 11.22% | 6962 | 6768 | 5655 | 7.51% | 76.19%
2 | Central Let | 46276804 | 45678849 | 46612467 | 45381278 | 0 | 45301362 | -0.8264% | 100% | 515021 | 1.127% | 335663 | 0.7253% | 2685 | 373 | 13.89% | 278 | 10.35% | 44 | 1.639% | 64 | 2.384% | 2793 | 4.022% | 3444 | 3312 | 2661 | -0.8939% | 92.86%
| District Let | 26460502 | 26125736 | 26576975 | 26502103 | 0 | 26537186 | 1.575% | 100% | 229844 | 0.8798% | 116473 | 0.4402% | 947 | 175 | 18.48% | 238 | 25.13% | 153 | 16.16% | 75 | 7.92% | 1175 | 24.08% | 1588 | 1849 | 1436 | 51.64% | 50%
| All Contracts | 72737306 | 71804585 | 73189442 | 71883381 | 0 | 71838548 | 0.0473% | 100% | 744865 | 1.037% | 452136 | 0.6216% | 3632 | 548 | 15.09% | 516 | 14.21% | 197 | 5.424% | 139 | 3.827% | 3968 | 9.251% | 5032 | 5161 | 4097 | 12.8% | 83.33%
3 | Central Let | 27404780 | 27173797 | 27617243 | 27467220 | 0 | 27882179 | 2.607% | 100% | 139579 | 0.5137% | 212464 | 0.7753% | 1552 | 582 | 37.5% | 221 | 14.24% | 172 | 11.08% | 6 | 0.3866% | 1730 | 11.47% | 2533 | 2498 | 1695 | 9.214% | 88.89%
| District Let | 27246925 | 26655983 | 28147187 | 27443642 | 0 | 27166716 | 1.916% | 92.86% | 1033955 | 3.879% | 900260 | 3.304% | 2040 | 490 | 24.02% | 314 | 15.39% | 107 | 5.245% | 409 | 20.05% | 2556 | 25.29% | 3360 | 3232 | 2428 | 19.02% | 57.14%
| All Contracts | 54651705 | 53829780 | 55764430 | 54910862 | 0 | 55048895 | 2.265% | 95.65% | 1173534 | 2.18% | 1112724 | 2.036% | 3592 | 1072 | 29.84% | 535 | 14.89% | 279 | 7.767% | 415 | 11.55% | 4286 | 19.32% | 5893 | 5730 | 4123 | 14.78% | 69.57%
4 | Central Let | 52338822 | 51628877 | 54225635 | 52594576 | 0 | 52911996 | 2.485% | 100% | 2030956 | 3.934% | 1886810 | 3.605% | 3117 | 704 | 22.59% | 311 | 9.978% | 93 | 2.984% | 178 | 5.711% | 3388 | 8.694% | 4389 | 4325 | 3310 | 6.192% | 100%
| District Let | 36648931 | 36196019 | 38213938 | 37937793 | 0 | 36861914 | 1.84% | 100% | 1637565 | 4.524% | 1565006 | 4.27% | 2563 | 564 | 22.01% | 201 | 7.842% | 94 | 3.668% | 262 | 10.22% | 2919 | 13.89% | 3684 | 3459 | 2694 | 5.111% | 100%
| All Contracts | 88987753 | 87824896 | 92439573 | 90532369 | 0 | 89773910 | 2.219% | 100% | 3668521 | 4.177% | 3451816 | 3.879% | 5680 | 1268 | 22.32% | 512 | 9.014% | 187 | 3.292% | 440 | 7.746% | 6307 | 11.04% | 8073 | 7784 | 6004 | 5.704% | 100%
5 | Central Let | 129106275 | 128072273 | 133470588 | 136274365 | 586693 | 135081966 | 5.473% | 91.67% | 4295521 | 3.354% | 4364314 | 3.38% | 4250 | 664 | 15.62% | 424 | 9.976% | 42 | 0.9882% | 520 | 12.24% | 4812 | 13.22% | 5921 | 5929 | 4841 | 13.91% | 83.33%
| District Let | 35679288 | 35175033 | 36072586 | 35866013 | 0 | 35727364 | 1.57% | 100% | 457110 | 1.3% | 393298 | 1.102% | 2894 | 337 | 11.64% | 355 | 12.27% | 22 | 0.7602% | 240 | 8.293% | 3156 | 9.053% | 3848 | 4482 | 3790 | 30.96% | 69.23%
| All Contracts | 164785563 | 163247306 | 169543174 | 172140378 | 586693 | 170809330 | 4.632% | 96% | 4752631 | 2.911% | 4757612 | 2.887% | 7144 | 1001 | 14.01% | 779 | 10.9% | 64 | 0.8959% | 760 | 10.64% | 7968 | 11.53% | 9769 | 10411 | 8631 | 20.81% | 76%
6 | Central Let | 68245152 | 67487208 | 69629304 | 68428636 | 3410000 | 68164651 | 1.004% | 100% | 1546885 | 2.292% | 1384152 | 2.028% | 2849 | 377 | 13.23% | 235 | 8.249% | 75 | 2.633% | 58 | 2.036% | 2982 | 4.668% | 3624 | 3391 | 2779 | -2.457% | 100%
| District Let | 8923337 | 8651916 | 9062215 | 8708947 | 0 | 8699149 | 0.5459% | 85.71% | 224876 | 2.599% | 138878 | 1.556% | 1895 | 383 | 20.21% | 178 | 9.393% | 9 | 0.4749% | 0 | 0% | 1904 | 0.4749% | 2530 | 2116 | 1555 | -17.94% | 100%
| All Contracts | 77168489 | 76139124 | 78691519 | 77137583 | 3410000 | 76863800 | 0.9518% | 93.75% | 1771761 | 2.327% | 1523030 | 1.974% | 4744 | 760 | 16.02% | 413 | 8.706% | 84 | 1.771% | 58 | 1.223% | 4886 | 2.993% | 6154 | 5507 | 4334 | -8.642% | 100%
7 | Central Let | 66153936 | 65483936 | 68364639 | 68970995 | 0 | 68817401 | 5.091% | 87.5% | 2488056 | 3.799% | 2210703 | 3.342% | 2151 | 458 | 21.29% | 258 | 11.99% | 0 | 0% | 213 | 9.902% | 2364 | 9.902% | 3080 | 2994 | 2278 | 5.904% | 87.5%
| District Let | 20976509 | 20642909 | 21497878 | 21232284 | 0 | 21232551 | 2.856% | 100% | 649069 | 3.144% | 521369 | 2.485% | 2653 | 248 | 9.348% | 184 | 6.936% | 0 | 0% | 110 | 4.146% | 2763 | 4.146% | 3240 | 2972 | 2540 | -4.259% | 100%
| All Contracts | 87130445 | 86126845 | 89862517 | 90203279 | 0 | 90049952 | 4.555% | 94.44% | 3137125 | 3.642% | 2732072 | 3.136% | 4804 | 706 | 14.7% | 442 | 9.201% | 0 | 0% | 323 | 6.724% | 5127 | 6.724% | 6320 | 5966 | 4818 | 0.2914% | 94.44%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 404922718 | 403675650 | 428623884 | 429265863 | 0 | 428092461 | 6.049% | 91.67% | 22599086 | 5.598% | 23701167 | 5.853% | 6350 | 1125 | 17.72% | 683 | 10.76% | 434 | 6.835% | 1084 | 17.07% | 7868 | 23.91% | 9684 | 9393 | 7585 | 19.45% | 0%
| All Contracts | 404922718 | 403675650 | 428623884 | 429265863 | 0 | 428092461 | 6.049% | 91.67% | 22599086 | 5.598% | 23701167 | 5.853% | 6350 | 1125 | 17.72% | 683 | 10.76% | 434 | 6.835% | 1084 | 17.07% | 7868 | 23.91% | 9684 | 9393 | 7585 | 19.45% | 91.67%
Totals This Qtr | Central Let | 465944788 | 461458147 | 477303475 | 475834772 | 3996693 | 475813544 | 3.111% | 97.26% | 11939313 | 2.587% | 11358685 | 2.438% | 19284 | 3398 | 17.62% | 1919 | 9.951% | 426 | 2.209% | 1132 | 5.87% | 20842 | 8.079% | 26193 | 25565 | 20248 | 4.999% | 90.41%
| District Let | 599277836 | 594867705 | 627611484 | 626051446 | 0 | 623398658 | 4.796% | 95% | 27895195 | 4.689% | 28333648 | 4.728% | 21922 | 3806 | 17.36% | 2350 | 10.72% | 931 | 4.247% | 2565 | 11.7% | 25418 | 15.95% | 31694 | 31155 | 24999 | 14.04% | 80%
| All Contracts | 1065222624 | 1056325852 | 1104914959 | 1101886218 | 3996693 | 1099212202 | 4.06% | 96.08% | 39834508 | 3.771% | 39692333 | 3.726% | 41206 | 7204 | 17.48% | 4269 | 10.36% | 1357 | 3.293% | 3697 | 8.972% | 46260 | 12.27% | 57887 | 56720 | 45247 | 9.807% | 84.97%
Totals Previous Quarter | Central Let | 275938190 | 273334425 | 283625187 | 282656848 | 3206693 | 281526488 | 2.997% | 97.78% | 8180554 | 2.993% | 7686997 | 2.786% | 12114 | 1948 | 16.08% | 1262 | 10.42% | 331 | 2.732% | 618 | 5.102% | 13063 | 7.834% | 16321 | 15695 | 12485 | 3.063% | 91.11%
| District Let | 485846228 | 483354827 | 513314120 | 512159122 | 0 | 509483822 | 5.406% | 92.5% | 26665749 | 5.517% | 27467893 | 5.654% | 13186 | 2254 | 17.09% | 1415 | 10.73% | 602 | 4.565% | 2051 | 15.55% | 15839 | 20.12% | 19538 | 19276 | 15607 | 18.36% | 72.5%
| All Contracts | 761784418 | 756689252 | 796939307 | 794815970 | 3206693 | 791010310 | 4.536% | 95.29% | 34846303 | 4.605% | 35154890 | 4.615% | 25300 | 4202 | 16.61% | 2677 | 10.58% | 933 | 3.688% | 2669 | 10.55% | 28902 | 14.24% | 35859 | 34971 | 28092 | 11.04% | 82.35%
Totals Fiscal Year 2019/2020 | Central Let | 988991659 | 977780000 | 1022343017 | 1014413734 | 5645500 | 1017429355 | 4.055% | 88.24% | 34731579 | 3.552% | 33351357 | 3.372% | 47880 | 9559 | 19.96% | 4613 | 9.635% | 1119 | 2.337% | 3967 | 8.285% | 52966 | 10.62% | 67141 | 64834 | 50662 | 5.81% | 85.29%
| District Let | 1803149100 | 1793976712 | 1897132458 | 1887556879 | 10770000 | 1855703838 | 3.441% | 92.36% | 91015984 | 5.073% | 92450946 | 5.127% | 49124 | 7332 | 14.93% | 4291 | 8.735% | 659 | 1.342% | 5069 | 10.32% | 54852 | 11.66% | 66476 | 65192 | 53569 | 9.049% | 86.81%
| All Contracts | 2792140759 | 2771756712 | 2919475475 | 2901970613 | 16415500 | 2873133193 | 3.657% | 90.13% | 125747563 | 4.537% | 125802303 | 4.506% | 97004 | 16891 | 17.41% | 8904 | 9.179% | 1778 | 1.833% | 9036 | 9.315% | 107818 | 11.15% | 133617 | 130026 | 104231 | 7.45% | 85.99%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | 140.7% | 0 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 91.39% | 1 | 1353 | 15508 | 22 | 21 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31
| 01 | T1675 | 43088715201 | 2017-08-30 | QTR1 | 17/18 | 3 | 3 | 150 | 282 | 282 | 150% | 0 | 0 | 0 | 0 | 57 | 75 | 815194 | 35094 | 780100 | 856566 | 821472 | 0 | 0 | 0 | 821472 | 822481 | 105.4% | 1 | 1009 | 41372 | 36 | 21 | 0 | 0 | -1090 | 868 | 0 | 72 | 48111 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 41372 | 31652 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 |  | 2019-03-21 | QTR3 | 18/19 | 113 | 783433.16 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1702 | 43509015201 | 2018-02-28 | QTR3 | 17/18 | 2 | 2 | 240 | 285 | 282 | 98.75% | 1 | 3 | 0 | 0 | 45 | 0 | 2098354 | 50000 | 2048354 | 2203054 | 2035840 | 0 | 0 | 0 | 2035840 | 2034275 | 99.31% | 1 | -1565 | 104700 | 29 | 16 | 0 | 0 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104700 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-06 | QTR2 | 20/21 |  | 2019-04-29 | QTR4 | 18/19 | 115 | 2050385.52 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1742 | 43539015201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 350 | 433 | 402 | 91.14% | 1 | 31 | 0 | 0 | 83 | 0 | 3732644 | 50000 | 3682644 | 3755256 | 3738358 | 0 | 0 | 0 | 3738358 | 3735826 | 101.4% | 1 | -2532 | 22611 | 53 | 30 | 0 | 0 | 12441 | 12441 | 0 | 0 | 13919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26360 | 12441 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 |  | 2020-10-30 | QTR2 | 20/21 | 113 | 3397781.79
| 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | 104.2% | 1 | -19598 | 2100 | 10 | 24 | 0 | 3 | 2846 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4946 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6
| 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 97.86% | 1 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | 101.4% | 1 | -317 | 3200 | 16 | 9 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55
| 01 | T1758 | 43943715201 | 2019-07-31 | QTR1 | 19/20 | 2 | 2 | 265 | 288 | 219 | 74.34% | 1 | 69 | 0 | 0 | 22 | 1 | 7004551 | 95304 | 6909247 | 7119832 | 7259276 | 0 | 0 | 0 | 7259276 | 7106733 | 102.9% | 1 | -152543 | 115281 | 17 | 5 | 0 | 1 | 114321 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 115281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-08-10 | QTR1 | 20/21 | 108 | 9375095.25
| 01 | T1773 | 44067215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 75 | 83 | 70 | 82.67% | 1 | 13 | 0 | 0 | 8 | 0 | 214731 | 9756 | 204975 | 214731 | 194639 | 0 | 0 | 0 | 194639 | 194639 | 94.96% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-08-21 | QTR1 | 20/21 | 108 | 215733.31
| 01 | T1997 | 40828665201 | 2017-01-25 | QTR3 | 16/17 | 2 | 11 | 1100 | 1215 | 1201 | 98.73% | 1 | 14 | 0 | 0 | 115 | 0 | 58011809 | 150000 | 57861809 | 58671616 | 58073269 | 0 | 0 | 0 | 58073269 | 59258196 | 102.4% | 1 | 1257928 | 659807 | 51 | 64 | 0 | 0 | 424487 | 0 | 0 | 0 | 290901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143938 | 0 | 0 | 0 | 603216 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 |  | 2020-08-13 | QTR1 | 20/21 | 118 | 69879385.2
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 9 | 15 | 24 | 2680 | 3202 | 3116 | 77.78% | 7 | 86 | 47 | 0 | 432 | 90 | 76419019 | 485812 | 75933207 | 77383599 | 76717702 | -74448 | 0 | -74448 | 76643254 | 77653989 | 100% | 9 | 1083735 | 964579 | 240 | 192 | 0 | 18 | 681925 | 13309 | 0 | 72 | 359191 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143938 | 0 | 0 | 93 | 923295 | 44093
| 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 125% | 0 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 102.4% | 1 | 19995 | 355643 | 83 | 66 | 0 | 200 | 43207 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 423577 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 01 | E1P46 | 43580715201 | 2017-10-19 | QTR2 | 17/18 | 1 | 1 | 125 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 84 | 0 | 869954 | 43581 | 826373 | 869954 | 834474 | 0 | 0 | 0 | 834474 | 836068 | 101.2% | 1 | 1595 | 0 | 79 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2018-07-30 | QTR1 | 18/19 | 108 | 794913.85
| 01 | E1R05 | 43629915201 | 2018-03-01 | QTR3 | 17/18 | 1 | 9 | 320 | 663 | 663 | 172.5% | 0 | 0 | 0 | 0 | 183 | 160 | 7996438 | 89923 | 7906515 | 8606992 | 8773391 | 0 | 0 | 0 | 8773391 | 8748736 | 110.7% | 0 | -916 | 610555 | 76 | 35 | 72 | 159 | 583162 | 0 | 0 | 1 | 13293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 160 | 596455 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-11-12 | QTR2 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 115 | 8160370.04 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 96.67% | 1 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | 101.1% | 1 | -259 | 29714 | 51 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91
| 01 | E1R78 | 43502915201 | 2019-03-21 | QTR3 | 18/19 | 1 | 0 | 100 | 164 | 166 | 102% | 1 | -2 | 2 | 0 | 64 | 0 | 982956 | 35636 | 947320 | 982956 | 953745 | -3330 | 0 | -3330 | 950415 | 950415 | 100.3% | 1 | 0 | 0 | 50 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-10-19 | QTR2 | 20/21 |  | 2020-06-07 | QTR4 | 19/20 | 113 | 837254.07 | B0 | ACC - LUMP SUM
| 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 148.8% | 0 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 100.3% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM
| 01 | E1R86 | 44108815201 | 2018-11-09 | QTR2 | 18/19 | 1 | 0 | 370 | 470 | 470 | 106.5% | 1 | 0 | 0 | 0 | 76 | 24 | 2469000 | 50000 | 2419000 | 2469000 | 2431659 | 0 | 0 | 0 | 2431659 | 2431659 | 100.5% | 1 | 0 | 0 | 49 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 113 | 3306921.72 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 85.88% | 1 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | 100.1% | 1 | -4903 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM
| 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 98.75% | 1 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | 98.18% | 1 | -8 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15
| 01 | E1S13 | 44462715201 | 2020-01-16 | QTR3 | 19/20 | 1 | 1 | 130 | 168 | 130 | 72.31% | 1 | 38 | 0 | 0 | 36 | 2 | 993513 | 50000 | 943513 | 994797 | 930694 | 0 | 0 | 0 | 930694 | 928776 | 98.44% | 1 | -1919 | 1285 | 27 | 9 | 0 | 0 | 1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-10-01 | QTR2 | 20/21 | 108 | 1140044.02
| 01 | E1S47 | 43997015201 | 2020-01-16 | QTR3 | 19/20 | 1 | 0 | 100 | 125 | 89 | 64% | 1 | 36 | 0 | 0 | 25 | 0 | 450312 | 27504 | 422808 | 450312 | 440733 | 0 | 0 | 0 | 440733 | 440733 | 104.2% | 1 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 115 | 480716.09
| 01 | E1S50 | 44525715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 0 | 45 | 53 | 51 | 95.56% | 1 | 2 | 0 | 0 | 8 | 0 | 279624 | 14400 | 265224 | 279624 | 287046 | 0 | 0 | 0 | 287046 | 287046 | 108.2% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 |  | 2020-07-30 | QTR1 | 20/21 | 108 | 268843.45
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 12 | 16 | 20 | 2580 | 3760 | 3652 | 75% | 9 | 108 | 2 | 0 | 793 | 387 | 38419626 | 675167 | 37744459 | 39416821 | 39094801 | -3330 | 0 | -3330 | 39091471 | 39081317 | 91.67% | 11 | 13585 | 997197 | 484 | 197 | 72 | 359 | 627654 | 0 | 0 | 2 | 239682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 385 | 1063690 | 0
| District 01 Totals |  |  |  |  | 21 | 31 | 44 | 5260 | 6962 | 6768 | 76.19% | 16 | 194 | 49 | 0 | 1225 | 477 | 114838645 | 1160979 | 113677666 | 116800420 | 115812503 | -77778 | 0 | -77778 | 115734725 | 116735306 | 95.24% | 20 | 1097320 | 1961776 | 724 | 389 | 72 | 377 | 1309579 | 13309 | 0 | 74 | 598873 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215461 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143938 | 0 | 112 | 478 | 1986985 | 44093
| 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 104.5% | 1 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 102% | 1 | 60614 | 12839 | 39 | 74 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 |  | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28
| 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 120% | 1 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 104.9% | 1 | 67515 | 100000 | 78 | 19 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17
| 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 99.69% | 1 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 101.3% | 1 | 1507 | 42749 | 55 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149
| 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 95% | 1 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 78.26% | 1 | 0 | 0 | 1 | 26 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67
| 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | 90.39% | 1 | -98689 | 0 | 33 | 28 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-03 | QTR1 | 20/21 |  | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11
| 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 84.44% | 1 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 106.7% | 1 | 579 | 100000 | 13 | 11 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72
| 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | 139.4% | 0 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | 102% | 1 | -3801 | 80075 | 21 | 26 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85
| 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 84.56% | 1 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | 99.08% | 1 | -36444 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03
| 02 | T2735 | 44119515201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 100 | 142 | 142 | 100% | 1 | 0 | 0 | 0 | 13 | 29 | 421053 | 19914 | 401139 | 421053 | 394439 | 0 | 0 | 0 | 394439 | 394439 | 98.33% | 1 | 0 | 0 | 41 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-12-08 | QTR2 | 20/21 |  | 2020-05-26 | QTR4 | 19/20 | 208 | 428177.97
| 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 72.22% | 1 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | 102.8% | 1 | -18603 | 0 | 18 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04
| 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 95% | 1 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 94.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-02-21 | QTR3 | 19/20 | 209 | 84351.5
| 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 103.3% | 1 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 108% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95
| 02 | T2761 | 43934515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 180 | 215 | 211 | 97.78% | 1 | 4 | 0 | 0 | 35 | 0 | 4189603 | 51877 | 4137726 | 4189603 | 4189658 | 0 | 0 | 0 | 4189658 | 4163139 | 100.6% | 1 | -26519 | 0 | 30 | 5 | 0 | 0 | 4541 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6304 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-08-24 | QTR1 | 20/21 | 214 | 5262360.58
| 02 | T2766 | 44348915201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 130 | 146 | 144 | 98.46% | 1 | 2 | 0 | 0 | 16 | 0 | 1081333 | 50000 | 1031333 | 1081333 | 1019859 | 0 | 0 | 0 | 1019859 | 1018371 | 98.74% | 1 | -1488 | 0 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-04 | QTR2 | 20/21 |  | 2020-06-16 | QTR4 | 19/20 | 214 | 1202483.05
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 14 | 19 | 15 | 2685 | 3444 | 3312 | 92.86% | 13 | 132 | 9 | 0 | 666 | 93 | 46276804 | 597955 | 45678849 | 46612467 | 45381278 | -14985 | 0 | -14985 | 45366293 | 45301362 | 100% | 14 | -55329 | 335663 | 373 | 278 | 0 | 40 | 250010 | 0 | 12 | 24 | 210116 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47245 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 64 | 515021 | 27355
| 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 1 | 460 | 671 | 891 | 148.7% | 0 | -220 | 220 | 0 | 207 | 4 | 17417591 | 200000 | 17217591 | 17434064 | 17148118 | -1033560 | 0 | -1033560 | 16114558 | 17365029 | 100.9% | 1 | 1266944 | 16473 | 97 | 110 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 92445 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97
| 02 | E2X06 | 43076015201 | 2018-04-18 | QTR4 | 17/18 | 1 | 2 | 190 | 489 | 545 | 236.8% | 0 | -56 | 56 | 0 | 248 | 51 | 2957443 | 50000 | 2907443 | 3057443 | 3046193 | -151872 | 0 | -151872 | 2894321 | 2894277 | 99.55% | 1 | -43 | 100000 | 19 | 76 | 0 | 44 | 94877 | 0 | 0 | 7 | 5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 51 | 100035 | 0 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 |  | 2020-02-14 | QTR3 | 19/20 | 208 | 2882464.65
| 02 | E2Y25 | 43761715201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 250 | 365 | 351 | 100.8% | 1 | 14 | 0 | 0 | 99 | 16 | 5599368 | 63324 | 5536044 | 5599368 | 5849866 | 0 | 0 | 0 | 5849866 | 5819954 | 105.1% | 1 | -29911 | 0 | 48 | 51 | 0 | 0 | 2537 | 0 | 0 | 3 | 23074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 11453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 37064 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-05 | QTR2 | 20/21 |  | 2020-06-19 | QTR4 | 19/20 | 216 | 6362327.21
| 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 106.4% | 1 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 98.55% | 1 | 0 | 0 | 11 | 1 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 4 | 6 | 3 | 947 | 1588 | 1849 | 50% | 2 | -261 | 276 | 0 | 566 | 75 | 26460502 | 334766 | 26125736 | 26576975 | 26502103 | -1185432 | 0 | -1185432 | 25316671 | 26537186 | 100% | 4 | 1236990 | 116473 | 175 | 238 | 0 | 48 | 124154 | 0 | 0 | 10 | 87787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 17 | 11453 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 75 | 229844 | 0
| District 02 Totals |  |  |  |  | 18 | 25 | 18 | 3632 | 5032 | 5161 | 83.33% | 15 | -129 | 285 | 0 | 1232 | 168 | 72737306 | 932721 | 71804585 | 73189442 | 71883381 | -1200417 | 0 | -1200417 | 70682964 | 71838548 | 100% | 18 | 1181661 | 452136 | 548 | 516 | 0 | 88 | 374164 | 0 | 12 | 34 | 297903 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 6450 | 0 | 0 | 17 | 11453 | 0 | 15 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47245 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 139 | 744865 | 27355
| 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 137.2% | 0 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 109.8% | 1 | 2492 | -1395 | 58 | 27 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34
| 03 | T3619 | 43390215201 | 2018-11-14 | QTR2 | 18/19 | 1 | 1 | 175 | 253 | 248 | 114.9% | 1 | 5 | 0 | 0 | 72 | 6 | 1114410 | 0 | 1114410 | 1163460 | 1226323 | 0 | 0 | 0 | 1226323 | 1224530 | 109.9% | 1 | -1793 | 49050 | 34 | 13 | 10 | 6 | 49050 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | 49050 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2020-12-10 | QTR2 | 20/21 |  | 2019-10-07 | QTR2 | 19/20 | 313 | 1475964.98
| 03 | T3642 | 43274025201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 250 | 555 | 555 | 100% | 1 | 0 | 0 | 0 | 305 | 0 | 8739221 | 84002 | 8655219 | 8879082 | 9063602 | -14091 | 0 | -14091 | 9049511 | 9512844 | 109.9% | 1 | 541744 | 139862 | 250 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 |  | 2019-07-11 | QTR1 | 19/20 | 314 | 8488154.79
| 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | 93.61% | 1 | -3093 | 3300 | 17 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34
| 03 | T3663 | 43188345201 | 2019-08-28 | QTR1 | 19/20 | 1 | 2 | 85 | 155 | 155 | 117.6% | 1 | 0 | 0 | 0 | 70 | 0 | 656987 | 29252 | 627735 | 668791 | 649887 | 0 | 0 | 0 | 649887 | 649887 | 103.5% | 1 | 0 | 11804 | 25 | 30 | 12 | 0 | 11597 | 2421 | 3 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 13154 | 2421 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-05-04 | QTR4 | 19/20 | 308 | 691494.24
| 03 | T3668 | 43580015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 4 | 250 | 295 | 271 | 90.4% | 1 | 24 | 0 | 0 | 45 | 0 | 1427167 | 0 | 1427167 | 1429917 | 1395761 | 0 | 0 | 0 | 1395761 | 1394795 | 97.73% | 1 | -966 | 2750 | 34 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 |  | 2020-10-02 | QTR2 | 20/21 | 321 | 1392503.71
| 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 115% | 1 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | 97% | 1 | -30923 | 0 | 80 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22
| 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 113.3% | 1 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 96.92% | 1 | 0 | 0 | 72 | 38 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32
| 03 | T3739 | 44173715201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 45 | 64 | 63 | 106.7% | 1 | 1 | 0 | 0 | 19 | 0 | 229048 | 6715 | 222333 | 236141 | 232144 | 0 | 0 | 0 | 232144 | 232144 | 104.4% | 1 | 0 | 7093 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 7093 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 |  | 2020-08-14 | QTR1 | 20/21 | 308 | 145096.15
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 9 | 10 | 17 | 1552 | 2533 | 2498 | 88.89% | 8 | 35 | 0 | 0 | 975 | 6 | 27404780 | 230983 | 27173797 | 27617243 | 27467220 | -14091 | 0 | -14091 | 27453129 | 27882179 | 100% | 9 | 507461 | 212464 | 582 | 221 | 22 | 6 | 60647 | 2421 | 64 | 0 | 15919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 63013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 6 | 139579 | 2421
| 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 173.9% | 0 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | 108.5% | 1 | -3036 | 251063 | 77 | 50 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000
| 03 | E3P37 | 22280225201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 120 | 154 | 152 | 98.33% | 1 | 2 | 0 | 0 | 34 | 0 | 398582 | 35644 | 362938 | 398582 | 363870 | 0 | 0 | 0 | 363870 | 363870 | 100.3% | 1 | 0 | 0 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F811252530 | OMEGA COATINGS & CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 |  | 2019-11-24 | QTR2 | 19/20 | 313 | 733124
| 03 | E3Q54 | 22253925201 | 2019-05-09 | QTR4 | 18/19 | 1 | 1 | 90 | 110 | 103 | 92.22% | 1 | 7 | 0 | 0 | 20 | 0 | 922444 | 50000 | 872444 | 846935 | 658266 | 0 | 0 | 0 | 658266 | 658266 | 75.45% | 1 | 0 | -75510 | 16 | 4 | 0 | 0 | 12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 0 | 0 | -63199 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-05 | QTR2 | 20/21 |  | 2019-11-22 | QTR2 | 19/20 | 321 | 919379.25
| 03 | E3R03 | 41343525201 | 2018-05-10 | QTR4 | 17/18 | 4 | 9 | 210 | 403 | 403 | 129.5% | 0 | 0 | 0 | 0 | 165 | 28 | 1381327 | 50000 | 1331327 | 1468091 | 1381221 | -4783 | 0 | -4783 | 1376437 | 1365035 | 102.5% | 1 | -1916 | 86763 | 94 | 37 | 0 | 0 | 0 | 0 | 0 | 3 | 15065 | 1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 52304 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 28 | 80290 | 15961 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2019-09-13 | QTR1 | 19/20 | 308 | 1155000
| 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 145.7% | 0 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | 102.4% | 1 | -52116 | 158902 | 66 | 62 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94
| 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 251.7% | 0 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 119.3% | 0 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79
| 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 273 | 280 | 128.3% | 0 | -7 | 7 | 0 | 49 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4457789 | -18984 | 0 | -18984 | 4438805 | 4364461 | 101.9% | 1 | -74345 | 123339 | 26 | 23 | 0 | 14 | 48949 | 0 | 0 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04
| 03 | E3R75 | 40731075201 | 2019-06-13 | QTR4 | 18/19 | 2 | 4 | 180 | 236 | 236 | 102.2% | 1 | 0 | 0 | 0 | 52 | 4 | 1896816 | 50000 | 1846816 | 2013742 | 1899113 | 0 | 0 | 0 | 1899113 | 1899113 | 102.8% | 1 | 0 | 116926 | 22 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 102982 | 7592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 116926 | 9300 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-10-07 | QTR2 | 20/21 |  | 2020-06-19 | QTR4 | 19/20 | 308 | 1645052.8
| 03 | E3R78 | 43813815201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 90 | 124 | 116 | 91.11% | 1 | 8 | 0 | 0 | 34 | 0 | 467023 | 24986 | 442037 | 467023 | 452193 | 0 | 0 | 0 | 452193 | 452193 | 102.3% | 1 | 0 | 0 | 27 | 7 | 0 | 0 | 3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 |  | 2020-08-03 | QTR1 | 20/21 | 314 | 567888.91
| 03 | E3R84 | 43736715201 | 2019-05-09 | QTR4 | 18/19 | 3 | 1 | 150 | 273 | 264 | 134% | 0 | 9 | 0 | 0 | 63 | 60 | 1890085 | 52035 | 1838050 | 1993510 | 1844667 | 0 | 0 | 0 | 1844667 | 1822661 | 99.16% | 1 | -22007 | 103425 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 313 | 1951315.61
| 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 102.5% | 1 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | 102.3% | 1 | -82786 | 42363 | 60 | 45 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75
| 03 | E3S48 | 43973015201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 150 | 167 | 153 | 90.67% | 1 | 14 | 0 | 0 | 17 | 0 | 2362840 | 50000 | 2312840 | 2362840 | 2375062 | 0 | 0 | 0 | 2375062 | 2367596 | 102.4% | 1 | -7466 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 2687906.81
| 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 101.2% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65
| 03 | E3S50 | 22253625201 | 2019-11-14 | QTR2 | 19/20 | 2 | 0 | 120 | 125 | 50 | 37.5% | 1 | 75 | 0 | 0 | 5 | 0 | 688910 | 0 | 688910 | 688910 | 677594 | 0 | 0 | 0 | 677594 | 677594 | 98.36% | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2020-04-06 | QTR4 | 19/20 | 321 | 1158620.3
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 14 | 25 | 28 | 2040 | 3360 | 3232 | 57.14% | 8 | 128 | 7 | 0 | 911 | 409 | 27246925 | 590943 | 26655983 | 28147187 | 27443642 | -23767 | 0 | -23767 | 27419874 | 27166716 | 92.86% | 13 | -243672 | 900260 | 490 | 314 | 0 | 55 | 345209 | 0 | 73 | 106 | 237725 | 10111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 513611 | 86659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 107 | 409 | 1033955 | 109692
| District 03 Totals |  |  |  |  | 23 | 35 | 45 | 3592 | 5893 | 5730 | 69.57% | 16 | 163 | 7 | 0 | 1886 | 415 | 54651705 | 821926 | 53829780 | 55764430 | 54910862 | -37858 | 0 | -37858 | 54873003 | 55048895 | 95.65% | 22 | 263789 | 1112724 | 1072 | 535 | 22 | 61 | 405856 | 2421 | 137 | 106 | 253644 | 10111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 248 | 576624 | 86659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 279 | 415 | 1173534 | 112113
| 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 119% | 1 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 106.4% | 1 | 233861 | 985075 | 115 | 55 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22
| 04 | T4473 | 42751615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 4 | 335 | 483 | 483 | 103.6% | 1 | 0 | 0 | 0 | 148 | 0 | 14954960 | 127766 | 14827195 | 14788864 | 14238463 | 0 | 0 | 0 | 14238463 | 14552841 | 98.15% | 1 | 324737 | -166097 | 91 | 45 | 0 | 0 | 144864 | 0 | 0 | 0 | 5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 26899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -324121 | 0 | 12 | 0 | -147083 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 |  | 2020-02-06 | QTR3 | 19/20 | 409 | 12073779.82 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4479 | 43059025201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 179 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 815678 | 34169 | 781510 | 823050 | 757384 | 0 | 0 | 0 | 757384 | 756711 | 96.83% | 1 | -673 | 7371 | 93 | 22 | 0 | 0 | 7371 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9340 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 |  | 2020-06-16 | QTR4 | 19/20 | 412 | 726059.56
| 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 116.6% | 1 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | 86.03% | 1 | -253 | 22625 | 66 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52
| 04 | T4489 | 43770115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 3 | 350 | 447 | 437 | 97.14% | 1 | 10 | 0 | 0 | 97 | 0 | 5985000 | 64375 | 5920625 | 6208144 | 6389050 | 0 | 0 | 0 | 6389050 | 6213547 | 104.9% | 1 | -39102 | 223144 | 60 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 88252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506 | 0 | 0 | 0 | 7907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101665 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-07-02 | QTR1 | 20/21 | 408 | 6481016.05
| 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 103.9% | 1 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | 103.4% | 1 | -14110 | 229825 | 55 | 28 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 |  | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93
| 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 102.5% | 1 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | 105.3% | 1 | -2608 | 349724 | 45 | 28 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28
| 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 108.6% | 1 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | 106.2% | 1 | -18 | 103884 | 25 | 23 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65
| 04 | T4503 | 43611115201 | 2019-01-30 | QTR3 | 18/19 | 2 | 3 | 205 | 289 | 289 | 112.2% | 1 | 0 | 0 | 0 | 84 | 0 | 2257891 | 50000 | 2207891 | 2372485 | 2277661 | 0 | 0 | 0 | 2277661 | 2279759 | 103.3% | 1 | 2097 | 114594 | 40 | 19 | 14 | 0 | 21562 | 0 | 25 | 0 | 100250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6266 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 136606 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 412 | 2312700.41
| 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | 100.1% | 1 | -62 | 0 | 11 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89
| 04 | T4520 | 43770215201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 136 | 238 | 235 | 97.79% | 1 | 3 | 0 | 0 | 102 | 0 | 511111 | 24274 | 486837 | 511111 | 500925 | 0 | 0 | 0 | 500925 | 500762 | 102.9% | 1 | -163 | 0 | 96 | 6 | 0 | 0 | 1690 | 0 | 0 | 0 | 12605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14295 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 |  | 2020-08-27 | QTR1 | 20/21 | 412 | 517002.15
| 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 62.11% | 1 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 91.64% | 1 | 0 | 16665 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 |  | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 12 | 25 | 37 | 3117 | 4389 | 4325 | 100% | 12 | 64 | 0 | 0 | 1094 | 178 | 52338822 | 709948 | 51628877 | 54225635 | 52594576 | 0 | 0 | 0 | 52594576 | 52911996 | 100% | 12 | 503706 | 1886810 | 704 | 311 | 44 | 114 | 1190852 | 49892 | 25 | 19 | 891408 | 81663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 16 | 34397 | 0 | 12 | 14 | 200065 | 32223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -324121 | 0 | 93 | 178 | 2030956 | 189542
| 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 119.7% | 1 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | 101.8% | 1 | -998657 | 1434680 | 296 | 112 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 |  | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 119.4% | 1 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 106.5% | 1 | 0 | 107565 | 96 | 28 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428
| 04 | E4T54 | 42957525201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 158 | 281 | 242 | 87.97% | 1 | 39 | 0 | 0 | 123 | 0 | 1034836 | 50000 | 984836 | 1034836 | 958378 | 0 | 0 | 0 | 958378 | 958293 | 97.3% | 1 | -85 | 0 | 81 | 22 | 0 | 0 | 11025 | 0 | 5 | 0 | 8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 19498 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 412 | 1135394.39
| 04 | E4T56 | 43578125201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 203 | 306 | 306 | 116.7% | 1 | 0 | 0 | 0 | 103 | 0 | 1488175 | 50000 | 1438175 | 1499756 | 1508806 | 0 | 0 | 0 | 1508806 | 1504997 | 104.6% | 1 | -3808 | 11580 | 44 | 25 | 10 | 0 | 36888 | 0 | 0 | 0 | 10773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 11580 | 11580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 59242 | 11580 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 412 | 1272541.13
| 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 35.71% | 1 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 99.76% | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96
| 04 | E4T84 | 43389615201 | 2019-12-06 | QTR2 | 19/20 | 1 | 1 | 80 | 91 | 91 | 81.25% | 1 | 0 | 0 | 0 | 26 | -15 | 802818 | 31559 | 771259 | 802818 | 776329 | 0 | 0 | 0 | 776329 | 776329 | 100.7% | 1 | 0 | 0 | 22 | 4 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 |  | 2020-11-06 | QTR2 | 20/21 | 409 | 659386.45 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 94.48% | 1 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 99.71% | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89
| 04 | E4T92 | 44140915201 | 2020-01-17 | QTR3 | 19/20 | 1 | 1 | 130 | 156 | 131 | 80.77% | 1 | 25 | 0 | 0 | 26 | 0 | 888985 | 50000 | 838985 | 900166 | 850166 | 0 | 0 | 0 | 850166 | 838985 | 100% | 1 | 0 | 11181 | 23 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-09 | QTR2 | 20/21 |  | 2020-11-14 | QTR2 | 20/21 | 408 | 1308480
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 8 | 9 | 16 | 2563 | 3684 | 3459 | 100% | 8 | 225 | 0 | 0 | 859 | 262 | 36648931 | 452912 | 36196019 | 38213938 | 37937793 | 0 | 0 | 0 | 37937793 | 36861914 | 100% | 8 | -1002550 | 1565006 | 564 | 201 | 10 | 17 | 768492 | 182287 | 45 | -15 | 285408 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 12 | 221 | 123119 | 111779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 262 | 1637565 | 309575
| District 04 Totals |  |  |  |  | 20 | 34 | 53 | 5680 | 8073 | 7784 | 100% | 20 | 289 | 0 | 0 | 1953 | 440 | 88987753 | 1162860 | 87824896 | 92439573 | 90532369 | 0 | 0 | 0 | 90532369 | 89773910 | 100% | 20 | -498844 | 3451816 | 1268 | 512 | 54 | 131 | 1959344 | 232179 | 70 | 4 | 1176816 | 93213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 55 | 494942 | 3959 | 24 | 235 | 323184 | 144002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -324121 | 0 | 187 | 440 | 3668521 | 499117
| 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 111.6% | 1 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | 111.1% | 0 | -797738 | 2915022 | 79 | 65 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 |  | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06
| 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 83.33% | 1 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | 103% | 1 | -284799 | 843098 | 69 | 32 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76
| 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 101% | 1 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 108.4% | 1 | 353955 | 51986 | 59 | 40 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41
| 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 105.6% | 1 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | 99.8% | 1 | -24609 | 54891 | 45 | 47 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742
| 05 | T5615 | 43793115201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 200 | 438 | 665 | 309% | 0 | -227 | 227 | 0 | 47 | 191 | 1435273 | 48389 | 1386883 | 1466273 | 1433905 | -119880 | 0 | -119880 | 1314025 | 1313837 | 94.73% | 1 | -188 | 31000 | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 15 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 31450 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-04-13 | QTR4 | 19/20 | 507 | 1578332.97
| 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 99.92% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8
| 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 108% | 1 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | 101% | 1 | -94321 | 93683 | 136 | 54 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 512 | 0
| 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 138.5% | 0 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | 107.8% | 1 | -2583 | 3778 | 20 | 14 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 |  | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9
| 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 102% | 1 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | 101.5% | 1 | -92470 | 42528 | 52 | 32 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 |  | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55
| 05 | T5634 | 43734815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 350 | 469 | 469 | 104.3% | 1 | 0 | 0 | 0 | 104 | 15 | 7052425 | 108401 | 6944024 | 7232569 | 7465970 | 0 | 0 | 0 | 7465970 | 7453020 | 107.3% | 1 | -10558 | 180144 | 49 | 55 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 |  | 2020-07-26 | QTR1 | 20/21 | 515 | 10311527.59
| 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 100% | 1 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | 99.52% | 1 | -49387 | 3208 | 82 | 43 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78
| 05 | T5677 | 43923315201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 160 | 196 | 195 | 99.38% | 1 | 1 | 0 | 0 | 36 | 0 | 6452955 | 68620 | 6384335 | 6597931 | 6823659 | 0 | 0 | 0 | 6823659 | 6790182 | 106.4% | 1 | -33477 | 144976 | 26 | 10 | 0 | 0 | 4727 | 0 | 0 | 0 | 144976 | 9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149703 | 9705 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-30 | QTR2 | 20/21 |  | 2020-09-23 | QTR1 | 20/21 | 514 | 7161772.24 | B0 | ACC - LUMP SUM
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 12 | 27 | 50 | 4250 | 5921 | 5929 | 83.33% | 10 | -8 | 227 | 0 | 1130 | 541 | 129106275 | 1034001 | 128072273 | 133470588 | 136274365 | -140090 | 586693 | 446603 | 136720967 | 135081966 | 91.67% | 11 | -1036175 | 4364314 | 664 | 424 | 42 | 7 | 988090 | 0 | 0 | 299 | 3341716 | 168213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43079 | 3610 | 0 | 3 | 70325 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 31000 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 42 | 520 | 4295521 | 231114
| 05 | E5Y62 | 23831925201 | 2017-03-21 | QTR3 | 16/17 | 3 | 6 | 950 | 1198 | 1188 | 109.8% | 1 | 10 | 0 | 0 | 145 | 103 | 22219000 | 150000 | 22069000 | 22351916 | 22222555 | 0 | 0 | 0 | 22222555 | 22255595 | 100.8% | 1 | 54139 | 132916 | 69 | 76 | 0 | 0 | 40787 | 0 | 0 | 0 | 90621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 14091 | 0 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 156363 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2020-10-30 | QTR2 | 20/21 |  | 2020-09-14 | QTR1 | 20/21 | 515 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Z19 | 43927315201 | 2018-04-03 | QTR4 | 17/18 | 1 | 0 | 130 | 145 | 501 | 373.8% | 0 | -356 | 356 | 0 | 15 | 0 | 149935 | 9480 | 140455 | 149935 | 128601 | -51092 | 0 | -51092 | 77509 | 77509 | 55.18% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-05-27 | QTR4 | 19/20 | 513 | 204099
| 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 124% | 0 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 102.8% | 1 | 0 | 0 | 10 | 35 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 |  | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8
| 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | 294.5% | 0 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 79.35% | 1 | 0 | 0 | 2 | 18 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2019-10-17 | QTR2 | 19/20 | 513 | 307382
| 05 | E5Z64 | 44121015201 | 2018-08-07 | QTR1 | 18/19 | 2 | 7 | 420 | 552 | 552 | 111% | 1 | 0 | 0 | 0 | 86 | 46 | 4022402 | 50000 | 3972402 | 4286073 | 4275710 | 0 | 0 | 0 | 4275710 | 4234199 | 106.6% | 1 | -37972 | 263671 | 31 | 55 | 0 | 0 | 124080 | 0 | 0 | 46 | 104836 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40146 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 274759 | 14901 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-07-07 | QTR1 | 20/21 | 513 | 4100417.85
| 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 111.7% | 1 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | 99.98% | 1 | -199 | 4115 | 84 | 25 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6
| 05 | E5Z77 | 43912115201 | 2019-07-02 | QTR1 | 19/20 | 2 | 1 | 200 | 327 | 326 | 99.5% | 1 | 1 | 0 | 0 | 127 | 0 | 3278490 | 50000 | 3228490 | 3271086 | 3476815 | 0 | 0 | 0 | 3476815 | 3410719 | 105.6% | 1 | -66096 | -7404 | 72 | 55 | 0 | 0 | 23209 | 0 | 0 | 0 | -7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15805 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-08-17 | QTR1 | 20/21 | 513 | 3806383.67
| 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | 187.3% | 0 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 94.9% | 1 | 0 | 0 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-08-11 | QTR1 | 20/21 | 513 | 141232
| 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 99.39% | 1 | 0 | 0 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9
| 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 96.7% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25
| 05 | E5Z91 | 43912215201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 115 | 121 | 120 | 99.13% | 1 | 1 | 0 | 0 | 6 | 0 | 1447000 | 50000 | 1397000 | 1447000 | 1407072 | 0 | 0 | 0 | 1407072 | 1407072 | 100.7% | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-05-19 | QTR4 | 19/20 | 509 | 1302060.71
| 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 98.89% | 1 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 105.3% | 1 | 0 | 0 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5
| 05 | E5Z98 | 43618725201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 90 | 124 | 125 | 101.1% | 1 | -1 | 1 | 0 | 34 | 0 | 675628 | 31129 | 644499 | 675628 | 649188 | 0 | 0 | 0 | 649188 | 649188 | 100.7% | 1 | 0 | 0 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2020-11-25 | QTR2 | 20/21 |  | 2020-08-13 | QTR1 | 20/21 | 514 | 631570
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 13 | 18 | 18 | 2894 | 3848 | 4482 | 69.23% | 9 | -634 | 648 | 0 | 714 | 240 | 35679288 | 504255 | 35175033 | 36072586 | 35866013 | -59768 | 0 | -59768 | 35806245 | 35727364 | 100% | 13 | -50128 | 393298 | 337 | 355 | 4 | 20 | 189168 | 0 | 18 | 115 | 192509 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 58872 | 3472 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 240 | 457110 | 14901
| District 05 Totals |  |  |  |  | 25 | 45 | 68 | 7144 | 9769 | 10411 | 76% | 19 | -642 | 875 | 0 | 1844 | 781 | 164785563 | 1538256 | 163247306 | 169543174 | 172140378 | -199858 | 586693 | 386835 | 172527212 | 170809330 | 96% | 24 | -1086303 | 4757612 | 1001 | 779 | 46 | 27 | 1177258 | 0 | 18 | 414 | 3534225 | 179642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 101951 | 7082 | 0 | 4 | 81189 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 176 | 31000 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 64 | 760 | 4752631 | 246015
| 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 84.25% | 1 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | 90.62% | 1 | -289635 | -403730 | 22 | 17 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 |  | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 86% | 1 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | 102.7% | 1 | -2140213 | 1115676 | 16 | 11 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 |  | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 109.4% | 1 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 96.45% | 1 | 578 | 96399 | 60 | 44 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 78.21% | 1 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | 100.8% | 1 | -201766 | 12198 | 24 | 25 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6442 | 43063735201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 419 | 517 | 474 | 99.28% | 1 | 43 | 0 | 0 | 58 | 40 | 12892744 | 274969 | 12617775 | 13383683 | 13072251 | 0 | 790000 | 790000 | 13862251 | 12904020 | 102.3% | 1 | -845455 | 490939 | 35 | 23 | 0 | 40 | 504378 | 375054 | 0 | 0 | 22795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 550031 | 375054 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 606 | 14924931.96 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 117.9% | 1 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 97.66% | 1 | 81 | 0 | 77 | 34 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 |  | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5
| 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 112.1% | 1 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | 96.93% | 1 | -1589 | 27177 | 90 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35
| 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | 103.6% | 1 | -846 | 30818 | 24 | 22 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8
| 06 | T6477 | 44281315201 | 2019-03-27 | QTR3 | 18/19 | 9 | 4 | 360 | 432 | 432 | 105% | 1 | 0 | 0 | 0 | 54 | 18 | 2060596 | 50000 | 2010596 | 2075271 | 2107347 | 0 | 0 | 0 | 2107347 | 2106923 | 104.8% | 1 | -424 | 14675 | 29 | 25 | 0 | 18 | 4869 | 0 | 0 | 0 | 15072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27688 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2020-12-14 | QTR2 | 20/21 |  | 2020-10-09 | QTR2 | 20/21 | 606 | 2038302.5
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 9 | 40 | 26 | 2849 | 3624 | 3391 | 100% | 9 | 233 | 0 | 0 | 717 | 58 | 68245152 | 757944 | 67487208 | 69629304 | 68428636 | 0 | 3410000 | 3410000 | 71838636 | 68164651 | 100% | 9 | -3479269 | 1384152 | 377 | 235 | 75 | 58 | 883144 | 381983 | 0 | 0 | 286651 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 804850 | 0 | 0 | 0 | 15855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 75 | 58 | 1546885 | 402674
| 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 47.33% | 1 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 94.14% | 1 | 0 | 0 | 30 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95
| 06 | E6K57 | 43854015201 | 2017-05-15 | QTR4 | 16/17 | 1 | 0 | 750 | 1065 | 881 | 84.13% | 1 | 184 | 0 | 0 | 315 | 0 | 3582848 | 50000 | 3532848 | 3582848 | 3528511 | 0 | 0 | 0 | 3528511 | 3528511 | 99.88% | 1 | 0 | 0 | 168 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-10-23 | QTR2 | 20/21 |  | 2020-09-09 | QTR1 | 20/21 | 606 | 3999000 | LBDB | LOW BID DESIGN BUILD
| 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 111.7% | 0 | 0 | 139878 | 27 | 23 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132
| 06 | E6L73 | 44183715201 | 2019-03-28 | QTR3 | 18/19 | 3 | 0 | 180 | 256 | 253 | 98.33% | 1 | 3 | 0 | 0 | 76 | 0 | 1046629 | 50000 | 996629 | 1046629 | 1032137 | 0 | 0 | 0 | 1032137 | 1030814 | 103.4% | 1 | -1322 | 0 | 49 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 613 | 1027325.45
| 06 | E6L77 | 44059015201 | 2019-02-28 | QTR3 | 18/19 | 1 | 0 | 150 | 227 | 212 | 90% | 1 | 15 | 0 | 0 | 77 | 0 | 569569 | 25452 | 544117 | 569569 | 532425 | 0 | 0 | 0 | 532425 | 532327 | 97.83% | 1 | -98 | 0 | 65 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 |  | 2020-08-04 | QTR1 | 20/21 | 613 | 521617.9
| 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 61.43% | 1 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | 95.7% | 1 | -189 | -1000 | 35 | 1 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15
| 06 | E6M59 | 43634425201 | 2020-02-27 | QTR3 | 19/20 | 1 | 0 | 100 | 124 | 124 | 109% | 1 | 0 | 0 | 0 | 24 | 0 | 548409 | 24409 | 524000 | 548409 | 466503 | 0 | 0 | 0 | 466503 | 466503 | 89.03% | 1 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 |  | 2020-10-10 | QTR2 | 20/21 | 636 | 490515.2
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 7 | 11 | 5 | 1895 | 2530 | 2116 | 100% | 7 | 414 | 0 | 0 | 635 | 0 | 8923337 | 271421 | 8651916 | 9062215 | 8708947 | 0 | 0 | 0 | 8708947 | 8699149 | 85.71% | 6 | -1609 | 138878 | 383 | 178 | 0 | 0 | 20689 | 0 | 0 | 0 | 145583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 224876 | 0
| District 06 Totals |  |  |  |  | 16 | 51 | 31 | 4744 | 6154 | 5507 | 100% | 16 | 647 | 0 | 0 | 1352 | 58 | 77168489 | 1029365 | 76139124 | 78691519 | 77137583 | 0 | 3410000 | 3410000 | 80547583 | 76863800 | 93.75% | 15 | -3480878 | 1523030 | 760 | 413 | 75 | 58 | 903833 | 381983 | 0 | 0 | 432234 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863454 | 0 | 0 | 0 | 15855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 84 | 58 | 1771761 | 402674
| 07 | T7403 | 43484815201 | 2018-05-23 | QTR4 | 17/18 | 4 | 11 | 365 | 520 | 520 | 113.4% | 1 | 0 | 0 | 0 | 106 | 49 | 15246325 | 150000 | 15096325 | 16369545 | 16674514 | 0 | 0 | 0 | 16674514 | 16720307 | 110.8% | 0 | 65791 | 1123220 | 63 | 43 | 0 | 14 | 656978 | 126004 | 0 | 35 | 570684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28923 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1198739 | 126713 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 |  | 2020-03-24 | QTR3 | 19/20 | 796 | 16929302.14
| 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 84% | 1 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | 107.8% | 1 | -14840 | 688152 | 70 | 32 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 |  | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63
| 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 119.6% | 1 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | 99.14% | 1 | -20 | 0 | 91 | 73 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8
| 07 | T7413 | 43658815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 480 | 699 | 697 | 103.5% | 1 | 2 | 0 | 0 | 200 | 19 | 26892177 | 150000 | 26742177 | 27245569 | 27594120 | -41000 | 0 | -41000 | 27553120 | 27404700 | 102.5% | 1 | -148420 | 353392 | 151 | 49 | 0 | 0 | 138794 | 0 | 0 | 19 | 407728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 0 | 19 | 422365 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-12-30 | QTR2 | 20/21 |  | 2020-08-27 | QTR1 | 20/21 | 714 | 31660666.96
| 07 | T7419 | 43050225201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 272 | 272 | 183.3% | 0 | 0 | 0 | 0 | 52 | 100 | 987665 | 50000 | 937665 | 987665 | 987634 | 0 | 0 | 0 | 987634 | 987634 | 105.3% | 1 | 0 | 0 | 27 | 25 | 0 | 100 | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 31825 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-03-14 | QTR3 | 19/20 | 796 | 1403000
| 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 98.33% | 1 | 4907 | 45939 | 13 | 11 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185
| 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | 92.73% | 1 | -16 | 0 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 799 | 490000
| 07 | T7440 | 44286215201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 116 | 167 | 163 | 96.55% | 1 | 4 | 0 | 0 | 30 | 21 | 2725693 | 50000 | 2675693 | 2725693 | 2560514 | 0 | 0 | 0 | 2560514 | 2560514 | 95.7% | 1 | 0 | 0 | 42 | 9 | 0 | 0 | 20000 | 0 | 0 | 0 | 3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23652 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 |  | 2020-10-06 | QTR2 | 20/21 | 798 | 2929941.26
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 8 | 14 | 28 | 2151 | 3080 | 2994 | 87.5% | 7 | 86 | 0 | 0 | 695 | 234 | 66153936 | 670000 | 65483936 | 68364639 | 68970995 | -41000 | 0 | -41000 | 68929995 | 68817401 | 87.5% | 7 | -92598 | 2210703 | 458 | 258 | 0 | 159 | 1538050 | 147004 | 0 | 54 | 1099863 | 5053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28923 | 709 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 0 | 213 | 2488056 | 152766
| 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 108.6% | 1 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 108.9% | 1 | 302 | 625193 | 45 | 66 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 66.67% | 1 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 99.99% | 1 | 0 | 0 | 95 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000
| 07 | E7M31 | 43751715201 | 2019-03-13 | QTR3 | 18/19 | 1 | 2 | 360 | 436 | 435 | 108.9% | 1 | 1 | 0 | 0 | 43 | 33 | 2064981 | 50000 | 2014981 | 1997687 | 1923224 | 0 | 0 | 0 | 1923224 | 1923189 | 95.44% | 1 | -35 | -67294 | 14 | 29 | 0 | 33 | -66214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | -26781 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-08-21 | QTR1 | 20/21 | 799 | 2265000
| 07 | E7M50 | 42905925201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 80 | 125 | 114 | 86.25% | 1 | 11 | 0 | 0 | 45 | 0 | 257038 | 11000 | 246038 | 257038 | 238009 | 0 | 0 | 0 | 238009 | 238009 | 96.74% | 1 | 0 | 0 | 34 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2019-12-20 | QTR2 | 19/20 | 796 | 255036.03
| 07 | E7M74 | 43955115201 | 2019-09-11 | QTR1 | 19/20 | 1 | 0 | 260 | 282 | 171 | 57.31% | 1 | 111 | 0 | 0 | 22 | 0 | 555000 | 48000 | 507000 | 555000 | 507000 | 0 | 0 | 0 | 507000 | 507000 | 100% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2020-07-31 | QTR1 | 20/21 | 796 | 1075906 | B0 | ACC - LUMP SUM
| 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 92.5% | 1 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 799 | 280000
| 07 | E7M90 | 43983015201 | 2020-02-12 | QTR3 | 19/20 | 1 | 0 | 100 | 126 | 126 | 104% | 1 | 0 | 0 | 0 | 22 | 4 | 682863 | 38200 | 644663 | 682863 | 661465 | 0 | 0 | 0 | 661465 | 661465 | 102.6% | 1 | 0 | 0 | 16 | 6 | 0 | 4 | 22230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22230 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-24 | QTR2 | 20/21 |  | 2020-10-16 | QTR2 | 20/21 | 796 | 786200
| 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 72.06% | 1 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 93.26% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89
| 07 | E7N04 | 44580315201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 50 | 61 | 61 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 342938 | 15400 | 327538 | 342938 | 334918 | 0 | 0 | 0 | 334918 | 334918 | 102.3% | 1 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-16 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 796 | 323540.7
| 07 | E7R14 | 43402715201 | 2019-01-22 | QTR3 | 18/19 | 1 | 1 | 485 | 580 | 577 | 108.7% | 1 | 3 | 0 | 0 | 50 | 45 | 3891051 | 50000 | 3841051 | 3854521 | 3786721 | 0 | 0 | 0 | 3786721 | 3786721 | 98.59% | 1 | 0 | -36530 | 18 | 32 | 0 | 0 | -197831 | 0 | 0 | 0 | 11095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36530 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 |  |  | QTR2 | 00/01 | 796 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 10 | 11 | 11 | 2653 | 3240 | 2972 | 100% | 10 | 268 | 0 | 0 | 432 | 155 | 20976509 | 333600 | 20642909 | 21497878 | 21232284 | 0 | 0 | 0 | 21232284 | 21232551 | 100% | 10 | 267 | 521369 | 248 | 184 | 0 | 37 | -71746 | 0 | 0 | 37 | 525251 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 649069 | 21130
| District 07 Totals |  |  |  |  | 18 | 25 | 39 | 4804 | 6320 | 5966 | 94.44% | 17 | 354 | 0 | 0 | 1127 | 389 | 87130445 | 1003600 | 86126845 | 89862517 | 90203279 | -41000 | 0 | -41000 | 90162279 | 90049952 | 94.44% | 17 | -92331 | 2732072 | 706 | 442 | 0 | 196 | 1466304 | 147004 | 0 | 91 | 1625114 | 26183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166641 | 709 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 0 | 323 | 3137125 | 173896
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 180.6% | 0 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | 105.2% | 1 | -2369264 | 11648418 | 291 | 106 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1439 | 117.5% | 1 | 14 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 109.1% | 1 | 991193 | 5429118 | 149 | 127 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 |  | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 119.5% | 1 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | 106.1% | 1 | -551574 | 4550344 | 122 | 82 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12
| 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | 119.6% | 1 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 106.6% | 1 | 496445 | 1556062 | 183 | 99 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 0
| 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 113.2% | 1 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 106.9% | 1 | 1490912 | 597011 | 172 | 84 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09
| 08 | E8Q94 | 43947815201 | 2018-03-27 | QTR3 | 17/18 | 4 | 6 | 525 | 723 | 723 | 101.3% | 1 | 0 | 0 | 0 | 198 | 0 | 18860577 | 150000 | 18710577 | 18748056 | 18778411 | -36500 | 0 | -36500 | 18741911 | 19317651 | 103.2% | 1 | 583633 | -112521 | 130 | 61 | 0 | 0 | -519709 | 0 | 0 | 0 | 381340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 106099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -32270 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2020-06-30 | QTR4 | 19/20 | 854 | 29028001.13
| 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 106.8% | 1 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | 97.91% | 1 | -7 | 70000 | 23 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49
| 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 102% | 1 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | 119.1% | 0 | -3862 | 142527 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 |  | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97
| 08 | E8R76 | 43945715201 | 2019-03-12 | QTR3 | 18/19 | 1 | 6 | 415 | 477 | 405 | 82.65% | 1 | 72 | 0 | 0 | 62 | 0 | 12161596 | 125391 | 12036204 | 11888308 | 12421672 | 0 | 0 | 0 | 12421672 | 12302929 | 102.2% | 1 | -84308 | -273288 | 21 | 41 | 0 | 0 | -340280 | 0 | 0 | 0 | 51302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287059 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 |  | 2020-06-30 | QTR4 | 19/20 | 854 | 12670789.67
| 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 106% | 1 | 0 | 94072 | 5 | 28 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98
| 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 37.17% | 1 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 90.79% | 1 | 0 | -576 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64
| 08 | E8S47 | 44400315201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 65 | 75 | 64 | 83.08% | 1 | 11 | 0 | 0 | 10 | 0 | 254205 | 21677 | 232529 | 254205 | 227921 | 0 | 0 | 0 | 227921 | 227921 | 98.02% | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 |  | 2020-11-08 | QTR2 | 20/21 | 854 | 465727.12
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 12 | 28 | 113 | 6350 | 9684 | 9393 | 0% | 11 | 291 | 42 | 0 | 2242 | 1092 | 404922718 | 1247068 | 403675650 | 428623884 | 429265863 | -411724 | 0 | -411724 | 428854139 | 428092461 | 91.67% | 11 | 553168 | 23701167 | 1125 | 683 | 0 | 748 | 12565308 | 1567394 | 0 | 24 | 1406300 | 61112 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 434 | 296 | 6492479 | 402197 | 0 | 16 | 762160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83068 | 0 | 0 | 0 | 395000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 434 | 1084 | 22599086 | 2050305
| District 08 Totals |  |  |  |  | 12 | 28 | 113 | 6350 | 9684 | 9393 | 91.67% | 11 | 291 | 42 | 0 | 2242 | 1092 | 404922718 | 1247068 | 403675650 | 428623884 | 429265863 | -411724 | 0 | -411724 | 428854139 | 428092461 | 91.67% | 11 | 553168 | 23701167 | 1125 | 683 | 0 | 748 | 12565308 | 1567394 | 0 | 24 | 1406300 | 61112 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 434 | 296 | 6492479 | 402197 | 0 | 16 | 762160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83068 | 0 | 0 | 0 | 395000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 434 | 1084 | 22599086 | 2050305
| Statewide Central Let Contracts SubTotal |  |  |  |  | 73 | 150 | 197 | 19284 | 26193 | 25565 | 90.41% | 66 | 628 | 283 | 0 | 5709 | 1200 | 465944788 | 4486643 | 461458147 | 477303475 | 475834772 | -284614 | 3996693 | 3712079 | 479546850 | 475813544 | 97.26% | 71 | -2568469 | 11358685 | 3398 | 1919 | 183 | 402 | 5592718 | 594609 | 101 | 468 | 6204864 | 333759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 4000 | 0 | 86 | 16 | 948182 | 4319 | 12 | 17 | 297121 | 91514 | 0 | 0 | 0 | 0 | 0 | 0 | 57099 | 0 | 0 | 176 | 31000 | 0 | 30 | 53 | 28706 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -1224372 | 0 | 426 | 1132 | 11939313 | 1049965
| Statewide District Let Contracts SubTotal |  |  |  |  | 80 | 124 | 214 | 21922 | 31694 | 31155 | 80% | 64 | 539 | 975 | 0 | 7152 | 2620 | 599277836 | 4410132 | 594867705 | 627611484 | 626051446 | -1684021 | 0 | -1684021 | 624367424 | 623398658 | 95% | 76 | 506051 | 28333648 | 3806 | 2350 | 86 | 1284 | 14568928 | 1749681 | 136 | 279 | 3120245 | 115332 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 | 0 | 434 | 704 | 7974823 | 496287 | 27 | 262 | 908802 | 111779 | 0 | 0 | 0 | 0 | 0 | 0 | 88765 | 0 | 0 | 0 | 395000 | 19602 | 239 | 36 | 12921 | 12921 | 9 | 0 | 0 | 0 | 0 | 0 | -163914 | 0 | 931 | 2565 | 27895195 | 2505603
| Statewide Totals |  |  |  |  | 153 | 274 | 411 | 41206 | 57887 | 56720 | 84.97% | 130 | 1167 | 1258 | 0 | 12861 | 3820 | 1065222624 | 8896775 | 1056325852 | 1104914959 | 1101886218 | -1968635 | 3996693 | 2028058 | 1103914274 | 1099212202 | 96.08% | 147 | -2062418 | 39692333 | 7204 | 4269 | 269 | 1686 | 20161646 | 2344290 | 237 | 747 | 9325109 | 449091 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 46750 | 0 | 520 | 720 | 8923005 | 500606 | 39 | 279 | 1205923 | 203293 | 0 | 0 | 0 | 0 | 0 | 0 | 145864 | 0 | 0 | 176 | 426000 | 19602 | 269 | 89 | 41627 | 38686 | 9 | 0 | 0 | 0 | 0 | 0 | -1388286 | 0 | 1357 | 3697 | 39834508 | 3555568

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P44 | 43797315201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-01-27 | 18051494 | 18407137 | 18281638 | 355642.62 | 0 | 18301633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
1 | E1P46 | 43580715201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 869954 | 869954 | 834474 | 0 | 0 | 836068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834474 | 836068 | 1595 | 794914
1 | E1R05 | 43629915201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-03-01 | 7996438 | 8606992 | 8773391 | 610554.93 | 0 | 8772475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8773391 | 8772475 | -916 | 8160370 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R06 | 43658015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-14 | 2206728 | 2236442 | 2181738 | 29714.23 | 0 | 2202526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181738 | 2202526 | 20788 | 2403604
1 | E1R78 | 43502915201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-03-21 | 982956 | 982956 | 953745 | 0 | -3330 | 950415 | -3330 | 0 | 0 | 0 | 0 | 0 | -3330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3330 | 950415 | 950415 | 0 | 837254 | B0 | ACC - LUMP SUM
1 | E1R81 | 43528615201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-05-23 | 682196 | 682196 | 657412 | 0 | 0 | 657412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657412 | 657412 | 0 | 659798 | B0 | ACC - LUMP SUM
1 | E1R86 | 44108815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-11-09 | 2469000 | 2469000 | 2431659 | 0 | 0 | 2431659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431659 | 2431659 | 0 | 3306922 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1R99 | 43942615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-10-17 | 2118027 | 2118027 | 2076020 | 0 | 0 | 2071117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 2188397 | B0 | ACC - LUMP SUM
1 | E1S01 | 43796215201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-18 | 1319384 | 1319384 | 1246251 | 0 | 0 | 1246243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 1628857
1 | E1S13 | 44462715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-16 | 993513 | 994797 | 930694 | 1284.91 | 0 | 928776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930694 | 928776 | -1919 | 1140044
1 | E1S47 | 43997015201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 450312 | 450312 | 440733 | 0 | 0 | 440733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440733 | 440733 | 0 | 480716
1 | E1S50 | 44525715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-03-19 | 279624 | 279624 | 287046 | 0 | 0 | 287046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287046 | 287046 | 0 | 268843
1 | T1670 | 43512015201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-03-29 | 774103 | 789611 | 780581 | 15508.02 | -74448 | 707486 | -74448 | 0 | 0 | 0 | 0 | 0 | -74448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74448 | 706133 | 707486 | 1353 | 746976
1 | T1675 | 43088715201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-30 | 815194 | 856566 | 821472 | 41371.58 | 0 | 822481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821472 | 822481 | 1009 | 783433 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1702 | 43509015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2098354 | 2203054 | 2035840 | 104699.5 | 0 | 2034275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035840 | 2034275 | -1565 | 2050386 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1742 | 43539015201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 3732644 | 3755256 | 3738358 | 22611.39 | 0 | 3735826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3738358 | 3735826 | -2532 | 3397782
1 | T1744 | 43806115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 2622633 | 2624733 | 2699418 | 2100 | 0 | 2679820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2884387
1 | T1748 | 43510815201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1145000 | 1148200 | 1114849 | 3200.4 | 0 | 1114533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 980185
1 | T1758 | 43943715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-31 | 7004551 | 7119832 | 7259276 | 115281.22 | 0 | 7106733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7259276 | 7106733 | -152543 | 9375095
1 | T1773 | 44067215201 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 214731 | 214731 | 194639 | 0 | 0 | 194639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194639 | 194639 | 0 | 215733
1 | T1997 | 40828665201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-01-25 | 58011809 | 58671616 | 58073269 | 659806.55 | 0 | 59331197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58073269 | 59331197 | 1257928 | 69879385
2 | E2W31 | 43373015201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-03-15 | 17417591 | 17434064 | 17148118 | 16473.12 | -1033560 | 17381502 | -1033560 | 0 | 0 | 0 | 0 | 0 | -1033560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1033560 | 16114558 | 17381502 | 1266944 | 16736577
2 | E2X06 | 43076015201 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2018-04-18 | 2957443 | 3057443 | 3046193 | 100000 | -151872 | 2894277 | -151872 | 0 | 0 | 0 | 0 | 0 | -151872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -151872 | 2894321 | 2894277 | -43 | 2882465
2 | E2Y25 | 43761715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 5599368 | 5599368 | 5849866 | 0 | 0 | 5819954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849866 | 5819954 | -29911 | 6362327
2 | E2Z22 | 44199725215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2019-10-16 | 486100 | 486100 | 457926 | 0 | 0 | 457926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457926 | 457926 | 0 | 464975
2 | T2675 | 43611415201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 8842976 | 8855815 | 8862510 | 12839.16 | 0 | 8968366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8862510 | 8968366 | 105856 | 9571732
2 | T2702 | 43616515201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-05-23 | 4160007 | 4260007 | 4244965 | 100000 | 0 | 4312480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 3742257
2 | T2709 | 21284435201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 3462428 | 3505177 | 3504649 | 42749.1 | 0 | 3506156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 3179149
2 | T2719 | 44089815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 1184584 | 1184584 | 887887 | 0 | 0 | 887887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887887 | 887887 | 0 | 1509948
2 | T2721 | 43761915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 8899704 | 8899704 | 8066755 | 0 | 0 | 7968066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 9019727
2 | T2722 | 43761515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 3029745 | 3129745 | 3172572 | 100000 | 0 | 3184741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3172572 | 3184741 | 12169 | 3135452
2 | T2726 | 43583715201 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2018-09-26 | 2039829 | 2119904 | 2083011 | 80074.99 | -14985 | 2064225 | -14985 | 0 | 0 | 0 | 0 | 0 | -14985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14985 | 2068026 | 2064225 | -3801 | 2155262
2 | T2728 | 43732115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-30 | 5318835 | 5318835 | 5249772 | 0 | 0 | 5213329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 5787088
2 | T2735 | 44119515201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 421053 | 421053 | 394439 | 0 | 0 | 394439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394439 | 394439 | 0 | 428178
2 | T2738 | 43934615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | 3397538 | 3397538 | 3460508 | 0 | 0 | 3441905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 3973731
2 | T2742 | 44272415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 99208 | 99208 | 93539 | 0 | 0 | 93539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93539 | 93539 | 0 | 84352
2 | T2745 | 43398815201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2019-08-28 | 149961 | 149961 | 151154 | 0 | 0 | 151154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151154 | 151154 | 0 | 204916
2 | T2761 | 43934515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 4189603 | 4189603 | 4189658 | 0 | 0 | 4163139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4189658 | 4163139 | -26519 | 5262361
2 | T2766 | 44348915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1081333 | 1081333 | 1019859 | 0 | 0 | 1018371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1019859 | 1018371 | -1488 | 1202483
3 | E3O87 | 42820825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-12 | 2143658 | 2394721 | 2274840 | 251062.72 | 0 | 2271803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 1738000
3 | E3P37 | 22280225201 | F811252530 | OMEGA COATINGS & CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-04-11 | 398582 | 398582 | 363870 | 0 | 0 | 363870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363870 | 363870 | 0 | 733124
3 | E3Q54 | 22253925201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-05-09 | 922444 | 846935 | 658266 | -75509.51 | 0 | 658266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658266 | 658266 | 0 | 919379
3 | E3R03 | 41343525201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-10 | 1381327 | 1468091 | 1381221 | 86763.05 | -4783 | 1374521 | 0 | 0 | 0 | 0 | 0 | -4783 | -4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4783 | 1376437 | 1374521 | -1916 | 1155000
3 | E3R51 | 22023625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4578865 | 4737767 | 4690378 | 158901.87 | 0 | 4638261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 4615476
3 | E3R70 | 43814115201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 628778 | 721767 | 721738 | 92989.29 | 0 | 721738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721738 | 721738 | 0 | 499880
3 | E3R72 | 43255415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-11 | 4336259 | 4459598 | 4457789 | 123338.96 | -18984 | 4364461 | -18984 | 0 | 0 | 0 | 0 | 0 | -18984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18984 | 4438805 | 4364461 | -74345 | 5281573
3 | E3R75 | 40731075201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-06-13 | 1896816 | 2013742 | 1899113 | 116926.29 | 0 | 1899113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899113 | 1899113 | 0 | 1645053
3 | E3R78 | 43813815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-14 | 467023 | 467023 | 452193 | 0 | 0 | 452193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452193 | 452193 | 0 | 567889
3 | E3R84 | 43736715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-05-09 | 1890085 | 1993510 | 1844667 | 103424.95 | 0 | 1822661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844667 | 1822661 | -22007 | 1951316
3 | E3S03 | 43775215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-16 | 4297338 | 4339701 | 4428331 | 42363.01 | 0 | 4345545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 4833697
3 | E3S48 | 43973015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-14 | 2362840 | 2362840 | 2375062 | 0 | 0 | 2367596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375062 | 2367596 | -7466 | 2687907
3 | E3S49 | 44350315201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-11-14 | 1254000 | 1254000 | 1218580 | 0 | 0 | 1218580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 1226090
3 | E3S50 | 22253625201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-11-14 | 688910 | 688910 | 677594 | 0 | 0 | 677594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677594 | 677594 | 0 | 1158620
3 | T3585 | 43228515201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 1883515 | 1882120 | 2065179 | -1394.8 | 0 | 2067671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | 1839571
3 | T3619 | 43390215201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2018-11-14 | 1114410 | 1163460 | 1226323 | 49049.79 | 0 | 1224530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226323 | 1224530 | -1793 | 1475965
3 | T3642 | 43274025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 8739221 | 8879082 | 9063602 | 139861.6 | -14091 | 9591255 | 0 | 0 | 0 | 0 | 0 | -14091 | -14091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14091 | 9049511 | 9591255 | 541744 | 8488155
3 | T3648 | 43580215201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-08-28 | 1301561 | 1304861 | 1221532 | 3300 | 0 | 1218439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 1531944
3 | T3663 | 43188345201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-08-28 | 656987 | 668791 | 649887 | 11804.09 | 0 | 649887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649887 | 649887 | 0 | 691494
3 | T3668 | 43580015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | 1427167 | 1429917 | 1395761 | 2750 | 0 | 1394795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395761 | 1394795 | -966 | 1392504
3 | T3695 | 43775415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 9989122 | 9989122 | 9612555 | 0 | 0 | 9581632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 10772800
3 | T3708 | 43662015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-05-31 | 2063749 | 2063749 | 2000237 | 0 | 0 | 2000237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 1864559
3 | T3739 | 44173715201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-03-25 | 229048 | 236141 | 232144 | 7093.4 | 0 | 232144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232144 | 232144 | 0 | 145096
4 | E4N82 | 22777515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-05-20 | 29568100 | 31002780 | 30989356 | 1434680.24 | 0 | 29990698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30989356 | 29990698 | -998657 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4T46 | 43388815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-01-04 | 1592830 | 1700395 | 1656013 | 107565.12 | 0 | 1656013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656013 | 1656013 | 0 | 1969428
4 | E4T54 | 42957525201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2019-02-01 | 1034836 | 1034836 | 958378 | 0 | 0 | 958293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958378 | 958293 | -85 | 1135394
4 | E4T56 | 43578125201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-08 | 1488175 | 1499756 | 1508806 | 11580.46 | 0 | 1504997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508806 | 1504997 | -3808 | 1272541
4 | E4T78 | 43996015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-12-06 | 886114 | 886114 | 834084 | 0 | 0 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834084 | 834084 | 0 | 1407859
4 | E4T84 | 43389615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-12-06 | 802818 | 802818 | 776329 | 0 | 0 | 776329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776329 | 776329 | 0 | 659386 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4T90 | 43995815201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 387073 | 387073 | 364661 | 0 | 0 | 364661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364661 | 364661 | 0 | 430109
4 | E4T92 | 44140915201 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-17 | 888985 | 900166 | 850166 | 11180.7 | 0 | 850166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850166 | 850166 | 0 | 1308480
4 | T4461 | 42793715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-24 | 13403577 | 14388653 | 13899377 | 985075.39 | 0 | 14133238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13899377 | 14133238 | 233861 | 14532810
4 | T4473 | 42751615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-03-28 | 14954960 | 14788864 | 14238463 | -166096.87 | 0 | 14563199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14238463 | 14563199 | 324737 | 12073780 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4479 | 43059025201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-26 | 815678 | 823050 | 757384 | 7371.16 | 0 | 756711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757384 | 756711 | -673 | 726060
4 | T4483 | 44008115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 977778 | 1000403 | 798387 | 22625.47 | 0 | 798134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798387 | 798134 | -253 | 1192931
4 | T4489 | 43770115201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 5985000 | 6208144 | 6389050 | 223143.55 | 0 | 6349948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6389050 | 6349948 | -39102 | 6481016
4 | T4491 | 43234815201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 5272134 | 5501959 | 5429646 | 229824.88 | 0 | 5415536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5429646 | 5415536 | -14110 | 4730109
4 | T4496 | 43288335201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 3387195 | 3736919 | 3518847 | 349724.02 | 0 | 3516238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518847 | 3516238 | -2608 | 2883072
4 | T4498 | 43689315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 3421871 | 3525755 | 3579940 | 103883.53 | 0 | 3579922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 2478815
4 | T4503 | 43611115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 2257891 | 2372485 | 2277661 | 114594.11 | 0 | 2279759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2277661 | 2279759 | 2097 | 2312700
4 | T4507 | 43771815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 345927 | 345927 | 329094 | 0 | 0 | 329032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329094 | 329032 | -62 | 362984
4 | T4520 | 43770215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 511111 | 511111 | 500925 | 0 | 0 | 500762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500925 | 500762 | -163 | 517002
4 | T4540 | 43834515201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-01-29 | 1005700 | 1022365 | 875802 | 16665 | 0 | 875802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875802 | 875802 | 0 | 1115608
5 | E5Y62 | 23831925201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-03-21 | 22219000 | 22351916 | 22222555 | 132915.67 | 0 | 22276693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22222555 | 22276693 | 54139 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Z19 | 43927315201 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2018-04-03 | 149935 | 149935 | 128601 | 0 | -51092 | 77509 | -51092 | 0 | 0 | 0 | 0 | 0 | -51092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51092 | 77509 | 77509 | 0 | 204099
5 | E5Z20 | 43632415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-05 | 1052310 | 1052310 | 1030338 | 0 | 0 | 1030338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 1235089
5 | E5Z30 | 43952115201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2018-06-05 | 257400 | 257400 | 193136 | 0 | 0 | 193136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193136 | 193136 | 0 | 307382
5 | E5Z64 | 44121015201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-07 | 4022402 | 4286073 | 4275710 | 263671.46 | 0 | 4237738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4275710 | 4237738 | -37972 | 4100418
5 | E5Z68 | 44096915201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-05 | 1563424 | 1567539 | 1517384 | 4114.91 | 0 | 1517184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517384 | 1517184 | -199 | 2235952
5 | E5Z77 | 43912115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | 3278490 | 3271086 | 3476815 | -7404 | 0 | 3410719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3476815 | 3410719 | -66096 | 3806384
5 | E5Z83 | 44326615201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-06-04 | 176487 | 176487 | 170000 | 0 | -8676 | 161324 | -8676 | 0 | 0 | 0 | 0 | 0 | -8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8676 | 161324 | 161324 | 0 | 141232
5 | E5Z84 | 43643425201 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 296220 | 296220 | 278504 | 0 | 0 | 278504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278504 | 278504 | 0 | 340891
5 | E5Z89 | 44326815201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2019-10-01 | 301514 | 301514 | 272690 | 0 | 0 | 272690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272690 | 272690 | 0 | 414691
5 | E5Z91 | 43912215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-01 | 1447000 | 1447000 | 1407072 | 0 | 0 | 1407072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407072 | 1407072 | 0 | 1302061
5 | E5Z97 | 44330815201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 239478 | 239478 | 244020 | 0 | 0 | 244020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244020 | 244020 | 0 | 158006
5 | E5Z98 | 43618725201 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2020-01-07 | 675628 | 675628 | 649188 | 0 | 0 | 649188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649188 | 649188 | 0 | 631570
5 | T5530 | 23968215201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 37673821 | 40588843 | 42253807 | 2915022.11 | 586693 | 42067685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586693 | 0 | 0 | 0 | 0 | 0 | 586693 | 586693 | 42840500 | 42067685 | -772815 | 38523048
5 | T5590 | 42690535201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 38848299 | 39691396 | 40371218 | 843097.53 | 0 | 40086419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40371218 | 40086419 | -284799 | 42395483
5 | T5592 | 43440715201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2017-08-30 | 6864444 | 6916430 | 6987391 | 51985.55 | 0 | 7341346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 9424561
5 | T5604 | 43734515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 6332535 | 6387426 | 6284035 | 54891.24 | 0 | 6274517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6284035 | 6274517 | -9518 | 7459742
5 | T5615 | 43793115201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-03-28 | 1435273 | 1466273 | 1433905 | 31000 | -119880 | 1313837 | -119880 | 0 | 0 | 0 | 0 | 0 | -119880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119880 | 1314025 | 1313837 | -188 | 1578333
5 | T5618 | 43643515201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-01-29 | 249700 | 249700 | 238354 | 0 | 0 | 238354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238354 | 238354 | 0 | 259439
5 | T5624 | 43687915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 9260071 | 9353754 | 9333412 | 93683.37 | 0 | 9239091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9333412 | 9239091 | -94321 | 0
5 | T5629 | 43759215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-26 | 1369369 | 1373147 | 1429206 | 3778.24 | 0 | 1426624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429206 | 1426624 | -2583 | 1077107
5 | T5630 | 43732715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 7593730 | 7636258 | 7693686 | 42527.98 | 0 | 7601216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7693686 | 7601216 | -92470 | 10653193
5 | T5634 | 43734815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 7052425 | 7232569 | 7465970 | 180144.34 | 0 | 7455412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7465970 | 7455412 | -10558 | 10311528
5 | T5661 | 43968225201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5973653 | 5976861 | 5959722 | 3208.31 | -20210 | 5890124 | 0 | 0 | 0 | 0 | 0 | -20210 | -20210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20210 | 5939511 | 5890124 | -49387 | 5898605
5 | T5677 | 43923315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 6452955 | 6597931 | 6823659 | 144976.35 | 0 | 6790182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823659 | 6790182 | -33477 | 7161772 | B0 | ACC - LUMP SUM
6 | E6H56 | 42999615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | 1195598 | 1195598 | 1078448 | 0 | 0 | 1078448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 1501205
6 | E6K57 | 43854015201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-05-15 | 3582848 | 3582848 | 3528511 | 0 | 0 | 3528511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528511 | 3528511 | 0 | 3999000 | LBDB | LOW BID DESIGN BUILD
6 | E6K86 | 43653215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-27 | 1525830 | 1665708 | 1656441 | 139878.01 | 0 | 1656441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656441 | 1656441 | 0 | 1287132
6 | E6L73 | 44183715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | 1046629 | 1046629 | 1032137 | 0 | 0 | 1030814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032137 | 1030814 | -1322 | 1027325
6 | E6L77 | 44059015201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-28 | 569569 | 569569 | 532425 | 0 | 0 | 532327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532425 | 532327 | -98 | 521618
6 | E6L92 | 44203815201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-28 | 454454 | 453454 | 414482 | -1000 | 0 | 414293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414482 | 414293 | -189 | 422168
6 | E6M59 | 43634425201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-27 | 548409 | 548409 | 466503 | 0 | 0 | 466503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466503 | 466503 | 0 | 490515
6 | T6420 | 43345515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 5904592 | 5500862 | 5293728 | -403729.56 | 300000 | 5304093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 5593728 | 5304093 | -289635 | 5663802 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6422 | 42736925201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 37393744 | 38509420 | 38324783 | 1115676.08 | 2120000 | 38304570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 120000 | 0 | 2120000 | 2120000 | 40444783 | 38304570 | -2140213 | 43619309 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6425 | 42597925201 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2018-03-28 | 2976484 | 3072883 | 2821239 | 96399 | 0 | 2821817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 2758437 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6441 | 43117045201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 3159760 | 3171958 | 3147560 | 12198.41 | 200000 | 3145794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3347560 | 3145794 | -201766 | 3433250 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6442 | 43063735201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 12892744 | 13383683 | 13072251 | 490939.04 | 790000 | 13016796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750500 | 0 | 0 | 0 | 39500 | 0 | 790000 | 790000 | 13862251 | 13016796 | -845455 | 14924932 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6457 | 44018415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1600000 | 1600000 | 1513631 | 0 | 0 | 1513712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 1865185
6 | T6459 | 44018715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 1799799 | 1826976 | 1697745 | 27176.72 | 0 | 1696156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 1983631
6 | T6470 | 43991715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 457433 | 488251 | 450352 | 30818 | 0 | 449506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450352 | 449506 | -846 | 481418
6 | T6477 | 44281315201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-03-27 | 2060596 | 2075271 | 2107347 | 14675.27 | 0 | 2106923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107347 | 2106923 | -424 | 2038303
7 | E7K30 | 42450725201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 8315000 | 8940193 | 9001435 | 625193.38 | 0 | 9001737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
7 | E7M29 | 43954715201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-09 | 4417200 | 4417200 | 4366662 | 0 | 0 | 4366662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 5635000
7 | E7M31 | 43751715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-13 | 2064981 | 1997687 | 1923224 | -67293.76 | 0 | 1923189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923224 | 1923189 | -35 | 2265000
7 | E7M50 | 42905925201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-06-12 | 257038 | 257038 | 238009 | 0 | 0 | 238009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238009 | 238009 | 0 | 255036
7 | E7M74 | 43955115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-09-11 | 555000 | 555000 | 507000 | 0 | 0 | 507000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507000 | 507000 | 0 | 1075906 | B0 | ACC - LUMP SUM
7 | E7M89 | 43878615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-30 | 194157 | 194157 | 183157 | 0 | 0 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183157 | 183157 | 0 | 280000
7 | E7M90 | 43983015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-02-12 | 682863 | 682863 | 661465 | 0 | 0 | 661465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661465 | 661465 | 0 | 786200
7 | E7N03 | 43673425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 256281 | 256281 | 229693 | 0 | 0 | 229693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229693 | 229693 | 0 | 284492
7 | E7N04 | 44580315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-01-08 | 342938 | 342938 | 334918 | 0 | 0 | 334918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334918 | 334918 | 0 | 323541
7 | E7R14 | 43402715201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2019-01-22 | 3891051 | 3854521 | 3786721 | -36529.93 | 0 | 3786721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786721 | 3786721 | 0 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7403 | 43484815201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 15246325 | 16369545 | 16674514 | 1123220.1 | 0 | 16740305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16674514 | 16740305 | 65791 | 16929302
7 | T7406 | 42895715201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-05-23 | 15421093 | 16109245 | 16482253 | 688151.71 | 0 | 16467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 18474979
7 | T7411 | 43982925201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-04-25 | 2168162 | 2168162 | 2100062 | 0 | 0 | 2100043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 3284499
7 | T7413 | 43658815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 26892177 | 27245569 | 27594120 | 353391.83 | -41000 | 27404700 | 0 | 0 | 0 | 0 | 0 | -41000 | -41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41000 | 27553120 | 27404700 | -148420 | 31660667
7 | T7419 | 43050225201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 987665 | 987665 | 987634 | 0 | 0 | 987634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987634 | 987634 | 0 | 1403000
7 | T7426 | 43648715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 2303437 | 2349376 | 2210807 | 45938.74 | 0 | 2215714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 2215185
7 | T7432 | 43982955201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 409384 | 409384 | 361091 | 0 | 0 | 361076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361091 | 361076 | -16 | 490000
7 | T7440 | 44286215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2725693 | 2725693 | 2560514 | 0 | 0 | 2560514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560514 | 2560514 | 0 | 2929941
8 | E8M65 | 40609615201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2013-06-13 | 145330000 | 156978418 | 155492910 | 11648418.01 | 0 | 153123645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155492910 | 153123645 | -2369264 | 204625259 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
8 | E8N75 | 40611015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-03-08 | 68542000 | 73971118 | 73863918 | 5429118.38 | 0 | 74855111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73863918 | 74855111 | 991193 | 66110895 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8P02 | 40609055201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-16 | 92527388 | 97077732 | 98980425 | 4550343.91 | -16500 | 98412351 | 0 | 0 | 0 | 0 | 0 | -16500 | -16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16500 | 98963925 | 98412351 | -551574 | 105363394
8 | E8P82 | 43715615201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-06-14 | 31974887 | 33530949 | 33963963 | 1556062.19 | -335724 | 34124684 | -290724 | 0 | 0 | 0 | 0 | -45000 | -335724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -335724 | 33628239 | 34124684 | 496445 | 0
8 | E8Q53 | 43516915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-17 | 27945014 | 28542025 | 28268831 | 597010.58 | -3000 | 29756743 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 28265831 | 29756743 | 1490912 | 31134083
8 | E8Q94 | 43947815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-27 | 18860577 | 18748056 | 18778411 | -112521.32 | -36500 | 19325544 | 0 | 0 | 0 | 0 | 0 | -36500 | -36500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36500 | 18741911 | 19325544 | 583633 | 29028001
8 | E8R19 | 43560565201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-03-12 | 3952490 | 4022490 | 3821122 | 70000 | 0 | 3821116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 5097785
8 | E8R53 | 44130615201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2018-11-15 | 1048889 | 1191415 | 1210586 | 142526.5 | 0 | 1206725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210586 | 1206725 | -3862 | 1135062
8 | E8R76 | 43945715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-03-12 | 12161596 | 11888308 | 12421672 | -273288.03 | 0 | 12337364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12421672 | 12337364 | -84308 | 12670790
8 | E8R81 | 44132225201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-09-10 | 1331331 | 1425403 | 1378701 | 94071.53 | -20000 | 1358701 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 1358701 | 1358701 | 0 | 1246056
8 | E8R99 | 42897115201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2019-09-10 | 994341 | 993765 | 857403 | -576 | 0 | 857403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857403 | 857403 | 0 | 1572138
8 | E8S47 | 44400315201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-28 | 254205 | 254205 | 227921 | 0 | 0 | 227921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227921 | 227921 | 0 | 465727

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 |  | 17638.66 | 27615.75 | 12440.89 | 0 | 867.6 | -99989.98 | -41427.08 |  | 114838645 | 0.05024% | 57695.3
02 |  | 5087.77 |  | 683.4 |  | 30005.34 |  | 35776.51 |  | 72737306 | 0.007934% | 5771.17
03 |  | 26452.93 |  | 0 | 14133.44 | 100265.12 |  | 140851.49 |  | 54651705 | 0.07426% | 40586.37
04 |  | 117378.24 |  |  | 114261.47 | 408837.61 |  | 640477.32 |  | 88987753 | 0.2603% | 231639.71
05 |  | 176356.89 |  | 1322.3 | 40587.39 | 118359.34 | -199979.96 | 136645.96 |  | 164785563 | 0.1325% | 218266.58
06 |  | 20380.9 |  | 0 | 389363.02 | 82085.05 |  | 491828.97 |  | 77168489 | 0.531% | 409743.92
07 |  | 33498.06 | 40142.29 | 61468.2 | 147004 | 51822.83 |  | 333935.38 |  | 87130445 | 0.3238% | 282112.55
08 |  | 439083.75 |  |  | 0 | 1611221.16 |  | 2050304.91 |  | 404922718 | 0.1084% | 439083.75
Grand Total |  | 835877.2 | 67758.04 | 75914.79 | 705349.32 | 2403464.05 | -299969.94 | 3788393.46 |  | 1065222624 | 0.1582% | 1684899.35
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 |  | 1 | 72 | 1 | 3 | 398 | 0 | 475 |  | 77
02 |  | 6 |  | 10 |  | 152 |  | 168 |  | 16
03 |  | 5 |  | 13 | 12 | 385 |  | 415 |  | 30
04 |  | 5 |  |  | 66 | 369 |  | 440 |  | 71
05 |  | 124 |  | 0 | 80 | 577 | 0 | 781 |  | 204
06 |  | 0 |  | 0 | 40 | 18 |  | 58 |  | 40
07 |  | 125 | 0 | 56 | 36 | 172 |  | 389 |  | 217
08 |  | 156 |  |  | 0 | 936 |  | 1092 |  | 156
Grand Total |  | 422 | 72 | 80 | 237 | 3007 | 0 | 3818 |  | 811
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 |  |  |  |  | 40 | 186 | 226 |  | 40 | 117 | 5260 | 2.224%
02 |  |  |  |  | 140 | 57 | 197 |  | 140 | 156 | 3632 | 4.295%
03 |  | 122 |  | 75 |  | 82 | 279 |  | 197 | 227 | 3592 | 6.32%
04 |  | 40 |  |  | 57 | 266 | 363 |  | 97 | 168 | 5680 | 2.958%
05 | [5 empty] | 64 | 64 |  | 0 | 204 | 7144 | 2.856%
06 |  | 30 |  |  |  | 149 | 179 |  | 30 | 70 | 4744 | 1.476%
07 | [5 empty] | 2 | 2 |  | 0 | 217 | 4804 | 4.517%
08 | [5 empty] | 434 | 434 |  | 0 | 156 | 6350 | 2.457%
Grand Total |  | 192 |  | 75 | 237 | 1240 | 1744 |  | 504 | 1315 | 41206 | 3.191%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 1 | 503 | 260.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | [13 empty] | Avoidable, CEI Consultant
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 2 | 503 | 41.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 3 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 4 | 131 | 2114.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 5 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 6 | 131 | 4625.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 7 | 131 | 5579.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 8 | 131 | 10406 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 9 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 10 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 11 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 14 | 131 | 1011.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 15 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 16 | 131 | 5376.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 17 | 131 | 1298 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 18 | 131 | 22375.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 19 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 20 | 131 | 4591.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 21 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 22 | 131 | 1842.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 23 | 503 | 987.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 010 | 2 |  | 1 | 503 | 95021.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 027 | 2 | 850 | 1 | 012 | 6383.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43797315201 | 035 | 2 |  | 1 | 004 | -20000 | 0 | 0 |  | N | 200 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P44 | 43797315201 | 046 | 2 | 850 | 1 | 131 | 688.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 046 | 2 | 850 | 2 | 131 | 8814.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 058 | 2 |  | 1 | 113 | 80621.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 | 011 | 2 |  | 1 | 922 | 7675.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 | 012 | 2 |  | 1 | 001 | 48977.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 017 | 2 |  | 1 | 001 | 339503.5 | 0 | 0 |  | N | 49 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 028 | 2 |  | 1 | 101 | 6036.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 | 029 | 2 |  | 1 | 001 | 175457.23 | 0 | 0 |  | N | 110 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 030 | 2 |  | 1 | 001 | 12036.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 031 | 2 |  | 1 | 923 | 16063.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 042 | 2 |  | 1 | 012 | 7188.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R05 | 43629915201 | 043 | 2 |  | 1 | 107 | -2382.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R06 | 43658015201 | 008 | 2 |  | 1 | 105 | 29714.23 | 0 | 2 |  | N | 1 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S13 | 44462715201 | 007 | 2 |  | 1 | 007 | 1284.91 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1670 | 43512015201 | 010 | 2 |  | 1 | 012 | 17219.6 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1670 | 43512015201 | 013 | 2 |  | 1 | 001 | -1711.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1675 | 43088715201 | 013 | 2 |  | 1 | 005 | -5649.4 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1675 | 43088715201 | 014 | 2 |  | 1 | 115 | 15838.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 1 | 101 | 1749.52 | 260.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 2 | 105 | 2907.93 | 2907.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 3 | 130 | 27615.75 | 27615.75 | 4 |  | N | 72 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 4 | 003 | 2542 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1675 | 43088715201 | 015 | 2 |  | 5 | 003 | 867.6 | 867.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1675 | 43088715201 | 015 | 2 |  | 6 | 007 | -4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1702 | 43509015201 | 010 | 2 |  | 1 | 001 | 13626.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1702 | 43509015201 | 011 | 2 |  | 1 | 015 | 91073.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1742 | 43539015201 | 008 | 2 |  | 1 | 105 | 10170.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1742 | 43539015201 | 017 | 2 |  | 1 | 003 | 12440.89 | 12440.89 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1744 | 43806115201 | 005 | 2 |  | 1 | 101 | 2100 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1748 | 43510815201 | 006 | 2 |  | 1 | 101 | 3200.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1758 | 43943715201 | 002 | 2 |  | 1 | 007 | 89683.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1758 | 43943715201 | 004 | 2 |  | 1 | 001 | 24637.41 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1758 | 43943715201 | 004 | 2 |  | 2 | 101 | 960 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828665201 | 002 | 2 |  | 2 | 105 | -76737.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 009 | 2 |  | 1 | 919 | 4698.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 010 | 2 |  | 1 | 919 | 53137.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 016 | 2 |  | 1 | 004 | 419961.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 | 021 | 2 |  | 1 | 305 | -143937.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 | 029 | 2 |  | 1 | 105 | 17068.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 029 | 2 |  | 2 | 107 | 26.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 039 | 2 |  | 1 | 923 | 7185.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 040 | 2 |  | 1 | 923 | 7979.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 050 | 2 |  | 1 | 126 | 83920.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1997 | 40828665201 | 050 | 2 |  | 2 | 117 | 254738.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1997 | 40828665201 | 053 | 2 |  | 1 | 503 | 31766.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2W31 | 43373015201 | 011 | 2 |  | 1 | 919 | 16473.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 1 | 001 | 10229.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 2 | 001 | 11127.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 3 | 001 | 7896.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 4 | 001 | 11415.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 5 | 106 | 5158.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X06 | 43076015201 | 032 | 2 | 850 | 1 | 001 | 14052.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2675 | 43611415201 | 008 | 2 |  | 1 | 107 | 2312 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2675 | 43611415201 | 012 | 2 |  | 1 | 012 | 10527.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2702 | 43616515201 | 009 | 2 | 850 | 1 | 001 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2702 | 43616515201 | 019 | 2 | 850 | 1 | 001 | 24505.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2709 | 21284435201 | 001 | 2 |  | 1 | 101 | 42749.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2722 | 43761515201 | 007 | 2 | 850 | 1 | 012 | 25000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2722 | 43761515201 | 007 | 2 | 850 | 2 | 010 | 23751.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2726 | 43583715201 | 001 | 2 |  | 1 | 105 | 15546.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 002 | 2 |  | 1 | 105 | 22177.27 | 1482.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 003 | 2 |  | 1 | 105 | 555.5 | 555.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 004 | 2 |  | 1 | 105 | 6875.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 012 | 2 |  | 1 | 105 | 25316.91 | 25316.91 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 019 | 2 |  | 1 | 923 | 9602.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3O87 | 42820825201 | 009 | 2 |  | 1 | 012 | 24302.18 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3O87 | 42820825201 | 009 | 2 |  | 2 | 101 | 0 | 1451.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 | 017 | 2 |  | 1 | 919 | 5319.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 | 026 | 2 |  | 1 | 503 | 2612 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O87 | 42820825201 | 027 | 2 |  | 1 | 115 | 26599.01 | 5124.7 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 | 032 | 2 |  | 1 | 015 | 192230 | 0 | 5 |  | N | 11 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | E3Q54 | 22253925201 | 006 | 2 |  | 1 | 305 | -75509.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | E3R03 | 41343525201 | 013 | 2 |  | 1 | 005 | 12921.46 | 12921.46 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 016 | 2 |  | 1 | 922 | 9486.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 024 | 2 |  | 1 | 503 | -7302.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 026 | 2 |  | 1 | 112 | 15065.19 | 1827.1 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | E3R03 | 41343525201 | 032 | 2 |  | 1 | 503 | 1211.98 | 1211.98 | 5 |  | N | 1 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 033 | 2 |  | 1 | 503 | 7926.77 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 034 | 2 |  | 1 | 503 | 4936.5 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 035 | 2 |  | 1 | 503 | 34513.57 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 036 | 2 |  | 1 | 503 | 8003.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 | 013 | 2 |  | 1 | 503 | 158901.87 | 0 | 0 |  | E | 96 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 003 | 2 |  | 1 | 503 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 1 | 503 | 69177.42 | 69177.42 | 0 |  | N | 55 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 2 | 503 | 4011.87 | 4011.87 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 3 | 503 | 0 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 4 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 5 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 6 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 7 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 | 009 | 2 |  | 1 | 113 | -5016 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3R72 | 43255415201 | 010 | 2 |  | 1 | 012 | 47176 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R72 | 43255415201 | 012 | 2 |  | 1 | 503 | 14454.7 | 4665.88 | 1 |  | N | 3 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 | 013 | 2 |  | 1 | 503 | 66724.26 | 0 | 2 |  | N | 13 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 002 | 2 |  | 1 | 101 | 13944 | 1708.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R75 | 40731075201 | 003 | 2 |  | 1 | 503 | 7592.35 | 7592.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 013 | 2 |  | 1 | 503 | 70580.44 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 015 | 2 |  | 1 | 503 | 24809.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R84 | 43736715201 | 001 | 2 |  | 1 | 106 | 103424.95 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3S03 | 43775215201 | 013 | 2 |  | 1 | 012 | 42363.01 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3585 | 43228515201 | 002 | 2 |  | 1 | 503 | -1394.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3619 | 43390215201 | 008 | 2 |  | 1 | 001 | 49049.79 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3642 | 43274025201 | 008 | 2 |  | 1 | 503 | 55550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3642 | 43274025201 | 026 | 2 |  | 1 | 922 | 78411 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3642 | 43274025201 | 032 | 2 |  | 1 | 503 | 5900.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3648 | 43580215201 | 007 | 2 |  | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3663 | 43188345201 | 003 | 2 |  | 1 | 503 | 207.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3663 | 43188345201 | 012 | 2 |  | 1 | 012 | 11597.01 | 2420.63 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3668 | 43580015201 | 004 | 2 |  | 1 | 503 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3739 | 44173715201 | 003 | 2 |  | 1 | 128 | 7093.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | E4N82 | 22777515201 | 023 | 2 |  | 1 | 116 | 90064.65 | 11550 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | E4N82 | 22777515201 | 027 | 2 |  | 1 | 008 | 49760.94 | 49760.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4N82 | 22777515201 | 039 | 2 |  | 1 | 008 | 69424.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 1 | 106 | 13193.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 2 | 007 | 13700.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 3 | 503 | 6725.87 | 3959.42 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 4 | 503 | 3499.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 5 | 503 | 9259.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 6 | 503 | 4885.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 057 | 2 |  | 1 | 503 | 40631.41 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 062 | 2 |  | 1 | 503 | 161008.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 078 | 2 |  | 1 | 919 | 49745.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 092 | 2 |  | 1 | 106 | 55770.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 | 103 | 2 |  | 1 | 015 | 269840.95 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 | 111 | 2 |  | 1 | 015 | 197239.08 | 132525.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 | 111 | 2 |  | 2 | 503 | 225994.99 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 111 | 2 |  | 3 | 022 | 81051.53 | 81051.53 | 0 |  | C | 170 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 111 | 2 |  | 4 | 024 | 19147.5 | 19147.5 | 5 |  | C | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 137 | 2 |  | 1 | 024 | 0 | 0 | 5 |  | N | 51 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T46 | 43388815201 | 006 | 2 |  | 1 | 923 | 12401.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T46 | 43388815201 | 017 | 2 |  | 1 | 106 | 95163.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T56 | 43578125201 | 021 | 2 |  | 1 | 024 | 11580.46 | 11580.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T84 | 43389615201 | 005 | 2 |  | 1 | 107 | 0 | 0 | 0 |  | N | -15 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T92 | 44140915201 | 002 | 2 |  | 1 | 926 | 11180.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 008 | 2 |  | 1 | 919 | 7079.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 1 | 007 | 5216.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 2 | 003 | 1145.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 3 | 003 | 1221.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 4 | 003 | 3260.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 5 | 108 | 15447.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 6 | 108 | 16783.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 7 | 115 | 483.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 8 | 108 | 3205.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 9 | 003 | 2067.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 10 | 003 | 2186.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 11 | 023 | 6538.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 12 | 003 | 2411.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 13 | 003 | 3058.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 14 | 003 | 2349.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 15 | 101 | 3484.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 16 | 123 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 17 | 001 | 17087.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 18 | 023 | 17657.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 19 | 101 | 3936.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 20 | 023 | 2172.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 21 | 115 | 3937.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 22 | 105 | 1612.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 23 | 003 | 1895.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 24 | 101 | 3910.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 25 | 023 | -90 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 26 | 023 | -2172.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 036 | 2 |  | 1 | 106 | 7501.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4461 | 42793715201 | 039 | 2 |  | 1 | 012 | 65130.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 044 | 2 |  | 1 | 007 | 46192.27 | 46192.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 | 049 | 2 |  | 1 | 106 | 13058.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4461 | 42793715201 | 050 | 2 |  | 1 | 012 | 597998.67 | 0 | 0 |  | N | 100 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 061 | 2 |  | 1 | 923 | 14701.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 065 | 2 |  | 1 | 101 | 36450.19 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 068 | 2 |  | 1 | 012 | 73262.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4473 | 42751615201 | 007 | 2 |  | 1 | 004 | 144864 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4473 | 42751615201 | 014 | 2 |  | 1 | 305 | -324121 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4473 | 42751615201 | 027 | 2 |  | 1 | 101 | 2801.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4473 | 42751615201 | 030 | 2 |  | 1 | 923 | 10358.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4479 | 43059025201 | 021 | 2 |  | 1 | 001 | 7371.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4483 | 44008115201 | 024 | 2 |  | 1 | 503 | 22625.47 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4489 | 43770115201 | 016 | 2 |  | 1 | 923 | 136401.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4489 | 43770115201 | 024 | 2 |  | 1 | 105 | 86742.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4491 | 43234815201 | 005 | 2 |  | 1 | 007 | 21683.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4491 | 43234815201 | 012 | 2 |  | 1 | 923 | 15850.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4491 | 43234815201 | 021 | 2 |  | 1 | 106 | 29233.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 022 | 2 |  | 1 | 012 | 105884.74 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4491 | 43234815201 | 023 | 2 | 850 | 1 | 001 | 6105.76 | 2611.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 | 023 | 2 | 850 | 2 | 122 | 1593.86 | 1593.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4491 | 43234815201 | 023 | 2 | 850 | 3 | 106 | 5142.7 | 5142.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 023 | 2 | 850 | 4 | 022 | 31506.88 | 31506.88 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 029 | 2 |  | 1 | 101 | 7173.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4496 | 43288335201 | 005 | 2 |  | 1 | 126 | 165747.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4496 | 43288335201 | 006 | 2 |  | 1 | 126 | 22386.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4496 | 43288335201 | 006 | 2 |  | 4 | 101 | 8956.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4496 | 43288335201 | 007 | 2 | 850 | 1 | 108 | 966.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4496 | 43288335201 | 007 | 2 | 850 | 2 | 001 | 6130.19 | 1088.95 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335201 | 019 | 2 |  | 1 | 105 | 100000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 | 026 | 2 |  | 1 | 923 | 1894.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 | 031 | 2 |  | 1 | 128 | 30738.63 | 30738.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4498 | 43689315201 | 009 | 2 | 850 | 1 | 001 | 7891.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 | 009 | 2 | 850 | 2 | 005 | 10121.73 | 10121.73 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 009 | 2 | 850 | 3 | 024 | 715.5 | 715.5 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 009 | 2 | 850 | 4 | 005 | 15642.8 | 15642.8 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 011 | 2 |  | 1 | 126 | 53883.53 | 44187.03 | 1 |  | N | 5 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4503 | 43611115201 | 017 | 2 |  | 1 | 105 | 59638.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4503 | 43611115201 | 019 | 2 | 850 | 1 | 108 | 20932.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 | 019 | 2 | 850 | 2 | 105 | 1079.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4503 | 43611115201 | 023 | 2 |  | 1 | 101 | 5865.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4540 | 43834515201 | 001 | 2 |  | 1 | 101 | 16665 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 004 | 2 |  | 1 | 919 | 7917.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 011 | 2 |  | 1 | 004 | 12868.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y62 | 23831925201 | 012 | 2 |  | 1 | 106 | 11046.34 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 012 | 2 |  | 2 | 106 | 73812 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 012 | 2 |  | 3 | 503 | 14090.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y62 | 23831925201 | 033 | 2 |  | 1 | 923 | 13180.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y62 | 23831925201 | 051 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 102 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 | 010 | 2 |  | 1 | 112 | 0 | 0 | 1 |  | N | 64 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 1 | 112 | 27788.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 2 | 503 | 6502.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 3 | 503 | 12252.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 4 | 010 | 3456.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z64 | 44121015201 | 006 | 2 |  | 1 | 503 | 6240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 006 | 2 |  | 2 | 101 | 6978.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 006 | 2 |  | 3 | 503 | 15151.43 | 3472.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 008 | 2 |  | 1 | 923 | 3539.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 013 | 2 |  | 1 | 007 | 120628.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 1 | 010 | 2240.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 2 | 105 | 4403.6 | 4403.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 3 | 115 | 1473.63 | 1473.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 4 | 112 | 6509.04 | 5551.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 021 | 2 |  | 1 | 126 | -1568.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 021 | 2 |  | 2 | 122 | 12701.95 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 025 | 2 |  | 1 | 112 | 0 | 0 | 1 |  | N | 16 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z68 | 44096915201 | 001 | 2 |  | 1 | 923 | 4114.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z77 | 43912115201 | 015 | 2 |  | 1 | 118 | -7404 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5530 | 23968215201 | 011 | 2 |  | 1 | 107 | 19000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 016 | 2 |  | 1 | 115 | -37015.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 017 | 2 |  | 1 | 105 | 121734.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 019 | 2 |  | 1 | 107 | 184263.43 | 0 | 1 |  | N | 44 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 025 | 2 |  | 1 | 107 | 390710.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 025 | 2 |  | 2 | 106 | 0 | 0 | 5 |  | N | 80 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 026 | 2 |  | 1 | 305 | -178686.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 027 | 2 |  | 1 | 917 | 79449.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 030 | 2 |  | 1 | 919 | 249920.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 041 | 2 |  | 1 | 112 | 52090.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 046 | 2 |  | 1 | 105 | 24128.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 058 | 2 | 850 | 1 | 015 | 16276.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 058 | 2 | 850 | 2 | 015 | 16276.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 066 | 2 |  | 1 | 112 | 605227.55 | 0 | 0 |  | N | 108 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 070 | 2 |  | 1 | 112 | 262387.98 | 57126.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 071 | 2 |  | 1 | 106 | 189994.45 | 70225.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 073 | 2 | 850 | 1 | 015 | 2819.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 073 | 2 | 850 | 2 | 015 | 8774.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 076 | 2 |  | 1 | 106 | 92410.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 077 | 2 |  | 1 | 112 | 108283.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 080 | 2 |  | 1 | 923 | 27671.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 083 | 2 |  | 1 | 101 | 55475 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 1 | 106 | 2245.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 2 | 106 | 6721.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 3 | 106 | 8188.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 4 | 106 | 3088.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 086 | 2 |  | 1 | 105 | 29353.67 | 27458.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 088 | 2 |  | 1 | 001 | 86428.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 | 092 | 2 |  | 1 | 001 | 487803.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5590 | 42690535201 | 013 | 2 |  | 1 | 003 | 112019.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5590 | 42690535201 | 014 | 2 |  | 1 | 923 | 219530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5590 | 42690535201 | 015 | 2 |  | 1 | 106 | 3734 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5590 | 42690535201 | 016 | 2 |  | 1 | 105 | 111390.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 017 | 2 |  | 1 | 112 | 103337.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5590 | 42690535201 | 031 | 2 | 850 | 1 | 004 | 25169.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5590 | 42690535201 | 031 | 2 | 850 | 2 | 105 | 2476.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 031 | 2 | 850 | 3 | 503 | 11200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5590 | 42690535201 | 031 | 2 | 850 | 4 | 105 | 35359.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 034 | 2 |  | 1 | 115 | 203086.04 | 3698.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 | 041 | 2 |  | 1 | 004 | 28277.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5592 | 43440715201 | 041 | 2 |  | 2 | 118 | 10783.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5592 | 43440715201 | 041 | 2 |  | 3 | 118 | 12925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5604 | 43734515201 | 003 | 2 |  | 1 | 004 | 17639.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5604 | 43734515201 | 006 | 2 |  | 1 | 923 | 12252.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5604 | 43734515201 | 019 | 2 |  | 1 | 117 | 25000 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5615 | 43793115201 | 015 | 2 |  | 1 | 860 | 31000 | 0 | 0 |  | N | 176 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5624 | 43687915201 | 019 | 2 |  | 1 | 923 | 2683.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5624 | 43687915201 | 031 | 2 | 850 | 1 | 012 | 6115.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5624 | 43687915201 | 031 | 2 | 850 | 2 | 105 | 6182.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5624 | 43687915201 | 031 | 2 | 850 | 3 | 118 | 56055.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5624 | 43687915201 | 031 | 2 | 850 | 4 | 503 | 3609.5 | 3609.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5624 | 43687915201 | 035 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5629 | 43759215201 | 007 | 2 |  | 1 | 923 | 3778.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5630 | 43732715201 | 018 | 2 |  | 1 | 923 | 1940.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5630 | 43732715201 | 035 | 2 |  | 1 | 022 | 40587.39 | 40587.39 | 5 |  | C | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5634 | 43734815201 | 007 | 2 |  | 1 | 923 | 2392.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5634 | 43734815201 | 027 | 2 |  | 1 | 107 | 14861.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5634 | 43734815201 | 027 | 2 |  | 2 | 115 | 162890.44 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5661 | 43968225201 | 001 | 2 |  | 1 | 923 | 3208.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5677 | 43923315201 | 006 | 2 |  | 1 | 115 | 144976.35 | 9704.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K86 | 43653215201 | 002 | 2 |  | 1 | 101 | 5393.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 005 | 2 |  | 1 | 101 | 88680.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 008 | 2 |  | 1 | 923 | 8188.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 013 | 2 |  | 1 | 108 | 37614.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L92 | 44203815201 | 003 | 2 |  | 1 | 007 | -1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6420 | 43345515201 | 007 | 2 |  | 1 | 305 | -453467.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6420 | 43345515201 | 017 | 2 | 850 | 1 | 503 | 14364.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 017 | 2 | 850 | 2 | 503 | 5124.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 017 | 2 | 850 | 3 | 503 | 4622.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 018 | 2 |  | 1 | 923 | 5263.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 003 | 2 |  | 1 | 503 | 314858.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 003 | 2 |  | 2 | 503 | 342248.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 015 | 2 | 850 | 1 | 004 | 6035.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 2 | 001 | 15390.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 3 | 112 | 5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 4 | 112 | 5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 5 | 115 | 2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 6 | 101 | 13980 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 7 | 004 | 12782.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 8 | 105 | 6925.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 9 | 113 | 2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 10 | 007 | 2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 11 | 105 | -6925.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 12 | 112 | -5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 13 | 105 | 6928.85 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 14 | 112 | 5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 15 | 112 | -5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 16 | 115 | 2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 17 | 113 | 2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 18 | 115 | -2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 19 | 007 | 2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 20 | 112 | 5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 21 | 113 | -2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 22 | 007 | -2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 016 | 2 | 850 | 1 | 101 | 11160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 | 016 | 2 | 850 | 2 | 105 | 5990.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 016 | 2 | 850 | 3 | 003 | 2944.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6422 | 42736925201 | 016 | 2 | 850 | 4 | 113 | 12869.5 | 12869.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 018 | 2 |  | 1 | 923 | 64478.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 021 | 2 |  | 1 | 001 | 245590.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 | 016 | 2 | 850 | 1 | 023 | 5813.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 | 016 | 2 | 850 | 2 | 118 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 3 | 118 | 817.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 4 | 101 | 5191.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 5 | 503 | 3786.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6425 | 42597925201 | 016 | 2 | 850 | 6 | 112 | 19139.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6425 | 42597925201 | 017 | 2 | 850 | 1 | 850 | 9500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6425 | 42597925201 | 024 | 2 | 850 | 1 | 023 | 739.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6425 | 42597925201 | 025 | 2 | 850 | 1 | 118 | 1228.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6441 | 43117045201 | 008 | 2 |  | 1 | 923 | 12198.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6442 | 43063735201 | 009 | 2 |  | 1 | 107 | 3108.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6442 | 43063735201 | 024 | 2 |  | 1 | 923 | 112776.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6442 | 43063735201 | 026 | 2 |  | 1 | 015 | 375053.74 | 375053.74 | 5 |  | C | 40 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6459 | 44018715201 | 011 | 2 |  | 1 | 503 | 27176.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6470 | 43991715201 | 009 | 2 |  | 1 | 503 | 30818 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6477 | 44281315201 | 008 | 2 |  | 1 | 010 | 3563.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 | 009 | 2 |  | 1 | 101 | 2098.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44281315201 | 014 | 2 |  | 1 | 101 | 2056 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44281315201 | 015 | 2 |  | 1 | 101 | 6957 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7K30 | 42450725201 | 003 | 2 |  | 1 | 004 | 53910 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 003 | 2 |  | 2 | 004 | 53910 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 005 | 2 |  | 1 | 105 | 21129.93 | 21129.93 | 2 |  | N | 37 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K30 | 42450725201 | 006 | 2 |  | 1 | 004 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 007 | 2 |  | 1 | 122 | 374565.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K30 | 42450725201 | 011 | 2 |  | 1 | 122 | 103510.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K30 | 42450725201 | 014 | 2 |  | 1 | 004 | 22139.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 027 | 2 |  | 1 | 004 | -6972.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 037 | 2 |  | 1 | 005 | 0 | 0 | 5 |  | N | 36 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7M31 | 43751715201 | 009 | 2 | 850 | 2 | 012 | 5653.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 009 | 2 | 850 | 3 | 012 | 34858.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 012 | 2 |  | 1 | 012 | -215166.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 012 | 2 |  | 2 | 012 | 97872.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
07 | E7R14 | 43402715201 | 019 | 2 |  | 1 | 019 | -197831.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
07 | E7R14 | 43402715201 | 019 | 2 |  | 2 | 503 | 150206.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R14 | 43402715201 | 019 | 2 |  | 3 | 101 | 11094.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7R14 | 43402715201 | 019 | 2 |  | 4 | 924 | 0 | 0 | 1 |  | N | 45 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7403 | 43484815201 | 002 | 2 |  | 1 | 107 | 272000 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7403 | 43484815201 | 015 | 2 |  | 1 | 001 | 10764.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 | 015 | 2 |  | 2 | 001 | 62227.26 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 | 015 | 2 |  | 3 | 503 | -36724.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7403 | 43484815201 | 016 | 2 |  | 1 | 015 | 18962.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 019 | 2 | 850 | 1 | 004 | 74905.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 | 023 | 2 |  | 1 | 007 | 126004 | 126004 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7403 | 43484815201 | 024 | 2 |  | 1 | 015 | 312498.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 026 | 2 |  | 1 | 101 | 193376.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7403 | 43484815201 | 027 | 2 |  | 1 | 015 | 24665.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 028 | 2 |  | 1 | 923 | 19997.87 | 19997.87 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 037 | 2 |  | 1 | 126 | 1147.94 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Computation Error | Plan Modifications | 2
07 | T7403 | 43484815201 | 038 | 2 |  | 1 | 502 | 7800.89 | 709.17 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | T7403 | 43484815201 | 038 | 2 |  | 2 | 126 | 5500 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Computation Error | Plan Modifications | 2
07 | T7406 | 42895715201 | 010 | 2 |  | 1 | 119 | 4543 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
07 | T7406 | 42895715201 | 013 | 2 |  | 1 | 101 | 38081.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 | 013 | 2 |  | 2 | 012 | 19158.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 | 021 | 2 |  | 1 | 105 | 3359.89 | 2053.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7406 | 42895715201 | 024 | 2 |  | 1 | 024 | 3225.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7406 | 42895715201 | 025 | 2 |  | 1 | 115 | 1579.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 030 | 2 |  | 1 | 001 | 21907.79 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 030 | 2 |  | 2 | 107 | 6174.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 033 | 2 |  | 1 | 923 | 15801.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 033 | 2 |  | 2 | 012 | 6136.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 | 036 | 2 |  | 1 | 001 | 90700.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 037 | 2 |  | 1 | 001 | 92484 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 038 | 2 |  | 1 | 001 | 385000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 009 | 2 |  | 1 | 305 | -124157.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 009 | 2 |  | 2 | 107 | 1586.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7413 | 43658815201 | 015 | 2 |  | 1 | 001 | 119288.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 027 | 2 |  | 1 | 101 | 356674.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 1 | 001 | 3888 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 2 | 001 | 8552.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 3 | 007 | 3122.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 4 | 128 | 3000 | 3000 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 5 | 923 | 1609.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 6 | 108 | 2108.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 7 | 126 | 2658.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | T7426 | 43648715201 | 013 | 2 |  | 1 | 019 | 21000 | 21000 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 1 | 012 | 5997.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 2 | 012 | 1260.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 3 | 503 | 2997.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 4 | 012 | 5222.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 5 | 012 | 7502 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 6 | 012 | 400.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 7 | 012 | 1484.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 8 | 007 | 7529.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 9 | 012 | 11124.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 10 | 012 | 5597.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 11 | 012 | 5530.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 12 | 917 | 91439.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 13 | 012 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 030 | 2 |  | 1 | 004 | 158905.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 031 | 2 |  | 1 | 107 | 28187.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8M65 | 40609615201 | 033 | 2 |  | 1 | 004 | 48400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 036 | 2 |  | 1 | 004 | 126116.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 037 | 2 |  | 1 | 003 | 62415.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8M65 | 40609615201 | 039 | 2 |  | 1 | 503 | 712709.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 039 | 2 |  | 2 | 004 | -184400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 039 | 2 |  | 3 | 003 | -191534.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8M65 | 40609615201 | 046 | 2 |  | 1 | 004 | 24762.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 051 | 2 |  | 1 | 004 | 262895.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 052 | 2 |  | 1 | 503 | 616622.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 055 | 2 |  | 1 | 004 | 16228.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 058 | 2 |  | 1 | 004 | 164985.31 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 059 | 2 |  | 1 | 208 | 946875.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
08 | E8M65 | 40609615201 | 078 | 2 |  | 1 | 004 | 7933388.17 | 1383054.63 | 0 |  | N | 270 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 1 | 021 | 6678.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 2 | 503 | 5120.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 3 | 503 | 4176 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 4 | 503 | 13122.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 5 | 503 | 10246.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 6 | 012 | 1600.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 8 | 012 | 2564.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 9 | 503 | 2525.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 10 | 503 | 7547.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 11 | 012 | 2525.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 12 | 503 | 44764.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 15 | 010 | 26723.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 18 | 503 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 098 | 2 |  | 1 | 004 | 0 | 0 | 0 |  | N | 220 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 102 | 2 |  | 1 | 919 | 377151.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 123 | 2 |  | 1 | 503 | 144144.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 124 | 2 |  | 1 | 019 | -543418.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 1 | 503 | 8701.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 2 | 503 | 5819 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 3 | 503 | 54120 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 4 | 923 | 19317.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 5 | 503 | 11145.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 6 | 012 | 2188.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 7 | 503 | 29349.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 8 | 503 | 15394.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 127 | 2 |  | 1 | 503 | 343981.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 128 | 2 | 850 | 1 | 503 | 60948.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 128 | 2 | 850 | 2 | 503 | 7547.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 004 | 2 |  | 1 | 305 | -63028.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 028 | 2 |  | 1 | 919 | 150132.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 1 | 023 | 9375.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 2 | 023 | 7181.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 3 | 021 | 13533.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 4 | 023 | 5732.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 5 | 023 | 2189.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 6 | 115 | 8805.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 7 | 107 | 7236.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 8 | 003 | 56698.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 032 | 2 |  | 1 | 305 | -25375.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 039 | 2 |  | 1 | 009 | 291584.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N75 | 40611015201 | 049 | 2 |  | 1 | 503 | 43063.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 1 | 001 | 60829.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 2 | 004 | 2182 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 3 | 023 | 5182.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 4 | 023 | 1376.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 5 | 023 | 2888.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 6 | 023 | 12546.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 7 | 023 | 11149.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 8 | 023 | 14613.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 9 | 023 | 3511.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 10 | 108 | 16747.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 11 | 107 | 4875.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 12 | 023 | 4680.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 058 | 2 |  | 1 | 860 | 270000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8N75 | 40611015201 | 059 | 2 |  | 1 | 001 | 643196 | 0 | 0 |  | N | 54 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 060 | 2 |  | 1 | 001 | 2368613.36 | 0 | 0 |  | N | 44 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 061 | 2 |  | 1 | 004 | 960545.48 | 0 | 0 |  | N | 89 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 066 | 2 |  | 1 | 003 | 261289.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 069 | 2 |  | 1 | 012 | 92000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 078 | 2 |  | 1 | 923 | 78934.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 1 | 023 | 12773.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 2 | 021 | 23708.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 3 | 021 | 21680.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 007 | 2 |  | 1 | 503 | -44517.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 007 | 2 |  | 2 | 004 | -6451.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 023 | 2 |  | 1 | 503 | -393246.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 023 | 2 |  | 2 | 915 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 1 | 003 | 23309.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 2 | 105 | 10556.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 3 | 019 | 2074.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 4 | 018 | 16386.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 5 | 023 | 22586.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 6 | 101 | 3958.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 7 | 101 | 1188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 8 | 101 | 31600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 9 | 101 | 8316 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 10 | 115 | 2677.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 11 | 010 | 4296.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 12 | 021 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 13 | 503 | 1816.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 14 | 105 | 8533.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 15 | 115 | 4475.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 16 | 115 | 5724.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 030 | 2 |  | 1 | 914 | 45911.34 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 032 | 2 |  | 1 | 503 | 29077.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 032 | 2 |  | 2 | 916 | 41701.47 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 033 | 2 |  | 1 | 503 | 455166 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 033 | 2 |  | 2 | 503 | 264834 | 10885.05 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 1 | 115 | 12774.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 2 | 115 | 29411.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 3 | 503 | 14099.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 4 | 503 | 9248.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 5 | 101 | 5608.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 6 | 115 | 5785.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 7 | 503 | 5968.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 8 | 107 | 30708.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 9 | 105 | 2844.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 10 | 108 | 3068.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 11 | 115 | 5694.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 12 | 128 | 22749.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 13 | 106 | 2038.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P02 | 40609055201 | 040 | 2 |  | 2 | 012 | 8793.08 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 1 | 128 | 1250.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 2 | 503 | 21622.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 3 | 115 | 4022.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 4 | 115 | 2915.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 5 | 503 | 4750.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 6 | 503 | 200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 7 | 022 | 5676.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 8 | 503 | 1925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 9 | 115 | 2838.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 10 | 012 | 9386.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 11 | 003 | 2118.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 12 | 115 | 1106.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 13 | 115 | 1799.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 14 | 018 | 6840.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 15 | 112 | 15831.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 16 | 503 | 2888.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 17 | 503 | 3467.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 18 | 022 | 2569.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 19 | 126 | 12794.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 20 | 023 | 4861.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 21 | 503 | 988.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 22 | 112 | 12174.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 23 | 115 | 10457.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 24 | 022 | 15514.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 25 | 503 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 046 | 2 |  | 1 | 503 | 112313.5 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 047 | 2 |  | 1 | 503 | 6851.77 | 6851.77 | 0 |  | C | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 047 | 2 |  | 2 | 001 | 162000 | 162000 | 0 |  | C | 20 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 047 | 2 |  | 3 | 001 | 22339.17 | 22339.17 | 0 |  | C | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 047 | 2 |  | 4 | 503 | 18000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 051 | 2 |  | 1 | 503 | 153602.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 051 | 2 |  | 2 | 101 | 87028.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 051 | 2 |  | 3 | 101 | 75050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 051 | 2 |  | 4 | 503 | 60305.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 2 | 503 | 0 | 0 | 0 |  | N | -3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 3 | 503 | 0 | 0 | 0 |  | N | -4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 1 | 115 | 1267.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 2 | 503 | 40149 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 3 | 503 | 7705.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 4 | 503 | 4291.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 5 | 023 | 11093.08 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 6 | 503 | 64000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 7 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 8 | 115 | 1615.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 10 | 503 | 6570.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 11 | 503 | 107.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 063 | 2 |  | 1 | 503 | 121447.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 063 | 2 |  | 2 | 503 | 44478.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 066 | 2 |  | 1 | 919 | 372612.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 1 | 503 | 5819.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 3 | 018 | 9176.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 5 | 503 | 18214.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 7 | 003 | 3062.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 8 | 106 | 17942.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 9 | 108 | 1049.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 10 | 118 | 1157.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 11 | 112 | 18181.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 12 | 108 | 12975.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 13 | 115 | 2000.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 14 | 022 | 4951.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 15 | 024 | 2475.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 16 | 003 | 557.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 19 | 118 | 5134.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 20 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 21 | 001 | 10344.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 22 | 112 | 6783.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 23 | 118 | 4678.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 25 | 101 | 3621.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 26 | 118 | 2071.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 069 | 2 |  | 1 | 503 | 127046.82 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 070 | 2 |  | 1 | 503 | 210944.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 1 | 503 | 11109.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 2 | 503 | 29536.92 | 9494.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 3 | 503 | 105715.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 4 | 503 | 21387.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 5 | 503 | 548155.14 | 274077.57 | 1 |  | N | 150 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 6 | 503 | 279804.4 | 94399.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 081 | 2 |  | 1 | 503 | -128857.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 1 | 118 | 6158.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 3 | 108 | 31064.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 4 | 108 | 1978.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 090 | 2 |  | 1 | 503 | 54918.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 2 | 503 | 126665.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 3 | 503 | 4480.83 | 4480.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 4 | 503 | 3963.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 5 | 503 | 6353.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 6 | 503 | 2007.38 | 2007.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 7 | 503 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 8 | 503 | 3405.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 9 | 503 | 4926.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 10 | 503 | 3567.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 11 | 503 | 222514.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 1 | 917 | 98329.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 2 | 503 | 33003.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 3 | 004 | 162566.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 1 | 022 | 11329.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 2 | 023 | 2816.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 3 | 503 | 67355.72 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 093 | 2 |  | 1 | 917 | 0 | 0 | 0 |  | N | -4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 012 | 2 |  | 1 | 003 | -155000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 | 017 | 2 |  | 1 | 128 | 22000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P82 | 43715615201 | 020 | 2 |  | 1 | 003 | 24876.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 | 024 | 2 |  | 1 | 503 | 22695 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 026 | 2 |  | 1 | 503 | 223422.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 030 | 2 |  | 1 | 503 | 122021.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 032 | 2 |  | 1 | 919 | 105075.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 035 | 2 |  | 1 | 503 | 69149 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 1 | 106 | 10299.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 2 | 023 | 8854.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 3 | 502 | 8997.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 4 | 012 | 3144 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 5 | 012 | 12082.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 6 | 503 | 19275.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 7 | 012 | 3157.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 8 | 115 | 17807.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 9 | 105 | 7051.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 10 | 012 | 8048.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 11 | 113 | 28166.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 12 | 105 | 5099.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 13 | 012 | 6508.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 041 | 2 |  | 1 | 503 | 224400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 043 | 2 |  | 1 | 503 | 39500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 044 | 2 |  | 1 | 503 | 17617.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 047 | 2 |  | 1 | 503 | 21836.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 049 | 2 |  | 1 | 503 | 137382.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 051 | 2 |  | 1 | 105 | 77562.19 | 61112.19 | 1 |  | N | 6 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 052 | 2 |  | 1 | 503 | 53774.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 055 | 2 |  | 1 | 503 | 16048.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 070 | 2 |  | 1 | 118 | 22420.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 | 078 | 2 |  | 1 | 113 | 19307 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 079 | 2 |  | 1 | 503 | 62997.61 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 082 | 2 |  | 1 | 024 | 50341.84 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 105 | 2 |  | 1 | 923 | 88416.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 114 | 2 |  | 1 | 503 | 38190.96 | 0 | 0 |  | N | 42 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 116 | 2 |  | 1 | 012 | 102025.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 | 021 | 2 |  | 1 | 503 | 365648.34 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 1 | 023 | 12863.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 2 | 023 | 14371.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 3 | 023 | 57300.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 4 | 023 | 8384.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 048 | 2 |  | 1 | 923 | 36759.43 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 052 | 2 | 850 | 1 | 023 | 64632.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 059 | 2 |  | 1 | 105 | -46875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q53 | 43516915201 | 059 | 2 |  | 2 | 101 | 56477.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q53 | 43516915201 | 064 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 016 | 2 |  | 1 | 112 | 344805.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 1 | 106 | 1746.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 2 | 105 | 3063.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 3 | 023 | 11156.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 4 | 118 | 1520.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 023 | 2 |  | 1 | 112 | 4488.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 037 | 2 |  | 1 | 923 | 7893.31 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 038 | 2 |  | 1 | 003 | -519709.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q94 | 43947815201 | 054 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8R19 | 43560565201 | 014 | 2 | 850 | 1 | 503 | 38093.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 | 014 | 2 | 850 | 2 | 503 | 5040.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 | 014 | 2 |  | 1 | 923 | 17526.5 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 | 015 | 2 |  | 1 | 860 | 125000 | 19602.33 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R76 | 43945715201 | 003 | 2 | 850 | 1 | 107 | 13354.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R76 | 43945715201 | 003 | 2 | 850 | 2 | 010 | 1919.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R76 | 43945715201 | 011 | 2 |  | 1 | 012 | 204265.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 015 | 2 |  | 1 | 923 | 34435.62 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 018 | 2 |  | 1 | 012 | -936460.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 027 | 2 |  | 1 | 012 | 304471.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 028 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R81 | 44132225201 | 007 | 2 |  | 1 | 010 | 45965 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R81 | 44132225201 | 007 | 2 |  | 2 | 018 | 48106.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8R99 | 42897115201 | 005 | 2 |  | 1 | 107 | -576 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 359.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1440.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1460 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1133.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 012 | 1684.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 012 | 6575.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | -1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 107 | -466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 3 | 107 | -373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 4 | 107 | -386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 5 | 107 | -466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 6 | 107 | -279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 7 | 107 | -466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 8 | 107 | -479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 9 | 107 | -8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 10 | 107 | -3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 585.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 107 | 1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 3 | 107 | 466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 4 | 107 | 373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 5 | 107 | 386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 6 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 7 | 107 | 279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 8 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 9 | 107 | 479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 10 | 107 | 8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 11 | 107 | 3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | -15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 2 | 503 | -47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 855.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 2 | 503 | 15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 3 | 503 | 47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 269.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 105 | 11644.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 2184.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | -24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43852815201 |  | 2 | CPI | 2 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 1468.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 4852.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 5579.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 6792.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 131 | 323.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 1842.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 503 | 1437.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 107 | 7394.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 107 | -2396.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 2 | 101 | 1026.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 101 | 3615 | 2585.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R86 | 44108815201 |  | 2 | CPI | 1 | 024 | 12659.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R86 | 44108815201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1S13 | 44462715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
01 | T1742 | 43539015201 |  | 2 | CPI | 1 | 017 | 3026.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1742 | 43539015201 |  | 2 | CPI | 2 | 118 | 1820.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1742 | 43539015201 |  | 2 | CPI | 1 | 118 | 1928.94 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1744 | 43806115201 |  | 2 | CPI | 1 | 001 | 2845.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1748 | 43510815201 |  | 2 | CPI | 1 | 003 | 8712 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 001 | 4525.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 7583.1 | 7583.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 72 | 72 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 4229.66 | 4229.66 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 107 | 3842.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2W31 | 43373015201 |  | 2 | CPI | 2 | 105 | 33477.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W31 | 43373015601 |  | 2 | CPI | 1 | 015 | 12500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 105 | 22235.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2W31 | 43373015601 |  | 2 | CPI | 1 | 015 | 13515.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015601 |  | 2 | CPI | 2 | 015 | 424.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 923 | 16678.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 350 | 6450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 1302.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 923 | 6960.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 32487.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 2 | 001 | 3085.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 3280.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 14105.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 2 | 115 | 2553.35 | 2553.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 001 | 2537.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 503 | 11453.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 6415.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 003 | 300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 012 | 5177.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 115 | 2135.08 | 2135.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 010 | 2864.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 105 | 5800.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | -10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 923 | 7180.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 7150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 1375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 17338.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 101 | 27341.53 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 101 | 683.4 | 683.4 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 112 | 4100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 001 | 17875.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 2 |  | N | 8 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 108 | 5620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 019 | 689.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 019 | 16258.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2721 | 43761915201 |  | 2 | CPI | 1 | 101 | 8789 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2721 | 43761915201 |  | 2 | CPI | 2 | 007 | 32502.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2721 | 43761915201 |  | 2 | CPI | 3 | 024 | 7651.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 1 | 001 | 17144.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 2 | 010 | 20629.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2722 | 43761515201 |  | 2 | CPI | 3 | 012 | 4002.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 1 | 012 | 5727.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 923 | 2676.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 101 | 4406.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 101 | 1756.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2735 | 44119515201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 10088.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 9555.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 2 | 923 | -10088.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 3 | 112 | 28655.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 533.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 482 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 3050 | 3050 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2761 | 43934515201 |  | 2 | CPI | 1 | 113 | 1512.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2761 | 43934515201 |  | 2 | CPI | 2 | 004 | 2365 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2761 | 43934515201 |  | 2 | CPI | 1 | 001 | 2176.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2761 | 43934515201 |  | 2 | CPI | 2 | 118 | 250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 3000 | 12169.21 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 14000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 10000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 2 | 115 | 5158.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 001 | 5436.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O87 | 42820825201 |  | 2 | CPI | 2 | 115 | 5158.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 3 | 101 | 1475.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3Q54 | 22253925201 |  | 2 | CPI | 1 | 001 | 12310.59 | 8260 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q54 | 22253925201 |  | 2 | CPI | 1 | 923 | 727.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R03 | 41343525201 |  | 2 | CPI | 1 | 503 | 3014 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 012 | 12225.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R51 | 22023625201 |  | 2 | CPI | 2 | 012 | 4330.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R51 | 22023625201 |  | 2 | CPI | 3 | 128 | 14324.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 4 | 117 | 987.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 503 | 15630.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 117 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3R70 | 43814115201 |  | 2 | CPI | 1 | 503 | 7012.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 012 | 1773.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 107 | 16000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3R78 | 43813815201 |  | 2 | CPI | 1 | 004 | 3060.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3S03 | 43775215201 |  | 2 | CPI | 1 | 101 | 13602.6 | 9443.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3663 | 43188345201 |  | 2 | CPI | 1 | 107 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3663 | 43188345201 |  | 2 | CPI | 1 | 107 | -1350 | -1134 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
03 | T3663 | 43188345201 |  | 2 | CPI | 2 | 107 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3695 | 43775415201 |  | 2 | CPI | 1 | 105 | 4175.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 004 | 26400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 122 | 11699 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4N82 | 22777515201 |  | 2 | CPI | 3 | 007 | 5775 | 5775 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 25943.5 | 7700 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 6000 | 6000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 007 | 5720 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 024 | 992.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 024 | 1571.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 5257.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 007 | 4400.3 | 4400.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 023 | 4133.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 2890.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 015 | 17798 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 106 | 270.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 8538.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 2419.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 14610.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 2 | 015 | 3398.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T46 | 43388815201 |  | 2 | CPI | 1 | 024 | 4642.4 | 4642.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 007 | 6187.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 123 | 822 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 123 | 6825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 2 | 123 | 825.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 007 | 4837.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T56 | 43578125201 |  | 2 | CPI | 1 | 112 | 8903.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T56 | 43578125201 |  | 2 | CPI | 1 | 101 | 1870.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T56 | 43578125201 |  | 2 | CPI | 2 | 001 | 36888.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 2066.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 115 | 4643.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 5945.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 12280.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 105 | 3113.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 003 | 2409 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 545.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 12344.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 3920.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 023 | 1259.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793725202 |  | 2 | CPI | 2 | 023 | 805.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 108 | 3307.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 26110.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 27326.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 3 | 023 | 15493.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 007 | 213.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 023 | 314.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 116 | 3388 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 007 | 9153.86 | 9153.86 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 3991.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793725202 |  | 2 | CPI | 1 | 108 | 1574.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 021 | 4305.18 | 4305.18 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 2 | 021 | 4665.5 | 4665.5 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 3 | 021 | 3021.81 | 3021.81 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 021 | 3208 | 3208 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 2 | 023 | 935.97 | 935.97 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 3 | 023 | 5068 | 5068 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 101 | 2472.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 023 | 5694.93 | 5694.93 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4479 | 43059025201 |  | 2 | CPI | 1 | 118 | 1969.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008415201 |  | 2 | CPI | 1 | 118 | 3733.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008415201 |  | 2 | CPI | 1 | 118 | 1044.62 | 1044.62 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008515201 |  | 2 | CPI | 1 | 106 | 3638.7 | 3638.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 106 | 1064.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 105 | 445.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 024 | 7907.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 2 | 503 | 5506.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 112 | 6121.07 | 6121.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 105 | 6791.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 128 | 2716.96 | 2716.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 106 | 8811.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 3 | 001 | 925.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 128 | 12459.64 | 12459.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 003 | 2948.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 115 | 1185.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 001 | 768.76 | 768.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 001 | 4035.29 | 4035.29 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 112 | 1637.22 | 1637.22 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4496 | 43288335201 |  | 2 | CPI | 2 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 007 | 1782.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 105 | 286.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 001 | 18472.1 | 18472.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 108 | 3789.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 007 | 754.95 | 754.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 001 | 1613.37 | 1613.37 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 106 | 193.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 005 | 8590.45 | 8590.45 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 122 | 39495.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 001 | 106.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 024 | 3707.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 023 | 3357.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4503 | 43611115201 |  | 2 | CPI | 3 | 024 | 1463.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 001 | 8856.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 001 | 12705 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 503 | 3935.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 503 | 2330.49 | 2330.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 108 | 4258.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 108 | 1248.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 108 | 7227.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4507 | 43771815201 |  | 2 | CPI | 1 | 101 | 6506.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4507 | 43771815201 |  | 2 | CPI | 1 | 112 | 1094.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4520 | 43770215201 |  | 2 | CPI | 1 | 106 | 12605.27 | 12605.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4520 | 43770215201 |  | 2 | CPI | 1 | 003 | 1689.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4540 | 43834515201 |  | 2 | CPI | 1 | 112 | 470.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 003 | 17568.1 | 17568.1 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 003 | 7550.4 | 25118.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 012 | 2799.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 107 | 420 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 023 | 8018.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 104 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 234 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 118 | 143 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 3 | 021 | 2845.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 494 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 312 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 728 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 286 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 598 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 884 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 624 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 416 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 503 | 4634.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 4455.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 012 | 1091.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z30 | 43952115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 018 | 3451.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 107 | 33500.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 107 | 9500.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 112 | 3547.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z77 | 43912115201 |  | 2 | CPI | 1 | 012 | 9663.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z77 | 43912115201 |  | 2 | CPI | 1 | 012 | 13545.33 | 13545.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 001 | 4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | -11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | 4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 115 | 19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | -11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | -4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 115 | -19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 106 | 1949.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 106 | 1114.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 106 | 1558.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 4 | 106 | 3140.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215601 |  | 2 | CPI | 1 | 015 | 1141.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215601 |  | 2 | CPI | 2 | 015 | 16268.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 108 | 1189.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 108 | 1789.26 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 101 | 2359.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 112 | 2001.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 112 | 1639.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 128 | 11744.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 001 | 5722.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 117 | 3437.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 119 | 2751.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 112 | 1377.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 107 | 1443.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 4 | 503 | 7375.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5530 | 23968215201 |  | 2 | CPI | 5 | 003 | 3353.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5530 | 23968215601 |  | 2 | CPI | 1 | 015 | 2589.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 108 | 5274.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 117 | 6350.74 | 8905.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | 1077.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 8895.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 003 | 2145 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 11221.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 105 | 4348.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 001 | 5087.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 108 | 14022.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 007 | 737 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5590 | 42690535201 |  | 2 | CPI | 2 | 108 | 6557.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 3 | 106 | 5622.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 4 | 108 | 5882.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 105 | 37534.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 2 | 004 | 10206.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 9579.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 30081.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 106 | 2500 | 2500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5604 | 43734515201 |  | 2 | CPI | 1 | 503 | 4561.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5604 | 43734515201 |  | 2 | CPI | 2 | 503 | 4561.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5604 | 43734515201 |  | 2 | CPI | 1 | 023 | 7577.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5615 | 43793115201 |  | 2 | CPI | 1 | 106 | 450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5615 | 43793115201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 106 | 14234.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 113 | 5470.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 012 | 99294.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 108 | 2854.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 2 | 107 | 5414.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 3 | 001 | 3192.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5629 | 43759215201 |  | 2 | CPI | 4 | 115 | 3912.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 5 | 018 | 667.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 106 | 2947.5 | 2947.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 105 | 4977.3 | 1322.3 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 503 | 11770.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 101 | 28850.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 2 | 024 | 10777.02 | 10777.02 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 3 | 024 | 7926.68 | 7926.68 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 101 | 28850.1 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 024 | 0 | 10777.02 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 024 | 0 | 7926.68 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 101 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 118 | 17161.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 112 | 1763.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 2 | 101 | 5040 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 023 | 3456.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 101 | 1936.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 012 | 2898.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5661 | 43968225201 |  | 2 | CPI | 2 | 012 | 825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 101 | 645.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 012 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5677 | 43923315201 |  | 2 | CPI | 1 | 004 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K57 | 43854015201 |  | 2 | CPI | 1 | 503 | 30012.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K86 | 43653215201 |  | 2 | CPI | 1 | 108 | 569.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6K86 | 43653215201 |  | 2 | CPI | 1 | 012 | 21689.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L73 | 44183715201 |  | 2 | CPI | 1 | 118 | 3830.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L73 | 44183715201 |  | 2 | CPI | 1 | 118 | 2413.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L73 | 44183715201 |  | 2 | CPI | 2 | 101 | 7079.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 14416.8 | 14416.8 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 6050.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 1 | 503 | 2092.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 2 | 503 | 3273.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 1 | 503 | 1986.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 |  | 2 | CPI | 1 | 115 | 16778.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6420 | 43345515201 |  | 2 | CPI | 2 | 503 | 9291.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 |  | 2 | CPI | 2 | 503 | 7900.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 |  | 2 | CPI | 3 | 001 | 7655 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345515201 |  | 2 | CPI | 1 | 001 | 2848.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345525201 |  | 2 | CPI | 1 | 001 | 2349.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345525201 |  | 2 | CPI | 1 | 118 | 747.53 | 747.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 105 | 36378.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 105 | 9706.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 115 | 9362.94 | 9362.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 107 | 7701.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 012 | 5508.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 107 | 2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 001 | 16495.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 |  | 2 | CPI | 2 | 105 | 2540.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | 4161 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 001 | 3221.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 |  | 2 | CPI | 2 | 112 | 11962.36 | 11962.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 3 | 004 | 3191.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | 27668 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 2 | 022 | 2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 3 | 004 | 2312.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | -27668 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 2 | 101 | 27688 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 3 | 107 | -2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 4 | 107 | 2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 5 | 022 | -2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 022 | 2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 105 | 1273.66 | 1273.66 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 001 | 2547.31 | 2547.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 001 | 3850.04 | 3850.04 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 004 | 18901.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 012 | 3329.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 023 | 2497.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 023 | 4289.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925202 |  | 2 | CPI | 1 | 118 | 7784.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 023 | -4289.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 023 | 4289.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925202 |  | 2 | CPI | 1 | 118 | 3765.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 123 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 2988.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 2 | 010 | 2106.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6441 | 43117035201 |  | 2 | CPI | 1 | 503 | 9360.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 7668.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 564.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 012 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 016 | 22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 019 | 1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | 10000 | 10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | -10000 | -10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | 10000 | 10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 4143.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 106 | 4309.28 | 4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 503 | 3440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 004 | 11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 546.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 2 | 015 | 41610.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 003 | 5640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 016 | -22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 3 | 106 | -4309.28 | -4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 4 | 019 | -1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 5 | 004 | -11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 115 | 5377.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 016 | 22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 3 | 106 | 4309.28 | 4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 4 | 019 | 1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 5 | 004 | 11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | -8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 2 | 015 | 17233.53 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 503 | 19417.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 004 | 15272.5 | 15272.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6457 | 44018815201 |  | 2 | CPI | 1 | 004 | 9205.18 | 9205.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6459 | 44018015201 |  | 2 | CPI | 1 | 116 | 3985.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6459 | 44018015201 |  | 2 | CPI | 1 | 116 | 6208 | 6208 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6459 | 44018625201 |  | 2 | CPI | 1 | 503 | 1217.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6470 | 43991715201 |  | 2 | CPI | 1 | 007 | 3064.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6470 | 43991715201 |  | 2 | CPI | 2 | 001 | 2147.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6470 | 43991715201 |  | 2 | CPI | 3 | 007 | 1224 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6477 | 44297115201 |  | 2 | CPI | 1 | 010 | 4183.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 101 | 3960 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44319715201 |  | 2 | CPI | 1 | 012 | 994.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6477 | 44357015201 |  | 2 | CPI | 1 | 012 | 3874.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 007 | 4322.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 101 | 6951.93 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 2 | 007 | 30256.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 502 | 2310 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 502 | 39433.12 | 39433.12 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 3 | 502 | 0 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 4 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M31 | 43751715201 |  | 2 | CPI | 5 | 012 | 10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | -10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | 11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | 11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 2 | 013 | 10255.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | -11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7N03 | 43673425201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N03 | 43673425201 |  | 2 | CPI | 2 | 004 | 9503.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N04 | 44580315201 |  | 2 | CPI | 1 | 503 | 3614.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7N04 | 44580315201 |  | 2 | CPI | 2 | 118 | 7998.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 001 | 24315.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 122 | 4059.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 122 | 2531.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 2 | 112 | 62068.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | -62068.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 2 | 112 | 28651.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | 33416.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815202 |  | 2 | CPI | 1 | 101 | 22000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 001 | 2636.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815202 |  | 2 | CPI | 1 | 106 | 8000 | 8000 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 004 | 4778.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 001 | 15523.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 001 | 2525.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 012 | 4215.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 101 | 20229.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 101 | 4968.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 012 | 2282.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 105 | 5875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | 9175 | 3300 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | -9175 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 2 | 009 | 5875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 105 | 13844.62 | 13844.62 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7411 | 43982925201 |  | 2 | CPI | 2 | 009 | 3300 | 3300 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 1 |  | N | 45 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 3 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 012 | 2562.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 108 | 9128.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 001 | 1480.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 001 | 470.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 3 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 012 | 14993.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 113 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 130 | 40338.27 | 40338.27 | 2 |  | N | 0 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 2 |  | N | 19 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 923 | 5734.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 012 | 31824.96 | 31824.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | C | 100 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7426 | 43648715201 |  | 2 | CPI | 1 | 115 | 7738.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7426 | 43648715201 |  | 2 | CPI | 2 | 113 | 3637.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 008 | 20000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 107 | 3652 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 3066.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 2743.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 2 | 503 | 1381.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 |  | 2 | CPI | 3 | 012 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 4 | 012 | 2032.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 5 | 012 | 4231.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 445.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 8767 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 2 | 012 | 942.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 477.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4494.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4945.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4121.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 2707.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 5764.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 9857.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 9295.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 5476.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 6578.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 007 | 3038.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 023 | 1412.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 3 | 004 | 1713.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 6047.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 012 | 1296.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 007 | 4673.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 107 | 28952 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 503 | 25375.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 012 | 5940 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 113 | 15657.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 113 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 4502.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 023 | 2874.61 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611025201 |  | 2 | CPI | 1 | 003 | 25801.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611025201 |  | 2 | CPI | 1 | 023 | 3741.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 012 | 3012.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 107 | 15814.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | 8970.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | -8970.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 001 | 2100.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 021 | 2823.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 4 | 023 | 2854.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 5 | 012 | 1191.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 003 | 10825.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 012 | 7840 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 001 | 1068.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 018 | 19261.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 4 | 018 | 6420.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 023 | 2069.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 107 | 3090.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 023 | 12436.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 003 | 56690.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 018 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 021 | 8272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 503 | 1957.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 021 | 4310.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 6439.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 118 | 13581.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 5288.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 023 | 2184.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 012 | 1019.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 106 | 1834.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 012 | 2303.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 003 | 3453.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 6376.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 503 | 1099.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 023 | 3986.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 112 | 12956.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 019 | 15740.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 115 | 3871.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 112 | 1485.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 107 | 10966.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 023 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 6382.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 115 | 5387.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 003 | 4994.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 106 | 13325.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 105 | 1888.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 118 | 2640.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 9860.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 54604.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 35140.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516935201 |  | 2 | CPI | 1 | 101 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q53 | 43516935201 |  | 2 | CPI | 2 | 012 | 3085.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516935201 |  | 2 | CPI | 1 | 112 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 021 | 11873.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947815201 |  | 2 | CPI | 2 | 021 | 13850.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 023 | 12245.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947815202 |  | 2 | CPI | 1 | 023 | 9318.67 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 021 | 11108.89 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 021 | 1707.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947915201 |  | 2 | CPI | 3 | 023 | 13071.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 021 | 1912.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 023 | 19853.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 118 | 8441.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 118 | 11189.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 118 | 6082.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 5250.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 2 | 101 | 5013.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 1192.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 1386.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 2 | 503 | 2600.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 34557.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 |  | 2 | CPI | 1 | 101 | 330 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R53 | 44130615201 |  | 2 | CPI | 2 | 101 | 38.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 012 | 87443.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 107 | 27366.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 107 | 10581.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R99 | 42897115201 |  | 2 | CPI | 1 | 010 | 4163.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R99 | 42897115201 |  | 2 | CPI | 2 | 105 | 4062.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R99 | 42897115201 |  | 2 | CPI | 1 | 023 | 1932.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P44 | 43797315201 | 924 |  | 22 | 061 | 1 | 0 | N | Unavoidable, No Remedial Action Required
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1R05 | 43629915201 | 001 |  | 72 | 044 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R78 | 43502915201 | 924 |  | 49 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R81 | 43528615201 | 005 |  | 40 | 002 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1R86 | 44108815201 | 924 |  | 43 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 22 | 011 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 30 | 014 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 42 | 016 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 28 | 020 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 16 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 023 |  | 15 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2726 | 43583715201 | 005 |  | 18 | 018 | 1 | 5 | C | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2726 | 43583715201 | 325 |  | 14 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | T2726 | 43583715201 | 106 |  | 12 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3O87 | 42820825201 | 106 |  | 47 | 013 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3O87 | 42820825201 | 115 |  | 14 | 024 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 | 118 |  | 12 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | E3R03 | 41343525201 | 005 |  | 38 | 009 | 1 | 1 | C | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 005 |  | -4 | 012 | 1 | 1 | C | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
03 | T3585 | 43228515201 | 503 |  | 30 | 014 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3585 | 43228515201 | 126 |  | 16 | 019 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3585 | 43228515201 | 128 |  | 2 | 020 | 1 | 2 | N | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3585 | 43228515201 | 503 |  | 12 | 021 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3585 | 43228515201 | 126 |  | 8 | 023 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3619 | 43390215201 | 016 |  | 10 | 012 | 1 | 2 | N | Avoidable, In-House Designer | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | T3619 | 43390215201 | 130 |  | 15 | 013 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
03 | T3663 | 43188345201 | 003 |  | 2 | 004 | 1 | 2 | N | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3663 | 43188345201 | 128 |  | 3 | 007 | 1 | 1 | N | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3663 | 43188345201 | 012 |  | 10 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3695 | 43775415201 | 503 |  | 40 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3708 | 43662015201 | 115 |  | 20 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3739 | 44173715201 | 503 |  | 4 | 002 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T46 | 43388815201 | 105 |  | 40 | 015 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T46 | 43388815201 | 924 |  | 45 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T54 | 42957525201 | 005 |  | 15 | 010 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 924 |  | 35 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 924 |  | 17 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 118 |  | 5 | 017 | 1 | 5 | N | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T56 | 43578125201 | 005 |  | 12 | 014 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T56 | 43578125201 | 001 |  | 10 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T56 | 43578125201 | 022 |  | 12 | 019 | 1 | 5 | N | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4473 | 42751615201 | 023 |  | 6 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4473 | 42751615201 | 023 |  | 6 | 039 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4479 | 43059025201 | 924 |  | 52 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4483 | 44008115201 | 019 |  | 30 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4496 | 43288335201 | 005 |  | 12 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4503 | 43611115201 | 106 |  | 13 | 015 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4503 | 43611115201 | 009 |  | 14 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | T4503 | 43611115201 | 108 |  | 12 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4520 | 43770215201 | 924 |  | 27 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z68 | 44096915201 | 105 |  | 3 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z68 | 44096915201 | 012 |  | 4 | 022 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z68 | 44096915201 | 130 |  | 15 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
05 | T5629 | 43759215201 | 004 |  | 42 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K57 | 43854015201 | 924 |  | 65 | 045 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6M59 | 43634425201 | 401 |  | 9 | 002 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
06 | T6425 | 42597925201 | 012 |  | 30 | 033 | 1 | 1 | N | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
06 | T6457 | 44018415201 | 009 |  | 45 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6459 | 44018715201 | 924 |  | 30 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | E7M74 | 43955115201 | 925 |  | 2 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8M65 | 40609615201 | 503 |  | 405 | 125 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 503 |  | 22 | 062 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q94 | 43947815201 | 503 |  | 1 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q94 | 43947815201 | 503 |  | 1 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q94 | 43947815201 | 503 |  | 5 | 053 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 1353 | 15508 | 22 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 9 | 01co | 1 | 9
01CO | 01 | T1675 | 43088715201 | 2017-08-30 | QTR1 | 17/18 | 3 | 3 | 150 | 282 | 282 | 0 | 0 | 0 | 57 | 75 | 815194 | 35094 | 780100 | 856566 | 821472 | 0 | 0 | 0 | 821472 | 822481 | 1009 | 41372 | 36 | 0 | 0 | -1090 | 868 | 0 | 72 | 48111 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 41372 | 31652 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 | 2019-03-21 | QTR3 | 18/19 | 113 | 783433.16 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 12 | 01do | 10 | 21
01CO | 01 | T1702 | 43509015201 | 2018-02-28 | QTR3 | 17/18 | 2 | 2 | 240 | 285 | 282 | 3 | 0 | 0 | 45 | 0 | 2098354 | 50000 | 2048354 | 2203054 | 2035840 | 0 | 0 | 0 | 2035840 | 2034275 | -1565 | 104700 | 29 | 0 | 0 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104700 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-06 | QTR2 | 20/21 | 2019-04-29 | QTR4 | 18/19 | 115 | 2050385.52 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 14 | 02co | 22 | 35
01CO | 01 | T1742 | 43539015201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 350 | 433 | 402 | 31 | 0 | 0 | 83 | 0 | 3732644 | 50000 | 3682644 | 3755256 | 3738358 | 0 | 0 | 0 | 3738358 | 3735826 | -2532 | 22611 | 53 | 0 | 0 | 12441 | 12441 | 0 | 0 | 13919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26360 | 12441 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 | 2020-10-30 | QTR2 | 20/21 | 113 | 3397781.79 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO | 4 | 02do | 36 | 39
01CO | 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2100 | 10 | 0 | 3 | 2846 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4946 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 9 | 03co | 40 | 48
01CO | 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 3200 | 16 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 14 | 03do | 49 | 62
01CO | 01 | T1758 | 43943715201 | 2019-07-31 | QTR1 | 19/20 | 2 | 2 | 265 | 288 | 219 | 69 | 0 | 0 | 22 | 1 | 7004551 | 95304 | 6909247 | 7119832 | 7259276 | 0 | 0 | 0 | 7259276 | 7106733 | -152543 | 115281 | 17 | 0 | 1 | 114321 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 115281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-08-10 | QTR1 | 20/21 | 108 | 9375095.25 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 12 | 04co | 63 | 74
01CO | 01 | T1773 | 44067215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 75 | 83 | 70 | 13 | 0 | 0 | 8 | 0 | 214731 | 9756 | 204975 | 214731 | 194639 | 0 | 0 | 0 | 194639 | 194639 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-08-21 | QTR1 | 20/21 | 108 | 215733.31 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 8 | 04do | 75 | 82
01CO | 01 | T1997 | 40828665201 | 2017-01-25 | QTR3 | 16/17 | 2 | 11 | 1100 | 1215 | 1201 | 14 | 0 | 0 | 115 | 0 | 58011809 | 150000 | 57861809 | 58671616 | 58073269 | 0 | 0 | 0 | 58073269 | 59258196 | 1257928 | 659807 | 51 | 0 | 0 | 424487 | 0 | 0 | 0 | 290901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603216 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 | 2020-08-13 | QTR1 | 20/21 | 118 | 69879385.2 |  |  | 0 | 64 | 0 | 0 | -143938 | 0 |  | CO | 12 | 05co | 83 | 94
01DO | 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 355643 | 83 | 0 | 200 | 43207 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 423577 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 66 | 0 | 0 | 0 | 0 | T | DO | 13 | 05do | 95 | 107
01DO | 01 | E1P46 | 43580715201 | 2017-10-19 | QTR2 | 17/18 | 1 | 1 | 125 | 209 | 209 | 0 | 0 | 0 | 84 | 0 | 869954 | 43581 | 826373 | 869954 | 834474 | 0 | 0 | 0 | 834474 | 836068 | 1595 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2018-07-30 | QTR1 | 18/19 | 108 | 794913.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO | 9 | 06co | 108 | 116
01DO | 01 | E1R05 | 43629915201 | 2018-03-01 | QTR3 | 17/18 | 1 | 9 | 320 | 663 | 663 | 0 | 0 | 0 | 183 | 160 | 7996438 | 89923 | 7906515 | 8606992 | 8773391 | 0 | 0 | 0 | 8773391 | 8748736 | -916 | 610555 | 76 | 72 | 159 | 583162 | 0 | 0 | 1 | 13293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 160 | 596455 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-11-12 | QTR2 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 115 | 8160370.04 | B5 | ACC - INCENTIVE/DISINCENTIVE | 1 | 35 | 0 | 0 | 0 | 0 |  | DO | 7 | 06do | 117 | 123
01DO | 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | -259 | 29714 | 51 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO | 8 | 07co | 124 | 131
01DO | 01 | E1R78 | 43502915201 | 2019-03-21 | QTR3 | 18/19 | 1 | 0 | 100 | 164 | 166 | -2 | 2 | 0 | 64 | 0 | 982956 | 35636 | 947320 | 982956 | 953745 | -3330 | 0 | -3330 | 950415 | 950415 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-10-19 | QTR2 | 20/21 | 2020-06-07 | QTR4 | 19/20 | 113 | 837254.07 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | DO | 10 | 07do | 132 | 141
01DO | 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 142 | 141
01DO | 01 | E1R86 | 44108815201 | 2018-11-09 | QTR2 | 18/19 | 1 | 0 | 370 | 470 | 470 | 0 | 0 | 0 | 76 | 24 | 2469000 | 50000 | 2419000 | 2469000 | 2431659 | 0 | 0 | 0 | 2431659 | 2431659 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 113 | 3306921.72 | A3 | ICC - DESIGN/BUILD - MINOR | 24 | 27 | 0 | 0 | 0 | 0 |  | DO | 12 | 08do | 142 | 153
01DO | 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S13 | 44462715201 | 2020-01-16 | QTR3 | 19/20 | 1 | 1 | 130 | 168 | 130 | 38 | 0 | 0 | 36 | 2 | 993513 | 50000 | 943513 | 994797 | 930694 | 0 | 0 | 0 | 930694 | 928776 | -1919 | 1285 | 27 | 0 | 0 | 1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-10-01 | QTR2 | 20/21 | 108 | 1140044.02 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1S47 | 43997015201 | 2020-01-16 | QTR3 | 19/20 | 1 | 0 | 100 | 125 | 89 | 36 | 0 | 0 | 25 | 0 | 450312 | 27504 | 422808 | 450312 | 440733 | 0 | 0 | 0 | 440733 | 440733 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 115 | 480716.09 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S50 | 44525715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 0 | 45 | 53 | 51 | 2 | 0 | 0 | 8 | 0 | 279624 | 14400 | 265224 | 279624 | 287046 | 0 | 0 | 0 | 287046 | 287046 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 | 2020-07-30 | QTR1 | 20/21 | 108 | 268843.45 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 60614 | 12839 | 39 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28 |  |  | 18 | 74 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 100000 | 78 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17 |  |  | 30 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 42749 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 0 | 0 | 1 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 0 | 33 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-03 | QTR1 | 20/21 | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 579 | 100000 | 13 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | -3801 | 80075 | 21 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2735 | 44119515201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 100 | 142 | 142 | 0 | 0 | 0 | 13 | 29 | 421053 | 19914 | 401139 | 421053 | 394439 | 0 | 0 | 0 | 394439 | 394439 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-12-08 | QTR2 | 20/21 | 2020-05-26 | QTR4 | 19/20 | 208 | 428177.97 |  |  | 29 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-02-21 | QTR3 | 19/20 | 209 | 84351.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95 |  |  | 2 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2761 | 43934515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 180 | 215 | 211 | 4 | 0 | 0 | 35 | 0 | 4189603 | 51877 | 4137726 | 4189603 | 4189658 | 0 | 0 | 0 | 4189658 | 4163139 | -26519 | 0 | 30 | 0 | 0 | 4541 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6304 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-08-24 | QTR1 | 20/21 | 214 | 5262360.58 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2766 | 44348915201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 130 | 146 | 144 | 2 | 0 | 0 | 16 | 0 | 1081333 | 50000 | 1031333 | 1081333 | 1019859 | 0 | 0 | 0 | 1019859 | 1018371 | -1488 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-04 | QTR2 | 20/21 | 2020-06-16 | QTR4 | 19/20 | 214 | 1202483.05 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 1 | 460 | 671 | 891 | -220 | 220 | 0 | 207 | 4 | 17417591 | 200000 | 17217591 | 17434064 | 17148118 | -1033560 | 0 | -1033560 | 16114558 | 17365029 | 1266944 | 16473 | 97 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 92445 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97 |  |  | 4 | 110 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X06 | 43076015201 | 2018-04-18 | QTR4 | 17/18 | 1 | 2 | 190 | 489 | 545 | -56 | 56 | 0 | 248 | 51 | 2957443 | 50000 | 2907443 | 3057443 | 3046193 | -151872 | 0 | -151872 | 2894321 | 2894277 | -43 | 100000 | 19 | 0 | 44 | 94877 | 0 | 0 | 7 | 5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 51 | 100035 | 0 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 | 2020-02-14 | QTR3 | 19/20 | 208 | 2882464.65 |  |  | 51 | 76 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y25 | 43761715201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 250 | 365 | 351 | 14 | 0 | 0 | 99 | 16 | 5599368 | 63324 | 5536044 | 5599368 | 5849866 | 0 | 0 | 0 | 5849866 | 5819954 | -29911 | 0 | 48 | 0 | 0 | 2537 | 0 | 0 | 3 | 23074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 11453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 37064 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-05 | QTR2 | 20/21 | 2020-06-19 | QTR4 | 19/20 | 216 | 6362327.21 |  |  | 16 | 51 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 0 | 0 | 11 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26 |  |  | 4 | 1 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | -1395 | 58 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3619 | 43390215201 | 2018-11-14 | QTR2 | 18/19 | 1 | 1 | 175 | 253 | 248 | 5 | 0 | 0 | 72 | 6 | 1114410 | 0 | 1114410 | 1163460 | 1226323 | 0 | 0 | 0 | 1226323 | 1224530 | -1793 | 49050 | 34 | 10 | 6 | 49050 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | 49050 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2020-12-10 | QTR2 | 20/21 | 2019-10-07 | QTR2 | 19/20 | 313 | 1475964.98 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3642 | 43274025201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 250 | 555 | 555 | 0 | 0 | 0 | 305 | 0 | 8739221 | 84002 | 8655219 | 8879082 | 9063602 | -14091 | 0 | -14091 | 9049511 | 9512844 | 541744 | 139862 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 | 2019-07-11 | QTR1 | 19/20 | 314 | 8488154.79 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 3300 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3663 | 43188345201 | 2019-08-28 | QTR1 | 19/20 | 1 | 2 | 85 | 155 | 155 | 0 | 0 | 0 | 70 | 0 | 656987 | 29252 | 627735 | 668791 | 649887 | 0 | 0 | 0 | 649887 | 649887 | 0 | 11804 | 25 | 12 | 0 | 11597 | 2421 | 3 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 13154 | 2421 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-05-04 | QTR4 | 19/20 | 308 | 691494.24 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3668 | 43580015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 4 | 250 | 295 | 271 | 24 | 0 | 0 | 45 | 0 | 1427167 | 0 | 1427167 | 1429917 | 1395761 | 0 | 0 | 0 | 1395761 | 1394795 | -966 | 2750 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 | 2020-10-02 | QTR2 | 20/21 | 321 | 1392503.71 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3739 | 44173715201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 45 | 64 | 63 | 1 | 0 | 0 | 19 | 0 | 229048 | 6715 | 222333 | 236141 | 232144 | 0 | 0 | 0 | 232144 | 232144 | 0 | 7093 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 7093 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 | 2020-08-14 | QTR1 | 20/21 | 308 | 145096.15 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 251063 | 77 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P37 | 22280225201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 120 | 154 | 152 | 2 | 0 | 0 | 34 | 0 | 398582 | 35644 | 362938 | 398582 | 363870 | 0 | 0 | 0 | 363870 | 363870 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F811252530 | OMEGA COATINGS & CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 | 2019-11-24 | QTR2 | 19/20 | 313 | 733124 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q54 | 22253925201 | 2019-05-09 | QTR4 | 18/19 | 1 | 1 | 90 | 110 | 103 | 7 | 0 | 0 | 20 | 0 | 922444 | 50000 | 872444 | 846935 | 658266 | 0 | 0 | 0 | 658266 | 658266 | 0 | -75510 | 16 | 0 | 0 | 12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63199 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-05 | QTR2 | 20/21 | 2019-11-22 | QTR2 | 19/20 | 321 | 919379.25 |  |  | 0 | 4 | 0 | 0 | -75510 | 0 |  | DO
03DO | 03 | E3R03 | 41343525201 | 2018-05-10 | QTR4 | 17/18 | 4 | 9 | 210 | 403 | 403 | 0 | 0 | 0 | 165 | 28 | 1381327 | 50000 | 1331327 | 1468091 | 1381221 | -4783 | 0 | -4783 | 1376437 | 1365035 | -1916 | 86763 | 94 | 0 | 0 | 0 | 0 | 0 | 3 | 15065 | 1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 52304 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 34 | 28 | 80290 | 15961 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2019-09-13 | QTR1 | 19/20 | 308 | 1155000 |  |  | 2 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 158902 | 66 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94 |  |  | 6 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 273 | 280 | -7 | 7 | 0 | 49 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4457789 | -18984 | 0 | -18984 | 4438805 | 4364461 | -74345 | 123339 | 26 | 0 | 14 | 48949 | 0 | 0 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04 |  |  | 14 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R75 | 40731075201 | 2019-06-13 | QTR4 | 18/19 | 2 | 4 | 180 | 236 | 236 | 0 | 0 | 0 | 52 | 4 | 1896816 | 50000 | 1846816 | 2013742 | 1899113 | 0 | 0 | 0 | 1899113 | 1899113 | 0 | 116926 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 102982 | 7592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 116926 | 9300 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-10-07 | QTR2 | 20/21 | 2020-06-19 | QTR4 | 19/20 | 308 | 1645052.8 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R78 | 43813815201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 90 | 124 | 116 | 8 | 0 | 0 | 34 | 0 | 467023 | 24986 | 442037 | 467023 | 452193 | 0 | 0 | 0 | 452193 | 452193 | 0 | 0 | 27 | 0 | 0 | 3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 | 2020-08-03 | QTR1 | 20/21 | 314 | 567888.91 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R84 | 43736715201 | 2019-05-09 | QTR4 | 18/19 | 3 | 1 | 150 | 273 | 264 | 9 | 0 | 0 | 63 | 60 | 1890085 | 52035 | 1838050 | 1993510 | 1844667 | 0 | 0 | 0 | 1844667 | 1822661 | -22007 | 103425 | 27 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 313 | 1951315.61 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 42363 | 60 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S48 | 43973015201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 150 | 167 | 153 | 14 | 0 | 0 | 17 | 0 | 2362840 | 50000 | 2312840 | 2362840 | 2375062 | 0 | 0 | 0 | 2375062 | 2367596 | -7466 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-07-27 | QTR1 | 20/21 | 321 | 2687906.81 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S50 | 22253625201 | 2019-11-14 | QTR2 | 19/20 | 2 | 0 | 120 | 125 | 50 | 75 | 0 | 0 | 5 | 0 | 688910 | 0 | 688910 | 688910 | 677594 | 0 | 0 | 0 | 677594 | 677594 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2020-04-06 | QTR4 | 19/20 | 321 | 1158620.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 233861 | 985075 | 115 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22 |  |  | 14 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4473 | 42751615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 4 | 335 | 483 | 483 | 0 | 0 | 0 | 148 | 0 | 14954960 | 127766 | 14827195 | 14788864 | 14238463 | 0 | 0 | 0 | 14238463 | 14552841 | 324737 | -166097 | 91 | 0 | 0 | 144864 | 0 | 0 | 0 | 5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 26899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -147083 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 | 2020-02-06 | QTR3 | 19/20 | 409 | 12073779.82 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 45 | 0 | 0 | -324121 | 0 |  | CO
04CO | 04 | T4479 | 43059025201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 179 | 294 | 294 | 0 | 0 | 0 | 115 | 0 | 815678 | 34169 | 781510 | 823050 | 757384 | 0 | 0 | 0 | 757384 | 756711 | -673 | 7371 | 93 | 0 | 0 | 7371 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9340 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 | 2020-06-16 | QTR4 | 19/20 | 412 | 726059.56 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | -253 | 22625 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4489 | 43770115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 3 | 350 | 447 | 437 | 10 | 0 | 0 | 97 | 0 | 5985000 | 64375 | 5920625 | 6208144 | 6389050 | 0 | 0 | 0 | 6389050 | 6213547 | -39102 | 223144 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 88252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506 | 0 | 0 | 0 | 7907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101665 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-07-02 | QTR1 | 20/21 | 408 | 6481016.05 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | -14110 | 229825 | 55 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | -2608 | 349724 | 45 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 103884 | 25 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65 |  |  | 15 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4503 | 43611115201 | 2019-01-30 | QTR3 | 18/19 | 2 | 3 | 205 | 289 | 289 | 0 | 0 | 0 | 84 | 0 | 2257891 | 50000 | 2207891 | 2372485 | 2277661 | 0 | 0 | 0 | 2277661 | 2279759 | 2097 | 114594 | 40 | 14 | 0 | 21562 | 0 | 25 | 0 | 100250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6266 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 136606 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 412 | 2312700.41 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | -62 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4520 | 43770215201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 136 | 238 | 235 | 3 | 0 | 0 | 102 | 0 | 511111 | 24274 | 486837 | 511111 | 500925 | 0 | 0 | 0 | 500925 | 500762 | -163 | 0 | 96 | 0 | 0 | 1690 | 0 | 0 | 0 | 12605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14295 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 | 2020-08-27 | QTR1 | 20/21 | 412 | 517002.15 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 0 | 16665 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | -998657 | 1434680 | 296 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 11 | 112 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 0 | 107565 | 96 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T54 | 42957525201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 158 | 281 | 242 | 39 | 0 | 0 | 123 | 0 | 1034836 | 50000 | 984836 | 1034836 | 958378 | 0 | 0 | 0 | 958378 | 958293 | -85 | 0 | 81 | 0 | 0 | 11025 | 0 | 5 | 0 | 8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 19498 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 412 | 1135394.39 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T56 | 43578125201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 203 | 306 | 306 | 0 | 0 | 0 | 103 | 0 | 1488175 | 50000 | 1438175 | 1499756 | 1508806 | 0 | 0 | 0 | 1508806 | 1504997 | -3808 | 11580 | 44 | 10 | 0 | 36888 | 0 | 0 | 0 | 10773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 11580 | 11580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 59242 | 11580 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 412 | 1272541.13 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T84 | 43389615201 | 2019-12-06 | QTR2 | 19/20 | 1 | 1 | 80 | 91 | 91 | 0 | 0 | 0 | 26 | -15 | 802818 | 31559 | 771259 | 802818 | 776329 | 0 | 0 | 0 | 776329 | 776329 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 | 2020-11-06 | QTR2 | 20/21 | 409 | 659386.45 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T92 | 44140915201 | 2020-01-17 | QTR3 | 19/20 | 1 | 1 | 130 | 156 | 131 | 25 | 0 | 0 | 26 | 0 | 888985 | 50000 | 838985 | 900166 | 850166 | 0 | 0 | 0 | 850166 | 838985 | 0 | 11181 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-09 | QTR2 | 20/21 | 2020-11-14 | QTR2 | 20/21 | 408 | 1308480 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | -797738 | 2915022 | 79 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06 |  |  | 0 | 65 | 0 | 0 | -178687 | 0 |  | CO
05CO | 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | -284799 | 843098 | 69 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 51986 | 59 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41 |  |  | 4 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | -24609 | 54891 | 45 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5615 | 43793115201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 200 | 438 | 665 | -227 | 227 | 0 | 47 | 191 | 1435273 | 48389 | 1386883 | 1466273 | 1433905 | -119880 | 0 | -119880 | 1314025 | 1313837 | -188 | 31000 | 20 | 0 | 0 | 0 | 0 | 0 | 15 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 31450 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-04-13 | QTR4 | 19/20 | 507 | 1578332.97 |  |  | 15 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | -94321 | 93683 | 136 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 512 | 0 |  |  | 7 | 54 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | -2583 | 3778 | 20 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9 |  |  | 35 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | -92470 | 42528 | 52 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5634 | 43734815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 350 | 469 | 469 | 0 | 0 | 0 | 104 | 15 | 7052425 | 108401 | 6944024 | 7232569 | 7465970 | 0 | 0 | 0 | 7465970 | 7453020 | -10558 | 180144 | 49 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 | 2020-07-26 | QTR1 | 20/21 | 515 | 10311527.59 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | -49387 | 3208 | 82 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5677 | 43923315201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 160 | 196 | 195 | 1 | 0 | 0 | 36 | 0 | 6452955 | 68620 | 6384335 | 6597931 | 6823659 | 0 | 0 | 0 | 6823659 | 6790182 | -33477 | 144976 | 26 | 0 | 0 | 4727 | 0 | 0 | 0 | 144976 | 9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149703 | 9705 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-30 | QTR2 | 20/21 | 2020-09-23 | QTR1 | 20/21 | 514 | 7161772.24 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5Y62 | 23831925201 | 2017-03-21 | QTR3 | 16/17 | 3 | 6 | 950 | 1198 | 1188 | 10 | 0 | 0 | 145 | 103 | 22219000 | 150000 | 22069000 | 22351916 | 22222555 | 0 | 0 | 0 | 22222555 | 22255595 | 54139 | 132916 | 69 | 0 | 0 | 40787 | 0 | 0 | 0 | 90621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 14091 | 0 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 156363 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2020-10-30 | QTR2 | 20/21 | 2020-09-14 | QTR1 | 20/21 | 515 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR | 1 | 76 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z19 | 43927315201 | 2018-04-03 | QTR4 | 17/18 | 1 | 0 | 130 | 145 | 501 | -356 | 356 | 0 | 15 | 0 | 149935 | 9480 | 140455 | 149935 | 128601 | -51092 | 0 | -51092 | 77509 | 77509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-05-27 | QTR4 | 19/20 | 513 | 204099 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 0 | 10 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8 |  |  | 8 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2019-10-17 | QTR2 | 19/20 | 513 | 307382 |  |  | 19 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z64 | 44121015201 | 2018-08-07 | QTR1 | 18/19 | 2 | 7 | 420 | 552 | 552 | 0 | 0 | 0 | 86 | 46 | 4022402 | 50000 | 3972402 | 4286073 | 4275710 | 0 | 0 | 0 | 4275710 | 4234199 | -37972 | 263671 | 31 | 0 | 0 | 124080 | 0 | 0 | 46 | 104836 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40146 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 274759 | 14901 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-07-07 | QTR1 | 20/21 | 513 | 4100417.85 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | -199 | 4115 | 84 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z77 | 43912115201 | 2019-07-02 | QTR1 | 19/20 | 2 | 1 | 200 | 327 | 326 | 1 | 0 | 0 | 127 | 0 | 3278490 | 50000 | 3228490 | 3271086 | 3476815 | 0 | 0 | 0 | 3476815 | 3410719 | -66096 | -7404 | 72 | 0 | 0 | 23209 | 0 | 0 | 0 | -7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15805 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-08-17 | QTR1 | 20/21 | 513 | 3806383.67 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-08-11 | QTR1 | 20/21 | 513 | 141232 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z91 | 43912215201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 115 | 121 | 120 | 1 | 0 | 0 | 6 | 0 | 1447000 | 50000 | 1397000 | 1447000 | 1407072 | 0 | 0 | 0 | 1407072 | 1407072 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-05-19 | QTR4 | 19/20 | 509 | 1302060.71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z98 | 43618725201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 90 | 124 | 125 | -1 | 1 | 0 | 34 | 0 | 675628 | 31129 | 644499 | 675628 | 649188 | 0 | 0 | 0 | 649188 | 649188 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2020-11-25 | QTR2 | 20/21 | 2020-08-13 | QTR1 | 20/21 | 514 | 631570 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | -289635 | -403730 | 22 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 17 | 0 | 0 | -453468 | 0 |  | CO
06CO | 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | -2140213 | 1115676 | 16 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 96399 | 60 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | -201766 | 12198 | 24 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6442 | 43063735201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 419 | 517 | 474 | 43 | 0 | 0 | 58 | 40 | 12892744 | 274969 | 12617775 | 13383683 | 13072251 | 0 | 790000 | 790000 | 13862251 | 12904020 | -845455 | 490939 | 35 | 0 | 40 | 504378 | 375054 | 0 | 0 | 22795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 550031 | 375054 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 606 | 14924931.96 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 0 | 77 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 27177 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | -846 | 30818 | 24 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6477 | 44281315201 | 2019-03-27 | QTR3 | 18/19 | 9 | 4 | 360 | 432 | 432 | 0 | 0 | 0 | 54 | 18 | 2060596 | 50000 | 2010596 | 2075271 | 2107347 | 0 | 0 | 0 | 2107347 | 2106923 | -424 | 14675 | 29 | 0 | 18 | 4869 | 0 | 0 | 0 | 15072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 27688 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2020-12-14 | QTR2 | 20/21 | 2020-10-09 | QTR2 | 20/21 | 606 | 2038302.5 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K57 | 43854015201 | 2017-05-15 | QTR4 | 16/17 | 1 | 0 | 750 | 1065 | 881 | 184 | 0 | 0 | 315 | 0 | 3582848 | 50000 | 3532848 | 3582848 | 3528511 | 0 | 0 | 0 | 3528511 | 3528511 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-10-23 | QTR2 | 20/21 | 2020-09-09 | QTR1 | 20/21 | 606 | 3999000 | LBDB | LOW BID DESIGN BUILD | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 0 | 139878 | 27 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L73 | 44183715201 | 2019-03-28 | QTR3 | 18/19 | 3 | 0 | 180 | 256 | 253 | 3 | 0 | 0 | 76 | 0 | 1046629 | 50000 | 996629 | 1046629 | 1032137 | 0 | 0 | 0 | 1032137 | 1030814 | -1322 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 613 | 1027325.45 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L77 | 44059015201 | 2019-02-28 | QTR3 | 18/19 | 1 | 0 | 150 | 227 | 212 | 15 | 0 | 0 | 77 | 0 | 569569 | 25452 | 544117 | 569569 | 532425 | 0 | 0 | 0 | 532425 | 532327 | -98 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 | 2020-08-04 | QTR1 | 20/21 | 613 | 521617.9 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | -189 | -1000 | 35 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M59 | 43634425201 | 2020-02-27 | QTR3 | 19/20 | 1 | 0 | 100 | 124 | 124 | 0 | 0 | 0 | 24 | 0 | 548409 | 24409 | 524000 | 548409 | 466503 | 0 | 0 | 0 | 466503 | 466503 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 | 2020-10-10 | QTR2 | 20/21 | 636 | 490515.2 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7403 | 43484815201 | 2018-05-23 | QTR4 | 17/18 | 4 | 11 | 365 | 520 | 520 | 0 | 0 | 0 | 106 | 49 | 15246325 | 150000 | 15096325 | 16369545 | 16674514 | 0 | 0 | 0 | 16674514 | 16720307 | 65791 | 1123220 | 63 | 0 | 14 | 656978 | 126004 | 0 | 35 | 570684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28923 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1198739 | 126713 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 | 2020-03-24 | QTR3 | 19/20 | 796 | 16929302.14 |  |  | 10 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 688152 | 70 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 0 | 91 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8 |  |  | 45 | 73 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7413 | 43658815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 480 | 699 | 697 | 2 | 0 | 0 | 200 | 19 | 26892177 | 150000 | 26742177 | 27245569 | 27594120 | -41000 | 0 | -41000 | 27553120 | 27404700 | -148420 | 353392 | 151 | 0 | 0 | 138794 | 0 | 0 | 19 | 407728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 422365 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-12-30 | QTR2 | 20/21 | 2020-08-27 | QTR1 | 20/21 | 714 | 31660666.96 |  |  | 19 | 49 | 0 | 0 | -124158 | 0 |  | CO
07CO | 07 | T7419 | 43050225201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 272 | 272 | 0 | 0 | 0 | 52 | 100 | 987665 | 50000 | 937665 | 987665 | 987634 | 0 | 0 | 0 | 987634 | 987634 | 0 | 0 | 27 | 0 | 100 | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 31825 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-03-14 | QTR3 | 19/20 | 796 | 1403000 |  |  | 100 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 45939 | 13 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | -16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 799 | 490000 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7440 | 44286215201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 116 | 167 | 163 | 4 | 0 | 0 | 30 | 21 | 2725693 | 50000 | 2675693 | 2725693 | 2560514 | 0 | 0 | 0 | 2560514 | 2560514 | 0 | 0 | 42 | 0 | 0 | 20000 | 0 | 0 | 0 | 3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23652 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 | 2020-10-06 | QTR2 | 20/21 | 798 | 2929941.26 |  |  | 21 | 9 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 625193 | 45 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M31 | 43751715201 | 2019-03-13 | QTR3 | 18/19 | 1 | 2 | 360 | 436 | 435 | 1 | 0 | 0 | 43 | 33 | 2064981 | 50000 | 2014981 | 1997687 | 1923224 | 0 | 0 | 0 | 1923224 | 1923189 | -35 | -67294 | 14 | 0 | 33 | -66214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | -26781 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-08-21 | QTR1 | 20/21 | 799 | 2265000 |  |  | 33 | 29 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M50 | 42905925201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 80 | 125 | 114 | 11 | 0 | 0 | 45 | 0 | 257038 | 11000 | 246038 | 257038 | 238009 | 0 | 0 | 0 | 238009 | 238009 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2019-12-20 | QTR2 | 19/20 | 796 | 255036.03 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M74 | 43955115201 | 2019-09-11 | QTR1 | 19/20 | 1 | 0 | 260 | 282 | 171 | 111 | 0 | 0 | 22 | 0 | 555000 | 48000 | 507000 | 555000 | 507000 | 0 | 0 | 0 | 507000 | 507000 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2020-07-31 | QTR1 | 20/21 | 796 | 1075906 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 799 | 280000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M90 | 43983015201 | 2020-02-12 | QTR3 | 19/20 | 1 | 0 | 100 | 126 | 126 | 0 | 0 | 0 | 22 | 4 | 682863 | 38200 | 644663 | 682863 | 661465 | 0 | 0 | 0 | 661465 | 661465 | 0 | 0 | 16 | 0 | 4 | 22230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22230 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-24 | QTR2 | 20/21 | 2020-10-16 | QTR2 | 20/21 | 796 | 786200 |  |  | 4 | 6 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 0 | 0 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N04 | 44580315201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 50 | 61 | 61 | 0 | 0 | 0 | 11 | 0 | 342938 | 15400 | 327538 | 342938 | 334918 | 0 | 0 | 0 | 334918 | 334918 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-16 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 796 | 323540.7 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R14 | 43402715201 | 2019-01-22 | QTR3 | 18/19 | 1 | 1 | 485 | 580 | 577 | 3 | 0 | 0 | 50 | 45 | 3891051 | 50000 | 3841051 | 3854521 | 3786721 | 0 | 0 | 0 | 3786721 | 3786721 | 0 | -36530 | 18 | 0 | 0 | -197831 | 0 | 0 | 0 | 11095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36530 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 |  | QTR2 | 00/01 | 796 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | -2369264 | 11648418 | 291 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1439 | 14 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 991193 | 5429118 | 149 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 127 | 0 | 0 | -88404 | 0 |  | DO
08DO | 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | -551574 | 4550344 | 122 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12 |  |  | 1 | 82 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 496445 | 1556062 | 183 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 0 |  |  | 36 | 99 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 1490912 | 597011 | 172 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09 |  |  | 16 | 84 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q94 | 43947815201 | 2018-03-27 | QTR3 | 17/18 | 4 | 6 | 525 | 723 | 723 | 0 | 0 | 0 | 198 | 0 | 18860577 | 150000 | 18710577 | 18748056 | 18778411 | -36500 | 0 | -36500 | 18741911 | 19317651 | 583633 | -112521 | 130 | 0 | 0 | -519709 | 0 | 0 | 0 | 381340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 106099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -32270 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2020-06-30 | QTR4 | 19/20 | 854 | 29028001.13 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 70000 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49 |  |  | 18 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | -3862 | 142527 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R76 | 43945715201 | 2019-03-12 | QTR3 | 18/19 | 1 | 6 | 415 | 477 | 405 | 72 | 0 | 0 | 62 | 0 | 12161596 | 125391 | 12036204 | 11888308 | 12421672 | 0 | 0 | 0 | 12421672 | 12302929 | -84308 | -273288 | 21 | 0 | 0 | -340280 | 0 | 0 | 0 | 51302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287059 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 | 2020-06-30 | QTR4 | 19/20 | 854 | 12670789.67 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 0 | 94072 | 5 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 0 | -576 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S47 | 44400315201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 65 | 75 | 64 | 11 | 0 | 0 | 10 | 0 | 254205 | 21677 | 232529 | 254205 | 227921 | 0 | 0 | 0 | 227921 | 227921 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 | 2020-11-08 | QTR2 | 20/21 | 854 | 465727.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0