## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 124220780 | 123102688 | 125602045 | 124394750 | 200000 | 124742713 | 1.332% | 100% | 1572887 | 1.278% | 1381262 | 1.112% | 5899 | 785 | 13.31% | 447 | 7.578% | 8 | 0.1356% | 483 | 8.188% | 6390 | 8.323% | 7619 | 7606 | 6374 | 8.052% | 76%
| District Let | 104473297 | 103136823 | 108593922 | 106428255 | 0 | 106142475 | 2.914% | 81.82% | 4293735 | 4.163% | 4120628 | 3.944% | 5657 | 1179 | 20.84% | 508 | 8.98% | 395 | 6.982% | 1022 | 18.07% | 7074 | 25.05% | 8878 | 8587 | 6900 | 21.97% | 72.73%
| All Contracts | 228694077 | 226239511 | 234195967 | 230823005 | 200000 | 230885188 | 2.053% | 91.49% | 5866622 | 2.593% | 5501890 | 2.406% | 11556 | 1964 | 17% | 955 | 8.264% | 403 | 3.487% | 1505 | 13.02% | 13464 | 16.51% | 16497 | 16193 | 13274 | 14.87% | 74.47%
2 | Central Let | 132884709 | 131301056 | 134322069 | 128602913 | 0 | 128570334 | -2.08% | 96.43% | 1954471 | 1.489% | 1437360 | 1.082% | 7255 | 1078 | 14.86% | 821 | 11.32% | 167 | 2.302% | 160 | 2.205% | 7582 | 4.507% | 9465 | 8993 | 7094 | -2.219% | 92.86%
| District Let | 289241161 | 288058380 | 315522567 | 313378604 | 0 | 287400697 | -0.2283% | 92.86% | 6802911 | 2.362% | 26281406 | 9.086% | 5156 | 894 | 17.34% | 736 | 14.27% | 269 | 5.217% | 1098 | 21.3% | 6523 | 26.51% | 9691 | 10905 | 9275 | 79.89% | 50%
| All Contracts | 422125870 | 419359436 | 449844636 | 441981517 | 0 | 415971031 | -0.808% | 95.24% | 8757382 | 2.088% | 27718766 | 6.566% | 12411 | 1972 | 15.89% | 1557 | 12.55% | 436 | 3.513% | 1258 | 10.14% | 14105 | 13.65% | 19156 | 19898 | 16369 | 31.89% | 78.57%
3 | Central Let | 99272019 | 98319405 | 100826981 | 103654805 | 1500000 | 103897917 | 5.674% | 90.91% | 1590112 | 1.617% | 1554964 | 1.566% | 4786 | 1687 | 35.25% | 545 | 11.39% | 274 | 5.725% | -128 | -2.674% | 4932 | 3.051% | 7164 | 7044 | 4812 | 0.5433% | 90.91%
| District Let | 35318233 | 34569889 | 36218495 | 35240895 | 200000 | 34433334 | -0.395% | 95.24% | 1033955 | 2.991% | 900260 | 2.549% | 3000 | 606 | 20.2% | 381 | 12.7% | 112 | 3.733% | 409 | 13.63% | 3521 | 17.37% | 4522 | 4267 | 3280 | 9.333% | 66.67%
| All Contracts | 134590252 | 132889294 | 137045476 | 138895700 | 1700000 | 138331251 | 4.095% | 93.02% | 2624067 | 1.975% | 2455224 | 1.824% | 7786 | 2293 | 29.45% | 926 | 11.89% | 386 | 4.958% | 281 | 3.609% | 8453 | 8.567% | 11686 | 11311 | 8092 | 3.93% | 79.07%
4 | Central Let | 118843477 | 117065265 | 126626863 | 123250127 | 0 | 123237192 | 5.272% | 91.43% | 7951411 | 6.792% | 7783383 | 6.549% | 9451 | 2048 | 21.67% | 925 | 9.787% | 211 | 2.233% | 1033 | 10.93% | 10695 | 13.16% | 13627 | 13144 | 10171 | 7.618% | 94.29%
| District Let | 131062288 | 129997933 | 151599741 | 149984663 | 325000 | 129509498 | -0.3757% | 100% | 20522609 | 15.79% | 20537451 | 15.67% | 6219 | 1139 | 18.31% | 504 | 8.104% | 151 | 2.428% | 657 | 10.56% | 7027 | 12.99% | 8684 | 8071 | 6428 | 3.361% | 90%
| All Contracts | 249905765 | 247063198 | 278226604 | 273234790 | 325000 | 252746690 | 2.3% | 94.55% | 28474020 | 11.52% | 28320834 | 11.33% | 15670 | 3187 | 20.34% | 1429 | 9.119% | 362 | 2.31% | 1690 | 10.78% | 17722 | 13.1% | 22311 | 21215 | 16599 | 5.929% | 92.73%
5 | Central Let | 191219742 | 189439127 | 198533484 | 202311510 | 582122 | 201615288 | 6.427% | 86.36% | 7412344 | 3.913% | 7313743 | 3.825% | 7590 | 1524 | 20.08% | 866 | 11.41% | 42 | 0.5534% | 1090 | 14.36% | 8722 | 14.91% | 11160 | 11068 | 8678 | 14.33% | 81.82%
| District Let | 257929910 | 256938687 | 259914591 | 259301798 | 1323936 | 243339134 | -5.293% | 95.65% | 1248555 | 0.4859% | 1984681 | 0.7695% | 6160 | 1244 | 20.19% | 796 | 12.92% | 41 | 0.6656% | 563 | 9.14% | 6764 | 9.805% | 8991 | 9917 | 7877 | 27.87% | 69.57%
| All Contracts | 449149652 | 446377814 | 458448075 | 461613308 | 1906058 | 444954422 | -0.3189% | 91.11% | 8660899 | 1.94% | 9298424 | 2.07% | 13750 | 2768 | 20.13% | 1662 | 12.09% | 83 | 0.6036% | 1653 | 12.02% | 15486 | 12.63% | 20151 | 20985 | 16555 | 20.4% | 75.56%
6 | Central Let | 133607016 | 131971233 | 136693564 | 134310147 | 7340000 | 133351861 | 1.046% | 100% | 3633909 | 2.754% | 3086548 | 2.31% | 6074 | 749 | 12.33% | 429 | 7.063% | 75 | 1.235% | 58 | 0.9549% | 6207 | 2.19% | 7473 | 6823 | 5645 | -7.063% | 100%
| District Let | 34511913 | 33949488 | 36688333 | 35555205 | 796000 | 32767730 | -3.481% | 90.91% | 2408674 | 7.095% | 2176420 | 6.306% | 3325 | 765 | 23.01% | 316 | 9.504% | 9 | 0.2707% | 282 | 8.481% | 3616 | 8.752% | 4762 | 4268 | 3187 | -4.15% | 90.91%
| All Contracts | 168118929 | 165920721 | 173381897 | 169865352 | 8136000 | 166119591 | 0.1199% | 96.97% | 6042583 | 3.642% | 5262968 | 3.131% | 9399 | 1514 | 16.11% | 745 | 7.926% | 84 | 0.8937% | 340 | 3.617% | 9823 | 4.511% | 12235 | 11091 | 8832 | -6.033% | 96.97%
7 | Central Let | 114200275 | 112834075 | 116615991 | 116849604 | 1600000 | 116559263 | 3.301% | 95.24% | 2602262 | 2.306% | 2414511 | 2.114% | 4962 | 1122 | 22.61% | 592 | 11.93% | 16 | 0.3225% | 444 | 8.948% | 5422 | 9.27% | 7188 | 6840 | 5126 | 3.305% | 85.71%
| District Let | 36331121 | 35558026 | 36912119 | 36276179 | 0 | 36169635 | 1.72% | 95.45% | 870802 | 2.449% | 580998 | 1.599% | 4405 | 519 | 11.78% | 354 | 8.036% | 3 | 0.0681% | 168 | 3.814% | 4576 | 3.882% | 5494 | 5034 | 4161 | -5.539% | 95.45%
| All Contracts | 150531396 | 148392101 | 153528110 | 153125783 | 1600000 | 152728898 | 2.923% | 95.35% | 3473064 | 2.34% | 2995509 | 1.99% | 9367 | 1641 | 17.52% | 946 | 10.1% | 19 | 0.2028% | 612 | 6.534% | 9998 | 6.736% | 12682 | 11874 | 9287 | -0.8541% | 90.7%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 626315738 | 623903783 | 658686936 | 657628524 | 0 | 655889837 | 5.127% | 91.3% | 31638404 | 5.071% | 32371199 | 5.169% | 12649 | 2129 | 16.83% | 1425 | 11.27% | 706 | 5.581% | 2120 | 16.76% | 15475 | 22.34% | 19037 | 18499 | 14945 | 18.15% | 0%
| All Contracts | 626315738 | 623903783 | 658686936 | 657628524 | 0 | 655889837 | 5.127% | 91.3% | 31638404 | 5.071% | 32371199 | 5.169% | 12649 | 2129 | 16.83% | 1425 | 11.27% | 706 | 5.581% | 2120 | 16.76% | 15475 | 22.34% | 19037 | 18499 | 14945 | 18.15% | 86.96%
Totals This Qtr | Central Let | 914248018 | 904032849 | 939220997 | 933373856 | 11222122 | 931974568 | 3.091% | 94.29% | 26717396 | 2.955% | 24971771 | 2.731% | 46017 | 8993 | 19.54% | 4625 | 10.05% | 793 | 1.723% | 3140 | 6.824% | 49950 | 8.547% | 63696 | 61518 | 47900 | 4.092% | 89.14%
| District Let | 1515183661 | 1506113009 | 1604136704 | 1593794123 | 2644936 | 1525652340 | 1.297% | 92.95% | 68819645 | 4.569% | 88953043 | 5.871% | 46571 | 8475 | 18.2% | 5020 | 10.78% | 1686 | 3.62% | 6319 | 13.57% | 54576 | 17.19% | 70059 | 69548 | 56053 | 20.36% | 78.21%
| All Contracts | 2429431679 | 2410145858 | 2543357701 | 2527167979 | 13867058 | 2457626908 | 1.97% | 93.66% | 95537041 | 3.964% | 113924814 | 4.689% | 92588 | 17468 | 18.87% | 9645 | 10.42% | 2479 | 2.677% | 9459 | 10.22% | 104526 | 12.89% | 133755 | 131066 | 103953 | 12.27% | 83.99%
Totals Previous Quarter | Central Let | 2785584454 | 2760453025 | 2899661280 | 2889173487 | 13853386 | 2866278384 | 3.834% | 0% | 115530953 | 4.185% | 114076821 | 4.095% | 118318 | 22733 | 19.21% | 12299 | 10.39% | 3133 | 2.648% | 11153 | 9.426% | 132604 | 12.07% | 168043 | 163018 | 127986 | 8.171% | 0%
| District Let | 1119978950 | 1107246826 | 1149109949 | 1144086454 | 13053386 | 1140602020 | 3.012% | 0% | 31211372 | 2.819% | 29130996 | 2.601% | 53370 | 11231 | 21.04% | 5394 | 10.11% | 1060 | 1.986% | 3346 | 6.269% | 57776 | 8.256% | 74478 | 71747 | 55122 | 3.283% | 0%
| All Contracts | 1541957061 | 1531090298 | 1622620714 | 1618242015 | 800000 | 1599006535 | 4.436% | 0% | 79791340 | 5.211% | 80663652 | 5.231% | 57963 | 10419 | 17.98% | 5921 | 10.22% | 1830 | 3.157% | 7064 | 12.19% | 66857 | 15.34% | 83526 | 81260 | 64920 | 12% | 0%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1665 | 43545015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 225 | 360 | 425 | 172.9% | 0 | -65 | 65 | 0 | 36 | 99 | 1995871 | 0 | 1995871 | 2060794 | 2106268 | -99792 | 0 | -99792 | 2006476 | 2010824 | 100.7% | 1 | 4348 | 64923 | 11 | 25 | 0 | 10 | 6687 | 0 | 0 | 0 | 2174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 54642 | 54642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1419 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 64923 | 56062 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-27 | QTR4 | 20/21 |  | 2019-01-04 | QTR3 | 18/19 | 115 | 2185570.99
| 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | 140.7% | 0 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 91.39% | 1 | 1353 | 15508 | 22 | 21 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31
| 01 | T1675 | 43088715201 | 2017-08-30 | QTR1 | 17/18 | 3 | 3 | 150 | 282 | 282 | 150% | 0 | 0 | 0 | 0 | 57 | 75 | 815194 | 35094 | 780100 | 856566 | 821472 | 0 | 0 | 0 | 821472 | 822481 | 105.4% | 1 | 1009 | 41372 | 36 | 21 | 0 | 0 | -1090 | 868 | 0 | 72 | 48111 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 41372 | 31652 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 |  | 2019-03-21 | QTR3 | 18/19 | 113 | 783433.16 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1702 | 43509015201 | 2018-02-28 | QTR3 | 17/18 | 2 | 2 | 240 | 285 | 282 | 98.75% | 1 | 3 | 0 | 0 | 45 | 0 | 2098354 | 50000 | 2048354 | 2203054 | 2035840 | 0 | 0 | 0 | 2035840 | 2034275 | 99.31% | 1 | -1565 | 104700 | 29 | 16 | 0 | 0 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104700 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-06 | QTR2 | 20/21 |  | 2019-04-29 | QTR4 | 18/19 | 115 | 2050385.52 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1712 | 43355025201 | 2018-04-25 | QTR4 | 17/18 | 1 | 1 | 390 | 460 | 459 | 101.5% | 1 | 1 | 0 | 0 | 63 | 7 | 5536538 | 50000 | 5486538 | 5542551 | 5605616 | 0 | 200000 | 200000 | 5805616 | 5601941 | 102.1% | 1 | -197662 | 6013 | 40 | 23 | 0 | 0 | 15589 | 0 | 0 | 7 | 12866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 28455 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 |  | 2019-11-15 | QTR2 | 19/20 | 115 | 5608551.81 | B10 | ACC - BONUS/INCENT/DISINCENT
| 01 | T1718 | 44011815201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 135 | 199 | 198 | 99.26% | 1 | 1 | 0 | 0 | 64 | 0 | 440982 | 24215 | 416767 | 440982 | 416149 | 0 | 0 | 0 | 416149 | 416078 | 99.83% | 1 | -71 | 0 | 56 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-02-15 | QTR3 | 20/21 |  | 2019-10-02 | QTR2 | 19/20 | 115 | 501429.8
| 01 | T1719 | 43800915201 | 2019-06-12 | QTR4 | 18/19 | 2 | 2 | 250 | 345 | 339 | 98% | 1 | 6 | 0 | 0 | 94 | 1 | 4444444 | 50000 | 4394444 | 4440169 | 4492709 | 0 | 0 | 0 | 4492709 | 4400827 | 100.1% | 1 | -91882 | -4276 | 78 | 16 | 0 | 1 | 30594 | 0 | 0 | 0 | 9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 32083 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-10 | QTR4 | 20/21 |  | 2020-12-16 | QTR2 | 20/21 | 108 | 4966062.8
| 01 | T1720 | 43655115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 200 | 419 | 415 | 167% | 0 | 4 | 0 | 0 | 81 | 138 | 4987470 | 50000 | 4937470 | 5081049 | 5094971 | 0 | 0 | 0 | 5094971 | 5026709 | 101.8% | 1 | -68262 | 93578 | 58 | 23 | 0 | 0 | 7545 | 0 | 0 | 138 | 101101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 116681 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-06-15 | QTR4 | 20/21 |  | 2021-02-23 | QTR3 | 20/21 | 115 | 5203469.32
| 01 | T1721 | 43955515201 | 2019-03-27 | QTR3 | 18/19 | 2 | 3 | 300 | 402 | 402 | 100% | 1 | 0 | 0 | 0 | 102 | 0 | 4793304 | 54777 | 4738527 | 4836240 | 4588281 | 0 | 0 | 0 | 4588281 | 4543144 | 95.88% | 1 | -45137 | 42936 | 70 | 32 | 0 | 0 | 66835 | 0 | 0 | 0 | 6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25510 | 25510 | 0 | 0 | 0 | 0 | 0 | 0 | -49409 | 0 | 0 | 0 | 49718 | 25510 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 |  | 2020-09-30 | QTR1 | 20/21 | 113 | 5287557.25
| 01 | T1722 | 43806015201 | 2019-04-24 | QTR4 | 18/19 | 3 | 5 | 400 | 457 | 457 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 11567352 | 137224 | 11430128 | 11561213 | 11392803 | 0 | 0 | 0 | 11392803 | 11280748 | 98.69% | 1 | -95187 | -6139 | 24 | 33 | 0 | 0 | -6793 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550 | 0 | 0 | 0 | 5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23265 | 0 | 0 | 0 | -4047 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 |  | 2020-10-09 | QTR2 | 20/21 | 118 | 13570915.56
| 01 | T1731 | 44012015201 | 2018-12-05 | QTR2 | 18/19 | 2 | 1 | 200 | 268 | 293 | 129.5% | 0 | -25 | 25 | 0 | 34 | 34 | 800698 | 46403 | 754295 | 822869 | 716288 | -41625 | 0 | -41625 | 674663 | 674668 | 89.44% | 1 | 5 | 22171 | 11 | 23 | 0 | 29 | 12897 | 2231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 22171 | 2231 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-02-24 | QTR3 | 20/21 |  | 2020-03-31 | QTR3 | 19/20 | 115 | 965767.02
| 01 | T1742 | 43539015201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 350 | 433 | 402 | 91.14% | 1 | 31 | 0 | 0 | 83 | 0 | 3732644 | 50000 | 3682644 | 3755256 | 3738358 | 0 | 0 | 0 | 3738358 | 3735826 | 101.4% | 1 | -2532 | 22611 | 53 | 30 | 0 | 0 | 24777 | 12441 | 0 | 0 | 44641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69418 | 12441 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 |  | 2020-10-30 | QTR2 | 20/21 | 113 | 3397781.79
| 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | 104.2% | 1 | -19598 | 2100 | 10 | 24 | 0 | 3 | 4793 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6893 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6
| 01 | T1746 | 43801415201 | 2019-03-27 | QTR3 | 18/19 | 2 | 1 | 200 | 283 | 283 | 109.5% | 1 | 0 | 0 | 0 | 72 | 11 | 3284806 | 50000 | 3234806 | 3448596 | 3473733 | -10000 | 0 | -10000 | 3463733 | 3433178 | 106.1% | 1 | -30555 | 163791 | 43 | 21 | 0 | 2 | 8167 | 0 | 8 | 0 | 3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 163791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11 | 175805 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 108 | 4171539.82
| 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 97.86% | 1 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | 101.4% | 1 | -317 | 3200 | 16 | 9 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55
| 01 | T1750 | 44385115201 | 2019-08-28 | QTR1 | 19/20 | 2 | 1 | 165 | 233 | 233 | 119.4% | 1 | 0 | 0 | 0 | 36 | 32 | 2676999 | 50000 | 2626999 | 2703686 | 2688376 | 0 | 0 | 0 | 2688376 | 2686495 | 102.3% | 1 | -1882 | 26687 | 27 | 9 | 0 | 32 | 31861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 31861 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-02-03 | QTR3 | 20/21 |  | 2020-09-14 | QTR1 | 20/21 | 108 | 2027464.68
| 01 | T1752 | 43942315201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 250 | 299 | 296 | 98.8% | 1 | 3 | 0 | 0 | 49 | 0 | 3291059 | 50000 | 3241059 | 3259973 | 3120660 | 0 | 0 | 0 | 3120660 | 3033429 | 93.59% | 1 | -87231 | -31087 | 26 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31087 | 0 | 0 | 0 | -31087 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-06-28 | QTR4 | 20/21 |  | 2021-03-15 | QTR3 | 20/21 | 115 | 3526242.99
| 01 | T1756 | 43511415201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 150 | 234 | 234 | 145.3% | 0 | 0 | 0 | 0 | 16 | 68 | 1037000 | 0 | 1037000 | 1084886 | 1084886 | 0 | 0 | 0 | 1084886 | 1084595 | 104.6% | 1 | -291 | 47886 | 10 | 6 | 0 | 0 | 20000 | 0 | 0 | 68 | 27886 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 47886 | 1076 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 |  | 2020-09-02 | QTR1 | 20/21 | 113 | 1002063.72 | B0 | ACC - LUMP SUM
| 01 | T1758 | 43943715201 | 2019-07-31 | QTR1 | 19/20 | 2 | 2 | 265 | 288 | 219 | 74.34% | 1 | 69 | 0 | 0 | 22 | 1 | 7004551 | 95304 | 6909247 | 7119832 | 7259276 | 0 | 0 | 0 | 7259276 | 7106733 | 102.9% | 1 | -152543 | 115281 | 17 | 5 | 0 | 1 | 114321 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 115281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-08-10 | QTR1 | 20/21 | 108 | 9375095.25
| 01 | T1759 | 44067015201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 125 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 1338165 | 49310 | 1288855 | 1328365 | 1305338 | 0 | 0 | 0 | 1305338 | 1305118 | 101.3% | 1 | -220 | -9800 | 49 | 9 | 0 | 0 | 19798 | 0 | 0 | 0 | 6314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16312 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-01-13 | QTR3 | 20/21 |  | 2020-10-26 | QTR2 | 20/21 | 113 | 1044391.47 | B0 | ACC - LUMP SUM
| 01 | T1767 | 44068115201 | 2019-07-31 | QTR1 | 19/20 | 2 | 0 | 79 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 561733 | 20351 | 541382 | 561733 | 545876 | 0 | 0 | 0 | 545876 | 545876 | 100.8% | 1 | 0 | 0 | 23 | 3 | 0 | 0 | 1036 | 0 | 0 | 0 | 3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4632 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 |  | 2020-07-15 | QTR1 | 20/21 | 115 | 444415.31
| 01 | T1773 | 44067215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 75 | 83 | 70 | 82.67% | 1 | 13 | 0 | 0 | 8 | 0 | 214731 | 9756 | 204975 | 214731 | 194639 | 0 | 0 | 0 | 194639 | 194639 | 94.96% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-08-21 | QTR1 | 20/21 | 108 | 215733.31
| 01 | T1776 | 43535815201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 50 | 67 | 65 | 96% | 1 | 2 | 0 | 0 | 17 | 0 | 140340 | 0 | 140340 | 140340 | 140340 | 0 | 0 | 0 | 140340 | 140340 | 100% | 1 | 0 | 0 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-18 | QTR4 | 20/21 |  | 2021-03-09 | QTR3 | 20/21 | 113 | 104699.84 | B0 | ACC - LUMP SUM
| 01 | T1779 | 43808615201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 103 | 103 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 905000 | 0 | 905000 | 905000 | 904754 | 0 | 0 | 0 | 904754 | 904754 | 99.97% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F454013430 | MSB SERVICES LLC | N/A | N/A | N/A | N/A | 2021-06-02 | QTR4 | 20/21 |  | 2021-05-07 | QTR4 | 20/21 | 115 | 658934.61 | B0 | ACC - LUMP SUM
| 01 | T1997 | 40828665201 | 2017-01-25 | QTR3 | 16/17 | 2 | 11 | 1100 | 1215 | 1201 | 98.73% | 1 | 14 | 0 | 0 | 115 | 0 | 58011809 | 150000 | 57861809 | 58671616 | 58073269 | 0 | 0 | 0 | 58073269 | 59258196 | 102.4% | 1 | 1257928 | 659807 | 51 | 64 | 0 | 0 | 424487 | 0 | 0 | 0 | 340095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143938 | 0 | 0 | 0 | 652410 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 |  | 2020-08-13 | QTR1 | 20/21 | 118 | 69879385.2
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 25 | 43 | 46 | 5899 | 7619 | 7606 | 76% | 19 | 13 | 137 | 0 | 1240 | 480 | 124220780 | 1118092 | 123102688 | 125602045 | 124394750 | -225865 | 200000 | -25865 | 124368885 | 124742713 | 100% | 25 | 469708 | 1381262 | 785 | 447 | 0 | 92 | 910424 | 15540 | 8 | 285 | 628718 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 254859 | 54642 | 0 | 0 | 5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 21280 | 26929 | 0 | 0 | 0 | 0 | 0 | 0 | -247699 | 0 | 8 | 483 | 1572887 | 128972
| 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 125% | 0 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 102.4% | 1 | 19995 | 355643 | 83 | 66 | 0 | 200 | 49249 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 429619 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 01 | E1P46 | 43580715201 | 2017-10-19 | QTR2 | 17/18 | 1 | 1 | 125 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 84 | 0 | 869954 | 43581 | 826373 | 869954 | 834474 | 0 | 0 | 0 | 834474 | 836068 | 101.2% | 1 | 1595 | 0 | 79 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2018-07-30 | QTR1 | 18/19 | 108 | 794913.85
| 01 | E1P87 | 43504015201 | 2017-04-20 | QTR4 | 16/17 | 1 | 6 | 175 | 654 | 654 | 324.6% | 0 | 0 | 0 | 0 | 132 | 347 | 2037254 | 50000 | 1987254 | 2546460 | 2602954 | 0 | 0 | 0 | 2602954 | 2606824 | 131.2% | 0 | 3870 | 509206 | 44 | 42 | 0 | 98 | 114422 | 91269 | 13 | 249 | 352422 | 200403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 37265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 347 | 509206 | 291672 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-04-13 | QTR4 | 20/21 |  | 2019-08-05 | QTR1 | 19/20 | 113 | 2970496.06
| 01 | E1R03 | 44021215201 | 2018-01-03 | QTR3 | 17/18 | 1 | 4 | 498 | 897 | 897 | 144.8% | 0 | 0 | 0 | 0 | 279 | 120 | 1441171 | 50000 | 1391171 | 1857076 | 1804938 | 0 | 0 | 0 | 1804938 | 1804938 | 129.7% | 0 | 0 | 415905 | 118 | 58 | 0 | 120 | 415905 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 120 | 415905 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-03-03 | QTR3 | 20/21 |  | 2020-08-28 | QTR1 | 20/21 | 113 | 1515907.88 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1R05 | 43629915201 | 2018-03-01 | QTR3 | 17/18 | 1 | 9 | 320 | 663 | 663 | 172.5% | 0 | 0 | 0 | 0 | 183 | 160 | 7996438 | 89923 | 7906515 | 8606992 | 8773391 | 0 | 0 | 0 | 8773391 | 8748736 | 110.7% | 0 | -916 | 610555 | 76 | 35 | 72 | 159 | 583162 | 0 | 0 | 1 | 13293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 160 | 596455 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-11-12 | QTR2 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 115 | 8160370.04 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 96.67% | 1 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | 101.1% | 1 | -259 | 29714 | 51 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91
| 01 | E1R07 | 19602255201 | 2018-06-14 | QTR4 | 17/18 | 3 | 9 | 380 | 716 | 746 | 164.2% | 0 | -30 | 30 | 0 | 213 | 123 | 4989441 | 0 | 4989441 | 5299029 | 4998104 | -64274 | -150000 | -214274 | 4783829 | 4757758 | 95.36% | 1 | -26072 | 309588 | 81 | 41 | 81 | 0 | 67703 | 40859 | 0 | 34 | 133445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 43418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 50 | 244566 | 40859 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-04-28 | QTR4 | 20/21 |  | 2020-11-06 | QTR2 | 20/21 | 115 | 4839623.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R08 | 43526515201 | 2018-05-17 | QTR4 | 17/18 | 1 | 1 | 225 | 342 | 341 | 99.56% | 1 | 1 | 0 | 0 | 117 | 0 | 1717172 | 50000 | 1667172 | 1717172 | 1457666 | 0 | 0 | 0 | 1457666 | 1601560 | 96.06% | 1 | 143895 | 0 | 102 | 15 | 0 | 0 | 1432 | 0 | 0 | 0 | 2731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 |  | 2019-12-17 | QTR2 | 19/20 | 113 | 2389311.47
| 01 | E1R11 | 41066625201 | 2018-06-14 | QTR4 | 17/18 | 3 | 12 | 574 | 772 | 710 | 102.1% | 1 | 62 | 0 | 0 | 184 | 14 | 20022782 | 150000 | 19872782 | 20456986 | 19822369 | 0 | 0 | 0 | 19822369 | 19631063 | 98.78% | 1 | -127528 | 434204 | 76 | 48 | 10 | 14 | 383963 | 16731 | 36 | 0 | 116041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 501902 | 16731 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 |  | 2020-12-21 | QTR2 | 20/21 | 108 | 22152761.07 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R39 | 43802415201 | 2018-10-18 | QTR2 | 18/19 | 1 | 1 | 200 | 279 | 275 | 99% | 1 | 4 | 0 | 0 | 77 | 2 | 2883484 | 50000 | 2833484 | 2929980 | 2732452 | 0 | 0 | 0 | 2732452 | 2828698 | 99.83% | 1 | 96246 | 46496 | 67 | 10 | 0 | 2 | 13860 | 0 | 0 | 0 | 46496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 60356 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 |  | 2019-11-20 | QTR2 | 19/20 | 108 | 3497647.15
| 01 | E1R62 | 43795815201 | 2018-08-16 | QTR1 | 18/19 | 1 | 1 | 147 | 263 | 263 | 117% | 1 | 0 | 0 | 0 | 91 | 25 | 1959744 | 50000 | 1909744 | 2208518 | 2188843 | 0 | 0 | 0 | 2188843 | 2188837 | 114.6% | 0 | -6 | 248774 | 64 | 27 | 0 | 25 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248774 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 |  | 2020-01-15 | QTR3 | 19/20 | 113 | 2795997.92
| 01 | E1R64 | 42584125201 | 2019-01-24 | QTR3 | 18/19 | 1 | 7 | 378 | 498 | 395 | 82.8% | 1 | 103 | 0 | 0 | 82 | 38 | 22161010 | 150000 | 22011010 | 23160665 | 22864939 | 0 | 0 | 0 | 22864939 | 22869487 | 103.9% | 1 | 7885 | 999656 | 64 | 18 | 0 | 38 | 590493 | 0 | 0 | 0 | 149445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1038401 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 |  | 2020-10-16 | QTR2 | 20/21 | 113 | 21356227.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R78 | 43502915201 | 2019-03-21 | QTR3 | 18/19 | 1 | 0 | 100 | 164 | 166 | 102% | 1 | -2 | 2 | 0 | 64 | 0 | 982956 | 35636 | 947320 | 982956 | 953745 | -3330 | 0 | -3330 | 950415 | 950415 | 100.3% | 1 | 0 | 0 | 50 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-10-19 | QTR2 | 20/21 |  | 2020-06-07 | QTR4 | 19/20 | 113 | 837254.07 | B0 | ACC - LUMP SUM
| 01 | E1R79 | 43806215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 4 | 300 | 457 | 422 | 110.3% | 1 | 35 | 0 | 0 | 118 | 39 | 6263696 | 61307 | 6202389 | 6369605 | 6356261 | 0 | 0 | 0 | 6356261 | 6267065 | 101% | 1 | -89196 | 105909 | 58 | 33 | 0 | 3 | 55425 | 0 | 27 | 36 | 130411 | 81997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74488 | 0 | 27 | 39 | 111348 | 81997 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 |  | 2020-12-14 | QTR2 | 20/21 | 115 | 6188091.23
| 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 148.8% | 0 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 100.3% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 1845 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM
| 01 | E1R86 | 44108815201 | 2018-11-09 | QTR2 | 18/19 | 1 | 0 | 370 | 470 | 470 | 106.5% | 1 | 0 | 0 | 0 | 76 | 24 | 2469000 | 50000 | 2419000 | 2469000 | 2431659 | 0 | 0 | 0 | 2431659 | 2431659 | 100.5% | 1 | 0 | 0 | 49 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 113 | 3306921.72 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 85.88% | 1 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | 100.1% | 1 | -4903 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM
| 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 98.75% | 1 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | 98.18% | 1 | -8 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15
| 01 | E1S13 | 44462715201 | 2020-01-16 | QTR3 | 19/20 | 1 | 1 | 130 | 168 | 130 | 72.31% | 1 | 38 | 0 | 0 | 36 | 2 | 993513 | 50000 | 943513 | 994797 | 930694 | 0 | 0 | 0 | 930694 | 928776 | 98.44% | 1 | -1919 | 1285 | 27 | 9 | 0 | 0 | 3447 | 0 | 0 | 2 | 13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 17405 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-10-01 | QTR2 | 20/21 | 108 | 1140044.02
| 01 | E1S47 | 43997015201 | 2020-01-16 | QTR3 | 19/20 | 1 | 0 | 100 | 125 | 89 | 64% | 1 | 36 | 0 | 0 | 25 | 0 | 450312 | 27504 | 422808 | 450312 | 440733 | 0 | 0 | 0 | 440733 | 440733 | 104.2% | 1 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 115 | 480716.09
| 01 | E1S48 | 44005515201 | 2020-02-20 | QTR3 | 19/20 | 1 | 2 | 200 | 240 | 232 | 96% | 1 | 8 | 0 | 0 | 40 | 0 | 2577917 | 50000 | 2527917 | 2631610 | 2504928 | 0 | 150000 | 150000 | 2654928 | 2504928 | 99.09% | 1 | -150000 | 53693 | 21 | 19 | 0 | 0 | 9324 | 0 | 0 | 0 | 53693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63017 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 |  | 2021-02-08 | QTR3 | 20/21 | 118 | 2532689.82 | B10 | ACC - BONUS/INCENT/DISINCENT
| 01 | E1S50 | 44525715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 0 | 45 | 53 | 51 | 95.56% | 1 | 2 | 0 | 0 | 8 | 0 | 279624 | 14400 | 265224 | 279624 | 287046 | 0 | 0 | 0 | 287046 | 287046 | 108.2% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 |  | 2020-07-30 | QTR1 | 20/21 | 108 | 268843.45
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 22 | 30 | 67 | 5657 | 8878 | 8587 | 72.73% | 16 | 291 | 32 | 0 | 2126 | 1095 | 104473297 | 1336474 | 103136823 | 108593922 | 106428255 | -67604 | 0 | -67604 | 106360650 | 106142475 | 81.82% | 18 | -127321 | 4120628 | 1179 | 508 | 163 | 659 | 2537159 | 148859 | 129 | 323 | 1246594 | 282400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 521397 | 0 | 0 | 24 | 14557 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 5097 | 0 | 0 | 16 | 43418 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74488 | 0 | 395 | 1022 | 4293735 | 431259
| District 01 Totals |  |  |  |  | 47 | 73 | 113 | 11556 | 16497 | 16193 | 74.47% | 35 | 304 | 169 | 0 | 3366 | 1575 | 228694077 | 2454566 | 226239511 | 234195967 | 230823005 | -293469 | 200000 | -93469 | 230729535 | 230885188 | 91.49% | 43 | 342387 | 5501890 | 1964 | 955 | 163 | 751 | 3447583 | 164399 | 137 | 608 | 1875312 | 314260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 91 | 776256 | 54642 | 0 | 24 | 19861 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 5097 | 0 | 0 | 16 | 43418 | 0 | 54 | 15 | 21280 | 26929 | 0 | 0 | 0 | 0 | 0 | 0 | -322187 | 0 | 403 | 1505 | 5866622 | 560231
| 02 | T2660 | 43607715201 | 2017-12-06 | QTR2 | 17/18 | 3 | 3 | 700 | 1072 | 1070 | 102.7% | 1 | 2 | 0 | 0 | 362 | 10 | 25775068 | 150000 | 25625068 | 25930204 | 26452915 | 0 | 0 | 0 | 26452915 | 26446407 | 103.2% | 1 | -6508 | 155136 | 207 | 144 | 11 | 7 | 52750 | 0 | 0 | 0 | 67478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 10 | 273866 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 |  | 2021-02-26 | QTR3 | 20/21 | 208 | 25496503.99
| 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 104.5% | 1 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 102% | 1 | 60614 | 12839 | 39 | 74 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 |  | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28
| 02 | T2690 | 42880715201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 445 | 649 | 612 | 98.43% | 1 | 37 | 0 | 0 | 174 | 30 | 7990153 | 93100 | 7897053 | 7990153 | 7911166 | 0 | 0 | 0 | 7911166 | 8230419 | 104.2% | 1 | 319253 | 0 | 60 | 114 | 0 | 0 | 13185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 40654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 16789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 70627 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-03-18 | QTR3 | 20/21 |  | 2020-02-24 | QTR3 | 19/20 | 208 | 8670416
| 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 120% | 1 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 104.9% | 1 | 67515 | 100000 | 78 | 19 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17
| 02 | T2706 | 42879615201 | 2018-02-28 | QTR3 | 17/18 | 2 | 5 | 300 | 499 | 488 | 134.7% | 0 | 11 | 0 | 0 | 190 | 9 | 7792915 | 80790 | 7712125 | 8443153 | 8718430 | 0 | 0 | 0 | 8718430 | 8716846 | 113% | 0 | -1584 | 650238 | 46 | 38 | 2 | 5 | 33906 | 0 | 96 | 2 | 122684 | 3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 475000 | 0 | 2 | 15735 | 15735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 9 | 647325 | 494380 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 |  | 2019-11-15 | QTR2 | 19/20 | 208 | 7769629.39
| 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 99.69% | 1 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 101.3% | 1 | 1507 | 42749 | 55 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149
| 02 | T2713 | 43613525201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 220 | 271 | 271 | 105% | 1 | 0 | 0 | 0 | 40 | 11 | 1975147 | 50000 | 1925147 | 1975147 | 1947179 | 0 | 0 | 0 | 1947179 | 1945873 | 101.1% | 1 | -1305 | 0 | 29 | 11 | 0 | 11 | 23153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 23153 | 0 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 |  | 2019-09-30 | QTR1 | 19/20 | 208 | 1272155.66
| 02 | T2716 | 43763015201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 600 | 675 | 627 | 92% | 1 | 48 | 0 | 0 | 75 | 0 | 4888889 | 53430 | 4835459 | 4888889 | 4688077 | 0 | 0 | 0 | 4688077 | 4687157 | 96.93% | 1 | -920 | 0 | 34 | 41 | 0 | 0 | 23805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31225 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-03 | QTR4 | 20/21 |  | 2020-12-22 | QTR2 | 20/21 | 216 | 5384748.68
| 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 95% | 1 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 78.26% | 1 | 0 | 0 | 1 | 26 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67
| 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | 90.39% | 1 | -98689 | 0 | 33 | 28 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 |  | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11
| 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 84.44% | 1 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 106.7% | 1 | 579 | 100000 | 13 | 11 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72
| 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | 139.4% | 0 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | 102% | 1 | -3801 | 80075 | 21 | 26 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85
| 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 84.56% | 1 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | 99.08% | 1 | -36444 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03
| 02 | T2729 | 43499715201 | 2019-02-27 | QTR3 | 18/19 | 2 | 0 | 180 | 285 | 284 | 112.8% | 1 | 1 | 0 | 0 | 51 | 54 | 2001734 | 50000 | 1951734 | 2001734 | 1943094 | 0 | 0 | 0 | 1943094 | 1943094 | 99.56% | 1 | 0 | 0 | 62 | 19 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 |  | 2020-06-06 | QTR4 | 19/20 | 209 | 2294575.66
| 02 | T2731 | 43617915201 | 2019-02-27 | QTR3 | 18/19 | 1 | 1 | 300 | 355 | 353 | 99.33% | 1 | 2 | 0 | 0 | 51 | 4 | 4898898 | 57023 | 4841876 | 4948898 | 4982985 | 0 | 0 | 0 | 4982985 | 4949350 | 102.2% | 1 | -33636 | 50000 | 28 | 27 | 0 | 0 | 15868 | 0 | 0 | 4 | 72023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 88330 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 |  | 2020-07-08 | QTR1 | 20/21 | 214 | 5966985.97
| 02 | T2735 | 44119515201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 100 | 142 | 142 | 100% | 1 | 0 | 0 | 0 | 13 | 29 | 421053 | 19914 | 401139 | 421053 | 394439 | 0 | 0 | 0 | 394439 | 394439 | 98.33% | 1 | 0 | 0 | 41 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-12-08 | QTR2 | 20/21 |  | 2020-05-26 | QTR4 | 19/20 | 208 | 428177.97
| 02 | T2737 | 43433315201 | 2019-04-24 | QTR4 | 18/19 | 2 | 2 | 300 | 365 | 295 | 79.33% | 1 | 70 | 0 | 0 | 63 | 2 | 2819291 | 50000 | 2769291 | 2969291 | 2939393 | 0 | 0 | 0 | 2939393 | 2937611 | 106.1% | 1 | -1782 | 150000 | 22 | 35 | 0 | 2 | 54696 | 0 | 6 | 0 | 81150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 136986 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | QTR3 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 208 | 1924121.6
| 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 72.22% | 1 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | 102.8% | 1 | -18603 | 0 | 18 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04
| 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 95% | 1 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 94.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2019-11-01 | QTR2 | 19/20 | 209 | 84351.5
| 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 103.3% | 1 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 108% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95
| 02 | T2747 | 43934815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 210 | 268 | 261 | 96.67% | 1 | 7 | 0 | 0 | 58 | 0 | 5571370 | 66973 | 5504397 | 5571370 | 5579362 | 0 | 0 | 0 | 5579362 | 5469678 | 99.37% | 1 | -109684 | 0 | 36 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 |  | 2020-07-29 | QTR1 | 20/21 | 216 | 6661155.86
| 02 | T2748 | 43911615201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 225 | 255 | 254 | 99.56% | 1 | 1 | 0 | 0 | 30 | 0 | 4749617 | 58060 | 4691557 | 4779617 | 4835839 | 0 | 0 | 0 | 4835839 | 4774010 | 101.8% | 1 | -61829 | 30000 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 31084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31084 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-02 | QTR4 | 20/21 |  | 2020-09-15 | QTR1 | 20/21 | 214 | 5777785.83
| 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 2 | 1 | 600 | 684 | 525 | 71.5% | 1 | 159 | 0 | 0 | 96 | 0 | 11950705 | 126323 | 11824382 | 12017028 | 7108680 | 0 | 0 | 0 | 7108680 | 7101059 | 60.05% | 1 | -7620 | 66323 | 64 | 32 | 0 | 0 | 3314 | 0 | 0 | 0 | 35690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44977 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 |  |  | QTR2 | 00/01 | 208 | 11844644.47
| 02 | T2750 | 43908015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 130 | 148 | 145 | 97.69% | 1 | 3 | 0 | 0 | 18 | 0 | 1515900 | 50000 | 1465900 | 1515900 | 1353861 | 0 | 0 | 0 | 1353861 | 1345218 | 91.77% | 1 | -8642 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 |  | 2020-05-29 | QTR4 | 19/20 | 216 | 1652876.26
| 02 | T2761 | 43934515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 180 | 215 | 211 | 97.78% | 1 | 4 | 0 | 0 | 35 | 0 | 4189603 | 51877 | 4137726 | 4189603 | 4189658 | 0 | 0 | 0 | 4189658 | 4163139 | 100.6% | 1 | -26519 | 0 | 30 | 5 | 0 | 0 | 4541 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6304 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-08-24 | QTR1 | 20/21 | 214 | 5262360.58
| 02 | T2764 | 44140615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 209 | 205 | 98.89% | 1 | 4 | 0 | 0 | 27 | 2 | 954146 | 50000 | 904146 | 954146 | 884664 | 0 | 0 | 0 | 884664 | 884785 | 97.86% | 1 | 121 | 0 | 9 | 18 | 0 | 2 | 6540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6540 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 |  | 2021-02-23 | QTR3 | 20/21 | 216 | 1080912.01
| 02 | T2765 | 43934415201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 286 | 291 | 105% | 1 | -5 | 5 | 0 | 102 | 4 | 3724072 | 50000 | 3674072 | 3724072 | 3875990 | -13560 | 0 | -13560 | 3862430 | 3837465 | 104.4% | 1 | -24965 | 0 | 70 | 32 | 0 | 4 | 71389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 80917 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2021-06-21 | QTR4 | 20/21 |  | 2021-03-04 | QTR3 | 20/21 | 214 | 4321210.18
| 02 | T2766 | 44348915201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 130 | 146 | 144 | 98.46% | 1 | 2 | 0 | 0 | 16 | 0 | 1081333 | 50000 | 1031333 | 1081333 | 1019859 | 0 | 0 | 0 | 1019859 | 1018371 | 98.74% | 1 | -1488 | 0 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-04 | QTR2 | 20/21 |  | 2020-06-16 | QTR4 | 19/20 | 214 | 1202483.05
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 28 | 39 | 28 | 7255 | 9465 | 8993 | 92.86% | 26 | 472 | 14 | 0 | 2003 | 219 | 132884709 | 1583654 | 131301056 | 134322069 | 128602913 | -28545 | 0 | -28545 | 128574368 | 128570334 | 96.43% | 27 | 5570 | 1437360 | 1078 | 821 | 13 | 71 | 548616 | 0 | 114 | 54 | 624645 | 30999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 23 | 51490 | 0 | 8 | 0 | 24734 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 94256 | 0 | 0 | 0 | 475000 | 475000 | 18 | 2 | 135735 | 15735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 160 | 1954471 | 521735
| 02 | E2Q19 | 43056535201 | 2013-03-27 | QTR3 | 12/13 | 2 | 7 | 898 | 1741 | 2245 | 236% | 0 | -504 | 504 | 0 | 126 | 717 | 76890000 | 250000 | 76640000 | 84056110 | 83001547 | -5396832 | 0 | -5396832 | 77604715 | 73874610 | 96.39% | 1 | -3730105 | 7166110 | 72 | 54 | 0 | 26 | 2691 | 0 | 0 | 0 | 5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117673 | 0 | 0 | 0 | 192400 | 0 | 0 | 24 | 55423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 138372 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 |  | 2019-07-30 | QTR1 | 19/20 | 208 | 86651500 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 13 | 798 | 1777 | 1998 | 234.5% | 0 | -221 | 221 | 0 | 127 | 852 | 84850000 | 175000 | 84675000 | 92836344 | 92314884 | -2553772 | 0 | -2553772 | 89761112 | 83827180 | 99% | 1 | -5933932 | 7986344 | 82 | 45 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 254205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271502 | 0 | 0 | 204 | 818390 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 |  | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 02 | E2S01 | 21334575201 | 2014-05-29 | QTR4 | 13/14 | 2 | 9 | 670 | 1514 | 1849 | 200.7% | 0 | -335 | 335 | 0 | 504 | 340 | 88950000 | 150000 | 88800000 | 95522820 | 95155243 | -3789520 | 0 | -3789520 | 91365723 | 87555364 | 98.6% | 1 | -3397345 | 6572820 | 339 | 165 | 0 | 95 | 635772 | 0 | 0 | 22 | 510778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1201150 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 |  | 2019-08-16 | QTR1 | 19/20 | 208 | 87843647.44 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2V62 | 43742915201 | 2017-04-19 | QTR4 | 16/17 | 2 | 3 | 538 | 1135 | 1132 | 185.9% | 0 | 3 | 0 | 0 | 172 | 425 | 2735951 | 50000 | 2685951 | 5631812 | 5550491 | 0 | 0 | 0 | 5550491 | 5348614 | 199.1% | 0 | -100997 | 2895861 | 78 | 54 | 40 | 0 | 36258 | 0 | 0 | 425 | 2744981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 425 | 2781240 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 |  | 2020-10-26 | QTR2 | 20/21 | 208 | 2961809.1
| 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 2 | 460 | 774 | 891 | 148.7% | 0 | -117 | 117 | 0 | 207 | 107 | 17417591 | 200000 | 17217591 | 18912363 | 18626417 | -549666 | 0 | -549666 | 18076751 | 18293661 | 106.2% | 1 | 233384 | 1494772 | 97 | 110 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1478299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1570743 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRAC | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 |  | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97
| 02 | E2X06 | 43076015201 | 2018-04-18 | QTR4 | 17/18 | 1 | 2 | 190 | 489 | 545 | 236.8% | 0 | -56 | 56 | 0 | 248 | 51 | 2957443 | 50000 | 2907443 | 3057443 | 3046193 | -151872 | 0 | -151872 | 2894321 | 2894277 | 99.55% | 1 | -43 | 100000 | 19 | 76 | 0 | 44 | 97963 | 0 | 0 | 7 | 5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 3616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 51 | 106737 | 0 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 |  | 2020-02-14 | QTR3 | 19/20 | 208 | 2882464.65
| 02 | E2X64 | 20964255201 | 2018-09-19 | QTR1 | 18/19 | 1 | 0 | 420 | 509 | 509 | 104.5% | 1 | 0 | 0 | 0 | 89 | 0 | 2988353 | 50000 | 2938353 | 2988353 | 3023872 | 0 | 0 | 0 | 3023872 | 3021571 | 102.8% | 1 | -2301 | 0 | 16 | 54 | 0 | 0 | 0 | 0 | 19 | 0 | 4770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 4770 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2021-02-23 | QTR3 | 20/21 |  | 2020-10-02 | QTR2 | 20/21 | 208 | 3026820.72
| 02 | E2X65 | 43239615201 | 2018-12-19 | QTR2 | 18/19 | 1 | 1 | 300 | 518 | 532 | 153% | 0 | -14 | 14 | 0 | 130 | 88 | 2683748 | 50000 | 2633748 | 2672792 | 2635955 | -37968 | 0 | -37968 | 2597987 | 2597896 | 98.64% | 1 | -90 | -10956 | 24 | 49 | 0 | 87 | -10956 | 0 | 30 | 1 | 13931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 88 | 2976 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 |  | 2020-12-09 | QTR2 | 20/21 | 208 | 2688578.12
| 02 | E2Y25 | 43761715201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 250 | 365 | 351 | 100.8% | 1 | 14 | 0 | 0 | 99 | 16 | 5599368 | 63324 | 5536044 | 5599368 | 5849866 | 0 | 0 | 0 | 5849866 | 5819954 | 105.1% | 1 | -29911 | 0 | 48 | 51 | 0 | 0 | 2537 | 0 | 0 | 3 | 23074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 11453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 37064 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-05 | QTR2 | 20/21 |  | 2020-06-19 | QTR4 | 19/20 | 216 | 6362327.21
| 02 | E2Y27 | 44129815201 | 2019-05-15 | QTR4 | 18/19 | 3 | 2 | 360 | 494 | 494 | 108.3% | 1 | 0 | 0 | 0 | 101 | 33 | 2191115 | 60000 | 2131115 | 2260070 | 2293916 | 0 | 0 | 0 | 2293916 | 2287350 | 107.3% | 1 | -6566 | 68955 | 45 | 59 | 0 | 13 | 8989 | 0 | 0 | 14 | 75803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 91019 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2021-03-31 | QTR3 | 20/21 |  | 2020-12-11 | QTR2 | 20/21 | 208 | 2136569.19
| 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 106.4% | 1 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 98.55% | 1 | 0 | 0 | 11 | 1 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26
| 02 | E2Z35 | 43593915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 1 | 75 | 92 | 92 | 104% | 1 | 0 | 0 | 0 | 14 | 3 | 484693 | 14625 | 470068 | 492193 | 451960 | 0 | 0 | 0 | 451960 | 451960 | 96.15% | 1 | 0 | 7500 | 8 | 6 | 0 | 3 | 14105 | 0 | 0 | 0 | 3513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17618 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-05-14 | QTR4 | 20/21 |  | 2020-12-18 | QTR2 | 20/21 | 209 | 351994.25
| 02 | E2Z37 | 43616525201 | 2020-03-18 | QTR3 | 19/20 | 1 | 0 | 90 | 150 | 141 | 90% | 1 | 9 | 0 | 0 | 45 | 15 | 335202 | 15218 | 319984 | 335202 | 332890 | 0 | 0 | 0 | 332890 | 332890 | 104% | 1 | 0 | 0 | 52 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27171 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2021-04-16 | QTR4 | 20/21 |  | 2020-11-30 | QTR2 | 20/21 | 209 | 321539.88
| 02 | E2Z38 | 43958915201 | 2019-12-18 | QTR2 | 19/20 | 1 | 0 | 60 | 70 | 64 | 95% | 1 | 6 | 0 | 0 | 7 | 3 | 671597 | 33172 | 638425 | 671597 | 637444 | 0 | 0 | 0 | 637444 | 637444 | 99.85% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 5361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5361 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 |  | 2020-11-23 | QTR2 | 20/21 | 208 | 705487.5
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 14 | 24 | 40 | 5156 | 9691 | 10905 | 50% | 7 | -1214 | 1247 | 0 | 1881 | 2654 | 289241161 | 1182781 | 288058380 | 315522567 | 313378604 | -12479630 | 0 | -12479630 | 300898974 | 287400697 | 92.86% | 13 | -12967906 | 26281406 | 894 | 736 | 40 | 310 | 1384795 | 0 | 49 | 580 | 3542782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117673 | 0 | 0 | 0 | 414050 | 0 | 0 | 41 | 80940 | 0 | 15 | 0 | 3616 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 281376 | 0 | 0 | 103 | 1478299 | 0 | 165 | 3 | 6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271502 | 0 | 269 | 1098 | 6802911 | 0
| District 02 Totals |  |  |  |  | 42 | 63 | 68 | 12411 | 19156 | 19898 | 78.57% | 33 | -742 | 1261 | 0 | 3884 | 2873 | 422125870 | 2766435 | 419359436 | 449844636 | 441981517 | -12508175 | 0 | -12508175 | 429473342 | 415971031 | 95.24% | 40 | -12962336 | 27718766 | 1972 | 1557 | 53 | 381 | 1933411 | 0 | 163 | 634 | 4167427 | 30999 | 0 | 0 | 0 | 0 | 0 | 0 | -117673 | 0 | 14 | 0 | 414050 | 0 | 0 | 64 | 132430 | 0 | 23 | 0 | 28350 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 375632 | 0 | 0 | 103 | 1953299 | 475000 | 183 | 5 | 141963 | 15735 | 0 | 0 | 0 | 0 | 0 | 0 | -271502 | 0 | 436 | 1258 | 8757382 | 521735
| 03 | T3287 | 22044245201 | 2015-04-29 | QTR4 | 14/15 | 1 | 7 | 580 | 1033 | 1033 | 108.4% | 1 | 0 | 0 | 0 | 446 | 7 | 18411475 | 150000 | 18261475 | 18469826 | 18803780 | 0 | 0 | 0 | 18803780 | 18257490 | 99.98% | 1 | -528638 | 58351 | 335 | 69 | 0 | 5 | 113096 | 0 | 42 | 0 | 6384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -114120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 128733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 7 | 134093 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 |  | 2018-08-16 | QTR1 | 18/19 | 308 | 19760913.51
| 03 | T3578 | 41413235201 | 2017-04-26 | QTR4 | 16/17 | 3 | 15 | 1220 | 1365 | 1303 | 80.74% | 1 | 62 | 0 | 0 | 318 | -173 | 33319378 | 177050 | 33142328 | 34311548 | 36973951 | -94250 | 1500000 | 1405750 | 38379701 | 37310664 | 112.6% | 0 | -1041419 | 992170 | 229 | 89 | 0 | 0 | -9279 | 0 | 0 | 0 | 30465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173 | 947928 | 627929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173 | 970022 | 627929 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 |  | 2021-03-21 | QTR3 | 20/21 | 306 | 33490900.73
| 03 | T3582 | 43483715201 | 2017-01-25 | QTR3 | 16/17 | 1 | 5 | 200 | 489 | 489 | 100% | 1 | 0 | 0 | 0 | 289 | 0 | 6289025 | 76080 | 6212946 | 6444360 | 6415800 | -47198 | 0 | -47198 | 6368602 | 6491338 | 104.5% | 1 | 125354 | 155335 | 238 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 28118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 |  | 2018-08-15 | QTR1 | 18/19 | 308 | 7725569.14
| 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 137.2% | 0 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 109.8% | 1 | 2492 | -1395 | 58 | 27 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34
| 03 | T3619 | 43390215201 | 2018-11-14 | QTR2 | 18/19 | 1 | 1 | 175 | 253 | 248 | 114.9% | 1 | 5 | 0 | 0 | 72 | 6 | 1114410 | 0 | 1114410 | 1163460 | 1226323 | 0 | 0 | 0 | 1226323 | 1224530 | 109.9% | 1 | -1793 | 49050 | 34 | 13 | 10 | 6 | 49050 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | 49050 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2020-12-10 | QTR2 | 20/21 |  | 2019-10-07 | QTR2 | 19/20 | 313 | 1475964.98
| 03 | T3627 | 43228915201 | 2017-10-25 | QTR2 | 17/18 | 1 | 3 | 335 | 448 | 447 | 102.7% | 1 | 1 | 0 | 0 | 113 | 0 | 3174345 | 0 | 3174345 | 3223970 | 3466393 | 0 | 0 | 0 | 3466393 | 3468474 | 109.3% | 1 | 2081 | 49626 | 79 | 24 | 10 | 0 | 40110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 40110 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 |  | 2019-04-13 | QTR4 | 18/19 | 321 | 3241141.96
| 03 | T3642 | 43274025201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 250 | 555 | 555 | 100% | 1 | 0 | 0 | 0 | 305 | 0 | 8739221 | 84002 | 8655219 | 8879082 | 9063602 | -14091 | 0 | -14091 | 9049511 | 9512844 | 109.9% | 1 | 541744 | 139862 | 250 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 |  | 2019-07-11 | QTR1 | 19/20 | 314 | 8488154.79
| 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | 93.61% | 1 | -3093 | 3300 | 17 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34
| 03 | T3659 | 43728425201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 45 | 135 | 133 | 191.1% | 0 | 2 | 0 | 0 | 74 | 16 | 1158389 | 50000 | 1108389 | 1230266 | 1207818 | 0 | 0 | 0 | 1207818 | 1207818 | 109% | 1 | 0 | 71877 | 42 | 5 | 0 | 0 | 0 | 0 | 0 | 12 | 53227 | 11252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 4 | 18650 | 16090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 16 | 71877 | 27342 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 |  | 2018-08-09 | QTR1 | 18/19 | 321 | 1285000
| 03 | T3663 | 43188345201 | 2019-08-28 | QTR1 | 19/20 | 1 | 2 | 85 | 155 | 155 | 117.6% | 1 | 0 | 0 | 0 | 70 | 0 | 656987 | 29252 | 627735 | 668791 | 649887 | 0 | 0 | 0 | 649887 | 649887 | 103.5% | 1 | 0 | 11804 | 25 | 30 | 12 | 0 | 11597 | 2421 | 3 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 13154 | 2421 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-05-04 | QTR4 | 19/20 | 308 | 691494.24
| 03 | T3668 | 43580015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 4 | 250 | 295 | 271 | 90.4% | 1 | 24 | 0 | 0 | 45 | 0 | 1427167 | 0 | 1427167 | 1429917 | 1395761 | 0 | 0 | 0 | 1395761 | 1394795 | 97.73% | 1 | -966 | 2750 | 34 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 |  | 2020-10-02 | QTR2 | 20/21 | 321 | 1392503.71
| 03 | T3694 | 43814015201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 150 | 172 | 156 | 89.33% | 1 | 16 | 0 | 0 | 22 | 0 | 1092210 | 50455 | 1041755 | 1092210 | 1034116 | 0 | 0 | 0 | 1034116 | 1032121 | 99.08% | 1 | -1995 | 0 | 15 | 7 | 0 | 0 | 880 | 0 | 0 | 0 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5695 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-04-21 | QTR4 | 20/21 |  | 2020-11-10 | QTR2 | 20/21 | 321 | 1201384.89
| 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 115% | 1 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | 97% | 1 | -30923 | 0 | 80 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22
| 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 113.3% | 1 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 96.92% | 1 | 0 | 0 | 72 | 38 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32
| 03 | T3724 | 43972215201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 150 | 279 | 279 | 100% | 1 | 0 | 0 | 0 | 129 | 0 | 4652882 | 50000 | 4602882 | 4613196 | 4707642 | 0 | 0 | 0 | 4707642 | 4673127 | 101.5% | 1 | -34515 | -39686 | 96 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-04-14 | QTR4 | 20/21 |  | 2020-11-30 | QTR2 | 20/21 | 314 | 4516754.11
| 03 | T3732 | 44172515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 90 | 123 | 123 | 107.8% | 1 | 0 | 0 | 0 | 33 | 0 | 724625 | 27004 | 697621 | 724625 | 671669 | 0 | 0 | 0 | 671669 | 671669 | 96.28% | 1 | 0 | 0 | 20 | 6 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 |  | 2020-08-14 | QTR1 | 20/21 | 308 | 569928.95
| 03 | T3734 | 44174315201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 60 | 65 | 63 | 96.67% | 1 | 2 | 0 | 0 | 5 | 0 | 161220 | 10585 | 150635 | 161220 | 147933 | 0 | 0 | 0 | 147933 | 147933 | 98.21% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 |  | 2020-08-06 | QTR1 | 20/21 | 321 | 223390.28
| 03 | T3737 | 44174415201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 60 | 72 | 70 | 96.67% | 1 | 2 | 0 | 0 | 12 | 0 | 163087 | 11619 | 151468 | 163087 | 147675 | 0 | 0 | 0 | 147675 | 147675 | 97.5% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 |  | 2020-10-12 | QTR2 | 20/21 | 321 | 241246.7
| 03 | T3739 | 44173715201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 45 | 64 | 63 | 106.7% | 1 | 1 | 0 | 0 | 19 | 0 | 229048 | 6715 | 222333 | 236141 | 232144 | 0 | 0 | 0 | 232144 | 232144 | 104.4% | 1 | 0 | 7093 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 7093 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 |  | 2020-08-14 | QTR1 | 20/21 | 308 | 145096.15
| 03 | T3747 | 44173515201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 120 | 151 | 151 | 111.7% | 1 | 0 | 0 | 0 | 17 | 14 | 512999 | 25267 | 487732 | 567826 | 538766 | 0 | 0 | 0 | 538766 | 538766 | 110.5% | 0 | 0 | 54827 | 8 | 9 | 0 | 14 | 47827 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 54827 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-18 | QTR4 | 20/21 |  | 2020-12-10 | QTR2 | 20/21 | 313 | 532693.81
| 03 | T3748 | 44404215201 | 2020-04-29 | QTR4 | 19/20 | 2 | 0 | 74 | 104 | 106 | 102.7% | 1 | -2 | 2 | 0 | 30 | 0 | 600835 | 43572 | 557263 | 600835 | 529358 | -3380 | 0 | -3380 | 525978 | 525978 | 94.39% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 |  | 2020-12-19 | QTR2 | 20/21 | 313 | 859032.72
| 03 | T9021 | 44531225216 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 150 | 195 | 193 | 110.7% | 1 | 2 | 0 | 0 | 43 | 2 | 1606769 | 50000 | 1556769 | 1606769 | 1542684 | 0 | 0 | 0 | 1542684 | 1542685 | 99.1% | 1 | 1 | 0 | 12 | 15 | 16 | 0 | 0 | 0 | 0 | 2 | 7007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 7007 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 |  | 2021-01-14 | QTR3 | 20/21 | 314 | 1883890.6
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 22 | 27 | 53 | 4786 | 7164 | 7044 | 90.91% | 20 | 120 | 2 | 0 | 2506 | -128 | 99272019 | 952615 | 98319405 | 100826981 | 103654805 | -158919 | 1500000 | 1341081 | 104995886 | 103897917 | 90.91% | 20 | -971670 | 1554964 | 1687 | 545 | 48 | 25 | 253281 | 2421 | 113 | 14 | 151915 | 11252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | -168 | 915471 | 644019 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 268425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | -128 | 1590112 | 657692
| 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 173.9% | 0 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | 108.5% | 1 | -3036 | 251063 | 77 | 50 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000
| 03 | E3P37 | 22280225201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 120 | 154 | 152 | 98.33% | 1 | 2 | 0 | 0 | 34 | 0 | 398582 | 35644 | 362938 | 398582 | 363870 | 0 | 0 | 0 | 363870 | 363870 | 100.3% | 1 | 0 | 0 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F811252530 | OMEGA COATINGS & CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 |  | 2019-11-24 | QTR2 | 19/20 | 313 | 733124
| 03 | E3Q54 | 22253925201 | 2019-05-09 | QTR4 | 18/19 | 1 | 1 | 90 | 110 | 103 | 92.22% | 1 | 7 | 0 | 0 | 20 | 0 | 922444 | 50000 | 872444 | 846935 | 658266 | 0 | 0 | 0 | 658266 | 658266 | 75.45% | 1 | 0 | -75510 | 16 | 4 | 0 | 0 | 12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 0 | 0 | -63199 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-05 | QTR2 | 20/21 |  | 2019-11-22 | QTR2 | 19/20 | 321 | 919379.25
| 03 | E3R03 | 41343525201 | 2018-05-10 | QTR4 | 17/18 | 4 | 9 | 210 | 403 | 403 | 129.5% | 0 | 0 | 0 | 0 | 165 | 28 | 1381327 | 50000 | 1331327 | 1468091 | 1381221 | -4783 | 0 | -4783 | 1376437 | 1365035 | 102.5% | 1 | -1916 | 86763 | 94 | 37 | 0 | 0 | 0 | 0 | 0 | 3 | 15065 | 1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 52304 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 28 | 80290 | 15961 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2019-09-13 | QTR1 | 19/20 | 308 | 1155000
| 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 145.7% | 0 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | 102.4% | 1 | -52116 | 158902 | 66 | 62 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94
| 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 251.7% | 0 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 119.3% | 0 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79
| 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 278 | 280 | 128.3% | 0 | -2 | 2 | 0 | 54 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4468867 | -5424 | 0 | -5424 | 4463443 | 4390050 | 102.5% | 1 | -73393 | 123339 | 26 | 23 | 0 | 14 | 48949 | 0 | 5 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-16 | QTR4 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04
| 03 | E3R75 | 40731075201 | 2019-06-13 | QTR4 | 18/19 | 2 | 4 | 180 | 236 | 236 | 102.2% | 1 | 0 | 0 | 0 | 52 | 4 | 1896816 | 50000 | 1846816 | 2013742 | 1899113 | 0 | 0 | 0 | 1899113 | 1899113 | 102.8% | 1 | 0 | 116926 | 22 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 102982 | 7592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 116926 | 9300 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-10-07 | QTR2 | 20/21 |  | 2020-06-19 | QTR4 | 19/20 | 308 | 1645052.8
| 03 | E3R78 | 43813815201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 90 | 124 | 116 | 91.11% | 1 | 8 | 0 | 0 | 34 | 0 | 467023 | 24986 | 442037 | 467023 | 452193 | 0 | 0 | 0 | 452193 | 452193 | 102.3% | 1 | 0 | 0 | 27 | 7 | 0 | 0 | 3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 |  | 2020-08-03 | QTR1 | 20/21 | 314 | 567888.91
| 03 | E3R84 | 43736715201 | 2019-05-09 | QTR4 | 18/19 | 3 | 1 | 150 | 273 | 264 | 134% | 0 | 9 | 0 | 0 | 63 | 60 | 1890085 | 52035 | 1838050 | 1993510 | 1844667 | 0 | 0 | 0 | 1844667 | 1822661 | 99.16% | 1 | -22007 | 103425 | 27 | 36 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 313 | 1951315.61
| 03 | E3R95 | 41558035201 | 2020-02-13 | QTR3 | 19/20 | 1 | 0 | 90 | 117 | 109 | 91.11% | 1 | 8 | 0 | 0 | 27 | 0 | 328111 | 23276 | 304835 | 328111 | 264195 | 0 | 0 | 0 | 264195 | 264195 | 86.67% | 1 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-01-20 | QTR3 | 20/21 |  | 2020-12-10 | QTR2 | 20/21 | 308 | 491599.69
| 03 | E3S02 | 21939725201 | 2019-12-12 | QTR2 | 19/20 | 1 | 0 | 90 | 91 | 36 | 38.89% | 1 | 55 | 0 | 0 | 1 | 0 | 427396 | 14431 | 412964 | 427396 | 396531 | 0 | 0 | 0 | 396531 | 396531 | 96.02% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 |  | 2020-05-26 | QTR4 | 19/20 | 321 | 321776.39
| 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 102.5% | 1 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | 102.3% | 1 | -82786 | 42363 | 60 | 45 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75
| 03 | E3S37 | 43972615201 | 2019-08-08 | QTR1 | 19/20 | 3 | 0 | 150 | 174 | 167 | 95.33% | 1 | 7 | 0 | 0 | 24 | 0 | 1570270 | 51725 | 1518545 | 1570270 | 1528065 | 0 | 0 | 0 | 1528065 | 1509877 | 99.43% | 1 | -18188 | 0 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-03-22 | QTR3 | 20/21 |  | 2020-07-29 | QTR1 | 20/21 | 321 | 1812371.83
| 03 | E3S48 | 43973015201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 150 | 167 | 153 | 90.67% | 1 | 14 | 0 | 0 | 17 | 0 | 2362840 | 50000 | 2312840 | 2362840 | 2375062 | 0 | 0 | 0 | 2375062 | 2367596 | 102.4% | 1 | -7466 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 2687906.81
| 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 101.2% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65
| 03 | E3S50 | 22253625201 | 2019-11-14 | QTR2 | 19/20 | 2 | 0 | 120 | 125 | 50 | 37.5% | 1 | 75 | 0 | 0 | 5 | 0 | 688910 | 0 | 688910 | 688910 | 677594 | 0 | 0 | 0 | 677594 | 677594 | 98.36% | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2020-04-06 | QTR4 | 19/20 | 321 | 1158620.3
| 03 | E3S58 | 43992625201 | 2019-09-12 | QTR1 | 19/20 | 1 | 0 | 425 | 492 | 458 | 92% | 1 | 34 | 0 | 0 | 67 | 0 | 4969434 | 55861 | 4913574 | 4969434 | 4898737 | 0 | 0 | 0 | 4898737 | 4882975 | 99.38% | 1 | -15762 | 0 | 44 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 |  | 2021-04-08 | QTR4 | 20/21 | 321 | 5633775.36
| 03 | E3S66 | 4450183H201 | 2019-04-26 | QTR4 | 18/19 | 1 | 0 | 75 | 93 | 92 | 98.67% | 1 | 1 | 0 | 0 | 18 | 0 | 280576 | 0 | 280576 | 280576 | 224753 | 0 | 0 | 0 | 224753 | 0 | 0% | 1 | -224753 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 |  | 2019-10-02 | QTR2 | 19/20 | 314 | 275520.59
| 03 | E3T19 | 4453861K201 | 2019-10-14 | QTR2 | 19/20 | 2 | 1 | 70 | 130 | 137 | 130% | 0 | -7 | 7 | 0 | 60 | 0 | 289955 | 0 | 289955 | 289955 | 286443 | -8687 | 0 | -8687 | 277756 | 0 | 0% | 1 | -277756 | 0 | 26 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201212361 | PBROWN BUILDERS LLC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 |  | 2020-06-11 | QTR4 | 19/20 | 313 | 279453.29
| 03 | E3T53 | 42187835201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 60 | 60 | 36 | 60% | 1 | 24 | 0 | 0 | 0 | 0 | 205566 | 12109 | 193457 | 205566 | 187451 | 0 | 200000 | 200000 | 387451 | 187451 | 96.9% | 1 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-04-14 | QTR4 | 20/21 |  | 2020-11-03 | QTR2 | 20/21 | 313 | 257559.58 | B10 | ACC - BONUS/INCENT/DISINCENT
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 21 | 35 | 29 | 3000 | 4522 | 4267 | 66.67% | 14 | 255 | 9 | 0 | 1113 | 409 | 35318233 | 748345 | 34569889 | 36218495 | 35240895 | -18894 | 200000 | 181106 | 35422000 | 34433334 | 95.24% | 20 | -979179 | 900260 | 606 | 381 | 0 | 55 | 345209 | 0 | 78 | 106 | 237725 | 10111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 513611 | 86659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 112 | 409 | 1033955 | 109692
| District 03 Totals |  |  |  |  | 43 | 62 | 82 | 7786 | 11686 | 11311 | 79.07% | 34 | 375 | 11 | 0 | 3619 | 281 | 134590252 | 1700960 | 132889294 | 137045476 | 138895700 | -177813 | 1700000 | 1522187 | 140417886 | 138331251 | 93.02% | 40 | -1950849 | 2455224 | 2293 | 926 | 48 | 80 | 598490 | 2421 | 191 | 120 | 389640 | 21363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 80 | 1429082 | 730678 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 268425 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 0 | 0 | -75510 | 0 | 386 | 281 | 2624067 | 767384
| 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 119% | 1 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 106.4% | 1 | 233861 | 985075 | 115 | 55 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22
| 04 | T4462 | 43232315203 | 2017-05-24 | QTR4 | 16/17 | 3 | 18 | 349 | 1018 | 1024 | 253.9% | 0 | -6 | 6 | 0 | 144 | 525 | 9366292 | 77893 | 9288399 | 10932113 | 10870783 | -21870 | 0 | -21870 | 10848913 | 10912061 | 117.5% | 0 | 107174 | 1565821 | 95 | 43 | 0 | 45 | 152933 | 19651 | 6 | 480 | 1355104 | 233357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73285 | 1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 525 | 1581322 | 254305 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2021-05-12 | QTR4 | 20/21 |  | 2020-07-28 | QTR1 | 20/21 | 412 | 8174810.53
| 04 | T4473 | 42751615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 4 | 335 | 483 | 483 | 103.6% | 1 | 0 | 0 | 0 | 148 | 0 | 14954960 | 127766 | 14827195 | 14788864 | 14238463 | 0 | 0 | 0 | 14238463 | 14552841 | 98.15% | 1 | 324737 | -166097 | 91 | 45 | 0 | 0 | 144864 | 0 | 0 | 0 | 5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 26899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -324121 | 0 | 12 | 0 | -147083 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 |  | 2020-02-06 | QTR3 | 19/20 | 409 | 12073779.82 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4479 | 43059025201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 179 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 815678 | 34169 | 781510 | 823050 | 757384 | 0 | 0 | 0 | 757384 | 756711 | 96.83% | 1 | -673 | 7371 | 93 | 22 | 0 | 0 | 7371 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9340 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 |  | 2020-06-16 | QTR4 | 19/20 | 412 | 726059.56
| 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 116.6% | 1 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | 86.03% | 1 | -253 | 22625 | 66 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52
| 04 | T4485 | 43634115201 | 2018-06-13 | QTR4 | 17/18 | 2 | 2 | 239 | 422 | 422 | 118% | 1 | 0 | 0 | 0 | 140 | 43 | 1979980 | 50000 | 1929980 | 2224615 | 2010428 | 0 | 0 | 0 | 2010428 | 2010404 | 104.2% | 1 | -24 | 244635 | 112 | 28 | 0 | 0 | 0 | 0 | 0 | 43 | 264928 | 244635 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 269674 | 244635 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-02 | QTR3 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 412 | 2546948.04
| 04 | T4489 | 43770115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 3 | 350 | 447 | 437 | 97.14% | 1 | 10 | 0 | 0 | 97 | 0 | 5985000 | 64375 | 5920625 | 6208144 | 6389050 | 0 | 0 | 0 | 6389050 | 6213547 | 104.9% | 1 | -39102 | 223144 | 60 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 88252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506 | 0 | 0 | 0 | 7907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101665 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-07-02 | QTR1 | 20/21 | 408 | 6481016.05
| 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 103.9% | 1 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | 103.4% | 1 | -14110 | 229825 | 55 | 28 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 |  | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93
| 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 102.5% | 1 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | 105.3% | 1 | -2608 | 349724 | 45 | 28 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28
| 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 108.6% | 1 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | 106.2% | 1 | -18 | 103884 | 25 | 23 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65
| 04 | T4499 | 44055425201 | 2019-01-30 | QTR3 | 18/19 | 2 | 5 | 372 | 656 | 601 | 131.7% | 0 | 55 | 0 | 0 | 121 | 163 | 5385476 | 50611 | 5334864 | 8390963 | 8381389 | 0 | 0 | 0 | 8381389 | 8373187 | 157% | 0 | 940 | 3005487 | 61 | 50 | 0 | 140 | 2521590 | 1067356 | 10 | 23 | 240752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 163 | 2768740 | 1067356 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 |  | 2021-01-28 | QTR3 | 20/21 | 408 | 5178383.74
| 04 | T4500 | 43435915201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 349 | 540 | 540 | 116.9% | 1 | 0 | 0 | 0 | 132 | 59 | 2477341 | 50000 | 2427341 | 2477341 | 2598284 | 0 | 0 | 0 | 2598284 | 2597220 | 107% | 1 | -1063 | 0 | 98 | 34 | 0 | 0 | 3012 | 0 | 0 | 59 | 26361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 31204 | 0 | F591358949 | ANZAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-21 | QTR4 | 20/21 |  | 2021-04-26 | QTR4 | 20/21 | 412 | 1937290.89
| 04 | T4501 | 43468615201 | 2019-01-30 | QTR3 | 18/19 | 3 | 2 | 398 | 604 | 604 | 107.3% | 1 | 0 | 0 | 0 | 206 | 0 | 4133433 | 50000 | 4083433 | 4218884 | 4214126 | 0 | 0 | 0 | 4214126 | 4198022 | 102.8% | 1 | -14662 | 85450 | 140 | 37 | 0 | 0 | -83910 | 0 | 0 | 0 | 190412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 106502 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 |  | 2021-03-06 | QTR3 | 20/21 | 412 | 4929152.55
| 04 | T4502 | 43630315202 | 2019-03-27 | QTR3 | 18/19 | 2 | 1 | 205 | 256 | 256 | 100% | 1 | 0 | 0 | 0 | 51 | 0 | 1465257 | 50000 | 1415257 | 1481535 | 1429078 | 0 | 0 | 0 | 1429078 | 1429078 | 101% | 1 | 0 | 16278 | 30 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 13973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30251 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 |  | 2020-06-17 | QTR4 | 19/20 | 412 | 1399471.05
| 04 | T4503 | 43611115201 | 2019-01-30 | QTR3 | 18/19 | 2 | 3 | 205 | 289 | 289 | 112.2% | 1 | 0 | 0 | 0 | 84 | 0 | 2257891 | 50000 | 2207891 | 2372485 | 2277661 | 0 | 0 | 0 | 2277661 | 2279759 | 103.3% | 1 | 2097 | 114594 | 40 | 19 | 14 | 0 | 21562 | 0 | 25 | 0 | 100250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6266 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 136606 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 412 | 2312700.41
| 04 | T4506 | 43783215201 | 2019-04-24 | QTR4 | 18/19 | 1 | 2 | 252 | 390 | 387 | 98.81% | 1 | 3 | 0 | 0 | 138 | 0 | 8509769 | 99739 | 8410031 | 8729916 | 8272368 | 0 | 0 | 0 | 8272368 | 8168439 | 97.13% | 1 | -103929 | 220147 | 112 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 189437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 55163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 244600 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-02-23 | QTR3 | 20/21 |  | 2020-08-11 | QTR1 | 20/21 | 412 | 10259256.99
| 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | 100.1% | 1 | -62 | 0 | 11 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89
| 04 | T4508 | 43773115201 | 2019-03-27 | QTR3 | 18/19 | 9 | 3 | 486 | 593 | 593 | 101% | 1 | 0 | 0 | 0 | 102 | 5 | 6817376 | 73217 | 6744159 | 6968476 | 6729053 | 0 | 0 | 0 | 6729053 | 6684935 | 99.12% | 1 | -33744 | 151101 | 56 | 46 | 0 | 0 | 133625 | 0 | 0 | 0 | 38977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10794 | 0 | 0 | 0 | 1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 184735 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 |  | 2021-02-08 | QTR3 | 20/21 | 412 | 7367257.98
| 04 | T4510 | 43234415201 | 2019-05-22 | QTR4 | 18/19 | 2 | 8 | 430 | 566 | 565 | 99.77% | 1 | 1 | 0 | 0 | 136 | 0 | 8369134 | 9646 | 8359488 | 8429194 | 8328626 | 0 | 0 | 0 | 8328626 | 8158766 | 97.6% | 1 | -169861 | 60060 | 89 | 47 | 0 | 0 | 7635 | 0 | 0 | 0 | 28604 | 947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45448 | 947 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2021-02-16 | QTR3 | 20/21 | 409 | 9265922.68
| 04 | T4513 | 43770815201 | 2019-07-31 | QTR1 | 19/20 | 2 | 0 | 120 | 239 | 234 | 95.83% | 1 | 5 | 0 | 0 | 119 | 0 | 602298 | 27028 | 575270 | 602298 | 562547 | 0 | 0 | 0 | 562547 | 562065 | 97.7% | 1 | -482 | 0 | 110 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6428 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 |  | 2020-09-13 | QTR1 | 20/21 | 412 | 569665.71
| 04 | T4514 | 43778515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 128 | 208 | 208 | 118% | 1 | 0 | 0 | 0 | 57 | 23 | 277929 | 15062 | 262868 | 277929 | 262174 | 0 | 0 | 0 | 262174 | 261778 | 99.59% | 1 | -397 | 0 | 47 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | F261264765 | HIGHSTYLE ENGINEERING & CONSTRUCTION SER | N/A | N/A | N/A | N/A | 2021-04-06 | QTR4 | 20/21 |  | 2020-11-13 | QTR2 | 20/21 | 412 | 312613.57
| 04 | T4518 | 43829115201 | 2019-05-22 | QTR4 | 18/19 | 2 | 0 | 406 | 544 | 544 | 107.4% | 1 | 0 | 0 | 0 | 138 | 0 | 1840414 | 50000 | 1790414 | 1840414 | 1784131 | 0 | 0 | 0 | 1784131 | 1773135 | 99.03% | 1 | -10996 | 0 | 65 | 43 | 30 | 0 | 0 | 0 | 0 | 0 | 13142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 13967 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 |  | 2021-03-10 | QTR3 | 20/21 | 409 | 1949951.04
| 04 | T4520 | 43770215201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 136 | 238 | 235 | 97.79% | 1 | 3 | 0 | 0 | 102 | 0 | 511111 | 24274 | 486837 | 511111 | 500925 | 0 | 0 | 0 | 500925 | 500762 | 102.9% | 1 | -163 | 0 | 96 | 6 | 0 | 0 | 1690 | 0 | 0 | 0 | 12605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14295 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 |  | 2020-08-27 | QTR1 | 20/21 | 412 | 517002.15
| 04 | T4524 | 43770715201 | 2019-05-22 | QTR4 | 18/19 | 1 | 1 | 380 | 456 | 456 | 100.5% | 1 | 0 | 0 | 0 | 74 | 2 | 3289804 | 50000 | 3239804 | 3447958 | 3265220 | 0 | 0 | 0 | 3265220 | 3255145 | 100.5% | 1 | -10075 | 158154 | 32 | 42 | 0 | 2 | 7700 | 0 | 0 | 0 | 173819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 206719 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-18 | QTR4 | 20/21 |  | 2021-01-11 | QTR3 | 20/21 | 412 | 2506277.97
| 04 | T4526 | 43689425201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 360 | 406 | 327 | 78.06% | 1 | 79 | 0 | 0 | 46 | 0 | 2010552 | 50000 | 1960552 | 2002087 | 1918992 | 0 | 0 | 0 | 1918992 | 1917486 | 97.8% | 1 | -1506 | -8465 | 33 | 13 | 0 | 0 | -8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8465 | 0 | F590229150 | EBSARY FOUNDATION COMPANY | N/A | N/A | N/A | N/A | 2021-01-19 | QTR3 | 20/21 |  | 2020-12-11 | QTR2 | 20/21 | 409 | 2144002.51
| 04 | T4529 | 44271915201 | 2019-10-30 | QTR2 | 19/20 | 2 | 1 | 76 | 104 | 86 | 76.32% | 1 | 18 | 0 | 0 | 28 | 0 | 190000 | 7948 | 182052 | 193240 | 183953 | 0 | 0 | 0 | 183953 | 183953 | 101% | 1 | 0 | 3240 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 7433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7433 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-04-08 | QTR4 | 20/21 |  | 2020-09-22 | QTR1 | 20/21 | 412 | 172636.44
| 04 | T4531 | 44313515201 | 2019-10-30 | QTR2 | 19/20 | 3 | 1 | 285 | 314 | 222 | 67.72% | 1 | 92 | 0 | 0 | 29 | 0 | 1219731 | 46309 | 1173423 | 1221270 | 1174601 | 0 | 0 | 0 | 1174601 | 1173062 | 99.97% | 1 | 0 | 1539 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3801 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-01-08 | QTR3 | 20/21 |  | 2020-12-11 | QTR2 | 20/21 | 408 | 921804.84
| 04 | T4534 | 43654115201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 167 | 298 | 298 | 109.6% | 1 | 0 | 0 | 0 | 131 | 0 | 1247199 | 50000 | 1197199 | 1247199 | 1170098 | 0 | 0 | 0 | 1170098 | 1169903 | 97.72% | 1 | -195 | 0 | 95 | 20 | 0 | 0 | 0 | 0 | 16 | 0 | 5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 5589 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2021-03-19 | QTR3 | 20/21 | 412 | 1326125
| 04 | T4536 | 43838915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 274 | 313 | 312 | 99.64% | 1 | 1 | 0 | 0 | 39 | 0 | 1482069 | 50000 | 1432069 | 1482069 | 1327510 | 0 | 0 | 0 | 1327510 | 1325299 | 92.54% | 1 | -2211 | 0 | 15 | 24 | 0 | 0 | 8116 | 0 | 0 | 0 | 5151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13267 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 |  | 2021-02-19 | QTR3 | 20/21 | 409 | 1483089.53
| 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 62.11% | 1 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 91.64% | 1 | 0 | 16665 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 |  | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19
| 04 | T4545 | 43984415201 | 2020-02-26 | QTR3 | 19/20 | 2 | 7 | 198 | 313 | 313 | 117.7% | 1 | 0 | 0 | 0 | 80 | 35 | 2092533 | 50000 | 2042533 | 2459453 | 2601638 | 0 | 0 | 0 | 2601638 | 2600754 | 127.3% | 0 | -884 | 366920 | 59 | 21 | 0 | 0 | 13206 | 0 | 0 | 35 | 358633 | 180233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197 | 0 | 0 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 374481 | 180233 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-06-15 | QTR4 | 20/21 |  | 2021-05-20 | QTR4 | 20/21 | 409 | 2283381.44
| 04 | T4547 | 43838715201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 349 | 379 | 211 | 51.86% | 1 | 168 | 0 | 0 | 30 | 0 | 844444 | 47721 | 796723 | 844444 | 723057 | 0 | 0 | 0 | 723057 | 723057 | 90.75% | 1 | 0 | 0 | 9 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-29 | QTR3 | 20/21 |  | 2021-03-15 | QTR3 | 20/21 | 409 | 1015766.34
| 04 | T4548 | 44368515201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 115 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 255430 | 13096 | 242335 | 255430 | 242375 | 0 | 0 | 0 | 242375 | 242375 | 100% | 1 | 0 | 0 | 19 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 |  | 2021-03-05 | QTR3 | 20/21 | 408 | 277363.65
| 04 | T4549 | 43783015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 180 | 219 | 217 | 98.89% | 1 | 2 | 0 | 0 | 39 | 0 | 1201295 | 50000 | 1151295 | 1201295 | 1104692 | 0 | 0 | 0 | 1104692 | 1104644 | 95.95% | 1 | -48 | 0 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 |  | 2021-02-16 | QTR3 | 20/21 | 412 | 1290271.59
| 04 | T4550 | 43689715201 | 2020-02-26 | QTR3 | 19/20 | 1 | 1 | 216 | 248 | 247 | 99.54% | 1 | 1 | 0 | 0 | 32 | 0 | 1446899 | 50000 | 1396899 | 1473105 | 1500428 | 0 | 0 | 0 | 1500428 | 1500428 | 107.4% | 1 | 0 | 26206 | 12 | 20 | 0 | 0 | 34759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34759 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 |  | 2021-03-15 | QTR3 | 20/21 | 409 | 1630170.95
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 35 | 70 | 92 | 9451 | 13627 | 13144 | 94.29% | 33 | 483 | 6 | 0 | 3143 | 1033 | 118843477 | 1778218 | 117065265 | 126626863 | 123250127 | -21870 | 0 | -21870 | 123228257 | 123237192 | 91.43% | 32 | 261743 | 7783383 | 2048 | 925 | 74 | 301 | 3981053 | 1136899 | 57 | 659 | 3813952 | 740835 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 27 | 44 | 137936 | 1296 | 41 | 14 | 301980 | 32223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -324121 | 0 | 211 | 1033 | 7951411 | 1937018
| 04 | E4M90 | 41242035201 | 2013-04-24 | QTR4 | 12/13 | 7 | 16 | 1141 | 1773 | 1782 | 128% | 0 | -9 | 9 | 0 | 378 | 254 | 66615000 | 150000 | 66465000 | 69280598 | 68971834 | -91753 | 0 | -91753 | 68880082 | 65635992 | 98.75% | 1 | -2942512 | 2665598 | 233 | 88 | 57 | 160 | 2469562 | 690281 | 0 | 13 | -11729 | 0 | 0 | 7 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 19800 | 0 | 0 | 0 | 19625 | 222877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46689 | 0 | 57 | 240 | 2450569 | 913159 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2021-01-27 | QTR3 | 20/21 |  | 2018-06-14 | QTR4 | 17/18 | 409 | 64729280.95 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 119.7% | 1 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | 101.8% | 1 | -998657 | 1434680 | 296 | 112 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 |  | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4T09 | 42264125201 | 2018-06-14 | QTR4 | 17/18 | 2 | 10 | 720 | 883 | 740 | 80.14% | 1 | 143 | 0 | 0 | 163 | 0 | 12892089 | 150000 | 12742089 | 13358507 | 13278726 | 0 | 0 | 0 | 13278726 | 13184941 | 103.5% | 1 | -74765 | 466418 | 118 | 45 | 0 | 0 | 208568 | 13035 | 0 | 0 | 644589 | 13207 | 0 | 0 | 0 | 0 | 0 | 0 | -308042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28215 | 0 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580245 | 26243 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 |  | 2021-04-30 | QTR4 | 20/21 | 408 | 15739611.8
| 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 119.4% | 1 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 106.5% | 1 | 0 | 107565 | 96 | 28 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428
| 04 | E4T54 | 42957525201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 158 | 281 | 242 | 87.97% | 1 | 39 | 0 | 0 | 123 | 0 | 1034836 | 50000 | 984836 | 1034836 | 958378 | 0 | 0 | 0 | 958378 | 958293 | 97.3% | 1 | -85 | 0 | 81 | 22 | 0 | 0 | 11025 | 0 | 5 | 0 | 8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 19498 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 412 | 1135394.39
| 04 | E4T56 | 43578125201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 203 | 306 | 306 | 116.7% | 1 | 0 | 0 | 0 | 103 | 0 | 1488175 | 50000 | 1438175 | 1499756 | 1508806 | 0 | 0 | 0 | 1508806 | 1504997 | 104.6% | 1 | -3808 | 11580 | 44 | 25 | 10 | 0 | 36888 | 0 | 0 | 0 | 10773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 11580 | 11580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 59242 | 11580 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 412 | 1272541.13
| 04 | E4T61 | 43783415201 | 2019-04-05 | QTR4 | 18/19 | 2 | 3 | 355 | 433 | 434 | 100.3% | 1 | -1 | 1 | 0 | 78 | 0 | 5430718 | 52907 | 5377811 | 5477794 | 5212471 | -3447 | 0 | -3447 | 5209024 | 5104984 | 94.93% | 1 | -104039 | 47075 | 44 | 34 | 0 | 0 | 139626 | 0 | 0 | 0 | 16589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -73852 | 0 | 0 | 0 | 82362 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 |  | 2020-12-23 | QTR2 | 20/21 | 409 | 5340256.18
| 04 | E4T65 | 44144215201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 325 | 350 | 203 | 54.77% | 1 | 147 | 0 | 0 | 25 | 0 | 1246700 | 50000 | 1196700 | 1246700 | 1046614 | 0 | 0 | 0 | 1046614 | 1046614 | 87.46% | 1 | 0 | 0 | 3 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2021-04-05 | QTR4 | 20/21 |  | 2021-01-20 | QTR3 | 20/21 | 409 | 2119585.65
| 04 | E4T67 | 43990015201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 171 | 222 | 222 | 100% | 1 | 0 | 0 | 0 | 51 | 0 | 399288 | 21675 | 377614 | 399288 | 314456 | 0 | 0 | 0 | 314456 | 314456 | 83.27% | 1 | 0 | 0 | 36 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 |  | 2020-11-30 | QTR2 | 20/21 | 412 | 459766.37
| 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 35.71% | 1 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 99.76% | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96
| 04 | E4T84 | 43389615201 | 2019-12-06 | QTR2 | 19/20 | 1 | 1 | 80 | 91 | 91 | 81.25% | 1 | 0 | 0 | 0 | 26 | -15 | 802818 | 31559 | 771259 | 802818 | 776329 | 0 | 0 | 0 | 776329 | 776329 | 100.7% | 1 | 0 | 0 | 22 | 4 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 |  | 2020-11-06 | QTR2 | 20/21 | 409 | 659386.45 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4T85 | 43984315201 | 2020-01-03 | QTR3 | 19/20 | 2 | 1 | 246 | 258 | 180 | 68.29% | 1 | 78 | 0 | 0 | 12 | 0 | 3861123 | 52156 | 3808968 | 3862794 | 3684709 | 0 | 325000 | 325000 | 4009709 | 3665629 | 96.24% | 1 | -342410 | 1671 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2021-01-22 | QTR3 | 20/21 |  | 2020-09-10 | QTR1 | 20/21 | 409 | 5435661.92 | B1:B3 | ACC - NO EXCUSE BONUS:ACC - LANE RENTAL
| 04 | E4T86 | 44061215201 | 2020-02-07 | QTR3 | 19/20 | 1 | 1 | 66 | 125 | 125 | 100% | 1 | 0 | 0 | 0 | 59 | 0 | 600421 | 307 | 600114 | 614749 | 545426 | 0 | 0 | 0 | 545426 | 545426 | 90.89% | 1 | 0 | 14328 | 53 | 6 | 0 | 0 | 2938 | 0 | 0 | 0 | 11391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14328 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2021-01-21 | QTR3 | 20/21 |  | 2020-10-09 | QTR2 | 20/21 | 412 | 606555.66
| 04 | E4T88 | 43986015201 | 2020-03-06 | QTR3 | 19/20 | 1 | 1 | 175 | 196 | 174 | 87.43% | 1 | 22 | 0 | 0 | 21 | 0 | 1568562 | 50000 | 1518562 | 1545768 | 1524057 | 0 | 0 | 0 | 1524057 | 1524072 | 100.4% | 1 | 15 | -22794 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | -22794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5165 | 0 | F650405645 | STATE CONTRACTING & ENGINEERING CORPORAT | N/A | N/A | N/A | N/A | 2021-03-03 | QTR3 | 20/21 |  | 2021-01-29 | QTR3 | 20/21 | 409 | 1393385.55
| 04 | E4T89 | 43214615201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 89 | 155 | 153 | 97.75% | 1 | 2 | 0 | 0 | 66 | 0 | 641391 | 39929 | 601462 | 641391 | 602117 | 0 | 0 | 0 | 602117 | 602117 | 100.1% | 1 | 0 | 0 | 48 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4224 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 |  | 2021-02-08 | QTR3 | 20/21 | 412 | 898061.48
| 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 94.48% | 1 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 99.71% | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89
| 04 | E4T92 | 44140915201 | 2020-01-17 | QTR3 | 19/20 | 1 | 1 | 130 | 156 | 131 | 80.77% | 1 | 25 | 0 | 0 | 26 | 0 | 888985 | 50000 | 838985 | 900166 | 850166 | 0 | 0 | 0 | 850166 | 838985 | 100% | 1 | 0 | 11181 | 23 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-09 | QTR2 | 20/21 |  | 2020-11-14 | QTR2 | 20/21 | 408 | 1308480
| 04 | E4U43 | 44332215201 | 2020-04-03 | QTR4 | 19/20 | 1 | 1 | 167 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 444903 | 16132 | 428771 | 444903 | 440091 | 0 | 0 | 0 | 440091 | 440091 | 102.6% | 1 | 0 | 0 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | -8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2021-05-11 | QTR4 | 20/21 |  | 2021-04-16 | QTR4 | 20/21 | 409 | 336190.55
| 04 | E4U55 | 43996115201 | 2020-03-06 | QTR3 | 19/20 | 1 | 0 | 171 | 194 | 188 | 96.49% | 1 | 6 | 0 | 0 | 23 | 0 | 613162 | 28339 | 584823 | 613162 | 583262 | 0 | 0 | 0 | 583262 | 583262 | 99.73% | 1 | 0 | 0 | 6 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-05-20 | QTR4 | 20/21 |  | 2021-03-15 | QTR3 | 20/21 | 409 | 649888.02
| 04 | E4U78 | 4476871H201 | 2020-07-14 | QTR1 | 20/21 | 1 | 7 | 30 | 222 | 222 | 616.7% | 0 | 0 | 0 | 0 | 37 | 155 | 100000 | 0 | 100000 | 15900149 | 15843107 | 0 | 0 | 0 | 15843107 | 0 | 0% | 1 | -15843107 | 15800149 | 21 | 16 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 15734283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 15743107 | 0 | F522113986 | STRUCTURAL TECHNOLOGIES LLC | N/A | N/A | N/A | N/A | 2021-04-27 | QTR4 | 20/21 |  | 2021-02-27 | QTR3 | 20/21 | 408 | 100000
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 20 | 30 | 56 | 6219 | 8684 | 8071 | 90% | 18 | 613 | 10 | 0 | 1794 | 671 | 131062288 | 1064357 | 129997933 | 151599741 | 149984663 | -95200 | 325000 | 229800 | 150214464 | 129509498 | 100% | 20 | -20309368 | 20537451 | 1139 | 504 | 67 | 177 | 3598010 | 885603 | 45 | -2 | 919998 | 24757 | 0 | 7 | 0 | 0 | 0 | 60 | -308042 | 0 | 0 | 0 | 19800 | 0 | 0 | 194 | 16242668 | 226836 | 12 | 221 | 131647 | 111779 | 0 | 0 | 0 | 0 | 0 | 0 | 2611 | 0 | 0 | 0 | 8500 | 0 | 27 | 0 | 27959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120541 | 0 | 151 | 657 | 20522609 | 1248977
| District 04 Totals |  |  |  |  | 55 | 100 | 148 | 15670 | 22311 | 21215 | 92.73% | 51 | 1096 | 16 | 0 | 4937 | 1704 | 249905765 | 2842575 | 247063198 | 278226604 | 273234790 | -117070 | 325000 | 207930 | 273442721 | 252746690 | 94.55% | 52 | -20047625 | 28320834 | 3187 | 1429 | 141 | 478 | 7579063 | 2022502 | 102 | 657 | 4733950 | 765592 | 0 | 7 | 2255 | 0 | 0 | 60 | -308042 | 0 | 0 | 0 | 23800 | 0 | 27 | 238 | 16380604 | 228132 | 53 | 235 | 433627 | 144002 | 0 | 0 | 0 | 0 | 0 | 0 | 2611 | 0 | 0 | 0 | 8500 | 0 | 39 | 15 | 62314 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -444662 | 0 | 362 | 1690 | 28474020 | 3185995
| 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 111.6% | 1 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | 111.1% | 0 | -797738 | 2915022 | 79 | 65 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 |  | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06
| 05 | T5589 | 23827525201 | 2017-06-14 | QTR4 | 16/17 | 4 | 17 | 850 | 1130 | 1095 | 101.9% | 1 | 35 | 0 | 0 | 200 | 80 | 32839302 | 150000 | 32689302 | 33739239 | 34780986 | 0 | -4571 | -4571 | 34776415 | 35569988 | 108.8% | 1 | 827889 | 899937 | 150 | 79 | 0 | 0 | -43955 | 2420 | 0 | 13 | 705345 | 171095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304966 | 64111 | 0 | 11 | 23824 | 13904 | 0 | 0 | 0 | 0 | 0 | 0 | 1542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 991722 | 251530 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 |  |  | QTR2 | 00/01 | 515 | 46309915.72
| 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 83.33% | 1 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | 103% | 1 | -284799 | 843098 | 69 | 32 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76
| 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 101% | 1 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 108.4% | 1 | 353955 | 51986 | 59 | 40 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41
| 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 105.6% | 1 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | 99.8% | 1 | -24609 | 54891 | 45 | 47 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742
| 05 | T5605 | 43565925201 | 2018-03-28 | QTR3 | 17/18 | 4 | 7 | 400 | 813 | 813 | 119.8% | 1 | 0 | 0 | 0 | 334 | 79 | 7668889 | 150000 | 7518889 | 8851634 | 8747850 | -12870 | 0 | -12870 | 8734980 | 8814553 | 117.2% | 0 | 86738 | 1182745 | 278 | 56 | 0 | 2 | 304852 | 1295 | 0 | 48 | 733352 | 29035 | 0 | 0 | 32760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73962 | 28150 | 0 | 0 | 0 | 0 | 0 | 0 | 7236 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 47691 | 47691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1199853 | 106171 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-03-12 | QTR3 | 20/21 |  | 2020-11-19 | QTR2 | 20/21 | 512 | 9666692
| 05 | T5607 | 43612315201 | 2019-10-30 | QTR2 | 19/20 | 1 | 1 | 130 | 186 | 185 | 99.23% | 1 | 1 | 0 | 0 | 56 | 0 | 1114942 | 50000 | 1064942 | 1116831 | 1062929 | 0 | 0 | 0 | 1062929 | 1058191 | 99.37% | 1 | -2848 | 1889 | 39 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-03-12 | QTR3 | 20/21 |  | 2020-12-09 | QTR2 | 20/21 | 514 | 1090281.76
| 05 | T5615 | 43793115201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 200 | 438 | 665 | 309% | 0 | -227 | 227 | 0 | 47 | 191 | 1435273 | 48389 | 1386883 | 1466273 | 1433905 | -119880 | 0 | -119880 | 1314025 | 1313837 | 94.73% | 1 | -188 | 31000 | 20 | 27 | 0 | 0 | 0 | 0 | 0 | 15 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 31450 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 |  | 2020-04-13 | QTR4 | 19/20 | 507 | 1578332.97
| 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 99.92% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8
| 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 108% | 1 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | 101% | 1 | -94321 | 93683 | 136 | 54 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 512 | 12044261
| 05 | T5625 | 42421715201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 480 | 806 | 801 | 114.8% | 1 | 5 | 0 | 0 | 250 | 76 | 7136709 | 75000 | 7061709 | 7786367 | 8041380 | 0 | 0 | 0 | 8041380 | 7881784 | 111.6% | 0 | -123601 | 649658 | 154 | 96 | 0 | 46 | 435937 | 0 | 0 | 30 | 224253 | 69614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 660190 | 69614 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 |  | 2021-04-16 | QTR4 | 20/21 | 507 | 7854126.8
| 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 138.5% | 0 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | 107.8% | 1 | -2583 | 3778 | 20 | 14 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 |  | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9
| 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 102% | 1 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | 101.5% | 1 | -92470 | 42528 | 52 | 32 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 |  | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55
| 05 | T5634 | 43734815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 350 | 469 | 469 | 104.3% | 1 | 0 | 0 | 0 | 104 | 15 | 7052425 | 108401 | 6944024 | 7232569 | 7465970 | 0 | 0 | 0 | 7465970 | 7453020 | 107.3% | 1 | -10558 | 180144 | 49 | 55 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 |  | 2020-07-26 | QTR1 | 20/21 | 515 | 10311527.59
| 05 | T5648 | 43759515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 1 | 250 | 374 | 344 | 97.6% | 1 | 30 | 0 | 0 | 100 | 24 | 2614878 | 50000 | 2564878 | 2614878 | 2572113 | 0 | 0 | 0 | 2572113 | 2540351 | 99.04% | 1 | -31762 | 0 | 64 | 36 | 0 | 0 | 0 | 0 | 0 | 24 | 7039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 7039 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 |  | 2020-10-01 | QTR2 | 20/21 | 513 | 3184786.93
| 05 | T5649 | 43747015201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 250 | 493 | 526 | 176% | 0 | -33 | 33 | 0 | 86 | 157 | 1816910 | 50000 | 1766910 | 1816910 | 1789398 | -54945 | 0 | -54945 | 1734453 | 1734453 | 98.16% | 1 | 0 | 0 | 30 | 56 | 0 | 0 | 0 | 0 | 0 | 157 | 18121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 18121 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2021-01-21 | QTR3 | 20/21 | 509 | 2329182
| 05 | T5652 | 43097555201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 290 | 314 | 290 | 91.72% | 1 | 24 | 0 | 0 | 24 | 0 | 2616100 | 50000 | 2566100 | 2718053 | 2707282 | 0 | 0 | 0 | 2707282 | 2685273 | 104.6% | 1 | -22009 | 101953 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 101953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101953 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-19 | QTR3 | 20/21 |  | 2020-12-18 | QTR2 | 20/21 | 515 | 3057554.72
| 05 | T5653 | 43967915201 | 2019-03-27 | QTR3 | 18/19 | 1 | 2 | 140 | 372 | 337 | 184.3% | 0 | 35 | 0 | 0 | 79 | 153 | 782050 | 37000 | 745050 | 805120 | 729222 | 0 | 0 | 0 | 729222 | 728882 | 97.83% | 1 | -340 | 23070 | 53 | 26 | 0 | 0 | 6257 | 0 | 0 | 153 | 16813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 23070 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 |  | 2020-09-30 | QTR1 | 20/21 | 509 | 797259.75
| 05 | T5660 | 24099255201 | 2018-10-31 | QTR2 | 18/19 | 3 | 5 | 430 | 611 | 611 | 113.3% | 1 | 0 | 0 | 0 | 124 | 57 | 4991772 | 107663 | 4884109 | 5081949 | 5090998 | 0 | 0 | 0 | 5090998 | 5004860 | 102.5% | 1 | -78604 | 90177 | 76 | 48 | 0 | 49 | 42996 | 0 | 0 | 8 | 57439 | 2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 100436 | 2168 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 |  | 2020-11-17 | QTR2 | 20/21 | 513 | 4917854.1
| 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 100% | 1 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | 99.52% | 1 | -49387 | 3208 | 82 | 43 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78
| 05 | T5677 | 43923315201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 160 | 196 | 195 | 99.38% | 1 | 1 | 0 | 0 | 36 | 0 | 6452955 | 68620 | 6384335 | 6597931 | 6823659 | 0 | 0 | 0 | 6823659 | 6790182 | 106.4% | 1 | -33477 | 144976 | 26 | 10 | 0 | 0 | 4727 | 0 | 0 | 0 | 144976 | 9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149703 | 9705 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-30 | QTR2 | 20/21 |  | 2020-09-23 | QTR1 | 20/21 | 514 | 7161772.24 | B0 | ACC - LUMP SUM
| 05 | T5714 | 44137015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 120 | 140 | 137 | 97.5% | 1 | 3 | 0 | 0 | 20 | 0 | 531915 | 26950 | 504965 | 531915 | 514987 | 0 | 0 | 0 | 514987 | 514987 | 102% | 1 | 0 | 0 | 4 | 16 | 0 | 0 | 6829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12250 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-03-26 | QTR3 | 20/21 |  | 2021-02-18 | QTR3 | 20/21 | 515 | 535536.17
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 22 | 46 | 90 | 7590 | 11160 | 11068 | 81.82% | 18 | 92 | 260 | 0 | 2403 | 1167 | 191219742 | 1780614 | 189439127 | 198533484 | 202311510 | -207905 | 582122 | 374217 | 202685726 | 201615288 | 86.36% | 19 | -380712 | 7313743 | 1524 | 866 | 42 | 104 | 1741006 | 3715 | 0 | 732 | 5208220 | 440125 | 0 | 0 | 32760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348045 | 67721 | 0 | 14 | 168111 | 101345 | 0 | 0 | 0 | 0 | 0 | 0 | 8778 | 0 | 0 | 176 | 31000 | 0 | 0 | 64 | 53112 | 47691 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 42 | 1090 | 7412344 | 660597
| 05 | E50A1 | 44327115201 | 2020-02-04 | QTR3 | 19/20 | 1 | 0 | 130 | 135 | 125 | 92.31% | 1 | 10 | 0 | 0 | 5 | 0 | 258893 | 12893 | 246000 | 258893 | 238371 | 0 | 0 | 0 | 238371 | 238371 | 96.9% | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2021-02-04 | QTR3 | 20/21 |  | 2020-10-23 | QTR2 | 20/21 | 513 | 275763
| 05 | E50A4 | 43754315201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 180 | 285 | 282 | 98.33% | 1 | 3 | 0 | 0 | 105 | 0 | 7148284 | 75220 | 7073064 | 7148284 | 7569825 | 0 | 0 | 0 | 7569825 | 7442288 | 105.2% | 1 | -127537 | 0 | 82 | 23 | 0 | 0 | 20101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20101 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2021-02-12 | QTR3 | 20/21 | 509 | 7601971.91
| 05 | E52A4 | 44539715201 | 2020-09-01 | QTR1 | 20/21 | 1 | 0 | 90 | 90 | 54 | 60% | 1 | 36 | 0 | 0 | 0 | 0 | 220607 | 12082 | 208525 | 220607 | 186260 | 0 | 0 | 0 | 186260 | 186260 | 89.32% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 |  | 2021-01-08 | QTR3 | 20/21 | 507 | 258724.75
| 05 | E53A0 | 44327015201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 218 | 155 | 65% | 1 | 63 | 0 | 0 | 38 | 0 | 341127 | 18594 | 322533 | 328648 | 362626 | 0 | 0 | 0 | 362626 | 362626 | 112.4% | 0 | 0 | -12479 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | -12479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12479 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 |  | 2020-11-17 | QTR2 | 20/21 | 512 | 395487.73
| 05 | E54A5 | 44417615201 | 2020-06-02 | QTR4 | 19/20 | 1 | 0 | 90 | 169 | 165 | 95.56% | 1 | 4 | 0 | 0 | 79 | 0 | 755986 | 39900 | 716086 | 755986 | 748590 | 0 | 0 | 0 | 748590 | 748590 | 104.5% | 1 | 0 | 0 | 52 | 27 | 0 | 0 | 3648 | 0 | 0 | 0 | 8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12434 | 0 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2021-06-23 | QTR4 | 20/21 |  | 2021-03-17 | QTR3 | 20/21 | 514 | 843431.25
| 05 | E5W26 | 24271525201 | 2014-09-05 | QTR1 | 14/15 | 3 | 7 | 1100 | 1747 | 2097 | 149.7% | 0 | -350 | 350 | 0 | 450 | 197 | 204975000 | 150000 | 204825000 | 206461939 | 205886429 | -5989463 | 1323936 | -4665526 | 201220903 | 190316791 | 92.92% | 1 | -10375239 | 1486939 | 258 | 192 | 0 | 0 | 153517 | 0 | 0 | 30 | 575563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 771389 | 0 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-05-13 | QTR4 | 20/21 |  | 2020-08-21 | QTR1 | 20/21 | 513 | 204975000 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y62 | 23831925201 | 2017-03-21 | QTR3 | 16/17 | 3 | 6 | 950 | 1198 | 1188 | 109.8% | 1 | 10 | 0 | 0 | 145 | 103 | 22219000 | 150000 | 22069000 | 22351916 | 22222555 | 0 | 0 | 0 | 22222555 | 22255595 | 100.8% | 1 | 54139 | 132916 | 69 | 76 | 0 | 0 | 40787 | 0 | 0 | 0 | 90621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 14091 | 0 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 156363 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2020-10-30 | QTR2 | 20/21 |  | 2020-09-14 | QTR1 | 20/21 | 515 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Z19 | 43927315201 | 2018-04-03 | QTR4 | 17/18 | 1 | 0 | 130 | 145 | 501 | 373.8% | 0 | -356 | 356 | 0 | 15 | 0 | 149935 | 9480 | 140455 | 149935 | 128601 | -51092 | 0 | -51092 | 77509 | 77509 | 55.18% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-05-27 | QTR4 | 19/20 | 513 | 204099
| 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 124% | 0 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 102.8% | 1 | 0 | 0 | 10 | 35 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 |  | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8
| 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | 294.5% | 0 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 79.35% | 1 | 0 | 0 | 2 | 18 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2019-10-17 | QTR2 | 19/20 | 513 | 307382
| 05 | E5Z32 | 43927515201 | 2018-02-06 | QTR3 | 17/18 | 2 | 1 | 680 | 927 | 912 | 97.79% | 1 | 15 | 0 | 0 | 247 | 0 | 3899386 | 50000 | 3849386 | 3941689 | 3941568 | 0 | 0 | 0 | 3941568 | 3896961 | 101.2% | 1 | -2304 | 42303 | 188 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 |  | 2020-11-05 | QTR2 | 20/21 | 514 | 4041614
| 05 | E5Z46 | 44116815201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 136 | 657 | 715 | 351.5% | 0 | -58 | 58 | 0 | 256 | 265 | 546235 | 28279 | 517956 | 620855 | 527394 | -96570 | 0 | -96570 | 430824 | 526966 | 101.7% | 1 | 96143 | 74620 | 208 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 245 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 |  | 2021-02-12 | QTR3 | 20/21 | 514 | 603864
| 05 | E5Z61 | 43544625201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 550 | 693 | 693 | 100% | 1 | 0 | 0 | 0 | 143 | 0 | 2660660 | 50000 | 2610660 | 2660660 | 2610660 | 0 | 0 | 0 | 2610660 | 2610660 | 100% | 1 | 0 | 0 | 63 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2021-05-27 | QTR4 | 20/21 |  | 2021-03-30 | QTR3 | 20/21 | 509 | 2903534 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5Z64 | 44121015201 | 2018-08-07 | QTR1 | 18/19 | 2 | 7 | 420 | 552 | 552 | 111% | 1 | 0 | 0 | 0 | 86 | 46 | 4022402 | 50000 | 3972402 | 4286073 | 4275710 | 0 | 0 | 0 | 4275710 | 4234199 | 106.6% | 1 | -37972 | 263671 | 31 | 55 | 0 | 0 | 124080 | 0 | 0 | 46 | 104836 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40146 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 274759 | 14901 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 |  | 2020-07-07 | QTR1 | 20/21 | 513 | 4100417.85
| 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 111.7% | 1 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | 99.98% | 1 | -199 | 4115 | 84 | 25 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6
| 05 | E5Z77 | 43912115201 | 2019-07-02 | QTR1 | 19/20 | 2 | 1 | 200 | 327 | 326 | 99.5% | 1 | 1 | 0 | 0 | 127 | 0 | 3278490 | 50000 | 3228490 | 3271086 | 3476815 | 0 | 0 | 0 | 3476815 | 3410719 | 105.6% | 1 | -66096 | -7404 | 72 | 55 | 0 | 0 | 23209 | 0 | 0 | 0 | -7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15805 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 |  | 2020-08-17 | QTR1 | 20/21 | 513 | 3806383.67
| 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | 187.3% | 0 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 94.9% | 1 | 0 | 0 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-08-11 | QTR1 | 20/21 | 513 | 141232
| 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 99.39% | 1 | 0 | 0 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9
| 05 | E5Z85 | 43923615201 | 2019-08-06 | QTR1 | 19/20 | 1 | 1 | 130 | 222 | 237 | 148.5% | 0 | -15 | 15 | 0 | 44 | 48 | 1444444 | 50000 | 1394444 | 1444444 | 1364062 | -69930 | 0 | -69930 | 1294132 | 1282257 | 91.95% | 1 | -11875 | 0 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 |  | 2020-07-28 | QTR1 | 20/21 | 509 | 1314465.56
| 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 96.7% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25
| 05 | E5Z91 | 43912215201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 115 | 121 | 120 | 99.13% | 1 | 1 | 0 | 0 | 6 | 0 | 1447000 | 50000 | 1397000 | 1447000 | 1407072 | 0 | 0 | 0 | 1407072 | 1407072 | 100.7% | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 |  | 2020-05-19 | QTR4 | 19/20 | 509 | 1302060.71
| 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 98.89% | 1 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 105.3% | 1 | 0 | 0 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5
| 05 | E5Z98 | 43618725201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 90 | 124 | 125 | 101.1% | 1 | -1 | 1 | 0 | 34 | 0 | 675628 | 31129 | 644499 | 675628 | 649188 | 0 | 0 | 0 | 649188 | 649188 | 100.7% | 1 | 0 | 0 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2020-11-25 | QTR2 | 20/21 |  | 2020-08-13 | QTR1 | 20/21 | 514 | 631570
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 23 | 32 | 30 | 6160 | 8991 | 9917 | 69.57% | 16 | -926 | 1071 | 0 | 2081 | 750 | 257929910 | 991223 | 256938687 | 259914591 | 259301798 | -6215731 | 1323936 | -4891794 | 254410004 | 243339134 | 95.65% | 22 | -10470940 | 1984681 | 1244 | 796 | 4 | 20 | 366434 | 0 | 18 | 193 | 764379 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 101180 | 3472 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 563 | 1248555 | 14901
| District 05 Totals |  |  |  |  | 45 | 78 | 120 | 13750 | 20151 | 20985 | 75.56% | 34 | -834 | 1331 | 0 | 4484 | 1917 | 449149652 | 2771837 | 446377814 | 458448075 | 461613308 | -6423636 | 1906058 | -4517577 | 457095730 | 444954422 | 91.11% | 41 | -10851652 | 9298424 | 2768 | 1662 | 46 | 124 | 2107440 | 3715 | 18 | 925 | 5972599 | 451554 | 0 | 0 | 32760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 449225 | 71193 | 0 | 15 | 178975 | 101345 | 0 | 0 | 0 | 0 | 0 | 0 | 14475 | 0 | 0 | 176 | 31000 | 0 | 0 | 64 | 53112 | 47691 | 19 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 83 | 1653 | 8660899 | 675498
| 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 84.25% | 1 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | 90.62% | 1 | -289635 | -403730 | 22 | 17 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 |  | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 86% | 1 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | 102.7% | 1 | -2140213 | 1115676 | 16 | 11 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 |  | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6424 | 42736915201 | 2019-04-24 | QTR4 | 18/19 | 3 | 8 | 385 | 412 | 361 | 86.75% | 1 | 51 | 0 | 0 | 27 | 0 | 31696367 | 150560 | 31545807 | 32356389 | 32549528 | 0 | 2000000 | 2000000 | 34549528 | 32091160 | 101.7% | 1 | -2458368 | 660022 | 12 | 15 | 0 | 0 | 835731 | 0 | 0 | 0 | 255737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -351436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33504 | 0 | 0 | 0 | 3031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709560 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-03-16 | QTR3 | 20/21 |  | 2021-01-15 | QTR3 | 20/21 | 636 | 37329749.69 | B5:B2:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 109.4% | 1 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 96.45% | 1 | 578 | 96399 | 60 | 44 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 78.21% | 1 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | 100.8% | 1 | -201766 | 12198 | 24 | 25 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6442 | 43063735201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 419 | 517 | 474 | 99.28% | 1 | 43 | 0 | 0 | 58 | 40 | 12892744 | 274969 | 12617775 | 13383683 | 13072251 | 0 | 790000 | 790000 | 13862251 | 12904020 | 102.3% | 1 | -845455 | 490939 | 35 | 23 | 0 | 40 | 504378 | 375054 | 0 | 0 | 22795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 550031 | 375054 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 |  | 2020-05-01 | QTR4 | 19/20 | 606 | 14924931.96 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6447 | 43791515201 | 2019-04-24 | QTR4 | 18/19 | 4 | 2 | 250 | 272 | 239 | 86.8% | 1 | 33 | 0 | 0 | 22 | 0 | 2469000 | 50215 | 2418785 | 2562153 | 2344210 | 0 | 150000 | 150000 | 2494210 | 2343341 | 96.88% | 1 | -150869 | 93153 | 14 | 8 | 0 | 0 | 48601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44551 | 4910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93153 | 4910 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 |  | 2020-09-29 | QTR1 | 20/21 | 636 | 2116609.4 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6449 | 43345545201 | 2019-02-27 | QTR3 | 18/19 | 4 | 3 | 280 | 311 | 311 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 2745127 | 50000 | 2695127 | 2934099 | 2882088 | 0 | 0 | 0 | 2882088 | 2869467 | 106.5% | 1 | -12621 | 188972 | 8 | 23 | 0 | 0 | 201958 | 20245 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14623 | 0 | 0 | 0 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221836 | 20245 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 |  | 2020-08-19 | QTR1 | 20/21 | 606 | 2941132.7
| 06 | T6450 | 40557565201 | 2019-06-12 | QTR4 | 18/19 | 4 | 11 | 400 | 424 | 380 | 89% | 1 | 44 | 0 | 0 | 24 | 0 | 16353017 | 242694 | 16110323 | 17066081 | 16492362 | 0 | 1340000 | 1340000 | 17832362 | 16289899 | 101.1% | 1 | -1542462 | 713064 | 5 | 19 | 0 | 0 | 385449 | 21500 | 0 | 0 | 206212 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104075 | 54241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847864 | 76615 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-06-24 | QTR4 | 20/21 |  | 2021-03-30 | QTR3 | 20/21 | 606 | 18314994.47 | B2:B5:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6456 | 44001315201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 140 | 149 | 132 | 87.86% | 1 | 17 | 0 | 0 | 9 | 0 | 277873 | 14914 | 262959 | 277873 | 253147 | 0 | 0 | 0 | 253147 | 252697 | 96.1% | 1 | -451 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115 | 0 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2021-01-13 | QTR3 | 20/21 |  | 2020-08-27 | QTR1 | 20/21 | 613 | 307708.25
| 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 117.9% | 1 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 97.66% | 1 | 81 | 0 | 77 | 34 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 |  | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5
| 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 112.1% | 1 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | 96.93% | 1 | -1589 | 27177 | 90 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35
| 06 | T6463 | 43791615201 | 2019-01-30 | QTR3 | 18/19 | 4 | 0 | 160 | 220 | 219 | 99.38% | 1 | 1 | 0 | 0 | 60 | 0 | 893110 | 47891 | 845219 | 893110 | 829996 | 0 | 0 | 0 | 829996 | 829996 | 98.2% | 1 | 0 | 0 | 47 | 13 | 0 | 0 | 3918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 4477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11695 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-02-15 | QTR3 | 20/21 |  | 2020-08-10 | QTR1 | 20/21 | 613 | 974751.05
| 06 | T6464 | 43908815201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 300 | 409 | 389 | 102.3% | 1 | 20 | 0 | 0 | 109 | 0 | 2747184 | 50000 | 2697184 | 2747184 | 2689934 | 0 | 160000 | 160000 | 2849934 | 2684826 | 99.54% | 1 | -165108 | 0 | 55 | 27 | 0 | 0 | 12619 | 0 | 0 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33650 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 |  | 2021-01-28 | QTR3 | 20/21 | 613 | 2857611.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | 103.6% | 1 | -846 | 30818 | 24 | 22 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8
| 06 | T6471 | 43998315201 | 2019-10-30 | QTR2 | 19/20 | 3 | 1 | 200 | 257 | 257 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 1419001 | 50000 | 1369001 | 1428592 | 1341311 | 0 | 0 | 0 | 1341311 | 1340742 | 97.94% | 1 | -569 | 9591 | 36 | 21 | 0 | 0 | 9103 | 0 | 0 | 0 | 4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14767 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 |  | 2021-03-19 | QTR3 | 20/21 | 636 | 1482286.6
| 06 | T6473 | 43326425201 | 2020-01-29 | QTR3 | 19/20 | 2 | 0 | 240 | 279 | 215 | 73.33% | 1 | 64 | 0 | 0 | 39 | 0 | 1569997 | 50995 | 1519002 | 1569997 | 1553340 | 0 | 100000 | 100000 | 1653340 | 1548938 | 102% | 1 | -104402 | 0 | 30 | 9 | 0 | 0 | 14486 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32803 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-02-26 | QTR3 | 20/21 |  | 2020-11-20 | QTR2 | 20/21 | 636 | 1744257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6474 | 43991915201 | 2019-10-30 | QTR2 | 19/20 | 2 | 0 | 280 | 327 | 264 | 77.5% | 1 | 63 | 0 | 0 | 47 | 0 | 2171998 | 50000 | 2121998 | 2171998 | 2087179 | 0 | 80000 | 80000 | 2167179 | 2084071 | 98.21% | 1 | -83108 | 0 | 34 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 14701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14701 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 |  | 2020-10-05 | QTR2 | 20/21 | 613 | 1943700.4 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6477 | 44281315201 | 2019-03-27 | QTR3 | 18/19 | 9 | 4 | 360 | 432 | 432 | 105% | 1 | 0 | 0 | 0 | 54 | 18 | 2060596 | 50000 | 2010596 | 2075271 | 2107347 | 0 | 0 | 0 | 2107347 | 2106923 | 104.8% | 1 | -424 | 14675 | 29 | 25 | 0 | 18 | 12276 | 0 | 0 | 0 | 18162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 53089 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2020-12-14 | QTR2 | 20/21 |  | 2020-10-09 | QTR2 | 20/21 | 606 | 2038302.5
| 06 | T6484 | 44017515201 | 2019-09-25 | QTR1 | 19/20 | 2 | 0 | 180 | 300 | 300 | 117.2% | 1 | 0 | 0 | 0 | 120 | 0 | 800000 | 41439 | 758561 | 800000 | 759142 | 0 | 0 | 0 | 759142 | 758896 | 100% | 1 | -246 | 0 | 64 | 25 | 0 | 0 | 3076 | 0 | 0 | 0 | 5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13058 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 |  | 2021-01-13 | QTR3 | 20/21 | 636 | 865771.05
| 06 | T6499 | 43992215201 | 2020-01-29 | QTR3 | 19/20 | 2 | 0 | 160 | 182 | 135 | 70.62% | 1 | 47 | 0 | 0 | 22 | 0 | 630688 | 29131 | 601557 | 630688 | 630936 | 0 | 0 | 0 | 630936 | 630438 | 104.8% | 1 | -499 | 0 | 18 | 4 | 0 | 0 | 8611 | 0 | 0 | 0 | 4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16057 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 |  | 2020-12-01 | QTR2 | 20/21 | 636 | 547117.1
| 06 | T6523 | 42918535201 | 2020-01-29 | QTR3 | 19/20 | 2 | 2 | 250 | 307 | 230 | 69.2% | 1 | 77 | 0 | 0 | 57 | 0 | 1588502 | 50000 | 1538502 | 1626096 | 1468338 | 0 | 100000 | 100000 | 1568338 | 1462739 | 95.08% | 1 | -101006 | 37594 | 45 | 12 | 0 | 0 | 12813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37551 | 19916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50364 | 19916 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 |  | 2020-12-27 | QTR2 | 20/21 | 613 | 1654598.85 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 22 | 74 | 53 | 6074 | 7473 | 6823 | 100% | 22 | 650 | 0 | 0 | 1341 | 58 | 133607016 | 1635783 | 131971233 | 136693564 | 134310147 | 0 | 7340000 | 7340000 | 141650147 | 133351861 | 100% | 22 | -8098978 | 3086548 | 749 | 429 | 75 | 58 | 2426916 | 423728 | 0 | 0 | 810141 | 21566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578548 | 24826 | 0 | 0 | 173412 | 0 | 0 | 0 | -33504 | 0 | 0 | 0 | 27789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104075 | 54241 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 75 | 58 | 3633909 | 524360
| 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 47.33% | 1 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 94.14% | 1 | 0 | 0 | 30 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95
| 06 | E6J97 | 43338115201 | 2016-09-29 | QTR1 | 16/17 | 3 | 5 | 700 | 1353 | 1353 | 140.3% | 0 | 0 | 0 | 0 | 371 | 282 | 14830791 | 150000 | 14680791 | 16868333 | 16284955 | 0 | 0 | 0 | 16284955 | 13510574 | 92.03% | 1 | -2748287 | 2037542 | 277 | 94 | 0 | 0 | 189712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 1897649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 2102488 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-03-17 | QTR3 | 20/21 |  | 2020-12-23 | QTR2 | 20/21 | 606 | 15266369.1
| 06 | E6K57 | 43854015201 | 2017-05-15 | QTR4 | 16/17 | 1 | 0 | 750 | 1065 | 881 | 84.13% | 1 | 184 | 0 | 0 | 315 | 0 | 3582848 | 50000 | 3532848 | 3582848 | 3528511 | 0 | 0 | 0 | 3528511 | 3528511 | 99.88% | 1 | 0 | 0 | 168 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-10-23 | QTR2 | 20/21 |  | 2020-09-09 | QTR1 | 20/21 | 606 | 3999000 | LBDB | LOW BID DESIGN BUILD
| 06 | E6K74 | 43652715201 | 2019-04-25 | QTR4 | 18/19 | 1 | 0 | 300 | 359 | 351 | 97.33% | 1 | 8 | 0 | 0 | 59 | 0 | 4041049 | 50000 | 3991049 | 4041049 | 3981909 | 0 | 0 | 0 | 3981909 | 3981877 | 99.77% | 1 | -32 | 0 | 37 | 22 | 0 | 0 | 13129 | 0 | 0 | 0 | 16554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29684 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 |  | 2021-01-25 | QTR3 | 20/21 | 613 | 4437637.8
| 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 111.7% | 0 | 0 | 139878 | 27 | 23 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132
| 06 | E6L73 | 44183715201 | 2019-03-28 | QTR3 | 18/19 | 3 | 0 | 180 | 256 | 253 | 98.33% | 1 | 3 | 0 | 0 | 76 | 0 | 1046629 | 50000 | 996629 | 1046629 | 1032137 | 0 | 0 | 0 | 1032137 | 1030814 | 103.4% | 1 | -1322 | 0 | 49 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 613 | 1027325.45
| 06 | E6L77 | 44059015201 | 2019-02-28 | QTR3 | 18/19 | 1 | 0 | 150 | 227 | 212 | 90% | 1 | 15 | 0 | 0 | 77 | 0 | 569569 | 25452 | 544117 | 569569 | 532425 | 0 | 0 | 0 | 532425 | 532327 | 97.83% | 1 | -98 | 0 | 65 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 |  | 2020-08-04 | QTR1 | 20/21 | 613 | 521617.9
| 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 61.43% | 1 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | 95.7% | 1 | -189 | -1000 | 35 | 1 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15
| 06 | E6L95 | 44174015201 | 2019-10-31 | QTR2 | 19/20 | 1 | 1 | 290 | 307 | 247 | 79.31% | 1 | 60 | 0 | 0 | 17 | 0 | 6166186 | 64668 | 6101518 | 6166186 | 6056649 | 0 | 796000 | 796000 | 6852649 | 6054106 | 99.22% | 1 | -798543 | 0 | 14 | 3 | 0 | 0 | 7070 | 0 | 0 | 0 | 34534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50206 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 |  | 2020-11-17 | QTR2 | 20/21 | 636 | 6464443.31 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6M35 | 42934165201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 140 | 213 | 201 | 91.43% | 1 | 12 | 0 | 0 | 73 | 0 | 550550 | 26336 | 524214 | 550550 | 522745 | 0 | 0 | 0 | 522745 | 522024 | 99.58% | 1 | -721 | 0 | 54 | 19 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-18 | QTR3 | 20/21 |  | 2021-02-05 | QTR3 | 20/21 | 636 | 547294.25
| 06 | E6M59 | 43634425201 | 2020-02-27 | QTR3 | 19/20 | 1 | 0 | 100 | 124 | 124 | 109% | 1 | 0 | 0 | 0 | 24 | 0 | 548409 | 24409 | 524000 | 548409 | 466503 | 0 | 0 | 0 | 466503 | 466503 | 89.03% | 1 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 |  | 2020-10-10 | QTR2 | 20/21 | 636 | 490515.2
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 11 | 17 | 11 | 3325 | 4762 | 4268 | 90.91% | 10 | 494 | 0 | 0 | 1155 | 282 | 34511913 | 562425 | 33949488 | 36688333 | 35555205 | 0 | 796000 | 796000 | 36351205 | 32767730 | 90.91% | 10 | -3549192 | 2176420 | 765 | 316 | 0 | 0 | 232020 | 0 | 0 | 0 | 196671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 1963253 | 0 | 0 | 0 | 1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 282 | 2408674 | 0
| District 06 Totals |  |  |  |  | 33 | 91 | 64 | 9399 | 12235 | 11091 | 96.97% | 32 | 1144 | 0 | 0 | 2496 | 340 | 168118929 | 2198208 | 165920721 | 173381897 | 169865352 | 0 | 8136000 | 8136000 | 178001352 | 166119591 | 96.97% | 32 | -11648170 | 5262968 | 1514 | 745 | 75 | 58 | 2658936 | 423728 | 0 | 0 | 1006812 | 21566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 2541801 | 24826 | 0 | 0 | 175013 | 0 | 0 | 0 | -33504 | 0 | 0 | 0 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104075 | 54241 | 9 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 84 | 340 | 6042583 | 524360
| 07 | T7375 | 25729865201 | 2017-02-22 | QTR3 | 16/17 | 2 | 6 | 335 | 578 | 588 | 135.5% | 0 | -10 | 10 | 0 | 134 | 109 | 8414444 | 81000 | 8333444 | 8827124 | 8758066 | -36450 | 0 | -36450 | 8721616 | 8915602 | 107% | 1 | 257489 | 411474 | 99 | 35 | 0 | 11 | 14363 | 5606 | 0 | 83 | 164873 | 25488 | 0 | 0 | 15135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 208722 | 31094 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-04-08 | QTR4 | 20/21 |  | 2019-01-22 | QTR3 | 18/19 | 798 | 9174081.12 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7403 | 43484815201 | 2018-05-23 | QTR4 | 17/18 | 4 | 11 | 365 | 520 | 520 | 113.4% | 1 | 0 | 0 | 0 | 106 | 49 | 15246325 | 150000 | 15096325 | 16369545 | 16674514 | 0 | 0 | 0 | 16674514 | 16720307 | 110.8% | 0 | 65791 | 1123220 | 63 | 43 | 0 | 14 | 656978 | 126004 | 0 | 35 | 570684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28923 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1198739 | 126713 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 |  | 2020-03-24 | QTR3 | 19/20 | 796 | 16929302.14
| 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 84% | 1 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | 107.8% | 1 | -14840 | 688152 | 70 | 32 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 |  | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63
| 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 119.6% | 1 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | 99.14% | 1 | -20 | 0 | 91 | 73 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8
| 07 | T7413 | 43658815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 480 | 699 | 697 | 103.5% | 1 | 2 | 0 | 0 | 200 | 19 | 26892177 | 150000 | 26742177 | 27245569 | 27594120 | -41000 | 0 | -41000 | 27553120 | 27404700 | 102.5% | 1 | -148420 | 353392 | 151 | 49 | 0 | 0 | 138794 | 0 | 0 | 19 | 407728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 0 | 19 | 422365 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-12-30 | QTR2 | 20/21 |  | 2020-08-27 | QTR1 | 20/21 | 714 | 31660666.96
| 07 | T7414 | 43571915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 7 | 275 | 584 | 562 | 130.5% | 0 | 22 | 0 | 0 | 203 | 106 | 2614444 | 50000 | 2564444 | 2751684 | 2735520 | 0 | 0 | 0 | 2735520 | 2737146 | 106.7% | 1 | 1626 | 137240 | 161 | 42 | 0 | 0 | 51550 | 0 | 0 | 106 | 99770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 151320 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 |  | 2020-01-21 | QTR3 | 19/20 | 799 | 3125000
| 07 | T7419 | 43050225201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 272 | 272 | 183.3% | 0 | 0 | 0 | 0 | 52 | 100 | 987665 | 50000 | 937665 | 987665 | 987634 | 0 | 0 | 0 | 987634 | 987634 | 105.3% | 1 | 0 | 0 | 27 | 25 | 0 | 100 | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 31825 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-03-14 | QTR3 | 19/20 | 796 | 1403000
| 07 | T7420 | 43982945201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 365 | 523 | 584 | 116.7% | 1 | -61 | 61 | 0 | 158 | 0 | 1212499 | 50000 | 1162499 | 1212499 | 1154516 | -101565 | 0 | -101565 | 1052951 | 1052959 | 90.58% | 1 | 8 | 0 | 108 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2021-01-15 | QTR3 | 20/21 | 796 | 1500000
| 07 | T7425 | 43982965201 | 2019-09-25 | QTR1 | 19/20 | 2 | 2 | 185 | 228 | 228 | 108.6% | 1 | 0 | 0 | 0 | 27 | 16 | 914914 | 49000 | 865914 | 939896 | 895662 | 0 | 0 | 0 | 895662 | 895638 | 103.4% | 1 | -24 | 24982 | 18 | 9 | 0 | 1 | 1723 | 0 | 0 | 15 | 25632 | 14104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 27355 | 14104 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 |  | 2020-11-06 | QTR2 | 20/21 | 798 | 1060000
| 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 98.33% | 1 | 4907 | 45939 | 13 | 11 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185
| 07 | T7431 | 41685615201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 200 | 352 | 391 | 119.5% | 1 | -39 | 39 | 0 | 152 | 0 | 2024792 | 50000 | 1974792 | 2024792 | 1923484 | -64935 | 0 | -64935 | 1858549 | 1857569 | 94.06% | 1 | -979 | 0 | 81 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-02-09 | QTR3 | 20/21 |  | 2020-10-19 | QTR2 | 20/21 | 796 | 2200000
| 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | 92.73% | 1 | -16 | 0 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 799 | 490000
| 07 | T7435 | 43731215201 | 2019-10-30 | QTR2 | 19/20 | 1 | 2 | 425 | 535 | 345 | 67.53% | 1 | 190 | 0 | 0 | 58 | 52 | 20077627 | 150000 | 19927627 | 19707738 | 19775513 | 0 | 1600000 | 1600000 | 21375513 | 19707851 | 98.9% | 1 | -1667662 | -369888 | 46 | 12 | 0 | 0 | -369888 | 0 | 0 | 0 | 15538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -354350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 |  | 2020-12-16 | QTR2 | 20/21 | 796 | 32430000 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7436 | 43648515201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 270 | 348 | 313 | 87.04% | 1 | 35 | 0 | 0 | 38 | 40 | 6816208 | 60000 | 6756208 | 6816208 | 6910378 | 0 | 0 | 0 | 6910378 | 6856508 | 101.5% | 1 | -53870 | 0 | 53 | 25 | 0 | 0 | 43044 | 0 | 0 | 0 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44444 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 |  | 2021-03-12 | QTR3 | 20/21 | 799 | 6893701.91
| 07 | T7440 | 44286215201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 116 | 167 | 163 | 96.55% | 1 | 4 | 0 | 0 | 30 | 21 | 2725693 | 50000 | 2675693 | 2725693 | 2560514 | 0 | 0 | 0 | 2560514 | 2560514 | 95.7% | 1 | 0 | 0 | 42 | 9 | 0 | 0 | 20000 | 0 | 0 | 0 | 3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23652 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 |  | 2020-10-06 | QTR2 | 20/21 | 798 | 2929941.26
| 07 | T7441 | 43764315201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 122 | 148 | 142 | 95.08% | 1 | 6 | 0 | 0 | 26 | 0 | 2094475 | 50000 | 2044475 | 2094475 | 2116984 | 0 | 0 | 0 | 2116984 | 2111225 | 103.3% | 1 | -5759 | 0 | 2 | 24 | 0 | 0 | 1658 | 0 | 0 | 0 | 11303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12961 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-21 | QTR4 | 20/21 |  | 2021-04-06 | QTR4 | 20/21 | 799 | 1713900
| 07 | T7443 | 44109815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 149 | 169 | 169 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 1372094 | 50000 | 1322094 | 1372094 | 1285441 | 0 | 0 | 0 | 1285441 | 1284319 | 97.14% | 1 | -1122 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-03-01 | QTR3 | 20/21 |  | 2020-11-30 | QTR2 | 20/21 | 796 | 1324000
| 07 | T7452 | 43969915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 90 | 161 | 160 | 116.7% | 1 | 1 | 0 | 0 | 71 | 0 | 533787 | 28000 | 505787 | 533787 | 537223 | 0 | 0 | 0 | 537223 | 537223 | 106.2% | 1 | 0 | 0 | 38 | 17 | 0 | 0 | 23754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 23754 | 0 | F465262082 | HARTMAN CIVIL CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 |  | 2021-02-04 | QTR3 | 20/21 | 798 | 665000
| 07 | T7453 | 44582415201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 80 | 147 | 145 | 97.5% | 1 | 2 | 0 | 0 | 67 | 0 | 607102 | 20000 | 587102 | 607102 | 507221 | 0 | 0 | 0 | 507221 | 507221 | 86.39% | 1 | 0 | 0 | 46 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 |  | 2021-01-22 | QTR3 | 20/21 | 796 | 562013.56
| 07 | T7454 | 44582715201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 115 | 117 | 117 | 100% | 1 | 0 | 0 | 0 | 2 | 0 | 273542 | 8200 | 265342 | 273542 | 259612 | 0 | 0 | 0 | 259612 | 259612 | 97.84% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-06-25 | QTR4 | 20/21 |  | 2021-05-03 | QTR4 | 20/21 | 799 | 245561.6
| 07 | T7457 | 44541015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 200 | 218 | 102 | 42% | 1 | 116 | 0 | 0 | 18 | 0 | 1090411 | 50000 | 1040411 | 1090411 | 1018989 | 0 | 0 | 0 | 1018989 | 1018989 | 97.94% | 1 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-03 | QTR4 | 20/21 |  | 2021-02-03 | QTR3 | 20/21 | 799 | 1330400
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 21 | 31 | 45 | 4962 | 7188 | 6840 | 85.71% | 18 | 348 | 110 | 0 | 1669 | 557 | 114200275 | 1366200 | 112834075 | 116615991 | 116849604 | -243950 | 1600000 | 1356050 | 118205654 | 116559263 | 95.24% | 20 | -1562891 | 2414511 | 1122 | 592 | 0 | 171 | 1304254 | 152610 | 0 | 258 | 1418378 | 44645 | 0 | 0 | 15135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -14572 | 709 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 16 | 444 | 2602262 | 197964
| 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 108.6% | 1 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 108.9% | 1 | 302 | 625193 | 45 | 66 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 66.67% | 1 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 99.99% | 1 | 0 | 0 | 95 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000
| 07 | E7M31 | 43751715201 | 2019-03-13 | QTR3 | 18/19 | 1 | 2 | 360 | 436 | 435 | 108.9% | 1 | 1 | 0 | 0 | 43 | 33 | 2064981 | 50000 | 2014981 | 1997687 | 1923224 | 0 | 0 | 0 | 1923224 | 1923189 | 95.44% | 1 | -35 | -67294 | 14 | 29 | 0 | 33 | -66214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | -26781 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 |  | 2020-08-21 | QTR1 | 20/21 | 799 | 2265000
| 07 | E7M35 | 43642115201 | 2019-04-10 | QTR4 | 18/19 | 2 | 1 | 180 | 246 | 246 | 116.7% | 1 | 0 | 0 | 0 | 36 | 30 | 3208889 | 50000 | 3158889 | 3213321 | 3310989 | 0 | 0 | 0 | 3310989 | 3270137 | 103.5% | 1 | -40853 | 4433 | 29 | 7 | 0 | 0 | 0 | 0 | 0 | 30 | 34925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34925 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 |  | 2020-09-25 | QTR1 | 20/21 | 798 | 3417308.79
| 07 | E7M50 | 42905925201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 80 | 125 | 114 | 86.25% | 1 | 11 | 0 | 0 | 45 | 0 | 257038 | 11000 | 246038 | 257038 | 238009 | 0 | 0 | 0 | 238009 | 238009 | 96.74% | 1 | 0 | 0 | 34 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 |  | 2019-12-20 | QTR2 | 19/20 | 796 | 255036.03
| 07 | E7M53 | 43878315201 | 2019-07-10 | QTR1 | 19/20 | 1 | 0 | 210 | 266 | 264 | 99.05% | 1 | 2 | 0 | 0 | 56 | 0 | 1279713 | 50000 | 1229713 | 1279713 | 1030596 | 0 | 0 | 0 | 1030596 | 1029149 | 83.69% | 1 | -1447 | 0 | 46 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 48740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48740 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 |  | 2020-10-02 | QTR2 | 20/21 | 796 | 2158375.3
| 07 | E7M74 | 43955115201 | 2019-09-11 | QTR1 | 19/20 | 1 | 0 | 260 | 282 | 171 | 57.31% | 1 | 111 | 0 | 0 | 22 | 0 | 555000 | 48000 | 507000 | 555000 | 507000 | 0 | 0 | 0 | 507000 | 507000 | 100% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 |  | 2020-07-31 | QTR1 | 20/21 | 796 | 1075906 | B0 | ACC - LUMP SUM
| 07 | E7M78 | 43624315201 | 2019-12-11 | QTR2 | 19/20 | 1 | 0 | 147 | 244 | 244 | 116.3% | 1 | 0 | 0 | 0 | 73 | 24 | 761530 | 25000 | 736530 | 761530 | 782626 | 0 | 0 | 0 | 782626 | 757851 | 102.9% | 1 | -24775 | 0 | 47 | 26 | 0 | 0 | 0 | 0 | 0 | 24 | 24463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24463 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 |  | 2021-02-18 | QTR3 | 20/21 | 796 | 720000
| 07 | E7M87 | 43952515201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 105 | 113 | 106 | 93.33% | 1 | 7 | 0 | 0 | 8 | 0 | 211449 | 7500 | 203949 | 219152 | 195461 | 0 | 0 | 0 | 195461 | 195461 | 95.84% | 1 | 0 | 7703 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7703 | 7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7703 | 7703 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 |  | 2020-07-20 | QTR1 | 20/21 | 799 | 206943.72
| 07 | E7M88 | 43751915201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 300 | 329 | 196 | 55.67% | 1 | 133 | 0 | 0 | 29 | 0 | 748000 | 50000 | 698000 | 748000 | 716109 | 0 | 0 | 0 | 716109 | 716109 | 102.6% | 1 | 0 | 0 | 7 | 22 | 0 | 0 | 18109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18109 | 0 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 |  | 2021-04-02 | QTR4 | 20/21 | 799 | 1657500 | B0 | ACC - LUMP SUM
| 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 92.5% | 1 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 799 | 280000
| 07 | E7M90 | 43983015201 | 2020-02-12 | QTR3 | 19/20 | 1 | 0 | 100 | 126 | 126 | 104% | 1 | 0 | 0 | 0 | 22 | 4 | 682863 | 38200 | 644663 | 682863 | 661465 | 0 | 0 | 0 | 661465 | 661465 | 102.6% | 1 | 0 | 0 | 16 | 6 | 0 | 4 | 22230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22230 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-24 | QTR2 | 20/21 |  | 2020-10-16 | QTR2 | 20/21 | 796 | 786200
| 07 | E7M92 | 44146815201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 162 | 151 | 90.83% | 1 | 11 | 0 | 0 | 42 | 0 | 657608 | 35295 | 622313 | 657608 | 639093 | 0 | 0 | 0 | 639093 | 639093 | 102.7% | 1 | 0 | 0 | 18 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-05-21 | QTR4 | 20/21 |  | 2021-03-15 | QTR3 | 20/21 | 799 | 830250
| 07 | E7M95 | 43762315201 | 2020-04-08 | QTR4 | 19/20 | 1 | 1 | 120 | 149 | 149 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 2367977 | 50000 | 2317977 | 2362575 | 2251785 | 0 | 0 | 0 | 2251785 | 2251785 | 97.14% | 1 | 0 | -5402 | 11 | 18 | 0 | 0 | 9437 | 0 | 0 | 0 | 5930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11036 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-05-25 | QTR4 | 20/21 |  | 2021-01-12 | QTR3 | 20/21 | 799 | 2542381.46
| 07 | E7M97 | 44024515201 | 2020-04-08 | QTR4 | 19/20 | 1 | 1 | 90 | 124 | 128 | 104.4% | 1 | -4 | 4 | 0 | 34 | 0 | 1873216 | 50000 | 1823216 | 1882322 | 1896442 | -6760 | 0 | -6760 | 1889682 | 1877971 | 103% | 1 | -11712 | 9105 | 24 | 10 | 0 | 0 | 1975 | 0 | 0 | 0 | 9105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 |  | 2020-12-08 | QTR2 | 20/21 | 799 | 1912250
| 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 72.06% | 1 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 93.26% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89
| 07 | E7N04 | 44580315201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 50 | 61 | 61 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 342938 | 15400 | 327538 | 342938 | 334918 | 0 | 0 | 0 | 334918 | 334918 | 102.3% | 1 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-16 | QTR2 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 796 | 323540.7
| 07 | E7N06 | 44108415201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 150 | 220 | 218 | 98.67% | 1 | 2 | 0 | 0 | 70 | 0 | 2651273 | 50000 | 2601273 | 2651273 | 2594154 | 0 | 0 | 0 | 2594154 | 2581698 | 99.25% | 1 | -12456 | 0 | 43 | 27 | 0 | 0 | 17137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17137 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-06-10 | QTR4 | 20/21 |  | 2021-04-16 | QTR4 | 20/21 | 796 | 2513322.8
| 07 | E7N20 | 25693135201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 60 | 90 | 98 | 125% | 0 | -8 | 8 | 0 | 26 | 4 | 217378 | 12000 | 205378 | 261168 | 240911 | -8360 | 0 | -8360 | 232551 | 232551 | 113.2% | 0 | 0 | 43790 | 17 | 6 | 0 | 0 | 0 | 0 | 3 | 4 | 43790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 43790 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 |  | 2020-12-13 | QTR2 | 20/21 | 799 | 350000
| 07 | E7N22 | 41101455201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 150 | 191 | 191 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 1199360 | 50000 | 1149360 | 1199360 | 1220405 | 0 | 0 | 0 | 1220405 | 1219955 | 106.1% | 1 | -449 | 0 | 26 | 15 | 0 | 0 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 |  | 2021-03-19 | QTR3 | 20/21 | 798 | 1261100
| 07 | E7N47 | 43955015201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 120 | 120 | 71 | 59.17% | 1 | 49 | 0 | 0 | 0 | 0 | 178219 | 9700 | 168519 | 178219 | 165324 | 0 | 0 | 0 | 165324 | 165324 | 98.1% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-05-12 | QTR4 | 20/21 |  | 2021-04-12 | QTR4 | 20/21 | 796 | 214800
| 07 | E7R14 | 43402715201 | 2019-01-22 | QTR3 | 18/19 | 1 | 1 | 485 | 580 | 577 | 108.7% | 1 | 3 | 0 | 0 | 50 | 45 | 3891051 | 50000 | 3841051 | 3854521 | 3786721 | 0 | 0 | 0 | 3786721 | 3786721 | 98.59% | 1 | 0 | -36530 | 18 | 32 | 0 | 0 | -197831 | 0 | 0 | 0 | 11095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36530 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 |  | 2020-10-31 | QTR2 | 20/21 | 796 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 22 | 24 | 16 | 4405 | 5494 | 5034 | 95.45% | 21 | 460 | 12 | 0 | 876 | 213 | 36331121 | 773095 | 35558026 | 36912119 | 36276179 | -15120 | 0 | -15120 | 36261059 | 36169635 | 95.45% | 21 | -91425 | 580998 | 519 | 354 | 0 | 37 | -20338 | 0 | 3 | 95 | 692204 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 7703 | 7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 168 | 870802 | 28833
| District 07 Totals |  |  |  |  | 43 | 55 | 61 | 9367 | 12682 | 11874 | 90.7% | 39 | 808 | 122 | 0 | 2545 | 770 | 150531396 | 2139295 | 148392101 | 153528110 | 153125783 | -259070 | 1600000 | 1340930 | 154466713 | 152728898 | 95.35% | 41 | -1654316 | 2995509 | 1641 | 946 | 0 | 208 | 1283916 | 152610 | 3 | 353 | 2110582 | 65775 | 0 | 0 | 15135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 175590 | 709 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 16 | 36 | 7703 | 7703 | 0 | 0 | 0 | 0 | 0 | 0 | -124158 | 0 | 19 | 612 | 3473064 | 226797
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 180.6% | 0 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | 105.2% | 1 | -2369264 | 11648418 | 291 | 106 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 08 | E8N20 | 42714615201 | 2014-06-23 | QTR4 | 13/14 | 8 | 19 | 1150 | 2322 | 2322 | 155% | 0 | 0 | 0 | 0 | 537 | 635 | 54444321 | 150000 | 54294321 | 55997037 | 56078061 | -16000 | 0 | -16000 | 56062061 | 54752460 | 100.8% | 1 | -1173828 | 1552716 | 341 | 198 | 0 | 170 | 1375824 | 0 | 0 | 0 | 111160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 463 | -106171 | 0 | 0 | 0 | 31771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 1428816 | 0 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 |  | 2021-02-26 | QTR3 | 20/21 | 854 | 59644380.55 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
| 08 | E8N58 | 40610315201 | 2015-05-19 | QTR4 | 14/15 | 2 | 34 | 1210 | 1688 | 1688 | 116.9% | 1 | 0 | 0 | 0 | 274 | 204 | 49459029 | 150000 | 49309029 | 53635234 | 54832716 | -13000 | 0 | -13000 | 54819716 | 54685458 | 110.9% | 0 | -82853 | 4176205 | 153 | 121 | 0 | 18 | 308998 | 88734 | 0 | 43 | 1321673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 2378855 | 0 | 0 | 0 | 139746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 4149273 | 88734 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-02-19 | QTR3 | 20/21 |  | 2020-06-14 | QTR4 | 19/20 | 854 | 55428349.1
| 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1438 | 117.4% | 1 | 15 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 109.1% | 1 | 991193 | 5429118 | 149 | 127 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 |  | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 119.5% | 1 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | 106.1% | 1 | -551574 | 4550344 | 122 | 82 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12
| 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | 119.6% | 1 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 106.6% | 1 | 496445 | 1556062 | 183 | 99 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 0
| 08 | E8Q10 | 43661915201 | 2016-06-14 | QTR4 | 15/16 | 1 | 3 | 949 | 1351 | 1351 | 128.7% | 0 | 0 | 0 | 0 | 402 | 0 | 29944488 | 150000 | 29794488 | 30283733 | 28559596 | -3000 | 0 | -3000 | 28556596 | 28668240 | 96.22% | 1 | 121829 | 339245 | 40 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 70922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 0 | 392961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 0 | 463883 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 |  | 2020-08-28 | QTR1 | 20/21 | 854 | 22863153.07
| 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 113.2% | 1 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 106.9% | 1 | 1490912 | 597011 | 172 | 84 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09
| 08 | E8Q85 | 43651715201 | 2018-01-23 | QTR3 | 17/18 | 2 | 10 | 620 | 882 | 882 | 105.3% | 1 | 0 | 0 | 0 | 229 | 33 | 35890871 | 150000 | 35740871 | 36842857 | 35395810 | -10000 | 0 | -10000 | 35385810 | 36250675 | 101.4% | 1 | 867370 | 951986 | 161 | 68 | 0 | 18 | 192480 | 0 | 0 | 8 | 52057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348416 | 0 | 0 | 7 | 364088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 957041 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 |  | 2020-12-21 | QTR2 | 20/21 | 854 | 26738962.29
| 08 | E8Q93 | 42933915201 | 2017-12-12 | QTR2 | 17/18 | 1 | 17 | 600 | 929 | 901 | 112.3% | 1 | 28 | 0 | 0 | 227 | 102 | 20384811 | 150000 | 20234811 | 21680602 | 22044940 | 0 | 0 | 0 | 22044940 | 22209747 | 109.8% | 1 | 178193 | 1295791 | 132 | 95 | 0 | 0 | 87536 | 0 | 0 | 0 | 1014524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 194931 | 0 | 0 | 0 | 257578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -126793 | 0 | 0 | 102 | 1427776 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 |  | 2020-12-04 | QTR2 | 20/21 | 854 | 18579757.33
| 08 | E8Q94 | 43947815201 | 2018-03-27 | QTR3 | 17/18 | 4 | 6 | 525 | 723 | 723 | 101.3% | 1 | 0 | 0 | 0 | 198 | 0 | 18860577 | 150000 | 18710577 | 18748056 | 18778411 | -36500 | 0 | -36500 | 18741911 | 19317651 | 103.2% | 1 | 583633 | -112521 | 130 | 61 | 0 | 0 | -519709 | 0 | 0 | 0 | 381340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 106099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -32270 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 |  | 2020-06-30 | QTR4 | 19/20 | 854 | 29028001.13
| 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 106.8% | 1 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | 97.91% | 1 | -7 | 70000 | 23 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49
| 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 102% | 1 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | 119.1% | 0 | -3862 | 142527 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 |  | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97
| 08 | E8R58 | 43799115201 | 2019-05-14 | QTR4 | 18/19 | 2 | 4 | 315 | 471 | 471 | 108.9% | 1 | 0 | 0 | 0 | 128 | 28 | 10199910 | 125662 | 10074248 | 10499910 | 10355353 | -12500 | 0 | -12500 | 10342853 | 10192921 | 101.2% | 1 | -149932 | 300000 | 73 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 35979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2089 | 0 | 0 | 23 | 332378 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 389600 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 |  | 2020-12-21 | QTR2 | 20/21 | 854 | 11724624.47
| 08 | E8R76 | 43945715201 | 2019-03-12 | QTR3 | 18/19 | 1 | 6 | 415 | 477 | 405 | 82.65% | 1 | 72 | 0 | 0 | 62 | 0 | 12161596 | 125391 | 12036204 | 11888308 | 12421672 | 0 | 0 | 0 | 12421672 | 12302929 | 102.2% | 1 | -84308 | -273288 | 21 | 41 | 0 | 0 | -340280 | 0 | 0 | 0 | 51302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287059 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 |  | 2020-06-30 | QTR4 | 19/20 | 854 | 12670789.67
| 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 106% | 1 | 0 | 94072 | 5 | 28 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98
| 08 | E8R95 | 43560575201 | 2019-09-10 | QTR1 | 19/20 | 1 | 5 | 385 | 466 | 438 | 101.6% | 1 | 28 | 0 | 0 | 47 | 34 | 7288625 | 83306 | 7205319 | 7325241 | 7238007 | 0 | 0 | 0 | 7238007 | 7237793 | 100.5% | 1 | -213 | 36616 | 21 | 26 | 0 | 30 | 85031 | 0 | 0 | 4 | -45819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 104762 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-06-11 | QTR4 | 20/21 |  | 2021-04-30 | QTR4 | 20/21 | 854 | 9629063.11
| 08 | E8R96 | 44130915201 | 2019-08-20 | QTR1 | 19/20 | 1 | 3 | 463 | 493 | 369 | 73.22% | 1 | 124 | 0 | 0 | 30 | 0 | 4958767 | 54870 | 4903898 | 4943242 | 4981728 | 0 | 0 | 0 | 4981728 | 4960014 | 101.1% | 1 | -21714 | -15525 | 5 | 25 | 0 | 0 | -15248 | 0 | 0 | 0 | 53090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37842 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-01-08 | QTR3 | 20/21 |  | 2020-11-23 | QTR2 | 20/21 | 854 | 5574450.77
| 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 37.17% | 1 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 90.79% | 1 | 0 | -576 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64
| 08 | E8S01 | 43651615201 | 2019-11-19 | QTR2 | 19/20 | 2 | 0 | 219 | 289 | 289 | 100% | 1 | 0 | 0 | 0 | 70 | 0 | 6508469 | 70860 | 6437610 | 6508469 | 6539682 | 0 | 0 | 0 | 6539682 | 6503176 | 101% | 1 | -36506 | 0 | 51 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 11164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-29 | QTR3 | 20/21 |  | 2020-12-14 | QTR2 | 20/21 | 854 | 7009172.74
| 08 | E8S20 | 43801915201 | 2020-03-10 | QTR3 | 19/20 | 1 | 0 | 157 | 177 | 113 | 59.24% | 1 | 64 | 0 | 0 | 20 | 0 | 438700 | 30191 | 408509 | 438700 | 378146 | 0 | 0 | 0 | 378146 | 378146 | 92.57% | 1 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2021-04-12 | QTR4 | 20/21 |  | 2021-01-20 | QTR3 | 20/21 | 854 | 627428.86
| 08 | E8S33 | 44261815201 | 2020-05-12 | QTR4 | 19/20 | 2 | 2 | 231 | 285 | 285 | 100.9% | 1 | 0 | 0 | 0 | 52 | 2 | 1875029 | 50000 | 1825029 | 1908027 | 1958622 | 0 | 0 | 0 | 1958622 | 1958746 | 107.3% | 1 | 123 | 32998 | 27 | 25 | 0 | 0 | 11458 | 0 | 0 | 2 | 48392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 59850 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 |  | 2021-05-14 | QTR4 | 20/21 | 854 | 1327553.52
| 08 | E8S47 | 44400315201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 65 | 75 | 62 | 80% | 1 | 13 | 0 | 0 | 10 | 0 | 254205 | 21677 | 232529 | 254205 | 227921 | 0 | 0 | 0 | 227921 | 227921 | 98.02% | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 |  | 2020-11-08 | QTR2 | 20/21 | 854 | 465727.12
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 23 | 51 | 210 | 12649 | 19037 | 18499 | 0% | 20 | 538 | 42 | 0 | 4258 | 2130 | 626315738 | 2411957 | 623903783 | 658686936 | 657628524 | -466224 | 0 | -466224 | 657162300 | 655889837 | 91.3% | 21 | 255637 | 32371199 | 2129 | 1425 | 0 | 984 | 14611387 | 1656128 | 0 | 81 | 4079442 | 61112 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 706 | 1007 | 9712871 | 402197 | 0 | 46 | 1953272 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 111855 | 0 | 0 | 0 | 395000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -215197 | 0 | 706 | 2120 | 31638404 | 2139039
| District 08 Totals |  |  |  |  | 23 | 51 | 210 | 12649 | 19037 | 18499 | 86.96% | 20 | 538 | 42 | 0 | 4258 | 2130 | 626315738 | 2411957 | 623903783 | 658686936 | 657628524 | -466224 | 0 | -466224 | 657162300 | 655889837 | 91.3% | 21 | 255637 | 32371199 | 2129 | 1425 | 0 | 984 | 14611387 | 1656128 | 0 | 81 | 4079442 | 61112 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42900 | 0 | 706 | 1007 | 9712871 | 402197 | 0 | 46 | 1953272 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 111855 | 0 | 0 | 0 | 395000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -215197 | 0 | 706 | 2120 | 31638404 | 2139039
| Statewide Central Let Contracts SubTotal |  |  |  |  | 175 | 330 | 407 | 46017 | 63696 | 61518 | 89.14% | 156 | 2178 | 529 | 0 | 14305 | 3386 | 914248018 | 10215176 | 904032849 | 939220997 | 933373856 | -887054 | 11222122 | 10335068 | 943708923 | 931974568 | 94.29% | 165 | -10277230 | 24971771 | 8993 | 4625 | 252 | 822 | 11165550 | 1734913 | 292 | 2002 | 12655969 | 1321282 | 0 | 0 | 50150 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 4000 | 0 | 140 | 5 | 2271777 | 793213 | 49 | 28 | 677786 | 133568 | 0 | 0 | -33504 | 0 | 0 | 11 | 399248 | 0 | 0 | 176 | 506000 | 475000 | 46 | 96 | 348557 | 170361 | 0 | 0 | 0 | 0 | 0 | 0 | -1328133 | 0 | 793 | 3140 | 26717396 | 4628338
| Statewide District Let Contracts SubTotal |  |  |  |  | 156 | 243 | 459 | 46571 | 70059 | 69548 | 78.21% | 122 | 511 | 2423 | 0 | 15284 | 8204 | 1515183661 | 9070657 | 1506113009 | 1604136704 | 1593794123 | -19358403 | 2644936 | -16713466 | 1577080656 | 1525652340 | 92.95% | 145 | -48239694 | 88953043 | 8475 | 5020 | 274 | 2242 | 23054676 | 2690590 | 322 | 1376 | 11679795 | 410939 | 0 | 7 | 946876 | 0 | 0 | 60 | -425715 | 0 | 0 | 0 | 476750 | 0 | 739 | 2121 | 29326082 | 719164 | 27 | 292 | 2115557 | 111779 | 0 | 0 | 0 | 0 | 16 | 63 | 422834 | 0 | 0 | 119 | 1925217 | 19602 | 280 | 39 | 54811 | 20624 | 28 | 0 | 0 | 0 | 0 | 0 | -757238 | 0 | 1686 | 6319 | 68819645 | 3972701
| Statewide Totals |  |  |  |  | 331 | 573 | 866 | 92588 | 133755 | 131066 | 83.99% | 278 | 2689 | 2952 | 0 | 29589 | 11590 | 2429431679 | 19285833 | 2410145858 | 2543357701 | 2527167979 | -20245457 | 13867058 | -6378398 | 2520789579 | 2457626908 | 93.66% | 310 | -58516924 | 113924814 | 17468 | 9645 | 526 | 3064 | 34220226 | 4425503 | 614 | 3378 | 24335764 | 1732221 | 0 | 7 | 997026 | 0 | 0 | 60 | -425715 | 0 | 14 | 0 | 480750 | 0 | 879 | 2126 | 31597859 | 1512377 | 76 | 320 | 2793343 | 245347 | 0 | 0 | -33504 | 0 | 16 | 74 | 822082 | 0 | 0 | 295 | 2431217 | 494602 | 326 | 135 | 403368 | 190985 | 28 | 0 | 0 | 0 | 0 | 0 | -2085371 | 0 | 2479 | 9459 | 95537041 | 8601039

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P44 | 43797315201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-01-27 | 18051494 | 18407137 | 18281638 | 355642.62 | 0 | 18301633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
1 | E1P46 | 43580715201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 869954 | 869954 | 834474 | 0 | 0 | 836068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834474 | 836068 | 1595 | 794914
1 | E1P87 | 43504015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-04-20 | 2037254 | 2546460 | 2602954 | 509206.08 | 0 | 2606824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602954 | 2606824 | 3870 | 2970496
1 | E1R03 | 44021215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-01-03 | 1441171 | 1857076 | 1804938 | 415904.86 | 0 | 1804938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804938 | 1804938 | 0 | 1515908 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1R05 | 43629915201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-03-01 | 7996438 | 8606992 | 8773391 | 610554.93 | 0 | 8772475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8773391 | 8772475 | -916 | 8160370 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R06 | 43658015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-14 | 2206728 | 2236442 | 2181738 | 29714.23 | 0 | 2202526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181738 | 2202526 | 20788 | 2403604
1 | E1R07 | 19602255201 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-06-14 | 4989441 | 5299029 | 4998104 | 309587.77 | -214274 | 4757758 | -64274 | 0 | 0 | 0 | 0 | 0 | -64274 | 0 | 0 | 0 | 0 | -150000 | 0 | -150000 | -214274 | 4783829 | 4757758 | -26072 | 4839623 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R08 | 43526515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-05-17 | 1717172 | 1717172 | 1457666 | 0 | 0 | 1601560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1457666 | 1601560 | 143895 | 2389311
1 | E1R11 | 41066625201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-06-14 | 20022782 | 20456986 | 19822369 | 434203.87 | 0 | 19694841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19822369 | 19694841 | -127528 | 22152761 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R39 | 43802415201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-10-18 | 2883484 | 2929980 | 2732452 | 46495.87 | 0 | 2828698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2732452 | 2828698 | 96246 | 3497647
1 | E1R62 | 43795815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-08-16 | 1959744 | 2208518 | 2188843 | 248774.15 | 0 | 2188837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2188843 | 2188837 | -6 | 2795998
1 | E1R64 | 42584125201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-01-24 | 22161010 | 23160665 | 22864939 | 999655.76 | 0 | 22872824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22864939 | 22872824 | 7885 | 21356227 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1R78 | 43502915201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-03-21 | 982956 | 982956 | 953745 | 0 | -3330 | 950415 | -3330 | 0 | 0 | 0 | 0 | 0 | -3330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3330 | 950415 | 950415 | 0 | 837254 | B0 | ACC - LUMP SUM
1 | E1R79 | 43806215201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-02-21 | 6263696 | 6369605 | 6356261 | 105908.79 | 0 | 6267065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6356261 | 6267065 | -89196 | 6188091
1 | E1R81 | 43528615201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-05-23 | 682196 | 682196 | 657412 | 0 | 0 | 657412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657412 | 657412 | 0 | 659798 | B0 | ACC - LUMP SUM
1 | E1R86 | 44108815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-11-09 | 2469000 | 2469000 | 2431659 | 0 | 0 | 2431659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431659 | 2431659 | 0 | 3306922 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1R99 | 43942615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-10-17 | 2118027 | 2118027 | 2076020 | 0 | 0 | 2071117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 2188397 | B0 | ACC - LUMP SUM
1 | E1S01 | 43796215201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-18 | 1319384 | 1319384 | 1246251 | 0 | 0 | 1246243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 1628857
1 | E1S13 | 44462715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-16 | 993513 | 994797 | 930694 | 1284.91 | 0 | 928776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930694 | 928776 | -1919 | 1140044
1 | E1S47 | 43997015201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 450312 | 450312 | 440733 | 0 | 0 | 440733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440733 | 440733 | 0 | 480716
1 | E1S48 | 44005515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-02-20 | 2577917 | 2631610 | 2504928 | 53692.73 | 150000 | 2504928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000 | 150000 | 2654928 | 2504928 | -150000 | 2532690 | B10 | ACC - BONUS/INCENT/DISINCENT
1 | E1S50 | 44525715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-03-19 | 279624 | 279624 | 287046 | 0 | 0 | 287046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287046 | 287046 | 0 | 268843
1 | T1665 | 43545015201 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1995871 | 2060794 | 2106268 | 64922.5 | -99792 | 2010824 | -99792 | 0 | 0 | 0 | 0 | 0 | -99792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99792 | 2006476 | 2010824 | 4348 | 2185571
1 | T1670 | 43512015201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-03-29 | 774103 | 789611 | 780581 | 15508.02 | -74448 | 707486 | -74448 | 0 | 0 | 0 | 0 | 0 | -74448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74448 | 706133 | 707486 | 1353 | 746976
1 | T1675 | 43088715201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-30 | 815194 | 856566 | 821472 | 41371.58 | 0 | 822481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821472 | 822481 | 1009 | 783433 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1702 | 43509015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2098354 | 2203054 | 2035840 | 104699.5 | 0 | 2034275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035840 | 2034275 | -1565 | 2050386 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1712 | 43355025201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-04-25 | 5536538 | 5542551 | 5605616 | 6013.22 | 200000 | 5607954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000 | 200000 | 5805616 | 5607954 | -197662 | 5608552 | B10 | ACC - BONUS/INCENT/DISINCENT
1 | T1718 | 44011815201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-07-25 | 440982 | 440982 | 416149 | 0 | 0 | 416078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416149 | 416078 | -71 | 501430
1 | T1719 | 43800915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 4444444 | 4440169 | 4492709 | -4275.84 | 0 | 4400827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492709 | 4400827 | -91882 | 4966063
1 | T1720 | 43655115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 4987470 | 5081049 | 5094971 | 93578.25 | 0 | 5026709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094971 | 5026709 | -68262 | 5203469
1 | T1721 | 43955515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 4793304 | 4836240 | 4588281 | 42935.96 | 0 | 4543144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4588281 | 4543144 | -45137 | 5287557
1 | T1722 | 43806015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-04-24 | 11567352 | 11561213 | 11392803 | -6138.58 | 0 | 11297616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11392803 | 11297616 | -95187 | 13570916
1 | T1731 | 44012015201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 800698 | 822869 | 716288 | 22171 | -41625 | 674668 | -41625 | 0 | 0 | 0 | 0 | 0 | -41625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41625 | 674663 | 674668 | 5 | 965767
1 | T1742 | 43539015201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 3732644 | 3755256 | 3738358 | 22611.39 | 0 | 3735826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3738358 | 3735826 | -2532 | 3397782
1 | T1744 | 43806115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 2622633 | 2624733 | 2699418 | 2100 | 0 | 2679820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2884387
1 | T1746 | 43801415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 3284806 | 3448596 | 3473733 | 163790.71 | -10000 | 3433178 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 3463733 | 3433178 | -30555 | 4171540
1 | T1748 | 43510815201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1145000 | 1148200 | 1114849 | 3200.4 | 0 | 1114533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 980185
1 | T1750 | 44385115201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 2676999 | 2703686 | 2688376 | 26686.83 | 0 | 2686495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688376 | 2686495 | -1882 | 2027465
1 | T1752 | 43942315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-01-29 | 3291059 | 3259973 | 3120660 | -31086.57 | 0 | 3033429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3120660 | 3033429 | -87231 | 3526243
1 | T1756 | 43511415201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2019-09-25 | 1037000 | 1084886 | 1084886 | 47885.96 | 0 | 1084595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084886 | 1084595 | -291 | 1002064 | B0 | ACC - LUMP SUM
1 | T1758 | 43943715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-07-31 | 7004551 | 7119832 | 7259276 | 115281.22 | 0 | 7106733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7259276 | 7106733 | -152543 | 9375095
1 | T1759 | 44067015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 1338165 | 1328365 | 1305338 | -9800 | 0 | 1305118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305338 | 1305118 | -220 | 1044391 | B0 | ACC - LUMP SUM
1 | T1767 | 44068115201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 561733 | 561733 | 545876 | 0 | 0 | 545876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545876 | 545876 | 0 | 444415
1 | T1773 | 44067215201 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 214731 | 214731 | 194639 | 0 | 0 | 194639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194639 | 194639 | 0 | 215733
1 | T1776 | 43535815201 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 140340 | 140340 | 140340 | 0 | 0 | 140340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140340 | 140340 | 0 | 104700 | B0 | ACC - LUMP SUM
1 | T1779 | 43808615201 | F454013430 | MSB SERVICES LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 905000 | 905000 | 904754 | 0 | 0 | 904754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904754 | 904754 | 0 | 658935 | B0 | ACC - LUMP SUM
1 | T1997 | 40828665201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-01-25 | 58011809 | 58671616 | 58073269 | 659806.55 | 0 | 59331197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58073269 | 59331197 | 1257928 | 69879385
2 | E2Q19 | 43056535201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 76890000 | 84056110 | 83001547 | 7166110.1 | -5396832 | 75663703 | -5396832 | 0 | 0 | 0 | 0 | 0 | -5396832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5396832 | 77604715 | 75663703 | -1941012 | 86651500 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2Q20 | 43056515201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-10-10 | 84850000 | 92836344 | 92314884 | 7986344.16 | -2553772 | 83827180 | -2454647 | 0 | 0 | 0 | -99125 | 0 | -2553772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2553772 | 89761112 | 83827180 | -5933932 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
2 | E2S01 | 21334575201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2014-05-29 | 88950000 | 95522820 | 95155243 | 6572819.67 | -3789520 | 89141350 | -3789520 | 0 | 0 | 0 | 0 | 0 | -3789520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3789520 | 91365723 | 89141350 | -2224374 | 87843647 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2V62 | 43742915201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-04-19 | 2735951 | 5631812 | 5550491 | 2895861.36 | 0 | 5449494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550491 | 5449494 | -100997 | 2961809
2 | E2W31 | 43373015201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRAC | N/A | N/A | N/A | N/A | 2017-03-15 | 17417591 | 18912363 | 18626417 | 1494771.62 | -549666 | 18310135 | -549666 | 0 | 0 | 0 | 0 | 0 | -549666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -549666 | 18076751 | 18310135 | 233384 | 16736577
2 | E2X06 | 43076015201 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2018-04-18 | 2957443 | 3057443 | 3046193 | 100000 | -151872 | 2894277 | -151872 | 0 | 0 | 0 | 0 | 0 | -151872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -151872 | 2894321 | 2894277 | -43 | 2882465
2 | E2X64 | 20964255201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2018-09-19 | 2988353 | 2988353 | 3023872 | 0 | 0 | 3021571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023872 | 3021571 | -2301 | 3026821
2 | E2X65 | 43239615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-12-19 | 2683748 | 2672792 | 2635955 | -10955.81 | -37968 | 2597896 | -37968 | 0 | 0 | 0 | 0 | 0 | -37968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37968 | 2597987 | 2597896 | -90 | 2688578
2 | E2Y25 | 43761715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 5599368 | 5599368 | 5849866 | 0 | 0 | 5819954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849866 | 5819954 | -29911 | 6362327
2 | E2Y27 | 44129815201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2019-05-15 | 2191115 | 2260070 | 2293916 | 68954.88 | 0 | 2287350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2293916 | 2287350 | -6566 | 2136569
2 | E2Z22 | 44199725215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2019-10-16 | 486100 | 486100 | 457926 | 0 | 0 | 457926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457926 | 457926 | 0 | 464975
2 | E2Z35 | 43593915201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-03-18 | 484693 | 492193 | 451960 | 7500 | 0 | 451960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451960 | 451960 | 0 | 351994
2 | E2Z37 | 43616525201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2020-03-18 | 335202 | 335202 | 332890 | 0 | 0 | 332890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332890 | 332890 | 0 | 321540
2 | E2Z38 | 43958915201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-18 | 671597 | 671597 | 637444 | 0 | 0 | 637444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637444 | 637444 | 0 | 705488
2 | T2660 | 43607715201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2017-12-06 | 25775068 | 25930204 | 26452915 | 155135.86 | 0 | 26446407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26452915 | 26446407 | -6508 | 25496504
2 | T2675 | 43611415201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 8842976 | 8855815 | 8862510 | 12839.16 | 0 | 8968366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8862510 | 8968366 | 105856 | 9571732
2 | T2690 | 42880715201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 7990153 | 7990153 | 7911166 | 0 | 0 | 8230419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7911166 | 8230419 | 319253 | 8670416
2 | T2702 | 43616515201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-05-23 | 4160007 | 4260007 | 4244965 | 100000 | 0 | 4312480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 3742257
2 | T2706 | 42879615201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 7792915 | 8443153 | 8718430 | 650238.2 | 0 | 8716846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8718430 | 8716846 | -1584 | 7769629
2 | T2709 | 21284435201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 3462428 | 3505177 | 3504649 | 42749.1 | 0 | 3506156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 3179149
2 | T2713 | 43613525201 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2018-09-26 | 1975147 | 1975147 | 1947179 | 0 | 0 | 1945873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947179 | 1945873 | -1305 | 1272156
2 | T2716 | 43763015201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 4888889 | 4888889 | 4688077 | 0 | 0 | 4687157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688077 | 4687157 | -920 | 5384749
2 | T2719 | 44089815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 1184584 | 1184584 | 887887 | 0 | 0 | 887887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887887 | 887887 | 0 | 1509948
2 | T2721 | 43761915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 8899704 | 8899704 | 8066755 | 0 | 0 | 7968066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 9019727
2 | T2722 | 43761515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 3029745 | 3129745 | 3172572 | 100000 | 0 | 3184741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3172572 | 3184741 | 12169 | 3135452
2 | T2726 | 43583715201 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2018-09-26 | 2039829 | 2119904 | 2083011 | 80074.99 | -14985 | 2064225 | -14985 | 0 | 0 | 0 | 0 | 0 | -14985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14985 | 2068026 | 2064225 | -3801 | 2155262
2 | T2728 | 43732115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-30 | 5318835 | 5318835 | 5249772 | 0 | 0 | 5213329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 5787088
2 | T2729 | 43499715201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2001734 | 2001734 | 1943094 | 0 | 0 | 1943094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943094 | 1943094 | 0 | 2294576
2 | T2731 | 43617915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 4898898 | 4948898 | 4982985 | 50000 | 0 | 4949350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4982985 | 4949350 | -33636 | 5966986
2 | T2735 | 44119515201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 421053 | 421053 | 394439 | 0 | 0 | 394439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394439 | 394439 | 0 | 428178
2 | T2737 | 43433315201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2819291 | 2969291 | 2939393 | 150000 | 0 | 2975999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2939393 | 2975999 | 36605 | 1924122
2 | T2738 | 43934615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | 3397538 | 3397538 | 3460508 | 0 | 0 | 3441905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 3973731
2 | T2742 | 44272415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 99208 | 99208 | 93539 | 0 | 0 | 93539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93539 | 93539 | 0 | 84352
2 | T2745 | 43398815201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2019-08-28 | 149961 | 149961 | 151154 | 0 | 0 | 151154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151154 | 151154 | 0 | 204916
2 | T2747 | 43934815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 5571370 | 5571370 | 5579362 | 0 | 0 | 5481318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5579362 | 5481318 | -98044 | 6661156
2 | T2748 | 43911615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 4749617 | 4779617 | 4835839 | 30000 | 0 | 4774010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4835839 | 4774010 | -61829 | 5777786
2 | T2749 | 43946715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11950705 | 12017028 | 7108680 | 66323 | 0 | 7101059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7108680 | 7101059 | -7620 | 11844644
2 | T2750 | 43908015201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 1515900 | 1515900 | 1353861 | 0 | 0 | 1345218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353861 | 1345218 | -8642 | 1652876
2 | T2761 | 43934515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 4189603 | 4189603 | 4189658 | 0 | 0 | 4163139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4189658 | 4163139 | -26519 | 5262361
2 | T2764 | 44140615201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 954146 | 954146 | 884664 | 0 | 0 | 884785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884664 | 884785 | 121 | 1080912
2 | T2765 | 43934415201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 3724072 | 3724072 | 3875990 | 0 | -13560 | 3837465 | -13560 | 0 | 0 | 0 | 0 | 0 | -13560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13560 | 3862430 | 3837465 | -24965 | 4321210
2 | T2766 | 44348915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1081333 | 1081333 | 1019859 | 0 | 0 | 1018371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1019859 | 1018371 | -1488 | 1202483
3 | E3O87 | 42820825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-12 | 2143658 | 2394721 | 2274840 | 251062.72 | 0 | 2271803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 1738000
3 | E3P37 | 22280225201 | F811252530 | OMEGA COATINGS & CONSTRUCTION | N/A | N/A | N/A | N/A | 2019-04-11 | 398582 | 398582 | 363870 | 0 | 0 | 363870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363870 | 363870 | 0 | 733124
3 | E3Q54 | 22253925201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-05-09 | 922444 | 846935 | 658266 | -75509.51 | 0 | 658266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658266 | 658266 | 0 | 919379
3 | E3R03 | 41343525201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-10 | 1381327 | 1468091 | 1381221 | 86763.05 | -4783 | 1374521 | 0 | 0 | 0 | 0 | 0 | -4783 | -4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4783 | 1376437 | 1374521 | -1916 | 1155000
3 | E3R51 | 22023625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4578865 | 4737767 | 4690378 | 158901.87 | 0 | 4638261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 4615476
3 | E3R70 | 43814115201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 628778 | 721767 | 721738 | 92989.29 | 0 | 721738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721738 | 721738 | 0 | 499880
3 | E3R72 | 43255415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-11 | 4336259 | 4459598 | 4468867 | 123338.96 | -5424 | 4390050 | -5424 | 0 | 0 | 0 | 0 | 0 | -5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5424 | 4463443 | 4390050 | -73393 | 5281573
3 | E3R75 | 40731075201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-06-13 | 1896816 | 2013742 | 1899113 | 116926.29 | 0 | 1899113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899113 | 1899113 | 0 | 1645053
3 | E3R78 | 43813815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-14 | 467023 | 467023 | 452193 | 0 | 0 | 452193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452193 | 452193 | 0 | 567889
3 | E3R84 | 43736715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-05-09 | 1890085 | 1993510 | 1844667 | 103424.95 | 0 | 1822661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844667 | 1822661 | -22007 | 1951316
3 | E3R95 | 41558035201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-02-13 | 328111 | 328111 | 264195 | 0 | 0 | 264195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264195 | 264195 | 0 | 491600
3 | E3S02 | 21939725201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-12-12 | 427396 | 427396 | 396531 | 0 | 0 | 396531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396531 | 396531 | 0 | 321776
3 | E3S03 | 43775215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-16 | 4297338 | 4339701 | 4428331 | 42363.01 | 0 | 4345545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 4833697
3 | E3S37 | 43972615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-08-08 | 1570270 | 1570270 | 1528065 | 0 | 0 | 1509877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528065 | 1509877 | -18188 | 1812372
3 | E3S48 | 43973015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-14 | 2362840 | 2362840 | 2375062 | 0 | 0 | 2367596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375062 | 2367596 | -7466 | 2687907
3 | E3S49 | 44350315201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-11-14 | 1254000 | 1254000 | 1218580 | 0 | 0 | 1218580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 1226090
3 | E3S50 | 22253625201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-11-14 | 688910 | 688910 | 677594 | 0 | 0 | 677594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677594 | 677594 | 0 | 1158620
3 | E3S58 | 43992625201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 4969434 | 4969434 | 4898737 | 0 | 0 | 4882975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4898737 | 4882975 | -15762 | 5633775
3 | E3S66 | 4450183H201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2019-04-26 | 280576 | 280576 | 224753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224753 | 0 | -224753 | 275521
3 | E3T19 | 4453861K201 | F201212361 | PBROWN BUILDERS LLC | N/A | N/A | N/A | N/A | 2019-10-14 | 289955 | 289955 | 286443 | 0 | -8687 | 0 | -8687 | 0 | 0 | 0 | 0 | 0 | -8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8687 | 277756 | 0 | -277756 | 279453
3 | E3T53 | 42187835201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 205566 | 205566 | 187451 | 0 | 200000 | 187451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 387451 | 187451 | -200000 | 257560 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | T3287 | 22044245201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 18411475 | 18469826 | 18803780 | 58350.97 | 0 | 18275141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18803780 | 18275141 | -528638 | 19760914
3 | T3578 | 41413235201 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 33319378 | 34311548 | 36973951 | 992169.71 | 1405750 | 37338282 | 0 | 0 | 0 | 0 | 0 | -94250 | -94250 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1405750 | 38379701 | 37338282 | -1041419 | 33490901
3 | T3582 | 43483715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 6289025 | 6444360 | 6415800 | 155334.85 | -47198 | 6493957 | 0 | 0 | 0 | 0 | 0 | -47198 | -47198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47198 | 6368602 | 6493957 | 125354 | 7725569
3 | T3585 | 43228515201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 1883515 | 1882120 | 2065179 | -1394.8 | 0 | 2067671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | 1839571
3 | T3619 | 43390215201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2018-11-14 | 1114410 | 1163460 | 1226323 | 49049.79 | 0 | 1224530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226323 | 1224530 | -1793 | 1475965
3 | T3627 | 43228915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 3174345 | 3223970 | 3466393 | 49625.5 | 0 | 3468474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3466393 | 3468474 | 2081 | 3241142
3 | T3642 | 43274025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 8739221 | 8879082 | 9063602 | 139861.6 | -14091 | 9591255 | 0 | 0 | 0 | 0 | 0 | -14091 | -14091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14091 | 9049511 | 9591255 | 541744 | 8488155
3 | T3648 | 43580215201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-08-28 | 1301561 | 1304861 | 1221532 | 3300 | 0 | 1218439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 1531944
3 | T3659 | 43728425201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-06-14 | 1158389 | 1230266 | 1207818 | 71877.06 | 0 | 1207818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207818 | 1207818 | 0 | 1285000
3 | T3663 | 43188345201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2019-08-28 | 656987 | 668791 | 649887 | 11804.09 | 0 | 649887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649887 | 649887 | 0 | 691494
3 | T3668 | 43580015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-09-25 | 1427167 | 1429917 | 1395761 | 2750 | 0 | 1394795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395761 | 1394795 | -966 | 1392504
3 | T3694 | 43814015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 1092210 | 1092210 | 1034116 | 0 | 0 | 1032121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034116 | 1032121 | -1995 | 1201385
3 | T3695 | 43775415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 9989122 | 9989122 | 9612555 | 0 | 0 | 9581632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 10772800
3 | T3708 | 43662015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-05-31 | 2063749 | 2063749 | 2000237 | 0 | 0 | 2000237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 1864559
3 | T3724 | 43972215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 4652882 | 4613196 | 4707642 | -39686.22 | 0 | 4673127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4707642 | 4673127 | -34515 | 4516754
3 | T3732 | 44172515201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-01-29 | 724625 | 724625 | 671669 | 0 | 0 | 671669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671669 | 671669 | 0 | 569929
3 | T3734 | 44174315201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-03-25 | 161220 | 161220 | 147933 | 0 | 0 | 147933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147933 | 147933 | 0 | 223390
3 | T3737 | 44174415201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2020-05-20 | 163087 | 163087 | 147675 | 0 | 0 | 147675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147675 | 147675 | 0 | 241247
3 | T3739 | 44173715201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-03-25 | 229048 | 236141 | 232144 | 7093.4 | 0 | 232144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232144 | 232144 | 0 | 145096
3 | T3747 | 44173515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 512999 | 567826 | 538766 | 54827.08 | 0 | 538766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538766 | 538766 | 0 | 532694
3 | T3748 | 44404215201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2020-04-29 | 600835 | 600835 | 529358 | 0 | -3380 | 525978 | -3380 | 0 | 0 | 0 | 0 | 0 | -3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3380 | 525978 | 525978 | 0 | 859033
3 | T9021 | 44531225216 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 1606769 | 1606769 | 1542684 | 0 | 0 | 1542685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542684 | 1542685 | 1 | 1883891
4 | E4M90 | 41242035201 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2013-04-24 | 66615000 | 69280598 | 68971834 | 2665598.47 | -91753 | 65937569 | -91753 | 0 | 0 | 0 | 0 | 0 | -91753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91753 | 68880082 | 65937569 | -2942512 | 64729281 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4N82 | 22777515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-05-20 | 29568100 | 31002780 | 30989356 | 1434680.24 | 0 | 29990698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30989356 | 29990698 | -998657 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4T09 | 42264125201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-06-14 | 12892089 | 13358507 | 13278726 | 466418.45 | 0 | 13203962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13278726 | 13203962 | -74765 | 15739612
4 | E4T46 | 43388815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-01-04 | 1592830 | 1700395 | 1656013 | 107565.12 | 0 | 1656013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656013 | 1656013 | 0 | 1969428
4 | E4T54 | 42957525201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2019-02-01 | 1034836 | 1034836 | 958378 | 0 | 0 | 958293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958378 | 958293 | -85 | 1135394
4 | E4T56 | 43578125201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2019-03-08 | 1488175 | 1499756 | 1508806 | 11580.46 | 0 | 1504997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508806 | 1504997 | -3808 | 1272541
4 | E4T61 | 43783415201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2019-04-05 | 5430718 | 5477794 | 5212471 | 47075.43 | -3447 | 5104984 | -3447 | 0 | 0 | 0 | 0 | 0 | -3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3447 | 5209024 | 5104984 | -104039 | 5340256
4 | E4T65 | 44144215201 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 1246700 | 1246700 | 1046614 | 0 | 0 | 1046614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046614 | 1046614 | 0 | 2119586
4 | E4T67 | 43990015201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 399288 | 399288 | 314456 | 0 | 0 | 314456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314456 | 314456 | 0 | 459766
4 | E4T78 | 43996015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-12-06 | 886114 | 886114 | 834084 | 0 | 0 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834084 | 834084 | 0 | 1407859
4 | E4T84 | 43389615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-12-06 | 802818 | 802818 | 776329 | 0 | 0 | 776329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776329 | 776329 | 0 | 659386 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4T85 | 43984315201 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2020-01-03 | 3861123 | 3862794 | 3684709 | 1671.09 | 325000 | 3667300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 100000 | 0 | 0 | 0 | 325000 | 325000 | 4009709 | 3667300 | -342410 | 5435662 | B1:B3 | ACC - NO EXCUSE BONUS:ACC - LANE RENTAL
4 | E4T86 | 44061215201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2020-02-07 | 600421 | 614749 | 545426 | 14328.17 | 0 | 545426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545426 | 545426 | 0 | 606556
4 | E4T88 | 43986015201 | F650405645 | STATE CONTRACTING & ENGINEERING CORPORAT | N/A | N/A | N/A | N/A | 2020-03-06 | 1568562 | 1545768 | 1524057 | -22794.12 | 0 | 1524072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1524057 | 1524072 | 15 | 1393386
4 | E4T89 | 43214615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 641391 | 641391 | 602117 | 0 | 0 | 602117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602117 | 602117 | 0 | 898061
4 | E4T90 | 43995815201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 387073 | 387073 | 364661 | 0 | 0 | 364661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364661 | 364661 | 0 | 430109
4 | E4T92 | 44140915201 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-17 | 888985 | 900166 | 850166 | 11180.7 | 0 | 850166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850166 | 850166 | 0 | 1308480
4 | E4U43 | 44332215201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2020-04-03 | 444903 | 444903 | 440091 | 0 | 0 | 440091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440091 | 440091 | 0 | 336191
4 | E4U55 | 43996115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-03-06 | 613162 | 613162 | 583262 | 0 | 0 | 583262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583262 | 583262 | 0 | 649888
4 | E4U78 | 4476871H201 | F522113986 | STRUCTURAL TECHNOLOGIES LLC | N/A | N/A | N/A | N/A | 2020-07-14 | 100000 | 15900149 | 15843107 | 15800148.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15843107 | 0 | -15843107 | 100000
4 | T4461 | 42793715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-24 | 13403577 | 14388653 | 13899377 | 985075.39 | 0 | 14133238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13899377 | 14133238 | 233861 | 14532810
4 | T4462 | 43232315203 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-24 | 9366292 | 10932113 | 10870783 | 1565821.06 | -21870 | 10956087 | -21870 | 0 | 0 | 0 | 0 | 0 | -21870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21870 | 10848913 | 10956087 | 107174 | 8174811
4 | T4473 | 42751615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-03-28 | 14954960 | 14788864 | 14238463 | -166096.87 | 0 | 14563199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14238463 | 14563199 | 324737 | 12073780 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4479 | 43059025201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-26 | 815678 | 823050 | 757384 | 7371.16 | 0 | 756711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757384 | 756711 | -673 | 726060
4 | T4483 | 44008115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 977778 | 1000403 | 798387 | 22625.47 | 0 | 798134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798387 | 798134 | -253 | 1192931
4 | T4485 | 43634115201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-06-13 | 1979980 | 2224615 | 2010428 | 244634.8 | 0 | 2010404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010428 | 2010404 | -24 | 2546948
4 | T4489 | 43770115201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 5985000 | 6208144 | 6389050 | 223143.55 | 0 | 6349948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6389050 | 6349948 | -39102 | 6481016
4 | T4491 | 43234815201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 5272134 | 5501959 | 5429646 | 229824.88 | 0 | 5415536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5429646 | 5415536 | -14110 | 4730109
4 | T4496 | 43288335201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 3387195 | 3736919 | 3518847 | 349724.02 | 0 | 3516238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518847 | 3516238 | -2608 | 2883072
4 | T4498 | 43689315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 3421871 | 3525755 | 3579940 | 103883.53 | 0 | 3579922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 2478815
4 | T4499 | 44055425201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2019-01-30 | 5385476 | 8390963 | 8381389 | 3005487.33 | 0 | 8382329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8381389 | 8382329 | 940 | 5178384
4 | T4500 | 43435915201 | F591358949 | ANZAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2477341 | 2477341 | 2598284 | 0 | 0 | 2597220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2598284 | 2597220 | -1063 | 1937291
4 | T4501 | 43468615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 4133433 | 4218884 | 4214126 | 85450.43 | 0 | 4199464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4214126 | 4199464 | -14662 | 4929153
4 | T4502 | 43630315202 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1465257 | 1481535 | 1429078 | 16277.94 | 0 | 1429078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429078 | 1429078 | 0 | 1399471
4 | T4503 | 43611115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 2257891 | 2372485 | 2277661 | 114594.11 | 0 | 2279759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2277661 | 2279759 | 2097 | 2312700
4 | T4506 | 43783215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 8509769 | 8729916 | 8272368 | 220146.63 | 0 | 8168439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8272368 | 8168439 | -103929 | 10259257
4 | T4507 | 43771815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 345927 | 345927 | 329094 | 0 | 0 | 329032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329094 | 329032 | -62 | 362984
4 | T4508 | 43773115201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 6817376 | 6968476 | 6729053 | 151100.52 | 0 | 6695309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6729053 | 6695309 | -33744 | 7367258
4 | T4510 | 43234415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 8369134 | 8429194 | 8328626 | 60059.55 | 0 | 8158766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8328626 | 8158766 | -169861 | 9265923
4 | T4513 | 43770815201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-07-31 | 602298 | 602298 | 562547 | 0 | 0 | 562065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562547 | 562065 | -482 | 569666
4 | T4514 | 43778515201 | F261264765 | HIGHSTYLE ENGINEERING & CONSTRUCTION SER | N/A | N/A | N/A | N/A | 2020-01-29 | 277929 | 277929 | 262174 | 0 | 0 | 261778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262174 | 261778 | -397 | 312614
4 | T4518 | 43829115201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 1840414 | 1840414 | 1784131 | 0 | 0 | 1773834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1784131 | 1773834 | -10297 | 1949951
4 | T4520 | 43770215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 511111 | 511111 | 500925 | 0 | 0 | 500762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500925 | 500762 | -163 | 517002
4 | T4524 | 43770715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 3289804 | 3447958 | 3265220 | 158153.57 | 0 | 3255145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3265220 | 3255145 | -10075 | 2506278
4 | T4526 | 43689425201 | F590229150 | EBSARY FOUNDATION COMPANY | N/A | N/A | N/A | N/A | 2019-09-25 | 2010552 | 2002087 | 1918992 | -8464.5 | 0 | 1917486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918992 | 1917486 | -1506 | 2144003
4 | T4529 | 44271915201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-10-30 | 190000 | 193240 | 183953 | 3239.67 | 0 | 183953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183953 | 183953 | 0 | 172636
4 | T4531 | 44313515201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1219731 | 1221270 | 1174601 | 1538.68 | 0 | 1174601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174601 | 1174601 | 0 | 921805
4 | T4534 | 43654115201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2020-02-26 | 1247199 | 1247199 | 1170098 | 0 | 0 | 1169903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170098 | 1169903 | -195 | 1326125
4 | T4536 | 43838915201 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2020-01-29 | 1482069 | 1482069 | 1327510 | 0 | 0 | 1325299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1327510 | 1325299 | -2211 | 1483090
4 | T4540 | 43834515201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-01-29 | 1005700 | 1022365 | 875802 | 16665 | 0 | 875802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875802 | 875802 | 0 | 1115608
4 | T4545 | 43984415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 2092533 | 2459453 | 2601638 | 366919.82 | 0 | 2600754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601638 | 2600754 | -884 | 2283381
4 | T4547 | 43838715201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-04-29 | 844444 | 844444 | 723057 | 0 | 0 | 723057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723057 | 723057 | 0 | 1015766
4 | T4548 | 44368515201 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 255430 | 255430 | 242375 | 0 | 0 | 242375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242375 | 242375 | 0 | 277364
4 | T4549 | 43783015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 1201295 | 1201295 | 1104692 | 0 | 0 | 1104644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104692 | 1104644 | -48 | 1290272
4 | T4550 | 43689715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-02-26 | 1446899 | 1473105 | 1500428 | 26206.14 | 0 | 1500428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500428 | 1500428 | 0 | 1630171
5 | E50A1 | 44327115201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2020-02-04 | 258893 | 258893 | 238371 | 0 | 0 | 238371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238371 | 238371 | 0 | 275763
5 | E50A4 | 43754315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-01-07 | 7148284 | 7148284 | 7569825 | 0 | 0 | 7442288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7569825 | 7442288 | -127537 | 7601972
5 | E52A4 | 44539715201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-09-01 | 220607 | 220607 | 186260 | 0 | 0 | 186260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186260 | 186260 | 0 | 258725
5 | E53A0 | 44327015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-03-03 | 341127 | 328648 | 362626 | -12478.53 | 0 | 362626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362626 | 362626 | 0 | 395488
5 | E54A5 | 44417615201 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2020-06-02 | 755986 | 755986 | 748590 | 0 | 0 | 748590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748590 | 748590 | 0 | 843431
5 | E5W26 | 24271525201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2014-09-05 | 204975000 | 206461939 | 205886429 | 1486938.81 | -4665526 | 190845664 | -5989463 | 0 | 0 | 0 | 0 | 0 | -5989463 | -645264 | 0 | 2000000 | 0 | 0 | -30800 | 1323936 | -4665526 | 201220903 | 190845664 | -10375239 | 204975000 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Y62 | 23831925201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-03-21 | 22219000 | 22351916 | 22222555 | 132915.67 | 0 | 22276693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22222555 | 22276693 | 54139 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Z19 | 43927315201 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2018-04-03 | 149935 | 149935 | 128601 | 0 | -51092 | 77509 | -51092 | 0 | 0 | 0 | 0 | 0 | -51092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51092 | 77509 | 77509 | 0 | 204099
5 | E5Z20 | 43632415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-05 | 1052310 | 1052310 | 1030338 | 0 | 0 | 1030338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 1235089
5 | E5Z30 | 43952115201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2018-06-05 | 257400 | 257400 | 193136 | 0 | 0 | 193136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193136 | 193136 | 0 | 307382
5 | E5Z32 | 43927515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-02-06 | 3899386 | 3941689 | 3941568 | 42303.43 | 0 | 3939264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3941568 | 3939264 | -2304 | 4041614
5 | E5Z46 | 44116815201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2018-11-06 | 546235 | 620855 | 527394 | 74620 | -96570 | 526966 | -96570 | 0 | 0 | 0 | 0 | 0 | -96570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96570 | 430824 | 526966 | 96143 | 603864
5 | E5Z61 | 43544625201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-03-20 | 2660660 | 2660660 | 2610660 | 0 | 0 | 2610660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2610660 | 2610660 | 0 | 2903534 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5Z64 | 44121015201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-07 | 4022402 | 4286073 | 4275710 | 263671.46 | 0 | 4237738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4275710 | 4237738 | -37972 | 4100418
5 | E5Z68 | 44096915201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-05 | 1563424 | 1567539 | 1517384 | 4114.91 | 0 | 1517184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517384 | 1517184 | -199 | 2235952
5 | E5Z77 | 43912115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-02 | 3278490 | 3271086 | 3476815 | -7404 | 0 | 3410719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3476815 | 3410719 | -66096 | 3806384
5 | E5Z83 | 44326615201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-06-04 | 176487 | 176487 | 170000 | 0 | -8676 | 161324 | -8676 | 0 | 0 | 0 | 0 | 0 | -8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8676 | 161324 | 161324 | 0 | 141232
5 | E5Z84 | 43643425201 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 296220 | 296220 | 278504 | 0 | 0 | 278504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278504 | 278504 | 0 | 340891
5 | E5Z85 | 43923615201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-08-06 | 1444444 | 1444444 | 1364062 | 0 | -69930 | 1311383 | -69930 | 0 | 0 | 0 | 0 | 0 | -69930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69930 | 1294132 | 1311383 | 17251 | 1314466
5 | E5Z89 | 44326815201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2019-10-01 | 301514 | 301514 | 272690 | 0 | 0 | 272690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272690 | 272690 | 0 | 414691
5 | E5Z91 | 43912215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-01 | 1447000 | 1447000 | 1407072 | 0 | 0 | 1407072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407072 | 1407072 | 0 | 1302061
5 | E5Z97 | 44330815201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 239478 | 239478 | 244020 | 0 | 0 | 244020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244020 | 244020 | 0 | 158006
5 | E5Z98 | 43618725201 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2020-01-07 | 675628 | 675628 | 649188 | 0 | 0 | 649188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649188 | 649188 | 0 | 631570
5 | T5530 | 23968215201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 37673821 | 40588843 | 42253807 | 2915022.11 | 586693 | 42067685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586693 | 0 | 0 | 0 | 0 | 0 | 586693 | 586693 | 42840500 | 42067685 | -772815 | 38523048
5 | T5589 | 23827525201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2017-06-14 | 32839302 | 33739239 | 34780986 | 899936.95 | -4571 | 35604304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4571 | -4571 | -4571 | 34776415 | 35604304 | 827889 | 46309916
5 | T5590 | 42690535201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 38848299 | 39691396 | 40371218 | 843097.53 | 0 | 40086419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40371218 | 40086419 | -284799 | 42395483
5 | T5592 | 43440715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 6864444 | 6916430 | 6987391 | 51985.55 | 0 | 7341346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 9424561
5 | T5604 | 43734515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 6332535 | 6387426 | 6284035 | 54891.24 | 0 | 6274517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6284035 | 6274517 | -9518 | 7459742
5 | T5605 | 43565925201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 7668889 | 8851634 | 8747850 | 1182744.75 | -12870 | 8821718 | 0 | 0 | 0 | 0 | 0 | -12870 | -12870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12870 | 8734980 | 8821718 | 86738 | 9666692
5 | T5607 | 43612315201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1114942 | 1116831 | 1062929 | 1889.41 | 0 | 1060081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062929 | 1060081 | -2848 | 1090282
5 | T5615 | 43793115201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-03-28 | 1435273 | 1466273 | 1433905 | 31000 | -119880 | 1313837 | -119880 | 0 | 0 | 0 | 0 | 0 | -119880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119880 | 1314025 | 1313837 | -188 | 1578333
5 | T5618 | 43643515201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-01-29 | 249700 | 249700 | 238354 | 0 | 0 | 238354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238354 | 238354 | 0 | 259439
5 | T5624 | 43687915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 9260071 | 9353754 | 9333412 | 93683.37 | 0 | 9239091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9333412 | 9239091 | -94321 | 12044261
5 | T5625 | 42421715201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-10-31 | 7136709 | 7786367 | 8041380 | 649657.5 | 0 | 7917779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8041380 | 7917779 | -123601 | 7854127
5 | T5629 | 43759215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-26 | 1369369 | 1373147 | 1429206 | 3778.24 | 0 | 1426624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429206 | 1426624 | -2583 | 1077107
5 | T5630 | 43732715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 7593730 | 7636258 | 7693686 | 42527.98 | 0 | 7601216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7693686 | 7601216 | -92470 | 10653193
5 | T5634 | 43734815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 7052425 | 7232569 | 7465970 | 180144.34 | 0 | 7455412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7465970 | 7455412 | -10558 | 10311528
5 | T5648 | 43759515201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 2614878 | 2614878 | 2572113 | 0 | 0 | 2540351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2572113 | 2540351 | -31762 | 3184787
5 | T5649 | 43747015201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 1816910 | 1816910 | 1789398 | 0 | -54945 | 1734453 | -54945 | 0 | 0 | 0 | 0 | 0 | -54945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -54945 | 1734453 | 1734453 | 0 | 2329182
5 | T5652 | 43097555201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2616100 | 2718053 | 2707282 | 101952.75 | 0 | 2685273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707282 | 2685273 | -22009 | 3057555
5 | T5653 | 43967915201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 782050 | 805120 | 729222 | 23069.54 | 0 | 728882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729222 | 728882 | -340 | 797260
5 | T5660 | 24099255201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-10-31 | 4991772 | 5081949 | 5090998 | 90176.63 | 0 | 5012393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5090998 | 5012393 | -78604 | 4917854
5 | T5661 | 43968225201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5973653 | 5976861 | 5959722 | 3208.31 | -20210 | 5890124 | 0 | 0 | 0 | 0 | 0 | -20210 | -20210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20210 | 5939511 | 5890124 | -49387 | 5898605
5 | T5677 | 43923315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 6452955 | 6597931 | 6823659 | 144976.35 | 0 | 6790182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823659 | 6790182 | -33477 | 7161772 | B0 | ACC - LUMP SUM
5 | T5714 | 44137015201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2020-07-29 | 531915 | 531915 | 514987 | 0 | 0 | 514987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514987 | 514987 | 0 | 535536
6 | E6H56 | 42999615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | 1195598 | 1195598 | 1078448 | 0 | 0 | 1078448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 1501205
6 | E6J97 | 43338115201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-09-29 | 14830791 | 16868333 | 16284955 | 2037542.36 | 0 | 13536669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16284955 | 13536669 | -2748287 | 15266369
6 | E6K57 | 43854015201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-05-15 | 3582848 | 3582848 | 3528511 | 0 | 0 | 3528511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528511 | 3528511 | 0 | 3999000 | LBDB | LOW BID DESIGN BUILD
6 | E6K74 | 43652715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-04-25 | 4041049 | 4041049 | 3981909 | 0 | 0 | 3981877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3981909 | 3981877 | -32 | 4437638
6 | E6K86 | 43653215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-27 | 1525830 | 1665708 | 1656441 | 139878.01 | 0 | 1656441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656441 | 1656441 | 0 | 1287132
6 | E6L73 | 44183715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-28 | 1046629 | 1046629 | 1032137 | 0 | 0 | 1030814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032137 | 1030814 | -1322 | 1027325
6 | E6L77 | 44059015201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-02-28 | 569569 | 569569 | 532425 | 0 | 0 | 532327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532425 | 532327 | -98 | 521618
6 | E6L92 | 44203815201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-28 | 454454 | 453454 | 414482 | -1000 | 0 | 414293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414482 | 414293 | -189 | 422168
6 | E6L95 | 44174015201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-10-31 | 6166186 | 6166186 | 6056649 | 0 | 796000 | 6054106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796000 | 0 | 0 | 0 | 0 | 0 | 796000 | 796000 | 6852649 | 6054106 | -798543 | 6464443 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE
6 | E6M35 | 42934165201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 550550 | 550550 | 522745 | 0 | 0 | 522024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522745 | 522024 | -721 | 547294
6 | E6M59 | 43634425201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-27 | 548409 | 548409 | 466503 | 0 | 0 | 466503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466503 | 466503 | 0 | 490515
6 | T6420 | 43345515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 5904592 | 5500862 | 5293728 | -403729.56 | 300000 | 5304093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 5593728 | 5304093 | -289635 | 5663802 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6422 | 42736925201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 37393744 | 38509420 | 38324783 | 1115676.08 | 2120000 | 38304570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 120000 | 0 | 2120000 | 2120000 | 40444783 | 38304570 | -2140213 | 43619309 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6424 | 42736915201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 31696367 | 32356389 | 32549528 | 660021.56 | 2000000 | 32091160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 200000 | 0 | 2000000 | 2000000 | 34549528 | 32091160 | -2458368 | 37329750 | B5:B2:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6425 | 42597925201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 2976484 | 3072883 | 2821239 | 96399 | 0 | 2821817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 2758437 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6441 | 43117045201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 3159760 | 3171958 | 3147560 | 12198.41 | 200000 | 3145794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3347560 | 3145794 | -201766 | 3433250 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6442 | 43063735201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 12892744 | 13383683 | 13072251 | 490939.04 | 790000 | 13016796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750500 | 0 | 0 | 0 | 39500 | 0 | 790000 | 790000 | 13862251 | 13016796 | -845455 | 14924932 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6447 | 43791515201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2469000 | 2562153 | 2344210 | 93152.77 | 150000 | 2343341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2494210 | 2343341 | -150869 | 2116609 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6449 | 43345545201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 2745127 | 2934099 | 2882088 | 188972.29 | 0 | 2869467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882088 | 2869467 | -12621 | 2941133
6 | T6450 | 40557565201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 16353017 | 17066081 | 16492362 | 713064.4 | 1340000 | 16289899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260000 | 0 | 0 | 0 | 80000 | 0 | 1340000 | 1340000 | 17832362 | 16289899 | -1542462 | 18314994 | B2:B5:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6456 | 44001315201 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 277873 | 277873 | 253147 | 0 | 0 | 252697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253147 | 252697 | -451 | 307708
6 | T6457 | 44018415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1600000 | 1600000 | 1513631 | 0 | 0 | 1513712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 1865185
6 | T6459 | 44018715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 1799799 | 1826976 | 1697745 | 27176.72 | 0 | 1696156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 1983631
6 | T6463 | 43791615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 893110 | 893110 | 829996 | 0 | 0 | 829996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829996 | 829996 | 0 | 974751
6 | T6464 | 43908815201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 2747184 | 2747184 | 2689934 | 0 | 160000 | 2684826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000 | 2849934 | 2684826 | -165108 | 2857612 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6470 | 43991715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 457433 | 488251 | 450352 | 30818 | 0 | 449506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450352 | 449506 | -846 | 481418
6 | T6471 | 43998315201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1419001 | 1428592 | 1341311 | 9590.66 | 0 | 1340742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341311 | 1340742 | -569 | 1482287
6 | T6473 | 43326425201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 1569997 | 1569997 | 1553340 | 0 | 100000 | 1548938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1653340 | 1548938 | -104402 | 1744258 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6474 | 43991915201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2019-10-30 | 2171998 | 2171998 | 2087179 | 0 | 80000 | 2084071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000 | 80000 | 2167179 | 2084071 | -83108 | 1943700 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6477 | 44281315201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2019-03-27 | 2060596 | 2075271 | 2107347 | 14675.27 | 0 | 2106923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107347 | 2106923 | -424 | 2038303
6 | T6484 | 44017515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-09-25 | 800000 | 800000 | 759142 | 0 | 0 | 758896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759142 | 758896 | -246 | 865771
6 | T6499 | 43992215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 630688 | 630688 | 630936 | 0 | 0 | 630438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630936 | 630438 | -499 | 547117
6 | T6523 | 42918535201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-01-29 | 1588502 | 1626096 | 1468338 | 37593.55 | 100000 | 1467332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1568338 | 1467332 | -101006 | 1654599 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE
7 | E7K30 | 42450725201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 8315000 | 8940193 | 9001435 | 625193.38 | 0 | 9001737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
7 | E7M29 | 43954715201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-09 | 4417200 | 4417200 | 4366662 | 0 | 0 | 4366662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 5635000
7 | E7M31 | 43751715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2019-03-13 | 2064981 | 1997687 | 1923224 | -67293.76 | 0 | 1923189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923224 | 1923189 | -35 | 2265000
7 | E7M35 | 43642115201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-04-10 | 3208889 | 3213321 | 3310989 | 4432.58 | 0 | 3270137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310989 | 3270137 | -40853 | 3417309
7 | E7M50 | 42905925201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2019-06-12 | 257038 | 257038 | 238009 | 0 | 0 | 238009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238009 | 238009 | 0 | 255036
7 | E7M53 | 43878315201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-10 | 1279713 | 1279713 | 1030596 | 0 | 0 | 1029149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030596 | 1029149 | -1447 | 2158375
7 | E7M74 | 43955115201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2019-09-11 | 555000 | 555000 | 507000 | 0 | 0 | 507000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507000 | 507000 | 0 | 1075906 | B0 | ACC - LUMP SUM
7 | E7M78 | 43624315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-11 | 761530 | 761530 | 782626 | 0 | 0 | 782314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782626 | 782314 | -312 | 720000
7 | E7M87 | 43952515201 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2019-11-13 | 211449 | 219152 | 195461 | 7703.18 | 0 | 195461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195461 | 195461 | 0 | 206944
7 | E7M88 | 43751915201 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-08 | 748000 | 748000 | 716109 | 0 | 0 | 716109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716109 | 716109 | 0 | 1657500 | B0 | ACC - LUMP SUM
7 | E7M89 | 43878615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-30 | 194157 | 194157 | 183157 | 0 | 0 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183157 | 183157 | 0 | 280000
7 | E7M90 | 43983015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-02-12 | 682863 | 682863 | 661465 | 0 | 0 | 661465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661465 | 661465 | 0 | 786200
7 | E7M92 | 44146815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-04-08 | 657608 | 657608 | 639093 | 0 | 0 | 639093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639093 | 639093 | 0 | 830250
7 | E7M95 | 43762315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 2367977 | 2362575 | 2251785 | -5402.04 | 0 | 2251785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2251785 | 2251785 | 0 | 2542381
7 | E7M97 | 44024515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 1873216 | 1882322 | 1896442 | 9105.36 | -6760 | 1877971 | -6760 | 0 | 0 | 0 | 0 | 0 | -6760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6760 | 1889682 | 1877971 | -11712 | 1912250
7 | E7N03 | 43673425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 256281 | 256281 | 229693 | 0 | 0 | 229693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229693 | 229693 | 0 | 284492
7 | E7N04 | 44580315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-01-08 | 342938 | 342938 | 334918 | 0 | 0 | 334918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334918 | 334918 | 0 | 323541
7 | E7N06 | 44108415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-03-11 | 2651273 | 2651273 | 2594154 | 0 | 0 | 2581698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2594154 | 2581698 | -12456 | 2513323
7 | E7N20 | 25693135201 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 217378 | 261168 | 240911 | 43790 | -8360 | 232551 | -8360 | 0 | 0 | 0 | 0 | 0 | -8360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8360 | 232551 | 232551 | 0 | 350000
7 | E7N22 | 41101455201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2020-03-11 | 1199360 | 1199360 | 1220405 | 0 | 0 | 1219955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220405 | 1219955 | -449 | 1261100
7 | E7N47 | 43955015201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-09-09 | 178219 | 178219 | 165324 | 0 | 0 | 165324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165324 | 165324 | 0 | 214800
7 | E7R14 | 43402715201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2019-01-22 | 3891051 | 3854521 | 3786721 | -36529.93 | 0 | 3786721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786721 | 3786721 | 0 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7375 | 25729865201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 8414444 | 8827124 | 8758066 | 411473.84 | -36450 | 8979106 | -36450 | 0 | 0 | 0 | 0 | 0 | -36450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36450 | 8721616 | 8979106 | 257489 | 9174081 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7403 | 43484815201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 15246325 | 16369545 | 16674514 | 1123220.1 | 0 | 16740305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16674514 | 16740305 | 65791 | 16929302
7 | T7406 | 42895715201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-05-23 | 15421093 | 16109245 | 16482253 | 688151.71 | 0 | 16467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 18474979
7 | T7411 | 43982925201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-04-25 | 2168162 | 2168162 | 2100062 | 0 | 0 | 2100043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 3284499
7 | T7413 | 43658815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 26892177 | 27245569 | 27594120 | 353391.83 | -41000 | 27404700 | 0 | 0 | 0 | 0 | 0 | -41000 | -41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41000 | 27553120 | 27404700 | -148420 | 31660667
7 | T7414 | 43571915201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 2614444 | 2751684 | 2735520 | 137239.87 | 0 | 2737146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735520 | 2737146 | 1626 | 3125000
7 | T7419 | 43050225201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 987665 | 987665 | 987634 | 0 | 0 | 987634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987634 | 987634 | 0 | 1403000
7 | T7420 | 43982945201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 1212499 | 1212499 | 1154516 | 0 | -101565 | 1052959 | -101565 | 0 | 0 | 0 | 0 | 0 | -101565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101565 | 1052951 | 1052959 | 8 | 1500000
7 | T7425 | 43982965201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 914914 | 939896 | 895662 | 24981.9 | 0 | 895638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895662 | 895638 | -24 | 1060000
7 | T7426 | 43648715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 2303437 | 2349376 | 2210807 | 45938.74 | 0 | 2215714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 2215185
7 | T7431 | 41685615201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 2024792 | 2024792 | 1923484 | 0 | -64935 | 1857569 | -64935 | 0 | 0 | 0 | 0 | 0 | -64935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64935 | 1858549 | 1857569 | -979 | 2200000
7 | T7432 | 43982955201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 409384 | 409384 | 361091 | 0 | 0 | 361076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361091 | 361076 | -16 | 490000
7 | T7435 | 43731215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 20077627 | 19707738 | 19775513 | -369888.35 | 1600000 | 19707851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 21375513 | 19707851 | -1667662 | 32430000 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7436 | 43648515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 6816208 | 6816208 | 6910378 | 0 | 0 | 6860977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6910378 | 6860977 | -49401 | 6893702
7 | T7440 | 44286215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2725693 | 2725693 | 2560514 | 0 | 0 | 2560514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560514 | 2560514 | 0 | 2929941
7 | T7441 | 43764315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 2094475 | 2094475 | 2116984 | 0 | 0 | 2111225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116984 | 2111225 | -5759 | 1713900
7 | T7443 | 44109815201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 1372094 | 1372094 | 1285441 | 0 | 0 | 1284319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285441 | 1284319 | -1122 | 1324000
7 | T7452 | 43969915201 | F465262082 | HARTMAN CIVIL CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 533787 | 533787 | 537223 | 0 | 0 | 537223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537223 | 537223 | 0 | 665000
7 | T7453 | 44582415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | 607102 | 607102 | 507221 | 0 | 0 | 507221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507221 | 507221 | 0 | 562014
7 | T7454 | 44582715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-06-10 | 273542 | 273542 | 259612 | 0 | 0 | 259612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259612 | 259612 | 0 | 245562
7 | T7457 | 44541015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 1090411 | 1090411 | 1018989 | 0 | 0 | 1018989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1018989 | 1018989 | 0 | 1330400
8 | E8M65 | 40609615201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2013-06-13 | 145330000 | 156978418 | 155492910 | 11648418.01 | 0 | 153123645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155492910 | 153123645 | -2369264 | 204625259 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
8 | E8N20 | 42714615201 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2014-06-23 | 54444321 | 55997037 | 56078061 | 1552716.3 | -16000 | 54888233 | 0 | 0 | 0 | 0 | 0 | -16000 | -16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16000 | 56062061 | 54888233 | -1173828 | 59644381 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR
8 | E8N58 | 40610315201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2015-05-19 | 49459029 | 53635234 | 54832716 | 4176205.25 | -13000 | 54736862 | 0 | 0 | 0 | 0 | 0 | -13000 | -13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 54819716 | 54736862 | -82853 | 55428349
8 | E8N75 | 40611015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-03-08 | 68542000 | 73971118 | 73863918 | 5429118.38 | 0 | 74855111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73863918 | 74855111 | 991193 | 66110895 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8P02 | 40609055201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-16 | 92527388 | 97077732 | 98980425 | 4550343.91 | -16500 | 98412351 | 0 | 0 | 0 | 0 | 0 | -16500 | -16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16500 | 98963925 | 98412351 | -551574 | 105363394
8 | E8P82 | 43715615201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-06-14 | 31974887 | 33530949 | 33963963 | 1556062.19 | -335724 | 34124684 | -290724 | 0 | 0 | 0 | 0 | -45000 | -335724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -335724 | 33628239 | 34124684 | 496445 | 0
8 | E8Q10 | 43661915201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2016-06-14 | 29944488 | 30283733 | 28559596 | 339245.44 | -3000 | 28678425 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 28556596 | 28678425 | 121829 | 22863153
8 | E8Q53 | 43516915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-17 | 27945014 | 28542025 | 28268831 | 597010.58 | -3000 | 29756743 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 28265831 | 29756743 | 1490912 | 31134083
8 | E8Q85 | 43651715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-01-23 | 35890871 | 36842857 | 35395810 | 951985.75 | -10000 | 36253180 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 35385810 | 36253180 | 867370 | 26738962
8 | E8Q93 | 42933915201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-12-12 | 20384811 | 21680602 | 22044940 | 1295791.06 | 0 | 22223134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22044940 | 22223134 | 178193 | 18579757
8 | E8Q94 | 43947815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-27 | 18860577 | 18748056 | 18778411 | -112521.32 | -36500 | 19325544 | 0 | 0 | 0 | 0 | 0 | -36500 | -36500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36500 | 18741911 | 19325544 | 583633 | 29028001
8 | E8R19 | 43560565201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-03-12 | 3952490 | 4022490 | 3821122 | 70000 | 0 | 3821116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 5097785
8 | E8R53 | 44130615201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1048889 | 1191415 | 1210586 | 142526.5 | 0 | 1206725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210586 | 1206725 | -3862 | 1135062
8 | E8R58 | 43799115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-05-14 | 10199910 | 10499910 | 10355353 | 300000 | -12500 | 10192921 | 0 | 0 | 0 | 0 | 0 | -12500 | -12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12500 | 10342853 | 10192921 | -149932 | 11724624
8 | E8R76 | 43945715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-03-12 | 12161596 | 11888308 | 12421672 | -273288.03 | 0 | 12337364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12421672 | 12337364 | -84308 | 12670790
8 | E8R81 | 44132225201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-09-10 | 1331331 | 1425403 | 1378701 | 94071.53 | -20000 | 1358701 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 1358701 | 1358701 | 0 | 1246056
8 | E8R95 | 43560575201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-09-10 | 7288625 | 7325241 | 7238007 | 36615.63 | 0 | 7237793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238007 | 7237793 | -213 | 9629063
8 | E8R96 | 44130915201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2019-08-20 | 4958767 | 4943242 | 4981728 | -15525 | 0 | 4960014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4981728 | 4960014 | -21714 | 5574451
8 | E8R99 | 42897115201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2019-09-10 | 994341 | 993765 | 857403 | -576 | 0 | 857403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857403 | 857403 | 0 | 1572138
8 | E8S01 | 43651615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-11-19 | 6508469 | 6508469 | 6539682 | 0 | 0 | 6503176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6539682 | 6503176 | -36506 | 7009173
8 | E8S20 | 43801915201 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2020-03-10 | 438700 | 438700 | 378146 | 0 | 0 | 378146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378146 | 378146 | 0 | 627429
8 | E8S33 | 44261815201 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-05-12 | 1875029 | 1908027 | 1958622 | 32997.96 | 0 | 1958746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1958622 | 1958746 | 123 | 1327554
8 | E8S47 | 44400315201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-28 | 254205 | 254205 | 227921 | 0 | 0 | 227921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227921 | 227921 | 0 | 465727

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 |  | 280843.42 | 39772.99 | 22812.23 | 107188.42 | 151545.99 |  | 602163.05 |  | 228694077 | 0.197% | 450617.06
02 | 0 | 13845.99 |  | 1591.46 | 21963.49 | 558955.08 | -99989.98 | 496366.04 |  | 422125870 | 0.00886% | 37400.94
03 |  | 37704.78 |  | 16090.1 | 14133.44 | 730286.44 |  | 798214.76 |  | 134590252 | 0.05047% | 67928.32
04 | 0 | 420616.42 |  | 28763.69 | 407781.52 | 2617100.01 |  | 3474261.64 |  | 249905765 | 0.343% | 857161.63
05 |  | 411024.82 |  | 1322.3 | 89573.49 | 288412.6 | -199979.96 | 590353.25 |  | 449149652 | 0.1117% | 501920.61
06 |  | 44185.34 | 257 | 13415.95 | 464023.73 | 156649.28 |  | 678531.3 |  | 168118929 | 0.3104% | 521882.02
07 |  | 83449.15 | 40142.29 | 76900.88 | 154707.18 | 68484.6 |  | 423684.1 |  | 150531396 | 0.236% | 355199.5
08 |  | 439083.75 | 0 |  | 0 | 1699954.96 |  | 2139038.71 |  | 626315738 | 0.07011% | 439083.75
Grand Total | 0 | 1730753.67 | 80172.28 | 160896.61 | 1259371.27 | 6271388.96 | -299969.94 | 9202612.85 |  | 2429431679 | 0.133% | 3231193.83
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 |  | 260 | 205 | 141 | 55 | 914 |  | 1575 |  | 661
02 | 0 | 12 |  | 14 | 34 | 1275 | 0 | 1335 |  | 60
03 |  | 17 |  | 13 | 12 | 239 |  | 281 |  | 42
04 | 9 | 109 |  | 23 | 189 | 1374 |  | 1704 |  | 330
05 |  | 372 |  | 0 | 109 | 1436 | 0 | 1917 |  | 481
06 |  | 0 | 0 | 0 | 40 | 300 |  | 340 |  | 40
07 |  | 205 | 0 | 98 | 65 | 402 |  | 770 |  | 368
08 |  | 188 | 3 |  | 0 | 1939 |  | 2130 |  | 191
Grand Total | 9 | 1163 | 208 | 289 | 504 | 7879 | 0 | 10052 |  | 2173
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
4 |  | 16 |  |  |  | 23 | 39 |  | 16 | 677 | 11556 | 5.858%
5 | [5 empty] | 108 | 108 |  | 0 | 60 | 12411 | 0.4834%
6 |  | 30 |  |  |  | 207 | 237 |  | 30 | 72 | 7786 | 0.9247%
7 |  |  |  |  | 16 | 101 | 117 |  | 16 | 346 | 15670 | 2.208%
8 | [5 empty] | 838 | 838 |  | 0 | 481 | 13750 | 3.498%
01 |  | 38 | 107 |  | 123 | 367 | 635 |  | 268 | 308 | 9399 | 3.277%
02 |  | 30 |  |  | 200 | 223 | 453 |  | 230 | 598 | 9367 | 6.384%
03 |  | 151 |  | 75 | 5 | 183 | 414 |  | 231 | 422 | 12649 | 3.336%
04 |  | 40 |  |  | 57 | 645 | 742 |  | 97 | 2270 | 92588 | 2.452%
05
06
07
08
Grand Total |  | 305 | 107 | 75 | 401 | 2695 | 3583

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 1 | 503 | 260.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 2 | 503 | 41.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 3 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 4 | 131 | 2114.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 8 | 131 | 10406 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 5 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 6 | 131 | 4625.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 7 | 131 | 5579.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 10 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 11 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 14 | 131 | 1011.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 16 | 131 | 5376.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 17 | 131 | 1298 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 18 | 131 | 22375.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 19 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 22 | 131 | 1842.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 23 | 503 | 987.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 9 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 15 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 20 | 131 | 4591.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 005 | 2 | 850 | 21 | 503 | 1440.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 010 | 2 |  | 1 | 503 | 95021.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 | 027 | 2 | 850 | 1 | 012 | 6383.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43797315201 | 035 | 2 |  | 1 | 004 | -20000 | 0 | 0 |  | N | 200 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P44 | 43797315201 | 046 | 2 | 850 | 1 | 131 | 688.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 046 | 2 | 850 | 2 | 131 | 8814.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 | 058 | 2 |  | 1 | 113 | 80621.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
01 | E1P87 | 43504015201 | 007 | 2 |  | 1 | 004 | 5877.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P87 | 43504015201 | 012 | 2 |  | 1 | 012 | 4250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P87 | 43504015201 | 012 | 2 |  | 2 | 106 | 5225.47 | 5225.47 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P87 | 43504015201 | 012 | 2 |  | 3 | 115 | 95687.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P87 | 43504015201 | 012 | 2 |  | 4 | 130 | 15577.08 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | E1P87 | 43504015201 | 013 | 2 |  | 1 | 115 | 7349.33 | 7349.33 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P87 | 43504015201 | 013 | 2 |  | 2 | 101 | 16260 | 1109.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P87 | 43504015201 | 013 | 2 |  | 3 | 130 | 7603.36 | 3990 | 4 |  | N | 131 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 1 | 106 | 6786.09 | 6786.09 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 2 | 105 | 22093.75 | 22093.75 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 3 | 128 | 6501.11 | 6501.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 4 | 128 | 4743.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 5 | 010 | 5097.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1P87 | 43504015201 | 026 | 2 |  | 6 | 128 | 3542.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 026 | 2 |  | 7 | 007 | 4647.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1P87 | 43504015201 | 026 | 2 |  | 8 | 012 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P87 | 43504015201 | 026 | 2 |  | 9 | 007 | 3432 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1P87 | 43504015201 | 027 | 2 |  | 1 | 128 | 36321.48 | 36321.48 | 1 |  | C | 39 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 027 | 2 |  | 2 | 003 | 94894.61 | 91269.36 | 0 |  | N | 98 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P87 | 43504015201 | 027 | 2 |  | 3 | 128 | 87278 | 73574.28 | 1 |  | N | 79 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 028 | 2 |  | 1 | 106 | 10679.43 | 10679.43 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P87 | 43504015201 | 028 | 2 |  | 2 | 106 | 4750.43 | 4750.43 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P87 | 43504015201 | 028 | 2 |  | 3 | 106 | 2995.36 | 2995.36 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P87 | 43504015201 | 028 | 2 |  | 4 | 128 | 19026.51 | 19026.51 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P87 | 43504015201 | 028 | 2 |  | 5 | 502 | 37265.42 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
01 | E1R03 | 44021215201 | 001 | 2 |  | 1 | 004 | 2137.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R03 | 44021215201 | 005 | 2 |  | 1 | 003 | 27500 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R03 | 44021215201 | 013 | 2 |  | 1 | 003 | 386267.66 | 0 | 0 |  | N | 120 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R05 | 43629915201 | 011 | 2 |  | 1 | 922 | 7675.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R05 | 43629915201 | 012 | 2 |  | 1 | 001 | 48977.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 017 | 2 |  | 1 | 001 | 339503.5 | 0 | 0 |  | N | 49 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 028 | 2 |  | 1 | 101 | 6036.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 | 029 | 2 |  | 1 | 001 | 175457.23 | 0 | 0 |  | N | 110 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 030 | 2 |  | 1 | 001 | 12036.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 031 | 2 |  | 1 | 923 | 16063.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R05 | 43629915201 | 042 | 2 |  | 1 | 012 | 7188.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R05 | 43629915201 | 043 | 2 |  | 1 | 107 | -2382.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R06 | 43658015201 | 008 | 2 |  | 1 | 105 | 29714.23 | 0 | 2 |  | N | 1 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R07 | 19602255201 | 002 | 2 | 850 | 1 | 101 | 3752.06 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R07 | 19602255201 | 002 | 2 | 850 | 2 | 101 | 8230.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R07 | 19602255201 | 002 | 2 | 850 | 3 | 101 | 21618.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R07 | 19602255201 | 002 | 2 | 850 | 4 | 101 | 0.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R07 | 19602255201 | 003 | 2 |  | 1 | 101 | 62200 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R07 | 19602255201 | 004 | 2 | 850 | 1 | 015 | 6703.35 | 751.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 004 | 2 | 850 | 2 | 015 | 8296.65 | 8296.65 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 018 | 2 |  | 1 | 107 | -10655.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R07 | 19602255201 | 019 | 2 |  | 1 | 105 | 1165.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R07 | 19602255201 | 026 | 2 | 850 | 1 | 015 | 31810.76 | 31810.76 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 026 | 2 | 850 | 2 | 015 | 11651.84 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 026 | 2 | 850 | 3 | 015 | 9240.51 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 043 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 73 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R07 | 19602255201 | 043 | 2 |  | 2 | 860 | 43418.24 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
01 | E1R07 | 19602255201 | 043 | 2 |  | 3 | 105 | 47134.04 | 0 | 1 |  | N | 34 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R11 | 41066625201 | 008 | 2 |  | 1 | 015 | 77663.8 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 015 | 2 | 850 | 1 | 015 | 1715.32 | 1715.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 015 | 2 | 850 | 2 | 015 | 1975.68 | 1975.68 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 015 | 2 | 850 | 3 | 015 | 5511.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 015 | 2 | 850 | 4 | 015 | 20024.66 | 3791.32 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 015 | 2 | 850 | 5 | 015 | 2784.96 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 028 | 2 |  | 1 | 923 | 63777.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 1 | 001 | 663.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 2 | 012 | 16791.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 3 | 115 | 2148.22 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 4 | 012 | 12989.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 5 | 001 | 1936.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 6 | 003 | 6011.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 7 | 115 | 14298.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R11 | 41066625201 | 032 | 2 | 850 | 8 | 108 | 9664.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1R11 | 41066625201 | 033 | 2 | 850 | 1 | 015 | 36812.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 033 | 2 | 850 | 2 | 015 | 402.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 042 | 2 | 850 | 1 | 015 | 14632.75 | 1000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 042 | 2 | 850 | 2 | 015 | 19918.12 | 6918.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 042 | 2 | 850 | 3 | 015 | 2771.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 042 | 2 | 850 | 4 | 015 | 1678.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 047 | 2 |  | 1 | 128 | 49970.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1R11 | 41066625201 | 047 | 2 |  | 2 | 101 | 18564.81 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R11 | 41066625201 | 052 | 2 | 850 | 1 | 015 | 33306.1 | 1330.56 | 1 |  | E | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 052 | 2 | 850 | 2 | 015 | 4693.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 061 | 2 | 850 | 1 | 015 | 4971.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 062 | 2 |  | 1 | 015 | 0 | 0 | 5 |  | N | 14 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R39 | 43802415201 | 008 | 2 |  | 1 | 112 | 46495.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R62 | 43795815201 | 013 | 2 |  | 1 | 012 | 248774.15 | 0 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R64 | 42584125201 | 004 | 2 |  | 1 | 101 | 130800 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R64 | 42584125201 | 009 | 2 |  | 1 | 003 | 231894.52 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R64 | 42584125201 | 010 | 2 |  | 1 | 923 | 3336.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R64 | 42584125201 | 017 | 2 |  | 1 | 503 | 298462.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R64 | 42584125201 | 022 | 2 |  | 1 | 003 | 29327.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R64 | 42584125201 | 025 | 2 |  | 1 | 003 | 305835.34 | 0 | 0 |  | N | 38 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R79 | 43806215201 | 002 | 2 |  | 1 | 101 | 44008 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R79 | 43806215201 | 004 | 2 |  | 1 | 305 | -74488.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R79 | 43806215201 | 006 | 2 |  | 1 | 101 | 4406 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R79 | 43806215201 | 024 | 2 |  | 1 | 115 | 81997.11 | 81997.11 | 1 |  | N | 36 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1R79 | 43806215201 | 024 | 2 |  | 2 | 001 | 49986 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S13 | 44462715201 | 007 | 2 |  | 1 | 007 | 1284.91 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S48 | 44005515201 | 010 | 2 |  | 1 | 112 | 53692.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1665 | 43545015201 | 007 | 2 |  | 1 | 005 | 1419.28 | 1419.28 | 5 |  | N | 12 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1665 | 43545015201 | 007 | 2 |  | 2 | 503 | 54642.28 | 54642.28 | 0 |  | N | 77 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1665 | 43545015201 | 007 | 2 |  | 4 | 107 | 1733.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1665 | 43545015201 | 011 | 2 |  | 1 | 107 | 440 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1665 | 43545015201 | 011 | 2 |  | 2 | 007 | 3628.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1665 | 43545015201 | 016 | 2 |  | 1 | 003 | 3058.79 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1670 | 43512015201 | 010 | 2 |  | 1 | 012 | 17219.6 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1670 | 43512015201 | 013 | 2 |  | 1 | 001 | -1711.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1675 | 43088715201 | 013 | 2 |  | 1 | 005 | -5649.4 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1675 | 43088715201 | 014 | 2 |  | 1 | 115 | 15838.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 1 | 101 | 1749.52 | 260.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 2 | 105 | 2907.93 | 2907.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 3 | 130 | 27615.75 | 27615.75 | 4 |  | N | 72 | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | T1675 | 43088715201 | 015 | 2 |  | 4 | 003 | 2542 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1675 | 43088715201 | 015 | 2 |  | 5 | 003 | 867.6 | 867.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1675 | 43088715201 | 015 | 2 |  | 6 | 007 | -4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1702 | 43509015201 | 010 | 2 |  | 1 | 001 | 13626.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1702 | 43509015201 | 011 | 2 |  | 1 | 015 | 91073.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1712 | 43355025201 | 021 | 2 |  | 1 | 923 | 6013.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1719 | 43800915201 | 007 | 2 |  | 1 | 101 | 4124.16 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1719 | 43800915201 | 013 | 2 |  | 1 | 503 | -8400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1720 | 43655115201 | 010 | 2 |  | 1 | 107 | 93578.25 | 0 | 2 |  | N | 138 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
01 | T1721 | 43955515201 | 010 | 2 |  | 1 | 305 | -49408.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1721 | 43955515201 | 019 | 2 |  | 1 | 012 | 66834.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1721 | 43955515201 | 023 | 2 |  | 1 | 005 | 25509.91 | 25509.91 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1722 | 43806015201 | 007 | 2 |  | 1 | 923 | 16868.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
01 | T1722 | 43806015201 | 013 | 2 |  | 1 | 101 | 1800 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1722 | 43806015201 | 015 | 2 |  | 1 | 305 | -23265.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1722 | 43806015201 | 016 | 2 |  | 1 | 007 | -3902.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1722 | 43806015201 | 016 | 2 |  | 2 | 004 | -10996.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1722 | 43806015201 | 023 | 2 |  | 1 | 101 | 13357.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1731 | 44012015201 | 011 | 2 |  | 1 | 019 | 2230.85 | 2230.85 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | T1731 | 44012015201 | 011 | 2 |  | 2 | 007 | 1087.86 | 0 | 5 |  | N | 26 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1731 | 44012015201 | 011 | 2 |  | 3 | 503 | 5233.26 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1731 | 44012015201 | 011 | 2 |  | 4 | 001 | 9578.51 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1731 | 44012015201 | 011 | 2 |  | 5 | 503 | 4040.52 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1742 | 43539015201 | 008 | 2 |  | 1 | 105 | 10170.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1742 | 43539015201 | 017 | 2 |  | 1 | 003 | 12440.89 | 12440.89 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1744 | 43806115201 | 005 | 2 |  | 1 | 101 | 2100 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1746 | 43801415201 | 002 | 2 |  | 1 | 503 | 163790.71 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1748 | 43510815201 | 006 | 2 |  | 1 | 101 | 3200.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1750 | 44385115201 | 011 | 2 |  | 1 | 001 | 26686.83 | 0 | 0 |  | N | 32 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1752 | 43942315201 | 005 | 2 |  | 1 | 305 | -31086.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1756 | 43511415201 | 007 | 2 |  | 1 | 115 | 27885.96 | 1075.71 | 1 |  | N | 68 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1756 | 43511415201 | 008 | 2 |  | 1 | 012 | 20000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
01 | T1758 | 43943715201 | 002 | 2 |  | 1 | 007 | 89683.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1758 | 43943715201 | 004 | 2 |  | 1 | 001 | 24637.41 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1758 | 43943715201 | 004 | 2 |  | 2 | 101 | 960 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1759 | 44067015201 | 011 | 2 |  | 1 | 503 | -9800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1997 | 40828665201 | 002 | 2 |  | 2 | 105 | -76737.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 009 | 2 |  | 1 | 919 | 4698.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 010 | 2 |  | 1 | 919 | 53137.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 016 | 2 |  | 1 | 004 | 419961.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 | 021 | 2 |  | 1 | 305 | -143937.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 | 029 | 2 |  | 1 | 105 | 17068.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828665201 | 029 | 2 |  | 2 | 107 | 26.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 039 | 2 |  | 1 | 923 | 7185.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 040 | 2 |  | 1 | 923 | 7979.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1997 | 40828665201 | 050 | 2 |  | 1 | 126 | 83920.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1997 | 40828665201 | 050 | 2 |  | 2 | 117 | 254738.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | T1997 | 40828665201 | 053 | 2 |  | 1 | 503 | 31766.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q19 | 43056535201 | 008 | 2 |  | 1 | 300 | -54937.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
02 | E2Q19 | 43056535201 | 008 | 2 |  | 2 | 300 | -27217.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
02 | E2Q19 | 43056535201 | 008 | 2 |  | 3 | 300 | -22854 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
02 | E2Q19 | 43056535201 | 008 | 2 |  | 4 | 004 | -76313.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 008 | 2 |  | 5 | 004 | -55759.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 1 | 004 | 19841.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 3 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 12 | 003 | 4256.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 13 | 350 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 14 | 350 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 21 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 31 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 5 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 6 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 8 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 10 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 11 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 15 | 350 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 16 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 19 | 350 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 20 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 22 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 23 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 24 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 25 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 26 | 003 | 879.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 27 | 350 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 28 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 29 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 026 | 2 | 850 | 30 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 | 027 | 2 |  | 1 | 300 | -8521.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
02 | E2Q19 | 43056535201 | 027 | 2 |  | 2 | 300 | -4142.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
02 | E2Q19 | 43056535201 | 027 | 2 |  | 3 | 019 | -257207.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 027 | 2 |  | 4 | 004 | 40455.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 027 | 2 |  | 5 | 503 | 41099.34 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q19 | 43056535201 | 029 | 2 |  | 1 | 007 | 241267.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q19 | 43056535201 | 031 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q19 | 43056535201 | 053 | 2 |  | 1 | 004 | 22707.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 006 | 2 |  | 1 | 305 | -18243.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 006 | 2 |  | 2 | 305 | -202219.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 006 | 2 |  | 3 | 305 | -43521.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 006 | 2 |  | 4 | 305 | -7517.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 027 | 2 |  | 1 | 007 | 332736.87 | 0 | 5 |  | N | 28 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 1 | 350 | 448.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 3 | 007 | 47220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 8 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 19 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 20 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 21 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 22 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 23 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 24 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 25 | 350 | 226.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 26 | 013 | 2714.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 27 | 004 | 22282.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 28 | 107 | 3810.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 16 | 004 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 10 | 007 | 5912.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 14 | 007 | 3585.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 029 | 2 | 850 | 15 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 035 | 2 |  | 1 | 004 | -60081.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 041 | 2 |  | 1 | 105 | 14220.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 048 | 2 |  | 1 | 503 | -16004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 1 | 350 | 1973.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 3 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 4 | 350 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 8 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 10 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 13 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 049 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 | 050 | 2 |  | 1 | 503 | 30068.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q20 | 43056515201 | 051 | 2 |  | 1 | 007 | 120878.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 | 053 | 2 |  | 1 | 115 | 72295.4 | 0 | 0 |  | N | 105 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q20 | 43056515201 | 054 | 2 |  | 1 | 010 | 254205.02 | 0 | 0 |  | N | 61 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2S01 | 21334575201 | 018 | 2 |  | 1 | 003 | 303082.74 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2S01 | 21334575201 | 022 | 2 |  | 1 | 107 | 362137 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2S01 | 21334575201 | 034 | 2 |  | 1 | 119 | 112341.4 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2S01 | 21334575201 | 041 | 2 |  | 1 | 917 | 187182.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2S01 | 21334575201 | 057 | 2 |  | 1 | 001 | 55395.58 | 0 | 0 |  | N | 52 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2S01 | 21334575201 | 079 | 2 |  | 1 | 001 | 29997.5 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2S01 | 21334575201 | 080 | 2 |  | 1 | 919 | 225831.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2S01 | 21334575201 | 090 | 2 |  | 1 | 004 | 192230.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V62 | 43742915201 | 013 | 2 |  | 1 | 119 | 2692084.44 | 0 | 0 |  | N | 425 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V62 | 43742915201 | 013 | 2 |  | 2 | 119 | 52896.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2V62 | 43742915201 | 019 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2V62 | 43742915201 | 029 | 2 |  | 1 | 923 | 100880.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2W31 | 43373015201 | 011 | 2 |  | 1 | 919 | 16473.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2W31 | 43373015201 | 042 | 2 |  | 1 | 860 | 1478298.5 | 0 | 0 |  | N | 103 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 1 | 001 | 10229.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 2 | 001 | 11127.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 3 | 001 | 7896.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 4 | 001 | 11415.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 026 | 2 | 850 | 5 | 106 | 5158.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X06 | 43076015201 | 032 | 2 | 850 | 1 | 001 | 14052.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 032 | 2 | 850 | 2 | 023 | 3615.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 | 032 | 2 | 850 | 3 | 001 | 3085.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X65 | 43239615201 | 015 | 2 |  | 1 | 003 | -13432.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X65 | 43239615201 | 015 | 2 |  | 2 | 001 | 2477.09 | 0 | 0 |  | N | 87 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y27 | 44129815201 | 009 | 2 |  | 1 | 115 | 1440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y27 | 44129815201 | 016 | 2 |  | 1 | 115 | 67514.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z35 | 43593915201 | 002 | 2 | 850 | 1 | 115 | 3513 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2660 | 43607715201 | 004 | 2 |  | 1 | 101 | 24300 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2660 | 43607715201 | 019 | 2 |  | 1 | 503 | 10835.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2660 | 43607715201 | 062 | 2 |  | 1 | 005 | 120000 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2675 | 43611415201 | 008 | 2 |  | 1 | 107 | 2312 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2675 | 43611415201 | 012 | 2 |  | 1 | 012 | 10527.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2702 | 43616515201 | 009 | 2 | 850 | 1 | 001 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2702 | 43616515201 | 019 | 2 | 850 | 1 | 001 | 24505.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2706 | 42879615201 | 007 | 2 | 850 | 1 | 115 | 49910.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 007 | 2 | 850 | 2 | 115 | 8981.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 007 | 2 | 850 | 3 | 115 | 10616.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 007 | 2 | 850 | 4 | 115 | 2044.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 007 | 2 | 850 | 5 | 115 | 5236.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 007 | 2 | 850 | 6 | 923 | 1139.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 020 | 2 |  | 1 | 005 | 10129.15 | 10129.15 | 5 |  | N | 2 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2706 | 42879615201 | 020 | 2 |  | 2 | 005 | 5606.31 | 5606.31 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2706 | 42879615201 | 020 | 2 |  | 3 | 106 | 3644.44 | 3644.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2706 | 42879615201 | 022 | 2 | 850 | 1 | 923 | 8929.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2706 | 42879615201 | 040 | 2 |  | 1 | 860 | 475000 | 475000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | T2709 | 21284435201 | 001 | 2 |  | 1 | 101 | 42749.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2722 | 43761515201 | 007 | 2 | 850 | 1 | 012 | 25000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2722 | 43761515201 | 007 | 2 | 850 | 2 | 010 | 23751.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2726 | 43583715201 | 001 | 2 |  | 1 | 105 | 15546.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 002 | 2 |  | 1 | 105 | 22177.27 | 1482.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 003 | 2 |  | 1 | 105 | 555.5 | 555.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 004 | 2 |  | 1 | 105 | 6875.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 012 | 2 |  | 1 | 105 | 25316.91 | 25316.91 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2726 | 43583715201 | 019 | 2 |  | 1 | 923 | 9602.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2731 | 43617915201 | 008 | 2 | 850 | 1 | 103 | 10424.38 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2731 | 43617915201 | 008 | 2 | 850 | 2 | 128 | 5261.38 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2731 | 43617915201 | 008 | 2 | 850 | 3 | 128 | 176.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2731 | 43617915201 | 008 | 2 | 850 | 4 | 003 | 2434.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2731 | 43617915201 | 008 | 2 | 850 | 5 | 003 | 13433.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 004 | 2 | 850 | 1 | 001 | 70.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2737 | 43433315201 | 004 | 2 | 850 | 2 | 003 | 37400.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 004 | 2 | 850 | 3 | 003 | 1714.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 004 | 2 | 850 | 4 | 105 | 1971.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2737 | 43433315201 | 004 | 2 | 850 | 5 | 003 | 5751.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 004 | 2 | 850 | 6 | 023 | 1140.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 018 | 2 | 850 | 1 | 112 | 3916.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2737 | 43433315201 | 018 | 2 | 850 | 2 | 112 | 41339.29 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2737 | 43433315201 | 018 | 2 | 850 | 3 | 101 | 553.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2737 | 43433315201 | 018 | 2 | 850 | 4 | 108 | 1985.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2737 | 43433315201 | 018 | 2 | 850 | 5 | 003 | 4579.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 | 018 | 2 | 850 | 6 | 101 | 1480.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2748 | 43911615201 | 009 | 2 | 850 | 1 | 850 | 30000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3O87 | 42820825201 | 009 | 2 |  | 1 | 012 | 24302.18 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3O87 | 42820825201 | 009 | 2 |  | 2 | 101 | 0 | 1451.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 | 017 | 2 |  | 1 | 919 | 5319.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 | 026 | 2 |  | 1 | 503 | 2612 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O87 | 42820825201 | 027 | 2 |  | 1 | 115 | 26599.01 | 5124.7 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 | 032 | 2 |  | 1 | 015 | 192230 | 0 | 5 |  | N | 11 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | E3Q54 | 22253925201 | 006 | 2 |  | 1 | 305 | -75509.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | E3R03 | 41343525201 | 013 | 2 |  | 1 | 005 | 12921.46 | 12921.46 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 016 | 2 |  | 1 | 922 | 9486.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 024 | 2 |  | 1 | 503 | -7302.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 026 | 2 |  | 1 | 112 | 15065.19 | 1827.1 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | E3R03 | 41343525201 | 032 | 2 |  | 1 | 503 | 1211.98 | 1211.98 | 5 |  | N | 1 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 033 | 2 |  | 1 | 503 | 7926.77 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 034 | 2 |  | 1 | 503 | 4936.5 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 035 | 2 |  | 1 | 503 | 34513.57 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 | 036 | 2 |  | 1 | 503 | 8003.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 | 013 | 2 |  | 1 | 503 | 158901.87 | 0 | 0 |  | E | 96 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 003 | 2 |  | 1 | 503 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 1 | 503 | 69177.42 | 69177.42 | 0 |  | N | 55 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 2 | 503 | 4011.87 | 4011.87 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 3 | 503 | 0 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 4 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 5 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 6 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R70 | 43814115201 | 007 | 2 |  | 7 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 | 009 | 2 |  | 1 | 113 | -5016 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3R72 | 43255415201 | 010 | 2 |  | 1 | 012 | 47176 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R72 | 43255415201 | 012 | 2 |  | 1 | 503 | 14454.7 | 4665.88 | 1 |  | N | 3 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 | 013 | 2 |  | 1 | 503 | 66724.26 | 0 | 2 |  | N | 13 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 002 | 2 |  | 1 | 101 | 13944 | 1708.14 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3R75 | 40731075201 | 003 | 2 |  | 1 | 503 | 7592.35 | 7592.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 013 | 2 |  | 1 | 503 | 70580.44 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R75 | 40731075201 | 015 | 2 |  | 1 | 503 | 24809.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R84 | 43736715201 | 001 | 2 |  | 1 | 106 | 103424.95 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3S03 | 43775215201 | 013 | 2 |  | 1 | 012 | 42363.01 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3287 | 22044245201 | 003 | 2 |  | 1 | 503 | -99598.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3287 | 22044245201 | 026 | 2 |  | 1 | 503 | 19547.67 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3287 | 22044245201 | 029 | 2 |  | 1 | 010 | 56999.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 | 037 | 2 |  | 1 | 007 | 68640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3287 | 22044245201 | 050 | 2 |  | 1 | 007 | 29180.45 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3287 | 22044245201 | 057 | 2 |  | 1 | 919 | 17651.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3287 | 22044245201 | 060 | 2 |  | 1 | 503 | -34069.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 002 | 2 |  | 1 | 503 | 201600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 006 | 2 |  | 1 | 919 | 1817.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 008 | 2 |  | 1 | 010 | 907.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3578 | 41413235201 | 010 | 2 |  | 1 | 503 | 4908.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 015 | 2 |  | 1 | 007 | -9278.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3578 | 41413235201 | 023 | 2 |  | 1 | 503 | 492639.97 | 492639.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 025 | 2 |  | 1 | 107 | 30465 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3578 | 41413235201 | 036 | 2 |  | 1 | 503 | 76942.07 | 76942.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 038 | 2 |  | 1 | 503 | 9220.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 040 | 2 |  | 1 | 922 | 26709.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 045 | 2 |  | 1 | 503 | 821 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 047 | 2 |  | 1 | 503 | 58347.35 | 58347.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 069 | 2 |  | 1 | 503 | 16620.87 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 071 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | -180 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 | 074 | 2 |  | 1 | 503 | 80447.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3582 | 43483715201 | 002 | 2 |  | 1 | 113 | 24785.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3582 | 43483715201 | 015 | 2 |  | 1 | 113 | 3331.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3582 | 43483715201 | 022 | 2 |  | 1 | 919 | 2618.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3582 | 43483715201 | 025 | 2 |  | 1 | 010 | 124598.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3585 | 43228515201 | 002 | 2 |  | 1 | 503 | -1394.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3619 | 43390215201 | 008 | 2 |  | 1 | 001 | 49049.79 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3627 | 43228915201 | 003 | 2 |  | 1 | 001 | -49220.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3627 | 43228915201 | 020 | 2 |  | 1 | 922 | 9515.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3627 | 43228915201 | 025 | 2 |  | 1 | 001 | 89331.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3642 | 43274025201 | 008 | 2 |  | 1 | 503 | 55550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3642 | 43274025201 | 026 | 2 |  | 1 | 922 | 78411 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3642 | 43274025201 | 032 | 2 |  | 1 | 503 | 5900.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3648 | 43580215201 | 007 | 2 |  | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3659 | 43728425201 | 001 | 2 |  | 1 | 105 | 11694.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3659 | 43728425201 | 002 | 2 |  | 1 | 101 | 8580 | 3189 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 1 | 112 | 18996.57 | 6599.77 | 1 |  | N | 6 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 2 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3659 | 43728425201 | 016 | 2 |  | 3 | 112 | 631.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 4 | 105 | 1561.02 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 5 | 112 | 7217.26 | 1463.08 | 1 |  | N | 3 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 6 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 7 | 503 | 806.85 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3659 | 43728425201 | 016 | 2 |  | 8 | 112 | 4547.23 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3659 | 43728425201 | 016 | 2 |  | 9 | 503 | 1752.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3659 | 43728425201 | 016 | 2 |  | 10 | 503 | 16090.1 | 16090.1 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3663 | 43188345201 | 003 | 2 |  | 1 | 503 | 207.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3663 | 43188345201 | 012 | 2 |  | 1 | 012 | 11597.01 | 2420.63 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3668 | 43580015201 | 004 | 2 |  | 1 | 503 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3724 | 43972215201 | 020 | 2 |  | 1 | 927 | -39686.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3739 | 44173715201 | 003 | 2 |  | 1 | 128 | 7093.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3747 | 44173515201 | 002 | 2 |  | 1 | 101 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3747 | 44173515201 | 006 | 2 |  | 1 | 007 | 47827.08 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4M90 | 41242035201 | 026 | 2 |  | 1 | 503 | 42102.5 | 42102.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4M90 | 41242035201 | 029 | 2 |  | 1 | 003 | 196574 | 196574 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 029 | 2 |  | 2 | 003 | 58591.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 029 | 2 |  | 3 | 503 | 180774.66 | 180774.66 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4M90 | 41242035201 | 029 | 2 |  | 4 | 003 | 97634.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 032 | 2 |  | 1 | 003 | -40926.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 032 | 2 |  | 2 | 300 | 0 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
04 | E4M90 | 41242035201 | 032 | 2 |  | 3 | 003 | 583830 | 415686.96 | 0 |  | N | 160 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 044 | 2 |  | 1 | 003 | 1221250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 | 044 | 2 |  | 2 | 009 | 15750 | 15750 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | E4M90 | 41242035201 | 044 | 2 |  | 3 | 105 | -127301.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4M90 | 41242035201 | 057 | 2 |  | 1 | 004 | 42000 | 10183.25 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4M90 | 41242035201 | 057 | 2 |  | 2 | 004 | -12000.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4M90 | 41242035201 | 059 | 2 |  | 1 | 118 | 67156.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4M90 | 41242035201 | 059 | 2 |  | 2 | 123 | 4272.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | E4M90 | 41242035201 | 059 | 2 |  | 3 | 004 | 4229.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4M90 | 41242035201 | 076 | 2 |  | 1 | 305 | -10516.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4M90 | 41242035201 | 082 | 2 |  | 1 | 350 | 19800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4M90 | 41242035201 | 082 | 2 |  | 2 | 305 | -36172.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | E4M90 | 41242035201 | 082 | 2 |  | 3 | 503 | -25500.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4M90 | 41242035201 | 082 | 2 |  | 4 | 503 | -177752.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4M90 | 41242035201 | 082 | 2 |  | 5 | 004 | 204000 | 8714.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4M90 | 41242035201 | 082 | 2 |  | 6 | 116 | -70160.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | E4M90 | 41242035201 | 082 | 2 |  | 7 | 012 | 1935.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 | 088 | 2 |  | 1 | 107 | 81075.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4M90 | 41242035201 | 090 | 2 |  | 1 | 917 | 59375.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4M90 | 41242035201 | 099 | 2 |  | 1 | 019 | 43372.59 | 43372.59 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
04 | E4M90 | 41242035201 | 124 | 2 |  | 1 | 919 | 242202.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4M90 | 41242035201 | 136 | 2 |  | 1 | 919 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4M90 | 41242035201 | 136 | 2 |  | 2 | 208 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
04 | E4M90 | 41242035201 | 136 | 2 |  | 3 | 130 | 0 | 0 | 3 |  | N | 9 | Avoidable, CEI Consultant | Indecision/Delayed Response | Plan Modifications | 2
04 | E4M90 | 41242035201 | 136 | 2 |  | 4 | 130 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | E4N82 | 22777515201 | 023 | 2 |  | 1 | 116 | 90064.65 | 11550 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | E4N82 | 22777515201 | 027 | 2 |  | 1 | 008 | 49760.94 | 49760.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4N82 | 22777515201 | 039 | 2 |  | 1 | 008 | 69424.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 1 | 106 | 13193.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 2 | 007 | 13700.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 3 | 503 | 6725.87 | 3959.42 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 4 | 503 | 3499.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 5 | 503 | 9259.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 048 | 2 | 850 | 6 | 503 | 4885.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 057 | 2 |  | 1 | 503 | 40631.41 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 062 | 2 |  | 1 | 503 | 161008.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 078 | 2 |  | 1 | 919 | 49745.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 092 | 2 |  | 1 | 106 | 55770.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 | 103 | 2 |  | 1 | 015 | 269840.95 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 | 111 | 2 |  | 1 | 015 | 197239.08 | 132525.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 | 111 | 2 |  | 2 | 503 | 225994.99 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 111 | 2 |  | 3 | 022 | 81051.53 | 81051.53 | 0 |  | C | 170 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 111 | 2 |  | 4 | 024 | 19147.5 | 19147.5 | 5 |  | C | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 | 137 | 2 |  | 1 | 024 | 0 | 0 | 5 |  | N | 51 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 021 | 2 |  | 1 | 923 | 14124.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 024 | 2 |  | 1 | 300 | -308042.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
04 | E4T09 | 42264125201 | 025 | 2 |  | 1 | 503 | -19939.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 030 | 2 |  | 1 | 009 | 60456.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | E4T09 | 42264125201 | 030 | 2 |  | 2 | 012 | 4087.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T09 | 42264125201 | 030 | 2 |  | 3 | 101 | 15677.02 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 1 | 115 | 14356.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 2 | 004 | 1490.85 | 1490.85 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 3 | 004 | 1021.13 | 1021.13 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 4 | 004 | 9837.57 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 5 | 003 | 2436.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 6 | 007 | 8011.4 | 8011.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 7 | 503 | 501.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 8 | 503 | 4531.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 9 | 010 | 2610.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 10 | 107 | 13434.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 11 | 115 | 7106.39 | 4554.62 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 12 | 115 | 6218.81 | 6218.81 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 13 | 105 | 1136.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 14 | 107 | 7141.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 15 | 101 | 1069.86 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 16 | 105 | 2433.99 | 2433.99 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 17 | 503 | 4968 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 18 | 503 | 4603.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 19 | 101 | 1069.86 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 20 | 004 | 2433.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 21 | 503 | 4531.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 25 | 003 | 2436.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 22 | 503 | 501.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 23 | 503 | 1300.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 24 | 007 | 8011.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 26 | 004 | 1490.85 | 1490.85 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 031 | 2 | 850 | 27 | 004 | 1021.13 | 1021.13 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 039 | 2 |  | 1 | 107 | 43495.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 040 | 2 |  | 1 | 926 | 4896.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 1 | 107 | 3049.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 2 | 107 | 8098 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 3 | 107 | 11581.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 4 | 126 | 20743.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 5 | 126 | 88894 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 6 | 003 | 2160.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T09 | 42264125201 | 042 | 2 |  | 7 | 118 | 9464 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 8 | 115 | 8074 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 042 | 2 |  | 9 | 015 | 11550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4T09 | 42264125201 | 051 | 2 |  | 1 | 004 | 67663.62 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T09 | 42264125201 | 051 | 2 |  | 2 | 107 | -10115.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 051 | 2 |  | 3 | 107 | -57552 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 052 | 2 |  | 1 | 113 | 108281.05 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 | 052 | 2 |  | 2 | 126 | 134252.73 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | E4T09 | 42264125201 | 052 | 2 |  | 3 | 126 | 117516.82 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | E4T46 | 43388815201 | 006 | 2 |  | 1 | 923 | 12401.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
04 | E4T46 | 43388815201 | 017 | 2 |  | 1 | 106 | 95163.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T56 | 43578125201 | 021 | 2 |  | 1 | 024 | 11580.46 | 11580.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T61 | 43783415201 | 011 | 2 |  | 1 | 305 | -73852.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T61 | 43783415201 | 012 | 2 |  | 1 | 004 | 109025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T61 | 43783415201 | 015 | 2 |  | 1 | 118 | 11902.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T84 | 43389615201 | 005 | 2 |  | 1 | 107 | 0 | 0 | 0 |  | N | -15 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T85 | 43984315201 | 010 | 2 |  | 1 | 926 | 1671.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T86 | 44061215201 | 004 | 2 |  | 1 | 004 | 2937.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4T86 | 44061215201 | 004 | 2 |  | 2 | 105 | 8927.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T86 | 44061215201 | 004 | 2 |  | 3 | 106 | 2463.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T88 | 43986015201 | 001 | 2 |  | 1 | 119 | -11094.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | E4T88 | 43986015201 | 001 | 2 |  | 2 | 107 | -11700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T92 | 44140915201 | 002 | 2 |  | 1 | 926 | 11180.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4U43 | 44332215201 | 008 | 2 |  | 1 | 107 | 7772 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4U43 | 44332215201 | 008 | 2 |  | 2 | 860 | 8500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | E4U43 | 44332215201 | 008 | 2 |  | 3 | 107 | -16272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4U78 | 4476871H201 | 001 | 2 |  | 1 | 503 | 9343116 | 0 | 0 |  | N | 117 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 002 | 2 | 850 | 1 | 503 | 26500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 002 | 2 | 850 | 2 | 004 | -1035.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U78 | 4476871H201 | 002 | 2 | 850 | 3 | 004 | 3426.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U78 | 4476871H201 | 002 | 2 | 850 | 4 | 004 | 6432.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U78 | 4476871H201 | 002 | 2 | 850 | 5 | 503 | 7634.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 004 | 2 |  | 1 | 503 | 2686279.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 008 | 2 |  | 1 | 503 | 3398971.47 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 012 | 2 |  | 1 | 503 | 300000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U78 | 4476871H201 | 019 | 2 |  | 1 | 503 | -28218.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4461 | 42793715201 | 008 | 2 |  | 1 | 919 | 7079.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4461 | 42793715201 | 035 | 2 | 850 | 1 | 007 | 5216.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 2 | 003 | 1145.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 3 | 003 | 1221.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 4 | 003 | 3260.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 5 | 108 | 15447.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 6 | 108 | 16783.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 7 | 115 | 483.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 8 | 108 | 3205.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 9 | 003 | 2067.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 10 | 003 | 2186.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 11 | 023 | 6538.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 12 | 003 | 2411.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 13 | 003 | 3058.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 14 | 003 | 2349.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 15 | 101 | 3484.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 16 | 123 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 17 | 001 | 17087.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 18 | 023 | 17657.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 19 | 101 | 3936.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 20 | 023 | 2172.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 21 | 115 | 3937.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 22 | 105 | 1612.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 23 | 003 | 1895.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 | 035 | 2 | 850 | 24 | 101 | 3910.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 25 | 023 | -90 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 035 | 2 | 850 | 26 | 023 | -2172.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 036 | 2 |  | 1 | 106 | 7501.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4461 | 42793715201 | 039 | 2 |  | 1 | 012 | 65130.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 044 | 2 |  | 1 | 007 | 46192.27 | 46192.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 | 049 | 2 |  | 1 | 106 | 13058.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4461 | 42793715201 | 050 | 2 |  | 1 | 012 | 597998.67 | 0 | 0 |  | N | 100 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 061 | 2 |  | 1 | 923 | 14701.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4461 | 42793715201 | 065 | 2 |  | 1 | 101 | 36450.19 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4461 | 42793715201 | 068 | 2 |  | 1 | 012 | 73262.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4462 | 43232315203 | 010 | 2 |  | 1 | 007 | -62.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315203 | 011 | 2 |  | 1 | 007 | 21979.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315203 | 013 | 2 | 850 | 1 | 115 | 8256.46 | 8256.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 013 | 2 | 850 | 2 | 001 | 21595.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 013 | 2 | 850 | 3 | 018 | 19651.16 | 19651.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | T4462 | 43232315203 | 013 | 2 | 850 | 4 | 003 | 1905.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315203 | 018 | 2 |  | 1 | 003 | 30996.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315203 | 019 | 2 | 850 | 1 | 115 | 34251.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 019 | 2 | 850 | 2 | 101 | 17157.75 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4462 | 43232315203 | 025 | 2 | 850 | 1 | 105 | 10952.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4462 | 43232315203 | 025 | 2 | 850 | 2 | 503 | 1757.47 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 025 | 2 | 850 | 3 | 101 | 11376.13 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4462 | 43232315203 | 025 | 2 | 850 | 4 | 001 | 13861.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 025 | 2 | 850 | 5 | 001 | 4805.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 025 | 2 | 850 | 6 | 105 | 5537.48 | 5537.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4462 | 43232315203 | 025 | 2 | 850 | 7 | 001 | 3117.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 026 | 2 |  | 1 | 101 | 75718.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4462 | 43232315203 | 027 | 2 |  | 1 | 007 | -91477.2 | 0 | 0 |  | N | 42 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315203 | 030 | 2 |  | 1 | 503 | -23615.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 034 | 2 |  | 1 | 105 | 204049.86 | 204049.86 | 5 |  | C | 120 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4462 | 43232315203 | 039 | 2 |  | 1 | 003 | 56934.04 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315203 | 040 | 2 | 850 | 1 | 001 | 3121.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 040 | 2 | 850 | 2 | 115 | 21795.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 040 | 2 | 850 | 3 | 012 | 4629.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4462 | 43232315203 | 040 | 2 | 850 | 4 | 003 | 6760.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315203 | 040 | 2 | 850 | 5 | 115 | 10454.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 040 | 2 | 850 | 6 | 503 | 1296.24 | 1296.24 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 040 | 2 | 850 | 7 | 503 | 3351.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 042 | 2 |  | 1 | 115 | 15513.54 | 15513.54 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 062 | 2 |  | 1 | 923 | 44025.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 063 | 2 | 850 | 1 | 503 | 31459.27 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 063 | 2 | 850 | 2 | 503 | 8316.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 065 | 2 |  | 1 | 503 | 49204.38 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 | 066 | 2 |  | 1 | 115 | 86874.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315203 | 070 | 2 |  | 1 | 105 | 838634.71 | 0 | 0 |  | N | 340 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4473 | 42751615201 | 007 | 2 |  | 1 | 004 | 144864 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4473 | 42751615201 | 014 | 2 |  | 1 | 305 | -324121 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4473 | 42751615201 | 027 | 2 |  | 1 | 101 | 2801.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4473 | 42751615201 | 030 | 2 |  | 1 | 923 | 10358.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4479 | 43059025201 | 021 | 2 |  | 1 | 001 | 7371.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4483 | 44008115201 | 024 | 2 |  | 1 | 503 | 22625.47 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4485 | 43634115201 | 013 | 2 |  | 1 | 108 | 244634.8 | 244634.8 | 1 |  | N | 43 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4489 | 43770115201 | 016 | 2 |  | 1 | 923 | 136401.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4489 | 43770115201 | 024 | 2 |  | 1 | 105 | 86742.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4491 | 43234815201 | 005 | 2 |  | 1 | 007 | 21683.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4491 | 43234815201 | 012 | 2 |  | 1 | 923 | 15850.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4491 | 43234815201 | 021 | 2 |  | 1 | 106 | 29233.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 022 | 2 |  | 1 | 012 | 105884.74 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4491 | 43234815201 | 023 | 2 | 850 | 1 | 001 | 6105.76 | 2611.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 | 023 | 2 | 850 | 2 | 122 | 1593.86 | 1593.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4491 | 43234815201 | 023 | 2 | 850 | 3 | 106 | 5142.7 | 5142.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 023 | 2 | 850 | 4 | 022 | 31506.88 | 31506.88 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 | 029 | 2 |  | 1 | 101 | 7173.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4496 | 43288335201 | 005 | 2 |  | 1 | 126 | 165747.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4496 | 43288335201 | 006 | 2 |  | 1 | 126 | 22386.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4496 | 43288335201 | 006 | 2 |  | 4 | 101 | 8956.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4496 | 43288335201 | 007 | 2 | 850 | 1 | 108 | 966.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4496 | 43288335201 | 007 | 2 | 850 | 2 | 001 | 6130.19 | 1088.95 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335201 | 019 | 2 |  | 1 | 105 | 100000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 | 026 | 2 |  | 1 | 923 | 1894.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 | 031 | 2 |  | 1 | 128 | 30738.63 | 30738.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4498 | 43689315201 | 009 | 2 | 850 | 1 | 001 | 7891.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 | 009 | 2 | 850 | 2 | 005 | 10121.73 | 10121.73 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 009 | 2 | 850 | 3 | 024 | 715.5 | 715.5 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 009 | 2 | 850 | 4 | 005 | 15642.8 | 15642.8 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 | 011 | 2 |  | 1 | 126 | 53883.53 | 44187.03 | 1 |  | N | 5 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4499 | 44055425201 | 016 | 2 |  | 1 | 112 | 181437.24 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425201 | 017 | 2 |  | 1 | 923 | 241269.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425201 | 020 | 2 |  | 1 | 001 | 2521590.46 | 1067355.75 | 0 |  | C | 140 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4499 | 44055425201 | 022 | 2 | 850 | 1 | 112 | 26494.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425201 | 036 | 2 |  | 1 | 926 | 9141.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 017 | 2 |  | 1 | 923 | 1442.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 024 | 2 |  | 1 | 126 | 27123.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4501 | 43468615201 | 024 | 2 |  | 2 | 007 | -89014.06 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4501 | 43468615201 | 024 | 2 |  | 3 | 003 | 5104.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4501 | 43468615201 | 024 | 2 |  | 4 | 112 | 6574.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 024 | 2 |  | 6 | 118 | 134220.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4502 | 43630315202 | 016 | 2 |  | 1 | 700 | 16277.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
04 | T4503 | 43611115201 | 017 | 2 |  | 1 | 105 | 59638.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4503 | 43611115201 | 019 | 2 | 850 | 1 | 108 | 20932.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 | 019 | 2 | 850 | 2 | 105 | 1079.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4503 | 43611115201 | 023 | 2 |  | 1 | 101 | 5865.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 | 003 | 2 |  | 1 | 101 | 164984 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 | 032 | 2 |  | 1 | 023 | 1430 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 | 032 | 2 |  | 2 | 023 | 1485 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 | 032 | 2 |  | 3 | 023 | 2230.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 | 032 | 2 |  | 4 | 023 | 50017.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4508 | 43773115201 | 015 | 2 |  | 1 | 101 | 7102.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4508 | 43773115201 | 020 | 2 |  | 1 | 923 | 10373.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4508 | 43773115201 | 021 | 2 |  | 1 | 004 | 133624.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4510 | 43234415201 | 010 | 2 |  | 1 | 007 | 3401.44 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4510 | 43234415201 | 018 | 2 |  | 1 | 004 | 44709.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4510 | 43234415201 | 021 | 2 |  | 1 | 001 | -99549 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4510 | 43234415201 | 021 | 2 |  | 2 | 001 | 53225.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4510 | 43234415201 | 024 | 2 | 850 | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4510 | 43234415201 | 024 | 2 | 850 | 3 | 115 | 3967.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4510 | 43234415201 | 024 | 2 | 850 | 4 | 001 | 121 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4510 | 43234415201 | 024 | 2 | 850 | 5 | 012 | 1453.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4510 | 43234415201 | 024 | 2 | 850 | 6 | 112 | 6506.48 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4510 | 43234415201 | 024 | 2 | 850 | 7 | 106 | 5590.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4510 | 43234415201 | 024 | 2 | 850 | 8 | 108 | 5105.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4510 | 43234415201 | 025 | 2 |  | 1 | 012 | 837.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4510 | 43234415201 | 031 | 2 |  | 1 | 115 | 6486.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4510 | 43234415201 | 036 | 2 |  | 1 | 128 | 947.19 | 947.19 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4524 | 43770715201 | 021 | 2 |  | 1 | 128 | 108550.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4524 | 43770715201 | 021 | 2 |  | 2 | 105 | 49602.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4526 | 43689425201 | 012 | 2 |  | 2 | 001 | -7522.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4526 | 43689425201 | 012 | 2 |  | 3 | 001 | -942 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4529 | 44271915201 | 006 | 2 |  | 1 | 118 | 3239.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4531 | 44313515201 | 010 | 2 |  | 1 | 926 | 1538.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4540 | 43834515201 | 001 | 2 |  | 1 | 101 | 16665 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4545 | 43984415201 | 008 | 2 |  | 1 | 126 | 6644.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4545 | 43984415201 | 010 | 2 |  | 1 | 113 | 164208.86 | 10016.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4545 | 43984415201 | 012 | 2 |  | 1 | 015 | 9771.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4545 | 43984415201 | 015 | 2 |  | 1 | 113 | 75714.16 | 70217.26 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4545 | 43984415201 | 019 | 2 |  | 1 | 101 | 556.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4545 | 43984415201 | 020 | 2 |  | 1 | 113 | 110024.35 | 100000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4550 | 43689715201 | 014 | 2 |  | 1 | 004 | 13122.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4550 | 43689715201 | 014 | 2 |  | 2 | 003 | 13084 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A0 | 44327015201 | 007 | 2 |  | 1 | 118 | -12478.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5W26 | 24271525201 | 056 | 2 |  | 1 | 917 | 202244.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5W26 | 24271525201 | 087 | 2 |  | 1 | 919 | 326628.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5W26 | 24271525201 | 101 | 2 |  | 1 | 004 | 101692.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W26 | 24271525201 | 104 | 2 |  | 1 | 007 | 47700.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5W26 | 24271525201 | 118 | 2 |  | 1 | 108 | 575563.41 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5W26 | 24271525201 | 138 | 2 |  | 1 | 503 | 42308.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W26 | 24271525201 | 138 | 2 |  | 2 | 923 | 186677 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5W26 | 24271525201 | 138 | 2 |  | 3 | 004 | 4124.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5W26 | 24271525201 | 138 | 2 |  | 4 | 850 | 0 | 0 | 0 |  | N | 167 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | E5Y62 | 23831925201 | 004 | 2 |  | 1 | 919 | 7917.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
05 | E5Y62 | 23831925201 | 011 | 2 |  | 1 | 004 | 12868.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Y62 | 23831925201 | 012 | 2 |  | 1 | 106 | 11046.34 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 012 | 2 |  | 2 | 106 | 73812 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Y62 | 23831925201 | 012 | 2 |  | 3 | 503 | 14090.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y62 | 23831925201 | 033 | 2 |  | 1 | 923 | 13180.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Y62 | 23831925201 | 051 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 102 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 | 010 | 2 |  | 1 | 112 | 0 | 0 | 1 |  | N | 64 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z32 | 43927515201 | 028 | 2 |  | 1 | 923 | 42303.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z46 | 44116815201 | 010 | 2 |  | 1 | 923 | 74620 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z46 | 44116815201 | 034 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 245 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 1 | 112 | 27788.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 2 | 503 | 6502.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 3 | 503 | 12252.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 001 | 2 | 850 | 4 | 010 | 3456.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z64 | 44121015201 | 006 | 2 |  | 1 | 503 | 6240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 006 | 2 |  | 2 | 101 | 6978.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 006 | 2 |  | 3 | 503 | 15151.43 | 3472.19 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 008 | 2 |  | 1 | 923 | 3539.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z64 | 44121015201 | 013 | 2 |  | 1 | 007 | 120628.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 1 | 010 | 2240.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 2 | 105 | 4403.6 | 4403.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 3 | 115 | 1473.63 | 1473.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 017 | 2 | 850 | 4 | 112 | 6509.04 | 5551.83 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 021 | 2 |  | 1 | 126 | -1568.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 021 | 2 |  | 2 | 122 | 12701.95 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Z64 | 44121015201 | 025 | 2 |  | 1 | 112 | 0 | 0 | 1 |  | N | 16 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z68 | 44096915201 | 001 | 2 |  | 1 | 923 | 4114.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z77 | 43912115201 | 015 | 2 |  | 1 | 118 | -7404 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Z85 | 43923615201 | 008 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 011 | 2 |  | 1 | 107 | 19000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 016 | 2 |  | 1 | 115 | -37015.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 017 | 2 |  | 1 | 105 | 121734.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 019 | 2 |  | 1 | 107 | 184263.43 | 0 | 1 |  | N | 44 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 025 | 2 |  | 1 | 107 | 390710.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 | 025 | 2 |  | 2 | 106 | 0 | 0 | 5 |  | N | 80 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 026 | 2 |  | 1 | 305 | -178686.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 027 | 2 |  | 1 | 917 | 79449.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 030 | 2 |  | 1 | 919 | 249920.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 041 | 2 |  | 1 | 112 | 52090.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 046 | 2 |  | 1 | 105 | 24128.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 058 | 2 | 850 | 1 | 015 | 16276.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 058 | 2 | 850 | 2 | 015 | 16276.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 066 | 2 |  | 1 | 112 | 605227.55 | 0 | 0 |  | N | 108 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 070 | 2 |  | 1 | 112 | 262387.98 | 57126.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 071 | 2 |  | 1 | 106 | 189994.45 | 70225.35 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 073 | 2 | 850 | 1 | 015 | 2819.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 073 | 2 | 850 | 2 | 015 | 8774.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 | 076 | 2 |  | 1 | 106 | 92410.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 077 | 2 |  | 1 | 112 | 108283.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 080 | 2 |  | 1 | 923 | 27671.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 | 083 | 2 |  | 1 | 101 | 55475 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 1 | 106 | 2245.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 2 | 106 | 6721.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 3 | 106 | 8188.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 085 | 2 |  | 4 | 106 | 3088.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 | 086 | 2 |  | 1 | 105 | 29353.67 | 27458.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5530 | 23968215201 | 088 | 2 |  | 1 | 001 | 86428.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 | 092 | 2 |  | 1 | 001 | 487803.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5589 | 23827525201 | 006 | 2 |  | 1 | 101 | 68760.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5589 | 23827525201 | 008 | 2 |  | 1 | 101 | 68635.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5589 | 23827525201 | 008 | 2 |  | 2 | 107 | 71664.65 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 008 | 2 |  | 3 | 115 | 916.05 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 1 | 003 | 1956.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 011 | 2 | 850 | 2 | 107 | 9533.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 3 | 024 | 1882.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 4 | 107 | 1283.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 5 | 115 | 1138 | 1138 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 6 | 024 | 378.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 7 | 115 | 3394.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 8 | 003 | -1956.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 011 | 2 | 850 | 9 | 503 | 4230.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 011 | 2 | 850 | 10 | 003 | 5011.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 011 | 2 | 850 | 11 | 106 | 1777.6 | 1777.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 12 | 024 | 1216.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 13 | 107 | 7348.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 14 | 107 | -7348.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 15 | 115 | 2640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 17 | 503 | 7864.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 011 | 2 | 850 | 18 | 115 | 2263.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 011 | 2 | 850 | 16 | 107 | 7384.14 | 2430.28 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 022 | 2 |  | 1 | 105 | 6019.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5589 | 23827525201 | 022 | 2 |  | 2 | 115 | 22200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 022 | 2 |  | 3 | 101 | 4054 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5589 | 23827525201 | 022 | 2 |  | 4 | 115 | 69047.47 | 56335.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 022 | 2 |  | 5 | 107 | 2102.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 1 | 024 | 1129.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 2 | 107 | 4778.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 3 | 003 | 3701.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 029 | 2 | 850 | 4 | 107 | 4778.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 5 | 107 | 4657.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 6 | 003 | 15027.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 029 | 2 | 850 | 7 | 107 | 2389.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 029 | 2 | 850 | 8 | 024 | 13538.5 | 13538.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 033 | 2 |  | 1 | 113 | -150862.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 033 | 2 |  | 2 | 107 | 43320.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 033 | 2 |  | 3 | 115 | 89462.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 033 | 2 |  | 4 | 126 | 1234.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5589 | 23827525201 | 033 | 2 |  | 5 | 105 | -16653 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 1 | 107 | 7321.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 2 | 503 | 12777.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 040 | 2 | 850 | 3 | 107 | 5030.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 4 | 105 | 3280 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 5 | 115 | 2263.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 6 | 107 | 269.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 7 | 004 | 2363.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5589 | 23827525201 | 040 | 2 | 850 | 8 | 115 | 3770.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 9 | 115 | -2263.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 10 | 115 | 5834.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 11 | 107 | 1125.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 040 | 2 | 850 | 12 | 115 | 8227.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 044 | 2 |  | 1 | 003 | 14820.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 044 | 2 |  | 2 | 101 | 22469 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5589 | 23827525201 | 044 | 2 |  | 3 | 503 | 189121.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 045 | 2 |  | 1 | 503 | 61259.68 | 61259.69 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 045 | 2 |  | 2 | 009 | -55638.1 | 2420 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
05 | T5589 | 23827525201 | 045 | 2 |  | 3 | 126 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | T5589 | 23827525201 | 054 | 2 |  | 1 | 923 | 34316.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | T5589 | 23827525201 | 058 | 2 |  | 1 | 128 | 99348.49 | 99348.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5589 | 23827525201 | 067 | 2 | 850 | 1 | 004 | 2363.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5589 | 23827525201 | 067 | 2 | 850 | 2 | 503 | 1457.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 067 | 2 | 850 | 3 | 024 | 365.36 | 365.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 067 | 2 | 850 | 4 | 107 | 2975.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 067 | 2 | 850 | 5 | 115 | 5053.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 067 | 2 | 850 | 6 | 503 | 1600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 067 | 2 | 850 | 7 | 503 | 695.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 067 | 2 | 850 | 8 | 503 | 1833 | 2851.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 067 | 2 | 850 | 9 | 105 | 8434.62 | 8532.8 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5589 | 23827525201 | 070 | 2 | 850 | 1 | 115 | 4435.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 070 | 2 | 850 | 2 | 115 | 10148.45 | 1532.48 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 070 | 2 | 850 | 3 | 126 | 2612.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5589 | 23827525201 | 070 | 2 | 850 | 4 | 503 | 4376.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 070 | 2 | 850 | 5 | 503 | 3426.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 071 | 2 |  | 1 | 115 | 19182.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 | 071 | 2 |  | 2 | 126 | 39054.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | T5589 | 23827525201 | 071 | 2 |  | 3 | 003 | -45000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827525201 | 080 | 2 | 850 | 1 | 503 | 1641.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 080 | 2 | 850 | 2 | 503 | 3200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 080 | 2 | 850 | 3 | 503 | 11481.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5589 | 23827525201 | 098 | 2 |  | 1 | 450 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
05 | T5590 | 42690535201 | 013 | 2 |  | 1 | 003 | 112019.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5590 | 42690535201 | 014 | 2 |  | 1 | 923 | 219530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5590 | 42690535201 | 015 | 2 |  | 1 | 106 | 3734 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5590 | 42690535201 | 016 | 2 |  | 1 | 105 | 111390.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 017 | 2 |  | 1 | 112 | 103337.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5590 | 42690535201 | 031 | 2 | 850 | 1 | 004 | 25169.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5590 | 42690535201 | 031 | 2 | 850 | 2 | 105 | 2476.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 031 | 2 | 850 | 3 | 503 | 11200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5590 | 42690535201 | 031 | 2 | 850 | 4 | 105 | 35359.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 | 034 | 2 |  | 1 | 115 | 203086.04 | 3698.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 | 041 | 2 |  | 1 | 004 | 28277.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5592 | 43440715201 | 041 | 2 |  | 2 | 118 | 10783.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5592 | 43440715201 | 041 | 2 |  | 3 | 118 | 12925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5604 | 43734515201 | 003 | 2 |  | 1 | 004 | 17639.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5604 | 43734515201 | 006 | 2 |  | 1 | 923 | 12252.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5604 | 43734515201 | 019 | 2 |  | 1 | 117 | 25000 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5605 | 43565925201 | 003 | 2 |  | 1 | 923 | 7165.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5605 | 43565925201 | 025 | 2 | 850 | 1 | 112 | 12364.58 | 29035.25 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 030 | 2 |  | 1 | 115 | 3205.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 030 | 2 |  | 2 | 112 | 36730.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 030 | 2 |  | 3 | 115 | 27120.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 035 | 2 |  | 1 | 010 | 6158.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5605 | 43565925201 | 035 | 2 |  | 2 | 005 | 29151.23 | 29151.23 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 035 | 2 |  | 3 | 112 | 1444.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 036 | 2 |  | 1 | 001 | 25344.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 | 036 | 2 |  | 2 | 115 | 2659.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 036 | 2 |  | 3 | 105 | 8386.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5605 | 43565925201 | 036 | 2 |  | 4 | 007 | 1295.33 | 1295.33 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
05 | T5605 | 43565925201 | 036 | 2 |  | 5 | 105 | 5864.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5605 | 43565925201 | 047 | 2 |  | 1 | 101 | 6667.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5605 | 43565925201 | 047 | 2 |  | 2 | 112 | 1824 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 047 | 2 |  | 3 | 103 | 13380.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | T5605 | 43565925201 | 047 | 2 |  | 4 | 005 | 9754.02 | 9754.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 047 | 2 |  | 5 | 001 | 25895.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 | 047 | 2 |  | 6 | 005 | 903.79 | 903.79 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 047 | 2 |  | 7 | 024 | 28149.56 | 28149.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 047 | 2 |  | 8 | 005 | 1087.45 | 1087.45 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 047 | 2 |  | 9 | 001 | 1496.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 | 050 | 2 |  | 1 | 004 | 29508.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5605 | 43565925201 | 050 | 2 |  | 2 | 101 | 3992.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 3 | 004 | 183789.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5605 | 43565925201 | 050 | 2 |  | 4 | 112 | 52934.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 5 | 115 | 259.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 6 | 112 | 9433.37 | 0 | 1 |  | N | 19 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 7 | 115 | 301.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 8 | 001 | 4435.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 | 050 | 2 |  | 9 | 010 | 1077.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5605 | 43565925201 | 050 | 2 |  | 10 | 112 | 13677.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 11 | 105 | 1567.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 12 | 005 | 4985.25 | 4985.25 | 5 |  | N | 20 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 050 | 2 |  | 13 | 103 | 66793.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 14 | 005 | 1809.03 | 1809.03 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 050 | 2 |  | 15 | 112 | 422.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 16 | 107 | 261598.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 17 | 005 | 0 | 0 | 5 |  | N | 9 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 050 | 2 |  | 18 | 024 | 45812.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | T5605 | 43565925201 | 050 | 2 |  | 19 | 106 | 17010.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 20 | 123 | 48941.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 21 | 118 | 24926.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 22 | 115 | 4779.19 | 0 | 1 |  | N | 12 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 23 | 106 | 17129.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 24 | 112 | 28294.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 25 | 115 | 3921.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 26 | 118 | 3894.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5605 | 43565925201 | 050 | 2 |  | 27 | 208 | 28828.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
05 | T5605 | 43565925201 | 050 | 2 |  | 28 | 208 | 3931.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
05 | T5607 | 43612315201 | 005 | 2 |  | 1 | 926 | 1889.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
05 | T5615 | 43793115201 | 015 | 2 |  | 1 | 860 | 31000 | 0 | 0 |  | N | 176 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5624 | 43687915201 | 019 | 2 |  | 1 | 923 | 2683.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5624 | 43687915201 | 031 | 2 | 850 | 1 | 012 | 6115.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5624 | 43687915201 | 031 | 2 | 850 | 2 | 105 | 6182.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5624 | 43687915201 | 031 | 2 | 850 | 3 | 118 | 56055.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5624 | 43687915201 | 031 | 2 | 850 | 4 | 503 | 3609.5 | 3609.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5624 | 43687915201 | 035 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5625 | 42421715201 | 008 | 2 |  | 1 | 923 | 35995.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5625 | 42421715201 | 017 | 2 |  | 1 | 007 | 287549.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5625 | 42421715201 | 022 | 2 | 850 | 1 | 003 | 4203.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5625 | 42421715201 | 022 | 2 | 850 | 2 | 003 | -4203.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5625 | 42421715201 | 022 | 2 | 850 | 3 | 115 | 1096.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5625 | 42421715201 | 022 | 2 | 850 | 4 | 105 | 42442.39 | 20977.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5625 | 42421715201 | 022 | 2 | 850 | 5 | 122 | 26461.23 | 26461.23 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5625 | 42421715201 | 034 | 2 | 850 | 1 | 122 | 12717.82 | 6797.58 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5625 | 42421715201 | 034 | 2 | 850 | 2 | 101 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5625 | 42421715201 | 034 | 2 | 850 | 3 | 012 | 21856.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5625 | 42421715201 | 035 | 2 |  | 1 | 003 | 49359.11 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5625 | 42421715201 | 049 | 2 |  | 1 | 128 | 51820.01 | 15378.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5625 | 42421715201 | 049 | 2 |  | 2 | 118 | 48179.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5625 | 42421715201 | 049 | 2 |  | 3 | 003 | 36753.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5629 | 43759215201 | 007 | 2 |  | 1 | 923 | 3778.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5630 | 43732715201 | 018 | 2 |  | 1 | 923 | 1940.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5630 | 43732715201 | 035 | 2 |  | 1 | 022 | 40587.39 | 40587.39 | 5 |  | C | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5634 | 43734815201 | 007 | 2 |  | 1 | 923 | 2392.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5634 | 43734815201 | 027 | 2 |  | 1 | 107 | 14861.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5634 | 43734815201 | 027 | 2 |  | 2 | 115 | 162890.44 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5648 | 43759515201 | 017 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5652 | 43097555201 | 005 | 2 |  | 1 | 105 | 101952.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5653 | 43967915201 | 004 | 2 |  | 1 | 001 | 4388.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5653 | 43967915201 | 004 | 2 |  | 2 | 003 | 1868.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5653 | 43967915201 | 007 | 2 |  | 1 | 106 | 16812.53 | 0 | 0 |  | N | 153 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5660 | 24099255201 | 010 | 2 |  | 1 | 923 | 7533.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5660 | 24099255201 | 025 | 2 |  | 1 | 101 | 16047.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5660 | 24099255201 | 025 | 2 |  | 2 | 105 | 10607.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5660 | 24099255201 | 032 | 2 | 850 | 1 | 128 | 12390.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5660 | 24099255201 | 032 | 2 | 850 | 2 | 123 | 5402.32 | 2167.9 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
05 | T5660 | 24099255201 | 036 | 2 |  | 1 | 004 | 5988.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5660 | 24099255201 | 051 | 2 |  | 1 | 016 | 0 | 0 | 0 |  | N | 47 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
05 | T5661 | 43968225201 | 001 | 2 |  | 1 | 923 | 3208.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
05 | T5677 | 43923315201 | 006 | 2 |  | 1 | 115 | 144976.35 | 9704.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6J97 | 43338115201 | 010 | 2 |  | 1 | 919 | 26094.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6J97 | 43338115201 | 040 | 2 |  | 1 | 503 | 625433.66 | 0 | 0 |  | N | 106 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J97 | 43338115201 | 055 | 2 |  | 1 | 503 | 1203608.79 | 0 | 0 |  | N | 57 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J97 | 43338115201 | 059 | 2 |  | 1 | 012 | 184259.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6J97 | 43338115201 | 067 | 2 |  | 1 | 503 | -110250 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J97 | 43338115201 | 067 | 2 |  | 2 | 503 | 108395.81 | 0 | 0 |  | N | 119 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K86 | 43653215201 | 002 | 2 |  | 1 | 101 | 5393.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 005 | 2 |  | 1 | 101 | 88680.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 008 | 2 |  | 1 | 923 | 8188.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6K86 | 43653215201 | 013 | 2 |  | 1 | 108 | 37614.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L92 | 44203815201 | 003 | 2 |  | 1 | 007 | -1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6420 | 43345515201 | 007 | 2 |  | 1 | 305 | -453467.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6420 | 43345515201 | 017 | 2 | 850 | 1 | 503 | 14364.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 017 | 2 | 850 | 2 | 503 | 5124.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 017 | 2 | 850 | 3 | 503 | 4622.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 | 018 | 2 |  | 1 | 923 | 5263.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 003 | 2 |  | 1 | 503 | 314858.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 003 | 2 |  | 2 | 503 | 342248.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6422 | 42736925201 | 015 | 2 | 850 | 1 | 004 | 6035.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 2 | 001 | 15390.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 3 | 112 | 5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 4 | 112 | 5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 5 | 115 | 2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 6 | 101 | 13980 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 7 | 004 | 12782.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 8 | 105 | 6925.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 9 | 113 | 2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 10 | 007 | 2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 11 | 105 | -6925.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 12 | 112 | -5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 13 | 105 | 6928.85 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 14 | 112 | 5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 15 | 112 | -5050.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 16 | 115 | 2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 17 | 113 | 2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 18 | 115 | -2325.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 19 | 007 | 2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 015 | 2 | 850 | 20 | 112 | 5138.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 21 | 113 | -2607 | 2607 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 015 | 2 | 850 | 22 | 007 | -2309.71 | 2309.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6422 | 42736925201 | 016 | 2 | 850 | 1 | 101 | 11160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 | 016 | 2 | 850 | 2 | 105 | 5990.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736925201 | 016 | 2 | 850 | 3 | 003 | 2944.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6422 | 42736925201 | 016 | 2 | 850 | 4 | 113 | 12869.5 | 12869.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 018 | 2 |  | 1 | 923 | 64478.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
06 | T6422 | 42736925201 | 021 | 2 |  | 1 | 001 | 245590.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 | 003 | 2 |  | 1 | 117 | 126812.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
06 | T6424 | 42736915201 | 004 | 2 |  | 1 | 003 | 406217.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6424 | 42736915201 | 007 | 2 | 850 | 1 | 010 | 1713.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6424 | 42736915201 | 007 | 2 | 850 | 2 | 001 | 1564.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 | 007 | 2 | 850 | 3 | 001 | 1711.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 | 007 | 2 | 850 | 4 | 004 | 2580.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6424 | 42736915201 | 008 | 2 |  | 1 | 116 | 67132.64 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6424 | 42736915201 | 009 | 2 |  | 1 | 503 | -351435.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6424 | 42736915201 | 013 | 2 |  | 1 | 001 | 402694.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 | 018 | 2 |  | 1 | 101 | 12104 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6424 | 42736915201 | 021 | 2 |  | 1 | 725 | -33503.88 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Defective Materials | Defective Materials | 8
06 | T6425 | 42597925201 | 016 | 2 | 850 | 1 | 023 | 5813.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
06 | T6425 | 42597925201 | 016 | 2 | 850 | 2 | 118 | 1760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 3 | 118 | 817.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 4 | 101 | 5191.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6425 | 42597925201 | 016 | 2 | 850 | 5 | 503 | 3786.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6425 | 42597925201 | 016 | 2 | 850 | 6 | 112 | 19139.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6425 | 42597925201 | 017 | 2 | 850 | 1 | 850 | 9500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6425 | 42597925201 | 024 | 2 | 850 | 1 | 023 | 739.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | T6425 | 42597925201 | 025 | 2 | 850 | 1 | 118 | 1228.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6441 | 43117045201 | 008 | 2 |  | 1 | 923 | 12198.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6442 | 43063735201 | 009 | 2 |  | 1 | 107 | 3108.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6442 | 43063735201 | 024 | 2 |  | 1 | 923 | 112776.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6442 | 43063735201 | 026 | 2 |  | 1 | 015 | 375053.74 | 375053.74 | 5 |  | C | 40 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6447 | 43791515201 | 002 | 2 |  | 1 | 503 | 44551.32 | 4910.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6447 | 43791515201 | 004 | 2 |  | 1 | 004 | 48601.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6449 | 43345545201 | 004 | 2 |  | 1 | 001 | 89201.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6449 | 43345545201 | 008 | 2 |  | 1 | 007 | 46870.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 | 008 | 2 |  | 2 | 007 | 8344.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 | 009 | 2 |  | 1 | 007 | 16140.88 | 7024.29 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 | 009 | 2 |  | 2 | 007 | 28415.46 | 13221.15 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 | 004 | 2 |  | 1 | 021 | 140630.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 | 007 | 2 | 850 | 1 | 005 | 54240.59 | 54240.59 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6450 | 40557565201 | 007 | 2 | 850 | 2 | 108 | 34055.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6450 | 40557565201 | 007 | 2 | 850 | 3 | 023 | 3157.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6450 | 40557565201 | 007 | 2 | 850 | 4 | 004 | 2400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6450 | 40557565201 | 007 | 2 | 850 | 5 | 122 | 3698.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6450 | 40557565201 | 007 | 2 | 850 | 6 | 001 | 12469.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 007 | 2 | 850 | 7 | 115 | 2829.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6450 | 40557565201 | 008 | 2 |  | 1 | 001 | 48933 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 008 | 2 |  | 2 | 001 | 28226.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 008 | 2 |  | 3 | 004 | 1920 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6450 | 40557565201 | 009 | 2 | 850 | 1 | 001 | 8904.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 009 | 2 | 850 | 2 | 105 | 874.68 | 874.68 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6450 | 40557565201 | 009 | 2 | 850 | 3 | 001 | 1403.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 009 | 2 | 850 | 4 | 001 | 8635.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 009 | 2 | 850 | 5 | 007 | 9960.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 | 015 | 2 | 850 | 1 | 108 | 1620.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6450 | 40557565201 | 015 | 2 | 850 | 2 | 023 | 2790.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6450 | 40557565201 | 016 | 2 | 850 | 1 | 001 | 27970.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 016 | 2 | 850 | 2 | 001 | 64150.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 016 | 2 | 850 | 3 | 001 | 10015.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 | 017 | 2 | 850 | 1 | 007 | 30000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 | 020 | 2 | 850 | 1 | 007 | 21500 | 21500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 | 021 | 2 | 850 | 1 | 118 | 15091.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6450 | 40557565201 | 022 | 2 | 850 | 1 | 118 | 33357.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6450 | 40557565201 | 022 | 2 | 850 | 2 | 005 | 42143.94 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6450 | 40557565201 | 023 | 2 |  | 1 | 118 | 24454.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6459 | 44018715201 | 011 | 2 |  | 1 | 503 | 27176.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6470 | 43991715201 | 009 | 2 |  | 1 | 503 | 30818 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6471 | 43998315201 | 002 | 2 |  | 1 | 503 | 1035.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6471 | 43998315201 | 002 | 2 |  | 2 | 004 | 8555 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6477 | 44281315201 | 008 | 2 |  | 1 | 010 | 3563.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 | 009 | 2 |  | 1 | 101 | 2098.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44281315201 | 014 | 2 |  | 1 | 101 | 2056 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44281315201 | 015 | 2 |  | 1 | 101 | 6957 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6523 | 42918535201 | 007 | 2 |  | 1 | 503 | 33000 | 19915.87 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6523 | 42918535201 | 013 | 2 |  | 1 | 926 | 4593.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7K30 | 42450725201 | 003 | 2 |  | 1 | 004 | 53910 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 003 | 2 |  | 2 | 004 | 53910 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 005 | 2 |  | 1 | 105 | 21129.93 | 21129.93 | 2 |  | N | 37 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7K30 | 42450725201 | 006 | 2 |  | 1 | 004 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 007 | 2 |  | 1 | 122 | 374565.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K30 | 42450725201 | 011 | 2 |  | 1 | 122 | 103510.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7K30 | 42450725201 | 014 | 2 |  | 1 | 004 | 22139.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 027 | 2 |  | 1 | 004 | -6972.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 | 037 | 2 |  | 1 | 005 | 0 | 0 | 5 |  | N | 36 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7M31 | 43751715201 | 009 | 2 | 850 | 2 | 012 | 5653.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 009 | 2 | 850 | 3 | 012 | 34858.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 012 | 2 |  | 1 | 012 | -215166.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 | 012 | 2 |  | 2 | 012 | 97872.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
07 | E7M35 | 43642115201 | 003 | 2 |  | 1 | 126 | 1100 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | E7M35 | 43642115201 | 003 | 2 |  | 2 | 126 | 300 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | E7M35 | 43642115201 | 003 | 2 |  | 3 | 101 | 3032.58 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M87 | 43952515201 | 006 | 2 |  | 1 | 005 | 7703.18 | 7703.18 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
07 | E7M95 | 43762315201 | 002 | 2 |  | 1 | 503 | -5402.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M97 | 44024515201 | 002 | 2 |  | 1 | 118 | 9105.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7N20 | 25693135201 | 005 | 2 |  | 1 | 101 | 43790 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7R14 | 43402715201 | 019 | 2 |  | 1 | 019 | -197831.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
07 | E7R14 | 43402715201 | 019 | 2 |  | 2 | 503 | 150206.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R14 | 43402715201 | 019 | 2 |  | 3 | 101 | 11094.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7R14 | 43402715201 | 019 | 2 |  | 4 | 924 | 0 | 0 | 1 |  | N | 45 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7375 | 25729865201 | 005 | 2 |  | 1 | 101 | 20846.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7375 | 25729865201 | 013 | 2 |  | 1 | 919 | 63503.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7375 | 25729865201 | 014 | 2 |  | 1 | 106 | 5265.85 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7375 | 25729865201 | 014 | 2 |  | 2 | 101 | 25996.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7375 | 25729865201 | 014 | 2 |  | 3 | 106 | 14861.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7375 | 25729865201 | 021 | 2 | 850 | 1 | 850 | 81000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7375 | 25729865201 | 024 | 2 | 850 | 1 | 850 | 81000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7375 | 25729865201 | 025 | 2 |  | 1 | 107 | 24380.8 | 0 | 1 |  | N | 16 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 2 | 107 | 22823.41 | 0 | 1 |  | N | 15 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 3 | 003 | 8757.18 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7375 | 25729865201 | 025 | 2 |  | 4 | 503 | 6850.78 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7375 | 25729865201 | 025 | 2 |  | 5 | 115 | 16752.41 | 16752.41 | 1 |  | N | 18 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 6 | 115 | 2807.06 | 2807.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 7 | 115 | 5928.46 | 5928.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 8 | 115 | 4437.35 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 9 | 115 | 1777.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 10 | 107 | 8175.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 11 | 101 | 1752.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7375 | 25729865201 | 025 | 2 |  | 12 | 007 | 5606 | 5606 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7375 | 25729865201 | 025 | 2 |  | 13 | 503 | 7500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7375 | 25729865201 | 025 | 2 |  | 14 | 107 | 1450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7403 | 43484815201 | 002 | 2 |  | 1 | 107 | 272000 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7403 | 43484815201 | 015 | 2 |  | 1 | 001 | 10764.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 | 015 | 2 |  | 2 | 001 | 62227.26 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 | 015 | 2 |  | 3 | 503 | -36724.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7403 | 43484815201 | 016 | 2 |  | 1 | 015 | 18962.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 019 | 2 | 850 | 1 | 004 | 74905.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 | 023 | 2 |  | 1 | 007 | 126004 | 126004 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7403 | 43484815201 | 024 | 2 |  | 1 | 015 | 312498.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 026 | 2 |  | 1 | 101 | 193376.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7403 | 43484815201 | 027 | 2 |  | 1 | 015 | 24665.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 028 | 2 |  | 1 | 923 | 19997.87 | 19997.87 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7403 | 43484815201 | 037 | 2 |  | 1 | 126 | 1147.94 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Computation Error | Plan Modifications | 2
07 | T7403 | 43484815201 | 038 | 2 |  | 1 | 502 | 7800.89 | 709.17 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | T7403 | 43484815201 | 038 | 2 |  | 2 | 126 | 5500 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Computation Error | Plan Modifications | 2
07 | T7406 | 42895715201 | 010 | 2 |  | 1 | 119 | 4543 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
07 | T7406 | 42895715201 | 013 | 2 |  | 1 | 101 | 38081.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 | 013 | 2 |  | 2 | 012 | 19158.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 | 021 | 2 |  | 1 | 105 | 3359.89 | 2053.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7406 | 42895715201 | 024 | 2 |  | 1 | 024 | 3225.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7406 | 42895715201 | 025 | 2 |  | 1 | 115 | 1579.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 030 | 2 |  | 1 | 001 | 21907.79 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 030 | 2 |  | 2 | 107 | 6174.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 033 | 2 |  | 1 | 923 | 15801.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7406 | 42895715201 | 033 | 2 |  | 2 | 012 | 6136.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 | 036 | 2 |  | 1 | 001 | 90700.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 037 | 2 |  | 1 | 001 | 92484 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 | 038 | 2 |  | 1 | 001 | 385000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 009 | 2 |  | 1 | 305 | -124157.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 009 | 2 |  | 2 | 107 | 1586.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7413 | 43658815201 | 015 | 2 |  | 1 | 001 | 119288.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 | 027 | 2 |  | 1 | 101 | 356674.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7414 | 43571915201 | 014 | 2 |  | 1 | 004 | 18081.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7414 | 43571915201 | 015 | 2 |  | 1 | 004 | -18081.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7414 | 43571915201 | 023 | 2 |  | 1 | 004 | 14282.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7414 | 43571915201 | 023 | 2 |  | 2 | 004 | 3799.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7414 | 43571915201 | 040 | 2 |  | 1 | 004 | 33468.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7414 | 43571915201 | 040 | 2 |  | 2 | 101 | 12675.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7414 | 43571915201 | 041 | 2 |  | 1 | 108 | 73014.3 | 0 | 0 |  | N | 106 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7425 | 43982965201 | 001 | 2 |  | 1 | 101 | 6547.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7425 | 43982965201 | 001 | 2 |  | 2 | 105 | 4330 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7425 | 43982965201 | 008 | 2 |  | 1 | 106 | 14104.4 | 14104.4 | 2 |  | N | 12 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 1 | 001 | 3888 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 2 | 001 | 8552.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 3 | 007 | 3122.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7426 | 43648715201 | 012 | 2 |  | 4 | 128 | 3000 | 3000 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 5 | 923 | 1609.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 6 | 108 | 2108.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7426 | 43648715201 | 012 | 2 |  | 7 | 126 | 2658.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | T7426 | 43648715201 | 013 | 2 |  | 1 | 019 | 21000 | 21000 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
07 | T7435 | 43731215201 | 007 | 2 |  | 1 | 004 | -369888.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7435 | 43731215201 | 016 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 52 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 1 | 012 | 5997.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 2 | 012 | 1260.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 3 | 503 | 2997.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 4 | 012 | 5222.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 7 | 012 | 1484.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 13 | 012 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 12 | 917 | 91439.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 5 | 012 | 7502 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 6 | 012 | 400.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 8 | 007 | 7529.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 9 | 012 | 11124.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 10 | 012 | 5597.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 021 | 2 | 850 | 11 | 012 | 5530.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 030 | 2 |  | 1 | 004 | 158905.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 031 | 2 |  | 1 | 107 | 28187.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8M65 | 40609615201 | 033 | 2 |  | 1 | 004 | 48400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 036 | 2 |  | 1 | 004 | 126116.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 037 | 2 |  | 1 | 003 | 62415.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8M65 | 40609615201 | 039 | 2 |  | 1 | 503 | 712709.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 039 | 2 |  | 2 | 004 | -184400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 039 | 2 |  | 3 | 003 | -191534.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8M65 | 40609615201 | 046 | 2 |  | 1 | 004 | 24762.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 051 | 2 |  | 1 | 004 | 262895.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 052 | 2 |  | 1 | 503 | 616622.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 055 | 2 |  | 1 | 004 | 16228.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 058 | 2 |  | 1 | 004 | 164985.31 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 059 | 2 |  | 1 | 208 | 946875.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
08 | E8M65 | 40609615201 | 078 | 2 |  | 1 | 004 | 7933388.17 | 1383054.63 | 0 |  | N | 270 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 1 | 021 | 6678.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 2 | 503 | 5120.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 3 | 503 | 4176 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 4 | 503 | 13122.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 5 | 503 | 10246.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 6 | 012 | 1600.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 8 | 012 | 2564.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 9 | 503 | 2525.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 10 | 503 | 7547.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 11 | 012 | 2525.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 12 | 503 | 44764.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 15 | 010 | 26723.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8M65 | 40609615201 | 084 | 2 | 850 | 18 | 503 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 098 | 2 |  | 1 | 004 | 0 | 0 | 0 |  | N | 220 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 102 | 2 |  | 1 | 919 | 377151.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8M65 | 40609615201 | 123 | 2 |  | 1 | 503 | 144144.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 124 | 2 |  | 1 | 019 | -543418.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 1 | 503 | 8701.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 2 | 503 | 5819 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 3 | 503 | 54120 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 4 | 923 | 19317.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 5 | 503 | 11145.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 6 | 012 | 2188.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 7 | 503 | 29349.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 126 | 2 | 850 | 8 | 503 | 15394.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 127 | 2 |  | 1 | 503 | 343981.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 128 | 2 | 850 | 1 | 503 | 60948.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 | 128 | 2 | 850 | 2 | 503 | 7547.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 | 016 | 2 |  | 1 | 004 | 122389.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 022 | 2 |  | 1 | 007 | 91225.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N20 | 42714615201 | 040 | 2 |  | 1 | 007 | 224638.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 1 | 004 | 36556.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 2 | 004 | 44370 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 3 | 004 | 7830.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 4 | 007 | 37995.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 5 | 001 | 15254.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 | 041 | 2 | 850 | 6 | 010 | 6325 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8N20 | 42714615201 | 054 | 2 |  | 1 | 919 | 135773.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8N20 | 42714615201 | 057 | 2 |  | 1 | 004 | 45512.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 1 | 004 | 51357.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 2 | 023 | 3589.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 3 | 004 | 55765.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 4 | 503 | 6205.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 5 | 350 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 6 | 004 | 11024.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 7 | 122 | 9267.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
08 | E8N20 | 42714615201 | 060 | 2 | 850 | 8 | 013 | 3395.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
08 | E8N20 | 42714615201 | 063 | 2 |  | 1 | 004 | 52411.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 067 | 2 | 850 | 1 | 001 | 80741.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 | 067 | 2 | 850 | 2 | 004 | 31235.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 067 | 2 | 850 | 3 | 012 | 9094 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N20 | 42714615201 | 067 | 2 | 850 | 4 | 012 | 20048.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N20 | 42714615201 | 068 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 463 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 | 080 | 2 | 850 | 1 | 923 | 51391.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 | 080 | 2 | 850 | 2 | 112 | 62665.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N20 | 42714615201 | 080 | 2 | 850 | 3 | 004 | 13534.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 080 | 2 | 850 | 4 | 013 | 13831.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
08 | E8N20 | 42714615201 | 083 | 2 |  | 1 | 004 | 65659.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 086 | 2 |  | 1 | 004 | -770442.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 091 | 2 |  | 1 | 503 | -136370.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 | 099 | 2 |  | 1 | 004 | 747681.56 | 0 | 0 |  | N | 87 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 109 | 2 | 850 | 1 | 004 | 91154.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 | 124 | 2 |  | 1 | 004 | 224237.37 | 0 | 0 |  | N | 83 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N58 | 40610315201 | 007 | 2 |  | 1 | 101 | 9230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 008 | 2 |  | 1 | 101 | 27071.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 1 | 105 | 14769.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 2 | 112 | 32819.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 3 | 001 | 10262.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 4 | 107 | 13370.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 5 | 503 | 5357 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 6 | 108 | 4758.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 7 | 503 | 7921.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 8 | 108 | 5400.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 9 | 108 | 6542.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 10 | 012 | 6835.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 11 | 115 | 2814.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 12 | 108 | 7402.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 13 | 007 | 13215.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 14 | 503 | 3593.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 15 | 105 | 2174.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 16 | 007 | 9987.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N58 | 40610315201 | 029 | 2 | 850 | 17 | 115 | 2776.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 041 | 2 |  | 1 | 919 | 51404.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 044 | 2 |  | 1 | 919 | 100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 048 | 2 |  | 1 | 101 | 72115.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 051 | 2 |  | 1 | 503 | 14767.03 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 1 | 115 | 3541.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 2 | 115 | 2432.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 3 | 115 | 5427.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 4 | 115 | 13912.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 5 | 115 | 25424.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 6 | 115 | 26748.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 7 | 107 | 46405.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 8 | 107 | 3549.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 052 | 2 | 850 | 9 | 503 | 22556.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 054 | 2 |  | 1 | 503 | 1017545.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 057 | 2 |  | 1 | 105 | 46178.61 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 058 | 2 |  | 1 | 001 | 239664.02 | 88733.8 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 1 | 503 | 21497.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 2 | 107 | 52433.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 3 | 105 | 35043 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 7 | 001 | 11747.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 4 | 108 | 10314.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 5 | 107 | 6973.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 6 | 115 | 7553.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 060 | 2 | 850 | 8 | 105 | 4437.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 065 | 2 |  | 1 | 503 | 76995.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 069 | 2 |  | 1 | 503 | 417093.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 071 | 2 | 850 | 1 | 105 | 46067.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N58 | 40610315201 | 071 | 2 | 850 | 2 | 112 | 97940.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N58 | 40610315201 | 071 | 2 | 850 | 3 | 107 | 5991.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 073 | 2 |  | 1 | 503 | 203333.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 1 | 107 | 7465.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 2 | 107 | 19859.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 3 | 115 | 24993.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 4 | 503 | 3247.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 5 | 108 | 11236.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 6 | 108 | 31259.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 7 | 503 | 17265.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 8 | 503 | 948.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 9 | 101 | 6029.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 10 | 112 | 14629.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 11 | 108 | 1100.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 075 | 2 | 850 | 12 | 128 | 11928.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8N58 | 40610315201 | 076 | 2 |  | 1 | 503 | -1479.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 081 | 2 |  | 1 | 101 | 104021.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 082 | 2 |  | 1 | 503 | 9075 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 1 | 128 | 10686.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 2 | 503 | 2939.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 3 | 108 | 1364.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 5 | 503 | 6358 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 6 | 108 | 25094.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 7 | 923 | 10803.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 8 | 101 | 12316.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 9 | 503 | 5885 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 10 | 024 | 3475.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 11 | 001 | 4026.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 | 086 | 2 | 850 | 12 | 108 | 67049.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 087 | 2 |  | 1 | 503 | 343352.1 | 0 | 0 |  | N | 119 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 096 | 2 |  | 1 | 101 | 29074.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N58 | 40610315201 | 104 | 2 |  | 1 | 115 | 177211.59 | 0 | 0 |  | N | 25 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 1 | 108 | 18405.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 2 | 108 | 3233.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 3 | 108 | 3647.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 4 | 503 | 25720.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 5 | 108 | 3994.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 107 | 2 | 850 | 6 | 022 | 1045 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 111 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | C | 21 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 115 | 2 |  | 1 | 022 | 27855.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 115 | 2 |  | 2 | 024 | 71103.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N58 | 40610315201 | 116 | 2 |  | 1 | 108 | 15609.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N58 | 40610315201 | 120 | 2 |  | 1 | 503 | 174881.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 004 | 2 |  | 1 | 305 | -63028.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 028 | 2 |  | 1 | 919 | 150132.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 1 | 023 | 9375.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 2 | 023 | 7181.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 3 | 021 | 13533.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 4 | 023 | 5732.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 5 | 023 | 2189.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 6 | 115 | 8805.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 7 | 107 | 7236.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 029 | 2 | 850 | 8 | 003 | 56698.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 032 | 2 |  | 1 | 305 | -25375.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 039 | 2 |  | 1 | 009 | 291584.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N75 | 40611015201 | 049 | 2 |  | 1 | 503 | 43063.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 1 | 001 | 60829.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 2 | 004 | 2182 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 3 | 023 | 5182.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 4 | 023 | 1376.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 5 | 023 | 2888.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 6 | 023 | 12546.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 7 | 023 | 11149.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 8 | 023 | 14613.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 9 | 023 | 3511.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 10 | 108 | 16747.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 11 | 107 | 4875.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 053 | 2 | 850 | 12 | 023 | 4680.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 | 058 | 2 |  | 1 | 860 | 270000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8N75 | 40611015201 | 059 | 2 |  | 1 | 001 | 643196 | 0 | 0 |  | N | 54 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 060 | 2 |  | 1 | 001 | 2368613.36 | 0 | 0 |  | N | 44 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N75 | 40611015201 | 061 | 2 |  | 1 | 004 | 960545.48 | 0 | 0 |  | N | 89 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 | 066 | 2 |  | 1 | 003 | 261289.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611015201 | 069 | 2 |  | 1 | 012 | 92000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 078 | 2 |  | 1 | 923 | 78934.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 1 | 023 | 12773.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 2 | 021 | 23708.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 | 079 | 2 |  | 3 | 021 | 21680.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 007 | 2 |  | 1 | 503 | -44517.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 007 | 2 |  | 2 | 004 | -6451.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 023 | 2 |  | 1 | 503 | -393246.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 023 | 2 |  | 2 | 915 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 1 | 003 | 23309.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 2 | 105 | 10556.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 3 | 019 | 2074.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 4 | 018 | 16386.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 5 | 023 | 22586.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 6 | 101 | 3958.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 7 | 101 | 1188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 8 | 101 | 31600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 9 | 101 | 8316 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 10 | 115 | 2677.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 11 | 010 | 4296.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 12 | 021 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 13 | 503 | 1816.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 14 | 105 | 8533.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 15 | 115 | 4475.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 027 | 2 | 850 | 16 | 115 | 5724.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 030 | 2 |  | 1 | 914 | 45911.34 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 032 | 2 |  | 1 | 503 | 29077.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 032 | 2 |  | 2 | 916 | 41701.47 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 033 | 2 |  | 1 | 503 | 455166 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 033 | 2 |  | 2 | 503 | 264834 | 10885.05 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 1 | 115 | 12774.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 2 | 115 | 29411.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 3 | 503 | 14099.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 4 | 503 | 9248.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 5 | 101 | 5608.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 6 | 115 | 5785.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 7 | 503 | 5968.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 8 | 107 | 30708.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 9 | 105 | 2844.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 10 | 108 | 3068.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 11 | 115 | 5694.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 12 | 128 | 22749.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P02 | 40609055201 | 038 | 2 | 850 | 13 | 106 | 2038.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P02 | 40609055201 | 040 | 2 |  | 2 | 012 | 8793.08 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 1 | 128 | 1250.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 2 | 503 | 21622.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 3 | 115 | 4022.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 4 | 115 | 2915.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 5 | 503 | 4750.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 6 | 503 | 200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 7 | 022 | 5676.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 8 | 503 | 1925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 9 | 115 | 2838.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 10 | 012 | 9386.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 11 | 003 | 2118.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 12 | 115 | 1106.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 13 | 115 | 1799.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 14 | 018 | 6840.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 15 | 112 | 15831.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 19 | 126 | 12794.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 16 | 503 | 2888.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 17 | 503 | 3467.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 18 | 022 | 2569.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 23 | 115 | 10457.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 20 | 023 | 4861.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 21 | 503 | 988.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 22 | 112 | 12174.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 24 | 022 | 15514.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 045 | 2 | 850 | 25 | 503 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 046 | 2 |  | 1 | 503 | 112313.5 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 047 | 2 |  | 1 | 503 | 6851.77 | 6851.77 | 0 |  | C | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 047 | 2 |  | 2 | 001 | 162000 | 162000 | 0 |  | C | 20 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 047 | 2 |  | 3 | 001 | 22339.17 | 22339.17 | 0 |  | C | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 047 | 2 |  | 4 | 503 | 18000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 051 | 2 |  | 1 | 503 | 153602.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 051 | 2 |  | 2 | 101 | 87028.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 051 | 2 |  | 3 | 101 | 75050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 051 | 2 |  | 4 | 503 | 60305.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 2 | 503 | 0 | 0 | 0 |  | N | -3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 059 | 2 |  | 3 | 503 | 0 | 0 | 0 |  | N | -4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 1 | 115 | 1267.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 2 | 503 | 40149 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 3 | 503 | 7705.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 4 | 503 | 4291.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 5 | 023 | 11093.08 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 6 | 503 | 64000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 7 | 350 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 8 | 115 | 1615.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 9 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 10 | 503 | 6570.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 061 | 2 | 850 | 11 | 503 | 107.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 063 | 2 |  | 1 | 503 | 121447.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 063 | 2 |  | 2 | 503 | 44478.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 066 | 2 |  | 1 | 919 | 372612.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 1 | 503 | 5819.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 3 | 018 | 9176.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 5 | 503 | 18214.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 6 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 7 | 003 | 3062.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 8 | 106 | 17942.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 9 | 108 | 1049.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 10 | 118 | 1157.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 11 | 112 | 18181.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 12 | 108 | 12975.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 13 | 115 | 2000.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 14 | 022 | 4951.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 15 | 024 | 2475.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 16 | 003 | 557.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 17 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 18 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 21 | 001 | 10344.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 22 | 112 | 6783.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 23 | 118 | 4678.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 25 | 101 | 3621.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 26 | 118 | 2071.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 20 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 068 | 2 | 850 | 19 | 118 | 5134.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 069 | 2 |  | 1 | 503 | 127046.82 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 070 | 2 |  | 1 | 503 | 210944.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 1 | 503 | 11109.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 2 | 503 | 29536.92 | 9494.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 3 | 503 | 105715.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 4 | 503 | 21387.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 5 | 503 | 548155.14 | 274077.57 | 1 |  | N | 150 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 075 | 2 |  | 6 | 503 | 279804.4 | 94399.98 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 081 | 2 |  | 1 | 503 | -128857.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 1 | 118 | 6158.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 3 | 108 | 31064.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 082 | 2 | 850 | 4 | 108 | 1978.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8P02 | 40609055201 | 090 | 2 |  | 1 | 503 | 54918.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 2 | 503 | 126665.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 3 | 503 | 4480.83 | 4480.83 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 4 | 503 | 3963.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 5 | 503 | 6353.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 6 | 503 | 2007.38 | 2007.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 7 | 503 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 8 | 503 | 3405.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 9 | 503 | 4926.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 10 | 503 | 3567.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 090 | 2 |  | 11 | 503 | 222514.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 1 | 917 | 98329.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 2 | 503 | 33003.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 091 | 2 |  | 3 | 004 | 162566.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 1 | 022 | 11329.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 2 | 023 | 2816.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8P02 | 40609055201 | 092 | 2 |  | 3 | 503 | 67355.72 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P02 | 40609055201 | 093 | 2 |  | 1 | 917 | 0 | 0 | 0 |  | N | -4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 012 | 2 |  | 1 | 003 | -155000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 | 017 | 2 |  | 1 | 128 | 22000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8P82 | 43715615201 | 020 | 2 |  | 1 | 003 | 24876.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 | 024 | 2 |  | 1 | 503 | 22695 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 026 | 2 |  | 1 | 503 | 223422.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 030 | 2 |  | 1 | 503 | 122021.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 032 | 2 |  | 1 | 919 | 105075.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 035 | 2 |  | 1 | 503 | 69149 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 1 | 106 | 10299.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 2 | 023 | 8854.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 3 | 502 | 8997.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 4 | 012 | 3144 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 5 | 012 | 12082.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 6 | 503 | 19275.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 7 | 012 | 3157.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 8 | 115 | 17807.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 9 | 105 | 7051.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 10 | 012 | 8048.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 11 | 113 | 28166.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 12 | 105 | 5099.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 037 | 2 | 850 | 13 | 012 | 6508.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 | 041 | 2 |  | 1 | 503 | 224400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 043 | 2 |  | 1 | 503 | 39500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 044 | 2 |  | 1 | 503 | 17617.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 047 | 2 |  | 1 | 503 | 21836.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 049 | 2 |  | 1 | 503 | 137382.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 051 | 2 |  | 1 | 105 | 77562.19 | 61112.19 | 1 |  | N | 6 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 | 052 | 2 |  | 1 | 503 | 53774.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 055 | 2 |  | 1 | 503 | 16048.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 070 | 2 |  | 1 | 118 | 22420.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 | 078 | 2 |  | 1 | 113 | 19307 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 | 079 | 2 |  | 1 | 503 | 62997.61 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 082 | 2 |  | 1 | 024 | 50341.84 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 105 | 2 |  | 1 | 923 | 88416.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 114 | 2 |  | 1 | 503 | 38190.96 | 0 | 0 |  | N | 42 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 | 116 | 2 |  | 1 | 012 | 102025.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q10 | 43661915201 | 005 | 2 |  | 1 | 503 | 197004.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 | 018 | 2 |  | 1 | 919 | 10185.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 | 043 | 2 |  | 1 | 503 | 132056.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 021 | 2 |  | 1 | 503 | 365648.34 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 1 | 023 | 12863.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 2 | 023 | 14371.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 3 | 023 | 57300.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 032 | 2 | 850 | 4 | 023 | 8384.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 048 | 2 |  | 1 | 923 | 36759.43 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 052 | 2 | 850 | 1 | 023 | 64632.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 | 059 | 2 |  | 1 | 105 | -46875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q53 | 43516915201 | 059 | 2 |  | 2 | 101 | 56477.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q53 | 43516915201 | 064 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 006 | 2 |  | 1 | 503 | 69271.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 017 | 2 |  | 1 | 503 | 55739.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 017 | 2 |  | 2 | 101 | 5524.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 021 | 2 |  | 1 | 503 | 15218.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 1 | 023 | 2620.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 2 | 023 | 832.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 3 | 021 | 5017.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 4 | 023 | 1542.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 5 | 023 | 679.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 6 | 021 | 826.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 7 | 023 | 832.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 8 | 023 | 3057.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 9 | 021 | 354.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 10 | 023 | 1896.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 11 | 021 | 1880.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 12 | 021 | 832.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 13 | 023 | 709.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 14 | 023 | 1418.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 15 | 021 | 1187.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 16 | 023 | 679.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 17 | 023 | 1310.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 18 | 023 | 1196.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 19 | 023 | 1073.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 20 | 023 | 1187.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 21 | 023 | 956.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 22 | 023 | 709.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 26 | 023 | 709.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 27 | 021 | 956.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 28 | 023 | 949.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 29 | 021 | 826.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 30 | 021 | 826.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 31 | 021 | 709.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 32 | 023 | 478.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 33 | 023 | 967.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 34 | 023 | 1190.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 35 | 023 | 967.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 36 | 023 | 1801.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 37 | 023 | 1913.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 38 | 023 | 1790.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 39 | 023 | 2509.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 40 | 023 | 1897.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 43 | 023 | 1114.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 23 | 021 | 14684.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 24 | 023 | 1199.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 25 | 021 | 2861.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 41 | 023 | 1315.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 42 | 023 | 963.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 44 | 023 | 1315.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 45 | 021 | 2467.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 46 | 023 | 1188.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 47 | 023 | 707.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 48 | 107 | 2047.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 49 | 023 | 7880.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 50 | 021 | 735.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 51 | 021 | 2285.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 52 | 021 | 837.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 53 | 007 | 380 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 54 | 023 | 710.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 55 | 023 | 481.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 56 | 023 | 837.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 57 | 023 | 10418.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 58 | 023 | 2263.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 59 | 023 | 712.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 60 | 105 | 24236.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 61 | 023 | 9725.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 023 | 2 | 850 | 62 | 107 | 9337.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 052 | 2 |  | 1 | 923 | 2504.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 055 | 2 |  | 1 | 503 | 203155.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651715201 | 061 | 2 | 850 | 1 | 107 | 1762.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 061 | 2 | 850 | 2 | 021 | 367.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 061 | 2 | 850 | 3 | 021 | 5328.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 061 | 2 | 850 | 4 | 023 | 931.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 | 068 | 2 |  | 1 | 012 | 121565.8 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 | 074 | 2 |  | 1 | 023 | 179005.83 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 1 | 105 | 4981.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 2 | 023 | 1221.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 3 | 023 | 772.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 4 | 023 | 826.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 5 | 023 | 659.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 6 | 021 | 1032.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 7 | 023 | 699.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 8 | 023 | 15936.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 9 | 023 | 818.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 10 | 023 | 2188.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 11 | 503 | 20078.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 12 | 023 | 2255 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 13 | 021 | 1343.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 14 | 101 | 25921.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 15 | 023 | 4097.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 16 | 023 | 8612.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 17 | 021 | 4895.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 18 | 108 | 5461.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 19 | 021 | 385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 20 | 503 | 3901.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 21 | 118 | 13160.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 22 | 023 | 6836.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 25 | 107 | 2699.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 24 | 108 | 8417.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 015 | 2 | 850 | 23 | 021 | 12329.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 023 | 2 |  | 1 | 503 | 92475.97 | 0 | 0 |  | N | 102 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 027 | 2 |  | 1 | 108 | 179575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 037 | 2 |  | 1 | 923 | 13387.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 040 | 2 |  | 1 | 115 | -15980.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 044 | 2 |  | 1 | 503 | -5349.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 044 | 2 |  | 2 | 503 | 3129.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 044 | 2 |  | 3 | 503 | 1354.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 044 | 2 |  | 4 | 503 | 39318.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 044 | 2 |  | 5 | 101 | 36146.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 044 | 2 |  | 6 | 101 | 1394.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 1 | 108 | 28638.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 2 | 106 | 31667.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 3 | 023 | 1155 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 4 | 021 | 5336.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 5 | 101 | 56264.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 6 | 012 | 25885.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q93 | 42933915201 | 047 | 2 | 850 | 7 | 023 | 1053.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 1 | 012 | 46296.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 2 | 101 | 35339.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 3 | 023 | 770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 4 | 021 | 6730.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 5 | 021 | 8971.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 6 | 105 | 40911.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 7 | 021 | 2225.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 052 | 2 | 850 | 8 | 108 | 8755.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 1 | 108 | 24420.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 2 | 101 | 19061.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 3 | 108 | 6385.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 4 | 101 | 2109.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 5 | 108 | 19207.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 6 | 023 | 5908.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 058 | 2 | 850 | 7 | 108 | 72905.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 060 | 2 |  | 1 | 118 | 250053.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 1 | 108 | 1939.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 2 | 108 | 2841.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 3 | 503 | 10147.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 4 | 108 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 5 | 023 | 3461.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 6 | 101 | 999.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 7 | 024 | 34051.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 8 | 023 | 11382.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 9 | 101 | 24208.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 10 | 503 | 10924.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 11 | 108 | 2422.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 12 | 023 | 2061.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 13 | 503 | 2582.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 14 | 023 | 24445.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 061 | 2 | 850 | 15 | 101 | 9972.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 072 | 2 |  | 1 | 305 | -79241.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 073 | 2 |  | 1 | 305 | -47552.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 076 | 2 |  | 1 | 503 | 16366.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 076 | 2 |  | 2 | 022 | 14419.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 076 | 2 |  | 3 | 023 | 4599.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q93 | 42933915201 | 076 | 2 |  | 4 | 118 | 355.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 076 | 2 |  | 5 | 108 | 27669.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q93 | 42933915201 | 077 | 2 |  | 1 | 004 | 13669.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q94 | 43947815201 | 016 | 2 |  | 1 | 112 | 344805.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 1 | 106 | 1746.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 2 | 105 | 3063.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 3 | 023 | 11156.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 019 | 2 | 850 | 4 | 118 | 1520.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 023 | 2 |  | 1 | 112 | 4488.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 037 | 2 |  | 1 | 923 | 7893.31 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q94 | 43947815201 | 038 | 2 |  | 1 | 003 | -519709.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q94 | 43947815201 | 054 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8R19 | 43560565201 | 014 | 2 | 850 | 1 | 503 | 38093.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 | 014 | 2 | 850 | 2 | 503 | 5040.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 | 014 | 2 |  | 1 | 923 | 17526.5 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 | 015 | 2 |  | 1 | 860 | 125000 | 19602.33 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 1 | 021 | 7437.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 2 | 021 | 7437.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 3 | 021 | 7437.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 4 | 021 | 7437.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 5 | 024 | 2106.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 6 | 022 | 6090.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 7 | 021 | 6531.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 8 | 021 | 2118.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 9 | 021 | 1497.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 10 | 023 | 2622.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 11 | 022 | 34927.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 12 | 023 | 8611.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 13 | 023 | 1017.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 011 | 2 | 850 | 14 | 024 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 1 | 023 | 4600.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 2 | 021 | 1184.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 3 | 023 | 2994.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 4 | 021 | 6531.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 5 | 021 | 7233.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 6 | 021 | 7233.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 7 | 021 | 1868.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 8 | 021 | 1868.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 9 | 023 | 934.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 10 | 023 | 3737.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 11 | 024 | 22001.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 12 | 023 | 2895.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 13 | 021 | 1868.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 14 | 022 | 34112.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 016 | 2 | 850 | 15 | 023 | 934.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 026 | 2 | 850 | 1 | 022 | 25733.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8R58 | 43799115201 | 026 | 2 | 850 | 2 | 010 | 19154.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 | 026 | 2 | 850 | 3 | 023 | 743 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 | 026 | 2 | 850 | 4 | 021 | 2060.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 | 026 | 2 | 850 | 5 | 021 | 2309.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 1 | 021 | 685.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 2 | 101 | 791.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 3 | 021 | 743 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 4 | 021 | 743 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 5 | 023 | 1868.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 6 | 021 | 1486 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 7 | 021 | 743 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 8 | 021 | 11257.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 9 | 023 | 6322.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 10 | 021 | 1736 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 | 031 | 2 | 850 | 11 | 502 | 2088.76 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
08 | E8R76 | 43945715201 | 003 | 2 | 850 | 1 | 107 | 13354.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R76 | 43945715201 | 003 | 2 | 850 | 2 | 010 | 1919.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R76 | 43945715201 | 011 | 2 |  | 1 | 012 | 204265.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 015 | 2 |  | 1 | 923 | 34435.62 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 018 | 2 |  | 1 | 012 | -936460.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 027 | 2 |  | 1 | 012 | 304471.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 | 028 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R81 | 44132225201 | 007 | 2 |  | 1 | 010 | 45965 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R81 | 44132225201 | 007 | 2 |  | 2 | 018 | 48106.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8R95 | 43560575201 | 004 | 2 |  | 1 | 112 | 23169.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R95 | 43560575201 | 011 | 2 |  | 1 | 119 | -51627.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 1 | 101 | 2568.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 2 | 101 | 3520 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 3 | 101 | 4498.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 4 | 023 | 1163.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 5 | 101 | 8461.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 6 | 001 | 6397.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R95 | 43560575201 | 019 | 2 | 850 | 7 | 009 | 603.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8R95 | 43560575201 | 022 | 2 |  | 1 | 117 | -409201.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8R95 | 43560575201 | 022 | 2 |  | 2 | 700 | 64386.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
08 | E8R95 | 43560575201 | 022 | 2 |  | 3 | 117 | 154804.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8R95 | 43560575201 | 022 | 2 |  | 4 | 106 | 29979.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 | 022 | 2 |  | 5 | 106 | 11317.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 | 022 | 2 |  | 6 | 112 | 13786.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R95 | 43560575201 | 026 | 2 |  | 1 | 009 | 71182.44 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
08 | E8R95 | 43560575201 | 026 | 2 |  | 2 | 106 | 88817.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R96 | 44130915201 | 008 | 2 |  | 1 | 004 | -61096.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8R96 | 44130915201 | 011 | 2 | 850 | 1 | 115 | 48497.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R96 | 44130915201 | 017 | 2 |  | 1 | 118 | -4428.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R99 | 42897115201 | 005 | 2 |  | 1 | 107 | -576 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S33 | 44261815201 | 016 | 2 |  | 1 | 003 | 11457.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8S33 | 44261815201 | 019 | 2 |  | 1 | 128 | 21540.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | 359.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1440.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1460 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1133.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 012 | 1684.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 1152.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 012 | 6575.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 107 | -1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 107 | -466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 3 | 107 | -373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 4 | 107 | -386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 5 | 107 | -466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 6 | 107 | -279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 7 | 107 | -466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 8 | 107 | -479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 9 | 107 | -8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 10 | 107 | -3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 585.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 107 | 1389.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 3 | 107 | 466 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 4 | 107 | 373.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 5 | 107 | 386.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 6 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 7 | 107 | 279.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 8 | 107 | 466.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 9 | 107 | 479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 10 | 107 | 8084.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 11 | 107 | 3539.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | -15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 2 | 503 | -47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 855.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 2 | 503 | 15896.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 3 | 503 | 47689.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 503 | 269.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 105 | 11644.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 2184.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 012 | -24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43852815201 |  | 2 | CPI | 2 | 012 | 24281.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 864.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 503 | 1468.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 4852.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 5579.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 6792.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43763515201 |  | 2 | CPI | 2 | 131 | 323.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P44 | 43797315201 |  | 2 | CPI | 2 | 108 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P44 | 43763515201 |  | 2 | CPI | 1 | 131 | 1842.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
01 | E1P44 | 43797315201 |  | 2 | CPI | 1 | 012 | 6042.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1P44 | 43852815201 |  | 2 | CPI | 1 | 503 | 1437.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 107 | 7394.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 107 | -2396.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 2 | 101 | 1026.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 101 | 3615 | 2585.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R05 | 43629915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R08 | 43526515201 |  | 2 | CPI | 1 | 105 | 2070.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R08 | 43526515201 |  | 2 | CPI | 1 | 116 | 660 | 660 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | E1R08 | 43526515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R08 | 43526515201 |  | 2 | CPI | 1 | 001 | 1432.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1R08 | 43526515201 |  | 2 | CPI | 2 | 923 | 2569.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R11 | 41066625601 |  | 2 | CPI | 1 | 015 | 6418.24 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625601 |  | 2 | CPI | 2 | 015 | 22473.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 101 | 7077 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R11 | 41066625601 |  | 2 | CPI | 1 | 015 | 3120.6 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 023 | 1897.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625601 |  | 2 | CPI | 1 | 015 | 4383.87 | 2191.9 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625601 |  | 2 | CPI | 1 | 015 | 2986.79 | 2986.79 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625601 |  | 2 | CPI | 1 | 015 | 617.23 | 617.23 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 001 | 65000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 101 | 3982 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R11 | 41066625201 |  | 2 | CPI | 2 | 123 | 2753.4 | 2753.4 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 107 | 5196.23 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
01 | E1R11 | 41066625201 |  | 2 | CPI | 2 | 107 | 2386.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
01 | E1R11 | 41066625201 |  | 2 | CPI | 1 | 004 | 9706.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 2 | 001 | 2000.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R11 | 41066625201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R39 | 43802415201 |  | 2 | CPI | 1 | 009 | 13859.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1R39 | 43802415201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
01 | E1R64 | 42584125201 |  | 2 | CPI | 1 | 004 | 2625 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1R64 | 42584125201 |  | 2 | CPI | 1 | 105 | 4562.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R64 | 42584125201 |  | 2 | CPI | 1 | 007 | 20811.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R64 | 42584125201 |  | 2 | CPI | 1 | 115 | 14082.65 | 847.33 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1R78 | 43502915201 |  | 2 | CPI | 1 | 122 | 6425 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1R79 | 43806215201 |  | 2 | CPI | 1 | 007 | 5439.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1R81 | 43528615201 |  | 2 | CPI | 1 | 115 | 1845 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R86 | 44108815201 |  | 2 | CPI | 1 | 024 | 12659.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R86 | 44108815201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R99 | 43942615201 |  | 2 | CPI | 1 | 503 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1S13 | 44462715201 |  | 2 | CPI | 1 | 112 | 5595.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1S13 | 44462715201 |  | 2 | CPI | 1 | 007 | 1941.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S13 | 44462715201 |  | 2 | CPI | 1 | 112 | 1771 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1S13 | 44462715201 |  | 2 | CPI | 2 | 004 | 220 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1S13 | 44462715201 |  | 2 | CPI | 1 | 128 | 6591.66 | 6591.66 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1S13 | 44462715201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1S48 | 44005515201 |  | 2 | CPI | 1 | 012 | 9324.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1712 | 43355025201 |  | 2 | CPI | 1 | 107 | 876.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 1 | 107 | 1595 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 2 | 101 | 2108.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 1 | 007 | 15589.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1712 | 43355025201 |  | 2 | CPI | 2 | 105 | 2710.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 3 | 115 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 4 | 115 | 2531.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 5 | 101 | 3044.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1712 | 43355025201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1719 | 43800915201 |  | 2 | CPI | 1 | 112 | 5764.12 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1719 | 43800915201 |  | 2 | CPI | 1 | 001 | 5028.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1719 | 43800915201 |  | 2 | CPI | 1 | 012 | 25566.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1719 | 43800915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1720 | 43655125201 |  | 2 | CPI | 1 | 123 | 7522.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
01 | T1720 | 43655125201 |  | 2 | CPI | 1 | 503 | 8035.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1720 | 43655125201 |  | 2 | CPI | 1 | 007 | 4497.9 | 366.28 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
01 | T1720 | 43655125201 |  | 2 | CPI | 1 | 001 | 3047.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1721 | 43955515201 |  | 2 | CPI | 1 | 112 | 6782.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1722 | 43806015201 |  | 2 | CPI | 1 | 012 | 4650.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1722 | 43806015201 |  | 2 | CPI | 1 | 001 | 865.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | T1722 | 43806015201 |  | 2 | CPI | 2 | 924 | 2300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1722 | 43806015601 |  | 2 | CPI | 1 | 015 | 1940.5 | 500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1722 | 43806015201 |  | 2 | CPI | 1 | 503 | 5550 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1722 | 43806015201 |  | 2 | CPI | 1 | 012 | 650.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1722 | 43806015201 |  | 2 | CPI | 2 | 024 | 5303.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1742 | 43539015201 |  | 2 | CPI | 1 | 017 | 3026.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1742 | 43539015201 |  | 2 | CPI | 2 | 118 | 1820.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1742 | 43539015201 |  | 2 | CPI | 1 | 118 | 1928.94 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1742 | 43539015201 |  | 2 | CPI | 1 | 112 | 14779.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1742 | 43539015201 |  | 2 | CPI | 2 | 001 | 12336.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1742 | 43539015201 |  | 2 | CPI | 3 | 105 | 15941.18 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1744 | 43806115201 |  | 2 | CPI | 1 | 001 | 2845.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1744 | 43806115201 |  | 2 | CPI | 1 | 007 | 1202.66 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
01 | T1744 | 43806115201 |  | 2 | CPI | 1 | 007 | 745.03 | 745.03 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1746 | 43801415201 |  | 2 | CPI | 1 | 112 | 3847.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1746 | 43801415201 |  | 2 | CPI | 1 | 019 | 8167.24 | 8167.24 | 4 |  | N | 0 | Avoidable, In-House CEI | Conflict With Other Contractors | Changed Conditions | 1
01 | T1746 | 43801415201 |  | 2 | CPI | 1 | 019 | 0 | 0 | 4 |  | N | 2 | Avoidable, In-House CEI | Conflict With Other Contractors | Changed Conditions | 1
01 | T1748 | 43510815201 |  | 2 | CPI | 1 | 003 | 8712 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1750 | 44385115202 |  | 2 | CPI | 1 | 001 | 5174.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1759 | 44067015201 |  | 2 | CPI | 1 | 925 | 1297.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1759 | 44067015201 |  | 2 | CPI | 1 | 112 | 691.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1759 | 44067015201 |  | 2 | CPI | 2 | 122 | 1513.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1759 | 44067015201 |  | 2 | CPI | 3 | 112 | 4108.92 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1759 | 44067015201 |  | 2 | CPI | 4 | 007 | 19797.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1767 | 44068115201 |  | 2 | CPI | 1 | 105 | 3595.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1767 | 44068115201 |  | 2 | CPI | 1 | 007 | 1035.9 | 1035.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 001 | 4525.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 7583.1 | 7583.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 72 | 72 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 119 | 4229.66 | 4229.66 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
01 | T1997 | 40828655201 |  | 2 | CPI | 1 | 101 | 5166 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 101 | 3157 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828655201 |  | 2 | CPI | 1 | 924 | 1150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 924 | 1150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828655201 |  | 2 | CPI | 1 | 105 | 24368.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1997 | 40828655201 |  | 2 | CPI | 1 | 101 | 7031.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828665201 |  | 2 | CPI | 1 | 101 | 5883.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1997 | 40828655201 |  | 2 | CPI | 1 | 101 | 3587.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 003 | 9144.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | -3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 117 | 2621.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535602 |  | 2 | CPI | 1 | 115 | 2193.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535602 |  | 2 | CPI | 1 | 015 | 21144.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 007 | 26617.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q19 | 43056535602 |  | 2 | CPI | 1 | 015 | 4425.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 503 | 14323.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Q19 | 43056535602 |  | 2 | CPI | 1 | 015 | 354.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 3 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 4 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 122 | 716.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | E2Q19 | 43056535201 |  | 2 | CPI | 3 | 350 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 2 | 350 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 3 | 004 | 876.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q19 | 43056535201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 26 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 007 | 715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 2255.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 007 | 6699.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 5 | 007 | 5671.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 6 | 003 | 7500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 3 | 007 | 10049.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 007 | 4192.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 3 | 350 | 2851.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2Q20 | 43056515201 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2Q20 | 20821195201 |  | 2 | CPI | 1 | 013 | 8285 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 003 | 26121.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Q20 | 43056525201 |  | 2 | CPI | 1 | 013 | 21757.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Q20 | 43056515201 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 003 | 16439.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2S01 | 21334575201 |  | 2 | CPI | 3 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 101 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 3 | 101 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 4 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 5 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2S01 | 21334575201 |  | 2 | CPI | 6 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2S01 | 21334575201 |  | 2 | CPI | 1 | 004 | 38625.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2S01 | 21334575201 |  | 2 | CPI | 2 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 012 | 2812.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 012 | 5369.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 012 | 340.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 012 | 15714.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 012 | 12020.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 |  | 2 | CPI | 1 | 926 | 6878.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 107 | 3842.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2W31 | 43373015201 |  | 2 | CPI | 2 | 105 | 33477.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W31 | 43373015601 |  | 2 | CPI | 1 | 015 | 12500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 105 | 22235.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2W31 | 43373015601 |  | 2 | CPI | 1 | 015 | 13515.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015601 |  | 2 | CPI | 2 | 015 | 424.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 923 | 16678.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 350 | 6450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | E2W31 | 43373015201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 1302.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 923 | 6960.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 32487.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 2 | 001 | 3085.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 3280.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X06 | 43076015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X64 | 20964255201 |  | 2 | CPI | 1 | 923 | 1823.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X64 | 20964255201 |  | 2 | CPI | 1 | 108 | 4246.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X64 | 20964255201 |  | 2 | CPI | 1 | 108 | 523.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X65 | 43239615201 |  | 2 | CPI | 1 | 108 | 946.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X65 | 43239615201 |  | 2 | CPI | 1 | 108 | 8448 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X65 | 43239615201 |  | 2 | CPI | 1 | 106 | 4536.53 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X65 | 43239615201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 5 |  | N | 1 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 14105.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 2 | 115 | 2553.35 | 2553.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 001 | 2537.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 503 | 11453.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 6415.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y25 | 43761715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 115 | 1036.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y27 | 44129815601 |  | 2 | CPI | 1 | 015 | 3275 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Y27 | 44129815601 |  | 2 | CPI | 2 | 015 | 406 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Y27 | 44129815601 |  | 2 | CPI | 1 | 015 | 3608.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 012 | 1699.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 101 | 5811 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Y27 | 44129815201 |  | 2 | CPI | 2 | 005 | 6228.03 | 6228.03 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 923 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y27 | 44129815201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 003 | 300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Z22 | 44199725215 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Z35 | 43593915201 |  | 2 | CPI | 1 | 001 | 14105.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | E2Z35 | 43593915201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | E2Z37 | 43616525201 |  | 2 | CPI | 1 | 010 | 13585.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2Z37 | 44129815201 |  | 2 | CPI | 2 | 010 | 13585.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2Z37 | 43616525201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2Z38 | 43958915201 |  | 2 | CPI | 1 | 128 | 1116.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | E2Z38 | 43958915201 |  | 2 | CPI | 2 | 118 | 4245.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2Z38 | 43958915201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 010 | 4654.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | 9259.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 012 | 1087.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 115 | 1248.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 010 | -4654.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | -9259.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 012 | -1087.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 115 | -1248.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 003 | 9259.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 012 | 1087.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 115 | 1248.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 010 | 4654.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 010 | 18147.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 107 | 35329.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 001 | 2064.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 001 | 1077.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 015 | 18011.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 004 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | 4950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 105 | 6600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | 2069.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | 9479.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 003 | 2774.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2660 | 43607715201 |  | 2 | CPI | 2 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 3 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2660 | 43607715201 |  | 2 | CPI | 4 | 015 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 012 | 5177.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 115 | 2135.08 | 2135.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 010 | 2864.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 105 | 5800.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | -10194.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 923 | 7180.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 7150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 1375 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2675 | 43616315201 |  | 2 | CPI | 1 | 012 | 17338.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2675 | 43611415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 003 | 990 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 012 | 12194.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 923 | 4517.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 010 | 16788.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 503 | 40654.11 | 40654.11 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2690 | 42880715201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2690 | 42880715201 |  | 2 | CPI | 2 | 503 | 0 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 101 | 27341.53 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 101 | 683.4 | 683.4 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 112 | 4100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 001 | 17875.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 2 |  | N | 8 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2702 | 43616515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 115 | 4124.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 2 | 115 | 3616.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 3 | 115 | 8063.35 | 8063.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 012 | 17998.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2706 | 42879615201 |  | 2 | CPI | 2 | 115 | 3172.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 012 | 7992.12 | 1587.84 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2706 | 42879615201 |  | 2 | CPI | 2 | 115 | 1014.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 3 | 115 | 3218.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 115 | 19038.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 012 | 7914.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2713 | 43613525201 |  | 2 | CPI | 1 | 012 | 4371.93 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 1 | 003 | 12440.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 2 | 003 | 3420.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 3 | 003 | 2920.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2713 | 43613525201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2716 | 43763015201 |  | 2 | CPI | 1 | 010 | 6822.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2716 | 43763015201 |  | 2 | CPI | 1 | 010 | 598 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2716 | 43763015201 |  | 2 | CPI | 1 | 004 | 10000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2716 | 43763015201 |  | 2 | CPI | 1 | 004 | 12432.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2716 | 43763015201 |  | 2 | CPI | 2 | 003 | 1372.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 108 | 5620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 019 | 689.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2719 | 44089815201 |  | 2 | CPI | 1 | 019 | 16258.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2721 | 43761915201 |  | 2 | CPI | 1 | 101 | 8789 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2721 | 43761915201 |  | 2 | CPI | 2 | 007 | 32502.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2721 | 43761915201 |  | 2 | CPI | 3 | 024 | 7651.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 1 | 001 | 17144.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 2 | 010 | 20629.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2722 | 43761515201 |  | 2 | CPI | 3 | 012 | 4002.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2722 | 43761515201 |  | 2 | CPI | 1 | 012 | 5727.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 923 | 2676.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 101 | 4406.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2728 | 43732115201 |  | 2 | CPI | 1 | 101 | 1756.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2729 | 43499715201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2729 | 43499715201 |  | 2 | CPI | 2 | 106 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2729 | 43499715201 |  | 2 | CPI | 3 | 106 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2729 | 43499715201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2731 | 43617915201 |  | 2 | CPI | 1 | 107 | 36449.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
02 | T2731 | 43617915201 |  | 2 | CPI | 1 | 103 | 19710.74 | 8758.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2731 | 43617915201 |  | 2 | CPI | 1 | 023 | 440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2731 | 43617915201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 2 |  | N | 4 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
02 | T2735 | 44119515201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2737 | 43433315201 |  | 2 | CPI | 1 | 107 | 6222.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2737 | 43433315201 |  | 2 | CPI | 1 | 923 | 14918.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2737 | 43433315201 |  | 2 | CPI | 2 | 012 | 218.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2737 | 43433315201 |  | 2 | CPI | 1 | 003 | 2154.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2737 | 43433315201 |  | 2 | CPI | 2 | 012 | 548.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2737 | 43433315201 |  | 2 | CPI | 3 | 001 | 514.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 107 | 1210.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 108 | 984.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2737 | 43433315201 |  | 2 | CPI | 1 | 001 | 424.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 001 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2737 | 44106215201 |  | 2 | CPI | 2 | 101 | 3504.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 3 | 108 | 652.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 128 | 4700.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 2 | 103 | 2654.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 112 | 9251.93 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2737 | 44106215201 |  | 2 | CPI | 1 | 107 | 720.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
02 | T2737 | 43433315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 10088.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 9555.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2738 | 43934615201 |  | 2 | CPI | 2 | 923 | -10088.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2738 | 43934615201 |  | 2 | CPI | 3 | 112 | 28655.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2738 | 43934615201 |  | 2 | CPI | 1 | 923 | 533.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 482 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 3050 | 3050 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2745 | 43398815201 |  | 2 | CPI | 1 | 122 | 0 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2748 | 43911615201 |  | 2 | CPI | 1 | 113 | 908.06 | 908.06 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
02 | T2748 | 43911615201 |  | 2 | CPI | 1 | 115 | 25000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2748 | 43911615201 |  | 2 | CPI | 2 | 108 | 5175.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 101 | 5757.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 926 | 3549.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 2 | 101 | 591.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 101 | 3769.87 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 107 | 18123.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 023 | 5973.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
02 | T2749 | 43946715601 |  | 2 | CPI | 1 | 015 | 3313.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 107 | 3701.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 107 | 936.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2749 | 43946715201 |  | 2 | CPI | 1 | 107 | 2809.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2750 | 43908015201 |  | 2 | CPI | 1 | 101 | 1372.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2750 | 43908015201 |  | 2 | CPI | 1 | 105 | 3047 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2761 | 43934515201 |  | 2 | CPI | 1 | 113 | 1512.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2761 | 43934515201 |  | 2 | CPI | 2 | 004 | 2365 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2761 | 43934515201 |  | 2 | CPI | 1 | 001 | 2176.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2761 | 43934515201 |  | 2 | CPI | 2 | 118 | 250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2764 | 44140615201 |  | 2 | CPI | 1 | 003 | 6540.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2764 | 44140615201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2765 | 43934415201 |  | 2 | CPI | 1 | 001 | 35694.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2765 | 43934415201 |  | 2 | CPI | 1 | 022 | 9528 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2765 | 42293865201 |  | 2 | CPI | 2 | 001 | 35694.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2765 | 43934415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 3000 | 12169.21 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 14000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 101 | 10000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 2 | 115 | 5158.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 001 | 5436.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O87 | 42820825201 |  | 2 | CPI | 2 | 115 | 5158.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 3 | 101 | 1475.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3O87 | 42820825201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3Q54 | 22253925201 |  | 2 | CPI | 1 | 001 | 12310.59 | 8260 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3Q54 | 22253925201 |  | 2 | CPI | 1 | 923 | 727.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3R03 | 41343525201 |  | 2 | CPI | 1 | 503 | 3014 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R03 | 41343525201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 012 | 12225.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R51 | 22023625201 |  | 2 | CPI | 2 | 012 | 4330.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R51 | 22023625201 |  | 2 | CPI | 3 | 128 | 14324.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 4 | 117 | 987.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 503 | 15630.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | E3R51 | 22023625201 |  | 2 | CPI | 1 | 117 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3R70 | 43814115201 |  | 2 | CPI | 1 | 503 | 7012.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 012 | 1773.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 107 | 16000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3R72 | 43255415201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3R78 | 43813815201 |  | 2 | CPI | 1 | 004 | 3060.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3S03 | 43775215201 |  | 2 | CPI | 1 | 101 | 13602.6 | 9443.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 21397.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 012 | 12061.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 15030.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 16899.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 7865 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 107 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 007 | 3214.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 115 | 2091.93 | 2091.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 10539.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3287 | 22044245201 |  | 2 | CPI | 2 | 107 | 1156.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3287 | 22044245201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3578 | 41413235201 |  | 2 | CPI | 1 | 503 | 6380 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3578 | 41413235201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3582 | 43483715201 |  | 2 | CPI | 1 | 010 | 14185.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3663 | 43188345201 |  | 2 | CPI | 1 | 107 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3663 | 43188345201 |  | 2 | CPI | 1 | 107 | -1350 | -1134 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
03 | T3663 | 43188345201 |  | 2 | CPI | 2 | 107 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3694 | 43814015201 |  | 2 | CPI | 1 | 105 | 3166.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3694 | 43814015201 |  | 2 | CPI | 2 | 003 | 880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3694 | 43814015201 |  | 2 | CPI | 1 | 101 | 628.65 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3694 | 43814015201 |  | 2 | CPI | 1 | 024 | 1020 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3695 | 43775415201 |  | 2 | CPI | 1 | 105 | 4175.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T9021 | 44531225216 |  | 2 | CPI | 1 | 107 | 6598.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T9021 | 44531225216 |  | 2 | CPI | 1 | 107 | 407.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T9021 | 44531225216 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4M90 | 41242035201 |  | 2 | CPI | 1 | 012 | 14998.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 2 | 105 | 7083.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4M90 | 41242035201 |  | 2 | CPI | 3 | 003 | 15382.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 1 | 012 | -14998.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 2 | 012 | 14988.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 1 | 118 | 17202.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4M90 | 41242035201 |  | 2 | CPI | 2 | 122 | 8941.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4M90 | 41242035201 |  | 2 | CPI | 1 | 012 | 5449.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 1 | 012 | 958.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 2 | 012 | 11572.51 | 1198.8 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4M90 | 41242035201 |  | 2 | CPI | 2 | 012 | 4968.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 004 | 26400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 122 | 11699 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4N82 | 22777515201 |  | 2 | CPI | 3 | 007 | 5775 | 5775 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 25943.5 | 7700 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 6000 | 6000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 007 | 5720 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 024 | 992.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 024 | 1571.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 007 | 5257.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 007 | 4400.3 | 4400.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 023 | 4133.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 2890.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 015 | 17798 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 2 | 106 | 270.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 8538.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 2419.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 1 | 015 | 14610.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515601 |  | 2 | CPI | 2 | 015 | 3398.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4N82 | 22777515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 107 | 214.11 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 107 | 1836.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 112 | 15518.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 023 | 4304.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 503 | 396 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 503 | 5809.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 503 | 17817.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 009 | 2132.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 503 | 3192.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 4 | 107 | 422.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 107 | -214.11 | -214.11 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 107 | -1836.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 112 | -15518.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 4 | 503 | -396 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 5 | 503 | -5809.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 6 | 503 | -17817.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 7 | 009 | -2132.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 8 | 107 | -422.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 9 | 503 | -3192.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 107 | 214.11 | 214.11 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 107 | 1836.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 112 | 15518.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 4 | 503 | 396 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 5 | 503 | 5809.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 6 | 503 | 17817.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 7 | 009 | 2132.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 8 | 107 | 422.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 9 | 115 | 5794.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 10 | 107 | 4922.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 11 | 001 | 8910 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 12 | 503 | 3192.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 007 | 9483.69 | 9483.69 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 115 | 61.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 003 | 1280.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 117 | 9782.59 | 9782.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 003 | 2650.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 115 | 14370.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 118 | 6795.62 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 107 | 1848 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 115 | 9544.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 2 | 115 | 6892.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 3 | 115 | 4898.15 | 4898.15 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | E4T09 | 42264125201 |  | 2 | CPI | 1 | 105 | 6257.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T46 | 43388815201 |  | 2 | CPI | 1 | 024 | 4642.4 | 4642.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 007 | 6187.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 123 | 822 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 123 | 6825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 2 | 123 | 825.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | E4T54 | 42957525201 |  | 2 | CPI | 1 | 007 | 4837.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T56 | 43578125201 |  | 2 | CPI | 1 | 112 | 8903.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4T56 | 43578125201 |  | 2 | CPI | 1 | 101 | 1870.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T56 | 43578125201 |  | 2 | CPI | 2 | 001 | 36888.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T61 | 43783415201 |  | 2 | CPI | 1 | 101 | 4686 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T61 | 43783415201 |  | 2 | CPI | 1 | 012 | 30600.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T67 | 43990015201 |  | 2 | CPI | 1 | 105 | 786.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T85 | 43984315201 |  | 2 | CPI | 1 | 107 | 4031.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | E4T88 | 43986015201 |  | 2 | CPI | 1 | 005 | 27959.16 | 27959.16 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T89 | 43214615201 |  | 2 | CPI | 1 | 023 | 4224 | 4224 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4U43 | 44332215201 |  | 2 | CPI | 1 | 108 | 226.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | E4U78 | 4476871H201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 2066.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 115 | 4643.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 5945.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 12280.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 105 | 3113.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 003 | 2409 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 545.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 12344.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 3920.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 023 | 1259.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793725202 |  | 2 | CPI | 2 | 023 | 805.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 108 | 3307.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 26110.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 2 | 023 | 27326.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 3 | 023 | 15493.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 007 | 213.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 023 | 314.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 116 | 3388 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
04 | T4461 | 42793725201 |  | 2 | CPI | 1 | 007 | 9153.86 | 9153.86 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 115 | 3991.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4461 | 42793725202 |  | 2 | CPI | 1 | 108 | 1574.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4461 | 42793715201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4462 | 43232315201 |  | 2 | CPI | 1 | 001 | 9680.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 2 | 001 | 5714.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 3 | 001 | 2349.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 1 | 001 | 1126.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 1 | 101 | 8968.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4462 | 43232315201 |  | 2 | CPI | 2 | 112 | 935 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4462 | 43232315201 |  | 2 | CPI | 3 | 003 | 1723.71 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 4 | 001 | 11170.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 1 | 003 | 1772.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 2 | 007 | 3339.27 | 3339.27 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315201 |  | 2 | CPI | 1 | 115 | 4627.93 | 4627.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 007 | 4950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 007 | 2008.22 | 2008.22 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 007 | 1563.77 | 1563.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 007 | 6850.65 | 6850.65 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 003 | 1894.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 2 | 003 | 969.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4462 | 43232315202 |  | 2 | CPI | 1 | 503 | 1514.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4462 | 43232315203 |  | 2 | CPI | 1 | 007 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 021 | 4305.18 | 4305.18 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 2 | 021 | 4665.5 | 4665.5 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 3 | 021 | 3021.81 | 3021.81 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 021 | 3208 | 3208 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 2 | 023 | 935.97 | 935.97 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 3 | 023 | 5068 | 5068 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 101 | 2472.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4473 | 42751615201 |  | 2 | CPI | 1 | 023 | 5694.93 | 5694.93 | 5 |  | N | 0 | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4479 | 43059025201 |  | 2 | CPI | 1 | 118 | 1969.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008415201 |  | 2 | CPI | 1 | 118 | 3733.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008415201 |  | 2 | CPI | 1 | 118 | 1044.62 | 1044.62 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4483 | 44008515201 |  | 2 | CPI | 1 | 106 | 3638.7 | 3638.7 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4485 | 43634115201 |  | 2 | CPI | 1 | 023 | 2490 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4485 | 43634115202 |  | 2 | CPI | 1 | 105 | 3760 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4485 | 43634115202 |  | 2 | CPI | 2 | 208 | 2255.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
04 | T4485 | 43634115201 |  | 2 | CPI | 1 | 118 | 8753.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4485 | 43634115201 |  | 2 | CPI | 2 | 118 | 7779.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 106 | 1064.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 105 | 445.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 1 | 024 | 7907.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4489 | 43770115201 |  | 2 | CPI | 2 | 503 | 5506.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 112 | 6121.07 | 6121.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 105 | 6791.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 128 | 2716.96 | 2716.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 106 | 8811.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 3 | 001 | 925.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 128 | 12459.64 | 12459.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 003 | 2948.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 115 | 1185.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4491 | 43234815201 |  | 2 | CPI | 1 | 001 | 768.76 | 768.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4491 | 43234815201 |  | 2 | CPI | 2 | 001 | 4035.29 | 4035.29 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 112 | 1637.22 | 1637.22 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4496 | 43288335201 |  | 2 | CPI | 2 | 350 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 007 | 1782.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 105 | 286.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4496 | 43288335201 |  | 2 | CPI | 1 | 001 | 18472.1 | 18472.1 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 108 | 3789.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4496 | 43288335202 |  | 2 | CPI | 1 | 007 | 754.95 | 754.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 001 | 1613.37 | 1613.37 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 106 | 193.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 005 | 8590.45 | 8590.45 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 122 | 39495.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 001 | 106.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4498 | 43689315201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 112 | 6319.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 503 | 6397.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 112 | 13304.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 112 | -131.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 119 | 6076.18 | 6076.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 1 | 101 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 2 | 101 | -139.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 3 | 101 | -1.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4499 | 44055425202 |  | 2 | CPI | 4 | 122 | 7393.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 119 | 3198.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 115 | 5740 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 007 | 3012.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 503 | 1831.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 119 | 17422.55 | 17422.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4500 | 43435915201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 1 |  | N | 59 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4501 | 43468615201 |  | 2 | CPI | 1 | 107 | 1501.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
04 | T4501 | 43468615201 |  | 2 | CPI | 1 | 108 | 2433.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4501 | 43468615201 |  | 2 | CPI | 1 | 106 | 3339.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4501 | 43468615201 |  | 2 | CPI | 1 | 118 | 15219.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4502 | 43630315202 |  | 2 | CPI | 1 | 115 | 7041.64 | 1496.72 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4502 | 43630315202 |  | 2 | CPI | 1 | 101 | 6163.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4502 | 43630315202 |  | 2 | CPI | 1 | 106 | 411.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4502 | 43630315202 |  | 2 | CPI | 2 | 101 | 356.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 024 | 3707.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 023 | 3357.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 3 | 024 | 1463.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 001 | 8856.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 001 | 12705 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 503 | 3935.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 503 | 2330.49 | 2330.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 108 | 4258.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 2 | 108 | 1248.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4503 | 43611115201 |  | 2 | CPI | 1 | 108 | 7227.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4506 | 43783215201 |  | 2 | CPI | 1 | 118 | 5261.8 | 170.62 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4506 | 43783215201 |  | 2 | CPI | 2 | 101 | 10056.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4506 | 43783215201 |  | 2 | CPI | 3 | 106 | 8964.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4506 | 43783215201 |  | 2 | CPI | 1 | 118 | 170.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4507 | 43771815201 |  | 2 | CPI | 1 | 101 | 6506.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4507 | 43771815201 |  | 2 | CPI | 1 | 112 | 1094.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4508 | 43206655201 |  | 2 | CPI | 1 | 503 | 8028.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4508 | 43206665201 |  | 2 | CPI | 1 | 106 | 11896.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4508 | 43206665201 |  | 2 | CPI | 2 | 128 | 7735.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4508 | 43206665201 |  | 2 | CPI | 3 | 106 | 4227.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4508 | 42956945201 |  | 2 | CPI | 1 | 106 | 8016 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4508 | 42956945201 |  | 2 | CPI | 1 | 503 | 1541.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4508 | 43206655201 |  | 2 | CPI | 1 | 926 | 1122.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4508 | 43206655201 |  | 2 | CPI | 1 | 023 | 1339.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4508 | 43206665201 |  | 2 | CPI | 1 | 503 | 1223.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4508 | 43773115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4510 | 43234415201 |  | 2 | CPI | 1 | 503 | 495 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4510 | 43234415201 |  | 2 | CPI | 1 | 503 | 6627.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4510 | 43234415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4510 | 43234415201 |  | 2 | CPI | 1 | 503 | 2086.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4513 | 43770815201 |  | 2 | CPI | 1 | 118 | 2824.14 | 2824.14 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4513 | 43770815202 |  | 2 | CPI | 1 | 106 | 3604.01 | 2666.51 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4514 | 43778515201 |  | 2 | CPI | 1 | 502 | 0 | 0 | 2 |  | N | 23 | Avoidable, In-House Designer | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 503 | 825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 106 | 1471.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 503 | 825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 503 | -825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 106 | 1471.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 106 | 9904.65 | 9904.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4518 | 43829115201 |  | 2 | CPI | 1 | 106 | 293.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4520 | 43770215201 |  | 2 | CPI | 1 | 106 | 12605.27 | 12605.27 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4520 | 43770215201 |  | 2 | CPI | 1 | 003 | 1689.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 022 | 25200 | 25200 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 101 | 5947.92 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 112 | 3934.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 2 | 926 | 282.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 112 | 1239.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 101 | 3062.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 2 | 101 | 1255.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 3 | 118 | 226.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4524 | 43770715201 |  | 2 | CPI | 4 | 007 | 7700 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4524 | 43770715201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
04 | T4529 | 44313215201 |  | 2 | CPI | 1 | 118 | 4193.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4531 | 44313515201 |  | 2 | CPI | 1 | 112 | 1271.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4531 | 44322315201 |  | 2 | CPI | 1 | 118 | 1098.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4531 | 44322315201 |  | 2 | CPI | 1 | 118 | 1431.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4534 | 43654115201 |  | 2 | CPI | 1 | 926 | 3594.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4534 | 43654115201 |  | 2 | CPI | 1 | 103 | 5588.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | T4536 | 43838915201 |  | 2 | CPI | 1 | 118 | 3724.52 | 3724.52 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4536 | 43838915201 |  | 2 | CPI | 1 | 115 | 1426.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4536 | 43838915201 |  | 2 | CPI | 1 | 007 | 1661.31 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4536 | 43838915201 |  | 2 | CPI | 1 | 007 | 6454.59 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4540 | 43834515201 |  | 2 | CPI | 1 | 112 | 470.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 023 | 400.88 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 023 | 400.88 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 023 | -400.88 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 023 | 1044.53 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4545 | 43984415201 |  | 2 | CPI | 2 | 503 | 1196.92 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4545 | 43984415201 |  | 2 | CPI | 1 | 113 | 1485 | 1485 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4549 | 43783015201 |  | 2 | CPI | 1 | 926 | 641.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4550 | 43689715201 |  | 2 | CPI | 1 | 926 | 1294.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4550 | 43689715201 |  | 2 | CPI | 1 | 012 | 8552.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E50A4 | 43754315201 |  | 2 | CPI | 1 | 003 | 20101.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E54A5 | 44417615201 |  | 2 | CPI | 1 | 115 | 8395.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E54A5 | 44417615201 |  | 2 | CPI | 1 | 115 | 390.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E54A5 | 44417615201 |  | 2 | CPI | 1 | 001 | 3647.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 003 | 17568.1 | 17568.1 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 003 | 7550.4 | 25118.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 012 | 2799.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 107 | 420 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 023 | 8018.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 104 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 234 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 2 | 118 | 143 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 3 | 021 | 2845.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 494 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 312 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 728 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 286 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 598 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 884 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 624 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 107 | 416 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Y62 | 23831925201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 503 | 4634.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 4455.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 012 | 1091.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z20 | 43632415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z30 | 43952115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 018 | 3451.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 107 | 33500.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 107 | 9500.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | E5Z64 | 44121015201 |  | 2 | CPI | 1 | 112 | 3547.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E5Z77 | 43912115201 |  | 2 | CPI | 1 | 012 | 9663.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z77 | 43912115201 |  | 2 | CPI | 1 | 012 | 13545.33 | 13545.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 001 | 4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | -11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | 11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | 4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 115 | 19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 008 | -11904 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | -4800.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 115 | -19392.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 106 | 1949.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 106 | 1114.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 106 | 1558.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 4 | 106 | 3140.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5530 | 23968215601 |  | 2 | CPI | 1 | 015 | 1141.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215601 |  | 2 | CPI | 2 | 015 | 16268.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 108 | 1189.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 108 | 1789.26 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 101 | 2359.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 112 | 2001.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 112 | 1639.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 128 | 11744.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 001 | 5722.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 117 | 3437.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 119 | 2751.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 112 | 1377.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 3 | 107 | 1443.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 4 | 503 | 7375.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5530 | 23968215201 |  | 2 | CPI | 5 | 003 | 3353.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5530 | 23968215601 |  | 2 | CPI | 1 | 015 | 2589.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 108 | 5274.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 117 | 6350.74 | 8905.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 001 | 1077.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 8895.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5530 | 23968215201 |  | 2 | CPI | 2 | 003 | 2145 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5530 | 23968215201 |  | 2 | CPI | 1 | 115 | 11221.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 010 | 1541.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 107 | 49382.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 115 | 19865.61 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 2 | 107 | 24421.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 107 | 1988.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 107 | 2831.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 008 | 7553.28 | 7553.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5589 | 23827535201 |  | 2 | CPI | 2 | 008 | 3884.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 024 | 2914.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 024 | 2397.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
05 | T5589 | 23827535201 |  | 2 | CPI | 2 | 107 | 15182.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 115 | 3951.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 115 | 3951.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 003 | 1956.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5589 | 23827535201 |  | 2 | CPI | 1 | 107 | 8175.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5589 | 23827525201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 105 | 4348.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 001 | 5087.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 108 | 14022.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 007 | 737 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5590 | 42690535201 |  | 2 | CPI | 2 | 108 | 6557.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 3 | 106 | 5622.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 4 | 108 | 5882.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 1 | 105 | 37534.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5590 | 42690535201 |  | 2 | CPI | 2 | 004 | 10206.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 9579.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 30081.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 106 | 2500 | 2500 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5592 | 43440715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5604 | 43734515201 |  | 2 | CPI | 1 | 503 | 4561.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5604 | 43734515201 |  | 2 | CPI | 2 | 503 | 4561.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5604 | 43734515201 |  | 2 | CPI | 1 | 023 | 7577.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 115 | 6676.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 |  | 2 | CPI | 2 | 001 | 21178.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 112 | 20171.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 112 | 10303.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 112 | 16670.67 | 16670.67 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5605 | 43734415201 |  | 2 | CPI | 1 | 003 | 11988.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5605 | 43734415201 |  | 2 | CPI | 1 | 003 | -11988.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5605 | 43734415201 |  | 2 | CPI | 2 | 003 | 11909 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5605 | 43565925201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 15 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5607 | 43612315201 |  | 2 | CPI | 1 | 118 | 2189 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5615 | 43793115201 |  | 2 | CPI | 1 | 106 | 450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5615 | 43793115201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 106 | 14234.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 113 | 5470.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Pavement Design Modification | Plan Modifications | 2
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 012 | 99294.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5624 | 43687915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 115 | 10381.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5625 | 43793115201 |  | 2 | CPI | 1 | 003 | 4203.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 115 | 13222.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 001 | 19691.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 003 | 4203.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 115 | 15181.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 012 | 12320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 126 | 0 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5625 | 42421715201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 108 | 2854.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 2 | 107 | 5414.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 3 | 001 | 3192.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5629 | 43759215201 |  | 2 | CPI | 4 | 115 | 3912.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 5 | 018 | 667.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 106 | 2947.5 | 2947.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5629 | 43759215201 |  | 2 | CPI | 1 | 005 | 0 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 105 | 4977.3 | 1322.3 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 503 | 11770.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 101 | 28850.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 2 | 024 | 10777.02 | 10777.02 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 3 | 024 | 7926.68 | 7926.68 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 101 | 28850.1 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 024 | 0 | 10777.02 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5630 | 43732715201 |  | 2 | CPI | 1 | 024 | 0 | 7926.68 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5648 | 43759515201 |  | 2 | CPI | 1 | 107 | 7038.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5649 | 43747015201 |  | 2 | CPI | 1 | 105 | 18121.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5649 | 43747015201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5649 | 43747015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 127 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 012 | 21091.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 001 | 6502.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 115 | 4722.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 2 | 128 | 2956.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 3 | 128 | 5313.29 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 007 | 9413.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5660 | 24099255201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 101 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 118 | 17161.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 112 | 1763.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 2 | 101 | 5040 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 023 | 3456.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 101 | 1936.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968225201 |  | 2 | CPI | 1 | 012 | 2898.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5661 | 43968225201 |  | 2 | CPI | 2 | 012 | 825 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 101 | 645.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5661 | 43968255201 |  | 2 | CPI | 1 | 012 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5677 | 43923315201 |  | 2 | CPI | 1 | 004 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5714 | 44137015201 |  | 2 | CPI | 1 | 005 | 5421.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
05 | T5714 | 44137015201 |  | 2 | CPI | 2 | 001 | 5035.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5714 | 44137015201 |  | 2 | CPI | 3 | 001 | 1793.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6J97 | 43338115201 |  | 2 | CPI | 1 | 018 | 5452.54 | 5452.54 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | E6J97 | 43338115201 |  | 2 | CPI | 1 | 503 | 70460.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6J97 | 43338127201 |  | 2 | CPI | 1 | 010 | 15126.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | E6K57 | 43854015201 |  | 2 | CPI | 1 | 503 | 30012.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K74 | 43652715201 |  | 2 | CPI | 1 | 012 | 13129.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K74 | 43652715201 |  | 2 | CPI | 1 | 131 | 16554.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Architectural Feature Related Issue | Plan Modifications | 2
06 | E6K86 | 43653215201 |  | 2 | CPI | 1 | 108 | 569.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6K86 | 43653215201 |  | 2 | CPI | 1 | 012 | 21689.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L73 | 44183715201 |  | 2 | CPI | 1 | 118 | 3830.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L73 | 44183715201 |  | 2 | CPI | 1 | 118 | 2413.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L73 | 44183715201 |  | 2 | CPI | 2 | 101 | 7079.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 770 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 14416.8 | 14416.8 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L77 | 44059015201 |  | 2 | CPI | 1 | 503 | 6050.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 1 | 503 | 2092.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 2 | 503 | 3273.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L92 | 44203815201 |  | 2 | CPI | 1 | 503 | 1986.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 108 | 24194.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 101 | 898.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 118 | 2103.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 108 | 7338.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 023 | 1601.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 012 | 7070.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L95 | 44174015201 |  | 2 | CPI | 1 | 503 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M35 | 42934165201 |  | 2 | CPI | 1 | 004 | 1419.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6420 | 43345515201 |  | 2 | CPI | 1 | 115 | 16778.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6420 | 43345515201 |  | 2 | CPI | 2 | 503 | 9291.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 |  | 2 | CPI | 2 | 503 | 7900.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6420 | 43345515201 |  | 2 | CPI | 3 | 001 | 7655 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345515201 |  | 2 | CPI | 1 | 001 | 2848.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345525201 |  | 2 | CPI | 1 | 001 | 2349.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6420 | 43345525201 |  | 2 | CPI | 1 | 118 | 747.53 | 747.53 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 105 | 36378.86 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 105 | 9706.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 115 | 9362.94 | 9362.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 107 | 7701.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 012 | 5508.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 107 | 2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 001 | 16495.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 |  | 2 | CPI | 2 | 105 | 2540.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | 4161 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 1 | 001 | 3221.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6422 | 42736925201 |  | 2 | CPI | 2 | 112 | 11962.36 | 11962.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6422 | 42736925201 |  | 2 | CPI | 3 | 004 | 3191.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | 27668 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 2 | 022 | 2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 3 | 004 | 2312.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 101 | -27668 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 2 | 101 | 27688 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 3 | 107 | -2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 4 | 107 | 2902.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 5 | 022 | -2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6422 | 42736935201 |  | 2 | CPI | 1 | 022 | 2514.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6424 | 40557595201 |  | 2 | CPI | 1 | 001 | 2216.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 |  | 2 | CPI | 1 | 101 | 17376.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6424 | 42736915201 |  | 2 | CPI | 2 | 001 | 1711.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6424 | 42736915201 |  | 2 | CPI | 1 | 106 | 8858.8 | 8858.8 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6424 | 42736915201 |  | 2 | CPI | 2 | 106 | 1737.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6424 | 40557595201 |  | 2 | CPI | 1 | 116 | 13415.95 | 13415.95 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6424 | 42736915201 |  | 2 | CPI | 1 | 106 | 7391.47 | 7391.47 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6424 | 40557595201 |  | 2 | CPI | 1 | 010 | 1317.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6424 | 42736915201 |  | 2 | CPI | 1 | 004 | 1161.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6424 | 42736915201 |  | 2 | CPI | 2 | 004 | 15872.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6424 | 42736915201 |  | 2 | CPI | 1 | 108 | 908 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 105 | 1273.66 | 1273.66 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 001 | 2547.31 | 2547.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 001 | 3850.04 | 3850.04 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 004 | 18901.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 012 | 3329.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 023 | 2497.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 023 | 4289.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6425 | 42597925202 |  | 2 | CPI | 1 | 118 | 7784.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 1 | 023 | -4289.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925201 |  | 2 | CPI | 2 | 023 | 4289.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6425 | 42597925202 |  | 2 | CPI | 1 | 118 | 3765.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 123 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 2988.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 2 | 010 | 2106.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6441 | 43117035201 |  | 2 | CPI | 1 | 503 | 9360.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 7668.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 503 | 564.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6441 | 43117045201 |  | 2 | CPI | 1 | 012 | 990 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 016 | 22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 019 | 1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | 10000 | 10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | -10000 | -10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 103 | 10000 | 10000 | 5 |  | N | 0 | Avoidable, Third Party | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 4143.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 106 | 4309.28 | 4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 503 | 3440 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 004 | 11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 546.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 2 | 015 | 41610.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 003 | 5640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 016 | -22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 3 | 106 | -4309.28 | -4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 4 | 019 | -1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 5 | 004 | -11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 115 | 5377.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 2 | 016 | 22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 3 | 106 | 4309.28 | 4309.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6442 | 43063735201 |  | 2 | CPI | 4 | 019 | 1565.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 5 | 004 | 11770.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | -8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 1 | 015 | 8575.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735601 |  | 2 | CPI | 2 | 015 | 17233.53 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 503 | 19417.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6442 | 43063735201 |  | 2 | CPI | 1 | 004 | 15272.5 | 15272.5 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6449 | 43791815201 |  | 2 | CPI | 1 | 004 | 1189.77 | 1189.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 108 | 3900.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6449 | 43791815201 |  | 2 | CPI | 1 | 007 | 5843.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 503 | 13592.03 | 13592.03 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 022 | 951.73 | 951.73 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 001 | 253 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 503 | 1030.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6449 | 43791815201 |  | 2 | CPI | 1 | 007 | 800.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43791815201 |  | 2 | CPI | 2 | 007 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 118 | 403.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6449 | 43345545201 |  | 2 | CPI | 2 | 007 | 1273.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43345545201 |  | 2 | CPI | 1 | 007 | 403.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6449 | 43791815202 |  | 2 | CPI | 1 | 007 | 2122.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | 6423.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | 6423.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | -6423.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | 1024.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 105 | 3849.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 003 | 5967.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 004 | 4200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 001 | 1825.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 2 | 001 | 7034.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 001 | 1216.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 2 | 001 | 1016.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 3 | 105 | 3421.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 118 | 2322.23 | 2322.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6450 | 40557565601 |  | 2 | CPI | 1 | 105 | 2361.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 112 | 2591.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6450 | 40557565201 |  | 2 | CPI | 2 | 112 | 70163.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6450 | 40557565201 |  | 2 | CPI | 3 | 001 | 8960.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 4 | 107 | 3543.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 005 | 1070.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6450 | 40557565601 |  | 2 | CPI | 1 | 003 | 9742.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 005 | 3401.96 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
06 | T6450 | 40557575201 |  | 2 | CPI | 1 | 105 | 1976.27 | 1976.27 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6450 | 40557575201 |  | 2 | CPI | 2 | 005 | 3218.12 | 3218.12 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | 4246.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 1 | 001 | 1387.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565201 |  | 2 | CPI | 2 | 001 | 2497.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565601 |  | 2 | CPI | 1 | 001 | 31063.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565601 |  | 2 | CPI | 2 | 007 | 8524.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557565601 |  | 2 | CPI | 3 | 001 | 9542.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6450 | 40557565601 |  | 2 | CPI | 4 | 007 | 4284.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6450 | 40557585201 |  | 2 | CPI | 1 | 023 | 5550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6456 | 44001315201 |  | 2 | CPI | 1 | 503 | 2115 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6457 | 44018815201 |  | 2 | CPI | 1 | 004 | 9205.18 | 9205.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6459 | 44018015201 |  | 2 | CPI | 1 | 116 | 3985.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6459 | 44018015201 |  | 2 | CPI | 1 | 116 | 6208 | 6208 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
06 | T6459 | 44018625201 |  | 2 | CPI | 1 | 503 | 1217.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6463 | 43791615201 |  | 2 | CPI | 1 | 503 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6463 | 43791615201 |  | 2 | CPI | 2 | 004 | 3917.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6463 | 43791625201 |  | 2 | CPI | 1 | 024 | 4477.31 | 4477.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | 2278.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | 2278.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 2 | 003 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | -2278.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 003 | -4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 003 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | 1877.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 123 | 6775.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 123 | 6775.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 123 | -6775.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | 8785.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 503 | 1039.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 1 | 012 | 6292 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 2 | 007 | 1927.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6464 | 43908815201 |  | 2 | CPI | 3 | 503 | -8785.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 4 | 503 | 8785.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6464 | 43908815201 |  | 2 | CPI | 5 | 123 | 275 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6470 | 43991715201 |  | 2 | CPI | 1 | 007 | 3064.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6470 | 43991715201 |  | 2 | CPI | 2 | 001 | 2147.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6470 | 43991715201 |  | 2 | CPI | 3 | 007 | 1224 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6471 | 43998315201 |  | 2 | CPI | 1 | 001 | 548.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6471 | 44017215201 |  | 2 | CPI | 1 | 112 | 1952.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6471 | 44017315201 |  | 2 | CPI | 1 | 112 | 2675.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6473 | 43326425201 |  | 2 | CPI | 1 | 101 | 663.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6473 | 43326425201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6473 | 43326425201 |  | 2 | CPI | 2 | 101 | 15333.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6473 | 43326425201 |  | 2 | CPI | 1 | 003 | 3861.92 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6473 | 43326425201 |  | 2 | CPI | 1 | 122 | 2319.96 | 257 | 4 |  | N | 0 | Avoidable, In-House CEI | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | T6473 | 43326425201 |  | 2 | CPI | 2 | 001 | 7189.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6474 | 43991915201 |  | 2 | CPI | 1 | 118 | 14701.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6477 | 44297115201 |  | 2 | CPI | 1 | 010 | 4183.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 101 | 3960 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44319715201 |  | 2 | CPI | 1 | 012 | 994.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6477 | 44357015201 |  | 2 | CPI | 1 | 012 | 3874.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 010 | 17552.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 |  | 2 | CPI | 2 | 010 | -17552.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 |  | 2 | CPI | 3 | 010 | 14903.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6477 | 44281315201 |  | 2 | CPI | 4 | 007 | 2648.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6477 | 44281315201 |  | 2 | CPI | 5 | 101 | 3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 101 | -3960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6477 | 44296915201 |  | 2 | CPI | 1 | 007 | 4758.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6477 | 44319715201 |  | 2 | CPI | 1 | 126 | 3090 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
06 | T6477 | 44281315201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6484 | 44017515201 |  | 2 | CPI | 1 | 503 | 4898 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6484 | 44017415201 |  | 2 | CPI | 1 | 001 | 760.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6484 | 44017415201 |  | 2 | CPI | 1 | 105 | 1912.3 | 1912.3 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6484 | 44017515201 |  | 2 | CPI | 1 | 001 | 2315.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6484 | 44017515201 |  | 2 | CPI | 1 | 101 | 251.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6484 | 44017415201 |  | 2 | CPI | 1 | 101 | 2920.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6499 | 43992215201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6499 | 43992215201 |  | 2 | CPI | 1 | 503 | 3079.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6499 | 43992215201 |  | 2 | CPI | 2 | 118 | 2314.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6499 | 43992215201 |  | 2 | CPI | 2 | 001 | 1940.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6499 | 43992215201 |  | 2 | CPI | 3 | 001 | 3236.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6499 | 43992215201 |  | 2 | CPI | 4 | 118 | 2053.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6523 | 42918535201 |  | 2 | CPI | 1 | 001 | 4883.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6523 | 42918535201 |  | 2 | CPI | 1 | 001 | 3970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6523 | 42918535201 |  | 2 | CPI | 1 | 503 | 2232.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6523 | 42918535201 |  | 2 | CPI | 2 | 503 | 2318.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6523 | 42918535201 |  | 2 | CPI | 3 | 001 | 3959.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 007 | 4322.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 101 | 6951.93 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 2 | 007 | 30256.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7K30 | 42450725201 |  | 2 | CPI | 1 | 502 | 2310 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 502 | 39433.12 | 39433.12 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 3 | 502 | 0 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7M31 | 43751715201 |  | 2 | CPI | 4 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M31 | 43751715201 |  | 2 | CPI | 5 | 012 | 10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | -10566.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M31 | 43751715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M35 | 43642115201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 107 | 29274.16 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | E7M35 | 43642115201 |  | 2 | CPI | 2 | 105 | 1218.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 107 | -1328.28 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 107 | 1328.28 | 1328.28 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | E7M35 | 43642115201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 2 |  | N | 30 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | E7M53 | 43878315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M53 | 43878315201 |  | 2 | CPI | 1 | 126 | 48740.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
07 | E7M78 | 43624315201 |  | 2 | CPI | 1 | 119 | 24463.16 | 24463.16 | 1 |  | C | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
07 | E7M78 | 43624315201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 1 |  | C | 24 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
07 | E7M88 | 43751915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M88 | 43751915201 |  | 2 | CPI | 1 | 012 | 18108.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | 11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | 11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 2 | 013 | 10255.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 004 | -11974.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M90 | 43983015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M95 | 43762315201 |  | 2 | CPI | 1 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M95 | 43762315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M95 | 43762315201 |  | 2 | CPI | 1 | 118 | 5930.14 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M95 | 43762315201 |  | 2 | CPI | 2 | 007 | 1897.25 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M95 | 43762315201 |  | 2 | CPI | 3 | 010 | 1070.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7M95 | 43762315201 |  | 2 | CPI | 1 | 012 | 7539.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M97 | 44024515201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M97 | 44024515201 |  | 2 | CPI | 2 | 004 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N03 | 43673425201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N03 | 43673425201 |  | 2 | CPI | 2 | 004 | 9503.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N04 | 44580315201 |  | 2 | CPI | 1 | 503 | 3614.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7N04 | 44580315201 |  | 2 | CPI | 2 | 118 | 7998.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7N06 | 44108415201 |  | 2 | CPI | 1 | 001 | 17137.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7N22 | 41101455201 |  | 2 | CPI | 1 | 003 | 4750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7375 | 25729865201 |  | 2 | CPI | 1 | 208 | 15134.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | No Specification Provided for Work | Specification Modification | 3
07 | T7375 | 25729865201 |  | 2 | CPI | 1 | 115 | 7616.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7375 | 25729865201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7375 | 25729865201 |  | 2 | CPI | 2 | 106 | 0 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7375 | 25729865201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 5 |  | N | 29 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 001 | 24315.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 122 | 4059.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 122 | 2531.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 2 | 112 | 62068.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | -62068.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 2 | 112 | 28651.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | 33416.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7403 | 43484815202 |  | 2 | CPI | 1 | 101 | 22000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 001 | 2636.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7403 | 43484815202 |  | 2 | CPI | 1 | 106 | 8000 | 8000 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7403 | 43484815201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 004 | 4778.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 001 | 15523.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 001 | 2525.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 012 | 4215.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 101 | 20229.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 1 | 101 | 4968.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7406 | 42895715201 |  | 2 | CPI | 2 | 012 | 2282.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 105 | 5875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | 9175 | 3300 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | -9175 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 2 | 009 | 5875 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 4 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 105 | 13844.62 | 13844.62 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7411 | 43982925201 |  | 2 | CPI | 2 | 009 | 3300 | 3300 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7411 | 43982925201 |  | 2 | CPI | 1 | 009 | 0 | 0 | 1 |  | N | 45 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 3 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 012 | 2562.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 108 | 9128.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 001 | 1480.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 001 | 470.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 3 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 012 | 14993.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7413 | 43658815201 |  | 2 | CPI | 2 | 113 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 130 | 40338.27 | 40338.27 | 2 |  | N | 0 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7413 | 43658815201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 2 |  | N | 19 | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
07 | T7414 | 43571915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7414 | 43571915201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7414 | 43571915201 |  | 2 | CPI | 2 | 101 | 7040 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7414 | 43571915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7414 | 43571915201 |  | 2 | CPI | 1 | 101 | 7040 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 923 | 5734.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 012 | 31824.96 | 31824.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7419 | 43050225201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | C | 100 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7420 | 43982945201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7425 | 43982965201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7425 | 43982965201 |  | 2 | CPI | 1 | 012 | 1722.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7425 | 43982965201 |  | 2 | CPI | 1 | 115 | 650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7425 | 43982965201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7425 | 43982965201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7426 | 43648715201 |  | 2 | CPI | 1 | 115 | 7738.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
07 | T7426 | 43648715201 |  | 2 | CPI | 2 | 113 | 3637.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
07 | T7435 | 43731215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7435 | 43731215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7435 | 43731215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7435 | 43731215201 |  | 2 | CPI | 1 | 101 | 15538.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7435 | 43731215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7435 | 43731215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 1 | 106 | 1399.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7436 | 43648515201 |  | 2 | CPI | 1 | 003 | 7606.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 2 | 001 | 2557.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 2 | 001 | 18547.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 3 | 001 | 486.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 4 | 001 | 11512.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 5 | 012 | 2334.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 6 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7436 | 43648515201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 008 | 20000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | R/W Requested Change | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 107 | 3652 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7440 | 44286215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7441 | 43764315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7441 | 43764315201 |  | 2 | CPI | 2 | 117 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7441 | 43764315201 |  | 2 | CPI | 3 | 105 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7441 | 43764315201 |  | 2 | CPI | 4 | 007 | 1658.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7441 | 43764315201 |  | 2 | CPI | 5 | 118 | 11302.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7441 | 43764315201 |  | 2 | CPI | 6 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7452 | 43969915201 |  | 2 | CPI | 1 | 003 | 12698.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7452 | 43969915201 |  | 2 | CPI | 1 | 003 | 11055.77 | 11055.77 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7453 | 44582415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7454 | 44582715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 3066.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 2743.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 2 | 503 | 1381.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8M65 | 40609615201 |  | 2 | CPI | 3 | 012 | 3850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 4 | 012 | 2032.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 5 | 012 | 4231.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 445.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 8767 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 2 | 012 | 942.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 477.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4494.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4945.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 4121.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 2707.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8M65 | 40609615201 |  | 2 | CPI | 1 | 012 | 5764.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 503 | 1386 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 004 | 1894.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 010 | 3306.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8N20 | 42714615201 |  | 2 | CPI | 2 | 007 | 32063 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 105 | 39188.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 001 | 5100.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 021 | 5556.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 105 | 38.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 917 | 5933.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 001 | 6601.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 023 | 911.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 2 | 021 | 7762.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 2 | 023 | 7006.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 503 | 22608.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 022 | 4208.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 |  | 2 | CPI | 2 | 023 | 2736.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 004 | 3659.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N20 | 42714615201 |  | 2 | CPI | 1 | 923 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 024 | 2386.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 022 | 12049.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 3 | 107 | 1692.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 115 | 9578.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 024 | 3300.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 3 | 022 | 2171.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 023 | 1993.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 107 | 4401.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 3 | 107 | 19682.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 917 | 20634.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 107 | 25590.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 3 | 012 | 2892.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 024 | 4162.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 024 | 3133.01 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 023 | 3035.07 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 001 | 7325.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 106 | 3890.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 3 | 106 | 13978.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 001 | 1511.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 024 | 2604.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 2 | 022 | 2476.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 009 | 1530.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 112 | 1024.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N58 | 40610315201 |  | 2 | CPI | 1 | 022 | -1045 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 9857.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 9295.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 5476.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 6578.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 007 | 3038.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 023 | 1412.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 3 | 004 | 1713.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 012 | 6047.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 012 | 1296.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 007 | 4673.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 107 | 28952 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 503 | 25375.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 012 | 5940 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 113 | 15657.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 113 | -0.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 1 | 023 | 4502.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611015201 |  | 2 | CPI | 2 | 023 | 2874.61 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8N75 | 40611025201 |  | 2 | CPI | 1 | 003 | 25801.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N75 | 40611025201 |  | 2 | CPI | 1 | 023 | 3741.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 012 | 3012.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 107 | 15814.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | 8970.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | -8970.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 001 | 2100.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 021 | 2823.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 4 | 023 | 2854.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 5 | 012 | 1191.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 003 | 10825.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 012 | 7840 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 001 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 001 | 1068.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 018 | 19261.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 4 | 018 | 6420.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 023 | 2069.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 2 | 107 | 3090.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 3 | 023 | 12436.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 003 | 56690.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P02 | 40609055201 |  | 2 | CPI | 1 | 018 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 021 | 8272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 503 | 1957.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 021 | 4310.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 6439.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 118 | 13581.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 5288.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 023 | 2184.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 012 | 1019.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 106 | 1834.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 012 | 2303.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 003 | 3453.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 023 | 6376.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 503 | 1099.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 023 | 3986.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 112 | 12956.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 019 | 15740.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 115 | 3871.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 112 | 1485.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 107 | 10966.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 023 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 6382.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 115 | 5387.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 3 | 003 | 4994.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 4 | 106 | 13325.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 105 | 1888.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 2 | 118 | 2640.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
08 | E8P82 | 43715615201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 503 | 4050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 503 | -4050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 2 | 503 | 4107.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 3 | 503 | 10624.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 105 | 8481 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 118 | 1155 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 118 | 1155 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 101 | 31497.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 128 | 6270 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 2 | 128 | 3336.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 1 | 503 | 25129.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 2 | 105 | 8478.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 3 | 503 | 4909.4 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q10 | 43661915201 |  | 2 | CPI | 4 | 101 | 10549 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q10 | 43661915201 |  | 2 | CPI | 5 | 503 | 19129.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 9860.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 54604.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 35140.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q53 | 43516935201 |  | 2 | CPI | 1 | 101 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q53 | 43516935201 |  | 2 | CPI | 2 | 012 | 3085.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516935201 |  | 2 | CPI | 1 | 112 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q53 | 43516915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 1249.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 8374.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 2 | 023 | 2852.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 3 | 023 | 8428.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 4 | 023 | 2133.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 5 | 023 | 1293.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 6 | 023 | 3942.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 1811.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 012 | 70534.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 2 | 021 | 1344.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 3 | 023 | 2002.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 021 | 2009.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 1776.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 2 | 023 | 5675.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 3 | 023 | 4377.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 3191.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 2 | 021 | 2526.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 3 | 023 | 1684.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 4 | 021 | 1098.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 5 | 023 | 732.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 6 | 023 | 2512.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 7 | 023 | 732.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 8 | 023 | 1684.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 9 | 023 | 826.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 023 | 1542.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 2 | 023 | 652.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q85 | 43651735201 |  | 2 | CPI | 1 | 115 | 6517.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q85 | 43651735201 |  | 2 | CPI | 1 | 503 | 5030.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q85 | 43651735201 |  | 2 | CPI | 1 | 105 | 2632 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q85 | 43651715201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 021 | 3230.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 1560.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 3 | 016 | 1685.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
08 | E8Q93 | 42933915201 |  | 2 | CPI | 4 | 023 | 1463.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 101 | 860 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 893.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 3 | 101 | 62396.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 103 | 11760.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 021 | 10606.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 7455.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 023 | 752.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 2567.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 3 | 023 | 10544.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 4 | 023 | 6995.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 5 | 021 | 1545.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 6 | 101 | 3452.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 023 | 1430 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 2035 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 023 | 680.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 2 | 023 | 732.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 3 | 023 | 8982.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 4 | 021 | 1603.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 5 | 023 | 690.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 6 | 021 | 900.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 7 | 101 | 430.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 8 | 101 | 2332.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 9 | 023 | 1430 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q93 | 42933915201 |  | 2 | CPI | 1 | 105 | 985.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 021 | 11873.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 |  | 2 | CPI | 2 | 021 | 13850.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 023 | 12245.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815202 |  | 2 | CPI | 1 | 023 | 9318.67 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 021 | 11108.89 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 021 | 1707.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 3 | 023 | 13071.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 021 | 1912.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 023 | 19853.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q94 | 43947815201 |  | 2 | CPI | 1 | 118 | 8441.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 1 | 118 | 11189.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q94 | 43947915201 |  | 2 | CPI | 2 | 118 | 6082.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 5250.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 2 | 101 | 5013.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 1192.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 1386.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 2 | 503 | 2600.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 34557.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R19 | 43560565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R53 | 44130615201 |  | 2 | CPI | 1 | 101 | 330 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R53 | 44130615201 |  | 2 | CPI | 2 | 101 | 38.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 6531.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 2 | 108 | 1377.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 993 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 2 | 021 | 2681.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 3 | 021 | 5966.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 4 | 021 | 1364.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 5 | 021 | 2229 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 6 | 021 | 3737.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 7 | 021 | 13463.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 4840.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 105 | 24606.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 2 | 021 | 7069.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 6531.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 2 | 021 | 3746.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 13458.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 2 | 115 | 9202.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 3332.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 022 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R58 | 43799115201 |  | 2 | CPI | 1 | 502 | 0 | 0 | 4 |  | N | 3 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 012 | 87443.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 107 | 27366.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R76 | 43945715201 |  | 2 | CPI | 1 | 107 | 10581.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 101 | 1838.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 106 | 1872.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 105 | 4423.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 2 | 106 | 2408.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 106 | 2980.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 106 | 2405.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 2 | 019 | 2411.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8R95 | 43560575201 |  | 2 | CPI | 3 | 106 | 32608.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 4 | 106 | 2937.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 001 | 4435.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R95 | 43560575201 |  | 2 | CPI | 2 | 106 | 20128.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 101 | 2482.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R95 | 43560575201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 001 | 1367.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 2 | 123 | 3401.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 004 | 3270.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 2 | 123 | 952.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 123 | 2108.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 2 | 001 | 8904.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 001 | 1424.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 118 | 420.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 2 | 118 | 1213.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 3 | 118 | 629.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 4 | 001 | 6933.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 5 | 001 | 15743.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 6 | 012 | 1426.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 003 | 6778.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8R96 | 44130915201 |  | 2 | CPI | 1 | 123 | -3401.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 2 | 123 | 3401.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8R96 | 44130915201 |  | 2 | CPI | 3 | 115 | 293.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R99 | 42897115201 |  | 2 | CPI | 1 | 010 | 4163.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R99 | 42897115201 |  | 2 | CPI | 2 | 105 | 4062.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R99 | 42897115201 |  | 2 | CPI | 1 | 023 | 1932.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S01 | 43651635201 |  | 2 | CPI | 1 | 101 | 11164.01 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S01 | 43651615201 |  | 2 | CPI | 1 | 503 | 9310.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S33 | 44261815202 |  | 2 | CPI | 1 | 118 | 2215.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8S33 | 44261815202 |  | 2 | CPI | 1 | 118 | 11460 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8S33 | 44261815202 |  | 2 | CPI | 2 | 101 | 13176.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S33 | 44261815201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P44 | 43797315201 | 924 |  | 22 | 061 | 1 | 0 | N | Unavoidable, No Remedial Action Required
08 | [9 empty] | Unavoidable, No Remedial Action Required
07 | [9 empty] | Unavoidable, No Remedial Action Required
06 | [9 empty] | Unavoidable, No Remedial Action Required
05 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1P87 | 43504015201 | 130 |  | 13 | 008 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | E1P87 | 43504015201 | 503 |  | 33 | 029 | 1 | 4 | N | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R03 | 44021215201 | 924 |  | 34 | 039 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R03 | 44021215201 | 130 |  | 53 | 039 | 2 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | E1R03 | 44021215201 | 010 |  | 16 | 039 | 3 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1R05 | 43629915201 | 001 |  | 72 | 044 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R07 | 19602255201 | 009 |  | 38 | 022 | 1 | 1 | N | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
01 | E1R07 | 19602255201 | 450 |  | 10 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
01 | E1R07 | 19602255201 | 015 |  | 43 | 038 | 1 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 005 |  | 14 | 013 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1R11 | 41066625201 | 015 |  | 10 | 016 | 1 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1R11 | 41066625201 | 115 |  | 20 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R11 | 41066625201 | 106 |  | 10 | 067 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R11 | 41066625201 | 106 |  | 6 | 069 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R78 | 43502915201 | 924 |  | 49 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R79 | 43806215201 | 120 |  | 24 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
01 | E1R79 | 43806215201 | 106 |  | 3 | 013 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R79 | 43806215201 | 924 |  | 14 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R79 | 43806215201 | 924 |  | 15 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1R81 | 43528615201 | 005 |  | 40 | 002 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1R86 | 44108815201 | 924 |  | 43 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
01 | T1719 | 43800915201 | 924 |  | 30 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
01 | T1746 | 43801415201 | 130 |  | 8 | 015 | 1 | 4 | N | Avoidable, In-House CEI | Indecision/Delayed Response | Plan Modifications | 2
01 | T1767 | 44068115201 | 924 |  | 15 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2V62 | 43742915201 | 924 |  | 17 | 041 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
02 | E2V62 | 43742915201 | 012 |  | 7 | 042 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V62 | 43742915201 | 012 |  | 33 | 043 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X06 | 43076015201 | 005 |  | 22 | 011 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 30 | 014 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 42 | 016 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 28 | 020 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 005 |  | 16 | 023 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | E2X06 | 43076015201 | 023 |  | 15 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | E2X64 | 20964255201 | 106 |  | 19 | 022 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2X65 | 43239615201 | 118 |  | 30 | 032 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2X65 | 43239615201 | 005 |  | 27 | 038 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2660 | 43607715201 | 019 |  | 11 | 057 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2706 | 42879615201 | 106 |  | 1 | 015 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2706 | 42879615201 | 015 |  | 1 | 015 | 2 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2706 | 42879615201 | 106 |  | 1 | 015 | 3 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2706 | 42879615201 | 021 |  | 8 | 015 | 4 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2706 | 42879615201 | 015 |  | 1 | 021 | 1 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2706 | 42879615201 | 115 |  | 33 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 115 |  | 59 | 034 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2706 | 42879615201 | 106 |  | 2 | 035 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2726 | 43583715201 | 005 |  | 18 | 018 | 1 | 5 | C | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2726 | 43583715201 | 325 |  | 14 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
02 | T2726 | 43583715201 | 106 |  | 12 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2737 | 43433315201 | 128 |  | 2 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2737 | 43433315201 | 103 |  | 4 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | E3O87 | 42820825201 | 106 |  | 47 | 013 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3O87 | 42820825201 | 115 |  | 14 | 024 | 1 | 1 | N | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | E3O87 | 42820825201 | 118 |  | 12 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | E3R03 | 41343525201 | 005 |  | 38 | 009 | 1 | 1 | C | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
03 | E3R03 | 41343525201 | 005 |  | -4 | 012 | 1 | 1 | C | Avoidable, Design Consultant | Utility Adjustments | Utility Delays | 11
03 | E3R72 | 43255415201 | 106 |  | 1 | 021 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | E3R72 | 43255415201 | 130 |  | 4 | 022 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
03 | E3T19 | 4453861K201 | 922 |  | 14 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | E3T19 | 4453861K201 | 924 |  | 14 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | T3287 | 22044245201 | 106 |  | 20 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3287 | 22044245201 | 106 |  | 22 | 071 | 1 | 1 | C | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3585 | 43228515201 | 503 |  | 30 | 014 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3585 | 43228515201 | 126 |  | 16 | 019 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3585 | 43228515201 | 128 |  | 2 | 020 | 1 | 2 | N | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3585 | 43228515201 | 503 |  | 12 | 021 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3585 | 43228515201 | 126 |  | 8 | 023 | 1 | 1 | N | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
03 | T3619 | 43390215201 | 016 |  | 10 | 012 | 1 | 2 | N | Avoidable, In-House Designer | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | T3619 | 43390215201 | 130 |  | 15 | 013 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
03 | T3627 | 43228915201 | 001 |  | 10 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3659 | 43728425201 | 503 |  | 3 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3659 | 43728425201 | 503 |  | 14 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3659 | 43728425201 | 503 |  | 10 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3663 | 43188345201 | 003 |  | 2 | 004 | 1 | 2 | N | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3663 | 43188345201 | 128 |  | 3 | 007 | 1 | 1 | N | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
03 | T3663 | 43188345201 | 012 |  | 10 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3695 | 43775415201 | 503 |  | 40 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3708 | 43662015201 | 115 |  | 20 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3732 | 44172515201 | 107 |  | 7 | 008 | 1 | 1 | N | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
03 | T3739 | 44173715201 | 503 |  | 4 | 002 | 1 | 2 | N | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T9021 | 44531225216 | 016 |  | 16 | 006 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 1 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 1 | 062 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 1 | 073 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 1 | 093 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 48 | 117 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 2 | 121 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4M90 | 41242035201 | 018 |  | 3 | 127 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
04 | E4T46 | 43388815201 | 105 |  | 40 | 015 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T46 | 43388815201 | 924 |  | 45 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4T54 | 42957525201 | 005 |  | 15 | 010 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 924 |  | 35 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 924 |  | 17 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T54 | 42957525201 | 118 |  | 5 | 017 | 1 | 5 | N | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T56 | 43578125201 | 005 |  | 12 | 014 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T56 | 43578125201 | 001 |  | 10 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T56 | 43578125201 | 022 |  | 12 | 019 | 1 | 5 | N | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | E4T86 | 44061215201 | 924 |  | 28 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T89 | 43214615201 | 924 |  | 12 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4462 | 43232315203 | 106 |  | 6 | 053 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4473 | 42751615201 | 023 |  | 6 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4473 | 42751615201 | 023 |  | 6 | 039 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4479 | 43059025201 | 924 |  | 52 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4483 | 44008115201 | 019 |  | 30 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4485 | 43634115201 | 924 |  | 53 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4496 | 43288335201 | 005 |  | 12 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4499 | 44055425201 | 112 |  | 10 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4500 | 43435915201 | 924 |  | 35 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 022 |  | 20 | 041 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 924 |  | 11 | 042 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4501 | 43468615201 | 022 |  | 9 | 043 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4503 | 43611115201 | 106 |  | 13 | 015 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4503 | 43611115201 | 009 |  | 14 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
04 | T4503 | 43611115201 | 108 |  | 12 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4506 | 43783215201 | 503 |  | 27 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4513 | 43770815201 | 924 |  | 52 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4518 | 43829115201 | 003 |  | 30 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4520 | 43770215201 | 924 |  | 27 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4534 | 43654115201 | 924 |  | 29 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
4 | T4534 | 43654115201 | 922 |  | 23 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
4 | T4534 | 43654115201 | 105 |  | 16 | 21 | 1 | 1 | N | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
5 | E50A4 | 43754315201 | 924 |  | 25 | 11 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
5 | E5Z46 | 44116815201 | 401 |  | 19 | 30 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
5 | E5Z68 | 44096915201 | 105 |  | 3 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
5 | E5Z68 | 44096915201 | 12 |  | 4 | 22 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
5 | E5Z68 | 44096915201 | 130 |  | 15 | 25 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
5 | T5629 | 43759215201 | 4 |  | 42 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | E6K57 | 43854015201 | 924 |  | 65 | 45 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
6 | E6M59 | 43634425201 | 401 |  | 9 | 2 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
6 | T6425 | 42597925201 | 12 |  | 30 | 33 | 1 | 1 | N | Avoidable, Design Consultant | Material Shortage | Material Shortage | 12
6 | T6457 | 44018415201 | 9 |  | 45 | 19 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
6 | T6459 | 44018715201 | 924 |  | 30 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
6 | T6464 | 43908815201 | 924 |  | 27 | 22 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
6 | T6484 | 44017515201 | 924 |  | 31 | 13 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
7 | E7M74 | 43955115201 | 925 |  | 2 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
7 | E7N20 | 25693135201 | 924 |  | 4 | 8 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
7 | E7N20 | 25693135201 | 130 |  | 3 | 9 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7420 | 43982945201 | 924 |  | 18 | 16 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7420 | 43982945201 | 924 |  | 17 | 18 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7431 | 41685615201 | 924 |  | 6 | 12 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7431 | 41685615201 | 924 |  | 15 | 15 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7431 | 41685615201 | 925 |  | 10 | 17 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7452 | 43969915201 | 924 |  | 26 | 3 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
7 | T7452 | 43969915201 | 5 |  | 12 | 6 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
7 | T7452 | 43969915201 | 5 |  | 4 | 7 | 1 | 5 | N | Avoidable, Third Party | Indecision/Delayed Response | Plan Modifications | 2
8 | E8M65 | 40609615201 | 503 |  | 405 | 125 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8N20 | 42714615201 | 923 |  | 132 | 113 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8P82 | 43715615201 | 503 |  | 22 | 62 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q10 | 43661915201 | 503 |  | 272 | 40 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q94 | 43947815201 | 503 |  | 1 | 6 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q94 | 43947815201 | 503 |  | 1 | 14 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
8 | E8Q94 | 43947815201 | 503 |  | 5 | 53 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1665 | 43545015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 225 | 360 | 425 | -65 | 65 | 0 | 36 | 99 | 1995871 | 0 | 1995871 | 2060794 | 2106268 | -99792 | 0 | -99792 | 2006476 | 2010824 | 4348 | 64923 | 11 | 0 | 10 | 6687 | 0 | 0 | 0 | 2174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 54642 | 54642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1419 | 1419 | 0 | 0 | 0 | 0 | 0 | 99 | 64923 | 56062 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-27 | QTR4 | 20/21 | 2019-01-04 | QTR3 | 18/19 | 115 | 2185570.99 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 25 | 01co | 1 | 25
01CO | 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 1353 | 15508 | 22 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 22 | 01do | 26 | 47
01CO | 01 | T1675 | 43088715201 | 2017-08-30 | QTR1 | 17/18 | 3 | 3 | 150 | 282 | 282 | 0 | 0 | 0 | 57 | 75 | 815194 | 35094 | 780100 | 856566 | 821472 | 0 | 0 | 0 | 821472 | 822481 | 1009 | 41372 | 36 | 0 | 0 | -1090 | 868 | 0 | 72 | 48111 | 30784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -5649 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 41372 | 31652 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 | 2019-03-21 | QTR3 | 18/19 | 113 | 783433.16 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 28 | 02co | 48 | 75
01CO | 01 | T1702 | 43509015201 | 2018-02-28 | QTR3 | 17/18 | 2 | 2 | 240 | 285 | 282 | 3 | 0 | 0 | 45 | 0 | 2098354 | 50000 | 2048354 | 2203054 | 2035840 | 0 | 0 | 0 | 2035840 | 2034275 | -1565 | 104700 | 29 | 0 | 0 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104700 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-06 | QTR2 | 20/21 | 2019-04-29 | QTR4 | 18/19 | 115 | 2050385.52 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 14 | 02do | 76 | 89
01CO | 01 | T1712 | 43355025201 | 2018-04-25 | QTR4 | 17/18 | 1 | 1 | 390 | 460 | 459 | 1 | 0 | 0 | 63 | 7 | 5536538 | 50000 | 5486538 | 5542551 | 5605616 | 0 | 200000 | 200000 | 5805616 | 5601941 | -197662 | 6013 | 40 | 0 | 0 | 15589 | 0 | 0 | 7 | 12866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 28455 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 | 2019-11-15 | QTR2 | 19/20 | 115 | 5608551.81 | B10 | ACC - BONUS/INCENT/DISINCENT | 7 | 23 | 0 | 0 | 0 | 0 |  | CO | 22 | 03co | 90 | 111
01CO | 01 | T1718 | 44011815201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 135 | 199 | 198 | 1 | 0 | 0 | 64 | 0 | 440982 | 24215 | 416767 | 440982 | 416149 | 0 | 0 | 0 | 416149 | 416078 | -71 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-02-15 | QTR3 | 20/21 | 2019-10-02 | QTR2 | 19/20 | 115 | 501429.8 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO | 21 | 03do | 112 | 132
01CO | 01 | T1719 | 43800915201 | 2019-06-12 | QTR4 | 18/19 | 2 | 2 | 250 | 345 | 339 | 6 | 0 | 0 | 94 | 1 | 4444444 | 50000 | 4394444 | 4440169 | 4492709 | 0 | 0 | 0 | 4492709 | 4400827 | -91882 | -4276 | 78 | 0 | 1 | 30594 | 0 | 0 | 0 | 9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 32083 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-10 | QTR4 | 20/21 | 2020-12-16 | QTR2 | 20/21 | 108 | 4966062.8 |  |  | 1 | 16 | 0 | 0 | 0 | 0 |  | CO | 35 | 04co | 133 | 167
01CO | 01 | T1720 | 43655115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 200 | 419 | 415 | 4 | 0 | 0 | 81 | 138 | 4987470 | 50000 | 4937470 | 5081049 | 5094971 | 0 | 0 | 0 | 5094971 | 5026709 | -68262 | 93578 | 58 | 0 | 0 | 7545 | 0 | 0 | 138 | 101101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 116681 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-06-15 | QTR4 | 20/21 | 2021-02-23 | QTR3 | 20/21 | 115 | 5203469.32 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 20 | 04do | 168 | 187
01CO | 01 | T1721 | 43955515201 | 2019-03-27 | QTR3 | 18/19 | 2 | 3 | 300 | 402 | 402 | 0 | 0 | 0 | 102 | 0 | 4793304 | 54777 | 4738527 | 4836240 | 4588281 | 0 | 0 | 0 | 4588281 | 4543144 | -45137 | 42936 | 70 | 0 | 0 | 66835 | 0 | 0 | 0 | 6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25510 | 25510 | 0 | 0 | 0 | 0 | 0 | 0 | 49718 | 25510 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 | 2020-09-30 | QTR1 | 20/21 | 113 | 5287557.25 |  |  | 0 | 32 | 0 | 0 | -49409 | 0 |  | CO | 22 | 05co | 188 | 209
01CO | 01 | T1722 | 43806015201 | 2019-04-24 | QTR4 | 18/19 | 3 | 5 | 400 | 457 | 457 | 0 | 0 | 0 | 57 | 0 | 11567352 | 137224 | 11430128 | 11561213 | 11392803 | 0 | 0 | 0 | 11392803 | 11280748 | -95187 | -6139 | 24 | 0 | 0 | -6793 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550 | 0 | 0 | 0 | 5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4047 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 | 2020-10-09 | QTR2 | 20/21 | 118 | 13570915.56 |  |  | 0 | 33 | 0 | 0 | -23265 | 0 | T | CO | 23 | 05do | 210 | 232
01CO | 01 | T1731 | 44012015201 | 2018-12-05 | QTR2 | 18/19 | 2 | 1 | 200 | 268 | 293 | -25 | 25 | 0 | 34 | 34 | 800698 | 46403 | 754295 | 822869 | 716288 | -41625 | 0 | -41625 | 674663 | 674668 | 5 | 22171 | 11 | 0 | 29 | 12897 | 2231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 22171 | 2231 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-02-24 | QTR3 | 20/21 | 2020-03-31 | QTR3 | 19/20 | 115 | 965767.02 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 22 | 06co | 233 | 254
01CO | 01 | T1742 | 43539015201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 350 | 433 | 402 | 31 | 0 | 0 | 83 | 0 | 3732644 | 50000 | 3682644 | 3755256 | 3738358 | 0 | 0 | 0 | 3738358 | 3735826 | -2532 | 22611 | 53 | 0 | 0 | 24777 | 12441 | 0 | 0 | 44641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69418 | 12441 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2020-12-21 | QTR2 | 20/21 | 2020-10-30 | QTR2 | 20/21 | 113 | 3397781.79 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO | 11 | 06do | 255 | 265
01CO | 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2100 | 10 | 0 | 3 | 4793 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6893 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 21 | 07co | 266 | 286
01CO | 01 | T1746 | 43801415201 | 2019-03-27 | QTR3 | 18/19 | 2 | 1 | 200 | 283 | 283 | 0 | 0 | 0 | 72 | 11 | 3284806 | 50000 | 3234806 | 3448596 | 3473733 | -10000 | 0 | -10000 | 3463733 | 3433178 | -30555 | 163791 | 43 | 0 | 2 | 8167 | 0 | 8 | 0 | 3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 163791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11 | 175805 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 108 | 4171539.82 |  |  | 2 | 21 | 0 | 0 | 0 | 0 |  | CO | 22 | 07do | 287 | 308
01CO | 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 3200 | 16 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 309 | 308
01CO | 01 | T1750 | 44385115201 | 2019-08-28 | QTR1 | 19/20 | 2 | 1 | 165 | 233 | 233 | 0 | 0 | 0 | 36 | 32 | 2676999 | 50000 | 2626999 | 2703686 | 2688376 | 0 | 0 | 0 | 2688376 | 2686495 | -1882 | 26687 | 27 | 0 | 32 | 31861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 31861 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-02-03 | QTR3 | 20/21 | 2020-09-14 | QTR1 | 20/21 | 108 | 2027464.68 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 23 | 08do | 309 | 331
01CO | 01 | T1752 | 43942315201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 250 | 299 | 296 | 3 | 0 | 0 | 49 | 0 | 3291059 | 50000 | 3241059 | 3259973 | 3120660 | 0 | 0 | 0 | 3120660 | 3033429 | -87231 | -31087 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31087 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-06-28 | QTR4 | 20/21 | 2021-03-15 | QTR3 | 20/21 | 115 | 3526242.99 |  |  | 0 | 23 | 0 | 0 | -31087 | 0 |  | CO
01CO | 01 | T1756 | 43511415201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 150 | 234 | 234 | 0 | 0 | 0 | 16 | 68 | 1037000 | 0 | 1037000 | 1084886 | 1084886 | 0 | 0 | 0 | 1084886 | 1084595 | -291 | 47886 | 10 | 0 | 0 | 20000 | 0 | 0 | 68 | 27886 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 47886 | 1076 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 | 2020-09-02 | QTR1 | 20/21 | 113 | 1002063.72 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1758 | 43943715201 | 2019-07-31 | QTR1 | 19/20 | 2 | 2 | 265 | 288 | 219 | 69 | 0 | 0 | 22 | 1 | 7004551 | 95304 | 6909247 | 7119832 | 7259276 | 0 | 0 | 0 | 7259276 | 7106733 | -152543 | 115281 | 17 | 0 | 1 | 114321 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 115281 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-08-10 | QTR1 | 20/21 | 108 | 9375095.25 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1759 | 44067015201 | 2019-07-31 | QTR1 | 19/20 | 2 | 1 | 125 | 183 | 183 | 0 | 0 | 0 | 58 | 0 | 1338165 | 49310 | 1288855 | 1328365 | 1305338 | 0 | 0 | 0 | 1305338 | 1305118 | -220 | -9800 | 49 | 0 | 0 | 19798 | 0 | 0 | 0 | 6314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16312 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-01-13 | QTR3 | 20/21 | 2020-10-26 | QTR2 | 20/21 | 113 | 1044391.47 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1767 | 44068115201 | 2019-07-31 | QTR1 | 19/20 | 2 | 0 | 79 | 105 | 105 | 0 | 0 | 0 | 26 | 0 | 561733 | 20351 | 541382 | 561733 | 545876 | 0 | 0 | 0 | 545876 | 545876 | 0 | 0 | 23 | 0 | 0 | 1036 | 0 | 0 | 0 | 3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4632 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 | 2020-07-15 | QTR1 | 20/21 | 115 | 444415.31 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1773 | 44067215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 75 | 83 | 70 | 13 | 0 | 0 | 8 | 0 | 214731 | 9756 | 204975 | 214731 | 194639 | 0 | 0 | 0 | 194639 | 194639 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-08-21 | QTR1 | 20/21 | 108 | 215733.31 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1776 | 43535815201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 50 | 67 | 65 | 2 | 0 | 0 | 17 | 0 | 140340 | 0 | 140340 | 140340 | 140340 | 0 | 0 | 0 | 140340 | 140340 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-18 | QTR4 | 20/21 | 2021-03-09 | QTR3 | 20/21 | 113 | 104699.84 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1779 | 43808615201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 103 | 103 | 0 | 0 | 0 | 3 | 0 | 905000 | 0 | 905000 | 905000 | 904754 | 0 | 0 | 0 | 904754 | 904754 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F454013430 | MSB SERVICES LLC | N/A | N/A | N/A | N/A | 2021-06-02 | QTR4 | 20/21 | 2021-05-07 | QTR4 | 20/21 | 115 | 658934.61 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1997 | 40828665201 | 2017-01-25 | QTR3 | 16/17 | 2 | 11 | 1100 | 1215 | 1201 | 14 | 0 | 0 | 115 | 0 | 58011809 | 150000 | 57861809 | 58671616 | 58073269 | 0 | 0 | 0 | 58073269 | 59258196 | 1257928 | 659807 | 51 | 0 | 0 | 424487 | 0 | 0 | 0 | 340095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652410 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 | 2020-08-13 | QTR1 | 20/21 | 118 | 69879385.2 |  |  | 0 | 64 | 0 | 0 | -143938 | 0 |  | CO
01DO | 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 355643 | 83 | 0 | 200 | 49249 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 429619 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P46 | 43580715201 | 2017-10-19 | QTR2 | 17/18 | 1 | 1 | 125 | 209 | 209 | 0 | 0 | 0 | 84 | 0 | 869954 | 43581 | 826373 | 869954 | 834474 | 0 | 0 | 0 | 834474 | 836068 | 1595 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2018-07-30 | QTR1 | 18/19 | 108 | 794913.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P87 | 43504015201 | 2017-04-20 | QTR4 | 16/17 | 1 | 6 | 175 | 654 | 654 | 0 | 0 | 0 | 132 | 347 | 2037254 | 50000 | 1987254 | 2546460 | 2602954 | 0 | 0 | 0 | 2602954 | 2606824 | 3870 | 509206 | 44 | 0 | 98 | 114422 | 91269 | 13 | 249 | 352422 | 200403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 37265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 347 | 509206 | 291672 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-04-13 | QTR4 | 20/21 | 2019-08-05 | QTR1 | 19/20 | 113 | 2970496.06 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R03 | 44021215201 | 2018-01-03 | QTR3 | 17/18 | 1 | 4 | 498 | 897 | 897 | 0 | 0 | 0 | 279 | 120 | 1441171 | 50000 | 1391171 | 1857076 | 1804938 | 0 | 0 | 0 | 1804938 | 1804938 | 0 | 415905 | 118 | 0 | 120 | 415905 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 120 | 415905 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-03-03 | QTR3 | 20/21 | 2020-08-28 | QTR1 | 20/21 | 113 | 1515907.88 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 58 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R05 | 43629915201 | 2018-03-01 | QTR3 | 17/18 | 1 | 9 | 320 | 663 | 663 | 0 | 0 | 0 | 183 | 160 | 7996438 | 89923 | 7906515 | 8606992 | 8773391 | 0 | 0 | 0 | 8773391 | 8748736 | -916 | 610555 | 76 | 72 | 159 | 583162 | 0 | 0 | 1 | 13293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 160 | 596455 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2020-11-12 | QTR2 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 115 | 8160370.04 | B5 | ACC - INCENTIVE/DISINCENTIVE | 1 | 35 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | -259 | 29714 | 51 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R07 | 19602255201 | 2018-06-14 | QTR4 | 17/18 | 3 | 9 | 380 | 716 | 746 | -30 | 30 | 0 | 213 | 123 | 4989441 | 0 | 4989441 | 5299029 | 4998104 | -64274 | -150000 | -214274 | 4783829 | 4757758 | -26072 | 309588 | 81 | 81 | 0 | 67703 | 40859 | 0 | 34 | 133445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 43418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 50 | 244566 | 40859 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-04-28 | QTR4 | 20/21 | 2020-11-06 | QTR2 | 20/21 | 115 | 4839623.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R08 | 43526515201 | 2018-05-17 | QTR4 | 17/18 | 1 | 1 | 225 | 342 | 341 | 1 | 0 | 0 | 117 | 0 | 1717172 | 50000 | 1667172 | 1717172 | 1457666 | 0 | 0 | 0 | 1457666 | 1601560 | 143895 | 0 | 102 | 0 | 0 | 1432 | 0 | 0 | 0 | 2731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 | 2019-12-17 | QTR2 | 19/20 | 113 | 2389311.47 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R11 | 41066625201 | 2018-06-14 | QTR4 | 17/18 | 3 | 12 | 574 | 772 | 710 | 62 | 0 | 0 | 184 | 14 | 20022782 | 150000 | 19872782 | 20456986 | 19822369 | 0 | 0 | 0 | 19822369 | 19631063 | -127528 | 434204 | 76 | 10 | 14 | 383963 | 16731 | 36 | 0 | 116041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 501902 | 16731 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 | 2020-12-21 | QTR2 | 20/21 | 108 | 22152761.07 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 48 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R39 | 43802415201 | 2018-10-18 | QTR2 | 18/19 | 1 | 1 | 200 | 279 | 275 | 4 | 0 | 0 | 77 | 2 | 2883484 | 50000 | 2833484 | 2929980 | 2732452 | 0 | 0 | 0 | 2732452 | 2828698 | 96246 | 46496 | 67 | 0 | 2 | 13860 | 0 | 0 | 0 | 46496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 60356 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 | 2019-11-20 | QTR2 | 19/20 | 108 | 3497647.15 |  |  | 2 | 10 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R62 | 43795815201 | 2018-08-16 | QTR1 | 18/19 | 1 | 1 | 147 | 263 | 263 | 0 | 0 | 0 | 91 | 25 | 1959744 | 50000 | 1909744 | 2208518 | 2188843 | 0 | 0 | 0 | 2188843 | 2188837 | -6 | 248774 | 64 | 0 | 25 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248774 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 | 2020-01-15 | QTR3 | 19/20 | 113 | 2795997.92 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R64 | 42584125201 | 2019-01-24 | QTR3 | 18/19 | 1 | 7 | 378 | 498 | 395 | 103 | 0 | 0 | 82 | 38 | 22161010 | 150000 | 22011010 | 23160665 | 22864939 | 0 | 0 | 0 | 22864939 | 22869487 | 7885 | 999656 | 64 | 0 | 38 | 590493 | 0 | 0 | 0 | 149445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1038401 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 | 2020-10-16 | QTR2 | 20/21 | 113 | 21356227.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R78 | 43502915201 | 2019-03-21 | QTR3 | 18/19 | 1 | 0 | 100 | 164 | 166 | -2 | 2 | 0 | 64 | 0 | 982956 | 35636 | 947320 | 982956 | 953745 | -3330 | 0 | -3330 | 950415 | 950415 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-10-19 | QTR2 | 20/21 | 2020-06-07 | QTR4 | 19/20 | 113 | 837254.07 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R79 | 43806215201 | 2019-02-21 | QTR3 | 18/19 | 1 | 4 | 300 | 457 | 422 | 35 | 0 | 0 | 118 | 39 | 6263696 | 61307 | 6202389 | 6369605 | 6356261 | 0 | 0 | 0 | 6356261 | 6267065 | -89196 | 105909 | 58 | 0 | 3 | 55425 | 0 | 27 | 36 | 130411 | 81997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 39 | 111348 | 81997 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 | 2020-12-14 | QTR2 | 20/21 | 115 | 6188091.23 |  |  | 0 | 33 | 0 | 0 | -74488 | 0 |  | DO
01DO | 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 1845 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R86 | 44108815201 | 2018-11-09 | QTR2 | 18/19 | 1 | 0 | 370 | 470 | 470 | 0 | 0 | 0 | 76 | 24 | 2469000 | 50000 | 2419000 | 2469000 | 2431659 | 0 | 0 | 0 | 2431659 | 2431659 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12659 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 113 | 3306921.72 | A3 | ICC - DESIGN/BUILD - MINOR | 24 | 27 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S13 | 44462715201 | 2020-01-16 | QTR3 | 19/20 | 1 | 1 | 130 | 168 | 130 | 38 | 0 | 0 | 36 | 2 | 993513 | 50000 | 943513 | 994797 | 930694 | 0 | 0 | 0 | 930694 | 928776 | -1919 | 1285 | 27 | 0 | 0 | 3447 | 0 | 0 | 2 | 13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 17405 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-10-01 | QTR2 | 20/21 | 108 | 1140044.02 |  |  | 2 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S47 | 43997015201 | 2020-01-16 | QTR3 | 19/20 | 1 | 0 | 100 | 125 | 89 | 36 | 0 | 0 | 25 | 0 | 450312 | 27504 | 422808 | 450312 | 440733 | 0 | 0 | 0 | 440733 | 440733 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 115 | 480716.09 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S48 | 44005515201 | 2020-02-20 | QTR3 | 19/20 | 1 | 2 | 200 | 240 | 232 | 8 | 0 | 0 | 40 | 0 | 2577917 | 50000 | 2527917 | 2631610 | 2504928 | 0 | 150000 | 150000 | 2654928 | 2504928 | -150000 | 53693 | 21 | 0 | 0 | 9324 | 0 | 0 | 0 | 53693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63017 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 | 2021-02-08 | QTR3 | 20/21 | 118 | 2532689.82 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S50 | 44525715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 0 | 45 | 53 | 51 | 2 | 0 | 0 | 8 | 0 | 279624 | 14400 | 265224 | 279624 | 287046 | 0 | 0 | 0 | 287046 | 287046 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 | 2020-07-30 | QTR1 | 20/21 | 108 | 268843.45 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2660 | 43607715201 | 2017-12-06 | QTR2 | 17/18 | 3 | 3 | 700 | 1072 | 1070 | 2 | 0 | 0 | 362 | 10 | 25775068 | 150000 | 25625068 | 25930204 | 26452915 | 0 | 0 | 0 | 26452915 | 26446407 | -6508 | 155136 | 207 | 11 | 7 | 52750 | 0 | 0 | 0 | 67478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 11 | 10 | 273866 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 | 2021-02-26 | QTR3 | 20/21 | 208 | 25496503.99 |  |  | 10 | 144 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 60614 | 12839 | 39 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28 |  |  | 18 | 74 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2690 | 42880715201 | 2018-02-28 | QTR3 | 17/18 | 1 | 0 | 445 | 649 | 612 | 37 | 0 | 0 | 174 | 30 | 7990153 | 93100 | 7897053 | 7990153 | 7911166 | 0 | 0 | 0 | 7911166 | 8230419 | 319253 | 0 | 60 | 0 | 0 | 13185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 40654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 16789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 70627 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-03-18 | QTR3 | 20/21 | 2020-02-24 | QTR3 | 19/20 | 208 | 8670416 |  |  | 30 | 114 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 100000 | 78 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17 |  |  | 30 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2706 | 42879615201 | 2018-02-28 | QTR3 | 17/18 | 2 | 5 | 300 | 499 | 488 | 11 | 0 | 0 | 190 | 9 | 7792915 | 80790 | 7712125 | 8443153 | 8718430 | 0 | 0 | 0 | 8718430 | 8716846 | -1584 | 650238 | 46 | 2 | 5 | 33906 | 0 | 96 | 2 | 122684 | 3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 475000 | 0 | 2 | 15735 | 15735 | 0 | 0 | 0 | 0 | 106 | 9 | 647325 | 494380 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 | 2019-11-15 | QTR2 | 19/20 | 208 | 7769629.39 |  |  | 7 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 42749 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2713 | 43613525201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 220 | 271 | 271 | 0 | 0 | 0 | 40 | 11 | 1975147 | 50000 | 1925147 | 1975147 | 1947179 | 0 | 0 | 0 | 1947179 | 1945873 | -1305 | 0 | 29 | 0 | 11 | 23153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 23153 | 0 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 | 2019-09-30 | QTR1 | 19/20 | 208 | 1272155.66 |  |  | 11 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2716 | 43763015201 | 2018-09-26 | QTR1 | 18/19 | 1 | 0 | 600 | 675 | 627 | 48 | 0 | 0 | 75 | 0 | 4888889 | 53430 | 4835459 | 4888889 | 4688077 | 0 | 0 | 0 | 4688077 | 4687157 | -920 | 0 | 34 | 0 | 0 | 23805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31225 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-03 | QTR4 | 20/21 | 2020-12-22 | QTR2 | 20/21 | 216 | 5384748.68 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 0 | 0 | 1 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 0 | 33 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 579 | 100000 | 13 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | -3801 | 80075 | 21 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2729 | 43499715201 | 2019-02-27 | QTR3 | 18/19 | 2 | 0 | 180 | 285 | 284 | 1 | 0 | 0 | 51 | 54 | 2001734 | 50000 | 1951734 | 2001734 | 1943094 | 0 | 0 | 0 | 1943094 | 1943094 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 | 2020-06-06 | QTR4 | 19/20 | 209 | 2294575.66 |  |  | 54 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2731 | 43617915201 | 2019-02-27 | QTR3 | 18/19 | 1 | 1 | 300 | 355 | 353 | 2 | 0 | 0 | 51 | 4 | 4898898 | 57023 | 4841876 | 4948898 | 4982985 | 0 | 0 | 0 | 4982985 | 4949350 | -33636 | 50000 | 28 | 0 | 0 | 15868 | 0 | 0 | 4 | 72023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 88330 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 | 2020-07-08 | QTR1 | 20/21 | 214 | 5966985.97 |  |  | 4 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2735 | 44119515201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 100 | 142 | 142 | 0 | 0 | 0 | 13 | 29 | 421053 | 19914 | 401139 | 421053 | 394439 | 0 | 0 | 0 | 394439 | 394439 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-12-08 | QTR2 | 20/21 | 2020-05-26 | QTR4 | 19/20 | 208 | 428177.97 |  |  | 29 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2737 | 43433315201 | 2019-04-24 | QTR4 | 18/19 | 2 | 2 | 300 | 365 | 295 | 70 | 0 | 0 | 63 | 2 | 2819291 | 50000 | 2769291 | 2969291 | 2939393 | 0 | 0 | 0 | 2939393 | 2937611 | -1782 | 150000 | 22 | 0 | 2 | 54696 | 0 | 6 | 0 | 81150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 136986 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | QTR3 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 208 | 1924121.6 |  |  | 2 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2019-11-01 | QTR2 | 19/20 | 209 | 84351.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95 |  |  | 2 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2747 | 43934815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 210 | 268 | 261 | 7 | 0 | 0 | 58 | 0 | 5571370 | 66973 | 5504397 | 5571370 | 5579362 | 0 | 0 | 0 | 5579362 | 5469678 | -109684 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 | 2020-07-29 | QTR1 | 20/21 | 216 | 6661155.86 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2748 | 43911615201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 225 | 255 | 254 | 1 | 0 | 0 | 30 | 0 | 4749617 | 58060 | 4691557 | 4779617 | 4835839 | 0 | 0 | 0 | 4835839 | 4774010 | -61829 | 30000 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 31084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31084 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-02 | QTR4 | 20/21 | 2020-09-15 | QTR1 | 20/21 | 214 | 5777785.83 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 2 | 1 | 600 | 684 | 525 | 159 | 0 | 0 | 96 | 0 | 11950705 | 126323 | 11824382 | 12017028 | 7108680 | 0 | 0 | 0 | 7108680 | 7101059 | -7620 | 66323 | 64 | 0 | 0 | 3314 | 0 | 0 | 0 | 35690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44977 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 |  | QTR2 | 00/01 | 208 | 11844644.47 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2750 | 43908015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 130 | 148 | 145 | 3 | 0 | 0 | 18 | 0 | 1515900 | 50000 | 1465900 | 1515900 | 1353861 | 0 | 0 | 0 | 1353861 | 1345218 | -8642 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 | 2020-05-29 | QTR4 | 19/20 | 216 | 1652876.26 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2761 | 43934515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 180 | 215 | 211 | 4 | 0 | 0 | 35 | 0 | 4189603 | 51877 | 4137726 | 4189603 | 4189658 | 0 | 0 | 0 | 4189658 | 4163139 | -26519 | 0 | 30 | 0 | 0 | 4541 | 0 | 0 | 0 | 1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6304 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-08-24 | QTR1 | 20/21 | 214 | 5262360.58 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2764 | 44140615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 209 | 205 | 4 | 0 | 0 | 27 | 2 | 954146 | 50000 | 904146 | 954146 | 884664 | 0 | 0 | 0 | 884664 | 884785 | 121 | 0 | 9 | 0 | 2 | 6540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6540 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 | 2021-02-23 | QTR3 | 20/21 | 216 | 1080912.01 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2765 | 43934415201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 286 | 291 | -5 | 5 | 0 | 102 | 4 | 3724072 | 50000 | 3674072 | 3724072 | 3875990 | -13560 | 0 | -13560 | 3862430 | 3837465 | -24965 | 0 | 70 | 0 | 4 | 71389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 80917 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2021-06-21 | QTR4 | 20/21 | 2021-03-04 | QTR3 | 20/21 | 214 | 4321210.18 |  |  | 4 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2766 | 44348915201 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 130 | 146 | 144 | 2 | 0 | 0 | 16 | 0 | 1081333 | 50000 | 1031333 | 1081333 | 1019859 | 0 | 0 | 0 | 1019859 | 1018371 | -1488 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-04 | QTR2 | 20/21 | 2020-06-16 | QTR4 | 19/20 | 214 | 1202483.05 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2Q19 | 43056535201 | 2013-03-27 | QTR3 | 12/13 | 2 | 7 | 898 | 1741 | 2245 | -504 | 504 | 0 | 126 | 717 | 76890000 | 250000 | 76640000 | 84056110 | 83001547 | -5396832 | 0 | -5396832 | 77604715 | 73874610 | -3730105 | 7166110 | 72 | 0 | 26 | 2691 | 0 | 0 | 0 | 5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117673 | 0 | 0 | 0 | 192400 | 0 | 0 | 24 | 55423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 138372 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 | 2019-07-30 | QTR1 | 19/20 | 208 | 86651500 | B8 | ACC - DESIGN/BUILD - MAJOR | 26 | 54 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Q20 | 43056515201 | 2013-10-10 | QTR2 | 13/14 | 4 | 13 | 798 | 1777 | 1998 | -221 | 221 | 0 | 127 | 852 | 84850000 | 175000 | 84675000 | 92836344 | 92314884 | -2553772 | 0 | -2553772 | 89761112 | 83827180 | -5933932 | 7986344 | 82 | 0 | 38 | 570696 | 0 | 0 | 105 | 90327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160600 | 0 | 0 | 0 | 14064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 254205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 818390 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 | 2019-05-29 | QTR4 | 18/19 | 208 | 91515175 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 10 | 45 | 0 | 0 | -271502 | 0 |  | DO
02DO | 02 | E2S01 | 21334575201 | 2014-05-29 | QTR4 | 13/14 | 2 | 9 | 670 | 1514 | 1849 | -335 | 335 | 0 | 504 | 340 | 88950000 | 150000 | 88800000 | 95522820 | 95155243 | -3789520 | 0 | -3789520 | 91365723 | 87555364 | -3397345 | 6572820 | 339 | 0 | 95 | 635772 | 0 | 0 | 22 | 510778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1201150 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2021-06-14 | QTR4 | 20/21 | 2019-08-16 | QTR1 | 19/20 | 208 | 87843647.44 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 165 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V62 | 43742915201 | 2017-04-19 | QTR4 | 16/17 | 2 | 3 | 538 | 1135 | 1132 | 3 | 0 | 0 | 172 | 425 | 2735951 | 50000 | 2685951 | 5631812 | 5550491 | 0 | 0 | 0 | 5550491 | 5348614 | -100997 | 2895861 | 78 | 40 | 0 | 36258 | 0 | 0 | 425 | 2744981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 425 | 2781240 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 | 2020-10-26 | QTR2 | 20/21 | 208 | 2961809.1 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 2 | 460 | 774 | 891 | -117 | 117 | 0 | 207 | 107 | 17417591 | 200000 | 17217591 | 18912363 | 18626417 | -549666 | 0 | -549666 | 18076751 | 18293661 | 233384 | 1494772 | 97 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1478299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1570743 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRAC | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97 |  |  | 4 | 110 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X06 | 43076015201 | 2018-04-18 | QTR4 | 17/18 | 1 | 2 | 190 | 489 | 545 | -56 | 56 | 0 | 248 | 51 | 2957443 | 50000 | 2907443 | 3057443 | 3046193 | -151872 | 0 | -151872 | 2894321 | 2894277 | -43 | 100000 | 19 | 0 | 44 | 97963 | 0 | 0 | 7 | 5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 3616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 51 | 106737 | 0 | F381884765 | CONTI LLC | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 | 2020-02-14 | QTR3 | 19/20 | 208 | 2882464.65 |  |  | 51 | 76 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X64 | 20964255201 | 2018-09-19 | QTR1 | 18/19 | 1 | 0 | 420 | 509 | 509 | 0 | 0 | 0 | 89 | 0 | 2988353 | 50000 | 2938353 | 2988353 | 3023872 | 0 | 0 | 0 | 3023872 | 3021571 | -2301 | 0 | 16 | 0 | 0 | 0 | 0 | 19 | 0 | 4770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 4770 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2021-02-23 | QTR3 | 20/21 | 2020-10-02 | QTR2 | 20/21 | 208 | 3026820.72 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X65 | 43239615201 | 2018-12-19 | QTR2 | 18/19 | 1 | 1 | 300 | 518 | 532 | -14 | 14 | 0 | 130 | 88 | 2683748 | 50000 | 2633748 | 2672792 | 2635955 | -37968 | 0 | -37968 | 2597987 | 2597896 | -90 | -10956 | 24 | 0 | 87 | -10956 | 0 | 30 | 1 | 13931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 88 | 2976 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 | 2020-12-09 | QTR2 | 20/21 | 208 | 2688578.12 |  |  | 1 | 49 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y25 | 43761715201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 250 | 365 | 351 | 14 | 0 | 0 | 99 | 16 | 5599368 | 63324 | 5536044 | 5599368 | 5849866 | 0 | 0 | 0 | 5849866 | 5819954 | -29911 | 0 | 48 | 0 | 0 | 2537 | 0 | 0 | 3 | 23074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 11453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 37064 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-05 | QTR2 | 20/21 | 2020-06-19 | QTR4 | 19/20 | 216 | 6362327.21 |  |  | 16 | 51 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y27 | 44129815201 | 2019-05-15 | QTR4 | 18/19 | 3 | 2 | 360 | 494 | 494 | 0 | 0 | 0 | 101 | 33 | 2191115 | 60000 | 2131115 | 2260070 | 2293916 | 0 | 0 | 0 | 2293916 | 2287350 | -6566 | 68955 | 45 | 0 | 13 | 8989 | 0 | 0 | 14 | 75803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6228 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 91019 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2021-03-31 | QTR3 | 20/21 | 2020-12-11 | QTR2 | 20/21 | 208 | 2136569.19 |  |  | 33 | 59 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 0 | 0 | 11 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26 |  |  | 4 | 1 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z35 | 43593915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 1 | 75 | 92 | 92 | 0 | 0 | 0 | 14 | 3 | 484693 | 14625 | 470068 | 492193 | 451960 | 0 | 0 | 0 | 451960 | 451960 | 0 | 7500 | 8 | 0 | 3 | 14105 | 0 | 0 | 0 | 3513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17618 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-05-14 | QTR4 | 20/21 | 2020-12-18 | QTR2 | 20/21 | 209 | 351994.25 |  |  | 3 | 6 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z37 | 43616525201 | 2020-03-18 | QTR3 | 19/20 | 1 | 0 | 90 | 150 | 141 | 9 | 0 | 0 | 45 | 15 | 335202 | 15218 | 319984 | 335202 | 332890 | 0 | 0 | 0 | 332890 | 332890 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27171 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2021-04-16 | QTR4 | 20/21 | 2020-11-30 | QTR2 | 20/21 | 209 | 321539.88 |  |  | 15 | 8 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z38 | 43958915201 | 2019-12-18 | QTR2 | 19/20 | 1 | 0 | 60 | 70 | 64 | 6 | 0 | 0 | 7 | 3 | 671597 | 33172 | 638425 | 671597 | 637444 | 0 | 0 | 0 | 637444 | 637444 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 5361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5361 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 | 2020-11-23 | QTR2 | 20/21 | 208 | 705487.5 |  |  | 3 | 4 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3287 | 22044245201 | 2015-04-29 | QTR4 | 14/15 | 1 | 7 | 580 | 1033 | 1033 | 0 | 0 | 0 | 446 | 7 | 18411475 | 150000 | 18261475 | 18469826 | 18803780 | 0 | 0 | 0 | 18803780 | 18257490 | -528638 | 58351 | 335 | 0 | 5 | 113096 | 0 | 42 | 0 | 6384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -114120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 128733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 7 | 134093 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 | 2018-08-16 | QTR1 | 18/19 | 308 | 19760913.51 |  |  | 3 | 69 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3578 | 41413235201 | 2017-04-26 | QTR4 | 16/17 | 3 | 15 | 1220 | 1365 | 1303 | 62 | 0 | 0 | 318 | -173 | 33319378 | 177050 | 33142328 | 34311548 | 36973951 | -94250 | 1500000 | 1405750 | 38379701 | 37310664 | -1041419 | 992170 | 229 | 0 | 0 | -9279 | 0 | 0 | 0 | 30465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173 | 947928 | 627929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173 | 970022 | 627929 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 | 2021-03-21 | QTR3 | 20/21 | 306 | 33490900.73 |  |  | 1 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3582 | 43483715201 | 2017-01-25 | QTR3 | 16/17 | 1 | 5 | 200 | 489 | 489 | 0 | 0 | 0 | 289 | 0 | 6289025 | 76080 | 6212946 | 6444360 | 6415800 | -47198 | 0 | -47198 | 6368602 | 6491338 | 125354 | 155335 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 28118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 | 2018-08-15 | QTR1 | 18/19 | 308 | 7725569.14 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | -1395 | 58 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3619 | 43390215201 | 2018-11-14 | QTR2 | 18/19 | 1 | 1 | 175 | 253 | 248 | 5 | 0 | 0 | 72 | 6 | 1114410 | 0 | 1114410 | 1163460 | 1226323 | 0 | 0 | 0 | 1226323 | 1224530 | -1793 | 49050 | 34 | 10 | 6 | 49050 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | 49050 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2020-12-10 | QTR2 | 20/21 | 2019-10-07 | QTR2 | 19/20 | 313 | 1475964.98 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3627 | 43228915201 | 2017-10-25 | QTR2 | 17/18 | 1 | 3 | 335 | 448 | 447 | 1 | 0 | 0 | 113 | 0 | 3174345 | 0 | 3174345 | 3223970 | 3466393 | 0 | 0 | 0 | 3466393 | 3468474 | 2081 | 49626 | 79 | 10 | 0 | 40110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 40110 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 | 2019-04-13 | QTR4 | 18/19 | 321 | 3241141.96 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3642 | 43274025201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 250 | 555 | 555 | 0 | 0 | 0 | 305 | 0 | 8739221 | 84002 | 8655219 | 8879082 | 9063602 | -14091 | 0 | -14091 | 9049511 | 9512844 | 541744 | 139862 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61451 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 | 2019-07-11 | QTR1 | 19/20 | 314 | 8488154.79 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 3300 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3659 | 43728425201 | 2017-06-14 | QTR4 | 16/17 | 1 | 3 | 45 | 135 | 133 | 2 | 0 | 0 | 74 | 16 | 1158389 | 50000 | 1108389 | 1230266 | 1207818 | 0 | 0 | 0 | 1207818 | 1207818 | 0 | 71877 | 42 | 0 | 0 | 0 | 0 | 0 | 12 | 53227 | 11252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 4 | 18650 | 16090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 16 | 71877 | 27342 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-24 | QTR3 | 20/21 | 2018-08-09 | QTR1 | 18/19 | 321 | 1285000 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3663 | 43188345201 | 2019-08-28 | QTR1 | 19/20 | 1 | 2 | 85 | 155 | 155 | 0 | 0 | 0 | 70 | 0 | 656987 | 29252 | 627735 | 668791 | 649887 | 0 | 0 | 0 | 649887 | 649887 | 0 | 11804 | 25 | 12 | 0 | 11597 | 2421 | 3 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 13154 | 2421 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-05-04 | QTR4 | 19/20 | 308 | 691494.24 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3668 | 43580015201 | 2019-09-25 | QTR1 | 19/20 | 1 | 4 | 250 | 295 | 271 | 24 | 0 | 0 | 45 | 0 | 1427167 | 0 | 1427167 | 1429917 | 1395761 | 0 | 0 | 0 | 1395761 | 1394795 | -966 | 2750 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-12-17 | QTR2 | 20/21 | 2020-10-02 | QTR2 | 20/21 | 321 | 1392503.71 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3694 | 43814015201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 150 | 172 | 156 | 16 | 0 | 0 | 22 | 0 | 1092210 | 50455 | 1041755 | 1092210 | 1034116 | 0 | 0 | 0 | 1034116 | 1032121 | -1995 | 0 | 15 | 0 | 0 | 880 | 0 | 0 | 0 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5695 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-04-21 | QTR4 | 20/21 | 2020-11-10 | QTR2 | 20/21 | 321 | 1201384.89 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3724 | 43972215201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 150 | 279 | 279 | 0 | 0 | 0 | 129 | 0 | 4652882 | 50000 | 4602882 | 4613196 | 4707642 | 0 | 0 | 0 | 4707642 | 4673127 | -34515 | -39686 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-04-14 | QTR4 | 20/21 | 2020-11-30 | QTR2 | 20/21 | 314 | 4516754.11 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3732 | 44172515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 90 | 123 | 123 | 0 | 0 | 0 | 33 | 0 | 724625 | 27004 | 697621 | 724625 | 671669 | 0 | 0 | 0 | 671669 | 671669 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 | 2020-08-14 | QTR1 | 20/21 | 308 | 569928.95 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3734 | 44174315201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 60 | 65 | 63 | 2 | 0 | 0 | 5 | 0 | 161220 | 10585 | 150635 | 161220 | 147933 | 0 | 0 | 0 | 147933 | 147933 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 | 2020-08-06 | QTR1 | 20/21 | 321 | 223390.28 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3737 | 44174415201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 60 | 72 | 70 | 2 | 0 | 0 | 12 | 0 | 163087 | 11619 | 151468 | 163087 | 147675 | 0 | 0 | 0 | 147675 | 147675 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 | 2020-10-12 | QTR2 | 20/21 | 321 | 241246.7 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3739 | 44173715201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 45 | 64 | 63 | 1 | 0 | 0 | 19 | 0 | 229048 | 6715 | 222333 | 236141 | 232144 | 0 | 0 | 0 | 232144 | 232144 | 0 | 7093 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 7093 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 | 2020-08-14 | QTR1 | 20/21 | 308 | 145096.15 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3747 | 44173515201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 120 | 151 | 151 | 0 | 0 | 0 | 17 | 14 | 512999 | 25267 | 487732 | 567826 | 538766 | 0 | 0 | 0 | 538766 | 538766 | 0 | 54827 | 8 | 0 | 14 | 47827 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 54827 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-18 | QTR4 | 20/21 | 2020-12-10 | QTR2 | 20/21 | 313 | 532693.81 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3748 | 44404215201 | 2020-04-29 | QTR4 | 19/20 | 2 | 0 | 74 | 104 | 106 | -2 | 2 | 0 | 30 | 0 | 600835 | 43572 | 557263 | 600835 | 529358 | -3380 | 0 | -3380 | 525978 | 525978 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 | 2020-12-19 | QTR2 | 20/21 | 313 | 859032.72 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9021 | 44531225216 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 150 | 195 | 193 | 2 | 0 | 0 | 43 | 2 | 1606769 | 50000 | 1556769 | 1606769 | 1542684 | 0 | 0 | 0 | 1542684 | 1542685 | 1 | 0 | 12 | 16 | 0 | 0 | 0 | 0 | 2 | 7007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 7007 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 | 2021-01-14 | QTR3 | 20/21 | 314 | 1883890.6 |  |  | 2 | 15 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 251063 | 77 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P37 | 22280225201 | 2019-04-11 | QTR4 | 18/19 | 1 | 0 | 120 | 154 | 152 | 2 | 0 | 0 | 34 | 0 | 398582 | 35644 | 362938 | 398582 | 363870 | 0 | 0 | 0 | 363870 | 363870 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F811252530 | OMEGA COATINGS & CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 | 2019-11-24 | QTR2 | 19/20 | 313 | 733124 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q54 | 22253925201 | 2019-05-09 | QTR4 | 18/19 | 1 | 1 | 90 | 110 | 103 | 7 | 0 | 0 | 20 | 0 | 922444 | 50000 | 872444 | 846935 | 658266 | 0 | 0 | 0 | 658266 | 658266 | 0 | -75510 | 16 | 0 | 0 | 12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63199 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-05 | QTR2 | 20/21 | 2019-11-22 | QTR2 | 19/20 | 321 | 919379.25 |  |  | 0 | 4 | 0 | 0 | -75510 | 0 |  | DO
03DO | 03 | E3R03 | 41343525201 | 2018-05-10 | QTR4 | 17/18 | 4 | 9 | 210 | 403 | 403 | 0 | 0 | 0 | 165 | 28 | 1381327 | 50000 | 1331327 | 1468091 | 1381221 | -4783 | 0 | -4783 | 1376437 | 1365035 | -1916 | 86763 | 94 | 0 | 0 | 0 | 0 | 0 | 3 | 15065 | 1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 52304 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 12921 | 12921 | 0 | 0 | 0 | 0 | 34 | 28 | 80290 | 15961 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2019-09-13 | QTR1 | 19/20 | 308 | 1155000 |  |  | 2 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 158902 | 66 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94 |  |  | 6 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 278 | 280 | -2 | 2 | 0 | 54 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4468867 | -5424 | 0 | -5424 | 4463443 | 4390050 | -73393 | 123339 | 26 | 0 | 14 | 48949 | 0 | 5 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-16 | QTR4 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04 |  |  | 14 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R75 | 40731075201 | 2019-06-13 | QTR4 | 18/19 | 2 | 4 | 180 | 236 | 236 | 0 | 0 | 0 | 52 | 4 | 1896816 | 50000 | 1846816 | 2013742 | 1899113 | 0 | 0 | 0 | 1899113 | 1899113 | 0 | 116926 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 102982 | 7592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 116926 | 9300 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-10-07 | QTR2 | 20/21 | 2020-06-19 | QTR4 | 19/20 | 308 | 1645052.8 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R78 | 43813815201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 90 | 124 | 116 | 8 | 0 | 0 | 34 | 0 | 467023 | 24986 | 442037 | 467023 | 452193 | 0 | 0 | 0 | 452193 | 452193 | 0 | 0 | 27 | 0 | 0 | 3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-20 | QTR2 | 20/21 | 2020-08-03 | QTR1 | 20/21 | 314 | 567888.91 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R84 | 43736715201 | 2019-05-09 | QTR4 | 18/19 | 3 | 1 | 150 | 273 | 264 | 9 | 0 | 0 | 63 | 60 | 1890085 | 52035 | 1838050 | 1993510 | 1844667 | 0 | 0 | 0 | 1844667 | 1822661 | -22007 | 103425 | 27 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 103425 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 313 | 1951315.61 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R95 | 41558035201 | 2020-02-13 | QTR3 | 19/20 | 1 | 0 | 90 | 117 | 109 | 8 | 0 | 0 | 27 | 0 | 328111 | 23276 | 304835 | 328111 | 264195 | 0 | 0 | 0 | 264195 | 264195 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-01-20 | QTR3 | 20/21 | 2020-12-10 | QTR2 | 20/21 | 308 | 491599.69 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S02 | 21939725201 | 2019-12-12 | QTR2 | 19/20 | 1 | 0 | 90 | 91 | 36 | 55 | 0 | 0 | 1 | 0 | 427396 | 14431 | 412964 | 427396 | 396531 | 0 | 0 | 0 | 396531 | 396531 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-30 | QTR3 | 20/21 | 2020-05-26 | QTR4 | 19/20 | 321 | 321776.39 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 42363 | 60 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S37 | 43972615201 | 2019-08-08 | QTR1 | 19/20 | 3 | 0 | 150 | 174 | 167 | 7 | 0 | 0 | 24 | 0 | 1570270 | 51725 | 1518545 | 1570270 | 1528065 | 0 | 0 | 0 | 1528065 | 1509877 | -18188 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-03-22 | QTR3 | 20/21 | 2020-07-29 | QTR1 | 20/21 | 321 | 1812371.83 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S48 | 43973015201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 150 | 167 | 153 | 14 | 0 | 0 | 17 | 0 | 2362840 | 50000 | 2312840 | 2362840 | 2375062 | 0 | 0 | 0 | 2375062 | 2367596 | -7466 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-07-27 | QTR1 | 20/21 | 321 | 2687906.81 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S50 | 22253625201 | 2019-11-14 | QTR2 | 19/20 | 2 | 0 | 120 | 125 | 50 | 75 | 0 | 0 | 5 | 0 | 688910 | 0 | 688910 | 688910 | 677594 | 0 | 0 | 0 | 677594 | 677594 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2020-04-06 | QTR4 | 19/20 | 321 | 1158620.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S58 | 43992625201 | 2019-09-12 | QTR1 | 19/20 | 1 | 0 | 425 | 492 | 458 | 34 | 0 | 0 | 67 | 0 | 4969434 | 55861 | 4913574 | 4969434 | 4898737 | 0 | 0 | 0 | 4898737 | 4882975 | -15762 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 | 2021-04-08 | QTR4 | 20/21 | 321 | 5633775.36 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S66 | 4450183H201 | 2019-04-26 | QTR4 | 18/19 | 1 | 0 | 75 | 93 | 92 | 1 | 0 | 0 | 18 | 0 | 280576 | 0 | 280576 | 280576 | 224753 | 0 | 0 | 0 | 224753 | 0 | -224753 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 | 2019-10-02 | QTR2 | 19/20 | 314 | 275520.59 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T19 | 4453861K201 | 2019-10-14 | QTR2 | 19/20 | 2 | 1 | 70 | 130 | 137 | -7 | 7 | 0 | 60 | 0 | 289955 | 0 | 289955 | 289955 | 286443 | -8687 | 0 | -8687 | 277756 | 0 | -277756 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201212361 | PBROWN BUILDERS LLC | N/A | N/A | N/A | N/A | 2021-03-09 | QTR3 | 20/21 | 2020-06-11 | QTR4 | 19/20 | 313 | 279453.29 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T53 | 42187835201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 60 | 60 | 36 | 24 | 0 | 0 | 0 | 0 | 205566 | 12109 | 193457 | 205566 | 187451 | 0 | 200000 | 200000 | 387451 | 187451 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-04-14 | QTR4 | 20/21 | 2020-11-03 | QTR2 | 20/21 | 313 | 257559.58 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 233861 | 985075 | 115 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22 |  |  | 14 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4462 | 43232315203 | 2017-05-24 | QTR4 | 16/17 | 3 | 18 | 349 | 1018 | 1024 | -6 | 6 | 0 | 144 | 525 | 9366292 | 77893 | 9288399 | 10932113 | 10870783 | -21870 | 0 | -21870 | 10848913 | 10912061 | 107174 | 1565821 | 95 | 0 | 45 | 152933 | 19651 | 6 | 480 | 1355104 | 233357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73285 | 1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 525 | 1581322 | 254305 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2021-05-12 | QTR4 | 20/21 | 2020-07-28 | QTR1 | 20/21 | 412 | 8174810.53 |  |  | 3 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4473 | 42751615201 | 2018-03-28 | QTR3 | 17/18 | 2 | 4 | 335 | 483 | 483 | 0 | 0 | 0 | 148 | 0 | 14954960 | 127766 | 14827195 | 14788864 | 14238463 | 0 | 0 | 0 | 14238463 | 14552841 | 324737 | -166097 | 91 | 0 | 0 | 144864 | 0 | 0 | 0 | 5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 26899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -147083 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 | 2020-02-06 | QTR3 | 19/20 | 409 | 12073779.82 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 45 | 0 | 0 | -324121 | 0 |  | CO
04CO | 04 | T4479 | 43059025201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 179 | 294 | 294 | 0 | 0 | 0 | 115 | 0 | 815678 | 34169 | 781510 | 823050 | 757384 | 0 | 0 | 0 | 757384 | 756711 | -673 | 7371 | 93 | 0 | 0 | 7371 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9340 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 | 2020-06-16 | QTR4 | 19/20 | 412 | 726059.56 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | -253 | 22625 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4485 | 43634115201 | 2018-06-13 | QTR4 | 17/18 | 2 | 2 | 239 | 422 | 422 | 0 | 0 | 0 | 140 | 43 | 1979980 | 50000 | 1929980 | 2224615 | 2010428 | 0 | 0 | 0 | 2010428 | 2010404 | -24 | 244635 | 112 | 0 | 0 | 0 | 0 | 0 | 43 | 264928 | 244635 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 269674 | 244635 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-02 | QTR3 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 412 | 2546948.04 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4489 | 43770115201 | 2018-12-05 | QTR2 | 18/19 | 1 | 3 | 350 | 447 | 437 | 10 | 0 | 0 | 97 | 0 | 5985000 | 64375 | 5920625 | 6208144 | 6389050 | 0 | 0 | 0 | 6389050 | 6213547 | -39102 | 223144 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 88252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506 | 0 | 0 | 0 | 7907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101665 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-07-02 | QTR1 | 20/21 | 408 | 6481016.05 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | -14110 | 229825 | 55 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | -2608 | 349724 | 45 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 103884 | 25 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65 |  |  | 15 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4499 | 44055425201 | 2019-01-30 | QTR3 | 18/19 | 2 | 5 | 372 | 656 | 601 | 55 | 0 | 0 | 121 | 163 | 5385476 | 50611 | 5334864 | 8390963 | 8381389 | 0 | 0 | 0 | 8381389 | 8373187 | 940 | 3005487 | 61 | 0 | 140 | 2521590 | 1067356 | 10 | 23 | 240752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 163 | 2768740 | 1067356 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 | 2021-01-28 | QTR3 | 20/21 | 408 | 5178383.74 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4500 | 43435915201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 349 | 540 | 540 | 0 | 0 | 0 | 132 | 59 | 2477341 | 50000 | 2427341 | 2477341 | 2598284 | 0 | 0 | 0 | 2598284 | 2597220 | -1063 | 0 | 98 | 0 | 0 | 3012 | 0 | 0 | 59 | 26361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 31204 | 0 | F591358949 | ANZAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-21 | QTR4 | 20/21 | 2021-04-26 | QTR4 | 20/21 | 412 | 1937290.89 |  |  | 59 | 34 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4501 | 43468615201 | 2019-01-30 | QTR3 | 18/19 | 3 | 2 | 398 | 604 | 604 | 0 | 0 | 0 | 206 | 0 | 4133433 | 50000 | 4083433 | 4218884 | 4214126 | 0 | 0 | 0 | 4214126 | 4198022 | -14662 | 85450 | 140 | 0 | 0 | -83910 | 0 | 0 | 0 | 190412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 106502 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 | 2021-03-06 | QTR3 | 20/21 | 412 | 4929152.55 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4502 | 43630315202 | 2019-03-27 | QTR3 | 18/19 | 2 | 1 | 205 | 256 | 256 | 0 | 0 | 0 | 51 | 0 | 1465257 | 50000 | 1415257 | 1481535 | 1429078 | 0 | 0 | 0 | 1429078 | 1429078 | 0 | 16278 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 13973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30251 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-01-11 | QTR3 | 20/21 | 2020-06-17 | QTR4 | 19/20 | 412 | 1399471.05 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4503 | 43611115201 | 2019-01-30 | QTR3 | 18/19 | 2 | 3 | 205 | 289 | 289 | 0 | 0 | 0 | 84 | 0 | 2257891 | 50000 | 2207891 | 2372485 | 2277661 | 0 | 0 | 0 | 2277661 | 2279759 | 2097 | 114594 | 40 | 14 | 0 | 21562 | 0 | 25 | 0 | 100250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6266 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 136606 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-26 | QTR2 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 412 | 2312700.41 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4506 | 43783215201 | 2019-04-24 | QTR4 | 18/19 | 1 | 2 | 252 | 390 | 387 | 3 | 0 | 0 | 138 | 0 | 8509769 | 99739 | 8410031 | 8729916 | 8272368 | 0 | 0 | 0 | 8272368 | 8168439 | -103929 | 220147 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 189437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 55163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 244600 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-02-23 | QTR3 | 20/21 | 2020-08-11 | QTR1 | 20/21 | 412 | 10259256.99 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | -62 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4508 | 43773115201 | 2019-03-27 | QTR3 | 18/19 | 9 | 3 | 486 | 593 | 593 | 0 | 0 | 0 | 102 | 5 | 6817376 | 73217 | 6744159 | 6968476 | 6729053 | 0 | 0 | 0 | 6729053 | 6684935 | -33744 | 151101 | 56 | 0 | 0 | 133625 | 0 | 0 | 0 | 38977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10794 | 0 | 0 | 0 | 1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 184735 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-06-09 | QTR4 | 20/21 | 2021-02-08 | QTR3 | 20/21 | 412 | 7367257.98 |  |  | 5 | 46 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4510 | 43234415201 | 2019-05-22 | QTR4 | 18/19 | 2 | 8 | 430 | 566 | 565 | 1 | 0 | 0 | 136 | 0 | 8369134 | 9646 | 8359488 | 8429194 | 8328626 | 0 | 0 | 0 | 8328626 | 8158766 | -169861 | 60060 | 89 | 0 | 0 | 7635 | 0 | 0 | 0 | 28604 | 947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45448 | 947 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2021-02-16 | QTR3 | 20/21 | 409 | 9265922.68 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4513 | 43770815201 | 2019-07-31 | QTR1 | 19/20 | 2 | 0 | 120 | 239 | 234 | 5 | 0 | 0 | 119 | 0 | 602298 | 27028 | 575270 | 602298 | 562547 | 0 | 0 | 0 | 562547 | 562065 | -482 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 6428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6428 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 | 2020-09-13 | QTR1 | 20/21 | 412 | 569665.71 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4514 | 43778515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 128 | 208 | 208 | 0 | 0 | 0 | 57 | 23 | 277929 | 15062 | 262868 | 277929 | 262174 | 0 | 0 | 0 | 262174 | 261778 | -397 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | F261264765 | HIGHSTYLE ENGINEERING & CONSTRUCTION SER | N/A | N/A | N/A | N/A | 2021-04-06 | QTR4 | 20/21 | 2020-11-13 | QTR2 | 20/21 | 412 | 312613.57 |  |  | 23 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4518 | 43829115201 | 2019-05-22 | QTR4 | 18/19 | 2 | 0 | 406 | 544 | 544 | 0 | 0 | 0 | 138 | 0 | 1840414 | 50000 | 1790414 | 1840414 | 1784131 | 0 | 0 | 0 | 1784131 | 1773135 | -10996 | 0 | 65 | 30 | 0 | 0 | 0 | 0 | 0 | 13142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 13967 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 | 2021-03-10 | QTR3 | 20/21 | 409 | 1949951.04 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4520 | 43770215201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 136 | 238 | 235 | 3 | 0 | 0 | 102 | 0 | 511111 | 24274 | 486837 | 511111 | 500925 | 0 | 0 | 0 | 500925 | 500762 | -163 | 0 | 96 | 0 | 0 | 1690 | 0 | 0 | 0 | 12605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14295 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-02 | QTR2 | 20/21 | 2020-08-27 | QTR1 | 20/21 | 412 | 517002.15 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4524 | 43770715201 | 2019-05-22 | QTR4 | 18/19 | 1 | 1 | 380 | 456 | 456 | 0 | 0 | 0 | 74 | 2 | 3289804 | 50000 | 3239804 | 3447958 | 3265220 | 0 | 0 | 0 | 3265220 | 3255145 | -10075 | 158154 | 32 | 0 | 2 | 7700 | 0 | 0 | 0 | 173819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 206719 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-06-18 | QTR4 | 20/21 | 2021-01-11 | QTR3 | 20/21 | 412 | 2506277.97 |  |  | 2 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4526 | 43689425201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 360 | 406 | 327 | 79 | 0 | 0 | 46 | 0 | 2010552 | 50000 | 1960552 | 2002087 | 1918992 | 0 | 0 | 0 | 1918992 | 1917486 | -1506 | -8465 | 33 | 0 | 0 | -8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8465 | 0 | F590229150 | EBSARY FOUNDATION COMPANY | N/A | N/A | N/A | N/A | 2021-01-19 | QTR3 | 20/21 | 2020-12-11 | QTR2 | 20/21 | 409 | 2144002.51 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4529 | 44271915201 | 2019-10-30 | QTR2 | 19/20 | 2 | 1 | 76 | 104 | 86 | 18 | 0 | 0 | 28 | 0 | 190000 | 7948 | 182052 | 193240 | 183953 | 0 | 0 | 0 | 183953 | 183953 | 0 | 3240 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 7433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7433 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-04-08 | QTR4 | 20/21 | 2020-09-22 | QTR1 | 20/21 | 412 | 172636.44 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4531 | 44313515201 | 2019-10-30 | QTR2 | 19/20 | 3 | 1 | 285 | 314 | 222 | 92 | 0 | 0 | 29 | 0 | 1219731 | 46309 | 1173423 | 1221270 | 1174601 | 0 | 0 | 0 | 1174601 | 1173062 | 0 | 1539 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3801 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-01-08 | QTR3 | 20/21 | 2020-12-11 | QTR2 | 20/21 | 408 | 921804.84 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4534 | 43654115201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 167 | 298 | 298 | 0 | 0 | 0 | 131 | 0 | 1247199 | 50000 | 1197199 | 1247199 | 1170098 | 0 | 0 | 0 | 1170098 | 1169903 | -195 | 0 | 95 | 0 | 0 | 0 | 0 | 16 | 0 | 5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 5589 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2021-03-19 | QTR3 | 20/21 | 412 | 1326125 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4536 | 43838915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 274 | 313 | 312 | 1 | 0 | 0 | 39 | 0 | 1482069 | 50000 | 1432069 | 1482069 | 1327510 | 0 | 0 | 0 | 1327510 | 1325299 | -2211 | 0 | 15 | 0 | 0 | 8116 | 0 | 0 | 0 | 5151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13267 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2021-06-08 | QTR4 | 20/21 | 2021-02-19 | QTR3 | 20/21 | 409 | 1483089.53 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 0 | 16665 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4545 | 43984415201 | 2020-02-26 | QTR3 | 19/20 | 2 | 7 | 198 | 313 | 313 | 0 | 0 | 0 | 80 | 35 | 2092533 | 50000 | 2042533 | 2459453 | 2601638 | 0 | 0 | 0 | 2601638 | 2600754 | -884 | 366920 | 59 | 0 | 0 | 13206 | 0 | 0 | 35 | 358633 | 180233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197 | 0 | 0 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 374481 | 180233 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-06-15 | QTR4 | 20/21 | 2021-05-20 | QTR4 | 20/21 | 409 | 2283381.44 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4547 | 43838715201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 349 | 379 | 211 | 168 | 0 | 0 | 30 | 0 | 844444 | 47721 | 796723 | 844444 | 723057 | 0 | 0 | 0 | 723057 | 723057 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-03-29 | QTR3 | 20/21 | 2021-03-15 | QTR3 | 20/21 | 409 | 1015766.34 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4548 | 44368515201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 115 | 152 | 152 | 0 | 0 | 0 | 37 | 0 | 255430 | 13096 | 242335 | 255430 | 242375 | 0 | 0 | 0 | 242375 | 242375 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F262583742 | WIRETEK SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 | 2021-03-05 | QTR3 | 20/21 | 408 | 277363.65 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4549 | 43783015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 180 | 219 | 217 | 2 | 0 | 0 | 39 | 0 | 1201295 | 50000 | 1151295 | 1201295 | 1104692 | 0 | 0 | 0 | 1104692 | 1104644 | -48 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 | 2021-02-16 | QTR3 | 20/21 | 412 | 1290271.59 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4550 | 43689715201 | 2020-02-26 | QTR3 | 19/20 | 1 | 1 | 216 | 248 | 247 | 1 | 0 | 0 | 32 | 0 | 1446899 | 50000 | 1396899 | 1473105 | 1500428 | 0 | 0 | 0 | 1500428 | 1500428 | 0 | 26206 | 12 | 0 | 0 | 34759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34759 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 | 2021-03-15 | QTR3 | 20/21 | 409 | 1630170.95 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4M90 | 41242035201 | 2013-04-24 | QTR4 | 12/13 | 7 | 16 | 1141 | 1773 | 1782 | -9 | 9 | 0 | 378 | 254 | 66615000 | 150000 | 66465000 | 69280598 | 68971834 | -91753 | 0 | -91753 | 68880082 | 65635992 | -2942512 | 2665598 | 233 | 57 | 160 | 2469562 | 690281 | 0 | 13 | -11729 | 0 | 0 | 7 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 19800 | 0 | 0 | 0 | 19625 | 222877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 240 | 2450569 | 913159 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2021-01-27 | QTR3 | 20/21 | 2018-06-14 | QTR4 | 17/18 | 409 | 64729280.95 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 88 | 0 | 0 | -46689 | 0 |  | DO
04DO | 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | -998657 | 1434680 | 296 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 11 | 112 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T09 | 42264125201 | 2018-06-14 | QTR4 | 17/18 | 2 | 10 | 720 | 883 | 740 | 143 | 0 | 0 | 163 | 0 | 12892089 | 150000 | 12742089 | 13358507 | 13278726 | 0 | 0 | 0 | 13278726 | 13184941 | -74765 | 466418 | 118 | 0 | 0 | 208568 | 13035 | 0 | 0 | 644589 | 13207 | 0 | 0 | 0 | 0 | 0 | 0 | -308042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28215 | 0 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580245 | 26243 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 | 2021-04-30 | QTR4 | 20/21 | 408 | 15739611.8 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 0 | 107565 | 96 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T54 | 42957525201 | 2019-02-01 | QTR3 | 18/19 | 1 | 0 | 158 | 281 | 242 | 39 | 0 | 0 | 123 | 0 | 1034836 | 50000 | 984836 | 1034836 | 958378 | 0 | 0 | 0 | 958378 | 958293 | -85 | 0 | 81 | 0 | 0 | 11025 | 0 | 5 | 0 | 8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 19498 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 412 | 1135394.39 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T56 | 43578125201 | 2019-03-08 | QTR3 | 18/19 | 1 | 1 | 203 | 306 | 306 | 0 | 0 | 0 | 103 | 0 | 1488175 | 50000 | 1438175 | 1499756 | 1508806 | 0 | 0 | 0 | 1508806 | 1504997 | -3808 | 11580 | 44 | 10 | 0 | 36888 | 0 | 0 | 0 | 10773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 11580 | 11580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 59242 | 11580 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 412 | 1272541.13 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T61 | 43783415201 | 2019-04-05 | QTR4 | 18/19 | 2 | 3 | 355 | 433 | 434 | -1 | 1 | 0 | 78 | 0 | 5430718 | 52907 | 5377811 | 5477794 | 5212471 | -3447 | 0 | -3447 | 5209024 | 5104984 | -104039 | 47075 | 44 | 0 | 0 | 139626 | 0 | 0 | 0 | 16589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82362 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2021-04-15 | QTR4 | 20/21 | 2020-12-23 | QTR2 | 20/21 | 409 | 5340256.18 |  |  | 0 | 34 | 0 | 0 | -73852 | 0 |  | DO
04DO | 04 | E4T65 | 44144215201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 325 | 350 | 203 | 147 | 0 | 0 | 25 | 0 | 1246700 | 50000 | 1196700 | 1246700 | 1046614 | 0 | 0 | 0 | 1046614 | 1046614 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2021-04-05 | QTR4 | 20/21 | 2021-01-20 | QTR3 | 20/21 | 409 | 2119585.65 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T67 | 43990015201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 171 | 222 | 222 | 0 | 0 | 0 | 51 | 0 | 399288 | 21675 | 377614 | 399288 | 314456 | 0 | 0 | 0 | 314456 | 314456 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 | 2020-11-30 | QTR2 | 20/21 | 412 | 459766.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T84 | 43389615201 | 2019-12-06 | QTR2 | 19/20 | 1 | 1 | 80 | 91 | 91 | 0 | 0 | 0 | 26 | -15 | 802818 | 31559 | 771259 | 802818 | 776329 | 0 | 0 | 0 | 776329 | 776329 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 | 2020-11-06 | QTR2 | 20/21 | 409 | 659386.45 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T85 | 43984315201 | 2020-01-03 | QTR3 | 19/20 | 2 | 1 | 246 | 258 | 180 | 78 | 0 | 0 | 12 | 0 | 3861123 | 52156 | 3808968 | 3862794 | 3684709 | 0 | 325000 | 325000 | 4009709 | 3665629 | -342410 | 1671 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031 | 0 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2021-01-22 | QTR3 | 20/21 | 2020-09-10 | QTR1 | 20/21 | 409 | 5435661.92 | B1:B3 | ACC - NO EXCUSE BONUS:ACC - LANE RENTAL | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T86 | 44061215201 | 2020-02-07 | QTR3 | 19/20 | 1 | 1 | 66 | 125 | 125 | 0 | 0 | 0 | 59 | 0 | 600421 | 307 | 600114 | 614749 | 545426 | 0 | 0 | 0 | 545426 | 545426 | 0 | 14328 | 53 | 0 | 0 | 2938 | 0 | 0 | 0 | 11391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14328 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2021-01-21 | QTR3 | 20/21 | 2020-10-09 | QTR2 | 20/21 | 412 | 606555.66 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T88 | 43986015201 | 2020-03-06 | QTR3 | 19/20 | 1 | 1 | 175 | 196 | 174 | 22 | 0 | 0 | 21 | 0 | 1568562 | 50000 | 1518562 | 1545768 | 1524057 | 0 | 0 | 0 | 1524057 | 1524072 | 15 | -22794 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -22794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5165 | 0 | F650405645 | STATE CONTRACTING & ENGINEERING CORPORAT | N/A | N/A | N/A | N/A | 2021-03-03 | QTR3 | 20/21 | 2021-01-29 | QTR3 | 20/21 | 409 | 1393385.55 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T89 | 43214615201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 89 | 155 | 153 | 2 | 0 | 0 | 66 | 0 | 641391 | 39929 | 601462 | 641391 | 602117 | 0 | 0 | 0 | 602117 | 602117 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4224 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 | 2021-02-08 | QTR3 | 20/21 | 412 | 898061.48 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T92 | 44140915201 | 2020-01-17 | QTR3 | 19/20 | 1 | 1 | 130 | 156 | 131 | 25 | 0 | 0 | 26 | 0 | 888985 | 50000 | 838985 | 900166 | 850166 | 0 | 0 | 0 | 850166 | 838985 | 0 | 11181 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-12-09 | QTR2 | 20/21 | 2020-11-14 | QTR2 | 20/21 | 408 | 1308480 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U43 | 44332215201 | 2020-04-03 | QTR4 | 19/20 | 1 | 1 | 167 | 189 | 189 | 0 | 0 | 0 | 22 | 0 | 444903 | 16132 | 428771 | 444903 | 440091 | 0 | 0 | 0 | 440091 | 440091 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | -8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2021-05-11 | QTR4 | 20/21 | 2021-04-16 | QTR4 | 20/21 | 409 | 336190.55 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U55 | 43996115201 | 2020-03-06 | QTR3 | 19/20 | 1 | 0 | 171 | 194 | 188 | 6 | 0 | 0 | 23 | 0 | 613162 | 28339 | 584823 | 613162 | 583262 | 0 | 0 | 0 | 583262 | 583262 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-05-20 | QTR4 | 20/21 | 2021-03-15 | QTR3 | 20/21 | 409 | 649888.02 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U78 | 4476871H201 | 2020-07-14 | QTR1 | 20/21 | 1 | 7 | 30 | 222 | 222 | 0 | 0 | 0 | 37 | 155 | 100000 | 0 | 100000 | 15900149 | 15843107 | 0 | 0 | 0 | 15843107 | 0 | -15843107 | 15800149 | 21 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 15734283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 15743107 | 0 | F522113986 | STRUCTURAL TECHNOLOGIES LLC | N/A | N/A | N/A | N/A | 2021-04-27 | QTR4 | 20/21 | 2021-02-27 | QTR3 | 20/21 | 408 | 100000 |  |  | 8 | 16 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | -797738 | 2915022 | 79 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06 |  |  | 0 | 65 | 0 | 0 | -178687 | 0 |  | CO
05CO | 05 | T5589 | 23827525201 | 2017-06-14 | QTR4 | 16/17 | 4 | 17 | 850 | 1130 | 1095 | 35 | 0 | 0 | 200 | 80 | 32839302 | 150000 | 32689302 | 33739239 | 34780986 | 0 | -4571 | -4571 | 34776415 | 35569988 | 827889 | 899937 | 150 | 0 | 0 | -43955 | 2420 | 0 | 13 | 705345 | 171095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304966 | 64111 | 0 | 11 | 23824 | 13904 | 0 | 0 | 0 | 0 | 0 | 0 | 1542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 991722 | 251530 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2021-04-07 | QTR4 | 20/21 |  | QTR2 | 00/01 | 515 | 46309915.72 |  |  | 46 | 79 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | -284799 | 843098 | 69 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 51986 | 59 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41 |  |  | 4 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | -24609 | 54891 | 45 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5605 | 43565925201 | 2018-03-28 | QTR3 | 17/18 | 4 | 7 | 400 | 813 | 813 | 0 | 0 | 0 | 334 | 79 | 7668889 | 150000 | 7518889 | 8851634 | 8747850 | -12870 | 0 | -12870 | 8734980 | 8814553 | 86738 | 1182745 | 278 | 0 | 2 | 304852 | 1295 | 0 | 48 | 733352 | 29035 | 0 | 0 | 32760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73962 | 28150 | 0 | 0 | 0 | 0 | 0 | 0 | 7236 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 47691 | 47691 | 0 | 0 | 0 | 0 | 0 | 79 | 1199853 | 106171 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-03-12 | QTR3 | 20/21 | 2020-11-19 | QTR2 | 20/21 | 512 | 9666692 |  |  | 19 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5607 | 43612315201 | 2019-10-30 | QTR2 | 19/20 | 1 | 1 | 130 | 186 | 185 | 1 | 0 | 0 | 56 | 0 | 1114942 | 50000 | 1064942 | 1116831 | 1062929 | 0 | 0 | 0 | 1062929 | 1058191 | -2848 | 1889 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 2189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-03-12 | QTR3 | 20/21 | 2020-12-09 | QTR2 | 20/21 | 514 | 1090281.76 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5615 | 43793115201 | 2018-03-28 | QTR3 | 17/18 | 1 | 1 | 200 | 438 | 665 | -227 | 227 | 0 | 47 | 191 | 1435273 | 48389 | 1386883 | 1466273 | 1433905 | -119880 | 0 | -119880 | 1314025 | 1313837 | -188 | 31000 | 20 | 0 | 0 | 0 | 0 | 0 | 15 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 31450 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-11-18 | QTR2 | 20/21 | 2020-04-13 | QTR4 | 19/20 | 507 | 1578332.97 |  |  | 15 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | -94321 | 93683 | 136 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 512 | 12044261 |  |  | 7 | 54 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5625 | 42421715201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 480 | 806 | 801 | 5 | 0 | 0 | 250 | 76 | 7136709 | 75000 | 7061709 | 7786367 | 8041380 | 0 | 0 | 0 | 8041380 | 7881784 | -123601 | 649658 | 154 | 0 | 46 | 435937 | 0 | 0 | 30 | 224253 | 69614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 660190 | 69614 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 | 2021-04-16 | QTR4 | 20/21 | 507 | 7854126.8 |  |  | 30 | 96 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | -2583 | 3778 | 20 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9 |  |  | 35 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | -92470 | 42528 | 52 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5634 | 43734815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 2 | 350 | 469 | 469 | 0 | 0 | 0 | 104 | 15 | 7052425 | 108401 | 6944024 | 7232569 | 7465970 | 0 | 0 | 0 | 7465970 | 7453020 | -10558 | 180144 | 49 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 177752 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 | 2020-07-26 | QTR1 | 20/21 | 515 | 10311527.59 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5648 | 43759515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 1 | 250 | 374 | 344 | 30 | 0 | 0 | 100 | 24 | 2614878 | 50000 | 2564878 | 2614878 | 2572113 | 0 | 0 | 0 | 2572113 | 2540351 | -31762 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 24 | 7039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 7039 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-15 | QTR3 | 20/21 | 2020-10-01 | QTR2 | 20/21 | 513 | 3184786.93 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5649 | 43747015201 | 2019-05-22 | QTR4 | 18/19 | 1 | 0 | 250 | 493 | 526 | -33 | 33 | 0 | 86 | 157 | 1816910 | 50000 | 1766910 | 1816910 | 1789398 | -54945 | 0 | -54945 | 1734453 | 1734453 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 157 | 18121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 18121 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2021-01-21 | QTR3 | 20/21 | 509 | 2329182 |  |  | 157 | 56 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5652 | 43097555201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 290 | 314 | 290 | 24 | 0 | 0 | 24 | 0 | 2616100 | 50000 | 2566100 | 2718053 | 2707282 | 0 | 0 | 0 | 2707282 | 2685273 | -22009 | 101953 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 101953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101953 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-19 | QTR3 | 20/21 | 2020-12-18 | QTR2 | 20/21 | 515 | 3057554.72 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5653 | 43967915201 | 2019-03-27 | QTR3 | 18/19 | 1 | 2 | 140 | 372 | 337 | 35 | 0 | 0 | 79 | 153 | 782050 | 37000 | 745050 | 805120 | 729222 | 0 | 0 | 0 | 729222 | 728882 | -340 | 23070 | 53 | 0 | 0 | 6257 | 0 | 0 | 153 | 16813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 23070 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 | 2020-09-30 | QTR1 | 20/21 | 509 | 797259.75 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5660 | 24099255201 | 2018-10-31 | QTR2 | 18/19 | 3 | 5 | 430 | 611 | 611 | 0 | 0 | 0 | 124 | 57 | 4991772 | 107663 | 4884109 | 5081949 | 5090998 | 0 | 0 | 0 | 5090998 | 5004860 | -78604 | 90177 | 76 | 0 | 49 | 42996 | 0 | 0 | 8 | 57439 | 2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 100436 | 2168 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 | 2020-11-17 | QTR2 | 20/21 | 513 | 4917854.1 |  |  | 10 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | -49387 | 3208 | 82 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5677 | 43923315201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 160 | 196 | 195 | 1 | 0 | 0 | 36 | 0 | 6452955 | 68620 | 6384335 | 6597931 | 6823659 | 0 | 0 | 0 | 6823659 | 6790182 | -33477 | 144976 | 26 | 0 | 0 | 4727 | 0 | 0 | 0 | 144976 | 9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149703 | 9705 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-11-30 | QTR2 | 20/21 | 2020-09-23 | QTR1 | 20/21 | 514 | 7161772.24 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5714 | 44137015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 120 | 140 | 137 | 3 | 0 | 0 | 20 | 0 | 531915 | 26950 | 504965 | 531915 | 514987 | 0 | 0 | 0 | 514987 | 514987 | 0 | 0 | 4 | 0 | 0 | 6829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12250 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-03-26 | QTR3 | 20/21 | 2021-02-18 | QTR3 | 20/21 | 515 | 535536.17 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50A1 | 44327115201 | 2020-02-04 | QTR3 | 19/20 | 1 | 0 | 130 | 135 | 125 | 10 | 0 | 0 | 5 | 0 | 258893 | 12893 | 246000 | 258893 | 238371 | 0 | 0 | 0 | 238371 | 238371 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2021-02-04 | QTR3 | 20/21 | 2020-10-23 | QTR2 | 20/21 | 513 | 275763 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50A4 | 43754315201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 180 | 285 | 282 | 3 | 0 | 0 | 105 | 0 | 7148284 | 75220 | 7073064 | 7148284 | 7569825 | 0 | 0 | 0 | 7569825 | 7442288 | -127537 | 0 | 82 | 0 | 0 | 20101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20101 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2021-02-12 | QTR3 | 20/21 | 509 | 7601971.91 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A4 | 44539715201 | 2020-09-01 | QTR1 | 20/21 | 1 | 0 | 90 | 90 | 54 | 36 | 0 | 0 | 0 | 0 | 220607 | 12082 | 208525 | 220607 | 186260 | 0 | 0 | 0 | 186260 | 186260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 | 2021-01-08 | QTR3 | 20/21 | 507 | 258724.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A0 | 44327015201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 218 | 155 | 63 | 0 | 0 | 38 | 0 | 341127 | 18594 | 322533 | 328648 | 362626 | 0 | 0 | 0 | 362626 | 362626 | 0 | -12479 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | -12479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12479 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 | 2020-11-17 | QTR2 | 20/21 | 512 | 395487.73 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A5 | 44417615201 | 2020-06-02 | QTR4 | 19/20 | 1 | 0 | 90 | 169 | 165 | 4 | 0 | 0 | 79 | 0 | 755986 | 39900 | 716086 | 755986 | 748590 | 0 | 0 | 0 | 748590 | 748590 | 0 | 0 | 52 | 0 | 0 | 3648 | 0 | 0 | 0 | 8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12434 | 0 | F980461222 | OHL USA INC | N/A | N/A | N/A | N/A | 2021-06-23 | QTR4 | 20/21 | 2021-03-17 | QTR3 | 20/21 | 514 | 843431.25 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W26 | 24271525201 | 2014-09-05 | QTR1 | 14/15 | 3 | 7 | 1100 | 1747 | 2097 | -350 | 350 | 0 | 450 | 197 | 204975000 | 150000 | 204825000 | 206461939 | 205886429 | -5989463 | 1323936 | -4665526 | 201220903 | 190316791 | -10375239 | 1486939 | 258 | 0 | 0 | 153517 | 0 | 0 | 30 | 575563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 771389 | 0 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-05-13 | QTR4 | 20/21 | 2020-08-21 | QTR1 | 20/21 | 513 | 204975000 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 192 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y62 | 23831925201 | 2017-03-21 | QTR3 | 16/17 | 3 | 6 | 950 | 1198 | 1188 | 10 | 0 | 0 | 145 | 103 | 22219000 | 150000 | 22069000 | 22351916 | 22222555 | 0 | 0 | 0 | 22222555 | 22255595 | 54139 | 132916 | 69 | 0 | 0 | 40787 | 0 | 0 | 0 | 90621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 14091 | 0 | 0 | 1 | 10864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 156363 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2020-10-30 | QTR2 | 20/21 | 2020-09-14 | QTR1 | 20/21 | 515 | 44314871 | B8 | ACC - DESIGN/BUILD - MAJOR | 1 | 76 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z19 | 43927315201 | 2018-04-03 | QTR4 | 17/18 | 1 | 0 | 130 | 145 | 501 | -356 | 356 | 0 | 15 | 0 | 149935 | 9480 | 140455 | 149935 | 128601 | -51092 | 0 | -51092 | 77509 | 77509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Z23-0961349 | PENNSYLVANIA NATIONAL MUTUAL CASUALTY I | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-05-27 | QTR4 | 19/20 | 513 | 204099 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 0 | 10 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8 |  |  | 8 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2019-10-17 | QTR2 | 19/20 | 513 | 307382 |  |  | 19 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z32 | 43927515201 | 2018-02-06 | QTR3 | 17/18 | 2 | 1 | 680 | 927 | 912 | 15 | 0 | 0 | 247 | 0 | 3899386 | 50000 | 3849386 | 3941689 | 3941568 | 0 | 0 | 0 | 3941568 | 3896961 | -2304 | 42303 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 | 2020-11-05 | QTR2 | 20/21 | 514 | 4041614 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z46 | 44116815201 | 2018-11-06 | QTR2 | 18/19 | 2 | 2 | 136 | 657 | 715 | -58 | 58 | 0 | 256 | 265 | 546235 | 28279 | 517956 | 620855 | 527394 | -96570 | 0 | -96570 | 430824 | 526966 | 96143 | 74620 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 245 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2021-04-19 | QTR4 | 20/21 | 2021-02-12 | QTR3 | 20/21 | 514 | 603864 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z61 | 43544625201 | 2019-03-20 | QTR3 | 18/19 | 1 | 0 | 550 | 693 | 693 | 0 | 0 | 0 | 143 | 0 | 2660660 | 50000 | 2610660 | 2660660 | 2610660 | 0 | 0 | 0 | 2610660 | 2610660 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2021-05-27 | QTR4 | 20/21 | 2021-03-30 | QTR3 | 20/21 | 509 | 2903534 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 80 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z64 | 44121015201 | 2018-08-07 | QTR1 | 18/19 | 2 | 7 | 420 | 552 | 552 | 0 | 0 | 0 | 86 | 46 | 4022402 | 50000 | 3972402 | 4286073 | 4275710 | 0 | 0 | 0 | 4275710 | 4234199 | -37972 | 263671 | 31 | 0 | 0 | 124080 | 0 | 0 | 46 | 104836 | 11429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40146 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 274759 | 14901 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-10 | QTR2 | 20/21 | 2020-07-07 | QTR1 | 20/21 | 513 | 4100417.85 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | -199 | 4115 | 84 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z77 | 43912115201 | 2019-07-02 | QTR1 | 19/20 | 2 | 1 | 200 | 327 | 326 | 1 | 0 | 0 | 127 | 0 | 3278490 | 50000 | 3228490 | 3271086 | 3476815 | 0 | 0 | 0 | 3476815 | 3410719 | -66096 | -7404 | 72 | 0 | 0 | 23209 | 0 | 0 | 0 | -7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15805 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-16 | QTR2 | 20/21 | 2020-08-17 | QTR1 | 20/21 | 513 | 3806383.67 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-08-11 | QTR1 | 20/21 | 513 | 141232 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z85 | 43923615201 | 2019-08-06 | QTR1 | 19/20 | 1 | 1 | 130 | 222 | 237 | -15 | 15 | 0 | 44 | 48 | 1444444 | 50000 | 1394444 | 1444444 | 1364062 | -69930 | 0 | -69930 | 1294132 | 1282257 | -11875 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 | 2020-07-28 | QTR1 | 20/21 | 509 | 1314465.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z91 | 43912215201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 115 | 121 | 120 | 1 | 0 | 0 | 6 | 0 | 1447000 | 50000 | 1397000 | 1447000 | 1407072 | 0 | 0 | 0 | 1407072 | 1407072 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-01 | QTR2 | 20/21 | 2020-05-19 | QTR4 | 19/20 | 509 | 1302060.71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z98 | 43618725201 | 2020-01-07 | QTR3 | 19/20 | 1 | 0 | 90 | 124 | 125 | -1 | 1 | 0 | 34 | 0 | 675628 | 31129 | 644499 | 675628 | 649188 | 0 | 0 | 0 | 649188 | 649188 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2020-11-25 | QTR2 | 20/21 | 2020-08-13 | QTR1 | 20/21 | 514 | 631570 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | -289635 | -403730 | 22 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 17 | 0 | 0 | -453468 | 0 |  | CO
06CO | 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | -2140213 | 1115676 | 16 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6424 | 42736915201 | 2019-04-24 | QTR4 | 18/19 | 3 | 8 | 385 | 412 | 361 | 51 | 0 | 0 | 27 | 0 | 31696367 | 150560 | 31545807 | 32356389 | 32549528 | 0 | 2000000 | 2000000 | 34549528 | 32091160 | -2458368 | 660022 | 12 | 0 | 0 | 835731 | 0 | 0 | 0 | 255737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -351436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33504 | 0 | 0 | 0 | 3031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709560 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-03-16 | QTR3 | 20/21 | 2021-01-15 | QTR3 | 20/21 | 636 | 37329749.69 | B5:B2:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 96399 | 60 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | -201766 | 12198 | 24 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6442 | 43063735201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 419 | 517 | 474 | 43 | 0 | 0 | 58 | 40 | 12892744 | 274969 | 12617775 | 13383683 | 13072251 | 0 | 790000 | 790000 | 13862251 | 12904020 | -845455 | 490939 | 35 | 0 | 40 | 504378 | 375054 | 0 | 0 | 22795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 550031 | 375054 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-11-13 | QTR2 | 20/21 | 2020-05-01 | QTR4 | 19/20 | 606 | 14924931.96 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6447 | 43791515201 | 2019-04-24 | QTR4 | 18/19 | 4 | 2 | 250 | 272 | 239 | 33 | 0 | 0 | 22 | 0 | 2469000 | 50215 | 2418785 | 2562153 | 2344210 | 0 | 150000 | 150000 | 2494210 | 2343341 | -150869 | 93153 | 14 | 0 | 0 | 48601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44551 | 4910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93153 | 4910 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 | 2020-09-29 | QTR1 | 20/21 | 636 | 2116609.4 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6449 | 43345545201 | 2019-02-27 | QTR3 | 18/19 | 4 | 3 | 280 | 311 | 311 | 0 | 0 | 0 | 31 | 0 | 2745127 | 50000 | 2695127 | 2934099 | 2882088 | 0 | 0 | 0 | 2882088 | 2869467 | -12621 | 188972 | 8 | 0 | 0 | 201958 | 20245 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14623 | 0 | 0 | 0 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221836 | 20245 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 | 2020-08-19 | QTR1 | 20/21 | 606 | 2941132.7 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6450 | 40557565201 | 2019-06-12 | QTR4 | 18/19 | 4 | 11 | 400 | 424 | 380 | 44 | 0 | 0 | 24 | 0 | 16353017 | 242694 | 16110323 | 17066081 | 16492362 | 0 | 1340000 | 1340000 | 17832362 | 16289899 | -1542462 | 713064 | 5 | 0 | 0 | 385449 | 21500 | 0 | 0 | 206212 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104075 | 54241 | 0 | 0 | 0 | 0 | 0 | 0 | 847864 | 76615 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-06-24 | QTR4 | 20/21 | 2021-03-30 | QTR3 | 20/21 | 606 | 18314994.47 | B2:B5:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6456 | 44001315201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 140 | 149 | 132 | 17 | 0 | 0 | 9 | 0 | 277873 | 14914 | 262959 | 277873 | 253147 | 0 | 0 | 0 | 253147 | 252697 | -451 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115 | 0 | F203345775 | MAGGOLC INC. | N/A | N/A | N/A | N/A | 2021-01-13 | QTR3 | 20/21 | 2020-08-27 | QTR1 | 20/21 | 613 | 307708.25 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 0 | 77 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 27177 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6463 | 43791615201 | 2019-01-30 | QTR3 | 18/19 | 4 | 0 | 160 | 220 | 219 | 1 | 0 | 0 | 60 | 0 | 893110 | 47891 | 845219 | 893110 | 829996 | 0 | 0 | 0 | 829996 | 829996 | 0 | 0 | 47 | 0 | 0 | 3918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 4477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11695 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-02-15 | QTR3 | 20/21 | 2020-08-10 | QTR1 | 20/21 | 613 | 974751.05 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6464 | 43908815201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 300 | 409 | 389 | 20 | 0 | 0 | 109 | 0 | 2747184 | 50000 | 2697184 | 2747184 | 2689934 | 0 | 160000 | 160000 | 2849934 | 2684826 | -165108 | 0 | 55 | 0 | 0 | 12619 | 0 | 0 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33650 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 | 2021-01-28 | QTR3 | 20/21 | 613 | 2857611.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | -846 | 30818 | 24 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6471 | 43998315201 | 2019-10-30 | QTR2 | 19/20 | 3 | 1 | 200 | 257 | 257 | 0 | 0 | 0 | 57 | 0 | 1419001 | 50000 | 1369001 | 1428592 | 1341311 | 0 | 0 | 0 | 1341311 | 1340742 | -569 | 9591 | 36 | 0 | 0 | 9103 | 0 | 0 | 0 | 4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14767 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 | 2021-03-19 | QTR3 | 20/21 | 636 | 1482286.6 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6473 | 43326425201 | 2020-01-29 | QTR3 | 19/20 | 2 | 0 | 240 | 279 | 215 | 64 | 0 | 0 | 39 | 0 | 1569997 | 50995 | 1519002 | 1569997 | 1553340 | 0 | 100000 | 100000 | 1653340 | 1548938 | -104402 | 0 | 30 | 0 | 0 | 14486 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32803 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-02-26 | QTR3 | 20/21 | 2020-11-20 | QTR2 | 20/21 | 636 | 1744257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6474 | 43991915201 | 2019-10-30 | QTR2 | 19/20 | 2 | 0 | 280 | 327 | 264 | 63 | 0 | 0 | 47 | 0 | 2171998 | 50000 | 2121998 | 2171998 | 2087179 | 0 | 80000 | 80000 | 2167179 | 2084071 | -83108 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 14701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14701 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-01-28 | QTR3 | 20/21 | 2020-10-05 | QTR2 | 20/21 | 613 | 1943700.4 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6477 | 44281315201 | 2019-03-27 | QTR3 | 18/19 | 9 | 4 | 360 | 432 | 432 | 0 | 0 | 0 | 54 | 18 | 2060596 | 50000 | 2010596 | 2075271 | 2107347 | 0 | 0 | 0 | 2107347 | 2106923 | -424 | 14675 | 29 | 0 | 18 | 12276 | 0 | 0 | 0 | 18162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 53089 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2020-12-14 | QTR2 | 20/21 | 2020-10-09 | QTR2 | 20/21 | 606 | 2038302.5 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6484 | 44017515201 | 2019-09-25 | QTR1 | 19/20 | 2 | 0 | 180 | 300 | 300 | 0 | 0 | 0 | 120 | 0 | 800000 | 41439 | 758561 | 800000 | 759142 | 0 | 0 | 0 | 759142 | 758896 | -246 | 0 | 64 | 0 | 0 | 3076 | 0 | 0 | 0 | 5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13058 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-02-22 | QTR3 | 20/21 | 2021-01-13 | QTR3 | 20/21 | 636 | 865771.05 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6499 | 43992215201 | 2020-01-29 | QTR3 | 19/20 | 2 | 0 | 160 | 182 | 135 | 47 | 0 | 0 | 22 | 0 | 630688 | 29131 | 601557 | 630688 | 630936 | 0 | 0 | 0 | 630936 | 630438 | -499 | 0 | 18 | 0 | 0 | 8611 | 0 | 0 | 0 | 4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16057 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 | 2020-12-01 | QTR2 | 20/21 | 636 | 547117.1 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6523 | 42918535201 | 2020-01-29 | QTR3 | 19/20 | 2 | 2 | 250 | 307 | 230 | 77 | 0 | 0 | 57 | 0 | 1588502 | 50000 | 1538502 | 1626096 | 1468338 | 0 | 100000 | 100000 | 1568338 | 1462739 | -101006 | 37594 | 45 | 0 | 0 | 12813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37551 | 19916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50364 | 19916 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-03-10 | QTR3 | 20/21 | 2020-12-27 | QTR2 | 20/21 | 613 | 1654598.85 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J97 | 43338115201 | 2016-09-29 | QTR1 | 16/17 | 3 | 5 | 700 | 1353 | 1353 | 0 | 0 | 0 | 371 | 282 | 14830791 | 150000 | 14680791 | 16868333 | 16284955 | 0 | 0 | 0 | 16284955 | 13510574 | -2748287 | 2037542 | 277 | 0 | 0 | 189712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 1897649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 2102488 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-03-17 | QTR3 | 20/21 | 2020-12-23 | QTR2 | 20/21 | 606 | 15266369.1 |  |  | 0 | 94 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K57 | 43854015201 | 2017-05-15 | QTR4 | 16/17 | 1 | 0 | 750 | 1065 | 881 | 184 | 0 | 0 | 315 | 0 | 3582848 | 50000 | 3532848 | 3582848 | 3528511 | 0 | 0 | 0 | 3528511 | 3528511 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30013 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-10-23 | QTR2 | 20/21 | 2020-09-09 | QTR1 | 20/21 | 606 | 3999000 | LBDB | LOW BID DESIGN BUILD | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K74 | 43652715201 | 2019-04-25 | QTR4 | 18/19 | 1 | 0 | 300 | 359 | 351 | 8 | 0 | 0 | 59 | 0 | 4041049 | 50000 | 3991049 | 4041049 | 3981909 | 0 | 0 | 0 | 3981909 | 3981877 | -32 | 0 | 37 | 0 | 0 | 13129 | 0 | 0 | 0 | 16554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29684 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-03-04 | QTR3 | 20/21 | 2021-01-25 | QTR3 | 20/21 | 613 | 4437637.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 0 | 139878 | 27 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L73 | 44183715201 | 2019-03-28 | QTR3 | 18/19 | 3 | 0 | 180 | 256 | 253 | 3 | 0 | 0 | 76 | 0 | 1046629 | 50000 | 996629 | 1046629 | 1032137 | 0 | 0 | 0 | 1032137 | 1030814 | -1322 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13324 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 613 | 1027325.45 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L77 | 44059015201 | 2019-02-28 | QTR3 | 18/19 | 1 | 0 | 150 | 227 | 212 | 15 | 0 | 0 | 77 | 0 | 569569 | 25452 | 544117 | 569569 | 532425 | 0 | 0 | 0 | 532425 | 532327 | -98 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21238 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-10-14 | QTR2 | 20/21 | 2020-08-04 | QTR1 | 20/21 | 613 | 521617.9 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | -189 | -1000 | 35 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L95 | 44174015201 | 2019-10-31 | QTR2 | 19/20 | 1 | 1 | 290 | 307 | 247 | 60 | 0 | 0 | 17 | 0 | 6166186 | 64668 | 6101518 | 6166186 | 6056649 | 0 | 796000 | 796000 | 6852649 | 6054106 | -798543 | 0 | 14 | 0 | 0 | 7070 | 0 | 0 | 0 | 34534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50206 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 | 2020-11-17 | QTR2 | 20/21 | 636 | 6464443.31 | A5:B5 | ICC - BAM/BONUS:ACC - INCENTIVE/DISINCENTIVE | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M35 | 42934165201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 140 | 213 | 201 | 12 | 0 | 0 | 73 | 0 | 550550 | 26336 | 524214 | 550550 | 522745 | 0 | 0 | 0 | 522745 | 522024 | -721 | 0 | 54 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-18 | QTR3 | 20/21 | 2021-02-05 | QTR3 | 20/21 | 636 | 547294.25 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M59 | 43634425201 | 2020-02-27 | QTR3 | 19/20 | 1 | 0 | 100 | 124 | 124 | 0 | 0 | 0 | 24 | 0 | 548409 | 24409 | 524000 | 548409 | 466503 | 0 | 0 | 0 | 466503 | 466503 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-12-22 | QTR2 | 20/21 | 2020-10-10 | QTR2 | 20/21 | 636 | 490515.2 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7375 | 25729865201 | 2017-02-22 | QTR3 | 16/17 | 2 | 6 | 335 | 578 | 588 | -10 | 10 | 0 | 134 | 109 | 8414444 | 81000 | 8333444 | 8827124 | 8758066 | -36450 | 0 | -36450 | 8721616 | 8915602 | 257489 | 411474 | 99 | 0 | 11 | 14363 | 5606 | 0 | 83 | 164873 | 25488 | 0 | 0 | 15135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 208722 | 31094 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-04-08 | QTR4 | 20/21 | 2019-01-22 | QTR3 | 18/19 | 798 | 9174081.12 | B5 | ACC - INCENTIVE/DISINCENTIVE | 29 | 35 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7403 | 43484815201 | 2018-05-23 | QTR4 | 17/18 | 4 | 11 | 365 | 520 | 520 | 0 | 0 | 0 | 106 | 49 | 15246325 | 150000 | 15096325 | 16369545 | 16674514 | 0 | 0 | 0 | 16674514 | 16720307 | 65791 | 1123220 | 63 | 0 | 14 | 656978 | 126004 | 0 | 35 | 570684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28923 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1198739 | 126713 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-11-06 | QTR2 | 20/21 | 2020-03-24 | QTR3 | 19/20 | 796 | 16929302.14 |  |  | 10 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 688152 | 70 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 0 | 91 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8 |  |  | 45 | 73 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7413 | 43658815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 3 | 480 | 699 | 697 | 2 | 0 | 0 | 200 | 19 | 26892177 | 150000 | 26742177 | 27245569 | 27594120 | -41000 | 0 | -41000 | 27553120 | 27404700 | -148420 | 353392 | 151 | 0 | 0 | 138794 | 0 | 0 | 19 | 407728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 422365 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-12-30 | QTR2 | 20/21 | 2020-08-27 | QTR1 | 20/21 | 714 | 31660666.96 |  |  | 19 | 49 | 0 | 0 | -124158 | 0 |  | CO
07CO | 07 | T7414 | 43571915201 | 2018-03-28 | QTR3 | 17/18 | 1 | 7 | 275 | 584 | 562 | 22 | 0 | 0 | 203 | 106 | 2614444 | 50000 | 2564444 | 2751684 | 2735520 | 0 | 0 | 0 | 2735520 | 2737146 | 1626 | 137240 | 161 | 0 | 0 | 51550 | 0 | 0 | 106 | 99770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 151320 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-01-14 | QTR3 | 20/21 | 2020-01-21 | QTR3 | 19/20 | 799 | 3125000 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7419 | 43050225201 | 2019-02-27 | QTR3 | 18/19 | 1 | 0 | 120 | 272 | 272 | 0 | 0 | 0 | 52 | 100 | 987665 | 50000 | 937665 | 987665 | 987634 | 0 | 0 | 0 | 987634 | 987634 | 0 | 0 | 27 | 0 | 100 | 31825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 31825 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-03-14 | QTR3 | 19/20 | 796 | 1403000 |  |  | 100 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7420 | 43982945201 | 2018-12-05 | QTR2 | 18/19 | 1 | 0 | 365 | 523 | 584 | -61 | 61 | 0 | 158 | 0 | 1212499 | 50000 | 1162499 | 1212499 | 1154516 | -101565 | 0 | -101565 | 1052951 | 1052959 | 8 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2021-01-15 | QTR3 | 20/21 | 796 | 1500000 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7425 | 43982965201 | 2019-09-25 | QTR1 | 19/20 | 2 | 2 | 185 | 228 | 228 | 0 | 0 | 0 | 27 | 16 | 914914 | 49000 | 865914 | 939896 | 895662 | 0 | 0 | 0 | 895662 | 895638 | -24 | 24982 | 18 | 0 | 1 | 1723 | 0 | 0 | 15 | 25632 | 14104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 27355 | 14104 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2021-01-26 | QTR3 | 20/21 | 2020-11-06 | QTR2 | 20/21 | 798 | 1060000 |  |  | 4 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 45939 | 13 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7431 | 41685615201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 200 | 352 | 391 | -39 | 39 | 0 | 152 | 0 | 2024792 | 50000 | 1974792 | 2024792 | 1923484 | -64935 | 0 | -64935 | 1858549 | 1857569 | -979 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-02-09 | QTR3 | 20/21 | 2020-10-19 | QTR2 | 20/21 | 796 | 2200000 |  |  | 0 | 71 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | -16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 799 | 490000 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7435 | 43731215201 | 2019-10-30 | QTR2 | 19/20 | 1 | 2 | 425 | 535 | 345 | 190 | 0 | 0 | 58 | 52 | 20077627 | 150000 | 19927627 | 19707738 | 19775513 | 0 | 1600000 | 1600000 | 21375513 | 19707851 | -1667662 | -369888 | 46 | 0 | 0 | -369888 | 0 | 0 | 0 | 15538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -354350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-17 | QTR4 | 20/21 | 2020-12-16 | QTR2 | 20/21 | 796 | 32430000 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7436 | 43648515201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 270 | 348 | 313 | 35 | 0 | 0 | 38 | 40 | 6816208 | 60000 | 6756208 | 6816208 | 6910378 | 0 | 0 | 0 | 6910378 | 6856508 | -53870 | 0 | 53 | 0 | 0 | 43044 | 0 | 0 | 0 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44444 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 | 2021-03-12 | QTR3 | 20/21 | 799 | 6893701.91 |  |  | 40 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7440 | 44286215201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 116 | 167 | 163 | 4 | 0 | 0 | 30 | 21 | 2725693 | 50000 | 2675693 | 2725693 | 2560514 | 0 | 0 | 0 | 2560514 | 2560514 | 0 | 0 | 42 | 0 | 0 | 20000 | 0 | 0 | 0 | 3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23652 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-02 | QTR2 | 20/21 | 2020-10-06 | QTR2 | 20/21 | 798 | 2929941.26 |  |  | 21 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7441 | 43764315201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 122 | 148 | 142 | 6 | 0 | 0 | 26 | 0 | 2094475 | 50000 | 2044475 | 2094475 | 2116984 | 0 | 0 | 0 | 2116984 | 2111225 | -5759 | 0 | 2 | 0 | 0 | 1658 | 0 | 0 | 0 | 11303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12961 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-06-21 | QTR4 | 20/21 | 2021-04-06 | QTR4 | 20/21 | 799 | 1713900 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7443 | 44109815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 0 | 149 | 169 | 169 | 0 | 0 | 0 | 20 | 0 | 1372094 | 50000 | 1322094 | 1372094 | 1285441 | 0 | 0 | 0 | 1285441 | 1284319 | -1122 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-03-01 | QTR3 | 20/21 | 2020-11-30 | QTR2 | 20/21 | 796 | 1324000 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7452 | 43969915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 90 | 161 | 160 | 1 | 0 | 0 | 71 | 0 | 533787 | 28000 | 505787 | 533787 | 537223 | 0 | 0 | 0 | 537223 | 537223 | 0 | 0 | 38 | 0 | 0 | 23754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 23754 | 0 | F465262082 | HARTMAN CIVIL CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-06-03 | QTR4 | 20/21 | 2021-02-04 | QTR3 | 20/21 | 798 | 665000 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7453 | 44582415201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 80 | 147 | 145 | 2 | 0 | 0 | 67 | 0 | 607102 | 20000 | 587102 | 607102 | 507221 | 0 | 0 | 0 | 507221 | 507221 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 | 2021-01-22 | QTR3 | 20/21 | 796 | 562013.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7454 | 44582715201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 115 | 117 | 117 | 0 | 0 | 0 | 2 | 0 | 273542 | 8200 | 265342 | 273542 | 259612 | 0 | 0 | 0 | 259612 | 259612 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-06-25 | QTR4 | 20/21 | 2021-05-03 | QTR4 | 20/21 | 799 | 245561.6 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7457 | 44541015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 200 | 218 | 102 | 116 | 0 | 0 | 18 | 0 | 1090411 | 50000 | 1040411 | 1090411 | 1018989 | 0 | 0 | 0 | 1018989 | 1018989 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-03 | QTR4 | 20/21 | 2021-02-03 | QTR3 | 20/21 | 799 | 1330400 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 625193 | 45 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M31 | 43751715201 | 2019-03-13 | QTR3 | 18/19 | 1 | 2 | 360 | 436 | 435 | 1 | 0 | 0 | 43 | 33 | 2064981 | 50000 | 2014981 | 1997687 | 1923224 | 0 | 0 | 0 | 1923224 | 1923189 | -35 | -67294 | 14 | 0 | 33 | -66214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | -26781 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-12-29 | QTR2 | 20/21 | 2020-08-21 | QTR1 | 20/21 | 799 | 2265000 |  |  | 33 | 29 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M35 | 43642115201 | 2019-04-10 | QTR4 | 18/19 | 2 | 1 | 180 | 246 | 246 | 0 | 0 | 0 | 36 | 30 | 3208889 | 50000 | 3158889 | 3213321 | 3310989 | 0 | 0 | 0 | 3310989 | 3270137 | -40853 | 4433 | 29 | 0 | 0 | 0 | 0 | 0 | 30 | 34925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34925 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-05-10 | QTR4 | 20/21 | 2020-09-25 | QTR1 | 20/21 | 798 | 3417308.79 |  |  | 30 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M50 | 42905925201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 80 | 125 | 114 | 11 | 0 | 0 | 45 | 0 | 257038 | 11000 | 246038 | 257038 | 238009 | 0 | 0 | 0 | 238009 | 238009 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-10-15 | QTR2 | 20/21 | 2019-12-20 | QTR2 | 19/20 | 796 | 255036.03 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M53 | 43878315201 | 2019-07-10 | QTR1 | 19/20 | 1 | 0 | 210 | 266 | 264 | 2 | 0 | 0 | 56 | 0 | 1279713 | 50000 | 1229713 | 1279713 | 1030596 | 0 | 0 | 0 | 1030596 | 1029149 | -1447 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 48740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48740 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-12 | QTR3 | 20/21 | 2020-10-02 | QTR2 | 20/21 | 796 | 2158375.3 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M74 | 43955115201 | 2019-09-11 | QTR1 | 19/20 | 1 | 0 | 260 | 282 | 171 | 111 | 0 | 0 | 22 | 0 | 555000 | 48000 | 507000 | 555000 | 507000 | 0 | 0 | 0 | 507000 | 507000 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2020-11-09 | QTR2 | 20/21 | 2020-07-31 | QTR1 | 20/21 | 796 | 1075906 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M78 | 43624315201 | 2019-12-11 | QTR2 | 19/20 | 1 | 0 | 147 | 244 | 244 | 0 | 0 | 0 | 73 | 24 | 761530 | 25000 | 736530 | 761530 | 782626 | 0 | 0 | 0 | 782626 | 757851 | -24775 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 24 | 24463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24463 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-04-23 | QTR4 | 20/21 | 2021-02-18 | QTR3 | 20/21 | 796 | 720000 |  |  | 24 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M87 | 43952515201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 105 | 113 | 106 | 7 | 0 | 0 | 8 | 0 | 211449 | 7500 | 203949 | 219152 | 195461 | 0 | 0 | 0 | 195461 | 195461 | 0 | 7703 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7703 | 7703 | 0 | 0 | 0 | 0 | 0 | 0 | 7703 | 7703 | F812720632 | FLORIDA SILT AND SOD INC | N/A | N/A | N/A | N/A | 2021-03-05 | QTR3 | 20/21 | 2020-07-20 | QTR1 | 20/21 | 799 | 206943.72 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M88 | 43751915201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 300 | 329 | 196 | 133 | 0 | 0 | 29 | 0 | 748000 | 50000 | 698000 | 748000 | 716109 | 0 | 0 | 0 | 716109 | 716109 | 0 | 0 | 7 | 0 | 0 | 18109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18109 | 0 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-28 | QTR4 | 20/21 | 2021-04-02 | QTR4 | 20/21 | 799 | 1657500 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 799 | 280000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M90 | 43983015201 | 2020-02-12 | QTR3 | 19/20 | 1 | 0 | 100 | 126 | 126 | 0 | 0 | 0 | 22 | 4 | 682863 | 38200 | 644663 | 682863 | 661465 | 0 | 0 | 0 | 661465 | 661465 | 0 | 0 | 16 | 0 | 4 | 22230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22230 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-11-24 | QTR2 | 20/21 | 2020-10-16 | QTR2 | 20/21 | 796 | 786200 |  |  | 4 | 6 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M92 | 44146815201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 162 | 151 | 11 | 0 | 0 | 42 | 0 | 657608 | 35295 | 622313 | 657608 | 639093 | 0 | 0 | 0 | 639093 | 639093 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-05-21 | QTR4 | 20/21 | 2021-03-15 | QTR3 | 20/21 | 799 | 830250 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M95 | 43762315201 | 2020-04-08 | QTR4 | 19/20 | 1 | 1 | 120 | 149 | 149 | 0 | 0 | 0 | 29 | 0 | 2367977 | 50000 | 2317977 | 2362575 | 2251785 | 0 | 0 | 0 | 2251785 | 2251785 | 0 | -5402 | 11 | 0 | 0 | 9437 | 0 | 0 | 0 | 5930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11036 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-05-25 | QTR4 | 20/21 | 2021-01-12 | QTR3 | 20/21 | 799 | 2542381.46 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M97 | 44024515201 | 2020-04-08 | QTR4 | 19/20 | 1 | 1 | 90 | 124 | 128 | -4 | 4 | 0 | 34 | 0 | 1873216 | 50000 | 1823216 | 1882322 | 1896442 | -6760 | 0 | -6760 | 1889682 | 1877971 | -11712 | 9105 | 24 | 0 | 0 | 1975 | 0 | 0 | 0 | 9105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-04-22 | QTR4 | 20/21 | 2020-12-08 | QTR2 | 20/21 | 799 | 1912250 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 0 | 0 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N04 | 44580315201 | 2020-01-08 | QTR3 | 19/20 | 1 | 0 | 50 | 61 | 61 | 0 | 0 | 0 | 11 | 0 | 342938 | 15400 | 327538 | 342938 | 334918 | 0 | 0 | 0 | 334918 | 334918 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2020-12-16 | QTR2 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 796 | 323540.7 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N06 | 44108415201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 150 | 220 | 218 | 2 | 0 | 0 | 70 | 0 | 2651273 | 50000 | 2601273 | 2651273 | 2594154 | 0 | 0 | 0 | 2594154 | 2581698 | -12456 | 0 | 43 | 0 | 0 | 17137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17137 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-06-10 | QTR4 | 20/21 | 2021-04-16 | QTR4 | 20/21 | 796 | 2513322.8 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N20 | 25693135201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 60 | 90 | 98 | -8 | 8 | 0 | 26 | 4 | 217378 | 12000 | 205378 | 261168 | 240911 | -8360 | 0 | -8360 | 232551 | 232551 | 0 | 43790 | 17 | 0 | 0 | 0 | 0 | 3 | 4 | 43790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 43790 | 0 | F341337287 | AKCA LLC | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 | 2020-12-13 | QTR2 | 20/21 | 799 | 350000 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N22 | 41101455201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 150 | 191 | 191 | 0 | 0 | 0 | 41 | 0 | 1199360 | 50000 | 1149360 | 1199360 | 1220405 | 0 | 0 | 0 | 1220405 | 1219955 | -449 | 0 | 26 | 0 | 0 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 | 2021-03-19 | QTR3 | 20/21 | 798 | 1261100 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N47 | 43955015201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 120 | 120 | 71 | 49 | 0 | 0 | 0 | 0 | 178219 | 9700 | 168519 | 178219 | 165324 | 0 | 0 | 0 | 165324 | 165324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-05-12 | QTR4 | 20/21 | 2021-04-12 | QTR4 | 20/21 | 796 | 214800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R14 | 43402715201 | 2019-01-22 | QTR3 | 18/19 | 1 | 1 | 485 | 580 | 577 | 3 | 0 | 0 | 50 | 45 | 3891051 | 50000 | 3841051 | 3854521 | 3786721 | 0 | 0 | 0 | 3786721 | 3786721 | 0 | -36530 | 18 | 0 | 0 | -197831 | 0 | 0 | 0 | 11095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36530 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2020-12-28 | QTR2 | 20/21 | 2020-10-31 | QTR2 | 20/21 | 796 | 4668000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | -2369264 | 11648418 | 291 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N20 | 42714615201 | 2014-06-23 | QTR4 | 13/14 | 8 | 19 | 1150 | 2322 | 2322 | 0 | 0 | 0 | 537 | 635 | 54444321 | 150000 | 54294321 | 55997037 | 56078061 | -16000 | 0 | -16000 | 56062061 | 54752460 | -1173828 | 1552716 | 341 | 0 | 170 | 1375824 | 0 | 0 | 0 | 111160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 463 | -106171 | 0 | 0 | 0 | 31771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 1428816 | 0 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 | 2021-02-26 | QTR3 | 20/21 | 854 | 59644380.55 | B0:B8 | ACC - LUMP SUM:ACC - DESIGN/BUILD - MAJOR | 2 | 198 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N58 | 40610315201 | 2015-05-19 | QTR4 | 14/15 | 2 | 34 | 1210 | 1688 | 1688 | 0 | 0 | 0 | 274 | 204 | 49459029 | 150000 | 49309029 | 53635234 | 54832716 | -13000 | 0 | -13000 | 54819716 | 54685458 | -82853 | 4176205 | 153 | 0 | 18 | 308998 | 88734 | 0 | 43 | 1321673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 2378855 | 0 | 0 | 0 | 139746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 4149273 | 88734 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-02-19 | QTR3 | 20/21 | 2020-06-14 | QTR4 | 19/20 | 854 | 55428349.1 |  |  | 0 | 121 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1438 | 15 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 991193 | 5429118 | 149 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 127 | 0 | 0 | -88404 | 0 |  | DO
08DO | 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | -551574 | 4550344 | 122 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12 |  |  | 1 | 82 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 496445 | 1556062 | 183 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 0 |  |  | 36 | 99 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q10 | 43661915201 | 2016-06-14 | QTR4 | 15/16 | 1 | 3 | 949 | 1351 | 1351 | 0 | 0 | 0 | 402 | 0 | 29944488 | 150000 | 29794488 | 30283733 | 28559596 | -3000 | 0 | -3000 | 28556596 | 28668240 | 121829 | 339245 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 70922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 0 | 392961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 0 | 463883 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | QTR4 | 20/21 | 2020-08-28 | QTR1 | 20/21 | 854 | 22863153.07 |  |  | 0 | 90 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 1490912 | 597011 | 172 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09 |  |  | 16 | 84 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q85 | 43651715201 | 2018-01-23 | QTR3 | 17/18 | 2 | 10 | 620 | 882 | 882 | 0 | 0 | 0 | 229 | 33 | 35890871 | 150000 | 35740871 | 36842857 | 35395810 | -10000 | 0 | -10000 | 35385810 | 36250675 | 867370 | 951986 | 161 | 0 | 18 | 192480 | 0 | 0 | 8 | 52057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348416 | 0 | 0 | 7 | 364088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 957041 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2021-05-07 | QTR4 | 20/21 | 2020-12-21 | QTR2 | 20/21 | 854 | 26738962.29 |  |  | 11 | 68 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q93 | 42933915201 | 2017-12-12 | QTR2 | 17/18 | 1 | 17 | 600 | 929 | 901 | 28 | 0 | 0 | 227 | 102 | 20384811 | 150000 | 20234811 | 21680602 | 22044940 | 0 | 0 | 0 | 22044940 | 22209747 | 178193 | 1295791 | 132 | 0 | 0 | 87536 | 0 | 0 | 0 | 1014524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 194931 | 0 | 0 | 0 | 257578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1427776 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-02-16 | QTR3 | 20/21 | 2020-12-04 | QTR2 | 20/21 | 854 | 18579757.33 |  |  | 0 | 95 | 0 | 0 | -126793 | 0 |  | DO
08DO | 08 | E8Q94 | 43947815201 | 2018-03-27 | QTR3 | 17/18 | 4 | 6 | 525 | 723 | 723 | 0 | 0 | 0 | 198 | 0 | 18860577 | 150000 | 18710577 | 18748056 | 18778411 | -36500 | 0 | -36500 | 18741911 | 19317651 | 583633 | -112521 | 130 | 0 | 0 | -519709 | 0 | 0 | 0 | 381340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 106099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -32270 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-10-27 | QTR2 | 20/21 | 2020-06-30 | QTR4 | 19/20 | 854 | 29028001.13 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 70000 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49 |  |  | 18 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | -3862 | 142527 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R58 | 43799115201 | 2019-05-14 | QTR4 | 18/19 | 2 | 4 | 315 | 471 | 471 | 0 | 0 | 0 | 128 | 28 | 10199910 | 125662 | 10074248 | 10499910 | 10355353 | -12500 | 0 | -12500 | 10342853 | 10192921 | -149932 | 300000 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 35979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2089 | 0 | 0 | 23 | 332378 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 389600 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-17 | QTR4 | 20/21 | 2020-12-21 | QTR2 | 20/21 | 854 | 11724624.47 |  |  | 28 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R76 | 43945715201 | 2019-03-12 | QTR3 | 18/19 | 1 | 6 | 415 | 477 | 405 | 72 | 0 | 0 | 62 | 0 | 12161596 | 125391 | 12036204 | 11888308 | 12421672 | 0 | 0 | 0 | 12421672 | 12302929 | -84308 | -273288 | 21 | 0 | 0 | -340280 | 0 | 0 | 0 | 51302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287059 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 | 2020-06-30 | QTR4 | 19/20 | 854 | 12670789.67 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 0 | 94072 | 5 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R95 | 43560575201 | 2019-09-10 | QTR1 | 19/20 | 1 | 5 | 385 | 466 | 438 | 28 | 0 | 0 | 47 | 34 | 7288625 | 83306 | 7205319 | 7325241 | 7238007 | 0 | 0 | 0 | 7238007 | 7237793 | -213 | 36616 | 21 | 0 | 30 | 85031 | 0 | 0 | 4 | -45819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 104762 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-06-11 | QTR4 | 20/21 | 2021-04-30 | QTR4 | 20/21 | 854 | 9629063.11 |  |  | 4 | 26 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R96 | 44130915201 | 2019-08-20 | QTR1 | 19/20 | 1 | 3 | 463 | 493 | 369 | 124 | 0 | 0 | 30 | 0 | 4958767 | 54870 | 4903898 | 4943242 | 4981728 | 0 | 0 | 0 | 4981728 | 4960014 | -21714 | -15525 | 5 | 0 | 0 | -15248 | 0 | 0 | 0 | 53090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37842 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-01-08 | QTR3 | 20/21 | 2020-11-23 | QTR2 | 20/21 | 854 | 5574450.77 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 0 | -576 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S01 | 43651615201 | 2019-11-19 | QTR2 | 19/20 | 2 | 0 | 219 | 289 | 289 | 0 | 0 | 0 | 70 | 0 | 6508469 | 70860 | 6437610 | 6508469 | 6539682 | 0 | 0 | 0 | 6539682 | 6503176 | -36506 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 11164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20475 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-29 | QTR3 | 20/21 | 2020-12-14 | QTR2 | 20/21 | 854 | 7009172.74 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S20 | 43801915201 | 2020-03-10 | QTR3 | 19/20 | 1 | 0 | 157 | 177 | 113 | 64 | 0 | 0 | 20 | 0 | 438700 | 30191 | 408509 | 438700 | 378146 | 0 | 0 | 0 | 378146 | 378146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2021-04-12 | QTR4 | 20/21 | 2021-01-20 | QTR3 | 20/21 | 854 | 627428.86 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S33 | 44261815201 | 2020-05-12 | QTR4 | 19/20 | 2 | 2 | 231 | 285 | 285 | 0 | 0 | 0 | 52 | 2 | 1875029 | 50000 | 1825029 | 1908027 | 1958622 | 0 | 0 | 0 | 1958622 | 1958746 | 123 | 32998 | 27 | 0 | 0 | 11458 | 0 | 0 | 2 | 48392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 59850 | 0 | F842663349 | TURTLE INFRASTRUCTURE PARTNERS LLC | N/A | N/A | N/A | N/A | 2021-06-22 | QTR4 | 20/21 | 2021-05-14 | QTR4 | 20/21 | 854 | 1327553.52 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S47 | 44400315201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 65 | 75 | 62 | 13 | 0 | 0 | 10 | 0 | 254205 | 21677 | 232529 | 254205 | 227921 | 0 | 0 | 0 | 227921 | 227921 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-18 | QTR2 | 20/21 | 2020-11-08 | QTR2 | 20/21 | 854 | 465727.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0