## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 4541736 | 4446078 | 4562544 | 4594848 | 0 | 4501839 | 1.254% | 100% | 32366 | 0.728% | 20808 | 0.4582% | 500 | 48 | 9.6% | 54 | 10.8% | 0 | 0% | 17 | 3.4% | 517 | 3.4% | 616 | 660 | 558 | 11.6% | 66.67%
| District Let | 24377829 | 24013706 | 24763186 | 24443059 | 0 | 24457884 | 1.85% | 100% | 453291 | 1.888% | 385357 | 1.581% | 1390 | 155 | 11.15% | 100 | 7.194% | 40 | 2.878% | 201 | 14.46% | 1631 | 17.34% | 1908 | 1874 | 1619 | 16.47% | 60%
| All Contracts | 28919565 | 28459784 | 29325730 | 29037907 | 0 | 28959723 | 1.757% | 100% | 485657 | 1.706% | 406165 | 1.404% | 1890 | 203 | 10.74% | 154 | 8.148% | 40 | 2.116% | 218 | 11.53% | 2148 | 13.65% | 2524 | 2534 | 2177 | 15.19% | 62.5%
2 | Central Let | 40584815 | 40108651 | 40920478 | 39777322 | 0 | 39725413 | -0.9555% | 100% | 508717 | 1.268% | 335663 | 0.8271% | 2275 | 292 | 12.84% | 266 | 11.69% | 44 | 1.934% | 64 | 2.813% | 2383 | 4.747% | 2941 | 2815 | 2257 | -0.7912% | 90.91%
| District Let | 17903691 | 17682249 | 17920164 | 17606044 | 0 | 17822955 | 0.7957% | 100% | 92745 | 0.5245% | 16473 | 0.09201% | 507 | 108 | 21.3% | 111 | 21.89% | 0 | 0% | 8 | 1.578% | 515 | 1.578% | 734 | 953 | 734 | 44.77% | 50%
| All Contracts | 58488506 | 57790900 | 58840642 | 57383366 | 0 | 57548368 | -0.4197% | 100% | 601462 | 1.041% | 352136 | 0.6021% | 2782 | 400 | 14.38% | 377 | 13.55% | 44 | 1.582% | 72 | 2.588% | 2898 | 4.17% | 3675 | 3768 | 2991 | 7.513% | 84.62%
3 | Central Let | 15237947 | 15126933 | 15239852 | 14899503 | 0 | 14867979 | -1.712% | 100% | 6081 | 0.0402% | 1905 | 0.0125% | 747 | 227 | 30.39% | 109 | 14.59% | 128 | 17.14% | 0 | 0% | 875 | 17.14% | 1211 | 1206 | 870 | 16.47% | 75%
| District Let | 17238898 | 16960621 | 17907554 | 17791656 | 0 | 17560388 | 3.536% | 83.33% | 793452 | 4.678% | 668656 | 3.879% | 930 | 264 | 28.39% | 184 | 19.78% | 73 | 7.849% | 317 | 34.09% | 1320 | 41.94% | 1768 | 1755 | 1307 | 40.54% | 33.33%
| All Contracts | 32476845 | 32087554 | 33147406 | 32691159 | 0 | 32428367 | 1.062% | 90% | 799533 | 2.492% | 670561 | 2.065% | 1677 | 491 | 29.28% | 293 | 17.47% | 201 | 11.99% | 317 | 18.9% | 2195 | 30.89% | 2979 | 2961 | 2177 | 29.82% | 50%
4 | Central Let | 27814182 | 27404819 | 29521981 | 28431093 | 0 | 28608376 | 4.392% | 100% | 1916133 | 6.992% | 1707798 | 6.14% | 1912 | 324 | 16.95% | 182 | 9.519% | 42 | 2.197% | 178 | 9.31% | 2132 | 11.51% | 2638 | 2587 | 2081 | 8.839% | 100%
| District Let | 32434117 | 32162764 | 33976362 | 33844114 | 0 | 32783310 | 1.929% | 100% | 1558825 | 4.847% | 1542245 | 4.755% | 1992 | 394 | 19.78% | 147 | 7.38% | 40 | 2.008% | 277 | 13.91% | 2309 | 15.91% | 2850 | 2689 | 2148 | 7.831% | 100%
| All Contracts | 60248299 | 59567583 | 63498343 | 62275207 | 0 | 61391686 | 3.062% | 100% | 3474958 | 5.834% | 3250043 | 5.394% | 3904 | 718 | 18.39% | 329 | 8.427% | 82 | 2.1% | 455 | 11.65% | 4441 | 13.76% | 5488 | 5276 | 4229 | 8.325% | 100%
5 | Central Let | 114165622 | 113357031 | 118173815 | 120550831 | 586693 | 119524927 | 5.441% | 88.89% | 3936616 | 3.473% | 4008194 | 3.511% | 3540 | 569 | 16.07% | 332 | 9.379% | 42 | 1.186% | 314 | 8.87% | 3896 | 10.06% | 4818 | 4600 | 3699 | 4.492% | 88.89%
| District Let | 3886833 | 3723187 | 3890948 | 3706072 | 0 | 3693082 | -0.8086% | 100% | 10183 | 0.2735% | 4115 | 0.1059% | 989 | 134 | 13.55% | 145 | 14.66% | 22 | 2.224% | 91 | 9.201% | 1102 | 11.43% | 1381 | 1670 | 1391 | 40.65% | 57.14%
| All Contracts | 118052455 | 117080218 | 122064763 | 124256903 | 586693 | 123218009 | 5.242% | 93.75% | 3946799 | 3.371% | 4012309 | 3.399% | 4529 | 703 | 15.52% | 477 | 10.53% | 64 | 1.413% | 405 | 8.942% | 4998 | 10.36% | 6199 | 6270 | 5090 | 12.39% | 75%
6 | Central Let | 53291812 | 52858837 | 54170350 | 53249038 | 2620000 | 53153708 | 0.5578% | 100% | 969166 | 1.833% | 878538 | 1.649% | 2070 | 313 | 15.12% | 187 | 9.034% | 75 | 3.623% | 0 | 0% | 2145 | 3.623% | 2675 | 2485 | 1985 | -4.106% | 100%
| District Let | 3175882 | 3054322 | 3314760 | 3149371 | 0 | 3140994 | 2.838% | 66.67% | 160301 | 5.248% | 138878 | 4.373% | 715 | 92 | 12.87% | 51 | 7.133% | 0 | 0% | 0 | 0% | 715 | 0% | 858 | 646 | 503 | -29.65% | 100%
| All Contracts | 56467694 | 55913159 | 57485110 | 56398409 | 2620000 | 56294702 | 0.6824% | 90% | 1129467 | 2.02% | 1017416 | 1.802% | 2785 | 405 | 14.54% | 238 | 8.546% | 75 | 2.693% | 0 | 0% | 2860 | 2.693% | 3533 | 3131 | 2488 | -10.66% | 100%
7 | Central Let | 20302076 | 20032076 | 21036167 | 21154213 | 0 | 21144246 | 5.552% | 100% | 811475 | 4.051% | 734091 | 3.616% | 1070 | 175 | 16.36% | 132 | 12.34% | 0 | 0% | 45 | 4.206% | 1115 | 4.206% | 1422 | 1342 | 1035 | -3.271% | 100%
| District Let | 13182638 | 13061638 | 13807831 | 13780947 | 0 | 13781249 | 5.509% | 100% | 678537 | 5.195% | 625193 | 4.743% | 1318 | 143 | 10.85% | 96 | 7.284% | 0 | 0% | 73 | 5.539% | 1391 | 5.539% | 1630 | 1488 | 1249 | -5.235% | 100%
| All Contracts | 33484714 | 33093714 | 34843998 | 34935160 | 0 | 34925495 | 5.535% | 100% | 1490012 | 4.502% | 1359284 | 4.059% | 2388 | 318 | 13.32% | 228 | 9.548% | 0 | 0% | 118 | 4.941% | 2506 | 4.941% | 3052 | 2830 | 2284 | -4.355% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 373646340 | 372696340 | 397733315 | 397837859 | 0 | 396243960 | 6.318% | 88.89% | 22918415 | 6.149% | 24086976 | 6.446% | 5345 | 964 | 18.04% | 581 | 10.87% | 427 | 7.989% | 1084 | 20.28% | 6856 | 28.27% | 8409 | 8201 | 6656 | 24.53% | 0%
| All Contracts | 373646340 | 372696340 | 397733315 | 397837859 | 0 | 396243960 | 6.318% | 88.89% | 22918415 | 6.149% | 24086976 | 6.446% | 5345 | 964 | 18.04% | 581 | 10.87% | 427 | 7.989% | 1084 | 20.28% | 6856 | 28.27% | 8409 | 8201 | 6656 | 24.53% | 88.89%
Totals This Qtr | Central Let | 275938190 | 273334425 | 283625187 | 282656848 | 3206693 | 281526488 | 2.997% | 97.78% | 8180554 | 2.993% | 7686997 | 2.786% | 12114 | 1948 | 16.08% | 1262 | 10.42% | 331 | 2.732% | 618 | 5.102% | 13063 | 7.834% | 16321 | 15695 | 12485 | 3.063% | 91.11%
| District Let | 485846228 | 483354827 | 513314120 | 512159122 | 0 | 509483822 | 5.406% | 92.5% | 26665749 | 5.517% | 27467893 | 5.654% | 13186 | 2254 | 17.09% | 1415 | 10.73% | 602 | 4.565% | 2051 | 15.55% | 15839 | 20.12% | 19538 | 19276 | 15607 | 18.36% | 72.5%
| All Contracts | 761784418 | 756689252 | 796939307 | 794815970 | 3206693 | 791010310 | 4.536% | 95.29% | 34846303 | 4.605% | 35154890 | 4.615% | 25300 | 4202 | 16.61% | 2677 | 10.58% | 933 | 3.688% | 2669 | 10.55% | 28902 | 14.24% | 35859 | 34971 | 28092 | 11.04% | 82.35%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2019/2020 | Central Let | 988991659 | 977780000 | 1022343017 | 1014413734 | 5645500 | 1017429355 | 4.055% | 88.24% | 34731579 | 3.552% | 33351357 | 3.372% | 47880 | 9559 | 19.96% | 4613 | 9.635% | 1119 | 2.337% | 3967 | 8.285% | 52966 | 10.62% | 67141 | 64834 | 50662 | 5.81% | 85.29%
| District Let | 1803149100 | 1793976712 | 1897132458 | 1887556879 | 10770000 | 1855703838 | 3.441% | 92.36% | 91015984 | 5.073% | 92450946 | 5.127% | 49124 | 7332 | 14.93% | 4291 | 8.735% | 659 | 1.342% | 5069 | 10.32% | 54852 | 11.66% | 66476 | 65192 | 53569 | 9.049% | 86.81%
| All Contracts | 2792140759 | 2771756712 | 2919475475 | 2901970613 | 16415500 | 2873133193 | 3.657% | 90.13% | 125747563 | 4.537% | 125802303 | 4.506% | 97004 | 16891 | 17.41% | 8904 | 9.179% | 1778 | 1.833% | 9036 | 9.315% | 107818 | 11.15% | 133617 | 130026 | 104231 | 7.45% | 85.99%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | 140.7% | 0 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 91.39% | 1 | 1353 | 15508 | 22 | 21 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31
| 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | 104.2% | 1 | -19598 | 2100 | 10 | 24 | 0 | 3 | 2846 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4946 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6
| 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 97.86% | 1 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | 101.4% | 1 | -317 | 3200 | 16 | 9 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 3 | 4 | 4 | 500 | 616 | 660 | 66.67% | 2 | -44 | 47 | 0 | 102 | 14 | 4541736 | 95658 | 4446078 | 4562544 | 4594848 | -74448 | 0 | -74448 | 4520400 | 4501839 | 100% | 3 | -18562 | 20808 | 48 | 54 | 0 | 17 | 27066 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 32366 | 0
| 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 127.8% | 0 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 102.4% | 1 | 19995 | 355643 | 61 | 66 | 0 | 200 | 43207 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 423577 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 96.67% | 1 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | 101.1% | 1 | -259 | 29714 | 51 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91
| 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 148.8% | 0 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 100.3% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM
| 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 85.88% | 1 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | 100.1% | 1 | -4903 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM
| 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 98.75% | 1 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | 98.18% | 1 | -8 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 5 | 9 | 9 | 1390 | 1908 | 1874 | 60% | 3 | 34 | 0 | 0 | 317 | 201 | 24377829 | 364123 | 24013706 | 24763186 | 24443059 | 0 | 0 | 0 | 24443059 | 24457884 | 100% | 5 | 14825 | 385357 | 155 | 100 | 0 | 200 | 43207 | 0 | 0 | 1 | 226389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 201 | 453291 | 0
| District 01 Totals |  |  |  |  | 8 | 13 | 13 | 1890 | 2524 | 2534 | 62.5% | 5 | -10 | 47 | 0 | 419 | 215 | 28919565 | 459781 | 28459784 | 29325730 | 29037907 | -74448 | 0 | -74448 | 28963459 | 28959723 | 100% | 8 | -3737 | 406165 | 203 | 154 | 0 | 217 | 70273 | 0 | 0 | 1 | 231689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 218 | 485657 | 0
| 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 104.5% | 1 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 102% | 1 | 60614 | 12839 | 39 | 74 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 |  | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28
| 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 120% | 1 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 104.9% | 1 | 67515 | 100000 | 78 | 19 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17
| 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 99.69% | 1 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 101.3% | 1 | 1507 | 42749 | 55 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149
| 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 95% | 1 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 78.26% | 1 | 0 | 0 | 1 | 26 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 |  | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67
| 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | 90.39% | 1 | -98689 | 0 | 33 | 28 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-03 | QTR1 | 20/21 |  | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11
| 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 84.44% | 1 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 106.7% | 1 | 579 | 100000 | 13 | 11 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72
| 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | 139.4% | 0 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | 102% | 1 | -3801 | 80075 | 21 | 26 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85
| 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 84.56% | 1 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | 99.08% | 1 | -36444 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03
| 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 72.22% | 1 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | 102.8% | 1 | -18603 | 0 | 18 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04
| 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 95% | 1 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 94.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-02-21 | QTR3 | 19/20 | 209 | 84351.5
| 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 103.3% | 1 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 108% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 11 | 16 | 15 | 2275 | 2941 | 2815 | 90.91% | 10 | 126 | 9 | 0 | 602 | 64 | 40584815 | 476164 | 40108651 | 40920478 | 39777322 | -14985 | 0 | -14985 | 39762337 | 39725413 | 100% | 11 | -27322 | 335663 | 292 | 266 | 0 | 40 | 245469 | 0 | 12 | 24 | 208353 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47245 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 64 | 508717 | 27355
| 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 1 | 460 | 671 | 891 | 148.7% | 0 | -220 | 220 | 0 | 207 | 4 | 17417591 | 200000 | 17217591 | 17434064 | 17148118 | -1033560 | 0 | -1033560 | 16114558 | 17365029 | 100.9% | 1 | 1266944 | 16473 | 97 | 110 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 92445 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97
| 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 106.4% | 1 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 98.55% | 1 | 0 | 0 | 11 | 1 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 2 | 4 | 1 | 507 | 734 | 953 | 50% | 1 | -219 | 220 | 0 | 219 | 8 | 17903691 | 221442 | 17682249 | 17920164 | 17606044 | -1033560 | 0 | -1033560 | 16572484 | 17822955 | 100% | 2 | 1266944 | 16473 | 108 | 111 | 0 | 4 | 26740 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 92745 | 0
| District 02 Totals |  |  |  |  | 13 | 20 | 16 | 2782 | 3675 | 3768 | 84.62% | 11 | -93 | 229 | 0 | 821 | 72 | 58488506 | 697606 | 57790900 | 58840642 | 57383366 | -1048545 | 0 | -1048545 | 56334821 | 57548368 | 100% | 13 | 1239622 | 352136 | 400 | 377 | 0 | 44 | 272209 | 0 | 12 | 24 | 267908 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 6450 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47245 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 72 | 601462 | 27355
| 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 137.2% | 0 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 109.8% | 1 | 2492 | -1395 | 58 | 27 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34
| 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | 93.61% | 1 | -3093 | 3300 | 17 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34
| 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 115% | 1 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | 97% | 1 | -30923 | 0 | 80 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 |  | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22
| 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 113.3% | 1 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 96.92% | 1 | 0 | 0 | 72 | 38 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 4 | 5 | 6 | 747 | 1211 | 1206 | 75% | 3 | 5 | 0 | 0 | 464 | 0 | 15237947 | 111014 | 15126933 | 15239852 | 14899503 | 0 | 0 | 0 | 14899503 | 14867979 | 100% | 4 | -31524 | 1905 | 227 | 109 | 0 | 0 | 0 | 0 | 46 | 0 | 7476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 6081 | 0
| 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 173.9% | 0 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | 108.5% | 1 | -3036 | 251063 | 77 | 50 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000
| 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 145.7% | 0 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | 102.4% | 1 | -52116 | 158902 | 66 | 62 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94
| 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 251.7% | 0 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 119.3% | 0 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 |  | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79
| 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 273 | 280 | 128.3% | 0 | -7 | 7 | 0 | 49 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4457789 | -18984 | 0 | -18984 | 4438805 | 4364461 | 101.9% | 1 | -74345 | 123339 | 26 | 23 | 0 | 14 | 48949 | 0 | 0 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04
| 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 102.5% | 1 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | 102.3% | 1 | -82786 | 42363 | 60 | 45 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75
| 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 101.2% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 6 | 10 | 13 | 930 | 1768 | 1755 | 33.33% | 2 | 13 | 7 | 0 | 521 | 317 | 17238898 | 278278 | 16960621 | 17907554 | 17791656 | -18984 | 0 | -18984 | 17772672 | 17560388 | 83.33% | 5 | -212283 | 668656 | 264 | 184 | 0 | 55 | 329837 | 0 | 73 | 43 | 105291 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219 | 358325 | 77855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 317 | 793452 | 84431
| District 03 Totals |  |  |  |  | 10 | 15 | 19 | 1677 | 2979 | 2961 | 50% | 5 | 18 | 7 | 0 | 985 | 317 | 32476845 | 389292 | 32087554 | 33147406 | 32691159 | -18984 | 0 | -18984 | 32672175 | 32428367 | 90% | 9 | -243807 | 670561 | 491 | 293 | 0 | 55 | 329837 | 0 | 119 | 43 | 112767 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 219 | 356930 | 77855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 317 | 799533 | 84431
| 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 119% | 1 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 106.4% | 1 | 233861 | 985075 | 115 | 55 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22
| 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 116.6% | 1 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | 86.03% | 1 | -253 | 22625 | 66 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52
| 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 103.9% | 1 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | 103.4% | 1 | -14110 | 229825 | 55 | 28 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 |  | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93
| 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 102.5% | 1 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | 105.3% | 1 | -2608 | 349724 | 45 | 28 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28
| 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 108.6% | 1 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | 106.2% | 1 | -18 | 103884 | 25 | 23 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 |  | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65
| 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | 100.1% | 1 | -62 | 0 | 11 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 |  | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89
| 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 62.11% | 1 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 91.64% | 1 | 0 | 16665 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 |  | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 7 | 18 | 26 | 1912 | 2638 | 2587 | 100% | 7 | 51 | 0 | 0 | 548 | 178 | 27814182 | 409364 | 27404819 | 29521981 | 28431093 | 0 | 0 | 0 | 28431093 | 28608376 | 100% | 7 | 216810 | 1707798 | 324 | 182 | 30 | 114 | 1015365 | 49892 | 0 | 19 | 683058 | 81663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 16 | 22625 | 0 | 0 | 14 | 156731 | 32223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 178 | 1916133 | 189542
| 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 119.7% | 1 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | 101.8% | 1 | -998657 | 1434680 | 296 | 112 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 |  | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 119.4% | 1 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 106.5% | 1 | 0 | 107565 | 96 | 28 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428
| 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 35.71% | 1 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 99.76% | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96
| 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 94.48% | 1 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 99.71% | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 4 | 5 | 13 | 1992 | 2850 | 2689 | 100% | 4 | 161 | 0 | 0 | 581 | 277 | 32434117 | 271353 | 32162764 | 33976362 | 33844114 | 0 | 0 | 0 | 33844114 | 32783310 | 100% | 4 | -998657 | 1542245 | 394 | 147 | 0 | 17 | 720579 | 182287 | 40 | 0 | 266162 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 111539 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 277 | 1558825 | 297995
| District 04 Totals |  |  |  |  | 11 | 23 | 39 | 3904 | 5488 | 5276 | 100% | 11 | 212 | 0 | 0 | 1129 | 455 | 60248299 | 680717 | 59567583 | 63498343 | 62275207 | 0 | 0 | 0 | 62275207 | 61391686 | 100% | 11 | -781847 | 3250043 | 718 | 329 | 30 | 131 | 1735944 | 232179 | 40 | 19 | 949220 | 93213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 55 | 483170 | 3959 | 0 | 235 | 268270 | 132422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 455 | 3474958 | 487537
| 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 111.6% | 1 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | 111.1% | 0 | -797738 | 2915022 | 79 | 65 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 |  | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06
| 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 83.33% | 1 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | 103% | 1 | -284799 | 843098 | 69 | 32 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 |  | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76
| 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 101% | 1 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 108.4% | 1 | 353955 | 51986 | 59 | 40 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41
| 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 105.6% | 1 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | 99.8% | 1 | -24609 | 54891 | 45 | 47 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742
| 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 99.92% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8
| 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 108% | 1 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | 101% | 1 | -94321 | 93683 | 136 | 54 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 512 | 0
| 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 138.5% | 0 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | 107.8% | 1 | -2583 | 3778 | 20 | 14 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 |  | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9
| 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 102% | 1 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | 101.5% | 1 | -92470 | 42528 | 52 | 32 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 |  | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55
| 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 100% | 1 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | 99.52% | 1 | -49387 | 3208 | 82 | 43 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 9 | 23 | 46 | 3540 | 4818 | 4600 | 88.89% | 8 | 218 | 0 | 0 | 943 | 335 | 114165622 | 808591 | 113357031 | 118173815 | 120550831 | -20210 | 586693 | 566483 | 121117313 | 119524927 | 88.89% | 8 | -991952 | 4008194 | 569 | 332 | 42 | 7 | 983363 | 0 | 0 | 269 | 3018538 | 158508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43079 | 3610 | 0 | 3 | 70325 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 42 | 314 | 3936616 | 221409
| 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 124% | 0 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 102.8% | 1 | 0 | 0 | 10 | 35 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 |  | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8
| 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | 294.5% | 0 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 79.35% | 1 | 0 | 0 | 2 | 18 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 |  | 2019-10-17 | QTR2 | 19/20 | 513 | 307382
| 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 111.7% | 1 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | 99.98% | 1 | -199 | 4115 | 84 | 25 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 |  | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6
| 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | 187.3% | 0 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 94.9% | 1 | 0 | 0 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 |  | 2020-08-11 | QTR1 | 20/21 | 513 | 141232
| 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 99.39% | 1 | 0 | 0 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 |  | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9
| 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 96.7% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 |  | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25
| 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 98.89% | 1 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 105.3% | 1 | 0 | 0 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 7 | 8 | 4 | 989 | 1381 | 1670 | 57.14% | 4 | -289 | 291 | 0 | 301 | 91 | 3886833 | 163646 | 3723187 | 3890948 | 3706072 | -8676 | 0 | -8676 | 3697396 | 3693082 | 100% | 7 | -199 | 4115 | 134 | 145 | 4 | 20 | 1092 | 0 | 18 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 91 | 10183 | 0
| District 05 Totals |  |  |  |  | 16 | 31 | 50 | 4529 | 6199 | 6270 | 75% | 12 | -71 | 291 | 0 | 1244 | 426 | 118052455 | 972237 | 117080218 | 122064763 | 124256903 | -28886 | 586693 | 557807 | 124814709 | 123218009 | 93.75% | 15 | -992151 | 4012309 | 703 | 477 | 46 | 27 | 984455 | 0 | 18 | 338 | 3022994 | 158508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 47714 | 3610 | 0 | 3 | 70325 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178687 | 0 | 64 | 405 | 3946799 | 221409
| 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 84.25% | 1 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | 90.62% | 1 | -289635 | -403730 | 22 | 17 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 |  | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 86% | 1 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | 102.7% | 1 | -2140213 | 1115676 | 16 | 11 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 |  | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 109.4% | 1 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 96.45% | 1 | 578 | 96399 | 60 | 44 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 |  | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 78.21% | 1 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | 100.8% | 1 | -201766 | 12198 | 24 | 25 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 |  | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 117.9% | 1 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 97.66% | 1 | 81 | 0 | 77 | 34 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 |  | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5
| 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 112.1% | 1 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | 96.93% | 1 | -1589 | 27177 | 90 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35
| 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | 103.6% | 1 | -846 | 30818 | 24 | 22 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 |  | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 7 | 28 | 19 | 2070 | 2675 | 2485 | 100% | 7 | 190 | 0 | 0 | 605 | 0 | 53291812 | 432975 | 52858837 | 54170350 | 53249038 | 0 | 2620000 | 2620000 | 55869038 | 53153708 | 100% | 7 | -2633390 | 878538 | 313 | 187 | 75 | 0 | 373897 | 6929 | 0 | 0 | 248784 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781992 | 0 | 0 | 0 | 15855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 75 | 0 | 969166 | 27620
| 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 47.33% | 1 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 94.14% | 1 | 0 | 0 | 30 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95
| 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 100% | 1 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 111.7% | 0 | 0 | 139878 | 27 | 23 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 |  | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132
| 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 61.43% | 1 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | 95.7% | 1 | -189 | -1000 | 35 | 1 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 |  | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 3 | 5 | 5 | 715 | 858 | 646 | 100% | 3 | 212 | 0 | 0 | 143 | 0 | 3175882 | 121560 | 3054322 | 3314760 | 3149371 | 0 | 0 | 0 | 3149371 | 3140994 | 66.67% | 2 | -189 | 138878 | 92 | 51 | 0 | 0 | 20689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160301 | 0
| District 06 Totals |  |  |  |  | 10 | 33 | 24 | 2785 | 3533 | 3131 | 100% | 10 | 402 | 0 | 0 | 748 | 0 | 56467694 | 554535 | 55913159 | 57485110 | 56398409 | 0 | 2620000 | 2620000 | 59018409 | 56294702 | 90% | 9 | -2633579 | 1017416 | 405 | 238 | 75 | 0 | 394586 | 6929 | 0 | 0 | 381043 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789345 | 0 | 0 | 0 | 15855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453468 | 0 | 75 | 0 | 1129467 | 27620
| 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 84% | 1 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | 107.8% | 1 | -14840 | 688152 | 70 | 32 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 |  | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63
| 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 119.6% | 1 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | 99.14% | 1 | -20 | 0 | 91 | 73 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 |  | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8
| 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 98.33% | 1 | 4907 | 45939 | 13 | 11 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 |  | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185
| 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | 92.73% | 1 | -16 | 0 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 |  | 2020-05-05 | QTR4 | 19/20 | 799 | 490000
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 4 | 4 | 14 | 1070 | 1422 | 1342 | 100% | 4 | 80 | 0 | 0 | 307 | 45 | 20302076 | 270000 | 20032076 | 21036167 | 21154213 | 0 | 0 | 0 | 21154213 | 21144246 | 100% | 4 | -9969 | 734091 | 175 | 132 | 0 | 45 | 690453 | 21000 | 0 | 0 | 117799 | 5053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 811475 | 26053
| 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 108.6% | 1 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 108.9% | 1 | 302 | 625193 | 45 | 66 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 66.67% | 1 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 99.99% | 1 | 0 | 0 | 95 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 |  | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000
| 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 92.5% | 1 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 799 | 280000
| 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 72.06% | 1 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 93.26% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 4 | 5 | 8 | 1318 | 1630 | 1488 | 100% | 4 | 142 | 0 | 0 | 239 | 73 | 13182638 | 121000 | 13061638 | 13807831 | 13780947 | 0 | 0 | 0 | 13780947 | 13781249 | 100% | 4 | 302 | 625193 | 143 | 96 | 0 | 0 | 170069 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 678537 | 21130
| District 07 Totals |  |  |  |  | 8 | 9 | 22 | 2388 | 3052 | 2830 | 100% | 8 | 222 | 0 | 0 | 546 | 118 | 33484714 | 391000 | 33093714 | 34843998 | 34935160 | 0 | 0 | 0 | 34935160 | 34925495 | 100% | 8 | -9667 | 1359284 | 318 | 228 | 0 | 45 | 860522 | 21000 | 0 | 37 | 623957 | 26183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1490012 | 47183
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 180.6% | 0 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | 105.2% | 1 | -2369264 | 11648418 | 291 | 106 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1439 | 117.5% | 1 | 14 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 109.1% | 1 | 991193 | 5429118 | 149 | 127 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 |  | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 119.5% | 1 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | 106.1% | 1 | -551574 | 4550344 | 122 | 82 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 |  | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12
| 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | 119.6% | 1 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 106.6% | 1 | 496445 | 1556062 | 183 | 99 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 0
| 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 113.2% | 1 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 106.9% | 1 | 1490912 | 597011 | 172 | 84 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09
| 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 106.8% | 1 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | 97.91% | 1 | -7 | 70000 | 23 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49
| 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 102% | 1 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | 119.1% | 0 | -3862 | 142527 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 |  | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97
| 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 106% | 1 | 0 | 94072 | 5 | 28 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 |  | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98
| 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 37.17% | 1 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 90.79% | 1 | 0 | -576 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 |  | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 9 | 22 | 101 | 5345 | 8409 | 8201 | 0% | 8 | 208 | 42 | 0 | 1972 | 1092 | 373646340 | 950000 | 372696340 | 397733315 | 397837859 | -375224 | 0 | -375224 | 397462635 | 396243960 | 88.89% | 8 | 53843 | 24086976 | 964 | 581 | 0 | 748 | 13425297 | 1567394 | 0 | 24 | 1098658 | 80714 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 427 | 296 | 6492479 | 402197 | 0 | 16 | 656061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81148 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 427 | 1084 | 22918415 | 2050305
| District 08 Totals |  |  |  |  | 9 | 22 | 101 | 5345 | 8409 | 8201 | 88.89% | 8 | 208 | 42 | 0 | 1972 | 1092 | 373646340 | 950000 | 372696340 | 397733315 | 397837859 | -375224 | 0 | -375224 | 397462635 | 396243960 | 88.89% | 8 | 53843 | 24086976 | 964 | 581 | 0 | 748 | 13425297 | 1567394 | 0 | 24 | 1098658 | 80714 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 427 | 296 | 6492479 | 402197 | 0 | 16 | 656061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81148 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 427 | 1084 | 22918415 | 2050305
| Statewide Central Let Contracts SubTotal |  |  |  |  | 45 | 98 | 130 | 12114 | 16321 | 15695 | 91.11% | 41 | 626 | 56 | 0 | 3571 | 636 | 275938190 | 2603766 | 273334425 | 283625187 | 282656848 | -109643 | 3206693 | 3097050 | 285753897 | 281526488 | 97.78% | 44 | -3495909 | 7686997 | 1948 | 1262 | 147 | 223 | 3335613 | 77821 | 58 | 312 | 4289308 | 293270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 4000 | 0 | 82 | 16 | 846301 | 3610 | 0 | 17 | 253787 | 91514 | 0 | 0 | 0 | 0 | 0 | 0 | 49352 | 0 | 0 | 0 | 0 | 0 | 30 | 50 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -632155 | 0 | 331 | 618 | 8180554 | 491979
| Statewide District Let Contracts SubTotal |  |  |  |  | 40 | 68 | 154 | 13186 | 19538 | 19276 | 72.5% | 29 | 262 | 560 | 0 | 4293 | 2059 | 485846228 | 2491402 | 483354827 | 513314120 | 512159122 | -1436444 | 0 | -1436444 | 510722678 | 509483822 | 92.5% | 37 | 124586 | 27467893 | 2254 | 1415 | 4 | 1044 | 14737510 | 1749681 | 131 | 174 | 2398928 | 119970 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 | 0 | 427 | 560 | 7509342 | 484011 | 0 | 237 | 767600 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 81148 | 0 | 0 | 0 | 270000 | 0 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88404 | 0 | 602 | 2051 | 26665749 | 2453861
| Statewide Totals |  |  |  |  | 85 | 166 | 284 | 25300 | 35859 | 34971 | 82.35% | 70 | 888 | 616 | 0 | 7864 | 2695 | 761784418 | 5095168 | 756689252 | 796939307 | 794815970 | -1546087 | 3206693 | 1660606 | 796476575 | 791010310 | 95.29% | 81 | -3371323 | 35154890 | 4202 | 2677 | 151 | 1267 | 18073123 | 1827502 | 189 | 486 | 6688236 | 413240 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 46750 | 0 | 509 | 576 | 8355643 | 487621 | 0 | 254 | 1021387 | 191713 | 0 | 0 | 0 | 0 | 0 | 0 | 130500 | 0 | 0 | 0 | 270000 | 0 | 70 | 86 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 0 | -720559 | 0 | 933 | 2669 | 34846303 | 2945840

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P44 | 43797315201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-01-27 | 18051494 | 18407137 | 18281638 | 355642.62 | 0 | 18301633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
1 | E1R06 | 43658015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-14 | 2206728 | 2236442 | 2181738 | 29714.23 | 0 | 2202526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181738 | 2202526 | 20788 | 2403604
1 | E1R81 | 43528615201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2019-05-23 | 682196 | 682196 | 657412 | 0 | 0 | 657412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657412 | 657412 | 0 | 659798 | B0 | ACC - LUMP SUM
1 | E1R99 | 43942615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-10-17 | 2118027 | 2118027 | 2076020 | 0 | 0 | 2071117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 2188397 | B0 | ACC - LUMP SUM
1 | E1S01 | 43796215201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2019-07-18 | 1319384 | 1319384 | 1246251 | 0 | 0 | 1246243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 1628857
1 | T1670 | 43512015201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-03-29 | 774103 | 789611 | 780581 | 15508.02 | -74448 | 707486 | -74448 | 0 | 0 | 0 | 0 | 0 | -74448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74448 | 706133 | 707486 | 1353 | 746976
1 | T1744 | 43806115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 2622633 | 2624733 | 2699418 | 2100 | 0 | 2679820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2884387
1 | T1748 | 43510815201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1145000 | 1148200 | 1114849 | 3200.4 | 0 | 1114533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 980185
2 | E2W31 | 43373015201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-03-15 | 17417591 | 17434064 | 17148118 | 16473.12 | -1033560 | 17381502 | -1033560 | 0 | 0 | 0 | 0 | 0 | -1033560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1033560 | 16114558 | 17381502 | 1266944 | 16736577
2 | E2Z22 | 44199725215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2019-10-16 | 486100 | 486100 | 457926 | 0 | 0 | 457926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457926 | 457926 | 0 | 464975
2 | T2675 | 43611415201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 8842976 | 8855815 | 8862510 | 12839.16 | 0 | 8968366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8862510 | 8968366 | 105856 | 9571732
2 | T2702 | 43616515201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2018-05-23 | 4160007 | 4260007 | 4244965 | 100000 | 0 | 4312480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 3742257
2 | T2709 | 21284435201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 3462428 | 3505177 | 3504649 | 42749.1 | 0 | 3506156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 3179149
2 | T2719 | 44089815201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 1184584 | 1184584 | 887887 | 0 | 0 | 887887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887887 | 887887 | 0 | 1509948
2 | T2721 | 43761915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 8899704 | 8899704 | 8066755 | 0 | 0 | 7968066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 9019727
2 | T2722 | 43761515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 3029745 | 3129745 | 3172572 | 100000 | 0 | 3184741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3172572 | 3184741 | 12169 | 3135452
2 | T2726 | 43583715201 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2018-09-26 | 2039829 | 2119904 | 2083011 | 80074.99 | -14985 | 2064225 | -14985 | 0 | 0 | 0 | 0 | 0 | -14985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14985 | 2068026 | 2064225 | -3801 | 2155262
2 | T2728 | 43732115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-01-30 | 5318835 | 5318835 | 5249772 | 0 | 0 | 5213329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 5787088
2 | T2738 | 43934615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | 3397538 | 3397538 | 3460508 | 0 | 0 | 3441905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 3973731
2 | T2742 | 44272415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-06-12 | 99208 | 99208 | 93539 | 0 | 0 | 93539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93539 | 93539 | 0 | 84352
2 | T2745 | 43398815201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2019-08-28 | 149961 | 149961 | 151154 | 0 | 0 | 151154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151154 | 151154 | 0 | 204916
3 | E3O87 | 42820825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-12 | 2143658 | 2394721 | 2274840 | 251062.72 | 0 | 2271803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 1738000
3 | E3R51 | 22023625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 4578865 | 4737767 | 4690378 | 158901.87 | 0 | 4638261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 4615476
3 | E3R70 | 43814115201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 628778 | 721767 | 721738 | 92989.29 | 0 | 721738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721738 | 721738 | 0 | 499880
3 | E3R72 | 43255415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2019-07-11 | 4336259 | 4459598 | 4457789 | 123338.96 | -18984 | 4364461 | -18984 | 0 | 0 | 0 | 0 | 0 | -18984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18984 | 4438805 | 4364461 | -74345 | 5281573
3 | E3S03 | 43775215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-04-16 | 4297338 | 4339701 | 4428331 | 42363.01 | 0 | 4345545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 4833697
3 | E3S49 | 44350315201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2019-11-14 | 1254000 | 1254000 | 1218580 | 0 | 0 | 1218580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 1226090
3 | T3585 | 43228515201 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 1883515 | 1882120 | 2065179 | -1394.8 | 0 | 2067671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | 1839571
3 | T3648 | 43580215201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-08-28 | 1301561 | 1304861 | 1221532 | 3300 | 0 | 1218439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 1531944
3 | T3695 | 43775415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 9989122 | 9989122 | 9612555 | 0 | 0 | 9581632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 10772800
3 | T3708 | 43662015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-05-31 | 2063749 | 2063749 | 2000237 | 0 | 0 | 2000237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 1864559
4 | E4N82 | 22777515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-05-20 | 29568100 | 31002780 | 30989356 | 1434680.24 | 0 | 29990698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30989356 | 29990698 | -998657 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4T46 | 43388815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-01-04 | 1592830 | 1700395 | 1656013 | 107565.12 | 0 | 1656013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656013 | 1656013 | 0 | 1969428
4 | E4T78 | 43996015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2019-12-06 | 886114 | 886114 | 834084 | 0 | 0 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834084 | 834084 | 0 | 1407859
4 | E4T90 | 43995815201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-01-03 | 387073 | 387073 | 364661 | 0 | 0 | 364661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364661 | 364661 | 0 | 430109
4 | T4461 | 42793715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-24 | 13403577 | 14388653 | 13899377 | 985075.39 | 0 | 14133238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13899377 | 14133238 | 233861 | 14532810
4 | T4483 | 44008115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 977778 | 1000403 | 798387 | 22625.47 | 0 | 798134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798387 | 798134 | -253 | 1192931
4 | T4491 | 43234815201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 5272134 | 5501959 | 5429646 | 229824.88 | 0 | 5415536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5429646 | 5415536 | -14110 | 4730109
4 | T4496 | 43288335201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 3387195 | 3736919 | 3518847 | 349724.02 | 0 | 3516238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518847 | 3516238 | -2608 | 2883072
4 | T4498 | 43689315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 3421871 | 3525755 | 3579940 | 103883.53 | 0 | 3579922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 2478815
4 | T4507 | 43771815201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 345927 | 345927 | 329094 | 0 | 0 | 329032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329094 | 329032 | -62 | 362984
4 | T4540 | 43834515201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-01-29 | 1005700 | 1022365 | 875802 | 16665 | 0 | 875802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875802 | 875802 | 0 | 1115608
5 | E5Z20 | 43632415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-05 | 1052310 | 1052310 | 1030338 | 0 | 0 | 1030338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 1235089
5 | E5Z30 | 43952115201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2018-06-05 | 257400 | 257400 | 193136 | 0 | 0 | 193136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193136 | 193136 | 0 | 307382
5 | E5Z68 | 44096915201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-05 | 1563424 | 1567539 | 1517384 | 4114.91 | 0 | 1517184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517384 | 1517184 | -199 | 2235952
5 | E5Z83 | 44326615201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-06-04 | 176487 | 176487 | 170000 | 0 | -8676 | 161324 | -8676 | 0 | 0 | 0 | 0 | 0 | -8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8676 | 161324 | 161324 | 0 | 141232
5 | E5Z84 | 43643425201 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 296220 | 296220 | 278504 | 0 | 0 | 278504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278504 | 278504 | 0 | 340891
5 | E5Z89 | 44326815201 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2019-10-01 | 301514 | 301514 | 272690 | 0 | 0 | 272690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272690 | 272690 | 0 | 414691
5 | E5Z97 | 44330815201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 239478 | 239478 | 244020 | 0 | 0 | 244020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244020 | 244020 | 0 | 158006
5 | T5530 | 23968215201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 37673821 | 40588843 | 42253807 | 2915022.11 | 586693 | 42067685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586693 | 0 | 0 | 0 | 0 | 0 | 586693 | 586693 | 42840500 | 42067685 | -772815 | 38523048
5 | T5590 | 42690535201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 38848299 | 39691396 | 40371218 | 843097.53 | 0 | 40086419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40371218 | 40086419 | -284799 | 42395483
5 | T5592 | 43440715201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 6864444 | 6916430 | 6987391 | 51985.55 | 0 | 7341346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 9424561
5 | T5604 | 43734515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 6332535 | 6387426 | 6284035 | 54891.24 | 0 | 6274517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6284035 | 6274517 | -9518 | 7459742
5 | T5618 | 43643515201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-01-29 | 249700 | 249700 | 238354 | 0 | 0 | 238354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238354 | 238354 | 0 | 259439
5 | T5624 | 43687915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 9260071 | 9353754 | 9333412 | 93683.37 | 0 | 9239091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9333412 | 9239091 | -94321 | 0
5 | T5629 | 43759215201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-09-26 | 1369369 | 1373147 | 1429206 | 3778.24 | 0 | 1426624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429206 | 1426624 | -2583 | 1077107
5 | T5630 | 43732715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-26 | 7593730 | 7636258 | 7693686 | 42527.98 | 0 | 7601216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7693686 | 7601216 | -92470 | 10653193
5 | T5661 | 43968225201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5973653 | 5976861 | 5959722 | 3208.31 | -20210 | 5890124 | 0 | 0 | 0 | 0 | 0 | -20210 | -20210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20210 | 5939511 | 5890124 | -49387 | 5898605
6 | E6H56 | 42999615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2019-07-25 | 1195598 | 1195598 | 1078448 | 0 | 0 | 1078448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 1501205
6 | E6K86 | 43653215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-27 | 1525830 | 1665708 | 1656441 | 139878.01 | 0 | 1656441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656441 | 1656441 | 0 | 1287132
6 | E6L92 | 44203815201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-28 | 454454 | 453454 | 414482 | -1000 | 0 | 414293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414482 | 414293 | -189 | 422168
6 | T6420 | 43345515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 5904592 | 5500862 | 5293728 | -403729.56 | 300000 | 5304093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 5593728 | 5304093 | -289635 | 5663802 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6422 | 42736925201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 37393744 | 38509420 | 38324783 | 1115676.08 | 2120000 | 38304570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 120000 | 0 | 2120000 | 2120000 | 40444783 | 38304570 | -2140213 | 43619309 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6425 | 42597925201 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2018-03-28 | 2976484 | 3072883 | 2821239 | 96399 | 0 | 2821817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 2758437 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6441 | 43117045201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-12-05 | 3159760 | 3171958 | 3147560 | 12198.41 | 200000 | 3145794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3347560 | 3145794 | -201766 | 3433250 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6457 | 44018415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-12-05 | 1600000 | 1600000 | 1513631 | 0 | 0 | 1513712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 1865185
6 | T6459 | 44018715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-10-31 | 1799799 | 1826976 | 1697745 | 27176.72 | 0 | 1696156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 1983631
6 | T6470 | 43991715201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 457433 | 488251 | 450352 | 30818 | 0 | 449506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450352 | 449506 | -846 | 481418
7 | E7K30 | 42450725201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 8315000 | 8940193 | 9001435 | 625193.38 | 0 | 9001737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
7 | E7M29 | 43954715201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2019-01-09 | 4417200 | 4417200 | 4366662 | 0 | 0 | 4366662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 5635000
7 | E7M89 | 43878615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-01-30 | 194157 | 194157 | 183157 | 0 | 0 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183157 | 183157 | 0 | 280000
7 | E7N03 | 43673425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 256281 | 256281 | 229693 | 0 | 0 | 229693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229693 | 229693 | 0 | 284492
7 | T7406 | 42895715201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-05-23 | 15421093 | 16109245 | 16482253 | 688151.71 | 0 | 16467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 18474979
7 | T7411 | 43982925201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-04-25 | 2168162 | 2168162 | 2100062 | 0 | 0 | 2100043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 3284499
7 | T7426 | 43648715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-01-30 | 2303437 | 2349376 | 2210807 | 45938.74 | 0 | 2215714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 2215185
7 | T7432 | 43982955201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 409384 | 409384 | 361091 | 0 | 0 | 361076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361091 | 361076 | -16 | 490000
8 | E8M65 | 40609615201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2013-06-13 | 145330000 | 156978418 | 155492910 | 11648418.01 | 0 | 153123645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155492910 | 153123645 | -2369264 | 204625259 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
8 | E8N75 | 40611015201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-03-08 | 68542000 | 73971118 | 73863918 | 5429118.38 | 0 | 74855111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73863918 | 74855111 | 991193 | 66110895 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8P02 | 40609055201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-06-16 | 92527388 | 97077732 | 98980425 | 4550343.91 | -16500 | 98412351 | 0 | 0 | 0 | 0 | 0 | -16500 | -16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16500 | 98963925 | 98412351 | -551574 | 105363394
8 | E8P82 | 43715615201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-06-14 | 31974887 | 33530949 | 33963963 | 1556062.19 | -335724 | 34124684 | -290724 | 0 | 0 | 0 | 0 | -45000 | -335724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -335724 | 33628239 | 34124684 | 496445 | 0
8 | E8Q53 | 43516915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-17 | 27945014 | 28542025 | 28268831 | 597010.58 | -3000 | 29756743 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 28265831 | 29756743 | 1490912 | 31134083
8 | E8R19 | 43560565201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-03-12 | 3952490 | 4022490 | 3821122 | 70000 | 0 | 3821116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 5097785
8 | E8R53 | 44130615201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-11-15 | 1048889 | 1191415 | 1210586 | 142526.5 | 0 | 1206725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210586 | 1206725 | -3862 | 1135062
8 | E8R81 | 44132225201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2019-09-10 | 1331331 | 1425403 | 1378701 | 94071.53 | -20000 | 1358701 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 1358701 | 1358701 | 0 | 1246056
8 | E8R99 | 42897115201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2019-09-10 | 994341 | 993765 | 857403 | -576 | 0 | 857403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857403 | 857403 | 0 | 1572138

## Sheet1 (hidden)
01CO | 01 | T1670 | 43512015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 150 | 207 | 254 | -47 | 47 | 0 | 43 | 14 | 774103 | 0 | 774103 | 789611 | 780581 | -74448 | 0 | -74448 | 706133 | 707486 | 1353 | 15508 | 22 | 0 | 14 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15508 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2018-05-01 | QTR4 | 17/18 | 115 | 746976.31 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 3 | 01co | 1 | 3
01CO | 01 | T1744 | 43806115201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 210 | 244 | 244 | 0 | 0 | 0 | 34 | 0 | 2622633 | 50000 | 2572633 | 2624733 | 2699418 | 0 | 0 | 0 | 2699418 | 2679820 | -19598 | 2100 | 10 | 0 | 3 | 2846 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4946 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 118 | 2884386.6 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 5 | 01do | 4 | 8
01CO | 01 | T1748 | 43510815201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 165 | 162 | 3 | 0 | 0 | 25 | 0 | 1145000 | 45658 | 1099342 | 1148200 | 1114849 | 0 | 0 | 0 | 1114849 | 1114533 | -317 | 3200 | 16 | 0 | 0 | 8712 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11912 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-02-28 | QTR3 | 19/20 | 108 | 980184.55 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 11 | 02co | 9 | 19
01DO | 01 | E1P44 | 43797315201 | 2017-01-27 | QTR3 | 16/17 | 3 | 8 | 800 | 1149 | 1149 | 0 | 0 | 0 | 149 | 200 | 18051494 | 187494 | 17864000 | 18407137 | 18281638 | 0 | 0 | 0 | 18281638 | 18301633 | 19995 | 355643 | 61 | 0 | 200 | 43207 | 0 | 0 | 0 | 196675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 423577 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-09-08 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 115 | 18051494 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 66 | 0 | 0 | 0 | 0 |  | DO | 2 | 02do | 20 | 21
01DO | 01 | E1R06 | 43658015201 | 2018-06-14 | QTR4 | 17/18 | 2 | 1 | 180 | 238 | 231 | 7 | 0 | 0 | 57 | 1 | 2206728 | 50000 | 2156728 | 2236442 | 2181738 | 0 | 0 | 0 | 2181738 | 2181479 | -259 | 29714 | 51 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29714 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2019-08-27 | QTR1 | 19/20 | 108 | 2403603.91 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO | 4 | 03co | 22 | 25
01DO | 01 | E1R81 | 43528615201 | 2019-05-23 | QTR4 | 18/19 | 1 | 0 | 80 | 142 | 141 | 1 | 0 | 0 | 62 | 0 | 682196 | 26629 | 655567 | 682196 | 657412 | 0 | 0 | 0 | 657412 | 657412 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-07-09 | QTR1 | 20/21 | 115 | 659797.5 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO | 6 | 03do | 26 | 31
01DO | 01 | E1R99 | 43942615201 | 2019-10-17 | QTR2 | 19/20 | 2 | 0 | 170 | 181 | 157 | 24 | 0 | 0 | 11 | 0 | 2118027 | 50000 | 2068027 | 2118027 | 2076020 | 0 | 0 | 0 | 2076020 | 2071117 | -4903 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-08-06 | QTR1 | 20/21 | 113 | 2188397.16 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO | 7 | 04co | 32 | 38
01DO | 01 | E1S01 | 43796215201 | 2019-07-18 | QTR1 | 19/20 | 1 | 0 | 160 | 198 | 196 | 2 | 0 | 0 | 38 | 0 | 1319384 | 50000 | 1269384 | 1319384 | 1246251 | 0 | 0 | 0 | 1246251 | 1246243 | -8 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-04-22 | QTR4 | 19/20 | 118 | 1628857.15 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO | 4 | 04do | 39 | 42
02CO | 02 | T2675 | 43611415201 | 2018-04-25 | QTR4 | 17/18 | 2 | 2 | 400 | 531 | 531 | 0 | 0 | 0 | 113 | 18 | 8842976 | 93739 | 8749237 | 8855815 | 8862510 | 0 | 0 | 0 | 8862510 | 8923124 | 60614 | 12839 | 39 | 0 | 18 | 51763 | 0 | 0 | 0 | 10247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64874 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-09-09 | QTR1 | 20/21 | 2020-03-10 | QTR3 | 19/20 | 208 | 9571732.28 |  |  | 18 | 74 | 0 | 0 | 0 | 0 |  | CO | 9 | 05co | 43 | 51
02CO | 02 | T2702 | 43616515201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 150 | 277 | 277 | 0 | 0 | 0 | 97 | 30 | 4160007 | 50000 | 4110007 | 4260007 | 4244965 | 0 | 0 | 0 | 4244965 | 4312480 | 67515 | 100000 | 78 | 0 | 22 | 92381 | 0 | 0 | 8 | 32125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 124506 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2019-06-29 | QTR4 | 18/19 | 209 | 3742257.17 |  |  | 30 | 19 | 0 | 0 | 0 | 0 | T | CO | 7 | 05do | 52 | 58
02CO | 02 | T2709 | 21284435201 | 2018-12-05 | QTR2 | 18/19 | 2 | 2 | 320 | 399 | 398 | 1 | 0 | 0 | 79 | 0 | 3462428 | 0 | 3462428 | 3505177 | 3504649 | 0 | 0 | 0 | 3504649 | 3506156 | 1507 | 42749 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42749 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 209 | 3179149 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 7 | 06co | 59 | 65
02CO | 02 | T2719 | 44089815201 | 2019-06-12 | QTR4 | 18/19 | 1 | 0 | 180 | 207 | 198 | 9 | 0 | 0 | 27 | 0 | 1184584 | 50000 | 1134584 | 1184584 | 887887 | 0 | 0 | 0 | 887887 | 887887 | 0 | 0 | 1 | 0 | 0 | 16948 | 0 | 0 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22568 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-11 | QTR1 | 20/21 | 2020-05-27 | QTR4 | 19/20 | 214 | 1509947.67 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 3 | 06do | 66 | 68
02CO | 02 | T2721 | 43761915201 | 2018-10-31 | QTR2 | 18/19 | 1 | 0 | 290 | 351 | 351 | 0 | 0 | 0 | 61 | 0 | 8899704 | 84384 | 8815320 | 8899704 | 8066755 | 0 | 0 | 0 | 8066755 | 7968066 | -98689 | 0 | 33 | 0 | 0 | 32503 | 0 | 0 | 0 | 8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48943 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-03 | QTR1 | 20/21 | 2020-01-09 | QTR3 | 19/20 | 214 | 9019727.11 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO | 4 | 07co | 69 | 72
02CO | 02 | T2722 | 43761515201 | 2019-02-27 | QTR3 | 18/19 | 2 | 2 | 180 | 204 | 176 | 28 | 0 | 0 | 24 | 0 | 3029745 | 55809 | 2973936 | 3129745 | 3172572 | 0 | 0 | 0 | 3172572 | 3173151 | 579 | 100000 | 13 | 0 | 0 | 51874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96254 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2019-11-08 | QTR2 | 19/20 | 208 | 3135451.72 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 4 | 07do | 73 | 76
02CO | 02 | T2726 | 43583715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 7 | 170 | 275 | 284 | -9 | 9 | 0 | 91 | 14 | 2039829 | 25000 | 2014829 | 2119904 | 2083011 | -14985 | 0 | -14985 | 2068026 | 2054622 | -3801 | 80075 | 21 | 0 | 0 | 0 | 0 | 12 | 14 | 70472 | 27355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 14 | 70472 | 27355 | F580641369 | R.B. BAKER CONSTRUCTION COMPANY A DIVIS | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-01-13 | QTR3 | 19/20 | 208 | 2155261.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 77 | 76
02CO | 02 | T2728 | 43732115201 | 2019-01-30 | QTR3 | 18/19 | 1 | 0 | 285 | 337 | 293 | 44 | 0 | 0 | 52 | 0 | 5318835 | 57165 | 5261670 | 5318835 | 5249772 | 0 | 0 | 0 | 5249772 | 5213329 | -36444 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-03-05 | QTR3 | 19/20 | 208 | 5787088.03 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 9 | 08do | 77 | 85
02CO | 02 | T2738 | 43934615201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 229 | 179 | 50 | 0 | 0 | 49 | 0 | 3397538 | 50000 | 3347538 | 3397538 | 3460508 | 0 | 0 | 0 | 3460508 | 3441905 | -18603 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28656 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-01-06 | QTR3 | 19/20 | 208 | 3973731.04 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2742 | 44272415201 | 2019-06-12 | QTR4 | 18/19 | 2 | 0 | 60 | 63 | 60 | 3 | 0 | 0 | 3 | 0 | 99208 | 120 | 99088 | 99208 | 93539 | 0 | 0 | 0 | 93539 | 93539 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-02-21 | QTR3 | 19/20 | 209 | 84351.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2745 | 43398815201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 60 | 68 | 68 | 0 | 0 | 0 | 6 | 2 | 149961 | 9947 | 140014 | 149961 | 151154 | 0 | 0 | 0 | 151154 | 151154 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3532 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 214 | 204915.95 |  |  | 2 | 1 | 0 | 0 | 0 | 0 |  | CO |  | 0
02DO | 02 | E2W31 | 43373015201 | 2017-03-15 | QTR3 | 16/17 | 3 | 1 | 460 | 671 | 891 | -220 | 220 | 0 | 207 | 4 | 17417591 | 200000 | 17217591 | 17434064 | 17148118 | -1033560 | 0 | -1033560 | 16114558 | 17365029 | 1266944 | 16473 | 97 | 0 | 4 | 26440 | 0 | 0 | 0 | 59555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 92445 | 0 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2019-12-17 | QTR2 | 19/20 | 208 | 16736576.97 |  |  | 4 | 110 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z22 | 44199725215 | 2019-10-16 | QTR2 | 19/20 | 1 | 0 | 47 | 63 | 62 | 1 | 0 | 0 | 12 | 4 | 486100 | 21442 | 464658 | 486100 | 457926 | 0 | 0 | 0 | 457926 | 457926 | 0 | 0 | 11 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 300 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 209 | 464975.26 |  |  | 4 | 1 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3585 | 43228515201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 180 | 333 | 332 | 1 | 0 | 0 | 153 | 0 | 1883515 | 0 | 1883515 | 1882120 | 2065179 | 0 | 0 | 0 | 2065179 | 2067671 | 2492 | -1395 | 58 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | -1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | -1395 | 0 | F814575837 | GDB-US CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-03-13 | QTR3 | 19/20 | 308 | 1839571.34 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3648 | 43580215201 | 2019-08-28 | QTR1 | 19/20 | 1 | 4 | 180 | 209 | 209 | 0 | 0 | 0 | 29 | 0 | 1301561 | 0 | 1301561 | 1304861 | 1221532 | 0 | 0 | 0 | 1221532 | 1218439 | -3093 | 3300 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-10 | QTR4 | 19/20 | 321 | 1531944.34 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3695 | 43775415201 | 2019-01-30 | QTR3 | 18/19 | 2 | 0 | 267 | 419 | 419 | 0 | 0 | 0 | 152 | 0 | 9989122 | 111014 | 9878108 | 9989122 | 9612555 | 0 | 0 | 0 | 9612555 | 9581632 | -30923 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 4176 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | QTR1 | 20/21 | 2020-06-15 | QTR4 | 19/20 | 313 | 10772800.22 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3708 | 43662015201 | 2019-05-31 | QTR4 | 18/19 | 1 | 0 | 120 | 250 | 246 | 4 | 0 | 0 | 130 | 0 | 2063749 | 0 | 2063749 | 2063749 | 2000237 | 0 | 0 | 0 | 2000237 | 2000237 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-27 | QTR4 | 19/20 | 314 | 1864559.32 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3O87 | 42820825201 | 2017-01-12 | QTR3 | 16/17 | 2 | 5 | 180 | 440 | 440 | 0 | 0 | 0 | 200 | 60 | 2143658 | 50000 | 2093658 | 2394721 | 2274840 | 0 | 0 | 0 | 2274840 | 2271803 | -3036 | 251063 | 77 | 0 | 21 | 221968 | 0 | 73 | 23 | 65391 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 60 | 289971 | 6576 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2018-08-31 | QTR1 | 18/19 | 308 | 1738000 |  |  | 4 | 50 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R51 | 22023625201 | 2018-11-15 | QTR2 | 18/19 | 1 | 1 | 210 | 440 | 434 | 6 | 0 | 0 | 128 | 102 | 4578865 | 50000 | 4528865 | 4737767 | 4690378 | 0 | 0 | 0 | 4690378 | 4638261 | -52116 | 158902 | 66 | 0 | 0 | 16557 | 0 | 0 | 6 | 15313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 174533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 206402 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-08 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 313 | 4615475.94 |  |  | 6 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R70 | 43814115201 | 2019-09-12 | QTR1 | 19/20 | 1 | 2 | 60 | 179 | 179 | 0 | 0 | 0 | 28 | 91 | 628778 | 23653 | 605125 | 721767 | 721738 | 0 | 0 | 0 | 721738 | 721738 | 0 | 92989 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 100001 | 73189 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-17 | QTR1 | 20/21 | 2020-07-02 | QTR1 | 20/21 | 321 | 499879.79 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R72 | 43255415201 | 2019-07-11 | QTR1 | 19/20 | 4 | 4 | 180 | 273 | 280 | -7 | 7 | 0 | 49 | 44 | 4336259 | 54625 | 4281635 | 4459598 | 4457789 | -18984 | 0 | -18984 | 4438805 | 4364461 | -74345 | 123339 | 26 | 0 | 14 | 48949 | 0 | 0 | 14 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81179 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 141112 | 4666 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 308 | 5281573.04 |  |  | 14 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S03 | 43775215201 | 2019-04-16 | QTR4 | 18/19 | 1 | 1 | 240 | 365 | 351 | 14 | 0 | 0 | 105 | 20 | 4297338 | 50000 | 4247338 | 4339701 | 4428331 | 0 | 0 | 0 | 4428331 | 4345545 | -82786 | 42363 | 60 | 0 | 20 | 42363 | 0 | 0 | 0 | 13603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 55966 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 313 | 4833696.75 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S49 | 44350315201 | 2019-11-14 | QTR2 | 19/20 | 1 | 0 | 60 | 71 | 71 | 0 | 0 | 0 | 11 | 0 | 1254000 | 50000 | 1204000 | 1254000 | 1218580 | 0 | 0 | 0 | 1218580 | 1218580 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-06 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 313 | 1226089.65 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4461 | 42793715201 | 2017-05-24 | QTR4 | 16/17 | 4 | 10 | 673 | 971 | 971 | 0 | 0 | 0 | 170 | 128 | 13403577 | 142198 | 13261379 | 14388653 | 13899377 | 0 | 0 | 0 | 13899377 | 14111457 | 233861 | 985075 | 115 | 0 | 100 | 836261 | 46192 | 0 | 14 | 140593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 124508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1101362 | 46192 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-05-07 | QTR4 | 19/20 | 412 | 14532810.22 |  |  | 14 | 55 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4483 | 44008115201 | 2018-05-23 | QTR4 | 17/18 | 6 | 1 | 265 | 405 | 403 | 2 | 0 | 0 | 124 | 16 | 977778 | 50000 | 927778 | 1000403 | 798387 | 0 | 0 | 0 | 798387 | 798134 | -253 | 22625 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 22625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 31042 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-02-13 | QTR3 | 19/20 | 412 | 1192930.52 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4491 | 43234815201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 280 | 377 | 374 | 3 | 0 | 0 | 83 | 14 | 5272134 | 49990 | 5222144 | 5501959 | 5429646 | 0 | 0 | 0 | 5429646 | 5399686 | -14110 | 229825 | 55 | 0 | 14 | 142353 | 2611 | 0 | 0 | 81230 | 6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31507 | 31507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 255089 | 40855 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-31 | QTR1 | 20/21 | 2020-06-24 | QTR4 | 19/20 | 408 | 4730108.93 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4496 | 43288335201 | 2018-10-31 | QTR2 | 18/19 | 2 | 6 | 284 | 369 | 364 | 5 | 0 | 0 | 85 | 0 | 3387195 | 50000 | 3337195 | 3736919 | 3518847 | 0 | 0 | 0 | 3518847 | 3514343 | -2608 | 349724 | 45 | 0 | 0 | 27140 | 1089 | 0 | 0 | 334509 | 30739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 365649 | 31828 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-27 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 409 | 2883072.28 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4498 | 43689315201 | 2019-02-27 | QTR3 | 18/19 | 1 | 2 | 175 | 243 | 238 | 5 | 0 | 0 | 48 | 20 | 3421871 | 50000 | 3371871 | 3525755 | 3579940 | 0 | 0 | 0 | 3579940 | 3579922 | -18 | 103884 | 25 | 0 | 0 | 9611 | 0 | 0 | 5 | 93573 | 44187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 34355 | 25765 | 0 | 0 | 0 | 0 | 0 | 20 | 138255 | 70667 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-27 | QTR1 | 20/21 | 2020-05-29 | QTR4 | 19/20 | 409 | 2478814.65 |  |  | 15 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4507 | 43771815201 | 2019-03-27 | QTR3 | 18/19 | 2 | 0 | 140 | 168 | 168 | 0 | 0 | 0 | 28 | 0 | 345927 | 17176 | 328752 | 345927 | 329094 | 0 | 0 | 0 | 329094 | 329032 | -62 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7601 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-03 | QTR1 | 20/21 | 2020-05-08 | QTR4 | 19/20 | 412 | 362983.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4540 | 43834515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 95 | 105 | 69 | 36 | 0 | 0 | 10 | 0 | 1005700 | 50000 | 955700 | 1022365 | 875802 | 0 | 0 | 0 | 875802 | 875802 | 0 | 16665 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2020-07-15 | QTR1 | 20/21 | 2020-06-23 | QTR4 | 19/20 | 408 | 1115608.19 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N82 | 22777515201 | 2014-05-20 | QTR4 | 13/14 | 2 | 11 | 1403 | 2088 | 2088 | 0 | 0 | 0 | 408 | 277 | 29568100 | 150000 | 29418100 | 31002780 | 30989356 | 0 | 0 | 0 | 30989356 | 29940953 | -998657 | 1434680 | 296 | 0 | 17 | 720579 | 182287 | 0 | 0 | 170998 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 460545 | 3959 | 0 | 221 | 106897 | 100199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1459019 | 297995 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2020-07-30 | QTR1 | 20/21 | 2020-04-02 | QTR4 | 19/20 | 412 | 32395868 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 11 | 112 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T46 | 43388815201 | 2019-01-04 | QTR3 | 18/19 | 1 | 2 | 206 | 370 | 370 | 0 | 0 | 0 | 164 | 0 | 1592830 | 50000 | 1542830 | 1700395 | 1656013 | 0 | 0 | 0 | 1656013 | 1643612 | 0 | 107565 | 51 | 0 | 0 | 0 | 0 | 40 | 0 | 95164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 99806 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2020-07-15 | QTR1 | 20/21 | 409 | 1969428 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T78 | 43996015201 | 2019-12-06 | QTR2 | 19/20 | 1 | 0 | 238 | 240 | 87 | 153 | 0 | 0 | 2 | 0 | 886114 | 50000 | 836114 | 886114 | 834084 | 0 | 0 | 0 | 834084 | 834084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-09-24 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 1407858.96 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T90 | 43995815201 | 2020-01-03 | QTR3 | 19/20 | 1 | 0 | 145 | 152 | 144 | 8 | 0 | 0 | 7 | 0 | 387073 | 21353 | 365720 | 387073 | 364661 | 0 | 0 | 0 | 364661 | 364661 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-09-03 | QTR1 | 20/21 | 412 | 430108.89 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5530 | 23968215201 | 2015-06-24 | QTR4 | 14/15 | 6 | 27 | 1100 | 1476 | 1372 | 104 | 0 | 0 | 144 | 232 | 37673821 | 150000 | 37523821 | 40588843 | 42253807 | 0 | 586693 | 586693 | 42840500 | 41685721 | -797738 | 2915022 | 79 | 0 | 0 | 667381 | 0 | 0 | 232 | 2206919 | 154810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 2702989 | 154810 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-22 | QTR1 | 20/21 | 2019-12-31 | QTR2 | 19/20 | 509 | 38523048.06 |  |  | 0 | 65 | 0 | 0 | -178687 | 0 |  | CO
05CO | 05 | T5590 | 42690535201 | 2018-06-13 | QTR4 | 17/18 | 4 | 7 | 600 | 701 | 601 | 100 | 0 | 0 | 101 | 0 | 38848299 | 150000 | 38698299 | 39691396 | 40371218 | 0 | 0 | 0 | 40371218 | 39866889 | -284799 | 843098 | 69 | 0 | 0 | 153221 | 0 | 0 | 0 | 533353 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697773 | 3698 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-08-07 | QTR1 | 20/21 | 2020-05-23 | QTR4 | 19/20 | 514 | 42395482.76 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5592 | 43440715201 | 2017-08-30 | QTR1 | 17/18 | 1 | 1 | 400 | 503 | 503 | 0 | 0 | 0 | 99 | 4 | 6864444 | 92000 | 6772444 | 6916430 | 6987391 | 0 | 0 | 0 | 6987391 | 7341346 | 353955 | 51986 | 59 | 0 | 0 | 28277 | 0 | 0 | 4 | 65869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 94146 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2019-04-30 | QTR4 | 18/19 | 515 | 9424561.41 |  |  | 4 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5604 | 43734515201 | 2018-12-05 | QTR2 | 18/19 | 2 | 3 | 270 | 391 | 377 | 14 | 0 | 0 | 92 | 29 | 6332535 | 73000 | 6259535 | 6387426 | 6284035 | 0 | 0 | 0 | 6284035 | 6247174 | -24609 | 54891 | 45 | 0 | 0 | 17639 | 0 | 0 | 29 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123 | 0 | 0 | 0 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59339 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-03-23 | QTR3 | 19/20 | 514 | 7459742 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5618 | 43643515201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 92 | 92 | 0 | 0 | 0 | 32 | 0 | 249700 | 11148 | 238552 | 249700 | 238354 | 0 | 0 | 0 | 238354 | 238354 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-07-20 | QTR1 | 20/21 | 507 | 259438.8 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5624 | 43687915201 | 2018-07-25 | QTR1 | 18/19 | 2 | 3 | 350 | 568 | 568 | 0 | 0 | 0 | 190 | 28 | 9260071 | 119000 | 9141071 | 9353754 | 9333412 | 0 | 0 | 0 | 9333412 | 9236408 | -94321 | 93683 | 136 | 0 | 7 | 105410 | 0 | 0 | 0 | 81943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3610 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190962 | 3610 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 512 | 0 |  |  | 7 | 54 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5629 | 43759215201 | 2018-09-26 | QTR1 | 18/19 | 2 | 1 | 200 | 311 | 311 | 0 | 0 | 0 | 76 | 35 | 1369369 | 50000 | 1319369 | 1373147 | 1429206 | 0 | 0 | 0 | 1429206 | 1422845 | -2583 | 3778 | 20 | 42 | 0 | 3861 | 0 | 0 | 0 | 15129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 35 | 18990 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-12 | QTR1 | 20/21 | 2019-12-12 | QTR2 | 19/20 | 509 | 1077106.9 |  |  | 35 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5630 | 43732715201 | 2018-09-26 | QTR1 | 18/19 | 2 | 2 | 350 | 441 | 441 | 0 | 0 | 0 | 84 | 7 | 7593730 | 105000 | 7488730 | 7636258 | 7693686 | 0 | 0 | 0 | 7693686 | 7599275 | -92470 | 42528 | 52 | 0 | 0 | 0 | 0 | 0 | 4 | 62678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11771 | 0 | 0 | 3 | 59291 | 59291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 133739 | 59291 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-10 | QTR1 | 20/21 | 2020-03-14 | QTR3 | 19/20 | 515 | 10653192.55 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5661 | 43968225201 | 2019-04-24 | QTR4 | 18/19 | 3 | 2 | 210 | 335 | 335 | 0 | 0 | 0 | 125 | 0 | 5973653 | 58443 | 5915210 | 5976861 | 5959722 | -20210 | 0 | -20210 | 5939511 | 5886915 | -49387 | 3208 | 82 | 0 | 0 | 7574 | 0 | 0 | 0 | 27647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38678 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-06-22 | QTR4 | 19/20 | 507 | 5898604.78 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5Z20 | 43632415201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 300 | 417 | 417 | 0 | 0 | 0 | 45 | 72 | 1052310 | 50000 | 1002310 | 1052310 | 1030338 | 0 | 0 | 0 | 1030338 | 1030338 | 0 | 0 | 10 | 0 | 1 | 1092 | 0 | 0 | 69 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10183 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-07-09 | QTR1 | 20/21 | 2020-02-25 | QTR3 | 19/20 | 512 | 1235088.8 |  |  | 8 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z30 | 43952115201 | 2018-06-05 | QTR4 | 17/18 | 1 | 1 | 110 | 149 | 344 | -195 | 195 | 0 | 20 | 19 | 257400 | 14000 | 243400 | 257400 | 193136 | 0 | 0 | 0 | 193136 | 193136 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2020-08-13 | QTR1 | 20/21 | 2019-10-17 | QTR2 | 19/20 | 513 | 307382 |  |  | 19 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z68 | 44096915201 | 2019-03-05 | QTR3 | 18/19 | 2 | 1 | 180 | 311 | 310 | 1 | 0 | 0 | 131 | 0 | 1563424 | 50000 | 1513424 | 1567539 | 1517384 | 0 | 0 | 0 | 1517384 | 1513070 | -199 | 4115 | 84 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-21 | QTR1 | 20/21 | 2020-05-14 | QTR4 | 19/20 | 514 | 2235951.6 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z83 | 44326615201 | 2019-06-04 | QTR4 | 18/19 | 1 | 1 | 110 | 155 | 251 | -96 | 96 | 0 | 45 | 0 | 176487 | 6487 | 170000 | 176487 | 170000 | -8676 | 0 | -8676 | 161324 | 161324 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-09-23 | QTR1 | 20/21 | 2020-08-11 | QTR1 | 20/21 | 513 | 141232 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z84 | 43643425201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 90 | 111 | 111 | 0 | 0 | 0 | 21 | 0 | 296220 | 16000 | 280220 | 296220 | 278504 | 0 | 0 | 0 | 278504 | 278504 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F841745638 | WEST TO WEST CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | QTR1 | 20/21 | 2020-04-24 | QTR4 | 19/20 | 513 | 340890.9 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z89 | 44326815201 | 2019-10-01 | QTR2 | 19/20 | 1 | 0 | 109 | 116 | 116 | 0 | 0 | 0 | 7 | 0 | 301514 | 19509 | 282005 | 301514 | 272690 | 0 | 0 | 0 | 272690 | 272690 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC D/B/A OCEANEER | N/A | N/A | N/A | N/A | 2020-09-25 | QTR1 | 20/21 | 2020-05-09 | QTR4 | 19/20 | 507 | 414691.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z97 | 44330815201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 90 | 122 | 121 | 1 | 0 | 0 | 32 | 0 | 239478 | 7650 | 231828 | 239478 | 244020 | 0 | 0 | 0 | 244020 | 244020 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-07-06 | QTR1 | 20/21 | 514 | 158005.5 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6420 | 43345515201 | 2018-03-28 | QTR3 | 17/18 | 7 | 3 | 400 | 439 | 376 | 63 | 0 | 0 | 39 | 0 | 5904592 | 57482 | 5847110 | 5500862 | 5293728 | 0 | 300000 | 300000 | 5593728 | 5298829 | -289635 | -403730 | 22 | 0 | 0 | 12853 | 0 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -381786 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-07-23 | QTR1 | 20/21 | 2019-12-06 | QTR2 | 19/20 | 606 | 5663801.78 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 17 | 0 | 0 | -453468 | 0 |  | CO
06CO | 06 | T6422 | 42736925201 | 2018-05-23 | QTR4 | 17/18 | 4 | 7 | 450 | 477 | 414 | 63 | 0 | 0 | 27 | 0 | 37393744 | 150000 | 37243744 | 38509420 | 38324783 | 0 | 2120000 | 2120000 | 40444783 | 38240092 | -2140213 | 1115676 | 16 | 0 | 0 | 315785 | 6929 | 0 | 0 | 178454 | 20691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657107 | 0 | 0 | 0 | 2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153860 | 27620 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-09-14 | QTR1 | 20/21 | 2020-03-03 | QTR3 | 19/20 | 606 | 43619308.55 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6425 | 42597925201 | 2018-03-28 | QTR3 | 17/18 | 5 | 6 | 320 | 454 | 454 | 0 | 0 | 0 | 134 | 0 | 2976484 | 50780 | 2925704 | 3072883 | 2821239 | 0 | 0 | 0 | 2821239 | 2821817 | 578 | 96399 | 60 | 30 | 0 | 28628 | 0 | 0 | 0 | 40961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 0 | 0 | 0 | 13340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 86716 | 0 | F650024320 | H & J ASPHALT INC | N/A | N/A | N/A | N/A | 2020-07-02 | QTR1 | 20/21 | 2020-01-25 | QTR3 | 19/20 | 606 | 2758437.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6441 | 43117045201 | 2018-12-05 | QTR2 | 18/19 | 5 | 1 | 280 | 329 | 268 | 61 | 0 | 0 | 49 | 0 | 3159760 | 51255 | 3108505 | 3171958 | 3147560 | 0 | 200000 | 200000 | 3347560 | 3133596 | -201766 | 12198 | 24 | 0 | 0 | 990 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25329 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-15 | QTR1 | 20/21 | 2020-04-06 | QTR4 | 19/20 | 606 | 3433250.3 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6457 | 44018415201 | 2018-12-05 | QTR2 | 18/19 | 3 | 0 | 240 | 396 | 394 | 2 | 0 | 0 | 156 | 0 | 1600000 | 50000 | 1550000 | 1600000 | 1513631 | 0 | 0 | 0 | 1513631 | 1513712 | 81 | 0 | 77 | 45 | 0 | 9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 9205 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-19 | QTR1 | 20/21 | 2020-07-07 | QTR1 | 20/21 | 606 | 1865184.5 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6459 | 44018715201 | 2018-10-31 | QTR2 | 18/19 | 3 | 1 | 240 | 394 | 393 | 1 | 0 | 0 | 154 | 0 | 1799799 | 50000 | 1749799 | 1826976 | 1697745 | 0 | 0 | 0 | 1697745 | 1696156 | -1589 | 27177 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 10193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38588 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2020-06-17 | QTR4 | 19/20 | 606 | 1983631.35 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6470 | 43991715201 | 2019-03-27 | QTR3 | 18/19 | 1 | 1 | 140 | 186 | 186 | 0 | 0 | 0 | 46 | 0 | 457433 | 23458 | 433975 | 488251 | 450352 | 0 | 0 | 0 | 450352 | 449506 | -846 | 30818 | 24 | 0 | 0 | 6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-11 | QTR1 | 20/21 | 2020-04-16 | QTR4 | 19/20 | 636 | 481417.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H56 | 42999615201 | 2019-07-25 | QTR1 | 19/20 | 1 | 0 | 300 | 357 | 199 | 158 | 0 | 0 | 57 | 0 | 1195598 | 50000 | 1145598 | 1195598 | 1078448 | 0 | 0 | 0 | 1078448 | 1078448 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-07-01 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 613 | 1501204.95 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K86 | 43653215201 | 2018-09-27 | QTR1 | 18/19 | 2 | 4 | 275 | 325 | 325 | 0 | 0 | 0 | 50 | 0 | 1525830 | 50000 | 1475830 | 1665708 | 1656441 | 0 | 0 | 0 | 1656441 | 1648253 | 0 | 139878 | 27 | 0 | 0 | 21689 | 0 | 0 | 0 | 132259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153948 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-08-25 | QTR1 | 20/21 | 2020-05-28 | QTR4 | 19/20 | 606 | 1287132 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L92 | 44203815201 | 2019-03-28 | QTR3 | 18/19 | 2 | 1 | 140 | 176 | 122 | 54 | 0 | 0 | 36 | 0 | 454454 | 21560 | 432894 | 453454 | 414482 | 0 | 0 | 0 | 414482 | 414293 | -189 | -1000 | 35 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-24 | QTR1 | 20/21 | 2020-05-13 | QTR4 | 19/20 | 613 | 422168.15 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7406 | 42895715201 | 2018-05-23 | QTR4 | 17/18 | 1 | 12 | 500 | 602 | 522 | 80 | 0 | 0 | 102 | 0 | 15421093 | 150000 | 15271093 | 16109245 | 16482253 | 0 | 0 | 0 | 16482253 | 16467413 | -14840 | 688152 | 70 | 0 | 0 | 644715 | 0 | 0 | 0 | 78936 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726875 | 2053 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-09-22 | QTR1 | 20/21 | 2020-02-07 | QTR3 | 19/20 | 714 | 18474978.63 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7411 | 43982925201 | 2018-04-25 | QTR4 | 17/18 | 1 | 0 | 230 | 439 | 439 | 0 | 0 | 0 | 164 | 45 | 2168162 | 50000 | 2118162 | 2168162 | 2100062 | 0 | 0 | 0 | 2100062 | 2100043 | -20 | 0 | 91 | 0 | 45 | 9175 | 0 | 0 | 0 | 19720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 28895 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-08-14 | QTR1 | 20/21 | 2020-03-16 | QTR3 | 19/20 | 796 | 3284498.8 |  |  | 45 | 73 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7426 | 43648715201 | 2019-01-30 | QTR3 | 18/19 | 1 | 2 | 160 | 184 | 184 | 0 | 0 | 0 | 24 | 0 | 2303437 | 50000 | 2253437 | 2349376 | 2210807 | 0 | 0 | 0 | 2210807 | 2215714 | 4907 | 45939 | 13 | 0 | 0 | 36563 | 21000 | 0 | 0 | 19143 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55705 | 24000 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-08-05 | QTR1 | 20/21 | 2019-11-14 | QTR2 | 19/20 | 799 | 2215185 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7432 | 43982955201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 180 | 197 | 197 | 0 | 0 | 0 | 17 | 0 | 409384 | 20000 | 389384 | 409384 | 361091 | 0 | 0 | 0 | 361091 | 361076 | -16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2020-08-18 | QTR1 | 20/21 | 2020-05-05 | QTR4 | 19/20 | 799 | 490000 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7K30 | 42450725201 | 2017-06-08 | QTR4 | 16/17 | 2 | 8 | 850 | 1034 | 1034 | 0 | 0 | 0 | 111 | 73 | 8315000 | 50000 | 8265000 | 8940193 | 9001435 | 0 | 0 | 0 | 9001435 | 9001737 | 302 | 625193 | 45 | 0 | 0 | 160566 | 0 | 0 | 37 | 506158 | 21130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 669034 | 21130 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-09 | QTR4 | 19/20 | 799 | 8315000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M29 | 43954715201 | 2019-01-09 | QTR3 | 18/19 | 1 | 0 | 360 | 482 | 362 | 120 | 0 | 0 | 122 | 0 | 4417200 | 50000 | 4367200 | 4417200 | 4366662 | 0 | 0 | 0 | 4366662 | 4366662 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-20 | QTR1 | 20/21 | 2020-06-12 | QTR4 | 19/20 | 799 | 5635000 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M89 | 43878615201 | 2020-01-30 | QTR3 | 19/20 | 1 | 0 | 40 | 40 | 37 | 3 | 0 | 0 | 0 | 0 | 194157 | 11000 | 183157 | 194157 | 183157 | 0 | 0 | 0 | 183157 | 183157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-07-31 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 799 | 280000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N03 | 43673425201 | 2019-11-13 | QTR2 | 19/20 | 1 | 0 | 68 | 74 | 55 | 19 | 0 | 0 | 6 | 0 | 256281 | 10000 | 246281 | 256281 | 229693 | 0 | 0 | 0 | 229693 | 229693 | 0 | 0 | 3 | 0 | 0 | 9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9503 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-07-13 | QTR1 | 20/21 | 796 | 284491.89 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M65 | 40609615201 | 2013-06-13 | QTR4 | 12/13 | 3 | 22 | 1148 | 2470 | 2470 | 0 | 0 | 0 | 802 | 520 | 145330000 | 150000 | 145180000 | 156978418 | 155492910 | 0 | 0 | 0 | 155492910 | 152746494 | -2369264 | 11648418 | 291 | 0 | 520 | 7990065 | 1383055 | 0 | 0 | 28188 | 0 | 0 | 0 | 946876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 2107756 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 520 | 11106286 | 1383055 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2020-05-20 | QTR4 | 19/20 | 854 | 204625259.43 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N75 | 40611015201 | 2016-03-08 | QTR3 | 15/16 | 2 | 15 | 990 | 1453 | 1439 | 14 | 0 | 0 | 276 | 187 | 68542000 | 150000 | 68392000 | 73971118 | 73863918 | 0 | 0 | 0 | 73863918 | 74626044 | 991193 | 5429118 | 149 | 0 | 187 | 4801886 | 0 | 0 | 0 | 82274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68439 | 0 | 0 | 0 | 179429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 5313624 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-07-17 | QTR1 | 20/21 | 2020-04-09 | QTR4 | 19/20 | 854 | 66110895.23 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 127 | 0 | 0 | -88404 | 0 |  | DO
08DO | 08 | E8P02 | 40609055201 | 2015-06-16 | QTR4 | 14/15 | 5 | 28 | 1000 | 1399 | 1399 | 0 | 0 | 0 | 204 | 195 | 92527388 | 150000 | 92377388 | 97077732 | 98980425 | -16500 | 0 | -16500 | 98963925 | 97993828 | -551574 | 4550344 | 122 | 0 | 23 | 543416 | 184339 | 0 | 0 | 561569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 167 | 2782149 | 402197 | 0 | 0 | 106560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 4034291 | 586536 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-14 | QTR1 | 20/21 | 2019-07-19 | QTR1 | 19/20 | 854 | 105363394.12 |  |  | 1 | 82 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P82 | 43715615201 | 2016-06-14 | QTR4 | 15/16 | 3 | 25 | 800 | 1197 | 1239 | -42 | 42 | 0 | 304 | 93 | 31974887 | 150000 | 31824887 | 33530949 | 33963963 | -335724 | 0 | -335724 | 33628239 | 33931192 | 496445 | 1556062 | 183 | 0 | 16 | 38738 | 0 | 0 | 24 | 277655 | 61112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 51 | 1080366 | 0 | 0 | 2 | 104305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 93 | 1501064 | 61112 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2020-09-21 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 0 |  |  | 36 | 99 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q53 | 43516915201 | 2017-10-17 | QTR2 | 17/18 | 5 | 6 | 575 | 907 | 907 | 0 | 0 | 0 | 256 | 76 | 27945014 | 150000 | 27795014 | 28542025 | 28268831 | -3000 | 0 | -3000 | 28265831 | 29719984 | 1490912 | 597011 | 172 | 0 | 2 | 3085 | 0 | 0 | 0 | 15103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 365648 | 0 | 0 | 14 | 257157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 640993 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-27 | QTR4 | 19/20 | 854 | 31134083.09 |  |  | 16 | 84 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R19 | 43560565201 | 2019-03-12 | QTR3 | 18/19 | 1 | 1 | 250 | 319 | 318 | 1 | 0 | 0 | 51 | 18 | 3952490 | 50000 | 3902490 | 4022490 | 3821122 | 0 | 0 | 0 | 3821122 | 3821116 | -7 | 70000 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 88121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 93134 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-06-25 | QTR4 | 19/20 | 854 | 5097785.49 |  |  | 18 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R53 | 44130615201 | 2018-11-15 | QTR2 | 18/19 | 1 | 2 | 151 | 179 | 179 | 0 | 0 | 0 | 25 | 3 | 1048889 | 50000 | 998889 | 1191415 | 1210586 | 0 | 0 | 0 | 1210586 | 1189198 | -3862 | 142527 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125369 | 19602 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-07-16 | QTR1 | 20/21 | 2019-10-09 | QTR2 | 19/20 | 854 | 1135061.97 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R81 | 44132225201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 57 | 90 | 90 | 0 | 0 | 0 | 33 | 0 | 1331331 | 50000 | 1281331 | 1425403 | 1378701 | -20000 | 0 | -20000 | 1358701 | 1358701 | 0 | 94072 | 5 | 0 | 0 | 48107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2020-09-28 | QTR1 | 20/21 | 2020-03-20 | QTR3 | 19/20 | 854 | 1246055.98 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R99 | 42897115201 | 2019-09-10 | QTR1 | 19/20 | 1 | 1 | 374 | 395 | 160 | 235 | 0 | 0 | 21 | 0 | 994341 | 50000 | 944341 | 993765 | 857403 | 0 | 0 | 0 | 857403 | 857403 | 0 | -576 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9582 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-08-24 | QTR1 | 20/21 | 2020-05-15 | QTR4 | 19/20 | 854 | 1572137.64 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0