## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 381859 | 366769 | 381859 | 358474 | 0 | 358474 | -2.262% | 100% | 0 | 0% | 0 | 0% | 100 | 33 | 33% | 4 | 4% | 0 | 0% | 0 | 0% | 100 | 0% | 137 | 137 | 100 | 0% | 100%
| District Let | 50862032 | 50509125 | 53898689 | 53362755 | 0 | 53243684 | 5.414% | 100% | 2983256 | 5.906% | 3036656 | 5.97% | 1626 | 271 | 16.67% | 127 | 7.811% | 51 | 3.137% | 147 | 9.041% | 1824 | 12.18% | 2267 | 2244 | 1846 | 13.53% | 66.67%
| All Contracts | 51243891 | 50875894 | 54280548 | 53721229 | 0 | 53602158 | 5.359% | 100% | 2983256 | 5.864% | 3036656 | 5.926% | 1726 | 304 | 17.61% | 131 | 7.59% | 51 | 2.955% | 147 | 8.517% | 1924 | 11.47% | 2404 | 2381 | 1946 | 12.75% | 71.43%
2 | Central Let | 65087370 | 64669258 | 67756062 | 68631376 | 0 | 69048554 | 6.772% | 90% | 2705998 | 4.184% | 2668692 | 4.1% | 3035 | 611 | 20.13% | 396 | 13.05% | 0 | 0% | 377 | 12.42% | 3412 | 12.42% | 4542 | 4267 | 3260 | 7.414% | 90%
| District Let | 26252631 | 25811700 | 27223895 | 26967858 | 1350000 | 26957699 | 4.44% | 100% | 1109336 | 4.298% | 971265 | 3.7% | 2200 | 194 | 8.818% | 219 | 9.955% | 0 | 0% | 60 | 2.727% | 2260 | 2.727% | 2673 | 2224 | 1811 | -17.68% | 100%
| All Contracts | 91340001 | 90480958 | 94979957 | 95599234 | 1350000 | 96006253 | 6.107% | 94.12% | 3815334 | 4.217% | 3639957 | 3.985% | 5235 | 805 | 15.38% | 615 | 11.75% | 0 | 0% | 437 | 8.348% | 5672 | 8.348% | 7215 | 6491 | 5071 | -3.133% | 94.12%
3 | Central Let | 17683530 | 17508536 | 17884935 | 18354139 | 0 | 18248616 | 4.227% | 100% | 216997 | 1.239% | 201405 | 1.139% | 845 | 402 | 47.57% | 121 | 14.32% | 40 | 4.734% | 5 | 0.5917% | 890 | 5.325% | 1413 | 1412 | 889 | 5.207% | 100%
| District Let | 9384355 | 9234355 | 9433471 | 9432002 | 0 | 8557842 | -7.326% | 100% | 3638 | 0.0394% | 49116 | 0.5234% | 890 | 502 | 56.4% | 137 | 15.39% | 244 | 27.42% | 89 | 10% | 1223 | 37.42% | 1874 | 1949 | 1310 | 47.19% | 60%
| All Contracts | 27067885 | 26742891 | 27318406 | 27786141 | 0 | 26806458 | 0.2377% | 100% | 220635 | 0.825% | 250521 | 0.9255% | 1735 | 904 | 52.1% | 258 | 14.87% | 284 | 16.37% | 94 | 5.418% | 2113 | 21.79% | 3287 | 3361 | 2199 | 26.74% | 80%
4 | Central Let | 44443057 | 43890547 | 47349707 | 46381054 | 0 | 45939243 | 4.668% | 90% | 3126056 | 7.122% | 2906650 | 6.54% | 3503 | 650 | 18.56% | 280 | 7.993% | 0 | 0% | 166 | 4.739% | 3669 | 4.739% | 4599 | 4390 | 3460 | -1.228% | 100%
| District Let | 2392134 | 2292134 | 2407221 | 2172532 | 100000 | 2177173 | -5.015% | 100% | 49311 | 2.151% | 15087 | 0.6307% | 373 | 37 | 9.92% | 27 | 7.239% | 0 | 0% | 14 | 3.753% | 387 | 3.753% | 451 | 451 | 387 | 3.753% | 100%
| All Contracts | 46835191 | 46182681 | 49756928 | 48553586 | 100000 | 48116416 | 4.187% | 91.67% | 3175367 | 6.876% | 2921737 | 6.238% | 3876 | 687 | 17.72% | 307 | 7.921% | 0 | 0% | 180 | 4.644% | 4056 | 4.644% | 5050 | 4841 | 3847 | -0.7482% | 100%
5 | Central Let | 60614816 | 60056905 | 64349714 | 65426011 | 0 | 65997761 | 9.892% | 85.71% | 3955260 | 6.586% | 3734898 | 6.162% | 2259 | 663 | 29.35% | 317 | 14.03% | 0 | 0% | 902 | 39.93% | 3161 | 39.93% | 4207 | 4140 | 3160 | 39.88% | 42.86%
| District Let | 5732057 | 5519930 | 5765448 | 5620067 | 0 | 5611255 | 1.654% | 100% | 83310 | 1.509% | 33391 | 0.5825% | 980 | 207 | 21.12% | 180 | 18.37% | 0 | 0% | 26 | 2.653% | 1006 | 2.653% | 1393 | 1307 | 920 | -6.122% | 100%
| All Contracts | 66346873 | 65576835 | 70115162 | 71046078 | 0 | 71609016 | 9.199% | 92.31% | 4038570 | 6.159% | 3768289 | 5.68% | 3239 | 870 | 26.86% | 497 | 15.34% | 0 | 0% | 928 | 28.65% | 4167 | 28.65% | 5600 | 5447 | 4080 | 25.96% | 69.23%
6 | Central Let | 6134730 | 5970194 | 6203519 | 5998442 | 170000 | 5971870 | 0.02807% | 100% | 155266 | 2.601% | 68789 | 1.121% | 830 | 130 | 15.66% | 81 | 9.759% | 25 | 3.012% | 0 | 0% | 855 | 3.012% | 1066 | 978 | 767 | -7.59% | 100%
| District Let | 102457808 | 102111104 | 101120040 | 100866233 | 1320000 | 96855558 | -5.147% | 100% | -1770966 | -1.734% | -1337767 | -1.306% | 2480 | 305 | 12.3% | 279 | 11.25% | 68 | 2.742% | 29 | 1.169% | 2577 | 3.911% | 3177 | 2655 | 2071 | -16.49% | 100%
| All Contracts | 108592538 | 108081298 | 107323559 | 106864675 | 1490000 | 102827428 | -4.861% | 100% | -1615700 | -1.495% | -1268978 | -1.169% | 3310 | 435 | 13.14% | 360 | 10.88% | 93 | 2.81% | 29 | 0.8761% | 3432 | 3.686% | 4243 | 3633 | 2838 | -14.26% | 100%
7 | Central Let | 12584444 | 12403344 | 14503972 | 15099334 | 0 | 15329276 | 23.59% | 0% | 1985862 | 16.01% | 1919528 | 15.25% | 620 | 100 | 16.13% | 56 | 9.032% | 0 | 0% | 161 | 25.97% | 781 | 25.97% | 937 | 937 | 781 | 25.97% | 0%
| District Let | 15838116 | 15535758 | 16348919 | 16076989 | 0 | 15943912 | 2.627% | 100% | 545717 | 3.513% | 510802 | 3.225% | 1403 | 162 | 11.55% | 178 | 12.69% | 48 | 3.421% | 51 | 3.635% | 1502 | 7.056% | 1842 | 1717 | 1377 | -1.853% | 87.5%
| All Contracts | 28422560 | 27939102 | 30852891 | 31176323 | 0 | 31273188 | 11.93% | 88.89% | 2531579 | 9.061% | 2430330 | 8.551% | 2023 | 262 | 12.95% | 234 | 11.57% | 48 | 2.373% | 212 | 10.48% | 2283 | 12.85% | 2779 | 2654 | 2158 | 6.673% | 77.78%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 8222932 | 8099713 | 8665835 | 6108460 | 0 | 6078753 | -24.95% | 100% | 483862 | 5.974% | 442902 | 5.386% | 846 | 25 | 2.955% | 49 | 5.792% | 0 | 0% | 12 | 1.418% | 858 | 1.418% | 932 | 736 | 662 | -21.75% | #VALUE!
| All Contracts | 8222932 | 8099713 | 8665835 | 6108460 | 0 | 6078753 | -24.95% | 100% | 483862 | 5.974% | 442902 | 5.386% | 846 | 25 | 2.955% | 49 | 5.792% | 0 | 0% | 12 | 1.418% | 858 | 1.418% | 932 | 736 | 662 | -21.75% | 100%
Totals This Qtr | Central Let | 206929806 | 204865553 | 218429768 | 220248830 | 170000 | 220893794 | 7.824% | 89.47% | 12145439 | 5.928% | 11499962 | 5.557% | 11192 | 2589 | 23.13% | 1255 | 11.21% | 65 | 0.5808% | 1611 | 14.39% | 12868 | 14.97% | 16901 | 16261 | 12417 | 10.95% | 84.21%
| District Let | 221142065 | 219113819 | 224863518 | 220606896 | 2770000 | 215425876 | -1.683% | 100% | 3487464 | 1.592% | 3721452 | 1.683% | 10798 | 1703 | 15.77% | 1196 | 11.08% | 411 | 3.806% | 428 | 3.964% | 11637 | 7.77% | 14609 | 13283 | 10384 | -3.834% | 87.8%
| All Contracts | 428071871 | 423979372 | 443293286 | 440855726 | 2940000 | 436319670 | 2.911% | 94.94% | 15632903 | 3.687% | 15221414 | 3.556% | 21990 | 4292 | 19.52% | 2451 | 11.15% | 476 | 2.165% | 2039 | 9.272% | 24505 | 11.44% | 31510 | 29544 | 22801 | 3.688% | 86.08%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 97.74% | 1 | 0 | 0 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 1 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 100% | 1 | 0 | 0 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 141.3% | 0 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 103.5% | 1 | 357 | 69031 | 29 | 20 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85
| 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 127.9% | 0 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | 106.1% | 1 | -23194 | 2868754 | 166 | 60 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 |  | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 92% | 1 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 104.8% | 1 | 596 | 98871 | 44 | 17 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 |  | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2
| 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | 97.68% | 1 | -5733 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85
| 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 100% | 1 | 520 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 6 | 10 | 24 | 1626 | 2267 | 2244 | 66.67% | 4 | 23 | 0 | 0 | 449 | 192 | 50862032 | 352907 | 50509125 | 53898689 | 53362755 | 0 | 0 | 0 | 53362755 | 53243684 | 100% | 6 | -27454 | 3036656 | 271 | 127 | 51 | 106 | 3137062 | 18162 | 0 | 41 | 382856 | 129070 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 147 | 2983256 | 147232
| District 01 Totals |  |  |  |  | 7 | 11 | 24 | 1726 | 2404 | 2381 | 71.43% | 5 | 23 | 0 | 0 | 486 | 192 | 51243891 | 367997 | 50875894 | 54280548 | 53721229 | 0 | 0 | 0 | 53721229 | 53602158 | 100% | 7 | -27454 | 3036656 | 304 | 131 | 51 | 106 | 3137062 | 18162 | 0 | 41 | 382856 | 129070 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 147 | 2983256 | 147232
| 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 106.7% | 1 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 108.4% | 1 | 593970 | 1812123 | 319 | 136 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1
| 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 109.6% | 1 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | 103% | 1 | -48704 | 243564 | 155 | 52 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69
| 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | 215.7% | 0 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | 102.4% | 1 | -1358 | 52280 | 46 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1
| 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 77% | 1 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | 115.8% | 0 | -19174 | 475406 | 27 | 28 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1
| 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 62.5% | 1 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 99.16% | 1 | 752 | 0 | 38 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42
| 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 60.56% | 1 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 97.14% | 1 | 0 | -4773 | 3 | 23 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49
| 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 98.67% | 1 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 99.41% | 1 | 338 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88
| 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 84% | 1 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 104% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46
| 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 65% | 1 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 99.22% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86
| 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 104.4% | 1 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 105.2% | 1 | 0 | 90092 | 12 | 17 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 10 | 16 | 28 | 3035 | 4542 | 4267 | 90% | 9 | 275 | 12 | 0 | 1130 | 377 | 65087370 | 418112 | 64669258 | 67756062 | 68631376 | -32544 | 0 | -32544 | 68598832 | 69048554 | 90% | 9 | 525824 | 2668692 | 611 | 396 | 0 | 95 | 1268047 | 14023 | 0 | 34 | 1116554 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 48568 | 40265 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 59 | 0 | 0 | 0 | 58 | 151235 | 151235 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 0 | 377 | 2705998 | 247943
| 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 108% | 1 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | 108.1% | 1 | -1354420 | 997337 | 55 | 118 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 |  | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 84% | 1 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 87.7% | 1 | 0 | -75888 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32
| 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 99.33% | 1 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | 98.28% | 1 | -1374 | 0 | 63 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78
| 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 98.33% | 1 | 0 | 0 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99
| 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 30.23% | 1 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 99.9% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7
| 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 62.58% | 1 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 105.3% | 1 | 0 | 49816 | 24 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86
| 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 99.07% | 1 | 0 | 0 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 7 | 10 | 15 | 2200 | 2673 | 2224 | 100% | 7 | 449 | 0 | 0 | 413 | 60 | 26252631 | 440931 | 25811700 | 27223895 | 26967858 | 0 | 1350000 | 1350000 | 28317858 | 26957699 | 100% | 7 | -1355794 | 971265 | 194 | 219 | 0 | 0 | 309118 | 216458 | 0 | 0 | 384427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | 0 | 60 | 1109336 | 216458
| District 02 Totals |  |  |  |  | 17 | 26 | 43 | 5235 | 7215 | 6491 | 94.12% | 16 | 724 | 12 | 0 | 1543 | 437 | 91340001 | 859043 | 90480958 | 94979957 | 95599234 | -32544 | 1350000 | 1317456 | 96916690 | 96006253 | 94.12% | 16 | -829970 | 3639957 | 805 | 615 | 0 | 95 | 1577165 | 230481 | 0 | 34 | 1500981 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 535882 | 40265 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 165545 | 0 | 0 | 119 | 0 | 0 | 0 | 58 | 151235 | 151235 | 0 | 0 | 0 | 0 | 0 | 0 | -149132 | 0 | 0 | 437 | 3815334 | 464401
| 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 99.27% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 |  | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM
| 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 115.3% | 1 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | 98.95% | 1 | -2489 | -30187 | 126 | 44 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8
| 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 101.3% | 1 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 104.2% | 1 | 247 | 27245 | 34 | 16 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46
| 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 102.7% | 1 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | 108.4% | 1 | -50153 | 204347 | 63 | 25 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85
| 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | 101.9% | 1 | -53128 | 0 | 168 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 5 | 6 | 4 | 845 | 1413 | 1412 | 100% | 5 | 1 | 0 | 0 | 563 | 5 | 17683530 | 174995 | 17508536 | 17884935 | 18354139 | 0 | 0 | 0 | 18354139 | 18248616 | 100% | 5 | -105523 | 201405 | 402 | 121 | 17 | 5 | 5518 | 0 | 21 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 216997 | 0
| 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | 208.7% | 0 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 91.39% | 1 | 0 | 49116 | 256 | 90 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 159.3% | 0 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 100% | 1 | 0 | 0 | 213 | 23 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 |  | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049
| 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 52.67% | 1 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | 0% | 1 | -174645 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33
| 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 101.7% | 1 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | 105.3% | 1 | -2525 | 0 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39
| 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 85.56% | 1 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | 0% | 1 | -225968 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-10-20 | QTR2 | 20/21 | 314 | 246220
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 5 | 9 | 8 | 890 | 1874 | 1949 | 60% | 3 | -75 | 160 | 0 | 883 | 101 | 9384355 | 150000 | 9234355 | 9433471 | 9432002 | -449760 | 0 | -449760 | 8982242 | 8557842 | 100% | 5 | -403138 | 49116 | 502 | 137 | 241 | 71 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 89 | 3638 | 0
| District 03 Totals |  |  |  |  | 10 | 15 | 12 | 1735 | 3287 | 3361 | 80% | 8 | -74 | 160 | 0 | 1446 | 106 | 27067885 | 324995 | 26742891 | 27318406 | 27786141 | -449760 | 0 | -449760 | 27336381 | 26806458 | 100% | 10 | -508661 | 250521 | 904 | 258 | 258 | 76 | 5518 | 0 | 21 | 0 | 10770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 18 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 94 | 220635 | 0
| 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | 110% | 1 | -79 | 50449 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52
| 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 103.4% | 1 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | 103.1% | 1 | -41100 | 238143 | 56 | 38 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83
| 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 120% | 1 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | 121.4% | 0 | -38478 | 1701896 | 99 | 57 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34
| 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 104.1% | 1 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | 108.7% | 1 | -136647 | 836144 | 110 | 44 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29
| 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 101.4% | 1 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | 96.13% | 1 | -58724 | -97855 | 61 | 33 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17
| 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 99.49% | 1 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | 104.1% | 1 | -17714 | 162310 | 92 | 33 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17
| 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 72.21% | 1 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | 92.16% | 1 | -17236 | -58454 | 82 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 |  | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2
| 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 102.5% | 1 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | 97.23% | 1 | -108218 | 74017 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95
| 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 90.84% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3
| 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66.83% | 1 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 98.35% | 1 | 237 | 0 | 25 | 18 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 10 | 18 | 30 | 3503 | 4599 | 4390 | 100% | 10 | 209 | 0 | 0 | 930 | 166 | 44443057 | 552510 | 43890547 | 47349707 | 46381054 | 0 | 0 | 0 | 46381054 | 45939243 | 90% | 9 | -417959 | 2906650 | 650 | 280 | 0 | 117 | 2399261 | 1339455 | 0 | 25 | 694733 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 61674 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 28229 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 166 | 3126056 | 1459832
| 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 100.7% | 1 | 95 | -399 | 22 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08
| 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 110.9% | 1 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | 88.88% | 1 | -95454 | 15486 | 15 | 5 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 |  | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 2 | 4 | 2 | 373 | 451 | 451 | 100% | 2 | 0 | 0 | 0 | 64 | 14 | 2392134 | 100000 | 2292134 | 2407221 | 2172532 | 0 | 100000 | 100000 | 2272532 | 2177173 | 100% | 2 | -95359 | 15087 | 37 | 27 | 0 | 0 | 5727 | 0 | 0 | 14 | 37601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 49311 | 0
| District 04 Totals |  |  |  |  | 12 | 22 | 32 | 3876 | 5050 | 4841 | 100% | 12 | 209 | 0 | 0 | 994 | 180 | 46835191 | 652510 | 46182681 | 49756928 | 48553586 | 0 | 100000 | 100000 | 48653586 | 48116416 | 91.67% | 11 | -513318 | 2921737 | 687 | 307 | 0 | 117 | 2404988 | 1339455 | 0 | 39 | 732334 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 67655 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 28229 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 180 | 3175367 | 1459832
| 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 113.9% | 1 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 105.7% | 1 | 430838 | 374749 | 219 | 102 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3
| 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 137.8% | 0 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 104% | 1 | 328547 | 8369 | 210 | 62 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22
| 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 347.9% | 0 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | 219.7% | 0 | -16169 | 3253176 | 23 | 51 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320
| 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 134.8% | 0 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | 101.4% | 1 | -48503 | 72336 | 18 | 22 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68
| 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 150% | 0 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | 105.3% | 1 | -28879 | 22908 | 74 | 22 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 |  | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09
| 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 89.33% | 1 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | 97.46% | 1 | -39533 | 3360 | 113 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7
| 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 99.23% | 1 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 100.2% | 1 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 7 | 15 | 26 | 2259 | 4207 | 4140 | 42.86% | 3 | 67 | 0 | 0 | 980 | 968 | 60614816 | 557911 | 60056905 | 64349714 | 65426011 | -7304 | 0 | -7304 | 65418707 | 65997761 | 85.71% | 6 | 627150 | 3734898 | 663 | 317 | 0 | 117 | 283289 | 19394 | 0 | 785 | 3457325 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902 | 3955260 | 32143
| 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 107.2% | 1 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 102.7% | 1 | 0 | 30409 | 84 | 17 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5
| 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 81.25% | 1 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 92.06% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 507 | 309304
| 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 117.1% | 1 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 102.1% | 1 | 0 | 0 | 7 | 5 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03
| 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 31% | 1 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 98.44% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5
| 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 99.5% | 1 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | 99.98% | 1 | -5035 | 2982 | 41 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55
| 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | 105.3% | 1 | -795 | 0 | 72 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 6 | 6 | 2 | 980 | 1393 | 1307 | 100% | 6 | 86 | 0 | 0 | 387 | 26 | 5732057 | 212127 | 5519930 | 5765448 | 5620067 | 0 | 0 | 0 | 5620067 | 5611255 | 100% | 6 | -5830 | 33391 | 207 | 180 | 0 | 26 | 94382 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 83310 | 0
| District 05 Totals |  |  |  |  | 13 | 21 | 28 | 3239 | 5600 | 5447 | 69.23% | 9 | 153 | 0 | 0 | 1367 | 994 | 66346873 | 770038 | 65576835 | 70115162 | 71046078 | -7304 | 0 | -7304 | 71038774 | 71609016 | 92.31% | 12 | 621320 | 3768289 | 870 | 497 | 0 | 143 | 377671 | 19394 | 0 | 785 | 3397725 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928 | 4038570 | 32143
| 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 78.39% | 1 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | 101.8% | 1 | -195345 | 68789 | 27 | 20 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 99.5% | 1 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | 98.87% | 1 | -98 | 0 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85
| 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 85.71% | 1 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 93.34% | 1 | 39 | 0 | 42 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5
| 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | 98.18% | 1 | -1169 | 0 | 36 | 18 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 4 | 9 | 1 | 830 | 1066 | 978 | 100% | 4 | 88 | 0 | 0 | 236 | 0 | 6134730 | 164536 | 5970194 | 6203519 | 5998442 | 0 | 170000 | 170000 | 6168442 | 5971870 | 100% | 4 | -196573 | 68789 | 130 | 81 | 0 | 0 | 17349 | 0 | 0 | 0 | 36674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 88829 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 155266 | 0
| 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 106.7% | 1 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 103.5% | 1 | 0 | 110603 | 110 | 22 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689
| 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 75.3% | 1 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | 101.6% | 1 | -991000 | 1610952 | 139 | 172 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 |  | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 119.2% | 1 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | 0% | 1 | -3778569 | 105786 | 32 | 57 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 58.73% | 1 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 30.46% | 1 | 0 | -3198332 | 6 | 25 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 100.9% | 1 | 0 | 33224 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 5 | 9 | 22 | 2480 | 3177 | 2655 | 100% | 5 | 522 | 0 | 0 | 668 | 29 | 102457808 | 346704 | 102111104 | 101120040 | 100866233 | 0 | 1320000 | 1320000 | 102186233 | 96855558 | 100% | 5 | -4769569 | -1337767 | 305 | 279 | 37 | 11 | -2091986 | 239375 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 18 | 516539 | 0 | 0 | 0 | 301908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 68 | 29 | -1770966 | 239375
| District 06 Totals |  |  |  |  | 9 | 18 | 23 | 3310 | 4243 | 3633 | 100% | 9 | 610 | 0 | 0 | 904 | 29 | 108592538 | 511240 | 108081298 | 107323559 | 106864675 | 0 | 1490000 | 1490000 | 108354675 | 102827428 | 100% | 9 | -4966142 | -1268978 | 435 | 360 | 37 | 11 | -2074637 | 239375 | 0 | 0 | 40591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 18 | 605368 | 0 | 0 | 0 | 314320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 93 | 29 | -1615700 | 239375
| 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 126% | 0 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 123.6% | 0 | 248412 | 1919528 | 100 | 56 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 1 | 4 | 13 | 620 | 937 | 937 | 0% | 0 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 0% | 0 | 248412 | 1919528 | 100 | 56 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580
| 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 101.1% | 1 | 0 | 0 | 33 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000
| 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 124.7% | 0 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | 98.85% | 1 | -57396 | 31514 | 24 | 30 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 |  | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300
| 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 72.14% | 1 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 109.2% | 1 | 0 | 49500 | 4 | 15 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7
| 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 90% | 1 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 100.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 796 | 485498
| 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 65.14% | 1 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | 100.8% | 1 | -35622 | 0 | 62 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64
| 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 98.24% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 796 | 127700
| 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 109.6% | 1 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | 107.1% | 1 | -41787 | 386330 | 30 | 49 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 106.7% | 1 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 103.7% | 1 | 1729 | 43458 | 9 | 15 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 8 | 8 | 8 | 1403 | 1842 | 1717 | 87.5% | 7 | 125 | 0 | 0 | 372 | 67 | 15838116 | 302358 | 15535758 | 16348919 | 16076989 | 0 | 0 | 0 | 16076989 | 15943912 | 100% | 8 | -133076 | 510802 | 162 | 178 | 21 | 14 | 89983 | 0 | 27 | 37 | 410735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 51 | 545717 | 16552
| District 07 Totals |  |  |  |  | 9 | 12 | 21 | 2023 | 2779 | 2654 | 77.78% | 7 | 125 | 0 | 0 | 528 | 228 | 28422560 | 483458 | 27939102 | 30852891 | 31176323 | 0 | 0 | 0 | 31176323 | 31273188 | 88.89% | 8 | 115336 | 2430330 | 262 | 234 | 21 | 65 | 875965 | 22437 | 27 | 147 | 1336593 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 212 | 2531579 | 422132
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 75.97% | 1 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | 74.35% | 1 | -1807 | 442902 | 15 | 45 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51
| 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 101.3% | 1 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 91.92% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 2 | 2 | 2 | 846 | 932 | 736 | #VALUE! | 2 | 196 | 0 | 0 | 74 | 12 | 8222932 | 123220 | 8099713 | 8665835 | 6108460 | 0 | 0 | 0 | 6108460 | 6078753 | 100% | 2 | -1807 | 442902 | 25 | 49 | 0 | 10 | 58365 | 0 | 0 | 2 | 423652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 483862 | 0
| District 08 Totals |  |  |  |  | 2 | 2 | 2 | 846 | 932 | 736 | 100% | 2 | 196 | 0 | 0 | 74 | 12 | 8222932 | 123220 | 8099713 | 8665835 | 6108460 | 0 | 0 | 0 | 6108460 | 6078753 | 100% | 2 | -1807 | 442902 | 25 | 49 | 0 | 10 | 58365 | 0 | 0 | 2 | 423652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 483862 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 38 | 69 | 102 | 11192 | 16901 | 16261 | 84.21% | 32 | 640 | 12 | 0 | 4032 | 1677 | 206929806 | 2064254 | 204865553 | 218429768 | 220248830 | -39848 | 170000 | 130152 | 220378982 | 220893794 | 89.47% | 34 | 681331 | 11499962 | 2589 | 1255 | 17 | 385 | 4759446 | 1395309 | 21 | 954 | 6238276 | 517162 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 25 | 141 | 533530 | 40265 | 2 | 0 | 304846 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 169671 | 0 | 0 | 59 | 182439 | 6450 | 0 | 72 | 158991 | 158991 | 0 | 0 | 0 | 0 | 0 | 0 | -172785 | 0 | 65 | 1611 | 12145439 | 2145498
| Statewide District Let Contracts SubTotal |  |  |  |  | 41 | 58 | 83 | 10798 | 14609 | 13283 | 87.8% | 36 | 1326 | 160 | 0 | 3310 | 501 | 221142065 | 2028247 | 219113819 | 224863518 | 220606896 | -449760 | 2770000 | 2320240 | 222927136 | 215425876 | 100% | 41 | -6792027 | 3721452 | 1703 | 1196 | 350 | 238 | 1602651 | 473995 | 27 | 94 | 1587226 | 129070 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 34 | 18 | 1189088 | 0 | 0 | 18 | -275244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54737 | 0 | 0 | 60 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -577232 | 0 | 411 | 428 | 3487464 | 619617
| Statewide Totals |  |  |  |  | 79 | 127 | 185 | 21990 | 31510 | 29544 | 86.08% | 68 | 1966 | 172 | 0 | 7342 | 2178 | 428071871 | 4092501 | 423979372 | 443293286 | 440855726 | -489608 | 2940000 | 2450392 | 443306118 | 436319670 | 94.94% | 75 | -6110696 | 15221414 | 4292 | 2451 | 367 | 623 | 6362097 | 1869304 | 48 | 1048 | 7825502 | 646232 | 0 | 0 | 0 | 0 | 0 | 0 | -167739 | 0 | 0 | 0 | 0 | 0 | 59 | 159 | 1722618 | 40265 | 2 | 18 | 29602 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 224408 | 0 | 0 | 119 | 227439 | 23002 | 0 | 72 | 158991 | 158991 | 0 | 0 | 0 | 0 | 0 | 0 | -750017 | 0 | 476 | 2039 | 15632903 | 2765115

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P48 | 43489815201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-01-16 | 881862 | 950893 | 869654 | 69030.94 | 0 | 870011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869654 | 870011 | 357 | 901555
1 | E1Q47 | 42584135201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-03-15 | 44539372 | 47408126 | 47193361 | 2868754.26 | 0 | 47170167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47193361 | 47170167 | -23194 | 59075332 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
1 | E1S53 | 43890215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1335282 | 1434154 | 1346419 | 98871.24 | 0 | 1347016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 1282338
1 | E1S54 | 44334015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-06-11 | 2038002 | 2038002 | 1947616 | 0 | 0 | 1941883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 2189903
1 | E1T47 | 44624415201 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2020-07-15 | 1836500 | 1836500 | 1786500 | 0 | 0 | 1787020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 1849529 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1T84 | 43506615201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 231014 | 231014 | 219205 | 0 | 0 | 219205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219205 | 219205 | 0 | 230282 | B0 | ACC - LUMP SUM
1 | T1764 | 44013015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 381859 | 381859 | 358474 | 0 | 0 | 358474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358474 | 358474 | 0 | 386666
2 | E2V69 | 21327275201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-10-18 | 16294500 | 17291837 | 17466265 | 997337.38 | 1350000 | 17461845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 350000 | 0 | 0 | 0 | 1350000 | 1350000 | 18816265 | 17461845 | -1354420 | 18122424 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | E2Y24 | 43743715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-05-13 | 1280762 | 1204874 | 1079365 | -75887.97 | 0 | 1079365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | 2106516
2 | E2Y85 | 43865025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 3884320 | 3884320 | 3769800 | 0 | 0 | 3768427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 4380189
2 | E2Z24 | 44199735216 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-02-19 | 1624143 | 1624143 | 1547862 | 0 | 0 | 1547862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 1701419
2 | E2Z39 | 43122445201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-15 | 788792 | 788792 | 738086 | 0 | 0 | 738086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738086 | 738086 | 0 | 1315900
2 | E2Z50 | 42848915201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-03-18 | 1635960 | 1685775 | 1669775 | 49815.5 | 0 | 1669775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 1762747
2 | E2Z56 | 43807915201 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 744154 | 744154 | 696705 | 0 | 0 | 696705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696705 | 696705 | 0 | 797486
2 | T2573 | 21071125201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 39980618 | 41792741 | 42556288 | 1812123.25 | 0 | 43150258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42556288 | 43150258 | 593970 | 35388991
2 | T2700 | 41525015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-04-25 | 11881880 | 12125444 | 12326250 | 243563.71 | 0 | 12277546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12326250 | 12277546 | -48704 | 8810905
2 | T2712 | 43240415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-29 | 3754465 | 3806745 | 3827055 | 52279.5 | -32544 | 3793154 | -32544 | 0 | 0 | 0 | 0 | 0 | -32544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32544 | 3794511 | 3793154 | -1358 | 4106536
2 | T2753 | 43980015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 3416497 | 3891903 | 3917050 | 475405.64 | 0 | 3897876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 3898969
2 | T2768 | 43948815201 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 1959598 | 1959598 | 1892736 | 0 | 0 | 1893489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 1755198
2 | T2770 | 43948915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 601043 | 596270 | 539883 | -4773.2 | 0 | 539883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539883 | 539883 | 0 | 942548
2 | T2774 | 43578015201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-05-20 | 1066490 | 1066490 | 1059789 | 0 | 0 | 1060127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 1110094
2 | T2776 | 43399315201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 198978 | 198978 | 196874 | 0 | 0 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196874 | 196874 | 0 | 202254
2 | T2780 | 43732515201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 237581 | 237581 | 222711 | 0 | 0 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222711 | 222711 | 0 | 289607
2 | T9022 | 44531935223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 1990220 | 2080312 | 2092740 | 90091.64 | 0 | 2092740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 1872855
3 | E3Q53 | 44009615201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2017-07-20 | 4412093 | 4461209 | 4457747 | 49116.18 | -449760 | 4007987 | -449760 | 0 | 0 | 0 | 0 | 0 | -449760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -449760 | 4007987 | 4007987 | 0 | 4688435 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
3 | E3S42 | 42187345201 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 2507433 | 2507433 | 2457433 | 0 | 0 | 2457433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 2985049
3 | E3S73 | 4453811H201 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2019-12-12 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174645 | 0 | -174645 | 212648
3 | E3T25 | 44154615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 2058102 | 2058102 | 2116209 | 0 | 0 | 2113685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 2347515
3 | E3T66 | 4450184H201 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2020-03-12 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225968 | 0 | -225968 | 246220
3 | T3640 | 43290925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 720412 | 720412 | 691249 | 0 | 0 | 691249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691249 | 691249 | 0 | 499997 | B0 | ACC - LUMP SUM
3 | T3699 | 43228415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2694142 | 2663955 | 2668318 | -30186.8 | 0 | 2665830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | 2634440
3 | T3717 | 43720215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 770613 | 797858 | 802448 | 27244.97 | 0 | 802695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802448 | 802695 | 247 | 750108
3 | T3729 | 43972715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 7592042 | 7796389 | 8177990 | 204347 | 0 | 8127837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 9289556
3 | T3744 | 43972415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 5906321 | 5906321 | 6014134 | 0 | 0 | 5961005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 5368996
4 | E4U24 | 43984115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2020-03-06 | 1238848 | 1238449 | 1196529 | -399.46 | 0 | 1196625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | 1271431
4 | E4U54 | 44330915201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-07 | 1153286 | 1168772 | 976003 | 15485.58 | 100000 | 980548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | T4488 | 43630415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 552418 | 602867 | 592608 | 50448.67 | 0 | 592529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592608 | 592529 | -79 | 285675
4 | T4494 | 43630715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5685198 | 5923341 | 5849802 | 238143.16 | 0 | 5808702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 5359259
4 | T4497 | 43783615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 7969825 | 9671721 | 9618307 | 1701895.88 | 0 | 9579829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9618307 | 9579829 | -38478 | 9083314
4 | T4504 | 43783815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 8446061 | 9282205 | 9225023 | 836144.4 | 0 | 9088376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 9046599
4 | T4505 | 43668515201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 7195336 | 7097482 | 6908157 | -97854.53 | 0 | 6849432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6908157 | 6849432 | -58724 | 7395888
4 | T4509 | 43177055201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-04-24 | 3049775 | 3212084 | 3151909 | 162309.67 | 0 | 3134194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151909 | 3134194 | -17714 | 2802936
4 | T4511 | 43469015201 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2099355 | 2040900 | 1905910 | -58454.44 | 0 | 1888675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | 2266163
4 | T4523 | 43469515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 8207877 | 8281895 | 8003190 | 74017.2 | 0 | 7894972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 8969821
4 | T4528 | 43696715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 547645 | 547645 | 476343 | 0 | 0 | 476343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476343 | 476343 | 0 | 487570
4 | T4543 | 43915915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 689567 | 689567 | 649805 | 0 | 0 | 650042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649805 | 650042 | 237 | 603406
5 | E50A9 | 44326415201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-03-03 | 1277250 | 1307659 | 1259799 | 30409.22 | 0 | 1259799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 1837867
5 | E52A3 | 44539615201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 254016 | 254016 | 220075 | 0 | 0 | 220075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220075 | 220075 | 0 | 309304
5 | E53A9 | 44101715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 789395 | 789395 | 772436 | 0 | 0 | 772436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772436 | 772436 | 0 | 659076
5 | E54A9 | 44541215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-03-02 | 239156 | 239156 | 221370 | 0 | 0 | 221370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221370 | 221370 | 0 | 305554
5 | E5Z88 | 43793715201 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 1872651 | 1875633 | 1830367 | 2981.59 | 0 | 1825332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830367 | 1825332 | -5035 | 1916337
5 | E5Z96 | 44116615201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 1299589 | 1299589 | 1316020 | 0 | 0 | 1315225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 1579621
5 | T5538 | 23949635201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 27752000 | 28126749 | 28782547 | 374748.52 | -7304 | 29206081 | 0 | 0 | 0 | 0 | 0 | -7304 | -7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7304 | 28775243 | 29206081 | 430838 | 28403237
5 | T5582 | 23827585201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 9883550 | 9891919 | 9834478 | 8369.37 | 0 | 10163025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834478 | 10163025 | 328547 | 14381890
5 | T5637 | 43386015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-10-31 | 3244000 | 6497176 | 7037281 | 3253176.27 | 0 | 7021113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037281 | 7021113 | -16169 | 3081320
5 | T5669 | 43923515201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2019-10-30 | 9146375 | 9218711 | 9241919 | 72336.38 | 0 | 9193416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 7779291
5 | T5676 | 43913915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 3433963 | 3456872 | 3590532 | 22908.37 | 0 | 3561652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 4003251
5 | T5681 | 43968215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-25 | 5811031 | 5814390 | 5643783 | 3359.62 | 0 | 5604250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 6194317
5 | T5701 | 44136515201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 1343897 | 1343897 | 1295471 | 0 | 0 | 1296320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 1376221
6 | E6K73 | 43653715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-25 | 4293668 | 4404270 | 4390585 | 110602.64 | 0 | 4390585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 3248689
6 | E6K77 | 42930035201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-23 | 89490000 | 91100952 | 91019470 | 1610951.88 | 1320000 | 91348469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 0 | 0 | 1320000 | 1320000 | 92339470 | 91348469 | -991000 | 75222050 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
6 | E6L90 | 43029139201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-05-03 | 3703968 | 3809754 | 3778569 | 105785.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6M32 | 44204015201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-05 | 4679092 | 1480760 | 1400668 | -3198331.59 | 0 | 1400668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
6 | E6M47 | 44196115201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 291080 | 324304 | 276941 | 33224 | 0 | 276941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276941 | 276941 | 0 | 335060
6 | T6465 | 43345535201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-12-04 | 3445403 | 3514192 | 3479994 | 68789.07 | 170000 | 3454649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 3079920 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6472 | 44167015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-02-26 | 1098693 | 1098693 | 1036954 | 0 | 0 | 1036856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 1175314
6 | T6478 | 44030415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 419419 | 419419 | 372140 | 0 | 0 | 372179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372140 | 372179 | 39 | 420618
6 | T6498 | 43080835201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 1171215 | 1171215 | 1109354 | 0 | 0 | 1108186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 865294
7 | E7M94 | 43673415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 1352812 | 1352812 | 1317432 | 0 | 0 | 1317432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 1640000
7 | E7M96 | 43762615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-13 | 4564698 | 4596212 | 4520073 | 31514.1 | 0 | 4462676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 5061300
7 | E7N02 | 44383315201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-03-11 | 741228 | 790728 | 771044 | 49500 | 0 | 771044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771044 | 771044 | 0 | 741279
7 | E7N46 | 43955415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-09 | 357252 | 357252 | 337890 | 0 | 0 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337890 | 337890 | 0 | 485498
7 | E7N48 | 44025215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | 3104340 | 3104340 | 3112890 | 0 | 0 | 3077268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 4202893
7 | E7N59 | 44701515201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-01-20 | 86342 | 86342 | 80991 | 0 | 0 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80991 | 80991 | 0 | 127700
7 | E7R17 | 44368415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-30 | 4637000 | 5023330 | 4952442 | 386330.45 | 0 | 4910655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R25 | 44335815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-04 | 994444 | 1037903 | 984227 | 43458.19 | 0 | 985956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 922458 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7385 | 25624325201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2016-06-20 | 12584444 | 14503972 | 15099334 | 1919527.94 | 0 | 15347747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15099334 | 15347747 | 248412 | 18085000
8 | E8R55 | 42815445201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2019-04-09 | 7871284 | 8314187 | 5811967 | 442902.29 | 0 | 5810160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5811967 | 5810160 | -1807 | 9545164
8 | E8S73 | 44429215201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2020-09-15 | 351648 | 351648 | 296493 | 0 | 0 | 296493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296493 | 296493 | 0 | 613041

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 |  | 82368.6 |  | 0 | 0 | 64863.48 |  | 147232.08 |  | 51243891 | 0.1607% | 82368.6
02 |  | 253197.39 |  |  | 169481.27 | 109062.76 |  | 531741.42 |  | 91340001 | 0.4628% | 422678.66
03 |  | 0 |  |  |  | 3760 |  | 3760 |  | 27067885 | 0% | 0
04 |  | 5836.77 | 23462.14 | 3759.87 | 108081.69 | 1355856.74 |  | 1496997.21 |  | 46835191 | 0.3014% | 141140.47
05 |  | 13444.86 |  | 0 | 6449.59 | 22667.56 | -199979.96 | -157417.95 |  | 66346873 | 0.02999% | 19894.45
06 |  | 21058.24 |  | 729.42 | 231933.48 | 16718.98 |  | 270440.12 |  | 108592538 | 0.2336% | 253721.14
07 |  | 2027.92 |  | 395425.93 | 11953.81 | 47021.97 |  | 456429.63 |  | 28422560 | 1.44% | 409407.66
08 | [5 empty] | 0 |  | 0 |  | 8222932 | 0% | 0
Grand Total |  | 377933.78 | 23462.14 | 399915.22 | 527899.84 | 1619951.49 | -199979.96 | 2749182.51 |  | 428071871 | 0.3105% | 1329210.98
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 |  | 11 |  | 41 | 0 | 140 |  | 192 |  | 52
02 |  | 34 |  |  | 117 | 286 |  | 437 |  | 151
03 |  | 0 |  |  |  | 106 |  | 106 |  | 0
04 |  | 39 | 0 | 0 | 14 | 127 |  | 180 |  | 53
05 |  | 40 |  | 0 | 0 | 954 | 0 | 994 |  | 40
06 |  | 0 |  | 0 | 0 | 29 |  | 29 |  | 0
07 |  | 0 |  | 163 | 33 | 32 |  | 228 |  | 196
08 | [5 empty] | 12 |  | 12 |  | 0
Grand Total |  | 124 | 0 | 204 | 164 | 1686 | 0 | 2178 |  | 492
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 | [5 empty] | 71 | 71 |  | 0 | 52 | 1726 | 3.013%
02 | [5 empty] | 66 | 66 |  | 0 | 151 | 5235 | 2.884%
03 |  | 7 |  |  | 2 | 518 | 527 |  | 9 | 9 | 1735 | 0.5187%
04 | [5 empty] | 42 | 42 |  | 0 | 53 | 3876 | 1.367%
05 | [8 empty] | 0 | 40 | 3239 | 1.235%
06 | [5 empty] | 109 | 109 |  | 0 | 0 | 3310 | 0%
07 |  | 27 |  |  |  | 21 | 48 |  | 27 | 223 | 2023 | 11.02%
08 | [8 empty] | 0 | 0 | 846 | 0%
Grand Total |  | 34 |  |  | 2 | 827 | 863 |  | 36 | 528 | 21990 | 2.401%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 012 | 2 |  | 1 | 019 | 22039.78 | 18162.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | [13 empty] | Avoidable, CEI Consultant
01 | E1P48 | 43489815201 | 013 | 2 |  | 1 | 106 | 41653.88 | 41653.88 | 1 |  | N | 11 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P48 | 43489815201 | 013 | 2 |  | 2 | 003 | 2927.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P48 | 43489815201 | 014 | 2 |  | 1 | 101 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P48 | 43489815201 | 014 | 2 |  | 2 | 101 | 1060 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 004 | 2 |  | 1 | 007 | -982399.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 006 | 2 |  | 1 | 300 | -138762.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
01 | E1Q47 | 42584135201 | 012 | 2 |  | 1 | 105 | 31099.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 012 | 2 |  | 2 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 015 | 2 |  | 1 | 105 | -387328.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 016 | 2 |  | 1 | 007 | 952605.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 023 | 2 |  | 1 | 503 | 179253.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q47 | 42584135201 | 028 | 2 |  | 1 | 103 | 16193 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 029 | 2 |  | 1 | 101 | 145385.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 035 | 2 |  | 1 | 923 | 91617.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 1 | 107 | 323521.84 | 46701.2 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 2 | 117 | 3803.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 037 | 2 |  | 1 | 107 | 11017.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 039 | 2 |  | 1 | 117 | -1032.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 042 | 2 |  | 1 | 001 | 838070.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 050 | 2 |  | 1 | 003 | 38861.27 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 057 | 2 |  | 1 | 001 | 1274886.31 | 0 | 2 |  | N | 41 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 059 | 2 |  | 1 | 700 | -577152.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | E1Q47 | 42584135201 | 060 | 2 |  | 1 | 001 | 175000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 061 | 2 |  | 1 | 001 | 811721.28 | 0 | 0 |  | N | 56 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 062 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 063 | 2 |  | 1 | 122 | 59392.02 | 40714.72 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1S53 | 43890215201 | 012 | 2 |  | 1 | 107 | 98871.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2V69 | 21327275201 | 006 | 2 |  | 1 | 004 | 17097.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V69 | 21327275201 | 014 | 2 |  | 1 | 001 | 208477.5 | 208477.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 024 | 2 |  | 1 | 503 | 6856.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 033 | 2 |  | 1 | 003 | 5110.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 036 | 2 |  | 1 | 112 | 2121.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 039 | 2 |  | 1 | 112 | 58190.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 041 | 2 |  | 1 | 001 | 32229.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 042 | 2 |  | 1 | 010 | 4365.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V69 | 21327275201 | 050 | 2 |  | 1 | 105 | 28860.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 2 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 3 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 055 | 2 | 850 | 1 | 850 | 75000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2V69 | 21327275201 | 057 | 2 |  | 1 | 503 | 480457.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 057 | 2 |  | 2 | 019 | 7980 | 7980 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 4 | 003 | 10110.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 16 | 860 | 0 | 0 | 0 |  | E | 60 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2Y24 | 43743715201 | 001 | 2 |  | 1 | 305 | -75887.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2Z50 | 42848915201 | 012 | 2 | 850 | 1 | 101 | 49467.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 | 014 | 2 |  | 1 | 101 | -184.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 009 | 2 |  | 1 | 101 | 492951.39 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 013 | 2 |  | 1 | 101 | 30144 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 018 | 2 |  | 1 | 005 | 73830.92 | 73830.92 | 5 |  | N | 23 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 021 | 2 |  | 1 | 919 | 36934.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 1 | 305 | -73244.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 2 | 005 | 60730.52 | 60730.52 | 5 |  | N | 13 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 3 | 024 | 27317 | 27317 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 4 | 001 | 97023.25 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 1 | 107 | 10344.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 2 | 005 | 4660.02 | 4660.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 036 | 2 | 850 | 3 | 107 | 2429.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 4 | 001 | 1009.96 | 1009.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 5 | 115 | 12188.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 6 | 008 | 5733.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 7 | 107 | 29247.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 8 | 010 | 12369.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 036 | 2 | 850 | 9 | 107 | 36401.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 10 | 115 | 3026.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 11 | 503 | 2818 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 12 | 923 | 1157.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 13 | 107 | 26690.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 14 | 015 | 1922.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 1 | 015 | 17510.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 2 | 015 | 1659.82 | 1659.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 3 | 015 | 761.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 4 | 015 | 11041.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 5 | 015 | 1087.23 | 1087.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 6 | 015 | 22572.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 7 | 015 | 15222.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 8 | 015 | 3160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 047 | 2 |  | 1 | 015 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 051 | 2 |  | 1 | 107 | 75248.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 1 | 107 | 23122.83 | 3011.06 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 2 | 107 | 6833.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 3 | 503 | 5485.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 059 | 2 | 850 | 4 | 107 | 814.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 5 | 107 | 20079.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 6 | 001 | 59132.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 7 | 004 | 956.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 8 | 004 | 33575.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 073 | 2 |  | 1 | 015 | 350144.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 1 | 004 | 9699.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 2 | 008 | 14103.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 3 | 010 | 7905 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 082 | 2 | 850 | 4 | 004 | 360.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 5 | 105 | 46101.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 6 | 107 | 28452.39 | 5644.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 8 | 107 | 16582.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 9 | 107 | 7513.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 087 | 2 |  | 1 | 010 | 109704 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 093 | 2 |  | 1 | 024 | 6339.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2700 | 41525015201 | 024 | 2 |  | 1 | 923 | 39169.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2700 | 41525015201 | 028 | 2 |  | 1 | 001 | 7570.83 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 2 | 015 | 10265.52 | 10265.52 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 3 | 012 | 38395.89 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2700 | 41525015201 | 032 | 2 |  | 1 | 004 | 39606.27 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 1 | 122 | 3256.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 2 | 001 | 6443.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 3 | 115 | 70103.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 4 | 015 | 22002.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 5 | 101 | 6750.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2712 | 43240415201 | 020 | 2 |  | 1 | 005 | 12014.29 | 12014.29 | 5 |  | N | 22 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2712 | 43240415201 | 025 | 2 |  | 1 | 503 | 40265.21 | 40265.21 | 0 |  | N | 131 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2712 | 43240415201 | 032 | 2 |  | 1 | 860 | 0 | 0 | 5 |  | N | 59 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | T2753 | 43980015201 | 005 | 2 |  | 1 | 001 | 425405.64 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2770 | 43948915201 | 007 | 2 |  | 1 | 007 | -4773.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T9022 | 44531935223 | 001 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 011 | 2 |  | 1 | 101 | 40091.64 | 6445.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T9022 | 44531935223 | 012 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 013 | 2 | 850 | 1 | 850 | -50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 021 | 2 |  | 1 | 922 | 6861.84 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 028 | 2 |  | 1 | 922 | 11333.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 029 | 2 |  | 1 | 922 | 9658.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 030 | 2 |  | 1 | 922 | 21263.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3S42 | 42187345201 | 012 | 2 |  | 1 | 001 | 0 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 2 | 023 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 3 | 001 | 0 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3699 | 43228415201 | 025 | 2 |  | 1 | 003 | -30186.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3717 | 43720215201 | 007 | 2 |  | 1 | 001 | 27244.97 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3729 | 43972715201 | 020 | 2 |  | 1 | 700 | 204347 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
04 | E4U24 | 43984115201 | 002 | 2 |  | 1 | 007 | -10792.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U24 | 43984115201 | 002 | 2 |  | 2 | 503 | 1766.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 | 002 | 2 |  | 3 | 004 | 8626.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U54 | 44330915201 | 003 | 2 |  | 1 | 105 | 15485.58 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4488 | 43630415201 | 017 | 2 |  | 1 | 860 | 28229.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4488 | 43630415201 | 017 | 2 |  | 2 | 118 | 22219.44 | 22219.44 | 4 |  | N | 0 | Avoidable, In-House CEI | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4494 | 43630715201 | 004 | 2 |  | 1 | 101 | 17582.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4494 | 43630715201 | 012 | 2 |  | 1 | 005 | 7756.24 | 7756.24 | 5 |  | C | 14 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4494 | 43630715201 | 020 | 2 |  | 1 | 001 | 56846.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4494 | 43630715201 | 031 | 2 |  | 1 | 106 | 78304.94 | 78304.94 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 1 | 106 | 8994.35 | 8994.35 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 2 | 105 | 3102.2 | 3102.2 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 3 | 106 | 9557.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 1 | 108 | 33739.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 2 | 007 | 4838.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4497 | 43783615201 | 010 | 2 |  | 3 | 108 | 59290 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 020 | 2 |  | 1 | 923 | 11340.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 027 | 2 |  | 1 | 004 | 143232.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 | 029 | 2 |  | 1 | 126 | 114822 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | T4497 | 43783615201 | 033 | 2 |  | 1 | 101 | -4821.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4497 | 43783615201 | 041 | 2 |  | 1 | 001 | 656775.31 | 656775.31 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 043 | 2 |  | 1 | 001 | 42114.46 | 42114.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 046 | 2 |  | 1 | 001 | 427380.56 | 427380.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 047 | 2 |  | 1 | 001 | 23184.23 | 23184.23 | 0 |  | C | 35 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 052 | 2 |  | 1 | 001 | 190000 | 190000 | 0 |  | C | 16 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 007 | 2 |  | 1 | 101 | 48087.98 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4504 | 43783815201 | 014 | 2 |  | 1 | 113 | 127922.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4504 | 43783815201 | 025 | 2 |  | 1 | 001 | 781896 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 025 | 2 |  | 2 | 503 | -121762.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 009 | 2 |  | 1 | 305 | -99541.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 028 | 2 |  | 1 | 926 | 1686.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 014 | 2 |  | 1 | 923 | 10823.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 029 | 2 |  | 1 | 105 | 82698 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4509 | 43177055201 | 034 | 2 |  | 1 | 113 | 68788 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4511 | 43469015201 | 021 | 2 |  | 1 | 106 | -58454.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4523 | 43469515201 | 009 | 2 |  | 1 | 300 | -28976.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
04 | T4523 | 43469515201 | 022 | 2 |  | 1 | 503 | 62365.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 | 028 | 2 |  | 1 | 503 | 40627.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E50A9 | 44326415201 | 002 | 2 |  | 1 | 012 | 90009.22 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E50A9 | 44326415201 | 002 | 2 |  | 2 | 126 | -59600 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E5Z88 | 43793715201 | 011 | 2 |  | 1 | 926 | 2981.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | T5538 | 23949635201 | 020 | 2 |  | 1 | 105 | 3577.8 | 893.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 | 033 | 2 |  | 1 | 118 | 28062.05 | 5406 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 043 | 2 |  | 1 | 923 | 36110.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 046 | 2 |  | 1 | 007 | 111063.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5538 | 23949635201 | 052 | 2 |  | 1 | 860 | 6449.59 | 6449.59 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
05 | T5538 | 23949635201 | 059 | 2 |  | 1 | 112 | 58725.69 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 083 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 66 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 101 | 2 |  | 1 | 860 | 130760.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 001 | 2 |  | 1 | 919 | 6918.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 037 | 2 |  | 1 | 923 | 1536.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 038 | 2 |  | 1 | 105 | 103979.5 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 2 | 107 | 6025.5 | 0 | 0 |  | N | 143 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 3 | 105 | -202363.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 4 | 503 | -3834 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5582 | 23827585201 | 038 | 2 |  | 5 | 101 | 33771.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 6 | 105 | -1936 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 7 | 503 | 64272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5637 | 43386015201 | 002 | 2 |  | 1 | 107 | 400900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 008 | 2 |  | 1 | 107 | 50537.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 013 | 2 |  | 1 | 107 | 2706273 | 0 | 0 |  | N | 390 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 014 | 2 |  | 1 | 107 | 74935.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 018 | 2 |  | 1 | 923 | 3530.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 052 | 2 |  | 1 | 860 | 17000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5669 | 43923515201 | 019 | 2 |  | 1 | 001 | 19098.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 | 020 | 2 |  | 1 | 118 | 24154.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5669 | 43923515201 | 023 | 2 |  | 1 | 007 | 29083.64 | 19393.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5669 | 43923515201 | 024 | 2 |  | 1 | 007 | 0 | 0 | 0 |  | N | 97 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5676 | 43913915201 | 012 | 2 |  | 1 | 101 | 12029.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 | 025 | 2 |  | 1 | 107 | 10878.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5681 | 43968215201 | 010 | 2 |  | 1 | 105 | 3359.62 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | E6K73 | 43653715201 | 014 | 2 |  | 1 | 012 | 60602.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 008 | 2 |  | 1 | 305 | -501344.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 017 | 2 | 850 | 1 | 503 | 16908.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 1 | 023 | 8091.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 2 | 023 | 1563.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 3 | 021 | 6782.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 4 | 023 | 7570.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 5 | 023 | 1719.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 6 | 023 | 2555.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 7 | 023 | 14691.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 8 | 503 | 60557.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 9 | 503 | 29209.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 10 | 023 | 306.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 025 | 2 |  | 1 | 919 | 519737.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 042 | 2 |  | 1 | 004 | 700013.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 1 | 023 | 16355.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 2 | 023 | 2109.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 3 | 023 | 13547.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 4 | 023 | 15948.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 5 | 012 | 7124.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 6 | 012 | 68465.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 7 | 012 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 8 | 023 | 1759.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 9 | 023 | 918.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 069 | 2 |  | 1 | 012 | 239955.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 1 | 012 | 40892.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 2 | 023 | 55909.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 3 | 023 | 4714.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 4 | 023 | 632.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 5 | 012 | 7710.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 6 | 023 | 3363.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 7 | 001 | 10625.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 8 | 001 | 7441.6 | 7441.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 9 | 012 | 1732.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 1 | 023 | 52390.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 2 | 012 | 4041.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 3 | 503 | 70110.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 083 | 2 |  | 1 | 923 | 41367.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 086 | 2 |  | 1 | 019 | -251871.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6K77 | 42930035201 | 088 | 2 |  | 1 | 001 | 126715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 091 | 2 |  | 1 | 503 | 187228.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 010 | 2 |  | 1 | 503 | 53775.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 025 | 2 |  | 1 | 503 | 52010.04 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M32 | 44204015201 | 009 | 2 |  | 1 | 007 | -3128331.59 | 231933.48 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M32 | 44204015201 | 011 | 2 |  | 1 | 007 | -70000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M47 | 44196115201 | 002 | 2 | 850 | 1 | 850 | 16612 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | E6M47 | 44196115201 | 005 | 2 | 850 | 2 | 503 | 2164.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6465 | 43345535201 | 013 | 2 |  | 1 | 503 | 68789.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M96 | 43762615201 | 004 | 2 |  | 1 | 007 | 8496.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 013 | 2 |  | 1 | 101 | 23017.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7N02 | 44383315201 | 005 | 2 |  | 1 | 004 | 4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N02 | 44383315201 | 006 | 2 |  | 1 | 860 | 45000 | 16551.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | E7R17 | 44368415201 | 003 | 2 |  | 1 | 004 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 | 010 | 2 |  | 1 | 122 | 348683.36 | 0 | 2 |  | N | 37 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7R17 | 44368415201 | 010 | 2 |  | 2 | 118 | 13692.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7R17 | 44368415201 | 022 | 2 |  | 1 | 012 | 16954.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 | 004 | 2 | 850 | 1 | 850 | 43458.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7385 | 25624325201 | 003 | 2 |  | 1 | 101 | 9360 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 003 | 2 |  | 2 | 003 | 78500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 003 | 2 |  | 3 | 101 | 18123.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 1 | 108 | 4652.82 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 2 | 003 | 2648.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 3 | 112 | 105000 | 14595.79 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 4 | 107 | 3985.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 5 | 007 | 4640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 6 | 007 | 6026.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 7 | 107 | 8324.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 8 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 9 | 107 | 11722.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 018 | 2 |  | 1 | 007 | 321706.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 018 | 2 |  | 2 | 101 | 31347.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 024 | 2 |  | 1 | 919 | 18470.4 | 18470.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 1 | 112 | 154658.68 | 48714 | 2 |  | N | 59 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 2 | 112 | 5210.71 | 5210.71 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 3 | 106 | 7226.87 | 7226.87 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 1 | 112 | 50593.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 2 | 107 | 10923.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 3 | 105 | 12628.34 | 750.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 4 | 115 | 3762 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 5 | 115 | 3870.25 | 3870.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 032 | 2 |  | 1 | 503 | 274021.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7385 | 25624325201 | 038 | 2 |  | 1 | 015 | 210084.2 | 17710.37 | 2 |  | N | 16 | Avoidable, In-House Designer | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 047 | 2 |  | 1 | 019 | 57447.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 049 | 2 |  | 1 | 112 | 312932.93 | 223679.73 | 2 |  | N | 15 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 1 | 122 | 3130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 2 | 118 | 35441.79 | 27604.6 | 2 |  | N | 28 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 3 | 113 | 51000 | 51000 | 2 |  | N | 8 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 4 | 019 | 3526.94 | 3526.94 | 5 |  | N | 15 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 5 | 007 | 1200 | 1200 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 6 | 126 | 370.04 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 7 | 113 | 490 | 490 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 8 | 128 | 1121.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 9 | 003 | 3897.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 10 | 015 | 0 | 0 | 5 |  | N | 18 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 11 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7385 | 25624325201 | 054 | 2 |  | 1 | 001 | 20259.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R55 | 42815445201 | 008 | 2 |  | 1 | 923 | 27899.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8R55 | 42815445201 | 025 | 2 |  | 1 | 126 | 415002.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
01 | E1Q47 | 42584145201 |  | 2 | CPI | 1 | 107 | 1369.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 143 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 482.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 1520.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 105 | 14320.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 001 | 1684.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 2 | 105 | 11683.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 101 | 665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2074.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3176.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 2309.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 4239.59 | 4239.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 106 | 1524.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 304.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 868.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 914.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3963.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1829.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2225.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1303.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 6853 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4799.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 007 | 322.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2217.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 769.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 106 | 5995 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | -4239.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 3942.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 5455.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4239.59 | 4239.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 5500 | 933 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 3177.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 012 | 4244.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2350.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 59910.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 001 | 1976.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y85 | 43865025201 |  | 2 | CPI | 1 | 115 | 15314.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 115 | 23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | 38928.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 3 | 115 | -10260.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 4 | 101 | 10592.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | -10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | -23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 012 | 1958 | 1958 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 108 | 1461.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 003 | 8872.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 112 | 5582.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 010 | 31201.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 10007.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 2816.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 019 | 5235.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 001 | 3538.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 4084.57 | 4084.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 16608.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 5600 | 5600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 018 | 3210.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3600 | 3600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 5796.91 | 5796.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3789.18 | 3789.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 107 | 15084.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3502.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 2008.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 9630.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 33101.44 | 33101.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 10609.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 101 | 1954.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 4680.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 8678.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 2169.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 115 | 3809.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 3 | 001 | 1665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 4 | 004 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 101 | 6413 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 115 | 9556.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 120 | 1567.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T9022 | 44531935223 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3T25 | 44154615201 |  | 2 | CPI | 1 | 117 | 3638.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 115 | 7132.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 8460 | 3760 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | 4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | -4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 503 | 4214.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 115 | 15685.46 | 3838.25 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 007 | 672.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 001 | 3787.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 105 | 6430.57 | 2734.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1195.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1278.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1403.59 | 1403.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 502 | 1242.7 | 1242.7 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 004 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 115 | 2724.61 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 007 | 1293.76 | 1293.76 | 5 |  | C | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 926 | 2950.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 503 | 1018.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 119 | 6441.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 503 | 423 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 128 | 5712.85 | 5712.85 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 106 | 3052.67 | 3052.67 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 123 | 12016.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 115 | 1226.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 3 | 108 | 5481.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 001 | 33966.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 105 | 870.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 503 | -932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 935.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 115 | 3357.15 | 3357.15 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 926 | 1714.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 108 | 402.72 | 402.72 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 003 | 3451.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4504 | 43783815201 |  | 2 | CPI | 2 | 108 | 1575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 115 | 2970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 6941.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 38809.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 024 | 8679.73 | 8679.73 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 17185.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 14389.34 | 5447.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 5447.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 112 | 2581.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 1609.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 001 | 2010.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 2 | 118 | 1184 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 118 | 2235.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 123 | 7672.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 118 | 1045 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 926 | 6050.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 1943.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 2094 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 22246.63 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 50538.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 101 | 1045.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | -8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 2 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 001 | 475.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 2 | 001 | 1000.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 106 | 1429.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 4372.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z96 | 44116615201 |  | 2 | CPI | 1 | 010 | 48527.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 3806.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 118 | 3195.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 106 | 1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 1085.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | -2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 106 | -1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 001 | 2481.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 106 | 2004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 107 | 25090.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 10416 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 115 | 4418.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 2133.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 5 | 118 | 3406.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 115 | 1209.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 003 | 8370.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 1659.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 3498.06 | 3498.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | 2486.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 5868.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 115 | 35290.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 105 | 3306.22 | 3306.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 1977.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 1 | 128 | 21312.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 2 | 007 | 1805.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5582 | 23827585201 |  | 2 | CPI | 3 | 007 | 2786.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 003 | 16192.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 3273.6 | 3273.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 373.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 341.18 | 341.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5669 | 43754415201 |  | 2 | CPI | 1 | 001 | 34432.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 1 | 012 | 30199.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 105 | 997.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 3457.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 6173.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 21764.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 4 | 112 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5701 | 44136515201 |  | 2 | CPI | 1 | 115 | 3638.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 17305.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 023 | 12874.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 3325.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 021 | 12038.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6982.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 2292.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 4161.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 3 | 023 | 4219.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 4 | 023 | 6174.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 5 | 023 | 2705.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 6 | 012 | 7465.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 023 | 3820.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 1339.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 1180.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6131.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 8290.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 9725.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 021 | 26375.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 29900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 739.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 503 | 13063.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 1799.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 13098.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 122 | 3916.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | E6M47 | 44196115201 |  | 2 | CPI | 1 | 503 | 14242.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M47 | 44196115201 |  | 2 | CPI | 2 | 503 | 2369.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 105 | 15535.31 | 15535.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 108 | 5682.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 001 | 3956.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 108 | 1496.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 012 | 10378.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1823.55 | 1823.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1458.84 | 1458.84 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 729.42 | 729.42 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 101 | 4114.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 118 | 1399.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 023 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 118 | 1399.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 022 | 9277.38 | 9277.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 2 | 115 | 2240.54 | 2240.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6478 | 44030415201 |  | 2 | CPI | 1 | 503 | 5010.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6478 | 44030415201 |  | 2 | CPI | 2 | 101 | 794.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | -9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | -3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 2122.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 007 | 3015.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 1040.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 12000 | 12000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1163.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 004 | 3990.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M96 | 43762615201 |  | 2 | CPI | 2 | 101 | 749.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1034 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 2027.92 | 2027.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7N02 | 44383315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N46 | 43955415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N48 | 44025215201 |  | 2 | CPI | 1 | 112 | 7325.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 4000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 2 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 1800 | 1800 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 115 | 2708.52 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 6578.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 2838.79 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 115 | 1794.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 4 | 107 | 5814.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 48842.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 105 | 4182.62 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 5244.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 45443.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 108 | 5480.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 877.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 8720.37 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 11473.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325601 |  | 2 | CPI | 1 | 015 | 3027.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 40430.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 926 | 5753.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 17935.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 869.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 974.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 2 | 115 | 6771.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 1879.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 019 |  | 51 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | [9 empty] | Unavoidable, No Remedial Action Required
05 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, In-House Designer
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
01 | T1764 | 44013015201 | 924 |  | 20 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2Y85 | 43865025201 | 924 |  | 16 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2Y85 | 43865025201 | 924 |  | 16 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2700 | 41525015201 | 924 |  | 34 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 009 |  | 7 | 012 | 1 | 1 | C | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 87 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 13 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 924 |  | 65 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 013 |  | 62 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 016 |  | 72 | 041 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3S42 | 42187345201 | 924 |  | 128 | 003 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3T25 | 44154615201 | 503 |  | 3 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3699 | 43228415201 | 018 |  | 15 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
03 | T3699 | 43228415201 | 106 |  | 21 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3729 | 43972715201 | 023 |  | 2 | 021 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3729 | 43972715201 | 012 |  | 2 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3744 | 43972415201 | 924 |  | 50 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4488 | 43630415201 | 924 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4505 | 43668515201 | 924 |  | 22 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 | 503 |  | 6 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 019 |  | 37 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 924 |  | 16 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 503 |  | 25 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 | 503 |  | 25 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M96 | 43762615201 | 007 |  | 21 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 118 |  | 27 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 1 | 01co | 1 | 1
01DO | 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 357 | 69031 | 29 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO | 6 | 01do | 2 | 7
01DO | 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | -23194 | 2868754 | 166 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 60 | 0 | 0 | 0 | 0 |  | DO | 10 | 02co | 8 | 17
01DO | 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 98871 | 44 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO | 7 | 02do | 18 | 24
01DO | 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO | 5 | 03co | 25 | 29
01DO | 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 13 | 0 | 0 | 0 | 0 |  | DO | 5 | 03do | 30 | 34
01DO | 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 10 | 04co | 35 | 44
02CO | 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 593970 | 1812123 | 319 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1 |  |  | 4 | 136 | 0 | 0 | -73244 | 0 |  | CO | 2 | 04do | 45 | 46
02CO | 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | -48704 | 243564 | 155 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO | 7 | 05co | 47 | 53
02CO | 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | -1358 | 52280 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1 |  |  | 0 | 56 | 0 | 0 | 0 | 0 | T | CO | 6 | 05do | 54 | 59
02CO | 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 475406 | 27 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO | 4 | 06co | 60 | 63
02CO | 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 0 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42 |  |  | 3 | 38 | 0 | 0 | 0 | 0 |  | CO | 5 | 06do | 64 | 68
02CO | 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 0 | -4773 | 3 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 1 | 07co | 69 | 69
02CO | 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 8 | 07do | 70 | 77
02CO | 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 78 | 77
02CO | 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 2 | 08do | 78 | 79
02CO | 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 90092 | 12 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66 |  |  | 11 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | -1354420 | 997337 | 55 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 118 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | -75888 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32 |  |  | 0 | 15 | 0 | 0 | -75888 | 0 |  | DO |  | 0
02DO | 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 49816 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | -30187 | 126 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 247 | 27245 | 34 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 204347 | 63 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 0 | 49116 | 256 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 90 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 0 | 213 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | -174645 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | -225968 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-10-20 | QTR2 | 20/21 | 314 | 246220 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | -79 | 50449 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 238143 | 56 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | -38478 | 1701896 | 99 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 836144 | 110 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | -58724 | -97855 | 61 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17 |  |  | 6 | 33 | 0 | 0 | -99541 | 0 |  | CO
04CO | 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | -17714 | 162310 | 92 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | -58454 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 74017 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95 |  |  | 10 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 237 | 0 | 25 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | -399 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 15486 | 15 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 430838 | 374749 | 219 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3 |  |  | 30 | 102 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 328547 | 8369 | 210 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | -16169 | 3253176 | 23 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320 |  |  | 20 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 72336 | 18 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 22908 | 74 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 3360 | 113 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 30409 | 84 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 507 | 309304 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 0 | 0 | 7 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03 |  |  | 12 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | -5035 | 2982 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55 |  |  | 0 | 138 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 68789 | 27 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 39 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 0 | 36 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 110603 | 110 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | -991000 | 1610952 | 139 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 172 | 0 | 0 | -501344 | 0 |  | DO
06DO | 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 105786 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | -3198332 | 6 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 0 | 33224 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 248412 | 1919528 | 100 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 31514 | 24 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 0 | 49500 | 4 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 796 | 485498 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 796 | 127700 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 386330 | 30 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 16 | 49 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 43458 | 9 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR | 14 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | -1807 | 442902 | 15 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51 |  |  | 10 | 45 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08 |  |  | 2 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0