## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 24409698 | 24034944 | 24483385 | 24291046 | 0 | 24193142 | 0.6582% | 100% | 148410 | 0.6175% | 73687 | 0.3019% | 1310 | 370 | 28.24% | 117 | 8.931% | 71 | 5.42% | 33 | 2.519% | 1414 | 7.939% | 1901 | 1865 | 1378 | 5.191% | 100%
| District Let | 57050723 | 56597816 | 60502176 | 59809329 | 0 | 59623804 | 5.346% | 100% | 3397419 | 6.003% | 3451452 | 6.05% | 2026 | 489 | 24.14% | 161 | 7.947% | 51 | 2.517% | 147 | 7.256% | 2224 | 9.773% | 2919 | 2891 | 2241 | 10.61% | 75%
| All Contracts | 81460421 | 80632760 | 84985561 | 84100375 | 0 | 83816946 | 3.949% | 100% | 3545829 | 4.398% | 3525139 | 4.327% | 3336 | 859 | 25.75% | 278 | 8.333% | 122 | 3.657% | 180 | 5.396% | 3638 | 9.053% | 4820 | 4756 | 3619 | 8.483% | 86.67%
2 | Central Let | 203481962 | 202535452 | 211816833 | 215035529 | 0 | 216620445 | 6.954% | 93.75% | 8077155 | 3.988% | 8334871 | 4.096% | 6074 | 1125 | 18.52% | 749 | 12.33% | 4 | 0.06585% | 922 | 15.18% | 7000 | 15.25% | 8997 | 8690 | 6816 | 12.22% | 75%
| District Let | 34228831 | 33561373 | 36906018 | 36870297 | 1350000 | 36860044 | 9.829% | 76.92% | 2898745 | 8.637% | 2677189 | 7.821% | 3307 | 454 | 13.73% | 433 | 13.09% | 125 | 3.78% | 281 | 8.497% | 3713 | 12.28% | 4599 | 4098 | 3211 | -2.903% | 76.92%
| All Contracts | 237710793 | 236096825 | 248722851 | 251905826 | 1350000 | 253480489 | 7.363% | 86.21% | 10975900 | 4.649% | 11012060 | 4.633% | 9381 | 1579 | 16.83% | 1182 | 12.6% | 129 | 1.375% | 1203 | 12.82% | 10713 | 14.2% | 13596 | 12788 | 10027 | 6.886% | 75.86%
3 | Central Let | 54263171 | 53582365 | 55202401 | 55026461 | 0 | 54701784 | 2.089% | 100% | 955478 | 1.783% | 939230 | 1.731% | 3045 | 1163 | 38.19% | 429 | 14.09% | 54 | 1.773% | 52 | 1.708% | 3151 | 3.481% | 4743 | 4654 | 3062 | 0.5583% | 100%
| District Let | 13177302 | 12905124 | 13916813 | 13719860 | 25000 | 11507508 | -10.83% | 100% | 698640 | 5.414% | 739512 | 5.612% | 1340 | 590 | 44.03% | 215 | 16.04% | 379 | 28.28% | 150 | 11.19% | 1869 | 39.48% | 2686 | 2673 | 1868 | 39.4% | 55.56%
| All Contracts | 67440473 | 66487489 | 69119214 | 68746321 | 25000 | 66209292 | -0.4184% | 100% | 1654118 | 2.488% | 1678742 | 2.489% | 4385 | 1753 | 39.98% | 644 | 14.69% | 433 | 9.875% | 202 | 4.607% | 5020 | 14.48% | 7429 | 7327 | 4930 | 12.43% | 82.61%
4 | Central Let | 55332327 | 54625508 | 58624253 | 57490073 | 0 | 56927558 | 4.214% | 92.86% | 3541273 | 6.483% | 3291925 | 5.949% | 4710 | 954 | 20.25% | 378 | 8.025% | 24 | 0.5096% | 245 | 5.202% | 4979 | 5.711% | 6426 | 6128 | 4796 | 1.826% | 92.86%
| District Let | 2392134 | 2292134 | 2407221 | 2172532 | 100000 | 2177173 | -5.015% | 100% | 49311 | 2.151% | 15087 | 0.6307% | 373 | 37 | 9.92% | 27 | 7.239% | 0 | 0% | 14 | 3.753% | 387 | 3.753% | 451 | 451 | 387 | 3.753% | 100%
| All Contracts | 57724461 | 56917642 | 61031474 | 59662605 | 100000 | 59104731 | 3.843% | 93.75% | 3590584 | 6.308% | 3307012 | 5.729% | 5083 | 991 | 19.5% | 405 | 7.968% | 24 | 0.4722% | 259 | 5.095% | 5366 | 5.568% | 6877 | 6579 | 5183 | 1.967% | 93.75%
5 | Central Let | 87443443 | 86520610 | 91264224 | 92440314 | 0 | 92633485 | 7.065% | 90% | 4205221 | 4.86% | 3820781 | 4.369% | 3379 | 906 | 26.81% | 495 | 14.65% | 0 | 0% | 925 | 27.37% | 4304 | 27.37% | 5771 | 5666 | 4265 | 26.22% | 60%
| District Let | 17947357 | 17564375 | 18093626 | 18129002 | 0 | 18099411 | 3.046% | 100% | 300722 | 1.712% | 146269 | 0.815% | 1600 | 315 | 19.69% | 266 | 16.62% | 0 | 0% | 70 | 4.375% | 1670 | 4.375% | 2256 | 2167 | 1586 | -0.875% | 100%
| All Contracts | 105390800 | 104084985 | 109357850 | 110569316 | 0 | 110732896 | 6.387% | 95% | 4505943 | 4.329% | 3967050 | 3.764% | 4979 | 1221 | 24.52% | 761 | 15.28% | 0 | 0% | 995 | 19.98% | 5974 | 19.98% | 8027 | 7833 | 5851 | 17.51% | 80%
6 | Central Let | 13877647 | 13555656 | 13967053 | 13138569 | 300000 | 13128303 | -3.153% | 100% | 180780 | 1.334% | 89406 | 0.6442% | 1840 | 346 | 18.8% | 184 | 10% | 33 | 1.793% | 0 | 0% | 1873 | 1.793% | 2403 | 2235 | 1705 | -7.337% | 100%
| District Let | 117880580 | 117304507 | 117657809 | 120357215 | 1320000 | 116291588 | -0.8635% | 87.5% | -697453 | -0.5946% | -222770 | -0.189% | 3640 | 457 | 12.55% | 328 | 9.011% | 68 | 1.868% | 29 | 0.7967% | 3737 | 2.665% | 4538 | 3945 | 3160 | -13.19% | 100%
| All Contracts | 131758227 | 130860163 | 131624862 | 133495784 | 1620000 | 129419891 | -1.101% | 93.75% | -516673 | -0.3948% | -133364 | -0.1012% | 5480 | 803 | 14.65% | 512 | 9.343% | 101 | 1.843% | 29 | 0.5292% | 5610 | 2.372% | 6941 | 6180 | 4865 | -11.22% | 100%
7 | Central Let | 19241675 | 18960575 | 21161203 | 21189964 | 0 | 21404223 | 12.89% | 66.67% | 1991432 | 10.5% | 1919528 | 9.976% | 1001 | 171 | 17.08% | 92 | 9.191% | 0 | 0% | 161 | 16.08% | 1162 | 16.08% | 1425 | 1422 | 1159 | 15.78% | 66.67%
| District Let | 18334271 | 17950035 | 18845074 | 18486122 | 0 | 18354067 | 2.251% | 100% | 581097 | 3.237% | 510802 | 2.786% | 1703 | 207 | 12.16% | 211 | 12.39% | 48 | 2.819% | 64 | 3.758% | 1815 | 6.577% | 2233 | 2058 | 1640 | -3.699% | 90%
| All Contracts | 37575946 | 36910610 | 40006277 | 39676086 | 0 | 39758290 | 7.715% | 92.31% | 2572529 | 6.97% | 2430330 | 6.468% | 2704 | 378 | 13.98% | 303 | 11.21% | 48 | 1.775% | 225 | 8.321% | 2977 | 10.1% | 3658 | 3480 | 2799 | 3.513% | 84.62%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 305723548 | 304758244 | 311083902 | 310101293 | 1200000 | 311364674 | 2.168% | 100% | 4831903 | 1.585% | 5360351 | 1.753% | 5511 | 573 | 10.4% | 438 | 7.948% | 10 | 0.1815% | 1051 | 19.07% | 6572 | 19.25% | 7583 | 7100 | 6089 | 10.49% | #VALUE!
| All Contracts | 305723548 | 304758244 | 311083902 | 310101293 | 1200000 | 311364674 | 2.168% | 100% | 4831903 | 1.585% | 5360351 | 1.753% | 5511 | 573 | 10.4% | 438 | 7.948% | 10 | 0.1815% | 1051 | 19.07% | 6572 | 19.25% | 7583 | 7100 | 6089 | 10.49% | 90%
Totals This Qtr | Central Let | 458049923 | 453815110 | 476519352 | 478611956 | 300000 | 479608940 | 5.684% | 94.44% | 19099749 | 4.209% | 18469428 | 4.032% | 21359 | 5035 | 23.57% | 2444 | 11.44% | 186 | 0.8708% | 2338 | 10.95% | 23883 | 11.82% | 31666 | 30660 | 23181 | 8.53% | 86.11%
| District Let | 566734746 | 562933608 | 579412639 | 579645650 | 3995000 | 574278269 | 2.015% | 94.29% | 12060384 | 2.142% | 12677892 | 2.237% | 19500 | 3122 | 16.01% | 2079 | 10.66% | 681 | 3.492% | 1806 | 9.262% | 21987 | 12.75% | 27265 | 25383 | 20182 | 3.497% | 84.29%
| All Contracts | 1024784669 | 1016748718 | 1055931991 | 1058257606 | 4295000 | 1053887209 | 3.653% | 94.37% | 31160133 | 3.065% | 31147320 | 3.039% | 40859 | 8157 | 19.96% | 4523 | 11.07% | 867 | 2.122% | 4144 | 10.14% | 45870 | 12.26% | 58931 | 56043 | 43363 | 6.128% | 85.21%
Totals Previous Quarter | Central Let | 206929806 | 204865553 | 218429768 | 220248830 | 170000 | 220893794 | 7.824% | 94.74% | 12145795 | 5.929% | 11499962 | 5.557% | 11192 | 2589 | 23.13% | 1255 | 11.21% | 65 | 0.5808% | 1611 | 14.39% | 12868 | 14.97% | 16901 | 16261 | 12417 | 10.95% | 84.21%
| District Let | 222596286 | 220518040 | 226410545 | 221977238 | 2795000 | 216796218 | -1.688% | 100% | 3588553 | 1.627% | 3814258 | 1.714% | 10888 | 1729 | 15.88% | 1213 | 11.14% | 417 | 3.83% | 435 | 3.995% | 11740 | 7.825% | 14755 | 13429 | 10487 | -3.683% | 88.1%
| All Contracts | 429526092 | 425383593 | 444840313 | 442226068 | 2965000 | 437690012 | 2.893% | 97.5% | 15734348 | 3.699% | 15314220 | 3.565% | 22080 | 4318 | 19.56% | 2468 | 11.18% | 482 | 2.183% | 2046 | 9.266% | 24608 | 11.45% | 31656 | 29690 | 22904 | 3.732% | 86.25%
Totals Fiscal Year 2021/2022 | Central Let | 664979729 | 658680663 | 694949120 | 698860786 | 470000 | 700502734 | 6.349% |  | 31245187 | 4.744% | 29969390 | 4.288% | 32551 | 7624 | 23.42% | 3699 | 11.36% | 251 | 0.7711% | 3949 | 12.13% | 36751 | 12.9% | 48567 | 46921 | 35598 | 9.361%
| District Let | 787460032 | 781630648 | 803952184 | 799735177 | 6790000 | 789108648 | 0.9567% |  | 15587915 | 1.994% | 16492150 | 2.062% | 30148 | 4800 | 15.92% | 3286 | 10.9% | 1098 | 3.642% | 2241 | 7.433% | 33487 | 11.08% | 41723 | 38526 | 30440 | 0.9686%
| All Contracts | 1452439761 | 1440311311 | 1498901304 | 1498595963 | 7260000 | 1489611382 | 3.423% |  | 46833102 | 3.252% | 46461540 | 3.1% | 62699 | 12424 | 19.82% | 6985 | 11.14% | 1349 | 2.152% | 6190 | 9.873% | 70238 | 12.02% | 90290 | 85447 | 66038 | 5.325%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 116.7% | 1 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 100.3% | 1 | 12243 | -8147 | 134 | 24 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88
| 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 84.71% | 1 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 96.23% | 1 | 0 | 8128 | 11 | 6 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21
| 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | 104.2% | 1 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | 100.2% | 1 | -35379 | -23800 | 78 | 28 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38003 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59
| 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 116.5% | 1 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 102.6% | 1 | 6923 | -17395 | 44 | 26 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 |  | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21
| 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 97.74% | 1 | 0 | 0 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82
| 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 264 | 97.5% | 1 | 37 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | 106.8% | 1 | -1156 | 114901 | 43 | 26 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43
| 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 92.86% | 1 | 2188 | 0 | 27 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 |  | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 7 | 9 | 12 | 1310 | 1901 | 1865 | 100% | 7 | 36 | 17 | 0 | 558 | 33 | 24409698 | 374754 | 24034944 | 24483385 | 24291046 | -82722 | 0 | -82722 | 24208324 | 24193142 | 100% | 7 | -15181 | 73687 | 370 | 117 | 0 | 1 | 355601 | 20602 | 1 | 32 | 52876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | -233898 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38003 | 0 | 71 | 33 | 148410 | 20602
| 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 141.3% | 0 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 103.5% | 1 | 357 | 69031 | 29 | 20 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85
| 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 127.9% | 0 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | 106.1% | 1 | -23194 | 2868754 | 166 | 60 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 |  | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 102.9% | 1 | 0 | 234222 | 11 | 6 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 |  | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33
| 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 97.5% | 1 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | 106.3% | 1 | -52866 | 180574 | 207 | 28 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 |  | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53
| 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 92% | 1 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 104.8% | 1 | 596 | 98871 | 44 | 17 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 |  | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2
| 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | 97.68% | 1 | -5733 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85
| 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 100% | 1 | 520 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 31 | 2026 | 2919 | 2891 | 75% | 6 | 28 | 0 | 0 | 701 | 192 | 57050723 | 452907 | 56597816 | 60502176 | 59809329 | 0 | 0 | 0 | 59809329 | 59623804 | 100% | 8 | -80320 | 3451452 | 489 | 161 | 51 | 106 | 3510223 | 33290 | 0 | 41 | 420637 | 129070 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182474 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 147 | 3397419 | 162360
| District 01 Totals |  |  |  |  | 15 | 22 | 43 | 3336 | 4820 | 4756 | 86.67% | 13 | 64 | 17 | 0 | 1259 | 225 | 81460421 | 827661 | 80632760 | 84985561 | 84100375 | -82722 | 0 | -82722 | 84017653 | 83816946 | 100% | 15 | -95501 | 3525139 | 859 | 278 | 51 | 107 | 3865824 | 53892 | 1 | 73 | 473513 | 129070 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | -51424 | 0 | 0 | 0 | -565317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38003 | 0 | 122 | 180 | 3545829 | 182962
| 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 106.7% | 1 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 108.4% | 1 | 593970 | 1812123 | 319 | 136 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1
| 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 122.1% | 0 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 109.7% | 1 | 337124 | 3379021 | 270 | 196 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71
| 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 120.9% | 0 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 107.3% | 1 | 1278355 | 2076018 | 139 | 86 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7
| 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 109.6% | 1 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | 103% | 1 | -48704 | 243564 | 155 | 52 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69
| 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | 215.7% | 0 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | 102.4% | 1 | -1358 | 52280 | 46 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1
| 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 77% | 1 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | 115.8% | 0 | -19174 | 475406 | 27 | 28 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1
| 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 100% | 1 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | 98.37% | 1 | -34064 | 0 | 32 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44
| 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | 132.5% | 0 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6267785 | 97.37% | 1 | 119272 | 124056 | 35 | 20 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49
| 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 119.6% | 1 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 87.38% | 1 | 0 | 87084 | 10 | 20 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705
| 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 62.5% | 1 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 99.16% | 1 | 752 | 0 | 38 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42
| 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 60.56% | 1 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 97.14% | 1 | 0 | -4773 | 3 | 23 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49
| 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 98.67% | 1 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 99.41% | 1 | 338 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88
| 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 84% | 1 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 104% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46
| 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 65% | 1 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 99.22% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86
| 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 72.4% | 1 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | 99.39% | 1 | -59022 | 0 | 28 | 20 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016
| 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 104.4% | 1 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 105.2% | 1 | 0 | 90092 | 12 | 17 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 16 | 24 | 63 | 6074 | 8997 | 8690 | 75% | 12 | 307 | 50 | 0 | 1988 | 935 | 203481962 | 946510 | 202535452 | 211816833 | 215035529 | -175272 | 0 | -175272 | 214860257 | 216620445 | 93.75% | 15 | 2167489 | 8334871 | 1125 | 749 | 4 | 543 | 5137285 | 109163 | 0 | 70 | 1952810 | 155965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 78881 | 40265 | 0 | 0 | 47286 | 27317 | 0 | 0 | 0 | 0 | 0 | 29 | 408109 | 0 | 0 | 59 | 0 | 0 | 0 | 90 | 526026 | 526026 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 4 | 922 | 8077155 | 858737
| 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 68% | 1 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 94.97% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08
| 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 150.4% | 0 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 132.8% | 0 | 0 | 177395 | 58 | 34 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36
| 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 108% | 1 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | 108.1% | 1 | -1354420 | 997337 | 55 | 118 | 0 | 0 | 307141 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1068650 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 |  | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 145.7% | 0 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 215.1% | 0 | 0 | 1396122 | 103 | 32 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42
| 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 84% | 1 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 87.7% | 1 | 0 | -75888 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32
| 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 106.4% | 1 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | 107.7% | 1 | -94 | 50000 | 30 | 77 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21
| 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 99.33% | 1 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | 98.28% | 1 | -1374 | 0 | 63 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78
| 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 98.33% | 1 | 0 | 0 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99
| 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 222.2% | 0 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 129.5% | 0 | 0 | 82407 | 16 | 20 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27
| 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 30.23% | 1 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 99.9% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7
| 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 62.58% | 1 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 105.3% | 1 | 0 | 49816 | 24 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 109543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109543 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86
| 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 109.5% | 1 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 103.7% | 1 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03
| 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 99.07% | 1 | 0 | 0 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 13 | 16 | 22 | 3307 | 4599 | 4098 | 76.92% | 10 | 501 | 0 | 0 | 1012 | 280 | 34228831 | 667459 | 33561373 | 36906018 | 36870297 | 0 | 1350000 | 1350000 | 38220297 | 36860044 | 76.92% | 10 | -1355888 | 2677189 | 454 | 433 | 21 | 118 | 421648 | 216458 | 104 | 64 | 614751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492143 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29056 | 0 | 0 | 78 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | -75888 | 0 | 125 | 281 | 2898745 | 216458
| District 02 Totals |  |  |  |  | 29 | 40 | 85 | 9381 | 13596 | 12788 | 75.86% | 22 | 808 | 50 | 0 | 3000 | 1215 | 237710793 | 1613969 | 236096825 | 248722851 | 251905826 | -175272 | 1350000 | 1174728 | 253080554 | 253480489 | 86.21% | 25 | 811601 | 11012060 | 1579 | 1182 | 25 | 661 | 5558933 | 325621 | 104 | 134 | 2567561 | 155965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 571024 | 40265 | 0 | 0 | 64198 | 27317 | 0 | 0 | 0 | 0 | 0 | 29 | 437165 | 0 | 0 | 137 | 1400122 | 0 | 0 | 90 | 526026 | 526026 | 0 | 21 | 0 | 0 | 0 | 0 | -149132 | 0 | 129 | 1203 | 10975900 | 1075195
| 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 99.27% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 |  | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM
| 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 99.53% | 1 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 97.72% | 1 | 28314 | 256400 | 170 | 73 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000
| 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 66.67% | 1 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 101.2% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 |  | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91
| 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 100.7% | 1 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | 104.7% | 1 | -86540 | 385593 | 320 | 100 | 0 | 3 | 71605 | 0 | 0 | 4 | 120094 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429239 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93
| 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 115.3% | 1 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | 98.95% | 1 | -2489 | -30187 | 126 | 44 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8
| 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 97.22% | 1 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 91.84% | 1 | 466 | 0 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24
| 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 101.3% | 1 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 104.2% | 1 | 247 | 27245 | 34 | 16 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46
| 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | 101.3% | 1 | -146878 | 58629 | 112 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83
| 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 102.7% | 1 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | 108.4% | 1 | -50153 | 204347 | 63 | 25 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85
| 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 107.8% | 1 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 101.2% | 1 | 1050 | 37203 | 43 | 34 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86
| 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | 101.9% | 1 | -53128 | 0 | 168 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9
| 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 88% | 1 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 108.1% | 1 | 76040 | 0 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13
| 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 90 | 174 | 176 | 110% | 1 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 755462 | 668670 | 0 | 0 | 0 | 668670 | 668670 | 93.29% | 1 | 0 | 0 | 39 | 38 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5200 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-12 | QTR2 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61
| 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 88% | 1 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 102.2% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 |  | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 14 | 23 | 31 | 3045 | 4743 | 4654 | 100% | 14 | 89 | 2 | 0 | 1646 | 52 | 54263171 | 680809 | 53582365 | 55202401 | 55026461 | -24500 | 0 | -24500 | 55001961 | 54701784 | 100% | 14 | -233071 | 939230 | 1163 | 429 | 17 | 15 | 110967 | 0 | 35 | 29 | 334286 | 90285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 218998 | 0 | 2 | 1 | 206446 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 84780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 52 | 955478 | 90285
| 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | 208.7% | 0 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 91.39% | 1 | 0 | 49116 | 256 | 90 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 159.3% | 0 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 100% | 1 | 0 | 0 | 213 | 23 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 |  | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049
| 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 52.67% | 1 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | 0% | 1 | -174645 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33
| 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 101.7% | 1 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | 105.3% | 1 | -2525 | 0 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39
| 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 51.67% | 1 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 99.94% | 1 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79
| 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 114.4% | 1 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | 101.6% | 1 | -25000 | 92806 | 26 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 253.3% | 0 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 104.6% | 1 | 0 | 14821 | 35 | 42 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 |  | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45
| 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 85.56% | 1 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | 0% | 1 | -225968 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-10-20 | QTR2 | 20/21 | 314 | 246220
| 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 148.9% | 0 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | 0% | 1 | -1338192 | 582769 | 17 | 11 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 9 | 15 | 13 | 1340 | 2686 | 2673 | 55.56% | 5 | 13 | 160 | 0 | 1184 | 162 | 13177302 | 272178 | 12905124 | 13916813 | 13719860 | -449760 | 25000 | -424760 | 13295100 | 11507508 | 100% | 9 | -1766330 | 739512 | 590 | 215 | 365 | 71 | 0 | 0 | 5 | 0 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 107627 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 150 | 698640 | 0
| District 03 Totals |  |  |  |  | 23 | 38 | 44 | 4385 | 7429 | 7327 | 82.61% | 19 | 102 | 162 | 0 | 2830 | 214 | 67440473 | 952987 | 66487489 | 69119214 | 68746321 | -474260 | 25000 | -449260 | 68297061 | 66209292 | 100% | 23 | -1999401 | 1678742 | 1753 | 644 | 382 | 86 | 110967 | 0 | 40 | 29 | 342530 | 90285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22 | 326625 | 0 | 2 | 19 | 206446 | 0 | 0 | 0 | 0 | 0 | 6 | 46 | 667549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 202 | 1654118 | 90285
| 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 154.1% | 0 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | 104.3% | 1 | -5522 | 345672 | 158 | 48 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 0 | 0 | -46629 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32
| 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | 110% | 1 | -79 | 50449 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52
| 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 103.4% | 1 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | 103.1% | 1 | -41100 | 238143 | 56 | 38 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83
| 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 120% | 1 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | 121.4% | 0 | -38478 | 1701896 | 99 | 57 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34
| 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 104.1% | 1 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | 108.7% | 1 | -136647 | 836144 | 110 | 44 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29
| 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 101.4% | 1 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | 96.13% | 1 | -58724 | -97855 | 61 | 33 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17
| 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 99.49% | 1 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | 104.1% | 1 | -17714 | 162310 | 92 | 33 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17
| 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 72.21% | 1 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | 92.16% | 1 | -17236 | -58454 | 82 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 |  | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2
| 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 102.5% | 1 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | 97.23% | 1 | -108218 | 74017 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95
| 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 90.84% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3
| 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 96.65% | 1 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | 100.6% | 1 | -30966 | 39603 | 54 | 27 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03
| 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 103.5% | 1 | 250 | 0 | 81 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89
| 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66.83% | 1 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 98.35% | 1 | 237 | 0 | 25 | 18 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94
| 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 75.77% | 1 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 96.14% | 1 | 93 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTIONLLC | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 14 | 25 | 48 | 4710 | 6426 | 6128 | 92.86% | 13 | 298 | 0 | 0 | 1356 | 360 | 55332327 | 706819 | 54625508 | 58624253 | 57490073 | -68940 | 0 | -68940 | 57421133 | 56927558 | 92.86% | 13 | -454104 | 3291925 | 954 | 378 | 0 | 117 | 2497520 | 1339455 | 6 | 56 | 843904 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 114714 | 0 | 0 | 6 | 86505 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 76532 | 48303 | 18 | 56 | 88757 | 82668 | 0 | 0 | 0 | 0 | 0 | 0 | -146170 | 0 | 24 | 245 | 3541273 | 1608687
| 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 100.7% | 1 | 95 | -399 | 22 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08
| 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 110.9% | 1 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | 88.88% | 1 | -95454 | 15486 | 15 | 5 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 |  | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 2 | 4 | 2 | 373 | 451 | 451 | 100% | 2 | 0 | 0 | 0 | 64 | 14 | 2392134 | 100000 | 2292134 | 2407221 | 2172532 | 0 | 100000 | 100000 | 2272532 | 2177173 | 100% | 2 | -95359 | 15087 | 37 | 27 | 0 | 0 | 5727 | 0 | 0 | 14 | 37601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 49311 | 0
| District 04 Totals |  |  |  |  | 16 | 29 | 50 | 5083 | 6877 | 6579 | 93.75% | 15 | 298 | 0 | 0 | 1420 | 374 | 57724461 | 806819 | 56917642 | 61031474 | 59662605 | -68940 | 100000 | 31060 | 59693665 | 59104731 | 93.75% | 15 | -549463 | 3307012 | 991 | 405 | 0 | 117 | 2503247 | 1339455 | 6 | 70 | 881505 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 120695 | 0 | 0 | 6 | 86505 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 76532 | 48303 | 18 | 56 | 88757 | 82668 | 0 | 0 | 0 | 0 | 0 | 0 | -146170 | 0 | 24 | 259 | 3590584 | 1608687
| 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 113.9% | 1 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 105.7% | 1 | 430838 | 374749 | 219 | 102 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3
| 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 137.8% | 0 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 104% | 1 | 328547 | 8369 | 210 | 62 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22
| 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 96.77% | 1 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | 103% | 1 | -222563 | -4 | 112 | 57 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38
| 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 347.9% | 0 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | 219.7% | 0 | -16169 | 3253176 | 23 | 51 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320
| 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 134.8% | 0 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | 101.4% | 1 | -48503 | 72336 | 18 | 22 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68
| 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 150% | 0 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | 105.3% | 1 | -28879 | 22908 | 74 | 22 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 |  | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09
| 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 106.8% | 1 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | 96.78% | 1 | -191521 | 85887 | 113 | 94 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87
| 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 89.33% | 1 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | 97.46% | 1 | -39533 | 3360 | 113 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7
| 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 86.92% | 1 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 99.25% | 1 | 35505 | 0 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04
| 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 99.23% | 1 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 100.2% | 1 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 10 | 21 | 29 | 3379 | 5771 | 5666 | 60% | 6 | 105 | 0 | 0 | 1401 | 991 | 87443443 | 922833 | 86520610 | 91264224 | 92440314 | -7304 | 0 | -7304 | 92433010 | 92633485 | 90% | 9 | 248571 | 3820781 | 906 | 495 | 0 | 124 | 382613 | 19394 | 0 | 785 | 3545024 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 16 | 50479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925 | 4205221 | 32143
| 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 107.2% | 1 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 102.7% | 1 | 0 | 30409 | 84 | 17 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5
| 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 101.1% | 1 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 102.8% | 1 | 0 | 0 | 13 | 6 | 0 | 0 | 7876 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7
| 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 81.25% | 1 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 92.06% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 507 | 309304
| 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 117.1% | 1 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 102.1% | 1 | 0 | 0 | 7 | 5 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03
| 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 31% | 1 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 98.44% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5
| 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 106.7% | 1 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 103.1% | 1 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7
| 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | 110% | 1 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | 101.7% | 1 | -20779 | 70000 | 38 | 56 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19
| 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 99.5% | 1 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | 99.98% | 1 | -5035 | 2982 | 41 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55
| 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 106.5% | 1 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 107.6% | 1 | 0 | 42878 | 52 | 20 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS
| 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | 105.3% | 1 | -795 | 0 | 72 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 10 | 11 | 6 | 1600 | 2256 | 2167 | 100% | 10 | 89 | 1 | 0 | 581 | 75 | 17947357 | 382982 | 17564375 | 18093626 | 18129002 | 0 | 0 | 0 | 18129002 | 18099411 | 100% | 10 | -26609 | 146269 | 315 | 266 | 0 | 41 | 205097 | 0 | 0 | 29 | 46733 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 300722 | 58655
| District 05 Totals |  |  |  |  | 20 | 32 | 35 | 4979 | 8027 | 7833 | 80% | 16 | 194 | 1 | 0 | 1982 | 1066 | 105390800 | 1305815 | 104084985 | 109357850 | 110569316 | -7304 | 0 | -7304 | 110562012 | 110732896 | 95% | 19 | 221962 | 3967050 | 1221 | 761 | 0 | 165 | 587710 | 19394 | 0 | 814 | 3591757 | 64954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 16 | 50843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60988 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 4505943 | 90798
| 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 78.39% | 1 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | 101.8% | 1 | -195345 | 68789 | 27 | 20 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 99.5% | 1 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | 98.87% | 1 | -98 | 0 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85
| 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 86.86% | 1 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | 98.61% | 1 | -113588 | 38150 | 11 | 23 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 85.71% | 1 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 93.34% | 1 | 39 | 0 | 42 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5
| 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 103.3% | 1 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | 101.4% | 1 | -2 | 32516 | 132 | 50 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 |  | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3
| 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 99.64% | 1 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | 85.44% | 1 | -106 | -50049 | 54 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2
| 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | 98.18% | 1 | -1169 | 0 | 36 | 18 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2
| 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 76.43% | 1 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 95.14% | 1 | 1 | 0 | 19 | 5 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 636 | 359443
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 8 | 28 | 8 | 1840 | 2403 | 2235 | 100% | 8 | 168 | 0 | 0 | 563 | 0 | 13877647 | 321991 | 13555656 | 13967053 | 13138569 | 0 | 300000 | 300000 | 13438569 | 13128303 | 100% | 8 | -310268 | 89406 | 346 | 184 | 8 | 0 | 36530 | 0 | 0 | 0 | 36918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 209289 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 33 | 0 | 180780 | 0
| 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 97.57% | 1 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 132.6% | 0 | 530 | 1114997 | 29 | 34 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57170 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05
| 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 106.7% | 1 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 103.5% | 1 | 0 | 110603 | 110 | 22 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689
| 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 75.3% | 1 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | 101.6% | 1 | -991000 | 1610952 | 139 | 172 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 |  | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 119.2% | 1 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | 0% | 1 | -3778569 | 105786 | 32 | 57 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 95.42% | 1 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 103.7% | 1 | 0 | 0 | 51 | 6 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25
| 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 58.73% | 1 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 30.46% | 1 | 0 | -3198332 | 6 | 25 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 76.67% | 1 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 100.2% | 1 | 168 | 0 | 72 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 |  | 2021-09-07 | QTR1 | 21/22 | 613 | 615217
| 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 100.9% | 1 | 0 | 33224 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 30 | 3640 | 4538 | 3945 | 100% | 8 | 593 | 0 | 0 | 869 | 29 | 117880580 | 576073 | 117304507 | 117657809 | 120357215 | 0 | 1320000 | 1320000 | 121677215 | 116291588 | 87.5% | 7 | -4768871 | -222770 | 457 | 328 | 37 | 11 | -1671255 | 239375 | 0 | 0 | 249328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 18 | 978709 | 0 | 0 | 0 | 304279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -558514 | 0 | 68 | 29 | -697453 | 239375
| District 06 Totals |  |  |  |  | 16 | 41 | 38 | 5480 | 6941 | 6180 | 100% | 16 | 761 | 0 | 0 | 1432 | 29 | 131758227 | 898064 | 130860163 | 131624862 | 133495784 | 0 | 1620000 | 1620000 | 135115784 | 129419891 | 93.75% | 15 | -5079139 | -133364 | 803 | 512 | 45 | 11 | -1634725 | 239375 | 0 | 0 | 286246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 18 | 1187998 | 0 | 0 | 0 | 316691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -679563 | 0 | 101 | 29 | -516673 | 239375
| 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 126% | 0 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 123.6% | 0 | 248412 | 1919528 | 100 | 56 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000
| 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | 101.1% | 1 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | 90.58% | 1 | -7946 | 0 | 46 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000
| 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 95% | 1 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 95.04% | 1 | 0 | 0 | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 3 | 7 | 13 | 1001 | 1425 | 1422 | 66.67% | 2 | 3 | 3 | 0 | 263 | 161 | 19241675 | 281100 | 18960575 | 21161203 | 21189964 | -7737 | 0 | -7737 | 21182227 | 21404223 | 66.67% | 2 | 240466 | 1919528 | 171 | 92 | 0 | 51 | 785982 | 22437 | 0 | 110 | 931428 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1991432 | 405580
| 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 84.38% | 1 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 99.31% | 1 | 552 | 0 | 23 | 28 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27
| 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 101.1% | 1 | 0 | 0 | 33 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000
| 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 124.7% | 0 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | 98.85% | 1 | -57396 | 31514 | 24 | 30 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 |  | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300
| 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 72.14% | 1 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 109.2% | 1 | 0 | 49500 | 4 | 15 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7
| 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 91.43% | 1 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 100.8% | 1 | 470 | 0 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-08-15 | QTR1 | 21/22 | 796 | 685000
| 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 90% | 1 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 100.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 796 | 485498
| 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 65.14% | 1 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | 100.8% | 1 | -35622 | 0 | 62 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64
| 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 98.24% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 796 | 127700
| 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 109.6% | 1 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | 107.1% | 1 | -41787 | 386330 | 30 | 49 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 106.7% | 1 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 103.7% | 1 | 1729 | 43458 | 9 | 15 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 10 | 11 | 8 | 1703 | 2233 | 2058 | 90% | 9 | 175 | 0 | 0 | 450 | 80 | 18334271 | 384236 | 17950035 | 18845074 | 18486122 | 0 | 0 | 0 | 18486122 | 18354067 | 100% | 10 | -132054 | 510802 | 207 | 211 | 21 | 14 | 90259 | 0 | 27 | 40 | 436148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 64 | 581097 | 16552
| District 07 Totals |  |  |  |  | 13 | 18 | 21 | 2704 | 3658 | 3480 | 84.62% | 11 | 178 | 3 | 0 | 713 | 241 | 37575946 | 665336 | 36910610 | 40006277 | 39676086 | -7737 | 0 | -7737 | 39668349 | 39758290 | 92.31% | 12 | 108412 | 2430330 | 378 | 303 | 21 | 65 | 876241 | 22437 | 27 | 150 | 1367576 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 283712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 225 | 2572529 | 422132
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 184.9% | 0 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | 98.49% | 1 | -1443556 | 402730 | 70 | 122 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -172782 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 87.8% | 1 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 105.7% | 1 | 2298953 | 4629463 | 130 | 104 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -433401 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 |  | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS
| 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 102.1% | 1 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | 102.9% | 1 | -71870 | 128744 | 80 | 36 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71
| 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 100% | 1 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | 95.54% | 1 | -25916 | -284543 | 188 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4
| 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 75.97% | 1 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | 74.35% | 1 | -1807 | 442902 | 15 | 45 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51
| 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 90.11% | 1 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | 101.3% | 1 | -6647 | 20210 | 13 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25
| 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 96.58% | 1 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | 99.91% | 1 | -41583 | 18865 | 18 | 25 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81
| 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 95.08% | 1 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 99.77% | 1 | 0 | 1980 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23
| 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 70.42% | 1 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 91.69% | 1 | 0 | 0 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75
| 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 101.3% | 1 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 91.92% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 10 | 18 | 68 | 5511 | 7583 | 7100 | #VALUE! | 9 | 483 | 0 | 0 | 1011 | 1061 | 305723548 | 965307 | 304758244 | 311083902 | 310101293 | -61000 | 1200000 | 1139000 | 311240293 | 311364674 | 100% | 10 | 707574 | 5360351 | 573 | 438 | 0 | 10 | 2100507 | 1278827 | 0 | 5 | -23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1918637 | 24202 | 0 | 0 | 282001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7813 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1051 | 4831903 | 1529194
| District 08 Totals |  |  |  |  | 10 | 18 | 68 | 5511 | 7583 | 7100 | 90% | 9 | 483 | 0 | 0 | 1011 | 1061 | 305723548 | 965307 | 304758244 | 311083902 | 310101293 | -61000 | 1200000 | 1139000 | 311240293 | 311364674 | 100% | 10 | 707574 | 5360351 | 573 | 438 | 0 | 10 | 2100507 | 1278827 | 0 | 5 | -23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1918637 | 24202 | 0 | 0 | 282001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7813 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1051 | 4831903 | 1529194
| Statewide Central Let Contracts SubTotal |  |  |  |  | 72 | 137 | 204 | 21359 | 31666 | 30660 | 86.11% | 62 | 1006 | 72 | 0 | 7775 | 2532 | 458049923 | 4234816 | 453815110 | 476519352 | 478611956 | -366475 | 300000 | -66475 | 478545481 | 479608940 | 94.44% | 68 | 1643902 | 18469428 | 5035 | 2444 | 29 | 851 | 9306498 | 1511051 | 42 | 1082 | 7697246 | 748311 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 50 | 142 | 722443 | 40265 | 2 | 23 | 414963 | 52957 | 0 | 0 | 0 | 0 | 0 | 35 | 513840 | 0 | 0 | 59 | 230742 | 54753 | 63 | 146 | 621461 | 608694 | 0 | 0 | 0 | 0 | 0 | 0 | -378466 | 0 | 186 | 2338 | 19099749 | 3016034
| Statewide District Let Contracts SubTotal |  |  |  |  | 70 | 101 | 180 | 19500 | 27265 | 25383 | 84.29% | 59 | 1882 | 161 | 0 | 5872 | 1893 | 566734746 | 3801142 | 562933608 | 579412639 | 579645650 | -510760 | 3995000 | 3484240 | 583129890 | 574278269 | 94.29% | 66 | -7517857 | 12677892 | 3122 | 2079 | 495 | 371 | 4662206 | 1767950 | 136 | 193 | 1790322 | 187725 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 44 | 1085 | 3695262 | 24202 | 0 | 18 | 26404 | 0 | 0 | 0 | 0 | 0 | 6 | 40 | 668166 | 0 | 0 | 84 | 2597369 | 242717 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | -6 | -1240585 | 0 | 681 | 1806 | 12060384 | 2222594
| Statewide Totals |  |  |  |  | 142 | 238 | 384 | 40859 | 58931 | 56043 | 85.21% | 121 | 2888 | 233 | 0 | 13647 | 4425 | 1024784669 | 8035958 | 1016748718 | 1055931991 | 1058257606 | -877235 | 4295000 | 3417765 | 1061675371 | 1053887209 | 94.37% | 134 | -5873955 | 31147320 | 8157 | 4523 | 524 | 1222 | 13968704 | 3279001 | 178 | 1275 | 9487568 | 936036 | 0 | 0 | 0 | 0 | 0 | 0 | -167739 | 0 | 0 | 0 | 0 | 0 | 94 | 1227 | 4417705 | 64467 | 2 | 41 | 441367 | 52957 | 0 | 0 | 0 | 0 | 6 | 75 | 1182006 | 0 | 0 | 143 | 2828111 | 297470 | 63 | 146 | 621461 | 608694 | 0 | 21 | 0 | 0 | 0 | -6 | -1619051 | 0 | 867 | 4144 | 31160133 | 5238628

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P48 | 43489815201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-01-16 | 881862 | 950893 | 869654 | 69030.94 | 0 | 870011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869654 | 870011 | 357 | 901555
1 | E1Q47 | 42584135201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-03-15 | 44539372 | 47408126 | 47193361 | 2868754.26 | 0 | 47170167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47193361 | 47170167 | -23194 | 59075332 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
1 | E1R56 | 43796615201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 2770000 | 3004222 | 2811795 | 234221.81 | 0 | 2811795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2811795 | 2811795 | 0 | 3199272
1 | E1S02 | 43942515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-09-19 | 3418691 | 3599265 | 3634779 | 180573.88 | 0 | 3581913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 3935083
1 | E1S53 | 43890215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1335282 | 1434154 | 1346419 | 98871.24 | 0 | 1347016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 1282338
1 | E1S54 | 44334015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-06-11 | 2038002 | 2038002 | 1947616 | 0 | 0 | 1941883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 2189903
1 | E1T47 | 44624415201 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2020-07-15 | 1836500 | 1836500 | 1786500 | 0 | 0 | 1787020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 1849529 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1T84 | 43506615201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 231014 | 231014 | 219205 | 0 | 0 | 219205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219205 | 219205 | 0 | 230282 | B0 | ACC - LUMP SUM
1 | T1700 | 43088615201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2262913 | 2254766 | 2207735 | -8146.86 | 0 | 2219978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | 2483173
1 | T1735 | 43654715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-09-26 | 409918 | 418046 | 383683 | 8128.44 | 0 | 383683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383683 | 383683 | 0 | 267364
1 | T1747 | 43355035201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-08-28 | 12256766 | 12232966 | 12265846 | -23799.95 | -82722 | 12147745 | -82722 | 0 | 0 | 0 | 0 | 0 | -82722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82722 | 12183124 | 12147745 | -35379 | 11662003
1 | T1755 | 43659715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 5620384 | 5602989 | 5688348 | -17394.84 | 0 | 5695271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | 6766075
1 | T1764 | 44013015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 381859 | 381859 | 358474 | 0 | 0 | 358474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358474 | 358474 | 0 | 386666
1 | T1768 | 43900215201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1847556 | 1962457 | 1921734 | 114901.14 | 0 | 1920578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 1876585
1 | T1786 | 41450665201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 1630302 | 1630302 | 1465226 | 0 | 0 | 1467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 2010635
2 | E20C2 | 44105115201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-16 | 539351 | 539351 | 482138 | 0 | 0 | 482138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482138 | 482138 | 0 | 678652
2 | E20D9 | 44703115201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-09-02 | 394410 | 571805 | 486787 | 177395.01 | 0 | 486787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486787 | 486787 | 0 | 493957
2 | E2V69 | 21327275201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-10-18 | 16294500 | 17291837 | 17466265 | 997337.38 | 1350000 | 17461845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 350000 | 0 | 0 | 0 | 1350000 | 1350000 | 18816265 | 17461845 | -1354420 | 18122424 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | E2W84 | 43384215201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 1444429 | 2840551 | 2999816 | 1396122.44 | 0 | 2999816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1103685
2 | E2Y24 | 43743715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-05-13 | 1280762 | 1204874 | 1079365 | -75887.97 | 0 | 1079365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | 2106516
2 | E2Y79 | 20968315201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2019-11-13 | 4028350 | 4078350 | 4286744 | 50000 | 0 | 4286650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 3704637
2 | E2Y85 | 43865025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 3884320 | 3884320 | 3769800 | 0 | 0 | 3768427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 4380189
2 | E2Z24 | 44199735216 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-02-19 | 1624143 | 1624143 | 1547862 | 0 | 0 | 1547862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 1701419
2 | E2Z36 | 43930315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-12-18 | 363396 | 445802 | 448483 | 82406.57 | 0 | 448483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448483 | 448483 | 0 | 356089
2 | E2Z39 | 43122445201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-15 | 788792 | 788792 | 738086 | 0 | 0 | 738086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738086 | 738086 | 0 | 1315900
2 | E2Z50 | 42848915201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-03-18 | 1635960 | 1685775 | 1669775 | 49815.5 | 0 | 1669775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 1762747
2 | E2Z52 | 43204815201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 1206264 | 1206264 | 1198471 | 0 | 0 | 1198471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 1268308
2 | E2Z56 | 43807915201 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 744154 | 744154 | 696705 | 0 | 0 | 696705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696705 | 696705 | 0 | 797486
2 | T2573 | 21071125201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 39980618 | 41792741 | 42556288 | 1812123.25 | 0 | 43150258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42556288 | 43150258 | 593970 | 35388991
2 | T2579 | 21071245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-28 | 59962436 | 63341457 | 65450734 | 3379021.04 | 0 | 65787858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65450734 | 65787858 | 337124 | 62411016
2 | T2641 | 20953745201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-10-26 | 60315650 | 62391668 | 63370802 | 2076017.6 | 0 | 64652436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63370802 | 64652436 | 1281634 | 62430987
2 | T2700 | 41525015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-04-25 | 11881880 | 12125444 | 12326250 | 243563.71 | 0 | 12277546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12326250 | 12277546 | -48704 | 8810905
2 | T2712 | 43240415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-29 | 3754465 | 3806745 | 3827055 | 52279.5 | -32544 | 3793154 | -32544 | 0 | 0 | 0 | 0 | 0 | -32544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32544 | 3794511 | 3793154 | -1358 | 4106536
2 | T2753 | 43980015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 3416497 | 3891903 | 3917050 | 475405.64 | 0 | 3897876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 3898969
2 | T2759 | 43617615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 4035736 | 4035736 | 3954853 | 0 | 0 | 3920789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 4365195
2 | T2760 | 44125815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 6493175 | 6617231 | 6291241 | 124056.15 | -142728 | 6267785 | -142728 | 0 | 0 | 0 | 0 | 0 | -142728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142728 | 6148513 | 6267785 | 119272 | 5584101
2 | T2762 | 44499015201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2020-04-29 | 1596635 | 1683719 | 1395080 | 87083.98 | 0 | 1395080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 1936705
2 | T2768 | 43948815201 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 1959598 | 1959598 | 1892736 | 0 | 0 | 1893489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 1755198
2 | T2770 | 43948915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 601043 | 596270 | 539883 | -4773.2 | 0 | 539883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539883 | 539883 | 0 | 942548
2 | T2774 | 43578015201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-05-20 | 1066490 | 1066490 | 1059789 | 0 | 0 | 1060127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 1110094
2 | T2776 | 43399315201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 198978 | 198978 | 196874 | 0 | 0 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196874 | 196874 | 0 | 202254
2 | T2780 | 43732515201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 237581 | 237581 | 222711 | 0 | 0 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222711 | 222711 | 0 | 289607
2 | T2786 | 43732315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 5990960 | 5990960 | 5941443 | 0 | 0 | 5882422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 7170016
2 | T9022 | 44531935223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 1990220 | 2080312 | 2092740 | 90091.64 | 0 | 2092740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 1872855
3 | E3Q53 | 44009615201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2017-07-20 | 4412093 | 4461209 | 4457747 | 49116.18 | -449760 | 4007987 | -449760 | 0 | 0 | 0 | 0 | 0 | -449760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -449760 | 4007987 | 4007987 | 0 | 4688435 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
3 | E3S42 | 42187345201 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 2507433 | 2507433 | 2457433 | 0 | 0 | 2457433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 2985049
3 | E3S73 | 4453811H201 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2019-12-12 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174645 | 0 | -174645 | 212648
3 | E3T25 | 44154615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 2058102 | 2058102 | 2116209 | 0 | 0 | 2113685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 2347515
3 | E3T27 | 40571925201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-17 | 673158 | 673158 | 632738 | 0 | 0 | 632738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632738 | 632738 | 0 | 803648
3 | E3T35 | 44291315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1454221 | 1547027 | 1426180 | 92805.8 | 25000 | 1426180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 1274994 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3T58 | 43815415201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-12 | 883399 | 898220 | 890748 | 14820.6 | 0 | 890748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890748 | 890748 | 0 | 673070
3 | E3T66 | 4450184H201 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2020-03-12 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225968 | 0 | -225968 | 246220
3 | E3T96 | 4453581G201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-13 | 782169 | 1364937 | 1338192 | 582768.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 1084959
3 | T3640 | 43290925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 720412 | 720412 | 691249 | 0 | 0 | 691249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691249 | 691249 | 0 | 499997 | B0 | ACC - LUMP SUM
3 | T3646 | 22049585201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 15646589 | 15902989 | 15169686 | 256399.6 | 0 | 15198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15169686 | 15198000 | 28314 | 21200000
3 | T3682 | 43812915201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 346966 | 346966 | 335754 | 0 | 0 | 335754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335754 | 335754 | 0 | 319060
3 | T3692 | 43774615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-03-27 | 8791950 | 9177543 | 9191379 | 385592.85 | 0 | 9104839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191379 | 9104839 | -86540 | 10784327
3 | T3699 | 43228415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2694142 | 2663955 | 2668318 | -30186.8 | 0 | 2665830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | 2634440
3 | T3700 | 43811115201 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 678788 | 678788 | 592391 | 0 | 0 | 592857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592391 | 592857 | 466 | 960134
3 | T3717 | 43720215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 770613 | 797858 | 802448 | 27244.97 | 0 | 802695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802448 | 802695 | 247 | 750108
3 | T3723 | 43972115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 4514950 | 4573579 | 4689305 | 58629.33 | -24500 | 4517927 | 0 | 0 | 0 | 0 | 0 | -24500 | -24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24500 | 4664805 | 4517927 | -146878 | 5332165
3 | T3729 | 43972715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 7592042 | 7796389 | 8177990 | 204347 | 0 | 8127837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 9289556
3 | T3738 | 44173815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-05-20 | 1336283 | 1373486 | 1300986 | 37202.72 | 0 | 1302036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 1328097
3 | T3744 | 43972415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 5906321 | 5906321 | 6014134 | 0 | 0 | 5961005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 5368996
3 | T3746 | 44154315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 4283738 | 4283738 | 4494319 | 0 | 0 | 4570359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 5641395
3 | T3749 | 44173215201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 755462 | 755462 | 668670 | 0 | 0 | 668670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668670 | 668670 | 0 | 824731
3 | T3770 | 44134715201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-02-17 | 224915 | 224915 | 229832 | 0 | 0 | 229832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229832 | 229832 | 0 | 248071
4 | E4U24 | 43984115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2020-03-06 | 1238848 | 1238449 | 1196529 | -399.46 | 0 | 1196625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | 1271431
4 | E4U54 | 44330915201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-07 | 1153286 | 1168772 | 976003 | 15485.58 | 100000 | 980548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | T4471 | 43472215201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 5223993 | 5569665 | 5480351 | 345672.31 | -68940 | 5405890 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5411411 | 5405890 | -5522 | 5507060
4 | T4488 | 43630415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 552418 | 602867 | 592608 | 50448.67 | 0 | 592529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592608 | 592529 | -79 | 285675
4 | T4494 | 43630715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5685198 | 5923341 | 5849802 | 238143.16 | 0 | 5808702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 5359259
4 | T4497 | 43783615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 7969825 | 9671721 | 9618307 | 1701895.88 | 0 | 9579829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9618307 | 9579829 | -38478 | 9083314
4 | T4504 | 43783815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 8446061 | 9282205 | 9225023 | 836144.4 | 0 | 9088376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 9046599
4 | T4505 | 43668515201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 7195336 | 7097482 | 6908157 | -97854.53 | 0 | 6849432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6908157 | 6849432 | -58724 | 7395888
4 | T4509 | 43177055201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-04-24 | 3049775 | 3212084 | 3151909 | 162309.67 | 0 | 3134194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151909 | 3134194 | -17714 | 2802936
4 | T4511 | 43469015201 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2099355 | 2040900 | 1905910 | -58454.44 | 0 | 1888675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | 2266163
4 | T4523 | 43469515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 8207877 | 8281895 | 8003190 | 74017.2 | 0 | 7894972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 8969821
4 | T4528 | 43696715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 547645 | 547645 | 476343 | 0 | 0 | 476343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476343 | 476343 | 0 | 487570
4 | T4530 | 43592515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2019-12-04 | 4642816 | 4682420 | 4650889 | 39603.28 | 0 | 4619922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 4777019
4 | T4538 | 44138115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 589517 | 589517 | 585765 | 0 | 0 | 586015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585765 | 586015 | 250 | 492571
4 | T4543 | 43915915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 689567 | 689567 | 649805 | 0 | 0 | 650042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649805 | 650042 | 237 | 603406
4 | T4553 | 43840215201 | F823160551 | LEON AMERICA CONSTRUCTIONLLC | N/A | N/A | N/A | N/A | 2020-07-29 | 432944 | 432944 | 392014 | 0 | 0 | 392107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392014 | 392107 | 93 | 514165
5 | E50A9 | 44326415201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-03-03 | 1277250 | 1307659 | 1259799 | 30409.22 | 0 | 1259799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 1837867
5 | E52A1 | 44208715201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-10-06 | 875517 | 875517 | 860515 | 0 | 0 | 862383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860515 | 862383 | 1868 | 776685
5 | E52A3 | 44539615201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 254016 | 254016 | 220075 | 0 | 0 | 220075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220075 | 220075 | 0 | 309304
5 | E53A9 | 44101715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 789395 | 789395 | 772436 | 0 | 0 | 772436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772436 | 772436 | 0 | 659076
5 | E54A9 | 44541215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-03-02 | 239156 | 239156 | 221370 | 0 | 0 | 221370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221370 | 221370 | 0 | 305554
5 | E57A9 | 43988085201 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-02-02 | 127056 | 127056 | 123994 | 0 | 0 | 123994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123994 | 123994 | 0 | 169610
5 | E5Z86 | 43913615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-07 | 7339262 | 7409262 | 7411267 | 70000 | 0 | 7390488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 7635147
5 | E5Z88 | 43793715201 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 1872651 | 1875633 | 1830367 | 2981.59 | 0 | 1825332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830367 | 1825332 | -5035 | 1916337
5 | E5Z90 | 44326915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-07 | 3873465 | 3916343 | 4113159 | 42878.1 | 0 | 4113159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 4116925 | B1 | ACC - NO EXCUSE BONUS
5 | E5Z96 | 44116615201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 1299589 | 1299589 | 1316020 | 0 | 0 | 1315225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 1579621
5 | T5538 | 23949635201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 27752000 | 28126749 | 28782547 | 374748.52 | -7304 | 29206081 | 0 | 0 | 0 | 0 | 0 | -7304 | -7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7304 | 28775243 | 29206081 | 430838 | 28403237
5 | T5582 | 23827585201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 9883550 | 9891919 | 9834478 | 8369.37 | 0 | 10163025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834478 | 10163025 | 328547 | 14381890
5 | T5628 | 43734115201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 16216216 | 16216212 | 16727455 | -4.3 | 0 | 16505113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16727455 | 16505113 | -222342 | 16716427
5 | T5637 | 43386015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-10-31 | 3244000 | 6497176 | 7037281 | 3253176.27 | 0 | 7021113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037281 | 7021113 | -16169 | 3081320
5 | T5669 | 43923515201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2019-10-30 | 9146375 | 9218711 | 9241919 | 72336.38 | 0 | 9193416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 7779291
5 | T5676 | 43913915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 3433963 | 3456872 | 3590532 | 22908.37 | 0 | 3561652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 4003251
5 | T5678 | 43913115201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 9468271 | 9554158 | 9236375 | 85887 | 0 | 9044854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 12400166
5 | T5681 | 43968215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-25 | 5811031 | 5814390 | 5643783 | 3359.62 | 0 | 5604250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 6194317
5 | T5685 | 44139615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 1144140 | 1144140 | 1050473 | 0 | 0 | 1085978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 1587329
5 | T5701 | 44136515201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 1343897 | 1343897 | 1295471 | 0 | 0 | 1296320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 1376221
6 | E6K72 | 43652215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-01-25 | 12962183 | 14077180 | 17042051 | 1114996.62 | 0 | 17042582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17042051 | 17042582 | 530 | 12118991
6 | E6K73 | 43653715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-25 | 4293668 | 4404270 | 4390585 | 110602.64 | 0 | 4390585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 3248689
6 | E6K77 | 42930035201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-23 | 89490000 | 91100952 | 91019470 | 1610951.88 | 1320000 | 91348469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 0 | 0 | 1320000 | 1320000 | 92339470 | 91348469 | -991000 | 75222050 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
6 | E6L90 | 43029139201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-05-03 | 3703968 | 3809754 | 3778569 | 105785.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6L94 | 43653915201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2020-07-30 | 1871000 | 1871000 | 1887711 | 0 | 0 | 1887711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 2130684
6 | E6M32 | 44204015201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-05 | 4679092 | 1480760 | 1400668 | -3198331.59 | 0 | 1400668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
6 | E6M37 | 44060415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-30 | 589589 | 589589 | 561220 | 0 | 0 | 561388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561220 | 561388 | 168 | 615217
6 | E6M47 | 44196115201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 291080 | 324304 | 276941 | 33224 | 0 | 276941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276941 | 276941 | 0 | 335060
6 | T6465 | 43345535201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-12-04 | 3445403 | 3514192 | 3479994 | 68789.07 | 170000 | 3454649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 3079920 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6472 | 44167015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-02-26 | 1098693 | 1098693 | 1036954 | 0 | 0 | 1036856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 1175314
6 | T6475 | 43635525201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 3771815 | 3809965 | 3652358 | 38150 | 130000 | 3668771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 4248051 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6478 | 44030415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 419419 | 419419 | 372140 | 0 | 0 | 372179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372140 | 372179 | 39 | 420618
6 | T6482 | 44017815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 996753 | 1029269 | 971330 | 32516 | 0 | 971328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 971330 | 971328 | -2 | 819497
6 | T6493 | 44331415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 2625000 | 2574951 | 2200098 | -50049.49 | 0 | 2199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | 2833197
6 | T6498 | 43080835201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 1171215 | 1171215 | 1109354 | 0 | 0 | 1108186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 865294
6 | T6526 | 44167215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 349349 | 349349 | 316341 | 0 | 0 | 316342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316341 | 316342 | 1 | 359443
7 | E7M91 | 44144125201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-03-11 | 1622282 | 1622282 | 1554003 | 0 | 0 | 1554555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 1262053
7 | E7M94 | 43673415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 1352812 | 1352812 | 1317432 | 0 | 0 | 1317432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 1640000
7 | E7M96 | 43762615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-13 | 4564698 | 4596212 | 4520073 | 31514.1 | 0 | 4462676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 5061300
7 | E7N02 | 44383315201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-03-11 | 741228 | 790728 | 771044 | 49500 | 0 | 771044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771044 | 771044 | 0 | 741279
7 | E7N26 | 43946015201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2020-07-08 | 873873 | 873873 | 855130 | 0 | 0 | 855600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855130 | 855600 | 470 | 685000
7 | E7N46 | 43955415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-09 | 357252 | 357252 | 337890 | 0 | 0 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337890 | 337890 | 0 | 485498
7 | E7N48 | 44025215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | 3104340 | 3104340 | 3112890 | 0 | 0 | 3077268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 4202893
7 | E7N59 | 44701515201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-01-20 | 86342 | 86342 | 80991 | 0 | 0 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80991 | 80991 | 0 | 127700
7 | E7R17 | 44368415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-30 | 4637000 | 5023330 | 4952442 | 386330.45 | 0 | 4910655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R25 | 44335815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-04 | 994444 | 1037903 | 984227 | 43458.19 | 0 | 985956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 922458 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7385 | 25624325201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2016-06-20 | 12584444 | 14503972 | 15099334 | 1919527.94 | 0 | 15347747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15099334 | 15347747 | 248412 | 18085000
7 | T7447 | 43764115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 3572269 | 3572269 | 3206137 | 0 | -7737 | 3190454 | -7737 | 0 | 0 | 0 | 0 | 0 | -7737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7737 | 3198400 | 3190454 | -7946 | 2900000
7 | T7466 | 43764615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-11-18 | 3084962 | 3084962 | 2884493 | 0 | 0 | 2884493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 2622400
8 | E8N18 | 41505115201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2014-05-16 | 73888232 | 74290962 | 74217617 | 402729.5 | -51000 | 72723061 | 0 | 0 | 0 | 0 | 0 | -51000 | -51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51000 | 74166617 | 72723061 | -1443556 | 78874307 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8Q12 | 41140615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-01 | 176976815 | 181606278 | 183899695 | 4629463.16 | 1190000 | 187388648 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 1190000 | 185089695 | 187388648 | 2298953 | 198773292 | A5 | ICC - BAM/BONUS
8 | E8Q95 | 43652015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-19 | 13519194 | 13647938 | 13835344 | 128743.5 | 0 | 13763473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 16504275
8 | E8R51 | 44132215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | 17604432 | 17319890 | 16726393 | -284542.88 | 0 | 16700477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726393 | 16700477 | -25916 | 15706807
8 | E8R55 | 42815445201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2019-04-09 | 7871284 | 8314187 | 5811967 | 442902.29 | 0 | 5810160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5811967 | 5810160 | -1807 | 9545164
8 | E8S00 | 44106715201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-09-10 | 5292443 | 5312653 | 5319849 | 20210.25 | 0 | 5313201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 4997184
8 | E8S18 | 44042315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-14 | 9095686 | 9114552 | 9001603 | 18865.24 | 0 | 8960020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 12888272
8 | E8S63 | 44514015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-12-08 | 281612 | 283592 | 264303 | 1980 | 0 | 264303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264303 | 264303 | 0 | 348350
8 | E8S68 | 44530715201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-01-12 | 842202 | 842202 | 728029 | 0 | 0 | 728029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728029 | 728029 | 0 | 1031657
8 | E8S73 | 44429215201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2020-09-15 | 351648 | 351648 | 296493 | 0 | 0 | 296493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296493 | 296493 | 0 | 613041

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | -8147 | 134 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 7 | 01co | 1 | 7
01CO | 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 0 | 8128 | 11 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 8 | 01do | 8 | 15
01CO | 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | -35379 | -23800 | 78 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59 |  |  | 1 | 28 | 0 | 0 | -38003 | 0 |  | CO | 16 | 02co | 16 | 31
01CO | 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | -17395 | 44 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 13 | 02do | 32 | 44
01CO | 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 14 | 03co | 45 | 58
01CO | 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 264 | 37 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 114901 | 43 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 9 | 03do | 59 | 67
01CO | 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 14 | 04co | 68 | 81
01DO | 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 357 | 69031 | 29 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO | 2 | 04do | 82 | 83
01DO | 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | -23194 | 2868754 | 166 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 60 | 0 | 0 | 0 | 0 |  | DO | 10 | 05co | 84 | 93
01DO | 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 0 | 234222 | 11 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33 |  |  | 0 | 6 | 0 | 0 | 0 | 0 | T | DO | 10 | 05do | 94 | 103
01DO | 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 180574 | 207 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO | 8 | 06co | 104 | 111
01DO | 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 98871 | 44 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO | 8 | 06do | 112 | 119
01DO | 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO | 3 | 07co | 120 | 122
01DO | 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 13 | 0 | 0 | 0 | 0 |  | DO | 10 | 07do | 123 | 132
01DO | 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 133 | 132
02CO | 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 593970 | 1812123 | 319 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1 |  |  | 4 | 136 | 0 | 0 | -73244 | 0 |  | CO | 10 | 08do | 133 | 142
02CO | 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 337124 | 3379021 | 270 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71 |  |  | 91 | 196 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 1278355 | 2076018 | 139 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7 |  |  | 0 | 86 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | -48704 | 243564 | 155 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | -1358 | 52280 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 475406 | 27 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6267785 | 119272 | 124056 | 35 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49 |  |  | 10 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 87084 | 10 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705 |  |  | 31 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 0 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42 |  |  | 3 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 0 | -4773 | 3 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 0 | 28 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 90092 | 12 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66 |  |  | 11 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 0 | 177395 | 58 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | -1354420 | 997337 | 55 | 0 | 0 | 307141 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1068650 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 118 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1396122 | 103 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42 |  |  | 27 | 32 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | -75888 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32 |  |  | 0 | 15 | 0 | 0 | -75888 | 0 |  | DO
02DO | 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 50000 | 30 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21 |  |  | 5 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 0 | 82407 | 16 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 49816 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 109543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109543 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03 |  |  | 21 | 48 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 28314 | 256400 | 170 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | -86540 | 385593 | 320 | 0 | 3 | 71605 | 0 | 0 | 4 | 120094 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429239 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93 |  |  | 6 | 100 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | -30187 | 126 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 466 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 247 | 27245 | 34 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | -146878 | 58629 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83 |  |  | 2 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 204347 | 63 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 37203 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 90 | 174 | 176 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 755462 | 668670 | 0 | 0 | 0 | 668670 | 668670 | 0 | 0 | 39 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5200 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-12 | QTR2 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61 |  |  | 7 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 0 | 49116 | 256 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 90 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 0 | 213 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | -174645 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 92806 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 0 | 14821 | 35 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | -225968 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK JR | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-10-20 | QTR2 | 20/21 | 314 | 246220 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 582769 | 17 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | -5522 | 345672 | 158 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32 |  |  | 7 | 48 | 0 | 0 | -46629 | 0 |  | CO
04CO | 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | -79 | 50449 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 238143 | 56 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | -38478 | 1701896 | 99 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 836144 | 110 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | -58724 | -97855 | 61 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17 |  |  | 6 | 33 | 0 | 0 | -99541 | 0 |  | CO
04CO | 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | -17714 | 162310 | 92 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | -58454 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 74017 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95 |  |  | 10 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 39603 | 54 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 250 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 237 | 0 | 25 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 93 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTIONLLC | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | -399 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 15486 | 15 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 430838 | 374749 | 219 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3 |  |  | 30 | 102 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 328547 | 8369 | 210 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | -222563 | -4 | 112 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | -16169 | 3253176 | 23 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320 |  |  | 20 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 72336 | 18 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 22908 | 74 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 85887 | 113 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87 |  |  | 23 | 94 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 3360 | 113 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 30409 | 84 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 0 | 0 | 13 | 0 | 0 | 7876 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 507 | 309304 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 0 | 0 | 7 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03 |  |  | 12 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 70000 | 38 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19 |  |  | 29 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | -5035 | 2982 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55 |  |  | 0 | 138 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 42878 | 52 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 68789 | 27 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 38150 | 11 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 39 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | -2 | 32516 | 132 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | -50049 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2 |  |  | 0 | 25 | 0 | 0 | -121049 | 0 |  | CO
06CO | 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 0 | 36 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 1 | 0 | 19 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 636 | 359443 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 530 | 1114997 | 29 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05 |  |  | 0 | 34 | 0 | 0 | -57170 | 0 |  | DO
06DO | 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 110603 | 110 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | -991000 | 1610952 | 139 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 172 | 0 | 0 | -501344 | 0 |  | DO
06DO | 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 105786 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 0 | 51 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | -3198332 | 6 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 168 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 | 2021-09-07 | QTR1 | 21/22 | 613 | 615217 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 0 | 33224 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 248412 | 1919528 | 100 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | -7946 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 0 | 23 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27 |  |  | 3 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 31514 | 24 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 0 | 49500 | 4 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 470 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-08-15 | QTR1 | 21/22 | 796 | 685000 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 796 | 485498 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 796 | 127700 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 386330 | 30 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 16 | 49 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 43458 | 9 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR | 14 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | -1443556 | 402730 | 70 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 122 | 0 | 0 | -172782 | 0 |  | DO
08DO | 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 2298953 | 4629463 | 130 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS | 2 | 104 | 0 | -6 | -433401 | 0 |  | DO
08DO | 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 128744 | 80 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | -25916 | -284543 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4 |  |  | 10 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | -1807 | 442902 | 15 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51 |  |  | 10 | 45 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 20210 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 18865 | 18 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 0 | 1980 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08 |  |  | 2 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0