## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 58321312 | 57502740 | 59190525 | 58537541 | -60000 | 58319435 | 1.42% | 92.31% | 1003691 | 1.745% | 869213 | 1.49% | 3020 | 700 | 23.18% | 220 | 7.285% | 71 | 2.351% | 64 | 2.119% | 3155 | 4.47% | 4132 | 4129 | 3209 | 6.258% | 100%
| District Let | 78098552 | 77416548 | 82456166 | 80923448 | -125000 | 80594930 | 4.106% | 92.31% | 4364596 | 5.638% | 4357613 | 5.58% | 3766 | 677 | 17.98% | 318 | 8.444% | 51 | 1.354% | 353 | 9.373% | 4170 | 10.73% | 5291 | 5362 | 4367 | 15.96% | 61.54%
| All Contracts | 136419864 | 134919288 | 141646691 | 139460989 | -185000 | 138914365 | 2.961% | 92.31% | 5368287 | 3.979% | 5226826 | 3.831% | 6786 | 1377 | 20.29% | 538 | 7.928% | 122 | 1.798% | 417 | 6.145% | 7325 | 7.943% | 9423 | 9491 | 7576 | 11.64% | 80.77%
2 | Central Let | 239678093 | 238372203 | 248748496 | 252387742 | 0 | 253738765 | 6.446% | 91.3% | 8902010 | 3.735% | 9070402 | 3.784% | 8454 | 1603 | 18.96% | 981 | 11.6% | 18 | 0.2129% | 1087 | 12.86% | 9559 | 13.07% | 12266 | 11827 | 9243 | 9.333% | 78.26%
| District Let | 40859639 | 40042181 | 43613739 | 42906803 | 1350000 | 42880753 | 7.089% | 81.25% | 2996585 | 7.484% | 2754102 | 6.74% | 4207 | 623 | 14.81% | 535 | 12.72% | 125 | 2.971% | 308 | 7.321% | 4640 | 10.29% | 5810 | 5303 | 4145 | -1.474% | 81.25%
| All Contracts | 280537732 | 278414384 | 292362235 | 295294545 | 1350000 | 296619518 | 6.539% | 87.18% | 11898595 | 4.274% | 11824504 | 4.215% | 12661 | 2226 | 17.58% | 1516 | 11.97% | 143 | 1.129% | 1395 | 11.02% | 14199 | 12.15% | 18076 | 17130 | 13388 | 5.742% | 79.49%
3 | Central Let | 73028044 | 72160488 | 74548608 | 74433149 | 0 | 74165056 | 2.778% | 100% | 1586220 | 2.198% | 1520564 | 2.082% | 4520 | 1467 | 32.46% | 565 | 12.5% | 73 | 1.615% | 99 | 2.19% | 4692 | 3.805% | 6724 | 6630 | 4598 | 1.726% | 100%
| District Let | 14963682 | 14632124 | 15703193 | 15402098 | 25000 | 13250684 | -9.441% | 100% | 698640 | 4.775% | 739512 | 4.942% | 1565 | 624 | 39.87% | 224 | 14.31% | 379 | 24.22% | 150 | 9.585% | 2094 | 33.8% | 2954 | 2926 | 2078 | 32.78% | 63.64%
| All Contracts | 87991726 | 86792612 | 90251801 | 89835247 | 25000 | 87415740 | 0.718% | 100% | 2284860 | 2.633% | 2260076 | 2.569% | 6085 | 2091 | 34.36% | 789 | 12.97% | 452 | 7.428% | 249 | 4.092% | 6786 | 11.52% | 9678 | 9556 | 6676 | 9.712% | 86.21%
4 | Central Let | 64036173 | 63194457 | 67586628 | 66183454 | 0 | 65561229 | 3.745% | 94.12% | 3821096 | 6.047% | 3550453 | 5.544% | 5580 | 1108 | 19.86% | 492 | 8.817% | 49 | 0.8781% | 305 | 5.466% | 5934 | 6.344% | 7649 | 7345 | 5745 | 2.957% | 94.12%
| District Let | 6504409 | 6254409 | 6518385 | 6080609 | 100000 | 6096698 | -2.522% | 100% | 114636 | 1.833% | 13976 | 0.2149% | 910 | 165 | 18.13% | 82 | 9.011% | 0 | 0% | 33 | 3.626% | 943 | 3.626% | 1190 | 1187 | 940 | 3.297% | 100%
| All Contracts | 70540582 | 69448866 | 74105013 | 72264063 | 100000 | 71657927 | 3.181% | 95.45% | 3935732 | 5.667% | 3564429 | 5.053% | 6490 | 1273 | 19.61% | 574 | 8.844% | 49 | 0.755% | 338 | 5.208% | 6877 | 5.963% | 8839 | 8532 | 6685 | 3.005% | 95.45%
5 | Central Let | 110266399 | 109109545 | 117215424 | 119502886 | 0 | 119588711 | 9.604% | 84.62% | 7451573 | 6.829% | 6949025 | 6.302% | 4235 | 1078 | 25.45% | 599 | 14.14% | 5 | 0.1181% | 1100 | 25.97% | 5340 | 26.09% | 7083 | 6967 | 5290 | 24.91% | 61.54%
| District Let | 43281836 | 42479459 | 44420191 | 44252030 | 0 | 44206713 | 4.066% | 100% | 1512578 | 3.561% | 1138355 | 2.63% | 2670 | 553 | 20.71% | 388 | 14.53% | 0 | 0% | 176 | 6.592% | 2846 | 6.592% | 3803 | 3702 | 2761 | 3.408% | 100%
| All Contracts | 153548235 | 151589004 | 161635615 | 163754916 | 0 | 163795424 | 8.052% | 92.86% | 8964151 | 5.913% | 8087380 | 5.267% | 6905 | 1631 | 23.62% | 987 | 14.29% | 5 | 0.07241% | 1276 | 18.48% | 8186 | 18.55% | 10886 | 10669 | 8051 | 16.6% | 82.14%
6 | Central Let | 32227560 | 31611887 | 32679015 | 31667195 | 1200000 | 31646817 | 0.1105% | 100% | 643504 | 2.036% | 451455 | 1.401% | 3219 | 614 | 19.07% | 264 | 8.201% | 78 | 2.423% | 0 | 0% | 3297 | 2.423% | 4175 | 3802 | 2924 | -9.164% | 100%
| District Let | 118541240 | 117933499 | 118318469 | 120991524 | 1320000 | 116926423 | -0.8539% | 88.89% | -671561 | -0.5694% | -222770 | -0.1879% | 3820 | 615 | 16.1% | 341 | 8.927% | 68 | 1.78% | 29 | 0.7592% | 3917 | 2.539% | 4889 | 4237 | 3281 | -14.11% | 100%
| All Contracts | 150768800 | 149545386 | 150997484 | 152658719 | 2520000 | 148573240 | -0.6501% | 95.45% | -28057 | -0.01876% | 228685 | 0.1517% | 7039 | 1229 | 17.46% | 605 | 8.595% | 146 | 2.074% | 29 | 0.412% | 7214 | 2.486% | 9064 | 8039 | 6205 | -11.85% | 100%
7 | Central Let | 50669253 | 49771882 | 56462531 | 57168255 | 0 | 57558216 | 15.64% | 62.5% | 5901945 | 11.86% | 5793277 | 11.43% | 2669 | 581 | 21.77% | 270 | 10.12% | 0 | 0% | 598 | 22.41% | 3267 | 22.41% | 4118 | 4411 | 3560 | 33.38% | 75%
| District Let | 57659883 | 57028147 | 58883558 | 58700702 | 1275000 | 58480642 | 2.547% | 93.33% | 1079413 | 1.893% | 1223673 | 2.122% | 3466 | 594 | 17.14% | 373 | 10.76% | 181 | 5.222% | 217 | 6.261% | 3864 | 11.48% | 4831 | 4570 | 3603 | 3.953% | 86.67%
| All Contracts | 108329136 | 106800029 | 115346089 | 115868957 | 1275000 | 116038858 | 8.651% | 82.61% | 6981358 | 6.537% | 7016950 | 6.477% | 6135 | 1175 | 19.15% | 643 | 10.48% | 181 | 2.95% | 815 | 13.28% | 7131 | 16.23% | 8949 | 8981 | 7163 | 16.76% | 82.61%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 318680546 | 317567433 | 324191882 | 323313461 | 1200000 | 324531147 | 2.193% | 100% | 5066064 | 1.595% | 5511333 | 1.729% | 5797 | 646 | 11.14% | 504 | 8.694% | 10 | 0.1725% | 1051 | 18.13% | 6858 | 18.3% | 8008 | 7525 | 6375 | 9.971% | 90.91%
| All Contracts | 318680546 | 317567433 | 324191882 | 323313461 | 1200000 | 324531147 | 2.193% | 100% | 5066064 | 1.595% | 5511333 | 1.729% | 5797 | 646 | 11.14% | 504 | 8.694% | 10 | 0.1725% | 1051 | 18.13% | 6858 | 18.3% | 8008 | 7525 | 6375 | 9.971% | 90.91%
Totals This Qtr | Central Let | 628226834 | 621723202 | 656431227 | 659880222 | 1140000 | 660578229 | 6.25% | 91.43% | 29310039 | 4.714% | 28204389 | 4.49% | 31697 | 7151 | 22.56% | 3391 | 10.7% | 294 | 0.9275% | 3253 | 10.26% | 35244 | 11.19% | 46147 | 45111 | 34569 | 9.061% | 87.62%
| District Let | 678589787 | 673353800 | 694105583 | 692570675 | 5145000 | 686967990 | 2.022% | 93.68% | 15160951 | 2.252% | 15515794 | 2.286% | 26201 | 4497 | 17.16% | 2765 | 10.55% | 814 | 3.107% | 2317 | 8.843% | 29332 | 11.95% | 36776 | 34812 | 27550 | 5.149% | 84.21%
| All Contracts | 1306816621 | 1295077002 | 1350536810 | 1352450897 | 6285000 | 1347546219 | 4.051% | 92.5% | 44470990 | 3.434% | 43720183 | 3.346% | 57898 | 11648 | 20.12% | 6156 | 10.63% | 1108 | 1.914% | 5570 | 9.62% | 64576 | 11.53% | 82923 | 79923 | 62119 | 7.29% | 86%
Totals Previous Quarter | Central Let | 206929806 | 204865553 | 218429768 | 220248830 | 170000 | 220893794 | 7.824% | 94.74% | 12145795 | 5.929% | 11499962 | 5.557% | 11192 | 2589 | 23.13% | 1255 | 11.21% | 65 | 0.5808% | 1611 | 14.39% | 12868 | 14.97% | 16901 | 16261 | 12417 | 10.95% | 84.21%
| District Let | 222596286 | 220518040 | 226410545 | 221977238 | 2795000 | 216796218 | -1.688% | 100% | 3588553 | 1.627% | 3814258 | 1.714% | 10888 | 1729 | 15.88% | 1213 | 11.14% | 417 | 3.83% | 435 | 3.995% | 11740 | 7.825% | 14755 | 13429 | 10487 | -3.683% | 88.1%
| All Contracts | 429526092 | 425383593 | 444840313 | 442226068 | 2965000 | 437690012 | 2.893% | 97.5% | 15734348 | 3.699% | 15314220 | 3.565% | 22080 | 4318 | 19.56% | 2468 | 11.18% | 482 | 2.183% | 2046 | 9.266% | 24608 | 11.45% | 31656 | 29690 | 22904 | 3.732% | 86.25%
Totals Fiscal Year 2021/2022 | Central Let | 664979729 | 658680663 | 694949120 | 698860786 | 470000 | 700502734 | 6.349% |  | 31245187 | 4.744% | 29969390 | 4.288% | 32551 | 7624 | 23.42% | 3699 | 11.36% | 251 | 0.7711% | 3949 | 12.13% | 36751 | 12.9% | 48567 | 46921 | 35598 | 9.361%
| District Let | 787460032 | 781630648 | 803952184 | 799735177 | 6790000 | 789108648 | 0.9567% |  | 15587915 | 1.994% | 16492150 | 2.062% | 30148 | 4800 | 15.92% | 3286 | 10.9% | 1098 | 3.642% | 2241 | 7.433% | 33487 | 11.08% | 41723 | 38526 | 30440 | 0.9686%
| All Contracts | 1452439761 | 1440311311 | 1498901304 | 1498595963 | 7260000 | 1489611382 | 3.423% |  | 46833102 | 3.252% | 46461540 | 3.1% | 62699 | 12424 | 19.82% | 6985 | 11.14% | 1349 | 2.152% | 6190 | 9.873% | 70238 | 12.02% | 90290 | 85447 | 66038 | 5.325%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 116.7% | 1 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 100.3% | 1 | 12243 | -8147 | 134 | 24 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88
| 01 | T1717 | 19801765201 | 2018-12-05 | QTR2 | 18/19 | 4 | 17 | 700 | 913 | 925 | 110.4% | 1 | -12 | 12 | 0 | 152 | 61 | 15860000 | 150000 | 15710000 | 16463364 | 16135347 | -90816 | -60000 | -150816 | 15984531 | 15920739 | 101.3% | 1 | -48363 | 603364 | 111 | 41 | 0 | 0 | 586377 | 3552 | 0 | 4 | 22688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101513 | 0 | 0 | 4 | 619221 | 3552 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2022-03-29 | QTR3 | 21/22 |  | 2021-10-08 | QTR2 | 21/22 | 115 | 15674640.54 | B10 | ACC - BONUS/INCENT/DISINCENT
| 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 84.71% | 1 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 96.23% | 1 | 0 | 8128 | 11 | 6 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21
| 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | 104.2% | 1 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | 100.2% | 1 | -35379 | -23800 | 78 | 28 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38003 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59
| 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 116.5% | 1 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 102.6% | 1 | 6923 | -17395 | 44 | 26 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 |  | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21
| 01 | T1757 | 43943615201 | 2020-07-29 | QTR1 | 20/21 | 3 | 4 | 200 | 261 | 260 | 113% | 1 | 1 | 0 | 0 | 34 | 27 | 2163088 | 50000 | 2113088 | 2182239 | 2172501 | 0 | 0 | 0 | 2172501 | 2181502 | 103.2% | 1 | 9002 | 19151 | 25 | 9 | 0 | 0 | 11573 | 0 | 0 | 27 | 103123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 43328 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 108 | 2199110.64 | B0 | ACC - LUMP SUM
| 01 | T1760 | 43943915201 | 2020-06-10 | QTR4 | 19/20 | 2 | 1 | 235 | 291 | 288 | 98.72% | 1 | 3 | 0 | 0 | 56 | 0 | 4964468 | 57276 | 4907192 | 4976639 | 5027641 | 0 | 0 | 0 | 5027641 | 5062613 | 103.2% | 1 | 34972 | 12171 | 47 | 9 | 0 | 0 | 13541 | 0 | 0 | 0 | 12171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30994 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 |  | 2021-10-18 | QTR2 | 21/22 | 108 | 5089189.35
| 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 97.74% | 1 | 0 | 0 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82
| 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 292 | 111.5% | 1 | 9 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | 106.8% | 1 | -1156 | 114901 | 43 | 26 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43
| 01 | T1775 | 44151915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 275 | 371 | 370 | 99.64% | 1 | 1 | 0 | 0 | 96 | 0 | 7746370 | 98021 | 7648349 | 7776109 | 7775281 | 0 | 0 | 0 | 7775281 | 7823279 | 102.3% | 1 | 47998 | 29739 | 73 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 |  | 2021-11-13 | QTR2 | 21/22 | 118 | 9281425.28
| 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 92.86% | 1 | 2188 | 0 | 27 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 |  | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43
| 01 | T1789 | 43693115201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 271 | 270 | 99.5% | 1 | 1 | 0 | 0 | 71 | 0 | 2359731 | 50000 | 2309731 | 2322360 | 2220739 | 0 | 0 | 0 | 2220739 | 2223174 | 96.25% | 1 | 2435 | -37371 | 55 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37371 | 0 | 0 | 0 | -36473 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-01-25 | QTR3 | 21/22 |  | 2021-08-26 | QTR1 | 21/22 | 113 | 2549900.36
| 01 | T1796 | 44050815201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 100 | 124 | 123 | 99% | 1 | 1 | 0 | 0 | 24 | 0 | 817957 | 38521 | 779436 | 986429 | 914986 | 0 | 0 | 0 | 914986 | 914986 | 117.4% | 0 | 0 | 168472 | 19 | 5 | 0 | 0 | 81012 | 0 | 0 | 0 | 87460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168472 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-07 | QTR3 | 21/22 |  | 2021-10-01 | QTR2 | 21/22 | 118 | 656746.29
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 13 | 22 | 39 | 3020 | 4132 | 4129 | 100% | 13 | 3 | 29 | 0 | 991 | 121 | 58321312 | 818572 | 57502740 | 59190525 | 58537541 | -173538 | -60000 | -233538 | 58304003 | 58319435 | 92.31% | 12 | 30863 | 869213 | 700 | 220 | 0 | 1 | 1048104 | 24154 | 1 | 63 | 308956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | -397893 | 0 | 0 | 0 | 17118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26139 | 0 | 71 | 64 | 1003691 | 24154
| 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 141.3% | 0 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 103.5% | 1 | 357 | 69031 | 29 | 20 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85
| 01 | E1P95 | 42838315201 | 2017-06-15 | QTR4 | 16/17 | 4 | 13 | 825 | 1189 | 1179 | 124.8% | 0 | 10 | 0 | 0 | 149 | 215 | 12611204 | 102103 | 12509101 | 13133768 | 12450757 | -35183 | -125000 | -160183 | 12290574 | 12343775 | 98.68% | 1 | 53201 | 522564 | 71 | 78 | 0 | 26 | 98702 | 3841 | 0 | 100 | 270614 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156514 | 0 | 0 | 0 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 567739 | 13064 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-15 | QTR3 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 115 | 10409514.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 127.9% | 0 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | 106.1% | 1 | -23194 | 2868754 | 166 | 60 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 |  | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 102.9% | 1 | 0 | 234222 | 11 | 6 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 |  | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33
| 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 97.5% | 1 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | 106.3% | 1 | -52866 | 180574 | 207 | 28 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 |  | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53
| 01 | E1S49 | 19602275201 | 2020-03-26 | QTR3 | 19/20 | 3 | 8 | 360 | 476 | 474 | 109.2% | 1 | 2 | 0 | 0 | 81 | 35 | 4765372 | 50000 | 4715372 | 5108479 | 5065730 | 0 | 0 | 0 | 5065730 | 5081869 | 107.8% | 1 | 16140 | 343107 | 55 | 26 | 0 | 35 | 331038 | 0 | 0 | 0 | 27910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 358948 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 |  | 2021-11-19 | QTR2 | 21/22 | 115 | 5214661.03
| 01 | E1S51 | 44002715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 1 | 80 | 152 | 191 | 182.5% | 0 | -39 | 39 | 0 | 45 | 27 | 407081 | 16632 | 390449 | 421138 | 368049 | -48399 | 0 | -48399 | 319650 | 319650 | 81.87% | 1 | 0 | 14057 | 26 | 19 | 0 | 27 | 14057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14057 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 |  | 2021-02-12 | QTR3 | 20/21 | 115 | 439357.58
| 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 92% | 1 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 104.8% | 1 | 596 | 98871 | 44 | 17 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 |  | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2
| 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | 97.68% | 1 | -5733 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85
| 01 | E1T46 | 44681615201 | 2020-07-23 | QTR1 | 20/21 | 1 | 1 | 400 | 449 | 449 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3083600 | 50000 | 3033600 | 3080211 | 3030211 | 0 | 0 | 0 | 3030211 | 3030211 | 99.89% | 1 | 0 | -3389 | 18 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 |  | 2021-12-20 | QTR2 | 21/22 | 106 | 4731071.94 | LBDB | LOW BID DESIGN BUILD
| 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 100% | 1 | 520 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1T68 | 43980115201 | 2020-12-03 | QTR2 | 20/21 | 1 | 1 | 75 | 106 | 178 | 209.3% | 0 | -72 | 72 | 0 | 21 | 10 | 180572 | 10362 | 170210 | 210394 | 199372 | -3750 | 0 | -3750 | 195621 | 195621 | 114.9% | 0 | 0 | 29822 | 18 | 3 | 0 | 10 | 29822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29822 | 0 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2022-01-21 | QTR3 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 108 | 260006.67
| 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 13 | 23 | 55 | 3766 | 5291 | 5362 | 61.54% | 8 | -71 | 111 | 0 | 1046 | 479 | 78098552 | 682004 | 77416548 | 82456166 | 80923448 | -87332 | -125000 | -212332 | 80711115 | 80594930 | 92.31% | 12 | -10979 | 4357613 | 677 | 318 | 51 | 204 | 3983842 | 37131 | 0 | 141 | 715772 | 138293 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338988 | 0 | 0 | 0 | -572124 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 353 | 4364596 | 175424
| District 01 Totals |  |  |  |  | 26 | 45 | 94 | 6786 | 9423 | 9491 | 80.77% | 21 | -68 | 140 | 0 | 2037 | 600 | 136419864 | 1500576 | 134919288 | 141646691 | 139460989 | -260870 | -185000 | -445870 | 139015118 | 138914365 | 92.31% | 24 | 19884 | 5226826 | 1377 | 538 | 51 | 205 | 5031946 | 61285 | 1 | 204 | 1024728 | 138293 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | -58905 | 0 | 0 | 0 | -555006 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 45 | 5 | 20102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26139 | 0 | 122 | 417 | 5368287 | 199578
| 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 106.7% | 1 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 108.4% | 1 | 593970 | 1812123 | 319 | 136 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1
| 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 122.1% | 0 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 109.7% | 1 | 337124 | 3379021 | 270 | 196 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71
| 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 120.9% | 0 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 107.3% | 1 | 1278355 | 2076018 | 139 | 86 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7
| 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 109.6% | 1 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | 103% | 1 | -48704 | 243564 | 155 | 52 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69
| 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | 215.7% | 0 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | 102.4% | 1 | -1358 | 52280 | 46 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1
| 02 | T2720 | 43735415201 | 2018-10-31 | QTR2 | 18/19 | 1 | 4 | 200 | 572 | 572 | 201% | 0 | 0 | 0 | 0 | 170 | 202 | 2468956 | 50000 | 2418956 | 2635619 | 2856937 | 0 | 0 | 0 | 2856937 | 2843130 | 117.5% | 0 | -13807 | 166663 | 95 | 75 | 0 | 42 | 7693 | 0 | 0 | 160 | 185011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 192704 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-03-29 | QTR3 | 20/21 | 214 | 2333570.34
| 02 | T2743 | 42845515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 4 | 750 | 857 | 857 | 94.67% | 1 | 0 | 0 | 0 | 147 | -40 | 12559204 | 120 | 12559084 | 13123013 | 13368899 | 0 | 0 | 0 | 13368899 | 13241202 | 105.4% | 1 | -127696 | 563809 | 108 | 39 | 0 | -30 | 143449 | 0 | 0 | 0 | 27147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904784 | 590741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -511572 | 0 | 0 | -40 | 563809 | 590741 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-10-27 | QTR2 | 21/22 | 208 | 13121490.39
| 02 | T2752 | 43395715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 400 | 548 | 485 | 85% | 1 | 63 | 0 | 0 | 145 | 3 | 6416755 | 63600 | 6353155 | 6416755 | 6306830 | 0 | 0 | 0 | 6306830 | 6314515 | 99.39% | 1 | 7685 | 0 | 111 | 34 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 209 | 6469876.4
| 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 77% | 1 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | 115.8% | 0 | -19174 | 475406 | 27 | 28 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1
| 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 100% | 1 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | 98.37% | 1 | -34064 | 0 | 32 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44
| 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | 132.5% | 0 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6136498 | 95.33% | 1 | -12015 | 124056 | 35 | 20 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49
| 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 119.6% | 1 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 87.38% | 1 | 0 | 87084 | 10 | 20 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705
| 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 62.5% | 1 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 99.16% | 1 | 752 | 0 | 38 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42
| 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 60.56% | 1 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 97.14% | 1 | 0 | -4773 | 3 | 23 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49
| 02 | T2773 | 43403815201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 350 | 408 | 389 | 94.57% | 1 | 19 | 0 | 0 | 58 | 0 | 3684895 | 58701 | 3626194 | 3684895 | 3598807 | 0 | 0 | 0 | 3598807 | 3601767 | 99.33% | 1 | 2960 | 0 | 19 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-08-05 | QTR1 | 21/22 | 214 | 3367569.01
| 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 98.67% | 1 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 99.41% | 1 | 338 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88
| 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 84% | 1 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 104% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46
| 02 | T2778 | 44105715201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 230 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 64 | 0 | 4660748 | 65000 | 4595748 | 4665808 | 4696793 | 0 | 0 | 0 | 4696793 | 4795119 | 104.3% | 1 | 98326 | 5059 | 51 | 13 | 0 | 0 | 12355 | 0 | 0 | 0 | 24208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36563 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-30 | QTR3 | 21/22 |  | 2021-12-06 | QTR2 | 21/22 | 216 | 4464709.06
| 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 65% | 1 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 99.22% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86
| 02 | T2781 | 44106015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 377 | 377 | 105.6% | 1 | 0 | 0 | 0 | 127 | 0 | 5821573 | 74375 | 5747198 | 5821573 | 5952158 | 0 | 0 | 0 | 5952158 | 5882048 | 102.3% | 1 | -70110 | 0 | 92 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-23 | QTR3 | 21/22 |  | 2021-10-27 | QTR2 | 21/22 | 214 | 7534069.47
| 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 72.4% | 1 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | 99.39% | 1 | -59022 | 0 | 28 | 20 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016
| 02 | T2799 | 43584515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 200 | 213 | 163 | 75% | 1 | 50 | 0 | 0 | 13 | 0 | 584000 | 47584 | 536416 | 584000 | 571789 | 0 | 0 | 0 | 571789 | 571826 | 106.6% | 1 | 37 | 0 | 2 | 11 | 0 | 0 | 2239 | 0 | 0 | 0 | 17521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20598 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-03-18 | QTR3 | 21/22 |  | 2021-09-24 | QTR1 | 21/22 | 208 | 883653.52
| 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 104.4% | 1 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 105.2% | 1 | 0 | 90092 | 12 | 17 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 23 | 33 | 73 | 8454 | 12266 | 11827 | 78.26% | 18 | 439 | 50 | 0 | 2712 | 1100 | 239678093 | 1305890 | 238372203 | 248748496 | 252387742 | -175272 | 0 | -175272 | 252212470 | 253738765 | 91.3% | 21 | 1933597 | 9070402 | 1603 | 981 | 4 | 555 | 5303021 | 109163 | 0 | 233 | 2217878 | 155965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 79719 | 40265 | 0 | 0 | 47286 | 27317 | 0 | 0 | 0 | 0 | 0 | 29 | 1312893 | 590741 | 0 | 59 | 0 | 0 | 0 | 90 | 526026 | 526026 | 14 | 0 | 0 | 0 | 0 | -10 | -584816 | 0 | 18 | 1087 | 8902010 | 1449478
| 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 68% | 1 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 94.97% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08
| 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 150.4% | 0 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 132.8% | 0 | 0 | 177395 | 58 | 34 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36
| 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 108% | 1 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | 108.1% | 1 | -1354420 | 997337 | 55 | 118 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 |  | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 145.7% | 0 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 215.1% | 0 | 0 | 1396122 | 103 | 32 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42
| 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 84% | 1 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 87.7% | 1 | 0 | -75888 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32
| 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 106.4% | 1 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | 107.7% | 1 | -94 | 50000 | 30 | 77 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21
| 02 | E2Y81 | 43197915201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 390 | 546 | 546 | 106.9% | 1 | 0 | 0 | 0 | 129 | 27 | 2424817 | 50000 | 2374817 | 2497783 | 2495432 | 0 | 0 | 0 | 2495432 | 2495432 | 105.1% | 1 | 0 | 72966 | 82 | 47 | 0 | 50 | 69881 | 69881 | 0 | -23 | 3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 72966 | 69881 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 |  | 2021-09-21 | QTR1 | 21/22 | 208 | 3472664.24
| 02 | E2Y84 | 43807515201 | 2019-11-13 | QTR2 | 19/20 | 3 | 1 | 160 | 223 | 223 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 1543447 | 50000 | 1493447 | 1543447 | 1581148 | 0 | 0 | 0 | 1581148 | 1565351 | 104.8% | 1 | -15797 | 0 | 54 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 |  | 2020-10-23 | QTR2 | 20/21 | 214 | 1817083.25
| 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 99.33% | 1 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | 98.28% | 1 | -1374 | 0 | 63 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78
| 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 98.33% | 1 | 0 | 0 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99
| 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 222.2% | 0 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 129.5% | 0 | 0 | 82407 | 16 | 20 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27
| 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 30.23% | 1 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 99.9% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7
| 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 62.58% | 1 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 105.3% | 1 | 0 | 49816 | 24 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86
| 02 | E2Z51 | 43384115201 | 2020-04-15 | QTR4 | 19/20 | 1 | 1 | 350 | 442 | 436 | 102% | 1 | 6 | 0 | 0 | 79 | 13 | 2662544 | 50000 | 2612544 | 2666491 | 1959926 | 0 | 0 | 0 | 1959926 | 1959926 | 75.02% | 1 | 0 | 3947 | 33 | 46 | 0 | 0 | 29210 | 0 | 0 | 0 | 3947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33157 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 |  | 2021-12-08 | QTR2 | 21/22 | 208 | 3385087.42
| 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 109.5% | 1 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 103.7% | 1 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03
| 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 99.07% | 1 | 0 | 0 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 16 | 21 | 25 | 4207 | 5810 | 5303 | 81.25% | 13 | 507 | 0 | 0 | 1283 | 320 | 40859639 | 817459 | 40042181 | 43613739 | 42906803 | 0 | 1350000 | 1350000 | 44256803 | 42880753 | 81.25% | 13 | -1371685 | 2754102 | 623 | 535 | 21 | 168 | 522716 | 286339 | 104 | 41 | 611523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492143 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29056 | 0 | 0 | 78 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | -75888 | 0 | 125 | 308 | 2996585 | 286339
| District 02 Totals |  |  |  |  | 39 | 54 | 98 | 12661 | 18076 | 17130 | 79.49% | 31 | 946 | 50 | 0 | 3995 | 1420 | 280537732 | 2123349 | 278414384 | 292362235 | 295294545 | -175272 | 1350000 | 1174728 | 296469273 | 296619518 | 87.18% | 34 | 561912 | 11824504 | 2226 | 1516 | 25 | 723 | 5825737 | 395502 | 104 | 274 | 2829401 | 155965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 571862 | 40265 | 0 | 0 | 64198 | 27317 | 0 | 0 | 0 | 0 | 0 | 29 | 1341949 | 590741 | 0 | 137 | 1400122 | 0 | 0 | 90 | 526026 | 526026 | 14 | 21 | 0 | 0 | 0 | -10 | -660704 | 0 | 143 | 1395 | 11898595 | 1735817
| 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 99.27% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 |  | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM
| 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 99.53% | 1 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 97.72% | 1 | 28314 | 256400 | 170 | 73 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000
| 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 66.67% | 1 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 101.2% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 |  | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91
| 03 | T3689 | 21876425201 | 2019-12-04 | QTR2 | 19/20 | 1 | 5 | 410 | 588 | 586 | 107.8% | 1 | 2 | 0 | 0 | 144 | 34 | 3948246 | 50000 | 3898246 | 4424349 | 4220133 | 0 | 0 | 0 | 4220133 | 4222745 | 108.3% | 1 | 2611 | 476103 | 106 | 38 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 |  | 2021-11-20 | QTR2 | 21/22 | 321 | 3709288.8
| 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 100.7% | 1 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | 104.7% | 1 | -86540 | 385593 | 320 | 100 | 0 | 3 | 71605 | 0 | 0 | 4 | 120253 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429398 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93
| 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 115.3% | 1 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | 98.95% | 1 | -2489 | -30187 | 126 | 44 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8
| 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 97.22% | 1 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 91.84% | 1 | 466 | 0 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24
| 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 101.3% | 1 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 104.2% | 1 | 247 | 27245 | 34 | 16 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46
| 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | 101.3% | 1 | -146878 | 58629 | 112 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83
| 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 102.7% | 1 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | 108.4% | 1 | -50153 | 204347 | 63 | 25 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85
| 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 107.8% | 1 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 101.2% | 1 | 1050 | 37203 | 43 | 34 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86
| 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | 101.9% | 1 | -53128 | 0 | 168 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9
| 03 | T3745 | 43972915201 | 2020-02-26 | QTR3 | 19/20 | 2 | 3 | 365 | 513 | 512 | 108.5% | 1 | 1 | 0 | 0 | 135 | 13 | 7352550 | 86750 | 7265800 | 7448821 | 7636800 | 0 | 0 | 0 | 7636800 | 7674029 | 105.6% | 1 | 37229 | 96271 | 76 | 40 | 0 | 13 | 91427 | 0 | 0 | 0 | 12701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 13 | 122618 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-16 | QTR3 | 21/22 |  | 2021-09-30 | QTR1 | 21/22 | 321 | 8840050.49
| 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 88% | 1 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 108.1% | 1 | 76040 | 0 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13
| 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 90 | 174 | 176 | 110% | 1 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 755462 | 668670 | 0 | 0 | 0 | 668670 | 668670 | 93.29% | 1 | 0 | 0 | 39 | 38 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5200 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-12 | QTR2 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61
| 03 | T3751 | 43775325201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 335 | 445 | 445 | 100% | 1 | 0 | 0 | 0 | 110 | 0 | 2569909 | 50000 | 2519909 | 2569909 | 2490758 | 0 | 0 | 0 | 2490758 | 2498656 | 99.16% | 1 | 7898 | 0 | 82 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 313 | 2572447.1
| 03 | T3763 | 43661515201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 365 | 435 | 433 | 99.45% | 1 | 2 | 0 | 0 | 70 | 0 | 4894168 | 0 | 4894168 | 4903128 | 5058997 | 0 | 0 | 0 | 5058997 | 5067842 | 103.5% | 1 | 8845 | 8960 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2022-01-18 | QTR3 | 21/22 |  | 2021-11-01 | QTR2 | 21/22 | 321 | 5019527.85
| 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 88% | 1 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 102.2% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 |  | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 18 | 28 | 40 | 4520 | 6724 | 6630 | 100% | 18 | 94 | 2 | 0 | 2105 | 99 | 73028044 | 867559 | 72160488 | 74548608 | 74433149 | -24500 | 0 | -24500 | 74408649 | 74165056 | 100% | 18 | -176488 | 1520564 | 1467 | 565 | 17 | 28 | 202394 | 0 | 35 | 63 | 855111 | 90285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 237488 | 0 | 2 | 1 | 206446 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 84780 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 99 | 1586220 | 90285
| 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | 208.7% | 0 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 91.39% | 1 | 0 | 49116 | 256 | 90 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 159.3% | 0 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 100% | 1 | 0 | 0 | 213 | 23 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 |  | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049
| 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 52.67% | 1 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | 0% | 1 | -174645 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33
| 03 | E3T18 | 42282325201 | 2020-12-17 | QTR2 | 20/21 | 1 | 0 | 45 | 46 | 32 | 68.89% | 1 | 14 | 0 | 0 | 1 | 0 | 145277 | 9380 | 135897 | 145277 | 129137 | 0 | 0 | 0 | 129137 | 129137 | 95.03% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-01-05 | QTR3 | 21/22 |  | 2021-04-23 | QTR4 | 20/21 | 321 | 213559.46
| 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 101.7% | 1 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | 105.3% | 1 | -2525 | 0 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39
| 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 51.67% | 1 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 99.94% | 1 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79
| 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 114.4% | 1 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | 101.6% | 1 | -25000 | 92806 | 26 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 253.3% | 0 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 104.6% | 1 | 0 | 14821 | 35 | 42 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 |  | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45
| 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 85.56% | 1 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | 0% | 1 | -225968 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-10-20 | QTR2 | 20/21 | 314 | 246220
| 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 148.9% | 0 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | 0% | 1 | -1338192 | 582769 | 17 | 11 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1
| 03 | E3U27 | 44154515201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 222 | 221 | 99.44% | 1 | 1 | 0 | 0 | 42 | 0 | 1641103 | 50000 | 1591103 | 1641103 | 1553101 | 0 | 0 | 0 | 1553101 | 1614039 | 101.4% | 1 | 60937 | 0 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2022-03-07 | QTR3 | 21/22 |  | 2021-11-01 | QTR2 | 21/22 | 321 | 2039669.94
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 11 | 18 | 13 | 1565 | 2954 | 2926 | 63.64% | 7 | 28 | 160 | 0 | 1227 | 162 | 14963682 | 331558 | 14632124 | 15703193 | 15402098 | -449760 | 25000 | -424760 | 14977338 | 13250684 | 100% | 11 | -1705393 | 739512 | 624 | 224 | 365 | 71 | 0 | 0 | 5 | 0 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 107627 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 150 | 698640 | 0
| District 03 Totals |  |  |  |  | 29 | 46 | 53 | 6085 | 9678 | 9556 | 86.21% | 25 | 122 | 162 | 0 | 3332 | 261 | 87991726 | 1199117 | 86792612 | 90251801 | 89835247 | -474260 | 25000 | -449260 | 89385987 | 87415740 | 100% | 29 | -1881881 | 2260076 | 2091 | 789 | 382 | 99 | 202394 | 0 | 40 | 63 | 863355 | 90285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22 | 345115 | 0 | 2 | 19 | 206446 | 0 | 0 | 0 | 0 | 0 | 6 | 46 | 667549 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 249 | 2284860 | 90285
| 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 154.1% | 0 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | 104.3% | 1 | -5522 | 345672 | 158 | 48 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 0 | 0 | -46629 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32
| 04 | T4476 | 43515815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 4 | 582 | 825 | 825 | 110.3% | 1 | 0 | 0 | 0 | 183 | 60 | 7524128 | 71928 | 7452200 | 7782657 | 7606665 | 0 | 0 | 0 | 7606665 | 7546955 | 101.3% | 1 | -47141 | 258528 | 91 | 92 | 0 | 0 | 12809 | 0 | 0 | 0 | 107865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34366 | 34366 | 0 | 60 | 107988 | 107988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 263028 | 142354 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 |  | 2021-01-18 | QTR3 | 20/21 | 409 | 7189789.75
| 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | 110% | 1 | -79 | 50449 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52
| 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 103.4% | 1 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | 103.1% | 1 | -41100 | 238143 | 56 | 38 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83
| 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 120% | 1 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | 121.4% | 0 | -38478 | 1701896 | 99 | 57 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34
| 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 104.1% | 1 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | 108.7% | 1 | -136647 | 836144 | 110 | 44 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29
| 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 101.4% | 1 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | 96.13% | 1 | -58724 | -97855 | 61 | 33 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17
| 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 99.49% | 1 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | 104.1% | 1 | -17714 | 162310 | 92 | 33 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17
| 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 72.21% | 1 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | 92.16% | 1 | -17236 | -58454 | 82 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 |  | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2
| 04 | T4521 | 43760515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 160 | 246 | 244 | 114.4% | 1 | 2 | 0 | 0 | 86 | 0 | 737736 | 38647 | 699089 | 737736 | 679527 | 0 | 0 | 0 | 679527 | 679527 | 97.2% | 1 | 0 | 0 | 47 | 14 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 |  | 2021-12-22 | QTR2 | 21/22 | 412 | 798445.57
| 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 102.5% | 1 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | 97.23% | 1 | -108218 | 74017 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95
| 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 90.84% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3
| 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 96.65% | 1 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | 100.6% | 1 | -30966 | 39603 | 54 | 27 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03
| 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 103.5% | 1 | 250 | 0 | 81 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89
| 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66.83% | 1 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 98.35% | 1 | 237 | 0 | 25 | 18 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94
| 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 75.77% | 1 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 96.14% | 1 | 93 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46
| 04 | T4555 | 43990915201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 128 | 152 | 148 | 96.88% | 1 | 4 | 0 | 0 | 24 | 0 | 441982 | 24322 | 417660 | 441982 | 407189 | 0 | 0 | 0 | 407189 | 407189 | 97.49% | 1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-10-06 | QTR2 | 21/22 | 412 | 501234.56
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 17 | 30 | 52 | 5580 | 7649 | 7345 | 94.12% | 16 | 304 | 0 | 0 | 1649 | 420 | 64036173 | 841716 | 63194457 | 67586628 | 66183454 | -68940 | 0 | -68940 | 66114514 | 65561229 | 94.12% | 16 | -501245 | 3550453 | 1108 | 492 | 0 | 117 | 2510329 | 1339455 | 31 | 56 | 968564 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 114714 | 0 | 0 | 6 | 86505 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 110898 | 82669 | 18 | 116 | 196745 | 190656 | 0 | 0 | 0 | 0 | 0 | 0 | -146170 | 0 | 49 | 305 | 3821096 | 1751041
| 04 | E4T83 | 42268145201 | 2020-05-01 | QTR4 | 19/20 | 1 | 0 | 240 | 375 | 375 | 107.9% | 1 | 0 | 0 | 0 | 116 | 19 | 2027817 | 50000 | 1977817 | 2027817 | 1963518 | 0 | 0 | 0 | 1963518 | 1968273 | 99.52% | 1 | 4756 | 0 | 91 | 25 | 0 | 0 | 14875 | 0 | 0 | 19 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 40339 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2022-01-27 | QTR3 | 21/22 |  | 2021-09-01 | QTR1 | 21/22 | 408 | 2656948.48
| 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 100.7% | 1 | 95 | -399 | 22 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08
| 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 110.9% | 1 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | 88.88% | 1 | -95454 | 15486 | 15 | 5 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 |  | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | E4U72 | 44162915201 | 2021-01-08 | QTR3 | 20/21 | 1 | 0 | 144 | 178 | 178 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 893625 | 50000 | 843625 | 893625 | 846410 | 0 | 0 | 0 | 846410 | 849948 | 100.7% | 1 | 3538 | 0 | 25 | 9 | 0 | 0 | 5931 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26097 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 |  | 2021-09-19 | QTR1 | 21/22 | 412 | 1052584.82
| 04 | E4U74 | 44162815201 | 2021-03-05 | QTR3 | 20/21 | 3 | 1 | 153 | 186 | 183 | 98.04% | 1 | 3 | 0 | 0 | 33 | 0 | 1190833 | 50000 | 1140833 | 1189722 | 1098149 | 0 | 0 | 0 | 1098149 | 1101304 | 96.54% | 1 | 3155 | -1111 | 12 | 21 | 0 | 0 | -1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1111 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-25 | QTR3 | 21/22 |  | 2022-01-17 | QTR3 | 21/22 | 412 | 1310702.75
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 5 | 9 | 3 | 910 | 1190 | 1187 | 100% | 5 | 3 | 0 | 0 | 247 | 33 | 6504409 | 250000 | 6254409 | 6518385 | 6080609 | 0 | 100000 | 100000 | 6180609 | 6096698 | 100% | 5 | -83910 | 13976 | 165 | 82 | 0 | 0 | 25422 | 0 | 0 | 33 | 81465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 114636 | 0
| District 04 Totals |  |  |  |  | 22 | 39 | 55 | 6490 | 8839 | 8532 | 95.45% | 21 | 307 | 0 | 0 | 1896 | 453 | 70540582 | 1091716 | 69448866 | 74105013 | 72264063 | -68940 | 100000 | 31060 | 72295123 | 71657927 | 95.45% | 21 | -585155 | 3564429 | 1273 | 574 | 0 | 117 | 2535751 | 1339455 | 31 | 89 | 1050029 | 112620 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 122462 | 0 | 0 | 6 | 86505 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 110898 | 82669 | 18 | 116 | 196745 | 190656 | 0 | 0 | 0 | 0 | 0 | 0 | -146170 | 0 | 49 | 338 | 3935732 | 1751041
| 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 113.9% | 1 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 105.7% | 1 | 430838 | 374749 | 219 | 102 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3
| 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 137.8% | 0 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 104% | 1 | 328547 | 8369 | 210 | 62 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22
| 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 96.77% | 1 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | 103% | 1 | -222563 | -4 | 112 | 57 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38
| 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 347.9% | 0 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | 219.7% | 0 | -16169 | 3253176 | 23 | 51 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320
| 05 | T5668 | 43968235201 | 2019-05-22 | QTR4 | 18/19 | 4 | 11 | 510 | 788 | 778 | 128.4% | 0 | 10 | 0 | 0 | 123 | 155 | 20003719 | 154151 | 19849568 | 23051817 | 24148539 | 0 | 0 | 0 | 24148539 | 24037958 | 121.1% | 0 | -110580 | 3048098 | 58 | 65 | 0 | 155 | 2206932 | 2589 | 0 | 0 | 818285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91658 | 0 | 0 | 0 | 52092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 3168966 | 2589 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-04 | QTR3 | 21/22 |  | 2021-10-21 | QTR2 | 21/22 | 507 | 16312265.29
| 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 134.8% | 0 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | 101.4% | 1 | -48503 | 72336 | 18 | 22 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68
| 05 | T5670 | 43020245201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 260 | 396 | 395 | 109.2% | 1 | 1 | 0 | 0 | 116 | 20 | 2204501 | 50000 | 2154501 | 2284647 | 2359499 | 0 | 0 | 0 | 2359499 | 2362734 | 109.7% | 1 | 13475 | 80146 | 76 | 35 | 0 | 0 | 4980 | 0 | 5 | 20 | 70131 | 7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 77386 | 7656 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-01-12 | QTR3 | 21/22 |  | 2020-08-11 | QTR1 | 20/21 | 514 | 1667431.38
| 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 150% | 0 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | 105.3% | 1 | -28879 | 22908 | 74 | 22 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 |  | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09
| 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 106.8% | 1 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | 96.78% | 1 | -191521 | 85887 | 113 | 94 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87
| 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 89.33% | 1 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | 97.46% | 1 | -39533 | 3360 | 113 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7
| 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 86.92% | 1 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 99.25% | 1 | 35505 | 0 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04
| 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 99.23% | 1 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 100.2% | 1 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25
| 05 | T5710 | 44136615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 86 | 128 | 128 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 614736 | 29870 | 584866 | 614736 | 554534 | 0 | 0 | 0 | 554534 | 554534 | 94.81% | 1 | 0 | 0 | 38 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 |  | 2021-11-09 | QTR2 | 21/22 | 512 | 624301.96
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 13 | 28 | 46 | 4235 | 7083 | 6967 | 61.54% | 8 | 116 | 0 | 0 | 1682 | 1166 | 110266399 | 1156854 | 109109545 | 117215424 | 119502886 | -7304 | 0 | -7304 | 119495582 | 119588711 | 84.62% | 11 | 151466 | 6949025 | 1078 | 599 | 0 | 279 | 2594525 | 21983 | 5 | 805 | 4433440 | 13955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154370 | 0 | 0 | 16 | 102571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1100 | 7451573 | 42388
| 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 107.2% | 1 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 102.7% | 1 | 0 | 30409 | 84 | 17 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5
| 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 101.1% | 1 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 102.8% | 1 | 0 | 0 | 13 | 6 | 0 | 0 | 7876 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7
| 05 | E52A2 | 44316815201 | 2020-10-06 | QTR2 | 20/21 | 2 | 1 | 220 | 274 | 276 | 100.9% | 1 | -2 | 2 | 0 | 54 | 0 | 7726425 | 101900 | 7624525 | 7711640 | 7780592 | 0 | 0 | 0 | 7780592 | 7870977 | 103.2% | 1 | 90385 | -14785 | 29 | 25 | 0 | 0 | -17404 | 0 | 0 | 0 | 2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7315 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2021-10-06 | QTR2 | 21/22 | 513 | 10078671.13
| 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 81.25% | 1 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 92.06% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 507 | 309304
| 05 | E53A6 | 44119715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 0 | 70 | 109 | 109 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 320193 | 13925 | 306268 | 320193 | 308143 | 0 | 0 | 0 | 308143 | 308143 | 100.6% | 1 | 0 | 0 | 24 | 15 | 0 | 0 | 12247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12247 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-12-02 | QTR2 | 21/22 | 507 | 289415.18
| 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 117.1% | 1 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 102.1% | 1 | 0 | 0 | 7 | 5 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03
| 05 | E54A0 | 44208815201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 190 | 190 | 115.7% | 1 | 0 | 0 | 0 | 109 | 11 | 524491 | 26260 | 498231 | 524491 | 485346 | 0 | 0 | 0 | 485346 | 485346 | 97.41% | 1 | 0 | 0 | 85 | 24 | 0 | 0 | 362 | 0 | 0 | 0 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2022-01-06 | QTR3 | 21/22 | 507 | 529396.72
| 05 | E54A2 | 44589615201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 140 | 158 | 144 | 90% | 1 | 14 | 0 | 0 | 18 | 0 | 553370 | 29890 | 523480 | 553370 | 525670 | 0 | 0 | 0 | 525670 | 525670 | 100.4% | 1 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-01-10 | QTR3 | 21/22 |  | 2021-10-07 | QTR2 | 21/22 | 514 | 622693
| 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 31% | 1 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 98.44% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5
| 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 106.7% | 1 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 103.1% | 1 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7
| 05 | E5Z71 | 43179835201 | 2019-05-07 | QTR4 | 18/19 | 2 | 7 | 570 | 816 | 816 | 118.6% | 1 | 0 | 0 | 0 | 140 | 106 | 16210000 | 247420 | 15962580 | 17216871 | 17023277 | 0 | 0 | 0 | 17023277 | 16917166 | 106% | 1 | -106111 | 1006871 | 91 | 49 | 0 | 0 | 767888 | 17768 | 0 | 90 | 237203 | 30782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168783 | 0 | 0 | 16 | 14196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1188071 | 48550 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-12-16 | QTR2 | 21/22 | 512 | 17297949.45
| 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | 110% | 1 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | 101.7% | 1 | -20779 | 70000 | 38 | 56 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19
| 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 99.5% | 1 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | 99.98% | 1 | -5035 | 2982 | 41 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55
| 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 106.5% | 1 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 107.6% | 1 | 0 | 42878 | 52 | 20 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS
| 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | 105.3% | 1 | -795 | 0 | 72 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 15 | 18 | 14 | 2670 | 3803 | 3702 | 100% | 15 | 101 | 3 | 0 | 941 | 192 | 43281836 | 802377 | 42479459 | 44420191 | 44252030 | 0 | 0 | 0 | 44252030 | 44206713 | 100% | 15 | -42335 | 1138355 | 553 | 388 | 0 | 41 | 968190 | 17768 | 0 | 119 | 288246 | 89437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193054 | 0 | 0 | 16 | 14560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1512578 | 107205
| District 05 Totals |  |  |  |  | 28 | 46 | 60 | 6905 | 10886 | 10669 | 82.14% | 23 | 217 | 3 | 0 | 2623 | 1358 | 153548235 | 1959231 | 151589004 | 161635615 | 163754916 | -7304 | 0 | -7304 | 163747612 | 163795424 | 92.86% | 26 | 109131 | 8087380 | 1631 | 987 | 0 | 320 | 3562715 | 39751 | 5 | 924 | 4721686 | 103392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347424 | 0 | 0 | 32 | 117131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60988 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1276 | 8964151 | 149593
| 06 | T6460 | 43081745201 | 2020-04-29 | QTR4 | 19/20 | 5 | 2 | 380 | 473 | 417 | 85.26% | 1 | 56 | 0 | 0 | 93 | 0 | 9621172 | 109381 | 9511791 | 9721667 | 9784724 | 0 | 580000 | 580000 | 10364724 | 9769960 | 102.7% | 1 | -594765 | 100495 | 78 | 15 | 0 | 0 | 19509 | 0 | 0 | 0 | 137279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160626 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-02 | QTR3 | 21/22 |  | 2021-08-26 | QTR1 | 21/22 | 613 | 9993234.21 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 78.39% | 1 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | 101.8% | 1 | -195345 | 68789 | 27 | 20 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6469 | 42930045201 | 2019-09-25 | QTR1 | 19/20 | 2 | 4 | 350 | 410 | 330 | 77.14% | 1 | 80 | 0 | 0 | 60 | 0 | 5172452 | 51320 | 5121132 | 5372452 | 5225454 | 0 | 220000 | 220000 | 5445454 | 5222651 | 102% | 1 | -222802 | 200000 | 43 | 17 | 0 | 0 | 38506 | 0 | 0 | 0 | 32542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134496 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212915 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-06 | QTR3 | 21/22 |  | 2021-05-21 | QTR4 | 20/21 | 613 | 4540257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 99.5% | 1 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | 98.87% | 1 | -98 | 0 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85
| 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 86.86% | 1 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | 98.61% | 1 | -113588 | 38150 | 11 | 23 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 85.71% | 1 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 93.34% | 1 | 39 | 0 | 42 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5
| 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 103.3% | 1 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | 101.4% | 1 | -2 | 32516 | 132 | 50 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 |  | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3
| 06 | T6483 | 44016915201 | 2019-09-25 | QTR1 | 19/20 | 3 | 4 | 260 | 436 | 436 | 117.3% | 1 | 0 | 0 | 0 | 176 | 0 | 1399991 | 50000 | 1349991 | 1461545 | 1445555 | 0 | 0 | 0 | 1445555 | 1445977 | 107.1% | 1 | 421 | 61554 | 99 | 32 | 0 | 0 | 1094 | 0 | 0 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 27009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 65528 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-12-17 | QTR2 | 21/22 | 613 | 1299243.3
| 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 99.64% | 1 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | 85.44% | 1 | -106 | -50049 | 54 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2
| 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | 98.18% | 1 | -1169 | 0 | 36 | 18 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2
| 06 | T6502 | 44385315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 184 | 155 | 80.67% | 1 | 29 | 0 | 0 | 34 | 0 | 619555 | 32981 | 586574 | 619555 | 571295 | 0 | 0 | 0 | 571295 | 572454 | 97.59% | 1 | 1159 | 0 | 31 | 3 | 0 | 0 | 2890 | 0 | 0 | 0 | 2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5408 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-02-14 | QTR3 | 21/22 |  | 2021-12-13 | QTR2 | 21/22 | 613 | 681973.35
| 06 | T6507 | 43991815201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 239 | 269 | 229 | 83.26% | 1 | 40 | 0 | 0 | 30 | 0 | 1536743 | 50000 | 1486743 | 1536743 | 1501598 | 0 | 100000 | 100000 | 1601598 | 1507472 | 101.4% | 1 | -94126 | 0 | 17 | 13 | 0 | 0 | 7665 | 0 | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18247 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-01-13 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 636 | 1644818.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 76.43% | 1 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 95.14% | 1 | 1 | 0 | 19 | 5 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 636 | 359443
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 13 | 40 | 18 | 3219 | 4175 | 3802 | 100% | 13 | 373 | 0 | 0 | 956 | 0 | 32227560 | 615673 | 31611887 | 32679015 | 31667195 | 0 | 1200000 | 1200000 | 32867195 | 31646817 | 100% | 13 | -1220381 | 451455 | 614 | 264 | 8 | 0 | 106194 | 0 | 0 | 0 | 253467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 374632 | 0 | 0 | 0 | 22477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 78 | 0 | 643504 | 0
| 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 97.57% | 1 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 132.6% | 0 | 530 | 1114997 | 29 | 34 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57170 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05
| 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 106.7% | 1 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 103.5% | 1 | 0 | 110603 | 110 | 22 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689
| 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 75.3% | 1 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | 101.6% | 1 | -991000 | 1610952 | 139 | 172 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 |  | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 119.2% | 1 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | 0% | 1 | -3778569 | 105786 | 32 | 57 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 95.42% | 1 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 103.7% | 1 | 0 | 0 | 51 | 6 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25
| 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 58.73% | 1 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 30.46% | 1 | 0 | -3198332 | 6 | 25 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 76.67% | 1 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 100.2% | 1 | 168 | 0 | 72 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 |  | 2021-09-07 | QTR1 | 21/22 | 613 | 615217
| 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 100.9% | 1 | 0 | 33224 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5
| 06 | E6N05 | 44188615201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 180 | 351 | 292 | 67.22% | 1 | 59 | 0 | 0 | 171 | 0 | 660660 | 31668 | 628992 | 660660 | 634309 | 0 | 0 | 0 | 634309 | 634835 | 100.9% | 1 | 526 | 0 | 158 | 13 | 0 | 0 | 4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25892 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-01-28 | QTR3 | 21/22 |  | 2021-12-10 | QTR2 | 21/22 | 613 | 655036.75
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 9 | 14 | 30 | 3820 | 4889 | 4237 | 100% | 9 | 652 | 0 | 0 | 1040 | 29 | 118541240 | 607741 | 117933499 | 118318469 | 120991524 | 0 | 1320000 | 1320000 | 122311524 | 116926423 | 88.89% | 8 | -4768345 | -222770 | 615 | 341 | 37 | 11 | -1667033 | 239375 | 0 | 0 | 249328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 18 | 1000378 | 0 | 0 | 0 | 304279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -558514 | 0 | 68 | 29 | -671561 | 239375
| District 06 Totals |  |  |  |  | 22 | 54 | 48 | 7039 | 9064 | 8039 | 100% | 22 | 1025 | 0 | 0 | 1996 | 29 | 150768800 | 1223414 | 149545386 | 150997484 | 152658719 | 0 | 2520000 | 2520000 | 155178719 | 148573240 | 95.45% | 21 | -5988726 | 228685 | 1229 | 605 | 45 | 11 | -1560839 | 239375 | 0 | 0 | 502795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 18 | 1375010 | 0 | 0 | 0 | 326756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -679563 | 0 | 146 | 29 | -28057 | 239375
| 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 126% | 0 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 123.6% | 0 | 248412 | 1919528 | 100 | 56 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000
| 07 | T7386 | 43002115201 | 2016-06-15 | QTR4 | 15/16 | 3 | 7 | 310 | 812 | 1136 | 310% | 0 | -324 | 324 | 0 | 175 | 327 | 6015645 | 88863 | 5926782 | 7425942 | 7629019 | 0 | 0 | 0 | 7629019 | 7799558 | 131.6% | 0 | 197466 | 1410297 | 132 | 43 | 0 | 318 | 1457786 | 195935 | 0 | 6 | 154100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1323906 | 195935 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2020-01-21 | QTR3 | 19/20 | 798 | 6465450.53 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7410 | 43649515201 | 2018-05-23 | QTR4 | 17/18 | 5 | 5 | 565 | 971 | 970 | 119.3% | 1 | 1 | 0 | 0 | 296 | 110 | 10099029 | 287408 | 9811621 | 12396490 | 12392490 | 0 | 0 | 0 | 12392490 | 12349457 | 125.9% | 0 | -43033 | 2297460 | 224 | 72 | 0 | 40 | 1272584 | 0 | 0 | 70 | 1132140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2418085 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-06-29 | QTR4 | 20/21 | 796 | 9905226.59
| 07 | T7437 | 43605615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 2 | 268 | 298 | 285 | 95.15% | 1 | 13 | 0 | 0 | 30 | 0 | 1903823 | 50000 | 1853823 | 2069815 | 2004923 | 0 | 0 | 0 | 2004923 | 2005258 | 108.2% | 1 | 335 | 165992 | 13 | 17 | 0 | 0 | 299339 | 0 | 0 | 0 | -122480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8337 | 0 | 0 | 0 | 168522 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 799 | 1500000
| 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | 101.1% | 1 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | 90.58% | 1 | -7946 | 0 | 46 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000
| 07 | T7450 | 43764015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 300 | 356 | 352 | 98.67% | 1 | 4 | 0 | 0 | 56 | 0 | 3698894 | 50000 | 3648894 | 3698894 | 3783529 | 0 | 0 | 0 | 3783529 | 3798642 | 104.1% | 1 | 15112 | 0 | 19 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-11 | QTR3 | 21/22 |  | 2021-10-15 | QTR2 | 21/22 | 796 | 2945400
| 07 | T7455 | 44140315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 0 | 225 | 256 | 246 | 95.56% | 1 | 10 | 0 | 0 | 31 | 0 | 9710187 | 140000 | 9570187 | 9710187 | 10168330 | 0 | 0 | 0 | 10168330 | 10201078 | 106.6% | 1 | 32748 | 0 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 796 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 95% | 1 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 95.04% | 1 | 0 | 0 | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 8 | 19 | 27 | 2669 | 4118 | 4411 | 75% | 6 | -293 | 327 | 0 | 851 | 598 | 50669253 | 897371 | 49771882 | 56462531 | 57168255 | -7737 | 0 | -7737 | 57160518 | 57558216 | 62.5% | 5 | 443094 | 5793277 | 581 | 270 | 0 | 409 | 3815691 | 218372 | 0 | 186 | 2095188 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287382 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8337 | 0 | 0 | 598 | 5901945 | 601515
| 07 | E7M61 | 43951615201 | 2019-07-10 | QTR1 | 19/20 | 2 | 0 | 430 | 707 | 698 | 97.91% | 1 | 9 | 0 | 0 | 277 | 0 | 3417860 | 50000 | 3367860 | 3417860 | 3733589 | 0 | 0 | 0 | 3733589 | 3733589 | 110.9% | 0 | 0 | 0 | 239 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-12-03 | QTR2 | 21/22 | 799 | 4777765.05
| 07 | E7M81 | 44335315201 | 2019-10-09 | QTR2 | 19/20 | 1 | 1 | 143 | 516 | 516 | 285.3% | 0 | 0 | 0 | 0 | 180 | 193 | 385385 | 7500 | 377885 | 398672 | 364686 | 0 | 0 | 0 | 364686 | 364686 | 96.51% | 1 | 0 | 13287 | 64 | 44 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-02-21 | QTR3 | 21/22 |  | 2021-11-17 | QTR2 | 21/22 | 799 | 300000
| 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 84.38% | 1 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 99.31% | 1 | 552 | 0 | 23 | 28 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27
| 07 | E7M93 | 44383215201 | 2020-02-12 | QTR3 | 19/20 | 1 | 2 | 550 | 601 | 524 | 86% | 1 | 77 | 0 | 0 | 51 | 0 | 1260367 | 20000 | 1240367 | 1319899 | 1294928 | 0 | 0 | 0 | 1294928 | 1294928 | 104.4% | 1 | 0 | 59531 | 4 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5962 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 |  | 2022-01-11 | QTR3 | 21/22 | 796 | 1500000
| 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 101.1% | 1 | 0 | 0 | 33 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000
| 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 124.7% | 0 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | 98.85% | 1 | -57396 | 31514 | 24 | 30 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 |  | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300
| 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 72.14% | 1 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 109.2% | 1 | 0 | 49500 | 4 | 15 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7
| 07 | E7N15 | 44539915201 | 2020-02-12 | QTR3 | 19/20 | 1 | 4 | 120 | 160 | 160 | 117.5% | 1 | 0 | 0 | 0 | 19 | 21 | 3408000 | 20000 | 3388000 | 3546613 | 3532479 | 0 | 0 | 0 | 3532479 | 3532479 | 104.3% | 1 | 0 | 138613 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-06-23 | QTR4 | 20/21 | 799 | 2952724 | B0 | ACC - LUMP SUM
| 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 91.43% | 1 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 100.8% | 1 | 470 | 0 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-08-15 | QTR1 | 21/22 | 796 | 685000
| 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 90% | 1 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 100.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 796 | 485498
| 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 65.14% | 1 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | 100.8% | 1 | -35622 | 0 | 62 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64
| 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 98.24% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 796 | 127700
| 07 | E7R13 | 44111115201 | 2019-01-10 | QTR3 | 18/19 | 1 | 10 | 520 | 614 | 614 | 100% | 1 | 0 | 0 | 0 | 94 | 0 | 30854000 | 150000 | 30704000 | 31355440 | 31288898 | -20000 | 1275000 | 1255000 | 32543898 | 31200893 | 101.6% | 1 | -1343005 | 501440 | 69 | 25 | 0 | 0 | 17636 | 0 | 0 | 0 | 225879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289031 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -167178 | 0 | 0 | 0 | 412383 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2022-03-16 | QTR3 | 21/22 |  | 2020-11-09 | QTR2 | 20/21 | 714 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 109.6% | 1 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | 107.1% | 1 | -41787 | 386330 | 30 | 49 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 106.7% | 1 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 103.7% | 1 | 1729 | 43458 | 9 | 15 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 15 | 17 | 25 | 3466 | 4831 | 4570 | 86.67% | 13 | 261 | 0 | 0 | 1071 | 294 | 57659883 | 631736 | 57028147 | 58883558 | 58700702 | -20000 | 1275000 | 1255000 | 59955702 | 58480642 | 93.33% | 14 | -1475059 | 1223673 | 594 | 373 | 21 | 14 | 107895 | 0 | 160 | 193 | 747960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 298722 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -167178 | 0 | 181 | 217 | 1079413 | 16552
| District 07 Totals |  |  |  |  | 23 | 36 | 52 | 6135 | 8949 | 8981 | 82.61% | 19 | -32 | 327 | 0 | 1922 | 892 | 108329136 | 1529107 | 106800029 | 115346089 | 115868957 | -27737 | 1275000 | 1247263 | 117116220 | 116038858 | 82.61% | 19 | -1031965 | 7016950 | 1175 | 643 | 21 | 423 | 3923586 | 218372 | 160 | 379 | 2843148 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 586104 | 0 | 0 | 3 | 65178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -261143 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175515 | 0 | 181 | 815 | 6981358 | 618067
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 184.9% | 0 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | 98.49% | 1 | -1443556 | 402730 | 70 | 122 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -172782 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 87.8% | 1 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 105.7% | 1 | 2298953 | 4629463 | 130 | 104 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -433401 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 |  | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS
| 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 102.1% | 1 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | 102.9% | 1 | -71870 | 128744 | 80 | 36 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71
| 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 100% | 1 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | 95.54% | 1 | -25916 | -284543 | 188 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4
| 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 75.97% | 1 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | 74.35% | 1 | -1807 | 442902 | 15 | 45 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51
| 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 90.11% | 1 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | 101.3% | 1 | -6647 | 20210 | 13 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25
| 08 | E8S11 | 44029115201 | 2020-04-14 | QTR4 | 19/20 | 3 | 3 | 286 | 425 | 425 | 100% | 1 | 0 | 0 | 0 | 139 | 0 | 12956998 | 147809 | 12809189 | 13107980 | 13212168 | -6500 | 0 | -6500 | 13205668 | 13166473 | 102.8% | 1 | -39196 | 150982 | 73 | 66 | 0 | 0 | 10213 | 0 | 0 | 0 | 213463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234161 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-02-17 | QTR3 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 854 | 14597378.87
| 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 96.58% | 1 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | 99.91% | 1 | -41583 | 18865 | 18 | 25 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81
| 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 95.08% | 1 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 99.77% | 1 | 0 | 1980 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23
| 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 70.42% | 1 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 91.69% | 1 | 0 | 0 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75
| 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 101.3% | 1 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 91.92% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 11 | 21 | 71 | 5797 | 8008 | 7525 | 90.91% | 10 | 483 | 0 | 0 | 1150 | 1061 | 318680546 | 1113116 | 317567433 | 324191882 | 323313461 | -67500 | 1200000 | 1132500 | 324445961 | 324531147 | 100% | 11 | 668378 | 5511333 | 646 | 504 | 0 | 10 | 2110720 | 1278827 | 0 | 5 | 190343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1918637 | 24202 | 0 | 0 | 282001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18299 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1051 | 5066064 | 1529194
| District 08 Totals |  |  |  |  | 11 | 21 | 71 | 5797 | 8008 | 7525 | 90.91% | 10 | 483 | 0 | 0 | 1150 | 1061 | 318680546 | 1113116 | 317567433 | 324191882 | 323313461 | -67500 | 1200000 | 1132500 | 324445961 | 324531147 | 100% | 11 | 668378 | 5511333 | 646 | 504 | 0 | 10 | 2110720 | 1278827 | 0 | 5 | 190343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1918637 | 24202 | 0 | 0 | 282001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18299 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1051 | 5066064 | 1529194
| Statewide Central Let Contracts SubTotal |  |  |  |  | 105 | 200 | 295 | 31697 | 46147 | 45111 | 87.62% | 92 | 1036 | 408 | 0 | 10946 | 3504 | 628226834 | 6503635 | 621723202 | 656431227 | 659880222 | -457291 | 1140000 | 682709 | 660562931 | 660578229 | 91.43% | 96 | 660906 | 28204389 | 7151 | 3391 | 29 | 1389 | 15580258 | 1713127 | 72 | 1406 | 11132604 | 755967 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 95 | 142 | 850412 | 40265 | 2 | 26 | 500566 | 52957 | 0 | 0 | 0 | 0 | 0 | 35 | 1419726 | 590741 | 0 | 59 | -41035 | 89119 | 82 | 206 | 730721 | 716682 | 14 | 0 | 0 | 0 | 0 | -10 | -834233 | 0 | 294 | 3253 | 29310039 | 3958861
| Statewide District Let Contracts SubTotal |  |  |  |  | 95 | 141 | 236 | 26201 | 36776 | 34812 | 84.21% | 80 | 1964 | 274 | 0 | 8005 | 2570 | 678589787 | 5235991 | 673353800 | 694105583 | 692570675 | -624592 | 5145000 | 4520408 | 697091082 | 686967990 | 93.68% | 89 | -8789328 | 15515794 | 4497 | 2765 | 495 | 519 | 6051752 | 1859440 | 269 | 532 | 2892881 | 227730 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 44 | 1085 | 4357297 | 24202 | 0 | 34 | 92643 | 0 | 0 | 0 | 0 | 0 | 6 | 43 | 696704 | 0 | 0 | 84 | 2597369 | 242717 | 0 | 5 | 18830 | 0 | 0 | 21 | 0 | 0 | 0 | -6 | -1407763 | 0 | 814 | 2317 | 15160951 | 2354089
| Statewide Totals |  |  |  |  | 200 | 341 | 531 | 57898 | 82923 | 79923 | 86% | 172 | 3000 | 682 | 0 | 18951 | 6074 | 1306816621 | 11739626 | 1295077002 | 1350536810 | 1352450897 | -1081883 | 6285000 | 5203117 | 1357654013 | 1347546219 | 92.5% | 185 | -8128422 | 43720183 | 11648 | 6156 | 524 | 1908 | 21632010 | 3572567 | 341 | 1938 | 14025485 | 983697 | 0 | 0 | 0 | 0 | 0 | 0 | -167739 | 0 | 0 | 0 | 0 | 0 | 139 | 1227 | 5207709 | 64467 | 2 | 60 | 593209 | 52957 | 0 | 0 | 0 | 0 | 6 | 78 | 2116430 | 590741 | 0 | 143 | 2556334 | 331836 | 82 | 211 | 749551 | 716682 | 14 | 21 | 0 | 0 | 0 | -16 | -2241996 | 0 | 1108 | 5570 | 44470990 | 6312950

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P48 | 43489815201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-01-16 | 881862 | 950893 | 869654 | 69030.94 | 0 | 870011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869654 | 870011 | 357 | 901555
1 | E1P95 | 42838315201 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-15 | 12611204 | 13133768 | 12450757 | 522563.69 | -160183 | 12343775 | -35183 | 0 | 0 | 0 | 0 | 0 | -35183 | 0 | 0 | 0 | 0 | -125000 | 0 | -125000 | -160183 | 12290574 | 12343775 | 53201 | 10409515 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1Q47 | 42584135201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-03-15 | 44539372 | 47408126 | 47193361 | 2868754.26 | 0 | 47170167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47193361 | 47170167 | -23194 | 59075332 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
1 | E1R56 | 43796615201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 2770000 | 3004222 | 2811795 | 234221.81 | 0 | 2811795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2811795 | 2811795 | 0 | 3199272
1 | E1S02 | 43942515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-09-19 | 3418691 | 3599265 | 3634779 | 180573.88 | 0 | 3581913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 3935083
1 | E1S49 | 19602275201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | 4765372 | 5108479 | 5065730 | 343107.11 | 0 | 5081869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5065730 | 5081869 | 16140 | 5214661
1 | E1S51 | 44002715201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-03-19 | 407081 | 421138 | 368049 | 14057.35 | -48399 | 319650 | -48399 | 0 | 0 | 0 | 0 | 0 | -48399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48399 | 319650 | 319650 | 0 | 439358
1 | E1S53 | 43890215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1335282 | 1434154 | 1346419 | 98871.24 | 0 | 1347016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 1282338
1 | E1S54 | 44334015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-06-11 | 2038002 | 2038002 | 1947616 | 0 | 0 | 1941883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 2189903
1 | E1T46 | 44681615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-07-23 | 3083600 | 3080211 | 3030211 | -3388.51 | 0 | 3030211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3030211 | 3030211 | 0 | 4731072 | LBDB | LOW BID DESIGN BUILD
1 | E1T47 | 44624415201 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2020-07-15 | 1836500 | 1836500 | 1786500 | 0 | 0 | 1787020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 1849529 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1T68 | 43980115201 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 180572 | 210394 | 199372 | 29821.5 | -3750 | 195621 | -3750 | 0 | 0 | 0 | 0 | 0 | -3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3750 | 195621 | 195621 | 0 | 260007
1 | E1T84 | 43506615201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 231014 | 231014 | 219205 | 0 | 0 | 219205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219205 | 219205 | 0 | 230282 | B0 | ACC - LUMP SUM
1 | T1700 | 43088615201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2262913 | 2254766 | 2207735 | -8146.86 | 0 | 2219978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | 2483173
1 | T1717 | 19801765201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-12-05 | 15860000 | 16463364 | 16135347 | 603363.88 | -150816 | 15936167 | -69816 | 0 | 0 | 0 | 0 | -21000 | -90816 | 0 | 0 | 0 | 0 | -60000 | 0 | -60000 | -150816 | 15984531 | 15936167 | -48363 | 15674641 | B10 | ACC - BONUS/INCENT/DISINCENT
1 | T1735 | 43654715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-09-26 | 409918 | 418046 | 383683 | 8128.44 | 0 | 383683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383683 | 383683 | 0 | 267364
1 | T1747 | 43355035201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-08-28 | 12256766 | 12232966 | 12265846 | -23799.95 | -82722 | 12147745 | -82722 | 0 | 0 | 0 | 0 | 0 | -82722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82722 | 12183124 | 12147745 | -35379 | 11662003
1 | T1755 | 43659715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 5620384 | 5602989 | 5688348 | -17394.84 | 0 | 5695271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | 6766075
1 | T1757 | 43943615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 2163088 | 2182239 | 2172501 | 19150.59 | 0 | 2181502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172501 | 2181502 | 9002 | 2199111 | B0 | ACC - LUMP SUM
1 | T1760 | 43943915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-10 | 4964468 | 4976639 | 5027641 | 12170.6 | 0 | 5069314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5027641 | 5069314 | 41673 | 5089189
1 | T1764 | 44013015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 381859 | 381859 | 358474 | 0 | 0 | 358474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358474 | 358474 | 0 | 386666
1 | T1768 | 43900215201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1847556 | 1962457 | 1921734 | 114901.14 | 0 | 1920578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 1876585
1 | T1775 | 44151915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 7746370 | 7776109 | 7775281 | 29738.5 | 0 | 7823279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7775281 | 7823279 | 47998 | 9281425
1 | T1786 | 41450665201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 1630302 | 1630302 | 1465226 | 0 | 0 | 1467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 2010635
1 | T1789 | 43693115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 2359731 | 2322360 | 2220739 | -37371.29 | 0 | 2223174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220739 | 2223174 | 2435 | 2549900
1 | T1796 | 44050815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 817957 | 986429 | 914986 | 168472.16 | 0 | 914986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914986 | 914986 | 0 | 656746
2 | E20C2 | 44105115201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-16 | 539351 | 539351 | 482138 | 0 | 0 | 482138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482138 | 482138 | 0 | 678652
2 | E20D9 | 44703115201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-09-02 | 394410 | 571805 | 486787 | 177395.01 | 0 | 486787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486787 | 486787 | 0 | 493957
2 | E2V69 | 21327275201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-10-18 | 16294500 | 17291837 | 17466265 | 997337.38 | 1350000 | 17461845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 350000 | 0 | 0 | 0 | 1350000 | 1350000 | 18816265 | 17461845 | -1354420 | 18122424 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | E2W84 | 43384215201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 1444429 | 2840551 | 2999816 | 1396122.44 | 0 | 2999816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1103685
2 | E2Y24 | 43743715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-05-13 | 1280762 | 1204874 | 1079365 | -75887.97 | 0 | 1079365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | 2106516
2 | E2Y79 | 20968315201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2019-11-13 | 4028350 | 4078350 | 4286744 | 50000 | 0 | 4286650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 3704637
2 | E2Y81 | 43197915201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2019-10-16 | 2424817 | 2497783 | 2495432 | 72965.76 | 0 | 2495432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495432 | 2495432 | 0 | 3472664
2 | E2Y84 | 43807515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 1543447 | 1543447 | 1581148 | 0 | 0 | 1565351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581148 | 1565351 | -15797 | 1817083
2 | E2Y85 | 43865025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 3884320 | 3884320 | 3769800 | 0 | 0 | 3768427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 4380189
2 | E2Z24 | 44199735216 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-02-19 | 1624143 | 1624143 | 1547862 | 0 | 0 | 1547862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 1701419
2 | E2Z36 | 43930315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-12-18 | 363396 | 445802 | 448483 | 82406.57 | 0 | 448483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448483 | 448483 | 0 | 356089
2 | E2Z39 | 43122445201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-15 | 788792 | 788792 | 738086 | 0 | 0 | 738086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738086 | 738086 | 0 | 1315900
2 | E2Z50 | 42848915201 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2020-03-18 | 1635960 | 1685775 | 1669775 | 49815.5 | 0 | 1669775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 1762747
2 | E2Z51 | 43384115201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-15 | 2662544 | 2666491 | 1959926 | 3946.98 | 0 | 1959926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959926 | 1959926 | 0 | 3385087
2 | E2Z52 | 43204815201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 1206264 | 1206264 | 1198471 | 0 | 0 | 1198471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 1268308
2 | E2Z56 | 43807915201 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 744154 | 744154 | 696705 | 0 | 0 | 696705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696705 | 696705 | 0 | 797486
2 | T2573 | 21071125201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 39980618 | 41792741 | 42556288 | 1812123.25 | 0 | 43150258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42556288 | 43150258 | 593970 | 35388991
2 | T2579 | 21071245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-28 | 59962436 | 63341457 | 65450734 | 3379021.04 | 0 | 65787858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65450734 | 65787858 | 337124 | 62411016
2 | T2641 | 20953745201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-10-26 | 60315650 | 62391668 | 63370802 | 2076017.6 | 0 | 64652436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63370802 | 64652436 | 1281634 | 62430987
2 | T2700 | 41525015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-04-25 | 11881880 | 12125444 | 12326250 | 243563.71 | 0 | 12277546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12326250 | 12277546 | -48704 | 8810905
2 | T2712 | 43240415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-29 | 3754465 | 3806745 | 3827055 | 52279.5 | -32544 | 3793154 | -32544 | 0 | 0 | 0 | 0 | 0 | -32544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32544 | 3794511 | 3793154 | -1358 | 4106536
2 | T2720 | 43735415201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 2468956 | 2635619 | 2856937 | 166663.01 | 0 | 2843130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856937 | 2843130 | -13807 | 2333570
2 | T2743 | 42845515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 12559204 | 13123013 | 13368899 | 563808.92 | 0 | 13241202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13368899 | 13241202 | -127696 | 13121490
2 | T2752 | 43395715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 6416755 | 6416755 | 6306830 | 0 | 0 | 6314515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6306830 | 6314515 | 7685 | 6469876
2 | T2753 | 43980015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 3416497 | 3891903 | 3917050 | 475405.64 | 0 | 3897876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 3898969
2 | T2759 | 43617615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 4035736 | 4035736 | 3954853 | 0 | 0 | 3920789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 4365195
2 | T2760 | 44125815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 6493175 | 6617231 | 6291241 | 124056.15 | -142728 | 6136498 | -142728 | 0 | 0 | 0 | 0 | 0 | -142728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142728 | 6148513 | 6136498 | -12015 | 5584101
2 | T2762 | 44499015201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2020-04-29 | 1596635 | 1683719 | 1395080 | 87083.98 | 0 | 1395080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 1936705
2 | T2768 | 43948815201 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 1959598 | 1959598 | 1892736 | 0 | 0 | 1893489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 1755198
2 | T2770 | 43948915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 601043 | 596270 | 539883 | -4773.2 | 0 | 539883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539883 | 539883 | 0 | 942548
2 | T2773 | 43403815201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-03-25 | 3684895 | 3684895 | 3598807 | 0 | 0 | 3601767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3598807 | 3601767 | 2960 | 3367569
2 | T2774 | 43578015201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-05-20 | 1066490 | 1066490 | 1059789 | 0 | 0 | 1060127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 1110094
2 | T2776 | 43399315201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 198978 | 198978 | 196874 | 0 | 0 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196874 | 196874 | 0 | 202254
2 | T2778 | 44105715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-09-30 | 4660748 | 4665808 | 4696793 | 5059.38 | 0 | 4795119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4696793 | 4795119 | 98326 | 4464709
2 | T2780 | 43732515201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 237581 | 237581 | 222711 | 0 | 0 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222711 | 222711 | 0 | 289607
2 | T2781 | 44106015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 5821573 | 5821573 | 5952158 | 0 | 0 | 5882048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952158 | 5882048 | -70110 | 7534069
2 | T2786 | 43732315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 5990960 | 5990960 | 5941443 | 0 | 0 | 5882422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 7170016
2 | T2799 | 43584515201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-01-27 | 584000 | 584000 | 571789 | 0 | 0 | 571826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571789 | 571826 | 37 | 883654
2 | T9022 | 44531935223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 1990220 | 2080312 | 2092740 | 90091.64 | 0 | 2092740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 1872855
3 | E3Q53 | 44009615201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2017-07-20 | 4412093 | 4461209 | 4457747 | 49116.18 | -449760 | 4007987 | -449760 | 0 | 0 | 0 | 0 | 0 | -449760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -449760 | 4007987 | 4007987 | 0 | 4688435 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
3 | E3S42 | 42187345201 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 2507433 | 2507433 | 2457433 | 0 | 0 | 2457433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 2985049
3 | E3S73 | 4453811H201 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-12-12 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174645 | 0 | -174645 | 212648
3 | E3T18 | 42282325201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-12-17 | 145277 | 145277 | 129137 | 0 | 0 | 129137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129137 | 129137 | 0 | 213559
3 | E3T25 | 44154615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 2058102 | 2058102 | 2116209 | 0 | 0 | 2113685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 2347515
3 | E3T27 | 40571925201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-17 | 673158 | 673158 | 632738 | 0 | 0 | 632738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632738 | 632738 | 0 | 803648
3 | E3T35 | 44291315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1454221 | 1547027 | 1426180 | 92805.8 | 25000 | 1426180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 1274994 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3T58 | 43815415201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-12 | 883399 | 898220 | 890748 | 14820.6 | 0 | 890748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890748 | 890748 | 0 | 673070
3 | E3T66 | 4450184H201 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-03-12 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225968 | 0 | -225968 | 246220
3 | E3T96 | 4453581G201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-13 | 782169 | 1364937 | 1338192 | 582768.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 1084959
3 | E3U27 | 44154515201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 1641103 | 1641103 | 1553101 | 0 | 0 | 1614039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1553101 | 1614039 | 60937 | 2039670
3 | T3640 | 43290925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 720412 | 720412 | 691249 | 0 | 0 | 691249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691249 | 691249 | 0 | 499997 | B0 | ACC - LUMP SUM
3 | T3646 | 22049585201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 15646589 | 15902989 | 15169686 | 256399.6 | 0 | 15198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15169686 | 15198000 | 28314 | 21200000
3 | T3682 | 43812915201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 346966 | 346966 | 335754 | 0 | 0 | 335754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335754 | 335754 | 0 | 319060
3 | T3689 | 21876425201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-12-04 | 3948246 | 4424349 | 4220133 | 476102.63 | 0 | 4222745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4220133 | 4222745 | 2611 | 3709289
3 | T3692 | 43774615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-03-27 | 8791950 | 9177543 | 9191379 | 385592.85 | 0 | 9104839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191379 | 9104839 | -86540 | 10784327
3 | T3699 | 43228415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2694142 | 2663955 | 2668318 | -30186.8 | 0 | 2665830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | 2634440
3 | T3700 | 43811115201 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 678788 | 678788 | 592391 | 0 | 0 | 592857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592391 | 592857 | 466 | 960134
3 | T3717 | 43720215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 770613 | 797858 | 802448 | 27244.97 | 0 | 802695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802448 | 802695 | 247 | 750108
3 | T3723 | 43972115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 4514950 | 4573579 | 4689305 | 58629.33 | -24500 | 4517927 | 0 | 0 | 0 | 0 | 0 | -24500 | -24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24500 | 4664805 | 4517927 | -146878 | 5332165
3 | T3729 | 43972715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 7592042 | 7796389 | 8177990 | 204347 | 0 | 8127837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 9289556
3 | T3738 | 44173815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-05-20 | 1336283 | 1373486 | 1300986 | 37202.72 | 0 | 1302036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 1328097
3 | T3744 | 43972415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 5906321 | 5906321 | 6014134 | 0 | 0 | 5961005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 5368996
3 | T3745 | 43972915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 7352550 | 7448821 | 7636800 | 96270.69 | 0 | 7674029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7636800 | 7674029 | 37229 | 8840050
3 | T3746 | 44154315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 4283738 | 4283738 | 4494319 | 0 | 0 | 4570359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 5641395
3 | T3749 | 44173215201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 755462 | 755462 | 668670 | 0 | 0 | 668670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668670 | 668670 | 0 | 824731
3 | T3751 | 43775325201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 2569909 | 2569909 | 2490758 | 0 | 0 | 2498656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490758 | 2498656 | 7898 | 2572447
3 | T3763 | 43661515201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 4894168 | 4903128 | 5058997 | 8960 | 0 | 5067842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5058997 | 5067842 | 8845 | 5019528
3 | T3770 | 44134715201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-02-17 | 224915 | 224915 | 229832 | 0 | 0 | 229832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229832 | 229832 | 0 | 248071
4 | E4T83 | 42268145201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-05-01 | 2027817 | 2027817 | 1963518 | 0 | 0 | 1976822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1963518 | 1976822 | 13305 | 2656948
4 | E4U24 | 43984115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2020-03-06 | 1238848 | 1238449 | 1196529 | -399.46 | 0 | 1196625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | 1271431
4 | E4U54 | 44330915201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-07 | 1153286 | 1168772 | 976003 | 15485.58 | 100000 | 980548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | E4U72 | 44162915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-08 | 893625 | 893625 | 846410 | 0 | 0 | 849948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846410 | 849948 | 3538 | 1052585
4 | E4U74 | 44162815201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2021-03-05 | 1190833 | 1189722 | 1098149 | -1110.99 | 0 | 1101304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098149 | 1101304 | 3155 | 1310703
4 | T4471 | 43472215201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 5223993 | 5569665 | 5480351 | 345672.31 | -68940 | 5405890 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5411411 | 5405890 | -5522 | 5507060
4 | T4476 | 43515815201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-06-13 | 7524128 | 7782657 | 7606665 | 258528.45 | 0 | 7559524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7606665 | 7559524 | -47141 | 7189790
4 | T4488 | 43630415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 552418 | 602867 | 592608 | 50448.67 | 0 | 592529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592608 | 592529 | -79 | 285675
4 | T4494 | 43630715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5685198 | 5923341 | 5849802 | 238143.16 | 0 | 5808702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 5359259
4 | T4497 | 43783615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 7969825 | 9671721 | 9618307 | 1701895.88 | 0 | 9579829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9618307 | 9579829 | -38478 | 9083314
4 | T4504 | 43783815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 8446061 | 9282205 | 9225023 | 836144.4 | 0 | 9088376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 9046599
4 | T4505 | 43668515201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 7195336 | 7097482 | 6908157 | -97854.53 | 0 | 6849432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6908157 | 6849432 | -58724 | 7395888
4 | T4509 | 43177055201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-04-24 | 3049775 | 3212084 | 3151909 | 162309.67 | 0 | 3134194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151909 | 3134194 | -17714 | 2802936
4 | T4511 | 43469015201 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2099355 | 2040900 | 1905910 | -58454.44 | 0 | 1888675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | 2266163
4 | T4521 | 43760515201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 737736 | 737736 | 679527 | 0 | 0 | 679527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679527 | 679527 | 0 | 798446
4 | T4523 | 43469515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 8207877 | 8281895 | 8003190 | 74017.2 | 0 | 7894972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 8969821
4 | T4528 | 43696715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 547645 | 547645 | 476343 | 0 | 0 | 476343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476343 | 476343 | 0 | 487570
4 | T4530 | 43592515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2019-12-04 | 4642816 | 4682420 | 4650889 | 39603.28 | 0 | 4619922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 4777019
4 | T4538 | 44138115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 589517 | 589517 | 585765 | 0 | 0 | 586015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585765 | 586015 | 250 | 492571
4 | T4543 | 43915915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 689567 | 689567 | 649805 | 0 | 0 | 650042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649805 | 650042 | 237 | 603406
4 | T4553 | 43840215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-07-29 | 432944 | 432944 | 392014 | 0 | 0 | 392107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392014 | 392107 | 93 | 514165
4 | T4555 | 43990915201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2020-09-30 | 441982 | 441982 | 407189 | 0 | 0 | 407189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407189 | 407189 | 0 | 501235
5 | E50A9 | 44326415201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-03-03 | 1277250 | 1307659 | 1259799 | 30409.22 | 0 | 1259799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 1837867
5 | E52A1 | 44208715201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-10-06 | 875517 | 875517 | 860515 | 0 | 0 | 862383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860515 | 862383 | 1868 | 776685
5 | E52A2 | 44316815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 7726425 | 7711640 | 7780592 | -14785.04 | 0 | 7870977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7780592 | 7870977 | 90385 | 10078671
5 | E52A3 | 44539615201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 254016 | 254016 | 220075 | 0 | 0 | 220075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220075 | 220075 | 0 | 309304
5 | E53A6 | 44119715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-15 | 320193 | 320193 | 308143 | 0 | 0 | 308143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308143 | 308143 | 0 | 289415
5 | E53A9 | 44101715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 789395 | 789395 | 772436 | 0 | 0 | 772436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772436 | 772436 | 0 | 659076
5 | E54A0 | 44208815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 524491 | 524491 | 485346 | 0 | 0 | 485346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485346 | 485346 | 0 | 529397
5 | E54A2 | 44589615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-01-05 | 553370 | 553370 | 525670 | 0 | 0 | 525670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525670 | 525670 | 0 | 622693
5 | E54A9 | 44541215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-03-02 | 239156 | 239156 | 221370 | 0 | 0 | 221370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221370 | 221370 | 0 | 305554
5 | E57A9 | 43988085201 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-02-02 | 127056 | 127056 | 123994 | 0 | 0 | 123994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123994 | 123994 | 0 | 169610
5 | E5Z71 | 43179835201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-07 | 16210000 | 17216871 | 17023277 | 1006870.83 | 0 | 16917166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17023277 | 16917166 | -106111 | 17297949
5 | E5Z86 | 43913615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-07 | 7339262 | 7409262 | 7411267 | 70000 | 0 | 7390488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 7635147
5 | E5Z88 | 43793715201 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2019-10-01 | 1872651 | 1875633 | 1830367 | 2981.59 | 0 | 1825332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830367 | 1825332 | -5035 | 1916337
5 | E5Z90 | 44326915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-07 | 3873465 | 3916343 | 4113159 | 42878.1 | 0 | 4113159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 4116925 | B1 | ACC - NO EXCUSE BONUS
5 | E5Z96 | 44116615201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 1299589 | 1299589 | 1316020 | 0 | 0 | 1315225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 1579621
5 | T5538 | 23949635201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 27752000 | 28126749 | 28782547 | 374748.52 | -7304 | 29206081 | 0 | 0 | 0 | 0 | 0 | -7304 | -7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7304 | 28775243 | 29206081 | 430838 | 28403237
5 | T5582 | 23827585201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 9883550 | 9891919 | 9834478 | 8369.37 | 0 | 10163025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834478 | 10163025 | 328547 | 14381890
5 | T5628 | 43734115201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 16216216 | 16216212 | 16727455 | -4.3 | 0 | 16505113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16727455 | 16505113 | -222342 | 16716427
5 | T5637 | 43386015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-10-31 | 3244000 | 6497176 | 7037281 | 3253176.27 | 0 | 7021113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037281 | 7021113 | -16169 | 3081320
5 | T5668 | 43968235201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-22 | 20003719 | 23051817 | 24148539 | 3048098.16 | 0 | 24037958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24148539 | 24037958 | -110580 | 16312265
5 | T5669 | 43923515201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2019-10-30 | 9146375 | 9218711 | 9241919 | 72336.38 | 0 | 9193416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 7779291
5 | T5670 | 43020245201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-30 | 2204501 | 2284647 | 2359499 | 80145.84 | 0 | 2372974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359499 | 2372974 | 13475 | 1667431
5 | T5676 | 43913915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 3433963 | 3456872 | 3590532 | 22908.37 | 0 | 3561652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 4003251
5 | T5678 | 43913115201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 9468271 | 9554158 | 9236375 | 85887 | 0 | 9044854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 12400166
5 | T5681 | 43968215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-25 | 5811031 | 5814390 | 5643783 | 3359.62 | 0 | 5604250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 6194317
5 | T5685 | 44139615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 1144140 | 1144140 | 1050473 | 0 | 0 | 1085978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 1587329
5 | T5701 | 44136515201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 1343897 | 1343897 | 1295471 | 0 | 0 | 1296320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 1376221
5 | T5710 | 44136615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 614736 | 614736 | 554534 | 0 | 0 | 554534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554534 | 554534 | 0 | 624302
6 | E6K72 | 43652215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-01-25 | 12962183 | 14077180 | 17042051 | 1114996.62 | 0 | 17042582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17042051 | 17042582 | 530 | 12118991
6 | E6K73 | 43653715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-25 | 4293668 | 4404270 | 4390585 | 110602.64 | 0 | 4390585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 3248689
6 | E6K77 | 42930035201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-23 | 89490000 | 91100952 | 91019470 | 1610951.88 | 1320000 | 91348469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 0 | 0 | 1320000 | 1320000 | 92339470 | 91348469 | -991000 | 75222050 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
6 | E6L90 | 43029139201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-05-03 | 3703968 | 3809754 | 3778569 | 105785.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6L94 | 43653915201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2020-07-30 | 1871000 | 1871000 | 1887711 | 0 | 0 | 1887711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 2130684
6 | E6M32 | 44204015201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-05 | 4679092 | 1480760 | 1400668 | -3198331.59 | 0 | 1400668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
6 | E6M37 | 44060415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-30 | 589589 | 589589 | 561220 | 0 | 0 | 561388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561220 | 561388 | 168 | 615217
6 | E6M47 | 44196115201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 291080 | 324304 | 276941 | 33224 | 0 | 276941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276941 | 276941 | 0 | 335060
6 | E6N05 | 44188615201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-05-28 | 660660 | 660660 | 634309 | 0 | 0 | 634835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634309 | 634835 | 526 | 655037
6 | T6460 | 43081745201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 9621172 | 9721667 | 9784724 | 100495 | 580000 | 9769960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 80000 | 0 | 580000 | 580000 | 10364724 | 9769960 | -594765 | 9993234 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6465 | 43345535201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-12-04 | 3445403 | 3514192 | 3479994 | 68789.07 | 170000 | 3454649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 3079920 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6469 | 42930045201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 5172452 | 5372452 | 5225454 | 200000 | 220000 | 5222651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 5445454 | 5222651 | -222802 | 4540258 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6472 | 44167015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-02-26 | 1098693 | 1098693 | 1036954 | 0 | 0 | 1036856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 1175314
6 | T6475 | 43635525201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 3771815 | 3809965 | 3652358 | 38150 | 130000 | 3668771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 4248051 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6478 | 44030415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 419419 | 419419 | 372140 | 0 | 0 | 372179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372140 | 372179 | 39 | 420618
6 | T6482 | 44017815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 996753 | 1029269 | 971330 | 32516 | 0 | 971328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 971330 | 971328 | -2 | 819497
6 | T6483 | 44016915201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-09-25 | 1399991 | 1461545 | 1445555 | 61553.6 | 0 | 1445977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445555 | 1445977 | 421 | 1299243
6 | T6493 | 44331415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 2625000 | 2574951 | 2200098 | -50049.49 | 0 | 2199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | 2833197
6 | T6498 | 43080835201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 1171215 | 1171215 | 1109354 | 0 | 0 | 1108186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 865294
6 | T6502 | 44385315201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2021-01-27 | 619555 | 619555 | 571295 | 0 | 0 | 572454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571295 | 572454 | 1159 | 681973
6 | T6507 | 43991815201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-07-29 | 1536743 | 1536743 | 1501598 | 0 | 100000 | 1507472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1601598 | 1507472 | -94126 | 1644819 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6526 | 44167215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 349349 | 349349 | 316341 | 0 | 0 | 316342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316341 | 316342 | 1 | 359443
7 | E7M61 | 43951615201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-10 | 3417860 | 3417860 | 3733589 | 0 | 0 | 3733589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3733589 | 3733589 | 0 | 4777765
7 | E7M81 | 44335315201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2019-10-09 | 385385 | 398672 | 364686 | 13287.38 | 0 | 364686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364686 | 364686 | 0 | 300000
7 | E7M91 | 44144125201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-03-11 | 1622282 | 1622282 | 1554003 | 0 | 0 | 1554555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 1262053
7 | E7M93 | 44383215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-02-12 | 1260367 | 1319899 | 1294928 | 59531.2 | 0 | 1294928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294928 | 1294928 | 0 | 1500000
7 | E7M94 | 43673415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 1352812 | 1352812 | 1317432 | 0 | 0 | 1317432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 1640000
7 | E7M96 | 43762615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-13 | 4564698 | 4596212 | 4520073 | 31514.1 | 0 | 4462676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 5061300
7 | E7N02 | 44383315201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-03-11 | 741228 | 790728 | 771044 | 49500 | 0 | 771044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771044 | 771044 | 0 | 741279
7 | E7N15 | 44539915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-02-12 | 3408000 | 3546613 | 3532479 | 138613.12 | 0 | 3532479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3532479 | 3532479 | 0 | 2952724 | B0 | ACC - LUMP SUM
7 | E7N26 | 43946015201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2020-07-08 | 873873 | 873873 | 855130 | 0 | 0 | 855600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855130 | 855600 | 470 | 685000
7 | E7N46 | 43955415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-09 | 357252 | 357252 | 337890 | 0 | 0 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337890 | 337890 | 0 | 485498
7 | E7N48 | 44025215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | 3104340 | 3104340 | 3112890 | 0 | 0 | 3077268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 4202893
7 | E7N59 | 44701515201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-01-20 | 86342 | 86342 | 80991 | 0 | 0 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80991 | 80991 | 0 | 127700
7 | E7R13 | 44111115201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-01-10 | 30854000 | 31355440 | 31288898 | 501439.84 | 1255000 | 31200893 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 1275000 | 0 | 0 | 0 | 0 | 0 | 1275000 | 1255000 | 32543898 | 31200893 | -1343005 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
7 | E7R17 | 44368415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-30 | 4637000 | 5023330 | 4952442 | 386330.45 | 0 | 4910655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R25 | 44335815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-04 | 994444 | 1037903 | 984227 | 43458.19 | 0 | 985956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 922458 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7385 | 25624325201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2016-06-20 | 12584444 | 14503972 | 15099334 | 1919527.94 | 0 | 15347747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15099334 | 15347747 | 248412 | 18085000
7 | T7386 | 43002115201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-06-15 | 6015645 | 7425942 | 7629019 | 1410297.05 | 0 | 7826485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7629019 | 7826485 | 197466 | 6465451 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7410 | 43649515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 10099029 | 12396490 | 12392490 | 2297460.32 | 0 | 12349457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12392490 | 12349457 | -43033 | 9905227
7 | T7437 | 43605615201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 1903823 | 2069815 | 2004923 | 165992 | 0 | 2005258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004923 | 2005258 | 335 | 1500000
7 | T7447 | 43764115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 3572269 | 3572269 | 3206137 | 0 | -7737 | 3190454 | -7737 | 0 | 0 | 0 | 0 | 0 | -7737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7737 | 3198400 | 3190454 | -7946 | 2900000
7 | T7450 | 43764015201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-29 | 3698894 | 3698894 | 3783529 | 0 | 0 | 3798642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783529 | 3798642 | 15112 | 2945400
7 | T7455 | 44140315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 9710187 | 9710187 | 10168330 | 0 | 0 | 10201078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10168330 | 10201078 | 32748 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
7 | T7466 | 43764615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-11-18 | 3084962 | 3084962 | 2884493 | 0 | 0 | 2884493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 2622400
8 | E8N18 | 41505115201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2014-05-16 | 73888232 | 74290962 | 74217617 | 402729.5 | -51000 | 72723061 | 0 | 0 | 0 | 0 | 0 | -51000 | -51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51000 | 74166617 | 72723061 | -1443556 | 78874307 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8Q12 | 41140615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-01 | 176976815 | 181606278 | 183899695 | 4629463.16 | 1190000 | 187388648 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 1190000 | 185089695 | 187388648 | 2298953 | 198773292 | A5 | ICC - BAM/BONUS
8 | E8Q95 | 43652015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-19 | 13519194 | 13647938 | 13835344 | 128743.5 | 0 | 13763473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 16504275
8 | E8R51 | 44132215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | 17604432 | 17319890 | 16726393 | -284542.88 | 0 | 16700477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726393 | 16700477 | -25916 | 15706807
8 | E8R55 | 42815445201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2019-04-09 | 7871284 | 8314187 | 5811967 | 442902.29 | 0 | 5810160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5811967 | 5810160 | -1807 | 9545164
8 | E8S00 | 44106715201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-09-10 | 5292443 | 5312653 | 5319849 | 20210.25 | 0 | 5313201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 4997184
8 | E8S11 | 44029115201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2020-04-14 | 12956998 | 13107980 | 13212168 | 150982.48 | -6500 | 13166473 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 13205668 | 13166473 | -39196 | 14597379
8 | E8S18 | 44042315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-14 | 9095686 | 9114552 | 9001603 | 18865.24 | 0 | 8960020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 12888272
8 | E8S63 | 44514015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-12-08 | 281612 | 283592 | 264303 | 1980 | 0 | 264303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264303 | 264303 | 0 | 348350
8 | E8S68 | 44530715201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-01-12 | 842202 | 842202 | 728029 | 0 | 0 | 728029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728029 | 728029 | 0 | 1031657
8 | E8S73 | 44429215201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2020-09-15 | 351648 | 351648 | 296493 | 0 | 0 | 296493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296493 | 296493 | 0 | 613041

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 | 0 | 113935.03 |  | 43152.32 | 10404.67 | 83598.62 |  | 251090.64 |  | 136419864 | 0.1228% | 167492.02
02 | 2500 | 431093.84 |  |  | 577924.78 | 855424.19 | -99989.98 | 1766952.83 |  | 280537732 | 0.3606% | 1011518.62
03 |  | 92502.15 |  |  |  | 3760 |  | 96262.15 |  | 87991726 | 0.1051% | 92502.15
04 |  | 23387.27 | 23462.14 | 7936.6 | 337378.28 | 1449492.03 |  | 1841656.32 |  | 70540582 | 0.5559% | 392164.29
05 |  | 89411.5 |  | 4538.3 | 6449.59 | 78273.13 | -499949.9 | -321277.38 |  | 153548235 | 0.06539% | 100399.39
06 | 0 | 21058.24 |  | 5125.87 | 238611.42 | 18638.74 |  | 283434.27 |  | 150768800 | 0.1756% | 264795.53
07 |  | 2027.92 |  | 395425.93 | 11953.81 | 269883.53 |  | 679291.19 |  | 108329136 | 0.3779% | 409407.66
08 |  | 0 | 0 | 1254202.74 | 0 | 282438.22 |  | 1536640.96 |  | 318680546 | 0.3936% | 1254202.74
Grand Total | 2500 | 773415.95 | 23462.14 | 1710381.76 | 1182722.55 | 3041508.46 | -599939.88 | 6134050.98 |  | 1306816621 | 0.2826% | 3692482.4
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 | 0 | 45 |  | 115 | 51 | 389 |  | 600 |  | 211
02 | 42 | 163 |  |  | 165 | 1037 | 0 | 1407 |  | 370
03 |  | 26 |  |  |  | 235 |  | 261 |  | 26
04 |  | 46 | 0 | 0 | 122 | 285 |  | 453 |  | 168
05 |  | 69 |  | 20 | 0 | 1253 | 0 | 1342 |  | 89
06 | 0 | 0 |  | 0 | 0 | 29 |  | 29 |  | 0
07 |  | 82 |  | 169 | 36 | 605 |  | 892 |  | 287
08 |  | 3 | 0 | 0 | 2 | 1056 |  | 1061 |  | 5
Grand Total | 42 | 434 | 0 | 304 | 376 | 4889 | 0 | 6045 |  | 1156
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 | 25 |  |  |  | 45 | 156 | 226 |  | 70 | 281 | 6786 | 4.141%
02 |  | 21 |  |  | 4 | 205 | 230 |  | 25 | 395 | 12661 | 3.12%
03 |  | 21 |  | 129 | 21 | 524 | 695 |  | 171 | 197 | 6085 | 3.237%
04 |  | 6 |  |  | 18 | 67 | 91 |  | 24 | 192 | 6490 | 2.958%
05 |  | 5 |  |  |  |  | 5 |  | 5 | 94 | 6905 | 1.361%
06 | [5 empty] | 162 | 162 |  | 0 | 0 | 7039 | 0%
07 |  | 27 |  |  |  | 154 | 181 |  | 27 | 314 | 6135 | 5.118%
08 | [5 empty] | 90 | 90 |  | 0 | 5 | 5797 | 0.08625%
Grand Total | 25 | 80 |  | 129 | 88 | 1358 | 1680 |  | 322 | 1478 | 57898 | 2.553%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 012 | 2 |  | 1 | 019 | 22039.78 | 18162.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | E1P48 | 43489815201 | 013 | 2 |  | 1 | 106 | 41653.88 | 41653.88 | 1 |  | N | 11 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P48 | 43489815201 | 013 | 2 |  | 2 | 003 | 2927.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P48 | 43489815201 | 014 | 2 |  | 1 | 101 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P48 | 43489815201 | 014 | 2 |  | 2 | 101 | 1060 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 1 | 115 | 27988.56 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 2 | 004 | 2172.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 3 | 003 | 2400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 4 | 004 | 6872.57 | 3841.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 5 | 112 | 4568.74 | 2103.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 6 | 107 | 2087.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 7 | 004 | 8954.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 8 | 023 | 5027.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 9 | 503 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P95 | 42838315201 | 022 | 2 |  | 1 | 106 | 32326.02 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 023 | 2 |  | 1 | 115 | 2624.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 034 | 2 |  | 1 | 118 | 32000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1P95 | 42838315201 | 039 | 2 |  | 1 | 013 | 8940.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
01 | E1P95 | 42838315201 | 039 | 2 |  | 2 | 120 | 13098.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 1 | 001 | 9836.36 | 0 | 1 |  | C | 24 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 041 | 2 |  | 2 | 106 | 5581.1 | 5581.1 | 5 |  | C | 7 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 3 | 120 | 40053.77 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 4 | 010 | 18051.67 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1P95 | 42838315201 | 044 | 2 |  | 1 | 106 | 5976.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 048 | 2 |  | 1 | 103 | 11928.1 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 048 | 2 |  | 2 | 001 | 3190.98 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 3 | 015 | 7506.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 4 | 015 | 16528.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 5 | 005 | 11036.59 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P95 | 42838315201 | 050 | 2 |  | 1 | 115 | 2359.73 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 2 | 106 | 0 | 0 | 5 |  | N | 4 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 3 | 001 | 2648.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 050 | 2 |  | 4 | 128 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 5 | 106 | 3801.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 6 | 005 | 7793.3 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P95 | 42838315201 | 055 | 2 |  | 1 | 007 | -22909.68 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 1 | 115 | 14081.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 2 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1P95 | 42838315201 | 056 | 2 |  | 3 | 106 | 4372.35 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 4 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 5 | 924 | 0 | 0 | 0 |  | N | 81 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 6 | 128 | 1538.41 | 1538.41 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 7 | 001 | 30268.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 8 | 001 | 6722.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 9 | 103 | 4693.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 10 | 503 | 123513.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q47 | 42584135201 | 004 | 2 |  | 1 | 007 | -982399.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 006 | 2 |  | 1 | 300 | -138762.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
01 | E1Q47 | 42584135201 | 012 | 2 |  | 1 | 105 | 31099.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 012 | 2 |  | 2 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 015 | 2 |  | 1 | 105 | -387328.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 016 | 2 |  | 1 | 007 | 952605.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 023 | 2 |  | 1 | 503 | 179253.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q47 | 42584135201 | 028 | 2 |  | 1 | 103 | 16193 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 029 | 2 |  | 1 | 101 | 145385.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 035 | 2 |  | 1 | 923 | 91617.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 1 | 107 | 323521.84 | 46701.2 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 2 | 117 | 3803.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 037 | 2 |  | 1 | 107 | 11017.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 039 | 2 |  | 1 | 117 | -1032.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 042 | 2 |  | 1 | 001 | 838070.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 050 | 2 |  | 1 | 003 | 38861.27 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 057 | 2 |  | 1 | 001 | 1274886.31 | 0 | 2 |  | N | 41 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 059 | 2 |  | 1 | 700 | -577152.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | E1Q47 | 42584135201 | 060 | 2 |  | 1 | 001 | 175000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 061 | 2 |  | 1 | 001 | 811721.28 | 0 | 0 |  | N | 56 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 062 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 063 | 2 |  | 1 | 122 | 59392.02 | 40714.72 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1R56 | 43796615201 | 008 | 2 |  | 1 | 929 | 13587.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1R56 | 43796615201 | 009 | 2 |  | 1 | 012 | 116397.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R56 | 43796615201 | 010 | 2 |  | 1 | 112 | 26109.1 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R56 | 43796615201 | 011 | 2 |  | 1 | 001 | 72952.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R56 | 43796615201 | 011 | 2 |  | 2 | 101 | 5174.97 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1S02 | 43942515201 | 002 | 2 |  | 1 | 118 | 3222.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1S02 | 43942515201 | 020 | 2 |  | 1 | 001 | 183811.41 | 15127.86 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1S02 | 43942515201 | 022 | 2 |  | 1 | 503 | -6459.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1S49 | 19602275201 | 001 | 2 |  | 1 | 118 | 8931.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1S49 | 19602275201 | 002 | 2 |  | 1 | 105 | -156 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S49 | 19602275201 | 008 | 2 |  | 1 | 003 | 1172.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S49 | 19602275201 | 013 | 2 |  | 1 | 007 | 14514 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S49 | 19602275201 | 013 | 2 |  | 3 | 004 | 36904.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1S49 | 19602275201 | 017 | 2 |  | 1 | 015 | 210126.66 | 0 | 5 |  | N | 35 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S49 | 19602275201 | 023 | 2 |  | 1 | 101 | 17365 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1S49 | 19602275201 | 024 | 2 |  | 1 | 003 | 59455.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S49 | 19602275201 | 026 | 2 |  | 1 | 015 | -5205.23 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S51 | 44002715201 | 006 | 2 |  | 1 | 001 | 14057.35 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S53 | 43890215201 | 012 | 2 |  | 1 | 107 | 98871.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1T46 | 44681615201 | 015 | 2 |  | 1 | 112 | -3388.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1T68 | 43980115201 | 002 | 2 |  | 1 | 001 | 29821.5 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1700 | 43088615201 | 011 | 2 |  | 1 | 001 | -8146.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 | 005 | 2 |  | 1 | 015 | 43920 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 012 | 2 |  | 1 | 106 | 104412.54 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 2 | 107 | 23323.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 3 | 101 | 14483.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 4 | 126 | 6024.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1717 | 19801765201 | 013 | 2 |  | 1 | 003 | 10703 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1717 | 19801765201 | 017 | 2 |  | 1 | 103 | 157356.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1717 | 19801765201 | 020 | 2 |  | 1 | 503 | -61274.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 021 | 2 |  | 1 | 923 | 15428.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 022 | 2 |  | 1 | 101 | 86898 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1717 | 19801765201 | 022 | 2 |  | 2 | 116 | 39613.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 024 | 2 |  | 1 | 305 | 101512.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 026 | 2 |  | 1 | 015 | 83591.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 029 | 2 |  | 1 | 503 | -30081.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 031 | 2 |  | 1 | 015 | 14216.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 036 | 2 |  | 1 | 007 | 378593.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1717 | 19801765201 | 036 | 2 |  | 2 | 106 | 14652.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1717 | 19801765201 | 047 | 2 |  | 1 | 107 | -400929.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1717 | 19801765201 | 047 | 2 |  | 2 | 116 | -39613.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 048 | 2 |  | 1 | 015 | 3552 | 3552 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 048 | 2 |  | 2 | 015 | 36982.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 061 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 57 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1735 | 43654715201 | 006 | 2 |  | 1 | 001 | 8128.44 | 6258.44 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | T1747 | 43355035201 | 004 | 2 |  | 1 | 503 | -233898.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 009 | 2 |  | 1 | 305 | -38003 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 010 | 2 |  | 1 | 007 | 14363.22 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1747 | 43355035201 | 019 | 2 |  | 1 | 001 | 95307.09 | 14344.05 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1747 | 43355035201 | 034 | 2 |  | 1 | 015 | 104274.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1747 | 43355035201 | 035 | 2 |  | 1 | 015 | 34156.61 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1755 | 43659715201 | 012 | 2 |  | 1 | 106 | -17394.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1757 | 43943615201 | 003 | 2 |  | 1 | 503 | -25972.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1757 | 43943615201 | 004 | 2 |  | 1 | 112 | 20145.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1757 | 43943615201 | 006 | 2 |  | 1 | 112 | 71644.68 | 0 | 2 |  | N | 27 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1757 | 43943615201 | 009 | 2 |  | 1 | 503 | -46666.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1760 | 43943915201 | 009 | 2 |  | 1 | 101 | 12170.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1768 | 43900215201 | 003 | 2 |  | 1 | 007 | 20460.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 003 | 2 |  | 2 | 004 | 1938.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1768 | 43900215201 | 015 | 2 |  | 1 | 106 | 17362.43 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1768 | 43900215201 | 022 | 2 |  | 1 | 105 | 11097.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1768 | 43900215201 | 022 | 2 |  | 2 | 007 | 12766.55 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 022 | 2 |  | 3 | 007 | 30400.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 022 | 2 |  | 4 | 106 | 20875.8 | 0 | 2 |  | N | 32 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1775 | 44151915201 | 001 | 2 |  | 1 | 101 | 21906.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1775 | 44151915201 | 004 | 2 |  | 1 | 101 | 7832 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1789 | 43693115201 | 006 | 2 |  | 1 | 305 | -37371.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1796 | 44050815201 | 001 | 2 |  | 1 | 101 | 87459.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1796 | 44050815201 | 002 | 2 |  | 1 | 007 | 81012.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E20D9 | 44703115201 | 010 | 2 |  | 1 | 105 | 64238.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20D9 | 44703115201 | 010 | 2 |  | 2 | 105 | 100336.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20D9 | 44703115201 | 010 | 2 |  | 3 | 105 | 12820.21 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 006 | 2 |  | 1 | 004 | 17097.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V69 | 21327275201 | 014 | 2 |  | 1 | 001 | 208477.5 | 208477.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 024 | 2 |  | 1 | 503 | 6856.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 033 | 2 |  | 1 | 003 | 5110.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 036 | 2 |  | 1 | 112 | 2121.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 039 | 2 |  | 1 | 112 | 58190.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 041 | 2 |  | 1 | 001 | 32229.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 042 | 2 |  | 1 | 010 | 4365.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V69 | 21327275201 | 050 | 2 |  | 1 | 105 | 28860.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 2 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 3 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 055 | 2 | 850 | 1 | 850 | 75000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2V69 | 21327275201 | 057 | 2 |  | 1 | 503 | 480457.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 057 | 2 |  | 2 | 019 | 7980 | 7980 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 4 | 003 | 10110.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 16 | 860 | 0 | 0 | 0 |  | E | 60 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2W84 | 43384215201 | 030 | 2 |  | 1 | 860 | 1396122.44 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2Y24 | 43743715201 | 001 | 2 |  | 1 | 305 | -75887.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 1 | 001 | 4538.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 2 | 115 | 14410.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 3 | 003 | 18671.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Y81 | 43197915201 | 036 | 2 |  | 1 | 019 | 69880.67 | 69880.67 | 0 |  | N | 50 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2Y81 | 43197915201 | 036 | 2 |  | 2 | 107 | 2085.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Y81 | 43197915201 | 036 | 2 |  | 3 | 107 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Z36 | 43930315201 | 010 | 2 |  | 1 | 001 | 15181.94 | 0 | 0 |  | C | 89 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Z36 | 43930315201 | 010 | 2 |  | 2 | 001 | 42943.63 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Z36 | 43930315201 | 012 | 2 |  | 1 | 012 | 24281 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2Z50 | 42848915201 | 012 | 2 | 850 | 1 | 101 | 49467.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 | 014 | 2 |  | 1 | 101 | -184.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z51 | 43384115201 | 007 | 2 |  | 1 | 107 | 3946.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 009 | 2 |  | 1 | 101 | 492951.39 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 013 | 2 |  | 1 | 101 | 30144 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 018 | 2 |  | 1 | 005 | 73830.92 | 73830.92 | 5 |  | N | 23 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 021 | 2 |  | 1 | 919 | 36934.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 1 | 305 | -73244.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 2 | 005 | 60730.52 | 60730.52 | 5 |  | N | 13 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 3 | 024 | 27317 | 27317 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 4 | 001 | 97023.25 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 1 | 107 | 10344.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 2 | 005 | 4660.02 | 4660.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 036 | 2 | 850 | 3 | 107 | 2429.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 4 | 001 | 1009.96 | 1009.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 5 | 115 | 12188.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 6 | 008 | 5733.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 7 | 107 | 29247.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 8 | 010 | 12369.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 036 | 2 | 850 | 9 | 107 | 36401.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 10 | 115 | 3026.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 11 | 503 | 2818 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 12 | 923 | 1157.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 13 | 107 | 26690.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 14 | 015 | 1922.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 1 | 015 | 17510.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 2 | 015 | 1659.82 | 1659.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 3 | 015 | 761.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 4 | 015 | 11041.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 5 | 015 | 1087.23 | 1087.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 8 | 015 | 3160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 7 | 015 | 15222.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 6 | 015 | 22572.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 047 | 2 |  | 1 | 015 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 051 | 2 |  | 1 | 107 | 75248.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 1 | 107 | 23122.83 | 3011.06 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 2 | 107 | 6833.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 3 | 503 | 5485.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 059 | 2 | 850 | 4 | 107 | 814.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 5 | 107 | 20079.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 8 | 004 | 33575.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 7 | 004 | 956.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 6 | 001 | 59132.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 073 | 2 |  | 1 | 015 | 350144.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 1 | 004 | 9699.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 2 | 008 | 14103.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 3 | 010 | 7905 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 082 | 2 | 850 | 4 | 004 | 360.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 5 | 105 | 46101.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 6 | 107 | 28452.39 | 5644.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 8 | 107 | 16582.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 9 | 107 | 7513.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 087 | 2 |  | 1 | 010 | 109704 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 093 | 2 |  | 1 | 024 | 6339.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 015 | 2 |  | 1 | 101 | 55058.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 023 | 2 |  | 1 | 001 | 1040278.96 | 0 | 1 |  | N | 111 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 1 | 015 | 2217.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 2 | 007 | 16362.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 3 | 106 | 441.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2579 | 21071245201 | 030 | 2 | 850 | 4 | 007 | 787.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 5 | 007 | 2265 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 6 | 007 | 4071.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 7 | 007 | 3495.07 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 10 | 015 | 11806.81 | 11806.81 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 9 | 007 | 3812.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 8 | 007 | 4740 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 1 | 012 | 3451.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 2 | 101 | 2380.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 031 | 2 | 850 | 3 | 012 | 91578.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 4 | 001 | 1604.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 5 | 012 | 47075.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 6 | 012 | 3909.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 037 | 2 |  | 1 | 919 | 119738.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 1 | 012 | 2703.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 2 | 012 | 19885.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 3 | 105 | 2805 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 4 | 115 | 31923.17 | 3873 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 5 | 012 | 39021.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 6 | 101 | 10730 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 7 | 018 | 18558.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 8 | 115 | 9222.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 9 | 105 | 5610 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 12 | 115 | 3930 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 11 | 105 | 2805 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 10 | 105 | 2805 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 049 | 2 |  | 1 | 117 | 149247.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2579 | 21071245201 | 055 | 2 |  | 1 | 010 | 37042.43 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 058 | 2 |  | 1 | 015 | 231148.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 067 | 2 |  | 1 | 012 | 293674.26 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 070 | 2 |  | 1 | 503 | 5468.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2579 | 21071245201 | 074 | 2 | 850 | 1 | 115 | 15164.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 2 | 004 | 7017.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2579 | 21071245201 | 074 | 2 | 850 | 3 | 112 | 11207.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 4 | 115 | 7805.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 5 | 001 | 6829.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 074 | 2 | 850 | 6 | 010 | 101975.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 075 | 2 | 850 | 1 | 015 | 18377.75 | 18377.75 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 075 | 2 | 850 | 2 | 015 | 3063.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 094 | 2 |  | 1 | 923 | 112708.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 102 | 2 |  | 1 | 113 | 125609.51 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 109 | 2 |  | 1 | 015 | 299.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 109 | 2 |  | 2 | 015 | 119832.08 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 109 | 2 |  | 3 | 015 | 14124.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 1 | 010 | 4703.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 117 | 2 | 850 | 2 | 003 | 9767.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 3 | 001 | 2938.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 4 | 101 | 544.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 124 | 2 |  | 1 | 005 | 9951.39 | 9951.39 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 2 | 005 | 62482.95 | 62482.95 | 5 |  | C | 6 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 3 | 005 | 8150.56 | 8150.56 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 4 | 005 | 12925.17 | 12925.17 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 5 | 005 | 50512.75 | 50512.75 | 5 |  | C | 4 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 6 | 005 | 28570.45 | 28570.45 | 5 |  | C | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 7 | 005 | 86101.38 | 86101.38 | 5 |  | C | 6 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 8 | 005 | 10227.47 | 10227.47 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 9 | 005 | 36925.49 | 36925.49 | 5 |  | C | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 10 | 005 | 13932.78 | 13932.78 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 129 | 2 |  | 1 | 005 | 55010.17 | 55010.17 | 5 |  | C | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2641 | 20953745201 | 003 | 2 |  | 1 | 101 | 7422.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 003 | 2 |  | 2 | 101 | 14852.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 015 | 2 |  | 1 | 919 | 98752.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 035 | 2 |  | 1 | 105 | 82701.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 | 038 | 2 |  | 1 | 503 | 24844.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2641 | 20953745201 | 040 | 2 |  | 1 | 003 | 431652.13 | 64955.38 | 0 |  | N | 82 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 1 | 923 | 56591.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 2 | 024 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 3 | 003 | 6852.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 4 | 024 | 8270.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 5 | 022 | 713.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 052 | 2 |  | 1 | 010 | 103206.76 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2641 | 20953745201 | 054 | 2 |  | 1 | 003 | 111065.72 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 059 | 2 |  | 1 | 004 | 271448.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2641 | 20953745201 | 062 | 2 |  | 1 | 003 | 141296.64 | 0 | 0 |  | N | 59 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 065 | 2 |  | 1 | 003 | 488774.79 | 0 | 0 |  | C | 73 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 070 | 2 | 850 | 1 | 105 | 136990.86 | 136990.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2700 | 41525015201 | 024 | 2 |  | 1 | 923 | 39169.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2700 | 41525015201 | 028 | 2 |  | 1 | 001 | 7570.83 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 2 | 015 | 10265.52 | 10265.52 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 3 | 012 | 38395.89 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2700 | 41525015201 | 032 | 2 |  | 1 | 004 | 39606.27 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 1 | 122 | 3256.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 2 | 001 | 6443.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 3 | 115 | 70103.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 4 | 015 | 22002.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 5 | 101 | 6750.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2712 | 43240415201 | 020 | 2 |  | 1 | 005 | 12014.29 | 12014.29 | 5 |  | N | 22 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2712 | 43240415201 | 025 | 2 |  | 1 | 503 | 40265.21 | 40265.21 | 0 |  | N | 131 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2712 | 43240415201 | 032 | 2 |  | 1 | 860 | 0 | 0 | 5 |  | N | 59 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | T2720 | 43735415201 | 062 | 2 |  | 1 | 106 | 29793.04 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 063 | 2 |  | 1 | 106 | 102561.17 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 064 | 2 |  | 1 | 106 | 24056.03 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 065 | 2 |  | 1 | 107 | 10252.77 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2743 | 42845515201 | 001 | 2 |  | 1 | 003 | 139983.91 | 0 | 0 |  | N | -30 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 1 | 305 | -125662.02 | 0 | 0 |  | N | -5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 2 | 003 | 3465 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 3 | 305 | -385909.61 | 0 | 0 |  | N | -5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 4 | 010 | 39780 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2743 | 42845515201 | 021 | 2 |  | 1 | 101 | 27147.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2743 | 42845515201 | 034 | 2 |  | 1 | 010 | 865004.19 | 590740.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2753 | 43980015201 | 005 | 2 |  | 1 | 001 | 425405.64 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2760 | 44125815201 | 012 | 2 |  | 1 | 001 | 124056.15 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2762 | 44499015201 | 005 | 2 |  | 1 | 128 | 26250 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2762 | 44499015201 | 010 | 2 |  | 1 | 007 | 60833.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2770 | 43948915201 | 007 | 2 |  | 1 | 007 | -4773.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2778 | 44105715201 | 003 | 2 | 850 | 2 | 106 | 5059.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T9022 | 44531935223 | 001 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 011 | 2 |  | 1 | 101 | 40091.64 | 6445.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T9022 | 44531935223 | 012 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 013 | 2 | 850 | 1 | 850 | -50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 021 | 2 |  | 1 | 922 | 6861.84 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 028 | 2 |  | 1 | 922 | 11333.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 029 | 2 |  | 1 | 922 | 9658.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 030 | 2 |  | 1 | 922 | 21263.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3S42 | 42187345201 | 012 | 2 |  | 1 | 001 | 0 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 2 | 023 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 3 | 001 | 0 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3T35 | 44291315201 | 006 | 2 |  | 1 | 503 | 7383 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T35 | 44291315201 | 009 | 2 |  | 1 | 503 | 85422.8 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T58 | 43815415201 | 007 | 2 |  | 1 | 503 | 14820.6 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T96 | 4453581G201 | 004 | 2 |  | 1 | 010 | 582768.6 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3646 | 22049585201 | 002 | 2 |  | 1 | 004 | 28644 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3646 | 22049585201 | 004 | 2 |  | 1 | 105 | 15970.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3646 | 22049585201 | 008 | 2 |  | 1 | 101 | 7260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3646 | 22049585201 | 016 | 2 |  | 1 | 922 | 55072.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3646 | 22049585201 | 027 | 2 |  | 1 | 112 | 149452.21 | 73650.34 | 1 |  | N | 25 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3689 | 21876425201 | 011 | 2 |  | 1 | 103 | 182665.96 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 015 | 2 |  | 1 | 103 | 75030 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 023 | 2 |  | 1 | 103 | 81936 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 031 | 2 |  | 1 | 103 | 140395.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 034 | 2 |  | 1 | 107 | -3924.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 003 | 2 |  | 1 | 105 | -33822.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 004 | 2 |  | 1 | 105 | -2247.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 011 | 2 |  | 1 | 101 | 310.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3692 | 43774615201 | 014 | 2 |  | 1 | 003 | 31379.15 | 0 | 1 |  | E | 1 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3692 | 43774615201 | 015 | 2 |  | 1 | 115 | 10200.5 | 12735.38 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 016 | 2 |  | 1 | 105 | 33837.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 019 | 2 |  | 1 | 105 | 34180.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 021 | 2 | 850 | 1 | 010 | 2521.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 | 021 | 2 | 850 | 2 | 003 | 19016.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3692 | 43774615201 | 021 | 2 | 850 | 3 | 010 | 1431.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 | 021 | 2 | 850 | 4 | 115 | 3661.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 022 | 2 |  | 1 | 105 | -22782.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 023 | 2 |  | 1 | 105 | 65206.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 031 | 2 |  | 1 | 503 | 211388.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3692 | 43774615201 | 037 | 2 |  | 1 | 105 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 042 | 2 |  | 1 | 105 | 3824.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 053 | 2 |  | 1 | 118 | 5720 | 3899.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3692 | 43774615201 | 055 | 2 |  | 1 | 927 | 12033.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3699 | 43228415201 | 025 | 2 |  | 1 | 003 | -30186.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3717 | 43720215201 | 007 | 2 |  | 1 | 001 | 27244.97 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3723 | 43972115201 | 012 | 2 |  | 1 | 010 | 58629.33 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3729 | 43972715201 | 020 | 2 |  | 1 | 700 | 204347 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3738 | 44173815201 | 012 | 2 |  | 1 | 503 | 483.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3738 | 44173815201 | 016 | 2 |  | 1 | 101 | 34377.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3738 | 44173815201 | 017 | 2 |  | 1 | 503 | 2342.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 | 006 | 2 |  | 1 | 503 | 9174.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 | 020 | 2 |  | 1 | 001 | 29854.35 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3745 | 43972915201 | 028 | 2 |  | 1 | 001 | 57241.58 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3763 | 43661515201 | 009 | 2 |  | 1 | 101 | 8960 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U24 | 43984115201 | 002 | 2 |  | 1 | 007 | -10792.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U24 | 43984115201 | 002 | 2 |  | 2 | 503 | 1766.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 | 002 | 2 |  | 3 | 004 | 8626.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U54 | 44330915201 | 003 | 2 |  | 1 | 105 | 15485.58 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4U74 | 44162815201 | 005 | 2 |  | 1 | 007 | -1110.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 007 | 2 |  | 1 | 305 | -33901.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 009 | 2 |  | 1 | 305 | -12727.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 022 | 2 |  | 1 | 106 | 24234.44 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 022 | 2 |  | 2 | 005 | 74911.83 | 74911.83 | 5 |  | N | 42 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 029 | 2 |  | 1 | 923 | 15618.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 031 | 2 | 850 | 1 | 118 | 3043.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4471 | 43472215201 | 031 | 2 | 850 | 2 | 503 | 4841.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 031 | 2 | 850 | 3 | 926 | 2264.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 038 | 2 |  | 1 | 101 | 4510 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 038 | 2 |  | 2 | 503 | -4560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 040 | 2 |  | 1 | 106 | 30458.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 1 | 106 | 3312.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 2 | 503 | 41959.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 041 | 2 |  | 3 | 101 | 8500 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 4 | 004 | 20679.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4471 | 43472215201 | 042 | 2 |  | 1 | 106 | 6112.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 045 | 2 |  | 1 | 001 | 7296.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 | 050 | 2 |  | 1 | 007 | -60.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 056 | 2 |  | 1 | 023 | 4749.8 | 4749.8 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 058 | 2 |  | 1 | 007 | 8142.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 061 | 2 |  | 1 | 101 | 4496.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 061 | 2 |  | 2 | 003 | 737.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 1 | 003 | 3472.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 2 | 023 | 20562.49 | 20562.49 | 5 |  | N | 6 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 3 | 024 | 327.91 | 327.91 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 4 | 101 | 7992.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 062 | 2 |  | 5 | 105 | 10544.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4471 | 43472215201 | 062 | 2 |  | 6 | 860 | 48303.09 | 48303.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 7 | 924 | 0 | 0 | 0 |  | N | 34 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 8 | 924 | 0 | 0 | 0 |  | N | 81 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 9 | 106 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4476 | 43515815201 | 029 | 2 |  | 1 | 923 | 12568.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4476 | 43515815201 | 038 | 2 |  | 1 | 005 | 100872.64 | 100872.64 | 5 |  | N | 60 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4476 | 43515815201 | 038 | 2 |  | 2 | 005 | 7114.93 | 7114.93 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4476 | 43515815201 | 038 | 2 |  | 3 | 001 | 6776.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815201 | 038 | 2 |  | 4 | 105 | 58474.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4476 | 43515815201 | 038 | 2 |  | 5 | 118 | 3010.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815201 | 048 | 2 |  | 1 | 115 | -4670 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4476 | 43515815201 | 059 | 2 |  | 1 | 105 | 40014.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4476 | 43515815201 | 059 | 2 |  | 2 | 860 | 34366.05 | 34366.05 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4488 | 43630415201 | 017 | 2 |  | 1 | 860 | 28229.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4488 | 43630415201 | 017 | 2 |  | 2 | 118 | 22219.44 | 22219.44 | 4 |  | N | 0 | Avoidable, In-House CEI | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4494 | 43630715201 | 004 | 2 |  | 1 | 101 | 17582.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4494 | 43630715201 | 012 | 2 |  | 1 | 005 | 7756.24 | 7756.24 | 5 |  | C | 14 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4494 | 43630715201 | 020 | 2 |  | 1 | 001 | 56846.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4494 | 43630715201 | 031 | 2 |  | 1 | 106 | 78304.94 | 78304.94 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 1 | 106 | 8994.35 | 8994.35 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 2 | 105 | 3102.2 | 3102.2 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 3 | 106 | 9557.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 1 | 108 | 33739.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 2 | 007 | 4838.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4497 | 43783615201 | 010 | 2 |  | 3 | 108 | 59290 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 020 | 2 |  | 1 | 923 | 11340.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 027 | 2 |  | 1 | 004 | 143232.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 | 029 | 2 |  | 1 | 126 | 114822 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | T4497 | 43783615201 | 033 | 2 |  | 1 | 101 | -4821.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4497 | 43783615201 | 041 | 2 |  | 1 | 001 | 656775.31 | 656775.31 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 043 | 2 |  | 1 | 001 | 42114.46 | 42114.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 046 | 2 |  | 1 | 001 | 427380.56 | 427380.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 047 | 2 |  | 1 | 001 | 23184.23 | 23184.23 | 0 |  | C | 35 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 052 | 2 |  | 1 | 001 | 190000 | 190000 | 0 |  | C | 16 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 007 | 2 |  | 1 | 101 | 48087.98 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4504 | 43783815201 | 014 | 2 |  | 1 | 113 | 127922.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4504 | 43783815201 | 025 | 2 |  | 1 | 001 | 781896 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 025 | 2 |  | 2 | 503 | -121762.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 009 | 2 |  | 1 | 305 | -99541.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 028 | 2 |  | 1 | 926 | 1686.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 014 | 2 |  | 1 | 923 | 10823.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 029 | 2 |  | 1 | 105 | 82698 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4509 | 43177055201 | 034 | 2 |  | 1 | 113 | 68788 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4511 | 43469015201 | 021 | 2 |  | 1 | 106 | -58454.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4523 | 43469515201 | 009 | 2 |  | 1 | 300 | -28976.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
04 | T4523 | 43469515201 | 022 | 2 |  | 1 | 503 | 62365.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 | 028 | 2 |  | 1 | 503 | 40627.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4530 | 43592515201 | 013 | 2 |  | 1 | 004 | 8037.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4530 | 43592515201 | 032 | 2 |  | 1 | 118 | 31565.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E50A9 | 44326415201 | 002 | 2 |  | 1 | 012 | 90009.22 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E50A9 | 44326415201 | 002 | 2 |  | 2 | 126 | -59600 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E52A2 | 44316815201 | 015 | 2 |  | 1 | 003 | -17404.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E52A2 | 44316815201 | 015 | 2 |  | 2 | 118 | 2619 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 005 | 2 |  | 1 | 004 | 10000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 1 | 115 | 1981.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 2 | 115 | 5465.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 3 | 115 | 12624.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 4 | 115 | 8223.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 5 | 115 | 7352.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 9 | 001 | 9367.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 6 | 115 | 2720.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 7 | 115 | 2429.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 8 | 115 | 10943.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 10 | 001 | 21857.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 16 | 105 | 165 | 165 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 17 | 001 | 13197.99 | 7993.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 18 | 106 | 13796.45 | 13796.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 11 | 101 | 3692.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 12 | 115 | 11105.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 13 | 001 | 18373.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 14 | 115 | 3396.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 15 | 122 | 3306.18 | 3024.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 026 | 2 |  | 1 | 503 | 168782.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z71 | 43179835201 | 029 | 2 |  | 1 | 015 | 91114.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 030 | 2 |  | 1 | 001 | 512140.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 036 | 2 |  | 1 | 001 | 24832.59 | 9774.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 040 | 2 | 850 | 1 | 001 | 21772.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 040 | 2 | 850 | 2 | 024 | 14196.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z86 | 43913615201 | 015 | 2 | 850 | 1 | 105 | 58655.11 | 58655.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z86 | 43913615201 | 015 | 2 | 850 | 2 | 024 | 364.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z88 | 43793715201 | 011 | 2 |  | 1 | 926 | 2981.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z90 | 44326915201 | 016 | 2 |  | 1 | 012 | 42878.1 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5538 | 23949635201 | 020 | 2 |  | 1 | 105 | 3577.8 | 893.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 | 033 | 2 |  | 1 | 118 | 28062.05 | 5406 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 043 | 2 |  | 1 | 923 | 36110.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 046 | 2 |  | 1 | 007 | 111063.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5538 | 23949635201 | 052 | 2 |  | 1 | 860 | 6449.59 | 6449.59 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
05 | T5538 | 23949635201 | 059 | 2 |  | 1 | 112 | 58725.69 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 083 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 66 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 101 | 2 |  | 1 | 860 | 130760.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 001 | 2 |  | 1 | 919 | 6918.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 037 | 2 |  | 1 | 923 | 1536.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 038 | 2 |  | 1 | 105 | 103979.5 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 2 | 107 | 6025.5 | 0 | 0 |  | N | 143 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 3 | 105 | -202363.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 4 | 503 | -3834 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5582 | 23827585201 | 038 | 2 |  | 5 | 101 | 33771.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 6 | 105 | -1936 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 7 | 503 | 64272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5628 | 43734115201 | 027 | 2 |  | 1 | 003 | -4.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5637 | 43386015201 | 002 | 2 |  | 1 | 107 | 400900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 008 | 2 |  | 1 | 107 | 50537.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 013 | 2 |  | 1 | 107 | 2706273 | 0 | 0 |  | N | 390 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 014 | 2 |  | 1 | 107 | 74935.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 018 | 2 |  | 1 | 923 | 3530.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 052 | 2 |  | 1 | 860 | 17000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5668 | 43968235201 | 001 | 2 |  | 1 | 003 | 168079.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 012 | 2 |  | 1 | 003 | 21942.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 012 | 2 |  | 2 | 106 | 594995.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 026 | 2 |  | 1 | 003 | 5260.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 2 | 106 | 90177.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 026 | 2 |  | 3 | 003 | 36294.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 4 | 003 | 784264.06 | 0 | 0 |  | N | 135 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 5 | 001 | 184228.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 029 | 2 |  | 1 | 106 | 44097.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 031 | 2 |  | 1 | 003 | 331170.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 1 | 023 | 170.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 2 | 101 | 13398 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 3 | 003 | 24061.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 4 | 001 | 8861.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 5 | 101 | 6641.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 6 | 003 | 3570.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 7 | 101 | 3520 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 8 | 101 | 4900.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 9 | 023 | 18993.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 10 | 024 | 779 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 042 | 2 |  | 1 | 001 | 327471.54 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 042 | 2 |  | 2 | 503 | 36216.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 042 | 2 |  | 3 | 003 | 67341.53 | 2589 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 043 | 2 |  | 1 | 003 | 53033.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 046 | 2 | 850 | 1 | 003 | 10127.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 046 | 2 | 850 | 2 | 115 | 2924.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 3 | 101 | 1905.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 4 | 101 | 3955.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 5 | 503 | 13454.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 1 | 101 | -4700.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 052 | 2 |  | 2 | 503 | 22993.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 3 | 503 | 20365.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 4 | 021 | 18403.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 5 | 503 | 8728.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 6 | 503 | -10102.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 7 | 001 | 87500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 055 | 2 |  | 1 | 024 | 10336.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 | 019 | 2 |  | 1 | 001 | 19098.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 | 020 | 2 |  | 1 | 118 | 24154.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5669 | 43923515201 | 023 | 2 |  | 1 | 007 | 29083.64 | 19393.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5669 | 43923515201 | 024 | 2 |  | 1 | 007 | 0 | 0 | 0 |  | N | 97 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5670 | 43020245201 | 004 | 2 |  | 1 | 923 | 9755.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5670 | 43020245201 | 005 | 2 |  | 1 | 105 | 14862.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 | 010 | 2 |  | 1 | 106 | 42923.56 | 7656 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5670 | 43020245201 | 030 | 2 |  | 1 | 926 | 484.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5670 | 43020245201 | 031 | 2 |  | 1 | 503 | 2274.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5670 | 43020245201 | 034 | 2 |  | 1 | 106 | 9845.01 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 | 012 | 2 |  | 1 | 101 | 12029.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 | 025 | 2 |  | 1 | 107 | 10878.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5678 | 43913115201 | 011 | 2 |  | 1 | 105 | 85887 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5681 | 43968215201 | 010 | 2 |  | 1 | 105 | 3359.62 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 1 | 012 | 85040.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 2 | 018 | 14265.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 3 | 503 | 18539.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 006 | 2 |  | 1 | 305 | -57170.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 008 | 2 |  | 1 | 503 | 230912.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 014 | 2 |  | 1 | 503 | 110000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 031 | 2 |  | 1 | 923 | 55650.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 034 | 2 |  | 1 | 012 | 243154.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 | 043 | 2 |  | 1 | 120 | 232450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
06 | E6K73 | 43653715201 | 014 | 2 |  | 1 | 012 | 60602.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 008 | 2 |  | 1 | 305 | -501344.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 017 | 2 | 850 | 1 | 503 | 16908.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 1 | 023 | 8091.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 2 | 023 | 1563.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 3 | 021 | 6782.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 10 | 023 | 306.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 4 | 023 | 7570.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 5 | 023 | 1719.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 6 | 023 | 2555.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 7 | 023 | 14691.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 8 | 503 | 60557.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 9 | 503 | 29209.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 025 | 2 |  | 1 | 919 | 519737.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 042 | 2 |  | 1 | 004 | 700013.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 1 | 023 | 16355.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 2 | 023 | 2109.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 3 | 023 | 13547.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 4 | 023 | 15948.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 7 | 012 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 8 | 023 | 1759.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 9 | 023 | 918.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 6 | 012 | 68465.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 5 | 012 | 7124.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 069 | 2 |  | 1 | 012 | 239955.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 1 | 012 | 40892.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 2 | 023 | 55909.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 3 | 023 | 4714.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 4 | 023 | 632.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 5 | 012 | 7710.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 6 | 023 | 3363.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 7 | 001 | 10625.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 8 | 001 | 7441.6 | 7441.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 9 | 012 | 1732.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 1 | 023 | 52390.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 2 | 012 | 4041.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 3 | 503 | 70110.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 083 | 2 |  | 1 | 923 | 41367.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 086 | 2 |  | 1 | 019 | -251871.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6K77 | 42930035201 | 088 | 2 |  | 1 | 001 | 126715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 091 | 2 |  | 1 | 503 | 187228.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 010 | 2 |  | 1 | 503 | 53775.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 025 | 2 |  | 1 | 503 | 52010.04 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M32 | 44204015201 | 009 | 2 |  | 1 | 007 | -3128331.59 | 231933.48 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M32 | 44204015201 | 011 | 2 |  | 1 | 007 | -70000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M47 | 44196115201 | 002 | 2 | 850 | 1 | 850 | 16612 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | E6M47 | 44196115201 | 005 | 2 | 850 | 2 | 503 | 2164.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6460 | 43081745201 | 017 | 2 | 850 | 1 | 115 | 13445.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6460 | 43081745201 | 017 | 2 | 850 | 2 | 012 | 11604.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6460 | 43081745201 | 018 | 2 | 850 | 1 | 101 | 30673.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081745201 | 018 | 2 | 850 | 2 | 001 | 4407.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6465 | 43345535201 | 013 | 2 |  | 1 | 503 | 68789.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 1 | 101 | 6599.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 009 | 2 | 850 | 2 | 001 | 1861.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 3 | 001 | 4691.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 4 | 001 | 3626.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 5 | 001 | 1264.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 6 | 503 | 7672.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 7 | 001 | 1685.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 8 | 503 | 16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 9 | 503 | -19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 10 | 503 | 19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 11 | 503 | 16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 12 | 503 | -16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 15 | 503 | 3750.01 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 13 | 101 | -6599.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 009 | 2 | 850 | 14 | 101 | 7919.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 017 | 2 | 850 | 1 | 503 | 6279.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 2 | 503 | 10372.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 3 | 503 | 8570.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 4 | 022 | 6268.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 6 | 503 | 15906.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 1 | 503 | 12905.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 2 | 903 | 1102.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6469 | 42930045201 | 019 | 2 | 850 | 3 | 503 | 6932.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 4 | 503 | 25208.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 020 | 2 | 850 | 1 | 503 | 19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 | 018 | 2 | 850 | 1 | 503 | 24400.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 | 019 | 2 |  | 1 | 503 | 3628.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 | 024 | 2 |  | 1 | 103 | 22965.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6483 | 44016915201 | 027 | 2 |  | 1 | 106 | 14459.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6493 | 44331415201 | 001 | 2 |  | 1 | 305 | -121048.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6493 | 44331415201 | 017 | 2 |  | 1 | 503 | 6499.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44331415201 | 019 | 2 |  | 1 | 503 | 64500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M81 | 44335315201 | 008 | 2 |  | 1 | 105 | 13287.38 | 0 | 0 |  | N | 86 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M93 | 44383215201 | 011 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7M93 | 44383215201 | 014 | 2 | 850 | 1 | 850 | 9531.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7M96 | 43762615201 | 004 | 2 |  | 1 | 007 | 8496.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 013 | 2 |  | 1 | 101 | 23017.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7N02 | 44383315201 | 005 | 2 |  | 1 | 004 | 4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N02 | 44383315201 | 006 | 2 |  | 1 | 860 | 45000 | 16551.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | E7N15 | 44539915201 | 005 | 2 |  | 1 | 105 | 40818.19 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 | 006 | 2 | 850 | 1 | 105 | 5117.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 | 006 | 2 | 850 | 2 | 112 | 747.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N15 | 44539915201 | 011 | 2 |  | 1 | 850 | 50487.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7N15 | 44539915201 | 012 | 2 |  | 1 | 850 | 27307.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 1 | 503 | 27181.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 2 | 021 | 3097.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 3 | 024 | 3132.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 4 | 024 | 5343.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 5 | 107 | 11440.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 6 | 024 | 2989.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 7 | 024 | 1987.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 8 | 021 | 1495.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 10 | 503 | 2226.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 9 | 021 | 2047.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 012 | 2 |  | 1 | 106 | 214437.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 013 | 2 |  | 1 | 305 | -58626.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 014 | 2 |  | 1 | 305 | -1644.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 016 | 2 |  | 1 | 503 | 175123.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 018 | 2 |  | 1 | 305 | -83500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 019 | 2 |  | 1 | 305 | -17754.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 027 | 2 |  | 1 | 503 | -20942.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 027 | 2 |  | 2 | 305 | -5652.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 028 | 2 | 850 | 1 | 850 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7R17 | 44368415201 | 003 | 2 |  | 1 | 004 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 | 010 | 2 |  | 1 | 122 | 348683.36 | 0 | 2 |  | N | 37 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7R17 | 44368415201 | 010 | 2 |  | 2 | 118 | 13692.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7R17 | 44368415201 | 022 | 2 |  | 1 | 012 | 16954.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 | 004 | 2 | 850 | 1 | 850 | 43458.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7385 | 25624325201 | 003 | 2 |  | 1 | 101 | 9360 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 003 | 2 |  | 2 | 003 | 78500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 003 | 2 |  | 3 | 101 | 18123.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 1 | 108 | 4652.82 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 2 | 003 | 2648.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 3 | 112 | 105000 | 14595.79 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 4 | 107 | 3985.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 5 | 007 | 4640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 6 | 007 | 6026.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 7 | 107 | 8324.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 9 | 107 | 11722.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 8 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 018 | 2 |  | 1 | 007 | 321706.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 018 | 2 |  | 2 | 101 | 31347.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 024 | 2 |  | 1 | 919 | 18470.4 | 18470.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 1 | 112 | 154658.68 | 48714 | 2 |  | N | 59 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 2 | 112 | 5210.71 | 5210.71 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 3 | 106 | 7226.87 | 7226.87 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 1 | 112 | 50593.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 2 | 107 | 10923.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 3 | 105 | 12628.34 | 750.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 4 | 115 | 3762 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 5 | 115 | 3870.25 | 3870.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 032 | 2 |  | 1 | 503 | 274021.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7385 | 25624325201 | 038 | 2 |  | 1 | 015 | 210084.2 | 17710.37 | 2 |  | N | 16 | Avoidable, In-House Designer | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 047 | 2 |  | 1 | 019 | 57447.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 049 | 2 |  | 1 | 112 | 312932.93 | 223679.73 | 2 |  | N | 15 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 1 | 122 | 3130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 2 | 118 | 35441.79 | 27604.6 | 2 |  | N | 28 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 3 | 113 | 51000 | 51000 | 2 |  | N | 8 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 4 | 019 | 3526.94 | 3526.94 | 5 |  | N | 15 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 5 | 007 | 1200 | 1200 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 6 | 126 | 370.04 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 7 | 113 | 490 | 490 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 8 | 128 | 1121.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 9 | 003 | 3897.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 10 | 015 | 0 | 0 | 5 |  | N | 18 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 11 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7385 | 25624325201 | 054 | 2 |  | 1 | 001 | 20259.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 010 | 2 | 850 | 1 | 117 | 3454.31 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 | 010 | 2 | 850 | 2 | 003 | 6906.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 010 | 2 | 850 | 3 | 105 | 20035.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7386 | 43002115201 | 010 | 2 | 850 | 4 | 107 | 7991.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 012 | 2 |  | 1 | 009 | 67157.31 | 67157.31 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 021 | 2 |  | 1 | 919 | 26926.07 | 26926.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 1 | 001 | 646831.85 | 0 | 0 |  | N | 202 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 2 | 001 | 372527.15 | 128778.18 | 0 |  | N | 98 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 3 | 009 | 271219.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 4 | 001 | 29381 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 031 | 2 | 850 | 1 | 115 | 7985.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 041 | 2 | 850 | 1 | 850 | 62000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7386 | 43002115201 | 043 | 2 |  | 1 | 860 | -306142.9 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | T7386 | 43002115201 | 043 | 2 |  | 2 | 003 | 17528.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 3 | 107 | 14495.74 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 4 | 003 | 7136.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 5 | 013 | 6810 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 6 | 107 | 33139.86 | 0 | 2 |  | N | 6 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 7 | 107 | 19420.44 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 8 | 115 | 17866.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7410 | 43649515201 | 006 | 2 |  | 1 | 107 | 1002574.87 | 0 | 1 |  | N | 70 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7410 | 43649515201 | 020 | 2 |  | 1 | 015 | 7859.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 2 | 015 | 18455.83 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 3 | 015 | 8886.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 4 | 015 | 11010.82 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 5 | 015 | 18534.92 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 6 | 015 | 831776.79 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 030 | 2 | 850 | 1 | 118 | 52233.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7410 | 43649515201 | 037 | 2 |  | 1 | 015 | 325000 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 050 | 2 |  | 1 | 503 | 13361 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7437 | 43605615201 | 005 | 2 |  | 1 | 305 | -8336.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7437 | 43605615201 | 008 | 2 |  | 1 | 012 | 163058.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7437 | 43605615201 | 008 | 2 |  | 2 | 007 | 133750.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7437 | 43605615201 | 008 | 2 |  | 3 | 126 | -122480 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8N18 | 41505115201 | 034 | 2 |  | 1 | 305 | -172781.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8N18 | 41505115201 | 040 | 2 |  | 1 | 003 | 199426.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 | 051 | 2 |  | 1 | 919 | 95808.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 | 054 | 2 |  | 1 | 503 | 130275.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 | 059 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 1036 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 005 | 2 |  | 1 | 103 | 62681.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 006 | 2 |  | 1 | 101 | 22479 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 009 | 2 |  | 1 | 860 | 61570.19 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 010 | 2 |  | 1 | 107 | -1767730.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 2 | 101 | 131384 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 3 | 503 | 456884.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 010 | 2 |  | 4 | 128 | 34800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 5 | 108 | 80135.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 015 | 2 |  | 1 | 305 | -92048.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 021 | 2 |  | 1 | 919 | 211015.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 024 | 2 |  | 1 | 503 | 158439.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 025 | 2 |  | 1 | 118 | 193527.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 026 | 2 |  | 1 | 128 | 54336.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 1 | 115 | 3480.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 2 | 012 | 25066.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 3 | 012 | 508.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 4 | 503 | 14701.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 6 | 012 | 10436.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 5 | 012 | 1930.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 1 | 012 | 5595.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 2 | 012 | 3037.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 3 | 012 | 3008.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 4 | 012 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 8 | 012 | 2122.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 9 | 012 | 7518.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 10 | 012 | 6470.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 12 | 012 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 20 | 503 | -6626.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 21 | 503 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 19 | 003 | 5751.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 5 | 115 | 4780.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 6 | 012 | 8026.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 7 | 012 | 11017.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 11 | 503 | 2791.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 13 | 012 | -6626.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 14 | 012 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 15 | 019 | 2610.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 16 | 101 | 2867.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 17 | 117 | 48438.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 18 | 503 | 24202.4 | 24202.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 037 | 2 |  | 1 | 004 | 30003.18 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 040 | 2 |  | 1 | 012 | 24623.91 | 24623.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 042 | 2 |  | 1 | 860 | 60654.29 | 36080.95 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 043 | 2 |  | 1 | 503 | 297550.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 047 | 2 |  | 1 | 015 | -146198.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 048 | 2 |  | 1 | 105 | 288837.32 | 0 | 1 |  | C | 3 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 053 | 2 |  | 1 | 922 | 14697.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 056 | 2 |  | 1 | 503 | 505075.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 066 | 2 |  | 1 | 305 | -126787.91 | 0 | 0 |  | N | -6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 067 | 2 |  | 1 | 012 | 62272.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 068 | 2 |  | 1 | 305 | -214564.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 073 | 2 |  | 1 | 007 | 3513792.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 1 | 503 | 4319.62 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 2 | 860 | 20567.95 | 20567.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 3 | 012 | 10580.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 4 | 108 | 26000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 5 | 012 | 8019.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 6 | 012 | 2480.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 7 | 112 | 38750 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 8 | 115 | 2834.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 9 | 105 | 2155.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 10 | 012 | 2883.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 11 | 012 | 4434.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 12 | 003 | 2049.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 13 | 101 | 5817.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 079 | 2 |  | 1 | 860 | 59000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 081 | 2 |  | 1 | 923 | 209769.41 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 082 | 2 |  | 1 | 860 | 15871.26 | 6003.12 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 083 | 2 |  | 1 | 131 | 3500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 094 | 2 |  | 1 | 004 | 17778.5 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 097 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 099 | 2 |  | 1 | 007 | 98417.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 100 | 2 |  | 1 | 860 | 692265.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 109 | 2 |  | 1 | 004 | -3687950.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 109 | 2 |  | 2 | 004 | 1254202.74 | 1254202.74 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 109 | 2 |  | 3 | 118 | 57821.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 109 | 2 |  | 4 | 012 | 107011.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 111 | 2 |  | 1 | 503 | 132410.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 113 | 2 |  | 1 | 126 | 222149.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 113 | 2 |  | 2 | 860 | 78805.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 119 | 2 |  | 1 | 128 | 60973.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 120 | 2 |  | 1 | 860 | 163512.48 | 163512.48 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 122 | 2 |  | 1 | 117 | 97840.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 122 | 2 |  | 2 | 019 | 29666.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 122 | 2 |  | 3 | 012 | 728 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 122 | 2 |  | 4 | 503 | 9907.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 5 | 101 | 1276.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 122 | 2 |  | 6 | 503 | 7780.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 7 | 503 | 4244.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 8 | 101 | 39795.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 125 | 2 |  | 1 | 012 | 110897.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 127 | 2 |  | 1 | 503 | 67262.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 129 | 2 |  | 1 | 503 | -67160.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 1 | 024 | 56632.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 2 | 022 | 77511.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 3 | 023 | 16807.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 4 | 105 | 4993.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 130 | 2 |  | 5 | 001 | 1621.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 130 | 2 |  | 6 | 503 | 10253.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 7 | 010 | 3208.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8Q12 | 41140615201 | 130 | 2 |  | 8 | 019 | 3225.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q95 | 43652015201 | 013 | 2 | 850 | 1 | 012 | 4074.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652015201 | 013 | 2 | 850 | 2 | 107 | 11901.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q95 | 43652015201 | 031 | 2 |  | 1 | 118 | 15743.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R51 | 44132215201 | 011 | 2 |  | 1 | 112 | -311170 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 013 | 2 |  | 1 | 923 | 24000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 020 | 2 |  | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 039 | 2 |  | 1 | 105 | -2099.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R55 | 42815445201 | 008 | 2 |  | 1 | 923 | 27899.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R55 | 42815445201 | 025 | 2 |  | 1 | 126 | 415002.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8S00 | 44106715201 | 005 | 2 |  | 2 | 503 | 12516.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S00 | 44106715201 | 005 | 2 |  | 3 | 101 | 5161.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 | 009 | 2 |  | 1 | 101 | 2532.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S11 | 44029115201 | 004 | 2 |  | 1 | 105 | 130298.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S11 | 44029115201 | 010 | 2 |  | 1 | 107 | 684 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
08 | E8S11 | 44029115201 | 023 | 2 | 850 | 1 | 105 | 14813.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S11 | 44029115201 | 023 | 2 | 850 | 2 | 001 | 4780.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S18 | 44042315201 | 009 | 2 |  | 1 | 001 | 18865.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S63 | 44514015201 | 002 | 2 |  | 1 | 101 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 107 | 1419 | 550 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 29461.04 | 12970.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 4374.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 2 | 003 | 15570.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 26278.05 | 17511.67 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 2 |  | N | 15 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1Q47 | 42584145201 |  | 2 | CPI | 1 | 107 | 1369.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 143 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 482.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 1520.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S02 | 43942515202 |  | 2 | CPI | 1 | 106 | 3274.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1S02 | 43942515201 |  | 2 | CPI | 1 | 503 | 9679.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1S49 | 19602275201 |  | 2 | CPI | 1 | 001 | 2148.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S49 | 19602275201 |  | 2 | CPI | 2 | 107 | 1769.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1S49 | 19602275601 |  | 2 | CPI | 1 | 015 | 10673.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S49 | 19602275202 |  | 2 | CPI | 1 | 007 | 1250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S49 | 19602275201 |  | 2 | CPI | 1 | 929 | 1658.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 105 | 14320.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 001 | 1684.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 2 | 105 | 11683.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1700 | 43088615201 |  | 2 | CPI | 1 | 007 | 3639.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
01 | T1700 | 43088615201 |  | 2 | CPI | 1 | 126 | 5417 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 001 | 1652.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 928 | 12020.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 924 | 4675 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 012 | 12300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 2 | 003 | 866.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 112 | 3547.5 | 3547.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 2 | 128 | 9128.19 | 7615.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 105 | 3791.38 | 3791.38 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 004 | 2850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 924 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 007 | 10864.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 2 | 105 | 3014.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 012 | 4465.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 105 | 5165.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 105 | 900 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 022 | 11834.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 115 | 3421.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 003 | 1638.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1757 | 43943615202 |  | 2 | CPI | 2 | 105 | 2266.78 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 005 | 1271.57 | 1271.57 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1757 | 43943615201 |  | 2 | CPI | 1 | 001 | 9346.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1757 | 43943615201 |  | 2 | CPI | 1 | 118 | 1286.44 | 1286.44 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 118 | 4590.41 | 2967.91 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 2 | 012 | 587.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1757 | 43943615202 |  | 2 | CPI | 3 | 108 | 3189.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1760 | 43943915201 |  | 2 | CPI | 1 | 001 | 8540.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1760 | 43943915201 |  | 2 | CPI | 1 | 024 | 5282.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1760 | 43943915202 |  | 2 | CPI | 1 | 001 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 012 | 5764.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 2 | 001 | 5343.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 2 | 003 | 2789.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 101 | 3016.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 007 | 6236.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1789 | 43693115201 |  | 2 | CPI | 1 | 112 | 898.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E20D9 | 44703115201 |  | 2 | CPI | 1 | 003 | 8890 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 101 | 665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2074.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3176.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 2309.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 4239.59 | 4239.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 304.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 6853 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 769.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 106 | 5995 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 3177.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 001 | 1976.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 106 | 1524.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 868.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 914.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3963.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1829.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2225.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1303.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4799.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 007 | 322.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2217.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | -4239.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 3942.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 5455.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4239.59 | 4239.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 5500 | 933 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 012 | 4244.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2350.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 59910.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 010 | 24691.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 861 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 108 | 4829.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 101 | 19008 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 503 | 4829.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y79 | 20968315201 |  | 2 | CPI | 2 | 024 | 16911.71 | 16911.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y79 | 20968315201 |  | 2 | CPI | 3 | 115 | 4421.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y81 | 43197915201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | -28 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2Y81 | 43197915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2Y85 | 43865025201 |  | 2 | CPI | 1 | 115 | 15314.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 115 | 23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | -10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 3 | 115 | -10260.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | 38928.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 4 | 101 | 10592.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | -23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 21907.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 6426.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 876.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | E2Z52 | 43204815201 |  | 2 | CPI | 1 | 401 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | E2Z52 | 43204815201 |  | 2 | CPI | 2 | 725 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 012 | 1958 | 1958 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 108 | 1461.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 003 | 8872.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 001 | 3538.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 112 | 5582.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 010 | 31201.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 10007.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 2816.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 019 | 5235.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 4084.57 | 4084.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 16608.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 5600 | 5600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 9630.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 33101.44 | 33101.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 101 | 1954.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 4680.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 10609.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 018 | 3210.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3600 | 3600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 5796.91 | 5796.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3789.18 | 3789.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 107 | 15084.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3502.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 2008.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 917 | 18825.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 28819.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 12538.2 | 12538.2 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 1892.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 2 | 001 | 33438.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 7472.09 | 3712.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 2 | 001 | 3054.65 | 3054.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245601 |  | 2 | CPI | 1 | 007 | 12407.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245601 |  | 2 | CPI | 1 | 015 | 21327.17 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 012 | 24155.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 16860.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 2944 | 2944 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245601 |  | 2 | CPI | 2 | 015 | 16265.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 1 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 3396.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 101 | 1441 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 3 | 012 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 1023.6 | 1023.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 012 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 003 | 5042.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 4644.49 | 4644.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 105 | 4154.63 | 4154.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 4417.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 112 | 15284.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 112 | 2380.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 6280.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 115 | 1442.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 3406.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 8833.93 | 8833.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 106 | 3468.39 | 3468.39 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 107 | 6418.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 4078.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 024 | 2176.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 024 | 1369.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 004 | 4228 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 012 | 45923.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 115 | 7538.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 004 | 2270.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 8678.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 2169.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 1712.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 968 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 8809.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 3388 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 2 | 118 | 3470 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 018 | 2500 | 2500 | 3 |  | N | 0 | Avoidable, CEI Consultant | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 004 | 5193.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 018 | 0 | 0 | 3 |  | N | 42 | Avoidable, CEI Consultant | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 5109.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 1080.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 2 | 108 | 1025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 3965.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 115 | 3809.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 3 | 001 | 1665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 4 | 004 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 101 | 6413 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2759 | 43617615201 |  | 2 | CPI | 1 | 115 | 2087.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2759 | 43617615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2760 | 44125815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2762 | 44499015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 31 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 115 | 9556.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 120 | 1567.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2778 | 44105715601 |  | 2 | CPI | 1 | 106 | 15000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 012 | 4031.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 115 | 1205.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 118 | 405.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 112 | 1658.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 2 | 012 | 2273.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 3 | 101 | 132 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 003 | 6050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 2 | 101 | 748 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2786 | 43732315201 |  | 2 | CPI | 1 | 001 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2786 | 43732315201 |  | 2 | CPI | 1 | 001 | 7392 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2799 | 43584515201 |  | 2 | CPI | 1 | 929 | 1038 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2799 | 43584515201 |  | 2 | CPI | 1 | 122 | 7491.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 2 | 503 | 837.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 128 | 5964.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 115 | 4064.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 007 | 2239.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T9022 | 44531935223 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3T25 | 44154615201 |  | 2 | CPI | 1 | 117 | 3638.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3T27 | 40571925201 |  | 2 | CPI | 1 | 107 | 2820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3T27 | 41557635201 |  | 2 | CPI | 1 | 107 | 1786 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 3414.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 5540.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 105 | 5818.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615202 |  | 2 | CPI | 2 | 001 | 4498.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 2380.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 004 | 16711.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 191.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 105 | 12338 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 101 | 158.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3692 | 43774615202 |  | 2 | CPI | 2 | 010 | 1280.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 9391.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 1387.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3723 | 43972115201 |  | 2 | CPI | 2 | 503 | 2566.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 712.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 115 | 7132.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 8460 | 3760 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3738 | 44173815201 |  | 2 | CPI | 1 | 503 | 2217.07 | 2217.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 503 | 7918.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 115 | 2763.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 012 | 3216.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3745 | 43972915201 |  | 2 | CPI | 2 | 115 | 8062.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 3 | 115 | 1506.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 4 | 107 | 368.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 5 | 503 | 1396.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 6 | 012 | 1114.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3749 | 44173215201 |  | 2 | CPI | 1 | 012 | 5200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3749 | 44173215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3751 | 43775325201 |  | 2 | CPI | 1 | 103 | 22902.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 003 | 1320.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 003 | 4144.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 17550 | 17550 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 007 | 9411.02 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0.5 | 0.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 115 | 4679.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 3 | 115 | 3233.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | 4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | -4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 503 | 4214.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 007 | 672.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 115 | 15685.46 | 3838.25 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 001 | 3787.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 105 | 6430.57 | 2734.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 1 | 001 | 851.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U72 | 44162915201 |  | 2 | CPI | 2 | 101 | 4846.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 3 | 101 | 9689.83 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 4 | 118 | 3863.48 | 3863.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 5 | 007 | 1821.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U72 | 44162915201 |  | 2 | CPI | 6 | 503 | 1766.74 | 313.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U72 | 44162915201 |  | 2 | CPI | 7 | 012 | 3257.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 023 | 6433.53 | 6433.53 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 001 | 942.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 2 | 106 | 1799.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 3 | 106 | 3235.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 4 | 001 | 1752.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 4 | 001 | 1288.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 108 | 710.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 2 | 001 | 979.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 3 | 105 | 2788.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 118 | 2210.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4471 | 43472215602 |  | 2 | CPI | 1 | 106 | 1599.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 005 | 6089.3 | 6089.3 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 |  | 2 | CPI | 5 | 001 | 12838 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 001 | 11945.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 107 | 1101.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 007 | 1494.85 | 1494.85 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 015 | 1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 015 | -1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 015 | 1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 001 | 2305.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 015 | 975.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 926 | 7919.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 2 | 928 | 834.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 118 | 8234.16 | 8234.16 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 107 | 1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1195.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1278.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1403.59 | 1403.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 502 | 1242.7 | 1242.7 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 004 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 115 | 2724.61 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 007 | 1293.76 | 1293.76 | 5 |  | C | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 926 | 2950.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 503 | 1018.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 119 | 6441.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 3 | 108 | 5481.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 503 | 423 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 128 | 5712.85 | 5712.85 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 106 | 3052.67 | 3052.67 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 123 | 12016.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 115 | 1226.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 001 | 33966.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 105 | 870.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 115 | 3357.15 | 3357.15 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 926 | 1714.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 108 | 402.72 | 402.72 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 503 | -932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 935.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 003 | 3451.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4504 | 43783815201 |  | 2 | CPI | 2 | 108 | 1575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 115 | 2970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 6941.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 38809.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 024 | 8679.73 | 8679.73 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 17185.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 14389.34 | 5447.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 5447.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 112 | 2581.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 1609.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 001 | 2010.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 2 | 118 | 1184 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 118 | 2235.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 123 | 7672.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 118 | 1045 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 1 | 105 | 1220.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 2 | 105 | 5359.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 3 | 105 | 5363.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 4 | 105 | 4850.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 926 | 6050.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 1943.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 2094 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 22246.63 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 50538.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 101 | 1045.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | -8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 2 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4530 | 43592515201 |  | 2 | CPI | 1 | 001 | 10020.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4530 | 43592515201 |  | 2 | CPI | 2 | 001 | 716.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4530 | 43592515201 |  | 2 | CPI | 1 | 019 | 9471.3 | 9471.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4538 | 44138115201 |  | 2 | CPI | 1 | 122 | 495 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4538 | 44138115201 |  | 2 | CPI | 1 | 503 | 10798.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4538 | 44138115201 |  | 2 | CPI | 2 | 123 | 1561.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 001 | 475.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 2 | 001 | 1000.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 106 | 1429.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E52A1 | 44208715201 |  | 2 | CPI | 1 | 001 | 7876.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E52A1 | 44208715201 |  | 2 | CPI | 1 | 118 | 1327.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E52A1 | 44208715201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | E52A2 | 44113815201 |  | 2 | CPI | 1 | 503 | 22100.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E53A6 | 44119715201 |  | 2 | CPI | 1 | 001 | 10409.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E53A6 | 44119715201 |  | 2 | CPI | 2 | 003 | 1837.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 4372.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E54A0 | 44208815201 |  | 2 | CPI | 1 | 106 | 1691.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E54A0 | 44208815201 |  | 2 | CPI | 2 | 003 | 361.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E54A0 | 44208815201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | E54A2 | 44589615201 |  | 2 | CPI | 1 | 503 | 2169.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E57A9 | 43988085201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | E5Z71 | 43179835601 |  | 2 | CPI | 1 | 015 | 45231.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 103 | 110463.47 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 105 | 11459.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 115 | 16531.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 115 | 11545.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 2 |  | N | 20 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 106 | 0 | 13796.45 | 0 |  | N | 70 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 101 | 4675 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 108 | 15035.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 107 | 10794.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 3 | 012 | 14140.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 001 | 15055.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 115 | 2708.69 | 2708.69 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 105 | 7921.71 | 7921.71 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 106 | 5214.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 29 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 8048.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 13022.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 9696.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | -9696.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 2 | 012 | 9693.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z96 | 44116615201 |  | 2 | CPI | 1 | 010 | 48527.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 3806.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 118 | 3195.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 106 | 1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 1085.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | -2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 106 | -1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 001 | 2481.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 106 | 2004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 107 | 25090.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 10416 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 115 | 4418.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 2133.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 5 | 118 | 3406.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 3498.06 | 3498.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | 2486.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 5868.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 115 | 35290.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 105 | 3306.22 | 3306.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 1977.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 1659.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 115 | 1209.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 003 | 8370.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 1 | 128 | 21312.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 2 | 007 | 1805.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5582 | 23827585201 |  | 2 | CPI | 3 | 007 | 2786.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 012 | 13114.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 001 | 13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 003 | 1175 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 023 | -30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 8001.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 023 | 30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 9874 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 004 | 55000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 001 | -13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 010 | 12460.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5628 | 43734115601 |  | 2 | CPI | 1 | 001 | 13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 003 | 16192.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 3273.6 | 3273.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 373.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 341.18 | 341.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 101 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 101 | 21230 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 003 | 33261.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 003 | 22097.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 101 | 9358.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 |  | 2 | CPI | 2 | 003 | 15052.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 023 | 3409.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 003 | 22942.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 007 | 371.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 2 | 122 | 1570.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 122 | 627.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 115 | 13257.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5668 | 43968245602 |  | 2 | CPI | 1 | 106 | 3658.89 | 3491.95 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968245602 |  | 2 | CPI | 1 | 106 | -54.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5669 | 43754415201 |  | 2 | CPI | 1 | 001 | 34432.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 1 | 012 | 30199.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5670 | 43020245201 |  | 2 | CPI | 1 | 003 | 441.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5670 | 43020245201 |  | 2 | CPI | 2 | 105 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 |  | 2 | CPI | 1 | 003 | 4538.3 | 4538.3 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 105 | 997.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 3457.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 6173.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 21764.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 4 | 112 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 105 | 1811.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 012 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 2 | 022 | 2312.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 3 | 001 | 15618.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 023 | 126.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5701 | 44136515201 |  | 2 | CPI | 1 | 115 | 3638.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 503 | 59068.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 012 | 5599.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 3 | 503 | 19834.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 012 | 5599.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 107 | 9130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 024 | 1689.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 012 | 24758.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 012 | 2630.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 024 | 682.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 503 | 14135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 17305.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 023 | 12874.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 3325.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 021 | 12038.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6982.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 2292.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 4161.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 023 | 3820.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 503 | 13063.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 |  | 2 | CPI | 3 | 023 | 4219.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 |  | 2 | CPI | 4 | 023 | 6174.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 |  | 2 | CPI | 5 | 023 | 2705.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 |  | 2 | CPI | 6 | 012 | 7465.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 1339.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 1180.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6131.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 8290.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 9725.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 021 | 26375.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 29900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 739.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 1799.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 13098.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 122 | 3916.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | E6L94 | 43653915201 |  | 2 | CPI | 1 | 001 | 37896 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | E6L94 | 43653915201 |  | 2 | CPI | 1 | 012 | 1787.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6M37 | 44060415201 |  | 2 | CPI | 1 | 503 | 4180 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M37 | 44060415201 |  | 2 | CPI | 2 | 503 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M37 | 44060415201 |  | 2 | CPI | 3 | 115 | 1163.65 | 1163.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6M37 | 44060415201 |  | 2 | CPI | 1 | 101 | 2667.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6M47 | 44196115201 |  | 2 | CPI | 1 | 503 | 14242.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M47 | 44196115201 |  | 2 | CPI | 2 | 503 | 2369.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6N05 | 44188615201 |  | 2 | CPI | 1 | 007 | 646 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6N05 | 44188615201 |  | 2 | CPI | 2 | 019 | 3576.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6N05 | 44188615201 |  | 2 | CPI | 3 | 503 | 1906.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6N05 | 44188615201 |  | 2 | CPI | 1 | 503 | 2484.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6N05 | 44188615201 |  | 2 | CPI | 2 | 503 | 17279.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 123 | 11428.39 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 123 | 11790.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 001 | 3497.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 503 | 3837.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 101 | 13838 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 101 | 14586 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 115 | 23432.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 101 | 18084.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 105 | 15535.31 | 15535.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 108 | 5682.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 001 | 3956.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 108 | 1496.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 012 | 10378.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1823.55 | 1823.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1458.84 | 1458.84 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 729.42 | 729.42 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 001 | 4807.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 2 | 007 | 20570 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 101 | 25942.65 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 3 | 103 | -25942.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 4 | 101 | 24622.65 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045601 |  | 2 | CPI | 1 | 503 | 1224 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 101 | 4114.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 118 | 1399.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 023 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 118 | 1399.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 022 | 9277.38 | 9277.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 2 | 115 | 2240.54 | 2240.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 001 | 1650.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 2 | 001 | 1578.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 3 | 001 | 2352.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 108 | 244.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 5266.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 005 | 6677.94 | 6677.94 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 685.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 001 | 1325.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 007 | 4544.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 2 | 001 | 357.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | -5266.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 2 | 001 | -685.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 3 | 001 | 3466.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 685.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 2 | 001 | 1800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6478 | 44030415201 |  | 2 | CPI | 1 | 503 | 5010.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6478 | 44030415201 |  | 2 | CPI | 2 | 101 | 794.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 3645.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 4970.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017825201 |  | 2 | CPI | 1 | 503 | 756.11 | 756.11 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 10767.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 1040.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 1379.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 7980.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 2 | 503 | 995.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017015201 |  | 2 | CPI | 1 | 001 | 1093.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 937.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 1300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017015201 |  | 2 | CPI | 1 | 503 | 421.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 3172.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 2 | 503 | 6154.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44396215201 |  | 2 | CPI | 1 | 503 | 2326.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44356415201 |  | 2 | CPI | 1 | 503 | 1128.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44396015201 |  | 2 | CPI | 1 | 503 | 1464.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | -9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | -3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 2122.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 007 | 3015.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6502 | 44385315201 |  | 2 | CPI | 1 | 101 | 2518 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6502 | 44385315201 |  | 2 | CPI | 1 | 001 | 2889.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 107 | 2388.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 023 | 3796.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 003 | 7665.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 105 | 4396.45 | 4396.45 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6526 | 44167215201 |  | 2 | CPI | 1 | 004 | 1419.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M61 | 43951615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M61 | 43951615201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 2 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 3 | 101 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 2 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 61 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 107 | 25412.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 001 | 275.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 503 | 1879.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | E7M93 | 44383215201 |  | 2 | CPI | 1 | 112 | 5962.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7M93 | 44383215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 1040.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 12000 | 12000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1163.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 004 | 3990.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M96 | 43762615201 |  | 2 | CPI | 2 | 101 | 749.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1034 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 2027.92 | 2027.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7N02 | 44383315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 101 | 3022.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | 1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 105 | 15926.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | 1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | -1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 9 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N26 | 43946015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N26 | 43946015201 |  | 2 | CPI | 2 | 502 | 7811.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7N26 | 43946015201 |  | 2 | CPI | 1 | 502 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7N46 | 43955415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N48 | 44025215201 |  | 2 | CPI | 1 | 112 | 7325.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 012 | 17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 503 | 23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 023 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 5 | 023 | 7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 012 | -17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | -4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | -3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 503 | -23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | 4117.15 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | -1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | -4117.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | 4117.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 5080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | 7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 012 | 17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 503 | 38335.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 923 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 34053.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 9583.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | -4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | -3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | -7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 4000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 2 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 1800 | 1800 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 115 | 2708.52 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 6578.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 2838.79 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 115 | 1794.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 4 | 107 | 5814.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 48842.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 5244.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 877.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 8720.37 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 11473.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325601 |  | 2 | CPI | 1 | 015 | 3027.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 108 | 5480.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 105 | 4182.62 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 45443.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 009 | 2334.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115601 |  | 2 | CPI | 1 | 021 | 6155.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115601 |  | 2 | CPI | 1 | 021 | 12007.43 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 009 | 10412.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 3 | 001 | 13333.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 117 | 16202.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 001 | 6208.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 117 | 13508.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515601 |  | 2 | CPI | 1 | 001 | 48529.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7410 | 43649515601 |  | 2 | CPI | 1 | 126 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 2 | 112 | 49057.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 118 | 8412.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7410 | 43649515204 |  | 2 | CPI | 1 | 118 | 19861.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7437 | 43605615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7437 | 43605615201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7437 | 43605615201 |  | 2 | CPI | 3 | 007 | 2529.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7447 | 43764115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7447 | 43764115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7455 | 44140315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7466 | 43764615201 |  | 2 | CPI | 1 | 101 | 5569.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 1090.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 8138.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 021 | 905.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 3 | 003 | 10849.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 748.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 503 | -8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 8266.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 1189.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 004 | 27296.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 926 | 9582.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 3 | 503 | 2400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 10641.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 981.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 503 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 503 | 8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 3666.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 2835.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 6219.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 3644.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 004 | 13254.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 1031.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 437.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 420.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 503 | 8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 2659.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 6695.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 11425.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 001 | 5808 | 5808 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 001 | 3246.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 11394 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 6 | 012 | 4725.71 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 6396.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 503 | 8291.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 503 | 2751.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 108 | 5153.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 004 | 8142.4 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 021 | 9478.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 007 | 10356.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 503 | 6947.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 012 | 7429.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 5 | 012 | 4691.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 4 | 012 | 19749.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 7 | 012 | 4879.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140645201 |  | 2 | CPI | 1 | 012 | 3933.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 012 | 468.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140645201 |  | 2 | CPI | 1 | 115 | 3116.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 012 | 11615.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 860 | 0 | 0 | 5 |  | N | 2 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 012 | 85783.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 001 | 20357.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 012 | 21974.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652035201 |  | 2 | CPI | 1 | 001 | 175 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q95 | 43652035201 |  | 2 | CPI | 2 | 105 | 7100.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 010 | 2761.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 107 | 1639.41 | 1639.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 021 | 19257.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 115 | 8068.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 3 | 118 | 4136 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 2648.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 4233.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 503 | 4542.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 107 | 1163.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 4509.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 924 | 14026.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 105 | 10563.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 024 | 7781.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 131 | 3314.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 40430.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 926 | 5753.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 17935.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 869.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 974.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 2 | 115 | 6771.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 5625.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 11747.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 926 | 689.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 107 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 3749.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 3279.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 13694.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 2 | 107 | 3575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 3 | 107 | 344.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 123 | 30606.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 115 | 16242.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 010 | 10485.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8S11 | 44029115201 |  | 2 | CPI | 2 | 003 | 5432.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8S11 | 44029125201 |  | 2 | CPI | 1 | 105 | 20817.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 021 | 5799.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 503 | 15605.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 503 | 12507.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 2 | 503 | 8114.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 3 | 023 | 29158.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 1 | 503 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 2 | 503 | 14262.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 3 | 503 | 2852.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 4 | 503 | 4237.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 5 | 503 | 22848.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S63 | 44514015201 |  | 2 | CPI | 1 | 101 | 2859.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 1879.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 019 |  | 51 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | [9 empty] | Avoidable, In-House CEI
01 | T1700 | 43088615201 | 503 |  | 25 | 015 | 1 | 3 | N | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 924 |  | 36 | 051 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 924 |  | 27 | 029 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1755 | 43659715201 | 005 |  | 45 | 007 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1755 | 43659715201 | 118 |  | 1 | 007 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1764 | 44013015201 | 924 |  | 20 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1786 | 41450665201 | 924 |  | 7 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1786 | 41450665201 | 924 |  | 14 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2W84 | 43384215201 | 108 |  | 93 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Y79 | 20968315201 | 106 |  | 11 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y85 | 43865025201 | 924 |  | 16 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y85 | 43865025201 | 924 |  | 16 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Z36 | 43930315201 | 012 |  | 21 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 015 |  | 4 | 077 | 1 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 924 |  | 34 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2743 | 42845515201 | 924 |  | 21 | 039 | 1 | 1 | N | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2781 | 44106015201 | 405 |  | 14 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 009 |  | 7 | 012 | 1 | 1 | C | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 87 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 13 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 924 |  | 65 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 013 |  | 62 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 016 |  | 72 | 041 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3S42 | 42187345201 | 924 |  | 128 | 003 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3T25 | 44154615201 | 503 |  | 3 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T35 | 44291315201 | 010 |  | 6 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3T58 | 43815415201 | 009 |  | 30 | 004 | 1 | 2 | N | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3T58 | 43815415201 | 009 |  | 94 | 016 | 1 | 2 | N | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3T96 | 4453581G201 | 130 |  | 5 | 008 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
03 | T3699 | 43228415201 | 018 |  | 15 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
03 | T3699 | 43228415201 | 106 |  | 21 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3729 | 43972715201 | 023 |  | 2 | 021 | 1 | 5 | N | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3729 | 43972715201 | 012 |  | 2 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3738 | 44173815201 | 106 |  | 2 | 006 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3738 | 44173815201 | 106 |  | 5 | 007 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3738 | 44173815201 | 106 |  | 7 | 010 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3744 | 43972415201 | 924 |  | 50 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3745 | 43972915201 | 005 |  | 19 | 031 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 005 |  | 18 | 053 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 118 |  | 6 | 059 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4488 | 43630415201 | 924 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4505 | 43668515201 | 924 |  | 22 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4521 | 43760515201 | 105 |  | 25 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 | 106 |  | 5 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K73 | 43653715201 | 503 |  | 6 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 019 |  | 37 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 924 |  | 16 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 503 |  | 25 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 | 001 |  | 8 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6483 | 44016915201 | 503 |  | 45 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 | 503 |  | 25 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M81 | 44335315201 | 112 |  | 133 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7M96 | 43762615201 | 007 |  | 21 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 118 |  | 27 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q95 | 43652015201 | 503 |  | 10 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R51 | 44132215201 | 924 |  | 80 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | -8147 | 134 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 13 | 01co | 1 | 13
01CO | 01 | T1717 | 19801765201 | 2018-12-05 | QTR2 | 18/19 | 4 | 17 | 700 | 913 | 925 | -12 | 12 | 0 | 152 | 61 | 15860000 | 150000 | 15710000 | 16463364 | 16135347 | -90816 | -60000 | -150816 | 15984531 | 15920739 | -48363 | 603364 | 111 | 0 | 0 | 586377 | 3552 | 0 | 4 | 22688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 619221 | 3552 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2022-03-29 | QTR3 | 21/22 | 2021-10-08 | QTR2 | 21/22 | 115 | 15674640.54 | B10 | ACC - BONUS/INCENT/DISINCENT | 4 | 41 | 0 | 0 | 101513 | 0 |  | CO | 13 | 01do | 14 | 26
01CO | 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 0 | 8128 | 11 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 23 | 02co | 27 | 49
01CO | 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | -35379 | -23800 | 78 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59 |  |  | 1 | 28 | 0 | 0 | -38003 | 0 |  | CO | 16 | 02do | 50 | 65
01CO | 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | -17395 | 44 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 18 | 03co | 66 | 83
01CO | 01 | T1757 | 43943615201 | 2020-07-29 | QTR1 | 20/21 | 3 | 4 | 200 | 261 | 260 | 1 | 0 | 0 | 34 | 27 | 2163088 | 50000 | 2113088 | 2182239 | 2172501 | 0 | 0 | 0 | 2172501 | 2181502 | 9002 | 19151 | 25 | 0 | 0 | 11573 | 0 | 0 | 27 | 103123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 43328 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 108 | 2199110.64 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 11 | 03do | 84 | 94
01CO | 01 | T1760 | 43943915201 | 2020-06-10 | QTR4 | 19/20 | 2 | 1 | 235 | 291 | 288 | 3 | 0 | 0 | 56 | 0 | 4964468 | 57276 | 4907192 | 4976639 | 5027641 | 0 | 0 | 0 | 5027641 | 5062613 | 34972 | 12171 | 47 | 0 | 0 | 13541 | 0 | 0 | 0 | 12171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30994 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 | 2021-10-18 | QTR2 | 21/22 | 108 | 5089189.35 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 17 | 04co | 95 | 111
01CO | 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 5 | 04do | 112 | 116
01CO | 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 292 | 9 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 114901 | 43 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 13 | 05co | 117 | 129
01CO | 01 | T1775 | 44151915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 275 | 371 | 370 | 1 | 0 | 0 | 96 | 0 | 7746370 | 98021 | 7648349 | 7776109 | 7775281 | 0 | 0 | 0 | 7775281 | 7823279 | 47998 | 29739 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 | 2021-11-13 | QTR2 | 21/22 | 118 | 9281425.28 |  |  | 0 | 23 | 0 | 0 | 0 | 0 | T | CO | 15 | 05do | 130 | 144
01CO | 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 13 | 06co | 145 | 157
01CO | 01 | T1789 | 43693115201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 271 | 270 | 1 | 0 | 0 | 71 | 0 | 2359731 | 50000 | 2309731 | 2322360 | 2220739 | 0 | 0 | 0 | 2220739 | 2223174 | 2435 | -37371 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36473 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-01-25 | QTR3 | 21/22 | 2021-08-26 | QTR1 | 21/22 | 113 | 2549900.36 |  |  | 0 | 16 | 0 | 0 | -37371 | 0 |  | CO | 9 | 06do | 158 | 166
01CO | 01 | T1796 | 44050815201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 100 | 124 | 123 | 1 | 0 | 0 | 24 | 0 | 817957 | 38521 | 779436 | 986429 | 914986 | 0 | 0 | 0 | 914986 | 914986 | 0 | 168472 | 19 | 0 | 0 | 81012 | 0 | 0 | 0 | 87460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168472 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-07 | QTR3 | 21/22 | 2021-10-01 | QTR2 | 21/22 | 118 | 656746.29 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 8 | 07co | 167 | 174
01DO | 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 357 | 69031 | 29 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO | 15 | 07do | 175 | 189
01DO | 01 | E1P95 | 42838315201 | 2017-06-15 | QTR4 | 16/17 | 4 | 13 | 825 | 1189 | 1179 | 10 | 0 | 0 | 149 | 215 | 12611204 | 102103 | 12509101 | 13133768 | 12450757 | -35183 | -125000 | -160183 | 12290574 | 12343775 | 53201 | 522564 | 71 | 0 | 26 | 98702 | 3841 | 0 | 100 | 270614 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156514 | 0 | 0 | 0 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 567739 | 13064 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-15 | QTR3 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 115 | 10409514.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 15 | 78 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 190 | 189
01DO | 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | -23194 | 2868754 | 166 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 60 | 0 | 0 | 0 | 0 |  | DO | 11 | 08do | 190 | 200
01DO | 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 0 | 234222 | 11 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 180574 | 207 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S49 | 19602275201 | 2020-03-26 | QTR3 | 19/20 | 3 | 8 | 360 | 476 | 474 | 2 | 0 | 0 | 81 | 35 | 4765372 | 50000 | 4715372 | 5108479 | 5065730 | 0 | 0 | 0 | 5065730 | 5081869 | 16140 | 343107 | 55 | 0 | 35 | 331038 | 0 | 0 | 0 | 27910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 358948 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 | 2021-11-19 | QTR2 | 21/22 | 115 | 5214661.03 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1S51 | 44002715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 1 | 80 | 152 | 191 | -39 | 39 | 0 | 45 | 27 | 407081 | 16632 | 390449 | 421138 | 368049 | -48399 | 0 | -48399 | 319650 | 319650 | 0 | 14057 | 26 | 0 | 27 | 14057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14057 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 | 2021-02-12 | QTR3 | 20/21 | 115 | 439357.58 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 98871 | 44 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T46 | 44681615201 | 2020-07-23 | QTR1 | 20/21 | 1 | 1 | 400 | 449 | 449 | 0 | 0 | 0 | 49 | 0 | 3083600 | 50000 | 3033600 | 3080211 | 3030211 | 0 | 0 | 0 | 3030211 | 3030211 | 0 | -3389 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 | 2021-12-20 | QTR2 | 21/22 | 106 | 4731071.94 | LBDB | LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T68 | 43980115201 | 2020-12-03 | QTR2 | 20/21 | 1 | 1 | 75 | 106 | 178 | -72 | 72 | 0 | 21 | 10 | 180572 | 10362 | 170210 | 210394 | 199372 | -3750 | 0 | -3750 | 195621 | 195621 | 0 | 29822 | 18 | 0 | 10 | 29822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29822 | 0 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2022-01-21 | QTR3 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 108 | 260006.67 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 593970 | 1812123 | 319 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1 |  |  | 4 | 136 | 0 | 0 | -73244 | 0 |  | CO
02CO | 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 337124 | 3379021 | 270 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71 |  |  | 91 | 196 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 1278355 | 2076018 | 139 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7 |  |  | 0 | 86 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | -48704 | 243564 | 155 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | -1358 | 52280 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2720 | 43735415201 | 2018-10-31 | QTR2 | 18/19 | 1 | 4 | 200 | 572 | 572 | 0 | 0 | 0 | 170 | 202 | 2468956 | 50000 | 2418956 | 2635619 | 2856937 | 0 | 0 | 0 | 2856937 | 2843130 | -13807 | 166663 | 95 | 0 | 42 | 7693 | 0 | 0 | 160 | 185011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 192704 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-03-29 | QTR3 | 20/21 | 214 | 2333570.34 |  |  | 202 | 75 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2743 | 42845515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 4 | 750 | 857 | 857 | 0 | 0 | 0 | 147 | -40 | 12559204 | 120 | 12559084 | 13123013 | 13368899 | 0 | 0 | 0 | 13368899 | 13241202 | -127696 | 563809 | 108 | 0 | -30 | 143449 | 0 | 0 | 0 | 27147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904784 | 590741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | 563809 | 590741 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-10-27 | QTR2 | 21/22 | 208 | 13121490.39 |  |  | 0 | 39 | 0 | -10 | -511572 | 0 |  | CO
02CO | 02 | T2752 | 43395715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 400 | 548 | 485 | 63 | 0 | 0 | 145 | 3 | 6416755 | 63600 | 6353155 | 6416755 | 6306830 | 0 | 0 | 0 | 6306830 | 6314515 | 7685 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 209 | 6469876.4 |  |  | 3 | 34 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 475406 | 27 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6136498 | -12015 | 124056 | 35 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49 |  |  | 10 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 87084 | 10 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705 |  |  | 31 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 0 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42 |  |  | 3 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 0 | -4773 | 3 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2773 | 43403815201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 350 | 408 | 389 | 19 | 0 | 0 | 58 | 0 | 3684895 | 58701 | 3626194 | 3684895 | 3598807 | 0 | 0 | 0 | 3598807 | 3601767 | 2960 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-08-05 | QTR1 | 21/22 | 214 | 3367569.01 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2778 | 44105715201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 230 | 294 | 294 | 0 | 0 | 0 | 64 | 0 | 4660748 | 65000 | 4595748 | 4665808 | 4696793 | 0 | 0 | 0 | 4696793 | 4795119 | 98326 | 5059 | 51 | 0 | 0 | 12355 | 0 | 0 | 0 | 24208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36563 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-30 | QTR3 | 21/22 | 2021-12-06 | QTR2 | 21/22 | 216 | 4464709.06 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2781 | 44106015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 377 | 377 | 0 | 0 | 0 | 127 | 0 | 5821573 | 74375 | 5747198 | 5821573 | 5952158 | 0 | 0 | 0 | 5952158 | 5882048 | -70110 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-23 | QTR3 | 21/22 | 2021-10-27 | QTR2 | 21/22 | 214 | 7534069.47 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 0 | 28 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2799 | 43584515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 200 | 213 | 163 | 50 | 0 | 0 | 13 | 0 | 584000 | 47584 | 536416 | 584000 | 571789 | 0 | 0 | 0 | 571789 | 571826 | 37 | 0 | 2 | 0 | 0 | 2239 | 0 | 0 | 0 | 17521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20598 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-03-18 | QTR3 | 21/22 | 2021-09-24 | QTR1 | 21/22 | 208 | 883653.52 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 90092 | 12 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66 |  |  | 11 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 0 | 177395 | 58 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | -1354420 | 997337 | 55 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 118 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1396122 | 103 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42 |  |  | 27 | 32 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | -75888 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32 |  |  | 0 | 15 | 0 | 0 | -75888 | 0 |  | DO
02DO | 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 50000 | 30 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21 |  |  | 5 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y81 | 43197915201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 390 | 546 | 546 | 0 | 0 | 0 | 129 | 27 | 2424817 | 50000 | 2374817 | 2497783 | 2495432 | 0 | 0 | 0 | 2495432 | 2495432 | 0 | 72966 | 82 | 0 | 50 | 69881 | 69881 | 0 | -23 | 3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 72966 | 69881 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 | 2021-09-21 | QTR1 | 21/22 | 208 | 3472664.24 |  |  | -23 | 47 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y84 | 43807515201 | 2019-11-13 | QTR2 | 19/20 | 3 | 1 | 160 | 223 | 223 | 0 | 0 | 0 | 63 | 0 | 1543447 | 50000 | 1493447 | 1543447 | 1581148 | 0 | 0 | 0 | 1581148 | 1565351 | -15797 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 | 2020-10-23 | QTR2 | 20/21 | 214 | 1817083.25 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 0 | 82407 | 16 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 49816 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING INC | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z51 | 43384115201 | 2020-04-15 | QTR4 | 19/20 | 1 | 1 | 350 | 442 | 436 | 6 | 0 | 0 | 79 | 13 | 2662544 | 50000 | 2612544 | 2666491 | 1959926 | 0 | 0 | 0 | 1959926 | 1959926 | 0 | 3947 | 33 | 0 | 0 | 29210 | 0 | 0 | 0 | 3947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33157 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 | 2021-12-08 | QTR2 | 21/22 | 208 | 3385087.42 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03 |  |  | 21 | 48 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING LLC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 28314 | 256400 | 170 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3689 | 21876425201 | 2019-12-04 | QTR2 | 19/20 | 1 | 5 | 410 | 588 | 586 | 2 | 0 | 0 | 144 | 34 | 3948246 | 50000 | 3898246 | 4424349 | 4220133 | 0 | 0 | 0 | 4220133 | 4222745 | 2611 | 476103 | 106 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 | 2021-11-20 | QTR2 | 21/22 | 321 | 3709288.8 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | -86540 | 385593 | 320 | 0 | 3 | 71605 | 0 | 0 | 4 | 120253 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429398 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93 |  |  | 6 | 100 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | -30187 | 126 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 466 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 247 | 27245 | 34 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | -146878 | 58629 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83 |  |  | 2 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 204347 | 63 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 37203 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3745 | 43972915201 | 2020-02-26 | QTR3 | 19/20 | 2 | 3 | 365 | 513 | 512 | 1 | 0 | 0 | 135 | 13 | 7352550 | 86750 | 7265800 | 7448821 | 7636800 | 0 | 0 | 0 | 7636800 | 7674029 | 37229 | 96271 | 76 | 0 | 13 | 91427 | 0 | 0 | 0 | 12701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 13 | 122618 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-16 | QTR3 | 21/22 | 2021-09-30 | QTR1 | 21/22 | 321 | 8840050.49 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 0 | 90 | 174 | 176 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 755462 | 668670 | 0 | 0 | 0 | 668670 | 668670 | 0 | 0 | 39 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5200 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-12 | QTR2 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61 |  |  | 7 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3751 | 43775325201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 335 | 445 | 445 | 0 | 0 | 0 | 110 | 0 | 2569909 | 50000 | 2519909 | 2569909 | 2490758 | 0 | 0 | 0 | 2490758 | 2498656 | 7898 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 313 | 2572447.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3763 | 43661515201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 365 | 435 | 433 | 2 | 0 | 0 | 70 | 0 | 4894168 | 0 | 4894168 | 4903128 | 5058997 | 0 | 0 | 0 | 5058997 | 5067842 | 8845 | 8960 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2022-01-18 | QTR3 | 21/22 | 2021-11-01 | QTR2 | 21/22 | 321 | 5019527.85 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 0 | 49116 | 256 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 90 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 0 | 213 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | -174645 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T18 | 42282325201 | 2020-12-17 | QTR2 | 20/21 | 1 | 0 | 45 | 46 | 32 | 14 | 0 | 0 | 1 | 0 | 145277 | 9380 | 135897 | 145277 | 129137 | 0 | 0 | 0 | 129137 | 129137 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-01-05 | QTR3 | 21/22 | 2021-04-23 | QTR4 | 20/21 | 321 | 213559.46 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 92806 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 0 | 14821 | 35 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | -225968 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-10-20 | QTR2 | 20/21 | 314 | 246220 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 582769 | 17 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U27 | 44154515201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 222 | 221 | 1 | 0 | 0 | 42 | 0 | 1641103 | 50000 | 1591103 | 1641103 | 1553101 | 0 | 0 | 0 | 1553101 | 1614039 | 60937 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2022-03-07 | QTR3 | 21/22 | 2021-11-01 | QTR2 | 21/22 | 321 | 2039669.94 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | -5522 | 345672 | 158 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32 |  |  | 7 | 48 | 0 | 0 | -46629 | 0 |  | CO
04CO | 04 | T4476 | 43515815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 4 | 582 | 825 | 825 | 0 | 0 | 0 | 183 | 60 | 7524128 | 71928 | 7452200 | 7782657 | 7606665 | 0 | 0 | 0 | 7606665 | 7546955 | -47141 | 258528 | 91 | 0 | 0 | 12809 | 0 | 0 | 0 | 107865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34366 | 34366 | 0 | 60 | 107988 | 107988 | 0 | 0 | 0 | 0 | 0 | 60 | 263028 | 142354 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 | 2021-01-18 | QTR3 | 20/21 | 409 | 7189789.75 |  |  | 0 | 92 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | -79 | 50449 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 238143 | 56 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | -38478 | 1701896 | 99 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 836144 | 110 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | -58724 | -97855 | 61 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17 |  |  | 6 | 33 | 0 | 0 | -99541 | 0 |  | CO
04CO | 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | -17714 | 162310 | 92 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | -58454 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4521 | 43760515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 160 | 246 | 244 | 2 | 0 | 0 | 86 | 0 | 737736 | 38647 | 699089 | 737736 | 679527 | 0 | 0 | 0 | 679527 | 679527 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 | 2021-12-22 | QTR2 | 21/22 | 412 | 798445.57 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 74017 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95 |  |  | 10 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 39603 | 54 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 250 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 237 | 0 | 25 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 93 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4555 | 43990915201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 128 | 152 | 148 | 4 | 0 | 0 | 24 | 0 | 441982 | 24322 | 417660 | 441982 | 407189 | 0 | 0 | 0 | 407189 | 407189 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-10-06 | QTR2 | 21/22 | 412 | 501234.56 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T83 | 42268145201 | 2020-05-01 | QTR4 | 19/20 | 1 | 0 | 240 | 375 | 375 | 0 | 0 | 0 | 116 | 19 | 2027817 | 50000 | 1977817 | 2027817 | 1963518 | 0 | 0 | 0 | 1963518 | 1968273 | 4756 | 0 | 91 | 0 | 0 | 14875 | 0 | 0 | 19 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 40339 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2022-01-27 | QTR3 | 21/22 | 2021-09-01 | QTR1 | 21/22 | 408 | 2656948.48 |  |  | 19 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | -399 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 15486 | 15 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U72 | 44162915201 | 2021-01-08 | QTR3 | 20/21 | 1 | 0 | 144 | 178 | 178 | 0 | 0 | 0 | 34 | 0 | 893625 | 50000 | 843625 | 893625 | 846410 | 0 | 0 | 0 | 846410 | 849948 | 3538 | 0 | 25 | 0 | 0 | 5931 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26097 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 | 2021-09-19 | QTR1 | 21/22 | 412 | 1052584.82 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U74 | 44162815201 | 2021-03-05 | QTR3 | 20/21 | 3 | 1 | 153 | 186 | 183 | 3 | 0 | 0 | 33 | 0 | 1190833 | 50000 | 1140833 | 1189722 | 1098149 | 0 | 0 | 0 | 1098149 | 1101304 | 3155 | -1111 | 12 | 0 | 0 | -1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1111 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-25 | QTR3 | 21/22 | 2022-01-17 | QTR3 | 21/22 | 412 | 1310702.75 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 430838 | 374749 | 219 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3 |  |  | 30 | 102 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 328547 | 8369 | 210 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | -222563 | -4 | 112 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | -16169 | 3253176 | 23 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320 |  |  | 20 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5668 | 43968235201 | 2019-05-22 | QTR4 | 18/19 | 4 | 11 | 510 | 788 | 778 | 10 | 0 | 0 | 123 | 155 | 20003719 | 154151 | 19849568 | 23051817 | 24148539 | 0 | 0 | 0 | 24148539 | 24037958 | -110580 | 3048098 | 58 | 0 | 155 | 2206932 | 2589 | 0 | 0 | 818285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91658 | 0 | 0 | 0 | 52092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 3168966 | 2589 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-04 | QTR3 | 21/22 | 2021-10-21 | QTR2 | 21/22 | 507 | 16312265.29 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 72336 | 18 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5670 | 43020245201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 260 | 396 | 395 | 1 | 0 | 0 | 116 | 20 | 2204501 | 50000 | 2154501 | 2284647 | 2359499 | 0 | 0 | 0 | 2359499 | 2362734 | 13475 | 80146 | 76 | 0 | 0 | 4980 | 0 | 5 | 20 | 70131 | 7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 77386 | 7656 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-01-12 | QTR3 | 21/22 | 2020-08-11 | QTR1 | 20/21 | 514 | 1667431.38 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 22908 | 74 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 85887 | 113 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87 |  |  | 23 | 94 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 3360 | 113 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5710 | 44136615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 86 | 128 | 128 | 0 | 0 | 0 | 42 | 0 | 614736 | 29870 | 584866 | 614736 | 554534 | 0 | 0 | 0 | 554534 | 554534 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 | 2021-11-09 | QTR2 | 21/22 | 512 | 624301.96 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 30409 | 84 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 0 | 0 | 13 | 0 | 0 | 7876 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A2 | 44316815201 | 2020-10-06 | QTR2 | 20/21 | 2 | 1 | 220 | 274 | 276 | -2 | 2 | 0 | 54 | 0 | 7726425 | 101900 | 7624525 | 7711640 | 7780592 | 0 | 0 | 0 | 7780592 | 7870977 | 90385 | -14785 | 29 | 0 | 0 | -17404 | 0 | 0 | 0 | 2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7315 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2021-10-06 | QTR2 | 21/22 | 513 | 10078671.13 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 507 | 309304 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A6 | 44119715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 0 | 70 | 109 | 109 | 0 | 0 | 0 | 39 | 0 | 320193 | 13925 | 306268 | 320193 | 308143 | 0 | 0 | 0 | 308143 | 308143 | 0 | 0 | 24 | 0 | 0 | 12247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12247 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-12-02 | QTR2 | 21/22 | 507 | 289415.18 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 0 | 0 | 7 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03 |  |  | 12 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A0 | 44208815201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 190 | 190 | 0 | 0 | 0 | 109 | 11 | 524491 | 26260 | 498231 | 524491 | 485346 | 0 | 0 | 0 | 485346 | 485346 | 0 | 0 | 85 | 0 | 0 | 362 | 0 | 0 | 0 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2022-01-06 | QTR3 | 21/22 | 507 | 529396.72 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A2 | 44589615201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 140 | 158 | 144 | 14 | 0 | 0 | 18 | 0 | 553370 | 29890 | 523480 | 553370 | 525670 | 0 | 0 | 0 | 525670 | 525670 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-01-10 | QTR3 | 21/22 | 2021-10-07 | QTR2 | 21/22 | 514 | 622693 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z71 | 43179835201 | 2019-05-07 | QTR4 | 18/19 | 2 | 7 | 570 | 816 | 816 | 0 | 0 | 0 | 140 | 106 | 16210000 | 247420 | 15962580 | 17216871 | 17023277 | 0 | 0 | 0 | 17023277 | 16917166 | -106111 | 1006871 | 91 | 0 | 0 | 767888 | 17768 | 0 | 90 | 237203 | 30782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168783 | 0 | 0 | 16 | 14196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1188071 | 48550 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-12-16 | QTR2 | 21/22 | 512 | 17297949.45 |  |  | 106 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 70000 | 38 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19 |  |  | 29 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | -5035 | 2982 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55 |  |  | 0 | 138 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 42878 | 52 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6460 | 43081745201 | 2020-04-29 | QTR4 | 19/20 | 5 | 2 | 380 | 473 | 417 | 56 | 0 | 0 | 93 | 0 | 9621172 | 109381 | 9511791 | 9721667 | 9784724 | 0 | 580000 | 580000 | 10364724 | 9769960 | -594765 | 100495 | 78 | 0 | 0 | 19509 | 0 | 0 | 0 | 137279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160626 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-02 | QTR3 | 21/22 | 2021-08-26 | QTR1 | 21/22 | 613 | 9993234.21 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 68789 | 27 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6469 | 42930045201 | 2019-09-25 | QTR1 | 19/20 | 2 | 4 | 350 | 410 | 330 | 80 | 0 | 0 | 60 | 0 | 5172452 | 51320 | 5121132 | 5372452 | 5225454 | 0 | 220000 | 220000 | 5445454 | 5222651 | -222802 | 200000 | 43 | 0 | 0 | 38506 | 0 | 0 | 0 | 32542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134496 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212915 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-06 | QTR3 | 21/22 | 2021-05-21 | QTR4 | 20/21 | 613 | 4540257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 38150 | 11 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 39 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | -2 | 32516 | 132 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6483 | 44016915201 | 2019-09-25 | QTR1 | 19/20 | 3 | 4 | 260 | 436 | 436 | 0 | 0 | 0 | 176 | 0 | 1399991 | 50000 | 1349991 | 1461545 | 1445555 | 0 | 0 | 0 | 1445555 | 1445977 | 421 | 61554 | 99 | 0 | 0 | 1094 | 0 | 0 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 27009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 65528 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-12-17 | QTR2 | 21/22 | 613 | 1299243.3 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | -50049 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2 |  |  | 0 | 25 | 0 | 0 | -121049 | 0 |  | CO
06CO | 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 0 | 36 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6502 | 44385315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 184 | 155 | 29 | 0 | 0 | 34 | 0 | 619555 | 32981 | 586574 | 619555 | 571295 | 0 | 0 | 0 | 571295 | 572454 | 1159 | 0 | 31 | 0 | 0 | 2890 | 0 | 0 | 0 | 2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5408 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-02-14 | QTR3 | 21/22 | 2021-12-13 | QTR2 | 21/22 | 613 | 681973.35 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6507 | 43991815201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 239 | 269 | 229 | 40 | 0 | 0 | 30 | 0 | 1536743 | 50000 | 1486743 | 1536743 | 1501598 | 0 | 100000 | 100000 | 1601598 | 1507472 | -94126 | 0 | 17 | 0 | 0 | 7665 | 0 | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18247 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-01-13 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 636 | 1644818.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 1 | 0 | 19 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 636 | 359443 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 530 | 1114997 | 29 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05 |  |  | 0 | 34 | 0 | 0 | -57170 | 0 |  | DO
06DO | 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 110603 | 110 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | -991000 | 1610952 | 139 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 172 | 0 | 0 | -501344 | 0 |  | DO
06DO | 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 105786 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 0 | 51 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | -3198332 | 6 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 168 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 | 2021-09-07 | QTR1 | 21/22 | 613 | 615217 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 0 | 33224 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N05 | 44188615201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 180 | 351 | 292 | 59 | 0 | 0 | 171 | 0 | 660660 | 31668 | 628992 | 660660 | 634309 | 0 | 0 | 0 | 634309 | 634835 | 526 | 0 | 158 | 0 | 0 | 4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25892 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-01-28 | QTR3 | 21/22 | 2021-12-10 | QTR2 | 21/22 | 613 | 655036.75 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 248412 | 1919528 | 100 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7386 | 43002115201 | 2016-06-15 | QTR4 | 15/16 | 3 | 7 | 310 | 812 | 1136 | -324 | 324 | 0 | 175 | 327 | 6015645 | 88863 | 5926782 | 7425942 | 7629019 | 0 | 0 | 0 | 7629019 | 7799558 | 197466 | 1410297 | 132 | 0 | 318 | 1457786 | 195935 | 0 | 6 | 154100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1323906 | 195935 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2020-01-21 | QTR3 | 19/20 | 798 | 6465450.53 | B5 | ACC - INCENTIVE/DISINCENTIVE | 3 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7410 | 43649515201 | 2018-05-23 | QTR4 | 17/18 | 5 | 5 | 565 | 971 | 970 | 1 | 0 | 0 | 296 | 110 | 10099029 | 287408 | 9811621 | 12396490 | 12392490 | 0 | 0 | 0 | 12392490 | 12349457 | -43033 | 2297460 | 224 | 0 | 40 | 1272584 | 0 | 0 | 70 | 1132140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2418085 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-06-29 | QTR4 | 20/21 | 796 | 9905226.59 |  |  | 0 | 72 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7437 | 43605615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 2 | 268 | 298 | 285 | 13 | 0 | 0 | 30 | 0 | 1903823 | 50000 | 1853823 | 2069815 | 2004923 | 0 | 0 | 0 | 2004923 | 2005258 | 335 | 165992 | 13 | 0 | 0 | 299339 | 0 | 0 | 0 | -122480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168522 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 799 | 1500000 |  |  | 0 | 17 | 0 | 0 | -8337 | 0 |  | CO
07CO | 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | -7946 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7450 | 43764015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 300 | 356 | 352 | 4 | 0 | 0 | 56 | 0 | 3698894 | 50000 | 3648894 | 3698894 | 3783529 | 0 | 0 | 0 | 3783529 | 3798642 | 15112 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-11 | QTR3 | 21/22 | 2021-10-15 | QTR2 | 21/22 | 796 | 2945400 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7455 | 44140315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 0 | 225 | 256 | 246 | 10 | 0 | 0 | 31 | 0 | 9710187 | 140000 | 9570187 | 9710187 | 10168330 | 0 | 0 | 0 | 10168330 | 10201078 | 32748 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 796 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7M61 | 43951615201 | 2019-07-10 | QTR1 | 19/20 | 2 | 0 | 430 | 707 | 698 | 9 | 0 | 0 | 277 | 0 | 3417860 | 50000 | 3367860 | 3417860 | 3733589 | 0 | 0 | 0 | 3733589 | 3733589 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-12-03 | QTR2 | 21/22 | 799 | 4777765.05 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M81 | 44335315201 | 2019-10-09 | QTR2 | 19/20 | 1 | 1 | 143 | 516 | 516 | 0 | 0 | 0 | 180 | 193 | 385385 | 7500 | 377885 | 398672 | 364686 | 0 | 0 | 0 | 364686 | 364686 | 0 | 13287 | 64 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-02-21 | QTR3 | 21/22 | 2021-11-17 | QTR2 | 21/22 | 799 | 300000 |  |  | 107 | 44 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 0 | 23 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27 |  |  | 3 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M93 | 44383215201 | 2020-02-12 | QTR3 | 19/20 | 1 | 2 | 550 | 601 | 524 | 77 | 0 | 0 | 51 | 0 | 1260367 | 20000 | 1240367 | 1319899 | 1294928 | 0 | 0 | 0 | 1294928 | 1294928 | 0 | 59531 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5962 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 | 2022-01-11 | QTR3 | 21/22 | 796 | 1500000 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 31514 | 24 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 0 | 49500 | 4 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N15 | 44539915201 | 2020-02-12 | QTR3 | 19/20 | 1 | 4 | 120 | 160 | 160 | 0 | 0 | 0 | 19 | 21 | 3408000 | 20000 | 3388000 | 3546613 | 3532479 | 0 | 0 | 0 | 3532479 | 3532479 | 0 | 138613 | 11 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-06-23 | QTR4 | 20/21 | 799 | 2952724 | B0 | ACC - LUMP SUM | 9 | 8 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 470 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-08-15 | QTR1 | 21/22 | 796 | 685000 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 796 | 485498 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 796 | 127700 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R13 | 44111115201 | 2019-01-10 | QTR3 | 18/19 | 1 | 10 | 520 | 614 | 614 | 0 | 0 | 0 | 94 | 0 | 30854000 | 150000 | 30704000 | 31355440 | 31288898 | -20000 | 1275000 | 1255000 | 32543898 | 31200893 | -1343005 | 501440 | 69 | 0 | 0 | 17636 | 0 | 0 | 0 | 225879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289031 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412383 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2022-03-16 | QTR3 | 21/22 | 2020-11-09 | QTR2 | 20/21 | 714 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 25 | 0 | 0 | -167178 | 0 |  | DO
07DO | 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 386330 | 30 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 16 | 49 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 43458 | 9 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR | 14 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | -1443556 | 402730 | 70 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 122 | 0 | 0 | -172782 | 0 |  | DO
08DO | 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 2298953 | 4629463 | 130 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS | 2 | 104 | 0 | -6 | -433401 | 0 |  | DO
08DO | 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 128744 | 80 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | -25916 | -284543 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4 |  |  | 10 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | -1807 | 442902 | 15 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51 |  |  | 10 | 45 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 20210 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S11 | 44029115201 | 2020-04-14 | QTR4 | 19/20 | 3 | 3 | 286 | 425 | 425 | 0 | 0 | 0 | 139 | 0 | 12956998 | 147809 | 12809189 | 13107980 | 13212168 | -6500 | 0 | -6500 | 13205668 | 13166473 | -39196 | 150982 | 73 | 0 | 0 | 10213 | 0 | 0 | 0 | 213463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234161 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-02-17 | QTR3 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 854 | 14597378.87 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 18865 | 18 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 0 | 1980 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08 |  |  | 2 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0