## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 86275005 | 85074467 | 87782506 | 87150754 | -60000 | 87085847 | 2.364% | 95.24% | 1720848 | 2.023% | 1507501 | 1.747% | 4542 | 1106 | 24.35% | 849 | 18.69% | 71 | 1.563% | 95 | 2.092% | 4708 | 3.655% | 6720 | 6759 | 4804 | 5.768% | 100%
| District Let | 79691125 | 78937369 | 84093724 | 82542742 | -125000 | 82214324 | 4.151% | 93.33% | 4421428 | 5.601% | 4402598 | 5.525% | 4066 | 714 | 17.56% | 355 | 8.731% | 51 | 1.254% | 354 | 8.706% | 4471 | 9.961% | 5666 | 5731 | 4662 | 14.66% | 66.67%
| All Contracts | 165966130 | 164011836 | 171876230 | 169693496 | -185000 | 169300171 | 3.224% | 94.44% | 6142276 | 3.745% | 5910099 | 3.561% | 8608 | 1820 | 21.14% | 1204 | 13.99% | 122 | 1.417% | 449 | 5.216% | 9179 | 6.633% | 12386 | 12490 | 9466 | 9.967% | 86.11%
2 | Central Let | 280925789 | 279211018 | 291396748 | 296252261 | 0 | 297650473 | 6.604% | 89.66% | 10565982 | 3.784% | 10470958 | 3.727% | 9958 | 1948 | 19.56% | 1220 | 12.25% | 48 | 0.482% | 1353 | 13.59% | 11359 | 14.07% | 14650 | 14199 | 11031 | 10.78% | 75.86%
| District Let | 57713105 | 56616300 | 60640688 | 59615142 | 1350000 | 59250940 | 4.654% | 85.71% | 3222542 | 5.692% | 2927585 | 5.073% | 5812 | 795 | 13.68% | 734 | 12.63% | 125 | 2.151% | 524 | 9.016% | 6461 | 11.17% | 8523 | 8149 | 6620 | 13.9% | 80.95%
| All Contracts | 338638894 | 335827318 | 352037436 | 355867403 | 1350000 | 356901413 | 6.275% | 88% | 13788524 | 4.106% | 13398543 | 3.957% | 15770 | 2743 | 17.39% | 1954 | 12.39% | 173 | 1.097% | 1877 | 11.9% | 17820 | 13% | 23173 | 22348 | 17651 | 11.93% | 78%
3 | Central Let | 225969828 | 224396537 | 233781473 | 236481262 | 0 | 237439061 | 5.812% | 100% | 7853143 | 3.5% | 7811645 | 3.457% | 8700 | 2875 | 33.05% | 1224 | 14.07% | 349 | 4.011% | 608 | 6.989% | 9657 | 11% | 13907 | 13800 | 9701 | 11.51% | 88%
| District Let | 22755519 | 22257432 | 23475597 | 23266772 | 25000 | 21192580 | -4.784% | 100% | 689279 | 3.097% | 720079 | 3.164% | 2035 | 738 | 36.27% | 275 | 13.51% | 379 | 18.62% | 150 | 7.371% | 2564 | 26% | 3589 | 3505 | 2492 | 22.46% | 73.33%
| All Contracts | 248725347 | 246653969 | 257257070 | 259748034 | 25000 | 258631641 | 4.856% | 100% | 8542422 | 3.463% | 8531724 | 3.43% | 10735 | 3613 | 33.66% | 1499 | 13.96% | 728 | 6.782% | 758 | 7.061% | 12221 | 13.84% | 17496 | 17305 | 12193 | 13.58% | 82.5%
4 | Central Let | 99065266 | 97833341 | 103363144 | 100569522 | 0 | 99929021 | 2.142% | 91.3% | 4605448 | 4.707% | 4297876 | 4.338% | 8280 | 1525 | 18.42% | 724 | 8.744% | 49 | 0.5918% | 674 | 8.14% | 9003 | 8.732% | 11367 | 11051 | 8802 | 6.304% | 91.3%
| District Let | 27161804 | 26673333 | 27610375 | 26872844 | 100000 | 26784501 | 0.4168% | 100% | 597601 | 2.24% | 448572 | 1.651% | 2439 | 472 | 19.35% | 230 | 9.43% | 94 | 3.854% | 84 | 3.444% | 2617 | 7.298% | 3335 | 3226 | 2524 | 3.485% | 100%
| All Contracts | 126227070 | 124506674 | 130973519 | 127442366 | 100000 | 126713522 | 1.772% | 93.75% | 5203049 | 4.179% | 4746448 | 3.76% | 10719 | 1997 | 18.63% | 954 | 8.9% | 143 | 1.334% | 758 | 7.072% | 11620 | 8.406% | 14702 | 14277 | 11326 | 5.663% | 93.75%
5 | Central Let | 149795662 | 148311041 | 157115245 | 158821712 | -56908 | 158072429 | 6.582% | 82.35% | 7741696 | 5.22% | 7319581 | 4.886% | 5495 | 1420 | 25.84% | 861 | 15.67% | 5 | 0.09099% | 1350 | 24.57% | 6850 | 24.66% | 9197 | 9041 | 6760 | 23.02% | 64.71%
| District Let | 56346906 | 55224457 | 57557471 | 57105489 | 0 | 57120561 | 3.433% | 95.65% | 1615962 | 2.926% | 1210565 | 2.148% | 3914 | 867 | 22.15% | 774 | 19.78% | 0 | 0% | 595 | 15.2% | 4509 | 15.2% | 6150 | 6040 | 4399 | 12.39% | 95.65%
| All Contracts | 206142568 | 203535498 | 214672716 | 215927201 | -56908 | 215192990 | 5.727% | 90% | 9357658 | 4.598% | 8530146 | 4.138% | 9409 | 2287 | 24.31% | 1635 | 17.38% | 5 | 0.05314% | 1945 | 20.67% | 11359 | 20.72% | 15347 | 15081 | 11159 | 18.6% | 82.5%
6 | Central Let | 57225612 | 55727539 | 60484193 | 58815287 | 2570000 | 58659376 | 5.261% | 95% | 3577395 | 6.419% | 3258581 | 5.694% | 4792 | 842 | 17.57% | 402 | 8.389% | 83 | 1.732% | 224 | 4.674% | 5099 | 6.407% | 6397 | 5833 | 4589 | -4.236% | 95%
| District Let | 154863632 | 154005891 | 160072322 | 166552813 | 1513479 | 160888051 | 4.469% | 83.33% | 4920267 | 3.195% | 5208691 | 3.363% | 5800 | 872 | 15.03% | 495 | 8.534% | 68 | 1.172% | -54 | -0.931% | 5814 | 0.2414% | 7211 | 6459 | 5092 | -12.21% | 100%
| All Contracts | 212089244 | 209733430 | 220556515 | 225368100 | 4083479 | 219547427 | 4.679% | 90.62% | 8497662 | 4.052% | 8467272 | 3.992% | 10592 | 1714 | 16.18% | 897 | 8.469% | 151 | 1.426% | 170 | 1.605% | 10913 | 3.031% | 13608 | 12292 | 9681 | -8.601% | 96.88%
7 | Central Let | 53502758 | 52505387 | 59008536 | 59596202 | 0 | 60036504 | 14.34% | 70% | 5614446 | 10.69% | 5505778 | 10.29% | 2969 | 586 | 19.74% | 283 | 9.532% | 0 | 0% | 598 | 20.14% | 3567 | 20.14% | 4436 | 5041 | 4172 | 40.52% | 70%
| District Let | 72311183 | 71557628 | 75875063 | 75706888 | 1275000 | 75486828 | 5.491% | 88.89% | 3618800 | 5.057% | 3563878 | 4.929% | 4011 | 746 | 18.6% | 478 | 11.92% | 259 | 6.457% | 868 | 21.64% | 5138 | 28.1% | 6349 | 6051 | 4827 | 20.34% | 83.33%
| All Contracts | 125813941 | 124063015 | 134883599 | 135303090 | 1275000 | 135523332 | 9.237% | 82.14% | 9233246 | 7.442% | 9069656 | 7.209% | 6980 | 1332 | 19.08% | 761 | 10.9% | 259 | 3.711% | 1466 | 21% | 8705 | 24.71% | 10785 | 11092 | 8999 | 28.93% | 78.57%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 321216972 | 320053859 | 327033639 | 325988774 | 1200000 | 327206738 | 2.235% | 100% | 5384831 | 1.682% | 5816664 | 1.811% | 6074 | 736 | 12.12% | 530 | 8.726% | 10 | 0.1646% | 1086 | 17.88% | 7170 | 18.04% | 8436 | 7948 | 6682 | 10.01% | #VALUE!
| All Contracts | 321216972 | 320053859 | 327033639 | 325988774 | 1200000 | 327206738 | 2.235% | 100% | 5384831 | 1.682% | 5816664 | 1.811% | 6074 | 736 | 12.12% | 530 | 8.726% | 10 | 0.1646% | 1086 | 17.88% | 7170 | 18.04% | 8436 | 7948 | 6682 | 10.01% | 91.67%
Totals This Qtr | Central Let | 952759920 | 943059330 | 992931845 | 997687000 | 2453092 | 998872711 | 5.918% | 91.03% | 41678958 | 4.42% | 40171920 | 4.216% | 44736 | 10302 | 23.03% | 5563 | 12.44% | 605 | 1.352% | 4902 | 10.96% | 50243 | 12.31% | 66674 | 65724 | 49859 | 11.45% | 84.83%
| District Let | 792060246 | 785326269 | 816358879 | 817651464 | 5338479 | 810144523 | 3.16% | 92.8% | 24470710 | 3.116% | 24298632 | 3.068% | 34151 | 5940 | 17.39% | 3871 | 11.33% | 986 | 2.887% | 3607 | 10.56% | 38744 | 13.45% | 49259 | 47109 | 37298 | 9.215% | 85.6%
| All Contracts | 1744820166 | 1728385599 | 1809290724 | 1815338464 | 7791571 | 1809017234 | 4.665% | 91.85% | 66149668 | 3.827% | 64470552 | 3.695% | 78887 | 16242 | 20.59% | 9434 | 11.96% | 1591 | 2.017% | 8509 | 10.79% | 88987 | 12.8% | 115933 | 112833 | 87157 | 10.48% | 85.19%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 116.7% | 1 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 100.3% | 1 | 12243 | -8147 | 134 | 24 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88
| 01 | T1708 | 43656915201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 285 | 365 | 396 | 119.6% | 1 | -31 | 31 | 0 | 55 | 25 | 4931384 | 50000 | 4881384 | 4944272 | 4958547 | -23106 | 0 | -23106 | 4935442 | 4958136 | 101.6% | 1 | 22695 | 12888 | 29 | 26 | 0 | 3 | 8110 | 0 | 0 | 22 | 6965 | 4778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 15075 | 4778 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-06-23 | QTR4 | 21/22 |  | 2020-03-19 | QTR3 | 19/20 | 108 | 5037240.78
| 01 | T1717 | 19801765201 | 2018-12-05 | QTR2 | 18/19 | 4 | 17 | 700 | 913 | 925 | 110.4% | 1 | -12 | 12 | 0 | 152 | 61 | 15860000 | 150000 | 15710000 | 16463364 | 16135347 | -90816 | -60000 | -150816 | 15984531 | 15920739 | 101.3% | 1 | -48363 | 603364 | 111 | 41 | 0 | 0 | 586377 | 3552 | 0 | 4 | 22688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101513 | 0 | 0 | 4 | 619221 | 3552 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2022-03-29 | QTR3 | 21/22 |  | 2021-10-08 | QTR2 | 21/22 | 115 | 15674640.54 | B10 | ACC - BONUS/INCENT/DISINCENT
| 01 | T1724 | 40622565201 | 2019-04-24 | QTR4 | 18/19 | 1 | 7 | 325 | 918 | 899 | 94.15% | 1 | 19 | 0 | 0 | 593 | 0 | 8657668 | 80604 | 8577064 | 9259778 | 9381182 | 0 | 0 | 0 | 9381182 | 9332082 | 108.8% | 1 | -49100 | 602110 | 128 | 465 | 0 | 0 | 283993 | 0 | 0 | 0 | 356793 | 63902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640786 | 63902 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-06-15 | QTR4 | 21/22 |  | 2022-04-01 | QTR4 | 21/22 | 113 | 7999281.74
| 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 84.71% | 1 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 96.23% | 1 | 0 | 8128 | 11 | 6 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21
| 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | 104.2% | 1 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | 100.2% | 1 | -35379 | -23800 | 78 | 28 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38003 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59
| 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 116.5% | 1 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 102.6% | 1 | 6923 | -17395 | 44 | 26 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 |  | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21
| 01 | T1757 | 43943615201 | 2020-07-29 | QTR1 | 20/21 | 3 | 4 | 200 | 261 | 260 | 113% | 1 | 1 | 0 | 0 | 34 | 27 | 2163088 | 50000 | 2113088 | 2182239 | 2172501 | 0 | 0 | 0 | 2172501 | 2181502 | 103.2% | 1 | 9002 | 19151 | 25 | 9 | 0 | 0 | 11573 | 0 | 0 | 27 | 103123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 43328 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 108 | 2199110.64 | B0 | ACC - LUMP SUM
| 01 | T1760 | 43943915201 | 2020-06-10 | QTR4 | 19/20 | 2 | 1 | 235 | 291 | 288 | 98.72% | 1 | 3 | 0 | 0 | 56 | 0 | 4964468 | 57276 | 4907192 | 4976639 | 5027641 | 0 | 0 | 0 | 5027641 | 5062613 | 103.2% | 1 | 34972 | 12171 | 47 | 9 | 0 | 0 | 13541 | 0 | 0 | 0 | 12171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30994 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 |  | 2021-10-18 | QTR2 | 21/22 | 108 | 5089189.35
| 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 97.74% | 1 | 0 | 0 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82
| 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 292 | 111.5% | 1 | 9 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | 106.8% | 1 | -1156 | 114901 | 43 | 26 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43
| 01 | T1774 | 43943315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 2 | 180 | 254 | 251 | 98.33% | 1 | 3 | 0 | 0 | 74 | 0 | 3486645 | 50000 | 3436645 | 3507153 | 3516611 | 0 | 0 | 0 | 3516611 | 3553965 | 103.4% | 1 | 37354 | 20508 | 50 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 20508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24633 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-05-16 | QTR4 | 21/22 |  | 2022-01-19 | QTR3 | 21/22 | 118 | 3999396.52
| 01 | T1775 | 44151915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 275 | 371 | 370 | 99.64% | 1 | 1 | 0 | 0 | 96 | 0 | 7746370 | 98021 | 7648349 | 7776109 | 7775281 | 0 | 0 | 0 | 7775281 | 7823279 | 102.3% | 1 | 47998 | 29739 | 73 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 |  | 2021-11-13 | QTR2 | 21/22 | 118 | 9281425.28
| 01 | T1782 | 44188915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 300 | 458 | 497 | 113% | 1 | -39 | 39 | 0 | 158 | 0 | 7817251 | 97842 | 7719409 | 7814901 | 7885666 | -47180 | 0 | -47180 | 7838486 | 8007597 | 103.7% | 1 | 169112 | -2350 | 112 | 46 | 0 | 0 | 5542 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34380 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 |  | 2022-05-16 | QTR4 | 21/22 | 106 | 9633676.97
| 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 92.86% | 1 | 2188 | 0 | 27 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 |  | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43
| 01 | T1789 | 43693115201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 271 | 270 | 99.5% | 1 | 1 | 0 | 0 | 71 | 0 | 2359731 | 50000 | 2309731 | 2322360 | 2220739 | 0 | 0 | 0 | 2220739 | 2223174 | 96.25% | 1 | 2435 | -37371 | 55 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37371 | 0 | 0 | 0 | -36473 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-01-25 | QTR3 | 21/22 |  | 2021-08-26 | QTR1 | 21/22 | 113 | 2549900.36
| 01 | T1793 | 43815115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 2 | 97 | 183 | 182 | 98.97% | 1 | 1 | 0 | 0 | 86 | 0 | 721749 | 0 | 721749 | 726881 | 731189 | 0 | 0 | 0 | 731189 | 731189 | 101.3% | 1 | 0 | 5132 | 65 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-04-07 | QTR4 | 21/22 |  | 2022-02-24 | QTR3 | 21/22 | 113 | 853456.97
| 01 | T1795 | 44012415201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 100 | 119 | 119 | 100% | 1 | 0 | 0 | 0 | 19 | 0 | 597800 | 23302 | 574498 | 597800 | 548637 | 0 | 0 | 0 | 548637 | 548637 | 95.5% | 1 | 0 | 0 | 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 |  | 2022-02-08 | QTR3 | 21/22 | 115 | 474793.61
| 01 | T1796 | 44050815201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 100 | 124 | 123 | 99% | 1 | 1 | 0 | 0 | 24 | 0 | 817957 | 38521 | 779436 | 986429 | 914986 | 0 | 0 | 0 | 914986 | 914986 | 117.4% | 0 | 0 | 168472 | 19 | 5 | 0 | 0 | 81012 | 0 | 0 | 0 | 87460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168472 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-07 | QTR3 | 21/22 |  | 2021-10-01 | QTR2 | 21/22 | 118 | 656746.29
| 01 | T1798 | 44013615201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 125 | 144 | 143 | 99.2% | 1 | 1 | 0 | 0 | 19 | 0 | 779141 | 30218 | 748923 | 779141 | 703853 | 0 | 0 | 0 | 703853 | 746933 | 99.73% | 1 | 43081 | 0 | 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-16 | QTR4 | 21/22 |  | 2022-03-04 | QTR3 | 21/22 | 115 | 689937.77
| 01 | T1802 | 44067315201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 110 | 147 | 143 | 101.8% | 1 | 4 | 0 | 0 | 31 | 6 | 962055 | 50000 | 912055 | 962055 | 887528 | 0 | 0 | 0 | 887528 | 887873 | 97.35% | 1 | 345 | 0 | 16 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 |  | 2022-03-15 | QTR3 | 21/22 | 108 | 1041118.33
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 21 | 34 | 55 | 4542 | 6720 | 6759 | 100% | 21 | -39 | 99 | 0 | 2026 | 152 | 86275005 | 1200538 | 85074467 | 87782506 | 87150754 | -243824 | -60000 | -303824 | 86846931 | 87085847 | 95.24% | 20 | 254350 | 1507501 | 1106 | 849 | 0 | 4 | 1345749 | 24154 | 1 | 85 | 696785 | 68680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | -393768 | 0 | 0 | 0 | 44677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26139 | 0 | 71 | 95 | 1720848 | 92834
| 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 141.3% | 0 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 103.5% | 1 | 357 | 69031 | 29 | 20 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85
| 01 | E1P95 | 42838315201 | 2017-06-15 | QTR4 | 16/17 | 4 | 13 | 825 | 1189 | 1179 | 124.8% | 0 | 10 | 0 | 0 | 149 | 215 | 12611204 | 102103 | 12509101 | 13133768 | 12450757 | -35183 | -125000 | -160183 | 12290574 | 12343775 | 98.68% | 1 | 53201 | 522564 | 71 | 78 | 0 | 26 | 98702 | 3841 | 0 | 100 | 270614 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156514 | 0 | 0 | 0 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 567739 | 13064 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-15 | QTR3 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 115 | 10409514.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 127.9% | 0 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | 106.1% | 1 | -23194 | 2868754 | 166 | 60 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 |  | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 102.9% | 1 | 0 | 234222 | 11 | 6 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 |  | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33
| 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 97.5% | 1 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | 106.3% | 1 | -52866 | 180574 | 207 | 28 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 |  | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53
| 01 | E1S49 | 19602275201 | 2020-03-26 | QTR3 | 19/20 | 3 | 8 | 360 | 476 | 474 | 109.2% | 1 | 2 | 0 | 0 | 81 | 35 | 4765372 | 50000 | 4715372 | 5108479 | 5065730 | 0 | 0 | 0 | 5065730 | 5081869 | 107.8% | 1 | 16140 | 343107 | 55 | 26 | 0 | 35 | 331038 | 0 | 0 | 0 | 27910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 358948 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 |  | 2021-11-19 | QTR2 | 21/22 | 115 | 5214661.03
| 01 | E1S51 | 44002715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 1 | 80 | 152 | 191 | 182.5% | 0 | -39 | 39 | 0 | 45 | 27 | 407081 | 16632 | 390449 | 421138 | 368049 | -48399 | 0 | -48399 | 319650 | 319650 | 81.87% | 1 | 0 | 14057 | 26 | 19 | 0 | 27 | 14057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14057 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 |  | 2021-02-12 | QTR3 | 20/21 | 115 | 439357.58
| 01 | E1S52 | 44317215201 | 2021-06-10 | QTR4 | 20/21 | 1 | 0 | 100 | 122 | 122 | 101% | 1 | 0 | 0 | 0 | 21 | 1 | 460332 | 21752 | 438580 | 460332 | 429428 | 0 | 0 | 0 | 429428 | 429528 | 97.94% | 1 | 100 | 0 | 5 | 16 | 0 | 1 | 1867 | 0 | 0 | 0 | 9980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11847 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2022-05-10 | QTR4 | 21/22 |  | 2022-01-26 | QTR3 | 21/22 | 118 | 486642.23
| 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 92% | 1 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 104.8% | 1 | 596 | 98871 | 44 | 17 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 |  | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2
| 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | 97.68% | 1 | -5733 | 0 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85
| 01 | E1T43 | 43485715201 | 2021-01-21 | QTR3 | 20/21 | 1 | 2 | 200 | 253 | 247 | 97% | 1 | 6 | 0 | 0 | 53 | 0 | 1132241 | 50000 | 1082241 | 1177226 | 1189866 | 0 | 0 | 0 | 1189866 | 1189866 | 109.9% | 1 | 0 | 44985 | 32 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 44985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44985 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 |  | 2022-03-22 | QTR3 | 21/22 | 113 | 1324427.78
| 01 | E1T46 | 44681615201 | 2020-07-23 | QTR1 | 20/21 | 1 | 1 | 400 | 449 | 449 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3083600 | 50000 | 3033600 | 3080211 | 3030211 | 0 | 0 | 0 | 3030211 | 3030211 | 99.89% | 1 | 0 | -3389 | 18 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 |  | 2021-12-20 | QTR2 | 21/22 | 106 | 4731071.94 | LBDB | LOW BID DESIGN BUILD
| 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 100% | 1 | 520 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1T68 | 43980115201 | 2020-12-03 | QTR2 | 20/21 | 1 | 1 | 75 | 106 | 178 | 209.3% | 0 | -72 | 72 | 0 | 21 | 10 | 180572 | 10362 | 170210 | 210394 | 199372 | -3750 | 0 | -3750 | 195621 | 195621 | 114.9% | 0 | 0 | 29822 | 18 | 3 | 0 | 10 | 29822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29822 | 0 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2022-01-21 | QTR3 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 108 | 260006.67
| 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 15 | 25 | 57 | 4066 | 5666 | 5731 | 66.67% | 10 | -65 | 111 | 0 | 1120 | 480 | 79691125 | 753756 | 78937369 | 84093724 | 82542742 | -87332 | -125000 | -212332 | 82330409 | 82214324 | 93.33% | 14 | -10879 | 4402598 | 714 | 355 | 51 | 205 | 3985709 | 37131 | 0 | 141 | 770737 | 138293 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338988 | 0 | 0 | 0 | -572124 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 354 | 4421428 | 175424
| District 01 Totals |  |  |  |  | 36 | 59 | 112 | 8608 | 12386 | 12490 | 86.11% | 31 | -104 | 210 | 0 | 3146 | 632 | 165966130 | 1954294 | 164011836 | 171876230 | 169693496 | -331156 | -185000 | -516156 | 169177340 | 169300171 | 94.44% | 34 | 243471 | 5910099 | 1820 | 1204 | 51 | 209 | 5331458 | 61285 | 1 | 226 | 1467522 | 206973 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 25 | 6 | -54780 | 0 | 0 | 0 | -527447 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 45 | 5 | 20102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26139 | 0 | 122 | 449 | 6142276 | 268258
| 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 106.7% | 1 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 108.4% | 1 | 593970 | 1812123 | 319 | 136 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 0 | -73244 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1
| 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 122.1% | 0 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 109.7% | 1 | 337124 | 3379021 | 270 | 196 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71
| 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 120.9% | 0 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 107.3% | 1 | 1278355 | 2076018 | 139 | 86 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7
| 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 109.6% | 1 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | 103% | 1 | -48704 | 243564 | 155 | 52 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69
| 02 | T2701 | 20936525201 | 2018-04-25 | QTR4 | 17/18 | 2 | 4 | 480 | 729 | 730 | 114.2% | 1 | -1 | 1 | 0 | 182 | 67 | 11196736 | 139554 | 11057182 | 11726950 | 11984103 | 0 | 0 | 0 | 11984103 | 11975790 | 108.3% | 1 | -8313 | 530213 | 99 | 83 | 0 | 57 | 397506 | 73135 | 0 | 10 | 201220 | 17861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 620548 | 90996 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-08 | QTR4 | 21/22 |  | 2020-07-27 | QTR1 | 20/21 | 208 | 9764053.56
| 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | 215.7% | 0 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | 102.4% | 1 | -1358 | 52280 | 46 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1
| 02 | T2720 | 43735415201 | 2018-10-31 | QTR2 | 18/19 | 1 | 4 | 200 | 572 | 572 | 201% | 0 | 0 | 0 | 0 | 170 | 202 | 2468956 | 50000 | 2418956 | 2635619 | 2856937 | 0 | 0 | 0 | 2856937 | 2843130 | 117.5% | 0 | -13807 | 166663 | 95 | 75 | 0 | 42 | 7693 | 0 | 0 | 160 | 185011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 192704 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-03-29 | QTR3 | 20/21 | 214 | 2333570.34
| 02 | T2743 | 42845515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 4 | 750 | 857 | 857 | 94.67% | 1 | 0 | 0 | 0 | 147 | -40 | 12559204 | 120 | 12559084 | 13123013 | 13368899 | 0 | 0 | 0 | 13368899 | 13241202 | 105.4% | 1 | -127696 | 563809 | 108 | 39 | 0 | -30 | 143449 | 0 | 0 | 0 | 27147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904784 | 590741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -511572 | 0 | 0 | -40 | 563809 | 590741 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-10-27 | QTR2 | 21/22 | 208 | 13121490.39
| 02 | T2744 | 43602315201 | 2019-12-04 | QTR2 | 19/20 | 4 | 6 | 450 | 711 | 711 | 109.1% | 1 | 0 | 0 | 0 | 220 | 41 | 19213273 | 153926 | 19059347 | 19486164 | 20329507 | 0 | 0 | 0 | 20329507 | 20310464 | 106.6% | 1 | -19043 | 272891 | 135 | 85 | 0 | 41 | 288595 | 0 | 0 | 0 | 21126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 403345 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-05-13 | QTR4 | 21/22 |  | 2022-02-07 | QTR3 | 21/22 | 216 | 20412508
| 02 | T2751 | 21172815201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 190 | 336 | 334 | 143.2% | 0 | 2 | 0 | 0 | 75 | 71 | 3950552 | 240 | 3950312 | 4195563 | 4295295 | 0 | 0 | 0 | 4295295 | 4276296 | 108.3% | 1 | -18999 | 245012 | 50 | 12 | 0 | 0 | 143610 | 0 | 13 | 71 | 101402 | 101402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 71 | 245012 | 101402 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 |  | 2020-12-23 | QTR2 | 20/21 | 214 | 4829848.48
| 02 | T2752 | 43395715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 400 | 548 | 485 | 85% | 1 | 63 | 0 | 0 | 145 | 3 | 6416755 | 63600 | 6353155 | 6416755 | 6306830 | 0 | 0 | 0 | 6306830 | 6314515 | 99.39% | 1 | 7685 | 0 | 111 | 34 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 209 | 6469876.4
| 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 77% | 1 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | 115.8% | 0 | -19174 | 475406 | 27 | 28 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1
| 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 100% | 1 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | 98.37% | 1 | -34064 | 0 | 32 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44
| 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | 132.5% | 0 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6136498 | 95.33% | 1 | -12015 | 124056 | 35 | 20 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49
| 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 119.6% | 1 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 87.38% | 1 | 0 | 87084 | 10 | 20 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705
| 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 62.5% | 1 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 99.16% | 1 | 752 | 0 | 38 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42
| 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 60.56% | 1 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 97.14% | 1 | 0 | -4773 | 3 | 23 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49
| 02 | T2773 | 43403815201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 350 | 408 | 389 | 94.57% | 1 | 19 | 0 | 0 | 58 | 0 | 3684895 | 58701 | 3626194 | 3684895 | 3598807 | 0 | 0 | 0 | 3598807 | 3601767 | 99.33% | 1 | 2960 | 0 | 19 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-08-05 | QTR1 | 21/22 | 214 | 3367569.01
| 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 98.67% | 1 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 99.41% | 1 | 338 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88
| 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 84% | 1 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 104% | 1 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46
| 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 108.9% | 1 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | 98.63% | 1 | -48916 | 0 | 24 | 22 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-04 | QTR4 | 21/22 |  | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94
| 02 | T2778 | 44105715201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 230 | 294 | 294 | 100% | 1 | 0 | 0 | 0 | 64 | 0 | 4660748 | 65000 | 4595748 | 4665808 | 4696793 | 0 | 0 | 0 | 4696793 | 4795119 | 104.3% | 1 | 98326 | 5059 | 51 | 13 | 0 | 0 | 12355 | 0 | 0 | 0 | 24208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36563 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-30 | QTR3 | 21/22 |  | 2021-12-06 | QTR2 | 21/22 | 216 | 4464709.06
| 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 65% | 1 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 99.22% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86
| 02 | T2781 | 44106015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 377 | 377 | 105.6% | 1 | 0 | 0 | 0 | 127 | 0 | 5821573 | 74375 | 5747198 | 5821573 | 5952158 | 0 | 0 | 0 | 5952158 | 5882048 | 102.3% | 1 | -70110 | 0 | 92 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-23 | QTR3 | 21/22 |  | 2021-10-27 | QTR2 | 21/22 | 214 | 7534069.47
| 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 72.4% | 1 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | 99.39% | 1 | -59022 | 0 | 28 | 20 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016
| 02 | T2794 | 44112915201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 150 | 283 | 282 | 156% | 0 | 1 | 0 | 0 | 48 | 85 | 3087746 | 50000 | 3037746 | 3440186 | 3518103 | 0 | 0 | 0 | 3518103 | 3660563 | 120.5% | 0 | 142461 | 352440 | 26 | 22 | 0 | 64 | 302440 | 0 | 0 | 21 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 370069 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-05-16 | QTR4 | 21/22 |  | 2021-11-30 | QTR2 | 21/22 | 214 | 3966460.12
| 02 | T2799 | 43584515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 200 | 213 | 163 | 75% | 1 | 50 | 0 | 0 | 13 | 0 | 584000 | 47584 | 536416 | 584000 | 571789 | 0 | 0 | 0 | 571789 | 571826 | 106.6% | 1 | 37 | 0 | 2 | 11 | 0 | 0 | 2239 | 0 | 0 | 0 | 17521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20598 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-03-18 | QTR3 | 21/22 |  | 2021-09-24 | QTR1 | 21/22 | 208 | 883653.52
| 02 | T2851 | 43916415201 | 2021-08-25 | QTR1 | 21/22 | 1 | 0 | 54 | 80 | 73 | 87.04% | 1 | 7 | 0 | 0 | 26 | 0 | 233424 | 15161 | 218263 | 233424 | 220944 | 0 | 0 | 0 | 220944 | 220944 | 101.2% | 1 | 0 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 |  | 2022-01-21 | QTR3 | 21/22 | 209 | 403783.51
| 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 104.4% | 1 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 105.2% | 1 | 0 | 90092 | 12 | 17 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 29 | 44 | 88 | 9958 | 14650 | 14199 | 75.86% | 22 | 451 | 51 | 0 | 3326 | 1366 | 280925789 | 1714771 | 279211018 | 291396748 | 296252261 | -175272 | 0 | -175272 | 296076989 | 297650473 | 89.66% | 26 | 1980787 | 10470958 | 1948 | 1220 | 4 | 717 | 6435172 | 182298 | 30 | 337 | 2616624 | 275228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 79719 | 40265 | 0 | 0 | 66817 | 27317 | 0 | 0 | 0 | 0 | 0 | 29 | 1312893 | 590741 | 0 | 59 | 0 | 0 | 0 | 90 | 639571 | 526026 | 14 | 0 | 0 | 0 | 0 | -10 | -584816 | 0 | 48 | 1353 | 10565982 | 1641876
| 02 | E20B5 | 43054225201 | 2020-10-14 | QTR2 | 20/21 | 1 | 0 | 200 | 272 | 266 | 107.5% | 1 | 6 | 0 | 0 | 51 | 21 | 2358839 | 50000 | 2308839 | 2358839 | 2227074 | 0 | 0 | 0 | 2227074 | 2268054 | 98.23% | 1 | 40980 | 0 | 17 | 34 | 0 | 3 | 23487 | 0 | 0 | 18 | 8087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 31574 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 |  | 2022-02-10 | QTR3 | 21/22 | 214 | 1902693.28
| 02 | E20B6 | 44199825215 | 2020-12-16 | QTR2 | 20/21 | 2 | 0 | 180 | 249 | 249 | 116.7% | 1 | 0 | 0 | 0 | 39 | 30 | 2043961 | 50000 | 1993961 | 2043961 | 1982318 | 0 | 0 | 0 | 1982318 | 2079733 | 104.3% | 1 | 97415 | 0 | 17 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-13 | QTR4 | 21/22 |  | 2022-02-24 | QTR3 | 21/22 | 208 | 2076999.7
| 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 68% | 1 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 94.97% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08
| 02 | E20C4 | 44119915201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 240 | 279 | 261 | 92.5% | 1 | 18 | 0 | 0 | 39 | 0 | 808267 | 48838 | 759429 | 808267 | 699578 | 0 | 0 | 0 | 699578 | 699578 | 92.12% | 1 | 0 | 0 | 11 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 |  | 2022-02-28 | QTR3 | 21/22 | 208 | 914587.52
| 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 150.4% | 0 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 132.8% | 0 | 0 | 177395 | 58 | 34 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 |  | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36
| 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 108% | 1 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | 108.1% | 1 | -1354420 | 997337 | 55 | 118 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 |  | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 145.7% | 0 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 215.1% | 0 | 0 | 1396122 | 103 | 32 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 |  | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42
| 02 | E2X05 | 44030215201 | 2017-12-13 | QTR2 | 17/18 | 1 | 3 | 485 | 1175 | 1344 | 261.4% | 0 | -169 | 169 | 0 | 76 | 614 | 3698384 | 57026 | 3641358 | 3798384 | 3762258 | -475059 | 0 | -475059 | 3287199 | 3287199 | 90.27% | 1 | 0 | 100000 | 26 | 50 | 0 | 84 | 86047 | 0 | 0 | 6 | 34852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120900 | 0 | F382907623 | THE GUARANTEE COMPANY OF NORTH AMERICA U | N/A | N/A | N/A | N/A | 2022-06-06 | QTR4 | 21/22 |  | 2021-12-07 | QTR2 | 21/22 | 209 | 5873791.11 | Y | DESIGN/BUILD PROJECT
| 02 | E2X66 | 43727415201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 500 | 738 | 726 | 112% | 1 | 12 | 0 | 0 | 140 | 98 | 7944015 | 73483 | 7870532 | 8017498 | 8037111 | 0 | 0 | 0 | 8037111 | 8035623 | 102.1% | 1 | -1488 | 73483 | 101 | 65 | 0 | 16 | 42391 | 0 | 0 | 16 | 19034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8993 | 0 | 0 | 0 | 3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 73483 | 0 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2022-05-25 | QTR4 | 21/22 |  | 2022-02-04 | QTR3 | 21/22 | 209 | 7457547.88
| 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 84% | 1 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 87.7% | 1 | 0 | -75888 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 |  | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32
| 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 106.4% | 1 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | 107.7% | 1 | -94 | 50000 | 30 | 77 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21
| 02 | E2Y81 | 43197915201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 390 | 546 | 546 | 106.9% | 1 | 0 | 0 | 0 | 129 | 27 | 2424817 | 50000 | 2374817 | 2497783 | 2495432 | 0 | 0 | 0 | 2495432 | 2495432 | 105.1% | 1 | 0 | 72966 | 82 | 47 | 0 | 50 | 69881 | 69881 | 0 | -23 | 3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 72966 | 69881 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 |  | 2021-09-21 | QTR1 | 21/22 | 208 | 3472664.24
| 02 | E2Y84 | 43807515201 | 2019-11-13 | QTR2 | 19/20 | 3 | 1 | 160 | 223 | 223 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 1543447 | 50000 | 1493447 | 1543447 | 1581148 | 0 | 0 | 0 | 1581148 | 1565351 | 104.8% | 1 | -15797 | 0 | 54 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 |  | 2020-10-23 | QTR2 | 20/21 | 214 | 1817083.25
| 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 99.33% | 1 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | 98.28% | 1 | -1374 | 0 | 63 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 |  | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78
| 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 98.33% | 1 | 0 | 0 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 |  | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99
| 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 222.2% | 0 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 129.5% | 0 | 0 | 82407 | 16 | 20 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27
| 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 30.23% | 1 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 99.9% | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 |  | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7
| 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 62.58% | 1 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 105.3% | 1 | 0 | 49816 | 24 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86
| 02 | E2Z51 | 43384115201 | 2020-04-15 | QTR4 | 19/20 | 1 | 1 | 350 | 442 | 436 | 102% | 1 | 6 | 0 | 0 | 79 | 13 | 2662544 | 50000 | 2612544 | 2666491 | 1959926 | 0 | 0 | 0 | 1959926 | 1959926 | 75.02% | 1 | 0 | 3947 | 33 | 46 | 0 | 0 | 29210 | 0 | 0 | 13 | 3947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 33157 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 |  | 2021-12-08 | QTR2 | 21/22 | 208 | 3385087.42
| 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 109.5% | 1 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 103.7% | 1 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03
| 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 99.07% | 1 | 0 | 0 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING L | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 21 | 27 | 29 | 5812 | 8523 | 8149 | 80.95% | 17 | 374 | 169 | 0 | 1628 | 1083 | 57713105 | 1096806 | 56616300 | 60640688 | 59615142 | -475059 | 1350000 | 874941 | 60490083 | 59250940 | 85.71% | 18 | -1234778 | 2927585 | 795 | 734 | 21 | 271 | 674641 | 286339 | 104 | 94 | 673496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 501136 | 0 | 0 | 0 | 19977 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 29056 | 0 | 0 | 78 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | -75888 | 0 | 125 | 524 | 3222542 | 286339
| District 02 Totals |  |  |  |  | 50 | 71 | 117 | 15770 | 23173 | 22348 | 78% | 39 | 825 | 220 | 0 | 4954 | 2449 | 338638894 | 2811577 | 335827318 | 352037436 | 355867403 | -650331 | 1350000 | 699669 | 356567072 | 356901413 | 88% | 44 | 746009 | 13398543 | 2743 | 1954 | 25 | 988 | 7109813 | 468637 | 134 | 431 | 3290120 | 275228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 580855 | 40265 | 0 | 0 | 86794 | 27317 | 0 | 30 | 0 | 0 | 0 | 29 | 1341949 | 590741 | 0 | 137 | 1400122 | 0 | 0 | 90 | 639571 | 526026 | 14 | 21 | 0 | 0 | 0 | -10 | -660704 | 0 | 173 | 1877 | 13788524 | 1928215
| 03 | T3359 | 21860315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 6 | 1390 | 1975 | 1972 | 104.9% | 1 | 3 | 0 | 0 | 554 | 31 | 48912840 | 150000 | 48762840 | 49557879 | 51455652 | -1500 | 0 | -1500 | 51454152 | 52944876 | 108.6% | 1 | 1630015 | 645040 | 374 | 140 | 37 | 4 | 203820 | 0 | 0 | 27 | 296208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 55749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 31 | 555777 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-04-12 | QTR4 | 21/22 |  | 2022-02-04 | QTR3 | 21/22 | 308 | 41351319.57
| 03 | T3533 | 21797635201 | 2015-05-20 | QTR4 | 14/15 | 2 | 35 | 970 | 1882 | 1882 | 139.3% | 0 | 0 | 0 | 0 | 531 | 381 | 67999204 | 150000 | 67849204 | 73183986 | 72810755 | 0 | 0 | 0 | 72810755 | 72504196 | 106.9% | 1 | -146921 | 5184782 | 356 | 175 | 0 | 0 | 19580 | 0 | 0 | 20 | 617542 | 34940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62700 | 0 | 0 | 77 | 1308271 | 134897 | 0 | 0 | 713312 | 5395 | 0 | 0 | 0 | 0 | 0 | 6 | 355429 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 4237789 | 4237789 | 0 | 0 | 0 | 0 | 0 | 0 | -2214282 | 0 | 0 | 381 | 5100342 | 4413021 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-04-05 | QTR4 | 21/22 |  | 2021-03-18 | QTR3 | 20/21 | 306 | 77505595.07 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 03 | T3632 | 43581515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 5 | 365 | 642 | 641 | 114% | 1 | 1 | 0 | 0 | 262 | 15 | 4962076 | 50000 | 4912076 | 5040837 | 5106121 | 0 | 0 | 0 | 5106121 | 5104120 | 103.9% | 1 | -2001 | 78760 | 171 | 54 | 0 | 15 | 72486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 41435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 15 | 113922 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 |  | 2021-10-25 | QTR2 | 21/22 | 314 | 4401368.62
| 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 99.27% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 |  | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM
| 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 99.53% | 1 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 97.72% | 1 | 28314 | 256400 | 170 | 73 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000
| 03 | T3660 | 40619435201 | 2018-05-23 | QTR4 | 17/18 | 1 | 6 | 750 | 1143 | 1143 | 122.3% | 0 | 0 | 0 | 0 | 371 | 22 | 8456503 | 83020 | 8373483 | 8769565 | 8750489 | 0 | 0 | 0 | 8750489 | 8742318 | 104.4% | 1 | -8170 | 313062 | 113 | 113 | 0 | 22 | 323879 | 180859 | 0 | 0 | 8846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 332725 | 180859 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 |  | 2021-12-21 | QTR2 | 21/22 | 308 | 7797092.45
| 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 66.67% | 1 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 101.2% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 |  | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91
| 03 | T3689 | 21876425201 | 2019-12-04 | QTR2 | 19/20 | 1 | 5 | 410 | 588 | 586 | 107.8% | 1 | 2 | 0 | 0 | 144 | 34 | 3948246 | 50000 | 3898246 | 4424349 | 4230338 | 0 | 0 | 0 | 4230338 | 4232949 | 108.6% | 1 | 2611 | 476103 | 106 | 38 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-05-02 | QTR4 | 21/22 |  | 2021-11-20 | QTR2 | 21/22 | 321 | 3709288.8
| 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 100.7% | 1 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | 104.7% | 1 | -86540 | 385593 | 320 | 100 | 0 | 3 | 71605 | 0 | 0 | 4 | 120253 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429398 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93
| 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 115.3% | 1 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | 98.95% | 1 | -2489 | -30187 | 126 | 44 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 |  | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8
| 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 97.22% | 1 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 91.84% | 1 | 466 | 0 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24
| 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 101.3% | 1 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 104.2% | 1 | 247 | 27245 | 34 | 16 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46
| 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | 101.3% | 1 | -146878 | 58629 | 112 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83
| 03 | T3725 | 43627315201 | 2020-02-26 | QTR3 | 19/20 | 1 | 4 | 255 | 618 | 618 | 195.3% | 0 | 0 | 0 | 0 | 325 | 38 | 6407925 | 72715 | 6335210 | 6454693 | 6883968 | 0 | 0 | 0 | 6883968 | 6913504 | 109.1% | 1 | 29535 | 46768 | 50 | 70 | 0 | 0 | 1320 | 0 | 205 | 38 | 77843 | 31122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 38 | 79163 | 31122 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-05 | QTR4 | 21/22 |  | 2022-01-19 | QTR3 | 21/22 | 308 | 7243439.74
| 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 102.7% | 1 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | 108.4% | 1 | -50153 | 204347 | 63 | 25 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85
| 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 107% | 1 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | 107.5% | 1 | -68789 | 0 | 292 | 81 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-19 | QTR4 | 21/22 |  | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94
| 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 107.8% | 1 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 101.2% | 1 | 1050 | 37203 | 43 | 34 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86
| 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | 101.9% | 1 | -53128 | 0 | 168 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 |  | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9
| 03 | T3745 | 43972915201 | 2020-02-26 | QTR3 | 19/20 | 2 | 3 | 365 | 513 | 512 | 108.5% | 1 | 1 | 0 | 0 | 135 | 13 | 7352550 | 86750 | 7265800 | 7448821 | 7636800 | 0 | 0 | 0 | 7636800 | 7674029 | 105.6% | 1 | 37229 | 96271 | 76 | 40 | 0 | 13 | 91427 | 0 | 0 | 0 | 29526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 13 | 139443 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-16 | QTR3 | 21/22 |  | 2021-09-30 | QTR1 | 21/22 | 321 | 8840050.49
| 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 88% | 1 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 108.1% | 1 | 76040 | 0 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13
| 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 90 | 174 | 176 | 110% | 1 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 778131 | 692739 | 0 | 0 | 0 | 692739 | 692739 | 96.65% | 1 | 0 | 22669 | 39 | 38 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22669 | 12169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 27869 | 12169 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61
| 03 | T3751 | 43775325201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 335 | 445 | 445 | 100% | 1 | 0 | 0 | 0 | 110 | 0 | 2569909 | 50000 | 2519909 | 2569909 | 2490758 | 0 | 0 | 0 | 2490758 | 2498656 | 99.16% | 1 | 7898 | 0 | 82 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 |  | 2021-08-24 | QTR1 | 21/22 | 313 | 2572447.1
| 03 | T3760 | 44154015201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 150 | 228 | 220 | 94.67% | 1 | 8 | 0 | 0 | 78 | 0 | 3001621 | 50000 | 2951621 | 3001621 | 2905181 | 0 | 0 | 0 | 2905181 | 2997834 | 101.6% | 1 | 92653 | 0 | 52 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-24 | QTR4 | 21/22 |  | 2022-01-06 | QTR3 | 21/22 | 321 | 2841104.56
| 03 | T3763 | 43661515201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 365 | 435 | 433 | 99.45% | 1 | 2 | 0 | 0 | 70 | 0 | 4894168 | 0 | 4894168 | 4903128 | 5058997 | 0 | 0 | 0 | 5058997 | 5067842 | 103.5% | 1 | 8845 | 8960 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2022-01-18 | QTR3 | 21/22 |  | 2021-11-01 | QTR2 | 21/22 | 321 | 5019527.85
| 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 88% | 1 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 102.2% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 |  | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 25 | 36 | 97 | 8700 | 13907 | 13800 | 88% | 22 | 107 | 2 | 0 | 4599 | 608 | 225969828 | 1573294 | 224396537 | 233781473 | 236481262 | -26000 | 0 | -26000 | 236455262 | 237439061 | 100% | 25 | 1349834 | 7811645 | 2875 | 1224 | 54 | 69 | 823479 | 180859 | 240 | 163 | 1893790 | 156347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62700 | 0 | 34 | 85 | 1689697 | 147066 | 2 | 1 | 919758 | 5395 | 0 | 0 | 0 | 0 | 0 | 12 | 440209 | 0 | 0 | 0 | 0 | 0 | 19 | 278 | 4237789 | 4237789 | 0 | 0 | 0 | 0 | 0 | 0 | -2214282 | 0 | 349 | 608 | 7853143 | 4727456
| 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | 208.7% | 0 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 91.39% | 1 | 0 | 49116 | 256 | 90 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 159.3% | 0 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 100% | 1 | 0 | 0 | 213 | 23 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 |  | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049
| 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 52.67% | 1 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | 0% | 1 | -174645 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33
| 03 | E3T18 | 42282325201 | 2020-12-17 | QTR2 | 20/21 | 1 | 0 | 45 | 46 | 32 | 68.89% | 1 | 14 | 0 | 0 | 1 | 0 | 145277 | 9380 | 135897 | 145277 | 129137 | 0 | 0 | 0 | 129137 | 129137 | 95.03% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-01-05 | QTR3 | 21/22 |  | 2021-04-23 | QTR4 | 20/21 | 321 | 213559.46
| 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 101.7% | 1 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | 105.3% | 1 | -2525 | 0 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39
| 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 51.67% | 1 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 99.94% | 1 | 0 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79
| 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 114.4% | 1 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | 101.6% | 1 | -25000 | 92806 | 26 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3T51 | 44154215201 | 2021-01-14 | QTR3 | 20/21 | 1 | 1 | 150 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 1940669 | 50000 | 1890669 | 1921236 | 1976977 | 0 | 0 | 0 | 1976977 | 2038310 | 107.8% | 1 | 61333 | -19433 | 67 | 18 | 0 | 0 | -19433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9361 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-05-02 | QTR4 | 21/22 |  | 2021-12-16 | QTR2 | 21/22 | 308 | 1982216.25
| 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 253.3% | 0 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 104.6% | 1 | 0 | 14821 | 35 | 42 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 |  | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45
| 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 85.56% | 1 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | 0% | 1 | -225968 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2020-10-20 | QTR2 | 20/21 | 314 | 246220
| 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 148.9% | 0 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | 0% | 1 | -1338192 | 582769 | 17 | 11 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 |  | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1
| 03 | E3U12 | 44365725201 | 2021-07-08 | QTR1 | 21/22 | 1 | 0 | 100 | 148 | 147 | 99% | 1 | 1 | 0 | 0 | 48 | 0 | 2742031 | 50000 | 2692031 | 2742031 | 2766138 | 0 | 0 | 0 | 2766138 | 2770405 | 102.9% | 1 | 4267 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-07 | QTR4 | 21/22 |  | 2022-03-02 | QTR3 | 21/22 | 314 | 2471807.29
| 03 | E3U25 | 44364215201 | 2021-07-08 | QTR1 | 21/22 | 1 | 0 | 160 | 192 | 151 | 74.38% | 1 | 41 | 0 | 0 | 32 | 0 | 2814688 | 50000 | 2764688 | 2814688 | 2846250 | 0 | 0 | 0 | 2846250 | 2857872 | 103.4% | 1 | 11622 | 0 | 15 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | QTR4 | 21/22 |  | 2022-03-04 | QTR3 | 21/22 | 321 | 4496574.19
| 03 | E3U27 | 44154515201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 222 | 221 | 99.44% | 1 | 1 | 0 | 0 | 42 | 0 | 1641103 | 50000 | 1591103 | 1641103 | 1553101 | 0 | 0 | 0 | 1553101 | 1614039 | 101.4% | 1 | 60937 | 0 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2022-03-07 | QTR3 | 21/22 |  | 2021-11-01 | QTR2 | 21/22 | 321 | 2039669.94
| 03 | E3U34 | 44718815201 | 2021-11-10 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 46 | 76.67% | 1 | 14 | 0 | 0 | 0 | 0 | 294449 | 16530 | 277920 | 294449 | 275309 | 0 | 0 | 0 | 275309 | 275309 | 99.06% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-06-07 | QTR4 | 21/22 |  | 2022-04-11 | QTR4 | 21/22 | 313 | 345934.65
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 15 | 22 | 14 | 2035 | 3589 | 3505 | 73.33% | 11 | 84 | 160 | 0 | 1392 | 162 | 22755519 | 498088 | 22257432 | 23475597 | 23266772 | -449760 | 25000 | -424760 | 22842012 | 21192580 | 100% | 15 | -1628171 | 720079 | 738 | 275 | 365 | 71 | -19433 | 0 | 5 | 0 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 117698 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 150 | 689279 | 0
| District 03 Totals |  |  |  |  | 40 | 58 | 111 | 10735 | 17496 | 17305 | 82.5% | 33 | 191 | 162 | 0 | 5991 | 770 | 248725347 | 2071382 | 246653969 | 257257070 | 259748034 | -475760 | 25000 | -450760 | 259297274 | 258631641 | 100% | 40 | -278337 | 8531724 | 3613 | 1499 | 419 | 140 | 804046 | 180859 | 245 | 163 | 1902034 | 156347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62700 | 0 | 37 | 106 | 1807395 | 147066 | 2 | 19 | 919758 | 5395 | 0 | 0 | 0 | 0 | 6 | 52 | 1022978 | 0 | 0 | 0 | 0 | 0 | 19 | 278 | 4237789 | 4237789 | 0 | 0 | 0 | 0 | 0 | 0 | -2214282 | 0 | 728 | 758 | 8542422 | 4727456
| 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 154.1% | 0 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | 104.3% | 1 | -5522 | 345672 | 158 | 48 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 0 | 0 | -46629 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32
| 04 | T4476 | 43515815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 4 | 582 | 825 | 825 | 110.3% | 1 | 0 | 0 | 0 | 183 | 60 | 7524128 | 71928 | 7452200 | 7782657 | 7606665 | 0 | 0 | 0 | 7606665 | 7546955 | 101.3% | 1 | -47141 | 258528 | 91 | 92 | 0 | 0 | 12809 | 0 | 0 | 0 | 107865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34366 | 34366 | 0 | 60 | 107988 | 107988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 263028 | 142354 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 |  | 2021-01-18 | QTR3 | 20/21 | 409 | 7189789.75
| 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | 110% | 1 | -79 | 50449 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 |  | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52
| 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 103.4% | 1 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | 103.1% | 1 | -41100 | 238143 | 56 | 38 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83
| 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 120% | 1 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | 121.4% | 0 | -38478 | 1701896 | 99 | 57 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34
| 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 104.1% | 1 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | 108.7% | 1 | -136647 | 836144 | 110 | 44 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29
| 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 101.4% | 1 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | 96.13% | 1 | -58724 | -97855 | 61 | 33 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99541 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17
| 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 99.49% | 1 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | 104.1% | 1 | -17714 | 162310 | 92 | 33 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17
| 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 72.21% | 1 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | 92.16% | 1 | -17236 | -58454 | 82 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 |  | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2
| 04 | T4512 | 44007715201 | 2019-04-24 | QTR4 | 18/19 | 4 | 1 | 498 | 864 | 892 | 168.1% | 0 | -28 | 28 | 0 | 55 | 311 | 1450367 | 50000 | 1400367 | 1450367 | 1167077 | -139860 | 0 | -139860 | 1027217 | 1108655 | 79.17% | 1 | 81438 | 0 | 17 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | Z31-0501234 | GREAT AMERICAN INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2022-06-14 | QTR4 | 21/22 |  | 2022-05-26 | QTR4 | 21/22 | 412 | 1609511.16
| 04 | T4519 | 43469715201 | 2019-05-22 | QTR4 | 18/19 | 2 | 2 | 677 | 987 | 987 | 100% | 1 | 0 | 0 | 0 | 310 | 0 | 4993117 | 59112 | 4934005 | 5545786 | 5542522 | 0 | 0 | 0 | 5542522 | 5530113 | 112.1% | 0 | -7312 | 552669 | 247 | 63 | 0 | 0 | -4497 | 0 | 0 | 0 | 552069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547573 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-05-31 | QTR4 | 21/22 |  | 2022-04-07 | QTR4 | 21/22 | 412 | 5587127.63
| 04 | T4521 | 43760515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 160 | 246 | 244 | 114.4% | 1 | 2 | 0 | 0 | 86 | 0 | 737736 | 38647 | 699089 | 737736 | 679527 | 0 | 0 | 0 | 679527 | 679527 | 97.2% | 1 | 0 | 0 | 47 | 14 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 |  | 2021-12-22 | QTR2 | 21/22 | 412 | 798445.57
| 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 102.5% | 1 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | 97.23% | 1 | -108218 | 74017 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 |  | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95
| 04 | T4525 | 42956955201 | 2019-10-30 | QTR2 | 19/20 | 2 | 6 | 621 | 777 | 775 | 106.1% | 1 | 2 | 0 | 0 | 116 | 40 | 3469054 | 50000 | 3419054 | 3785520 | 3699667 | 0 | 0 | 0 | 3699667 | 3693815 | 108% | 1 | -5852 | 316466 | 66 | 50 | 0 | 0 | 1783 | 0 | 0 | 0 | 273550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 51300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326632 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-05-18 | QTR4 | 21/22 |  | 2022-04-01 | QTR4 | 21/22 | 412 | 3402492.11
| 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 90.84% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3
| 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 96.65% | 1 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | 100.6% | 1 | -30966 | 39603 | 54 | 27 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03
| 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 103.5% | 1 | 250 | 0 | 81 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89
| 04 | T4542 | 43984215201 | 2020-02-26 | QTR3 | 19/20 | 3 | 4 | 536 | 613 | 608 | 98.32% | 1 | 5 | 0 | 0 | 81 | -4 | 21806360 | 150000 | 21656360 | 21667458 | 20680425 | 3782 | 0 | 3782 | 20684206 | 20634573 | 95.28% | 1 | -36266 | -138902 | 37 | 44 | 0 | 0 | -179532 | 0 | 0 | 0 | 221401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -184535 | 0 | 0 | -4 | -137070 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 |  | 2022-01-10 | QTR3 | 21/22 | 409 | 28727824.18
| 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66.83% | 1 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 98.35% | 1 | 237 | 0 | 25 | 18 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94
| 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 75.77% | 1 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 96.14% | 1 | 93 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 |  | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46
| 04 | T4555 | 43990915201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 128 | 152 | 148 | 96.88% | 1 | 4 | 0 | 0 | 24 | 0 | 441982 | 24322 | 417660 | 441982 | 407189 | 0 | 0 | 0 | 407189 | 407189 | 97.49% | 1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-10-06 | QTR2 | 21/22 | 412 | 501234.56
| 04 | T4556 | 43991015201 | 2020-11-18 | QTR2 | 20/21 | 3 | 1 | 146 | 231 | 231 | 115.1% | 1 | 0 | 0 | 0 | 63 | 22 | 2687973 | 50000 | 2637973 | 2705163 | 2740129 | 0 | 0 | 0 | 2740129 | 2844345 | 107.8% | 1 | 104217 | 17190 | 42 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 26851 | 10090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15508 | 0 | 0 | 0 | 4858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 47217 | 10090 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 |  | 2022-03-15 | QTR3 | 21/22 | 412 | 3230256.06
| 04 | T4574 | 44179515201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 222 | 246 | 213 | 85.14% | 1 | 33 | 0 | 0 | 24 | 0 | 622222 | 31098 | 591125 | 622222 | 556248 | 0 | 0 | 0 | 556248 | 556291 | 94.11% | 1 | 43 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 |  | 2022-05-18 | QTR4 | 21/22 | 412 | 654229.43
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 23 | 45 | 66 | 8280 | 11367 | 11051 | 91.3% | 21 | 316 | 28 | 0 | 2298 | 789 | 99065266 | 1231926 | 97833341 | 103363144 | 100569522 | -205018 | 0 | -205018 | 100364503 | 99929021 | 91.3% | 21 | -364977 | 4297876 | 1525 | 724 | 0 | 117 | 2328083 | 1339455 | 31 | 56 | 2042435 | 122710 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 383 | 181522 | 0 | 0 | 6 | 96959 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 110898 | 82669 | 18 | 116 | 196745 | 190656 | 0 | 0 | 0 | 0 | 0 | -4 | -330705 | 0 | 49 | 674 | 4605448 | 1761131
| 04 | E4T51 | 43785115201 | 2019-02-01 | QTR3 | 18/19 | 2 | 8 | 524 | 733 | 733 | 109.7% | 1 | 0 | 0 | 0 | 158 | 51 | 6476041 | 50000 | 6426041 | 6901248 | 6999986 | 0 | 0 | 0 | 6999986 | 6950609 | 108.2% | 1 | -10152 | 425207 | 126 | 32 | 0 | 10 | 116335 | 0 | 0 | 0 | 13376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 280242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 421482 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-04-04 | QTR4 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 412 | 6413384.4
| 04 | E4T80 | 43524515201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 447 | 612 | 612 | 114.5% | 1 | 0 | 0 | 0 | 165 | 0 | 6403403 | 65499 | 6337904 | 6403403 | 6376174 | 0 | 0 | 0 | 6376174 | 6376174 | 100.6% | 1 | 0 | 0 | 49 | 51 | 0 | 0 | 15582 | 0 | 65 | 0 | 28688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 44270 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 |  | 2022-01-19 | QTR3 | 21/22 | 408 | 6290935.81 | A3 | ICC - DESIGN/BUILD - MINOR
| 04 | E4T83 | 42268145201 | 2020-05-01 | QTR4 | 19/20 | 1 | 0 | 240 | 375 | 375 | 107.9% | 1 | 0 | 0 | 0 | 116 | 19 | 2027817 | 50000 | 1977817 | 2027817 | 1963518 | 0 | 0 | 0 | 1963518 | 1968273 | 99.52% | 1 | 4756 | 0 | 91 | 25 | 0 | 0 | 14875 | 0 | 0 | 19 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 40339 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2022-01-27 | QTR3 | 21/22 |  | 2021-09-01 | QTR1 | 21/22 | 408 | 2656948.48
| 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 100.7% | 1 | 95 | -399 | 22 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08
| 04 | E4U33 | 43804215201 | 2020-04-03 | QTR4 | 19/20 | 3 | 2 | 390 | 606 | 587 | 106.7% | 1 | 19 | 0 | 0 | 200 | 16 | 6709662 | 72972 | 6636690 | 6719050 | 6438347 | 0 | 0 | 0 | 6438347 | 6383292 | 96.18% | 1 | -45666 | 9389 | 123 | 48 | 0 | 0 | 0 | 0 | 29 | 0 | 15137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 17213 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-10 | QTR4 | 21/22 |  | 2022-02-17 | QTR3 | 21/22 | 408 | 7407886.85
| 04 | E4U47 | 44147315201 | 2021-04-02 | QTR4 | 20/21 | 1 | 0 | 168 | 194 | 107 | 48.21% | 1 | 87 | 0 | 0 | 26 | 0 | 1068289 | 50000 | 1018289 | 1068289 | 977728 | 0 | 0 | 0 | 977728 | 977728 | 96.02% | 1 | 0 | 0 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-05-05 | QTR4 | 21/22 |  | 2022-02-10 | QTR3 | 21/22 | 412 | 1267517.98
| 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 110.9% | 1 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | 88.88% | 1 | -95454 | 15486 | 15 | 5 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 |  | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | E4U72 | 44162915201 | 2021-01-08 | QTR3 | 20/21 | 1 | 0 | 144 | 178 | 178 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 893625 | 50000 | 843625 | 893625 | 846410 | 0 | 0 | 0 | 846410 | 849948 | 100.7% | 1 | 3538 | 0 | 25 | 9 | 0 | 0 | 5931 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26097 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 |  | 2021-09-19 | QTR1 | 21/22 | 412 | 1052584.82
| 04 | E4U74 | 44162815201 | 2021-03-05 | QTR3 | 20/21 | 3 | 1 | 153 | 186 | 183 | 98.04% | 1 | 3 | 0 | 0 | 33 | 0 | 1190833 | 50000 | 1140833 | 1189722 | 1098149 | 0 | 0 | 0 | 1098149 | 1101304 | 96.54% | 1 | 3155 | -1111 | 12 | 21 | 0 | 0 | -1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1111 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-25 | QTR3 | 21/22 |  | 2022-01-17 | QTR3 | 21/22 | 412 | 1310702.75
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 9 | 16 | 13 | 2439 | 3335 | 3226 | 100% | 9 | 109 | 0 | 0 | 796 | 100 | 27161804 | 488471 | 26673333 | 27610375 | 26872844 | 0 | 100000 | 100000 | 26972844 | 26784501 | 100% | 9 | -139728 | 448572 | 472 | 230 | 0 | 10 | 157339 | 0 | 94 | 33 | 138666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19277 | 0 | 0 | 0 | 2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 280242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 84 | 597601 | 0
| District 04 Totals |  |  |  |  | 32 | 61 | 79 | 10719 | 14702 | 14277 | 93.75% | 30 | 425 | 28 | 0 | 3094 | 889 | 126227070 | 1720397 | 124506674 | 130973519 | 127442366 | -205018 | 100000 | -105018 | 127337347 | 126713522 | 93.75% | 30 | -504705 | 4746448 | 1997 | 954 | 0 | 127 | 2485422 | 1339455 | 125 | 89 | 2181101 | 122710 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 383 | 200799 | 0 | 0 | 6 | 99035 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 110898 | 82669 | 18 | 157 | 476987 | 190656 | 0 | 0 | 0 | 0 | 0 | -4 | -330705 | 0 | 143 | 758 | 5203049 | 1761131
| 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 113.9% | 1 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 105.7% | 1 | 430838 | 374749 | 219 | 102 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3
| 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 137.8% | 0 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 104% | 1 | 328547 | 8369 | 210 | 62 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22
| 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 96.77% | 1 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | 103% | 1 | -222563 | -4 | 112 | 57 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38
| 05 | T5636 | 43800315201 | 2018-10-31 | QTR2 | 18/19 | 4 | 4 | 550 | 898 | 899 | 103.5% | 1 | -1 | 1 | 0 | 330 | 18 | 28838467 | 150000 | 28688467 | 29085178 | 28445436 | 0 | -56908 | -56908 | 28388528 | 27168457 | 94.7% | 1 | -1042919 | 246710 | 194 | 136 | 0 | 18 | 12551 | 0 | 0 | 0 | 3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24852 | 0 | 0 | 0 | 28328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 69559 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 |  | 2021-08-03 | QTR1 | 21/22 | 513 | 39785384.05
| 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 347.9% | 0 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | 219.7% | 0 | -16169 | 3253176 | 23 | 51 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320
| 05 | T5645 | 43988515201 | 2019-04-24 | QTR4 | 18/19 | 1 | 2 | 210 | 401 | 401 | 169% | 0 | 0 | 0 | 0 | 46 | 145 | 920856 | 50000 | 870856 | 858040 | 792026 | 0 | 0 | 0 | 792026 | 792105 | 90.96% | 1 | 79 | -62817 | 20 | 26 | 0 | 0 | -28659 | 0 | 0 | 0 | 24188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -32481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -36952 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 |  | 2021-07-13 | QTR1 | 21/22 | 509 | 1118770.85
| 05 | T5668 | 43968235201 | 2019-05-22 | QTR4 | 18/19 | 4 | 11 | 510 | 788 | 778 | 128.4% | 0 | 10 | 0 | 0 | 123 | 155 | 20003719 | 154151 | 19849568 | 23051817 | 24148539 | 0 | 0 | 0 | 24148539 | 24037958 | 121.1% | 0 | -110580 | 3048098 | 58 | 65 | 0 | 155 | 2206932 | 2589 | 0 | 0 | 818285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91658 | 0 | 0 | 0 | 52092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 3168966 | 2589 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-04 | QTR3 | 21/22 |  | 2021-10-21 | QTR2 | 21/22 | 507 | 16312265.29
| 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 134.8% | 0 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | 101.4% | 1 | -48503 | 72336 | 18 | 22 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68
| 05 | T5670 | 43020245201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 260 | 396 | 395 | 109.2% | 1 | 1 | 0 | 0 | 116 | 20 | 2204501 | 50000 | 2154501 | 2284647 | 2359499 | 0 | 0 | 0 | 2359499 | 2362734 | 109.7% | 1 | 13475 | 80146 | 76 | 35 | 0 | 0 | 4980 | 0 | 5 | 20 | 70131 | 7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 77386 | 7656 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-01-12 | QTR3 | 21/22 |  | 2020-08-11 | QTR1 | 20/21 | 514 | 1667431.38
| 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 150% | 0 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | 105.3% | 1 | -28879 | 22908 | 74 | 22 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 |  | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09
| 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 106.8% | 1 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | 96.78% | 1 | -191521 | 85887 | 113 | 94 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87
| 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 89.33% | 1 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | 97.46% | 1 | -39533 | 3360 | 113 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 |  | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7
| 05 | T5683 | 44141415201 | 2020-07-29 | QTR1 | 20/21 | 2 | 1 | 310 | 505 | 470 | 108.1% | 1 | 35 | 0 | 0 | 135 | 60 | 2891598 | 50000 | 2841598 | 3078261 | 3109373 | 0 | 0 | 0 | 3109373 | 3141296 | 110.5% | 0 | 31923 | 186663 | 58 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186663 | 226391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 190632 | 226391 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-10 | QTR4 | 21/22 |  | 2022-04-15 | QTR4 | 21/22 | 513 | 3095610.25
| 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 86.92% | 1 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 99.25% | 1 | 35505 | 0 | 18 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04
| 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 99.23% | 1 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 100.2% | 1 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25
| 05 | T5710 | 44136615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 86 | 128 | 128 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 614736 | 29870 | 584866 | 614736 | 554534 | 0 | 0 | 0 | 554534 | 554534 | 94.81% | 1 | 0 | 0 | 38 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 |  | 2021-11-09 | QTR2 | 21/22 | 512 | 624301.96
| 05 | T5734 | 44101315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 190 | 310 | 304 | 111.1% | 1 | 6 | 0 | 0 | 93 | 27 | 6878342 | 77767 | 6800575 | 6878342 | 6971991 | 0 | 0 | 0 | 6971991 | 7381860 | 108.5% | 1 | 409869 | 0 | 70 | 23 | 0 | 27 | 52873 | 0 | 0 | 0 | 10074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 66884 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-30 | QTR4 | 21/22 |  | 2022-04-27 | QTR4 | 21/22 | 514 | 7850496.57
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 17 | 36 | 53 | 5495 | 9197 | 9041 | 64.71% | 11 | 156 | 1 | 0 | 2286 | 1416 | 149795662 | 1484621 | 148311041 | 157115245 | 158821712 | -7304 | -56908 | -64212 | 158757500 | 158072429 | 82.35% | 14 | -449582 | 7319581 | 1420 | 861 | 0 | 324 | 2631290 | 21983 | 5 | 805 | 4475499 | 13955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 337341 | 226391 | 0 | 16 | 130899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1350 | 7741696 | 268779
| 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 107.2% | 1 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 102.7% | 1 | 0 | 30409 | 84 | 17 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 |  | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5
| 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 101.1% | 1 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 102.8% | 1 | 0 | 0 | 13 | 6 | 0 | 0 | 7876 | 0 | 0 | 3 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 |  | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7
| 05 | E52A2 | 44316815201 | 2020-10-06 | QTR2 | 20/21 | 2 | 1 | 220 | 274 | 276 | 100.9% | 1 | -2 | 2 | 0 | 54 | 0 | 7726425 | 101900 | 7624525 | 7711640 | 7780592 | 0 | 0 | 0 | 7780592 | 7870977 | 103.2% | 1 | 90385 | -14785 | 29 | 25 | 0 | 0 | -17404 | 0 | 0 | 0 | 2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7315 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2021-10-06 | QTR2 | 21/22 | 513 | 10078671.13
| 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 81.25% | 1 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 92.06% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-04-14 | QTR4 | 20/21 | 507 | 309304
| 05 | E53A6 | 44119715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 0 | 70 | 109 | 109 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 320193 | 13925 | 306268 | 320193 | 308143 | 0 | 0 | 0 | 308143 | 308143 | 100.6% | 1 | 0 | 0 | 24 | 15 | 0 | 0 | 12247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12247 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 |  | 2021-12-02 | QTR2 | 21/22 | 507 | 289415.18
| 05 | E53A7 | 44333415201 | 2020-12-15 | QTR2 | 20/21 | 1 | 1 | 100 | 318 | 318 | 100% | 1 | 0 | 0 | 0 | 218 | 0 | 1002182 | 50000 | 952182 | 1002182 | 953504 | 0 | 0 | 0 | 953504 | 953504 | 100.1% | 1 | 0 | 0 | 42 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2022-04-28 | QTR4 | 21/22 |  | 2022-02-04 | QTR3 | 21/22 | 514 | 1304377.5
| 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 117.1% | 1 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 102.1% | 1 | 0 | 0 | 7 | 5 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03
| 05 | E54A0 | 44208815201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 190 | 190 | 115.7% | 1 | 0 | 0 | 0 | 109 | 11 | 524491 | 26260 | 498231 | 524491 | 485346 | 0 | 0 | 0 | 485346 | 485346 | 97.41% | 1 | 0 | 0 | 85 | 24 | 0 | 0 | 362 | 0 | 0 | 11 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2053 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2022-01-06 | QTR3 | 21/22 | 507 | 529396.72
| 05 | E54A2 | 44589615201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 140 | 158 | 144 | 90% | 1 | 14 | 0 | 0 | 18 | 0 | 553370 | 29890 | 523480 | 553370 | 525670 | 0 | 0 | 0 | 525670 | 525670 | 100.4% | 1 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-01-10 | QTR3 | 21/22 |  | 2021-10-07 | QTR2 | 21/22 | 514 | 622693
| 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 31% | 1 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 98.44% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 |  | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5
| 05 | E55A1 | 44530925216 | 2021-04-06 | QTR4 | 20/21 | 1 | 0 | 190 | 235 | 235 | 105.3% | 1 | 0 | 0 | 0 | 35 | 10 | 1267718 | 50000 | 1217718 | 1267718 | 1235714 | 0 | 0 | 0 | 1235714 | 1293061 | 106.2% | 1 | 57347 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 10 | 12686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 21061 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-22 | QTR4 | 21/22 |  | 2022-05-17 | QTR4 | 21/22 | 513 | 1544976.74
| 05 | E55A4 | 44113715201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 170 | 216 | 216 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 1935472 | 50000 | 1885472 | 1935472 | 1855843 | 0 | 0 | 0 | 1855843 | 1859047 | 98.6% | 1 | 3204 | 0 | 21 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-06-17 | QTR4 | 21/22 |  | 2022-03-03 | QTR3 | 21/22 | 515 | 1850000
| 05 | E55A5 | 44333315201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 110 | 222 | 221 | 114.5% | 1 | 1 | 0 | 0 | 95 | 17 | 938530 | 50000 | 888530 | 938530 | 914587 | 0 | 0 | 0 | 914587 | 914587 | 102.9% | 1 | 0 | 0 | 32 | 63 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-05-26 | QTR4 | 21/22 |  | 2022-04-11 | QTR4 | 21/22 | 514 | 1183192.28
| 05 | E55A6 | 44589515201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 80 | 101 | 99 | 97.5% | 1 | 2 | 0 | 0 | 21 | 0 | 98489 | 6182 | 92307 | 98489 | 95948 | 0 | 0 | 0 | 95948 | 95948 | 103.9% | 1 | 0 | 0 | 3 | 18 | 0 | 0 | 4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4753 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 |  | 2022-02-09 | QTR3 | 21/22 | 513 | 144831
| 05 | E56A4 | 44395715201 | 2021-07-07 | QTR1 | 21/22 | 1 | 0 | 120 | 152 | 148 | 96.67% | 1 | 4 | 0 | 0 | 32 | 0 | 3298855 | 50000 | 3248855 | 3298855 | 3246694 | 0 | 0 | 0 | 3246694 | 3246744 | 99.94% | 1 | 50 | 0 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-25 | QTR4 | 21/22 |  | 2022-02-21 | QTR3 | 21/22 | 514 | 3710950.66
| 05 | E57A3 | 41125655201 | 2021-10-05 | QTR2 | 21/22 | 1 | 2 | 44 | 60 | 59 | 97.73% | 1 | 1 | 0 | 0 | 16 | 0 | 245824 | 9890 | 235934 | 268034 | 278169 | 0 | 0 | 0 | 278169 | 278169 | 117.9% | 0 | 0 | 22210 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 12320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23430 | 12320 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2022-05-18 | QTR4 | 21/22 |  | 2022-03-30 | QTR3 | 21/22 | 512 | 349506.95
| 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 106.7% | 1 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 103.1% | 1 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7
| 05 | E5Z71 | 43179835201 | 2019-05-07 | QTR4 | 18/19 | 2 | 7 | 570 | 816 | 816 | 118.6% | 1 | 0 | 0 | 0 | 140 | 106 | 16210000 | 247420 | 15962580 | 17216871 | 17023277 | 0 | 0 | 0 | 17023277 | 16917166 | 106% | 1 | -106111 | 1006871 | 91 | 49 | 0 | 0 | 767888 | 17768 | 0 | 90 | 237203 | 30782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168783 | 0 | 0 | 16 | 14196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1188071 | 48550 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-12-16 | QTR2 | 21/22 | 512 | 17297949.45
| 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | 110% | 1 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | 101.7% | 1 | -20779 | 70000 | 38 | 56 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19
| 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 99.5% | 1 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | 99.98% | 1 | -5035 | 2982 | 41 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 |  | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55
| 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 106.5% | 1 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 107.6% | 1 | 0 | 42878 | 52 | 20 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 |  | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS
| 05 | E5Z94 | 44121115201 | 2019-03-15 | QTR3 | 18/19 | 1 | 2 | 430 | 1043 | 1042 | 187.2% | 0 | 1 | 0 | 0 | 237 | 376 | 4278000 | 54000 | 4224000 | 4328000 | 4273000 | 0 | 0 | 0 | 4273000 | 4272788 | 101.2% | 1 | -212 | 50000 | 162 | 75 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 50000 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2022-06-01 | QTR4 | 21/22 |  | 2022-03-29 | QTR3 | 21/22 | 507 | 5431910 | LBDB | LOW BID DESIGN BUILD
| 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | 105.3% | 1 | -795 | 0 | 72 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 23 | 26 | 19 | 3914 | 6150 | 6040 | 95.65% | 22 | 110 | 3 | 0 | 1641 | 595 | 56346906 | 1122449 | 55224457 | 57557471 | 57105489 | 0 | 0 | 0 | 57105489 | 57120561 | 95.65% | 22 | 18054 | 1210565 | 867 | 774 | 0 | 58 | 972943 | 17768 | 0 | 295 | 314061 | 89437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 253551 | 0 | 0 | 16 | 14560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60848 | 12320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595 | 1615962 | 119525
| District 05 Totals |  |  |  |  | 40 | 62 | 72 | 9409 | 15347 | 15081 | 82.5% | 33 | 266 | 4 | 0 | 3927 | 2011 | 206142568 | 2607070 | 203535498 | 214672716 | 215927201 | -7304 | -56908 | -64212 | 215862989 | 215192990 | 90% | 36 | -431528 | 8530146 | 2287 | 1635 | 0 | 382 | 3604233 | 39751 | 5 | 1100 | 4789560 | 103392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 590892 | 226391 | 0 | 32 | 145459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73308 | 12320 | 0 | 0 | 154210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1945 | 9357658 | 388304
| 06 | T6427 | 43063715201 | 2018-06-13 | QTR4 | 17/18 | 4 | 17 | 539 | 983 | 940 | 139.3% | 0 | 43 | 0 | 0 | 189 | 255 | 18966444 | 656288 | 18310156 | 21723570 | 21496962 | 0 | 1120000 | 1120000 | 22616962 | 21341563 | 116.6% | 0 | -1230521 | 2757126 | 135 | 54 | 0 | 56 | 1209716 | 4016 | 0 | 168 | 1324053 | 2982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147142 | 0 | 0 | 0 | 3311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 2855556 | 6998 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 |  | 2021-11-02 | QTR2 | 21/22 | 606 | 22112131.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6460 | 43081745201 | 2020-04-29 | QTR4 | 19/20 | 5 | 2 | 380 | 473 | 417 | 85.26% | 1 | 56 | 0 | 0 | 93 | 0 | 9621172 | 109381 | 9511791 | 9721667 | 9784724 | 0 | 580000 | 580000 | 10364724 | 9769960 | 102.7% | 1 | -594765 | 100495 | 78 | 15 | 0 | 0 | 19509 | 0 | 0 | 0 | 137279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160626 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-02 | QTR3 | 21/22 |  | 2021-08-26 | QTR1 | 21/22 | 613 | 9993234.21 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 78.39% | 1 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | 101.8% | 1 | -195345 | 68789 | 27 | 20 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 |  | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6469 | 42930045201 | 2019-09-25 | QTR1 | 19/20 | 2 | 4 | 350 | 410 | 330 | 77.14% | 1 | 80 | 0 | 0 | 60 | 0 | 5172452 | 51320 | 5121132 | 5372452 | 5225454 | 0 | 220000 | 220000 | 5445454 | 5222651 | 102% | 1 | -222802 | 200000 | 43 | 17 | 0 | 0 | 38506 | 0 | 0 | 0 | 32542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134496 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212915 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-06 | QTR3 | 21/22 |  | 2021-05-21 | QTR4 | 20/21 | 613 | 4540257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 99.5% | 1 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | 98.87% | 1 | -98 | 0 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 |  | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85
| 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 86.86% | 1 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | 98.61% | 1 | -113588 | 38150 | 11 | 23 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 |  | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 85.71% | 1 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 93.34% | 1 | 39 | 0 | 42 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5
| 06 | T6479 | 44028115201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 155 | 194 | 190 | 97.42% | 1 | 4 | 0 | 0 | 39 | 0 | 557557 | 32224 | 525333 | 557557 | 512065 | 0 | 0 | 0 | 512065 | 512073 | 97.48% | 1 | 8 | 0 | 25 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-06 | QTR4 | 21/22 |  | 2022-02-21 | QTR3 | 21/22 | 613 | 667193.75
| 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 103.3% | 1 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | 101.4% | 1 | -2 | 32516 | 132 | 50 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 |  | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3
| 06 | T6483 | 44016915201 | 2019-09-25 | QTR1 | 19/20 | 3 | 4 | 260 | 436 | 436 | 117.3% | 1 | 0 | 0 | 0 | 176 | 0 | 1399991 | 50000 | 1349991 | 1461545 | 1445555 | 0 | 0 | 0 | 1445555 | 1445977 | 107.1% | 1 | 421 | 61554 | 99 | 32 | 0 | 0 | 1094 | 0 | 0 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 27009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 65528 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 |  | 2021-12-17 | QTR2 | 21/22 | 613 | 1299243.3
| 06 | T6488 | 43992415201 | 2021-01-27 | QTR3 | 20/21 | 2 | 1 | 220 | 250 | 200 | 77.27% | 1 | 50 | 0 | 0 | 30 | 0 | 1453437 | 50000 | 1403437 | 1453437 | 1311324 | 0 | 120000 | 120000 | 1431324 | 1321782 | 94.18% | 1 | -109542 | 0 | 9 | 21 | 0 | 0 | 3385 | 0 | 0 | 0 | 9417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12802 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 |  | 2022-02-10 | QTR3 | 21/22 | 636 | 1645444.71 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 99.64% | 1 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | 85.44% | 1 | -106 | -50049 | 54 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 |  | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2
| 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | 98.18% | 1 | -1169 | 0 | 36 | 18 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2
| 06 | T6501 | 43998515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 0 | 160 | 201 | 201 | 103.1% | 1 | 0 | 0 | 0 | 41 | 0 | 731741 | 36002 | 695739 | 731741 | 694244 | 0 | 0 | 0 | 694244 | 696196 | 100.1% | 1 | 1952 | 0 | 25 | 11 | 0 | 0 | 12125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 18191 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-13 | QTR4 | 21/22 |  | 2021-12-13 | QTR2 | 21/22 | 636 | 743253.85
| 06 | T6502 | 44385315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 184 | 155 | 80.67% | 1 | 29 | 0 | 0 | 34 | 0 | 619555 | 32981 | 586574 | 619555 | 571295 | 0 | 0 | 0 | 571295 | 572454 | 97.59% | 1 | 1159 | 0 | 31 | 3 | 0 | 0 | 2890 | 0 | 0 | 0 | 2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5408 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-02-14 | QTR3 | 21/22 |  | 2021-12-13 | QTR2 | 21/22 | 613 | 681973.35
| 06 | T6507 | 43991815201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 239 | 269 | 229 | 83.26% | 1 | 40 | 0 | 0 | 30 | 0 | 1536743 | 50000 | 1486743 | 1536743 | 1501598 | 0 | 100000 | 100000 | 1601598 | 1507472 | 101.4% | 1 | -94126 | 0 | 17 | 13 | 0 | 0 | 7665 | 0 | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18247 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-01-13 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 636 | 1644818.7 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6524 | 42934535201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 164 | 228 | 222 | 110.4% | 1 | 6 | 0 | 0 | 64 | 0 | 759415 | 38043 | 721372 | 759415 | 708132 | 0 | 0 | 0 | 708132 | 711882 | 98.68% | 1 | 3750 | 0 | 22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 |  | 2022-04-08 | QTR4 | 21/22 | 636 | 792991.75
| 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 76.43% | 1 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 95.14% | 1 | 1 | 0 | 19 | 5 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 636 | 359443
| 06 | T6528 | 44183215201 | 2021-04-28 | QTR4 | 20/21 | 2 | 1 | 195 | 218 | 184 | 82.56% | 1 | 34 | 0 | 0 | 23 | 0 | 2045400 | 51425 | 1993975 | 2095400 | 2038295 | 0 | 130000 | 130000 | 2168295 | 2041993 | 102.4% | 1 | -126302 | 50000 | 7 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47342 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-06-02 | QTR4 | 21/22 |  | 2022-01-25 | QTR3 | 21/22 | 613 | 2162364.7 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6560 | 44576315201 | 2021-09-29 | QTR1 | 21/22 | 2 | 0 | 140 | 148 | 94 | 61.43% | 1 | 54 | 0 | 0 | 8 | 0 | 484058 | 18418 | 465640 | 484058 | 387070 | 0 | 0 | 0 | 387070 | 387070 | 83.13% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 |  | 2022-04-04 | QTR4 | 21/22 | 636 | 411401.21
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 20 | 56 | 37 | 4792 | 6397 | 5833 | 95% | 19 | 564 | 0 | 0 | 1350 | 255 | 57225612 | 1498073 | 55727539 | 60484193 | 58815287 | 0 | 2570000 | 2570000 | 61385287 | 58659376 | 95% | 19 | -2681036 | 3258581 | 842 | 402 | 8 | 56 | 1331420 | 4016 | 0 | 168 | 1586937 | 2982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 570087 | 0 | 0 | 0 | 25788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121049 | 0 | 83 | 224 | 3577395 | 6998
| 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 97.57% | 1 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 132.6% | 0 | 530 | 1114997 | 29 | 34 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57170 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 |  | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05
| 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 106.7% | 1 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 103.5% | 1 | 0 | 110603 | 110 | 22 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 |  | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689
| 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 75.3% | 1 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | 101.6% | 1 | -991000 | 1610952 | 139 | 172 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -501344 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 |  | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 06 | E6L23 | 41372125201 | 2017-01-26 | QTR3 | 16/17 | 1 | 7 | 1400 | 1609 | 1510 | 87% | 1 | 99 | 0 | 0 | 292 | -83 | 33333000 | 150000 | 33183000 | 38916929 | 42819253 | 0 | 193479 | 193479 | 43012732 | 42822072 | 129% | 0 | -190660 | 5583929 | 191 | 101 | 0 | 0 | 510456 | 0 | 0 | 0 | 4990775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83 | 0 | 0 | 0 | -83 | 5733367 | 0 | F561830811 | SAFFO CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 |  | 2021-12-22 | QTR2 | 21/22 | 606 | 34695588 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 119.2% | 1 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | 0% | 1 | -3778569 | 105786 | 32 | 57 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 |  | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 95.42% | 1 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 103.7% | 1 | 0 | 0 | 51 | 6 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25
| 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 58.73% | 1 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 30.46% | 1 | 0 | -3198332 | 6 | 25 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 |  | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 76.67% | 1 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 100.2% | 1 | 168 | 0 | 72 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 |  | 2021-09-07 | QTR1 | 21/22 | 613 | 615217
| 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 100.9% | 1 | 0 | 33224 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 |  | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5
| 06 | E6M49 | 44197415201 | 2021-02-25 | QTR3 | 20/21 | 1 | 0 | 180 | 261 | 261 | 107.8% | 1 | 0 | 0 | 0 | 81 | 0 | 1171392 | 50000 | 1121392 | 1171392 | 1126504 | 0 | 0 | 0 | 1126504 | 1137831 | 101.5% | 1 | 11327 | 0 | 46 | 21 | 0 | 0 | 2817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-06-17 | QTR4 | 21/22 |  | 2022-03-28 | QTR3 | 21/22 | 636 | 1179270.9
| 06 | E6M90 | 43029149201 | 2020-07-13 | QTR1 | 20/21 | 2 | 3 | 400 | 452 | 451 | 99.75% | 1 | 1 | 0 | 0 | 52 | 0 | 1818000 | 50000 | 1768000 | 1665532 | 1615532 | 0 | 0 | 0 | 1615532 | 1725 | 0.09757% | 1 | -1615532 | -152468 | 20 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -150743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -150743 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-12 | QTR4 | 21/22 |  | 2021-12-03 | QTR2 | 21/22 | 636 | 2364500 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6N05 | 44188615201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 180 | 351 | 292 | 67.22% | 1 | 59 | 0 | 0 | 171 | 0 | 660660 | 31668 | 628992 | 660660 | 634309 | 0 | 0 | 0 | 634309 | 634835 | 100.9% | 1 | 526 | 0 | 158 | 13 | 0 | 0 | 4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25892 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-01-28 | QTR3 | 21/22 |  | 2021-12-10 | QTR2 | 21/22 | 613 | 655036.75
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 12 | 18 | 40 | 5800 | 7211 | 6459 | 100% | 12 | 752 | 0 | 0 | 1465 | -54 | 154863632 | 857741 | 154005891 | 160072322 | 166552813 | 0 | 1513479 | 1513479 | 168066292 | 160888051 | 83.33% | 10 | -6563210 | 5208691 | 872 | 495 | 37 | 11 | -1153760 | 239375 | 0 | 0 | 5240103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 18 | 1081771 | 0 | 0 | 0 | 304279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6387 | 0 | 0 | 0 | 0 | 0 | 0 | -83 | -558514 | 0 | 68 | -54 | 4920267 | 239375
| District 06 Totals |  |  |  |  | 32 | 74 | 77 | 10592 | 13608 | 12292 | 96.88% | 31 | 1316 | 0 | 0 | 2815 | 201 | 212089244 | 2355814 | 209733430 | 220556515 | 225368100 | 0 | 4083479 | 4083479 | 229451579 | 219547427 | 90.62% | 29 | -9244246 | 8467272 | 1714 | 897 | 45 | 67 | 177660 | 243391 | 0 | 168 | 6827040 | 2982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 18 | 1651858 | 0 | 0 | 0 | 330067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189493 | 0 | 0 | 0 | 0 | 0 | 0 | -83 | -679563 | 0 | 151 | 170 | 8497662 | 246373
| 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 126% | 0 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 123.6% | 0 | 248412 | 1919528 | 100 | 56 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 |  | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000
| 07 | T7386 | 43002115201 | 2016-06-15 | QTR4 | 15/16 | 3 | 7 | 310 | 812 | 1136 | 310% | 0 | -324 | 324 | 0 | 175 | 327 | 6015645 | 88863 | 5926782 | 7425942 | 7629019 | 0 | 0 | 0 | 7629019 | 7799558 | 131.6% | 0 | 197466 | 1410297 | 132 | 43 | 0 | 318 | 1457786 | 195935 | 0 | 6 | 154100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1323906 | 195935 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 |  | 2020-01-21 | QTR3 | 19/20 | 798 | 6465450.53 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7400 | 43483915201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 150 | 167 | 540 | 348.7% | 0 | -373 | 373 | 0 | 17 | 0 | 1728055 | 50000 | 1678055 | 1440555 | 1373802 | 0 | 0 | 0 | 1373802 | 1427923 | 85.09% | 1 | 54120 | -287499 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287499 | 0 | Z31-4177100 | NATIONWIDE MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2022-05-04 | QTR4 | 21/22 |  | 2019-12-05 | QTR2 | 19/20 | 799 | 1700000 | B0 | ACC - LUMP SUM
| 07 | T7410 | 43649515201 | 2018-05-23 | QTR4 | 17/18 | 5 | 5 | 565 | 971 | 970 | 119.3% | 1 | 1 | 0 | 0 | 296 | 110 | 10099029 | 287408 | 9811621 | 12396490 | 12392490 | 0 | 0 | 0 | 12392490 | 12349457 | 125.9% | 0 | -43033 | 2297460 | 224 | 72 | 0 | 40 | 1272584 | 0 | 0 | 70 | 1132140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2418085 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 |  | 2021-06-29 | QTR4 | 20/21 | 796 | 9905226.59
| 07 | T7437 | 43605615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 2 | 268 | 298 | 285 | 95.15% | 1 | 13 | 0 | 0 | 30 | 0 | 1903823 | 50000 | 1853823 | 2069815 | 2004923 | 0 | 0 | 0 | 2004923 | 2005258 | 108.2% | 1 | 335 | 165992 | 13 | 17 | 0 | 0 | 299339 | 0 | 0 | 0 | -122480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8337 | 0 | 0 | 0 | 168522 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 |  | 2021-09-10 | QTR1 | 21/22 | 799 | 1500000
| 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | 101.1% | 1 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | 90.58% | 1 | -7946 | 0 | 46 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000
| 07 | T7450 | 43764015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 300 | 356 | 352 | 98.67% | 1 | 4 | 0 | 0 | 56 | 0 | 3698894 | 50000 | 3648894 | 3698894 | 3783529 | 0 | 0 | 0 | 3783529 | 3798642 | 104.1% | 1 | 15112 | 0 | 19 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-11 | QTR3 | 21/22 |  | 2021-10-15 | QTR2 | 21/22 | 796 | 2945400
| 07 | T7455 | 44140315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 0 | 225 | 256 | 246 | 95.56% | 1 | 10 | 0 | 0 | 31 | 0 | 9710187 | 140000 | 9570187 | 9710187 | 10168330 | 0 | 0 | 0 | 10168330 | 10201078 | 106.6% | 1 | 32748 | 0 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 |  | 2021-10-12 | QTR2 | 21/22 | 796 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 95% | 1 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 95.04% | 1 | 0 | 0 | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 |  | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400
| 07 | T7479 | 44784525201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 150 | 151 | 90 | 59.33% | 1 | 61 | 0 | 0 | 1 | 0 | 1105450 | 50000 | 1055450 | 1105450 | 1054145 | 0 | 0 | 0 | 1054145 | 1050365 | 99.52% | 1 | -3780 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 |  | 2022-05-13 | QTR4 | 21/22 | 796 | 1665700
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 10 | 21 | 28 | 2969 | 4436 | 5041 | 70% | 7 | -605 | 700 | 0 | 869 | 598 | 53502758 | 997371 | 52505387 | 59008536 | 59596202 | -7737 | 0 | -7737 | 59588465 | 60036504 | 70% | 7 | 493434 | 5505778 | 586 | 283 | 0 | 409 | 3815691 | 218372 | 0 | 186 | 2095188 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8337 | 0 | 0 | 598 | 5614446 | 601515
| 07 | E7L84 | 43227015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 10 | 365 | 1295 | 1295 | 295.6% | 0 | 0 | 0 | 0 | 294 | 636 | 13880945 | 76000 | 13804945 | 16221150 | 16265882 | 0 | 0 | 0 | 16265882 | 16265882 | 117.8% | 0 | 0 | 2340205 | 124 | 92 | 0 | 123 | 197235 | 0 | 0 | 513 | 2081549 | 186647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 39069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 636 | 2412963 | 186647 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-06-01 | QTR4 | 21/22 |  | 2021-06-30 | QTR4 | 20/21 | 799 | 7705000
| 07 | E7M61 | 43951615201 | 2019-07-10 | QTR1 | 19/20 | 2 | 0 | 430 | 707 | 698 | 97.91% | 1 | 9 | 0 | 0 | 277 | 0 | 3417860 | 50000 | 3367860 | 3417860 | 3733589 | 0 | 0 | 0 | 3733589 | 3733589 | 110.9% | 0 | 0 | 0 | 239 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-12-03 | QTR2 | 21/22 | 799 | 4777765.05
| 07 | E7M81 | 44335315201 | 2019-10-09 | QTR2 | 19/20 | 1 | 1 | 143 | 516 | 516 | 285.3% | 0 | 0 | 0 | 0 | 180 | 193 | 385385 | 7500 | 377885 | 398672 | 364686 | 0 | 0 | 0 | 364686 | 364686 | 96.51% | 1 | 0 | 13287 | 64 | 44 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-02-21 | QTR3 | 21/22 |  | 2021-11-17 | QTR2 | 21/22 | 799 | 300000
| 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 84.38% | 1 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 99.31% | 1 | 552 | 0 | 23 | 28 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 |  | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27
| 07 | E7M93 | 44383215201 | 2020-02-12 | QTR3 | 19/20 | 1 | 2 | 550 | 601 | 524 | 86% | 1 | 77 | 0 | 0 | 51 | 0 | 1260367 | 20000 | 1240367 | 1319899 | 1294928 | 0 | 0 | 0 | 1294928 | 1294928 | 104.4% | 1 | 0 | 59531 | 4 | 47 | 0 | 0 | 14038 | 0 | 0 | 0 | 5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 |  | 2022-01-11 | QTR3 | 21/22 | 796 | 1500000
| 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 101.1% | 1 | 0 | 0 | 33 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000
| 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 124.7% | 0 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | 98.85% | 1 | -57396 | 31514 | 24 | 30 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 |  | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300
| 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 72.14% | 1 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 109.2% | 1 | 0 | 49500 | 4 | 15 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 |  | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7
| 07 | E7N15 | 44539915201 | 2020-02-12 | QTR3 | 19/20 | 1 | 4 | 120 | 160 | 160 | 117.5% | 1 | 0 | 0 | 0 | 19 | 21 | 3408000 | 20000 | 3388000 | 3546613 | 3532479 | 0 | 0 | 0 | 3532479 | 3532479 | 104.3% | 1 | 0 | 138613 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 |  | 2021-06-23 | QTR4 | 20/21 | 799 | 2952724 | B0 | ACC - LUMP SUM
| 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 91.43% | 1 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 100.8% | 1 | 470 | 0 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-08-15 | QTR1 | 21/22 | 796 | 685000
| 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 90% | 1 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 100.2% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 |  | 2021-07-02 | QTR1 | 21/22 | 796 | 485498
| 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 65.14% | 1 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | 100.8% | 1 | -35622 | 0 | 62 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 |  | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64
| 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 98.24% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 796 | 127700
| 07 | E7N64 | 44146715201 | 2021-02-10 | QTR3 | 20/21 | 1 | 0 | 120 | 163 | 163 | 101.7% | 1 | 0 | 0 | 0 | 33 | 10 | 599014 | 34000 | 565014 | 599014 | 566725 | 0 | 0 | 0 | 566725 | 566725 | 100.3% | 1 | 0 | 0 | 28 | 13 | 0 | 1 | 4550 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4550 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-06-14 | QTR4 | 21/22 |  | 2022-03-15 | QTR3 | 21/22 | 796 | 758700
| 07 | E7O05 | 44149315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 23 | 38.33% | 1 | 37 | 0 | 0 | 0 | 0 | 171341 | 11819 | 159522 | 171341 | 173579 | 0 | 0 | 0 | 173579 | 173579 | 108.8% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200721481 | BAY AREA SINKHOLE INVESTIGATION & CIVIL | N/A | N/A | N/A | N/A | 2022-04-20 | QTR4 | 21/22 |  | 2022-03-16 | QTR3 | 21/22 | 796 | 250600
| 07 | E7R13 | 44111115201 | 2019-01-10 | QTR3 | 18/19 | 1 | 10 | 520 | 614 | 614 | 100% | 1 | 0 | 0 | 0 | 94 | 0 | 30854000 | 150000 | 30704000 | 31355440 | 31288898 | -20000 | 1275000 | 1255000 | 32543898 | 31200893 | 101.6% | 1 | -1343005 | 501440 | 69 | 25 | 0 | 0 | 17636 | 0 | 0 | 0 | 333715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289031 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -167178 | 0 | 0 | 0 | 520219 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2022-03-16 | QTR3 | 21/22 |  | 2020-11-09 | QTR2 | 20/21 | 714 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 109.6% | 1 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | 107.1% | 1 | -41787 | 386330 | 30 | 49 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 |  | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
| 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 106.7% | 1 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 103.7% | 1 | 1729 | 43458 | 9 | 15 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 |  | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 18 | 20 | 35 | 4011 | 6349 | 6051 | 83.33% | 15 | 298 | 0 | 0 | 1398 | 940 | 72311183 | 753555 | 71557628 | 75875063 | 75706888 | -20000 | 1275000 | 1255000 | 76961888 | 75486828 | 88.89% | 16 | -1475059 | 3563878 | 746 | 478 | 21 | 138 | 323718 | 0 | 160 | 720 | 2937345 | 186647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 10 | 337791 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95111 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -167178 | 0 | 259 | 868 | 3618800 | 203199
| District 07 Totals |  |  |  |  | 28 | 41 | 63 | 6980 | 10785 | 11092 | 78.57% | 22 | -307 | 700 | 0 | 2267 | 1538 | 125813941 | 1750926 | 124063015 | 134883599 | 135303090 | -27737 | 1275000 | 1247263 | 136550353 | 135523332 | 82.14% | 23 | -981625 | 9069656 | 1332 | 761 | 21 | 547 | 4139409 | 218372 | 160 | 906 | 5032533 | 569789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 10 | 337674 | 0 | 0 | 3 | 65178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95111 | 0 | 0 | 0 | -261143 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -175515 | 0 | 259 | 1466 | 9233246 | 804714
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 184.9% | 0 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | 98.49% | 1 | -1443556 | 402730 | 70 | 122 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -172782 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 87.8% | 1 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 105.7% | 1 | 2298953 | 4629463 | 130 | 104 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -433401 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 |  | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS
| 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 102.1% | 1 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | 102.9% | 1 | -71870 | 128744 | 80 | 36 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71
| 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 100% | 1 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | 95.54% | 1 | -25916 | -284543 | 188 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 |  | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4
| 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 75.97% | 1 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | 74.35% | 1 | -1807 | 442902 | 15 | 45 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 |  | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51
| 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 90.11% | 1 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | 101.3% | 1 | -6647 | 20210 | 13 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 |  | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25
| 08 | E8S09 | 44263125201 | 2020-03-10 | QTR3 | 19/20 | 2 | 2 | 277 | 428 | 423 | 110.8% | 1 | 5 | 0 | 0 | 116 | 35 | 2536426 | 50000 | 2486426 | 2841757 | 2675313 | 0 | 0 | 0 | 2675313 | 2675591 | 107.6% | 1 | 277 | 305331 | 90 | 26 | 0 | 0 | 0 | 0 | 0 | 35 | 318436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17340 | 0 | 0 | 0 | 17671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 318767 | 0 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-05-24 | QTR4 | 21/22 |  | 2021-10-06 | QTR2 | 21/22 | 854 | 2736391.87
| 08 | E8S11 | 44029115201 | 2020-04-14 | QTR4 | 19/20 | 3 | 3 | 286 | 425 | 425 | 100% | 1 | 0 | 0 | 0 | 139 | 0 | 12956998 | 147809 | 12809189 | 13107980 | 13212168 | -6500 | 0 | -6500 | 13205668 | 13166473 | 102.8% | 1 | -39196 | 150982 | 73 | 66 | 0 | 0 | 10213 | 0 | 0 | 0 | 213463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234161 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-02-17 | QTR3 | 21/22 |  | 2021-10-22 | QTR2 | 21/22 | 854 | 14597378.87
| 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 96.58% | 1 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | 99.91% | 1 | -41583 | 18865 | 18 | 25 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 |  | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81
| 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 95.08% | 1 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 99.77% | 1 | 0 | 1980 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 |  | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23
| 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 70.42% | 1 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 91.69% | 1 | 0 | 0 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 |  | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75
| 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 101.3% | 1 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 91.92% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 |  | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 12 | 23 | 73 | 6074 | 8436 | 7948 | #VALUE! | 11 | 488 | 0 | 0 | 1266 | 1096 | 321216972 | 1163116 | 320053859 | 327033639 | 325988774 | -67500 | 1200000 | 1132500 | 327121274 | 327206738 | 100% | 12 | 668655 | 5816664 | 736 | 530 | 0 | 10 | 2110720 | 1278827 | 0 | 40 | 508779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1901297 | 24202 | 0 | 0 | 299672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18299 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1086 | 5384831 | 1529194
| District 08 Totals |  |  |  |  | 12 | 23 | 73 | 6074 | 8436 | 7948 | 91.67% | 11 | 488 | 0 | 0 | 1266 | 1096 | 321216972 | 1163116 | 320053859 | 327033639 | 325988774 | -67500 | 1200000 | 1132500 | 327121274 | 327206738 | 100% | 12 | 668655 | 5816664 | 736 | 530 | 0 | 10 | 2110720 | 1278827 | 0 | 40 | 508779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1036 | 1901297 | 24202 | 0 | 0 | 299672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18299 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -606183 | 0 | 10 | 1086 | 5384831 | 1529194
| Statewide Central Let Contracts SubTotal |  |  |  |  | 145 | 272 | 424 | 44736 | 66674 | 65724 | 84.83% | 123 | 950 | 881 | 0 | 16754 | 5184 | 952759920 | 9700594 | 943059330 | 992931845 | 997687000 | -665155 | 2453092 | 1787937 | 999474937 | 998872711 | 91.03% | 132 | 582810 | 40171920 | 10302 | 5563 | 66 | 1696 | 18710884 | 1971137 | 307 | 1800 | 15407258 | 1023044 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 62700 | 0 | 134 | 810 | 2464481 | 413722 | 2 | 26 | 1303061 | 58352 | 0 | 0 | 0 | 0 | 0 | 41 | 1775155 | 590741 | 0 | 59 | -41035 | 89119 | 82 | 484 | 5258483 | 4954471 | 14 | 0 | 0 | 0 | 0 | -14 | -3233050 | 0 | 605 | 4902 | 41678958 | 9100589
| Statewide District Let Contracts SubTotal |  |  |  |  | 125 | 177 | 280 | 34151 | 49259 | 47109 | 85.6% | 107 | 2150 | 443 | 0 | 10706 | 4402 | 792060246 | 6733982 | 785326269 | 816358879 | 817651464 | -1099651 | 5338479 | 4238828 | 821890291 | 810144523 | 92.8% | 116 | -10365116 | 24298632 | 5940 | 3871 | 495 | 774 | 7051877 | 1859440 | 363 | 1323 | 10591431 | 414377 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 122 | 1341 | 4551509 | 24202 | 0 | 34 | 115455 | 0 | 0 | 30 | 0 | 0 | 6 | 43 | 804135 | 12320 | 0 | 84 | 2597369 | 242717 | 0 | 46 | 305459 | 0 | 0 | 21 | 0 | 0 | 0 | -89 | -1407763 | 0 | 986 | 3607 | 24470710 | 2553056
| Statewide Totals |  |  |  |  | 270 | 449 | 704 | 78887 | 115933 | 112833 | 85.19% | 230 | 3100 | 1324 | 0 | 27460 | 9586 | 1744820166 | 16434576 | 1728385599 | 1809290724 | 1815338464 | -1764806 | 7791571 | 6026765 | 1821365228 | 1809017234 | 91.85% | 248 | -9782306 | 64470552 | 16242 | 9434 | 561 | 2470 | 25762761 | 3830577 | 670 | 3123 | 25998689 | 1437421 | 0 | 0 | 0 | 0 | 0 | 0 | -167739 | 0 | 0 | 0 | 62700 | 0 | 256 | 2151 | 7015990 | 437924 | 2 | 60 | 1418516 | 58352 | 0 | 30 | 0 | 0 | 6 | 84 | 2579290 | 603061 | 0 | 143 | 2556334 | 331836 | 82 | 530 | 5563942 | 4954471 | 14 | 21 | 0 | 0 | 0 | -103 | -4640813 | 0 | 1591 | 8509 | 66149668 | 11653645

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1P48 | 43489815201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-01-16 | 881862 | 950893 | 869654 | 69030.94 | 0 | 870011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869654 | 870011 | 357 | 901555
1 | E1P95 | 42838315201 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-15 | 12611204 | 13133768 | 12450757 | 522563.69 | -160183 | 12343775 | -35183 | 0 | 0 | 0 | 0 | 0 | -35183 | 0 | 0 | 0 | 0 | -125000 | 0 | -125000 | -160183 | 12290574 | 12343775 | 53201 | 10409515 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1Q47 | 42584135201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-03-15 | 44539372 | 47408126 | 47193361 | 2868754.26 | 0 | 47170167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47193361 | 47170167 | -23194 | 59075332 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
1 | E1R56 | 43796615201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-01-16 | 2770000 | 3004222 | 2811795 | 234221.81 | 0 | 2811795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2811795 | 2811795 | 0 | 3199272
1 | E1S02 | 43942515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-09-19 | 3418691 | 3599265 | 3634779 | 180573.88 | 0 | 3581913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 3935083
1 | E1S49 | 19602275201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-03-26 | 4765372 | 5108479 | 5065730 | 343107.11 | 0 | 5081869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5065730 | 5081869 | 16140 | 5214661
1 | E1S51 | 44002715201 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2020-03-19 | 407081 | 421138 | 368049 | 14057.35 | -48399 | 319650 | -48399 | 0 | 0 | 0 | 0 | 0 | -48399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48399 | 319650 | 319650 | 0 | 439358
1 | E1S52 | 44317215201 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2021-06-10 | 460332 | 460332 | 429428 | 0 | 0 | 429528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429428 | 429528 | 100 | 486642
1 | E1S53 | 43890215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1335282 | 1434154 | 1346419 | 98871.24 | 0 | 1347016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 1282338
1 | E1S54 | 44334015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-06-11 | 2038002 | 2038002 | 1947616 | 0 | 0 | 1941883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 2189903
1 | E1T43 | 43485715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-01-21 | 1132241 | 1177226 | 1189866 | 44985 | 0 | 1189866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189866 | 1189866 | 0 | 1324428
1 | E1T46 | 44681615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-07-23 | 3083600 | 3080211 | 3030211 | -3388.51 | 0 | 3030211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3030211 | 3030211 | 0 | 4731072 | LBDB | LOW BID DESIGN BUILD
1 | E1T47 | 44624415201 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2020-07-15 | 1836500 | 1836500 | 1786500 | 0 | 0 | 1787020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 1849529 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1T68 | 43980115201 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 180572 | 210394 | 199372 | 29821.5 | -3750 | 195621 | -3750 | 0 | 0 | 0 | 0 | 0 | -3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3750 | 195621 | 195621 | 0 | 260007
1 | E1T84 | 43506615201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-12-03 | 231014 | 231014 | 219205 | 0 | 0 | 219205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219205 | 219205 | 0 | 230282 | B0 | ACC - LUMP SUM
1 | T1700 | 43088615201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-02-28 | 2262913 | 2254766 | 2207735 | -8146.86 | 0 | 2219978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | 2483173
1 | T1708 | 43656915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-13 | 4931384 | 4944272 | 4958547 | 12887.86 | -23106 | 4958136 | -23106 | 0 | 0 | 0 | 0 | 0 | -23106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23106 | 4935442 | 4958136 | 22695 | 5037241
1 | T1717 | 19801765201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-12-05 | 15860000 | 16463364 | 16135347 | 603363.88 | -150816 | 15936167 | -69816 | 0 | 0 | 0 | 0 | -21000 | -90816 | 0 | 0 | 0 | 0 | -60000 | 0 | -60000 | -150816 | 15984531 | 15936167 | -48363 | 15674641 | B10 | ACC - BONUS/INCENT/DISINCENT
1 | T1724 | 40622565201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 8657668 | 9259778 | 9382959 | 602109.73 | 0 | 9332082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9382959 | 9332082 | -50877 | 7999282
1 | T1735 | 43654715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-09-26 | 409918 | 418046 | 383683 | 8128.44 | 0 | 383683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383683 | 383683 | 0 | 267364
1 | T1747 | 43355035201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2019-08-28 | 12256766 | 12232966 | 12265846 | -23799.95 | -82722 | 12147745 | -82722 | 0 | 0 | 0 | 0 | 0 | -82722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82722 | 12183124 | 12147745 | -35379 | 11662003
1 | T1755 | 43659715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 5620384 | 5602989 | 5688348 | -17394.84 | 0 | 5695271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | 6766075
1 | T1757 | 43943615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 2163088 | 2182239 | 2172501 | 19150.59 | 0 | 2181502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172501 | 2181502 | 9002 | 2199111 | B0 | ACC - LUMP SUM
1 | T1760 | 43943915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-06-10 | 4964468 | 4976639 | 5027641 | 12170.6 | 0 | 5069314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5027641 | 5069314 | 41673 | 5089189
1 | T1764 | 44013015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 381859 | 381859 | 358474 | 0 | 0 | 358474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358474 | 358474 | 0 | 386666
1 | T1768 | 43900215201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 1847556 | 1962457 | 1921734 | 114901.14 | 0 | 1920578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 1876585
1 | T1774 | 43943315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 3486645 | 3507153 | 3516611 | 20507.58 | 0 | 3553965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3516611 | 3553965 | 37354 | 3999397
1 | T1775 | 44151915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 7746370 | 7776109 | 7775281 | 29738.5 | 0 | 7823279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7775281 | 7823279 | 47998 | 9281425
1 | T1782 | 44188915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 7817251 | 7814901 | 7885666 | -2350 | -47180 | 8007597 | -37180 | 0 | 0 | 0 | 0 | -10000 | -47180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47180 | 7838486 | 8007597 | 169112 | 9633677
1 | T1786 | 41450665201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 1630302 | 1630302 | 1465226 | 0 | 0 | 1467413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 2010635
1 | T1789 | 43693115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 2359731 | 2322360 | 2220739 | -37371.29 | 0 | 2223174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220739 | 2223174 | 2435 | 2549900
1 | T1793 | 43815115201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-01-27 | 721749 | 726881 | 731189 | 5132.49 | 0 | 731189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 731189 | 731189 | 0 | 853457
1 | T1795 | 44012415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 597800 | 597800 | 548637 | 0 | 0 | 548637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548637 | 548637 | 0 | 474794
1 | T1796 | 44050815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 817957 | 986429 | 914986 | 168472.16 | 0 | 914986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914986 | 914986 | 0 | 656746
1 | T1798 | 44013615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 779141 | 779141 | 746911 | 0 | 0 | 746933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746911 | 746933 | 23 | 689938
1 | T1802 | 44067315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-28 | 962055 | 962055 | 887528 | 0 | 0 | 887873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887528 | 887873 | 345 | 1041118
2 | E20B5 | 43054225201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-10-14 | 2358839 | 2358839 | 2268040 | 0 | 0 | 2268054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268040 | 2268054 | 14 | 1902693
2 | E20B6 | 44199825215 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-12-16 | 2043961 | 2043961 | 2079727 | 0 | 0 | 2079733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079727 | 2079733 | 6 | 2077000
2 | E20C2 | 44105115201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-16 | 539351 | 539351 | 482138 | 0 | 0 | 482138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482138 | 482138 | 0 | 678652
2 | E20C4 | 44119915201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 808267 | 808267 | 699578 | 0 | 0 | 699578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699578 | 699578 | 0 | 914588
2 | E20D9 | 44703115201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-09-02 | 394410 | 571805 | 486787 | 177395.01 | 0 | 486787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486787 | 486787 | 0 | 493957
2 | E2V69 | 21327275201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-10-18 | 16294500 | 17291837 | 17466265 | 997337.38 | 1350000 | 17461845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 350000 | 0 | 0 | 0 | 1350000 | 1350000 | 18816265 | 17461845 | -1354420 | 18122424 | B5 | ACC - INCENTIVE/DISINCENTIVE
2 | E2W84 | 43384215201 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2017-11-15 | 1444429 | 2840551 | 2999816 | 1396122.44 | 0 | 2999816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1103685
2 | E2X05 | 44030215201 | F382907623 | THE GUARANTEE COMPANY OF NORTH AMERICA U | N/A | N/A | N/A | N/A | 2017-12-13 | 3698384 | 3798384 | 3762258 | 100000 | -475059 | 3762258 | -475059 | 0 | 0 | 0 | 0 | 0 | -475059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -475059 | 3287199 | 3762258 | 475059 | 5873791 | Y | DESIGN/BUILD PROJECT
2 | E2X66 | 43727415201 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2019-10-16 | 7944015 | 8017498 | 8037111 | 73483 | 0 | 8035623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8037111 | 8035623 | -1488 | 7457548
2 | E2Y24 | 43743715201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2020-05-13 | 1280762 | 1204874 | 1079365 | -75887.97 | 0 | 1079365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | 2106516
2 | E2Y79 | 20968315201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2019-11-13 | 4028350 | 4078350 | 4286744 | 50000 | 0 | 4286650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 3704637
2 | E2Y81 | 43197915201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2019-10-16 | 2424817 | 2497783 | 2495432 | 72965.76 | 0 | 2495432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495432 | 2495432 | 0 | 3472664
2 | E2Y84 | 43807515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 1543447 | 1543447 | 1581148 | 0 | 0 | 1565351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581148 | 1565351 | -15797 | 1817083
2 | E2Y85 | 43865025201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-11-13 | 3884320 | 3884320 | 3769800 | 0 | 0 | 3768427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 4380189
2 | E2Z24 | 44199735216 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-02-19 | 1624143 | 1624143 | 1547862 | 0 | 0 | 1547862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 1701419
2 | E2Z36 | 43930315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2019-12-18 | 363396 | 445802 | 448483 | 82406.57 | 0 | 448483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448483 | 448483 | 0 | 356089
2 | E2Z39 | 43122445201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-04-15 | 788792 | 788792 | 738086 | 0 | 0 | 738086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738086 | 738086 | 0 | 1315900
2 | E2Z50 | 42848915201 | F030467673 | EXTREME SANDBLASTING & PAINTING | N/A | N/A | N/A | N/A | 2020-03-18 | 1635960 | 1685775 | 1669775 | 49815.5 | 0 | 1669775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 1762747
2 | E2Z51 | 43384115201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-15 | 2662544 | 2666491 | 1959926 | 3946.98 | 0 | 1959926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959926 | 1959926 | 0 | 3385087
2 | E2Z52 | 43204815201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-05-13 | 1206264 | 1206264 | 1198471 | 0 | 0 | 1198471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 1268308
2 | E2Z56 | 43807915201 | F204553050 | HICKS SEAL COATING & STRIPING L | N/A | N/A | N/A | N/A | 2020-05-13 | 744154 | 744154 | 696705 | 0 | 0 | 696705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696705 | 696705 | 0 | 797486
2 | T2573 | 21071125201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 39980618 | 41792741 | 42556288 | 1812123.25 | 0 | 43150258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42556288 | 43150258 | 593970 | 35388991
2 | T2579 | 21071245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-28 | 59962436 | 63341457 | 65450734 | 3379021.04 | 0 | 65787858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65450734 | 65787858 | 337124 | 62411016
2 | T2641 | 20953745201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-10-26 | 60315650 | 62391668 | 63370802 | 2076017.6 | 0 | 64652436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63370802 | 64652436 | 1281634 | 62430987
2 | T2700 | 41525015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-04-25 | 11881880 | 12125444 | 12326250 | 243563.71 | 0 | 12277546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12326250 | 12277546 | -48704 | 8810905
2 | T2701 | 20936525201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 11196736 | 11726950 | 11984103 | 530213.26 | 0 | 11975790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984103 | 11975790 | -8313 | 9764054
2 | T2712 | 43240415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-29 | 3754465 | 3806745 | 3827055 | 52279.5 | -32544 | 3793154 | -32544 | 0 | 0 | 0 | 0 | 0 | -32544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32544 | 3794511 | 3793154 | -1358 | 4106536
2 | T2720 | 43735415201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2018-10-31 | 2468956 | 2635619 | 2856937 | 166663.01 | 0 | 2843130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856937 | 2843130 | -13807 | 2333570
2 | T2743 | 42845515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 12559204 | 13123013 | 13368899 | 563808.92 | 0 | 13241202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13368899 | 13241202 | -127696 | 13121490
2 | T2744 | 43602315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 19213273 | 19486164 | 20329507 | 272891.03 | 0 | 20310464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20329507 | 20310464 | -19043 | 20412508
2 | T2751 | 21172815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 3950552 | 4195563 | 4295295 | 245011.61 | 0 | 4276296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4295295 | 4276296 | -18999 | 4829848
2 | T2752 | 43395715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 6416755 | 6416755 | 6306830 | 0 | 0 | 6314515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6306830 | 6314515 | 7685 | 6469876
2 | T2753 | 43980015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 3416497 | 3891903 | 3917050 | 475405.64 | 0 | 3897876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 3898969
2 | T2759 | 43617615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 4035736 | 4035736 | 3954853 | 0 | 0 | 3920789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 4365195
2 | T2760 | 44125815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 6493175 | 6617231 | 6291241 | 124056.15 | -142728 | 6136498 | -142728 | 0 | 0 | 0 | 0 | 0 | -142728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142728 | 6148513 | 6136498 | -12015 | 5584101
2 | T2762 | 44499015201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2020-04-29 | 1596635 | 1683719 | 1395080 | 87083.98 | 0 | 1395080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 1936705
2 | T2768 | 43948815201 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 1959598 | 1959598 | 1892736 | 0 | 0 | 1893489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 1755198
2 | T2770 | 43948915201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 601043 | 596270 | 539883 | -4773.2 | 0 | 539883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539883 | 539883 | 0 | 942548
2 | T2773 | 43403815201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-03-25 | 3684895 | 3684895 | 3598807 | 0 | 0 | 3601767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3598807 | 3601767 | 2960 | 3367569
2 | T2774 | 43578015201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2020-05-20 | 1066490 | 1066490 | 1059789 | 0 | 0 | 1060127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 1110094
2 | T2776 | 43399315201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 198978 | 198978 | 196874 | 0 | 0 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196874 | 196874 | 0 | 202254
2 | T2777 | 44126215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 3565965 | 3565965 | 3516567 | 0 | 0 | 3519561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3516567 | 3519561 | 2994 | 4228845
2 | T2778 | 44105715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-09-30 | 4660748 | 4665808 | 4696793 | 5059.38 | 0 | 4795119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4696793 | 4795119 | 98326 | 4464709
2 | T2780 | 43732515201 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2020-07-29 | 237581 | 237581 | 222711 | 0 | 0 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222711 | 222711 | 0 | 289607
2 | T2781 | 44106015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 5821573 | 5821573 | 5952158 | 0 | 0 | 5882048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952158 | 5882048 | -70110 | 7534069
2 | T2786 | 43732315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-29 | 5990960 | 5990960 | 5941443 | 0 | 0 | 5882422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 7170016
2 | T2794 | 44112915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 3087746 | 3440186 | 3518103 | 352439.68 | 0 | 3660563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518103 | 3660563 | 142461 | 3966460
2 | T2799 | 43584515201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-01-27 | 584000 | 584000 | 571789 | 0 | 0 | 571826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571789 | 571826 | 37 | 883654
2 | T2851 | 43916415201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-25 | 233424 | 233424 | 220944 | 0 | 0 | 220944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220944 | 220944 | 0 | 403784
2 | T9022 | 44531935223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 1990220 | 2080312 | 2092740 | 90091.64 | 0 | 2092740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 1872855
3 | E3Q53 | 44009615201 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2017-07-20 | 4412093 | 4461209 | 4457747 | 49116.18 | -449760 | 4007987 | -449760 | 0 | 0 | 0 | 0 | 0 | -449760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -449760 | 4007987 | 4007987 | 0 | 4688435 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
3 | E3S42 | 42187345201 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2019-09-12 | 2507433 | 2507433 | 2457433 | 0 | 0 | 2457433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 2985049
3 | E3S73 | 4453811H201 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-12-12 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174645 | 0 | -174645 | 212648
3 | E3T18 | 42282325201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2020-12-17 | 145277 | 145277 | 129137 | 0 | 0 | 129137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129137 | 129137 | 0 | 213559
3 | E3T25 | 44154615201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 2058102 | 2058102 | 2116209 | 0 | 0 | 2113685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 2347515
3 | E3T27 | 40571925201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2020-12-17 | 673158 | 673158 | 632738 | 0 | 0 | 632738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632738 | 632738 | 0 | 803648
3 | E3T35 | 44291315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-06-11 | 1454221 | 1547027 | 1426180 | 92805.8 | 25000 | 1426180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 1274994 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3T51 | 44154215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-01-14 | 1940669 | 1921236 | 1976977 | -19432.73 | 0 | 2038310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1976977 | 2038310 | 61333 | 1982216
3 | E3T58 | 43815415201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-03-12 | 883399 | 898220 | 890748 | 14820.6 | 0 | 890748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890748 | 890748 | 0 | 673070
3 | E3T66 | 4450184H201 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2020-03-12 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225968 | 0 | -225968 | 246220
3 | E3T96 | 4453581G201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-08-13 | 782169 | 1364937 | 1338192 | 582768.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 1084959
3 | E3U12 | 44365725201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-08 | 2742031 | 2742031 | 2766138 | 0 | 0 | 2770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2766138 | 2770405 | 4267 | 2471807
3 | E3U25 | 44364215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-08 | 2814688 | 2814688 | 2846250 | 0 | 0 | 2857872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846250 | 2857872 | 11622 | 4496574
3 | E3U27 | 44154515201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 1641103 | 1641103 | 1553101 | 0 | 0 | 1614039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1553101 | 1614039 | 60937 | 2039670
3 | E3U34 | 44718815201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-11-10 | 294449 | 294449 | 275309 | 0 | 0 | 275309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275309 | 275309 | 0 | 345935
3 | T3359 | 21860315201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-05-25 | 48912840 | 49557879 | 51455652 | 645039.67 | -1500 | 53084167 | 0 | 0 | 0 | 0 | 0 | -1500 | -1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | 51454152 | 53084167 | 1630015 | 41351320
3 | T3533 | 21797635201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-05-20 | 67999204 | 73183986 | 72810755 | 5184781.64 | 0 | 72663834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72810755 | 72663834 | -146921 | 77505595 | B5 | ACC - INCENTIVE/DISINCENTIVE
3 | T3632 | 43581515201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 4962076 | 5040837 | 5106121 | 78760.22 | 0 | 5104120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5106121 | 5104120 | -2001 | 4401369
3 | T3640 | 43290925201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 720412 | 720412 | 691249 | 0 | 0 | 691249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691249 | 691249 | 0 | 499997 | B0 | ACC - LUMP SUM
3 | T3646 | 22049585201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-28 | 15646589 | 15902989 | 15169686 | 256399.6 | 0 | 15198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15169686 | 15198000 | 28314 | 21200000
3 | T3660 | 40619435201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 8456503 | 8769565 | 8750489 | 313061.54 | 0 | 8742318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750489 | 8742318 | -8170 | 7797092
3 | T3682 | 43812915201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 346966 | 346966 | 335754 | 0 | 0 | 335754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335754 | 335754 | 0 | 319060
3 | T3689 | 21876425201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2019-12-04 | 3948246 | 4424349 | 4230338 | 476102.63 | 0 | 4232949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4230338 | 4232949 | 2611 | 3709289
3 | T3692 | 43774615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2019-03-27 | 8791950 | 9177543 | 9191379 | 385592.85 | 0 | 9104839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191379 | 9104839 | -86540 | 10784327
3 | T3699 | 43228415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 2694142 | 2663955 | 2668318 | -30186.8 | 0 | 2665830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | 2634440
3 | T3700 | 43811115201 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 678788 | 678788 | 592391 | 0 | 0 | 592857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592391 | 592857 | 466 | 960134
3 | T3717 | 43720215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 770613 | 797858 | 802448 | 27244.97 | 0 | 802695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802448 | 802695 | 247 | 750108
3 | T3723 | 43972115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 4514950 | 4573579 | 4689305 | 58629.33 | -24500 | 4517927 | 0 | 0 | 0 | 0 | 0 | -24500 | -24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24500 | 4664805 | 4517927 | -146878 | 5332165
3 | T3725 | 43627315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 6407925 | 6454693 | 6883968 | 46768.31 | 0 | 6913504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6883968 | 6913504 | 29535 | 7243440
3 | T3729 | 43972715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 7592042 | 7796389 | 8177990 | 204347 | 0 | 8127837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 9289556
3 | T3730 | 43972515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 13201615 | 13201615 | 14101673 | 0 | 0 | 14032884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 14987298
3 | T3738 | 44173815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2020-05-20 | 1336283 | 1373486 | 1300986 | 37202.72 | 0 | 1302036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 1328097
3 | T3744 | 43972415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 5906321 | 5906321 | 6014134 | 0 | 0 | 5961005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 5368996
3 | T3745 | 43972915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 7352550 | 7448821 | 7636800 | 96270.69 | 0 | 7674029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7636800 | 7674029 | 37229 | 8840050
3 | T3746 | 44154315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 4283738 | 4283738 | 4494319 | 0 | 0 | 4570359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 5641395
3 | T3749 | 44173215201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 755462 | 778131 | 692739 | 22669.08 | 0 | 692739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692739 | 692739 | 0 | 824731
3 | T3751 | 43775325201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 2569909 | 2569909 | 2490758 | 0 | 0 | 2498656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490758 | 2498656 | 7898 | 2572447
3 | T3760 | 44154015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 3001621 | 3001621 | 2905181 | 0 | 0 | 2997834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905181 | 2997834 | 92653 | 2841105
3 | T3763 | 43661515201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2020-06-10 | 4894168 | 4903128 | 5058997 | 8960 | 0 | 5067842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5058997 | 5067842 | 8845 | 5019528
3 | T3770 | 44134715201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-02-17 | 224915 | 224915 | 229832 | 0 | 0 | 229832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229832 | 229832 | 0 | 248071
4 | E4T51 | 43785115201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-02-01 | 6476041 | 6901248 | 6999986 | 425207.14 | 0 | 6989833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6999986 | 6989833 | -10152 | 6413384
4 | E4T80 | 43524515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2020-03-11 | 6403403 | 6403403 | 6376174 | 0 | 0 | 6376174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6376174 | 6376174 | 0 | 6290936 | A3 | ICC - DESIGN/BUILD - MINOR
4 | E4T83 | 42268145201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2020-05-01 | 2027817 | 2027817 | 1963518 | 0 | 0 | 1976822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1963518 | 1976822 | 13305 | 2656948
4 | E4U24 | 43984115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2020-03-06 | 1238848 | 1238449 | 1196529 | -399.46 | 0 | 1196625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | 1271431
4 | E4U33 | 43804215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-03 | 6709662 | 6719050 | 6438347 | 9388.64 | 0 | 6392680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6438347 | 6392680 | -45666 | 7407887
4 | E4U47 | 44147315201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-04-02 | 1068289 | 1068289 | 977728 | 0 | 0 | 977728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977728 | 977728 | 0 | 1267518
4 | E4U54 | 44330915201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2020-08-07 | 1153286 | 1168772 | 976003 | 15485.58 | 100000 | 980548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | E4U72 | 44162915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-08 | 893625 | 893625 | 846410 | 0 | 0 | 849948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846410 | 849948 | 3538 | 1052585
4 | E4U74 | 44162815201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2021-03-05 | 1190833 | 1189722 | 1098149 | -1110.99 | 0 | 1101304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098149 | 1101304 | 3155 | 1310703
4 | T4471 | 43472215201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-04-25 | 5223993 | 5569665 | 5480351 | 345672.31 | -68940 | 5405890 | -68940 | 0 | 0 | 0 | 0 | 0 | -68940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68940 | 5411411 | 5405890 | -5522 | 5507060
4 | T4476 | 43515815201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-06-13 | 7524128 | 7782657 | 7606665 | 258528.45 | 0 | 7559524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7606665 | 7559524 | -47141 | 7189790
4 | T4488 | 43630415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 552418 | 602867 | 592608 | 50448.67 | 0 | 592529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592608 | 592529 | -79 | 285675
4 | T4494 | 43630715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 5685198 | 5923341 | 5849802 | 238143.16 | 0 | 5808702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 5359259
4 | T4497 | 43783615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2019-02-27 | 7969825 | 9671721 | 9618307 | 1701895.88 | 0 | 9579829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9618307 | 9579829 | -38478 | 9083314
4 | T4504 | 43783815201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2019-05-22 | 8446061 | 9282205 | 9225023 | 836144.4 | 0 | 9088376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 9046599
4 | T4505 | 43668515201 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2019-03-27 | 7195336 | 7097482 | 6908157 | -97854.53 | 0 | 6849432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6908157 | 6849432 | -58724 | 7395888
4 | T4509 | 43177055201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2019-04-24 | 3049775 | 3212084 | 3151909 | 162309.67 | 0 | 3134194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151909 | 3134194 | -17714 | 2802936
4 | T4511 | 43469015201 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 2099355 | 2040900 | 1905910 | -58454.44 | 0 | 1888675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | 2266163
4 | T4512 | 44007715201 | Z31-0501234 | GREAT AMERICAN INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2019-04-24 | 1450367 | 1450367 | 1167077 | 0 | -139860 | 1108655 | -139860 | 0 | 0 | 0 | 0 | 0 | -139860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139860 | 1027217 | 1108655 | 81438 | 1609511
4 | T4519 | 43469715201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 4993117 | 5545786 | 5542522 | 552669.26 | 0 | 5535210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5542522 | 5535210 | -7312 | 5587128
4 | T4521 | 43760515201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 737736 | 737736 | 679527 | 0 | 0 | 679527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679527 | 679527 | 0 | 798446
4 | T4523 | 43469515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 8207877 | 8281895 | 8003190 | 74017.2 | 0 | 7894972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 8969821
4 | T4525 | 42956955201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2019-10-30 | 3469054 | 3785520 | 3699667 | 316465.53 | 0 | 3693815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3699667 | 3693815 | -5852 | 3402492
4 | T4528 | 43696715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 547645 | 547645 | 476343 | 0 | 0 | 476343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476343 | 476343 | 0 | 487570
4 | T4530 | 43592515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2019-12-04 | 4642816 | 4682420 | 4650889 | 39603.28 | 0 | 4619922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 4777019
4 | T4538 | 44138115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 589517 | 589517 | 585765 | 0 | 0 | 586015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585765 | 586015 | 250 | 492571
4 | T4542 | 43984215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2020-02-26 | 21806360 | 21667458 | 20680425 | -138901.69 | 3782 | 20647940 | 0 | 0 | 0 | 0 | 3782 | 0 | 3782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3782 | 20684206 | 20647940 | -36266 | 28727824
4 | T4543 | 43915915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 689567 | 689567 | 649805 | 0 | 0 | 650042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649805 | 650042 | 237 | 603406
4 | T4553 | 43840215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-07-29 | 432944 | 432944 | 392014 | 0 | 0 | 392107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392014 | 392107 | 93 | 514165
4 | T4555 | 43990915201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2020-09-30 | 441982 | 441982 | 407189 | 0 | 0 | 407189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407189 | 407189 | 0 | 501235
4 | T4556 | 43991015201 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 2687973 | 2705163 | 2768629 | 17190 | 0 | 2844345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2768629 | 2844345 | 75716 | 3230256
4 | T4574 | 44179515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | 622222 | 622222 | 556248 | 0 | 0 | 557421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556248 | 557421 | 1174 | 654229
5 | E50A9 | 44326415201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-03-03 | 1277250 | 1307659 | 1259799 | 30409.22 | 0 | 1259799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 1837867
5 | E52A1 | 44208715201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-10-06 | 875517 | 875517 | 860515 | 0 | 0 | 862383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860515 | 862383 | 1868 | 776685
5 | E52A2 | 44316815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 7726425 | 7711640 | 7780592 | -14785.04 | 0 | 7870977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7780592 | 7870977 | 90385 | 10078671
5 | E52A3 | 44539615201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2020-10-06 | 254016 | 254016 | 220075 | 0 | 0 | 220075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220075 | 220075 | 0 | 309304
5 | E53A6 | 44119715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-12-15 | 320193 | 320193 | 308143 | 0 | 0 | 308143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308143 | 308143 | 0 | 289415
5 | E53A7 | 44333415201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2020-12-15 | 1002182 | 1002182 | 953504 | 0 | 0 | 953504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953504 | 953504 | 0 | 1304378
5 | E53A9 | 44101715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 789395 | 789395 | 772436 | 0 | 0 | 772436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772436 | 772436 | 0 | 659076
5 | E54A0 | 44208815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 524491 | 524491 | 485346 | 0 | 0 | 485346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485346 | 485346 | 0 | 529397
5 | E54A2 | 44589615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-01-05 | 553370 | 553370 | 525670 | 0 | 0 | 525670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525670 | 525670 | 0 | 622693
5 | E54A9 | 44541215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-03-02 | 239156 | 239156 | 221370 | 0 | 0 | 221370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221370 | 221370 | 0 | 305554
5 | E55A1 | 44530925216 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-06 | 1267718 | 1267718 | 1293061 | 0 | 0 | 1293061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293061 | 1293061 | 0 | 1544977
5 | E55A4 | 44113715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-05-04 | 1935472 | 1935472 | 1855843 | 0 | 0 | 1859047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855843 | 1859047 | 3204 | 1850000
5 | E55A5 | 44333315201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-05-04 | 938530 | 938530 | 914587 | 0 | 0 | 914587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914587 | 914587 | 0 | 1183192
5 | E55A6 | 44589515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-05-04 | 98489 | 98489 | 95948 | 0 | 0 | 95948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95948 | 95948 | 0 | 144831
5 | E56A4 | 44395715201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2021-07-07 | 3298855 | 3298855 | 3246694 | 0 | 0 | 3246744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3246694 | 3246744 | 50 | 3710951
5 | E57A3 | 41125655201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-10-05 | 245824 | 268034 | 278169 | 22210 | 0 | 278169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278169 | 278169 | 0 | 349507
5 | E57A9 | 43988085201 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-02-02 | 127056 | 127056 | 123994 | 0 | 0 | 123994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123994 | 123994 | 0 | 169610
5 | E5Z71 | 43179835201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-07 | 16210000 | 17216871 | 17023277 | 1006870.83 | 0 | 16917166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17023277 | 16917166 | -106111 | 17297949
5 | E5Z86 | 43913615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2020-04-07 | 7339262 | 7409262 | 7411267 | 70000 | 0 | 7390488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 7635147
5 | E5Z88 | 43793715201 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2019-10-01 | 1872651 | 1875633 | 1830367 | 2981.59 | 0 | 1825332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830367 | 1825332 | -5035 | 1916337
5 | E5Z90 | 44326915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-07 | 3873465 | 3916343 | 4113159 | 42878.1 | 0 | 4113159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 4116925 | B1 | ACC - NO EXCUSE BONUS
5 | E5Z94 | 44121115201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-03-15 | 4278000 | 4328000 | 4273000 | 50000.02 | 0 | 4272788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4273000 | 4272788 | -212 | 5431910 | LBDB | LOW BID DESIGN BUILD
5 | E5Z96 | 44116615201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-12-03 | 1299589 | 1299589 | 1316020 | 0 | 0 | 1315225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 1579621
5 | T5538 | 23949635201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 27752000 | 28126749 | 28782547 | 374748.52 | -7304 | 29206081 | 0 | 0 | 0 | 0 | 0 | -7304 | -7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7304 | 28775243 | 29206081 | 430838 | 28403237
5 | T5582 | 23827585201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 9883550 | 9891919 | 9834478 | 8369.37 | 0 | 10163025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834478 | 10163025 | 328547 | 14381890
5 | T5628 | 43734115201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-05-22 | 16216216 | 16216212 | 16727455 | -4.3 | 0 | 16505113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16727455 | 16505113 | -222342 | 16716427
5 | T5636 | 43800315201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-10-31 | 28838467 | 29085178 | 28445436 | 246710.48 | -56908 | 27345608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56908 | -56908 | -56908 | 28388528 | 27345608 | -1042919 | 39785384
5 | T5637 | 43386015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-10-31 | 3244000 | 6497176 | 7037281 | 3253176.27 | 0 | 7021113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037281 | 7021113 | -16169 | 3081320
5 | T5645 | 43988515201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2019-04-24 | 920856 | 858040 | 792026 | -62816.79 | 0 | 792105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792026 | 792105 | 79 | 1118771
5 | T5668 | 43968235201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2019-05-22 | 20003719 | 23051817 | 24148539 | 3048098.16 | 0 | 24037958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24148539 | 24037958 | -110580 | 16312265
5 | T5669 | 43923515201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2019-10-30 | 9146375 | 9218711 | 9241919 | 72336.38 | 0 | 9193416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 7779291
5 | T5670 | 43020245201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-01-30 | 2204501 | 2284647 | 2359499 | 80145.84 | 0 | 2372974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359499 | 2372974 | 13475 | 1667431
5 | T5676 | 43913915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 3433963 | 3456872 | 3590532 | 22908.37 | 0 | 3561652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 4003251
5 | T5678 | 43913115201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 9468271 | 9554158 | 9236375 | 85887 | 0 | 9044854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 12400166
5 | T5681 | 43968215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-03-25 | 5811031 | 5814390 | 5643783 | 3359.62 | 0 | 5604250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 6194317
5 | T5683 | 44141415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 2891598 | 3078261 | 3114426 | 186662.88 | 0 | 3141296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3114426 | 3141296 | 26870 | 3095610
5 | T5685 | 44139615201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 1144140 | 1144140 | 1050473 | 0 | 0 | 1085978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 1587329
5 | T5701 | 44136515201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2020-08-26 | 1343897 | 1343897 | 1295471 | 0 | 0 | 1296320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 1376221
5 | T5710 | 44136615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 614736 | 614736 | 554534 | 0 | 0 | 554534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554534 | 554534 | 0 | 624302
5 | T5734 | 44101315201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 6878342 | 6878342 | 6971991 | 0 | 0 | 7381860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6971991 | 7381860 | 409869 | 7850497
6 | E6K72 | 43652215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-01-25 | 12962183 | 14077180 | 17042051 | 1114996.62 | 0 | 17042582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17042051 | 17042582 | 530 | 12118991
6 | E6K73 | 43653715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-25 | 4293668 | 4404270 | 4390585 | 110602.64 | 0 | 4390585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 3248689
6 | E6K77 | 42930035201 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-23 | 89490000 | 91100952 | 91019470 | 1610951.88 | 1320000 | 91348469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320000 | 0 | 0 | 0 | 0 | 0 | 1320000 | 1320000 | 92339470 | 91348469 | -991000 | 75222050 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
6 | E6L23 | 41372125201 | F561830811 | SAFFO CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-01-26 | 33333000 | 38916929 | 42819253 | 5583929.39 | 193479 | 42822072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193479 | 0 | 0 | 0 | 0 | 0 | 193479 | 193479 | 43012732 | 42822072 | -190660 | 34695588 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6L90 | 43029139201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2019-05-03 | 3703968 | 3809754 | 3778569 | 105785.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6L94 | 43653915201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2020-07-30 | 1871000 | 1871000 | 1887711 | 0 | 0 | 1887711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 2130684
6 | E6M32 | 44204015201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2020-02-05 | 4679092 | 1480760 | 1400668 | -3198331.59 | 0 | 1400668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
6 | E6M37 | 44060415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-04-30 | 589589 | 589589 | 561220 | 0 | 0 | 561388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561220 | 561388 | 168 | 615217
6 | E6M47 | 44196115201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 291080 | 324304 | 276941 | 33224 | 0 | 276941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276941 | 276941 | 0 | 335060
6 | E6M49 | 44197415201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-02-25 | 1171392 | 1171392 | 1133249 | 0 | 0 | 1137831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133249 | 1137831 | 4582 | 1179271
6 | E6M90 | 43029149201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2020-07-13 | 1818000 | 1665532 | 1615532 | -152468.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1615532 | 0 | -1615532 | 2364500 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6N05 | 44188615201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-05-28 | 660660 | 660660 | 634309 | 0 | 0 | 634835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634309 | 634835 | 526 | 655037
6 | T6427 | 43063715201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-06-13 | 18966444 | 21723570 | 21496962 | 2757125.63 | 1120000 | 21386441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 120000 | 0 | 1120000 | 1120000 | 22616962 | 21386441 | -1230521 | 22112132 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6460 | 43081745201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-04-29 | 9621172 | 9721667 | 9784724 | 100495 | 580000 | 9769960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 80000 | 0 | 580000 | 580000 | 10364724 | 9769960 | -594765 | 9993234 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6465 | 43345535201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2019-12-04 | 3445403 | 3514192 | 3479994 | 68789.07 | 170000 | 3454649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 3079920 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6469 | 42930045201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 5172452 | 5372452 | 5225454 | 200000 | 220000 | 5222651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 5445454 | 5222651 | -222802 | 4540258 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6472 | 44167015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-02-26 | 1098693 | 1098693 | 1036954 | 0 | 0 | 1036856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 1175314
6 | T6475 | 43635525201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 3771815 | 3809965 | 3652358 | 38150 | 130000 | 3668771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 4248051 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6478 | 44030415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 419419 | 419419 | 372140 | 0 | 0 | 372179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372140 | 372179 | 39 | 420618
6 | T6479 | 44028115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 557557 | 557557 | 512065 | 0 | 0 | 512073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512065 | 512073 | 8 | 667194
6 | T6482 | 44017815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-12-04 | 996753 | 1029269 | 971330 | 32516 | 0 | 971328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 971330 | 971328 | -2 | 819497
6 | T6483 | 44016915201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2019-09-25 | 1399991 | 1461545 | 1445555 | 61553.6 | 0 | 1445977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445555 | 1445977 | 421 | 1299243
6 | T6488 | 43992415201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2021-01-27 | 1453437 | 1453437 | 1319273 | 0 | 120000 | 1321782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 1439273 | 1321782 | -117492 | 1645445 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6493 | 44331415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-10-30 | 2625000 | 2574951 | 2200098 | -50049.49 | 0 | 2199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | 2833197
6 | T6498 | 43080835201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-01-29 | 1171215 | 1171215 | 1109354 | 0 | 0 | 1108186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 865294
6 | T6501 | 43998515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 731741 | 731741 | 694244 | 0 | 0 | 696196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694244 | 696196 | 1952 | 743254
6 | T6502 | 44385315201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2021-01-27 | 619555 | 619555 | 571295 | 0 | 0 | 572454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571295 | 572454 | 1159 | 681973
6 | T6507 | 43991815201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2020-07-29 | 1536743 | 1536743 | 1501598 | 0 | 100000 | 1507472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 1601598 | 1507472 | -94126 | 1644819 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6524 | 42934535201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 759415 | 759415 | 708132 | 0 | 0 | 711882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708132 | 711882 | 3750 | 792992
6 | T6526 | 44167215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 349349 | 349349 | 316341 | 0 | 0 | 316342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316341 | 316342 | 1 | 359443
6 | T6528 | 44183215201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 2045400 | 2095400 | 2038295 | 50000 | 130000 | 2041993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 30000 | 0 | 130000 | 130000 | 2168295 | 2041993 | -126302 | 2162365 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6560 | 44576315201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-09-29 | 484058 | 484058 | 387070 | 0 | 0 | 387070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387070 | 387070 | 0 | 411401
7 | E7L84 | 43227015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-06-14 | 13880945 | 16221150 | 16265882 | 2340205.2 | 0 | 16265882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16265882 | 16265882 | 0 | 7705000
7 | E7M61 | 43951615201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2019-07-10 | 3417860 | 3417860 | 3733589 | 0 | 0 | 3733589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3733589 | 3733589 | 0 | 4777765
7 | E7M81 | 44335315201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2019-10-09 | 385385 | 398672 | 364686 | 13287.38 | 0 | 364686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364686 | 364686 | 0 | 300000
7 | E7M91 | 44144125201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2020-03-11 | 1622282 | 1622282 | 1554003 | 0 | 0 | 1554555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 1262053
7 | E7M93 | 44383215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-02-12 | 1260367 | 1319899 | 1294928 | 59531.2 | 0 | 1294928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294928 | 1294928 | 0 | 1500000
7 | E7M94 | 43673415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-04-08 | 1352812 | 1352812 | 1317432 | 0 | 0 | 1317432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 1640000
7 | E7M96 | 43762615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-05-13 | 4564698 | 4596212 | 4520073 | 31514.1 | 0 | 4462676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 5061300
7 | E7N02 | 44383315201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2020-03-11 | 741228 | 790728 | 771044 | 49500 | 0 | 771044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771044 | 771044 | 0 | 741279
7 | E7N15 | 44539915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2020-02-12 | 3408000 | 3546613 | 3532479 | 138613.12 | 0 | 3532479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3532479 | 3532479 | 0 | 2952724 | B0 | ACC - LUMP SUM
7 | E7N26 | 43946015201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2020-07-08 | 873873 | 873873 | 855130 | 0 | 0 | 855600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855130 | 855600 | 470 | 685000
7 | E7N46 | 43955415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-09-09 | 357252 | 357252 | 337890 | 0 | 0 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337890 | 337890 | 0 | 485498
7 | E7N48 | 44025215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-07-08 | 3104340 | 3104340 | 3112890 | 0 | 0 | 3077268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 4202893
7 | E7N59 | 44701515201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-01-20 | 86342 | 86342 | 80991 | 0 | 0 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80991 | 80991 | 0 | 127700
7 | E7N64 | 44146715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-02-10 | 599014 | 599014 | 566725 | 0 | 0 | 566725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566725 | 566725 | 0 | 758700
7 | E7O05 | 44149315201 | F200721481 | BAY AREA SINKHOLE INVESTIGATION & CIVIL | N/A | N/A | N/A | N/A | 2021-12-08 | 171341 | 171341 | 173579 | 0 | 0 | 173579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173579 | 173579 | 0 | 250600
7 | E7R13 | 44111115201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2019-01-10 | 30854000 | 31355440 | 31288898 | 501439.84 | 1255000 | 31200893 | 0 | 0 | 0 | 0 | 0 | -20000 | -20000 | 1275000 | 0 | 0 | 0 | 0 | 0 | 1275000 | 1255000 | 32543898 | 31200893 | -1343005 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
7 | E7R17 | 44368415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-30 | 4637000 | 5023330 | 4952442 | 386330.45 | 0 | 4910655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR
7 | E7R25 | 44335815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-08-04 | 994444 | 1037903 | 984227 | 43458.19 | 0 | 985956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 922458 | A3 | ICC - DESIGN/BUILD - MINOR
7 | T7385 | 25624325201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2016-06-20 | 12584444 | 14503972 | 15099334 | 1919527.94 | 0 | 15347747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15099334 | 15347747 | 248412 | 18085000
7 | T7386 | 43002115201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-06-15 | 6015645 | 7425942 | 7629019 | 1410297.05 | 0 | 7826485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7629019 | 7826485 | 197466 | 6465451 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7400 | 43483915201 | Z31-4177100 | NATIONWIDE MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2017-12-06 | 1728055 | 1440555 | 1373802 | -287499.46 | 0 | 1427923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373802 | 1427923 | 54120 | 1700000 | B0 | ACC - LUMP SUM
7 | T7410 | 43649515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 10099029 | 12396490 | 12392490 | 2297460.32 | 0 | 12349457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12392490 | 12349457 | -43033 | 9905227
7 | T7437 | 43605615201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 1903823 | 2069815 | 2004923 | 165992 | 0 | 2005258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004923 | 2005258 | 335 | 1500000
7 | T7447 | 43764115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-03-25 | 3572269 | 3572269 | 3206137 | 0 | -7737 | 3190454 | -7737 | 0 | 0 | 0 | 0 | 0 | -7737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7737 | 3198400 | 3190454 | -7946 | 2900000
7 | T7450 | 43764015201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2020-04-29 | 3698894 | 3698894 | 3783529 | 0 | 0 | 3798642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783529 | 3798642 | 15112 | 2945400
7 | T7455 | 44140315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 9710187 | 9710187 | 10168330 | 0 | 0 | 10201078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10168330 | 10201078 | 32748 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
7 | T7466 | 43764615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2020-11-18 | 3084962 | 3084962 | 2884493 | 0 | 0 | 2884493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 2622400
7 | T7479 | 44784525201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-06-09 | 1105450 | 1105450 | 1054145 | 0 | 0 | 1050365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054145 | 1050365 | -3780 | 1665700
8 | E8N18 | 41505115201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2014-05-16 | 73888232 | 74290962 | 74217617 | 402729.5 | -51000 | 72723061 | 0 | 0 | 0 | 0 | 0 | -51000 | -51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51000 | 74166617 | 72723061 | -1443556 | 78874307 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
8 | E8Q12 | 41140615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-01 | 176976815 | 181606278 | 183899695 | 4629463.16 | 1190000 | 187388648 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 1190000 | 185089695 | 187388648 | 2298953 | 198773292 | A5 | ICC - BAM/BONUS
8 | E8Q95 | 43652015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-19 | 13519194 | 13647938 | 13835344 | 128743.5 | 0 | 13763473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 16504275
8 | E8R51 | 44132215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2019-02-12 | 17604432 | 17319890 | 16726393 | -284542.88 | 0 | 16700477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726393 | 16700477 | -25916 | 15706807
8 | E8R55 | 42815445201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2019-04-09 | 7871284 | 8314187 | 5811967 | 442902.29 | 0 | 5810160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5811967 | 5810160 | -1807 | 9545164
8 | E8S00 | 44106715201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2019-09-10 | 5292443 | 5312653 | 5319849 | 20210.25 | 0 | 5313201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 4997184
8 | E8S09 | 44263125201 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2020-03-10 | 2536426 | 2841757 | 2675313 | 305331.25 | 0 | 2675591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2675313 | 2675591 | 277 | 2736392
8 | E8S11 | 44029115201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2020-04-14 | 12956998 | 13107980 | 13212168 | 150982.48 | -6500 | 13166473 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 13205668 | 13166473 | -39196 | 14597379
8 | E8S18 | 44042315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-14 | 9095686 | 9114552 | 9001603 | 18865.24 | 0 | 8960020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 12888272
8 | E8S63 | 44514015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-12-08 | 281612 | 283592 | 264303 | 1980 | 0 | 264303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264303 | 264303 | 0 | 348350
8 | E8S68 | 44530715201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-01-12 | 842202 | 842202 | 728029 | 0 | 0 | 728029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728029 | 728029 | 0 | 1031657
8 | E8S73 | 44429215201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2020-09-15 | 351648 | 351648 | 296493 | 0 | 0 | 296493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296493 | 296493 | 0 | 613041

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 | 0 | 193913.87 |  | 43152.32 | 10404.67 | 89140.2 |  | 336611.06 |  | 165966130 | 0.1491% | 247470.86
02 | 2500 | 466463.25 |  |  | 633908.46 | 992373.09 |  | 2095244.8 |  | 338638894 | 0.3257% | 1102871.71
03 |  | 252078.73 |  |  | 4274306.29 | 231728.8 |  | 4758113.82 |  | 248725347 | 1.82% | 4526385.02
04 |  | 34439.58 | 23462.14 | 7936.6 | 342974.34 | 1463978.64 |  | 1872791.3 |  | 126227070 | 0.3239% | 408812.66
05 |  | 89411.5 |  | 230929.29 | 6449.59 | 90593.13 | -199979.96 | 217403.55 |  | 206142568 | 0.1585% | 326790.38
06 | 0 | 25074.93 |  | 12840.66 | 271558.21 | 36693.09 |  | 346166.89 |  | 212089244 | 0.1459% | 309473.8
07 |  | 188674.87 |  | 395425.93 | 11953.81 | 279126.06 |  | 875180.67 |  | 125813941 | 0.4738% | 596054.61
08 |  | 0 | 0 | 1254202.74 | 0 | 282438.22 |  | 1536640.96 |  | 321216972 | 0.3905% | 1254202.74
Grand Total | 2500 | 1250056.73 | 23462.14 | 1944487.54 | 5551555.37 | 3466071.23 | -199979.96 | 12038153.05 |  | 1744820166 | 0.5027% | 8772061.78
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 | 0 | 67 |  | 118 | 51 | 396 |  | 632 |  | 236
02 | 42 | 175 |  |  | 180 | 1528 |  | 1925 |  | 397
03 |  | 107 |  |  | 307 | 356 |  | 770 |  | 414
04 |  | 68 | 0 | 0 | 163 | 658 |  | 889 |  | 231
05 |  | 72 |  | 80 | 0 | 1859 | 0 | 2011 |  | 152
06 | 0 | 0 |  | 0 | 149 | 52 |  | 201 |  | 149
07 |  | 202 |  | 169 | 36 | 1130 |  | 1537 |  | 407
08 |  | 3 | 0 | 0 | 2 | 1091 |  | 1096 |  | 5
Grand Total | 42 | 694 | 0 | 367 | 888 | 7070 | 0 | 9061 |  | 1991
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 | 25 |  |  |  | 45 | 173 | 243 |  | 70 | 306 | 8608 | 3.555%
02 |  | 21 |  |  | 4 | 265 | 290 |  | 25 | 422 | 15770 | 2.676%
03 |  | 226 |  | 129 | 21 | 853 | 1229 |  | 376 | 790 | 10735 | 7.359%
04 |  | 6 |  |  | 18 | 322 | 346 |  | 24 | 255 | 10719 | 2.379%
05 |  | 5 |  |  |  |  | 5 |  | 5 | 157 | 9409 | 1.669%
06 | [5 empty] | 204 | 204 |  | 0 | 149 | 10592 | 1.407%
07 |  | 27 |  |  |  | 232 | 259 |  | 27 | 434 | 6980 | 6.218%
08 | [5 empty] | 90 | 90 |  | 0 | 5 | 6074 | 0.08232%
Grand Total | 25 | 285 |  | 129 | 88 | 2139 | 2666 |  | 527 | 2518 | 78887 | 3.192%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 012 | 2 |  | 1 | 019 | 22039.78 | 18162.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | E1P48 | 43489815201 | 013 | 2 |  | 1 | 106 | 41653.88 | 41653.88 | 1 |  | N | 11 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P48 | 43489815201 | 013 | 2 |  | 2 | 003 | 2927.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P48 | 43489815201 | 014 | 2 |  | 1 | 101 | 1350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P48 | 43489815201 | 014 | 2 |  | 2 | 101 | 1060 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 1 | 115 | 27988.56 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 2 | 004 | 2172.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 3 | 003 | 2400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 4 | 004 | 6872.57 | 3841.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 5 | 112 | 4568.74 | 2103.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 6 | 107 | 2087.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 7 | 004 | 8954.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 8 | 023 | 5027.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1P95 | 42838315201 | 021 | 2 | 850 | 9 | 503 | 33000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1P95 | 42838315201 | 022 | 2 |  | 1 | 106 | 32326.02 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 023 | 2 |  | 1 | 115 | 2624.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 034 | 2 |  | 1 | 118 | 32000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1P95 | 42838315201 | 039 | 2 |  | 1 | 013 | 8940.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
01 | E1P95 | 42838315201 | 039 | 2 |  | 2 | 120 | 13098.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 1 | 001 | 9836.36 | 0 | 1 |  | C | 24 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 041 | 2 |  | 2 | 106 | 5581.1 | 5581.1 | 5 |  | C | 7 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 3 | 120 | 40053.77 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
01 | E1P95 | 42838315201 | 041 | 2 |  | 4 | 010 | 18051.67 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1P95 | 42838315201 | 044 | 2 |  | 1 | 106 | 5976.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 048 | 2 |  | 1 | 103 | 11928.1 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 048 | 2 |  | 2 | 001 | 3190.98 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 3 | 015 | 7506.19 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 4 | 015 | 16528.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1P95 | 42838315201 | 048 | 2 |  | 5 | 005 | 11036.59 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P95 | 42838315201 | 050 | 2 |  | 1 | 115 | 2359.73 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 2 | 106 | 0 | 0 | 5 |  | N | 4 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 3 | 001 | 2648.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 050 | 2 |  | 4 | 128 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 5 | 106 | 3801.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 050 | 2 |  | 6 | 005 | 7793.3 | 0 | 5 |  | N | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | E1P95 | 42838315201 | 055 | 2 |  | 1 | 007 | -22909.68 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 1 | 115 | 14081.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 2 | 010 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1P95 | 42838315201 | 056 | 2 |  | 3 | 106 | 4372.35 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 4 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 5 | 924 | 0 | 0 | 0 |  | N | 81 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 6 | 128 | 1538.41 | 1538.41 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 7 | 001 | 30268.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 8 | 001 | 6722.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1P95 | 42838315201 | 056 | 2 |  | 9 | 103 | 4693.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1P95 | 42838315201 | 056 | 2 |  | 10 | 503 | 123513.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q47 | 42584135201 | 004 | 2 |  | 1 | 007 | -982399.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 006 | 2 |  | 1 | 300 | -138762.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
01 | E1Q47 | 42584135201 | 012 | 2 |  | 1 | 105 | 31099.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 012 | 2 |  | 2 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 015 | 2 |  | 1 | 105 | -387328.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 016 | 2 |  | 1 | 007 | 952605.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 023 | 2 |  | 1 | 503 | 179253.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1Q47 | 42584135201 | 028 | 2 |  | 1 | 103 | 16193 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 029 | 2 |  | 1 | 101 | 145385.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 035 | 2 |  | 1 | 923 | 91617.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 1 | 107 | 323521.84 | 46701.2 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 036 | 2 |  | 2 | 117 | 3803.38 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 037 | 2 |  | 1 | 107 | 11017.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 039 | 2 |  | 1 | 117 | -1032.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
01 | E1Q47 | 42584135201 | 042 | 2 |  | 1 | 001 | 838070.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 050 | 2 |  | 1 | 003 | 38861.27 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 057 | 2 |  | 1 | 001 | 1274886.31 | 0 | 2 |  | N | 41 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 059 | 2 |  | 1 | 700 | -577152.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
01 | E1Q47 | 42584135201 | 060 | 2 |  | 1 | 001 | 175000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 061 | 2 |  | 1 | 001 | 811721.28 | 0 | 0 |  | N | 56 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 062 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 45 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1Q47 | 42584135201 | 063 | 2 |  | 1 | 122 | 59392.02 | 40714.72 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1R56 | 43796615201 | 008 | 2 |  | 1 | 929 | 13587.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1R56 | 43796615201 | 009 | 2 |  | 1 | 012 | 116397.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R56 | 43796615201 | 010 | 2 |  | 1 | 112 | 26109.1 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R56 | 43796615201 | 011 | 2 |  | 1 | 001 | 72952.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R56 | 43796615201 | 011 | 2 |  | 2 | 101 | 5174.97 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1S02 | 43942515201 | 002 | 2 |  | 1 | 118 | 3222.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1S02 | 43942515201 | 020 | 2 |  | 1 | 001 | 183811.41 | 15127.86 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | E1S02 | 43942515201 | 022 | 2 |  | 1 | 503 | -6459.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1S49 | 19602275201 | 001 | 2 |  | 1 | 118 | 8931.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | E1S49 | 19602275201 | 002 | 2 |  | 1 | 105 | -156 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S49 | 19602275201 | 008 | 2 |  | 1 | 003 | 1172.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S49 | 19602275201 | 013 | 2 |  | 1 | 007 | 14514 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S49 | 19602275201 | 013 | 2 |  | 3 | 004 | 36904.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1S49 | 19602275201 | 017 | 2 |  | 1 | 015 | 210126.66 | 0 | 5 |  | N | 35 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S49 | 19602275201 | 023 | 2 |  | 1 | 101 | 17365 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1S49 | 19602275201 | 024 | 2 |  | 1 | 003 | 59455.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S49 | 19602275201 | 026 | 2 |  | 1 | 015 | -5205.23 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S51 | 44002715201 | 006 | 2 |  | 1 | 001 | 14057.35 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S53 | 43890215201 | 012 | 2 |  | 1 | 107 | 98871.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1T43 | 43485715201 | 003 | 2 |  | 1 | 119 | -29140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
01 | E1T43 | 43485715201 | 014 | 2 |  | 1 | 119 | 74125 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
01 | E1T46 | 44681615201 | 015 | 2 |  | 1 | 112 | -3388.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1T68 | 43980115201 | 002 | 2 |  | 1 | 001 | 29821.5 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1700 | 43088615201 | 011 | 2 |  | 1 | 001 | -8146.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1708 | 43656915201 | 015 | 2 |  | 1 | 007 | 4570.92 | 0 | 2 |  | N | 3 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
01 | T1708 | 43656915201 | 016 | 2 |  | 1 | 128 | 4777.84 | 4777.84 | 1 |  | N | 22 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1708 | 43656915201 | 018 | 2 |  | 1 | 007 | 3539.1 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1717 | 19801765201 | 005 | 2 |  | 1 | 015 | 43920 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 012 | 2 |  | 1 | 106 | 104412.54 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 2 | 107 | 23323.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 3 | 101 | 14483.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1717 | 19801765201 | 012 | 2 |  | 4 | 126 | 6024.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1717 | 19801765201 | 013 | 2 |  | 1 | 003 | 10703 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1717 | 19801765201 | 017 | 2 |  | 1 | 103 | 157356.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
01 | T1717 | 19801765201 | 020 | 2 |  | 1 | 503 | -61274.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 021 | 2 |  | 1 | 923 | 15428.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 022 | 2 |  | 1 | 101 | 86898 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1717 | 19801765201 | 022 | 2 |  | 2 | 116 | 39613.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 024 | 2 |  | 1 | 305 | 101512.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 026 | 2 |  | 1 | 015 | 83591.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 029 | 2 |  | 1 | 503 | -30081.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 031 | 2 |  | 1 | 015 | 14216.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 036 | 2 |  | 1 | 007 | 378593.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1717 | 19801765201 | 036 | 2 |  | 2 | 106 | 14652.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1717 | 19801765201 | 047 | 2 |  | 1 | 107 | -400929.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1717 | 19801765201 | 047 | 2 |  | 2 | 116 | -39613.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
01 | T1717 | 19801765201 | 048 | 2 |  | 1 | 015 | 3552 | 3552 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 048 | 2 |  | 2 | 015 | 36982.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1717 | 19801765201 | 061 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 57 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1724 | 40622565201 | 025 | 2 |  | 1 | 004 | 346058.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1724 | 40622565201 | 037 | 2 |  | 1 | 126 | 296557.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1724 | 40622565201 | 040 | 2 |  | 1 | 126 | 17288.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1724 | 40622565201 | 055 | 2 |  | 1 | 118 | 63902.06 | 63902.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1724 | 40622565201 | 056 | 2 |  | 1 | 001 | 6049.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1724 | 40622565201 | 061 | 2 |  | 1 | 004 | -84635.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1724 | 40622565201 | 062 | 2 |  | 1 | 118 | -43111.81 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1735 | 43654715201 | 006 | 2 |  | 1 | 001 | 8128.44 | 6258.44 | 2 |  | N | 0 | Avoidable, In-House Designer | Subsurface Conditions | Changed Conditions | 1
01 | T1747 | 43355035201 | 004 | 2 |  | 1 | 503 | -233898.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 009 | 2 |  | 1 | 305 | -38003 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 010 | 2 |  | 1 | 007 | 14363.22 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1747 | 43355035201 | 019 | 2 |  | 1 | 001 | 95307.09 | 14344.05 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1747 | 43355035201 | 034 | 2 |  | 1 | 015 | 104274.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1747 | 43355035201 | 035 | 2 |  | 1 | 015 | 34156.61 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1755 | 43659715201 | 012 | 2 |  | 1 | 106 | -17394.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1757 | 43943615201 | 003 | 2 |  | 1 | 503 | -25972.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1757 | 43943615201 | 004 | 2 |  | 1 | 112 | 20145.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1757 | 43943615201 | 006 | 2 |  | 1 | 112 | 71644.68 | 0 | 2 |  | N | 27 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1757 | 43943615201 | 009 | 2 |  | 1 | 503 | -46666.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1760 | 43943915201 | 009 | 2 |  | 1 | 101 | 12170.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1768 | 43900215201 | 003 | 2 |  | 1 | 007 | 20460.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 003 | 2 |  | 2 | 004 | 1938.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1768 | 43900215201 | 015 | 2 |  | 1 | 106 | 17362.43 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1768 | 43900215201 | 022 | 2 |  | 1 | 105 | 11097.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1768 | 43900215201 | 022 | 2 |  | 2 | 007 | 12766.55 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 022 | 2 |  | 3 | 007 | 30400.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
01 | T1768 | 43900215201 | 022 | 2 |  | 4 | 106 | 20875.8 | 0 | 2 |  | N | 32 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1774 | 43943315201 | 006 | 2 |  | 1 | 118 | 13481.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1774 | 43943315201 | 006 | 2 |  | 2 | 106 | 6760.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1774 | 43943315201 | 006 | 2 |  | 3 | 118 | 265.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1775 | 44151915201 | 001 | 2 |  | 1 | 101 | 21906.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1775 | 44151915201 | 004 | 2 |  | 1 | 101 | 7832 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1782 | 44188915201 | 004 | 2 |  | 1 | 101 | -4150 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1782 | 44188915201 | 005 | 2 |  | 1 | 101 | 1800 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1789 | 43693115201 | 006 | 2 |  | 1 | 305 | -37371.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1793 | 43815115201 | 001 | 2 |  | 1 | 118 | 2283 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1796 | 44050815201 | 001 | 2 |  | 1 | 101 | 87459.84 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1796 | 44050815201 | 002 | 2 |  | 1 | 007 | 81012.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E20D9 | 44703115201 | 010 | 2 |  | 1 | 105 | 64238.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20D9 | 44703115201 | 010 | 2 |  | 2 | 105 | 100336.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20D9 | 44703115201 | 010 | 2 |  | 3 | 105 | 12820.21 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 006 | 2 |  | 1 | 004 | 17097.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2V69 | 21327275201 | 014 | 2 |  | 1 | 001 | 208477.5 | 208477.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 024 | 2 |  | 1 | 503 | 6856.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 033 | 2 |  | 1 | 003 | 5110.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 036 | 2 |  | 1 | 112 | 2121.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 039 | 2 |  | 1 | 112 | 58190.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 | 041 | 2 |  | 1 | 001 | 32229.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2V69 | 21327275201 | 042 | 2 |  | 1 | 010 | 4365.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2V69 | 21327275201 | 050 | 2 |  | 1 | 105 | 28860.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 2 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 050 | 2 |  | 3 | 105 | 30240 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 | 055 | 2 | 850 | 1 | 850 | 75000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2V69 | 21327275201 | 057 | 2 |  | 1 | 503 | 480457.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2V69 | 21327275201 | 057 | 2 |  | 2 | 019 | 7980 | 7980 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 4 | 003 | 10110.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 | 057 | 2 |  | 16 | 860 | 0 | 0 | 0 |  | E | 60 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2W84 | 43384215201 | 030 | 2 |  | 1 | 860 | 1396122.44 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 2 | 007 | 1788 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 3 | 007 | 15954.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 4 | 007 | 6399.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 5 | 007 | 12086.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 6 | 007 | 5573.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 8 | 007 | 551.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 020 | 2 | 850 | 9 | 007 | 1549.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 026 | 2 | 850 | 2 | 007 | 11244.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 026 | 2 | 850 | 3 | 007 | 7728.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 | 026 | 2 | 850 | 6 | 007 | 998.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X66 | 43727415201 | 033 | 2 | 850 | 1 | 850 | 73483 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2Y24 | 43743715201 | 001 | 2 |  | 1 | 305 | -75887.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 1 | 001 | 4538.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 2 | 115 | 14410.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 | 004 | 2 | 850 | 3 | 003 | 18671.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2Y81 | 43197915201 | 036 | 2 |  | 1 | 019 | 69880.67 | 69880.67 | 0 |  | N | 50 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | E2Y81 | 43197915201 | 036 | 2 |  | 2 | 107 | 2085.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Y81 | 43197915201 | 036 | 2 |  | 3 | 107 | 1000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Z36 | 43930315201 | 010 | 2 |  | 1 | 001 | 15181.94 | 0 | 0 |  | C | 89 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Z36 | 43930315201 | 010 | 2 |  | 2 | 001 | 42943.63 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Z36 | 43930315201 | 012 | 2 |  | 1 | 012 | 24281 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2Z50 | 42848915201 | 012 | 2 | 850 | 1 | 101 | 49467.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 | 014 | 2 |  | 1 | 101 | -184.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z51 | 43384115201 | 007 | 2 |  | 1 | 107 | 3946.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 009 | 2 |  | 1 | 101 | 492951.39 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 013 | 2 |  | 1 | 101 | 30144 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 | 018 | 2 |  | 1 | 005 | 73830.92 | 73830.92 | 5 |  | N | 23 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 021 | 2 |  | 1 | 919 | 36934.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 1 | 305 | -73244.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 2 | 005 | 60730.52 | 60730.52 | 5 |  | N | 13 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 3 | 024 | 27317 | 27317 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 024 | 2 |  | 4 | 001 | 97023.25 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 1 | 107 | 10344.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 2 | 005 | 4660.02 | 4660.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2573 | 21071125201 | 036 | 2 | 850 | 3 | 107 | 2429.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 4 | 001 | 1009.96 | 1009.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 5 | 115 | 12188.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 6 | 008 | 5733.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 036 | 2 | 850 | 7 | 107 | 29247.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 8 | 010 | 12369.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 036 | 2 | 850 | 9 | 107 | 36401.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 10 | 115 | 3026.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 11 | 503 | 2818 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 12 | 923 | 1157.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 036 | 2 | 850 | 13 | 107 | 26690.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 036 | 2 | 850 | 14 | 015 | 1922.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 1 | 015 | 17510.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 2 | 015 | 1659.82 | 1659.82 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 3 | 015 | 761.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 4 | 015 | 11041.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 5 | 015 | 1087.23 | 1087.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 6 | 015 | 22572.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 7 | 015 | 15222.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 046 | 2 | 850 | 8 | 015 | 3160 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 047 | 2 |  | 1 | 015 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 051 | 2 |  | 1 | 107 | 75248.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 1 | 107 | 23122.83 | 3011.06 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 2 | 107 | 6833.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 3 | 503 | 5485.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2573 | 21071125201 | 059 | 2 | 850 | 4 | 107 | 814.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 5 | 107 | 20079.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 059 | 2 | 850 | 6 | 001 | 59132.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 7 | 004 | 956.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 059 | 2 | 850 | 8 | 004 | 33575.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 073 | 2 |  | 1 | 015 | 350144.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 1 | 004 | 9699.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 2 | 008 | 14103.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 3 | 010 | 7905 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 082 | 2 | 850 | 4 | 004 | 360.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2573 | 21071125201 | 082 | 2 | 850 | 5 | 105 | 46101.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 6 | 107 | 28452.39 | 5644.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 8 | 107 | 16582.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 082 | 2 | 850 | 9 | 107 | 7513.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 | 087 | 2 |  | 1 | 010 | 109704 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 | 093 | 2 |  | 1 | 024 | 6339.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 015 | 2 |  | 1 | 101 | 55058.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 023 | 2 |  | 1 | 001 | 1040278.96 | 0 | 1 |  | N | 111 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 1 | 015 | 2217.97 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 2 | 007 | 16362.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 3 | 106 | 441.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2579 | 21071245201 | 030 | 2 | 850 | 4 | 007 | 787.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 5 | 007 | 2265 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 6 | 007 | 4071.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 7 | 007 | 3495.07 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 8 | 007 | 4740 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 9 | 007 | 3812.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245201 | 030 | 2 | 850 | 10 | 015 | 11806.81 | 11806.81 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 1 | 012 | 3451.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 2 | 101 | 2380.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 031 | 2 | 850 | 3 | 012 | 91578.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 4 | 001 | 1604.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 5 | 012 | 47075.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 031 | 2 | 850 | 6 | 012 | 3909.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 037 | 2 |  | 1 | 919 | 119738.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 1 | 012 | 2703.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 2 | 012 | 19885.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 3 | 105 | 2805 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 4 | 115 | 31923.17 | 3873 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 5 | 012 | 39021.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 6 | 101 | 10730 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 7 | 018 | 18558.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2579 | 21071245201 | 042 | 2 | 850 | 8 | 115 | 9222.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 9 | 105 | 5610 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 10 | 105 | 2805 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 11 | 105 | 2805 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2579 | 21071245201 | 042 | 2 | 850 | 12 | 115 | 3930 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 049 | 2 |  | 1 | 117 | 149247.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
02 | T2579 | 21071245201 | 055 | 2 |  | 1 | 010 | 37042.43 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 058 | 2 |  | 1 | 015 | 231148.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 067 | 2 |  | 1 | 012 | 293674.26 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 070 | 2 |  | 1 | 503 | 5468.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2579 | 21071245201 | 074 | 2 | 850 | 1 | 115 | 15164.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 2 | 004 | 7017.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2579 | 21071245201 | 074 | 2 | 850 | 3 | 112 | 11207.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 4 | 115 | 7805.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 074 | 2 | 850 | 5 | 001 | 6829.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 074 | 2 | 850 | 6 | 010 | 101975.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 075 | 2 | 850 | 1 | 015 | 18377.75 | 18377.75 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 075 | 2 | 850 | 2 | 015 | 3063.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 094 | 2 |  | 1 | 923 | 112708.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 102 | 2 |  | 1 | 113 | 125609.51 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2579 | 21071245201 | 109 | 2 |  | 1 | 015 | 299.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 109 | 2 |  | 2 | 015 | 119832.08 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 109 | 2 |  | 3 | 015 | 14124.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 1 | 010 | 4703.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 | 117 | 2 | 850 | 2 | 003 | 9767.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 3 | 001 | 2938.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 | 117 | 2 | 850 | 4 | 101 | 544.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2579 | 21071245201 | 124 | 2 |  | 1 | 005 | 9951.39 | 9951.39 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 2 | 005 | 62482.95 | 62482.95 | 5 |  | C | 6 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 3 | 005 | 8150.56 | 8150.56 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 4 | 005 | 12925.17 | 12925.17 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 5 | 005 | 50512.75 | 50512.75 | 5 |  | C | 4 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 6 | 005 | 28570.45 | 28570.45 | 5 |  | C | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 7 | 005 | 86101.38 | 86101.38 | 5 |  | C | 6 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 8 | 005 | 10227.47 | 10227.47 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 9 | 005 | 36925.49 | 36925.49 | 5 |  | C | 3 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 124 | 2 |  | 10 | 005 | 13932.78 | 13932.78 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2579 | 21071245201 | 129 | 2 |  | 1 | 005 | 55010.17 | 55010.17 | 5 |  | C | 5 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2641 | 20953745201 | 003 | 2 |  | 1 | 101 | 7422.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 003 | 2 |  | 2 | 101 | 14852.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 015 | 2 |  | 1 | 919 | 98752.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 | 035 | 2 |  | 1 | 105 | 82701.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 | 038 | 2 |  | 1 | 503 | 24844.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2641 | 20953745201 | 040 | 2 |  | 1 | 003 | 431652.13 | 64955.38 | 0 |  | N | 82 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 1 | 923 | 56591.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 2 | 024 | 1100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 3 | 003 | 6852.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 4 | 024 | 8270.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 051 | 2 | 850 | 5 | 022 | 713.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 052 | 2 |  | 1 | 010 | 103206.76 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2641 | 20953745201 | 054 | 2 |  | 1 | 003 | 111065.72 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 059 | 2 |  | 1 | 004 | 271448.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2641 | 20953745201 | 062 | 2 |  | 1 | 003 | 141296.64 | 0 | 0 |  | N | 59 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 065 | 2 |  | 1 | 003 | 488774.79 | 0 | 0 |  | C | 73 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 | 070 | 2 | 850 | 1 | 105 | 136990.86 | 136990.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2700 | 41525015201 | 024 | 2 |  | 1 | 923 | 39169.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2700 | 41525015201 | 028 | 2 |  | 1 | 001 | 7570.83 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 2 | 015 | 10265.52 | 10265.52 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 028 | 2 |  | 3 | 012 | 38395.89 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2700 | 41525015201 | 032 | 2 |  | 1 | 004 | 39606.27 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 1 | 122 | 3256.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 2 | 001 | 6443.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 3 | 115 | 70103.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2700 | 41525015201 | 045 | 2 |  | 4 | 015 | 22002.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 045 | 2 |  | 5 | 101 | 6750.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2701 | 20936525201 | 030 | 2 |  | 1 | 101 | 44468.07 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 1 | 101 | 35883.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 2 | 001 | 11035.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 3 | 015 | 27991.84 | 27991.84 | 5 |  | N | 15 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 4 | 015 | 27991.84 | 27991.84 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 5 | 005 | 19921.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2701 | 20936525201 | 034 | 2 |  | 6 | 115 | 38601.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 7 | 001 | 70579.41 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 8 | 003 | 60847.5 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 9 | 107 | 25216.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 10 | 107 | 6114.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 11 | 107 | 14055.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 12 | 003 | 21717.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 13 | 115 | 17861.14 | 17861.14 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2701 | 20936525201 | 034 | 2 |  | 14 | 008 | 1604.07 | 1604.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 15 | 008 | 15546.91 | 15546.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | R/W Requested Change | Changed Conditions | 1
02 | T2701 | 20936525201 | 034 | 2 |  | 16 | 015 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2701 | 20936525201 | 038 | 2 |  | 1 | 003 | 48519.19 | 0 | 0 |  | N | 26 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2701 | 20936525201 | 043 | 2 | 850 | 1 | 015 | 42258.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2712 | 43240415201 | 020 | 2 |  | 1 | 005 | 12014.29 | 12014.29 | 5 |  | N | 22 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2712 | 43240415201 | 025 | 2 |  | 1 | 503 | 40265.21 | 40265.21 | 0 |  | N | 131 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2712 | 43240415201 | 032 | 2 |  | 1 | 860 | 0 | 0 | 5 |  | N | 59 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
02 | T2720 | 43735415201 | 062 | 2 |  | 1 | 106 | 29793.04 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 063 | 2 |  | 1 | 106 | 102561.17 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 064 | 2 |  | 1 | 106 | 24056.03 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 | 065 | 2 |  | 1 | 107 | 10252.77 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2743 | 42845515201 | 001 | 2 |  | 1 | 003 | 139983.91 | 0 | 0 |  | N | -30 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 1 | 305 | -125662.02 | 0 | 0 |  | N | -5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 2 | 003 | 3465 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 3 | 305 | -385909.61 | 0 | 0 |  | N | -5 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2743 | 42845515201 | 013 | 2 |  | 4 | 010 | 39780 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2743 | 42845515201 | 021 | 2 |  | 1 | 101 | 27147.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2743 | 42845515201 | 034 | 2 |  | 1 | 010 | 865004.19 | 590740.67 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2744 | 43602315201 | 016 | 2 | 850 | 1 | 015 | 10382.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2744 | 43602315201 | 023 | 2 | 850 | 1 | 005 | 17387.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43602315201 | 023 | 2 | 850 | 2 | 005 | 2038.9 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43602315201 | 023 | 2 | 850 | 3 | 005 | 6321.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43602315201 | 030 | 2 |  | 1 | 001 | 72321.11 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2744 | 43602315201 | 031 | 2 |  | 1 | 001 | 3343.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | T2744 | 43602315201 | 032 | 2 |  | 1 | 012 | 47624.12 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2744 | 43602315201 | 041 | 2 |  | 1 | 007 | 104220.48 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2751 | 21172815201 | 002 | 2 |  | 1 | 001 | 129533.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2751 | 21172815201 | 004 | 2 |  | 1 | 001 | 14076.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2751 | 21172815201 | 011 | 2 |  | 1 | 119 | 101402 | 101402 | 0 |  | N | 71 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2753 | 43980015201 | 005 | 2 |  | 1 | 001 | 425405.64 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2760 | 44125815201 | 012 | 2 |  | 1 | 001 | 124056.15 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2762 | 44499015201 | 005 | 2 |  | 1 | 128 | 26250 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2762 | 44499015201 | 010 | 2 |  | 1 | 007 | 60833.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2770 | 43948915201 | 007 | 2 |  | 1 | 007 | -4773.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2778 | 44105715201 | 003 | 2 | 850 | 2 | 106 | 5059.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2794 | 44112915201 | 005 | 2 |  | 1 | 012 | 302439.68 | 0 | 0 |  | N | 64 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2794 | 44112915201 | 009 | 2 | 850 | 1 | 850 | 22247.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T2794 | 44112915201 | 009 | 2 | 850 | 2 | 024 | 17629.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 001 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 011 | 2 |  | 1 | 101 | 40091.64 | 6445.86 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T9022 | 44531935223 | 012 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
02 | T9022 | 44531935223 | 013 | 2 | 850 | 1 | 850 | -50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 021 | 2 |  | 1 | 922 | 6861.84 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 028 | 2 |  | 1 | 922 | 11333.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 029 | 2 |  | 1 | 922 | 9658.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3Q53 | 44009615201 | 030 | 2 |  | 1 | 922 | 21263.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
03 | E3S42 | 42187345201 | 012 | 2 |  | 1 | 001 | 0 | 0 | 0 |  | N | 23 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 2 | 023 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3S42 | 42187345201 | 012 | 2 |  | 3 | 001 | 0 | 0 | 0 |  | N | 48 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3T35 | 44291315201 | 006 | 2 |  | 1 | 503 | 7383 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T35 | 44291315201 | 009 | 2 |  | 1 | 503 | 85422.8 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T51 | 44154215201 | 004 | 2 |  | 1 | 003 | -19432.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3T58 | 43815415201 | 007 | 2 |  | 1 | 503 | 14820.6 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T96 | 4453581G201 | 004 | 2 |  | 1 | 010 | 582768.6 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3359 | 21860315201 | 014 | 2 |  | 1 | 503 | 55748.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3359 | 21860315201 | 032 | 2 | 850 | 1 | 115 | 3028.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 2 | 115 | 7638.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 3 | 115 | 1737.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 4 | 115 | 1705.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 5 | 115 | 4922.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 6 | 009 | 45951.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | T3359 | 21860315201 | 032 | 2 | 850 | 7 | 115 | 41968.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 8 | 115 | 6387.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 9 | 009 | 5287.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | T3359 | 21860315201 | 032 | 2 | 850 | 10 | 115 | 3187.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 11 | 115 | 6249.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 032 | 2 | 850 | 12 | 001 | 21936.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3359 | 21860315201 | 061 | 2 |  | 1 | 919 | 40381.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3359 | 21860315201 | 068 | 2 |  | 1 | 922 | 98909.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3359 | 21860315201 | 075 | 2 | 850 | 1 | 001 | 99822.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3359 | 21860315201 | 075 | 2 | 850 | 2 | 115 | 3274.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 075 | 2 | 850 | 3 | 115 | 23250.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 075 | 2 | 850 | 4 | 115 | 1782 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 075 | 2 | 850 | 5 | 115 | 1693.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 075 | 2 | 850 | 6 | 004 | 13526.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3359 | 21860315201 | 075 | 2 | 850 | 7 | 004 | 6650.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3359 | 21860315201 | 088 | 2 | 850 | 1 | 004 | 3062.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3359 | 21860315201 | 088 | 2 | 850 | 2 | 115 | 21213.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 | 088 | 2 | 850 | 3 | 101 | 1925 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3359 | 21860315201 | 088 | 2 | 850 | 4 | 003 | 4117.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3359 | 21860315201 | 088 | 2 | 850 | 5 | 012 | 1870 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3359 | 21860315201 | 088 | 2 | 850 | 6 | 115 | 17839.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 | 004 | 2 |  | 1 | 305 | -2179586.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 | 029 | 2 |  | 1 | 120 | 60423.76 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | T3533 | 21797635201 | 031 | 2 |  | 1 | 120 | 77030.36 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
03 | T3533 | 21797635201 | 032 | 2 |  | 1 | 115 | 87801.91 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 | 038 | 2 |  | 1 | 919 | 67851.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 | 041 | 2 |  | 1 | 005 | 476432.09 | 476432.09 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | T3533 | 21797635201 | 044 | 2 |  | 1 | 503 | 497193.58 | 0 | 1 |  | N | 60 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 048 | 2 |  | 1 | 106 | 116026 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3533 | 21797635201 | 051 | 2 |  | 1 | 503 | 47538.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 054 | 2 |  | 1 | 503 | -23642.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 055 | 2 |  | 1 | 503 | 15811 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 1 | 350 | 81.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 3 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 4 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 5 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 6 | 503 | 8622.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 7 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 8 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 9 | 024 | 5504.5 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 10 | 503 | 5205.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 11 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 12 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 14 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 | 067 | 2 | 850 | 16 | 503 | 10589.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 17 | 503 | 3183 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 18 | 503 | 3015.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 19 | 024 | 5395.06 | 5395.06 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 067 | 2 | 850 | 20 | 503 | 3900.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 073 | 2 |  | 1 | 700 | 702412.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3533 | 21797635201 | 074 | 2 |  | 1 | 922 | 91786.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3533 | 21797635201 | 076 | 2 |  | 1 | 005 | 3761357.23 | 3761357.23 | 5 |  | C | 278 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | T3533 | 21797635201 | 082 | 2 |  | 1 | 010 | 355429.11 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3533 | 21797635201 | 084 | 2 |  | 1 | 503 | 253295.58 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 091 | 2 |  | 1 | 305 | -34695.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 096 | 2 |  | 1 | 503 | 96218.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 099 | 2 |  | 1 | 503 | 10159.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 101 | 2 |  | 1 | 503 | 5445 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 104 | 2 |  | 1 | 113 | 187147.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3533 | 21797635201 | 105 | 2 |  | 1 | 503 | 26712.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 108 | 2 |  | 1 | 503 | 11233.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 111 | 2 |  | 1 | 503 | 1156 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 115 | 2 |  | 1 | 503 | 17054 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 119 | 2 |  | 1 | 118 | 34940.23 | 34940.23 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3533 | 21797635201 | 122 | 2 |  | 1 | 503 | 182746.71 | 134896.71 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 124 | 2 |  | 1 | 503 | 1730 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 125 | 2 |  | 1 | 503 | 29587.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 127 | 2 |  | 1 | 503 | 37862.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 | 130 | 2 |  | 1 | 503 | 20322.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3632 | 43581515201 | 013 | 2 |  | 1 | 503 | 3680 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3632 | 43581515201 | 020 | 2 |  | 1 | 503 | -3755 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3632 | 43581515201 | 026 | 2 |  | 1 | 503 | 6348.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3632 | 43581515201 | 031 | 2 |  | 1 | 001 | 72486.42 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3646 | 22049585201 | 002 | 2 |  | 1 | 004 | 28644 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3646 | 22049585201 | 004 | 2 |  | 1 | 105 | 15970.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3646 | 22049585201 | 008 | 2 |  | 1 | 101 | 7260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3646 | 22049585201 | 016 | 2 |  | 1 | 922 | 55072.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3646 | 22049585201 | 027 | 2 |  | 1 | 112 | 149452.21 | 73650.34 | 1 |  | N | 25 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3660 | 40619435201 | 008 | 2 |  | 1 | 101 | 1998.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3660 | 40619435201 | 034 | 2 |  | 1 | 009 | -3800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
03 | T3660 | 40619435201 | 040 | 2 |  | 1 | 001 | 109857.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3660 | 40619435201 | 054 | 2 |  | 1 | 001 | 24146.73 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3660 | 40619435201 | 062 | 2 |  | 1 | 001 | 180859.49 | 180859.49 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3689 | 21876425201 | 011 | 2 |  | 1 | 103 | 182665.96 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 015 | 2 |  | 1 | 103 | 75030 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 023 | 2 |  | 1 | 103 | 81936 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 031 | 2 |  | 1 | 103 | 140395.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
03 | T3689 | 21876425201 | 034 | 2 |  | 1 | 107 | -3924.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 003 | 2 |  | 1 | 105 | -33822.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 004 | 2 |  | 1 | 105 | -2247.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 011 | 2 |  | 1 | 101 | 310.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3692 | 43774615201 | 014 | 2 |  | 1 | 003 | 31379.15 | 0 | 1 |  | E | 1 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3692 | 43774615201 | 015 | 2 |  | 1 | 115 | 10200.5 | 12735.38 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 016 | 2 |  | 1 | 105 | 33837.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 019 | 2 |  | 1 | 105 | 34180.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 021 | 2 | 850 | 1 | 010 | 2521.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 | 021 | 2 | 850 | 2 | 003 | 19016.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3692 | 43774615201 | 021 | 2 | 850 | 3 | 010 | 1431.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 | 021 | 2 | 850 | 4 | 115 | 3661.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3692 | 43774615201 | 022 | 2 |  | 1 | 105 | -22782.91 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 023 | 2 |  | 1 | 105 | 65206.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 031 | 2 |  | 1 | 503 | 211388.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3692 | 43774615201 | 037 | 2 |  | 1 | 105 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 042 | 2 |  | 1 | 105 | 3824.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 | 053 | 2 |  | 1 | 118 | 5720 | 3899.36 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3692 | 43774615201 | 055 | 2 |  | 1 | 927 | 12033.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
03 | T3699 | 43228415201 | 025 | 2 |  | 1 | 003 | -30186.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3717 | 43720215201 | 007 | 2 |  | 1 | 001 | 27244.97 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3723 | 43972115201 | 012 | 2 |  | 1 | 010 | 58629.33 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3725 | 43627315201 | 010 | 2 |  | 1 | 108 | 15646.4 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
03 | T3725 | 43627315201 | 019 | 2 |  | 1 | 106 | 31121.91 | 31121.91 | 5 |  | N | 29 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3729 | 43972715201 | 020 | 2 |  | 1 | 700 | 204347 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3738 | 44173815201 | 012 | 2 |  | 1 | 503 | 483.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3738 | 44173815201 | 016 | 2 |  | 1 | 101 | 34377.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3738 | 44173815201 | 017 | 2 |  | 1 | 503 | 2342.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 | 006 | 2 |  | 1 | 503 | 9174.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 | 020 | 2 |  | 1 | 001 | 29854.35 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3745 | 43972915201 | 028 | 2 |  | 1 | 001 | 57241.58 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3749 | 44173215201 | 014 | 2 |  | 1 | 503 | 22669.08 | 12169.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3763 | 43661515201 | 009 | 2 |  | 1 | 101 | 8960 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4T51 | 43785115201 | 019 | 2 |  | 1 | 005 | 280242.09 | 0 | 5 |  | C | 41 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T51 | 43785115201 | 020 | 2 |  | 1 | 920 | 23230 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T51 | 43785115201 | 036 | 2 |  | 1 | 926 | 7837.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T51 | 43785115201 | 043 | 2 |  | 1 | 928 | 8156.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T51 | 43785115201 | 044 | 2 |  | 1 | 001 | 107978.34 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T51 | 43785115201 | 045 | 2 |  | 1 | 007 | -5328 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T51 | 43785115201 | 054 | 2 |  | 1 | 019 | 3090 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | E4U24 | 43984115201 | 002 | 2 |  | 1 | 007 | -10792.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U24 | 43984115201 | 002 | 2 |  | 2 | 503 | 1766.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 | 002 | 2 |  | 3 | 004 | 8626.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U33 | 43804215201 | 012 | 2 |  | 1 | 926 | 9388.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U33 | 43804215201 | 064 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | C | 16 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U54 | 44330915201 | 003 | 2 |  | 1 | 105 | 15485.58 | 0 | 1 |  | N | 14 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4U74 | 44162815201 | 005 | 2 |  | 1 | 007 | -1110.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 007 | 2 |  | 1 | 305 | -33901.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 009 | 2 |  | 1 | 305 | -12727.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 022 | 2 |  | 1 | 106 | 24234.44 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 022 | 2 |  | 2 | 005 | 74911.83 | 74911.83 | 5 |  | N | 42 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 029 | 2 |  | 1 | 923 | 15618.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 031 | 2 | 850 | 1 | 118 | 3043.27 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4471 | 43472215201 | 031 | 2 | 850 | 2 | 503 | 4841.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 031 | 2 | 850 | 3 | 926 | 2264.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 038 | 2 |  | 1 | 101 | 4510 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 038 | 2 |  | 2 | 503 | -4560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 040 | 2 |  | 1 | 106 | 30458.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 1 | 106 | 3312.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 2 | 503 | 41959.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4471 | 43472215201 | 041 | 2 |  | 3 | 101 | 8500 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 041 | 2 |  | 4 | 004 | 20679.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4471 | 43472215201 | 042 | 2 |  | 1 | 106 | 6112.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 | 045 | 2 |  | 1 | 001 | 7296.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 | 050 | 2 |  | 1 | 007 | -60.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 056 | 2 |  | 1 | 023 | 4749.8 | 4749.8 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 058 | 2 |  | 1 | 007 | 8142.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4471 | 43472215201 | 061 | 2 |  | 1 | 101 | 4496.59 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 061 | 2 |  | 2 | 003 | 737.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 1 | 003 | 3472.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 2 | 023 | 20562.49 | 20562.49 | 5 |  | N | 6 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 3 | 024 | 327.91 | 327.91 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4471 | 43472215201 | 062 | 2 |  | 4 | 101 | 7992.15 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4471 | 43472215201 | 062 | 2 |  | 5 | 105 | 10544.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4471 | 43472215201 | 062 | 2 |  | 6 | 860 | 48303.09 | 48303.09 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 7 | 924 | 0 | 0 | 0 |  | N | 34 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 8 | 924 | 0 | 0 | 0 |  | N | 81 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4471 | 43472215201 | 062 | 2 |  | 9 | 106 | 0 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4476 | 43515815201 | 029 | 2 |  | 1 | 923 | 12568.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4476 | 43515815201 | 038 | 2 |  | 1 | 005 | 100872.64 | 100872.64 | 5 |  | N | 60 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4476 | 43515815201 | 038 | 2 |  | 2 | 005 | 7114.93 | 7114.93 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4476 | 43515815201 | 038 | 2 |  | 3 | 001 | 6776.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815201 | 038 | 2 |  | 4 | 105 | 58474.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4476 | 43515815201 | 038 | 2 |  | 5 | 118 | 3010.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815201 | 048 | 2 |  | 1 | 115 | -4670 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4476 | 43515815201 | 059 | 2 |  | 1 | 105 | 40014.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4476 | 43515815201 | 059 | 2 |  | 2 | 860 | 34366.05 | 34366.05 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4488 | 43630415201 | 017 | 2 |  | 1 | 860 | 28229.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4488 | 43630415201 | 017 | 2 |  | 2 | 118 | 22219.44 | 22219.44 | 4 |  | N | 0 | Avoidable, In-House CEI | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4494 | 43630715201 | 004 | 2 |  | 1 | 101 | 17582.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4494 | 43630715201 | 012 | 2 |  | 1 | 005 | 7756.24 | 7756.24 | 5 |  | C | 14 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4494 | 43630715201 | 020 | 2 |  | 1 | 001 | 56846.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4494 | 43630715201 | 031 | 2 |  | 1 | 106 | 78304.94 | 78304.94 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 1 | 106 | 8994.35 | 8994.35 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 2 | 105 | 3102.2 | 3102.2 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4494 | 43630715201 | 038 | 2 |  | 3 | 106 | 9557.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 1 | 108 | 33739.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 010 | 2 |  | 2 | 007 | 4838.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4497 | 43783615201 | 010 | 2 |  | 3 | 108 | 59290 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 020 | 2 |  | 1 | 923 | 11340.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 | 027 | 2 |  | 1 | 004 | 143232.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 | 029 | 2 |  | 1 | 126 | 114822 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
04 | T4497 | 43783615201 | 033 | 2 |  | 1 | 101 | -4821.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4497 | 43783615201 | 041 | 2 |  | 1 | 001 | 656775.31 | 656775.31 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 043 | 2 |  | 1 | 001 | 42114.46 | 42114.46 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 046 | 2 |  | 1 | 001 | 427380.56 | 427380.56 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 047 | 2 |  | 1 | 001 | 23184.23 | 23184.23 | 0 |  | C | 35 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 | 052 | 2 |  | 1 | 001 | 190000 | 190000 | 0 |  | C | 16 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 007 | 2 |  | 1 | 101 | 48087.98 | 0 | 1 |  | N | 25 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4504 | 43783815201 | 014 | 2 |  | 1 | 113 | 127922.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4504 | 43783815201 | 025 | 2 |  | 1 | 001 | 781896 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4504 | 43783815201 | 025 | 2 |  | 2 | 503 | -121762.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 009 | 2 |  | 1 | 305 | -99541.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4505 | 43668515201 | 028 | 2 |  | 1 | 926 | 1686.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 014 | 2 |  | 1 | 923 | 10823.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4509 | 43177055201 | 029 | 2 |  | 1 | 105 | 82698 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4509 | 43177055201 | 034 | 2 |  | 1 | 113 | 68788 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4511 | 43469015201 | 021 | 2 |  | 1 | 106 | -58454.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4512 | 44007715201 | 027 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | C | 311 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4519 | 43469715201 | 016 | 2 |  | 1 | 923 | 5096.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4519 | 43469715201 | 048 | 2 |  | 1 | 126 | 31872 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4519 | 43469715201 | 048 | 2 |  | 2 | 007 | -4496.72 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4519 | 43469715201 | 048 | 2 |  | 3 | 113 | 163558.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4519 | 43469715201 | 048 | 2 |  | 4 | 126 | 356319.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4519 | 43469715201 | 048 | 2 |  | 5 | 101 | 319.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4523 | 43469515201 | 009 | 2 |  | 1 | 300 | -28976.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Value Engineering Change Proposal | Value Engineering | 4
04 | T4523 | 43469515201 | 022 | 2 |  | 1 | 503 | 62365.81 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 | 028 | 2 |  | 1 | 503 | 40627.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4525 | 42956955201 | 008 | 2 |  | 1 | 106 | 24300.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4525 | 42956955201 | 012 | 2 |  | 1 | 123 | 63137.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 | 034 | 2 |  | 1 | 113 | 90800.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
04 | T4525 | 42956955201 | 034 | 2 |  | 2 | 118 | 8365.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4525 | 42956955201 | 035 | 2 |  | 1 | 126 | 30543.38 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4525 | 42956955201 | 037 | 2 | 850 | 1 | 123 | 2664.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 | 037 | 2 | 850 | 2 | 123 | 10936.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 | 048 | 2 |  | 1 | 503 | 49587.75 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4530 | 43592515201 | 013 | 2 |  | 1 | 004 | 8037.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4530 | 43592515201 | 032 | 2 |  | 1 | 118 | 31565.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4542 | 43984215201 | 009 | 2 |  | 1 | 926 | 13367.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4542 | 43984215201 | 017 | 2 |  | 1 | 126 | 221401.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
04 | T4542 | 43984215201 | 017 | 2 |  | 2 | 012 | 61243.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4542 | 43984215201 | 017 | 2 |  | 3 | 004 | -250378.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4542 | 43984215201 | 018 | 2 |  | 1 | 305 | -184534.64 | 0 | 0 |  | N | -4 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4556 | 43991015201 | 009 | 2 | 850 | 1 | 118 | 10089.81 | 10089.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E50A9 | 44326415201 | 002 | 2 |  | 1 | 012 | 90009.22 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E50A9 | 44326415201 | 002 | 2 |  | 2 | 126 | -59600 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | E52A2 | 44316815201 | 015 | 2 |  | 1 | 003 | -17404.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E52A2 | 44316815201 | 015 | 2 |  | 2 | 118 | 2619 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E57A3 | 41125655201 | 004 | 2 | 850 | 1 | 106 | 7812.98 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E57A3 | 41125655201 | 004 | 2 | 850 | 2 | 105 | 1036.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E57A3 | 41125655201 | 004 | 2 | 850 | 3 | 105 | 1040.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E57A3 | 41125655201 | 005 | 2 |  | 1 | 010 | 12320 | 12320 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | E5Z71 | 43179835201 | 005 | 2 |  | 1 | 004 | 10000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 1 | 115 | 1981.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 2 | 115 | 5465.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 3 | 115 | 12624.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 4 | 115 | 8223.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 5 | 115 | 7352.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 6 | 115 | 2720.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 7 | 115 | 2429.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 8 | 115 | 10943.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 9 | 001 | 9367.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 10 | 001 | 21857.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 11 | 101 | 3692.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 12 | 115 | 11105.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 13 | 001 | 18373.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 14 | 115 | 3396.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 15 | 122 | 3306.18 | 3024.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 16 | 105 | 165 | 165 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 17 | 001 | 13197.99 | 7993.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 006 | 2 | 850 | 18 | 106 | 13796.45 | 13796.45 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z71 | 43179835201 | 026 | 2 |  | 1 | 503 | 168782.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E5Z71 | 43179835201 | 029 | 2 |  | 1 | 015 | 91114.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 030 | 2 |  | 1 | 001 | 512140.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 036 | 2 |  | 1 | 001 | 24832.59 | 9774.08 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 040 | 2 | 850 | 1 | 001 | 21772.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z71 | 43179835201 | 040 | 2 | 850 | 2 | 024 | 14196.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z86 | 43913615201 | 015 | 2 | 850 | 1 | 105 | 58655.11 | 58655.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z86 | 43913615201 | 015 | 2 | 850 | 2 | 024 | 364.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z88 | 43793715201 | 011 | 2 |  | 1 | 926 | 2981.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z90 | 44326915201 | 016 | 2 |  | 1 | 012 | 42878.1 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z94 | 44121115201 | 023 | 2 |  | 1 | 130 | 0 | 0 | 0 |  | N | 150 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
05 | E5Z94 | 44121115201 | 031 | 2 |  | 1 | 503 | 50000.02 | 0 | 0 |  | N | 226 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5538 | 23949635201 | 020 | 2 |  | 1 | 105 | 3577.8 | 893.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 | 033 | 2 |  | 1 | 118 | 28062.05 | 5406 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 043 | 2 |  | 1 | 923 | 36110.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 | 046 | 2 |  | 1 | 007 | 111063.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5538 | 23949635201 | 052 | 2 |  | 1 | 860 | 6449.59 | 6449.59 | 5 |  | C | 0 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
05 | T5538 | 23949635201 | 059 | 2 |  | 1 | 112 | 58725.69 | 0 | 1 |  | N | 10 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 083 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 66 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 | 101 | 2 |  | 1 | 860 | 130760.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 001 | 2 |  | 1 | 919 | 6918.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 037 | 2 |  | 1 | 923 | 1536.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5582 | 23827585201 | 038 | 2 |  | 1 | 105 | 103979.5 | 0 | 0 |  | N | 142 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 2 | 107 | 6025.5 | 0 | 0 |  | N | 143 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 3 | 105 | -202363.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 4 | 503 | -3834 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5582 | 23827585201 | 038 | 2 |  | 5 | 101 | 33771.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 6 | 105 | -1936 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5582 | 23827585201 | 038 | 2 |  | 7 | 503 | 64272 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5628 | 43734115201 | 027 | 2 |  | 1 | 003 | -4.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5636 | 43800315201 | 011 | 2 |  | 1 | 126 | -91620.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
05 | T5636 | 43800315201 | 012 | 2 |  | 1 | 923 | 177151.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
05 | T5636 | 43800315201 | 050 | 2 |  | 1 | 101 | 27681.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5636 | 43800315201 | 062 | 2 |  | 1 | 113 | 67766.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5636 | 43800315201 | 062 | 2 |  | 2 | 012 | 12550.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5636 | 43800315201 | 062 | 2 |  | 3 | 024 | 28327.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5636 | 43800315201 | 062 | 2 |  | 4 | 503 | 24852 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5637 | 43386015201 | 002 | 2 |  | 1 | 107 | 400900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 008 | 2 |  | 1 | 107 | 50537.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 013 | 2 |  | 1 | 107 | 2706273 | 0 | 0 |  | N | 390 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 014 | 2 |  | 1 | 107 | 74935.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 018 | 2 |  | 1 | 923 | 3530.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 | 052 | 2 |  | 1 | 860 | 17000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
05 | T5645 | 43988515201 | 004 | 2 |  | 1 | 007 | -30335.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5645 | 43988515201 | 019 | 2 |  | 1 | 503 | -32481.06 | 0 | 0 |  | N | 145 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 001 | 2 |  | 1 | 003 | 168079.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 012 | 2 |  | 1 | 003 | 21942.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 012 | 2 |  | 2 | 106 | 594995.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 026 | 2 |  | 1 | 003 | 5260.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 2 | 106 | 90177.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 026 | 2 |  | 3 | 003 | 36294.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 4 | 003 | 784264.06 | 0 | 0 |  | N | 135 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 026 | 2 |  | 5 | 001 | 184228.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 029 | 2 |  | 1 | 106 | 44097.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968235201 | 031 | 2 |  | 1 | 003 | 331170.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 1 | 023 | 170.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 2 | 101 | 13398 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 3 | 003 | 24061.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 4 | 001 | 8861.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 5 | 101 | 6641.63 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 6 | 003 | 3570.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 032 | 2 | 850 | 7 | 101 | 3520 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 8 | 101 | 4900.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 9 | 023 | 18993.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 032 | 2 | 850 | 10 | 024 | 779 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 042 | 2 |  | 1 | 001 | 327471.54 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 042 | 2 |  | 2 | 503 | 36216.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 042 | 2 |  | 3 | 003 | 67341.53 | 2589 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 043 | 2 |  | 1 | 003 | 53033.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 046 | 2 | 850 | 1 | 003 | 10127.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 | 046 | 2 | 850 | 2 | 115 | 2924.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 3 | 101 | 1905.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 4 | 101 | 3955.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 046 | 2 | 850 | 5 | 503 | 13454.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 1 | 101 | -4700.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 | 052 | 2 |  | 2 | 503 | 22993.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 3 | 503 | 20365.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 4 | 021 | 18403.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 5 | 503 | 8728.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 6 | 503 | -10102.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5668 | 43968235201 | 052 | 2 |  | 7 | 001 | 87500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5668 | 43968235201 | 055 | 2 |  | 1 | 024 | 10336.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 | 019 | 2 |  | 1 | 001 | 19098.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 | 020 | 2 |  | 1 | 118 | 24154.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5669 | 43923515201 | 023 | 2 |  | 1 | 007 | 29083.64 | 19393.96 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5669 | 43923515201 | 024 | 2 |  | 1 | 007 | 0 | 0 | 0 |  | N | 97 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5670 | 43020245201 | 004 | 2 |  | 1 | 923 | 9755.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5670 | 43020245201 | 005 | 2 |  | 1 | 105 | 14862.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 | 010 | 2 |  | 1 | 106 | 42923.56 | 7656 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5670 | 43020245201 | 030 | 2 |  | 1 | 926 | 484.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5670 | 43020245201 | 031 | 2 |  | 1 | 503 | 2274.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5670 | 43020245201 | 034 | 2 |  | 1 | 106 | 9845.01 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 | 012 | 2 |  | 1 | 101 | 12029.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 | 025 | 2 |  | 1 | 107 | 10878.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5678 | 43913115201 | 011 | 2 |  | 1 | 105 | 85887 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5681 | 43968215201 | 010 | 2 |  | 1 | 105 | 3359.62 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5683 | 44141415201 | 018 | 2 |  | 1 | 503 | 186662.88 | 226390.99 | 2 |  | N | 60 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 1 | 012 | 85040.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 2 | 018 | 14265.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
06 | E6K72 | 43652215201 | 004 | 2 | 850 | 3 | 503 | 18539.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 006 | 2 |  | 1 | 305 | -57170.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 008 | 2 |  | 1 | 503 | 230912.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 014 | 2 |  | 1 | 503 | 110000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 031 | 2 |  | 1 | 923 | 55650.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 | 034 | 2 |  | 1 | 012 | 243154.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 | 043 | 2 |  | 1 | 120 | 232450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
06 | E6K73 | 43653715201 | 014 | 2 |  | 1 | 012 | 60602.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 008 | 2 |  | 1 | 305 | -501344.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 017 | 2 | 850 | 1 | 503 | 16908.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 1 | 023 | 8091.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 2 | 023 | 1563.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 3 | 021 | 6782.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 4 | 023 | 7570.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 5 | 023 | 1719.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 6 | 023 | 2555.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 7 | 023 | 14691.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 8 | 503 | 60557.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 9 | 503 | 29209.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 018 | 2 | 850 | 10 | 023 | 306.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 025 | 2 |  | 1 | 919 | 519737.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 042 | 2 |  | 1 | 004 | 700013.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 1 | 023 | 16355.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 2 | 023 | 2109.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 3 | 023 | 13547.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 4 | 023 | 15948.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 5 | 012 | 7124.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 6 | 012 | 68465.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 7 | 012 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 8 | 023 | 1759.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 052 | 2 | 850 | 9 | 023 | 918.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 069 | 2 |  | 1 | 012 | 239955.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 1 | 012 | 40892.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 2 | 023 | 55909.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 3 | 023 | 4714.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 4 | 023 | 632.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 5 | 012 | 7710.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 6 | 023 | 3363.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 7 | 001 | 10625.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 8 | 001 | 7441.6 | 7441.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 076 | 2 | 850 | 9 | 012 | 1732.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 1 | 023 | 52390.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 2 | 012 | 4041.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 | 081 | 2 | 850 | 3 | 503 | 70110.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 083 | 2 |  | 1 | 923 | 41367.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K77 | 42930035201 | 086 | 2 |  | 1 | 019 | -251871.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6K77 | 42930035201 | 088 | 2 |  | 1 | 001 | 126715 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 | 091 | 2 |  | 1 | 503 | 187228.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L23 | 41372125201 | 006 | 2 |  | 1 | 503 | -263995.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L23 | 41372125201 | 010 | 2 |  | 1 | 112 | 4990774.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | E6L23 | 41372125201 | 049 | 2 |  | 1 | 503 | 120601.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L23 | 41372125201 | 050 | 2 |  | 1 | 012 | 361018.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L23 | 41372125201 | 072 | 2 |  | 1 | 305 | 0 | 0 | 0 |  | N | -83 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6L23 | 41372125201 | 073 | 2 |  | 1 | 503 | 375530.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 010 | 2 |  | 1 | 503 | 53775.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 025 | 2 |  | 1 | 503 | 52010.04 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M32 | 44204015201 | 009 | 2 |  | 1 | 007 | -3128331.59 | 231933.48 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M32 | 44204015201 | 011 | 2 |  | 1 | 007 | -70000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6M47 | 44196115201 | 002 | 2 | 850 | 1 | 850 | 16612 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
06 | E6M47 | 44196115201 | 005 | 2 | 850 | 2 | 503 | 2164.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M90 | 43029149201 | 006 | 2 |  | 1 | 503 | 47839.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M90 | 43029149201 | 010 | 2 |  | 1 | 503 | -17420.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M90 | 43029149201 | 010 | 2 |  | 2 | 503 | -181162.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M90 | 43029149201 | 014 | 2 |  | 1 | 924 | -1725.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 005 | 2 |  | 1 | 107 | 6274.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 020 | 2 |  | 1 | 923 | 35192.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 021 | 2 |  | 1 | 005 | 171334 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6427 | 43063715201 | 028 | 2 |  | 1 | 926 | 9685.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6427 | 43063715201 | 041 | 2 | 850 | 1 | 115 | 2981.69 | 2981.69 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 2 | 503 | 3919.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 3 | 115 | 9601.13 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 4 | 115 | 3574.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 5 | 019 | 4015.87 | 4015.87 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict With Other Contractors | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 6 | 115 | 17694.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 7 | 019 | 19745.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 8 | 105 | 5460.65 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 9 | 101 | 3536.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 10 | 503 | 9114.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 11 | 003 | 19477.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 12 | 024 | 1266.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 13 | 107 | 11980.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 14 | 503 | 11016.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 15 | 115 | 6562.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 16 | 007 | 2293.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 17 | 503 | 15060.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 18 | 503 | -3919.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 19 | 503 | 3919.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 041 | 2 | 850 | 20 | 115 | -9601.13 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 21 | 115 | 9601.13 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 22 | 115 | 17694.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 23 | 115 | -17694.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 24 | 105 | -5460.65 | -5460.65 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 25 | 105 | 5460.65 | 5460.65 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 26 | 101 | -3536.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 27 | 101 | 3536.72 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715201 | 041 | 2 | 850 | 28 | 003 | -19477.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6427 | 43063715201 | 041 | 2 | 850 | 29 | 004 | 19477.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6427 | 43063715201 | 048 | 2 |  | 1 | 001 | 100150.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6427 | 43063715201 | 052 | 2 |  | 1 | 106 | 861066.34 | 0 | 5 |  | C | 89 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6427 | 43063715201 | 053 | 2 |  | 1 | 106 | 423756.5 | 0 | 5 |  | N | 60 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6427 | 43063715201 | 055 | 2 |  | 1 | 015 | 93443.3 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 | 057 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | C | 14 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6427 | 43063715201 | 061 | 2 |  | 1 | 015 | 294594.66 | 0 | 0 |  | C | 31 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 | 062 | 2 |  | 1 | 017 | 260565 | 0 | 0 |  | C | 31 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 | 063 | 2 |  | 1 | 106 | 0 | 0 | 0 |  | C | 5 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6427 | 43063715201 | 064 | 2 |  | 1 | 015 | 139888.09 | 0 | 0 |  | C | 15 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 | 067 | 2 |  | 1 | 015 | 183885.15 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 | 068 | 2 |  | 1 | 503 | 85893.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 | 069 | 2 |  | 1 | 107 | -58603.35 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6460 | 43081745201 | 017 | 2 | 850 | 1 | 115 | 13445.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6460 | 43081745201 | 017 | 2 | 850 | 2 | 012 | 11604.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6460 | 43081745201 | 018 | 2 | 850 | 1 | 101 | 30673.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081745201 | 018 | 2 | 850 | 2 | 001 | 4407.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6465 | 43345535201 | 013 | 2 |  | 1 | 503 | 68789.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 1 | 101 | 6599.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 009 | 2 | 850 | 2 | 001 | 1861.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 3 | 001 | 4691.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 4 | 001 | 3626.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 5 | 001 | 1264.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 6 | 503 | 7672.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 7 | 001 | 1685.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 | 009 | 2 | 850 | 8 | 503 | 16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 9 | 503 | -19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 10 | 503 | 19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 11 | 503 | 16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 12 | 503 | -16018.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 009 | 2 | 850 | 13 | 101 | -6599.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 009 | 2 | 850 | 14 | 101 | 7919.48 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 | 009 | 2 | 850 | 15 | 503 | 3750.01 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 1 | 503 | 6279.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 2 | 503 | 10372.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 3 | 503 | 8570.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 4 | 022 | 6268.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 017 | 2 | 850 | 6 | 503 | 15906.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 1 | 503 | 12905.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 2 | 903 | 1102.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
06 | T6469 | 42930045201 | 019 | 2 | 850 | 3 | 503 | 6932.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 019 | 2 | 850 | 4 | 503 | 25208.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6469 | 42930045201 | 020 | 2 | 850 | 1 | 503 | 19656.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 | 018 | 2 | 850 | 1 | 503 | 24400.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 | 019 | 2 |  | 1 | 503 | 3628.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 | 024 | 2 |  | 1 | 103 | 22965.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6483 | 44016915201 | 027 | 2 |  | 1 | 106 | 14459.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6493 | 44331415201 | 001 | 2 |  | 1 | 305 | -121048.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6493 | 44331415201 | 017 | 2 |  | 1 | 503 | 6499.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44331415201 | 019 | 2 |  | 1 | 503 | 64500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L84 | 43227015201 | 008 | 2 |  | 1 | 105 | 1057642.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L84 | 43227015201 | 008 | 2 |  | 2 | 105 | 384971.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L84 | 43227015201 | 008 | 2 |  | 3 | 001 | 185593.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L84 | 43227015201 | 018 | 2 |  | 1 | 105 | 0 | 0 | 1 |  | N | 31 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7L84 | 43227015201 | 018 | 2 |  | 2 | 001 | 0 | 0 | 0 |  | N | 119 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L84 | 43227015201 | 023 | 2 | 850 | 1 | 010 | 32268.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 | 023 | 2 | 850 | 2 | 101 | 7842.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 023 | 2 | 850 | 3 | 503 | 2929.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L84 | 43227015201 | 023 | 2 | 850 | 4 | 010 | 32960.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 | 037 | 2 | 850 | 1 | 010 | 11324 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 | 037 | 2 | 850 | 2 | 101 | 23557.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 037 | 2 | 850 | 3 | 101 | 2843.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 037 | 2 | 850 | 4 | 101 | 25732.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 037 | 2 | 850 | 5 | 010 | 9300.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 | 038 | 2 |  | 1 | 101 | 266012.66 | 186646.95 | 1 |  | N | 84 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 039 | 2 |  | 1 | 130 | 149077.6 | 0 | 0 |  | N | 393 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
07 | E7L84 | 43227015201 | 041 | 2 |  | 1 | 101 | 108769.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 | 048 | 2 |  | 1 | 503 | 32650.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L84 | 43227015201 | 050 | 2 |  | 1 | 503 | 3488 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M81 | 44335315201 | 008 | 2 |  | 1 | 105 | 13287.38 | 0 | 0 |  | N | 86 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7M93 | 44383215201 | 011 | 2 | 850 | 1 | 850 | 50000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7M93 | 44383215201 | 014 | 2 | 850 | 1 | 850 | 9531.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7M96 | 43762615201 | 004 | 2 |  | 1 | 007 | 8496.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 013 | 2 |  | 1 | 101 | 23017.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7N02 | 44383315201 | 005 | 2 |  | 1 | 004 | 4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7N02 | 44383315201 | 006 | 2 |  | 1 | 860 | 45000 | 16551.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | E7N15 | 44539915201 | 005 | 2 |  | 1 | 105 | 40818.19 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 | 006 | 2 | 850 | 1 | 105 | 5117.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 | 006 | 2 | 850 | 2 | 112 | 747.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N15 | 44539915201 | 011 | 2 |  | 1 | 850 | 50487.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7N15 | 44539915201 | 012 | 2 |  | 1 | 850 | 27307.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 1 | 503 | 27181.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 2 | 021 | 3097.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 3 | 024 | 3132.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 4 | 024 | 5343.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 5 | 107 | 11440.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 6 | 024 | 2989.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 7 | 024 | 1987.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 8 | 021 | 1495.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 9 | 021 | 2047.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 10 | 503 | 2226.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 006 | 2 | 850 | 11 | 107 | 89057.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R13 | 44111115201 | 012 | 2 |  | 1 | 106 | 214437.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 013 | 2 |  | 1 | 305 | -58626.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 014 | 2 |  | 1 | 305 | -1644.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7R13 | 44111115201 | 016 | 2 |  | 1 | 503 | 175123.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 018 | 2 |  | 1 | 305 | -83500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 019 | 2 |  | 1 | 305 | -17754.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 027 | 2 |  | 1 | 503 | -20942.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 027 | 2 |  | 2 | 305 | -5652.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 | 028 | 2 | 850 | 2 | 107 | 18778.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7R17 | 44368415201 | 003 | 2 |  | 1 | 004 | 7000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 | 010 | 2 |  | 1 | 122 | 348683.36 | 0 | 2 |  | N | 37 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7R17 | 44368415201 | 010 | 2 |  | 2 | 118 | 13692.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7R17 | 44368415201 | 022 | 2 |  | 1 | 012 | 16954.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 | 004 | 2 | 850 | 1 | 850 | 43458.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7385 | 25624325201 | 003 | 2 |  | 1 | 101 | 9360 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 003 | 2 |  | 2 | 003 | 78500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 003 | 2 |  | 3 | 101 | 18123.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 1 | 108 | 4652.82 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 2 | 003 | 2648.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 3 | 112 | 105000 | 14595.79 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 4 | 107 | 3985.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 5 | 007 | 4640 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 6 | 007 | 6026.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 008 | 2 | 850 | 7 | 107 | 8324.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 8 | 101 | 3000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 008 | 2 | 850 | 9 | 107 | 11722.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 018 | 2 |  | 1 | 007 | 321706.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 018 | 2 |  | 2 | 101 | 31347.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 024 | 2 |  | 1 | 919 | 18470.4 | 18470.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 1 | 112 | 154658.68 | 48714 | 2 |  | N | 59 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 2 | 112 | 5210.71 | 5210.71 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 025 | 2 |  | 3 | 106 | 7226.87 | 7226.87 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 1 | 112 | 50593.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 2 | 107 | 10923.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 3 | 105 | 12628.34 | 750.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 4 | 115 | 3762 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 026 | 2 | 850 | 5 | 115 | 3870.25 | 3870.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 032 | 2 |  | 1 | 503 | 274021.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7385 | 25624325201 | 038 | 2 |  | 1 | 015 | 210084.2 | 17710.37 | 2 |  | N | 16 | Avoidable, In-House Designer | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 047 | 2 |  | 1 | 019 | 57447.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 049 | 2 |  | 1 | 112 | 312932.93 | 223679.73 | 2 |  | N | 15 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 1 | 122 | 3130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 2 | 118 | 35441.79 | 27604.6 | 2 |  | N | 28 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 3 | 113 | 51000 | 51000 | 2 |  | N | 8 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 4 | 019 | 3526.94 | 3526.94 | 5 |  | N | 15 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 5 | 007 | 1200 | 1200 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 6 | 126 | 370.04 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 7 | 113 | 490 | 490 | 2 |  | N | 0 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 8 | 128 | 1121.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7385 | 25624325201 | 052 | 2 |  | 9 | 003 | 3897.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 10 | 015 | 0 | 0 | 5 |  | N | 18 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7385 | 25624325201 | 052 | 2 |  | 11 | 001 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7385 | 25624325201 | 054 | 2 |  | 1 | 001 | 20259.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 010 | 2 | 850 | 1 | 117 | 3454.31 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 | 010 | 2 | 850 | 2 | 003 | 6906.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 010 | 2 | 850 | 3 | 105 | 20035.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7386 | 43002115201 | 010 | 2 | 850 | 4 | 107 | 7991.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 012 | 2 |  | 1 | 009 | 67157.31 | 67157.31 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 021 | 2 |  | 1 | 919 | 26926.07 | 26926.07 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 1 | 001 | 646831.85 | 0 | 0 |  | N | 202 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 2 | 001 | 372527.15 | 128778.18 | 0 |  | N | 98 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 3 | 009 | 271219.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 | 022 | 2 |  | 4 | 001 | 29381 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 | 031 | 2 | 850 | 1 | 115 | 7985.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 041 | 2 | 850 | 1 | 850 | 62000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7386 | 43002115201 | 043 | 2 |  | 1 | 860 | -306142.9 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
07 | T7386 | 43002115201 | 043 | 2 |  | 2 | 003 | 17528.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 3 | 107 | 14495.74 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 4 | 003 | 7136.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 5 | 013 | 6810 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
07 | T7386 | 43002115201 | 043 | 2 |  | 6 | 107 | 33139.86 | 0 | 2 |  | N | 6 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 7 | 107 | 19420.44 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7386 | 43002115201 | 043 | 2 |  | 8 | 115 | 17866.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7400 | 43483915201 | 007 | 2 |  | 1 | 503 | -287499.46 | 0 | 5 |  | C | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7410 | 43649515201 | 006 | 2 |  | 1 | 107 | 1002574.87 | 0 | 1 |  | N | 70 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7410 | 43649515201 | 020 | 2 |  | 1 | 015 | 7859.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 2 | 015 | 18455.83 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 3 | 015 | 8886.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 4 | 015 | 11010.82 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 5 | 015 | 18534.92 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 020 | 2 |  | 6 | 015 | 831776.79 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 030 | 2 | 850 | 1 | 118 | 52233.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7410 | 43649515201 | 037 | 2 |  | 1 | 015 | 325000 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7410 | 43649515201 | 050 | 2 |  | 1 | 503 | 13361 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7437 | 43605615201 | 005 | 2 |  | 1 | 305 | -8336.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7437 | 43605615201 | 008 | 2 |  | 1 | 012 | 163058.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7437 | 43605615201 | 008 | 2 |  | 2 | 007 | 133750.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7437 | 43605615201 | 008 | 2 |  | 3 | 126 | -122480 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8N18 | 41505115201 | 034 | 2 |  | 1 | 305 | -172781.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
08 | E8N18 | 41505115201 | 040 | 2 |  | 1 | 003 | 199426.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 | 051 | 2 |  | 1 | 919 | 95808.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 | 054 | 2 |  | 1 | 503 | 130275.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 | 059 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 1036 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 005 | 2 |  | 1 | 103 | 62681.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 006 | 2 |  | 1 | 101 | 22479 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 009 | 2 |  | 1 | 860 | 61570.19 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 010 | 2 |  | 1 | 107 | -1767730.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 2 | 101 | 131384 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 3 | 503 | 456884.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 010 | 2 |  | 4 | 128 | 34800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 010 | 2 |  | 5 | 108 | 80135.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 015 | 2 |  | 1 | 305 | -92048.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 021 | 2 |  | 1 | 919 | 211015.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 024 | 2 |  | 1 | 503 | 158439.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 025 | 2 |  | 1 | 118 | 193527.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 026 | 2 |  | 1 | 128 | 54336.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 1 | 115 | 3480.7 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 2 | 012 | 25066.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 3 | 012 | 508.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 4 | 503 | 14701.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 5 | 012 | 1930.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 029 | 2 | 850 | 6 | 012 | 10436.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 1 | 012 | 5595.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 2 | 012 | 3037.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 3 | 012 | 3008.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 4 | 012 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 5 | 115 | 4780.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 6 | 012 | 8026.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 7 | 012 | 11017.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 8 | 012 | 2122.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 9 | 012 | 7518.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 10 | 012 | 6470.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 11 | 503 | 2791.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 12 | 012 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 13 | 012 | -6626.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 14 | 012 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 15 | 019 | 2610.39 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 16 | 101 | 2867.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 17 | 117 | 48438.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 18 | 503 | 24202.4 | 24202.4 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 19 | 003 | 5751.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 20 | 503 | -6626.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 030 | 2 | 850 | 21 | 503 | 6262.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 037 | 2 |  | 1 | 004 | 30003.18 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 040 | 2 |  | 1 | 012 | 24623.91 | 24623.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 042 | 2 |  | 1 | 860 | 60654.29 | 36080.95 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 043 | 2 |  | 1 | 503 | 297550.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 047 | 2 |  | 1 | 015 | -146198.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 048 | 2 |  | 1 | 105 | 288837.32 | 0 | 1 |  | C | 3 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 053 | 2 |  | 1 | 922 | 14697.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 056 | 2 |  | 1 | 503 | 505075.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 066 | 2 |  | 1 | 305 | -126787.91 | 0 | 0 |  | N | -6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 067 | 2 |  | 1 | 012 | 62272.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 068 | 2 |  | 1 | 305 | -214564.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 073 | 2 |  | 1 | 007 | 3513792.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 1 | 503 | 4319.62 | 0 | 4 |  | N | 0 | Avoidable, In-House CEI | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 2 | 860 | 20567.95 | 20567.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 3 | 012 | 10580.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 4 | 108 | 26000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 5 | 012 | 8019.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 6 | 012 | 2480.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 7 | 112 | 38750 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 8 | 115 | 2834.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 9 | 105 | 2155.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 10 | 012 | 2883.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 11 | 012 | 4434.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 12 | 003 | 2049.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 074 | 2 | 850 | 13 | 101 | 5817.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 079 | 2 |  | 1 | 860 | 59000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 081 | 2 |  | 1 | 923 | 209769.41 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 082 | 2 |  | 1 | 860 | 15871.26 | 6003.12 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 083 | 2 |  | 1 | 131 | 3500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 094 | 2 |  | 1 | 004 | 17778.5 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 097 | 2 |  | 1 | 923 | 0 | 0 | 0 |  | N | -2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 099 | 2 |  | 1 | 007 | 98417.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 100 | 2 |  | 1 | 860 | 692265.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 109 | 2 |  | 1 | 004 | -3687950.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 109 | 2 |  | 2 | 004 | 1254202.74 | 1254202.74 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 109 | 2 |  | 3 | 118 | 57821.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 109 | 2 |  | 4 | 012 | 107011.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 111 | 2 |  | 1 | 503 | 132410.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 113 | 2 |  | 1 | 126 | 222149.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 113 | 2 |  | 2 | 860 | 78805.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 119 | 2 |  | 1 | 128 | 60973.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 120 | 2 |  | 1 | 860 | 163512.48 | 163512.48 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
08 | E8Q12 | 41140615201 | 122 | 2 |  | 1 | 117 | 97840.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 122 | 2 |  | 2 | 019 | 29666.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 122 | 2 |  | 3 | 012 | 728 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 122 | 2 |  | 4 | 503 | 9907.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 5 | 101 | 1276.34 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 122 | 2 |  | 6 | 503 | 7780.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 7 | 503 | 4244.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 122 | 2 |  | 8 | 101 | 39795.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 125 | 2 |  | 1 | 012 | 110897.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 127 | 2 |  | 1 | 503 | 67262.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 129 | 2 |  | 1 | 503 | -67160.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 1 | 024 | 56632.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 2 | 022 | 77511.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 3 | 023 | 16807.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 4 | 105 | 4993.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8Q12 | 41140615201 | 130 | 2 |  | 5 | 001 | 1621.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 | 130 | 2 |  | 6 | 503 | 10253.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 | 130 | 2 |  | 7 | 010 | 3208.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8Q12 | 41140615201 | 130 | 2 |  | 8 | 019 | 3225.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
08 | E8Q95 | 43652015201 | 013 | 2 | 850 | 1 | 012 | 4074.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652015201 | 013 | 2 | 850 | 2 | 107 | 11901.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8Q95 | 43652015201 | 031 | 2 |  | 1 | 118 | 15743.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R51 | 44132215201 | 011 | 2 |  | 1 | 112 | -311170 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 013 | 2 |  | 1 | 923 | 24000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 020 | 2 |  | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8R51 | 44132215201 | 039 | 2 |  | 1 | 105 | -2099.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R55 | 42815445201 | 008 | 2 |  | 1 | 923 | 27899.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R55 | 42815445201 | 025 | 2 |  | 1 | 126 | 415002.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
08 | E8S00 | 44106715201 | 005 | 2 |  | 2 | 503 | 12516.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S00 | 44106715201 | 005 | 2 |  | 3 | 101 | 5161.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 | 009 | 2 |  | 1 | 101 | 2532.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S09 | 44263125201 | 016 | 2 |  | 1 | 112 | 80000 | 0 | 0 |  | N | 35 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
08 | E8S09 | 44263125201 | 016 | 2 |  | 2 | 503 | -17340 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S09 | 44263125201 | 016 | 2 |  | 3 | 022 | 17671.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S09 | 44263125201 | 022 | 2 |  | 1 | 108 | 225000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8S11 | 44029115201 | 004 | 2 |  | 1 | 105 | 130298.48 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S11 | 44029115201 | 010 | 2 |  | 1 | 107 | 684 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
08 | E8S11 | 44029115201 | 023 | 2 | 850 | 1 | 105 | 14813.47 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S11 | 44029115201 | 023 | 2 | 850 | 2 | 001 | 4780.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S18 | 44042315201 | 009 | 2 |  | 1 | 001 | 18865.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S63 | 44514015201 | 002 | 2 |  | 1 | 101 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 107 | 1419 | 550 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 29461.04 | 12970.11 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 4374.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 2 | 003 | 15570.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 26278.05 | 17511.67 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1P95 | 42838315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 2 |  | N | 15 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1Q47 | 42584145201 |  | 2 | CPI | 1 | 107 | 1369.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 143 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 3506.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 107 | 482.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1Q47 | 42584135201 |  | 2 | CPI | 1 | 007 | 1520.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S02 | 43942515202 |  | 2 | CPI | 1 | 106 | 3274.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1S02 | 43942515201 |  | 2 | CPI | 1 | 503 | 9679.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1S49 | 19602275201 |  | 2 | CPI | 1 | 001 | 2148.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S49 | 19602275201 |  | 2 | CPI | 2 | 107 | 1769.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1S49 | 19602275601 |  | 2 | CPI | 1 | 015 | 10673.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | E1S49 | 19602275202 |  | 2 | CPI | 1 | 007 | 1250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S49 | 19602275201 |  | 2 | CPI | 1 | 929 | 1658.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | E1S52 | 44317215201 |  | 2 | CPI | 1 | 107 | 9979.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1S52 | 44317215201 |  | 2 | CPI | 2 | 003 | 1867.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S52 | 44317215201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 105 | 14320.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1S53 | 43890215201 |  | 2 | CPI | 1 | 001 | 1684.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1S53 | 43890215201 |  | 2 | CPI | 2 | 105 | 11683.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1700 | 43088615201 |  | 2 | CPI | 1 | 007 | 3639.88 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
01 | T1700 | 43088615201 |  | 2 | CPI | 1 | 126 | 5417 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Computation Error | Plan Modifications | 2
01 | T1708 | 43656915201 |  | 2 | CPI | 1 | 122 | 1286.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | T1708 | 43656915201 |  | 2 | CPI | 1 | 106 | 901.07 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 001 | 1652.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 928 | 12020.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 924 | 4675 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 012 | 12300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 2 | 003 | 866.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 112 | 3547.5 | 3547.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 105 | 3791.38 | 3791.38 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 2 | 128 | 9128.19 | 7615.96 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1717 | 19801765201 |  | 2 | CPI | 1 | 128 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1724 | 40622565201 |  | 2 | CPI | 1 | 101 | 10857 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1724 | 40622565201 |  | 2 | CPI | 1 | 118 | 11298.94 | 11298.94 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1724 | 40622565201 |  | 2 | CPI | 1 | 003 | 16520.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 004 | 2850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 924 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 007 | 10864.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 2 | 105 | 3014.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 012 | 4465.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1747 | 43355035201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 105 | 5165.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 105 | 900 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 022 | 11834.62 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1755 | 43659715201 |  | 2 | CPI | 1 | 115 | 3421.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 003 | 1638.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1757 | 43943615202 |  | 2 | CPI | 2 | 105 | 2266.78 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 005 | 1271.57 | 1271.57 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1757 | 43943615201 |  | 2 | CPI | 1 | 001 | 9346.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1757 | 43943615201 |  | 2 | CPI | 1 | 118 | 1286.44 | 1286.44 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 1 | 118 | 4590.41 | 2967.91 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1757 | 43943615202 |  | 2 | CPI | 2 | 012 | 587.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1757 | 43943615202 |  | 2 | CPI | 3 | 108 | 3189.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1760 | 43943915201 |  | 2 | CPI | 1 | 001 | 8540.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1760 | 43943915201 |  | 2 | CPI | 1 | 024 | 5282.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1760 | 43943915202 |  | 2 | CPI | 1 | 001 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 012 | 5764.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 2 | 001 | 5343.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 2 | 003 | 2789.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 101 | 3016.04 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1768 | 43900215201 |  | 2 | CPI | 1 | 007 | 6236.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1774 | 43943315202 |  | 2 | CPI | 1 | 503 | 4125 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1782 | 44188915201 |  | 2 | CPI | 1 | 022 | 27558.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1782 | 44188915202 |  | 2 | CPI | 1 | 101 | 3630 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1782 | 44188915201 |  | 2 | CPI | 1 | 012 | 5541.58 | 5541.58 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1789 | 43693115201 |  | 2 | CPI | 1 | 112 | 898.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1802 | 44067315201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 001 | 23487.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 101 | 1885.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 101 | 1939.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 105 | 4261.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E20B5 | 43054225201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E20B6 | 44199825215 |  | 2 | CPI | 1 | 725 | 0 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
02 | E20D9 | 44703115201 |  | 2 | CPI | 1 | 003 | 8890 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 101 | 665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2074.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3176.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 2309.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 4239.59 | 4239.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 106 | 1524.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 304.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 868.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 914.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 3963.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1829.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2225.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 1303.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 105 | 6853 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4799.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 007 | 322.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2217.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 769.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 106 | 5995 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | -4239.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 3942.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 105 | 5455.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 4239.59 | 4239.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 5500 | 933 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 105 | 2174.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 3177.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 2 | 012 | 13200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 3 | 012 | 4244.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 003 | 2350.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 112 | 59910.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | E2V69 | 21327275201 |  | 2 | CPI | 1 | 001 | 1976.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 010 | 24691.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 861 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
02 | E2W84 | 43384215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 108 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 2 | 108 | 9348.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 3 | 007 | 9926.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 108 | 9348.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 108 | 7905.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 2 | 007 | 12247 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | 551.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 2 | 007 | 1549.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | -2100.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X05 | 44030215201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 60 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 004 | 2950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 004 | 2950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 004 | -2950 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 3238.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 5832.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 2 | 001 | 8198.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 7769.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 2 | 001 | 11123.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 3 | 021 | 3065.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 503 | 8993.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 107 | 19033.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2X66 | 43727415201 |  | 2 | CPI | 2 | 001 | 7769.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 3 | 001 | 11123.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 4 | 021 | 3065.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | -7769.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 2 | 001 | -11123.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 3 | 021 | -3065.03 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 003 | 1889.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 003 | 1390.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 450 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Holiday Time Extension | Holiday Time Extension | 14
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 26 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2X66 | 43727415201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 108 | 4829.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 101 | 19008 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 503 | 4829.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y79 | 20968315201 |  | 2 | CPI | 2 | 024 | 16911.71 | 16911.71 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E2Y79 | 20968315201 |  | 2 | CPI | 3 | 115 | 4421.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Y79 | 20968315201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2Y81 | 43197915201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | -28 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2Y81 | 43197915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | E2Y85 | 43865025201 |  | 2 | CPI | 1 | 115 | 15314.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 115 | 23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | 10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | 38928.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 3 | 115 | -10260.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 4 | 101 | 10592.52 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 1 | 108 | -10739.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Z50 | 42848915201 |  | 2 | CPI | 2 | 115 | -23785.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 21907.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 6426.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 007 | 876.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | E2Z51 | 43384115201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | E2Z52 | 43204815201 |  | 2 | CPI | 1 | 401 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | E2Z52 | 43204815201 |  | 2 | CPI | 2 | 725 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Defective Materials | Defective Materials | 8
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 012 | 1958 | 1958 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 108 | 1461.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 003 | 8872.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 112 | 5582.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 010 | 31201.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 10007.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 2816.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 019 | 5235.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 001 | 3538.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 4084.57 | 4084.57 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 16608.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 5600 | 5600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 018 | 3210.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3600 | 3600 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 5796.91 | 5796.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3789.18 | 3789.18 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 2 | 107 | 15084.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 3502.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125601 |  | 2 | CPI | 2 | 015 | 2008.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 9630.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 33101.44 | 33101.44 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2573 | 21071125601 |  | 2 | CPI | 1 | 015 | 10609.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 105 | 3032.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 101 | 1954.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 107 | 4680.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2573 | 21071125201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 917 | 18825.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 28819.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 12538.2 | 12538.2 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 1892.23 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 2 | 001 | 33438.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 7472.09 | 3712.09 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 2 | 001 | 3054.65 | 3054.65 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245601 |  | 2 | CPI | 1 | 007 | 12407.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T2579 | 21071245601 |  | 2 | CPI | 1 | 015 | 21327.17 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245601 |  | 2 | CPI | 2 | 015 | 16265.33 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 012 | 24155.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 2944 | 2944 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 16860.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 1 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 5 |  | N | 1 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 010 | 0 | 0 | 0 |  | N | 22 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 13 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2579 | 21071245201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 3396.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 101 | 1441 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 3 | 012 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 1023.6 | 1023.6 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 012 | 5390 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 003 | 5042.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 4644.49 | 4644.49 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 105 | 4154.63 | 4154.63 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 4417.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 112 | 15284.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 112 | 2380.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 6280.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 115 | 1442.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 012 | 45923.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 3406.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 105 | 8833.93 | 8833.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 106 | 3468.39 | 3468.39 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 107 | 6418.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 115 | 7538.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 004 | 2270.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 004 | 4228 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 003 | 4078.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 2 | 024 | 2176.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2641 | 20953745201 |  | 2 | CPI | 1 | 024 | 1369.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 112 | 19019.41 | 19019.41 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 001 | 4080.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 001 | 7905.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 923 | 15216.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 2 | 001 | 4703.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 923 | 2007.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 024 | 1900.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2701 | 20936525601 |  | 2 | CPI | 1 | 015 | 49143 | 0 | 1 |  | E | 0 | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2701 | 20936525201 |  | 2 | CPI | 1 | 004 | 3582.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 8678.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2712 | 43240415201 |  | 2 | CPI | 1 | 101 | 2169.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 1712.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 968 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 8809.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 3388 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 2 | 118 | 3470 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 018 | 2500 | 2500 | 3 |  | N | 0 | Avoidable, CEI Consultant | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 004 | 5193.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 40 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 33 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2720 | 43735415201 |  | 2 | CPI | 1 | 018 | 0 | 0 | 3 |  | N | 42 | Avoidable, CEI Consultant | Special Events or Excessive Traffic | Changed Conditions | 1
02 | T2744 | 43935515601 |  | 2 | CPI | 1 | 015 | 3926 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 004 | 4900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2744 | 43602315201 |  | 2 | CPI | 1 | 001 | 1938.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 926 | 8563.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2744 | 43602315201 |  | 2 | CPI | 1 | 005 | 14396.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 128 | 4776.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 005 | 36409.87 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43935515202 |  | 2 | CPI | 1 | 005 | 7672.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43935515202 |  | 2 | CPI | 2 | 001 | 17726.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2744 | 43602315201 |  | 2 | CPI | 1 | 005 | 4665.2 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 005 | 4732.74 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 003 | 15832.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2744 | 43935515201 |  | 2 | CPI | 1 | 003 | 6380 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2744 | 43935515201 |  | 2 | CPI | 2 | 118 | 16350 | 16350 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2744 | 43602315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 5109.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 1080.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 2 | 108 | 1025 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 3965.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2752 | 43395715201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 115 | 3809.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2753 | 43980015201 |  | 2 | CPI | 3 | 001 | 1665.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 4 | 004 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2753 | 43980015201 |  | 2 | CPI | 1 | 101 | 6413 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2759 | 43617615201 |  | 2 | CPI | 1 | 115 | 2087.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2759 | 43617615201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2760 | 44125815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2762 | 44499015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 31 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 115 | 9556.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 120 | 1567.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Hazardous Materials | Plan Modifications | 2
02 | T2768 | 43948815201 |  | 2 | CPI | 1 | 015 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 5390.05 | 534.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 105 | 19607.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2778 | 44105715601 |  | 2 | CPI | 1 | 106 | 15000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 012 | 4031.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 115 | 1205.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 118 | 405.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 112 | 1658.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 2 | 012 | 2273.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 3 | 101 | 132 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2778 | 44105715201 |  | 2 | CPI | 1 | 003 | 6050 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2778 | 44105715201 |  | 2 | CPI | 2 | 101 | 748 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2786 | 43732315201 |  | 2 | CPI | 1 | 001 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2786 | 43732315201 |  | 2 | CPI | 1 | 001 | 7392 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2794 | 44112915201 |  | 2 | CPI | 1 | 115 | 7218.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2794 | 44112915201 |  | 2 | CPI | 1 | 128 | 6397.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2794 | 44112915201 |  | 2 | CPI | 1 | 115 | 36384.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2794 | 44112915201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 21 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 1 | 929 | 1038 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 1 | 122 | 7491.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 2 | 503 | 837.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 128 | 5964.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 115 | 4064.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2799 | 43584515201 |  | 2 | CPI | 3 | 007 | 2239.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
02 | T9022 | 44531935223 |  | 2 | CPI | 1 | 013 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3T25 | 44154615201 |  | 2 | CPI | 1 | 117 | 3638.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3T27 | 40571925201 |  | 2 | CPI | 1 | 107 | 2820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3T27 | 41557635201 |  | 2 | CPI | 1 | 107 | 1786 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3T51 | 44154215201 |  | 2 | CPI | 1 | 503 | 10071.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 17111.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 108 | 18001.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 64497.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 2 | 115 | 477.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 3 | 001 | 1594.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 2047.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 2 | 107 | 3081.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 3 | 115 | 6034.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 4 | 115 | 2028.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 5 | 115 | 3629.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 3664.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 2 | 115 | 2740.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 3 | 115 | 2061.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 4 | 115 | 5962.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 5 | 112 | 13599.9 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 3465.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 1 |  | N | 8 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3359 | 21860315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 012 | 19580 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 012 | 19580 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 012 | -19580 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 106 | 3537 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3533 | 21797635201 |  | 2 | CPI | 2 | 503 | 3992 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 3 | 503 | 3361 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 115 | 8733 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 503 | 12491.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 3 | 503 | 7966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 115 | 30267 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 |  | 2 | CPI | 2 | 115 | 11635 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 503 | 15519.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 503 | 15519.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 503 | -15519.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3533 | 21797635201 |  | 2 | CPI | 1 | 350 | 3218.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3632 | 43581515201 |  | 2 | CPI | 1 | 503 | 3700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3632 | 43581515201 |  | 2 | CPI | 1 | 503 | 31461.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3660 | 40619435201 |  | 2 | CPI | 1 | 105 | 3450 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3660 | 40619435201 |  | 2 | CPI | 1 | 107 | 3398 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
03 | T3660 | 40619435201 |  | 2 | CPI | 1 | 003 | 6962.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3660 | 40619435201 |  | 2 | CPI | 1 | 012 | 1192.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3660 | 40619435201 |  | 2 | CPI | 1 | 012 | 4660.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 3414.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 5540.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 105 | 5818.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615202 |  | 2 | CPI | 2 | 001 | 4498.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 9391.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 2 | 010 | 1280.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 2380.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 004 | 16711.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3692 | 43774615202 |  | 2 | CPI | 1 | 010 | 191.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 105 | 12338 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 101 | 158.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3692 | 43774615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 1387.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3723 | 43972115201 |  | 2 | CPI | 2 | 503 | 2566.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 712.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3723 | 43972115201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3725 | 43627315201 |  | 2 | CPI | 1 | 101 | 5225 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3725 | 43627315201 |  | 2 | CPI | 1 | 001 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3725 | 43627315201 |  | 2 | CPI | 2 | 101 | 1170.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3725 | 43627315201 |  | 2 | CPI | 1 | 101 | 24365.06 | 24365.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3725 | 43627315201 |  | 2 | CPI | 2 | 101 | 314.81 | 314.81 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3725 | 43627315201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 4 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 115 | 7132.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 8460 | 3760 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3729 | 43972715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 503 | 24084.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 113 | 15225 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3730 | 43972515201 |  | 2 | CPI | 2 | 113 | 2960 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3730 | 43972515201 |  | 2 | CPI | 3 | 101 | 3230 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | T3730 | 43972515201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3738 | 44173815201 |  | 2 | CPI | 1 | 503 | 2217.07 | 2217.07 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 503 | 7918.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 115 | 2763.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 012 | 3216.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3745 | 43972915201 |  | 2 | CPI | 2 | 115 | 8062.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 3 | 115 | 1506.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 4 | 107 | 368.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3745 | 43972915201 |  | 2 | CPI | 5 | 503 | 1396.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3745 | 43972915201 |  | 2 | CPI | 6 | 012 | 1114.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3745 | 43972915201 |  | 2 | CPI | 1 | 115 | 16824.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3749 | 44173215201 |  | 2 | CPI | 1 | 012 | 5200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3749 | 44173215201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3751 | 43775325201 |  | 2 | CPI | 1 | 103 | 22902.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
04 | E4T51 | 43785115201 |  | 2 | CPI | 1 | 001 | 1057.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4T51 | 43785115201 |  | 2 | CPI | 1 | 503 | 10557.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T51 | 43785115201 |  | 2 | CPI | 1 | 503 | 972.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4T51 | 43785115201 |  | 2 | CPI | 1 | 106 | 13375.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4T51 | 43785115201 |  | 2 | CPI | 1 | 007 | 9537.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T80 | 43524515201 |  | 2 | CPI | 1 | 118 | 11385 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4T80 | 43524515201 |  | 2 | CPI | 1 | 012 | 10494 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T80 | 43524515201 |  | 2 | CPI | 1 | 130 | 17303 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | E4T80 | 43524515201 |  | 2 | CPI | 1 | 012 | 2048.75 | 2048.75 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T80 | 43524515201 |  | 2 | CPI | 2 | 012 | 3038.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 003 | 1320.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 003 | 4144.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 17550 | 17550 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 007 | 9411.02 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0.5 | 0.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 2 | 115 | 4679.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 3 | 115 | 3233.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4T83 | 42268145201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | 4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 503 | -4214.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 503 | 4214.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U24 | 43984115201 |  | 2 | CPI | 1 | 115 | 15685.46 | 3838.25 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4U24 | 43984115201 |  | 2 | CPI | 2 | 007 | 672.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 112 | 1712 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 112 | 1017.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 112 | 2366.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 112 | 5810.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 023 | 2076.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 1 | 112 | -9195.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 2 | 112 | -1712 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 3 | 112 | 6930.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215201 |  | 2 | CPI | 4 | 112 | 8177.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U33 | 43804215203 |  | 2 | CPI | 1 | 112 | 29.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 001 | 3787.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U54 | 44330915201 |  | 2 | CPI | 1 | 105 | 6430.57 | 2734.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 1 | 001 | 851.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U72 | 44162915201 |  | 2 | CPI | 2 | 101 | 4846.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 3 | 101 | 9689.83 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 4 | 118 | 3863.48 | 3863.48 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | E4U72 | 44162915201 |  | 2 | CPI | 5 | 007 | 1821.09 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U72 | 44162915201 |  | 2 | CPI | 6 | 503 | 1766.74 | 313.25 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4U72 | 44162915201 |  | 2 | CPI | 7 | 012 | 3257.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 023 | 6433.53 | 6433.53 | 5 |  | N | 0 | Avoidable, Third Party | Non Weather Related Damages | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 001 | 942.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 2 | 106 | 1799.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 3 | 106 | 3235.27 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 4 | 001 | 1752.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 108 | 710.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 2 | 001 | 979.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 3 | 105 | 2788.12 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 4 | 001 | 1288.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 5 | 001 | 12838 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 001 | 11945.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 005 | 6089.3 | 6089.3 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 118 | 2210.79 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4471 | 43472215602 |  | 2 | CPI | 1 | 106 | 1599.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4471 | 43472215201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 7 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 107 | 1101.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 007 | 1494.85 | 1494.85 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 015 | 1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 015 | -1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 015 | 1255.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 001 | 2305.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 926 | 7919.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 2 | 928 | 834.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 118 | 8234.16 | 8234.16 | 5 |  | N | 0 | Avoidable, Third Party | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4476 | 43515815602 |  | 2 | CPI | 1 | 015 | 975.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
04 | T4476 | 43515815201 |  | 2 | CPI | 1 | 107 | 1700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1195.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1278.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 112 | 1403.59 | 1403.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4488 | 43630415201 |  | 2 | CPI | 1 | 502 | 1242.7 | 1242.7 | 4 |  | N | 0 | Avoidable, In-House CEI | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 004 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 115 | 2724.61 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 007 | 1293.76 | 1293.76 | 5 |  | C | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 926 | 2950.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 503 | 1018.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 119 | 6441.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 503 | 423 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 128 | 5712.85 | 5712.85 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 106 | 3052.67 | 3052.67 | 5 |  | C | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 1 | 123 | 12016.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 2 | 115 | 1226.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4494 | 43630715201 |  | 2 | CPI | 3 | 108 | 5481.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 001 | 33966.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 004 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 105 | 870.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 503 | -932.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 2 | 503 | 935.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 115 | 3357.15 | 3357.15 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 926 | 1714.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4497 | 43783615201 |  | 2 | CPI | 1 | 108 | 402.72 | 402.72 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 003 | 3451.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4504 | 43783815201 |  | 2 | CPI | 2 | 108 | 1575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 115 | 2970 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 6941.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 022 | 38809.69 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4504 | 43783815201 |  | 2 | CPI | 1 | 024 | 8679.73 | 8679.73 | 5 |  | N | 0 | Avoidable, Third Party | Drainage Modification | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 17185.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 14389.34 | 5447.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 5447.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 112 | 2581.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 106 | 1609.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4505 | 43668515201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 001 | 2010.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4509 | 43177055201 |  | 2 | CPI | 2 | 118 | 1184 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4509 | 43177055201 |  | 2 | CPI | 1 | 118 | 2235.78 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 123 | 7672.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4511 | 43469015201 |  | 2 | CPI | 1 | 118 | 1045 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 1 | 105 | 1220.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 2 | 105 | 5359.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 3 | 105 | 5363.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4521 | 43760515201 |  | 2 | CPI | 4 | 105 | 4850.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 924 | 4726.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 926 | 6050.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 1943.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 2094 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 22246.63 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 50538.51 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4523 | 43469515201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 106 | 7011.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 115 | 567.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 001 | 1782.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 115 | 1543.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 924 | 3434.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 503 | 962.5 | 962.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 123 | 7192.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 123 | 6050 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 503 | 749.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 123 | 8800 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 123 | 6050 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4525 | 42956955201 |  | 2 | CPI | 1 | 123 | 5585.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 101 | 1045.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4528 | 43696715201 |  | 2 | CPI | 1 | 010 | -8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4528 | 43696715201 |  | 2 | CPI | 2 | 010 | 8490.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
04 | T4530 | 43592515201 |  | 2 | CPI | 1 | 001 | 10020.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4530 | 43592515201 |  | 2 | CPI | 2 | 001 | 716.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4530 | 43592515201 |  | 2 | CPI | 1 | 019 | 9471.3 | 9471.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
04 | T4538 | 44138115201 |  | 2 | CPI | 1 | 122 | 495 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4538 | 44138115201 |  | 2 | CPI | 1 | 503 | 10798.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4538 | 44138115201 |  | 2 | CPI | 2 | 123 | 1561.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Landscaping Changes | Plan Modifications | 2
04 | T4542 | 43984215201 |  | 2 | CPI | 1 | 928 | 2810.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
04 | T4542 | 43984215201 |  | 2 | CPI | 1 | 001 | 9602.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4542 | 43984215203 |  | 2 | CPI | 1 | 023 | 3788.17 | 3788.17 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4542 | 43984215203 |  | 2 | CPI | 2 | 021 | 1807.89 | 1807.89 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 001 | 475.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 2 | 001 | 1000.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4543 | 43915915201 |  | 2 | CPI | 1 | 106 | 1429.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4556 | 43991015201 |  | 2 | CPI | 1 | 115 | 10188.75 | 6218.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4556 | 43991015201 |  | 2 | CPI | 1 | 115 | 6218.93 | 6218.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4556 | 44163015201 |  | 2 | CPI | 1 | 503 | 15507.77 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4556 | 44163015201 |  | 2 | CPI | 1 | 023 | 4857.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4556 | 44163015201 |  | 2 | CPI | 1 | 101 | 354 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4556 | 43991015201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 1 |  | N | 22 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E52A1 | 44208715201 |  | 2 | CPI | 1 | 001 | 7876.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E52A1 | 44208715201 |  | 2 | CPI | 1 | 118 | 1327.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E52A1 | 44208715201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E52A2 | 44113815201 |  | 2 | CPI | 1 | 503 | 22100.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E53A6 | 44119715201 |  | 2 | CPI | 1 | 001 | 10409.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E53A6 | 44119715201 |  | 2 | CPI | 2 | 003 | 1837.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A7 | 44333415201 |  | 2 | CPI | 1 | 503 | 2121.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 4372.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E53A9 | 44101715201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E54A0 | 44208815201 |  | 2 | CPI | 1 | 106 | 1691.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E54A0 | 44208815201 |  | 2 | CPI | 2 | 003 | 361.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E54A0 | 44208815201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E54A2 | 44589615201 |  | 2 | CPI | 1 | 503 | 2169.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E55A1 | 44530925216 |  | 2 | CPI | 1 | 503 | 8375.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E55A1 | 44530925216 |  | 2 | CPI | 1 | 106 | 4024.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E55A1 | 44530925216 |  | 2 | CPI | 2 | 106 | 8660.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E55A1 | 44530925216 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E55A1 | 44530925216 |  | 2 | CPI | 1 | 106 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E55A4 | 44113715201 |  | 2 | CPI | 1 | 118 | 985.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | E55A4 | 44113715201 |  | 2 | CPI | 1 | 105 | 1033.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E55A5 | 44333315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 17 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E55A6 | 44589515201 |  | 2 | CPI | 1 | 003 | 4752.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E57A3 | 41125655201 |  | 2 | CPI | 1 | 105 | 1220.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E57A9 | 43988085201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z71 | 43179835601 |  | 2 | CPI | 1 | 015 | 45231.04 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 103 | 110463.47 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 105 | 11459.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 115 | 16531.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 115 | 11545.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 103 | 0 | 0 | 2 |  | N | 20 | Avoidable, In-House Designer | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 106 | 0 | 13796.45 | 0 |  | N | 70 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z71 | 43179835201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 101 | 4675 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 108 | 15035.36 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 107 | 10794.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 3 | 012 | 14140.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 001 | 15055.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 115 | 2708.69 | 2708.69 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 106 | 5214.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 2 | 105 | 7921.71 | 7921.71 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z86 | 43913615201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 29 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 8048.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 13022.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | 9696.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 1 | 012 | -9696.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z90 | 44326915201 |  | 2 | CPI | 2 | 012 | 9693.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E5Z96 | 44116615201 |  | 2 | CPI | 1 | 010 | 48527.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 3806.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 118 | 3195.46 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 106 | 1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 1085.75 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | -2518.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 106 | -1628.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 001 | 2481.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 106 | 2004.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 107 | 25090.49 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 10416 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 3 | 115 | 4418.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 4 | 001 | 2133.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 5 | 118 | 3406.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 115 | 1209.95 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 003 | 8370.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 1659.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 3498.06 | 3498.06 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 001 | 2486.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 003 | 5868.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 115 | 35290.2 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 105 | 3306.22 | 3306.22 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5538 | 23949635201 |  | 2 | CPI | 2 | 001 | 1977.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
05 | T5538 | 23949635201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 30 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 1 | 128 | 21312.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5582 | 23827585201 |  | 2 | CPI | 2 | 007 | 1805.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5582 | 23827585201 |  | 2 | CPI | 3 | 007 | 2786.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 012 | 13114.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 001 | 13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 003 | 1175 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 023 | -30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 8001.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 023 | 30163.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 023 | 9874 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 004 | 55000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 1 | 001 | -13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5628 | 43734115201 |  | 2 | CPI | 2 | 010 | 12460.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
05 | T5628 | 43734115601 |  | 2 | CPI | 1 | 001 | 13100.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5636 | 43800315201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 18 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 003 | 16192.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 3273.6 | 3273.6 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 373.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43612715201 |  | 2 | CPI | 1 | 106 | 341.18 | 341.18 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 119 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
05 | T5637 | 43386015201 |  | 2 | CPI | 1 | 106 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5645 | 43988515201 |  | 2 | CPI | 1 | 106 | 24187.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5645 | 43988515201 |  | 2 | CPI | 1 | 003 | 1677.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 101 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 101 | 21230 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 003 | 33261.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 003 | 22097.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 101 | 9358.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5668 | 43968235201 |  | 2 | CPI | 2 | 003 | 15052.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968235201 |  | 2 | CPI | 1 | 023 | 3409.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 003 | 22942.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 007 | 371.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
05 | T5668 | 43968245202 |  | 2 | CPI | 2 | 122 | 1570.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 122 | 627.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
05 | T5668 | 43968245202 |  | 2 | CPI | 1 | 115 | 13257.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5668 | 43968245602 |  | 2 | CPI | 1 | 106 | 3658.89 | 3491.95 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5668 | 43968245602 |  | 2 | CPI | 1 | 106 | -54.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5669 | 43754415201 |  | 2 | CPI | 1 | 001 | 34432.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 1 | 012 | 30199.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5669 | 43923515201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
05 | T5670 | 43020245201 |  | 2 | CPI | 1 | 003 | 441.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5670 | 43020245201 |  | 2 | CPI | 2 | 105 | 2500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 |  | 2 | CPI | 1 | 003 | 4538.3 | 4538.3 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 105 | 997.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 3457.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 6173.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 21764.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 2 | 106 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 3 | 118 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 4 | 112 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5676 | 43913915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 105 | 1811.7 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 012 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 2 | 022 | 2312.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 3 | 001 | 15618.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 023 | 126.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5678 | 43913115201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5683 | 43896825201 |  | 2 | CPI | 1 | 118 | 2780 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5683 | 44141415201 |  | 2 | CPI | 1 | 107 | 1188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5683 | 44141415201 |  | 2 | CPI | 1 | 107 | 0.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5701 | 44136515201 |  | 2 | CPI | 1 | 115 | 3638.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5734 | 44101315201 |  | 2 | CPI | 1 | 115 | 4967.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5734 | 44101315201 |  | 2 | CPI | 2 | 012 | 18000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5734 | 44101315201 |  | 2 | CPI | 3 | 012 | 30761.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5734 | 44101315201 |  | 2 | CPI | 4 | 007 | 2901.51 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
05 | T5734 | 44101315201 |  | 2 | CPI | 5 | 001 | 1210.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5734 | 44101315201 |  | 2 | CPI | 6 | 118 | 5106.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5734 | 44101315201 |  | 2 | CPI | 1 | 503 | 3936.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5734 | 44101315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5734 | 44101315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 503 | 59068.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 012 | 5599.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 3 | 503 | 19834.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 012 | 5599.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 107 | 9130 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 024 | 1689.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | E6K72 | 43652215201 |  | 2 | CPI | 2 | 012 | 24758.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 024 | 682.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 503 | 14135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6K72 | 43652215201 |  | 2 | CPI | 1 | 012 | 2630.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 17305.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 023 | 12874.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K73 | 43653715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 11 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 3325.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 021 | 12038.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6982.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 2292.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 4161.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 3 | 023 | 4219.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 4 | 023 | 6174.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 5 | 023 | 2705.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 6 | 012 | 7465.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 023 | 3820.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 1339.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 023 | 1180.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 001 | 6131.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 8290.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 9725.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 2 | 021 | 26375.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 012 | 29900.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035201 |  | 2 | CPI | 1 | 023 | 739.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6K77 | 42930035202 |  | 2 | CPI | 1 | 503 | 13063.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L23 | 41372125201 |  | 2 | CPI | 1 | 019 | 149437.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 1799.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 503 | 13098.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 |  | 2 | CPI | 1 | 122 | 3916.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
06 | E6L94 | 43653915201 |  | 2 | CPI | 1 | 001 | 37896 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | E6L94 | 43653915201 |  | 2 | CPI | 1 | 012 | 1787.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | E6M37 | 44060415201 |  | 2 | CPI | 1 | 503 | 4180 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M37 | 44060415201 |  | 2 | CPI | 2 | 503 | 5500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M37 | 44060415201 |  | 2 | CPI | 3 | 115 | 1163.65 | 1163.65 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6M37 | 44060415201 |  | 2 | CPI | 1 | 101 | 2667.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6M47 | 44196115201 |  | 2 | CPI | 1 | 503 | 14242.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M47 | 44196115201 |  | 2 | CPI | 2 | 503 | 2369.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M49 | 44197415201 |  | 2 | CPI | 1 | 001 | 2816.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M49 | 44197415201 |  | 2 | CPI | 2 | 005 | 6386.91 | 6386.91 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | E6N05 | 44188615201 |  | 2 | CPI | 1 | 007 | 646 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6N05 | 44188615201 |  | 2 | CPI | 2 | 019 | 3576.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6N05 | 44188615201 |  | 2 | CPI | 3 | 503 | 1906.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6N05 | 44188615201 |  | 2 | CPI | 1 | 503 | 2484.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6N05 | 44188615201 |  | 2 | CPI | 2 | 503 | 17279.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 001 | 13409.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 004 | 3634.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 503 | 2110.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 503 | 9440.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 012 | 2591 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 101 | 13090 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 68008.44 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 6029.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 10304.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 115 | 5642.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 4292.63 | 4292.63 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 11442.64 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 6591.17 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 3 | 015 | 23711.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 003 | 9900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 013 | 5423.34 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Test Projects | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 745 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 3 | 015 | 10800.02 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 115 | -5642.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 503 | 10586.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6427 | 43063715201 |  | 2 | CPI | 3 | 115 | 2903.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 4 | 115 | 3062.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 115 | 5642.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 115 | 4751.61 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 101 | 13090 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 003 | 3941.63 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 3 | 016 | 22966 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 4 | 004 | 36617.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 101 | -13090 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 5855.31 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 8479.22 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 3 | 015 | 3952.75 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 4 | 015 | 5541.44 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 1 | 012 | 2590.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 2 | 024 | 2044.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6427 | 43063715201 |  | 2 | CPI | 3 | 115 | 717.23 | 717.23 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 4953.18 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 6183.43 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 3 | 015 | 5286.63 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 3807.52 | 1903.76 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 10691.37 | 5345.69 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 3 | 015 | 9245.02 | 9245.02 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 7490.11 | 4494.07 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 2 | 015 | 20139.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 16184.59 | 11625.7 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6427 | 43063715601 |  | 2 | CPI | 1 | 015 | 1413.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 123 | 11428.39 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 123 | 11790.24 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 001 | 3497.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 503 | 3837.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 101 | 13838 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 101 | 14586 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6460 | 43081735201 |  | 2 | CPI | 1 | 115 | 23432.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6460 | 43081745201 |  | 2 | CPI | 1 | 101 | 18084.45 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 105 | 15535.31 | 15535.31 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 108 | 5682.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 001 | 3956.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 108 | 1496.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 2 | 012 | 10378.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1823.55 | 1823.55 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 1458.84 | 1458.84 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6465 | 43345535201 |  | 2 | CPI | 1 | 118 | 729.42 | 729.42 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 001 | 4807.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 2 | 007 | 20570 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 101 | 25942.65 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
06 | T6469 | 42930045201 |  | 2 | CPI | 3 | 103 | -25942.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6469 | 42930045201 |  | 2 | CPI | 4 | 101 | 24622.65 | 0 | 3 |  | N | 0 | Avoidable, CEI Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6469 | 42930045601 |  | 2 | CPI | 1 | 503 | 1224 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 101 | 4114.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 118 | 1399.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 023 | 3135 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015202 |  | 2 | CPI | 1 | 118 | 1399.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 1 | 022 | 9277.38 | 9277.38 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6472 | 44167015201 |  | 2 | CPI | 2 | 115 | 2240.54 | 2240.54 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 001 | 1650.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 2 | 001 | 1578.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 3 | 001 | 2352.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 108 | 244.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 5266.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 005 | 6677.94 | 6677.94 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 685.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 001 | 1325.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 1 | 007 | 4544.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6475 | 43635525201 |  | 2 | CPI | 2 | 001 | 357.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | -5266.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 2 | 001 | -685.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 3 | 001 | 3466.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 1 | 001 | 685.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6475 | 43635535201 |  | 2 | CPI | 2 | 001 | 1800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6478 | 44030415201 |  | 2 | CPI | 1 | 503 | 5010.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6478 | 44030415201 |  | 2 | CPI | 2 | 101 | 794.56 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 3645.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 4970.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017825201 |  | 2 | CPI | 1 | 503 | 756.11 | 756.11 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 |  | 2 | CPI | 1 | 503 | 10767.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 1040.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 1379.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 7980.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 2 | 503 | 995.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017015201 |  | 2 | CPI | 1 | 001 | 1093.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 937.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44016915201 |  | 2 | CPI | 1 | 503 | 1300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017015201 |  | 2 | CPI | 1 | 503 | 421.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 1 | 503 | 3172.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6483 | 44017115201 |  | 2 | CPI | 2 | 503 | 6154.59 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6488 | 43992415201 |  | 2 | CPI | 1 | 108 | 2862.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6488 | 44254115201 |  | 2 | CPI | 1 | 101 | 2538 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6488 | 44254115201 |  | 2 | CPI | 2 | 007 | 3385.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6488 | 44254115201 |  | 2 | CPI | 3 | 105 | 4016.69 | 4016.69 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6493 | 44396215201 |  | 2 | CPI | 1 | 503 | 2326.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44356415201 |  | 2 | CPI | 1 | 503 | 1128.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6493 | 44396015201 |  | 2 | CPI | 1 | 503 | 1464.71 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | -9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | -3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 9745.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 2 | 503 | 3162.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 503 | 2122.53 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 |  | 2 | CPI | 1 | 007 | 3015.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6501 | 43998515201 |  | 2 | CPI | 1 | 503 | 971.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6501 | 43998515201 |  | 2 | CPI | 2 | 001 | 10005.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6501 | 43998515201 |  | 2 | CPI | 1 | 001 | 2119.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6501 | 43998515201 |  | 2 | CPI | 1 | 005 | 5094.42 | 5094.42 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6502 | 44385315201 |  | 2 | CPI | 1 | 101 | 2518 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6502 | 44385315201 |  | 2 | CPI | 1 | 001 | 2889.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 107 | 2388.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 023 | 3796.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 003 | 7665.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
06 | T6507 | 43991815201 |  | 2 | CPI | 1 | 105 | 4396.45 | 4396.45 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6526 | 44167215201 |  | 2 | CPI | 1 | 004 | 1419.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
06 | T6528 | 44183215201 |  | 2 | CPI | 1 | 503 | 2929.5 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6528 | 44183215201 |  | 2 | CPI | 2 | 503 | 17313.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6528 | 44183215201 |  | 2 | CPI | 3 | 502 | 10748.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
06 | T6528 | 44183215201 |  | 2 | CPI | 4 | 503 | 9132.4 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6528 | 44183215201 |  | 2 | CPI | 5 | 503 | 4604.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6528 | 44183215201 |  | 2 | CPI | 1 | 503 | 2612.94 | 2612.94 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 101 | 11771.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 112 | 29717.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 126 | 13610.8 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 001 | 11641.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 010 | 9242.53 | 9242.53 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 010 | 15.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L84 | 43227015201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7L84 | 43227015201 |  | 2 | CPI | 3 | 010 | 15.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
07 | E7L84 | 43227015201 |  | 2 | CPI | 2 | 010 | -15.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7L84 | 43227015201 |  | 2 | CPI | 1 | 130 | 0 | 0 | 1 |  | N | 5 | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
07 | E7M61 | 43951615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M61 | 43951615201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 2 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M81 | 44335315201 |  | 2 | CPI | 3 | 101 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 2 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 61 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M81 | 44335315201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 46 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 107 | 25412.83 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 001 | 275.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 503 | 1879.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M91 | 44144125201 |  | 2 | CPI | 1 | 107 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | E7M93 | 44383215201 |  | 2 | CPI | 1 | 112 | 5962.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7M93 | 44383215201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7M93 | 44383215201 |  | 2 | CPI | 1 | 012 | 14037.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 1040.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M94 | 43673415201 |  | 2 | CPI | 1 | 101 | 12000 | 12000 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1163.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 004 | 3990.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7M96 | 43762615201 |  | 2 | CPI | 2 | 101 | 749.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 1034 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7M96 | 43762615201 |  | 2 | CPI | 1 | 118 | 2027.92 | 2027.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7N02 | 44383315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 101 | 3022.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | 1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 105 | 15926.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | 1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 2 | 107 | -1051.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | E7N15 | 44539915201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N15 | 44539915201 |  | 2 | CPI | 1 | 105 | 0 | 0 | 1 |  | N | 9 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | E7N26 | 43946015201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N26 | 43946015201 |  | 2 | CPI | 2 | 502 | 7811.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7N26 | 43946015201 |  | 2 | CPI | 1 | 502 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
07 | E7N46 | 43955415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N48 | 44025215201 |  | 2 | CPI | 1 | 112 | 7325.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7N64 | 44146715201 |  | 2 | CPI | 1 | 012 | 4550 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7N64 | 44146715201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 8 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7N64 | 44146715201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 012 | 17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 012 | 17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 503 | 23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 023 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 5 | 023 | 7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 012 | -17636.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | -4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | -3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 4 | 503 | -23469.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | 4117.15 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | -1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | -4117.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 503 | 38335.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 1468.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 022 | 4117.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 923 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 5080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 34053.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 503 | 9583.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | -4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | -3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | -7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 1 | 022 | 4796.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 2 | 023 | 3639.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R13 | 44111115201 |  | 2 | CPI | 3 | 023 | 7819.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 4000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 2 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 007 | 1800 | 1800 | 2 |  | N | 0 | Avoidable, In-House Designer | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R17 | 44368415201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 16 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 21620.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7R25 | 44335815201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 115 | 2708.52 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 6578.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 2838.79 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 115 | 1794.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 4 | 107 | 5814.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 48842.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 105 | 4182.62 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 5244.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 45443.42 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 2 | 108 | 5480.99 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 877.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 107 | 8720.37 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
07 | T7385 | 25624325201 |  | 2 | CPI | 1 | 007 | 11473.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7385 | 25624325601 |  | 2 | CPI | 1 | 015 | 3027.36 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 009 | 2334.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 009 | 10412.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 3 | 001 | 13333.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115601 |  | 2 | CPI | 1 | 021 | 6155.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 117 | 16202.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 001 | 6208.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7386 | 43002115201 |  | 2 | CPI | 2 | 117 | 13508.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115601 |  | 2 | CPI | 1 | 021 | 12007.43 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7386 | 43002115201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 5 |  | N | 3 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
07 | T7400 | 43483915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7400 | 43483915201 |  | 2 | CPI | 2 | 105 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7400 | 43483915201 |  | 2 | CPI | 3 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7400 | 43483915201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515601 |  | 2 | CPI | 1 | 001 | 48529.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7410 | 43649515601 |  | 2 | CPI | 1 | 126 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 004 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 2 | 112 | 49057.62 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7410 | 43649515201 |  | 2 | CPI | 1 | 118 | 8412.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7410 | 43649515204 |  | 2 | CPI | 1 | 118 | 19861.94 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7437 | 43605615201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7437 | 43605615201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7437 | 43605615201 |  | 2 | CPI | 3 | 007 | 2529.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7447 | 43764115201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7447 | 43764115201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7455 | 44140315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7466 | 43764615201 |  | 2 | CPI | 1 | 101 | 5569.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 1090.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 8138.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 021 | 905.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8N18 | 41505115201 |  | 2 | CPI | 3 | 003 | 10849.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 748.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 3666.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 2835.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 6219.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 3644.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 004 | 13254.23 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 1031.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 437.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 023 | 420.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 503 | 8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 503 | -8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 6695.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 2659.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 8266.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 023 | 1189.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 004 | 27296.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 926 | 9582.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8N18 | 41505115201 |  | 2 | CPI | 3 | 503 | 2400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 10641.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 021 | 981.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 2 | 503 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8N18 | 41505115201 |  | 2 | CPI | 1 | 503 | 8350 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 11425.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 001 | 5808 | 5808 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 001 | 3246.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 11394 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 503 | 6396.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 503 | 8291.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 503 | 2751.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 108 | 5153.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 004 | 8142.4 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 021 | 9478.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 007 | 10356.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 503 | 6947.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8Q12 | 41140615201 |  | 2 | CPI | 3 | 012 | 7429.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 4 | 012 | 19749.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 5 | 012 | 4691.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 6 | 012 | 4725.71 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 7 | 012 | 4879.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140645201 |  | 2 | CPI | 1 | 012 | 3933.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 012 | 11615.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140615201 |  | 2 | CPI | 2 | 012 | 468.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q12 | 41140645201 |  | 2 | CPI | 1 | 115 | 3116.4 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
08 | E8Q12 | 41140615201 |  | 2 | CPI | 1 | 860 | 0 | 0 | 5 |  | N | 2 | Avoidable, Third Party | Claim Settlement | Claim Settlement | 10
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 012 | 85783.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 001 | 20357.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q95 | 43652015201 |  | 2 | CPI | 1 | 012 | 21974.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8Q95 | 43652035201 |  | 2 | CPI | 1 | 001 | 175 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8Q95 | 43652035201 |  | 2 | CPI | 2 | 105 | 7100.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 010 | 2761.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 107 | 1639.41 | 1639.41 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 021 | 19257.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 115 | 8068.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 3 | 118 | 4136 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 2648.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 4233.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 503 | 4542.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 107 | 1163.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 106 | 4509.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 924 | 14026.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 105 | 10563.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 024 | 7781.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 2 | 131 | 3314.95 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8R51 | 44132215201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 40430.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 926 | 5753.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 17935.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 869.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 010 | 974.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8R55 | 42815445201 |  | 2 | CPI | 2 | 115 | 6771.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8R55 | 42815445201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 5625.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 11747.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 926 | 689.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 107 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 3749.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 3279.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 1 | 101 | 13694.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 2 | 107 | 3575 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S00 | 44106715201 |  | 2 | CPI | 3 | 107 | 344.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
08 | E8S09 | 44263125201 |  | 2 | CPI | 1 | 103 | 13435.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 123 | 30606.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Landscaping Changes | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 115 | 16242.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
08 | E8S11 | 44029115201 |  | 2 | CPI | 1 | 010 | 10485.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
08 | E8S11 | 44029115201 |  | 2 | CPI | 2 | 003 | 5432.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8S11 | 44029125201 |  | 2 | CPI | 1 | 105 | 20817.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 021 | 5799.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 503 | 15605.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 1 | 503 | 12507.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 2 | 503 | 8114.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042315201 |  | 2 | CPI | 3 | 023 | 29158.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 1 | 503 | 1320 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 2 | 503 | 14262.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 3 | 503 | 2852.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 4 | 503 | 4237.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S18 | 44042325201 |  | 2 | CPI | 5 | 503 | 22848.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S63 | 44514015201 |  | 2 | CPI | 1 | 101 | 2859.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 1879.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8S73 | 44429215201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1P48 | 43489815201 | 019 |  | 51 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | [9 empty] | Avoidable, In-House CEI
01 | T1700 | 43088615201 | 503 |  | 25 | 015 | 1 | 3 | N | Avoidable, CEI Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1717 | 19801765201 | 924 |  | 36 | 051 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1747 | 43355035201 | 924 |  | 27 | 029 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1755 | 43659715201 | 005 |  | 45 | 007 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
01 | T1755 | 43659715201 | 118 |  | 1 | 007 | 2 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1764 | 44013015201 | 924 |  | 20 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1774 | 43943315201 | 924 |  | 14 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1782 | 44188915201 | 924 |  | 3 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1786 | 41450665201 | 924 |  | 7 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1786 | 41450665201 | 924 |  | 14 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | E2W84 | 43384215201 | 108 |  | 93 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E2Y79 | 20968315201 | 106 |  | 11 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y85 | 43865025201 | 924 |  | 16 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Y85 | 43865025201 | 924 |  | 16 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | E2Z36 | 43930315201 | 012 |  | 21 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2579 | 21071245201 | 015 |  | 4 | 077 | 1 | 5 | N | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2700 | 41525015201 | 924 |  | 34 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2743 | 42845515201 | 924 |  | 21 | 039 | 1 | 1 | N | Avoidable, Design Consultant | Joint Project Agreement Utility Conflict | Changed Conditions | 1
02 | T2751 | 21172815201 | 103 |  | 7 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2751 | 21172815201 | 103 |  | 6 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
02 | T2777 | 44126215201 | 126 |  | 17 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
02 | T2778 | 44105715201 | 924 |  | 30 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
02 | T2781 | 44106015201 | 405 |  | 14 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
03 | E3Q53 | 44009615201 | 009 |  | 7 | 012 | 1 | 1 | C | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 87 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 003 |  | 13 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 924 |  | 65 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 013 |  | 62 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
03 | E3Q53 | 44009615201 | 016 |  | 72 | 041 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3S42 | 42187345201 | 924 |  | 128 | 003 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
03 | E3T25 | 44154615201 | 503 |  | 3 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T35 | 44291315201 | 010 |  | 6 | 010 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3T58 | 43815415201 | 009 |  | 30 | 004 | 1 | 2 | N | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3T58 | 43815415201 | 009 |  | 94 | 016 | 1 | 2 | N | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3T96 | 4453581G201 | 130 |  | 5 | 008 | 1 | 2 | N | Avoidable, In-House Designer | Indecision/Delayed Response | Plan Modifications | 2
03 | E3U12 | 44365725201 | 924 |  | 21 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | T3359 | 21860315201 | 503 |  | 3 | 097 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3359 | 21860315201 | 001 |  | 37 | 112 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3632 | 43581515201 | 503 |  | 31 | 021 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3660 | 40619435201 | 927 |  | 145 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3699 | 43228415201 | 018 |  | 15 | 004 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Special Events or Excessive Traffic | Changed Conditions | 1
03 | T3699 | 43228415201 | 106 |  | 21 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3725 | 43627315201 | 101 |  | 205 | 034 | 1 | 1 | N | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3729 | 43972715201 | 023 |  | 2 | 021 | 1 | 5 | N | Avoidable, Third Party | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3729 | 43972715201 | 012 |  | 2 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3730 | 43972515201 | 924 |  | 55 | 032 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3730 | 43972515201 | 924 |  | 37 | 050 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3738 | 44173815201 | 106 |  | 2 | 006 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3738 | 44173815201 | 106 |  | 5 | 007 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3738 | 44173815201 | 106 |  | 7 | 010 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3744 | 43972415201 | 924 |  | 50 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3745 | 43972915201 | 005 |  | 19 | 031 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | E4T80 | 43524515201 | 924 |  | 7 | 019 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
04 | E4T80 | 43524515201 | 130 |  | 65 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | E4U33 | 43804215201 | 924 |  | 42 | 028 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | E4U33 | 43804215201 | 924 |  | 18 | 052 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
04 | E4U33 | 43804215201 | 128 |  | 29 | 053 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
04 | T4471 | 43472215201 | 005 |  | 18 | 053 | 1 | 5 | N | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
04 | T4471 | 43472215201 | 118 |  | 6 | 059 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4488 | 43630415201 | 924 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4505 | 43668515201 | 924 |  | 22 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4519 | 43469715201 | 924 |  | 30 | 055 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
04 | T4521 | 43760515201 | 105 |  | 25 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4538 | 44138115201 | 924 |  | 64 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | T5670 | 43020245201 | 106 |  | 5 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | E6K73 | 43653715201 | 503 |  | 6 | 017 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L90 | 43029139201 | 019 |  | 37 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 924 |  | 16 | 030 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
06 | E6L90 | 43029139201 | 503 |  | 25 | 031 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M49 | 44197415201 | 924 |  | 14 | 013 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6482 | 44017815201 | 001 |  | 8 | 025 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6483 | 44016915201 | 503 |  | 45 | 035 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6498 | 43080835201 | 503 |  | 25 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6501 | 43998515201 | 503 |  | 5 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6524 | 42934535201 | 924 |  | 23 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L84 | 43227015201 | 503 |  | 78 | 046 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7M81 | 44335315201 | 112 |  | 133 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7M96 | 43762615201 | 007 |  | 21 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7M96 | 43762615201 | 118 |  | 27 | 018 | 1 | 1 | N | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
08 | E8Q95 | 43652015201 | 503 |  | 10 | 026 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8R51 | 44132215201 | 924 |  | 80 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1700 | 43088615201 | 2018-02-28 | QTR3 | 17/18 | 1 | 1 | 150 | 333 | 333 | 0 | 0 | 0 | 183 | 0 | 2262913 | 50000 | 2212913 | 2254766 | 2207735 | 0 | 0 | 0 | 2207735 | 2219978 | 12243 | -8147 | 134 | 0 | 0 | -4507 | 0 | 0 | 0 | 5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 910 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2019-06-27 | QTR4 | 18/19 | 113 | 2483172.88 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 21 | 01co | 1 | 21
01CO | 01 | T1708 | 43656915201 | 2018-06-13 | QTR4 | 17/18 | 2 | 3 | 285 | 365 | 396 | -31 | 31 | 0 | 55 | 25 | 4931384 | 50000 | 4881384 | 4944272 | 4958547 | -23106 | 0 | -23106 | 4935442 | 4958136 | 22695 | 12888 | 29 | 0 | 3 | 8110 | 0 | 0 | 22 | 6965 | 4778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 15075 | 4778 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-06-23 | QTR4 | 21/22 | 2020-03-19 | QTR3 | 19/20 | 108 | 5037240.78 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 15 | 01do | 22 | 36
01CO | 01 | T1717 | 19801765201 | 2018-12-05 | QTR2 | 18/19 | 4 | 17 | 700 | 913 | 925 | -12 | 12 | 0 | 152 | 61 | 15860000 | 150000 | 15710000 | 16463364 | 16135347 | -90816 | -60000 | -150816 | 15984531 | 15920739 | -48363 | 603364 | 111 | 0 | 0 | 586377 | 3552 | 0 | 4 | 22688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 619221 | 3552 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2022-03-29 | QTR3 | 21/22 | 2021-10-08 | QTR2 | 21/22 | 115 | 15674640.54 | B10 | ACC - BONUS/INCENT/DISINCENT | 4 | 41 | 0 | 0 | 101513 | 0 |  | CO | 29 | 02co | 37 | 65
01CO | 01 | T1724 | 40622565201 | 2019-04-24 | QTR4 | 18/19 | 1 | 7 | 325 | 918 | 899 | 19 | 0 | 0 | 593 | 0 | 8657668 | 80604 | 8577064 | 9259778 | 9381182 | 0 | 0 | 0 | 9381182 | 9332082 | -49100 | 602110 | 128 | 0 | 0 | 283993 | 0 | 0 | 0 | 356793 | 63902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640786 | 63902 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-06-15 | QTR4 | 21/22 | 2022-04-01 | QTR4 | 21/22 | 113 | 7999281.74 |  |  | 0 | 465 | 0 | 0 | 0 | 0 |  | CO | 21 | 02do | 66 | 86
01CO | 01 | T1735 | 43654715201 | 2018-09-26 | QTR1 | 18/19 | 1 | 1 | 85 | 102 | 89 | 13 | 0 | 0 | 17 | 0 | 409918 | 11212 | 398706 | 418046 | 383683 | 0 | 0 | 0 | 383683 | 383683 | 0 | 8128 | 11 | 0 | 0 | 8128 | 6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8128 | 6258 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2019-09-30 | QTR1 | 19/20 | 113 | 267364.21 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 25 | 03co | 87 | 111
01CO | 01 | T1747 | 43355035201 | 2019-08-28 | QTR1 | 19/20 | 2 | 6 | 425 | 532 | 549 | -17 | 17 | 0 | 106 | 1 | 12256766 | 131640 | 12125126 | 12232966 | 12265846 | -82722 | 0 | -82722 | 12183124 | 12147745 | -35379 | -23800 | 78 | 0 | 1 | 266281 | 14344 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2605 | 14344 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 115 | 11662002.59 |  |  | 1 | 28 | 0 | 0 | -38003 | 0 |  | CO | 15 | 03do | 112 | 126
01CO | 01 | T1755 | 43659715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 1 | 260 | 376 | 373 | 3 | 0 | 0 | 116 | 0 | 5620384 | 66812 | 5553572 | 5602989 | 5688348 | 0 | 0 | 0 | 5688348 | 5695271 | 6923 | -17395 | 44 | 0 | 0 | 0 | 0 | 1 | 0 | -7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 3926 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-14 | QTR2 | 21/22 | 2021-07-23 | QTR1 | 21/22 | 113 | 6766075.21 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 23 | 04co | 127 | 149
01CO | 01 | T1757 | 43943615201 | 2020-07-29 | QTR1 | 20/21 | 3 | 4 | 200 | 261 | 260 | 1 | 0 | 0 | 34 | 27 | 2163088 | 50000 | 2113088 | 2182239 | 2172501 | 0 | 0 | 0 | 2172501 | 2181502 | 9002 | 19151 | 25 | 0 | 0 | 11573 | 0 | 0 | 27 | 103123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 43328 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 108 | 2199110.64 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 9 | 04do | 150 | 158
01CO | 01 | T1760 | 43943915201 | 2020-06-10 | QTR4 | 19/20 | 2 | 1 | 235 | 291 | 288 | 3 | 0 | 0 | 56 | 0 | 4964468 | 57276 | 4907192 | 4976639 | 5027641 | 0 | 0 | 0 | 5027641 | 5062613 | 34972 | 12171 | 47 | 0 | 0 | 13541 | 0 | 0 | 0 | 12171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30994 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 | 2021-10-18 | QTR2 | 21/22 | 108 | 5089189.35 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 17 | 05co | 159 | 175
01CO | 01 | T1764 | 44013015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 100 | 137 | 137 | 0 | 0 | 0 | 37 | 0 | 381859 | 15090 | 366769 | 381859 | 358474 | 0 | 0 | 0 | 358474 | 358474 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-01 | QTR4 | 20/21 | 113 | 386665.82 |  |  | 0 | 4 | 0 | 0 | 0 | 0 | T | CO | 23 | 05do | 176 | 198
01CO | 01 | T1768 | 43900215201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 200 | 301 | 292 | 9 | 0 | 0 | 69 | 32 | 1847556 | 50000 | 1797556 | 1962457 | 1921734 | 0 | 0 | 0 | 1921734 | 1920578 | -1156 | 114901 | 43 | 0 | 0 | 85699 | 0 | 0 | 32 | 52352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 138051 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-02-19 | QTR3 | 20/21 | 113 | 1876585.43 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 20 | 06co | 199 | 218
01CO | 01 | T1774 | 43943315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 2 | 180 | 254 | 251 | 3 | 0 | 0 | 74 | 0 | 3486645 | 50000 | 3436645 | 3507153 | 3516611 | 0 | 0 | 0 | 3516611 | 3553965 | 37354 | 20508 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 20508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24633 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-05-16 | QTR4 | 21/22 | 2022-01-19 | QTR3 | 21/22 | 118 | 3999396.52 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO | 12 | 06do | 219 | 230
01CO | 01 | T1775 | 44151915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 275 | 371 | 370 | 1 | 0 | 0 | 96 | 0 | 7746370 | 98021 | 7648349 | 7776109 | 7775281 | 0 | 0 | 0 | 7775281 | 7823279 | 47998 | 29739 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29739 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 | 2021-11-13 | QTR2 | 21/22 | 118 | 9281425.28 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 10 | 07co | 231 | 240
01CO | 01 | T1782 | 44188915201 | 2020-08-26 | QTR1 | 20/21 | 2 | 2 | 300 | 458 | 497 | -39 | 39 | 0 | 158 | 0 | 7817251 | 97842 | 7719409 | 7814901 | 7885666 | -47180 | 0 | -47180 | 7838486 | 8007597 | 169112 | -2350 | 112 | 0 | 0 | 5542 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34380 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 | 2022-05-16 | QTR4 | 21/22 | 106 | 9633676.97 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 18 | 07do | 241 | 258
01CO | 01 | T1786 | 41450665201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 90 | 120 | 120 | 0 | 0 | 0 | 30 | 0 | 1630302 | 50000 | 1580302 | 1630302 | 1465226 | 0 | 0 | 0 | 1465226 | 1467413 | 2188 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 | 2021-11-12 | QTR2 | 21/22 | 118 | 2010635.43 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 259 | 258
01CO | 01 | T1789 | 43693115201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 271 | 270 | 1 | 0 | 0 | 71 | 0 | 2359731 | 50000 | 2309731 | 2322360 | 2220739 | 0 | 0 | 0 | 2220739 | 2223174 | 2435 | -37371 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36473 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-01-25 | QTR3 | 21/22 | 2021-08-26 | QTR1 | 21/22 | 113 | 2549900.36 |  |  | 0 | 16 | 0 | 0 | -37371 | 0 |  | CO | 12 | 08do | 259 | 270
01CO | 01 | T1793 | 43815115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 2 | 97 | 183 | 182 | 1 | 0 | 0 | 86 | 0 | 721749 | 0 | 721749 | 726881 | 731189 | 0 | 0 | 0 | 731189 | 731189 | 0 | 5132 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-04-07 | QTR4 | 21/22 | 2022-02-24 | QTR3 | 21/22 | 113 | 853456.97 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1795 | 44012415201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 100 | 119 | 119 | 0 | 0 | 0 | 19 | 0 | 597800 | 23302 | 574498 | 597800 | 548637 | 0 | 0 | 0 | 548637 | 548637 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 | 2022-02-08 | QTR3 | 21/22 | 115 | 474793.61 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1796 | 44050815201 | 2021-03-31 | QTR3 | 20/21 | 1 | 2 | 100 | 124 | 123 | 1 | 0 | 0 | 24 | 0 | 817957 | 38521 | 779436 | 986429 | 914986 | 0 | 0 | 0 | 914986 | 914986 | 0 | 168472 | 19 | 0 | 0 | 81012 | 0 | 0 | 0 | 87460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168472 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-07 | QTR3 | 21/22 | 2021-10-01 | QTR2 | 21/22 | 118 | 656746.29 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1798 | 44013615201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 125 | 144 | 143 | 1 | 0 | 0 | 19 | 0 | 779141 | 30218 | 748923 | 779141 | 703853 | 0 | 0 | 0 | 703853 | 746933 | 43081 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-16 | QTR4 | 21/22 | 2022-03-04 | QTR3 | 21/22 | 115 | 689937.77 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1802 | 44067315201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 110 | 147 | 143 | 4 | 0 | 0 | 31 | 6 | 962055 | 50000 | 912055 | 962055 | 887528 | 0 | 0 | 0 | 887528 | 887873 | 345 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 | 2022-03-15 | QTR3 | 21/22 | 108 | 1041118.33 |  |  | 6 | 15 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1P48 | 43489815201 | 2020-01-16 | QTR3 | 19/20 | 3 | 3 | 150 | 261 | 261 | 0 | 0 | 0 | 100 | 11 | 881862 | 41098 | 840764 | 950893 | 869654 | 0 | 0 | 0 | 869654 | 870011 | 357 | 69031 | 29 | 51 | 0 | 24967 | 18162 | 0 | 11 | 44064 | 41654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 11 | 69031 | 59816 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-08-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 113 | 901554.85 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P95 | 42838315201 | 2017-06-15 | QTR4 | 16/17 | 4 | 13 | 825 | 1189 | 1179 | 10 | 0 | 0 | 149 | 215 | 12611204 | 102103 | 12509101 | 13133768 | 12450757 | -35183 | -125000 | -160183 | 12290574 | 12343775 | 53201 | 522564 | 71 | 0 | 26 | 98702 | 3841 | 0 | 100 | 270614 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156514 | 0 | 0 | 0 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18052 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 18830 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 567739 | 13064 | F352555020 | IBT CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-15 | QTR3 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 115 | 10409514.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 15 | 78 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q47 | 42584135201 | 2018-03-15 | QTR3 | 17/18 | 3 | 20 | 637 | 1044 | 1041 | 3 | 0 | 0 | 226 | 181 | 44539372 | 150000 | 44389372 | 47408126 | 47193361 | 0 | 0 | 0 | 47193361 | 47078549 | -23194 | 2868754 | 166 | 0 | 106 | 3110410 | 0 | 0 | 30 | 213917 | 87416 | 0 | 0 | 0 | 0 | 0 | 0 | -138763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179254 | 0 | 0 | 0 | -577152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2787665 | 87416 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2021-08-18 | QTR1 | 21/22 | 2021-05-14 | QTR4 | 20/21 | 113 | 59075331.91 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R56 | 43796615201 | 2020-01-16 | QTR3 | 19/20 | 1 | 4 | 200 | 217 | 217 | 0 | 0 | 0 | 17 | 0 | 2770000 | 50000 | 2720000 | 3004222 | 2811795 | 0 | 0 | 0 | 2811795 | 2798207 | 0 | 234222 | 11 | 0 | 0 | 189350 | 0 | 0 | 0 | 31284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220634 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-27 | QTR2 | 21/22 | 2021-08-23 | QTR1 | 21/22 | 115 | 3199272.33 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S02 | 43942515201 | 2019-09-19 | QTR1 | 19/20 | 2 | 3 | 200 | 435 | 430 | 5 | 0 | 0 | 235 | 0 | 3418691 | 50000 | 3368691 | 3599265 | 3634779 | 0 | 0 | 0 | 3634779 | 3581913 | -52866 | 180574 | 207 | 0 | 0 | 183811 | 15128 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193529 | 15128 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-26 | QTR2 | 21/22 | 2021-08-13 | QTR1 | 21/22 | 113 | 3935082.53 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S49 | 19602275201 | 2020-03-26 | QTR3 | 19/20 | 3 | 8 | 360 | 476 | 474 | 2 | 0 | 0 | 81 | 35 | 4765372 | 50000 | 4715372 | 5108479 | 5065730 | 0 | 0 | 0 | 5065730 | 5081869 | 16140 | 343107 | 55 | 0 | 35 | 331038 | 0 | 0 | 0 | 27910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 358948 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-03-15 | QTR3 | 21/22 | 2021-11-19 | QTR2 | 21/22 | 115 | 5214661.03 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S51 | 44002715201 | 2020-03-19 | QTR3 | 19/20 | 1 | 1 | 80 | 152 | 191 | -39 | 39 | 0 | 45 | 27 | 407081 | 16632 | 390449 | 421138 | 368049 | -48399 | 0 | -48399 | 319650 | 319650 | 0 | 14057 | 26 | 0 | 27 | 14057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14057 | 0 | F465439171 | HEAVY CIVIL INC | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 | 2021-02-12 | QTR3 | 20/21 | 115 | 439357.58 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S52 | 44317215201 | 2021-06-10 | QTR4 | 20/21 | 1 | 0 | 100 | 122 | 122 | 0 | 0 | 0 | 21 | 1 | 460332 | 21752 | 438580 | 460332 | 429428 | 0 | 0 | 0 | 429428 | 429528 | 100 | 0 | 5 | 0 | 1 | 1867 | 0 | 0 | 0 | 9980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11847 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2022-05-10 | QTR4 | 21/22 | 2022-01-26 | QTR3 | 21/22 | 118 | 486642.23 |  |  | 1 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S53 | 43890215201 | 2020-06-11 | QTR4 | 19/20 | 1 | 1 | 250 | 311 | 291 | 20 | 0 | 0 | 61 | 0 | 1335282 | 50000 | 1285282 | 1434154 | 1346419 | 0 | 0 | 0 | 1346419 | 1347016 | 596 | 98871 | 44 | 0 | 0 | 1685 | 0 | 0 | 0 | 124875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126560 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-17 | QTR1 | 21/22 | 2021-05-27 | QTR4 | 20/21 | 118 | 1282338.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S54 | 44334015201 | 2020-06-11 | QTR4 | 19/20 | 1 | 0 | 159 | 194 | 194 | 0 | 0 | 0 | 35 | 0 | 2038002 | 50000 | 1988002 | 2038002 | 1947616 | 0 | 0 | 0 | 1947616 | 1941883 | -5733 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-12 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 113 | 2189902.85 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T43 | 43485715201 | 2021-01-21 | QTR3 | 20/21 | 1 | 2 | 200 | 253 | 247 | 6 | 0 | 0 | 53 | 0 | 1132241 | 50000 | 1082241 | 1177226 | 1189866 | 0 | 0 | 0 | 1189866 | 1189866 | 0 | 44985 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 44985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44985 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 | 2022-03-22 | QTR3 | 21/22 | 113 | 1324427.78 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T46 | 44681615201 | 2020-07-23 | QTR1 | 20/21 | 1 | 1 | 400 | 449 | 449 | 0 | 0 | 0 | 49 | 0 | 3083600 | 50000 | 3033600 | 3080211 | 3030211 | 0 | 0 | 0 | 3030211 | 3030211 | 0 | -3389 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3389 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 | 2021-12-20 | QTR2 | 21/22 | 106 | 4731071.94 | LBDB | LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T47 | 44624415201 | 2020-07-15 | QTR1 | 20/21 | 1 | 0 | 350 | 366 | 366 | 0 | 0 | 0 | 16 | 0 | 1836500 | 50000 | 1786500 | 1836500 | 1786500 | 0 | 0 | 0 | 1786500 | 1787020 | 520 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851245849 | AJAX MSB JOINT VENTURE LLC | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 118 | 1849529.09 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T68 | 43980115201 | 2020-12-03 | QTR2 | 20/21 | 1 | 1 | 75 | 106 | 178 | -72 | 72 | 0 | 21 | 10 | 180572 | 10362 | 170210 | 210394 | 199372 | -3750 | 0 | -3750 | 195621 | 195621 | 0 | 29822 | 18 | 0 | 10 | 29822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29822 | 0 | F844347908 | TRAILS CLEARING SERVICE LLC | N/A | N/A | N/A | N/A | 2022-01-21 | QTR3 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 108 | 260006.67 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1T84 | 43506615201 | 2020-12-03 | QTR2 | 20/21 | 1 | 0 | 80 | 91 | 91 | 0 | 0 | 0 | 11 | 0 | 231014 | 11809 | 219205 | 231014 | 219205 | 0 | 0 | 0 | 219205 | 219205 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-08-23 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 118 | 230281.92 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2573 | 21071125201 | 2016-09-28 | QTR1 | 16/17 | 3 | 14 | 1040 | 1576 | 1565 | 11 | 0 | 0 | 455 | 81 | 39980618 | 200000 | 39780618 | 41792741 | 42556288 | 0 | 0 | 0 | 42556288 | 43113323 | 593970 | 1812123 | 319 | 0 | 11 | 719490 | 3757 | 0 | 34 | 964158 | 8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 33656 | 27317 | 0 | 0 | 0 | 0 | 0 | 0 | 161180 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 139221 | 139221 | 0 | 0 | 0 | 0 | 0 | 81 | 1952765 | 178951 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 208 | 35388991.1 |  |  | 4 | 136 | 0 | 0 | -73244 | 0 |  | CO
02CO | 02 | T2579 | 21071245201 | 2015-10-28 | QTR2 | 15/16 | 3 | 19 | 1200 | 1931 | 1931 | 0 | 0 | 0 | 457 | 274 | 59962436 | 200000 | 59762436 | 63341457 | 65450734 | 0 | 0 | 0 | 65450734 | 65555411 | 337124 | 3379021 | 270 | 4 | 173 | 2137240 | 30185 | 0 | 27 | 505924 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 143722 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 374791 | 374791 | 0 | 0 | 0 | 0 | 4 | 261 | 3167145 | 408848 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 208 | 62411015.71 |  |  | 91 | 196 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2641 | 20953745201 | 2016-10-26 | QTR2 | 16/17 | 1 | 13 | 1040 | 1482 | 1482 | 0 | 0 | 0 | 225 | 217 | 60315650 | 150000 | 60165650 | 62391668 | 63370802 | 0 | 0 | 0 | 63370802 | 64550404 | 1278355 | 2076018 | 139 | 0 | 217 | 1537516 | 64955 | 0 | 0 | 301994 | 136991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24844 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1981192 | 201946 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-03-26 | QTR3 | 20/21 | 208 | 62430986.7 |  |  | 0 | 86 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2700 | 41525015201 | 2018-04-25 | QTR4 | 17/18 | 4 | 4 | 480 | 733 | 733 | 0 | 0 | 0 | 207 | 46 | 11881880 | 0 | 11881880 | 12125444 | 12326250 | 0 | 0 | 0 | 12326250 | 12238377 | -48704 | 243564 | 155 | 0 | 46 | 124284 | 10266 | 0 | 0 | 80110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 204395 | 10266 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2020-09-11 | QTR1 | 20/21 | 208 | 8810904.69 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2701 | 20936525201 | 2018-04-25 | QTR4 | 17/18 | 2 | 4 | 480 | 729 | 730 | -1 | 1 | 0 | 182 | 67 | 11196736 | 139554 | 11057182 | 11726950 | 11984103 | 0 | 0 | 0 | 11984103 | 11975790 | -8313 | 530213 | 99 | 0 | 57 | 397506 | 73135 | 0 | 10 | 201220 | 17861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19921 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 620548 | 90996 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-08 | QTR4 | 21/22 | 2020-07-27 | QTR1 | 20/21 | 208 | 9764053.56 |  |  | 0 | 83 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2712 | 43240415201 | 2018-08-29 | QTR1 | 18/19 | 1 | 3 | 300 | 737 | 749 | -12 | 12 | 0 | 225 | 212 | 3754465 | 50000 | 3704465 | 3806745 | 3827055 | -32544 | 0 | -32544 | 3794511 | 3793154 | -1358 | 52280 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 10848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 40265 | 40265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 22 | 12014 | 12014 | 0 | 0 | 0 | 0 | 0 | 212 | 63127 | 52280 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-03-11 | QTR3 | 20/21 | 208 | 4106536.1 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2720 | 43735415201 | 2018-10-31 | QTR2 | 18/19 | 1 | 4 | 200 | 572 | 572 | 0 | 0 | 0 | 170 | 202 | 2468956 | 50000 | 2418956 | 2635619 | 2856937 | 0 | 0 | 0 | 2856937 | 2843130 | -13807 | 166663 | 95 | 0 | 42 | 7693 | 0 | 0 | 160 | 185011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 192704 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-03-29 | QTR3 | 20/21 | 214 | 2333570.34 |  |  | 202 | 75 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2743 | 42845515201 | 2019-05-22 | QTR4 | 18/19 | 1 | 4 | 750 | 857 | 857 | 0 | 0 | 0 | 147 | -40 | 12559204 | 120 | 12559084 | 13123013 | 13368899 | 0 | 0 | 0 | 13368899 | 13241202 | -127696 | 563809 | 108 | 0 | -30 | 143449 | 0 | 0 | 0 | 27147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904784 | 590741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40 | 563809 | 590741 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-10-27 | QTR2 | 21/22 | 208 | 13121490.39 |  |  | 0 | 39 | 0 | -10 | -511572 | 0 |  | CO
02CO | 02 | T2744 | 43602315201 | 2019-12-04 | QTR2 | 19/20 | 4 | 6 | 450 | 711 | 711 | 0 | 0 | 0 | 220 | 41 | 19213273 | 153926 | 19059347 | 19486164 | 20329507 | 0 | 0 | 0 | 20329507 | 20310464 | -19043 | 272891 | 135 | 0 | 41 | 288595 | 0 | 0 | 0 | 21126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93624 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 403345 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-05-13 | QTR4 | 21/22 | 2022-02-07 | QTR3 | 21/22 | 216 | 20412508 |  |  | 11 | 85 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2751 | 21172815201 | 2019-10-30 | QTR2 | 19/20 | 2 | 3 | 190 | 336 | 334 | 2 | 0 | 0 | 75 | 71 | 3950552 | 240 | 3950312 | 4195563 | 4295295 | 0 | 0 | 0 | 4295295 | 4276296 | -18999 | 245012 | 50 | 0 | 0 | 143610 | 0 | 13 | 71 | 101402 | 101402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 71 | 245012 | 101402 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 | 2020-12-23 | QTR2 | 20/21 | 214 | 4829848.48 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2752 | 43395715201 | 2019-12-04 | QTR2 | 19/20 | 1 | 0 | 400 | 548 | 485 | 63 | 0 | 0 | 145 | 3 | 6416755 | 63600 | 6353155 | 6416755 | 6306830 | 0 | 0 | 0 | 6306830 | 6314515 | 7685 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11181 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 209 | 6469876.4 |  |  | 3 | 34 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2753 | 43980015201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 300 | 379 | 286 | 93 | 0 | 0 | 55 | 24 | 3416497 | 50000 | 3366497 | 3891903 | 3917050 | 0 | 0 | 0 | 3917050 | 3897876 | -19174 | 475406 | 27 | 0 | 24 | 429046 | 0 | 0 | 0 | 10222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 439268 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 208 | 3898969.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2759 | 43617615201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 150 | 194 | 193 | 1 | 0 | 0 | 43 | 1 | 4035736 | 50000 | 3985736 | 4035736 | 3954853 | 0 | 0 | 0 | 3954853 | 3920789 | -34064 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2020-12-10 | QTR2 | 20/21 | 214 | 4365195.44 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2760 | 44125815201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 200 | 282 | 320 | -38 | 38 | 0 | 55 | 27 | 6493175 | 56059 | 6437116 | 6617231 | 6291241 | -142728 | 0 | -142728 | 6148513 | 6136498 | -12015 | 124056 | 35 | 0 | 27 | 124056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124056 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-07-24 | QTR1 | 21/22 | 209 | 5584101.49 |  |  | 10 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2762 | 44499015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 2 | 199 | 268 | 268 | 0 | 0 | 0 | 30 | 39 | 1596635 | 120 | 1596515 | 1683719 | 1395080 | 0 | 0 | 0 | 1395080 | 1395080 | 0 | 87084 | 10 | 0 | 31 | 60834 | 0 | 0 | 8 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 87084 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-06-29 | QTR4 | 20/21 | 209 | 1936705 |  |  | 31 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2768 | 43948815201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 160 | 239 | 176 | 63 | 0 | 0 | 76 | 3 | 1959598 | 50000 | 1909598 | 1959598 | 1892736 | 0 | 0 | 0 | 1892736 | 1893489 | 752 | 0 | 38 | 0 | 3 | 0 | 0 | 0 | 0 | 11124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11124 | 0 | F800219140 | WATSON CONSTRUCTION COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-04-28 | QTR4 | 20/21 | 214 | 1755198.42 |  |  | 3 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2770 | 43948915201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 180 | 206 | 135 | 71 | 0 | 0 | 26 | 0 | 601043 | 45269 | 555774 | 596270 | 539883 | 0 | 0 | 0 | 539883 | 539883 | 0 | -4773 | 3 | 0 | 0 | -4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4773 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-10 | QTR3 | 20/21 | 214 | 942548.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2773 | 43403815201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 350 | 408 | 389 | 19 | 0 | 0 | 58 | 0 | 3684895 | 58701 | 3626194 | 3684895 | 3598807 | 0 | 0 | 0 | 3598807 | 3601767 | 2960 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-08-05 | QTR1 | 21/22 | 214 | 3367569.01 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2774 | 43578015201 | 2020-05-20 | QTR4 | 19/20 | 1 | 0 | 150 | 176 | 174 | 2 | 0 | 0 | 26 | 0 | 1066490 | 120 | 1066370 | 1066490 | 1059789 | 0 | 0 | 0 | 1059789 | 1060127 | 338 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2021-09-23 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 214 | 1110093.88 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2776 | 43399315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 75 | 90 | 78 | 12 | 0 | 0 | 15 | 0 | 198978 | 9604 | 189374 | 198978 | 196874 | 0 | 0 | 0 | 196874 | 196874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-02-01 | QTR3 | 20/21 | 209 | 202254.46 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | -48916 | 0 | 24 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-04 | QTR4 | 21/22 | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94 |  |  | 2 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2778 | 44105715201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 230 | 294 | 294 | 0 | 0 | 0 | 64 | 0 | 4660748 | 65000 | 4595748 | 4665808 | 4696793 | 0 | 0 | 0 | 4696793 | 4795119 | 98326 | 5059 | 51 | 0 | 0 | 12355 | 0 | 0 | 0 | 24208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36563 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-30 | QTR3 | 21/22 | 2021-12-06 | QTR2 | 21/22 | 216 | 4464709.06 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2780 | 43732515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 100 | 116 | 81 | 35 | 0 | 0 | 16 | 0 | 237581 | 13119 | 224462 | 237581 | 222711 | 0 | 0 | 0 | 222711 | 222711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473319074 | ONYX SITE SERVICES LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 209 | 289606.86 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2781 | 44106015201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 377 | 377 | 0 | 0 | 0 | 127 | 0 | 5821573 | 74375 | 5747198 | 5821573 | 5952158 | 0 | 0 | 0 | 5952158 | 5882048 | -70110 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-23 | QTR3 | 21/22 | 2021-10-27 | QTR2 | 21/22 | 214 | 7534069.47 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2786 | 43732315201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 250 | 298 | 229 | 69 | 0 | 0 | 48 | 0 | 5990960 | 72219 | 5918741 | 5990960 | 5941443 | 0 | 0 | 0 | 5941443 | 5882422 | -59022 | 0 | 28 | 0 | 0 | 9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9592 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 208 | 7170016 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2794 | 44112915201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 150 | 283 | 282 | 1 | 0 | 0 | 48 | 85 | 3087746 | 50000 | 3037746 | 3440186 | 3518103 | 0 | 0 | 0 | 3518103 | 3660563 | 142461 | 352440 | 26 | 0 | 64 | 302440 | 0 | 0 | 21 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 370069 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-05-16 | QTR4 | 21/22 | 2021-11-30 | QTR2 | 21/22 | 214 | 3966460.12 |  |  | 21 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2799 | 43584515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 200 | 213 | 163 | 50 | 0 | 0 | 13 | 0 | 584000 | 47584 | 536416 | 584000 | 571789 | 0 | 0 | 0 | 571789 | 571826 | 37 | 0 | 2 | 0 | 0 | 2239 | 0 | 0 | 0 | 17521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20598 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-03-18 | QTR3 | 21/22 | 2021-09-24 | QTR1 | 21/22 | 208 | 883653.52 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2851 | 43916415201 | 2021-08-25 | QTR1 | 21/22 | 1 | 0 | 54 | 80 | 73 | 7 | 0 | 0 | 26 | 0 | 233424 | 15161 | 218263 | 233424 | 220944 | 0 | 0 | 0 | 220944 | 220944 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 | 2022-01-21 | QTR3 | 21/22 | 209 | 403783.51 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9022 | 44531935223 | 2020-04-29 | QTR4 | 19/20 | 2 | 4 | 250 | 290 | 290 | 0 | 0 | 0 | 29 | 11 | 1990220 | 0 | 1990220 | 2080312 | 2092740 | 0 | 0 | 0 | 2092740 | 2092740 | 0 | 90092 | 12 | 0 | 11 | 0 | 0 | 0 | 0 | 40092 | 6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40092 | 6446 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-07-28 | QTR1 | 21/22 | 209 | 1872854.66 |  |  | 11 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20B5 | 43054225201 | 2020-10-14 | QTR2 | 20/21 | 1 | 0 | 200 | 272 | 266 | 6 | 0 | 0 | 51 | 21 | 2358839 | 50000 | 2308839 | 2358839 | 2227074 | 0 | 0 | 0 | 2227074 | 2268054 | 40980 | 0 | 17 | 0 | 3 | 23487 | 0 | 0 | 18 | 8087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 31574 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 | 2022-02-10 | QTR3 | 21/22 | 214 | 1902693.28 |  |  | 21 | 34 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20B6 | 44199825215 | 2020-12-16 | QTR2 | 20/21 | 2 | 0 | 180 | 249 | 249 | 0 | 0 | 0 | 39 | 30 | 2043961 | 50000 | 1993961 | 2043961 | 1982318 | 0 | 0 | 0 | 1982318 | 2079733 | 97415 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-13 | QTR4 | 21/22 | 2022-02-24 | QTR3 | 21/22 | 208 | 2076999.7 |  |  | 30 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C2 | 44105115201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 150 | 158 | 110 | 48 | 0 | 0 | 8 | 0 | 539351 | 31674 | 507677 | 539351 | 482138 | 0 | 0 | 0 | 482138 | 482138 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-06-21 | QTR4 | 20/21 | 208 | 678652.08 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C4 | 44119915201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 240 | 279 | 261 | 18 | 0 | 0 | 39 | 0 | 808267 | 48838 | 759429 | 808267 | 699578 | 0 | 0 | 0 | 699578 | 699578 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 | 2022-02-28 | QTR3 | 21/22 | 208 | 914587.52 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20D9 | 44703115201 | 2020-09-02 | QTR1 | 20/21 | 1 | 2 | 115 | 267 | 265 | 2 | 0 | 0 | 92 | 60 | 394410 | 27902 | 366509 | 571805 | 486787 | 0 | 0 | 0 | 486787 | 486787 | 0 | 177395 | 58 | 0 | 0 | 8890 | 0 | 0 | 60 | 177395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186285 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | QTR2 | 21/22 | 2021-08-02 | QTR1 | 21/22 | 208 | 493957.36 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V69 | 21327275201 | 2017-10-18 | QTR2 | 17/18 | 3 | 12 | 750 | 983 | 983 | 0 | 0 | 0 | 173 | 60 | 16294500 | 150000 | 16144500 | 17291837 | 17466265 | 0 | 1350000 | 1350000 | 18816265 | 17457479 | -1354420 | 997337 | 55 | 0 | 0 | 309118 | 216458 | 0 | 0 | 269830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1070627 | 216458 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-15 | QTR1 | 21/22 | 2020-08-21 | QTR1 | 20/21 | 209 | 18122424.22 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 118 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W84 | 43384215201 | 2017-11-15 | QTR2 | 17/18 | 1 | 1 | 302 | 575 | 575 | 0 | 0 | 0 | 228 | 45 | 1444429 | 50000 | 1394429 | 2840551 | 2999816 | 0 | 0 | 0 | 2999816 | 2999816 | 0 | 1396122 | 103 | 0 | 27 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24691 | 0 | 0 | 18 | 1400122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 45 | 1424814 | 0 | F561918615 | ASTRON GENERAL CONTRACTING COMPANY INC. | N/A | N/A | N/A | N/A | 2021-10-15 | QTR2 | 21/22 | 2019-11-25 | QTR2 | 19/20 | 216 | 1103685.42 |  |  | 27 | 32 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X05 | 44030215201 | 2017-12-13 | QTR2 | 17/18 | 1 | 3 | 485 | 1175 | 1344 | -169 | 169 | 0 | 76 | 614 | 3698384 | 57026 | 3641358 | 3798384 | 3762258 | -475059 | 0 | -475059 | 3287199 | 3287199 | 0 | 100000 | 26 | 0 | 84 | 86047 | 0 | 0 | 6 | 34852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120900 | 0 | F382907623 | THE GUARANTEE COMPANY OF NORTH AMERICA U | N/A | N/A | N/A | N/A | 2022-06-06 | QTR4 | 21/22 | 2021-12-07 | QTR2 | 21/22 | 209 | 5873791.11 | Y | DESIGN/BUILD PROJECT | 90 | 50 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X66 | 43727415201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 500 | 738 | 726 | 12 | 0 | 0 | 140 | 98 | 7944015 | 73483 | 7870532 | 8017498 | 8037111 | 0 | 0 | 0 | 8037111 | 8035623 | -1488 | 73483 | 101 | 0 | 16 | 42391 | 0 | 0 | 16 | 19034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 8993 | 0 | 0 | 0 | 3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 73483 | 0 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2022-05-25 | QTR4 | 21/22 | 2022-02-04 | QTR3 | 21/22 | 209 | 7457547.88 |  |  | 98 | 65 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y24 | 43743715201 | 2020-05-13 | QTR4 | 19/20 | 1 | 1 | 150 | 169 | 145 | 24 | 0 | 0 | 19 | 0 | 1280762 | 50000 | 1230762 | 1204874 | 1079365 | 0 | 0 | 0 | 1079365 | 1079365 | 0 | -75888 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75888 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-08-02 | QTR1 | 21/22 | 2021-03-19 | QTR3 | 20/21 | 208 | 2106516.32 |  |  | 0 | 15 | 0 | 0 | -75888 | 0 |  | DO
02DO | 02 | E2Y79 | 20968315201 | 2019-11-13 | QTR2 | 19/20 | 1 | 1 | 250 | 373 | 373 | 0 | 0 | 0 | 118 | 5 | 4028350 | 50000 | 3978350 | 4078350 | 4286744 | 0 | 0 | 0 | 4286744 | 4286650 | -94 | 50000 | 30 | 0 | 2 | 23210 | 0 | 11 | 4 | 42669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829 | 0 | 0 | 0 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 6 | 87620 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 208 | 3704637.21 |  |  | 5 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y81 | 43197915201 | 2019-10-16 | QTR2 | 19/20 | 1 | 1 | 390 | 546 | 546 | 0 | 0 | 0 | 129 | 27 | 2424817 | 50000 | 2374817 | 2497783 | 2495432 | 0 | 0 | 0 | 2495432 | 2495432 | 0 | 72966 | 82 | 0 | 50 | 69881 | 69881 | 0 | -23 | 3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 72966 | 69881 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 | 2021-09-21 | QTR1 | 21/22 | 208 | 3472664.24 |  |  | -23 | 47 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y84 | 43807515201 | 2019-11-13 | QTR2 | 19/20 | 3 | 1 | 160 | 223 | 223 | 0 | 0 | 0 | 63 | 0 | 1543447 | 50000 | 1493447 | 1543447 | 1581148 | 0 | 0 | 0 | 1581148 | 1565351 | -15797 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-20 | QTR2 | 21/22 | 2020-10-23 | QTR2 | 20/21 | 214 | 1817083.25 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y85 | 43865025201 | 2019-11-13 | QTR2 | 19/20 | 2 | 0 | 300 | 385 | 383 | 2 | 0 | 0 | 85 | 0 | 3884320 | 50000 | 3834320 | 3884320 | 3769800 | 0 | 0 | 0 | 3769800 | 3768427 | -1374 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15314 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-07-30 | QTR1 | 21/22 | 2021-03-31 | QTR3 | 20/21 | 209 | 4380188.78 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z24 | 44199735216 | 2020-02-19 | QTR3 | 19/20 | 1 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1624143 | 50000 | 1574143 | 1624143 | 1547862 | 0 | 0 | 0 | 1547862 | 1547862 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-07-02 | QTR1 | 21/22 | 2021-02-11 | QTR3 | 20/21 | 209 | 1701418.99 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z36 | 43930315201 | 2019-12-18 | QTR2 | 19/20 | 1 | 3 | 90 | 236 | 236 | 0 | 0 | 0 | 57 | 89 | 363396 | 16952 | 346444 | 445802 | 448483 | 0 | 0 | 0 | 448483 | 448483 | 0 | 82407 | 16 | 21 | 89 | 82407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 89 | 82407 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 356089.27 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z39 | 43122445201 | 2020-04-15 | QTR4 | 19/20 | 1 | 0 | 440 | 444 | 137 | 307 | 0 | 0 | 4 | 0 | 788792 | 50000 | 738792 | 788792 | 738086 | 0 | 0 | 0 | 738086 | 738086 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-09-08 | QTR1 | 21/22 | 2021-06-04 | QTR4 | 20/21 | 208 | 1315899.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z50 | 42848915201 | 2020-03-18 | QTR3 | 19/20 | 1 | 2 | 310 | 356 | 240 | 116 | 0 | 0 | 46 | 0 | 1635960 | 50000 | 1585960 | 1685775 | 1669775 | 0 | 0 | 0 | 1669775 | 1669775 | 0 | 49816 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99283 | 0 | F030467673 | EXTREME SANDBLASTING & PAINTING | N/A | N/A | N/A | N/A | 2021-07-07 | QTR1 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 208 | 1762746.86 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z51 | 43384115201 | 2020-04-15 | QTR4 | 19/20 | 1 | 1 | 350 | 442 | 436 | 6 | 0 | 0 | 79 | 13 | 2662544 | 50000 | 2612544 | 2666491 | 1959926 | 0 | 0 | 0 | 1959926 | 1959926 | 0 | 3947 | 33 | 0 | 0 | 29210 | 0 | 0 | 13 | 3947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 33157 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 | 2021-12-08 | QTR2 | 21/22 | 208 | 3385087.42 |  |  | 13 | 46 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z52 | 43204815201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 200 | 317 | 315 | 2 | 0 | 0 | 96 | 21 | 1206264 | 50000 | 1156264 | 1206264 | 1198471 | 0 | 0 | 0 | 1198471 | 1198471 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 216 | 1268308.03 |  |  | 21 | 48 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z56 | 43807915201 | 2020-05-13 | QTR4 | 19/20 | 1 | 0 | 100 | 152 | 152 | 0 | 0 | 0 | 52 | 0 | 744154 | 40931 | 703223 | 744154 | 696705 | 0 | 0 | 0 | 696705 | 696705 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204553050 | HICKS SEAL COATING & STRIPING L | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-11 | QTR3 | 20/21 | 214 | 797485.71 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3359 | 21860315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 6 | 1390 | 1975 | 1972 | 3 | 0 | 0 | 554 | 31 | 48912840 | 150000 | 48762840 | 49557879 | 51455652 | -1500 | 0 | -1500 | 51454152 | 52944876 | 1630015 | 645040 | 374 | 37 | 4 | 203820 | 0 | 0 | 27 | 296208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 55749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 31 | 555777 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-04-12 | QTR4 | 21/22 | 2022-02-04 | QTR3 | 21/22 | 308 | 41351319.57 |  |  | 31 | 140 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3533 | 21797635201 | 2015-05-20 | QTR4 | 14/15 | 2 | 35 | 970 | 1882 | 1882 | 0 | 0 | 0 | 531 | 381 | 67999204 | 150000 | 67849204 | 73183986 | 72810755 | 0 | 0 | 0 | 72810755 | 72504196 | -146921 | 5184782 | 356 | 0 | 0 | 19580 | 0 | 0 | 20 | 617542 | 34940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62700 | 0 | 0 | 77 | 1308271 | 134897 | 0 | 0 | 713312 | 5395 | 0 | 0 | 0 | 0 | 0 | 6 | 355429 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 4237789 | 4237789 | 0 | 0 | 0 | 0 | 0 | 381 | 5100342 | 4413021 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-04-05 | QTR4 | 21/22 | 2021-03-18 | QTR3 | 20/21 | 306 | 77505595.07 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 175 | 0 | 0 | -2214282 | 0 |  | CO
03CO | 03 | T3632 | 43581515201 | 2019-10-30 | QTR2 | 19/20 | 1 | 5 | 365 | 642 | 641 | 1 | 0 | 0 | 262 | 15 | 4962076 | 50000 | 4912076 | 5040837 | 5106121 | 0 | 0 | 0 | 5106121 | 5104120 | -2001 | 78760 | 171 | 0 | 15 | 72486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 41435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 15 | 113922 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 | 2021-10-25 | QTR2 | 21/22 | 314 | 4401368.62 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3640 | 43290925201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 60 | 75 | 75 | 0 | 0 | 0 | 15 | 0 | 720412 | 24077 | 696335 | 720412 | 691249 | 0 | 0 | 0 | 691249 | 691249 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-20 | QTR1 | 21/22 | 2020-06-29 | QTR4 | 19/20 | 314 | 499996.54 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3646 | 22049585201 | 2018-03-28 | QTR3 | 17/18 | 2 | 5 | 850 | 1118 | 1089 | 29 | 0 | 0 | 243 | 25 | 15646589 | 150000 | 15496589 | 15902989 | 15169686 | 0 | 0 | 0 | 15169686 | 15142928 | 28314 | 256400 | 170 | 0 | 0 | 28644 | 0 | 0 | 25 | 172683 | 73650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 201327 | 73650 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 321 | 21200000 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3660 | 40619435201 | 2018-05-23 | QTR4 | 17/18 | 1 | 6 | 750 | 1143 | 1143 | 0 | 0 | 0 | 371 | 22 | 8456503 | 83020 | 8373483 | 8769565 | 8750489 | 0 | 0 | 0 | 8750489 | 8742318 | -8170 | 313062 | 113 | 0 | 22 | 323879 | 180859 | 0 | 0 | 8846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 332725 | 180859 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 | 2021-12-21 | QTR2 | 21/22 | 308 | 7797092.45 |  |  | 0 | 113 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3682 | 43812915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 75 | 81 | 56 | 25 | 0 | 0 | 6 | 0 | 346966 | 15090 | 331877 | 346966 | 335754 | 0 | 0 | 0 | 335754 | 335754 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-13 | QTR2 | 21/22 | 2021-08-18 | QTR1 | 21/22 | 313 | 319059.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3689 | 21876425201 | 2019-12-04 | QTR2 | 19/20 | 1 | 5 | 410 | 588 | 586 | 2 | 0 | 0 | 144 | 34 | 3948246 | 50000 | 3898246 | 4424349 | 4230338 | 0 | 0 | 0 | 4230338 | 4232949 | 2611 | 476103 | 106 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 476103 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2022-05-02 | QTR4 | 21/22 | 2021-11-20 | QTR2 | 21/22 | 321 | 3709288.8 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3692 | 43774615201 | 2019-03-27 | QTR3 | 18/19 | 3 | 17 | 420 | 847 | 843 | 4 | 0 | 0 | 420 | 7 | 8791950 | 109575 | 8682375 | 9177543 | 9191379 | 0 | 0 | 0 | 9191379 | 9092805 | -86540 | 385593 | 320 | 0 | 3 | 71605 | 0 | 0 | 4 | 120253 | 16635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 429398 | 16635 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-10-01 | QTR2 | 21/22 | 308 | 10784326.93 |  |  | 6 | 100 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3699 | 43228415201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 235 | 441 | 441 | 0 | 0 | 0 | 206 | 0 | 2694142 | 0 | 2694142 | 2663955 | 2668318 | 0 | 0 | 0 | 2668318 | 2665830 | -2489 | -30187 | 126 | 15 | 0 | -30187 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | -30187 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-09-29 | QTR1 | 21/22 | 2021-05-11 | QTR4 | 20/21 | 314 | 2634439.8 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3700 | 43811115201 | 2020-08-26 | QTR1 | 20/21 | 4 | 0 | 180 | 236 | 231 | 5 | 0 | 0 | 56 | 0 | 678788 | 33282 | 645507 | 678788 | 592391 | 0 | 0 | 0 | 592391 | 592857 | 466 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593534997 | BCL CIVIL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 314 | 960134.24 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3717 | 43720215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 150 | 203 | 202 | 1 | 0 | 0 | 50 | 3 | 770613 | 0 | 770613 | 797858 | 802448 | 0 | 0 | 0 | 802448 | 802695 | 247 | 27245 | 34 | 0 | 3 | 27245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27245 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-05-04 | QTR4 | 20/21 | 313 | 750108.46 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3723 | 43972115201 | 2020-01-29 | QTR3 | 19/20 | 2 | 1 | 180 | 323 | 323 | 0 | 0 | 0 | 135 | 8 | 4514950 | 52853 | 4462097 | 4573579 | 4689305 | -24500 | 0 | -24500 | 4664805 | 4517927 | -146878 | 58629 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2567 | 0 | 0 | 1 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 58629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 63295 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 308 | 5332164.83 |  |  | 2 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3725 | 43627315201 | 2020-02-26 | QTR3 | 19/20 | 1 | 4 | 255 | 618 | 618 | 0 | 0 | 0 | 325 | 38 | 6407925 | 72715 | 6335210 | 6454693 | 6883968 | 0 | 0 | 0 | 6883968 | 6913504 | 29535 | 46768 | 50 | 0 | 0 | 1320 | 0 | 205 | 38 | 77843 | 31122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 38 | 79163 | 31122 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-05 | QTR4 | 21/22 | 2022-01-19 | QTR3 | 21/22 | 308 | 7243439.74 |  |  | 4 | 70 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3729 | 43972715201 | 2020-04-29 | QTR4 | 19/20 | 2 | 1 | 220 | 314 | 314 | 0 | 0 | 0 | 92 | 2 | 7592042 | 95077 | 7496965 | 7796389 | 8177990 | 0 | 0 | 0 | 8177990 | 8127837 | -50153 | 204347 | 63 | 2 | 2 | 8460 | 0 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 204347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 219939 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2021-05-22 | QTR4 | 20/21 | 321 | 9289555.85 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3730 | 43972515201 | 2019-09-25 | QTR1 | 19/20 | 1 | 0 | 300 | 695 | 694 | 1 | 0 | 0 | 373 | 22 | 13201615 | 150000 | 13051615 | 13201615 | 14101673 | 0 | 0 | 0 | 14101673 | 14032884 | -68789 | 0 | 292 | 0 | 0 | 0 | 0 | 0 | 15 | 21415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 24085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 45500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-19 | QTR4 | 21/22 | 2021-11-29 | QTR2 | 21/22 | 314 | 14987297.94 |  |  | 22 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3738 | 44173815201 | 2020-05-20 | QTR4 | 19/20 | 2 | 3 | 180 | 271 | 271 | 0 | 0 | 0 | 91 | 0 | 1336283 | 50150 | 1286133 | 1373486 | 1300986 | 0 | 0 | 0 | 1300986 | 1302036 | 1050 | 37203 | 43 | 0 | 0 | 0 | 0 | 14 | 0 | 34377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 39420 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-11-08 | QTR2 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 308 | 1328096.86 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3744 | 43972415201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 380 | 380 | 0 | 0 | 0 | 200 | 0 | 5906321 | 55841 | 5850481 | 5906321 | 6014134 | 0 | 0 | 0 | 6014134 | 5961005 | -53128 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-21 | QTR1 | 21/22 | 2021-04-30 | QTR4 | 20/21 | 314 | 5368995.9 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3745 | 43972915201 | 2020-02-26 | QTR3 | 19/20 | 2 | 3 | 365 | 513 | 512 | 1 | 0 | 0 | 135 | 13 | 7352550 | 86750 | 7265800 | 7448821 | 7636800 | 0 | 0 | 0 | 7636800 | 7674029 | 37229 | 96271 | 76 | 0 | 13 | 91427 | 0 | 0 | 0 | 29526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 13 | 139443 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-16 | QTR3 | 21/22 | 2021-09-30 | QTR1 | 21/22 | 321 | 8840050.49 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3746 | 44154315201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 150 | 182 | 164 | 18 | 0 | 0 | 32 | 0 | 4283738 | 56162 | 4227576 | 4283738 | 4494319 | 0 | 0 | 0 | 4494319 | 4570359 | 76040 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-23 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 321 | 5641395.13 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3749 | 44173215201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 90 | 174 | 176 | -2 | 2 | 0 | 77 | 7 | 755462 | 38702 | 716760 | 778131 | 692739 | 0 | 0 | 0 | 692739 | 692739 | 0 | 22669 | 39 | 0 | 7 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22669 | 12169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 27869 | 12169 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 314 | 824730.61 |  |  | 7 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3751 | 43775325201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 335 | 445 | 445 | 0 | 0 | 0 | 110 | 0 | 2569909 | 50000 | 2519909 | 2569909 | 2490758 | 0 | 0 | 0 | 2490758 | 2498656 | 7898 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22902 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 | 2021-08-24 | QTR1 | 21/22 | 313 | 2572447.1 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3760 | 44154015201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 150 | 228 | 220 | 8 | 0 | 0 | 78 | 0 | 3001621 | 50000 | 2951621 | 3001621 | 2905181 | 0 | 0 | 0 | 2905181 | 2997834 | 92653 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-24 | QTR4 | 21/22 | 2022-01-06 | QTR3 | 21/22 | 321 | 2841104.56 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3763 | 43661515201 | 2020-06-10 | QTR4 | 19/20 | 1 | 1 | 365 | 435 | 433 | 2 | 0 | 0 | 70 | 0 | 4894168 | 0 | 4894168 | 4903128 | 5058997 | 0 | 0 | 0 | 5058997 | 5067842 | 8845 | 8960 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2022-01-18 | QTR3 | 21/22 | 2021-11-01 | QTR2 | 21/22 | 321 | 5019527.85 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3770 | 44134715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 1 | 75 | 98 | 89 | 9 | 0 | 0 | 23 | 0 | 224915 | 0 | 224915 | 224915 | 229832 | 0 | 0 | 0 | 229832 | 229832 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-11-24 | QTR2 | 21/22 | 2021-09-03 | QTR1 | 21/22 | 321 | 248070.75 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q53 | 44009615201 | 2017-07-20 | QTR1 | 17/18 | 1 | 4 | 380 | 979 | 1139 | -160 | 160 | 0 | 587 | 12 | 4412093 | 50000 | 4362093 | 4461209 | 4457747 | -449760 | 0 | -449760 | 4007987 | 3986724 | 0 | 49116 | 256 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | F631075391 | CONTACT NETWORK LLC | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-10-30 | QTR2 | 20/21 | 306 | 4688434.5 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 0 | 90 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S42 | 42187345201 | 2019-09-12 | QTR1 | 19/20 | 1 | 1 | 150 | 475 | 475 | 0 | 0 | 0 | 236 | 89 | 2507433 | 50000 | 2457433 | 2507433 | 2457433 | 0 | 0 | 0 | 2457433 | 2457433 | 0 | 0 | 213 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2021-07-21 | QTR1 | 21/22 | 2021-05-13 | QTR4 | 20/21 | 313 | 2985049 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S73 | 4453811H201 | 2019-12-12 | QTR2 | 19/20 | 5 | 2 | 150 | 156 | 85 | 71 | 0 | 0 | 6 | 0 | 174645 | 0 | 174645 | 174645 | 174645 | 0 | 0 | 0 | 174645 | 0 | -174645 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-07-27 | QTR1 | 20/21 | 321 | 212648.33 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T18 | 42282325201 | 2020-12-17 | QTR2 | 20/21 | 1 | 0 | 45 | 46 | 32 | 14 | 0 | 0 | 1 | 0 | 145277 | 9380 | 135897 | 145277 | 129137 | 0 | 0 | 0 | 129137 | 129137 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-01-05 | QTR3 | 21/22 | 2021-04-23 | QTR4 | 20/21 | 321 | 213559.46 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T25 | 44154615201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 120 | 165 | 164 | 1 | 0 | 0 | 45 | 0 | 2058102 | 50000 | 2008102 | 2058102 | 2116209 | 0 | 0 | 0 | 2116209 | 2113685 | -2525 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3638 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-08-24 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 321 | 2347515.39 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T27 | 40571925201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 198 | 111 | 87 | 0 | 0 | 18 | 0 | 673158 | 40026 | 633132 | 673158 | 632738 | 0 | 0 | 0 | 632738 | 632738 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 314 | 803647.79 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T35 | 44291315201 | 2020-06-11 | QTR4 | 19/20 | 1 | 3 | 90 | 146 | 146 | 0 | 0 | 0 | 49 | 7 | 1454221 | 50000 | 1404221 | 1547027 | 1426180 | 0 | 25000 | 25000 | 1451180 | 1426180 | -25000 | 92806 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 92806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 92806 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 308 | 1274993.94 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T51 | 44154215201 | 2021-01-14 | QTR3 | 20/21 | 1 | 1 | 150 | 235 | 235 | 0 | 0 | 0 | 85 | 0 | 1940669 | 50000 | 1890669 | 1921236 | 1976977 | 0 | 0 | 0 | 1976977 | 2038310 | 61333 | -19433 | 67 | 0 | 0 | -19433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9361 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-05-02 | QTR4 | 21/22 | 2021-12-16 | QTR2 | 21/22 | 308 | 1982216.25 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T58 | 43815415201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 305 | 305 | 0 | 0 | 0 | 201 | 14 | 883399 | 32152 | 851247 | 898220 | 890748 | 0 | 0 | 0 | 890748 | 890748 | 0 | 14821 | 35 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 14 | 14821 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2021-10-21 | QTR2 | 21/22 | 2021-08-09 | QTR1 | 21/22 | 313 | 673070.45 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T66 | 4450184H201 | 2020-03-12 | QTR3 | 19/20 | 1 | 1 | 90 | 99 | 86 | 13 | 0 | 0 | 9 | 0 | 232082 | 0 | 232082 | 232082 | 225968 | 0 | 0 | 0 | 225968 | 0 | -225968 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200531542 | PAUL PATRICK ELECTRIC INC | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2020-10-20 | QTR2 | 20/21 | 314 | 246220 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T96 | 4453581G201 | 2020-08-13 | QTR1 | 20/21 | 2 | 1 | 90 | 163 | 162 | 1 | 0 | 0 | 33 | 40 | 782169 | 0 | 782169 | 1364937 | 1338192 | 0 | 0 | 0 | 1338192 | 0 | -1338192 | 582769 | 17 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 582769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 40 | 582769 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-11-22 | QTR2 | 21/22 | 2021-05-12 | QTR4 | 20/21 | 313 | 1084959.1 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U12 | 44365725201 | 2021-07-08 | QTR1 | 21/22 | 1 | 0 | 100 | 148 | 147 | 1 | 0 | 0 | 48 | 0 | 2742031 | 50000 | 2692031 | 2742031 | 2766138 | 0 | 0 | 0 | 2766138 | 2770405 | 4267 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-07 | QTR4 | 21/22 | 2022-03-02 | QTR3 | 21/22 | 314 | 2471807.29 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U25 | 44364215201 | 2021-07-08 | QTR1 | 21/22 | 1 | 0 | 160 | 192 | 151 | 41 | 0 | 0 | 32 | 0 | 2814688 | 50000 | 2764688 | 2814688 | 2846250 | 0 | 0 | 0 | 2846250 | 2857872 | 11622 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-15 | QTR4 | 21/22 | 2022-03-04 | QTR3 | 21/22 | 321 | 4496574.19 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U27 | 44154515201 | 2020-12-17 | QTR2 | 20/21 | 2 | 0 | 180 | 222 | 221 | 1 | 0 | 0 | 42 | 0 | 1641103 | 50000 | 1591103 | 1641103 | 1553101 | 0 | 0 | 0 | 1553101 | 1614039 | 60937 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2022-03-07 | QTR3 | 21/22 | 2021-11-01 | QTR2 | 21/22 | 321 | 2039669.94 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U34 | 44718815201 | 2021-11-10 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 46 | 14 | 0 | 0 | 0 | 0 | 294449 | 16530 | 277920 | 294449 | 275309 | 0 | 0 | 0 | 275309 | 275309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-06-07 | QTR4 | 21/22 | 2022-04-11 | QTR4 | 21/22 | 313 | 345934.65 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4471 | 43472215201 | 2018-04-25 | QTR4 | 17/18 | 4 | 16 | 379 | 803 | 790 | 13 | 0 | 0 | 230 | 194 | 5223993 | 55803 | 5168190 | 5569665 | 5480351 | -68940 | 0 | -68940 | 5411411 | 5390271 | -5522 | 345672 | 158 | 0 | 0 | 70013 | 0 | 6 | 31 | 115548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42241 | 0 | 0 | 6 | 32074 | 25640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48303 | 48303 | 18 | 42 | 81001 | 74912 | 0 | 0 | 0 | 0 | 24 | 79 | 342551 | 148855 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-04-08 | QTR4 | 20/21 | 409 | 5507060.32 |  |  | 7 | 48 | 0 | 0 | -46629 | 0 |  | CO
04CO | 04 | T4476 | 43515815201 | 2018-06-13 | QTR4 | 17/18 | 3 | 4 | 582 | 825 | 825 | 0 | 0 | 0 | 183 | 60 | 7524128 | 71928 | 7452200 | 7782657 | 7606665 | 0 | 0 | 0 | 7606665 | 7546955 | -47141 | 258528 | 91 | 0 | 0 | 12809 | 0 | 0 | 0 | 107865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34366 | 34366 | 0 | 60 | 107988 | 107988 | 0 | 0 | 0 | 0 | 0 | 60 | 263028 | 142354 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2022-01-03 | QTR3 | 21/22 | 2021-01-18 | QTR3 | 20/21 | 409 | 7189789.75 |  |  | 0 | 92 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4488 | 43630415201 | 2019-08-28 | QTR1 | 19/20 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 552418 | 13640 | 538778 | 602867 | 592608 | 0 | 0 | 0 | 592608 | 592529 | -79 | 50449 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 26098 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55569 | 22219 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-28 | QTR1 | 21/22 | 2020-10-09 | QTR2 | 20/21 | 409 | 285674.52 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4494 | 43630715201 | 2019-04-24 | QTR4 | 18/19 | 3 | 7 | 410 | 518 | 518 | 0 | 0 | 0 | 94 | 14 | 5685198 | 52736 | 5632462 | 5923341 | 5849802 | 0 | 0 | 0 | 5849802 | 5808702 | -41100 | 238143 | 56 | 0 | 0 | 62867 | 0 | 0 | 0 | 154196 | 90401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7756 | 7756 | 0 | 0 | 0 | 0 | 0 | 14 | 226261 | 98158 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 409 | 5359258.83 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4497 | 43783615201 | 2019-02-27 | QTR3 | 18/19 | 2 | 10 | 501 | 768 | 757 | 11 | 0 | 0 | 156 | 111 | 7969825 | 89478 | 7880348 | 9671721 | 9618307 | 0 | 0 | 0 | 9618307 | 9568488 | -38478 | 1701896 | 99 | 0 | 111 | 1524927 | 1339455 | 0 | 0 | 207660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1733522 | 1339455 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-07-19 | QTR1 | 21/22 | 409 | 9083314.34 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4504 | 43783815201 | 2019-05-22 | QTR4 | 18/19 | 1 | 3 | 440 | 619 | 612 | 7 | 0 | 0 | 154 | 25 | 8446061 | 84606 | 8361454 | 9282205 | 9225023 | 0 | 0 | 0 | 9225023 | 9088376 | -136647 | 836144 | 110 | 0 | 0 | 785348 | 0 | 0 | 25 | 180556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -121762 | 0 | 0 | 0 | 54431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 898572 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-05-17 | QTR4 | 20/21 | 408 | 9046599.29 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4505 | 43668515201 | 2019-03-27 | QTR3 | 18/19 | 3 | 2 | 433 | 533 | 533 | 0 | 0 | 0 | 94 | 6 | 7195336 | 71972 | 7123364 | 7097482 | 6908157 | 0 | 0 | 0 | 6908157 | 6847745 | -58724 | -97855 | 61 | 0 | 6 | 22633 | 0 | 0 | 0 | 18580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -58328 | 0 | F650012669 | CONDOTTE AMERICA LLC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 7395888.17 |  |  | 6 | 33 | 0 | 0 | -99541 | 0 |  | CO
04CO | 04 | T4509 | 43177055201 | 2019-04-24 | QTR4 | 18/19 | 4 | 3 | 389 | 514 | 512 | 2 | 0 | 0 | 125 | 0 | 3049775 | 50000 | 2999775 | 3212084 | 3151909 | 0 | 0 | 0 | 3151909 | 3123371 | -17714 | 162310 | 92 | 0 | 0 | 2010 | 0 | 0 | 0 | 154906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156916 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2020-12-03 | QTR2 | 20/21 | 412 | 2802936.17 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4511 | 43469015201 | 2019-04-24 | QTR4 | 18/19 | 1 | 1 | 439 | 543 | 421 | 122 | 0 | 0 | 104 | 0 | 2099355 | 50000 | 2049355 | 2040900 | 1905910 | 0 | 0 | 0 | 1905910 | 1888675 | -17236 | -58454 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49737 | 0 | F591454861 | ACOSTA TRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-27 | QTR1 | 21/22 | 2021-04-05 | QTR4 | 20/21 | 412 | 2266163.2 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4512 | 44007715201 | 2019-04-24 | QTR4 | 18/19 | 4 | 1 | 498 | 864 | 892 | -28 | 28 | 0 | 55 | 311 | 1450367 | 50000 | 1400367 | 1450367 | 1167077 | -139860 | 0 | -139860 | 1027217 | 1108655 | 81438 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | Z31-0501234 | GREAT AMERICAN INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2022-06-14 | QTR4 | 21/22 | 2022-05-26 | QTR4 | 21/22 | 412 | 1609511.16 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4519 | 43469715201 | 2019-05-22 | QTR4 | 18/19 | 2 | 2 | 677 | 987 | 987 | 0 | 0 | 0 | 310 | 0 | 4993117 | 59112 | 4934005 | 5545786 | 5542522 | 0 | 0 | 0 | 5542522 | 5530113 | -7312 | 552669 | 247 | 0 | 0 | -4497 | 0 | 0 | 0 | 552069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547573 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-05-31 | QTR4 | 21/22 | 2022-04-07 | QTR4 | 21/22 | 412 | 5587127.63 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4521 | 43760515201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 160 | 246 | 244 | 2 | 0 | 0 | 86 | 0 | 737736 | 38647 | 699089 | 737736 | 679527 | 0 | 0 | 0 | 679527 | 679527 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 16795 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-03-22 | QTR3 | 21/22 | 2021-12-22 | QTR2 | 21/22 | 412 | 798445.57 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4523 | 43469515201 | 2019-08-28 | QTR1 | 19/20 | 1 | 3 | 367 | 479 | 478 | 1 | 0 | 0 | 102 | 10 | 8207877 | 88188 | 8119689 | 8281895 | 8003190 | 0 | 0 | 0 | 8003190 | 7894972 | -108218 | 74017 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28976 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 179816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150840 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-08-19 | QTR1 | 21/22 | 2021-04-27 | QTR4 | 20/21 | 412 | 8969820.95 |  |  | 10 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4525 | 42956955201 | 2019-10-30 | QTR2 | 19/20 | 2 | 6 | 621 | 777 | 775 | 2 | 0 | 0 | 116 | 40 | 3469054 | 50000 | 3419054 | 3785520 | 3699667 | 0 | 0 | 0 | 3699667 | 3693815 | -5852 | 316466 | 66 | 0 | 0 | 1783 | 0 | 0 | 0 | 273550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 51300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 326632 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-05-18 | QTR4 | 21/22 | 2022-04-01 | QTR4 | 21/22 | 412 | 3402492.11 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4528 | 43696715201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 100 | 105 | 105 | 0 | 0 | 0 | 5 | 0 | 547645 | 23267 | 524378 | 547645 | 476343 | 0 | 0 | 0 | 476343 | 476343 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-06-16 | QTR4 | 20/21 | 408 | 487570.3 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4530 | 43592515201 | 2019-12-04 | QTR2 | 19/20 | 1 | 2 | 388 | 469 | 456 | 13 | 0 | 0 | 81 | 0 | 4642816 | 50000 | 4592816 | 4682420 | 4650889 | 0 | 0 | 0 | 4650889 | 4619922 | -30966 | 39603 | 54 | 0 | 0 | 28246 | 0 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59811 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-10-27 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 412 | 4777019.03 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4538 | 44138115201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 180 | 278 | 278 | 0 | 0 | 0 | 98 | 0 | 589517 | 23421 | 566096 | 589517 | 585765 | 0 | 0 | 0 | 585765 | 586015 | 250 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12855 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 412 | 492570.89 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4542 | 43984215201 | 2020-02-26 | QTR3 | 19/20 | 3 | 4 | 536 | 613 | 608 | 5 | 0 | 0 | 81 | -4 | 21806360 | 150000 | 21656360 | 21667458 | 20680425 | 3782 | 0 | 3782 | 20684206 | 20634573 | -36266 | -138902 | 37 | 0 | 0 | -179532 | 0 | 0 | 0 | 221401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -137070 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 | 2022-01-10 | QTR3 | 21/22 | 409 | 28727824.18 |  |  | 0 | 44 | 0 | -4 | -184535 | 0 |  | CO
04CO | 04 | T4543 | 43915915201 | 2020-03-25 | QTR3 | 19/20 | 1 | 0 | 199 | 242 | 176 | 66 | 0 | 0 | 43 | 0 | 689567 | 28623 | 660944 | 689567 | 649805 | 0 | 0 | 0 | 649805 | 650042 | 237 | 0 | 25 | 0 | 0 | 1476 | 0 | 0 | 0 | 1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 412 | 603405.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4553 | 43840215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 260 | 277 | 214 | 63 | 0 | 0 | 17 | 0 | 432944 | 25085 | 407859 | 432944 | 392014 | 0 | 0 | 0 | 392014 | 392107 | 93 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-12-06 | QTR2 | 21/22 | 2021-08-12 | QTR1 | 21/22 | 409 | 514165.46 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4555 | 43990915201 | 2020-09-30 | QTR1 | 20/21 | 1 | 0 | 128 | 152 | 148 | 4 | 0 | 0 | 24 | 0 | 441982 | 24322 | 417660 | 441982 | 407189 | 0 | 0 | 0 | 407189 | 407189 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-10-06 | QTR2 | 21/22 | 412 | 501234.56 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4556 | 43991015201 | 2020-11-18 | QTR2 | 20/21 | 3 | 1 | 146 | 231 | 231 | 0 | 0 | 0 | 63 | 22 | 2687973 | 50000 | 2637973 | 2705163 | 2740129 | 0 | 0 | 0 | 2740129 | 2844345 | 104217 | 17190 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 26851 | 10090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15508 | 0 | 0 | 0 | 4858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 47217 | 10090 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2022-05-23 | QTR4 | 21/22 | 2022-03-15 | QTR3 | 21/22 | 412 | 3230256.06 |  |  | 22 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4574 | 44179515201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 222 | 246 | 213 | 33 | 0 | 0 | 24 | 0 | 622222 | 31098 | 591125 | 622222 | 556248 | 0 | 0 | 0 | 556248 | 556291 | 43 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-06-20 | QTR4 | 21/22 | 2022-05-18 | QTR4 | 21/22 | 412 | 654229.43 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T51 | 43785115201 | 2019-02-01 | QTR3 | 18/19 | 2 | 8 | 524 | 733 | 733 | 0 | 0 | 0 | 158 | 51 | 6476041 | 50000 | 6426041 | 6901248 | 6999986 | 0 | 0 | 0 | 6999986 | 6950609 | -10152 | 425207 | 126 | 0 | 10 | 116335 | 0 | 0 | 0 | 13376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 280242 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 421482 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-04-04 | QTR4 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 412 | 6413384.4 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T80 | 43524515201 | 2020-03-11 | QTR3 | 19/20 | 1 | 0 | 447 | 612 | 612 | 0 | 0 | 0 | 165 | 0 | 6403403 | 65499 | 6337904 | 6403403 | 6376174 | 0 | 0 | 0 | 6376174 | 6376174 | 0 | 0 | 49 | 0 | 0 | 15582 | 0 | 65 | 0 | 28688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 44270 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-11 | QTR4 | 21/22 | 2022-01-19 | QTR3 | 21/22 | 408 | 6290935.81 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 51 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4T83 | 42268145201 | 2020-05-01 | QTR4 | 19/20 | 1 | 0 | 240 | 375 | 375 | 0 | 0 | 0 | 116 | 19 | 2027817 | 50000 | 1977817 | 2027817 | 1963518 | 0 | 0 | 0 | 1963518 | 1968273 | 4756 | 0 | 91 | 0 | 0 | 14875 | 0 | 0 | 19 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 40339 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2022-01-27 | QTR3 | 21/22 | 2021-09-01 | QTR1 | 21/22 | 408 | 2656948.48 |  |  | 19 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U24 | 43984115201 | 2020-03-06 | QTR3 | 19/20 | 2 | 1 | 245 | 289 | 289 | 0 | 0 | 0 | 44 | 0 | 1238848 | 50000 | 1188848 | 1238449 | 1196529 | 0 | 0 | 0 | 1196529 | 1196625 | 95 | -399 | 22 | 0 | 0 | 1940 | 0 | 0 | 0 | 15685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23607 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 409 | 1271431.08 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U33 | 43804215201 | 2020-04-03 | QTR4 | 19/20 | 3 | 2 | 390 | 606 | 587 | 19 | 0 | 0 | 200 | 16 | 6709662 | 72972 | 6636690 | 6719050 | 6438347 | 0 | 0 | 0 | 6438347 | 6383292 | -45666 | 9389 | 123 | 0 | 0 | 0 | 0 | 29 | 0 | 15137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 17213 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-10 | QTR4 | 21/22 | 2022-02-17 | QTR3 | 21/22 | 408 | 7407886.85 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U47 | 44147315201 | 2021-04-02 | QTR4 | 20/21 | 1 | 0 | 168 | 194 | 107 | 87 | 0 | 0 | 26 | 0 | 1068289 | 50000 | 1018289 | 1068289 | 977728 | 0 | 0 | 0 | 977728 | 977728 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-05-05 | QTR4 | 21/22 | 2022-02-10 | QTR3 | 21/22 | 412 | 1267517.98 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U54 | 44330915201 | 2020-08-07 | QTR1 | 20/21 | 2 | 1 | 128 | 162 | 162 | 0 | 0 | 0 | 20 | 14 | 1153286 | 50000 | 1103286 | 1168772 | 976003 | 0 | 100000 | 100000 | 1076003 | 980548 | -95454 | 15486 | 15 | 0 | 0 | 3787 | 0 | 0 | 14 | 21916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25704 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-24 | QTR1 | 21/22 | 2021-07-15 | QTR1 | 21/22 | 412 | 1242928 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U72 | 44162915201 | 2021-01-08 | QTR3 | 20/21 | 1 | 0 | 144 | 178 | 178 | 0 | 0 | 0 | 34 | 0 | 893625 | 50000 | 843625 | 893625 | 846410 | 0 | 0 | 0 | 846410 | 849948 | 3538 | 0 | 25 | 0 | 0 | 5931 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26097 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-31 | QTR3 | 21/22 | 2021-09-19 | QTR1 | 21/22 | 412 | 1052584.82 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U74 | 44162815201 | 2021-03-05 | QTR3 | 20/21 | 3 | 1 | 153 | 186 | 183 | 3 | 0 | 0 | 33 | 0 | 1190833 | 50000 | 1140833 | 1189722 | 1098149 | 0 | 0 | 0 | 1098149 | 1101304 | 3155 | -1111 | 12 | 0 | 0 | -1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1111 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-25 | QTR3 | 21/22 | 2022-01-17 | QTR3 | 21/22 | 412 | 1310702.75 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5538 | 23949635201 | 2017-08-30 | QTR1 | 17/18 | 4 | 10 | 765 | 1192 | 1192 | 0 | 0 | 0 | 321 | 106 | 27752000 | 150000 | 27602000 | 28126749 | 28782547 | -7304 | 0 | -7304 | 28775243 | 29169971 | 430838 | 374749 | 219 | 0 | 0 | 149689 | 0 | 0 | 40 | 173446 | 6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137210 | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 460344 | 12749 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-04-13 | QTR4 | 20/21 | 509 | 28403237.3 |  |  | 30 | 102 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5582 | 23827585201 | 2017-02-22 | QTR3 | 16/17 | 3 | 3 | 650 | 1207 | 1168 | 39 | 0 | 0 | 272 | 285 | 9883550 | 120000 | 9763550 | 9891919 | 9834478 | 0 | 0 | 0 | 9834478 | 10154570 | 328547 | 8369 | 210 | 0 | 0 | 4593 | 0 | 0 | 285 | -39211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 25820 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2020-08-18 | QTR1 | 20/21 | 507 | 14381890.22 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5628 | 43734115201 | 2019-05-22 | QTR4 | 18/19 | 3 | 1 | 650 | 819 | 798 | 21 | 0 | 0 | 169 | 0 | 16216216 | 192922 | 16023294 | 16216212 | 16727455 | 0 | 0 | 0 | 16727455 | 16504892 | -222563 | -4 | 112 | 0 | 0 | 82386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142885 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-10-20 | QTR2 | 21/22 | 509 | 16716427.38 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5636 | 43800315201 | 2018-10-31 | QTR2 | 18/19 | 4 | 4 | 550 | 898 | 899 | -1 | 1 | 0 | 330 | 18 | 28838467 | 150000 | 28688467 | 29085178 | 28445436 | 0 | -56908 | -56908 | 28388528 | 27168457 | -1042919 | 246710 | 194 | 0 | 18 | 12551 | 0 | 0 | 0 | 3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24852 | 0 | 0 | 0 | 28328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 69559 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 | 2021-08-03 | QTR1 | 21/22 | 513 | 39785384.05 |  |  | 18 | 136 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5637 | 43386015201 | 2018-10-31 | QTR2 | 18/19 | 3 | 6 | 165 | 649 | 648 | 1 | 0 | 0 | 74 | 410 | 3244000 | 50000 | 3194000 | 6497176 | 7037281 | 0 | 0 | 0 | 7037281 | 7017582 | -16169 | 3253176 | 23 | 0 | 20 | 16193 | 0 | 0 | 390 | 3236635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 3269827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-03-05 | QTR3 | 20/21 | 515 | 3081320 |  |  | 20 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5645 | 43988515201 | 2019-04-24 | QTR4 | 18/19 | 1 | 2 | 210 | 401 | 401 | 0 | 0 | 0 | 46 | 145 | 920856 | 50000 | 870856 | 858040 | 792026 | 0 | 0 | 0 | 792026 | 792105 | 79 | -62817 | 20 | 0 | 0 | -28659 | 0 | 0 | 0 | 24188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -32481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -36952 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 | 2021-07-13 | QTR1 | 21/22 | 509 | 1118770.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5668 | 43968235201 | 2019-05-22 | QTR4 | 18/19 | 4 | 11 | 510 | 788 | 778 | 10 | 0 | 0 | 123 | 155 | 20003719 | 154151 | 19849568 | 23051817 | 24148539 | 0 | 0 | 0 | 24148539 | 24037958 | -110580 | 3048098 | 58 | 0 | 155 | 2206932 | 2589 | 0 | 0 | 818285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91658 | 0 | 0 | 0 | 52092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 3168966 | 2589 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-04 | QTR3 | 21/22 | 2021-10-21 | QTR2 | 21/22 | 507 | 16312265.29 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5669 | 43923515201 | 2019-10-30 | QTR2 | 19/20 | 2 | 4 | 279 | 416 | 416 | 0 | 0 | 0 | 40 | 97 | 9146375 | 76911 | 9069464 | 9218711 | 9241919 | 0 | 0 | 0 | 9241919 | 9193416 | -48503 | 72336 | 18 | 0 | 97 | 112814 | 19394 | 0 | 0 | 24154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 136968 | 19394 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-04-16 | QTR4 | 20/21 | 507 | 7779290.68 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5670 | 43020245201 | 2019-01-30 | QTR3 | 18/19 | 2 | 6 | 260 | 396 | 395 | 1 | 0 | 0 | 116 | 20 | 2204501 | 50000 | 2154501 | 2284647 | 2359499 | 0 | 0 | 0 | 2359499 | 2362734 | 13475 | 80146 | 76 | 0 | 0 | 4980 | 0 | 5 | 20 | 70131 | 7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 77386 | 7656 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-01-12 | QTR3 | 21/22 | 2020-08-11 | QTR1 | 20/21 | 514 | 1667431.38 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5676 | 43913915201 | 2020-05-20 | QTR4 | 19/20 | 1 | 2 | 120 | 276 | 276 | 0 | 0 | 0 | 96 | 60 | 3433963 | 50000 | 3383963 | 3456872 | 3590532 | 0 | 0 | 0 | 3590532 | 3561652 | -28879 | 22908 | 74 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 55302 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-17 | QTR1 | 21/22 | 2021-05-18 | QTR4 | 20/21 | 515 | 4003251.09 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5678 | 43913115201 | 2019-09-25 | QTR1 | 19/20 | 1 | 2 | 340 | 570 | 570 | 0 | 0 | 0 | 207 | 23 | 9468271 | 122000 | 9346271 | 9554158 | 9236375 | 0 | 0 | 0 | 9236375 | 9044854 | -191521 | 85887 | 113 | 0 | 7 | 16938 | 0 | 0 | 0 | 87699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 107076 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-07-27 | QTR1 | 21/22 | 513 | 12400165.87 |  |  | 23 | 94 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5681 | 43968215201 | 2020-03-25 | QTR3 | 19/20 | 1 | 1 | 150 | 331 | 305 | 26 | 0 | 0 | 171 | 10 | 5811031 | 61000 | 5750031 | 5814390 | 5643783 | 0 | 0 | 0 | 5643783 | 5604250 | -39533 | 3360 | 113 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3360 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-08-20 | QTR1 | 21/22 | 2021-05-16 | QTR4 | 20/21 | 507 | 6194316.7 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5683 | 44141415201 | 2020-07-29 | QTR1 | 20/21 | 2 | 1 | 310 | 505 | 470 | 35 | 0 | 0 | 135 | 60 | 2891598 | 50000 | 2841598 | 3078261 | 3109373 | 0 | 0 | 0 | 3109373 | 3141296 | 31923 | 186663 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 186663 | 226391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 190632 | 226391 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-10 | QTR4 | 21/22 | 2022-04-15 | QTR4 | 21/22 | 513 | 3095610.25 |  |  | 0 | 77 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5685 | 44139615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 130 | 175 | 158 | 17 | 0 | 0 | 45 | 0 | 1144140 | 50000 | 1094140 | 1144140 | 1050473 | 0 | 0 | 0 | 1050473 | 1085978 | 35505 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-08-03 | QTR1 | 21/22 | 513 | 1587329.04 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5701 | 44136515201 | 2020-08-26 | QTR1 | 20/21 | 1 | 0 | 130 | 136 | 135 | 1 | 0 | 0 | 6 | 0 | 1343897 | 50000 | 1293897 | 1343897 | 1295471 | 0 | 0 | 0 | 1295471 | 1296320 | 849 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3639 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 507 | 1376221.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5710 | 44136615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 86 | 128 | 128 | 0 | 0 | 0 | 42 | 0 | 614736 | 29870 | 584866 | 614736 | 554534 | 0 | 0 | 0 | 554534 | 554534 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-03 | QTR3 | 21/22 | 2021-11-09 | QTR2 | 21/22 | 512 | 624301.96 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5734 | 44101315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 190 | 310 | 304 | 6 | 0 | 0 | 93 | 27 | 6878342 | 77767 | 6800575 | 6878342 | 6971991 | 0 | 0 | 0 | 6971991 | 7381860 | 409869 | 0 | 70 | 0 | 27 | 52873 | 0 | 0 | 0 | 10074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 66884 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2022-06-30 | QTR4 | 21/22 | 2022-04-27 | QTR4 | 21/22 | 514 | 7850496.57 |  |  | 27 | 23 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50A9 | 44326415201 | 2020-03-03 | QTR3 | 19/20 | 1 | 1 | 180 | 295 | 294 | 1 | 0 | 0 | 101 | 14 | 1277250 | 50000 | 1227250 | 1307659 | 1259799 | 0 | 0 | 0 | 1259799 | 1259799 | 0 | 30409 | 84 | 0 | 14 | 90009 | 0 | 0 | 0 | -59600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 30409 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-07-06 | QTR1 | 21/22 | 2021-03-24 | QTR3 | 20/21 | 514 | 1837866.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A1 | 44208715201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 90 | 112 | 110 | 2 | 0 | 0 | 19 | 3 | 875517 | 38500 | 837017 | 875517 | 860515 | 0 | 0 | 0 | 860515 | 860515 | 0 | 0 | 13 | 0 | 0 | 7876 | 0 | 0 | 3 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9204 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-12-22 | QTR2 | 21/22 | 2021-09-23 | QTR1 | 21/22 | 509 | 776684.7 |  |  | 3 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A2 | 44316815201 | 2020-10-06 | QTR2 | 20/21 | 2 | 1 | 220 | 274 | 276 | -2 | 2 | 0 | 54 | 0 | 7726425 | 101900 | 7624525 | 7711640 | 7780592 | 0 | 0 | 0 | 7780592 | 7870977 | 90385 | -14785 | 29 | 0 | 0 | -17404 | 0 | 0 | 0 | 2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7315 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2021-10-06 | QTR2 | 21/22 | 513 | 10078671.13 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52A3 | 44539615201 | 2020-10-06 | QTR2 | 20/21 | 1 | 0 | 80 | 81 | 66 | 15 | 0 | 0 | 1 | 0 | 254016 | 14966 | 239050 | 254016 | 220075 | 0 | 0 | 0 | 220075 | 220075 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-04-14 | QTR4 | 20/21 | 507 | 309304 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A6 | 44119715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 0 | 70 | 109 | 109 | 0 | 0 | 0 | 39 | 0 | 320193 | 13925 | 306268 | 320193 | 308143 | 0 | 0 | 0 | 308143 | 308143 | 0 | 0 | 24 | 0 | 0 | 12247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12247 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-04 | QTR3 | 21/22 | 2021-12-02 | QTR2 | 21/22 | 507 | 289415.18 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A7 | 44333415201 | 2020-12-15 | QTR2 | 20/21 | 1 | 1 | 100 | 318 | 318 | 0 | 0 | 0 | 218 | 0 | 1002182 | 50000 | 952182 | 1002182 | 953504 | 0 | 0 | 0 | 953504 | 953504 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2022-04-28 | QTR4 | 21/22 | 2022-02-04 | QTR3 | 21/22 | 514 | 1304377.5 |  |  | 0 | 176 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A9 | 44101715201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 94 | 94 | 0 | 0 | 0 | 12 | 12 | 789395 | 32885 | 756510 | 789395 | 772436 | 0 | 0 | 0 | 772436 | 772436 | 0 | 0 | 7 | 0 | 12 | 4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4373 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-27 | QTR1 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 509 | 659076.03 |  |  | 12 | 5 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A0 | 44208815201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 70 | 190 | 190 | 0 | 0 | 0 | 109 | 11 | 524491 | 26260 | 498231 | 524491 | 485346 | 0 | 0 | 0 | 485346 | 485346 | 0 | 0 | 85 | 0 | 0 | 362 | 0 | 0 | 11 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2053 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2022-01-06 | QTR3 | 21/22 | 507 | 529396.72 |  |  | 11 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A2 | 44589615201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 140 | 158 | 144 | 14 | 0 | 0 | 18 | 0 | 553370 | 29890 | 523480 | 553370 | 525670 | 0 | 0 | 0 | 525670 | 525670 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-01-10 | QTR3 | 21/22 | 2021-10-07 | QTR2 | 21/22 | 514 | 622693 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A9 | 44541215201 | 2021-03-02 | QTR3 | 20/21 | 1 | 0 | 100 | 104 | 35 | 69 | 0 | 0 | 4 | 0 | 239156 | 14276 | 224880 | 239156 | 221370 | 0 | 0 | 0 | 221370 | 221370 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-09-01 | QTR1 | 21/22 | 2021-07-07 | QTR1 | 21/22 | 509 | 305553.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55A1 | 44530925216 | 2021-04-06 | QTR4 | 20/21 | 1 | 0 | 190 | 235 | 235 | 0 | 0 | 0 | 35 | 10 | 1267718 | 50000 | 1217718 | 1267718 | 1235714 | 0 | 0 | 0 | 1235714 | 1293061 | 57347 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 10 | 12686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 21061 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-22 | QTR4 | 21/22 | 2022-05-17 | QTR4 | 21/22 | 513 | 1544976.74 |  |  | 10 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55A4 | 44113715201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 170 | 216 | 216 | 0 | 0 | 0 | 46 | 0 | 1935472 | 50000 | 1885472 | 1935472 | 1855843 | 0 | 0 | 0 | 1855843 | 1859047 | 3204 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-06-17 | QTR4 | 21/22 | 2022-03-03 | QTR3 | 21/22 | 515 | 1850000 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55A5 | 44333315201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 110 | 222 | 221 | 1 | 0 | 0 | 95 | 17 | 938530 | 50000 | 888530 | 938530 | 914587 | 0 | 0 | 0 | 914587 | 914587 | 0 | 0 | 32 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-05-26 | QTR4 | 21/22 | 2022-04-11 | QTR4 | 21/22 | 514 | 1183192.28 |  |  | 17 | 63 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55A6 | 44589515201 | 2021-05-04 | QTR4 | 20/21 | 1 | 0 | 80 | 101 | 99 | 2 | 0 | 0 | 21 | 0 | 98489 | 6182 | 92307 | 98489 | 95948 | 0 | 0 | 0 | 95948 | 95948 | 0 | 0 | 3 | 0 | 0 | 4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4753 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 | 2022-02-09 | QTR3 | 21/22 | 513 | 144831 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56A4 | 44395715201 | 2021-07-07 | QTR1 | 21/22 | 1 | 0 | 120 | 152 | 148 | 4 | 0 | 0 | 32 | 0 | 3298855 | 50000 | 3248855 | 3298855 | 3246694 | 0 | 0 | 0 | 3246694 | 3246744 | 50 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-25 | QTR4 | 21/22 | 2022-02-21 | QTR3 | 21/22 | 514 | 3710950.66 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A3 | 41125655201 | 2021-10-05 | QTR2 | 21/22 | 1 | 2 | 44 | 60 | 59 | 1 | 0 | 0 | 16 | 0 | 245824 | 9890 | 235934 | 268034 | 278169 | 0 | 0 | 0 | 278169 | 278169 | 0 | 22210 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 11110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12320 | 12320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23430 | 12320 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2022-05-18 | QTR4 | 21/22 | 2022-03-30 | QTR3 | 21/22 | 512 | 349506.95 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A9 | 43988085201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 30 | 41 | 41 | 0 | 0 | 0 | 9 | 2 | 127056 | 6809 | 120247 | 127056 | 123994 | 0 | 0 | 0 | 123994 | 123994 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | F823681989 | UPRIGHT ELECTRICAL SERVICES LLC | N/A | N/A | N/A | N/A | 2021-12-07 | QTR2 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 509 | 169609.7 |  |  | 2 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z71 | 43179835201 | 2019-05-07 | QTR4 | 18/19 | 2 | 7 | 570 | 816 | 816 | 0 | 0 | 0 | 140 | 106 | 16210000 | 247420 | 15962580 | 17216871 | 17023277 | 0 | 0 | 0 | 17023277 | 16917166 | -106111 | 1006871 | 91 | 0 | 0 | 767888 | 17768 | 0 | 90 | 237203 | 30782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168783 | 0 | 0 | 16 | 14196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1188071 | 48550 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-12-16 | QTR2 | 21/22 | 512 | 17297949.45 |  |  | 106 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z86 | 43913615201 | 2020-04-07 | QTR4 | 19/20 | 1 | 2 | 300 | 423 | 424 | -1 | 1 | 0 | 94 | 29 | 7339262 | 75546 | 7263716 | 7409262 | 7411267 | 0 | 0 | 0 | 7411267 | 7390488 | -20779 | 70000 | 38 | 0 | 0 | 29196 | 0 | 0 | 29 | 105005 | 58655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 134565 | 58655 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-16 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 513 | 7635147.19 |  |  | 29 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z88 | 43793715201 | 2019-10-01 | QTR2 | 19/20 | 1 | 1 | 200 | 379 | 378 | 1 | 0 | 0 | 179 | 0 | 1872651 | 50000 | 1822651 | 1875633 | 1830367 | 0 | 0 | 0 | 1830367 | 1822350 | -5035 | 2982 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE | N/A | N/A | N/A | N/A | 2021-09-09 | QTR1 | 21/22 | 2021-01-22 | QTR3 | 20/21 | 514 | 1916336.55 |  |  | 0 | 138 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z90 | 44326915201 | 2020-04-07 | QTR4 | 19/20 | 2 | 2 | 200 | 287 | 285 | 2 | 0 | 0 | 72 | 15 | 3873465 | 50000 | 3823465 | 3916343 | 4113159 | 0 | 0 | 0 | 4113159 | 4113159 | 0 | 42878 | 52 | 0 | 15 | 73643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 73643 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-10-04 | QTR2 | 21/22 | 2021-08-16 | QTR1 | 21/22 | 514 | 4116924.5 | B1 | ACC - NO EXCUSE BONUS | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z94 | 44121115201 | 2019-03-15 | QTR3 | 18/19 | 1 | 2 | 430 | 1043 | 1042 | 1 | 0 | 0 | 237 | 376 | 4278000 | 54000 | 4224000 | 4328000 | 4273000 | 0 | 0 | 0 | 4273000 | 4272788 | -212 | 50000 | 162 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 50000 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2022-06-01 | QTR4 | 21/22 | 2022-03-29 | QTR3 | 21/22 | 507 | 5431910 | LBDB | LOW BID DESIGN BUILD | 0 | 75 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z96 | 44116615201 | 2019-12-03 | QTR2 | 19/20 | 1 | 0 | 350 | 440 | 440 | 0 | 0 | 0 | 90 | 0 | 1299589 | 50000 | 1249589 | 1299589 | 1316020 | 0 | 0 | 0 | 1316020 | 1315225 | -795 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48528 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-04 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 514 | 1579621 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6427 | 43063715201 | 2018-06-13 | QTR4 | 17/18 | 4 | 17 | 539 | 983 | 940 | 43 | 0 | 0 | 189 | 255 | 18966444 | 656288 | 18310156 | 21723570 | 21496962 | 0 | 1120000 | 1120000 | 22616962 | 21341563 | -1230521 | 2757126 | 135 | 0 | 56 | 1209716 | 4016 | 0 | 168 | 1324053 | 2982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147142 | 0 | 0 | 0 | 3311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171334 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 2855556 | 6998 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 | 2021-11-02 | QTR2 | 21/22 | 606 | 22112131.6 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6460 | 43081745201 | 2020-04-29 | QTR4 | 19/20 | 5 | 2 | 380 | 473 | 417 | 56 | 0 | 0 | 93 | 0 | 9621172 | 109381 | 9511791 | 9721667 | 9784724 | 0 | 580000 | 580000 | 10364724 | 9769960 | -594765 | 100495 | 78 | 0 | 0 | 19509 | 0 | 0 | 0 | 137279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160626 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-02 | QTR3 | 21/22 | 2021-08-26 | QTR1 | 21/22 | 613 | 9993234.21 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6465 | 43345535201 | 2019-12-04 | QTR2 | 19/20 | 3 | 1 | 310 | 357 | 290 | 67 | 0 | 0 | 47 | 0 | 3445403 | 51305 | 3394098 | 3514192 | 3479994 | 0 | 170000 | 170000 | 3649994 | 3454649 | -195345 | 68789 | 27 | 0 | 0 | 14334 | 0 | 0 | 0 | 26726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109849 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-08-09 | QTR1 | 21/22 | 2021-02-02 | QTR3 | 20/21 | 636 | 3079919.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6469 | 42930045201 | 2019-09-25 | QTR1 | 19/20 | 2 | 4 | 350 | 410 | 330 | 80 | 0 | 0 | 60 | 0 | 5172452 | 51320 | 5121132 | 5372452 | 5225454 | 0 | 220000 | 220000 | 5445454 | 5222651 | -222802 | 200000 | 43 | 0 | 0 | 38506 | 0 | 0 | 0 | 32542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134496 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212915 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-01-06 | QTR3 | 21/22 | 2021-05-21 | QTR4 | 20/21 | 613 | 4540257.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6472 | 44167015201 | 2020-02-26 | QTR3 | 19/20 | 2 | 0 | 200 | 251 | 250 | 1 | 0 | 0 | 51 | 0 | 1098693 | 50000 | 1048693 | 1098693 | 1036954 | 0 | 0 | 0 | 1036954 | 1036856 | -98 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2021-07-13 | QTR1 | 21/22 | 2021-01-23 | QTR3 | 20/21 | 636 | 1175313.85 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6475 | 43635525201 | 2020-03-25 | QTR3 | 19/20 | 4 | 3 | 350 | 384 | 338 | 46 | 0 | 0 | 34 | 0 | 3771815 | 51345 | 3720470 | 3809965 | 3652358 | 0 | 130000 | 130000 | 3782358 | 3668771 | -113588 | 38150 | 11 | 0 | 0 | 17761 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24683 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-08 | QTR2 | 21/22 | 2021-07-21 | QTR1 | 21/22 | 636 | 4248050.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6478 | 44030415201 | 2020-02-26 | QTR3 | 19/20 | 3 | 0 | 140 | 199 | 179 | 20 | 0 | 0 | 59 | 0 | 419419 | 20696 | 398723 | 419419 | 372140 | 0 | 0 | 0 | 372140 | 372179 | 39 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-29 | QTR4 | 20/21 | 613 | 420617.5 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6479 | 44028115201 | 2020-11-18 | QTR2 | 20/21 | 2 | 0 | 155 | 194 | 190 | 4 | 0 | 0 | 39 | 0 | 557557 | 32224 | 525333 | 557557 | 512065 | 0 | 0 | 0 | 512065 | 512073 | 8 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-06 | QTR4 | 21/22 | 2022-02-21 | QTR3 | 21/22 | 613 | 667193.75 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6482 | 44017815201 | 2019-12-04 | QTR2 | 19/20 | 2 | 1 | 240 | 430 | 430 | 0 | 0 | 0 | 190 | 0 | 996753 | 39258 | 957495 | 1029269 | 971330 | 0 | 0 | 0 | 971330 | 971328 | -2 | 32516 | 132 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 44541 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-12 | QTR2 | 21/22 | 2021-09-16 | QTR1 | 21/22 | 613 | 819497.3 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6483 | 44016915201 | 2019-09-25 | QTR1 | 19/20 | 3 | 4 | 260 | 436 | 436 | 0 | 0 | 0 | 176 | 0 | 1399991 | 50000 | 1349991 | 1461545 | 1445555 | 0 | 0 | 0 | 1445555 | 1445977 | 421 | 61554 | 99 | 0 | 0 | 1094 | 0 | 0 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 27009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 65528 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2022-02-28 | QTR3 | 21/22 | 2021-12-17 | QTR2 | 21/22 | 613 | 1299243.3 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6488 | 43992415201 | 2021-01-27 | QTR3 | 20/21 | 2 | 1 | 220 | 250 | 200 | 50 | 0 | 0 | 30 | 0 | 1453437 | 50000 | 1403437 | 1453437 | 1311324 | 0 | 120000 | 120000 | 1431324 | 1321782 | -109542 | 0 | 9 | 0 | 0 | 3385 | 0 | 0 | 0 | 9417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12802 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-04-21 | QTR4 | 21/22 | 2022-02-10 | QTR3 | 21/22 | 636 | 1645444.71 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6493 | 44331415201 | 2019-10-30 | QTR2 | 19/20 | 12 | 3 | 280 | 359 | 358 | 1 | 0 | 0 | 79 | 0 | 2625000 | 50000 | 2575000 | 2574951 | 2200098 | 0 | 0 | 0 | 2200098 | 2199992 | -106 | -50049 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45130 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-10-05 | QTR2 | 21/22 | 2021-08-11 | QTR1 | 21/22 | 613 | 2833197.2 |  |  | 0 | 25 | 0 | 0 | -121049 | 0 |  | CO
06CO | 06 | T6498 | 43080835201 | 2020-01-29 | QTR3 | 19/20 | 1 | 0 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 1171215 | 42535 | 1128680 | 1171215 | 1109354 | 0 | 0 | 0 | 1109354 | 1108186 | -1169 | 0 | 36 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 15030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 18046 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-06 | QTR4 | 20/21 | 613 | 865294.2 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6501 | 43998515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 0 | 160 | 201 | 201 | 0 | 0 | 0 | 41 | 0 | 731741 | 36002 | 695739 | 731741 | 694244 | 0 | 0 | 0 | 694244 | 696196 | 1952 | 0 | 25 | 0 | 0 | 12125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 18191 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-13 | QTR4 | 21/22 | 2021-12-13 | QTR2 | 21/22 | 636 | 743253.85 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6502 | 44385315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 184 | 155 | 29 | 0 | 0 | 34 | 0 | 619555 | 32981 | 586574 | 619555 | 571295 | 0 | 0 | 0 | 571295 | 572454 | 1159 | 0 | 31 | 0 | 0 | 2890 | 0 | 0 | 0 | 2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5408 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-02-14 | QTR3 | 21/22 | 2021-12-13 | QTR2 | 21/22 | 613 | 681973.35 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6507 | 43991815201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 239 | 269 | 229 | 40 | 0 | 0 | 30 | 0 | 1536743 | 50000 | 1486743 | 1536743 | 1501598 | 0 | 100000 | 100000 | 1601598 | 1507472 | -94126 | 0 | 17 | 0 | 0 | 7665 | 0 | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18247 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-01-13 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 636 | 1644818.7 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6524 | 42934535201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 164 | 228 | 222 | 6 | 0 | 0 | 64 | 0 | 759415 | 38043 | 721372 | 759415 | 708132 | 0 | 0 | 0 | 708132 | 711882 | 3750 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2022-06-08 | QTR4 | 21/22 | 2022-04-08 | QTR4 | 21/22 | 636 | 792991.75 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6526 | 44167215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 140 | 164 | 131 | 33 | 0 | 0 | 24 | 0 | 349349 | 16852 | 332497 | 349349 | 316341 | 0 | 0 | 0 | 316341 | 316342 | 1 | 0 | 19 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-11-16 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 636 | 359443 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6528 | 44183215201 | 2021-04-28 | QTR4 | 20/21 | 2 | 1 | 195 | 218 | 184 | 34 | 0 | 0 | 23 | 0 | 2045400 | 51425 | 1993975 | 2095400 | 2038295 | 0 | 130000 | 130000 | 2168295 | 2041993 | -126302 | 50000 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47342 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-06-02 | QTR4 | 21/22 | 2022-01-25 | QTR3 | 21/22 | 613 | 2162364.7 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6560 | 44576315201 | 2021-09-29 | QTR1 | 21/22 | 2 | 0 | 140 | 148 | 94 | 54 | 0 | 0 | 8 | 0 | 484058 | 18418 | 465640 | 484058 | 387070 | 0 | 0 | 0 | 387070 | 387070 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 | 2022-04-04 | QTR4 | 21/22 | 636 | 411401.21 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6K72 | 43652215201 | 2018-01-25 | QTR3 | 17/18 | 2 | 8 | 740 | 803 | 785 | 18 | 0 | 0 | 63 | 0 | 12962183 | 150000 | 12812183 | 14077180 | 17042051 | 0 | 0 | 0 | 17042051 | 16986931 | 530 | 1114997 | 29 | 0 | 0 | 381047 | 0 | 0 | 0 | 241580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452490 | 0 | 0 | 0 | 2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020318 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-10-25 | QTR2 | 21/22 | 2020-07-30 | QTR1 | 20/21 | 606 | 12118991.05 |  |  | 0 | 34 | 0 | 0 | -57170 | 0 |  | DO
06DO | 06 | E6K73 | 43653715201 | 2019-07-25 | QTR1 | 19/20 | 1 | 2 | 180 | 329 | 324 | 5 | 0 | 0 | 138 | 11 | 4293668 | 50000 | 4243668 | 4404270 | 4390585 | 0 | 0 | 0 | 4390585 | 4390585 | 0 | 110603 | 110 | 0 | 11 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 12874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 90783 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-09-30 | QTR1 | 21/22 | 2021-08-20 | QTR1 | 21/22 | 613 | 3248689 |  |  | 11 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K77 | 42930035201 | 2016-11-23 | QTR2 | 16/17 | 4 | 13 | 1150 | 1461 | 1177 | 284 | 0 | 0 | 311 | 0 | 89490000 | 150000 | 89340000 | 91100952 | 91019470 | 0 | 1320000 | 1320000 | 92339470 | 90787364 | -991000 | 1610952 | 139 | 0 | 0 | 1028437 | 7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377079 | 0 | 0 | 0 | 289034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193206 | 7442 | F270887868 | ARCHER WESTERN CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-03 | QTR1 | 21/22 | 2020-04-28 | QTR4 | 19/20 | 606 | 75222049.5 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 172 | 0 | 0 | -501344 | 0 |  | DO
06DO | 06 | E6L23 | 41372125201 | 2017-01-26 | QTR3 | 16/17 | 1 | 7 | 1400 | 1609 | 1510 | 99 | 0 | 0 | 292 | -83 | 33333000 | 150000 | 33183000 | 38916929 | 42819253 | 0 | 193479 | 193479 | 43012732 | 42822072 | -190660 | 5583929 | 191 | 0 | 0 | 510456 | 0 | 0 | 0 | 4990775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83 | 5733367 | 0 | F561830811 | SAFFO CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | QTR4 | 21/22 | 2021-12-22 | QTR2 | 21/22 | 606 | 34695588 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 101 | 0 | -83 | 0 | 0 |  | DO
06DO | 06 | E6L90 | 43029139201 | 2019-05-03 | QTR4 | 18/19 | 1 | 2 | 500 | 685 | 685 | 0 | 0 | 0 | 167 | 18 | 3703968 | 50000 | 3653968 | 3809754 | 3778569 | 0 | 0 | 0 | 3778569 | 0 | -3778569 | 105786 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 120684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 18 | 124601 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-08-13 | QTR1 | 21/22 | 2021-05-25 | QTR4 | 20/21 | 606 | 4250000 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L94 | 43653915201 | 2020-07-30 | QTR1 | 20/21 | 1 | 0 | 240 | 297 | 286 | 11 | 0 | 0 | 57 | 0 | 1871000 | 50000 | 1821000 | 1871000 | 1887711 | 0 | 0 | 0 | 1887711 | 1887711 | 0 | 0 | 51 | 0 | 0 | 39684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39684 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-12-15 | QTR2 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 613 | 2130684.25 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M32 | 44204015201 | 2020-02-05 | QTR3 | 19/20 | 2 | 3 | 550 | 581 | 354 | 227 | 0 | 0 | 31 | 0 | 4679092 | 80092 | 4599000 | 1480760 | 1400668 | 0 | 0 | 0 | 1400668 | 1400668 | 0 | -3198332 | 6 | 0 | 0 | -3198332 | 231933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3198332 | 231933 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-09-10 | QTR1 | 21/22 | 2021-06-09 | QTR4 | 20/21 | 636 | 4495092 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M37 | 44060415201 | 2020-04-30 | QTR4 | 19/20 | 1 | 0 | 180 | 261 | 219 | 42 | 0 | 0 | 81 | 0 | 589589 | 29369 | 560220 | 589589 | 561220 | 0 | 0 | 0 | 561220 | 561388 | 168 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13511 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-12-17 | QTR2 | 21/22 | 2021-09-07 | QTR1 | 21/22 | 613 | 615217 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M47 | 44196115201 | 2020-08-27 | QTR1 | 20/21 | 1 | 2 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 291080 | 16612 | 274468 | 324304 | 276941 | 0 | 0 | 0 | 276941 | 276941 | 0 | 33224 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18776 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2021-09-16 | QTR1 | 21/22 | 2021-06-03 | QTR4 | 20/21 | 613 | 335059.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M49 | 44197415201 | 2021-02-25 | QTR3 | 20/21 | 1 | 0 | 180 | 261 | 261 | 0 | 0 | 0 | 81 | 0 | 1171392 | 50000 | 1121392 | 1171392 | 1126504 | 0 | 0 | 0 | 1126504 | 1137831 | 11327 | 0 | 46 | 0 | 0 | 2817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-06-17 | QTR4 | 21/22 | 2022-03-28 | QTR3 | 21/22 | 636 | 1179270.9 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M90 | 43029149201 | 2020-07-13 | QTR1 | 20/21 | 2 | 3 | 400 | 452 | 451 | 1 | 0 | 0 | 52 | 0 | 1818000 | 50000 | 1768000 | 1665532 | 1615532 | 0 | 0 | 0 | 1615532 | 1725 | -1615532 | -152468 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -150743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -150743 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-12 | QTR4 | 21/22 | 2021-12-03 | QTR2 | 21/22 | 636 | 2364500 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N05 | 44188615201 | 2020-05-28 | QTR4 | 19/20 | 1 | 0 | 180 | 351 | 292 | 59 | 0 | 0 | 171 | 0 | 660660 | 31668 | 628992 | 660660 | 634309 | 0 | 0 | 0 | 634309 | 634835 | 526 | 0 | 158 | 0 | 0 | 4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25892 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-01-28 | QTR3 | 21/22 | 2021-12-10 | QTR2 | 21/22 | 613 | 655036.75 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7385 | 25624325201 | 2016-06-20 | QTR4 | 15/16 | 4 | 13 | 620 | 937 | 937 | 0 | 0 | 0 | 156 | 161 | 12584444 | 181100 | 12403344 | 14503972 | 15099334 | 0 | 0 | 0 | 15099334 | 15329276 | 248412 | 1919528 | 100 | 0 | 51 | 785982 | 22437 | 0 | 110 | 925858 | 383142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1985862 | 405580 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2021-08-11 | QTR1 | 21/22 | 2019-06-22 | QTR4 | 18/19 | 714 | 18085000 |  |  | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7386 | 43002115201 | 2016-06-15 | QTR4 | 15/16 | 3 | 7 | 310 | 812 | 1136 | -324 | 324 | 0 | 175 | 327 | 6015645 | 88863 | 5926782 | 7425942 | 7629019 | 0 | 0 | 0 | 7629019 | 7799558 | 197466 | 1410297 | 132 | 0 | 318 | 1457786 | 195935 | 0 | 6 | 154100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -306143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1323906 | 195935 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2022-02-23 | QTR3 | 21/22 | 2020-01-21 | QTR3 | 19/20 | 798 | 6465450.53 | B5 | ACC - INCENTIVE/DISINCENTIVE | 3 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7400 | 43483915201 | 2017-12-06 | QTR2 | 17/18 | 1 | 1 | 150 | 167 | 540 | -373 | 373 | 0 | 17 | 0 | 1728055 | 50000 | 1678055 | 1440555 | 1373802 | 0 | 0 | 0 | 1373802 | 1427923 | 54120 | -287499 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287499 | 0 | Z31-4177100 | NATIONWIDE MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2022-05-04 | QTR4 | 21/22 | 2019-12-05 | QTR2 | 19/20 | 799 | 1700000 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7410 | 43649515201 | 2018-05-23 | QTR4 | 17/18 | 5 | 5 | 565 | 971 | 970 | 1 | 0 | 0 | 296 | 110 | 10099029 | 287408 | 9811621 | 12396490 | 12392490 | 0 | 0 | 0 | 12392490 | 12349457 | -43033 | 2297460 | 224 | 0 | 40 | 1272584 | 0 | 0 | 70 | 1132140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2418085 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-10 | QTR3 | 21/22 | 2021-06-29 | QTR4 | 20/21 | 796 | 9905226.59 |  |  | 0 | 72 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7437 | 43605615201 | 2020-03-25 | QTR3 | 19/20 | 1 | 2 | 268 | 298 | 285 | 13 | 0 | 0 | 30 | 0 | 1903823 | 50000 | 1853823 | 2069815 | 2004923 | 0 | 0 | 0 | 2004923 | 2005258 | 335 | 165992 | 13 | 0 | 0 | 299339 | 0 | 0 | 0 | -122480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168522 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-01-04 | QTR3 | 21/22 | 2021-09-10 | QTR1 | 21/22 | 799 | 1500000 |  |  | 0 | 17 | 0 | 0 | -8337 | 0 |  | CO
07CO | 07 | T7447 | 43764115201 | 2020-03-25 | QTR3 | 19/20 | 2 | 0 | 261 | 338 | 341 | -3 | 3 | 0 | 77 | 0 | 3572269 | 50000 | 3522269 | 3572269 | 3206137 | -7737 | 0 | -7737 | 3198400 | 3190454 | -7946 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-07-30 | QTR1 | 21/22 | 796 | 2900000 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7450 | 43764015201 | 2020-04-29 | QTR4 | 19/20 | 1 | 0 | 300 | 356 | 352 | 4 | 0 | 0 | 56 | 0 | 3698894 | 50000 | 3648894 | 3698894 | 3783529 | 0 | 0 | 0 | 3783529 | 3798642 | 15112 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-11 | QTR3 | 21/22 | 2021-10-15 | QTR2 | 21/22 | 796 | 2945400 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7455 | 44140315201 | 2020-07-29 | QTR1 | 20/21 | 2 | 0 | 225 | 256 | 246 | 10 | 0 | 0 | 31 | 0 | 9710187 | 140000 | 9570187 | 9710187 | 10168330 | 0 | 0 | 0 | 10168330 | 10201078 | 32748 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-07 | QTR3 | 21/22 | 2021-10-12 | QTR2 | 21/22 | 796 | 14415700 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7466 | 43764615201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 120 | 150 | 144 | 6 | 0 | 0 | 30 | 0 | 3084962 | 50000 | 3034962 | 3084962 | 2884493 | 0 | 0 | 0 | 2884493 | 2884493 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5570 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-18 | QTR2 | 21/22 | 2021-07-12 | QTR1 | 21/22 | 796 | 2622400 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7479 | 44784525201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 150 | 151 | 90 | 61 | 0 | 0 | 1 | 0 | 1105450 | 50000 | 1055450 | 1105450 | 1054145 | 0 | 0 | 0 | 1054145 | 1050365 | -3780 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-06-28 | QTR4 | 21/22 | 2022-05-13 | QTR4 | 21/22 | 796 | 1665700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L84 | 43227015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 10 | 365 | 1295 | 1295 | 0 | 0 | 0 | 294 | 636 | 13880945 | 76000 | 13804945 | 16221150 | 16265882 | 0 | 0 | 0 | 16265882 | 16265882 | 0 | 2340205 | 124 | 0 | 123 | 197235 | 0 | 0 | 513 | 2081549 | 186647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 39069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 636 | 2412963 | 186647 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-06-01 | QTR4 | 21/22 | 2021-06-30 | QTR4 | 20/21 | 799 | 7705000 |  |  | 9 | 92 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M61 | 43951615201 | 2019-07-10 | QTR1 | 19/20 | 2 | 0 | 430 | 707 | 698 | 9 | 0 | 0 | 277 | 0 | 3417860 | 50000 | 3367860 | 3417860 | 3733589 | 0 | 0 | 0 | 3733589 | 3733589 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-12-03 | QTR2 | 21/22 | 799 | 4777765.05 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M81 | 44335315201 | 2019-10-09 | QTR2 | 19/20 | 1 | 1 | 143 | 516 | 516 | 0 | 0 | 0 | 180 | 193 | 385385 | 7500 | 377885 | 398672 | 364686 | 0 | 0 | 0 | 364686 | 364686 | 0 | 13287 | 64 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 132 | 13287 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-02-21 | QTR3 | 21/22 | 2021-11-17 | QTR2 | 21/22 | 799 | 300000 |  |  | 107 | 44 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M91 | 44144125201 | 2020-03-11 | QTR3 | 19/20 | 2 | 0 | 160 | 214 | 186 | 28 | 0 | 0 | 51 | 3 | 1622282 | 56878 | 1565404 | 1622282 | 1554003 | 0 | 0 | 0 | 1554003 | 1554555 | 552 | 0 | 23 | 0 | 0 | 276 | 0 | 0 | 3 | 25413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27568 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-10-29 | QTR2 | 21/22 | 2021-03-04 | QTR3 | 20/21 | 799 | 1262053.27 |  |  | 3 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M93 | 44383215201 | 2020-02-12 | QTR3 | 19/20 | 1 | 2 | 550 | 601 | 524 | 77 | 0 | 0 | 51 | 0 | 1260367 | 20000 | 1240367 | 1319899 | 1294928 | 0 | 0 | 0 | 1294928 | 1294928 | 0 | 59531 | 4 | 0 | 0 | 14038 | 0 | 0 | 0 | 5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-03-17 | QTR3 | 21/22 | 2022-01-11 | QTR3 | 21/22 | 796 | 1500000 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M94 | 43673415201 | 2020-04-08 | QTR4 | 19/20 | 1 | 0 | 120 | 189 | 189 | 0 | 0 | 0 | 69 | 0 | 1352812 | 50000 | 1302812 | 1352812 | 1317432 | 0 | 0 | 0 | 1317432 | 1317432 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13041 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-04-22 | QTR4 | 20/21 | 796 | 1640000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7M96 | 43762615201 | 2020-05-13 | QTR4 | 19/20 | 1 | 2 | 190 | 292 | 291 | 1 | 0 | 0 | 102 | 0 | 4564698 | 50000 | 4514698 | 4596212 | 4520073 | 0 | 0 | 0 | 4520073 | 4462676 | -57396 | 31514 | 24 | 21 | 0 | 12487 | 0 | 27 | 0 | 27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 40479 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-15 | QTR1 | 21/22 | 2021-05-20 | QTR4 | 20/21 | 799 | 5061300 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N02 | 44383315201 | 2020-03-11 | QTR3 | 19/20 | 1 | 2 | 140 | 159 | 120 | 39 | 0 | 0 | 19 | 0 | 741228 | 35000 | 706228 | 790728 | 771044 | 0 | 0 | 0 | 771044 | 771044 | 0 | 49500 | 4 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 16552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 16552 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2021-07-23 | QTR1 | 21/22 | 2021-01-05 | QTR3 | 20/21 | 799 | 741278.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N15 | 44539915201 | 2020-02-12 | QTR3 | 19/20 | 1 | 4 | 120 | 160 | 160 | 0 | 0 | 0 | 19 | 21 | 3408000 | 20000 | 3388000 | 3546613 | 3532479 | 0 | 0 | 0 | 3532479 | 3532479 | 0 | 138613 | 11 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 66684 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-01-20 | QTR3 | 21/22 | 2021-06-23 | QTR4 | 20/21 | 799 | 2952724 | B0 | ACC - LUMP SUM | 9 | 8 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N26 | 43946015201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 140 | 177 | 155 | 22 | 0 | 0 | 27 | 10 | 873873 | 25000 | 848873 | 873873 | 855130 | 0 | 0 | 0 | 855130 | 855600 | 470 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7812 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-08-15 | QTR1 | 21/22 | 796 | 685000 |  |  | 10 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N46 | 43955415201 | 2020-09-09 | QTR1 | 20/21 | 1 | 0 | 90 | 93 | 84 | 9 | 0 | 0 | 3 | 0 | 357252 | 20000 | 337252 | 357252 | 337890 | 0 | 0 | 0 | 337890 | 337890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-27 | QTR1 | 21/22 | 2021-07-02 | QTR1 | 21/22 | 796 | 485498 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N48 | 44025215201 | 2020-07-08 | QTR1 | 20/21 | 1 | 0 | 218 | 305 | 229 | 76 | 0 | 0 | 87 | 0 | 3104340 | 50000 | 3054340 | 3104340 | 3112890 | 0 | 0 | 0 | 3112890 | 3077268 | -35622 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-09-02 | QTR1 | 21/22 | 2021-05-07 | QTR4 | 20/21 | 796 | 4202892.64 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N59 | 44701515201 | 2021-01-20 | QTR3 | 20/21 | 1 | 0 | 50 | 55 | 55 | 0 | 0 | 0 | 5 | 0 | 86342 | 3900 | 82442 | 86342 | 80991 | 0 | 0 | 0 | 80991 | 80991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2021-08-26 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 796 | 127700 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N64 | 44146715201 | 2021-02-10 | QTR3 | 20/21 | 1 | 0 | 120 | 163 | 163 | 0 | 0 | 0 | 33 | 10 | 599014 | 34000 | 565014 | 599014 | 566725 | 0 | 0 | 0 | 566725 | 566725 | 0 | 0 | 28 | 0 | 1 | 4550 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4550 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-06-14 | QTR4 | 21/22 | 2022-03-15 | QTR3 | 21/22 | 796 | 758700 |  |  | 23 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O05 | 44149315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 23 | 37 | 0 | 0 | 0 | 0 | 171341 | 11819 | 159522 | 171341 | 173579 | 0 | 0 | 0 | 173579 | 173579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F200721481 | BAY AREA SINKHOLE INVESTIGATION & CIVIL | N/A | N/A | N/A | N/A | 2022-04-20 | QTR4 | 21/22 | 2022-03-16 | QTR3 | 21/22 | 796 | 250600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R13 | 44111115201 | 2019-01-10 | QTR3 | 18/19 | 1 | 10 | 520 | 614 | 614 | 0 | 0 | 0 | 94 | 0 | 30854000 | 150000 | 30704000 | 31355440 | 31288898 | -20000 | 1275000 | 1255000 | 32543898 | 31200893 | -1343005 | 501440 | 69 | 0 | 0 | 17636 | 0 | 0 | 0 | 333715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289031 | 0 | 0 | 0 | 47015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520219 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2022-03-16 | QTR3 | 21/22 | 2020-11-09 | QTR2 | 20/21 | 714 | 28805100 | B10:B5:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 25 | 0 | 0 | -167178 | 0 |  | DO
07DO | 07 | E7R17 | 44368415201 | 2019-07-30 | QTR1 | 19/20 | 1 | 3 | 385 | 501 | 501 | 0 | 0 | 0 | 63 | 53 | 4637000 | 50000 | 4587000 | 5023330 | 4952442 | 0 | 0 | 0 | 4952442 | 4910655 | -41787 | 386330 | 30 | 0 | 0 | 29755 | 0 | 0 | 37 | 362376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 392130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-09 | QTR1 | 21/22 | 2021-02-27 | QTR3 | 20/21 | 799 | 2700000 | A3 | ICC - DESIGN/BUILD - MINOR | 16 | 49 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R25 | 44335815201 | 2020-08-04 | QTR1 | 20/21 | 1 | 1 | 210 | 248 | 248 | 0 | 0 | 0 | 24 | 14 | 994444 | 43458 | 950986 | 1037903 | 984227 | 0 | 0 | 0 | 984227 | 985956 | 1729 | 43458 | 9 | 0 | 14 | 43241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43241 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-19 | QTR1 | 21/22 | 2021-06-17 | QTR4 | 20/21 | 798 | 922458.19 | A3 | ICC - DESIGN/BUILD - MINOR | 14 | 15 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N18 | 41505115201 | 2014-05-16 | QTR4 | 13/14 | 2 | 6 | 1220 | 2448 | 2448 | 0 | 0 | 0 | 192 | 1036 | 73888232 | 150000 | 73738232 | 74290962 | 74217617 | -51000 | 0 | -51000 | 74166617 | 72627252 | -1443556 | 402730 | 70 | 0 | 0 | 250827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 144325 | 0 | 0 | 0 | 59573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 281944 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2021-10-07 | QTR2 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 78874306.84 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 122 | 0 | 0 | -172782 | 0 |  | DO
08DO | 08 | E8Q12 | 41140615201 | 2016-12-01 | QTR2 | 16/17 | 6 | 48 | 1500 | 1737 | 1551 | 186 | 0 | 0 | 234 | 3 | 176976815 | 150000 | 176826815 | 181606278 | 183899695 | -10000 | 1200000 | 1190000 | 185089695 | 186953166 | 2298953 | 4629463 | 130 | 0 | 0 | 1640085 | 1278827 | 0 | 3 | -267804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675505 | 24202 | 0 | 0 | 160430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208 | 0 | 0 | 6 | 1152247 | 226165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3930269 | 1529194 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-12-10 | QTR2 | 21/22 | 2021-06-30 | QTR4 | 20/21 | 854 | 198773291.89 | A5 | ICC - BAM/BONUS | 2 | 104 | 0 | -6 | -433401 | 0 |  | DO
08DO | 08 | E8Q95 | 43652015201 | 2019-11-19 | QTR2 | 19/20 | 2 | 2 | 421 | 547 | 546 | 1 | 0 | 0 | 126 | 0 | 13519194 | 150000 | 13369194 | 13647938 | 13835344 | 0 | 0 | 0 | 13835344 | 13763473 | -71870 | 128744 | 80 | 0 | 0 | 132365 | 0 | 0 | 0 | 34746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 167111 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-08-28 | QTR1 | 21/22 | 854 | 16504274.71 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R51 | 44132215201 | 2019-02-12 | QTR3 | 18/19 | 1 | 5 | 554 | 797 | 797 | 0 | 0 | 0 | 233 | 10 | 17604432 | 150000 | 17454432 | 17319890 | 16726393 | 0 | 0 | 0 | 16726393 | 16676477 | -25916 | -284543 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | -272992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542 | 0 | 0 | 0 | 27040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -238649 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-11-15 | QTR2 | 21/22 | 2021-07-16 | QTR1 | 21/22 | 854 | 15706807.4 |  |  | 10 | 55 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R55 | 42815445201 | 2019-04-09 | QTR4 | 18/19 | 1 | 2 | 770 | 840 | 645 | 195 | 0 | 0 | 60 | 10 | 7871284 | 94139 | 7777146 | 8314187 | 5811967 | 0 | 0 | 0 | 5811967 | 5782260 | -1807 | 442902 | 15 | 0 | 10 | 58365 | 0 | 0 | 0 | 421773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 481983 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2021-07-28 | QTR1 | 21/22 | 2021-04-12 | QTR4 | 20/21 | 854 | 9545163.51 |  |  | 10 | 45 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S00 | 44106715201 | 2019-09-10 | QTR1 | 19/20 | 1 | 2 | 445 | 486 | 442 | 44 | 0 | 0 | 41 | 0 | 5292443 | 50000 | 5242443 | 5312653 | 5319849 | 0 | 0 | 0 | 5319849 | 5313201 | -6647 | 20210 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 54439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66955 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS INC. | N/A | N/A | N/A | N/A | 2021-10-06 | QTR2 | 21/22 | 2021-05-24 | QTR4 | 20/21 | 854 | 4997184.25 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S09 | 44263125201 | 2020-03-10 | QTR3 | 19/20 | 2 | 2 | 277 | 428 | 423 | 5 | 0 | 0 | 116 | 35 | 2536426 | 50000 | 2486426 | 2841757 | 2675313 | 0 | 0 | 0 | 2675313 | 2675591 | 277 | 305331 | 90 | 0 | 0 | 0 | 0 | 0 | 35 | 318436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17340 | 0 | 0 | 0 | 17671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 318767 | 0 | F471966508 | AMERICAN PIPELINE CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-05-24 | QTR4 | 21/22 | 2021-10-06 | QTR2 | 21/22 | 854 | 2736391.87 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S11 | 44029115201 | 2020-04-14 | QTR4 | 19/20 | 3 | 3 | 286 | 425 | 425 | 0 | 0 | 0 | 139 | 0 | 12956998 | 147809 | 12809189 | 13107980 | 13212168 | -6500 | 0 | -6500 | 13205668 | 13166473 | -39196 | 150982 | 73 | 0 | 0 | 10213 | 0 | 0 | 0 | 213463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234161 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2022-02-17 | QTR3 | 21/22 | 2021-10-22 | QTR2 | 21/22 | 854 | 14597378.87 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S18 | 44042315201 | 2020-04-14 | QTR4 | 19/20 | 2 | 2 | 322 | 365 | 354 | 11 | 0 | 0 | 43 | 0 | 9095686 | 127227 | 8968460 | 9114552 | 9001603 | 0 | 0 | 0 | 9001603 | 8960020 | -41583 | 18865 | 18 | 0 | 0 | 18865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81749 | 0 | 0 | 0 | 34958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135572 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-11-18 | QTR2 | 21/22 | 2021-07-22 | QTR1 | 21/22 | 854 | 12888271.81 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S63 | 44514015201 | 2020-12-08 | QTR2 | 20/21 | 1 | 1 | 61 | 89 | 86 | 3 | 0 | 0 | 28 | 0 | 281612 | 16689 | 264923 | 283592 | 264303 | 0 | 0 | 0 | 264303 | 264303 | 0 | 1980 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-11-09 | QTR2 | 21/22 | 2021-08-10 | QTR1 | 21/22 | 854 | 348350.23 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S68 | 44530715201 | 2021-01-12 | QTR3 | 20/21 | 1 | 0 | 142 | 182 | 140 | 42 | 0 | 0 | 40 | 0 | 842202 | 48171 | 794032 | 842202 | 728029 | 0 | 0 | 0 | 728029 | 728029 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2021-10-20 | QTR2 | 21/22 | 2021-09-08 | QTR1 | 21/22 | 854 | 1031656.75 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S73 | 44429215201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 76 | 92 | 91 | 1 | 0 | 0 | 14 | 2 | 351648 | 29081 | 322567 | 351648 | 296493 | 0 | 0 | 0 | 296493 | 296493 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1879 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2021-09-13 | QTR1 | 21/22 | 2021-06-28 | QTR4 | 20/21 | 854 | 613041.08 |  |  | 2 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0