## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 86690848 | 86357876 | 86236586 | 86832683 | 0 | 86650993 | 0.3394% | 100% | -488897 | -0.5661% | -454262 | -0.524% | 1652 | 524 | 31.72% | 149 | 9.019% | 0 | 0% | 43 | 2.603% | 1695 | 2.603% | 2368 | 2420 | 1747 | 5.751% | 83.33%
| District Let | 25581986 | 25381986 | 26122783 | 25719992 | 0 | 25700137 | 1.253% | 100% | 603858 | 2.379% | 540797 | 2.114% | 975 | 94 | 9.641% | 59 | 6.051% | 0 | 0% | 0 | 0% | 975 | 0% | 1128 | 1123 | 970 | -0.5128% | 100%
| All Contracts | 112272834 | 111739862 | 112359369 | 112552675 | 0 | 112351130 | 0.547% | 100% | 114961 | 0.1029% | 86535 | 0.07708% | 2627 | 618 | 23.52% | 208 | 7.918% | 0 | 0% | 43 | 1.637% | 2670 | 1.637% | 3496 | 3543 | 2717 | 3.426% | 87.5%
2 | Central Let | 99608112 | 98936000 | 103898463 | 103209517 | 0 | 102889366 | 3.996% | 85.71% | 4431307 | 4.479% | 4290353 | 4.307% | 3160 | 473 | 14.97% | 320 | 10.13% | 166 | 5.253% | 222 | 7.025% | 3548 | 12.28% | 4360 | 4322 | 3529 | 11.68% | 71.43%
| District Let | 4526984 | 4336649 | 4526984 | 4176415 | 0 | 4188637 | -3.413% | 100% | 0 | 0% | 0 | 0% | 810 | 64 | 7.901% | 63 | 7.778% | 14 | 1.728% | 15 | 1.852% | 839 | 3.58% | 966 | 899 | 772 | -4.691% | 100%
| All Contracts | 104135096 | 103272649 | 108425447 | 107385932 | 0 | 107078003 | 3.685% | 90.91% | 4431307 | 4.291% | 4290353 | 4.12% | 3970 | 537 | 13.53% | 383 | 9.647% | 180 | 4.534% | 237 | 5.97% | 4387 | 10.5% | 5326 | 5221 | 4301 | 8.338% | 81.82%
3 | Central Let | 4390423 | 4263612 | 4564047 | 4714117 | 0 | 4750180 | 11.41% | 66.67% | 127940 | 3.001% | 0 | 0% | 480 | 49 | 10.21% | 34 | 7.083% | 0 | 0% | 26 | 5.417% | 506 | 5.417% | 661 | 713 | 630 | 31.25% | 66.67%
| District Let | 37312398 | 36957168 | 44605227 | 46632703 | 150000 | 43859403 | 18.68% | 66.67% | 7353452 | 19.9% | 7292829 | 19.55% | 1814 | 854 | 47.08% | 339 | 18.69% | 469 | 25.85% | 515 | 28.39% | 2798 | 54.24% | 4000 | 3826 | 2633 | 45.15% | 66.67%
| All Contracts | 41702821 | 41220780 | 49169274 | 51346820 | 150000 | 48609583 | 17.92% | 66.67% | 7481392 | 18.15% | 7292829 | 17.49% | 2294 | 903 | 39.36% | 373 | 16.26% | 469 | 20.44% | 541 | 23.58% | 3304 | 44.03% | 4661 | 4539 | 3263 | 42.24% | 66.67%
4 | Central Let | 20196202 | 19906280 | 20460104 | 19859645 | 0 | 19947762 | 0.2084% | 75% | 394207 | 1.98% | 263902 | 1.307% | 1637 | 172 | 10.51% | 106 | 6.475% | 0 | 0% | 17 | 1.038% | 1654 | 1.038% | 1932 | 1924 | 1646 | 0.5498% | 100%
| District Let | 102676628 | 102494279 | 110735571 | 110576150 | 1500000 | 111423550 | 8.712% | 100% | 7765602 | 7.577% | 8058943 | 7.849% | 1626 | 71 | 4.367% | 100 | 6.15% | 0 | 0% | 0 | 0% | 1626 | 0% | 1797 | 1669 | 1498 | -7.872% | 100%
| All Contracts | 122872830 | 122400559 | 131195675 | 130435795 | 1500000 | 131371312 | 7.329% | 83.33% | 8159809 | 6.666% | 8322845 | 6.774% | 3263 | 243 | 7.447% | 206 | 6.313% | 0 | 0% | 17 | 0.521% | 3280 | 0.521% | 3729 | 3593 | 3144 | -3.647% | 100%
5 | Central Let | 20342403 | 20023021 | 20522547 | 20736388 | 0 | 21727742 | 8.514% | 60% | 311862 | 1.558% | 180143 | 0.8856% | 1010 | 221 | 21.88% | 298 | 29.5% | 0 | 0% | 55 | 5.446% | 1065 | 5.446% | 1584 | 1582 | 1063 | 5.248% | 100%
| District Let | 5818381 | 5638929 | 5900112 | 5681878 | 0 | 5736804 | 1.736% | 100% | 120428 | 2.136% | 81732 | 1.405% | 780 | 80 | 10.26% | 125 | 16.03% | 0 | 0% | 20 | 2.564% | 800 | 2.564% | 1005 | 890 | 685 | -12.18% | 100%
| All Contracts | 26160784 | 25661950 | 26422659 | 26418266 | 0 | 27464546 | 7.024% | 77.78% | 432290 | 1.685% | 261875 | 1.001% | 1790 | 301 | 16.82% | 423 | 23.63% | 0 | 0% | 75 | 4.19% | 1865 | 4.19% | 2589 | 2472 | 1748 | -2.346% | 100%
6 | Central Let | 71103518 | 70842109 | 76670842 | 77323265 | 4400000 | 77045955 | 8.757% | 100% | 5566695 | 7.858% | 5567324 | 7.83% | 1240 | 353 | 28.47% | 80 | 6.452% | 45 | 3.629% | 132 | 10.65% | 1417 | 14.27% | 1850 | 1698 | 1265 | 2.016% | 100%
| District Let | 56939752 | 56758883 | 62407935 | 62320345 | 0 | 62274971 | 9.718% | 100% | 5343799 | 9.415% | 5468183 | 9.603% | 1150 | 155 | 13.48% | 65 | 5.652% | 19 | 1.652% | 118 | 10.26% | 1287 | 11.91% | 1507 | 1479 | 1259 | 9.478% | 100%
| All Contracts | 128043270 | 127600992 | 139078777 | 139643610 | 4400000 | 139320926 | 9.185% | 100% | 10910494 | 8.55% | 11035507 | 8.619% | 2390 | 508 | 21.26% | 145 | 6.067% | 64 | 2.678% | 250 | 10.46% | 2704 | 13.14% | 3357 | 3177 | 2524 | 5.607% | 100%
7 | Central Let | 70386062 | 69964512 | 72139248 | 71885845 | 0 | 71935853 | 2.818% | 100% | 1742519 | 2.491% | 1753186 | 2.491% | 2168 | 261 | 12.04% | 175 | 8.072% | 0 | 0% | 50 | 2.306% | 2218 | 2.306% | 2700 | 2634 | 2198 | 1.384% | 100%
| District Let | 8604829 | 8440829 | 15199104 | 13860552 | 0 | 13875887 | 64.39% | 75% | 6594983 | 78.13% | 6594276 | 76.63% | 1366 | 88 | 6.442% | 174 | 12.74% | 78 | 5.71% | 28 | 2.05% | 1472 | 7.76% | 1734 | 1713 | 1451 | 6.223% | 100%
| All Contracts | 78990891 | 78405341 | 87338352 | 85746397 | 0 | 85811740 | 9.446% | 88.89% | 8337502 | 10.63% | 8347462 | 10.57% | 3534 | 349 | 9.875% | 349 | 9.875% | 78 | 2.207% | 78 | 2.207% | 3690 | 4.414% | 4434 | 4347 | 3649 | 3.254% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 4992370 | 4864209 | 4983506 | 4312252 | 0 | 4312712 | -11.34% | 100% | 5814 | 0.1195% | -8864 | -0.1776% | 463 | 69 | 14.9% | 41 | 8.855% | 7 | 1.512% | 0 | 0% | 470 | 1.512% | 580 | 568 | 458 | -1.08% | #VALUE!
| All Contracts | 4992370 | 4864209 | 4983506 | 4312252 | 0 | 4312712 | -11.34% | 100% | 5814 | 0.1195% | -8864 | -0.1776% | 463 | 69 | 14.9% | 41 | 8.855% | 7 | 1.512% | 0 | 0% | 470 | 1.512% | 580 | 568 | 458 | -1.08% | 100%
Totals This Qtr | Central Let | 372717568 | 370293410 | 384491837 | 384561460 | 4400000 | 384947851 | 3.958% | 85.29% | 12085633 | 3.264% | 11600646 | 3.112% | 11347 | 2053 | 18.09% | 1162 | 10.24% | 211 | 1.86% | 545 | 4.803% | 12103 | 6.663% | 15455 | 15293 | 12078 | 6.442% | 88.24%
| District Let | 246453328 | 244872932 | 274481222 | 273280287 | 1650000 | 271372101 | 10.82% | 88.46% | 27787936 | 11.35% | 28027896 | 11.37% | 8984 | 1475 | 16.42% | 966 | 10.75% | 587 | 6.534% | 696 | 7.747% | 10267 | 14.28% | 12717 | 12167 | 9726 | 8.259% | 92.31%
| All Contracts | 619170896 | 615166342 | 658973059 | 657841747 | 6050000 | 656319952 | 6.69% | 86.67% | 39873569 | 6.482% | 39628542 | 6.4% | 20331 | 3528 | 17.35% | 2128 | 10.47% | 798 | 3.925% | 1241 | 6.104% | 22370 | 10.03% | 28172 | 27460 | 21804 | 7.245% | 90%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1709 | 20103225201 | 2018-05-23 | QTR4 | 17/18 | 3 | 27 | 907 | 1313 | 1313 | 100% | 1 | 0 | 0 | 0 | 406 | 0 | 80840173 | 150000 | 80690173 | 80370929 | 81141842 | -44000 | 0 | -44000 | 81097842 | 80911304 | 100.3% | 1 | -90555 | -469244 | 327 | 79 | 0 | 0 | -1709315 | 0 | 0 | 0 | 1772025 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786283 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 0 | -509110 | 117720 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2022-09-16 | QTR1 | 22/23 |  | 2022-05-19 | QTR4 | 21/22 | 106 | 83257742.89 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1784 | 44210725201 | 2021-02-17 | QTR3 | 20/21 | 3 | 2 | 180 | 234 | 234 | 115% | 1 | 0 | 0 | 0 | 27 | 27 | 1091540 | 50000 | 1041540 | 1106522 | 1056999 | 0 | 0 | 0 | 1056999 | 1056999 | 101.5% | 1 | 43887 | 14982 | 8 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -48834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 63816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14982 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-03-23 | QTR3 | 21/22 | 108 | 1402962.42
| 01 | T1791 | 44034715201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 80 | 227 | 280 | 166.2% | 0 | -53 | 53 | 0 | 98 | 49 | 610558 | 24380 | 586178 | 610558 | 610907 | -3490 | 0 | -3490 | 607417 | 610907 | 104.2% | 1 | 3490 | 0 | 126 | 21 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-03-07 | QTR3 | 21/22 | 108 | 735869.89 | B0 | ACC - LUMP SUM
| 01 | T1794 | 44477915201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 270 | 353 | 352 | 105.6% | 1 | 1 | 0 | 0 | 67 | 16 | 2947759 | 50000 | 2897759 | 2947759 | 2877401 | 0 | 0 | 0 | 2877401 | 2926249 | 101% | 1 | 48848 | 0 | 47 | 20 | 0 | 14 | 0 | 0 | 0 | 2 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3850 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-05-18 | QTR4 | 21/22 | 108 | 2695046.26
| 01 | T1809 | 44624015201 | 2021-05-26 | QTR4 | 20/21 | 2 | 0 | 130 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 569569 | 27338 | 542231 | 569569 | 545539 | 0 | 0 | 0 | 545539 | 545539 | 100.6% | 1 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-06-18 | QTR4 | 21/22 | 113 | 560699.14
| 01 | T1823 | 44212415201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 85 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 631249 | 31254 | 599995 | 631249 | 599995 | 0 | 0 | 0 | 599995 | 599995 | 100% | 1 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-12 | QTR1 | 22/23 |  | 2022-04-12 | QTR4 | 21/22 | 118 | 604209.87 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 6 | 11 | 29 | 1652 | 2368 | 2420 | 83.33% | 5 | -52 | 53 | 0 | 624 | 92 | 86690848 | 332972 | 86357876 | 86236586 | 86832683 | -47490 | 0 | -47490 | 86785193 | 86650993 | 100% | 6 | 5670 | -454262 | 524 | 149 | 0 | 14 | -1707934 | 0 | 0 | 2 | 1727041 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 850099 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 43 | -488897 | 117720
| 01 | E1R65 | 43084915201 | 2019-07-18 | QTR1 | 19/20 | 2 | 4 | 825 | 967 | 964 | 99.64% | 1 | 3 | 0 | 0 | 142 | 0 | 24334683 | 150000 | 24184683 | 24901396 | 24523563 | 0 | 0 | 0 | 24523563 | 24408360 | 100.9% | 1 | -115203 | 566713 | 87 | 55 | 0 | 0 | 220062 | 0 | 0 | 0 | 315298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627938 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-06-24 | QTR4 | 21/22 | 113 | 29026731.23
| 01 | E1U26 | 44488315201 | 2021-07-15 | QTR1 | 21/22 | 1 | 1 | 150 | 161 | 159 | 98.67% | 1 | 2 | 0 | 0 | 11 | 0 | 1247303 | 50000 | 1197303 | 1221387 | 1196429 | 0 | 0 | 0 | 1196429 | 1291777 | 107.9% | 1 | 95349 | -25916 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-07-15 | QTR1 | 22/23 | 118 | 1391481.98
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 2 | 3 | 5 | 975 | 1128 | 1123 | 100% | 2 | 5 | 0 | 0 | 153 | 0 | 25581986 | 200000 | 25381986 | 26122783 | 25719992 | 0 | 0 | 0 | 25719992 | 25700137 | 100% | 2 | -19854 | 540797 | 94 | 59 | 0 | 0 | 220062 | 0 | 0 | 0 | 291218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603858 | 0
| District 01 Totals |  |  |  |  | 8 | 14 | 34 | 2627 | 3496 | 3543 | 87.5% | 7 | -47 | 53 | 0 | 777 | 92 | 112272834 | 532972 | 111739862 | 112359369 | 112552675 | -47490 | 0 | -47490 | 112505185 | 112351130 | 100% | 8 | -14184 | 86535 | 618 | 208 | 0 | 14 | -1487872 | 0 | 0 | 2 | 2018259 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 937782 | 79118 | 0 | 0 | 94241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 43 | 114961 | 117720
| 02 | T2669 | 43544415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 9 | 1200 | 1479 | 1493 | 110.5% | 1 | -14 | 14 | 0 | 177 | 102 | 36475260 | 150000 | 36325260 | 37438271 | 37041923 | -100058 | 0 | -100058 | 36941865 | 37105576 | 102.1% | 1 | 163711 | 963012 | 81 | 86 | 0 | 9 | 653509 | 14083 | 0 | 9 | 75992 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102 | 981827 | 21137 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-03 | QTR1 | 22/23 |  | 2022-03-04 | QTR3 | 21/22 | 216 | 37281732.61
| 02 | T2732 | 21002455201 | 2019-02-27 | QTR3 | 18/19 | 2 | 5 | 700 | 1008 | 1008 | 123% | 0 | 0 | 0 | 0 | 195 | 113 | 23611052 | 160000 | 23451052 | 26613712 | 27048870 | 0 | 0 | 0 | 27048870 | 26998931 | 115.1% | 0 | -49939 | 3002661 | 79 | 68 | 16 | 106 | 2872785 | 1293012 | 0 | 7 | 194376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 113 | 3084932 | 1293012 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 |  | 2022-02-13 | QTR3 | 21/22 | 216 | 26976039.76
| 02 | T2746 | 43761015201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 150 | 191 | 191 | 103.3% | 1 | 0 | 0 | 0 | 36 | 5 | 3853383 | 50000 | 3803383 | 3853383 | 3793632 | 0 | 0 | 0 | 3793632 | 3720865 | 97.83% | 1 | -72767 | 0 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 |  | 2020-05-22 | QTR4 | 19/20 | 209 | 4960764.49
| 02 | T2756 | 43461915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 600 | 789 | 732 | 85.5% | 1 | 57 | 0 | 0 | 219 | -30 | 22598230 | 150000 | 22448230 | 22650960 | 22469154 | 0 | 0 | 0 | 22469154 | 22293734 | 99.31% | 1 | -175420 | 52730 | 133 | 86 | 0 | 0 | 120739 | 2419 | 0 | 0 | 15228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 0 | -30 | 67600 | 2419 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-12 | QTR4 | 21/22 | 216 | 25503399.26
| 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 108.9% | 1 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | 98.63% | 1 | -48916 | 0 | 24 | 22 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94
| 02 | T2784 | 44133715201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 493 | 504 | 166% | 0 | -11 | 11 | 0 | 263 | 30 | 8801980 | 90457 | 8711523 | 9073930 | 8672744 | -41316 | 0 | -41316 | 8631428 | 8634109 | 99.11% | 1 | 2681 | 271950 | 134 | 38 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 |  | 2022-03-03 | QTR3 | 21/22 | 209 | 9187133.29
| 02 | T2807 | 44117315201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 130 | 155 | 152 | 112.3% | 1 | 3 | 0 | 0 | 6 | 19 | 702242 | 21655 | 680587 | 702242 | 666627 | 0 | 0 | 0 | 666627 | 668500 | 98.22% | 1 | 2938 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 |  | 2022-06-03 | QTR4 | 21/22 | 208 | 504802.01
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 7 | 8 | 16 | 3160 | 4360 | 4322 | 71.43% | 5 | 38 | 25 | 0 | 959 | 241 | 99608112 | 672112 | 98936000 | 103898463 | 103209517 | -141374 | 0 | -141374 | 103068143 | 102889366 | 85.71% | 6 | -177712 | 4290353 | 473 | 320 | 16 | 115 | 3647033 | 1309514 | 108 | 53 | 582544 | 274235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 166 | 222 | 4431307 | 1588518
| 02 | E20C3 | 44120015201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 300 | 340 | 275 | 78.33% | 1 | 65 | 0 | 0 | 40 | 0 | 1044910 | 50000 | 994910 | 1044910 | 947808 | 0 | 0 | 0 | 947808 | 947808 | 95.27% | 1 | 0 | 0 | 9 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-07-21 | QTR1 | 22/23 |  | 2022-03-16 | QTR3 | 21/22 | 208 | 1524812.56
| 02 | E20C5 | 43317145201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 180 | 241 | 241 | 103.3% | 1 | 0 | 0 | 0 | 55 | 6 | 1735613 | 50000 | 1685613 | 1735613 | 1621490 | 0 | 0 | 0 | 1621490 | 1633712 | 96.92% | 1 | 12222 | 0 | 43 | 12 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 |  | 2022-05-05 | QTR4 | 21/22 | 214 | 2079687.2
| 02 | E20C6 | 44119815201 | 2021-03-17 | QTR3 | 20/21 | 1 | 0 | 210 | 242 | 240 | 103.3% | 1 | 2 | 0 | 0 | 23 | 9 | 982581 | 50000 | 932581 | 982581 | 924634 | 0 | 0 | 0 | 924634 | 924634 | 99.15% | 1 | 0 | 0 | 8 | 15 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 |  | 2022-05-12 | QTR4 | 21/22 | 208 | 1257557.66
| 02 | E20F6 | 43439815201 | 2021-07-21 | QTR1 | 21/22 | 1 | 0 | 120 | 143 | 143 | 111.7% | 1 | 0 | 0 | 0 | 23 | 0 | 763880 | 40335 | 723545 | 763880 | 682483 | 0 | 0 | 0 | 682483 | 682483 | 94.32% | 1 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-06-16 | QTR4 | 21/22 | 208 | 820679.5
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 4 | 4 | 0 | 810 | 966 | 899 | 100% | 4 | 67 | 0 | 0 | 141 | 15 | 4526984 | 190335 | 4336649 | 4526984 | 4176415 | 0 | 0 | 0 | 4176415 | 4188637 | 100% | 4 | 12222 | 0 | 64 | 63 | 0 | 15 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15 | 0 | 0
| District 02 Totals |  |  |  |  | 11 | 12 | 16 | 3970 | 5326 | 5221 | 81.82% | 9 | 105 | 25 | 0 | 1100 | 256 | 104135096 | 862447 | 103272649 | 108425447 | 107385932 | -141374 | 0 | -141374 | 107244558 | 107078003 | 90.91% | 10 | -165490 | 4290353 | 537 | 383 | 16 | 130 | 3647033 | 1309514 | 122 | 53 | 582544 | 274235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 180 | 237 | 4431307 | 1588518
| 03 | 21585 | 22023925201 | 2002-06-19 | QTR4 | 01/02 | 1 | 0 | 270 | 368 | 426 | 157.8% | 0 | -58 | 58 | 0 | 0 | 0 | 943334 | 50000 | 893334 | 1116958 | 1163142 | 0 | 0 | 0 | 1163142 | 1088438 | 121.8% | 0 | -74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 32797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 123250 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 |  | 2022-01-14 | QTR3 | 21/22 | 313 | 0
| 03 | T3761 | 43776115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 201 | 198 | 98% | 1 | 3 | 0 | 0 | 51 | 0 | 2870000 | 50000 | 2820000 | 2870000 | 2988110 | 0 | 0 | 0 | 2988110 | 3098877 | 109.9% | 1 | 110767 | 0 | 39 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2021-10-29 | QTR2 | 21/22 | 321 | 3648686.57
| 03 | T3781 | 44403115201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 60 | 92 | 89 | 95% | 1 | 3 | 0 | 0 | 32 | 0 | 577089 | 26811 | 550278 | 577089 | 562865 | 0 | 0 | 0 | 562865 | 562865 | 102.3% | 1 | 0 | 0 | 10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-04 | QTR1 | 22/23 |  | 2022-03-28 | QTR3 | 21/22 | 314 | 581614.59
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 3 | 3 | 0 | 480 | 661 | 713 | 66.67% | 2 | -52 | 58 | 0 | 83 | 0 | 4390423 | 126811 | 4263612 | 4564047 | 4714117 | 0 | 0 | 0 | 4714117 | 4750180 | 66.67% | 2 | 36063 | 0 | 49 | 34 | 0 | 0 | 0 | 0 | 0 | 8 | 20440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 32797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 127940 | 0
| 03 | E3O54 | 21860565201 | 2016-01-29 | QTR3 | 15/16 | 7 | 30 | 789 | 2118 | 2097 | 161.1% | 0 | 21 | 0 | 0 | 835 | 494 | 29137700 | 150000 | 28987700 | 36335019 | 36358268 | 0 | 150000 | 150000 | 36508268 | 37056965 | 127.8% | 0 | 724562 | 7197319 | 641 | 185 | 0 | 119 | 1770045 | 309387 | 9 | 3 | 686825 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4298210 | 3702970 | 0 | 0 | 34680 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 494 | 7201002 | 4215560 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 |  | 2022-01-14 | QTR3 | 21/22 | 306 | 26259676.56 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 03 | E3S63 | 4452481G201 | 2019-04-16 | QTR4 | 18/19 | 4 | 3 | 180 | 796 | 796 | 355.6% | 0 | 0 | 0 | 0 | 616 | 0 | 1463233 | 0 | 1463233 | 1553233 | 3732786 | 0 | 0 | 0 | 3732786 | 0 | 0% | 1 | -3732786 | 90000 | 98 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 90000 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2022-07-18 | QTR1 | 22/23 |  | 2021-10-12 | QTR2 | 21/22 | 321 | 1676149.95
| 03 | E3T33 | 40674255201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 199 | 92 | 42.22% | 1 | 107 | 0 | 0 | 16 | 3 | 671000 | 46442 | 624558 | 671000 | 620160 | 0 | 0 | 0 | 620160 | 620160 | 99.3% | 1 | 0 | 0 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 |  | 2022-03-02 | QTR3 | 21/22 | 321 | 974400.82
| 03 | E3T37 | 44154715201 | 2020-12-17 | QTR2 | 20/21 | 4 | 0 | 150 | 219 | 228 | 120% | 1 | -9 | 9 | 0 | 57 | 12 | 1496843 | 58788 | 1438055 | 1496843 | 1510915 | -15210 | 0 | -15210 | 1495705 | 1559564 | 108.4% | 1 | 63859 | 0 | 31 | 17 | 0 | 9 | 9075 | 0 | 0 | 3 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20875 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-08-15 | QTR1 | 22/23 |  | 2021-12-16 | QTR2 | 21/22 | 321 | 2221301.11
| 03 | E3U03 | 43973915201 | 2020-12-17 | QTR2 | 20/21 | 1 | 1 | 335 | 433 | 433 | 101.8% | 1 | 0 | 0 | 0 | 92 | 6 | 3371488 | 50000 | 3321488 | 3376998 | 3480991 | 0 | 0 | 0 | 3480991 | 3693131 | 111.2% | 0 | 271808 | 5510 | 58 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 21671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 22488 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2022-05-31 | QTR4 | 21/22 | 321 | 4444370.86
| 03 | E3U13 | 42357755201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 235 | 180 | 69.44% | 1 | 55 | 0 | 0 | 55 | 0 | 1172134 | 50000 | 1122134 | 1172134 | 929583 | 0 | 0 | 0 | 929583 | 929583 | 82.84% | 1 | 0 | 0 | 21 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2022-05-02 | QTR4 | 21/22 | 314 | 2039783.8
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 6 | 18 | 34 | 1814 | 4000 | 3826 | 66.67% | 4 | 174 | 9 | 0 | 1671 | 515 | 37312398 | 355230 | 36957168 | 44605227 | 46632703 | -15210 | 150000 | 134790 | 46767493 | 43859403 | 66.67% | 4 | -2672557 | 7292829 | 854 | 339 | 0 | 128 | 1779120 | 309387 | 9 | 9 | 820883 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4306710 | 3702970 | 460 | 6 | 35497 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 515 | 7353452 | 4215560
| District 03 Totals |  |  |  |  | 9 | 21 | 34 | 2294 | 4661 | 4539 | 66.67% | 6 | 122 | 67 | 0 | 1754 | 515 | 41702821 | 482041 | 41220780 | 49169274 | 51346820 | -15210 | 150000 | 134790 | 51481610 | 48609583 | 66.67% | 6 | -2636494 | 7292829 | 903 | 373 | 0 | 128 | 1779120 | 309387 | 9 | 17 | 841323 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 4339507 | 3702970 | 460 | 6 | 35497 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 286652 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 541 | 7481392 | 4215560
| 04 | T4522 | 43631915201 | 2019-09-25 | QTR1 | 19/20 | 4 | 0 | 737 | 860 | 857 | 99.59% | 1 | 3 | 0 | 0 | 123 | 0 | 11069050 | 129285 | 10939766 | 11069050 | 10764445 | 0 | 0 | 0 | 10764445 | 10777804 | 98.52% | 1 | 13359 | 0 | 85 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 25517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30043 | 0 | 0 | 0 | 9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64956 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-11 | QTR4 | 21/22 | 412 | 13112789.31
| 04 | T4527 | 43689445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 323 | 400 | 400 | 100% | 1 | 0 | 0 | 0 | 77 | 0 | 1334388 | 50000 | 1284388 | 1536888 | 1454286 | 0 | 0 | 0 | 1454286 | 1453044 | 113.1% | 0 | -1243 | 202500 | 52 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206825 | 202500 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2021-03-08 | QTR3 | 20/21 | 409 | 2037845.47
| 04 | T4544 | 43984715201 | 2020-05-20 | QTR4 | 19/20 | 3 | 3 | 450 | 534 | 531 | 103.1% | 1 | 3 | 0 | 0 | 67 | 17 | 7223964 | 83864 | 7140100 | 7285366 | 7104914 | 0 | 0 | 0 | 7104914 | 7178924 | 100.5% | 1 | 76645 | 61402 | 27 | 40 | 0 | 0 | 15957 | 0 | 0 | 0 | 68904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326 | 0 | 0 | 17 | 28778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 115965 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2022-05-03 | QTR4 | 21/22 | 408 | 8446703.33
| 04 | T4569 | 44177415201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 127 | 138 | 136 | 98.43% | 1 | 2 | 0 | 0 | 11 | 0 | 568800 | 26773 | 542026 | 568800 | 536000 | 0 | 0 | 0 | 536000 | 537990 | 99.26% | 1 | 1990 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-06-10 | QTR4 | 21/22 | 412 | 559587.35
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 4 | 10 | 4 | 1637 | 1932 | 1924 | 100% | 4 | 8 | 0 | 0 | 278 | 17 | 20196202 | 289922 | 19906280 | 20460104 | 19859645 | 0 | 0 | 0 | 19859645 | 19947762 | 75% | 3 | 90751 | 263902 | 172 | 106 | 0 | 0 | 15957 | 0 | 0 | 0 | 104048 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32369 | 0 | 0 | 17 | 39333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 394207 | 202500
| 04 | E4R96 | 43310865201 | 2017-04-05 | QTR4 | 16/17 | 3 | 22 | 1500 | 1665 | 1573 | 93.87% | 1 | 92 | 0 | 0 | 165 | 0 | 102000000 | 150000 | 101850000 | 110058943 | 109950726 | 0 | 1500000 | 1500000 | 111450726 | 110798126 | 108.8% | 1 | -517524 | 8058943 | 68 | 97 | 0 | 0 | 4394429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707076 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7765602 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2021-10-29 | QTR2 | 21/22 | 412 | 111264427.38 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4V05 | 44531515215 | 2021-10-01 | QTR2 | 21/22 | 1 | 0 | 126 | 132 | 96 | 71.43% | 1 | 36 | 0 | 0 | 6 | 0 | 676628 | 32349 | 644279 | 676628 | 625424 | 0 | 0 | 0 | 625424 | 625424 | 97.07% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-06-10 | QTR4 | 21/22 | 408 | 664967.48
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 2 | 4 | 22 | 1626 | 1797 | 1669 | 100% | 2 | 128 | 0 | 0 | 171 | 0 | 102676628 | 182349 | 102494279 | 110735571 | 110576150 | 0 | 1500000 | 1500000 | 112076150 | 111423550 | 100% | 2 | -517524 | 8058943 | 71 | 100 | 0 | 0 | 4394429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707076 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7765602 | 0
| District 04 Totals |  |  |  |  | 6 | 14 | 26 | 3263 | 3729 | 3593 | 100% | 6 | 136 | 0 | 0 | 449 | 17 | 122872830 | 472271 | 122400559 | 131195675 | 130435795 | 0 | 1500000 | 1500000 | 131935795 | 131371312 | 83.33% | 5 | -426773 | 8322845 | 243 | 206 | 0 | 0 | 4410386 | 0 | 0 | 0 | 104048 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2739445 | 0 | 0 | 17 | 703431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 8159809 | 202500
| 05 | T5700 | 44293215201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 170 | 350 | 350 | 117.1% | 1 | 0 | 0 | 0 | 151 | 29 | 1579513 | 50000 | 1529513 | 1579513 | 1554158 | 0 | 0 | 0 | 1554158 | 1562899 | 102.2% | 1 | 19785 | 0 | 33 | 118 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-07-08 | QTR1 | 22/23 | 513 | 1579888.21
| 05 | T5708 | 44101415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 210 | 349 | 348 | 104.3% | 1 | 1 | 0 | 0 | 129 | 10 | 6490691 | 84382 | 6406309 | 6568600 | 6865453 | 0 | 0 | 0 | 6865453 | 7282431 | 113.7% | 0 | 416979 | 77909 | 53 | 76 | 0 | 10 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 92162 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 |  | 2022-03-18 | QTR3 | 21/22 | 515 | 8517614.92
| 05 | T5709 | 44113525201 | 2021-01-27 | QTR3 | 20/21 | 2 | 0 | 280 | 431 | 431 | 105.7% | 1 | 0 | 0 | 0 | 135 | 16 | 8389168 | 85000 | 8304168 | 8389168 | 8382005 | 0 | 0 | 0 | 8382005 | 8827365 | 106.3% | 1 | 485238 | 0 | 98 | 37 | 0 | 4 | 20466 | 0 | 0 | 11 | 55149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 82960 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 |  | 2022-07-06 | QTR1 | 22/23 | 515 | 8661613.49
| 05 | T5716 | 43745115201 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 200 | 246 | 245 | 99.5% | 1 | 1 | 0 | 0 | 46 | 0 | 2263271 | 50000 | 2213271 | 2365506 | 2356172 | 0 | 0 | 0 | 2356172 | 2456514 | 111% | 0 | 130713 | 102234 | 29 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 |  | 2022-06-30 | QTR4 | 21/22 | 509 | 2040645.74
| 05 | T5722 | 44350715201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 1619760 | 50000 | 1569760 | 1619760 | 1578600 | 0 | 0 | 0 | 1578600 | 1598533 | 101.8% | 1 | 19933 | 0 | 8 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 |  | 2022-07-11 | QTR1 | 22/23 | 515 | 1216963.81
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 5 | 6 | 3 | 1010 | 1584 | 1582 | 100% | 5 | 2 | 0 | 0 | 519 | 55 | 20342403 | 319382 | 20023021 | 20522547 | 20736388 | 0 | 0 | 0 | 20736388 | 21727742 | 60% | 3 | 1072648 | 180143 | 221 | 298 | 0 | 14 | 98375 | 0 | 0 | 40 | 191889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 311862 | 0
| 05 | E52A7 | 44194515201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 130 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 1902006 | 50000 | 1852006 | 1902006 | 1790542 | 0 | 0 | 0 | 1790542 | 1806715 | 97.55% | 1 | 16173 | 0 | 44 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14123 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-07-22 | QTR1 | 22/23 |  | 2022-04-08 | QTR4 | 21/22 | 514 | 1695842.63
| 05 | E53A8 | 43632525201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 310 | 383 | 382 | 99.68% | 1 | 1 | 0 | 0 | 73 | 0 | 1713111 | 50000 | 1663111 | 1713111 | 1658956 | 0 | 0 | 0 | 1658956 | 1658958 | 99.75% | 1 | 33039 | 0 | 24 | 49 | 0 | 0 | 24573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24573 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-08 | QTR1 | 22/23 |  | 2022-06-17 | QTR4 | 21/22 | 513 | 1970561.3
| 05 | E56A2 | 44113415201 | 2021-07-07 | QTR1 | 21/22 | 1 | 1 | 110 | 173 | 173 | 118.2% | 1 | 0 | 0 | 0 | 43 | 20 | 1492986 | 50000 | 1442986 | 1574717 | 1530292 | 0 | 0 | 0 | 1530292 | 1569043 | 108.7% | 1 | 38751 | 81732 | 12 | 31 | 0 | 20 | 81732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 81732 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2022-05-23 | QTR4 | 21/22 | 513 | 1629586.92
| 05 | E58A6 | 44845415201 | 2021-12-07 | QTR2 | 21/22 | 1 | 0 | 230 | 234 | 120 | 50.43% | 1 | 114 | 0 | 0 | 4 | 0 | 710278 | 29452 | 680826 | 710278 | 702088 | 0 | 0 | 0 | 702088 | 702088 | 103.1% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-22 | QTR1 | 22/23 |  | 2022-08-15 | QTR1 | 22/23 | 514 | 626464
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 4 | 4 | 1 | 780 | 1005 | 890 | 100% | 4 | 115 | 0 | 0 | 205 | 20 | 5818381 | 179452 | 5638929 | 5900112 | 5681878 | 0 | 0 | 0 | 5681878 | 5736804 | 100% | 4 | 87963 | 81732 | 80 | 125 | 0 | 20 | 106305 | 0 | 0 | 0 | 7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 120428 | 0
| District 05 Totals |  |  |  |  | 9 | 10 | 4 | 1790 | 2589 | 2472 | 100% | 9 | 117 | 0 | 0 | 724 | 75 | 26160784 | 498834 | 25661950 | 26422659 | 26418266 | 0 | 0 | 0 | 26418266 | 27464546 | 77.78% | 7 | 1160611 | 261875 | 301 | 423 | 0 | 34 | 204680 | 0 | 0 | 40 | 199695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 1 | 21597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 432290 | 0
| 06 | T6433 | 42440715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 15 | 700 | 1063 | 940 | 101.3% | 1 | 123 | 0 | 0 | 231 | 132 | 67230501 | 151730 | 67078771 | 72750415 | 73542354 | 0 | 4200000 | 4200000 | 77742354 | 73243755 | 109.2% | 1 | -4309470 | 5519914 | 198 | 33 | 0 | 0 | 557153 | 37295 | 0 | 132 | 4723947 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450249 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -309497 | 0 | 0 | 132 | 5471149 | 3100941 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 |  | 2021-12-16 | QTR2 | 21/22 | 606 | 76112026.4 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6480 | 44018215201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 170 | 277 | 266 | 93.53% | 1 | 11 | 0 | 0 | 107 | 0 | 515515 | 29915 | 485600 | 515515 | 456395 | 0 | 0 | 0 | 456395 | 453272 | 93.34% | 1 | -3123 | 0 | 87 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-30 | QTR1 | 22/23 |  | 2022-06-27 | QTR4 | 21/22 | 636 | 619720.15
| 06 | T6491 | 44183415201 | 2020-03-25 | QTR3 | 19/20 | 2 | 1 | 220 | 251 | 235 | 101.4% | 1 | 16 | 0 | 0 | 31 | 0 | 2816134 | 50000 | 2766134 | 2863544 | 2825607 | 0 | 200000 | 200000 | 3025607 | 2850019 | 103% | 1 | -175589 | 47410 | 3 | 9 | 19 | 0 | 46968 | 12079 | 0 | 0 | 5789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 83185 | 12079 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-09-08 | QTR1 | 22/23 |  | 2021-06-09 | QTR4 | 20/21 | 613 | 3231278.28 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6497 | 44516815201 | 2020-11-18 | QTR2 | 20/21 | 3 | 0 | 150 | 259 | 257 | 116% | 1 | 2 | 0 | 0 | 109 | 0 | 541368 | 29764 | 511604 | 541368 | 498909 | 0 | 0 | 0 | 498909 | 498909 | 97.52% | 1 | 0 | 0 | 65 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 4133 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 12361 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 |  | 2022-05-23 | QTR4 | 21/22 | 613 | 585940.8
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 4 | 10 | 16 | 1240 | 1850 | 1698 | 100% | 4 | 152 | 0 | 0 | 478 | 132 | 71103518 | 261409 | 70842109 | 76670842 | 77323265 | 0 | 4400000 | 4400000 | 81723265 | 77045955 | 100% | 4 | -4488182 | 5567324 | 353 | 80 | 19 | 0 | 604121 | 49374 | 0 | 132 | 4729736 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 484809 | 0 | 0 | 0 | 22961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -309497 | 0 | 45 | 132 | 5566695 | 3113020
| 06 | E6L38 | 25168465201 | 2018-05-02 | QTR4 | 17/18 | 2 | 6 | 1000 | 1287 | 1259 | 109% | 1 | 28 | 0 | 0 | 169 | 118 | 56331262 | 150000 | 56181262 | 61782326 | 61740658 | 0 | 0 | 0 | 61740658 | 61689883 | 109.8% | 1 | -2495 | 5451064 | 115 | 54 | 0 | 0 | 408613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4906149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76933 | 0 | 0 | 118 | 5342031 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-08-10 | QTR1 | 22/23 |  | 2022-02-11 | QTR3 | 21/22 | 606 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 06 | E6M84 | 44253915201 | 2020-08-27 | QTR1 | 20/21 | 2 | 1 | 150 | 220 | 220 | 112.7% | 1 | 0 | 0 | 0 | 70 | 0 | 608490 | 30869 | 577621 | 625609 | 579687 | 0 | 0 | 0 | 579687 | 585088 | 101.3% | 1 | 5401 | 17119 | 40 | 11 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1768 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-05-25 | QTR4 | 21/22 | 613 | 624645.65
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 2 | 4 | 7 | 1150 | 1507 | 1479 | 100% | 2 | 28 | 0 | 0 | 239 | 118 | 56939752 | 180869 | 56758883 | 62407935 | 62320345 | 0 | 0 | 0 | 62320345 | 62274971 | 100% | 2 | 2906 | 5468183 | 155 | 65 | 19 | 0 | 408613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4907917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76933 | 0 | 19 | 118 | 5343799 | 0
| District 06 Totals |  |  |  |  | 6 | 14 | 23 | 2390 | 3357 | 3177 | 100% | 6 | 180 | 0 | 0 | 717 | 250 | 128043270 | 442278 | 127600992 | 139078777 | 139643610 | 0 | 4400000 | 4400000 | 144043610 | 139320926 | 100% | 6 | -4485276 | 11035507 | 508 | 145 | 38 | 0 | 1012734 | 49374 | 0 | 132 | 4729736 | 3063646 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 118 | 5392726 | 0 | 0 | 0 | 22961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -386430 | 0 | 64 | 250 | 10910494 | 3113020
| 07 | T7408 | 42895315201 | 2018-06-13 | QTR4 | 17/18 | 4 | 25 | 1115 | 1267 | 1253 | 98.74% | 1 | 14 | 0 | 0 | 152 | 0 | 52309860 | 150000 | 52159860 | 53697121 | 53886362 | 0 | 0 | 0 | 53886362 | 53722937 | 103% | 1 | -163425 | 1387261 | 66 | 86 | 0 | 0 | 630838 | 47733 | 0 | 0 | 729633 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117242 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -227170 | 0 | 0 | 0 | 1315397 | 162073 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-07-15 | QTR1 | 22/23 |  | 2022-02-18 | QTR3 | 21/22 | 714 | 61751000
| 07 | T7444 | 44108325201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 443 | 585 | 581 | 110.4% | 1 | 4 | 0 | 0 | 92 | 50 | 10034121 | 129550 | 9904571 | 10350046 | 9810424 | 0 | 0 | 0 | 9810424 | 9853179 | 99.48% | 1 | 103829 | 315925 | 59 | 33 | 0 | 0 | 0 | 0 | 0 | 50 | 344704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 411706 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2022-05-31 | QTR4 | 21/22 | 714 | 12990036.6
| 07 | T7459 | 44550725201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 210 | 355 | 354 | 110.5% | 1 | 1 | 0 | 0 | 145 | 0 | 1887858 | 50000 | 1837858 | 1887858 | 1854136 | 0 | 0 | 0 | 1854136 | 1854136 | 100.9% | 1 | 38612 | 0 | 100 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-09-12 | QTR1 | 22/23 |  | 2022-07-07 | QTR1 | 22/23 | 799 | 2521800
| 07 | T7463 | 43762415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 200 | 271 | 271 | 111.5% | 1 | 0 | 0 | 0 | 50 | 21 | 5399019 | 50000 | 5349019 | 5449019 | 5598998 | 0 | 0 | 0 | 5598998 | 5769676 | 107.9% | 1 | 201519 | 50000 | 30 | 18 | 0 | 0 | 15416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15416 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-08-02 | QTR1 | 22/23 |  | 2022-04-08 | QTR4 | 21/22 | 799 | 5600000
| 07 | T7474 | 44555415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 200 | 222 | 175 | 76.5% | 1 | 47 | 0 | 0 | 22 | 0 | 755204 | 42000 | 713204 | 755204 | 735925 | 0 | 0 | 0 | 735925 | 735925 | 103.2% | 1 | 40677 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-06 | QTR4 | 21/22 | 796 | 918700
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 5 | 10 | 28 | 2168 | 2700 | 2634 | 100% | 5 | 66 | 0 | 0 | 461 | 71 | 70386062 | 421550 | 69964512 | 72139248 | 71885845 | 0 | 0 | 0 | 71885845 | 71935853 | 100% | 5 | 221212 | 1753186 | 261 | 175 | 0 | 0 | 646254 | 47733 | 0 | 50 | 1074337 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184244 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -227170 | 0 | 0 | 50 | 1742519 | 162073
| 07 | E7L92 | 43669715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 11 | 675 | 1004 | 1004 | 115.7% | 1 | 0 | 0 | 0 | 301 | 28 | 4257317 | 50000 | 4207317 | 10851592 | 9627641 | 0 | 0 | 0 | 9627641 | 9622285 | 228.7% | 0 | -5356 | 6594276 | 66 | 157 | 32 | 0 | 8007524 | 0 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2044097 | 0 | 78 | 28 | 6594983 | 8995 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-08 | QTR1 | 22/23 |  | 2022-01-26 | QTR3 | 21/22 | 799 | 4476953.25
| 07 | E7O21 | 44366415201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 44 | 73.33% | 1 | 16 | 0 | 0 | 0 | 0 | 397254 | 14000 | 383254 | 397254 | 370201 | 0 | 0 | 0 | 370201 | 370201 | 96.59% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-11 | QTR1 | 22/23 |  | 2022-04-26 | QTR4 | 21/22 | 796 | 296700
| 07 | E7R28 | 44769615201 | 2021-05-10 | QTR4 | 20/21 | 1 | 0 | 310 | 341 | 341 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 2063258 | 50000 | 2013258 | 2063258 | 2025710 | 0 | 0 | 0 | 2025710 | 2046401 | 101.6% | 1 | 20691 | 0 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2022-06-17 | QTR4 | 21/22 | 796 | 1523991.28 | LBDB | LOW BID DESIGN BUILD
| 07 | E7R29 | 43982995201 | 2021-05-17 | QTR4 | 20/21 | 2 | 0 | 321 | 329 | 324 | 98.44% | 1 | 5 | 0 | 0 | 8 | 0 | 1887000 | 50000 | 1837000 | 1887000 | 1837000 | 0 | 0 | 0 | 1837000 | 1837000 | 100% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 |  | 2022-06-03 | QTR4 | 21/22 | 796 | 2845446.28 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 4 | 6 | 11 | 1366 | 1734 | 1713 | 100% | 4 | 21 | 0 | 0 | 340 | 28 | 8604829 | 164000 | 8440829 | 15199104 | 13860552 | 0 | 0 | 0 | 13860552 | 13875887 | 75% | 3 | 15335 | 6594276 | 88 | 174 | 32 | 0 | 8007524 | 0 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2044097 | 0 | 78 | 28 | 6594983 | 8995
| District 07 Totals |  |  |  |  | 9 | 16 | 39 | 3534 | 4434 | 4347 | 100% | 9 | 87 | 0 | 0 | 801 | 99 | 78990891 | 585550 | 78405341 | 87338352 | 85746397 | 0 | 0 | 0 | 85746397 | 85811740 | 88.89% | 8 | 236547 | 8347462 | 349 | 349 | 32 | 0 | 8653778 | 47733 | 0 | 50 | 1339999 | 90710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 550138 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2271267 | 0 | 78 | 78 | 8337502 | 171068
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8S34 | 43798655201 | 2021-03-09 | QTR3 | 20/21 | 1 | 1 | 160 | 200 | 190 | 93.75% | 1 | 10 | 0 | 0 | 40 | 0 | 878913 | 50000 | 828913 | 870049 | 822741 | 0 | 0 | 0 | 822741 | 823180 | 99.31% | 1 | 7889 | -8864 | 24 | 16 | 0 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 0 | 0 | -5345 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 |  | 2022-05-06 | QTR4 | 21/22 | 854 | 1113411.37
| 08 | E8S70 | 44262215201 | 2020-11-17 | QTR2 | 20/21 | 5 | 0 | 303 | 380 | 378 | 101.7% | 1 | 2 | 0 | 0 | 77 | 0 | 4113457 | 78161 | 4035296 | 4113457 | 3489511 | 0 | 0 | 0 | 3489511 | 3489532 | 86.48% | 1 | 21 | 0 | 45 | 25 | 0 | 0 | 11159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11159 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 |  | 2022-06-13 | QTR4 | 21/22 | 854 | 7220597.77
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 2 | 6 | 1 | 463 | 580 | 568 | #VALUE! | 2 | 12 | 0 | 0 | 117 | 0 | 4992370 | 128161 | 4864209 | 4983506 | 4312252 | 0 | 0 | 0 | 4312252 | 4312712 | 100% | 2 | 7910 | -8864 | 69 | 41 | 0 | 0 | 14678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 7 | 0 | 5814 | 0
| District 08 Totals |  |  |  |  | 2 | 6 | 1 | 463 | 580 | 568 | 100% | 2 | 12 | 0 | 0 | 117 | 0 | 4992370 | 128161 | 4864209 | 4983506 | 4312252 | 0 | 0 | 0 | 4312252 | 4312712 | 100% | 2 | 7910 | -8864 | 69 | 41 | 0 | 0 | 14678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 7 | 0 | 5814 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 34 | 58 | 96 | 11347 | 15455 | 15293 | 88.24% | 30 | 162 | 136 | 0 | 3402 | 608 | 372717568 | 2424158 | 370293410 | 384491837 | 384561460 | -188864 | 4400000 | 4211136 | 388772596 | 384947851 | 85.29% | 29 | -3239550 | 11600646 | 2053 | 1162 | 35 | 143 | 3303806 | 1406621 | 108 | 285 | 8430035 | 3458198 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 129 | 1836644 | 83887 | 0 | 18 | 226363 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 114704 | 40000 | 0 | 0 | 34563 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -2052483 | 0 | 211 | 545 | 12085633 | 5183831
| Statewide District Let Contracts SubTotal |  |  |  |  | 26 | 49 | 81 | 8984 | 12717 | 12167 | 92.31% | 24 | 550 | 9 | 0 | 3037 | 696 | 246453328 | 1580396 | 244872932 | 274481222 | 273280287 | -15210 | 1650000 | 1634790 | 274915077 | 271372101 | 88.46% | 23 | -3083599 | 28027896 | 1475 | 966 | 51 | 163 | 14930731 | 309387 | 23 | 9 | 1385569 | 33322 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 485 | 12381597 | 3702970 | 460 | 6 | 704490 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | -2129894 | 0 | 587 | 696 | 27787936 | 4224555
| Statewide Totals |  |  |  |  | 60 | 107 | 177 | 20331 | 28172 | 27460 | 90% | 54 | 712 | 145 | 0 | 6439 | 1304 | 619170896 | 4004554 | 615166342 | 658973059 | 657841747 | -204074 | 6050000 | 5845926 | 663687673 | 656319952 | 86.67% | 52 | -6323149 | 39628542 | 3528 | 2128 | 86 | 306 | 18234537 | 1716008 | 131 | 294 | 9815604 | 3491520 | 0 | 0 | 266702 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 614 | 14218241 | 3786857 | 460 | 24 | 930853 | 67306 | 0 | 0 | 0 | 0 | 0 | 0 | 84599 | 0 | 0 | 0 | 326652 | 40000 | 0 | 33 | 178760 | 144197 | 32 | 0 | 0 | 0 | 0 | -30 | -4182377 | 0 | 798 | 1241 | 39873569 | 9408386

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1R65 | 43084915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-18 | 24334683 | 24901396 | 24523563 | 566712.9 | 0 | 24408360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24523563 | 24408360 | -115203 | 29026731
1 | E1U26 | 44488315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-15 | 1247303 | 1221387 | 1196429 | -25916 | 0 | 1291777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196429 | 1291777 | 95349 | 1391482
1 | T1709 | 20103225201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-05-23 | 80840173 | 80370929 | 81141842 | -469243.92 | -44000 | 81007287 | 0 | 0 | 0 | 0 | 0 | -44000 | -44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44000 | 81097842 | 81007287 | -90555 | 83257743 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1784 | 44210725201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 1091540 | 1106522 | 1100887 | 14982.17 | 0 | 1100887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100887 | 1100887 | 0 | 1402962
1 | T1791 | 44034715201 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-01-27 | 610558 | 610558 | 610907 | 0 | -3490 | 610907 | -3490 | 0 | 0 | 0 | 0 | 0 | -3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3490 | 607417 | 610907 | 3490 | 735870 | B0 | ACC - LUMP SUM
1 | T1794 | 44477915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 2947759 | 2947759 | 2877401 | 0 | 0 | 2926249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2877401 | 2926249 | 48848 | 2695046
1 | T1809 | 44624015201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 569569 | 569569 | 545539 | 0 | 0 | 545539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545539 | 545539 | 0 | 560699
1 | T1823 | 44212415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-09-29 | 631249 | 631249 | 599995 | 0 | 0 | 599995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599995 | 599995 | 0 | 604210 | B0 | ACC - LUMP SUM
2 | E20C3 | 44120015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-12-16 | 1044910 | 1044910 | 947808 | 0 | 0 | 947808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947808 | 947808 | 0 | 1524813
2 | E20C5 | 43317145201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 1735613 | 1735613 | 1621490 | 0 | 0 | 1633712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621490 | 1633712 | 12222 | 2079687
2 | E20C6 | 44119815201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-17 | 982581 | 982581 | 924634 | 0 | 0 | 924634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924634 | 924634 | 0 | 1257558
2 | E20F6 | 43439815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-07-21 | 763880 | 763880 | 682483 | 0 | 0 | 682483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682483 | 682483 | 0 | 820680
2 | T2669 | 43544415201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2017-10-25 | 36475260 | 37438271 | 37041923 | 963011.63 | -100058 | 37105576 | -100058 | 0 | 0 | 0 | 0 | 0 | -100058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100058 | 36941865 | 37105576 | 163711 | 37281733
2 | T2732 | 21002455201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 23611052 | 26613712 | 27048870 | 3002660.63 | 0 | 26998931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27048870 | 26998931 | -49939 | 26976040
2 | T2746 | 43761015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 3853383 | 3853383 | 3793632 | 0 | 0 | 3720865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3793632 | 3720865 | -72767 | 4960764
2 | T2756 | 43461915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-29 | 22598230 | 22650960 | 22469154 | 52729.99 | 0 | 22293734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22469154 | 22293734 | -175420 | 25503399
2 | T2777 | 44126215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 3565965 | 3565965 | 3516567 | 0 | 0 | 3519561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3516567 | 3519561 | 2994 | 4228845
2 | T2784 | 44133715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 8801980 | 9073930 | 8672744 | 271949.84 | -41316 | 8634109 | -41316 | 0 | 0 | 0 | 0 | 0 | -41316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41316 | 8631428 | 8634109 | 2681 | 9187133
2 | T2807 | 44117315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-03-31 | 702242 | 702242 | 667693 | 0 | 0 | 669566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667693 | 669566 | 1873 | 504802
3 | 21585 | 22023925201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2002-06-19 | 943334 | 1116958 | 1163142 | 0 | 0 | 1088438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163142 | 1088438 | -74704 | 0
3 | E3O54 | 21860565201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-01-29 | 29137700 | 36335019 | 36358268 | 7197319.1 | 150000 | 37232830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 36508268 | 37232830 | 724562 | 26259677 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
3 | E3S63 | 4452481G201 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2019-04-16 | 1463233 | 1553233 | 3732786 | 89999.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3732786 | 0 | -3732786 | 1676150
3 | E3T33 | 40674255201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-08-12 | 671000 | 671000 | 620160 | 0 | 0 | 620160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620160 | 620160 | 0 | 974401
3 | E3T37 | 44154715201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 1496843 | 1496843 | 1510915 | 0 | -15210 | 1559564 | -15210 | 0 | 0 | 0 | 0 | 0 | -15210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15210 | 1495705 | 1559564 | 63859 | 2221301
3 | E3U03 | 43973915201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 3371488 | 3376998 | 3540659 | 5510 | 0 | 3752799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3540659 | 3752799 | 212140 | 4444371
3 | E3U13 | 42357755201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2021-08-12 | 1172134 | 1172134 | 929583 | 0 | 0 | 929583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929583 | 929583 | 0 | 2039784
3 | T3761 | 43776115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2870000 | 2870000 | 2988110 | 0 | 0 | 3098877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2988110 | 3098877 | 110767 | 3648687
3 | T3781 | 44403115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 577089 | 577089 | 562865 | 0 | 0 | 562865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562865 | 562865 | 0 | 581615
4 | E4R96 | 43310865201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-04-05 | 102000000 | 110058943 | 109950726 | 8058942.97 | 1500000 | 110933202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 111450726 | 110933202 | -517524 | 111264427 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4V05 | 44531515215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | 676628 | 676628 | 625424 | 0 | 0 | 625424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625424 | 625424 | 0 | 664967
4 | T4522 | 43631915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11069050 | 11069050 | 10764445 | 0 | 0 | 10777804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10764445 | 10777804 | 13359 | 13112789
4 | T4527 | 43689445201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 1334388 | 1536888 | 1454286 | 202500 | 0 | 1453044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454286 | 1453044 | -1243 | 2037845
4 | T4544 | 43984715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 7223964 | 7285366 | 7107549 | 61402.36 | 0 | 7181559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7107549 | 7181559 | 74010 | 8446703
4 | T4569 | 44177415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-07-28 | 568800 | 568800 | 536000 | 0 | 0 | 537990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536000 | 537990 | 1990 | 559587
5 | E52A7 | 44194515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-02-02 | 1902006 | 1902006 | 1790542 | 0 | 0 | 1806715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1790542 | 1806715 | 16173 | 1695843
5 | E53A8 | 43632525201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 1713111 | 1713111 | 1691993 | 0 | 0 | 1691994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1691993 | 1691994 | 2 | 1970561
5 | E56A2 | 44113415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-07-07 | 1492986 | 1574717 | 1530292 | 81731.55 | 0 | 1583974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530292 | 1583974 | 53682 | 1629587
5 | E58A6 | 44845415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-12-07 | 710278 | 710278 | 702088 | 0 | 0 | 702088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702088 | 702088 | 0 | 626464
5 | T5700 | 44293215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 1579513 | 1579513 | 1565201 | 0 | 0 | 1573943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565201 | 1573943 | 8741 | 1579888
5 | T5708 | 44101415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 6490691 | 6568600 | 6865453 | 77909.15 | 0 | 7282431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6865453 | 7282431 | 416979 | 8517615
5 | T5709 | 44113525201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 8389168 | 8389168 | 8421882 | 0 | 0 | 8867242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8421882 | 8867242 | 445360 | 8661613
5 | T5716 | 43745115201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 2263271 | 2365506 | 2386543 | 102234.42 | 0 | 2486885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386543 | 2486885 | 100342 | 2040646
5 | T5722 | 44350715201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-07-28 | 1619760 | 1619760 | 1578600 | 0 | 0 | 1598533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1578600 | 1598533 | 19933 | 1216964
6 | E6L38 | 25168465201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-05-02 | 56331262 | 61782326 | 61740658 | 5451064.21 | 0 | 61738163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61740658 | 61738163 | -2495 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
6 | E6M84 | 44253915201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 608490 | 625609 | 579687 | 17119 | 0 | 585088 | -3380 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579687 | 585088 | 5401 | 624646
6 | T6433 | 42440715201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-06-13 | 67230501 | 72750415 | 73542354 | 5519913.82 | 4200000 | 73447058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 200000 | 0 | 4200000 | 4200000 | 77742354 | 73447058 | -4295296 | 76112026 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6480 | 44018215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 515515 | 515515 | 456395 | 0 | 0 | 453272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456395 | 453272 | -3123 | 619720
6 | T6491 | 44183415201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 2816134 | 2863544 | 2825607 | 47410 | 200000 | 2850019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3025607 | 2850019 | -175589 | 3231278 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6497 | 44516815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 541368 | 541368 | 498909 | 0 | 0 | 498909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498909 | 498909 | 0 | 585941
7 | E7L92 | 43669715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 4257317 | 10851592 | 9627641 | 6594275.62 | 0 | 9622285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9627641 | 9622285 | -5356 | 4476953
7 | E7O21 | 44366415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-08 | 397254 | 397254 | 370201 | 0 | 0 | 370201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370201 | 370201 | 0 | 296700
7 | E7R28 | 44769615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-05-10 | 2063258 | 2063258 | 2025710 | 0 | 0 | 2046401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025710 | 2046401 | 20691 | 1523991 | LBDB | LOW BID DESIGN BUILD
7 | E7R29 | 43982995201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-05-17 | 1887000 | 1887000 | 1837000 | 0 | 0 | 1837000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837000 | 1837000 | 0 | 2845446 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
7 | T7408 | 42895315201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-06-13 | 52309860 | 53697121 | 53886362 | 1387260.64 | 0 | 53722937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53886362 | 53722937 | -163425 | 61751000
7 | T7444 | 44108325201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 10034121 | 10350046 | 9871498 | 315924.97 | 0 | 9914253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871498 | 9914253 | 42755 | 12990037
7 | T7459 | 44550725201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 1887858 | 1887858 | 1892749 | 0 | 0 | 1892749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892749 | 1892749 | 0 | 2521800
7 | T7463 | 43762415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 5399019 | 5449019 | 5629840 | 50000 | 0 | 5800518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5629840 | 5800518 | 170678 | 5600000
7 | T7474 | 44555415201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 755204 | 755204 | 776603 | 0 | 0 | 776603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776603 | 776603 | 0 | 918700
8 | E8S34 | 43798655201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-09 | 878913 | 870049 | 830191 | -8863.5 | 0 | 830630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830191 | 830630 | 439 | 1113411
8 | E8S70 | 44262215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-11-17 | 4113457 | 4113457 | 3489511 | 0 | 0 | 3489532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3489511 | 3489532 | 21 | 7220598

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 |  | 40233.96 |  | 9396.46 | 0 | 80713.4 |  | 130343.82 |  | 112272834 | 0.04421% | 49630.42
02 |  | 16367.99 |  | 271949.84 | 11487.16 | 1307702.82 | -299969.94 | 1307537.87 |  | 104135096 | 0.2879% | 299804.99
03 |  | 2970 | 0 | 3674391.93 | 382195.69 | 243082.74 |  | 4302640.36 |  | 41702821 | 9.734% | 4059557.62
04 |  | 944.04 |  |  | 29937 | 207015.73 |  | 237896.77 |  | 122872830 | 0.02513% | 30881.04
05 |  | 1806.93 |  |  | 2148.4 | 0 |  | 3955.33 |  | 26160784 | 0.01512% | 3955.33
06 |  | 70087.7 |  | 0 | 3030853.3 | 12629.4 |  | 3113570.4 |  | 128043270 | 2.422% | 3100941
07 |  | 140760.37 |  | 8481.99 | 40958.8 | 0 | -99989.98 | 90211.18 |  | 78990891 | 0.2408% | 190201.16
08 | [5 empty] | 0 |  | 0 |  | 4992370 | 0% | 0
Grand Total |  | 273170.99 | 0 | 3964220.22 | 3497580.35 | 1851144.09 | -399959.92 | 9186155.73 |  | 619170896 | 1.249% | 7734971.56
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 |  | 2 |  | 0 | 0 | 90 |  | 92 |  | 2
02 |  | 15 |  | 30 | 0 | 192 | 0 | 237 |  | 45
03 |  | 11 | 2 | 325 | 153 | 50 |  | 541 |  | 491
04 |  | 0 |  |  | 17 | 0 |  | 17 |  | 17
05 |  | 0 |  |  | 0 | 75 |  | 75 |  | 0
06 |  | 0 |  | 0 | 132 | 118 |  | 250 |  | 132
07 |  | 0 |  | 0 | 0 | 78 | 0 | 78 |  | 0
08 | [5 empty] | 0 |  | 0 |  | 0
Grand Total |  | 28 | 2 | 355 | 302 | 603 | 0 | 1290 |  | 687
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 | [8 empty] | 0 | 2 | 2627 | 0.07613%
02 |  |  |  | 91 |  | 100 | 191 |  | 91 | 136 | 3970 | 3.426%
03 |  | 163 |  |  |  | 337 | 500 |  | 163 | 654 | 2294 | 28.51%
04 | [5 empty] | 20 | 20 |  | 0 | 17 | 3263 | 0.521%
05 | [8 empty] | 0 | 0 | 1790 | 0%
06 | [5 empty] | 64 | 64 |  | 0 | 132 | 2390 | 5.523%
07 | [5 empty] | 133 | 133 |  | 0 | 0 | 3534 | 0%
08 | [5 empty] | 26 | 26 |  | 0 | 0 | 463 | 0%
Grand Total |  | 163 |  | 91 |  | 680 | 934 |  | 254 | 941 | 20331 | 4.628%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1R65 | 43084915201 | 002 | 2 |  | 1 | 004 | 127200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | [13 empty] | Avoidable, CEI Consultant
01 | E1R65 | 43084915201 | 014 | 2 |  | 1 | 101 | 20409.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 2 | 115 | 38777.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 3 | 112 | 55111.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 4 | 503 | 86877.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 | 014 | 2 |  | 5 | 012 | 31902.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R65 | 43084915201 | 022 | 2 |  | 1 | 003 | 55876.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R65 | 43084915201 | 022 | 2 |  | 2 | 503 | 558 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 | 025 | 2 |  | 1 | 107 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1U26 | 44488315201 | 001 | 2 |  | 1 | 107 | -25916 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 004 | 2 |  | 1 | 003 | -1772543.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1709 | 20103225201 | 007 | 2 |  | 1 | 115 | 3897 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 008 | 2 |  | 1 | 305 | -557029.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 010 | 2 |  | 1 | 305 | -152551.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 011 | 2 |  | 1 | 305 | -737868.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 014 | 2 |  | 1 | 503 | 786282.89 | 79117.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1709 | 20103225201 | 018 | 2 | 850 | 1 | 105 | 6810.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 2 | 105 | 43240.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 3 | 024 | 15138.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 4 | 105 | 25394.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 5 | 105 | 18021.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 6 | 105 | 4026.12 | 4026.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 7 | 118 | 8902.23 | 8902.23 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 8 | 007 | 1.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 018 | 2 | 850 | 9 | 024 | 8465.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 036 | 2 |  | 1 | 923 | 55001.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 039 | 2 |  | 1 | 106 | -116158.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1709 | 20103225201 | 042 | 2 |  | 1 | 924 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1709 | 20103225201 | 043 | 2 |  | 1 | 105 | 182000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 1 | 128 | 715754.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 2 | 126 | 138841.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 3 | 105 | 42788.61 | 2167.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 057 | 2 |  | 1 | 126 | 309944.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1709 | 20103225201 | 058 | 2 |  | 1 | 107 | -2.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 059 | 2 |  | 1 | 928 | 40981.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 1 | 007 | 5323.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 2 | 001 | 11398.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 3 | 107 | 16232.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 4 | 105 | 8067.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 5 | 105 | 4225.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 6 | 107 | 16233 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 7 | 001 | 5071.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 8 | 107 | 6252.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 9 | 107 | 616 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 10 | 105 | 1595.88 | 1595.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 11 | 105 | 24203 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 12 | 107 | 780.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 064 | 2 |  | 1 | 012 | 8273.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1709 | 20103225201 | 067 | 2 | 850 | 1 | 001 | 32936.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 070 | 2 |  | 1 | 105 | 25959 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 070 | 2 |  | 2 | 101 | 10551.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1709 | 20103225201 | 074 | 2 |  | 1 | 007 | -20743.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 081 | 2 |  | 3 | 115 | 4952.76 | 4952.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 082 | 2 |  | 1 | 118 | 45957.5 | 16957.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1709 | 20103225201 | 087 | 2 |  | 1 | 128 | 113905.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 092 | 2 |  | 1 | 022 | 51320.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 092 | 2 |  | 2 | 024 | 14422.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1784 | 44210725201 | 001 | 2 |  | 1 | 112 | -48833.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1784 | 44210725201 | 013 | 2 |  | 1 | 503 | 63815.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 005 | 2 |  | 1 | 001 | 1647.6 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 013 | 2 |  | 1 | 009 | 14584.48 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
02 | T2669 | 43544415201 | 020 | 2 |  | 1 | 001 | 47635.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 021 | 2 |  | 1 | 503 | 247556.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 025 | 2 | 850 | 1 | 503 | 0 | 4769.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 025 | 2 | 850 | 2 | 003 | 6765.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 3 | 003 | 3517.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 4 | 112 | 2285.4 | 2285.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2669 | 43544415201 | 025 | 2 | 850 | 5 | 003 | 14082.59 | 14082.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 6 | 001 | 18484.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 027 | 2 |  | 1 | 001 | 325407.99 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 033 | 2 |  | 1 | 001 | 29000 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 036 | 2 |  | 1 | 012 | 147179.66 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2669 | 43544415201 | 050 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 84 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2732 | 21002455201 | 020 | 2 |  | 1 | 003 | 371906.87 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 1 | 001 | 40218.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 2 | 001 | 11423.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 3 | 023 | 17770.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 4 | 003 | 18283.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 5 | 001 | 4012.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 6 | 003 | 1521.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 8 | 101 | 11846.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2732 | 21002455201 | 021 | 2 | 850 | 9 | 003 | 7835.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 031 | 2 |  | 1 | 001 | 96454.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 033 | 2 |  | 1 | 112 | 97807.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2732 | 21002455201 | 034 | 2 |  | 1 | 012 | 2286491.33 | 1293012.1 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2756 | 43461915201 | 006 | 2 |  | 1 | 305 | -68366.53 | 0 | 0 |  | N | -30 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2756 | 43461915201 | 006 | 2 |  | 2 | 101 | 15228 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2756 | 43461915201 | 006 | 2 |  | 3 | 004 | 105868.52 | 2418.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2784 | 44133715201 | 009 | 2 |  | 1 | 113 | 271949.84 | 271949.84 | 2 |  | N | 30 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 012 | 2 |  | 1 | 003 | 392550 | 0 | 5 |  | N | 110 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 015 | 2 |  | 1 | 503 | 10043.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 017 | 2 |  | 1 | 105 | 68404.65 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 1 | 007 | 2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 2 | 107 | 2660 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 3 | 008 | 984 | 984 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 4 | 007 | -2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 5 | 007 | 2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 6 | 107 | -2660 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 7 | 107 | 2660 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 8 | 008 | -984 | 0 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 9 | 008 | 984 | 0 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 10 | 107 | 15041.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 11 | 107 | 50.65 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 13 | 107 | 3762 | 408.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 14 | 503 | 5260.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 15 | 107 | 401.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 16 | 107 | 33.5 | 33.5 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 17 | 009 | 13036.83 | 13036.83 | 2 |  | N | 0 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 18 | 107 | 42575.87 | 1107.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 19 | 003 | 2949.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 032 | 2 |  | 1 | 503 | 177019 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 038 | 2 |  | 1 | 010 | 33964.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3O54 | 21860565201 | 040 | 2 |  | 1 | 503 | 101189.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 041 | 2 |  | 1 | 503 | 1518.3 | 1518.3 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 042 | 2 |  | 1 | 503 | 16377.44 | 16377.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 1 | 503 | 90746.27 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 2 | 503 | 34514.49 | 34514.49 | 5 |  | N | 3 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 3 | 116 | 10761.88 | 10761.88 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3O54 | 21860565201 | 049 | 2 |  | 1 | 919 | 59336.24 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3O54 | 21860565201 | 062 | 2 |  | 1 | 861 | 76560 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
03 | E3O54 | 21860565201 | 063 | 2 |  | 1 | 861 | 135387.5 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
03 | E3O54 | 21860565201 | 068 | 2 |  | 1 | 503 | 959832 | 955929.65 | 2 |  | C | 190 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 073 | 2 |  | 1 | 922 | 45777.6 | 45777.6 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 074 | 2 |  | 1 | 008 | 87736.2 | 87736.2 | 5 |  | C | 7 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 075 | 2 |  | 1 | 503 | 1272867.56 | 1272867.56 | 2 |  | N | 135 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 075 | 2 |  | 2 | 503 | 81762.51 | 81762.51 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 077 | 2 |  | 1 | 503 | 1340000 | 1340000 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 085 | 2 |  | 1 | 005 | 131654.65 | 131654.65 | 5 |  | N | 31 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 086 | 2 |  | 1 | 005 | 5940.91 | 5940.91 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 087 | 2 |  | 1 | 005 | 6600.94 | 6600.94 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 096 | 2 |  | 1 | 001 | 1126139.26 | 176259.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O54 | 21860565201 | 101 | 2 |  | 1 | 009 | 31370.15 | 31370.15 | 5 |  | C | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
03 | E3O54 | 21860565201 | 110 | 2 |  | 1 | 117 | 12015.75 | 12015.75 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3O54 | 21860565201 | 113 | 2 | 850 | 1 | 107 | 116.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 117 | 2 |  | 1 | 010 | 21134.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3O54 | 21860565201 | 128 | 2 |  | 1 | 113 | 522000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 129 | 2 |  | 1 | 927 | 130087.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 138 | 2 |  | 1 | 003 | 29347.88 | 0 | 4 |  | E | 2 | Avoidable, In-House CEI | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 154 | 2 |  | 1 | 022 | 34679.65 | 34679.65 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3S63 | 4452481G201 | 012 | 2 |  | 1 | 101 | 89999.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3U03 | 43973915201 | 004 | 2 |  | 1 | 115 | 5510 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 | 006 | 2 |  | 1 | 004 | 117825.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 016 | 2 |  | 1 | 004 | 239615.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 033 | 2 |  | 1 | 004 | 304975.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 040 | 2 | 850 | 1 | 023 | 13430.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 040 | 2 | 850 | 2 | 023 | 25303.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 060 | 2 |  | 1 | 503 | 276902.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 061 | 2 |  | 1 | 004 | 2792006.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 1 | 503 | 80121.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 062 | 2 |  | 2 | 003 | 210513.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 3 | 023 | 129933.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 4 | 004 | -381537.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 065 | 2 |  | 1 | 503 | 1359809.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 075 | 2 |  | 1 | 503 | 209339.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 077 | 2 |  | 1 | 004 | 229772.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 080 | 2 |  | 1 | 503 | 771170.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 083 | 2 |  | 1 | 923 | 107912.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 084 | 2 |  | 1 | 926 | 27163.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 085 | 2 |  | 1 | 004 | 91860 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 086 | 2 |  | 1 | 003 | 159093.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 092 | 2 |  | 1 | 004 | 79918.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 094 | 2 |  | 1 | 503 | 9732.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 095 | 2 |  | 1 | 023 | 189959.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 097 | 2 |  | 1 | 003 | 468984.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 098 | 2 |  | 1 | 003 | 81400.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 099 | 2 |  | 1 | 023 | 202469.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4527 | 43689445201 | 026 | 2 |  | 1 | 208 | 162500 | 162500 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
04 | T4527 | 43689445201 | 026 | 2 |  | 2 | 860 | 40000 | 40000 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4544 | 43984715201 | 010 | 2 |  | 1 | 001 | 8502.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 | 013 | 2 |  | 1 | 101 | 49280 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 | 016 | 2 |  | 1 | 101 | 3620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E56A2 | 44113415201 | 006 | 2 |  | 1 | 003 | 81731.55 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5708 | 44101415201 | 012 | 2 |  | 1 | 001 | 77909.15 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5716 | 43745115201 | 005 | 2 | 850 | 1 | 107 | 15712.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5716 | 43745115201 | 005 | 2 | 850 | 2 | 112 | 9844.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5716 | 43745115201 | 005 | 2 | 850 | 3 | 118 | 346.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 1 | 106 | 18998.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 2 | 108 | 1051.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 3 | 101 | 479.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 4 | 112 | 32705.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | E6L38 | 25168465201 | 001 | 2 |  | 1 | 503 | 4636415 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 010 | 2 |  | 1 | 208 | 104202.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 022 | 2 |  | 1 | 923 | 48279.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 036 | 2 |  | 1 | 305 | -76932.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 047 | 2 |  | 1 | 009 | 389135.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | E6L38 | 25168465201 | 056 | 2 |  | 1 | 503 | 5640.17 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 056 | 2 |  | 2 | 503 | 162000 | 0 | 0 |  | C | 118 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 056 | 2 |  | 3 | 924 | 182323.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M84 | 44253915201 | 015 | 2 | 850 | 1 | 503 | 1768.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 001 | 2 |  | 1 | 305 | -309497 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 007 | 2 |  | 1 | 126 | 325063.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 1 | 108 | 48000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 2 | 107 | 58988.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 3 | 108 | 42973.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 4 | 103 | 37.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 016 | 2 |  | 1 | 923 | 189128.97 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 1 | 001 | 19567.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6433 | 42440715201 | 019 | 2 | 850 | 2 | 126 | 69654.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 3 | 107 | 8962.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 4 | 103 | 20834.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 5 | 108 | 30074 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 6 | 007 | 907.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 022 | 2 | 850 | 1 | 105 | 136059.98 | 36093.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 022 | 2 | 850 | 2 | 007 | 13940.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 024 | 2 |  | 1 | 106 | 2924729.56 | 2924729.56 | 5 |  | N | 132 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6433 | 42440715201 | 028 | 2 | 850 | 1 | 105 | 64285.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 028 | 2 | 850 | 2 | 007 | 47074.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 028 | 2 | 850 | 3 | 005 | 34563.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6433 | 42440715201 | 028 | 2 | 850 | 4 | 023 | 4076.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6433 | 42440715201 | 039 | 2 |  | 1 | 112 | 215308.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 1 | 115 | 6899.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 2 | 023 | 975.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 3 | 007 | 4620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 040 | 2 | 850 | 4 | 101 | 9349.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 5 | 115 | 22254.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 6 | 105 | 12823.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 7 | 007 | 75140.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 040 | 2 | 850 | 8 | 115 | 10885.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 9 | 112 | 2074.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 10 | 503 | 4976.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 044 | 2 | 850 | 1 | 503 | 130434.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 044 | 2 | 850 | 2 | 112 | 11708.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 044 | 2 | 850 | 3 | 017 | 7857.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 046 | 2 | 850 | 1 | 007 | 141260.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 046 | 2 | 850 | 2 | 115 | 8739.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 1 | 115 | 791.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 2 | 503 | 59464.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 048 | 2 | 850 | 3 | 105 | 25113.42 | 23950.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 4 | 123 | 36173.17 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 5 | 107 | 4716.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 6 | 107 | 11997.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 7 | 119 | 9964.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 1 | 115 | 16803.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 2 | 115 | 3611.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 3 | 009 | 34944.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 4 | 118 | 13730.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 5 | 107 | 11256.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 6 | 118 | 9625.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 7 | 105 | 10043.21 | 10043.21 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 8 | 131 | 14762.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Architectural Feature Related Issue | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 9 | 115 | 76552.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 10 | 503 | 10127.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 11 | 019 | 5235.11 | 5235.11 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 12 | 106 | 68828.57 | 68828.57 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 13 | 009 | 89292.29 | 2668.06 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 14 | 001 | 95778.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 15 | 503 | 7920 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 16 | 112 | 125691.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 17 | 503 | 68425.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 18 | 503 | 155516.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 19 | 007 | 29392 | 29392 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 20 | 106 | 127644.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6491 | 44183415201 | 007 | 2 | 850 | 1 | 001 | 3738.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 | 2 | 850 | 2 | 007 | 4198.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 | 2 | 850 | 3 | 503 | 4917.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 | 007 | 2 | 850 | 4 | 007 | 7880.49 | 7880.49 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 | 2 | 850 | 5 | 503 | 784.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 | 007 | 2 | 850 | 6 | 503 | 3695.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 | 007 | 2 | 850 | 7 | 101 | 2443.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6491 | 44183415201 | 007 | 2 | 850 | 8 | 007 | -4198.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 | 2 | 850 | 9 | 007 | 4198.91 | 4198.91 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 | 2 | 850 | 10 | 503 | 1935.32 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 | 007 | 2 | 850 | 11 | 503 | 5290.89 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 | 007 | 2 | 850 | 12 | 503 | 890.1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 001 | 2 |  | 1 | 007 | 7646917.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 007 | 2 |  | 1 | 305 | -4554.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 007 | 2 |  | 2 | 305 | -2039541.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 009 | 2 |  | 1 | 012 | 191560.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 1 | 115 | 8994.73 | 8994.73 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 2 | 108 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 3 | 112 | 6983.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 1 | 118 | 133624.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 2 | 118 | 47128.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 3 | 012 | 83187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 037 | 2 |  | 4 | 503 | 169393.4 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 047 | 2 |  | 1 | 850 | 21546.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L92 | 43669715201 | 049 | 2 |  | 1 | 012 | 85058.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 052 | 2 |  | 1 | 503 | 180872.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 053 | 2 |  | 1 | 108 | 22808.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7L92 | 43669715201 | 059 | 2 |  | 1 | 118 | 5474.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 059 | 2 |  | 2 | 012 | 800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 009 | 2 |  | 2 | 101 | 18400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 013 | 2 |  | 1 | 101 | 1049.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 016 | 2 |  | 1 | 305 | -227169.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 1 | 105 | 14023.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 2 | 107 | 2293.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 3 | 105 | 8200 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 4 | 001 | 3648.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 029 | 2 | 850 | 5 | 503 | 2142.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 6 | 023 | 100.8 | 100.8 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 7 | 105 | 3708.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 8 | 115 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 9 | 107 | 8432.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 10 | 503 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 11 | 107 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 12 | 105 | 19501.01 | 19501.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 1 | 105 | 28713.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 2 | 115 | 2109.32 | 2109.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 3 | 105 | 677.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 1 | 105 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 2 | 101 | -2909 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 3 | 106 | 4210 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 4 | 004 | -9761.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 | 031 | 2 |  | 5 | 105 | 780 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 2 | 112 | 32617.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 3 | 128 | 9689.61 | 6198.23 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 4 | 128 | 7136.64 | 2283.76 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 5 | 108 | 22000.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 6 | 105 | 5000 | 5000 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 7 | 923 | 77575.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 8 | 105 | 3486.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 9 | 010 | 17000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7408 | 42895315201 | 032 | 2 |  | 10 | 128 | 9543.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 036 | 2 |  | 1 | 503 | 2667 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 1 | 503 | 2919 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 2 | 012 | 1472.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 040 | 2 | 850 | 3 | 107 | 5390.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 4 | 107 | 4283.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 5 | 105 | 682.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 6 | 503 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 7 | 118 | 5341.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 043 | 2 | 850 | 1 | 850 | 1500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 044 | 2 | 850 | 1 | 105 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 2 | 115 | 2229.5 | 2229.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 3 | 115 | 138.12 | 138.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 4 | 107 | 7237.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 5 | 105 | 783.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 6 | 012 | 1183.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 044 | 2 | 850 | 7 | 503 | 1882.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 044 | 2 | 850 | 8 | 010 | 12500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7408 | 42895315201 | 044 | 2 | 850 | 9 | 118 | 7461.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 12 | 115 | 8756.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 13 | 115 | -8756.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 14 | 115 | 8756.55 | 1953.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 051 | 2 |  | 1 | 108 | 112000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895315201 | 054 | 2 |  | 1 | 128 | 92000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 1 | 105 | 1558.76 | 1558.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 2 | 122 | 7700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 3 | 009 | 47732.85 | 47732.85 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7408 | 42895315201 | 057 | 2 | 850 | 4 | 118 | 4197.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 5 | 115 | 10811.26 | 1953.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 058 | 2 | 850 | 1 | 850 | 31500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 064 | 2 | 850 | 1 | 115 | 13432.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 1 | 105 | 28265.29 | 28265.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 2 | 022 | 32524.9 | 32524.9 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 3 | 105 | 67073.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 4 | 503 | 23336.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 073 | 2 | 850 | 1 | 850 | 45000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 076 | 2 |  | 1 | 101 | 17745.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 1 | 007 | 30989.14 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7408 | 42895315201 | 078 | 2 |  | 2 | 112 | 10523.85 | 10523.85 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 3 | 112 | 47377.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 4 | 012 | 14109.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 079 | 2 |  | 1 | 001 | 56000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 079 | 2 |  | 2 | 928 | 29000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 080 | 2 |  | 1 | 009 | 450000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7444 | 44108325201 | 020 | 2 |  | 1 | 503 | 67002.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7444 | 44108325201 | 020 | 2 |  | 2 | 131 | 221716.08 | 0 | 0 |  | N | 50 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | T7444 | 44108325201 | 020 | 2 |  | 3 | 108 | 27206.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
08 | E8S34 | 43798655201 | 002 | 2 |  | 1 | 305 | -8863.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 001 | 5083.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | 685.02 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 924 | 6200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 107 | 14093.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 107 | 10663.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 128 | 7762.21 | 7762.21 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 503 | 247.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 105 | 4076.9 | 655.65 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 9786.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | -9786.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 1565.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 3 | 115 | 12739.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 4 | 024 | 4895.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | -1565.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 978.6 | 978.6 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1U26 | 44488315201 |  | 2 | CPI | 1 | 101 | 1835.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 71706.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 25337.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 1594.37 | 1594.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 019 | 1300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 2957.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 513.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 013 | 2057 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 1633.34 | 1633.34 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 012 | 17611.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 5288.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1784 | 44210725201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1791 | 44034715201 |  | 2 | CPI | 1 | 012 | 1380.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1791 | 44034715201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 49 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 108 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 3206.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 107 | 38029.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 22148.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 2116.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 503 | 4769.35 | 4769.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 115 | 2198.36 | 2198.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 3375.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 3840.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 2055.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 108 | 10907.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 003 | 7260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 31139.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 105 | 14476.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 3 | 004 | 3597.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 9 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 107 | 21680 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 12188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 2 | 923 | 27018.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 923 | 3622.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 3900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 12188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 57041.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 004 | 4146.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 2 | 115 | -2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 2363.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 003 | 3751.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2746 | 43761015201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 4228 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 001 | 3383.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 007 | 11487.16 | 11487.16 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 5390.05 | 534.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 105 | 19607.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
03 | 21585 | 22023925201 |  | 2 | CPI | 1 | 503 | 1945.67 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 2 | 503 | 25548.8 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 3 | 107 | 6979.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 4 | 105 | 5800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 6 | 503 | 198 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 7 | 503 | 5104.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 8 | 112 | 495 | 495 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 9 | 112 | 2475 | 2475 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 107 | 100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 11784.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 001 | 74844 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O54 | 21860565201 |  | 2 | CPI | 2 | 503 | 21633.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 007 | 5037.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 003 | 4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | 760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 003 | 4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | -760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 003 | -4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 7520.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | 23061.17 | 23061.17 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 107 | 619.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 0.95 | 0.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T33 | 40674255201 |  | 2 | CPI | 1 | 101 | 19086.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3T33 | 40674255201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 003 | 9075 | 3151.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 115 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 503 | 8500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 101 | 4042 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 105 | 12119.48 | 12119.48 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 023 | 816.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | T3761 | 43776115201 |  | 2 | CPI | 1 | 115 | 4689.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 1122 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 12651.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | -1122 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | -12651.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 12741.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310945201 |  | 2 | CPI | 1 | 023 | 25482.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310945201 |  | 2 | CPI | 2 | 023 | 16140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310945201 |  | 2 | CPI | 1 | 023 | 5879.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 14187.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 23366.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 2455.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 503 | 3775.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 106 | 12615.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 503 | 26267.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 106 | 12901.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4522 | 43631915201 |  | 2 | CPI | 2 | 024 | 9396.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4527 | 43689445201 |  | 2 | CPI | 1 | 105 | 3663 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4527 | 43689445201 |  | 2 | CPI | 2 | 115 | 661.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 101 | 676.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 503 | 2325.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 108 | 2695 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 101 | 10427.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 001 | 4565.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 001 | 578.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 023 | 5386.16 | 5386.16 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 022 | 9696 | 9696 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 003 | 2310 | 2310 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 122 | 2205.73 | 2205.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 024 | 6926.99 | 6926.99 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 024 | 6768.5 | 6768.5 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 5 |  | N | 17 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4569 | 44177415201 |  | 2 | CPI | 1 | 108 | 944.04 | 944.04 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4569 | 44179615201 |  | 2 | CPI | 1 | 112 | 4357.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4569 | 44179615201 |  | 2 | CPI | 2 | 023 | 1159.35 | 1159.35 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 1 | 503 | 6316.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E52A7 | 44194515201 |  | 2 | CPI | 2 | 112 | 1624.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 3 | 105 | 4713.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 4 | 112 | 1468.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E53A8 | 43632525201 |  | 2 | CPI | 1 | 003 | 626.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A8 | 43632525201 |  | 2 | CPI | 2 | 003 | 21797.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A8 | 43632525201 |  | 2 | CPI | 1 | 003 | 2148.4 | 2148.4 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 106 | 5795.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 112 | 1806.93 | 1806.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5708 | 44101415201 |  | 2 | CPI | 1 | 024 | 5384.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5708 | 44101415201 |  | 2 | CPI | 2 | 024 | 2050.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5708 | 44101415201 |  | 2 | CPI | 3 | 024 | 6818.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 021 | 7344.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 115 | 2586.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 2 | 115 | 4517.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 113 | 17013.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 2 | 012 | 20466.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 118 | 31031.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 1 | 107 | 41083.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 1 | 112 | 4972.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 2 | 118 | 3943.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 007 | 4869.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 007 | 14607.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 41951 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 8258.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 926 | 5520.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 35897.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 2 | 503 | 15987.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 107 | 33607.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 2 | 105 | 6183.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 3 | 108 | 3102 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 4 | 503 | 13385 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 108 | 47546.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 2 | 107 | 31330.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 023 | 9680.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 103 | 5164.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 503 | 895.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 2 | 001 | 9748.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 001 | -9748.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 001 | 9748.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 115 | 3346.28 | 550 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6491 | 44183415201 |  | 2 | CPI | 2 | 503 | 4347.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 3 | 503 | 522.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 503 | 4347.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 503 | -4347.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 2 | 503 | 6686.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 503 | 6686.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 2 | 503 | 462 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6491 | 44183415201 |  | 2 | CPI | 3 | 001 | 1062.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 |  | 2 | CPI | 4 | 001 | 20338.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6491 | 44183415201 |  | 2 | CPI | 1 | 503 | -6686.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6497 | 44516715201 |  | 2 | CPI | 1 | 023 | 5142.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6497 | 44516815201 |  | 2 | CPI | 1 | 503 | 4133 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6497 | 44516815201 |  | 2 | CPI | 1 | 023 | 3085.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 6262.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 17788.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 503 | 15628.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 3946.24 | 3946.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 115 | 8994.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | -8994.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 122 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 007 | 1300.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 105 | 5473.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 106 | 5503.28 | 5503.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | 1622.5 | 1622.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 001 | 23520.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | -1622.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | 1622.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 924 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 5 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 6 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 7 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 108 | 10550.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 001 | 10640.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 023 | 2729.02 | 2729.02 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 2 | 023 | 100.8 | 100.8 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 105 | 6410.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 105 | 685.5 | 685.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 2 | 105 | 7039.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 107 | 9519.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 023 | -100.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 43473825201 |  | 2 | CPI | 1 | 503 | 1167 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 503 | 7581 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 107 | 15136.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 503 | 4545.78 | 4545.78 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 41548935201 |  | 2 | CPI | 2 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | -32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 2 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 105 | 1310.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 108 | 1013.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 108 | 14338.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 105 | 40214 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 105 | 40215.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 001 | 1476.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 001 | 13939.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
08 | E8S34 | 43798655201 |  | 2 | CPI | 1 | 003 | 3519 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8S70 | 44262215201 |  | 2 | CPI | 1 | 001 | 1404.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S70 | 44262235201 |  | 2 | CPI | 1 | 001 | 9753.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
02 | E20F6 | 43439815201 | 106 |  | 14 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
02 | T2669 | 43544415201 | 503 |  | 10 | 042 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 924 |  | 11 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2732 | 21002455201 | 401 |  | 27 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | T2732 | 21002455201 | 003 |  | 16 | 047 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 405 |  | 5 | 050 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2777 | 44126215201 | 126 |  | 17 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
02 | T2784 | 44133715201 | 113 |  | 91 | 018 | 1 | 2 | N | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 130 |  | 9 | 013 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
03 | E3O54 | 21860565201 | 924 |  | 8 | 144 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | E3S63 | 4452481G201 | 700 |  | 154 | 009 | 1 | 1 | N | Avoidable, Design Consultant | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 924 |  | 14 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 700 |  | 106 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 700 |  | 200 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3T37 | 44154715201 | 924 |  | 9 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
04 | T4527 | 43689445201 | 924 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
06 | E6M84 | 44253915201 | 007 |  | 19 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6491 | 44183415201 | 007 |  | 19 | 009 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6497 | 44516815201 | 503 |  | 26 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 007 |  | 32 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 503 |  | 46 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 924 |  | 26 | 054 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7459 | 44550725201 | 924 |  | 29 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S70 | 44262215201 | 503 |  | 7 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S70 | 44262215201 | 924 |  | 19 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1709 | 20103225201 | 2018-05-23 | QTR4 | 17/18 | 3 | 27 | 907 | 1313 | 1313 | 0 | 0 | 0 | 406 | 0 | 80840173 | 150000 | 80690173 | 80370929 | 81141842 | -44000 | 0 | -44000 | 81097842 | 80911304 | -90555 | -469244 | 327 | 0 | 0 | -1709315 | 0 | 0 | 0 | 1772025 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786283 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -509110 | 117720 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2022-09-16 | QTR1 | 22/23 | 2022-05-19 | QTR4 | 21/22 | 106 | 83257742.89 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 79 | 0 | 0 | -1447449 | 0 |  | CO | 6 | 01co | 1 | 6
01CO | 01 | T1784 | 44210725201 | 2021-02-17 | QTR3 | 20/21 | 3 | 2 | 180 | 234 | 234 | 0 | 0 | 0 | 27 | 27 | 1091540 | 50000 | 1041540 | 1106522 | 1056999 | 0 | 0 | 0 | 1056999 | 1056999 | 43887 | 14982 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | -48834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 63816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14982 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-03-23 | QTR3 | 21/22 | 108 | 1402962.42 |  |  | 27 | 19 | 0 | 0 | 0 | 0 |  | CO | 2 | 01do | 7 | 8
01CO | 01 | T1791 | 44034715201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 80 | 227 | 280 | -53 | 53 | 0 | 98 | 49 | 610558 | 24380 | 586178 | 610558 | 610907 | -3490 | 0 | -3490 | 607417 | 610907 | 3490 | 0 | 126 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-03-07 | QTR3 | 21/22 | 108 | 735869.89 | B0 | ACC - LUMP SUM | 49 | 21 | 0 | 0 | 0 | 0 |  | CO | 7 | 02co | 9 | 15
01CO | 01 | T1794 | 44477915201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 270 | 353 | 352 | 1 | 0 | 0 | 67 | 16 | 2947759 | 50000 | 2897759 | 2947759 | 2877401 | 0 | 0 | 0 | 2877401 | 2926249 | 48848 | 0 | 47 | 0 | 14 | 0 | 0 | 0 | 2 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3850 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-05-18 | QTR4 | 21/22 | 108 | 2695046.26 |  |  | 16 | 20 | 0 | 0 | 0 | 0 |  | CO | 4 | 02do | 16 | 19
01CO | 01 | T1809 | 44624015201 | 2021-05-26 | QTR4 | 20/21 | 2 | 0 | 130 | 145 | 145 | 0 | 0 | 0 | 15 | 0 | 569569 | 27338 | 542231 | 569569 | 545539 | 0 | 0 | 0 | 545539 | 545539 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-06-18 | QTR4 | 21/22 | 113 | 560699.14 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 3 | 03co | 20 | 22
01CO | 01 | T1823 | 44212415201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 85 | 96 | 96 | 0 | 0 | 0 | 11 | 0 | 631249 | 31254 | 599995 | 631249 | 599995 | 0 | 0 | 0 | 599995 | 599995 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-12 | QTR1 | 22/23 | 2022-04-12 | QTR4 | 21/22 | 118 | 604209.87 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 6 | 03do | 23 | 28
01DO | 01 | E1R65 | 43084915201 | 2019-07-18 | QTR1 | 19/20 | 2 | 4 | 825 | 967 | 964 | 3 | 0 | 0 | 142 | 0 | 24334683 | 150000 | 24184683 | 24901396 | 24523563 | 0 | 0 | 0 | 24523563 | 24408360 | -115203 | 566713 | 87 | 0 | 0 | 220062 | 0 | 0 | 0 | 315298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627938 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-06-24 | QTR4 | 21/22 | 113 | 29026731.23 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO | 4 | 04co | 29 | 32
01DO | 01 | E1U26 | 44488315201 | 2021-07-15 | QTR1 | 21/22 | 1 | 1 | 150 | 161 | 159 | 2 | 0 | 0 | 11 | 0 | 1247303 | 50000 | 1197303 | 1221387 | 1196429 | 0 | 0 | 0 | 1196429 | 1291777 | 95349 | -25916 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-07-15 | QTR1 | 22/23 | 118 | 1391481.98 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO | 2 | 04do | 33 | 34
02CO | 02 | T2669 | 43544415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 9 | 1200 | 1479 | 1493 | -14 | 14 | 0 | 177 | 102 | 36475260 | 150000 | 36325260 | 37438271 | 37041923 | -100058 | 0 | -100058 | 36941865 | 37105576 | 163711 | 963012 | 81 | 0 | 9 | 653509 | 14083 | 0 | 9 | 75992 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102 | 981827 | 21137 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-03 | QTR1 | 22/23 | 2022-03-04 | QTR3 | 21/22 | 216 | 37281732.61 |  |  | 15 | 86 | 0 | 0 | 0 | 0 |  | CO | 5 | 05co | 35 | 39
02CO | 02 | T2732 | 21002455201 | 2019-02-27 | QTR3 | 18/19 | 2 | 5 | 700 | 1008 | 1008 | 0 | 0 | 0 | 195 | 113 | 23611052 | 160000 | 23451052 | 26613712 | 27048870 | 0 | 0 | 0 | 27048870 | 26998931 | -49939 | 3002661 | 79 | 16 | 106 | 2872785 | 1293012 | 0 | 7 | 194376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 48 | 113 | 3084932 | 1293012 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 | 2022-02-13 | QTR3 | 21/22 | 216 | 26976039.76 |  |  | 7 | 68 | 0 | 0 | 0 | 0 | T | CO | 4 | 05do | 40 | 43
02CO | 02 | T2746 | 43761015201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 150 | 191 | 191 | 0 | 0 | 0 | 36 | 5 | 3853383 | 50000 | 3803383 | 3853383 | 3793632 | 0 | 0 | 0 | 3793632 | 3720865 | -72767 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 | 2020-05-22 | QTR4 | 19/20 | 209 | 4960764.49 |  |  | 5 | 17 | 0 | 0 | 0 | 0 |  | CO | 4 | 06co | 44 | 47
02CO | 02 | T2756 | 43461915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 600 | 789 | 732 | 57 | 0 | 0 | 219 | -30 | 22598230 | 150000 | 22448230 | 22650960 | 22469154 | 0 | 0 | 0 | 22469154 | 22293734 | -175420 | 52730 | 133 | 0 | 0 | 120739 | 2419 | 0 | 0 | 15228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 67600 | 2419 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-12 | QTR4 | 21/22 | 216 | 25503399.26 |  |  | 0 | 86 | 0 | -30 | -68367 | 0 |  | CO | 2 | 06do | 48 | 49
02CO | 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | -48916 | 0 | 24 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94 |  |  | 2 | 22 | 0 | 0 | 0 | 0 |  | CO | 5 | 07co | 50 | 54
02CO | 02 | T2784 | 44133715201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 493 | 504 | -11 | 11 | 0 | 263 | 30 | 8801980 | 90457 | 8711523 | 9073930 | 8672744 | -41316 | 0 | -41316 | 8631428 | 8634109 | 2681 | 271950 | 134 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 | 2022-03-03 | QTR3 | 21/22 | 209 | 9187133.29 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO | 4 | 07do | 55 | 58
02CO | 02 | T2807 | 44117315201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 130 | 155 | 152 | 3 | 0 | 0 | 6 | 19 | 702242 | 21655 | 680587 | 702242 | 666627 | 0 | 0 | 0 | 666627 | 668500 | 2938 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 | 2022-06-03 | QTR4 | 21/22 | 208 | 504802.01 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 59 | 58
02DO | 02 | E20C3 | 44120015201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 300 | 340 | 275 | 65 | 0 | 0 | 40 | 0 | 1044910 | 50000 | 994910 | 1044910 | 947808 | 0 | 0 | 0 | 947808 | 947808 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-07-21 | QTR1 | 22/23 | 2022-03-16 | QTR3 | 21/22 | 208 | 1524812.56 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO | 2 | 08do | 59 | 60
02DO | 02 | E20C5 | 43317145201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 55 | 6 | 1735613 | 50000 | 1685613 | 1735613 | 1621490 | 0 | 0 | 0 | 1621490 | 1633712 | 12222 | 0 | 43 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 | 2022-05-05 | QTR4 | 21/22 | 214 | 2079687.2 |  |  | 6 | 12 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C6 | 44119815201 | 2021-03-17 | QTR3 | 20/21 | 1 | 0 | 210 | 242 | 240 | 2 | 0 | 0 | 23 | 9 | 982581 | 50000 | 932581 | 982581 | 924634 | 0 | 0 | 0 | 924634 | 924634 | 0 | 0 | 8 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 | 2022-05-12 | QTR4 | 21/22 | 208 | 1257557.66 |  |  | 9 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20F6 | 43439815201 | 2021-07-21 | QTR1 | 21/22 | 1 | 0 | 120 | 143 | 143 | 0 | 0 | 0 | 23 | 0 | 763880 | 40335 | 723545 | 763880 | 682483 | 0 | 0 | 0 | 682483 | 682483 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-06-16 | QTR4 | 21/22 | 208 | 820679.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO |  | 0
03CO | 03 | 21585 | 22023925201 | 2002-06-19 | QTR4 | 01/02 | 1 | 0 | 270 | 368 | 426 | -58 | 58 | 0 | 0 | 0 | 943334 | 50000 | 893334 | 1116958 | 1163142 | 0 | 0 | 0 | 1163142 | 1088438 | -74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 32797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 123250 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 | 2022-01-14 | QTR3 | 21/22 | 313 | 0 |  |  | 26 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3761 | 43776115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 201 | 198 | 3 | 0 | 0 | 51 | 0 | 2870000 | 50000 | 2820000 | 2870000 | 2988110 | 0 | 0 | 0 | 2988110 | 3098877 | 110767 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2021-10-29 | QTR2 | 21/22 | 321 | 3648686.57 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3781 | 44403115201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 60 | 92 | 89 | 3 | 0 | 0 | 32 | 0 | 577089 | 26811 | 550278 | 577089 | 562865 | 0 | 0 | 0 | 562865 | 562865 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-04 | QTR1 | 22/23 | 2022-03-28 | QTR3 | 21/22 | 314 | 581614.59 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3O54 | 21860565201 | 2016-01-29 | QTR3 | 15/16 | 7 | 30 | 789 | 2118 | 2097 | 21 | 0 | 0 | 835 | 494 | 29137700 | 150000 | 28987700 | 36335019 | 36358268 | 0 | 150000 | 150000 | 36508268 | 37056965 | 724562 | 7197319 | 641 | 0 | 119 | 1770045 | 309387 | 9 | 3 | 686825 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4298210 | 3702970 | 0 | 0 | 34680 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 9 | 494 | 7201002 | 4215560 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 | 2022-01-14 | QTR3 | 21/22 | 306 | 26259676.56 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 2 | 185 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S63 | 4452481G201 | 2019-04-16 | QTR4 | 18/19 | 4 | 3 | 180 | 796 | 796 | 0 | 0 | 0 | 616 | 0 | 1463233 | 0 | 1463233 | 1553233 | 3732786 | 0 | 0 | 0 | 3732786 | 0 | -3732786 | 90000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 90000 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2022-07-18 | QTR1 | 22/23 | 2021-10-12 | QTR2 | 21/22 | 321 | 1676149.95 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T33 | 40674255201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 199 | 92 | 107 | 0 | 0 | 16 | 3 | 671000 | 46442 | 624558 | 671000 | 620160 | 0 | 0 | 0 | 620160 | 620160 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 | 2022-03-02 | QTR3 | 21/22 | 321 | 974400.82 |  |  | 3 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T37 | 44154715201 | 2020-12-17 | QTR2 | 20/21 | 4 | 0 | 150 | 219 | 228 | -9 | 9 | 0 | 57 | 12 | 1496843 | 58788 | 1438055 | 1496843 | 1510915 | -15210 | 0 | -15210 | 1495705 | 1559564 | 63859 | 0 | 31 | 0 | 9 | 9075 | 0 | 0 | 3 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20875 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-08-15 | QTR1 | 22/23 | 2021-12-16 | QTR2 | 21/22 | 321 | 2221301.11 |  |  | 12 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U03 | 43973915201 | 2020-12-17 | QTR2 | 20/21 | 1 | 1 | 335 | 433 | 433 | 0 | 0 | 0 | 92 | 6 | 3371488 | 50000 | 3321488 | 3376998 | 3480991 | 0 | 0 | 0 | 3480991 | 3693131 | 271808 | 5510 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 21671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 22488 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2022-05-31 | QTR4 | 21/22 | 321 | 4444370.86 |  |  | 6 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U13 | 42357755201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 235 | 180 | 55 | 0 | 0 | 55 | 0 | 1172134 | 50000 | 1122134 | 1172134 | 929583 | 0 | 0 | 0 | 929583 | 929583 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2022-05-02 | QTR4 | 21/22 | 314 | 2039783.8 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4522 | 43631915201 | 2019-09-25 | QTR1 | 19/20 | 4 | 0 | 737 | 860 | 857 | 3 | 0 | 0 | 123 | 0 | 11069050 | 129285 | 10939766 | 11069050 | 10764445 | 0 | 0 | 0 | 10764445 | 10777804 | 13359 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 25517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30043 | 0 | 0 | 0 | 9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64956 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-11 | QTR4 | 21/22 | 412 | 13112789.31 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4527 | 43689445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 323 | 400 | 400 | 0 | 0 | 0 | 77 | 0 | 1334388 | 50000 | 1284388 | 1536888 | 1454286 | 0 | 0 | 0 | 1454286 | 1453044 | -1243 | 202500 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206825 | 202500 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2021-03-08 | QTR3 | 20/21 | 409 | 2037845.47 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4544 | 43984715201 | 2020-05-20 | QTR4 | 19/20 | 3 | 3 | 450 | 534 | 531 | 3 | 0 | 0 | 67 | 17 | 7223964 | 83864 | 7140100 | 7285366 | 7104914 | 0 | 0 | 0 | 7104914 | 7178924 | 76645 | 61402 | 27 | 0 | 0 | 15957 | 0 | 0 | 0 | 68904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326 | 0 | 0 | 17 | 28778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 115965 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2022-05-03 | QTR4 | 21/22 | 408 | 8446703.33 |  |  | 17 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4569 | 44177415201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 127 | 138 | 136 | 2 | 0 | 0 | 11 | 0 | 568800 | 26773 | 542026 | 568800 | 536000 | 0 | 0 | 0 | 536000 | 537990 | 1990 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-06-10 | QTR4 | 21/22 | 412 | 559587.35 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4R96 | 43310865201 | 2017-04-05 | QTR4 | 16/17 | 3 | 22 | 1500 | 1665 | 1573 | 92 | 0 | 0 | 165 | 0 | 102000000 | 150000 | 101850000 | 110058943 | 109950726 | 0 | 1500000 | 1500000 | 111450726 | 110798126 | -517524 | 8058943 | 68 | 0 | 0 | 4394429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707076 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7765602 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2021-10-29 | QTR2 | 21/22 | 412 | 111264427.38 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 97 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V05 | 44531515215 | 2021-10-01 | QTR2 | 21/22 | 1 | 0 | 126 | 132 | 96 | 36 | 0 | 0 | 6 | 0 | 676628 | 32349 | 644279 | 676628 | 625424 | 0 | 0 | 0 | 625424 | 625424 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-06-10 | QTR4 | 21/22 | 408 | 664967.48 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5700 | 44293215201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 170 | 350 | 350 | 0 | 0 | 0 | 151 | 29 | 1579513 | 50000 | 1529513 | 1579513 | 1554158 | 0 | 0 | 0 | 1554158 | 1562899 | 19785 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-07-08 | QTR1 | 22/23 | 513 | 1579888.21 |  |  | 29 | 118 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5708 | 44101415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 210 | 349 | 348 | 1 | 0 | 0 | 129 | 10 | 6490691 | 84382 | 6406309 | 6568600 | 6865453 | 0 | 0 | 0 | 6865453 | 7282431 | 416979 | 77909 | 53 | 0 | 10 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 92162 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 | 2022-03-18 | QTR3 | 21/22 | 515 | 8517614.92 |  |  | 0 | 76 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5709 | 44113525201 | 2021-01-27 | QTR3 | 20/21 | 2 | 0 | 280 | 431 | 431 | 0 | 0 | 0 | 135 | 16 | 8389168 | 85000 | 8304168 | 8389168 | 8382005 | 0 | 0 | 0 | 8382005 | 8827365 | 485238 | 0 | 98 | 0 | 4 | 20466 | 0 | 0 | 11 | 55149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 82960 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 | 2022-07-06 | QTR1 | 22/23 | 515 | 8661613.49 |  |  | 16 | 37 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5716 | 43745115201 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 200 | 246 | 245 | 1 | 0 | 0 | 46 | 0 | 2263271 | 50000 | 2213271 | 2365506 | 2356172 | 0 | 0 | 0 | 2356172 | 2456514 | 130713 | 102234 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 | 2022-06-30 | QTR4 | 21/22 | 509 | 2040645.74 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5722 | 44350715201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 1619760 | 50000 | 1569760 | 1619760 | 1578600 | 0 | 0 | 0 | 1578600 | 1598533 | 19933 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 | 2022-07-11 | QTR1 | 22/23 | 515 | 1216963.81 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E52A7 | 44194515201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 130 | 215 | 215 | 0 | 0 | 0 | 85 | 0 | 1902006 | 50000 | 1852006 | 1902006 | 1790542 | 0 | 0 | 0 | 1790542 | 1806715 | 16173 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14123 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-07-22 | QTR1 | 22/23 | 2022-04-08 | QTR4 | 21/22 | 514 | 1695842.63 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A8 | 43632525201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 310 | 383 | 382 | 1 | 0 | 0 | 73 | 0 | 1713111 | 50000 | 1663111 | 1713111 | 1658956 | 0 | 0 | 0 | 1658956 | 1658958 | 33039 | 0 | 24 | 0 | 0 | 24573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24573 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-08 | QTR1 | 22/23 | 2022-06-17 | QTR4 | 21/22 | 513 | 1970561.3 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56A2 | 44113415201 | 2021-07-07 | QTR1 | 21/22 | 1 | 1 | 110 | 173 | 173 | 0 | 0 | 0 | 43 | 20 | 1492986 | 50000 | 1442986 | 1574717 | 1530292 | 0 | 0 | 0 | 1530292 | 1569043 | 38751 | 81732 | 12 | 0 | 20 | 81732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 81732 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2022-05-23 | QTR4 | 21/22 | 513 | 1629586.92 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58A6 | 44845415201 | 2021-12-07 | QTR2 | 21/22 | 1 | 0 | 230 | 234 | 120 | 114 | 0 | 0 | 4 | 0 | 710278 | 29452 | 680826 | 710278 | 702088 | 0 | 0 | 0 | 702088 | 702088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-22 | QTR1 | 22/23 | 2022-08-15 | QTR1 | 22/23 | 514 | 626464 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6433 | 42440715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 15 | 700 | 1063 | 940 | 123 | 0 | 0 | 231 | 132 | 67230501 | 151730 | 67078771 | 72750415 | 73542354 | 0 | 4200000 | 4200000 | 77742354 | 73243755 | -4309470 | 5519914 | 198 | 0 | 0 | 557153 | 37295 | 0 | 132 | 4723947 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450249 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 5471149 | 3100941 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 | 2021-12-16 | QTR2 | 21/22 | 606 | 76112026.4 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | -309497 | 0 |  | CO
06CO | 06 | T6480 | 44018215201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 170 | 277 | 266 | 11 | 0 | 0 | 107 | 0 | 515515 | 29915 | 485600 | 515515 | 456395 | 0 | 0 | 0 | 456395 | 453272 | -3123 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-30 | QTR1 | 22/23 | 2022-06-27 | QTR4 | 21/22 | 636 | 619720.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6491 | 44183415201 | 2020-03-25 | QTR3 | 19/20 | 2 | 1 | 220 | 251 | 235 | 16 | 0 | 0 | 31 | 0 | 2816134 | 50000 | 2766134 | 2863544 | 2825607 | 0 | 200000 | 200000 | 3025607 | 2850019 | -175589 | 47410 | 3 | 19 | 0 | 46968 | 12079 | 0 | 0 | 5789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 83185 | 12079 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-09-08 | QTR1 | 22/23 | 2021-06-09 | QTR4 | 20/21 | 613 | 3231278.28 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6497 | 44516815201 | 2020-11-18 | QTR2 | 20/21 | 3 | 0 | 150 | 259 | 257 | 2 | 0 | 0 | 109 | 0 | 541368 | 29764 | 511604 | 541368 | 498909 | 0 | 0 | 0 | 498909 | 498909 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 4133 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 12361 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 | 2022-05-23 | QTR4 | 21/22 | 613 | 585940.8 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6L38 | 25168465201 | 2018-05-02 | QTR4 | 17/18 | 2 | 6 | 1000 | 1287 | 1259 | 28 | 0 | 0 | 169 | 118 | 56331262 | 150000 | 56181262 | 61782326 | 61740658 | 0 | 0 | 0 | 61740658 | 61689883 | -2495 | 5451064 | 115 | 0 | 0 | 408613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4906149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 5342031 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-08-10 | QTR1 | 22/23 | 2022-02-11 | QTR3 | 21/22 | 606 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 54 | 0 | 0 | -76933 | 0 |  | DO
06DO | 06 | E6M84 | 44253915201 | 2020-08-27 | QTR1 | 20/21 | 2 | 1 | 150 | 220 | 220 | 0 | 0 | 0 | 70 | 0 | 608490 | 30869 | 577621 | 625609 | 579687 | 0 | 0 | 0 | 579687 | 585088 | 5401 | 17119 | 40 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1768 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-05-25 | QTR4 | 21/22 | 613 | 624645.65 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7408 | 42895315201 | 2018-06-13 | QTR4 | 17/18 | 4 | 25 | 1115 | 1267 | 1253 | 14 | 0 | 0 | 152 | 0 | 52309860 | 150000 | 52159860 | 53697121 | 53886362 | 0 | 0 | 0 | 53886362 | 53722937 | -163425 | 1387261 | 66 | 0 | 0 | 630838 | 47733 | 0 | 0 | 729633 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117242 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315397 | 162073 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-07-15 | QTR1 | 22/23 | 2022-02-18 | QTR3 | 21/22 | 714 | 61751000 |  |  | 0 | 86 | 0 | 0 | -227170 | 0 |  | CO
07CO | 07 | T7444 | 44108325201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 443 | 585 | 581 | 4 | 0 | 0 | 92 | 50 | 10034121 | 129550 | 9904571 | 10350046 | 9810424 | 0 | 0 | 0 | 9810424 | 9853179 | 103829 | 315925 | 59 | 0 | 0 | 0 | 0 | 0 | 50 | 344704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 411706 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2022-05-31 | QTR4 | 21/22 | 714 | 12990036.6 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7459 | 44550725201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 210 | 355 | 354 | 1 | 0 | 0 | 145 | 0 | 1887858 | 50000 | 1837858 | 1887858 | 1854136 | 0 | 0 | 0 | 1854136 | 1854136 | 38612 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-09-12 | QTR1 | 22/23 | 2022-07-07 | QTR1 | 22/23 | 799 | 2521800 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7463 | 43762415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 200 | 271 | 271 | 0 | 0 | 0 | 50 | 21 | 5399019 | 50000 | 5349019 | 5449019 | 5598998 | 0 | 0 | 0 | 5598998 | 5769676 | 201519 | 50000 | 30 | 0 | 0 | 15416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15416 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-08-02 | QTR1 | 22/23 | 2022-04-08 | QTR4 | 21/22 | 799 | 5600000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7474 | 44555415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 200 | 222 | 175 | 47 | 0 | 0 | 22 | 0 | 755204 | 42000 | 713204 | 755204 | 735925 | 0 | 0 | 0 | 735925 | 735925 | 40677 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-06 | QTR4 | 21/22 | 796 | 918700 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L92 | 43669715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 11 | 675 | 1004 | 1004 | 0 | 0 | 0 | 301 | 28 | 4257317 | 50000 | 4207317 | 10851592 | 9627641 | 0 | 0 | 0 | 9627641 | 9622285 | -5356 | 6594276 | 66 | 32 | 0 | 8007524 | 0 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 28 | 6594983 | 8995 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-08 | QTR1 | 22/23 | 2022-01-26 | QTR3 | 21/22 | 799 | 4476953.25 |  |  | 0 | 157 | 0 | 0 | -2044097 | 0 |  | DO
07DO | 07 | E7O21 | 44366415201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 44 | 16 | 0 | 0 | 0 | 0 | 397254 | 14000 | 383254 | 397254 | 370201 | 0 | 0 | 0 | 370201 | 370201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-11 | QTR1 | 22/23 | 2022-04-26 | QTR4 | 21/22 | 796 | 296700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R28 | 44769615201 | 2021-05-10 | QTR4 | 20/21 | 1 | 0 | 310 | 341 | 341 | 0 | 0 | 0 | 31 | 0 | 2063258 | 50000 | 2013258 | 2063258 | 2025710 | 0 | 0 | 0 | 2025710 | 2046401 | 20691 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2022-06-17 | QTR4 | 21/22 | 796 | 1523991.28 | LBDB | LOW BID DESIGN BUILD | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R29 | 43982995201 | 2021-05-17 | QTR4 | 20/21 | 2 | 0 | 321 | 329 | 324 | 5 | 0 | 0 | 8 | 0 | 1887000 | 50000 | 1837000 | 1887000 | 1837000 | 0 | 0 | 0 | 1837000 | 1837000 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 | 2022-06-03 | QTR4 | 21/22 | 796 | 2845446.28 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S34 | 43798655201 | 2021-03-09 | QTR3 | 20/21 | 1 | 1 | 160 | 200 | 190 | 10 | 0 | 0 | 40 | 0 | 878913 | 50000 | 828913 | 870049 | 822741 | 0 | 0 | 0 | 822741 | 823180 | 7889 | -8864 | 24 | 0 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5345 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 | 2022-05-06 | QTR4 | 21/22 | 854 | 1113411.37 |  |  | 0 | 16 | 0 | 0 | -8864 | 0 |  | DO
08DO | 08 | E8S70 | 44262215201 | 2020-11-17 | QTR2 | 20/21 | 5 | 0 | 303 | 380 | 378 | 2 | 0 | 0 | 77 | 0 | 4113457 | 78161 | 4035296 | 4113457 | 3489511 | 0 | 0 | 0 | 3489511 | 3489532 | 21 | 0 | 45 | 0 | 0 | 11159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11159 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 | 2022-06-13 | QTR4 | 21/22 | 854 | 7220597.77 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0